## README
GMEPay+ — Service-Partitioned Task Backlog
Every ticket (Backlog sheet) is tagged with its owning Microservice / Repo so one agent can own one service.
See the 'By Microservice' sheet for counts + the suggested build/integration order.
SERVICE_MAP.md documents the partition; services_backlog/<service>.md is a per-service ticket bundle for each agent.
Totals: 3432 tickets across 22 services.

## Backlog
Ticket ID | Microservice / Repo | WBS Ref | Workstream | Work Package | Phase | Title | Context (self-contained) | Implementation Steps | Deliverable | Acceptance / Logic Checks | Est. Min | Dependencies | Role | Source Doc
1.1-T01 | program-mgmt | 1.1 | 1. Project Management & Mobilization | Project kickoff & mobilization | 1 | Create Git repository and establish trunk-based branching structure | GMEPay+ is a Global QR Payment Hub built by an external dev vendor for GME. The vendor is responsible for all code repository setup (DOC-00 Assumption A-00-04). OPS-13 mandates trunk-based development with branches: feature/<ticket> (PR to main), main (auto-deploys to int), release/<version> (auto-deploys to staging), hotfix/<ticket> (fast-track to prod). Repository must use GitHub or GitLab (recommended per SAD-02 tech stack). All code, migration scripts (db/migrations/), and OpenAPI spec are committed here. | • Create a new private repository named gmepay-plus (or equivalent org namespace) on GitHub or GitLab. • Create branch protection rules: require PR review and passing CI status before merge to main. • Commit an initial README.md and .gitignore (Java + PostgreSQL, no secrets or env files). • Create the db/migrations/ directory with a .gitkeep placeholder. • Add a CODEOWNERS file mapping backend, frontend, devops, and qa paths to initial team leads. • Confirm all provisioned team members can clone and push feature branches. | Git repository live at a confirmed URL with main branch protected, branch structure documented in repo README, and team access verified. | • main branch has at least one push-ruleset requiring 1 approving review and passing status checks before merge. • A developer with repo access can create feature/test-branch, push a commit, raise a PR to main, and see it blocked until approved. • db/migrations/ directory exists at repository root. • No secrets, credentials, or .env files are present in any commit. • CODEOWNERS file exists and maps at least 4 path patterns to named owners. | 45 |  | PM | DOC-00, PM-14
1.1-T02 | program-mgmt | 1.1 | 1. Project Management & Mobilization | Project kickoff & mobilization | 1 | Provision dev (E1) environment infrastructure and confirm access | OPS-13 §2 defines four environment tiers: E1 dev (individual feature work, synthetic data, developers only), E2 int, E3 staging, E4 prod. All tiers deploy the same container images; only runtime config differs. E1 uses: PostgreSQL primary, Redis cache, message queue. Network zones: Public DMZ (LB+WAF), API Zone, Worker Zone, Data Zone, Management Zone. Cloud provider is a GME infrastructure decision; dev vendor provisions via IaC (Terraform or Pulumi). Secrets injected from secrets manager at container start - never in env files or Docker images. | • Provision E1 (dev) cloud resources using IaC (Terraform or Pulumi): VPC/network, PostgreSQL instance, Redis, message queue placeholder, and a container runtime (Kubernetes or equivalent). • Configure secrets manager (HashiCorp Vault, AWS Secrets Manager, or Azure Key Vault) for the dev path and verify service retrieval at container start. • Deploy a skeleton hello-world container image to confirm the pipeline can reach E1. • Verify DNS label gmepay-dev (or equivalent) resolves and returns a 200 from the skeleton service. • Document all provisioned resource IDs, connection strings (without credentials), and environment-name conventions in a team wiki page. | E1 dev environment live and accessible to all developers; IaC scripts committed to repository under infra/; environment connection details documented in team wiki. | • Terraform/Pulumi plan applies with zero errors; state file stored in remote backend (not committed to repo). • PostgreSQL on E1 is reachable from the API zone container but NOT from the public internet. • Secrets manager dev path stores at least one test secret; a container can read it at startup and it does not appear in logs or image layers. • DNS name for E1 resolves and skeleton service returns HTTP 200. • A developer who was not the provisioner can access E1 using only the documented wiki instructions. | 60 | 1.1-T01 | PM | DOC-00, PM-14
1.1-T03 | program-mgmt | 1.1 | 1. Project Management & Mobilization | Project kickoff & mobilization | 1 | Provision int (E2) environment infrastructure and confirm access | OPS-13 §2.1 defines E2 integration as the environment for multi-service integration and eventual ZeroPay 한결원 test connection. E2 uses the same topology as E1 but is shared by Dev + QA. E2 is the only environment that will connect to 한결원 ZeroPay SFTP sandbox (separate SFTP credentials per environment; never share with prod). Milestone: dev environment provisioned by Apr 17, 2026 (PM-14 §3). Deploy same container images as E1; only runtime config differs. | • Provision E2 (int) cloud resources using the same IaC module as E1, parameterised for the int environment name. • Configure secrets manager int path; reserve a placeholder secret slot for 한결원 SFTP credentials (to be filled when 한결원 provides them, target mid-May 2026). • Configure CI/CD auto-deploy trigger: merge to main branch automatically deploys to E2. • Verify DNS label gmepay-int (or equivalent) resolves and smoke-test returns 200. • Document E2 access in team wiki; confirm QA team members have access. | E2 int environment live with auto-deploy from main branch; SFTP credential slot reserved in secrets manager; documented in wiki. | • Merging a trivial commit to main triggers an automated deploy to E2 within 5 minutes of merge. • E2 PostgreSQL and Redis are isolated from E1 (separate credentials, separate host names). • Secrets manager int path exists and has a named placeholder key ZEROPAY_SFTP_HOST with a sentinel value TBD_PENDING_KFTC. • QA team members can access E2 API endpoint but cannot access E1 secrets manager production path. • E2 environment name is identical to the string int in all CI/CD pipeline variables and DNS labels (per OPS-13 canonical naming convention). | 60 | 1.1-T02 | PM | DOC-00, PM-14
1.1-T04 | program-mgmt | 1.1 | 1. Project Management & Mobilization | Project kickoff & mobilization | 1 | Set up CI/CD pipeline skeleton with all 8 stages gated correctly | OPS-13 §4.1 mandates an 8-stage pipeline: (1) Build/lint/type-check, (2) Unit test (coverage >= 80%), (3) Security scan (SAST + dep vuln + secrets leak; no critical/high CVEs), (4) Integration test (ephemeral env), (5) Artifact (container image tagged <git-sha>+<branch>+<semver>, pushed to registry, signed), (6) Deploy to int (auto, smoke tests pass), (7) Deploy to staging (auto on release/* cut, manual approval gate), (8) Deploy to prod (human approval: Release Manager + change record + QA sign-off). Branching: feature/* -> main -> int (auto); release/* -> staging (auto); hotfix/* -> prod (expedited gate). Tool: GitHub Actions or GitLab CI. | • Create .github/workflows/ci.yml (or .gitlab-ci.yml) with all 8 stages as named jobs in the correct dependency order. • Stage 1: add a lint job that fails on any lint error; stage 2: run an empty test suite (placeholder) and assert coverage placeholder passes. • Stage 3: add SAST plugin (e.g. CodeQL or Semgrep) and a dependency scanner (e.g. OWASP Dependency Check or Snyk); configure to fail on critical/high CVEs. • Stage 5: build and push a hello-world container image to the artifact registry tagged with git SHA; add image signing step (placeholder if signing tooling not yet available). • Stage 6: trigger auto-deploy to E2 on main merge using the smoke test endpoint returning 200. • Stages 7-8: add manual approval gates as placeholder jobs (can be approved immediately for now); document approval flow in wiki. | CI/CD pipeline defined in version control; all 8 stages run on a test PR; stages 1-6 automated; stages 7-8 have manual gates defined. | • A PR to main that introduces a lint error causes stage 1 to fail and blocks merge. • A PR with a high-severity CVE in a dependency causes stage 3 to fail and blocks merge. • Merging to main triggers auto-deploy to E2 (stage 6) and smoke test passes without human intervention. • Container image in artifact registry has a tag matching the git SHA of the triggering commit. • Stages 7 (staging) and 8 (prod) are present in the pipeline definition and require a manual approval token before execution. | 60 | 1.1-T02, 1.1-T03 | PM | DOC-00, PM-14
1.1-T05 | program-mgmt | 1.1 | 1. Project Management & Mobilization | Project kickoff & mobilization | 1 | Configure project management tooling: Jira project, epics, and initial sprint | WBS 1.1 requires tooling setup. GMEPay+ has 4 phases: Phase 1 Build Core (Apr 10 - Jun 20, 2026), Phase 2 Integrate ZeroPay (May 15 - Jul 31), Phase 3 Launch GME Remit (Aug 1 - Oct 10), Phase 4 Launch Overseas Partners (Oct 1 - Dec 10). Go-live Oct 10, 2026. 8 workstreams: WS-1 Hub Core Backend, WS-2 Northbound API, WS-3 ZeroPay Southbound, WS-4 Admin System, WS-5 Partner Portal, WS-6 Security, WS-7 DevOps, WS-8 QA. RAID log entries from PM-14 must be tracked. Dev vendor PM is primary point of contact with GME Product Team (DOC-00 A-00-02). | • Create a Jira project named GMEPay+ (key: GMEP) with Scrum board and 2-week sprint cadence. • Create epics matching the 8 workstreams (WS-1 through WS-8) plus one epic for WBS 1.1 Project Kickoff. • Create milestone markers as Jira Versions: v0.0-kickoff (Apr 10), v1.0-phase1-gate (Jun 20), v2.0-phase2-gate (Jul 31), v3.0-go-live (Oct 10), v4.0-phase4-gate (Dec 10). • Import or create Jira issues for each RAID log entry from PM-14 §7: Risks R-01 through R-08, Issues I-01 through I-04, Dependencies D-01 through D-08. • Configure Jira to link to the Git repository for automatic branch/commit traceability (feature/<ticket-id> convention). • Create Sprint 1 (Apr 10-24, 2026) and add the WBS 1.1 mobilization tickets as the initial backlog. | Jira project GMEP live with 8 epics, 5 versions, all RAID items as issues, Sprint 1 created and populated, and Git integration confirmed. | • All 8 workstream epics exist in GMEP project with correct names. • Versions v1.0-phase1-gate through v4.0-phase4-gate exist with due dates matching PM-14 milestones (Jun 20, Jul 31, Oct 10, Dec 10, 2026). • RAID risks R-01 through R-08 exist as Jira issues with severity and owner fields populated per PM-14 §7.1. • Issues I-01 through I-04 exist as Jira issues with Open status and target dates matching PM-14 §7.3. • Creating a Git branch named feature/GMEP-1-test links to the corresponding Jira issue automatically. | 60 |  | PM | DOC-00, PM-14
1.1-T06 | program-mgmt | 1.1 | 1. Project Management & Mobilization | Project kickoff & mobilization | 1 | Set up team communication channels and meeting cadence | WBS 1.1 comms plan requirement. DOC-00 §7 and PM-14 §8 (RACI) require regular communication between: Dev Vendor (builds everything), GME Product (requirements owner, business gate sign-off, accountable for RACI items A/R), GME Ops/Finance (rates, settlement, UAT), GME Compliance (BOK reporting, tax), and external parties (한결원/KFTC for ZeroPay, partners GME Remit/SendMN/T-Bank). PM-14 A-14-03: vendor adds RAID items and notifies GME PM at weekly status meeting; GME Product reviews within 2 business days. DOC-00 A-00-02: dev vendor nominates lead architect, lead backend, lead frontend, and PM. | • Create a shared Slack (or Teams) workspace/channel structure: #gmepay-general, #gmepay-dev, #gmepay-ops, #gmepay-alerts (for CI/CD and monitoring), #gmepay-pm. • Schedule recurring meetings: (a) weekly status meeting (dev vendor PM + GME Product PM, 30 min), (b) bi-weekly sprint review/demo (all stakeholders, 45 min), (c) daily dev standup (dev vendor team only, 15 min). • Draft and circulate a one-page Comms Plan document listing: meeting cadence, channel purposes, escalation path for blockers, and contact roster (dev vendor leads + GME counterparts). • Confirm dev vendor lead nominations in writing to GME Product: lead architect, lead backend developer, lead frontend developer, PM (per DOC-00 A-00-02). • Set up an email distribution list (or equivalent) for formal written communications requiring a paper trail (spec changes, phase gate sign-offs, RAID updates). | Comms Plan document (PDF or Confluence page) circulated and acknowledged by GME Product; Slack/Teams channels live; recurring meetings in all calendars. | • Comms Plan lists a named contact for each of the 5 RACI roles: GME Product, GME Ops/Finance, GME Compliance, Dev Vendor, and a GME Business Development contact for 한결원 escalations. • All four dev vendor lead roles (architect, backend, frontend, PM) have been nominated in writing per DOC-00 A-00-02. • Weekly status meeting recurring invite exists in both the GME Product PM and dev vendor PM calendars. • #gmepay-alerts channel is configured to receive CI/CD build failure notifications from the pipeline. • Comms Plan explicitly states the RAID update protocol: vendor notifies GME PM at weekly status meeting; GME Product acknowledges within 2 business days. | 45 | 1.1-T05 | PM | DOC-00, PM-14
1.1-T07 | program-mgmt | 1.1 | 1. Project Management & Mobilization | Project kickoff & mobilization | 1 | Circulate and obtain acknowledgement of the full documentation handover package | DOC-00 states the handover package (16 documents) is self-contained; every developer, architect, QA, and PM must read relevant documents before raising clarification questions. Document statuses: For Development Handover (sufficient to begin Phase 1). Change control (DOC-00 §6.4): after vendor accepts, changes require written proposal, impact assessment by vendor, GME Product Owner approval, and a change note in the affected document. DOC-00 A-00-01: all 16 docs delivered simultaneously. A-00-03: For Development Handover status is sufficient to begin Phase 1 work. The 16 docs are: DOC-00, BRD-01, SAD-02, DAT-03, RATE-04, API-05, SCH-06, PRD-07, PRD-08, SEC-09, NFR-10, UX-11, QA-12, OPS-13, PM-14, REF-15. | • Confirm receipt of all 16 documents in the dev vendor's shared storage (Confluence, SharePoint, or equivalent); verify none are missing. • Create a distribution confirmation task: each nominated lead (architect, backend, frontend, PM) signs off in writing (email or Confluence) that they have received and begun reading their role-specific documents per DOC-00 §4 reading paths. • Log the acceptance date (Apr 10, 2026 per PM-14 milestone) and document status as For Development Handover in the project wiki. • Record any immediate clarification questions raised within 48 hours of receipt as Jira issues tagged CLARIFICATION, linked to the relevant source document code. • Confirm change control process is understood: create a template for the written change proposal format (document code, section, proposed change, impact estimate). | Signed acknowledgement (email or Confluence record) from all four dev vendor leads confirming receipt of all 16 documents; change control template committed to wiki. | • A dated acknowledgement record exists showing all 16 document codes (DOC-00 through REF-15) were received on or before Apr 10, 2026. • All four lead roles have individually acknowledged receipt in the record. • Change control proposal template exists in the project wiki with fields: document code, section reference, proposed change text, requester, impact estimate (effort + timeline delta). • Any clarification questions raised within 48 hours are logged as Jira issues with document code as a label. • The wiki page records document status as For Development Handover for all 16 documents. | 30 | 1.1-T05, 1.1-T06 | PM | DOC-00, PM-14
1.1-T08 | program-mgmt | 1.1 | 1. Project Management & Mobilization | Project kickoff & mobilization | 1 | Document ways-of-working: definition of done, branching convention, and ticket workflow | WBS 1.1 ways-of-working requirement. OPS-13 §4.2 mandates trunk-based development with feature/<ticket> branches. PM-14 A-14-04: config-only for new partner/scheme is an acceptance criterion from Phase 1 - a code change to add a second partner is a defect. QA-12 notes: unit test coverage >= 80%; P1 defects fixed within same sprint; P2 defects fixed before UAT entry. All services emit structured JSON logs with txn_ref, partner_id, scheme_id, request_id (SAD-02 §11.2). OpenAPI 3.x spec committed to repository; ADRs required for design deviations (NFR-10 §12.3). | • Write a Definition of Done (DoD) checklist covering: unit tests pass (coverage >= 80%), integration tests pass, no critical/high CVEs in security scan, OpenAPI spec updated if endpoint changed, structured JSON logs added for all new endpoints (fields: txn_ref, partner_id, scheme_id, request_id), PR reviewed by at least 1 peer, Jira ticket in Done state. • Write a branching and PR convention guide: branch naming feature/GMEP-{ticket-id}-{slug}, commit message format, PR description template, and squash-merge policy. • Define severity SLAs for defects: P1 (system down / data corruption) = fix within same sprint; P2 (functional defect blocking UAT) = fix before UAT entry; P3/P4 = scheduled per sprint priority. • Define ADR (Architecture Decision Record) template and location (docs/adr/) for design deviations from spec. • Publish all four documents to the project wiki and confirm acknowledgement from all team leads. | Four working-agreement documents in project wiki: Definition of Done, Branching Convention, Defect Severity SLAs, ADR template; all acknowledged by team leads. | • DoD checklist includes the structured JSON log requirement (fields txn_ref, partner_id, scheme_id, request_id) as a mandatory check. • DoD checklist includes a check that adding a new partner requires only configuration - no code change - per PM-14 A-14-04. • Branch naming guide specifies feature/GMEP-{ticket-id}-{slug} as the required format and includes an example. • Defect SLA table maps P1 to same-sprint fix and P2 to pre-UAT-entry fix. • ADR template exists at docs/adr/template.md in the repository. | 45 | 1.1-T07 | PM | DOC-00, PM-14
1.1-T09 | program-mgmt | 1.1 | 1. Project Management & Mobilization | Project kickoff & mobilization | 1 | Configure secrets manager paths and access policies for all environments | OPS-13 §3.5 and §4.7: secrets manager (HashiCorp Vault, AWS Secrets Manager, or Azure Key Vault) is the single source of truth for all credentials. Secrets are never stored in environment variable files, Docker images, or source code. Services retrieve secrets at startup. Secret categories (SEC-09 §4): DB credentials, Redis auth, API signing keys, SFTP credentials (한결원 - env-specific, never share across tiers), partner API keys. Path convention: gmepay/{env}/{service}/{secret-name} where env in {dev, int, staging, prod}. Dev and int use separate credential sets from staging and prod. | • Create the secrets manager namespace gmepay/ with four sub-paths: gmepay/dev/, gmepay/int/, gmepay/staging/, gmepay/prod/. • Populate each path with placeholder secrets for: DB_URL, DB_PASSWORD, REDIS_AUTH, API_SIGNING_KEY, ZEROPAY_SFTP_HOST, ZEROPAY_SFTP_PORT, ZEROPAY_SFTP_USER, ZEROPAY_SFTP_KEY. • Define access policies: developers read gmepay/dev/ and gmepay/int/ only; DBA role reads gmepay/staging/ DB secrets; Release Manager reads gmepay/prod/; no human role reads gmepay/prod/SFTP credentials directly (break-glass only). • Write a secrets-rotation runbook stub: SFTP credentials rotate per OPS-13; API keys rotate every 12 months or on request (SEC-09); DB passwords rotate on suspected compromise. • Verify no secret values appear in application logs by deploying the skeleton app and checking log output contains only redacted references (e.g. DB_URL=****). | Secrets manager namespace gmepay/ with 4 env sub-paths, placeholder secrets populated, access policies applied, rotation runbook stub in wiki, and log-redaction verified. | • A developer credential can read gmepay/dev/DB_PASSWORD but receives 403 when attempting to read gmepay/prod/DB_PASSWORD. • Container start logs show DB_URL=**** (redacted) not the actual connection string. • ZEROPAY_SFTP_HOST in gmepay/dev/ and gmepay/int/ have distinct values confirming env separation (per OPS-13 §2.2: never share SFTP credentials across tiers). • gmepay/prod/ SFTP credential path requires break-glass access (elevated role not held by any developer by default). • Rotation runbook stub exists in wiki with at minimum: secret name, rotation frequency, and responsible role for each secret category. | 60 | 1.1-T02, 1.1-T03 | PM | DOC-00, PM-14
1.1-T10 | program-mgmt | 1.1 | 1. Project Management & Mobilization | Project kickoff & mobilization | 1 | Set up observability stack: Prometheus, Grafana, and OpenTelemetry agent in E1/E2 | SAD-02 §11.2 mandates: Prometheus (metrics), Grafana (dashboards), OpenTelemetry (distributed tracing spanning all inbound API calls through scheme adapter). All services emit structured JSON logs with correlation fields: txn_ref, partner_id, scheme_id, request_id. Key metrics to capture from day one: payment success rate per partner, p99 API latency, prefunding balance per partner, SFTP batch delivery success, UNCERTAIN transaction count, webhook delivery success rate. Alert thresholds (SAD-02): partner p95 latency > 1000 ms, payment failure rate > 2%, UNCERTAIN transactions unresolved > 4 h, prefunding balance < USD 10,000 per partner. | • Deploy Prometheus, Grafana, and an OpenTelemetry Collector into the Management Zone of E1 and E2 environments. • Configure the OTel Collector to receive traces from services and export to a backend (Jaeger or equivalent); configure Prometheus to scrape a /metrics endpoint on the skeleton service. • Create a Grafana datasource pointing at Prometheus; create a starter dashboard with placeholder panels for each of the 6 key metrics listed in SAD-02 §11.2. • Configure 4 alert rules in Prometheus AlertManager matching the SAD-02 thresholds: p95 latency > 1000 ms, failure rate > 2%, UNCERTAIN unresolved > 4 h, prefunding balance < USD 10000 per partner. • Verify end-to-end: send a test request to the skeleton service, confirm a trace appears in Jaeger and a metric increment appears in Grafana. | Observability stack deployed in E1 and E2; Grafana dashboard with 6 metric panels; 4 Prometheus alert rules configured; trace visible for test request. | • Grafana dashboard named GMEPay+ Overview exists with panels for all 6 metrics: payment success rate, p99 latency, prefunding balance, SFTP batch success, UNCERTAIN count, webhook success rate. • AlertManager has exactly 4 alert rules with thresholds matching SAD-02: p95_latency_ms > 1000, failure_rate_pct > 2, uncertain_unresolved_hours > 4, prefunding_balance_usd < 10000. • A test HTTP request to the skeleton service produces a trace ID visible in Jaeger with at least one span tagged with request_id. • Prometheus scrapes the skeleton /metrics endpoint successfully (no scrape errors in Prometheus targets page). • Alert rules fire correctly when a test metric is manually set to exceed the threshold. | 60 | 1.1-T02, 1.1-T03 | PM | DOC-00, PM-14
1.1-T11 | program-mgmt | 1.1 | 1. Project Management & Mobilization | Project kickoff & mobilization | 1 | Create RACI register in project wiki and confirm stakeholder assignments | PM-14 §8 defines the full RACI matrix for all project activities. Roles: GME Product (A/R on requirements sign-off, phase gate sign-off business), GME Ops/Finance (A/R on rate/margin config, FX treasury updates, settlement batch monitoring, UAT), GME Compliance (R on BOK reporting format, tax invoice ID), Dev Vendor (A/R on architecture, rate engine, API build, ZeroPay integration, CI/CD, Admin/Partner portal, security impl, defect resolution, training), 한결원 (R on test environment access, ZP00xx spec), Partner (R on prefunding top-up, low-balance alert response). Activities include 28 rows in PM-14 §8. | • Create a RACI table in the project wiki (Confluence page or equivalent) with all 28 activity rows from PM-14 §8, each with R/A/C/I assignments for all 6 roles. • Add a named contact row below each role header: confirm actual named individuals for GME Product PM, GME Ops lead, GME Compliance lead, and dev vendor PM. • Flag the 4 open RACI items that are pending external parties: 한결원 test environment (D-01), ZP00xx file spec (D-02), BOK format (D-03), Tax invoice API (D-04). • Send the completed RACI to GME Product for formal acknowledgement; record the acknowledgement date. • Add a RACI change-log section at the bottom of the page: any subsequent changes require GME Product sign-off per DOC-00 §6.4 change control. | RACI register page in project wiki with all 28 activity rows, named contacts, 4 flagged open dependencies, and formal acknowledgement from GME Product. | • All 28 activity rows from PM-14 §8 are present in the wiki table with no blanks in any R/A/C/I column. • Dev Vendor is assigned A/R for: architecture design, rate engine implementation, Northbound API build, ZeroPay batch integration, Admin System build, Partner Portal build, CI/CD, security implementation, defect triage, production deployment. • GME Product is assigned A/R for: requirements sign-off and business phase gate sign-off. • The 4 external dependencies (한결원 test env, ZP00xx spec, BOK format, tax invoice API) are flagged as unconfirmed with the target dates from PM-14 (D-01: May 15; D-02: May 15; D-03: TBD; D-04: before Phase 1 dev start). • A date-stamped acknowledgement from GME Product is recorded on the wiki page. | 40 | 1.1-T07 | PM | DOC-00, PM-14
1.1-T12 | program-mgmt | 1.1 | 1. Project Management & Mobilization | Project kickoff & mobilization | 1 | Log and assign all open RAID items as tracked Jira issues | PM-14 §7 contains the full RAID log: 8 Risks (R-01 through R-08), 4 Issues (I-01 through I-04), 8 Assumptions (A-01 through A-08), 8 Dependencies (D-01 through D-08). PM-14 A-14-03: RAID is a living document; vendor adds new items and notifies GME PM weekly; GME Product acknowledges within 2 business days. Critical items: R-01 (한결원 test env delayed, High/High), I-04 (한결원 test env access not confirmed, open, due mid-May 2026), D-01 (한결원 ZeroPay test env, required by May 15, 2026). I-02 (Tax invoice API) is open-urgent and blocks Phase 1 go-live readiness (OI-02). I-03 (BOK reporting format OI-03) is open-urgent, blocks SEC-09 reporting module. | • Create Jira issues for all 8 Risks (R-01 to R-08) in GMEP project with type=Risk; populate fields: description (from PM-14), likelihood, impact, mitigation, owner (named role), linked epic. • Create Jira issues for all 4 Issues (I-01 to I-04) with type=Issue; for I-02 and I-03 set priority=Critical and add BLOCKER label; set target dates per PM-14 §7.3. • Create Jira issues for all 8 Dependencies (D-01 to D-08) with type=Dependency; set due dates from PM-14 §6: D-01 and D-02 due May 15, 2026; D-05 due Aug 1, 2026; D-06 due Oct 1, 2026. • Link R-01, I-04, and D-01 to each other as related issues (all concern 한결원 test environment). • Set up a weekly reminder or Jira automation: every Friday, post a summary of all open RAID items to #gmepay-pm Slack channel. | 20 RAID Jira issues created (8 risks, 4 issues, 8 dependencies); I-02 and I-03 marked Critical; D-01 through D-08 have due dates; weekly RAID summary automation configured. | • Jira contains exactly 8 issues of type=Risk named R-01 through R-08 with owner and mitigation fields populated. • I-02 (Tax Invoice API) and I-03 (BOK Reporting Format) have priority=Critical and label=BLOCKER; I-02 has target date before Phase 1 dev start. • D-01 (한결원 ZeroPay test env) is linked to R-01 and I-04 as related issues. • All 8 dependency issues have due dates: D-01 and D-02 = May 15, 2026; D-05 = Aug 1, 2026; D-06 = Oct 1, 2026; D-07 = before Phase 4 go-live; D-08 = Sep 26, 2026. • A Jira automation or scheduled report exists that outputs open RAID items to the PM channel every Friday. | 50 | 1.1-T05, 1.1-T11 | PM | DOC-00, PM-14
1.1-T13 | program-mgmt | 1.1 | 1. Project Management & Mobilization | Project kickoff & mobilization | 1 | Confirm and document open items OI-01, OI-02, OI-03 with interim development assumptions | PM-14 §9 lists three open items that block specific components. OI-01 (Customer Approval Method): approval UX for CPM/MPM not specified; dev vendor must implement a generic partner-configurable approval step; target before Phase 3 go-live. OI-02 (Tax Invoice API): Hometax or KFTC API not identified; UC-04-04 is blocked; interim: stub with manual admin-portal workflow; target before Phase 1 dev start (urgent). OI-03 (BOK Reporting Format): FX1014/FX1015 fields, frequency, channel unknown; rate engine produces correct derived rates but reporting output module is blocked; if not resolved before Oct 10, 2026, GME assumes regulatory risk. PM-14 A-14-03: vendor adds RAID items and notifies GME PM weekly. | • For OI-02: draft a one-paragraph interim assumption document stating that UC-04-04 will be implemented as a manual admin-portal workflow (operator manually triggers invoice issuance) with a future API hook stub; circulate to GME Account/Tech for written acknowledgement. • For OI-03: draft an interim assumption document stating that the BOK reporting module will be built with a pluggable output format interface; the data capture fields will be implemented from day one (preventing data loss); the submission channel and format will be integrated once OI-03 is confirmed; circulate to GME Compliance. • For OI-01: document that all approval steps will be implemented as a partner-configurable flag (no hard-coded approval mechanism); circulate to GME Tech/Product. • Create a Confluence table (or equivalent) listing OI-01, OI-02, OI-03 with: description, owner, target date, interim assumption text, acknowledgement status. • Add a recurring action item to the weekly status meeting agenda: check OI status and escalate if owner has not responded within 1 week. | Three interim assumption documents circulated and acknowledged; OI register page in wiki with current status and escalation path for each open item. | • OI-02 interim assumption explicitly states UC-04-04 will have a manual fallback in Phase 1 AND a future API hook stub in the codebase. • OI-03 interim assumption explicitly states the reporting module will have a pluggable output interface and will capture all BOK fields from day one. • OI-01 interim assumption explicitly states no approval mechanism will be hard-coded. • All three OI documents have a named owner from the RACI (OI-01: GME Tech/Product; OI-02: GME Account/Tech; OI-03: GME Account/Compliance) and a written target date. • The weekly status meeting agenda template includes a standing OI status check item. | 45 | 1.1-T12 | PM | DOC-00, PM-14
1.1-T14 | program-mgmt | 1.1 | 1. Project Management & Mobilization | Project kickoff & mobilization | 1 | Produce and distribute kickoff pack: project charter, milestone schedule, and team contacts | WBS 1.1 parent deliverable is a Kickoff Pack. PM-14 §3.1 milestones: contract signed Apr 10 2026; dev environment provisioned Apr 17 2026; Hub Core schema and rate engine May 9 2026; Admin portal core screens May 23 2026; Northbound API sandbox Jun 6 2026; Phase 1 gate Jun 20 2026; Phase 2 gate Jul 31 2026; Phase 3 go-live Oct 10 2026; Phase 4 gate Dec 10 2026. DOC-00 A-00-02: vendor nominates lead architect, lead backend, lead frontend, PM. Four components: Hub Core Backend, Admin System, Partner Portal, Northbound Partner API (all in scope Phase 1). Critical path: 한결원 test environment by mid-May 2026 (GME responsibility). | • Create a Kickoff Pack document (Confluence page or PDF) with sections: (1) Project Overview (GMEPay+ Global QR Payment Hub summary, go-live Oct 10, 2026), (2) Team Contacts (named leads for all 6 RACI roles), (3) Milestone Schedule (all 15 milestones from PM-14 §3.1 with dates and owners), (4) Phase Plan summary (4 phases, durations, gates), (5) Critical Path highlight (한결원 test env by mid-May 2026), (6) Communication channels and meeting cadence. • Include the 4-component scope summary: Hub Core Backend (scheme/partner registry, rate engine, settlement, prefunding, BOK hooks), Admin System (Ops portal), Partner Portal (read-only), Northbound REST API + sandbox docs. • Include the ways-of-working summary: trunk-based development, 2-week sprints, DoD checklist, RAID update protocol. • Distribute to: all dev vendor team leads, GME Product PM, GME Ops lead, GME Compliance lead; request read acknowledgements. • File the signed/acknowledged kickoff pack as the official record of Phase 1 commencement (date: Apr 10, 2026). | Kickoff Pack document containing all six sections; distributed to all stakeholders; acknowledgement received from GME Product confirming Phase 1 commencement. | • Kickoff Pack contains all 15 milestones from PM-14 §3.1 with correct dates and owners (e.g. development environment provisioned = Apr 17, 2026, Dev Vendor; Phase 1 gate = Jun 20, 2026, Dev Vendor). • All 6 RACI roles have a named contact in the Team Contacts section. • Critical path note explicitly states: 한결원 test environment must be available by mid-May 2026; any delay propagates 1:1 to Phase 2 and Phase 3 go-live; GME BD is responsible for securing access. • Scope section lists all 4 components as Phase 1 deliverables. • A dated acknowledgement from GME Product PM is on file confirming the kickoff pack was received and Phase 1 build is authorised to begin. | 50 | 1.1-T06, 1.1-T08, 1.1-T11, 1.1-T13 | PM | DOC-00, PM-14
1.1-T15 | program-mgmt | 1.1 | 1. Project Management & Mobilization | Project kickoff & mobilization | 1 | Confirm RACI is acknowledged and Phase 1 authority to proceed is granted | PM-14 §5.1 and DOC-00 §7.1: GME Product is accountable for requirements sign-off and phase gate sign-off (business). Dev Vendor is accountable for technical phase gate. The contract signed and handover package accepted milestone date is Apr 10, 2026. DOC-00 §6.4 change control is triggered from this point. PM-14 A-14-04 is an acceptance criterion from Phase 1: config-only for adding partner/scheme. This ticket closes WBS 1.1 by obtaining a formal sign-off that all pre-conditions for Phase 1 build are met. | • Prepare a Phase 1 Pre-Conditions Checklist with the following items: (a) Git repository created and team access confirmed, (b) E1 dev environment provisioned, (c) E2 int environment provisioned, (d) CI/CD pipeline skeleton live, (e) Jira project with all RAID items created, (f) Comms channels and meetings scheduled, (g) All 16 handover documents acknowledged, (h) Ways of working published and acknowledged, (i) Secrets manager configured, (j) Observability stack deployed in E1/E2, (k) RACI confirmed with named contacts, (l) Open items OI-01/OI-02/OI-03 documented with interim assumptions, (m) Kickoff pack distributed and acknowledged. • Send the checklist to GME Product PM and request sign-off that all 13 items are complete. • Record the sign-off date as the official Phase 1 Authority to Proceed (ATP) date. • Add an ATP record to the Jira project as a milestone marker and close all WBS 1.1 Jira tickets as Done. • Update the project wiki with the ATP date and the name of the GME Product signatory. | Phase 1 Authority to Proceed record with dated sign-off from GME Product PM; all 13 pre-condition items confirmed complete; WBS 1.1 Jira tickets closed. | • Phase 1 ATP record exists with a named GME Product signatory and a date on or before Apr 17, 2026 (development environment provisioned milestone). • All 13 checklist items are ticked with a reference ticket ID or wiki link for each. • The ATP date is recorded in the Jira project as a milestone event. • All Jira tickets in the WBS 1.1 epic have status=Done at the time of ATP. • The wiki ATP page references PM-14 A-14-04 explicitly: the Phase 1 build must support adding a second partner by configuration only; a code change to do so is a defect, not a change request. | 30 | 1.1-T01, 1.1-T02, 1.1-T03, 1.1-T04, 1.1-T05, 1.1-T06, 1.1-T07, 1.1-T08, 1.1-T09, 1.1-T10, 1.1-T11, 1.1-T12, 1.1-T13, 1.1-T14 | PM | DOC-00, PM-14
1.2-T01 | program-mgmt | 1.2 | 1. Project Management & Mobilization | Requirements walkthrough & open-item resolution | 1 | Compile master open-items register from all source docs | WBS 1.2 drives OI-01, OI-02, OI-03 to decisions. Before any resolution can happen, every reference to these three open items across all 16 spec docs must be collected into one authoritative register. PM-14 is the canonical tracking document. OI-01 = customer approval UX (CPM/MPM); OI-02 = tax-invoice API for Korean merchants (UC-04-04); OI-03 = BOK FX reporting format/frequency/channel (FX1014, FX1015). | • Read every Assumptions and Open Items section in spec_full.txt (BRD-01, SAD-02, DAT-03, RATE-04, API-05, SCH-06, PRD-07, PRD-08, SEC-09, QA-12, PM-14) and extract every mention of OI-01, OI-02, OI-03. • For each OI entry record: source document, section, current interim assumption, affected component, phase gate, owner, and urgency. • Produce a markdown table with columns: OI-ID, Source-Doc, Section, Current-Interim-Assumption, Affected-Component, Phase-Gate, Owner, Urgency. • Verify the table against the PM-14 RAID log entries I-01, I-02, I-03 and dependency entries D-03, D-04. • Save the consolidated register as docs/clarification-log/oi-register.md in the project repo. | docs/clarification-log/oi-register.md — a complete table of all OI-01/OI-02/OI-03 references across all 16 source documents, with interim assumptions and phase-gate dependencies. | • OI-01 has at least 8 unique source references (BRD-01 §9, SAD-02 §13, DAT-03 §12, API-05 §12, RATE-04 §8, PRD-07 §16, QA-12, PM-14 §9). • OI-02 is marked urgency=URGENT with target Before Phase 1 dev start and owner GME Account/Tech. • OI-03 is marked urgency=URGENT with target TBD and owner GME Account/Compliance. • Every entry carries the specific affected component (e.g. OI-03 affects bok_report_record schema, UC-08 main flow, SEC-09 §8.1.3, FEATURE_BOK_REPORTING flag). • The register is cross-referenced against PM-14 RAID issues I-01, I-02, I-03 and dependencies D-03, D-04 — no discrepancy. | 45 |  | BA | All
1.2-T02 | program-mgmt | 1.2 | 1. Project Management & Mobilization | Requirements walkthrough & open-item resolution | 1 | Draft OI-01 decision brief: customer approval UX options | OI-01 (Customer Approval Method): for CPM the customer sees the final collection_amount only after the merchant scans and payment.pending_debit is dispatched; for MPM the customer inputs the target_payout amount and sees the receipt post-payment. Three candidate approval mechanisms are PIN, biometric, and confirmation button. The spec requires a generic, partner-configurable approval step with no code change per partner (config only). Owner: GME Tech/Product; target: before Phase 3 go-live. The hub is not involved in approval UX — it dispatches payment.pending_debit with offer_rate and collection_amount and the partner app handles it. SAD-02 §13 confirms the hub architecture is unaffected. | • State the two payment modes with their timing constraints: MPM (customer inputs amount pre-payment; receipt shown post-payment) and CPM (customer sees collection_amount only after payment.pending_debit webhook arrives — after merchant scans). • List the three candidate approval mechanisms: PIN, biometric, confirmation button. • Identify the config field that enables each mechanism per partner without code change (suggest a partner-level field approval_method ENUM: PIN ¦ BIOMETRIC ¦ CONFIRMATION ¦ SILENT). • Document the hub-side contract: GMEPay+ is not aware of, does not validate, and does not change its API based on the partner-chosen approval method. payment.pending_debit always delivers offer_rate and collection_amount. • Document the implication for the payment.pending_debit webhook fields — no additional fields are required for any of the three options. • Produce a 1-page decision brief with: option comparison table, recommended default, config schema, and the question for GME Tech/Product to answer. | docs/clarification-log/oi-01-decision-brief.md — option table with config schema and a single yes/no question to GME Tech/Product. | • Brief specifies that SILENT option (no acknowledgement required) is architecturally valid because hub-side flow is unchanged. • Brief documents that CPM prefunding is deducted at POST /v1/payments/cpm/generate (QR token issuance), not at customer approval — this timing is fixed and not affected by OI-01 resolution. • Config field approval_method defined as partner-level ENUM, not rule-level, with default value CONFIRMATION. • Hub webhook payload section confirms payment.pending_debit fields (offer_rate, collection_amount, txn_ref) are sufficient for all three options with no field additions. • Decision question is unambiguous: Must the partner app gate the final scheme commit on an explicit customer action, or may it approve silently? | 40 | 1.2-T01 | BA | All
1.2-T03 | program-mgmt | 1.2 | 1. Project Management & Mobilization | Requirements walkthrough & open-item resolution | 1 | Draft OI-01 config schema: partner_approval_config table | OI-01 resolution requires a partner-level config table that stores the approval method without code change. The partner entity already exists (partner table with id, type LOCAL¦OVERSEAS, name, status). Adding approval_method as a column on partner or a separate partner_approval_config table allows ops to change it via the Admin portal. No code change per partner is the hard constraint (PM-14 A-14-04). Approval method applies to both CPM and MPM modes and may differ by mode. | • Design the partner_approval_config table: columns partner_id FK, payment_mode (MPM¦CPM¦ALL), approval_method ENUM(PIN, BIOMETRIC, CONFIRMATION, SILENT), effective_from TIMESTAMPTZ, created_by, created_at. • Write a SQL migration (V1.2__partner_approval_config.sql) using Flyway-style naming. • Add a CHECK constraint: payment_mode IN ('MPM','CPM','ALL'). • Add a UNIQUE constraint on (partner_id, payment_mode) to prevent duplicate rows. • Insert default rows for existing partners: payment_mode=ALL, approval_method=CONFIRMATION. • Verify the migration runs without error against an empty schema and against the schema with existing partner rows. | db/migration/V1.2__partner_approval_config.sql — migration file creating the partner_approval_config table with constraints and default seed rows. | • Table creates successfully in a clean PostgreSQL schema with no FK violations. • Inserting a second row for the same (partner_id, payment_mode) raises a unique-constraint violation. • payment_mode value OTHER raises a check-constraint violation. • Default rows seeded for all existing partners with approval_method=CONFIRMATION. • Migration is idempotent when re-applied to a schema that already contains the table (use CREATE TABLE IF NOT EXISTS or Flyway versioning). | 35 | 1.2-T02 | BA | All
1.2-T04 | program-mgmt | 1.2 | 1. Project Management & Mobilization | Requirements walkthrough & open-item resolution | 1 | Document OI-01 interim assumption and impact on QA-12 test cases | Until GME Tech/Product resolves OI-01, development proceeds with the interim assumption that the approval step is a generic confirmation button (CONFIRMATION). QA-12 test cases for CPM (HC-004, PA-008) and MPM payment flows reference the approval step. The test vector must be updated to note which field drives the step and that the field is configurable. The hub does not change its behaviour — the impact is entirely in partner integration tests. | • Locate QA-12 test cases HC-004 (CPM prefund at QR generate), PA-008 (rate quote TTL), and the MPM end-to-end test cases in the test case register. • For each affected test case add a note: Approval method = CONFIRMATION (interim default per OI-01); will be overridden when OI-01 is resolved. • Document that the hub-side acceptance criterion is unchanged: payment.pending_debit is dispatched after merchant scan; the test does not assert what the partner app does with it. • Add a new OI-01 assumption row to docs/clarification-log/assumptions-update.md: A-OI-01: approval_method defaults to CONFIRMATION per partner_approval_config; hub flow unchanged. • Update the PM-14 RAID issue I-03 status column to IN_PROGRESS with the interim assumption recorded. | docs/clarification-log/assumptions-update.md with A-OI-01 entry; updated QA-12 test case notes. | • A-OI-01 entry states the exact interim assumption (CONFIRMATION), the affected phase gate (Phase 3), and the owner (GME Tech/Product). • QA-12 test case HC-004 note specifies that prefunding deduction timing (at POST /v1/payments/cpm/generate) is independent of OI-01 and does not change under any resolution. • The assumptions update doc is appended, not overwriting existing assumptions. • PM-14 RAID I-03 reflects in-progress status with the interim assumption and target date. • No test case asserts a specific customer-app behaviour for the approval step. | 30 | 1.2-T03 | BA | All
1.2-T05 | program-mgmt | 1.2 | 1. Project Management & Mobilization | Requirements walkthrough & open-item resolution | 1 | Draft OI-02 decision brief: tax-invoice API options for Korean merchant billing | OI-02 (Tax Invoice API): GME must issue monthly tax invoices to Korean merchants for the merchant fee on overseas (cross-border) transactions (UC-04-04). Formula: merchant_fee_krw = monthly KRW total x fee_rate; vat_krw = merchant_fee_krw x 10%; invoice_amount_krw = merchant_fee_krw + vat_krw; zeropay_share_krw = monthly KRW total x 0.21%. The tax_invoice table already has invoice_ref VARCHAR(64) UNIQUE and issued_at TIMESTAMPTZ as placeholder columns pending API confirmation. Two candidate paths: (A) Hometax API (e-tax invoice API provided by NTS, National Tax Service); (B) KFTC-intermediated mechanism. Fallback: manual admin-portal workflow where GME Finance exports the monthly aggregation and issues invoices manually. Owner: GME Account/Tech; target: before Phase 1 dev start. Urgency = URGENT. | • State the business obligation: monthly KRW merchant fee invoicing for all inbound (Overseas partner) ZeroPay transactions. • List the two candidate APIs: Hometax NTS e-Tax API and KFTC-intermediated mechanism; document what is known and unknown about each. • Describe the fallback: manual export from Admin portal showing per-merchant monthly totals (total_transaction_amount_krw, fee_rate, merchant_fee_krw, vat_krw, invoice_amount_krw) — this must work for Phase 1. • Define the stub contract: the tax_invoice.invoice_ref column is NULL until OI-02 resolved; the issued_at column is set to the manual issuance timestamp; status transitions DRAFT -> ISSUED -> COLLECTED ¦ FAILED. • Specify the questions GME Account must answer: (1) Which API provider? (2) Is it a push (GME initiates) or pull (NTS pulls from GME) model? (3) What auth mechanism? • Produce a 1-page decision brief with the two options, the fallback, the stub contract, and the three questions. | docs/clarification-log/oi-02-decision-brief.md — option comparison, fallback spec, stub contract, and 3 questions for GME Account/Tech. | • Brief confirms that service charge (KRW 500 per transaction) and FX margin are NOT included in invoiceable merchant fee — they are GME-only revenue. • Brief specifies the manual fallback export fields exactly: merchant_id, invoice_period (first day of month), total_transaction_amount_krw, fee_rate, merchant_fee_krw, vat_krw, invoice_amount_krw, zeropay_share_krw. • Stub contract defines that tax_invoice rows are created in DRAFT status at month-end even with no API; status moves to ISSUED only after invoice_ref is populated. • Brief states the Phase 1 gate: manual fallback is acceptable for Phase 1; automated API is required before Phase 4 (overseas partner go-live, Dec 10 2026). • The three questions are answerable by GME Account with a one-line response each. | 40 | 1.2-T01 | BA | All
1.2-T06 | program-mgmt | 1.2 | 1. Project Management & Mobilization | Requirements walkthrough & open-item resolution | 1 | Specify tax_invoice table stub and manual-export endpoint contract | OI-02 resolution is blocked. Per PM-14 §10, if OI-02 is unresolved before Phase 1 dev start, UC-04-04 is implemented as a manual admin-portal workflow with a future API hook. The tax_invoice table schema exists (DAT-03 §8.3) with invoice_ref VARCHAR(64) UNIQUE, issued_at TIMESTAMPTZ, status ENUM(DRAFT, ISSUED, COLLECTED, FAILED). The monthly aggregation query must sum all committed inbound transactions grouped by merchant and month. fee_rate comes from the rule table (merchant fee rate configured per scheme). zeropay_share_krw = monthly_gross_krw x 0.0021 (0.21%, ZeroPay gross settlement share). | • Write the SQL query that aggregates per-merchant monthly fee data: SELECT merchant_id, DATE_TRUNC('month', committed_at) AS invoice_period, SUM(target_payout) AS total_krw, rule.merchant_fee_rate, SUM(target_payout) * rule.merchant_fee_rate AS merchant_fee_krw, ROUND(SUM(target_payout) * rule.merchant_fee_rate * 0.10) AS vat_krw, ROUND(SUM(target_payout) * rule.merchant_fee_rate * 0.0021) AS zeropay_share_krw FROM transaction JOIN rule USING (rule_id) WHERE transaction.direction = 'Inbound' AND transaction.status = 'COMMITTED' GROUP BY merchant_id, invoice_period, rule.merchant_fee_rate. • Define the Admin portal export endpoint: GET /admin/v1/tax-invoices/export?period=2026-05 returns CSV with the above columns. • Define the tax_invoice row lifecycle: one DRAFT row inserted per merchant per month by a scheduled job on the 1st of the following month; manual operator action sets status=ISSUED and populates invoice_ref; API hook slot is a no-op stub that logs INVOICE_API_STUB_CALLED. • Document the future hook interface: TaxInvoiceGateway.issue(invoice_id) -> InvoiceRef that the automated API will implement. • Verify: for a merchant with 100 transactions at KRW 50,000 each, fee_rate 0.50%: merchant_fee = 5,000 x 0.0050 x 100 = 2,500,000 x 0.0050 = 25,000 ... wait, correct calc: total_krw = 5,000,000; merchant_fee_krw = 5,000,000 x 0.005 = 25,000; vat_krw = 2,500; invoice_amount_krw = 27,500; zeropay_share_krw = ROUND(5,000,000 x 0.0021) = 10,500. | docs/clarification-log/oi-02-stub-contract.md with the aggregation SQL, export endpoint spec, lifecycle, and numeric example. | • Numeric example: total_transaction_amount_krw=5,000,000, fee_rate=0.50%, merchant_fee_krw=25,000, vat_krw=2,500, invoice_amount_krw=27,500, zeropay_share_krw=10,500. • Export endpoint returns 400 if period format is not YYYY-MM. • Stub logs INVOICE_API_STUB_CALLED when issue() is called; does not raise an error. • DRAFT row is created even if the merchant had zero transactions in the period (to support manual investigation); query result will show total_krw=0. • zeropay_share_krw is calculated on monthly gross KRW total, not on merchant_fee_krw. | 45 | 1.2-T05 | BA | All
1.2-T07 | program-mgmt | 1.2 | 1. Project Management & Mobilization | Requirements walkthrough & open-item resolution | 1 | Document OI-02 interim assumption and update PM-14 RAID | Until OI-02 is resolved, the system proceeds with the manual fallback for UC-04-04. The interim assumption must be recorded in the clarification log. PM-14 RAID issue I-02 must be updated with the interim assumption. The Admin portal (PRD-07) must include the placeholder invoice workflow. The tax_invoice table schema is not blocked — it is complete with stub columns. The issue is only the issuance mechanism (invoice_ref population). | • Add assumption A-OI-02 to docs/clarification-log/assumptions-update.md: Manual admin-portal export and manual invoice_ref entry is the Phase 1 fallback for OI-02. The TaxInvoiceGateway stub is deployed; automated issuance is deferred. • Update PM-14 RAID I-02 status to IN_PROGRESS with: interim assumption, fallback mechanism, and the gate condition (automated API required before Phase 4 overseas go-live). • Add a TODO comment in the TaxInvoiceGateway stub implementation pointing to OI-02 and the decision brief. • Cross-reference PRD-07 Admin System assumption A-08: the Admin System will display gross settlement amounts and allow Finance to export data for manual invoice preparation. • Confirm the affected test case (UC-04-04 in QA-12) is marked P2 pending OI-02. | Updated docs/clarification-log/assumptions-update.md with A-OI-02; updated PM-14 RAID I-02 notes. | • A-OI-02 entry names the exact fallback: GET /admin/v1/tax-invoices/export CSV export plus manual invoice_ref entry by operator. • A-OI-02 specifies the phase gate: automated issuance required before Dec 10 2026 (Phase 4 overseas go-live). • PM-14 RAID I-02 shows owner GME Account/Tech and target Before Phase 1 dev start. • QA-12 UC-04-04 test case marked P2-Medium with note OI-02 open. • No code path raises an unhandled exception when TaxInvoiceGateway.issue() is called in stub mode. | 25 | 1.2-T06 | BA | All
1.2-T08 | program-mgmt | 1.2 | 1. Project Management & Mobilization | Requirements walkthrough & open-item resolution | 1 | Draft OI-03 decision brief: BOK FX reporting format and channel | OI-03 (BOK Reporting Format): GME must submit FX reports to the Bank of Korea for all cross-border transactions. FX1014 = Korean customer paying overseas (Outbound); FX1015 = payment to Korean merchant by overseas payer (Inbound). Confirmed mapping: offer_rate_coll (= send_amount / (collection_usd - collection_margin_usd)) maps to FX1015 field #14. FX1015 source fields already captured: offer_rate_coll (locked at commit), target_payout (payout_amount KRW), payout_usd_cost (USD intermediate), committed_at timestamp, partner_id. FX1014 source fields: collection_ccy, collection_amount, send_amount, collection_usd, partner_id, committed_at. The bok_report_record table has report_type (FX1014¦FX1015), report_date, partner_id, collection_amount, collection_ccy, payout_amount, payout_ccy, offer_rate_coll, usd_amount, submission_status (PENDING¦SUBMITTED¦CONFIRMED¦FAILED). Three unknowns: format (CSV/XML/API), frequency (daily/monthly/real-time), channel (portal upload/API/SFTP). Owner: GME Account/Compliance; urgency URGENT. | • State what is confirmed: data capture complete at commit; offer_rate_coll = FX1015 #14; FX1014 fields captured in transaction record for Phase 2. • State what is unknown: file format, field order, encoding, submission frequency, submission channel. • List candidate channel options: (A) BOK portal manual upload (CSV); (B) BOK direct API; (C) SFTP batch. • For each option describe the implication for bok_report_record.submission_status lifecycle. • Document the interim build plan per SEC-09 §8.1.3: configurable export job (daily or on-demand), CSV or structured output, no hard-coded submission logic, FEATURE_BOK_REPORTING=false flag in Phase 1. • Identify the Hub direction sub-item OI-03a: overseas-to-overseas (Hub direction) has no confirmed FX form mapping; record as a separate open question. • Produce the decision brief with the 5 questions GME Compliance must answer. | docs/clarification-log/oi-03-decision-brief.md — confirmed fields, unknown elements, option table, interim build plan, 5 questions for GME Compliance. | • Brief confirms offer_rate_coll formula: send_amount / (collection_usd - collection_margin_usd), maps to FX1015 #14. Numeric example: send_amount=36.9714, collection_usd=36.9714, collection_margin_usd=0.3697 => offer_rate_coll = 36.9714/36.6017 = 1.01010. • Brief states all FX1015 source fields that are already captured and locked at commit (offer_rate_coll, target_payout, payout_usd_cost, committed_at, partner_id). • OI-03a (Hub direction) is listed as a separate sub-question with note: no confirmed FX form mapping exists. • Interim build plan specifies FEATURE_BOK_REPORTING feature flag defaulting to false; export job is pluggable with output format as a configuration parameter. • 5 questions are each answerable with a one-line response (format?, field order?, encoding?, frequency?, channel?). | 45 | 1.2-T01 | BA | All
1.2-T09 | program-mgmt | 1.2 | 1. Project Management & Mobilization | Requirements walkthrough & open-item resolution | 1 | Specify bok_report_record schema and population logic | OI-03 is unresolved but data capture must proceed from day one (SEC-09 §8.1.3: no data loss in interim). The bok_report_record table (DAT-03 §8.1) has: id BIGINT PK, txn_id BIGINT FK transaction, report_type VARCHAR(10) CHECK IN ('FX1014','FX1015'), report_date DATE, partner_id BIGINT FK partner, collection_amount DECIMAL(20,4), collection_ccy CHAR(3), payout_amount DECIMAL(20,4), payout_ccy CHAR(3), offer_rate_coll DECIMAL(20,8) — BOK FX1015 field #14, usd_amount DECIMAL(20,4) — payout_usd_cost, submission_status VARCHAR(20) DEFAULT 'PENDING', submitted_at TIMESTAMPTZ, created_at TIMESTAMPTZ, updated_at TIMESTAMPTZ. Population trigger: at transaction commit (step 6 of 8-step event trail), insert one FX1015 row for Inbound transactions; FX1014 row deferred to Phase 2 (Outbound). Domestic (same-currency) transactions are exempt. | • Write the SQL migration V1.2__bok_report_record_constraints.sql adding CHECK constraints for report_type and submission_status if not already present. • Specify the insert statement executed at CommitTransaction: INSERT INTO bok_report_record (txn_id, report_type, report_date, partner_id, collection_amount, collection_ccy, payout_amount, payout_ccy, offer_rate_coll, usd_amount, submission_status) SELECT id, 'FX1015', committed_at::DATE, partner_id, collection_amount, collection_ccy, target_payout, payout_ccy, offer_rate_coll, payout_usd_cost, 'PENDING' FROM transaction WHERE id = :txn_id AND direction = 'Inbound'. • Add a guard: if transaction.direction = 'Domestic' (same-currency), skip the insert. • Document the future FX1014 hook: a placeholder function insertFX1014Report(txn_id) that logs FX1014_DEFERRED and returns without inserting. • Verify with numeric example: txn with target_payout=50000 KRW, payout_usd_cost=36.2319, offer_rate_coll=1.01010, collection_amount=51086.49 KRW, collection_ccy=KRW, payout_ccy=KRW => FX1015 row has usd_amount=36.2319, offer_rate_coll=1.01010. | db/migration/V1.2__bok_report_record_constraints.sql and docs/clarification-log/oi-03-population-spec.md with insert logic and numeric example. | • FX1015 row is inserted for every Inbound committed transaction; no row for Domestic transactions. • offer_rate_coll in the inserted row equals the locked value from the transaction table (not recomputed). • submission_status defaults to PENDING on insert. • Numeric check: offer_rate_coll=1.01010, usd_amount=36.2319, payout_amount=50000, collection_amount matches the committed transaction value. • insertFX1014Report logs FX1014_DEFERRED and does not raise an exception. | 40 | 1.2-T08 | BA | All
1.2-T10 | program-mgmt | 1.2 | 1. Project Management & Mobilization | Requirements walkthrough & open-item resolution | 1 | Specify BOK report export job interface (pluggable output format) | Per SEC-09 §8.1.3, until OI-03 is resolved: a configurable export job that outputs all FX1014/FX1015 source fields per transaction must exist; output format (CSV or structured file) must be pluggable; no hard-coded submission logic. The FEATURE_BOK_REPORTING feature flag defaults to false. The export job reads from bok_report_record joining to transaction for any additional locked fields. Frequency is configurable (daily cron or on-demand via Admin portal). | • Define the BokReportExporter interface: exportPending(reportType: 'FX1015'¦'FX1014', fromDate: LocalDate, toDate: LocalDate, format: 'CSV'¦'JSON') -> ExportResult. • Define ExportResult: { rowCount: int, fileRef: string, generatedAt: Instant }. • Specify the CSV column order for FX1015: txn_id, report_date, partner_id, collection_amount, collection_ccy, payout_amount, payout_ccy, offer_rate_coll, usd_amount, submission_status. • Implement CsvBokReportFormatter as the only concrete formatter in Phase 1; add a JsonBokReportFormatter stub that throws UnsupportedOperationException. • Document: after successful export, submission_status remains PENDING; it only moves to SUBMITTED when the (future) submission channel confirms receipt. Admin portal shows count of PENDING rows as a compliance KPI. • Specify the on-demand Admin portal endpoint: POST /admin/v1/bok-reports/export with body { reportType, fromDate, toDate, format } returning ExportResult. | docs/clarification-log/oi-03-exporter-spec.md defining the BokReportExporter interface, CSV column order, and Admin portal endpoint contract. | • CsvBokReportFormatter produces a header row followed by one data row per bok_report_record; offer_rate_coll is formatted to 8 decimal places. • Exporting with FEATURE_BOK_REPORTING=false returns ExportResult { rowCount: 0, fileRef: null } without error. • exportPending with fromDate > toDate returns a 400 Bad Request. • offer_rate_coll in the exported CSV matches the value locked in the transaction table to 8 decimal places. • Column order in CSV matches the spec: txn_id first, offer_rate_coll in position 8. | 40 | 1.2-T09 | BA | All
1.2-T11 | program-mgmt | 1.2 | 1. Project Management & Mobilization | Requirements walkthrough & open-item resolution | 1 | Document OI-03 interim assumption and update PM-14 RAID | Until OI-03 is confirmed by GME Compliance / BOK, development proceeds with: (1) all FX1015 source fields captured and locked at commit; (2) pluggable export job built; (3) no hard-coded submission; (4) FEATURE_BOK_REPORTING=false. The bok_report_record schema is provisional — additional columns will be needed once the full BOK field list is confirmed. PM-14 RAID I-01 and D-03 track this. OI-03a (Hub direction reporting) is a separate sub-item with no confirmed form. | • Add assumption A-OI-03 to docs/clarification-log/assumptions-update.md with: data capture complete from day one; export job pluggable; submission deferred; schema provisional. • Add assumption A-OI-03a: Hub direction (overseas-to-overseas) BOK reporting form is undefined; no bok_report_record row is inserted for Hub direction transactions until OI-03a is resolved. • Update PM-14 RAID I-01 status to IN_PROGRESS with the interim assumption and the gate: format must be confirmed before Phase 3 go-live (Oct 10, 2026) or GME assumes regulatory risk. • Cross-reference SEC-09 §8.1.3 in the assumption: no data loss; all FX1015 source fields locked at commit. • Flag the schema column count as provisional: bok_report_record currently has 11 data columns; final BOK field list may require additional columns. | Updated docs/clarification-log/assumptions-update.md with A-OI-03 and A-OI-03a; updated PM-14 RAID I-01 notes. | • A-OI-03 states explicitly that all FX1015 source fields are captured at commit (offer_rate_coll, target_payout, payout_usd_cost, committed_at, partner_id). • A-OI-03a notes that Hub direction has no confirmed BOK form and zero rows will be inserted for Hub direction transactions. • PM-14 RAID I-01 shows urgency=URGENT, target TBD, and the regulatory risk statement if unresolved by Oct 10 2026. • The assumption doc states the column addition process: new migration file required when BOK field list is confirmed; existing rows remain valid. • No other assumption entries are modified or overwritten. | 25 | 1.2-T10 | BA | All
1.2-T12 | program-mgmt | 1.2 | 1. Project Management & Mobilization | Requirements walkthrough & open-item resolution | 1 | Conduct document-by-document requirements walkthrough: BRD-01 and SAD-02 | WBS 1.2 requires a structured walkthrough of all spec documents to confirm scope and surface conflicts. BRD-01 is the business requirements document; SAD-02 is the system architecture. Key items to confirm: (1) all 4 components in scope for Phase 1 (Hub Core, Admin portal, Partner Portal, ZeroPay Adapter); (2) go-live date Oct 10 2026 = Phase 3 gate (first domestic partner GME Remit on ZeroPay); (3) adding scheme/partner is config only, no code change; (4) prefunding for OVERSEAS only; (5) three-currency model with USD pivot required by BOK. Conflicts found: Business doc (UC-05-01) references xe.com/15-min live FX — PRD-07 §8 marks live FX feed out of scope for Phase 1; PRD wins per CONVENTIONS.md. | • Read BRD-01 §1–9 and list all in-scope features flagged for Phase 1. • Read SAD-02 §1–13 and confirm the four-component architecture matches BRD-01. • Record the xe.com FX conflict as a confirmed resolution: Phase 1 = manual treasury rate entry by GME Ops; Phase 2 = live FX feed. Record in docs/clarification-log/conflict-resolutions.md. • Confirm CPM prefunding deduction timing: at POST /v1/payments/cpm/generate per PRD-01 §5.8; Business doc UC-02-01 step 9 says at completion — PRD wins. Record in conflict-resolutions.md. • List any open questions or ambiguities in SAD-02 requiring GME clarification. | docs/clarification-log/conflict-resolutions.md with entries for the xe.com FX conflict and CPM prefunding timing conflict; BRD-01/SAD-02 walkthrough notes. | • xe.com conflict entry states: PRD-07 §8 wins; live FX feed deferred to Phase 2; Phase 1 uses manual treasury.usd_{ccy} updates by GME Ops. • CPM timing entry states: PRD-01 §5.8 wins; deduction at POST /v1/payments/cpm/generate; not at merchant scan or final approval. • SAD-02 four-component list matches BRD-01 in-scope list (Hub Core, Admin System, Partner Portal, ZeroPay Adapter). • go-live date Oct 10 2026 confirmed as Phase 3 gate (first domestic transaction), not full overseas partner launch. • Config-only constraint (A-14-04) confirmed as an acceptance criterion from Phase 1. | 50 | 1.2-T01 | BA | All
1.2-T13 | program-mgmt | 1.2 | 1. Project Management & Mobilization | Requirements walkthrough & open-item resolution | 1 | Conduct requirements walkthrough: DAT-03 and RATE-04 | DAT-03 is the data model; RATE-04 is the rate engine spec. Key items: (1) rate engine 5-step sequence must be implemented exactly — any deviation invalidates QA test vectors and BOK FX1015 #14; (2) pool identity invariant: ¦collection_usd - collection_margin_usd - payout_margin_usd - payout_usd_cost¦ < 0.01 USD; (3) all monetary values stored as DECIMAL(20,8); (4) KRW = 0 decimal places, USD = 2; (5) same-currency short-circuit when collection_ccy = settle_a = settle_b = payout_ccy; (6) min combined margin m_a + m_b >= 2.0% for cross-border, 0 allowed for same-currency; (7) rate-lock at commit — all 5-step values + derived rates stored immutably. | • Walk through RATE-04 §2–5 step by step and confirm all 5 formula steps are unambiguous. • Verify numeric example: target_payout=50,000 KRW, cost_rate_pay=1380.00, m_a=0.01, m_b=0.01, cost_rate_coll=1.0 (identity USD). Step1: payout_usd_cost=50000/1380=36.2319. Step2: collection_usd=36.2319/0.98=36.9714. Step3a: collection_margin=36.9714*0.01=0.3697. Step3b: payout_margin=36.9714*0.01=0.3697. Step4: send_amount=36.9714*1.0=36.9714. Step5: collection_amount=36.9714+service_charge. Derived: offer_rate_coll=36.9714/(36.9714-0.3697)=36.9714/36.6017=1.01010; cross_rate=50000/36.9714=1352.24. • Confirm DAT-03 column types: payout_usd_cost DECIMAL(20,8), collection_usd DECIMAL(20,8), offer_rate_coll DECIMAL(20,8). • Check RATE-04 §11.3: min margin check at rule configuration time, not at payment time. • Record any ambiguities in docs/clarification-log/walkthrough-notes.md. | docs/clarification-log/walkthrough-notes.md with RATE-04 numeric verification and any ambiguities; DAT-03 type confirmation. | • Numeric verification passes all 5 steps with values matching the spec exactly: payout_usd_cost=36.2319, collection_usd=36.9714, collection_margin_usd=0.3697, payout_margin_usd=0.3697, send_amount=36.9714, offer_rate_coll=1.01010, cross_rate=1352.24. • Pool identity check: 36.9714 - 0.3697 - 0.3697 = 36.2320; delta from payout_usd_cost=36.2319 is 0.0001, within 0.01 USD tolerance. • DAT-03 column types confirmed: all rate-engine intermediary values DECIMAL(20,8); collection_amount DECIMAL(20,4) for display. • Min margin rule confirmed as a configuration-time check, not a payment-time runtime guard. • Ambiguities list is either empty (no ambiguities found) or each entry has a proposed resolution and an owner. | 50 | 1.2-T12 | BA | All
1.2-T14 | program-mgmt | 1.2 | 1. Project Management & Mobilization | Requirements walkthrough & open-item resolution | 1 | Conduct requirements walkthrough: API-05 and SCH-06 | API-05 is the Northbound Partner API spec; SCH-06 is the ZeroPay scheme interface. Key items for API-05: (1) offer_rate in API responses is offer_rate_coll from RATE-04; (2) collection_amount in GET /v1/rates response = send_amount + service_charge; (3) partner does NOT validate or compute collection_amount — it is informational; (4) GMEPay+ debits partner prefunding by collection_usd, not collection_amount; (5) payment.pending_debit webhook delivers offer_rate and collection_amount for CPM. SCH-06: ZeroPay real-time API spec not yet in hand (external dependency; see PM-14 D-02). SFTP batch specs ZP0011-ZP0066 are defined by KFTC. | • Walk through API-05 §4–6 and confirm field name consistency: offer_rate = offer_rate_coll from RATE-04; collection_amount = send_amount + service_charge; collection_usd is the prefunding debit amount. • Confirm OI-01 impact on API-05: payment.pending_debit delivers offer_rate and collection_amount — no field change needed for any approval method (PIN/biometric/button/silent). • Confirm OI-03 impact on API-05: offer_rate_coll and cross_rate are admin-portal-only in responses — not in real-time partner API responses unless BOK requires partner submission (pending OI-03). • Review SCH-06 and confirm which items depend on the KFTC test environment (D-01, D-02) and which can proceed. • Record SCH-06 gaps in docs/clarification-log/walkthrough-notes.md. | Updated docs/clarification-log/walkthrough-notes.md with API-05 field mapping confirmation, OI-01/OI-03 API impact analysis, and SCH-06 dependency gaps. | • API-05 walkthrough confirms offer_rate in API responses corresponds to offer_rate_coll (= send_amount / (collection_usd - collection_margin_usd)); field is named offer_rate in partner-facing JSON. • Confirmed: GMEPay+ debits partner prefunding by collection_usd (not collection_amount); collection_amount is informational. • OI-01 API impact: no additional fields in payment.pending_debit are required for any of the three candidate approval methods. • OI-03 API impact: if BOK requires partner data submission, offer_rate_coll field would need to be added to GET /v1/rates response; noted as a conditional change pending OI-03. • SCH-06 gap list identifies which batch file types (ZP0011-ZP0066) are blocked on KFTC test environment (D-01) vs. those that can be spec-reviewed independently. | 50 | 1.2-T13 | BA | All
1.2-T15 | program-mgmt | 1.2 | 1. Project Management & Mobilization | Requirements walkthrough & open-item resolution | 1 | Conduct requirements walkthrough: SEC-09, PRD-07, PRD-08, QA-12 | SEC-09 is the security spec (BOK compliance architecture, §8); PRD-07 is the Admin System; PRD-08 is the Partner Portal; QA-12 is the QA plan. SEC-09 §8.1.3 defines the interim BOK build plan. PRD-07 A-08 confirms the manual invoice workflow fallback for OI-02. PRD-08 OI-01 note: the Partner Portal shows committed collection_amount and status only — approval UX is partner-app side, out of scope for portal. QA-12 UC-04-04 is marked P2 pending OI-02; UC-08-01/02 cannot be written until OI-03 confirmed. | • Walk through SEC-09 §8 and confirm the BOK compliance architecture is consistent with the interim assumptions (A-OI-03): data capture at commit, pluggable export, FEATURE_BOK_REPORTING flag. • Walk through PRD-07 §16 (open items) and confirm A-08 matches the OI-02 stub contract in 1.2-T06. • Walk through PRD-08 OI-01 entry and confirm the partner portal is unaffected by OI-01 resolution. • Walk through QA-12 §6.1 and list the test cases that are blocked or marked TBD due to OI-01, OI-02, OI-03. • Record findings in docs/clarification-log/walkthrough-notes.md. | Updated docs/clarification-log/walkthrough-notes.md with SEC-09/PRD-07/PRD-08/QA-12 walkthrough findings and blocked test case list. | • SEC-09 §8.1.3 interim plan is consistent with A-OI-03: all FX1015 source fields locked at commit, pluggable export, no hard-coded channel. • PRD-07 A-08 manual export is confirmed as the Phase 1 fallback; consistent with oi-02-stub-contract.md from 1.2-T06. • PRD-08 portal OI-01 note confirmed: portal shows committed collection_amount only; no UX change needed for any approval method. • Blocked QA-12 test cases are listed: UC-04-04 (OI-02, P2), UC-08-01 and UC-08-02 (OI-03, cannot be written). • No contradictions found between SEC-09, PRD-07, and the oi-03 interim build plan. | 45 | 1.2-T14 | BA | All
1.2-T16 | program-mgmt | 1.2 | 1. Project Management & Mobilization | Requirements walkthrough & open-item resolution | 1 | Compile clarification log and updated assumptions document | WBS 1.2 parent deliverable is a Clarification Log and Updated Assumptions document. All previous tickets have produced individual artifacts. This ticket assembles them into the final deliverable. The clarification log must record: all OI decisions made (interim assumptions), all conflicts resolved, all ambiguities still open, and the owner and target date for each open item. | • Merge the following into docs/clarification-log/CLARIFICATION_LOG.md: oi-register.md, oi-01-decision-brief.md, oi-02-decision-brief.md, oi-03-decision-brief.md, oi-02-stub-contract.md, oi-03-population-spec.md, oi-03-exporter-spec.md, conflict-resolutions.md, walkthrough-notes.md. • Produce a summary table: Section, OI/Conflict, Status (RESOLVED/INTERIM/OPEN), Decision/Assumption, Owner, Target Date. • Produce a second table: Updated Assumptions, with columns A-ID, Text, Affected-Component, Phase-Gate. • Mark OI-01 status as INTERIM (awaiting GME Tech/Product decision); OI-02 status as INTERIM (manual fallback active); OI-03 status as INTERIM (data capture active, submission deferred). • Add a cover section: Clarification Log for WBS 1.2, prepared by Dev Vendor, date, version 1.0. | docs/clarification-log/CLARIFICATION_LOG.md — the complete, assembled clarification log and updated assumptions document for WBS 1.2. | • Summary table has exactly 3 OI rows (OI-01, OI-02, OI-03) each with status INTERIM, and 2 conflict rows (xe.com FX, CPM prefunding timing) each with status RESOLVED. • Updated Assumptions table includes A-OI-01, A-OI-02, A-OI-03, A-OI-03a, plus the two conflict-resolution assumptions. • OI-02 row shows target Before Phase 1 dev start and urgency URGENT. • OI-03 row shows target TBD and the regulatory risk note: GME assumes risk of manual reporting if unresolved by Oct 10 2026. • The document is self-contained: a reader with no other context can understand the current status of all three open items and the interim assumptions in effect. | 45 | 1.2-T11, 1.2-T15 | BA | All
1.2-T17 | program-mgmt | 1.2 | 1. Project Management & Mobilization | Requirements walkthrough & open-item resolution | 1 | Unit test: OI-01 partner_approval_config table constraints | The partner_approval_config table created in 1.2-T03 must enforce its constraints correctly. Test vectors: (1) valid insert with payment_mode=ALL, approval_method=CONFIRMATION; (2) duplicate (partner_id, payment_mode) rejects; (3) invalid payment_mode rejects; (4) invalid approval_method rejects; (5) NULL partner_id rejects (FK or NOT NULL). This ticket writes integration tests against the actual database schema using a test DB container. | • Set up a test PostgreSQL database with the V1.2__partner_approval_config.sql migration applied. • Write test T1: INSERT with payment_mode='ALL', approval_method='CONFIRMATION' -> succeeds, row count = 1. • Write test T2: INSERT a second row with the same (partner_id, payment_mode) -> raises unique constraint violation. • Write test T3: INSERT with payment_mode='BOTH' (invalid) -> raises check constraint violation. • Write test T4: INSERT with approval_method='THUMBPRINT' (invalid) -> raises check constraint violation. • Write test T5: INSERT with partner_id=NULL -> raises NOT NULL or FK violation. | test/db/PartnerApprovalConfigConstraintTest.java (or equivalent) with 5 test methods covering all constraint paths. | • T1 passes: row inserted with approval_method=CONFIRMATION. • T2 fails with SQLIntegrityConstraintViolationException (unique). • T3 fails with SQLIntegrityConstraintViolationException (check). • T4 fails with SQLIntegrityConstraintViolationException (check). • T5 fails with NOT NULL or FK constraint error. | 30 | 1.2-T03 | BA | All
1.2-T18 | program-mgmt | 1.2 | 1. Project Management & Mobilization | Requirements walkthrough & open-item resolution | 1 | Unit test: bok_report_record population at CommitTransaction | At CommitTransaction (step 6 of 8-step event trail), a FX1015 row must be inserted into bok_report_record for Inbound transactions. Domestic transactions must not generate a row. The insert uses locked values from the transaction record. Test vectors: (A) Inbound transaction with offer_rate_coll=1.01010, payout_usd_cost=36.2319, target_payout=50000 KRW; (B) Domestic transaction (same-currency, direction=Domestic); (C) Hub direction transaction. | • Create a test transaction record with direction=Inbound, committed, offer_rate_coll=1.01010, payout_usd_cost=36.2319, target_payout=50000, payout_ccy=KRW, collection_amount=51136 KRW. • Call CommitTransaction and verify a FX1015 row is inserted into bok_report_record with offer_rate_coll=1.01010, usd_amount=36.2319, payout_amount=50000. • Create a Domestic transaction (direction=Domestic, same-currency KRW); call CommitTransaction; verify NO bok_report_record row is inserted. • Create a Hub direction transaction; call CommitTransaction; verify NO bok_report_record row is inserted (OI-03a not resolved). • Verify that the offer_rate_coll value in bok_report_record equals the locked value from transaction (not recomputed from current treasury rates). | test/domain/BokReportRecordPopulationTest.java with 4 test methods. | • Inbound test: bok_report_record row has report_type=FX1015, offer_rate_coll=1.01010 (8 decimal places), usd_amount=36.2319, submission_status=PENDING. • Domestic test: bok_report_record has zero rows after CommitTransaction. • Hub test: bok_report_record has zero rows after CommitTransaction. • The offer_rate_coll value is read from the locked transaction field, not computed at report-generation time. • Pool identity: verify the inserted usd_amount equals payout_usd_cost from the transaction; not collection_usd. | 35 | 1.2-T09, 1.2-T13 | BA | All
1.2-T19 | program-mgmt | 1.2 | 1. Project Management & Mobilization | Requirements walkthrough & open-item resolution | 1 | Unit test: BOK report CSV exporter output format | The CsvBokReportFormatter (specified in 1.2-T10) must produce a CSV with specific column order: txn_id, report_date, partner_id, collection_amount, collection_ccy, payout_amount, payout_ccy, offer_rate_coll, usd_amount, submission_status. offer_rate_coll must be formatted to 8 decimal places. Test with a known set of bok_report_record rows; verify exact CSV output. Also test: FEATURE_BOK_REPORTING=false returns empty result; fromDate > toDate returns 400. | • Insert 2 bok_report_record rows with known values into the test DB: row1 offer_rate_coll=1.01010000, row2 offer_rate_coll=1.00000000. • Call exportPending(reportType='FX1015', fromDate=2026-05-01, toDate=2026-05-31, format='CSV'). • Assert the CSV header equals: txn_id,report_date,partner_id,collection_amount,collection_ccy,payout_amount,payout_ccy,offer_rate_coll,usd_amount,submission_status • Assert row1 offer_rate_coll field is '1.01010000' (exactly 8 decimal places). • Set FEATURE_BOK_REPORTING=false, call exportPending, assert rowCount=0 and no exception. • Call exportPending with fromDate=2026-05-31, toDate=2026-05-01 (inverted range), assert 400 / IllegalArgumentException. | test/reporting/BokReportCsvExporterTest.java with 4 test methods. | • CSV header row matches exact column order as specified. • offer_rate_coll formatted as '1.01010000' (8 decimal places, no scientific notation). • FEATURE_BOK_REPORTING=false returns ExportResult { rowCount: 0, fileRef: null }. • Inverted date range throws IllegalArgumentException or returns HTTP 400. • Two data rows are present in the output for the two inserted records. | 30 | 1.2-T10, 1.2-T17 | BA | All
1.2-T20 | program-mgmt | 1.2 | 1. Project Management & Mobilization | Requirements walkthrough & open-item resolution | 1 | Unit test: tax_invoice monthly aggregation query | The monthly aggregation query (specified in 1.2-T06) computes merchant_fee_krw = total_transaction_amount_krw x fee_rate; vat_krw = merchant_fee_krw x 10%; zeropay_share_krw = total_krw x 0.0021. Test vector: 100 Inbound transactions at KRW 50,000 each for one merchant with fee_rate=0.50% (0.005). Expected: total_krw=5,000,000; merchant_fee_krw=25,000; vat_krw=2,500; invoice_amount_krw=27,500; zeropay_share_krw=10,500. Also test: no transactions in period returns a row with all amounts zero; Domestic transactions are excluded. | • Insert 100 committed Inbound transactions for merchant_id=1, target_payout=50000 KRW each, committed in May 2026. • Insert 10 committed Domestic transactions for the same merchant in May 2026 (should be excluded). • Run the aggregation query for merchant_id=1, period=2026-05. • Assert: total_transaction_amount_krw=5000000, merchant_fee_krw=25000, vat_krw=2500, invoice_amount_krw=27500, zeropay_share_krw=10500. • Run the aggregation for period=2026-04 (no transactions); assert a zero row is returned or an empty result, per the spec. • Verify the Domestic transactions are excluded from the total. | test/reporting/TaxInvoiceAggregationTest.java with 4 test methods covering normal case, zero-transaction month, Domestic exclusion, and fee arithmetic. | • Normal case: total_transaction_amount_krw=5,000,000, merchant_fee_krw=25,000, vat_krw=2,500, invoice_amount_krw=27,500, zeropay_share_krw=10,500. • Domestic transactions (direction=Domestic) do not appear in the aggregate total. • Zero-transaction month: query returns zero row without exception. • zeropay_share_krw = ROUND(5,000,000 * 0.0021) = 10,500 exactly. • invoice_amount_krw = merchant_fee_krw + vat_krw = 25,000 + 2,500 = 27,500. | 35 | 1.2-T06, 1.2-T17 | BA | All
1.3-T01 | program-mgmt | 1.3 | 1. Project Management & Mobilization | Delivery plan, environments & estimates | 1 | Draft WBS 1.3 scope document: delivery plan, environments and estimates | WBS 1.3 covers the Delivery Plan, Environments and Estimates work-package. Parent deliverable is a baselined project plan. This ticket produces the single scoping document that frames all subsequent 1.3 tickets so every developer knows what is in scope. GMEPay+ has four phases: Phase 1 Build Core (Apr 10 - Jun 20 2026, 10 weeks), Phase 2 Integrate ZeroPay (May 15 - Jul 31 2026, 11 weeks, overlaps Phase 1), Phase 3 Launch GME Remit (Aug 1 - Oct 10 2026), Phase 4 Launch Overseas Partners (Oct 1 - Dec 10 2026). Go-live is Oct 10 2026 (Phase 3 gate). Source: PM-14 Section 2. | • Create docs/planning/WBS_1.3_scope.md in the repository. • List all sub-deliverables: detailed schedule, environment plan, refined estimates, sprint cadence. • State the baseline date (Apr 10 2026 contract signed) and go-live date (Oct 10 2026). • Record the phase gate criteria as written in PM-14 Section 5 (each phase criterion must be met before the next phase is authorised). • Confirm out-of-scope items: partner app UIs, merchant-facing systems, live FX feed (Phase 1 uses manual rates). | docs/planning/WBS_1.3_scope.md containing phase boundaries, gate criteria, and out-of-scope items | • Document lists all four phases with exact start/end dates and durations matching PM-14: Ph1 Apr 10-Jun 20, Ph2 May 15-Jul 31, Ph3 Aug 1-Oct 10, Ph4 Oct 1-Dec 10. • All five Phase 1 acceptance criteria from PM-14 Section 5.1 are reproduced verbatim (rate-engine vectors, API sandbox, admin portal, partner portal, pool identity, same-currency short-circuit, audit log, security). • Out-of-scope list explicitly names live FX feed, partner app UIs, and merchant-facing systems. • Document is version-controlled and references PM-14 as canonical source. | 30 |  | PM | PM-14
1.3-T02 | program-mgmt | 1.3 | 1. Project Management & Mobilization | Delivery plan, environments & estimates | 1 | Produce milestone table with owners and target dates from PM-14 Section 3 | PM-14 Section 3.1 defines 19 milestones with target dates and owners. This ticket creates a machine-readable milestone register (CSV or YAML) that will feed sprint planning, burndown tracking, and the RAID log. Key milestones: contract signed Apr 10 2026 (GME Product); dev env provisioned Apr 17 (Dev Vendor); Hub Core schema + rate engine May 9 (Dev Vendor); Admin portal core May 23; Northbound API sandbox Jun 6; KFTC test env mid-May 2026; Phase 1 gate Jun 20; all ZP00xx verified Jul 18; Phase 2 gate Jul 31; GME Remit staging Sep 5; UAT sign-off Sep 26; prod deployment Oct 10; Phase 3 gate Oct 10; overseas partner staging Nov 7; UAT sign-off Phase 4 Nov 28; prod deployment Dec 10. | • Create docs/planning/milestones.csv with columns: id, name, target_date, owner, phase, status. • Populate all 19 milestones from PM-14 Section 3.1. • Mark status as PLANNED for all. • Cross-check that the critical-path dependency chain is represented: KFTC test env (mid-May) gates Phase 2; Phase 2 gates Phase 3; Phase 3 gates Phase 4. | docs/planning/milestones.csv with 19 rows covering all PM-14 Section 3.1 milestones | • CSV contains exactly 19 milestone rows matching PM-14 Section 3.1. • Phase 1 gate date is Jun 20 2026 with owner Dev Vendor. • Oct 10 2026 appears as both prod deployment and Phase 3 gate entries. • KFTC test environment milestone is flagged as critical-path with owner GME Business/KFTC and target mid-May 2026. • All Phase 4 milestones have dates in Oct-Dec 2026 range. | 35 | 1.3-T01 | PM | PM-14
1.3-T03 | program-mgmt | 1.3 | 1. Project Management & Mobilization | Delivery plan, environments & estimates | 1 | Define sprint cadence structure and sprint boundary dates for all phases | GMEPay+ is delivered across four phases spanning Apr 10 - Dec 10 2026. WBS 1.3 requires a sprint cadence that aligns sprint boundaries with phase gates. Phases 1 and 2 overlap (Phase 2 begins May 15 while Phase 1 runs until Jun 20). A 2-week sprint cadence is standard; sprints should be numbered S1 through S18 to cover the full programme. Sprint 1 starts Apr 10; Phase 1 spans approx S1-S11; Phase 2 S6-S16; Phase 3 S18-S27; Phase 4 S25-S35. Exact boundary alignment must ensure that each phase gate milestone lands at a sprint end. Source: PM-14 Sections 2 and 3. | • Create docs/planning/sprint_cadence.csv with columns: sprint_id, start_date, end_date, phase(s), key_milestone. • Assign 2-week sprints starting Apr 13 2026 (Monday after contract Apr 10). • Ensure phase gate milestones land at sprint ends: Phase 1 gate Jun 20, Phase 2 gate Jul 31, Phase 3 gate Oct 10, Phase 4 gate Dec 10. • Mark sprints where phases overlap (S6-S11) so staffing assignments can reflect dual-workstream load. • Add a row for Sprint 0 (Apr 10-Apr 12) for environment setup. | docs/planning/sprint_cadence.csv with sprint-by-sprint schedule aligned to all phase gates | • Sprint end dates for the four phase gates match PM-14 exactly: Jun 20, Jul 31, Oct 10, Dec 10. • Overlap period (Phase 1 and Phase 2 concurrent) is correctly marked for sprints whose date range falls between May 15 and Jun 20. • No sprint exceeds 2 weeks. • The final sprint ends on or before Dec 10 2026. • Sprint 0 covers environment provisioning with milestone Apr 17 2026. | 40 | 1.3-T02 | PM | PM-14
1.3-T04 | program-mgmt | 1.3 | 1. Project Management & Mobilization | Delivery plan, environments & estimates | 1 | Document environment tier definitions (E1-E4) and per-tier configuration matrix | OPS-13 Section 2 defines four environment tiers: E1 dev (individual feature work, synthetic data, developers only), E2 int (multi-service integration, ZeroPay 한결원 test SFTP, dev+QA), E3 staging/UAT (production-like masked PII, QA+Ops+partner tech leads), E4 prod (real data, break-glass access). Per-tier config from OPS-13 Section 5.3: DB pool sizes 5/20/80/200; prefunding low-balance threshold $100/$1000/$10000/$10000; rate quote TTL 300s/300s/per-config/per-config; log level DEBUG/DEBUG/INFO/INFO; batch schedule manual/manual/KST production windows/KST production windows. Secret paths follow convention gmepay/<env>/<service>/<secret-name>. | • Create docs/planning/environments.md with a definition table for tiers E1-E4. • Include access control rules from OPS-13 Section 2.5 for each tier. • Include the configuration matrix from OPS-13 Section 5.3 with all config items and their per-tier values. • Document the KFTC ZeroPay test env constraint: E2 connects exclusively to 한결원 test SFTP; never share credentials across tiers. • State the environment parity principle: same container images, only runtime config differs. | docs/planning/environments.md with environment tier table, access rules, and configuration matrix | • Four tiers (E1-E4) are defined with correct names (dev, int, staging, prod) and purposes matching OPS-13. • Configuration matrix shows DB pool 5/20/80/200 for dev/int/staging/prod. • E2 is explicitly mapped to 한결원 ZeroPay test SFTP; E4 to production SFTP. • Access control section states prod DB and secrets accessible only via break-glass procedure. • Secret path convention gmepay/<env>/<service>/<secret-name> is documented with an example. | 35 | 1.3-T01 | PM | PM-14
1.3-T05 | program-mgmt | 1.3 | 1. Project Management & Mobilization | Delivery plan, environments & estimates | 1 | Define feature flag register with Phase 1 defaults | OPS-13 Section 5.2 mandates a feature-flag mechanism for controlling in-flight features without deployment. Five flags are defined: FEATURE_LIVE_FX_FEED (default false - manual updates only Phase 1), FEATURE_PARTNER_REFUND_API (default false - admin portal only), FEATURE_OUTBOUND_PAYMENTS (default false), FEATURE_BOK_REPORTING (default false - pending OI-03 BOK format confirmation), FEATURE_MULTI_SCHEME_ROUTING (default false - Phase 1 single scheme). Flags are stored in secrets/config manager and loaded at service startup. Changing a flag requires config update and service restart (no full deployment). | • Create docs/planning/feature_flags.md listing all five flags. • For each flag record: name, what it controls, Phase 1 default value, and the open item or condition that gates enabling it. • State storage mechanism: config manager entry loaded at startup, not bundled in image. • State that enabling a flag requires a config update and service restart, not a code deployment. • Cross-reference OI-03 as the gate for FEATURE_BOK_REPORTING. | docs/planning/feature_flags.md with all five flags, defaults, and enabling conditions | • All five flags from OPS-13 Section 5.2 are present with exact names as listed. • FEATURE_LIVE_FX_FEED default is false with note that live FX feed is Phase 2 scope per PRD conflict-resolution note. • FEATURE_BOK_REPORTING default is false with reference to OI-03 (BOK reporting format not yet confirmed). • Document states flags are NOT application code constants - they are runtime config. • FEATURE_MULTI_SCHEME_ROUTING default false is explained by Phase 1 single-scheme constraint. | 25 | 1.3-T04 | PM | PM-14
1.3-T06 | program-mgmt | 1.3 | 1. Project Management & Mobilization | Delivery plan, environments & estimates | 1 | Produce workstream-to-phase staffing matrix from PM-14 Section 4 | PM-14 Section 4 defines eight workstreams: WS-1 Hub Core Backend (SAD-02, DAT-03, RATE-04 - active phases 1,2,3,4), WS-2 Northbound API (API-05, SEC-09 - phases 1,3,4), WS-3 ZeroPay Southbound (SCH-06, DAT-03 - phase 2), WS-4 Admin System (PRD-07, UX-11 - phases 1,2,3), WS-5 Partner Portal (PRD-08, UX-11 - phases 1,3,4), WS-6 Security (SEC-09, NFR-10 - phases 1,2,3,4), WS-7 DevOps (OPS-13, NFR-10 - phases 1,2,3,4), WS-8 QA (QA-12 - phases 1,2,3,4). PM-14 A-14-05 requires at least one senior backend developer allocated to ZeroPay batch interface from May 15 2026 independently of Phase 1 completion. | • Create docs/planning/staffing_matrix.md with workstreams as rows and phases (1-4) as columns. • Mark each cell as Active, Inactive, or Overlap. • Add a note for WS-1 and WS-3 overlap from May 15 - Jun 20 (assumption A-14-05: one senior backend dev must be allocated to ZeroPay from May 15 regardless of Phase 1 state). • State sequencing constraints from PM-14 Section 4.2 (WS-1 must be substantially complete before WS-2 can be fully tested; WS-4/WS-5 frontend can start in parallel once API contracts stable; WS-6 applies from Sprint 1; WS-8 starts Sprint 1 with RATE-04 unit tests). • List the primary reference documents for each workstream. | docs/planning/staffing_matrix.md mapping workstreams to phases with sequencing constraints | • All eight workstreams are present with correct phase activation matching PM-14 Section 4.1. • WS-3 (ZeroPay) is marked active only in Phase 2 per PM-14. • Overlap note for WS-1/WS-3 between May 15 and Jun 20 is explicitly stated with reference to A-14-05. • WS-6 (Security) and WS-8 (QA) are active in all four phases. • Sequencing constraint that WS-8 begins Sprint 1 with RATE-04 unit test vectors is documented. | 35 | 1.3-T03 | PM | PM-14
1.3-T07 | program-mgmt | 1.3 | 1. Project Management & Mobilization | Delivery plan, environments & estimates | 1 | Produce effort estimates table for Phase 1 deliverables | PM-14 Section 2.2 Phase 1 deliverables: Hub Core backend (scheme registry, partner registry, rate engine per RATE-04, settlement engine, prefunding ledger, revenue ledger, audit log); Admin System per PRD-07/UX-11; Partner Portal per PRD-08/UX-11; Northbound REST API per API-05 with sandbox docs; database schema and migration scripts per DAT-03; CI/CD pipeline and dev+staging environments per OPS-13. Phase 1 runs Apr 10 - Jun 20 2026 (10 weeks). Hub Core schema + rate engine milestone is May 9 (week 4), Admin portal core May 23 (week 6), API sandbox Jun 6 (week 8), Phase 1 gate Jun 20 (week 10). | • Create docs/planning/estimates_phase1.md with a table of Phase 1 deliverables. • For each deliverable assign estimate in person-days (backend, frontend, QA, DevOps breakdown). • Mark which WBS sub-packages and WBS IDs cover each deliverable. • Cross-reference each deliverable to its primary spec document (e.g., rate engine to RATE-04, schema to DAT-03). • Sum estimates to verify they are achievable within 10 weeks given the team size assumption from PM-14 (staffing to be confirmed with GME PM). • Highlight the critical path: Hub Core schema (May 9) is a hard dependency before other components can progress. | docs/planning/estimates_phase1.md with per-deliverable person-day estimates and WBS cross-references | • Table includes all seven Phase 1 deliverable categories from PM-14 Section 2.2. • Each deliverable is cross-referenced to at least one spec document (SAD-02, DAT-03, RATE-04, API-05, PRD-07, PRD-08, OPS-13). • Hub Core schema milestone May 9 is identified as blocking Admin System, Partner Portal, and Northbound API progress. • Estimates sum to a total that is achievable within 10 working weeks. • CI/CD pipeline and environment provisioning estimates are separate from application code estimates. | 45 | 1.3-T06 | PM | PM-14
1.3-T08 | program-mgmt | 1.3 | 1. Project Management & Mobilization | Delivery plan, environments & estimates | 1 | Produce effort estimates table for Phase 2 deliverables | PM-14 Section 2.2 Phase 2 deliverables: ZeroPay registered as active scheme in backend; all ZP00xx message types (ZP0011/0012/0021/0022/0041/0043/0045/0047/0051/0053/0055/0061-0066) verified against 한결원 test environment; SFTP batch proven end-to-end. Phase 2 runs May 15 - Jul 31 2026 (11 weeks, overlaps Phase 1). Milestones: ZeroPay merchant sync passing Jun 13, all ZP00xx verified Jul 18, Phase 2 gate Jul 31. Critical dependency: 한결원 test environment available by mid-May 2026 (D-01). If test env unavailable by May 15, dev vendor must use mock SFTP in parallel (risk mitigation R-01). SFTP batch job schedule: 13 job types with windows from 02:00 to 22:00 KST (OPS-13 Section 6.2). | • Create docs/planning/estimates_phase2.md with per-deliverable estimates. • List all 16 ZP00xx file type implementations as individual line items. • Flag D-01 (KFTC test env) as a hard external dependency with due date May 15 2026. • Include mock SFTP contingency estimate (R-01 mitigation) as a separate line item. • Cross-reference each ZP00xx type to SCH-06 section. • Sum estimates against 11 available weeks noting the Phase 1/Phase 2 overlap reduces available senior backend bandwidth in May-Jun. | docs/planning/estimates_phase2.md with ZP00xx line items, KFTC dependency flag, and contingency estimates | • 16 ZP00xx file types are listed individually as implementation line items. • D-01 KFTC dependency is flagged with target date May 15 2026 and stated impact (Phase 2 gate Jul 31 at risk if delayed). • Mock SFTP stub estimate is included as a risk-mitigation contingency line item. • Phase 1/Phase 2 overlap bandwidth reduction is noted in the header assumptions. • Total estimate fits within 11 weeks with stated staffing assumption. | 40 | 1.3-T07 | PM | PM-14
1.3-T09 | program-mgmt | 1.3 | 1. Project Management & Mobilization | Delivery plan, environments & estimates | 1 | Produce effort estimates table for Phase 3 and Phase 4 deliverables | PM-14 Section 2.2: Phase 3 (Aug 1 - Oct 10 2026, 10 weeks) deliverables: GME Remit partner onboarded (LOCAL type, KRW/KRW/KRW, same-currency short-circuit, KRW 500 service charge, no prefunding), MPM+CPM working in production, daily ZeroPay settlement batch running, GME Ops trained, BOK domestic reporting functional (gated by OI-03). Phase 4 (Oct 1 - Dec 10 2026, 10 weeks) deliverables: SendMN/T-Bank onboarded (OVERSEAS type, FX margin 2%, KRW 500 service charge, prefunding), MPM+CPM working, prefunding atomicity confirmed under load, low-balance alert at USD 10000, monthly merchant fee process (gated by OI-02). Phases 3 and 4 overlap Oct 1-10 per A-14-02. | • Create docs/planning/estimates_phase34.md with separate sections for Phase 3 and Phase 4. • List GME Remit onboarding config items: partner type LOCAL, settlement ccy KRW/KRW/KRW, service_charge KRW 500, prefunding not required. • List overseas partner onboarding config items: partner type OVERSEAS, m_a+m_b >= 2.0%, service_charge KRW 500, prefunding required. • Flag OI-02 (tax invoice API) as gating Phase 4 overseas merchant billing automation. • Flag OI-03 (BOK reporting format) as gating Phase 3 automated BOK submission. • Note A-14-02: Phase 3 production stability must be confirmed before primary resource shifts to Phase 4. | docs/planning/estimates_phase34.md with Phase 3 and Phase 4 deliverable estimates and open-item gates | • GME Remit is correctly specified as LOCAL type with KRW/KRW/KRW same-currency short-circuit and no prefunding requirement. • Overseas partners (SendMN/T-Bank) are correctly specified as OVERSEAS type requiring prefunding and m_a+m_b >= 2.0%. • OI-02 and OI-03 are flagged as gates with explicit description of what is blocked if unresolved. • Phase 3/Phase 4 overlap window Oct 1-10 is noted with A-14-02 constraint (Phase 3 stability first). • Service charge KRW 500 appears in both Phase 3 and Phase 4 onboarding specs. | 40 | 1.3-T08 | PM | PM-14
1.3-T10 | program-mgmt | 1.3 | 1. Project Management & Mobilization | Delivery plan, environments & estimates | 1 | Create RAID log template and populate from PM-14 Sections 7 and 9 | PM-14 Section 7 defines 8 risks, 8 assumptions, 4 issues, and 8 dependencies. Section 9 has 3 open items. Key risks: R-01 KFTC test env delayed (High/High); R-02 BOK reporting format late (Med/High); R-03 rate engine error (Med/High); R-04 prefunding atomicity bug (Med/High); R-05 tax invoice API unavailable (Med/Med); R-06 ZeroPay file format changes (Low/Med); R-07 overseas partner delayed (Med/Med); R-08 FX rates stale (Med/Med). Issues: I-01 OI-03 BOK spec open; I-02 OI-02 tax invoice open (urgent); I-03 OI-01 customer approval method open; I-04 KFTC test env access not confirmed. | • Create docs/planning/RAID_log.csv with columns: type (R/A/I/D), id, description, likelihood, impact, mitigation_or_status, owner, target_date. • Populate all 8 risks, 8 assumptions, 4 issues, and 8 dependencies from PM-14 Sections 7.1-7.4. • Populate 3 open items from PM-14 Section 9 as Issues. • Mark I-02 (OI-02 tax invoice) and I-04 (KFTC env) as URGENT with escalation owners. • Confirm that R-03 (rate engine error) mitigation is RATE-04 test vectors run from Sprint 1. | docs/planning/RAID_log.csv with all RAID entries from PM-14 Sections 7 and 9 | • CSV contains exactly 8 risk rows (R-01 through R-08), 8 assumption rows (A-01 through A-08), 4 issue rows (I-01 through I-04), and 8 dependency rows (D-01 through D-08). • R-01 has likelihood High, impact High, mitigation referencing mock SFTP contingency. • R-03 mitigation explicitly states RATE-04 test vectors run from Sprint 1. • I-02 and I-04 are marked urgent with correct owners (GME Account/Tech and GME BD respectively). • D-01 dependency from KFTC to Dev Vendor has required-by date May 15 2026. | 45 | 1.3-T01 | PM | PM-14
1.3-T11 | program-mgmt | 1.3 | 1. Project Management & Mobilization | Delivery plan, environments & estimates | 1 | Create RACI matrix document from PM-14 Section 8 | PM-14 Section 8 defines a RACI for 28 activities across six roles: GME Product, GME Ops/Finance, GME Compliance, Dev Vendor, KFTC/한결원, Partner. Key RACI entries include: Rate engine implementation (Dev Vendor A/R, GME Product C, GME Ops/Finance C); ZeroPay batch integration (Dev Vendor A/R, KFTC C); CI/CD and environments (Dev Vendor A/R only); Rate/margin configuration in Admin portal (GME Ops/Finance A/R); FX treasury rate updates Phase 1 (GME Ops/Finance A/R); Phase gate sign-off technical (Dev Vendor A/R); Phase gate sign-off business (GME Product A/R); UAT execution (GME Ops/Finance A/R, Dev Vendor R); Production deployment (Dev Vendor A/R). | • Create docs/planning/RACI.md with a matrix table: activities as rows, roles as columns. • Populate all 28 activities from PM-14 Section 8 with R/A/C/I values per role. • Highlight activities where Dev Vendor is solely accountable with no GME counterpart as Responsible (potential bottleneck). • Note activities where external parties (KFTC, Partner) have R or A responsibilities - these cannot be expedited by Dev Vendor. • Cross-reference RACI rows that relate to open items (e.g., BOK reporting format confirmation = GME Compliance R, GME Product A). | docs/planning/RACI.md with 28-row RACI matrix covering all activities from PM-14 Section 8 | • Matrix has exactly 28 activity rows and 6 role columns matching PM-14 Section 8. • Rate engine implementation row shows Dev Vendor as A/R and GME Ops/Finance as C. • FX treasury rate updates row shows GME Ops/Finance as A/R with no Dev Vendor responsibility. • ZP00xx file spec provision row shows KFTC as R and GME Product as A (outside Dev Vendor control). • Training (GME Ops on Admin portal) shows Dev Vendor as A/R. | 35 | 1.3-T01 | PM | PM-14
1.3-T12 | program-mgmt | 1.3 | 1. Project Management & Mobilization | Delivery plan, environments & estimates | 1 | Document external dependency schedule and escalation protocol | PM-14 Section 6 defines six external dependencies with due dates: KFTC test environment (mid-May 2026, owner GME BD, impact: Phase 2 and all downstream delayed 1:1); ZP00xx file specs (May 15 2026, owner GME BD/KFTC); BOK FX reporting format OI-03 (TBD - escalate urgently, owner GME Compliance); tax invoice API OI-02 (before Phase 1 dev start, owner GME Account/Tech); GME Remit integration readiness (Aug 1 2026, owner GME Remit Tech); SendMN/T-Bank integration readiness (Oct 1 2026, owner external partners); initial prefunding deposit (before Phase 4 go-live). PM-14 Section 3.2 states dev vendor must notify GME immediately if KFTC access not granted by May 15 2026. | • Create docs/planning/external_dependencies.md listing all dependencies from PM-14 Section 6 and RAID D-01 through D-08. • For each dependency include: id, description, owner, due date, impact-if-late, current-status. • Define escalation protocol: check KFTC access status weekly from Apr 10; if not confirmed by Apr 17 (written confirmation per I-04), escalate immediately. • Define fallback for D-01: begin mock SFTP development in parallel per R-01 mitigation. • Flag OI-02 and OI-03 as requiring urgent resolution before Phase 1 dev start and Phase 3 go-live respectively. | docs/planning/external_dependencies.md with dependency register and escalation protocol | • All six dependency categories from PM-14 Section 6 are present with correct owners and due dates. • KFTC test environment dependency impact is stated as 1:1 delay propagation to all downstream phases. • Escalation trigger for D-01/I-04 is written confirmation by Apr 17 2026 (as per I-04 action). • Mock SFTP fallback for R-01 is documented as a parallel workstream starting if KFTC access not confirmed by May 15. • OI-02 (tax invoice) is flagged as blocking UC-04-04 automation with manual fallback instruction matching PM-14 Section 10. | 35 | 1.3-T10 | PM | PM-14
1.3-T13 | program-mgmt | 1.3 | 1. Project Management & Mobilization | Delivery plan, environments & estimates | 1 | Define phase gate acceptance criteria checklist (Phases 1-4) | PM-14 Section 5 defines acceptance criteria per phase. Phase 1 (8 criteria): rate-engine test vectors in QA-12 pass within 0.01 USD tolerance; API sandbox all endpoints respond correctly; Admin portal allows scheme/partner/margin setup without developer assistance; Partner portal login + prefunding balance + transaction list visible; pool identity (collection_usd - collection_margin_usd - payout_margin_usd = payout_usd_cost) verified; same-currency short-circuit for KRW/KRW/KRW; audit log captures actor+timestamp+previous value; API auth+secrets+endpoints per SEC-09. Phase 2: all ZP00xx types correct; daily batch windows met; E2E test with zero reconciliation discrepancy; discrepancy alerts within SLA. Phase 3: UAT sign-off; 10 live E2E transactions; 3 consecutive settlement days clean; Ops trained. Phase 4: prefunding atomicity under load; 5 FX scenarios; low-balance alert at $10000; collection/payout match offer_rate. | • Create docs/planning/phase_gate_checklists.md with one section per phase. • For each criterion write a verifiable pass/fail test statement (who performs the test, what the expected outcome is). • Phase 1: include the pool identity formula explicitly: collection_usd - collection_margin_usd - payout_margin_usd == payout_usd_cost within 0.01 USD. • Phase 4: include the prefunding atomicity test description: concurrent POST requests must not over-deduct balance (SELECT FOR UPDATE pattern, see RATE-04). • Cross-reference each criterion to its source document. | docs/planning/phase_gate_checklists.md with verifiable pass/fail acceptance statements for all four phases | • Phase 1 checklist has 8 items matching PM-14 Section 5.1 exactly. • Pool identity criterion states tolerance 0.01 USD and references RATE-04. • Same-currency short-circuit criterion explicitly names KRW/KRW/KRW (Domestic direction, GME Remit). • Phase 3 criterion includes minimum 10 live E2E transactions and 3 consecutive settlement days. • Phase 4 prefunding atomicity test references SELECT FOR UPDATE and concurrent load scenario. | 40 | 1.3-T11 | PM | PM-14
1.3-T14 | program-mgmt | 1.3 | 1. Project Management & Mobilization | Delivery plan, environments & estimates | 1 | Create sprint-level backlog skeleton: Sprint 1 and Sprint 2 tickets for Phase 1 | Sprint 1 starts Apr 13 2026 (first sprint after contract signed Apr 10). PM-14 and WBS mandate: Sprint 1 must include RATE-04 unit tests (WS-8 starts Sprint 1 with rate-engine vectors), environment provisioning (milestone Apr 17), and DB schema + migration scripting start (DAT-03). Sprint 2 runs Apr 27 - May 10. Milestone May 9: Hub Core schema + rate engine implemented. Rate engine uses 5-step USD-volume margin RECEIVE mode: step 1 payout_usd_cost = target_payout / cost_rate_pay; step 2 collection_usd = payout_usd_cost / (1-m_a-m_b); step 3 margins; step 4 send_amount = collection_usd * cost_rate_coll; step 5 collection_amount = send_amount + service_charge. Min combined margin m_a+m_b >= 2.0% for cross-border. | • Create docs/planning/sprint_backlog_S1_S2.md listing epic-level tickets for Sprints 1 and 2. • Sprint 1 (Apr 13-26): environment provisioning (WS-7), DB schema setup (WS-1), RATE-04 unit test vectors (WS-8), CI/CD pipeline skeleton (WS-7). • Sprint 2 (Apr 27-May 10): complete Hub Core rate engine (WS-1), complete DB migration scripts (WS-1), Admin System skeleton (WS-4). • For each ticket stub include: title, workstream, primary doc reference, acceptance condition. • Flag the May 9 milestone as the Sprint 2 end deliverable gate. | docs/planning/sprint_backlog_S1_S2.md with Sprint 1 and 2 ticket stubs and milestone gate | • Sprint 1 includes RATE-04 unit tests as a first-class ticket (not optional). • Sprint 1 includes environment provisioning with Apr 17 milestone target. • Sprint 2 end date aligns with or precedes May 9 Hub Core schema milestone. • Each ticket stub references its primary spec document. • Rate engine 5-step RECEIVE mode is referenced as the Sprint 2 core implementation target. | 40 | 1.3-T03, 1.3-T07 | PM | PM-14
1.3-T15 | program-mgmt | 1.3 | 1. Project Management & Mobilization | Delivery plan, environments & estimates | 1 | Create sprint-level backlog skeleton: Sprints 3-6 covering Admin portal and Northbound API | Sprint 3 Apr 27-May 10 (overlaps with Sprint 2 boundary adjustment), Sprint 4 May 11-24, Sprint 5 May 25-Jun 7, Sprint 6 Jun 8-20. Milestone May 23: Admin portal core screens functional (scheme + partner setup). Milestone Jun 6: Northbound API sandbox available. Milestone Jun 20: Phase 1 gate. Phase 2 also starts May 15 (Sprint 4 begins ZeroPay WS-3). Admin System must allow GME Ops to: register a QR scheme, register a Partner (type LOCAL/OVERSEAS), set margins m_a and m_b, view test transactions. Partner Portal must show prefunding balance and transaction list. Adding scheme/partner is CONFIG not code - generic-build constraint A-14-04 applies from Phase 1. | • Create docs/planning/sprint_backlog_S3_S6.md for Sprints 3 through 6. • Sprint 4 (May 11-24): Admin portal core screens (WS-4), ZeroPay SFTP skeleton (WS-3 start). • Sprint 5 (May 25-Jun 7): Northbound API sandbox (WS-2), Partner Portal skeleton (WS-5). • Sprint 6 (Jun 8-20): Phase 1 gate preparation, integration testing, sandbox docs. • Flag generic-build constraint: no scheme/partner logic hardcoded - all registered via DB config. | docs/planning/sprint_backlog_S3_S6.md with Sprint 3-6 ticket stubs and two milestones (May 23, Jun 6) | • Sprint 4 stubs include Admin portal core screens with May 23 milestone gate. • Sprint 5 stubs include Northbound API sandbox with Jun 6 milestone gate. • Sprint 6 is explicitly reserved for Phase 1 gate preparation and demo. • ZeroPay WS-3 work appears starting Sprint 4 (after May 15). • Generic-build constraint is documented as a Phase 1 acceptance condition. | 40 | 1.3-T14 | PM | PM-14
1.3-T16 | program-mgmt | 1.3 | 1. Project Management & Mobilization | Delivery plan, environments & estimates | 1 | Create sprint-level backlog skeleton: Sprints 7-14 covering Phase 2 ZeroPay integration | Phase 2 spans May 15 - Jul 31 2026 (Sprints 4-14). Milestones: ZeroPay merchant sync (ZP0041/ZP0051) passing Jun 13 (Sprint 5-6 boundary); all ZP00xx verified Jul 18 (Sprint 12); Phase 2 gate Jul 31 (Sprint 14). 16 ZP00xx file types: ZP0011 payment result, ZP0012 payment reg result, ZP0021 refund result, ZP0022 refund reg result, ZP0041/0043/0045/0047 merchant sync, ZP0051/0053/0055 full merchant list, ZP0061-0066 settlement. OPS-13 Section 6.2 defines 13 batch job types (JOB-ZP-01 through JOB-ZP-13) with KST windows. SFTP batch must be idempotent: check run-state DB record before generating new file; unique job_run_id UUID per run. | • Create docs/planning/sprint_backlog_S7_S14.md for Sprints 7 through 14. • Group ZP00xx implementation by subsystem: payment/refund (ZP0011/0012/0021/0022), merchant sync (ZP0041-0055), settlement (ZP0061-0066). • Assign each ZP00xx group to a sprint with acceptance condition referencing SCH-06. • Sprint 12 target: all ZP00xx types verified (Jul 18 milestone). • Sprint 14 target: Phase 2 gate E2E ZeroPay test transaction (Jul 31 milestone). • Include idempotency requirements: job_run_id UUID, DB run-state check before file generation. | docs/planning/sprint_backlog_S7_S14.md with ZP00xx sprint assignments and two milestones (Jul 18, Jul 31) | • All 16 ZP00xx file types appear in the backlog distributed across Sprints 7-12. • Sprint 12 end is mapped to the Jul 18 milestone (all ZP00xx verified). • Sprint 14 end is mapped to the Jul 31 Phase 2 gate milestone. • Idempotency requirement (job_run_id, run-state DB record) is documented for each batch job type. • SFTP credential separation (test vs. production) is noted as a constraint. | 45 | 1.3-T15, 1.3-T08 | PM | PM-14
1.3-T17 | program-mgmt | 1.3 | 1. Project Management & Mobilization | Delivery plan, environments & estimates | 1 | Create sprint-level backlog skeleton: Sprints 15-22 covering Phase 3 GME Remit launch | Phase 3 runs Aug 1 - Oct 10 2026 (10 weeks, approx Sprints 15-24). Milestones: GME Remit staging integration test Sep 5 (Sprint 19-20 boundary); UAT sign-off Sep 26 (Sprint 22); Production deployment Oct 10 (Sprint 24); Phase 3 gate Oct 10. GME Remit: LOCAL partner, KRW/KRW/KRW, same-currency short-circuit (collection_amount = target_payout + service_charge, no USD pool), service_charge KRW 500. Phase 3 acceptance: UAT signed off by GME Ops and Finance per QA-12; at least 10 E2E live production transactions (MPM and CPM); settlement batch runs without exception for 3 consecutive business days; GME Ops trained and Admin portal runbook confirmed per OPS-13; payment success rate >= 98%; settlement batch delivery 100% on-time; new scheme/partner setup < 30 minutes. | • Create docs/planning/sprint_backlog_S15_S22.md for Sprints 15-22. • Sprint 15-18: GME Remit partner onboarding config, MPM+CPM production readiness, Ops training material. • Sprint 19-20: staging integration test with GME Remit tech team (D-05: readiness required Aug 1). • Sprint 21-22: UAT execution (Sep 26 milestone), defect remediation. • Document GME Remit same-currency short-circuit: when collection=settle_A=settle_B=payout=KRW, skip USD pool; collection_amount = target_payout + service_charge. • Include 30-minute partner setup benchmark as acceptance test. | docs/planning/sprint_backlog_S15_S22.md with Phase 3 sprint stubs and three milestones (Sep 5, Sep 26, Oct 10) | • Sprint 20 end is aligned to Sep 5 GME Remit staging test milestone. • Sprint 22 end is aligned to Sep 26 UAT sign-off milestone. • Same-currency short-circuit for KRW/KRW/KRW is documented as the key technical test case for Phase 3. • D-05 dependency (GME Remit tech team available Aug 1) is noted as gating Sprint 19 start. • 30-minute new partner setup time is listed as a Phase 3 success metric with reference to BRD-01 Section 9. | 40 | 1.3-T16, 1.3-T09 | PM | PM-14
1.3-T18 | program-mgmt | 1.3 | 1. Project Management & Mobilization | Delivery plan, environments & estimates | 1 | Create sprint-level backlog skeleton: Sprints 23-30 covering Phase 4 overseas partner launch | Phase 4 runs Oct 1 - Dec 10 2026 (10 weeks, overlaps Phase 3 tail per A-14-02). Milestones: SendMN/T-Bank staging test Nov 7 (Sprint 27); UAT sign-off Phase 4 Nov 28 (Sprint 29); Production deployment Dec 10 (Sprint 31). Overseas partner (OVERSEAS type): m_a+m_b >= 2.0%, service_charge KRW 500, prefunding required (SELECT FOR UPDATE deduction). Phase 4 acceptance: prefunding atomicity under concurrent load; FX margin correct for 5 distinct rate scenarios; low-balance alert at USD 10000 threshold; collection/payout amounts match offer_rate; monthly merchant fee process operational (gated by OI-02). D-06 SendMN/T-Bank integration readiness required Oct 1. D-07 initial prefunding deposit confirmed before Phase 4 go-live. | • Create docs/planning/sprint_backlog_S23_S30.md for Sprints 23-30. • Sprint 23-24: Phase 3 production stabilisation (A-14-02 constraint), Phase 4 overseas partner config preparation. • Sprint 25-27: overseas partner integration testing with SendMN/T-Bank (D-06 required Oct 1). • Sprint 28-29: Phase 4 UAT (Nov 28 milestone), prefunding load testing. • Sprint 30: Phase 4 go-live deployment (Dec 10 milestone). • Document D-07: initial prefunding deposit must be confirmed by GME Finance before Phase 4 activation. | docs/planning/sprint_backlog_S23_S30.md with Phase 4 sprint stubs and three milestones (Nov 7, Nov 28, Dec 10) | • A-14-02 constraint (Phase 3 production stability before Phase 4 primary resource) is explicitly noted on Sprint 23. • Sprint 25 start is gated by D-06 (external partner integration readiness Oct 1). • D-07 (initial prefunding deposit) is documented as a pre-activation gate, not a dev vendor action. • Prefunding atomicity load test is a Phase 4 UAT requirement with SELECT FOR UPDATE referenced. • Five distinct FX rate scenario tests are listed as Phase 4 acceptance criteria. | 40 | 1.3-T17 | PM | PM-14
1.3-T19 | program-mgmt | 1.3 | 1. Project Management & Mobilization | Delivery plan, environments & estimates | 1 | Define CI/CD pipeline stages specification document | OPS-13 Section 4.1 defines 8 pipeline stages for every code change: (1) Build - compile+lint, zero errors gate; (2) Unit test - all pass, coverage >= 80%; (3) Security scan - SAST, dependency vuln scan, secrets leak scan, no critical/high CVEs; (4) Integration test - ephemeral env with DB, all tests pass; (5) Artifact - build container image, tag with git-sha+branch+semver, push to registry, sign image; (6) Deploy to int - automated, smoke tests pass; (7) Deploy to staging - on release/* merge, manual approval gate; (8) Deploy to prod - Release Manager approval + change record + QA sign-off. Branching: trunk-based, feature/<ticket> -> main (int auto-deploy), release/<version> (staging auto), hotfix/<ticket> (fast-track with two senior engineers + on-call). | • Create docs/planning/cicd_pipeline_spec.md describing all 8 pipeline stages with gate conditions. • Define branching strategy: feature/<ticket>, main, release/<version>, hotfix/<ticket> with deploy targets. • Document approval gates: int = fully automated; staging = automated on release/* + stakeholder sign-off; prod = Release Manager + change record + QA sign-off. • Document rollback strategy: automated rollback on smoke test failure within 5 min (redeploys previous image tag); manual rollback via runbook (OPS-13 Section 8.1). • State migration rule: no down migrations in production; blue-green for reversibility. • State secret injection: gmepay/<env>/<service>/<secret-name> paths, loaded at container start. | docs/planning/cicd_pipeline_spec.md with 8-stage pipeline definition and branching strategy | • All 8 pipeline stages are listed with exact gate conditions from OPS-13 Section 4.1 (e.g., coverage >= 80%, no high/critical CVEs). • Three approval levels are defined: automated for int, stakeholder for staging, Release Manager + change record for prod. • Automated rollback trigger is specified as smoke test failure within 5 minutes. • Secret path convention is documented with an example path. • Hotfix branch fast-track approval (two senior engineers + on-call, post-deployment review mandatory) is documented. | 35 | 1.3-T04 | PM | PM-14
1.3-T20 | program-mgmt | 1.3 | 1. Project Management & Mobilization | Delivery plan, environments & estimates | 1 | Define database migration strategy and versioning rules | OPS-13 Section 4.6 mandates: versioned migration tool (Flyway or Liquibase); every migration has unique sequential version number; migrations applied automatically at deploy time before new app version starts; backward-compatible with currently running version (additive-only: add columns/tables, never rename or drop in same release); to remove a column: release 1 removes code references, release 2 drops column; scripts in db/migrations/ reviewed as strictly as app code; all runs logged with version, timestamp, duration, operator identity; no down migrations in production. Blue-green strategy provides reversibility. OPS-13 Section 4.5 also defines blue-green for major schema-changing deploys and canary (5% traffic, 15-min monitor, SLO-breach rollback) for high-risk API changes. | • Create docs/planning/db_migration_strategy.md with migration rules as numbered constraints. • Define the two-release column removal process with example: Release N removes code reference to column X; Release N+1 drops column X. • Document migration file naming convention: V<number>__<descriptive_name>.sql in db/migrations/. • Document the blue-green deployment process for schema-changing releases. • Document the canary deployment process: 5% traffic to new version, 15-minute window, auto-promote or auto-rollback based on SLO breach. • State that migration run logs must include: version, timestamp, duration, and operator identity (for audit trail per DAT-03 audit requirements). | docs/planning/db_migration_strategy.md with migration rules, naming convention, and deployment processes | • Two-release column removal process is documented with a concrete example. • Migration naming convention V<number>__<name>.sql matches Flyway/Liquibase convention. • Blue-green process states it provides rollback via LB/DNS pointer flip with zero downtime. • Canary process specifies 5% traffic, 15-minute window, and SLO-breach as the auto-rollback trigger. • No down migrations rule is stated with justification (blue-green provides reversibility). | 30 | 1.3-T19 | PM | PM-14
1.3-T21 | program-mgmt | 1.3 | 1. Project Management & Mobilization | Delivery plan, environments & estimates | 1 | Define observability and alerting plan: metrics, logging, and dashboard specifications | OPS-13 Section 7 defines: RED metrics (api_request_rate, api_error_rate < 1%, api_latency_p95 < 500ms); USE metrics for PostgreSQL (CPU/IOPS, replication lag), Redis (memory, eviction rate), SFTP worker (job duration, queue depth); structured JSON logging with required fields: timestamp ISO-8601 UTC, level, service, env, trace_id UUID, span_id UUID, partner_id, transaction_id UUID, event, message; OpenTelemetry tracing with 8-step transaction trail (rate_quote_issued, payment_initiated, prefund_deducted, scheme_request_sent, scheme_response_received, transaction_committed, webhook_dispatched, webhook_delivered/failed); six dashboards (Operations Overview, API SLO, Batch Health, Prefunding Monitor, Revenue, Security). | • Create docs/planning/observability_plan.md with sections for metrics, logging, tracing, dashboards, and alerts. • List all RED metrics with SLO thresholds (error rate < 1%, p95 latency < 500ms from NFR-10). • List all 8 required structured log fields and specify that monetary amounts (collection_amount, prefund_balance) are not logged in production log streams. • Define the 8 OpenTelemetry trace steps for a full transaction. • Specify all 6 dashboard names and their key panels. • Cross-reference OPS-13 Section 7.5 alert catalog for P1/P2/P3/P4 conditions. | docs/planning/observability_plan.md with metrics, logging schema, tracing spec, and dashboard list | • RED metrics include api_error_rate < 1% and api_latency_p95 < 500ms with reference to NFR-10. • All 10 required structured log fields are listed (timestamp, level, service, env, trace_id, span_id, partner_id, transaction_id, event, message). • Security note states that collection_amount and prefund_balance are excluded from production log streams. • 8 OpenTelemetry trace steps are listed in order matching OPS-13 Section 7.3. • 6 dashboard names match OPS-13 Section 7.4 (Operations Overview, API SLO, Batch Health, Prefunding Monitor, Revenue, Security). | 40 | 1.3-T04 | PM | PM-14
1.3-T22 | program-mgmt | 1.3 | 1. Project Management & Mobilization | Delivery plan, environments & estimates | 1 | Define prefunding alerting thresholds and escalation runbook per environment | OPS-13 Section 7.5.2 defines prefunding alerts: low balance < USD 10,000 (P2 - email partner + notify GME Ops); critical balance < USD 2,000 (P1 - suspend partner payments + escalate immediately); balance zero (P1 - all partner payments suspended). OPS-13 Section 5.3 environment config: dev $100, int $1,000, staging $10,000, prod $10,000 per partner config. OVERVIEW from canonical facts: prefunding applies only to OVERSEAS partners (SendMN, T-Bank type = OVERSEAS); LOCAL partners (GME Remit) require no prefunding. Deduction is atomic via SELECT FOR UPDATE. Low-balance alert is a Phase 4 acceptance criterion (PM-14 Section 5.4): alert at USD 10,000 must be confirmed working. | • Create docs/planning/prefunding_alert_spec.md with alert threshold table for each environment. • Define three alert levels: Low (P2 < $10,000), Critical (P1 < $2,000), Zero (P1 = 0), with actions for each. • State that prefunding applies only to OVERSEAS partner type; LOCAL partners do not have a prefunding balance. • Define escalation for P1: suspend partner payments, escalate to GME Ops; confirm partner is notified via email. • State that deduction atomicity (SELECT FOR UPDATE) prevents overdraft; schema design must ensure no race condition between concurrent payment requests. • Cross-reference Phase 4 acceptance criterion: low-balance alert at $10,000 must be demonstrated in UAT. | docs/planning/prefunding_alert_spec.md with per-tier thresholds, alert levels, and escalation actions | • Three alert levels are defined with exact USD thresholds: $10,000 (P2), $2,000 (P1), $0 (P1). • Per-environment threshold table matches OPS-13 Section 5.3 values (dev $100, int $1,000, staging $10,000, prod $10,000). • Document explicitly states prefunding applies to OVERSEAS partners only; LOCAL partners are excluded. • SELECT FOR UPDATE atomicity requirement is referenced for Phase 4 implementation. • Phase 4 UAT step to demonstrate low-balance alert firing is listed. | 30 | 1.3-T13 | PM | PM-14
1.3-T23 | program-mgmt | 1.3 | 1. Project Management & Mobilization | Delivery plan, environments & estimates | 1 | Define batch job schedule, retry policy, and alerting plan for ZeroPay SFTP jobs | OPS-13 Section 6 defines 13 ZeroPay batch jobs (JOB-ZP-01 through JOB-ZP-13) with KST windows. Critical jobs: JOB-ZP-01 ZP0011 GME->ZeroPay by 02:00 KST; JOB-ZP-02 ZP0021 GME->ZeroPay by 02:00 KST; JOB-ZP-03 ZP0012 ZeroPay->GME expected by 05:00 KST; JOB-ZP-05 ZP0061 settlement request GME->ZeroPay by 05:00 KST; JOB-ZP-06 ZP0062 settlement result expected by 10:00 KST. Retry policy: up to 3 automatic retries, exponential back-off 30s/120s/300s; after 3 failures job enters FAILED state, P1 alert fired, dependency chain halts. Alert on missed windows: ZP0011/0021 not submitted by 01:45 KST = P1 PagerDuty + Ops Slack. Idempotency: unique job_run_id UUID per run; duplicate runs for same logical date no-op. | • Create docs/planning/batch_job_schedule.md with a table of all 13 jobs. • For each job include: job_id, file(s), direction (GME->ZeroPay or ZeroPay->GME), submission or receipt window (KST), dependency on other jobs, criticality level. • Define the daily critical-path dependency chain: transactions close -> JOB-ZP-01/02 02:00 -> JOB-ZP-03/04 05:00 receive -> validate -> JOB-ZP-05 05:00 submit -> JOB-ZP-06 10:00 receive -> reconcile -> JOB-ZP-07 14:00 -> JOB-ZP-08 19:00 -> JOB-ZP-09 22:00. • Document retry policy: max 3 retries, back-off 30s/120s/300s, FAILED state after 3 failures with P1 alert. • Document P1 alert conditions for missed windows with exact KST times and notification channels (PagerDuty + Ops Slack). | docs/planning/batch_job_schedule.md with 13-job table, dependency chain, retry policy, and alert conditions | • All 13 batch jobs (JOB-ZP-01 through JOB-ZP-13) are present with correct KST windows matching OPS-13 Section 6.2. • Critical-path chain is documented in order: JOB-ZP-01/02 -> JOB-ZP-03/04 -> JOB-ZP-05 -> JOB-ZP-06 -> JOB-ZP-07 -> JOB-ZP-08 -> JOB-ZP-09. • Retry policy shows exactly 30s/120s/300s back-off intervals with FAILED state and P1 alert after 3rd failure. • P1 alert for ZP0011/0021 missed window is at 01:45 KST (15 minutes before 02:00 deadline). • Idempotency via job_run_id UUID and duplicate-run no-op is documented. | 40 | 1.3-T16 | PM | PM-14
1.3-T24 | program-mgmt | 1.3 | 1. Project Management & Mobilization | Delivery plan, environments & estimates | 1 | Unit test: verify sprint dates and phase gate alignment in sprint_cadence.csv | Sprint cadence document from ticket 1.3-T03 must have sprint boundaries correctly aligned to four phase gates: Phase 1 gate Jun 20 2026, Phase 2 gate Jul 31 2026, Phase 3 gate Oct 10 2026, Phase 4 gate Dec 10 2026. Sprint duration must be exactly 14 days (2 weeks). Phases 1 and 2 overlap May 15 - Jun 20. All dates must be Monday start (sprint starts on Monday). The test also verifies that no sprint spans across a phase gate date without the gate date landing exactly on a sprint end date. | • Write a test script in tests/planning/test_sprint_cadence.py (or equivalent). • Parse docs/planning/sprint_cadence.csv. • Assert all four phase gate dates are sprint end dates. • Assert all sprint durations are exactly 14 days. • Assert that sprints covering May 15 - Jun 20 are marked as Phase 1+2 overlap. • Assert no gap between consecutive sprint end and next sprint start. | tests/planning/test_sprint_cadence.py that validates sprint_cadence.csv structure and gate alignment | • Test passes when Jun 20, Jul 31, Oct 10, and Dec 10 all appear as sprint_end dates in the CSV. • Test fails with clear message if any sprint duration is not exactly 14 days. • Test confirms at least one sprint is marked with both Phase 1 and Phase 2 in its phase column (the overlap period). • Test confirms no date gaps between consecutive sprint rows. • Test is runnable with a single command and produces pass/fail output. | 30 | 1.3-T03 | PM | PM-14
1.3-T25 | program-mgmt | 1.3 | 1. Project Management & Mobilization | Delivery plan, environments & estimates | 1 | Unit test: verify RAID log completeness and required field population | RAID log document from ticket 1.3-T10 must contain exactly 8 risks, 8 assumptions, 4 issues, and 8 dependencies as defined in PM-14 Sections 7 and 9. Critical checks: R-01 must be present with High likelihood and High impact; R-03 mitigation must reference Sprint 1; D-01 must have due date May 15 2026; I-02 must be marked urgent; I-04 must have target date mid-May 2026. All rows must have non-empty id, description, owner, and status fields. | • Write tests/planning/test_raid_log.py (or equivalent) to validate RAID_log.csv. • Assert type=R count is 8, type=A count is 8, type=I count is 4, type=D count is 8. • Assert R-01 likelihood == High and impact == High. • Assert D-01 target_date contains May and 2026 and owner contains GME BD. • Assert I-02 status field contains urgent. • Assert all rows have non-empty id, description, owner columns. | tests/planning/test_raid_log.py that validates completeness and critical field values in RAID_log.csv | • Test counts exactly 8+8+4+8 = 28 rows in RAID_log.csv; fails with count mismatch message otherwise. • R-01 row validation passes when likelihood=High and impact=High. • D-01 due-date check passes when value references May 2026. • I-02 urgency check passes when status field contains urgent. • Test is runnable standalone and produces actionable error messages on failure. | 25 | 1.3-T10 | PM | PM-14
1.3-T26 | program-mgmt | 1.3 | 1. Project Management & Mobilization | Delivery plan, environments & estimates | 1 | Unit test: verify feature flag register completeness and default values | Feature flag register from ticket 1.3-T05 must contain exactly 5 flags as defined in OPS-13 Section 5.2: FEATURE_LIVE_FX_FEED (default false), FEATURE_PARTNER_REFUND_API (default false), FEATURE_OUTBOUND_PAYMENTS (default false), FEATURE_BOK_REPORTING (default false), FEATURE_MULTI_SCHEME_ROUTING (default false). All Phase 1 defaults must be false because: live FX feed is Phase 2 scope; refund API is admin-only in Phase 1; outbound payments not in Phase 1 scope; BOK reporting pending OI-03; multi-scheme routing not needed in Phase 1 single-scheme configuration. | • Write tests/planning/test_feature_flags.py to parse docs/planning/feature_flags.md. • Assert all 5 flag names are present (exact string match). • Assert all 5 Phase 1 default values are false. • Assert FEATURE_BOK_REPORTING has a reference to OI-03 in the enabling_condition field. • Assert FEATURE_LIVE_FX_FEED has a note referencing Phase 2. • Fail with clear message if any flag is missing or has a non-false default. | tests/planning/test_feature_flags.py that validates feature flag names and defaults | • Test asserts presence of all 5 exact flag names as listed in OPS-13 Section 5.2. • Test asserts all 5 default values are false for Phase 1. • FEATURE_BOK_REPORTING validation includes check for OI-03 reference. • FEATURE_LIVE_FX_FEED validation includes check for Phase 2 scope reference. • Test is runnable and produces clear output per flag checked. | 20 | 1.3-T05 | PM | PM-14
1.3-T27 | program-mgmt | 1.3 | 1. Project Management & Mobilization | Delivery plan, environments & estimates | 1 | Unit test: verify milestone table completeness and date consistency | Milestone table from ticket 1.3-T02 must contain exactly 19 milestones from PM-14 Section 3.1. Key date constraints: contract signed = Apr 10 2026; dev env provisioned = Apr 17 2026 (7 days after contract); Hub Core schema + rate engine = May 9 2026; Admin portal core = May 23 2026; Northbound API sandbox = Jun 6 2026; Phase 1 gate = Jun 20 2026; KFTC test env = mid-May 2026; all ZP00xx verified = Jul 18 2026; Phase 2 gate = Jul 31 2026; GME Remit staging = Sep 5 2026; UAT sign-off Phase 3 = Sep 26 2026; Production deployment = Oct 10 2026; Phase 3 gate = Oct 10 2026; overseas staging = Nov 7 2026; UAT sign-off Phase 4 = Nov 28 2026; prod deployment Phase 4 = Dec 10 2026. | • Write tests/planning/test_milestones.py to parse docs/planning/milestones.csv. • Assert row count is 19. • Assert specific target dates for at least 8 named milestones (contract Apr 10, dev env Apr 17, Hub Core May 9, API sandbox Jun 6, Phase 1 gate Jun 20, Phase 2 gate Jul 31, Phase 3 gate Oct 10, Phase 4 deployment Dec 10). • Assert phase gate milestones precede or equal the subsequent phase start date (e.g., Phase 1 gate Jun 20 <= Phase 2 start May 15 is intentional overlap - flag this as overlap not error). • Assert KFTC milestone is flagged as critical-path. | tests/planning/test_milestones.py that validates milestone count, dates, and critical-path flag | • Test asserts exactly 19 milestone rows; fails with count message otherwise. • 8 specific date assertions all pass for the named milestones. • Phase 1/Phase 2 date overlap is detected and accepted (not flagged as error) because PM-14 explicitly plans this overlap. • KFTC milestone critical-path flag check passes. • Test output identifies which specific milestone failed the date check. | 25 | 1.3-T02 | PM | PM-14
1.3-T28 | program-mgmt | 1.3 | 1. Project Management & Mobilization | Delivery plan, environments & estimates | 1 | Unit test: verify phase gate checklist completeness and acceptance criteria field presence | Phase gate checklists from ticket 1.3-T13 must contain: Phase 1 - 8 criteria including pool identity formula, same-currency short-circuit, audit log, security (SEC-09); Phase 2 - 4 criteria (ZP00xx types, batch windows, E2E test, discrepancy alert); Phase 3 - 5 criteria (UAT, 10 E2E transactions, 3 settlement days, Ops trained, success metrics); Phase 4 - 5 criteria (atomicity, 5 FX scenarios, $10,000 alert, offer_rate match, tax invoice). Pool identity formula must appear verbatim: collection_usd - collection_margin_usd - payout_margin_usd == payout_usd_cost. | • Write tests/planning/test_phase_gate_checklists.py to parse docs/planning/phase_gate_checklists.md. • Assert Phase 1 section contains 8 checklist items. • Assert pool identity formula string appears in Phase 1 section. • Assert Phase 3 section contains the text 10 E2E and 3 consecutive. • Assert Phase 4 section contains USD 10,000 and SELECT FOR UPDATE. • Assert all four phases have a section heading present. | tests/planning/test_phase_gate_checklists.py that validates checklist structure and key formula presence | • Phase 1 checklist count assertion passes for 8 items. • Pool identity formula string search finds the formula with collection_usd, collection_margin_usd, payout_margin_usd, payout_usd_cost all present. • Phase 3 assertions for 10 transactions and 3 consecutive days both pass. • Phase 4 assertions for $10,000 threshold and SELECT FOR UPDATE atomicity both pass. • Test fails gracefully with section name when a required term is missing. | 25 | 1.3-T13 | PM | PM-14
1.3-T29 | program-mgmt | 1.3 | 1. Project Management & Mobilization | Delivery plan, environments & estimates | 1 | Unit test: verify RACI matrix completeness (28 activities, 6 roles) | RACI document from ticket 1.3-T11 must contain 28 activity rows and 6 role columns (GME Product, GME Ops/Finance, GME Compliance, Dev Vendor, KFTC/한결원, Partner). Critical checks from PM-14 Section 8: Rate engine implementation - Dev Vendor must be A/R; FX treasury rate updates - GME Ops/Finance must be A/R and Dev Vendor must not appear; Production deployment - Dev Vendor must be A/R; ZP00xx file spec provision - KFTC must be R; Training GME Ops on Admin portal - Dev Vendor must be A/R. Every row must have exactly one A (Accountable) assignment. | • Write tests/planning/test_raci.py to parse docs/planning/RACI.md (or a RACI.csv version). • Assert 28 activity rows present. • Assert each row has exactly one cell with A or A/R value. • Assert Rate engine implementation row has Dev Vendor = A/R. • Assert FX treasury rate updates row has GME Ops/Finance = A/R and Dev Vendor cell is empty or I. • Assert ZP00xx file spec provision row has KFTC = R. | tests/planning/test_raci.py that validates RACI structure, row count, and critical role assignments | • Test passes on 28-row count; reports actual vs expected on failure. • Single-accountable-per-row rule check passes for all 28 rows. • Rate engine implementation role check passes (Dev Vendor A/R). • FX rate updates check passes (GME Ops/Finance A/R, Dev Vendor not responsible). • ZP00xx spec provision check passes (KFTC R). | 25 | 1.3-T11 | PM | PM-14
1.3-T30 | program-mgmt | 1.3 | 1. Project Management & Mobilization | Delivery plan, environments & estimates | 1 | Produce environment provisioning runbook for E1 (dev) and E2 (int) environments | OPS-13 Section 2 and Section 3 define the environment architecture. E1 (dev): synthetic data only, developers only, DB pool size 5, manual batch trigger, mock SFTP (no real KFTC connection), secret path gmepay/dev/<service>/<secret>. E2 (int): synthetic + ZeroPay sandbox data, dev+QA access, DB pool 20, manual batch trigger, live connection to 한결원 test SFTP (D-01 critical dependency - must not be configured until KFTC credentials received), secret path gmepay/int/<service>/<secret>. OPS-13 Section 3.1 defines cloud-agnostic topology: Public DMZ (WAF, LB), API Zone, Worker Zone, Data Zone (PostgreSQL primary+replica, Redis, message queue), Management Zone. | • Create docs/planning/env_runbook_E1_E2.md with step-by-step provisioning instructions for both tiers. • E1 dev: steps for provisioning PostgreSQL (pool 5), Redis, mock SFTP server, secret manager with gmepay/dev/* paths, log level DEBUG. • E2 int: same steps but pool 20, KFTC test SFTP credentials (note D-01 dependency - do not provision SFTP connection until credentials received from KFTC), log level DEBUG. • Include network zone boundaries from OPS-13 Section 3.2: Public DMZ, API Zone, Worker Zone, Data Zone, Management Zone. • Include smoke test commands to verify each environment tier is functional after provisioning. | docs/planning/env_runbook_E1_E2.md with provisioning steps, config values, and smoke tests for E1 and E2 | • E1 provisioning specifies DB pool = 5, mock SFTP, DEBUG log level, and synthetic data only. • E2 provisioning specifies DB pool = 20, KFTC test SFTP (with D-01 gate note), DEBUG log level. • Five network zones (Public DMZ, API Zone, Worker Zone, Data Zone, Management Zone) are described for each environment. • D-01 dependency (KFTC test SFTP credentials) is explicitly gated: E2 SFTP step must not be executed until credentials are in hand. • Smoke test section includes at least: API health check, DB connection test, and SFTP connectivity test. | 45 | 1.3-T04, 1.3-T12 | PM | PM-14
1.3-T31 | program-mgmt | 1.3 | 1. Project Management & Mobilization | Delivery plan, environments & estimates | 1 | Produce environment provisioning runbook for E3 (staging) and E4 (prod) environments | OPS-13 Section 2.3 and 2.4: E3 staging - production-like with masked PII, monthly refresh cycle, QA+Ops+partner tech leads access, PR merge approval required for deployment, DB pool 80, KST production batch windows, KFTC test SFTP (same as E2). E4 prod - real data, GDPR/PIPA data residency, break-glass only for DB and secrets, change-approval workflow for deployments, DB pool 200, KST production windows, KFTC production SFTP. OPS-13 Section 4.5: staging uses blue-green for major releases; prod uses blue-green for schema-changing deploys and canary (5% traffic, 15-min window) for high-risk API changes. Production DB and secrets accessible ONLY via break-glass procedure (SEC-09 Section 6). | • Create docs/planning/env_runbook_E3_E4.md. • E3 staging: provisioning steps for DB pool 80, KFTC test SFTP, KST batch windows, masked PII data refresh procedure, deployment gate (PR merge approval). • E4 prod: provisioning steps for DB pool 200, KFTC production SFTP, change-approval workflow, break-glass access procedure reference (SEC-09 Section 6). • Include data handling rules: staging = anonymised schema refresh monthly; prod = real data, GDPR/PIPA constraints. • Include blue-green and canary deployment instructions for E3 and E4. | docs/planning/env_runbook_E3_E4.md with provisioning steps, deployment gates, and access controls for E3 and E4 | • E3 provisioning specifies DB pool = 80, KFTC test SFTP (same credentials as E2), and deployment gate requiring PR merge approval. • E4 provisioning specifies DB pool = 200, KFTC production SFTP, and break-glass reference to SEC-09 Section 6. • Data handling rules correctly distinguish staging (masked/anonymised, monthly refresh) from prod (real data, GDPR/PIPA). • Blue-green deployment process references 5% canary traffic and 15-minute monitoring window for high-risk API changes in prod. • Batch job schedule for E3 and E4 specifies KST production windows (not manual trigger). | 45 | 1.3-T30 | PM | PM-14
1.3-T32 | program-mgmt | 1.3 | 1. Project Management & Mobilization | Delivery plan, environments & estimates | 1 | Define open items resolution plan and impact assessment for OI-01, OI-02, OI-03 | PM-14 Section 9 defines three open items. OI-01 Customer Approval Method: in-app UX for CPM/MPM not specified; dev vendor implements generic partner-configurable approval step; target before Phase 3 go-live. OI-02 Tax Invoice API: no confirmed third-party API (Hometax or KFTC) for Korean merchant monthly fee tax invoices; UC-04-04 blocked; dev vendor stubs with manual admin-portal workflow (operator triggers invoice issuance manually) with future API hook; target before Phase 1 dev start (urgent). OI-03 BOK Reporting Format: exact fields/frequency/channel for FX1014/FX1015 not confirmed; FEATURE_BOK_REPORTING flag is false until resolved; dev vendor captures all required fields from day one; target TBD (escalate urgently). PM-14 Section 10 confirms: if OI-03 unresolved before Phase 3 go-live, initial live service runs without automated BOK reporting and GME assumes regulatory risk. | • Create docs/planning/open_items_plan.md with one section per open item. • OI-01: document the generic partner-configurable approval step design requirement; state this cannot be hardcoded. • OI-02: document stub implementation plan (manual admin-portal workflow for UC-04-04 with future API hook); mark as urgent with owner GME Account/Tech. • OI-03: document the plug-in reporting module design requirement; state that all FX1014/FX1015 required fields must be captured from day 1 (no data loss if format later confirmed); state regulatory risk assumption from PM-14 Section 10. • For each open item list: current status, owner, target date, what is blocked, interim approach. | docs/planning/open_items_plan.md with resolution plans and interim approaches for OI-01, OI-02, OI-03 | • OI-01 section states approval step must be generic and partner-configurable, not hardcoded per partner. • OI-02 section describes manual stub for UC-04-04 in Phase 1 with explicit future API hook design point. • OI-03 section states that all FX1014/FX1015 fields must be stored from day 1 to avoid data loss when format is confirmed. • OI-03 section includes the PM-14 Section 10 regulatory risk assumption verbatim or paraphrased accurately. • Each section has owner, target date, and blocked-component fields populated. | 35 | 1.3-T12 | PM | PM-14
1.3-T33 | program-mgmt | 1.3 | 1. Project Management & Mobilization | Delivery plan, environments & estimates | 1 | Produce consolidated baselined plan document linking all planning artefacts | WBS 1.3 parent deliverable is a Baselined Plan. All planning artefacts created in WBS 1.3 (milestones.csv, sprint_cadence.csv, estimates_phase1-4, RAID_log.csv, RACI.md, environments.md, feature_flags.md, cicd_pipeline_spec.md, batch_job_schedule.md, observability_plan.md, open_items_plan.md) must be consolidated into a single baselined plan document that serves as the entry point for GME Product Team review and sign-off. The baselined plan is frozen at the end of WBS 1.3; all future changes require a change request reviewed by GME PM within 2 business days (per PM-14 A-14-03). | • Create docs/planning/BASELINED_PLAN.md as a table of contents linking all planning artefacts. • Include a version number (v1.0), baseline date (Apr 10 2026 or date of completion), and status (BASELINED). • Include a one-paragraph executive summary: four phases, Oct 10 2026 go-live, critical path dependency on KFTC, generic-build constraint. • List each planning artefact with its file path, description, and the PM-14 section it implements. • Add a change-control note: post-baseline changes require change request reviewed by GME PM within 2 business days. • Include the four phase gate dates as a top-level summary table. | docs/planning/BASELINED_PLAN.md serving as the consolidated entry point for all WBS 1.3 planning artefacts | • Document has version number, baseline date, and status = BASELINED in the header. • Executive summary accurately states Oct 10 2026 go-live, four phases, KFTC critical dependency, and generic-build constraint. • All planning artefact file paths listed are valid relative paths within docs/planning/. • Four phase gate dates (Jun 20, Jul 31, Oct 10, Dec 10) appear in the top-level summary table. • Change-control note references PM-14 A-14-03 and specifies 2 business days for GME PM review. | 30 | 1.3-T09, 1.3-T10, 1.3-T11, 1.3-T13, 1.3-T19, 1.3-T21, 1.3-T22, 1.3-T23, 1.3-T31, 1.3-T32 | PM | PM-14
1.4-T01 | program-mgmt | 1.4 | 1. Project Management & Mobilization | Architecture & design sign-off | 1 | Review SAD-02 architectural goals and non-negotiable constraints | WBS 1.4 architecture sign-off. SAD-02 defines 6 non-negotiable architectural goals: (1) config-not-code for schemes and partners, (2) BOK-compliant three-currency USD pivot, (3) scheme-agnostic routing via pluggable Scheme Adapters, (4) partner-agnostic Northbound API, (5) all four directions (Domestic/Inbound/Outbound/Hub) supported from day one with Phase 1 activating only Domestic and Inbound, (6) payout-first RECEIVE mode. Every design decision must preserve these goals. | • Read SAD-02 sections 1-2 (purpose, goals, ADR table AD-01 through AD-12) in full • For each of the 12 ADRs verify the proposed implementation approach complies • Flag any proposed deviations and document written justification for GME Product Team • Confirm in writing that RECEIVE mode (payout-first) is the only supported computation direction • Record sign-off against each ADR in the architecture review checklist | Completed architecture review checklist with pass/flag/defer status for all 12 ADRs (AD-01 through AD-12) | • All 12 ADRs reviewed; none marked pass without evidence • AD-04 (config-not-code) confirmed: adding ZeroPay as a scheme requires only a DB row insert, not a code change • AD-05 (payout-first) confirmed: no SEND-mode computation path exists in proposed design • AD-06 (atomic prefunding before scheme call) confirmed: SELECT FOR UPDATE on prefunding_account before any scheme call • Any flagged deviations have written GME Product Team approval or a remediation plan | 45 |  | ARCH | SAD-02
1.4-T02 | program-mgmt | 1.4 | 1. Project Management & Mobilization | Architecture & design sign-off | 1 | Review SAD-02 Logical Component Architecture and component inventory | WBS 1.4 architecture sign-off. SAD-02 section 4 defines 14 logical components across Northbound/Auth, Core Processing, Scheme Layer, Data/Config, and Supporting Services. Core components: API Gateway, Auth Service, QR Parser, Smart Router, Rate Engine, Transaction Orchestrator, Prefunding Ledger, Settlement Engine, Reconciliation Engine, Scheme Adapter (ZeroPay + future), Config/Registry, Audit Log Store, Admin Service, Partner Portal Service, Notification/Webhook, Reporting/BOK. Each has defined responsibilities and key dependencies. | • Walk through each of the 14 components in the inventory table • Verify all stated responsibilities are captured in the proposed build plan • Check that component dependencies (e.g. Rate Engine depends on Config/Registry and Rate Table) are reflected in the proposed module structure • Confirm no core component (Orchestrator, Rate Engine) contains scheme-specific or partner-specific code branches • Note any missing components or unassigned responsibilities | Component coverage matrix: each of the 14 SAD-02 components listed with build-plan reference, owner team, and sign-off status | • All 14 components are mapped to at least one concrete build task • Transaction Orchestrator is the ONLY component that transitions transaction state • Scheme Adapter boundary is clear: ZeroPay protocol details live inside the adapter only, not in Orchestrator or Rate Engine • Config/Registry is identified as the single source of truth for Scheme/Partner/Rule config with a Redis hot cache layer • No component missing from the build plan | 40 | 1.4-T01 | ARCH | SAD-02
1.4-T03 | program-mgmt | 1.4 | 1. Project Management & Mobilization | Architecture & design sign-off | 1 | Review SAD-02 Transaction Orchestrator state machine for correctness | WBS 1.4 architecture sign-off. SAD-02 section 5.2 defines 9 transaction states: QUOTED, PENDING_DEBIT, DEBITED, SCHEME_SENT, APPROVED, UNCERTAIN, FAILED, REVERSED, REFUNDED. Key transitions: QUOTED->PENDING_DEBIT (OVERSEAS commit), QUOTED->DEBITED (LOCAL commit, no prefund), PENDING_DEBIT->FAILED (insufficient balance), SCHEME_SENT->UNCERTAIN (timeout), UNCERTAIN->APPROVED/FAILED (batch reconciliation within 24h). Rate-lock happens at APPROVED. UNCERTAIN resolution uses ZP0012/ZP0022 files received ~05:00 KST daily. | • Draw the complete state transition diagram and compare against SAD-02 section 5.2 state machine • Verify every terminal state (FAILED, REVERSED, REFUNDED) has no outbound transitions • Confirm the UNCERTAIN->APPROVED and UNCERTAIN->FAILED transitions are driven only by the Settlement/Reconciliation Engine • Verify that rate-lock (all USD pool values + derived rates become immutable) occurs at CommitTransaction before APPROVED • Check that prefunding reversal on UNCERTAIN->FAILED is explicitly modelled | Annotated state machine diagram with transition guards, actors, and rate-lock trigger point marked; sign-off from tech lead and GME Product | • 9 states and all specified transitions are present; no undocumented states added • UNCERTAIN state has a 24-hour resolution SLA; unresolved > 24h triggers ops alert (per SAD-02 section 5.2) • Prefunding deduction is held during UNCERTAIN and reversed only on confirmed FAILED - not on timeout alone • Rate-lock (immutable USD pool columns) occurs at CommitTransaction call, not at APPROVED - SAD-02 AD-08 • LOCAL partner path skips PENDING_DEBIT and goes QUOTED->DEBITED directly | 50 | 1.4-T02 | ARCH | SAD-02
1.4-T04 | program-mgmt | 1.4 | 1. Project Management & Mobilization | Architecture & design sign-off | 1 | Review SAD-02 Rate Engine component design and 5-step formula alignment | WBS 1.4 architecture sign-off. Rate Engine executes 5-step RECEIVE-mode: (1) payout_usd_cost = target_payout / cost_rate_pay, (2) collection_usd = payout_usd_cost / (1 - m_a - m_b), (3) collection_margin_usd = collection_usd * m_a; payout_margin_usd = collection_usd * m_b, (4) send_amount = collection_usd * cost_rate_coll, (5) collection_amount = send_amount + service_charge. Pool identity: collection_usd - collection_margin_usd - payout_margin_usd == payout_usd_cost (tolerance 0.01 USD). Same-currency short-circuit: collection_amount = target_payout + service_charge. Rate source modes: IDENTITY, LIVE, MANUAL, PARTNER. | • Confirm the proposed Rate Engine module implements all 5 steps in exact sequence • Verify pool identity check is enforced after Step 3 and before committing any rate quote • Confirm same-currency short-circuit condition (collection = settle_A = settle_B = payout) is detected from rule.is_same_ccy_shortcircuit flag • Verify cross-border rules enforce m_a + m_b >= 0.02 (2% minimum) per DAT-03 rule table constraint • Confirm offer_rate_coll = send_amount / (collection_usd - collection_margin_usd) and cross_rate = target_payout / send_amount are derived (not configured) | Rate Engine design review sign-off document listing each of the 5 steps, the pool identity check, the short-circuit path, and derived field formulas with explicit confirmation or issue flag | • Example: target_payout=50000 KRW, cost_rate_pay=1380, m_a=0.01, m_b=0.01, cost_rate_coll=1.0, service_charge=0 -> payout_usd_cost=36.232 USD, collection_usd=36.966 USD, send_amount=36.966 USD, collection_amount=36.966 USD; pool identity holds within 0.01 USD • service_charge is not included in pool calculations - it is added after Step 4 only • m_a + m_b < 0.02 on a cross-border rule is rejected at rule save time (DB CHECK constraint) • IDENTITY rate source returns exactly 1.0 with no treasury lookup • PARTNER rate source triggers Partner B Quote Client call; deviation > 1% returns PARTNER_B_QUOTE_DEVIATION | 55 | 1.4-T02 | ARCH | SAD-02
1.4-T05 | program-mgmt | 1.4 | 1. Project Management & Mobilization | Architecture & design sign-off | 1 | Review SAD-02 Prefunding Ledger design for atomicity and OVERSEAS-only enforcement | WBS 1.4 architecture sign-off. Prefunding is OVERSEAS partners only (e.g. SendMN, T-Bank with partner_type = OVERSEAS). LOCAL partners (e.g. GME Remit) skip prefunding entirely. Deduction is atomic using SELECT FOR UPDATE on prefunding_account.balance. For MPM, deduction at POST /v1/payments. For CPM, deduction at POST /v1/payments/cpm/generate (AD-07). Scheme is NEVER called without a prior committed deduction (AD-06). prefunding_ledger_entry is immutable, append-only (no UPDATE/DELETE). Low-balance alert when balance < low_balance_threshold (default USD 10,000). | • Confirm prefunding deduction logic branches correctly on partner.partner_type: OVERSEAS deducts, LOCAL skips • Verify SELECT FOR UPDATE is used on prefunding_account row (not application-level locking) to prevent concurrent overdraw • Confirm CPM deduction happens at QR-generate step, not at confirm step (AD-07) • Verify prefunding_ledger_entry table has no UPDATE or DELETE paths - every balance change creates a new row • Confirm low-balance alert fires when balance_after < threshold and dispatches email to low_balance_alert_email | Prefunding design review checklist: partner-type branching, locking mechanism, CPM timing, ledger immutability, alert trigger - all signed off or flagged | • Concurrent requests from OVERSEAS partner cannot result in negative balance: only one SELECT FOR UPDATE succeeds per row at a time • LOCAL partner (GME_REMIT, partner_type=LOCAL) has no prefunding_account row and skips deduction without error • CPM deduction at generate means partner prefunding is held while QR is displayed but before merchant scans - balance_after reflects this reservation • balance_after on each ledger entry equals the sum of all prior entries for that account (running balance snapshot) • Insufficient balance returns HTTP 402 or equivalent rejection before any scheme call is attempted | 45 | 1.4-T03 | ARCH | SAD-02
1.4-T06 | program-mgmt | 1.4 | 1. Project Management & Mobilization | Architecture & design sign-off | 1 | Review SAD-02 Scheme Adapter pattern and pluggability contract | WBS 1.4 architecture sign-off. SAD-02 section 5.3 defines the SchemeAdapter interface with 6 methods: authoriseCpm, submitMpm, generateBatchFiles, parseBatchFile, processMerchantSync, healthCheck. Adding a new scheme requires only: (1) implement SchemeAdapter interface, (2) register in Config/Registry with scheme_id, (3) configure rules - no changes to Orchestrator, Rate Engine, or any other core component. ZeroPay Adapter handles: CPM relay to KFTC REST API, SFTP file assembly/parsing for all ZP00xx types, merchant/QR sync ingestion, net vs gross settlement logic. | • Verify the proposed SchemeAdapter interface exposes all 6 methods and no scheme-specific arguments leak into the interface signature • Confirm the Transaction Orchestrator calls only the interface methods - no instanceof or scheme_code conditionals • Verify ZeroPay-specific logic (ZP00xx file formats, KFTC API endpoint, net/gross settlement) is entirely within the ZeroPay Adapter class • Confirm registration: adding a second scheme would require only a new adapter class + Config/Registry insert • Review ZeroPay Adapter CPM relay path: inbound KFTC push -> inboundCpmPending event -> Orchestrator rate compute -> prefunding deduct -> confirm/decline to KFTC | Scheme Adapter interface review document: method signatures, pluggability test scenario, ZeroPay boundary confirmation, sign-off | • No scheme_code, zeropay, or KFTC references exist in Transaction Orchestrator source • SchemeAdapter interface compiles/type-checks independently of any ZeroPay implementation • CPM relay path diagram shows KFTC push arrives at adapter endpoint and is forwarded to Orchestrator via inboundCpmPending event • A hypothetical second scheme (e.g. KHQR) could be added by implementing 6 interface methods and inserting one Config/Registry row • healthCheck method returns AdapterHealth object usable by the observability stack without scheme-specific parsing | 40 | 1.4-T02 | ARCH | SAD-02
1.4-T07 | program-mgmt | 1.4 | 1. Project Management & Mobilization | Architecture & design sign-off | 1 | Review SAD-02 Settlement Engine design and batch scheduling correctness | WBS 1.4 architecture sign-off. SAD-02 section 5.4 defines Settlement Engine cron windows (all KST; note KST = UTC+09:00 constant, no DST): ZP0011/ZP0021 at ~02:00 KST (17:00 UTC prior day), ZP0061 at ~05:00 KST (20:00 UTC prior day), ZP0063 at ~14:00 KST (05:00 UTC), ZP0065/ZP0066 at ~22:00 KST (13:00 UTC). Inbound: ZP0012/ZP0022 polled ~05:00, ZP0062 ~10:00, ZP0064 ~19:00. All batch jobs must be idempotent. Distributed locking (Redis SETNX or K8s leader election) prevents duplicate execution. Net vs gross: domestic = net settlement, international = gross. | • Verify all 5 outbound file generation cron expressions are defined in UTC equivalents of the KST windows • Confirm all settlement batch jobs are idempotent (running twice does not generate duplicate files or double-debit ledger) • Verify distributed locking mechanism: only one instance generates each file type per settlement_date • Confirm inbound file polling schedule for ZP0012 (~05:00 KST), ZP0062 (~10:00 KST), ZP0064 (~19:00 KST) • Review UNCERTAIN resolution path: ZP0012/ZP0022 inbound triggers Orchestrator transition to APPROVED or FAILED | Settlement Engine scheduling review table: each file type with KST window, UTC cron expression, idempotency mechanism, and sign-off status | • 02:00 KST = 17:00 UTC (prior day); cron expression for ZP0011 generates is '0 17 * * *' UTC • A batch job triggered twice for the same settlement_date and file_type returns the existing settlement_batch row without creating a duplicate • UNCERTAIN transactions from prior day are resolved within the next ZP0012/ZP0022 processing cycle (no later than ~06:00 KST next day) • settlement_batch.status transitions: PENDING -> GENERATED -> TRANSMITTED -> RECEIVED -> RECONCILED; ERROR is a terminal recovery state • Domestic net settlement: GME retains its margin share and remits only the net amount to KFTC; cross-border gross settlement: GME remits full payout amount | 50 | 1.4-T03 | ARCH | SAD-02
1.4-T08 | program-mgmt | 1.4 | 1. Project Management & Mobilization | Architecture & design sign-off | 1 | Review SAD-02 integration architecture - Northbound API contracts | WBS 1.4 architecture sign-off. Northbound API: REST over HTTPS; authentication via HMAC-SHA256 API key+secret (per-request signature over canonical request string); Idempotency-Key header required on all POST calls (deduplicated for 24h via Redis keyed by partner_id + idempotency_key); per-partner rate limiting at API Gateway; versioned at /v1/; webhook events: payment.pending_debit, payment.approved, payment.failed, payment.reversed; webhook retry: exponential backoff 5s/30s/2min/10min/1h/6h max 6 attempts; partner returns HTTP 200 to acknowledge; dead-letter after final retry. | • Verify HMAC-SHA256 signature scheme covers the canonical request string (method + path + timestamp + body hash) • Confirm Idempotency-Key deduplication window is exactly 24 hours, keyed by (partner_id, idempotency_key) • Verify all 4 webhook event types are dispatched with HMAC signature and partner must return HTTP 200 • Confirm 6-attempt exponential backoff schedule matches: 5s, 30s, 2min, 10min, 1h, 6h • Verify that internal rate fields (m_a, m_b, cost_rate_coll, cost_rate_pay) are NOT included in any Northbound API response | Northbound API integration review checklist: auth scheme, idempotency, webhook delivery, backoff schedule, data privacy - signed off or flagged | • Replaying same POST /v1/payments with identical Idempotency-Key within 24h returns the stored response (HTTP 200 with original txn_ref) without creating a second transaction • Webhook delivery failure after 6 attempts stores a dead-letter event in a queryable ops table • Partner API response for GET /v1/rates contains offer_rate, send_amount, service_charge, collection_amount, validUntil - but NOT m_a, m_b, cost_rate_coll, or cost_rate_pay • HMAC-SHA256 signature verification rejects any request where the signature does not match, returning HTTP 401 • URL-path versioning: /v1/ prefix on all endpoints; v2 introduced only for breaking changes | 40 | 1.4-T02 | ARCH | SAD-02
1.4-T09 | program-mgmt | 1.4 | 1. Project Management & Mobilization | Architecture & design sign-off | 1 | Review SAD-02 technology stack and infrastructure topology | WBS 1.4 architecture sign-off. SAD-02 section 9 recommends: Java 21 + Spring Boot 3.x (or Node.js 20 + NestJS); PostgreSQL 16 (OLTP); Redis 7 (rate quote cache TTL, idempotency keys, config hot cache); Apache Kafka or RabbitMQ (message broker); AWS S3 or S3-compatible (object storage for ZP00xx batch files); Docker + Kubernetes (EKS/GKE/on-prem); Kong/AWS API Gateway/Spring Cloud Gateway; HashiCorp Vault or AWS Secrets Manager. Section 10 defines 4 environments: dev, sandbox, staging, production. Production must be in Korea region (Seoul ap-northeast-2 or Korean colocation) per data residency requirement. | • Confirm vendor has selected one backend language (Java or Node) and documented the choice • Verify PostgreSQL is selected and PostgreSQL 16 or higher for SELECT FOR UPDATE support • Confirm Redis 7 is selected for rate quote cache with TTL support • Verify Korea-region deployment is planned for production (AWS ap-northeast-2 or equivalent) • Confirm secrets are managed via Vault or AWS Secrets Manager - no credentials in env vars or source code • Review message broker choice (Kafka vs RabbitMQ) against event-replay requirement for BOK audit trail | Technology stack decision record: each SAD-02 recommended component with selected technology, justification, and deviations (if any) approved by GME Product Team | • Backend language is standardised to one choice across all services; no mixed Java/Node polyglot without explicit approval • PostgreSQL version >= 16 confirmed; floating-point money types (FLOAT/DOUBLE/REAL) are absent from schema design • Redis TTL configuration supports range 60-1800 seconds per rate_quote_ttl_seconds field on partner table • No SFTP credentials, API keys, or DB passwords appear in source code, Dockerfiles, or CI/CD pipeline definitions • Any deviation from recommended stack has written GME Product Team approval documented in the stack decision record | 35 | 1.4-T01 | ARCH | SAD-02
1.4-T10 | program-mgmt | 1.4 | 1. Project Management & Mobilization | Architecture & design sign-off | 1 | Review SAD-02 deployment topology and network zone architecture | WBS 1.4 architecture sign-off. SAD-02 section 10.4 defines 3 network zones: (1) DMZ/public subnet - API Gateway and Load Balancer only, (2) Application subnet (private) - Hub Core, Admin Service, Partner Portal Service, Rate Engine, Transaction Orchestrator, Settlement Engine, (3) Data subnet (private, most restricted) - PostgreSQL, Redis, Message Broker; plus a dedicated (4) Egress/SFTP proxy zone with static IP for KFTC SFTP allow-listing. Key HA requirements: min 2 replicas for API Gateway and Hub Core; PostgreSQL primary + synchronous standby with Patroni-style failover; Redis cluster (3+3 nodes); message broker replication factor >= 2; distributed locking for settlement batch jobs. | • Verify the 4-zone network topology is represented in the infrastructure design (DMZ, App, Data, Egress/SFTP) • Confirm API Gateway is the only component accessible from the public internet • Confirm PostgreSQL resides in the data subnet with no direct access from outside the application subnet • Verify SFTP proxy has a static/fixed IP registered with KFTC for allow-listing (SAD-02 assumption A-04) • Review HA configuration: 2+ API Gateway replicas, PostgreSQL synchronous standby, Redis cluster mode | Infrastructure topology review checklist: 4-zone network design, HA targets, SFTP proxy static IP, Korea-region data residency - all confirmed or flagged | • Only port 443 (HTTPS) is inbound to the DMZ; no direct inbound to Application or Data subnets • PostgreSQL has a synchronous standby replica (not async) to meet RPO <= 1 hour per NFR-10 • SFTP outbound traffic to KFTC originates from a fixed IP; the IP is registered with KFTC before sandbox testing • Settlement Engine batch jobs use distributed locking so that two pod instances do not generate duplicate ZP00xx files for the same settlement_date • Kubernetes liveness and readiness probes are defined for all Hub Core services | 35 | 1.4-T09 | ARCH | SAD-02
1.4-T11 | program-mgmt | 1.4 | 1. Project Management & Mobilization | Architecture & design sign-off | 1 | Review DAT-03 modelling conventions and money/currency handling rules | WBS 1.4 data model sign-off. DAT-03 defines: all table/column names snake_case; BIGINT surrogate PK on every table; natural keys as UNIQUE constraints; all timestamps as TIMESTAMPTZ (UTC); soft-delete with is_active BOOLEAN + deactivated_at; audit columns (created_at, updated_at, created_by, updated_by) on all mutable tables; FKs enforced at DB level with ON DELETE RESTRICT default; enums stored as VARCHAR with CHECK constraints. Money: KRW stored as BIGINT (whole won); USD and cross-currency amounts as DECIMAL(20,4); FX-derived intermediary amounts as DECIMAL(20,8). Every amount column paired with a currency column (e.g. collection_amount DECIMAL(20,4) + collection_ccy CHAR(3)). | • Review proposed schema DDL for compliance with snake_case naming, BIGINT surrogate PKs, and UNIQUE natural keys • Verify no FLOAT, DOUBLE, or REAL types are used for any monetary column • Verify all amount columns have a paired _ccy CHAR(3) column in the same table • Confirm soft-delete pattern (is_active + deactivated_at) is present on all partner, scheme, and rule tables • Verify all timestamps are TIMESTAMPTZ (not TIMESTAMP WITHOUT TIME ZONE) | Schema modelling conventions review: DDL checklist for naming, money types, currency pairing, soft-delete, timestamp types - signed off or flagged | • KRW amounts (e.g. target_payout for ZeroPay transactions) are stored as BIGINT, not DECIMAL • No table uses FLOAT or DOUBLE for any column including rate fields - all rates use DECIMAL(20,8) • collection_amount column is always accompanied by collection_ccy CHAR(3) in the same row • transaction.payout_usd_cost, collection_usd, collection_margin_usd, payout_margin_usd are DECIMAL(20,8) not DECIMAL(20,4) • All tables that can be referenced by a transaction have is_active BOOLEAN and deactivated_at TIMESTAMPTZ; hard DELETE is prohibited | 40 | 1.4-T01 | ARCH | SAD-02
1.4-T12 | program-mgmt | 1.4 | 1. Project Management & Mobilization | Architecture & design sign-off | 1 | Review DAT-03 Configuration entities: qr_scheme, scheme_country, partner, partner_credential | WBS 1.4 data model sign-off. DAT-03 section 4 defines 4 core config entities. qr_scheme: scheme_code VARCHAR(30) UNIQUE, payout_ccy CHAR(3), supported_modes VARCHAR(20) (MPM/CPM/BOTH), partner_b_quote_enabled BOOLEAN, partner_b_quote_deviation_pct DECIMAL(6,4) default 0.0100, sftp_host VARCHAR(255) stored encrypted, api_credential_ref VARCHAR(120) referencing secrets vault, status VARCHAR(20) CHECK IN (TESTING,ACTIVE,INACTIVE). scheme_country: UNIQUE(scheme_id, country_code). partner: partner_code UNIQUE, partner_type CHECK IN (LOCAL,OVERSEAS), rate_quote_ttl_seconds INT CHECK BETWEEN 60 AND 1800 DEFAULT 300, is_active DEFAULT FALSE (Ops activates). partner_credential: api_secret_hash bcrypt-hashed, only one active credential per partner. | • Verify qr_scheme DDL includes all columns from DAT-03 section 4.1 with correct types • Verify scheme_country has UNIQUE(scheme_id, country_code) constraint for CPM location-based selection • Verify partner.partner_type CHECK constraint limits to LOCAL and OVERSEAS only • Verify partner_credential stores api_secret_hash (bcrypt) not plaintext; expires_at TIMESTAMPTZ allows credential rotation • Confirm partner.is_active DEFAULT FALSE so new partners are inactive until Ops activates | Config entity DDL review: qr_scheme, scheme_country, partner, partner_credential tables verified against DAT-03 spec with pass/flag per column | • qr_scheme.partner_b_quote_deviation_pct defaults to 0.0100 (1.0%) and is DECIMAL(6,4) • scheme_country INSERT of (ZEROPAY_scheme_id, 'KR') succeeds; duplicate insert of same pair fails with UNIQUE constraint violation • partner.rate_quote_ttl_seconds = 59 is rejected by CHECK BETWEEN 60 AND 1800 • partner_credential.api_secret_hash is a bcrypt hash string starting with '$2a$' or '$2b$'; raw secret is not stored anywhere in DB • Deactivating partner sets is_active = FALSE and deactivated_at = NOW(); existing transactions are not deleted | 45 | 1.4-T11 | ARCH | SAD-02
1.4-T13 | program-mgmt | 1.4 | 1. Project Management & Mobilization | Architecture & design sign-off | 1 | Review DAT-03 rule entity and constraint correctness for rate engine integration | WBS 1.4 data model sign-off. DAT-03 section 4.6 defines the rule table: PK is BIGINT id; UNIQUE(partner_id, scheme_id, direction); direction CHECK IN (INBOUND,OUTBOUND,DOMESTIC,HUB); rate_coll_source and rate_pay_source CHECK IN (IDENTITY,LIVE,MANUAL,PARTNER); m_a DECIMAL(8,6) CHECK >= 0; m_b DECIMAL(8,6) CHECK >= 0; CHECK constraint: is_same_ccy_shortcircuit OR (m_a + m_b) >= 0.02 (cross-border rules need min 2% combined margin); service_charge_ccy must equal settle_a_ccy; is_same_ccy_shortcircuit is a computed flag set to TRUE when collection_ccy = settle_a_ccy = settle_b_ccy = payout_ccy; status CHECK IN (DRAFT,ACTIVE,SUSPENDED); effective_from TIMESTAMPTZ (changes apply to new transactions only). | • Verify UNIQUE(partner_id, scheme_id, direction) constraint exists in DDL • Verify DB-level CHECK: (is_same_ccy_shortcircuit = TRUE OR (m_a + m_b) >= 0.02) • Verify is_same_ccy_shortcircuit is computed (trigger or application logic) and never manually editable • Verify manual_rate_coll is NOT NULL when rate_coll_source = 'MANUAL' (enforced by application-level validation or CHECK) • Verify service_charge_ccy = settle_a_ccy is enforced (application rule or DB constraint) | Rule entity DDL and constraint review document: all CHECK constraints listed and verified with test SQL examples, sign-off status | • INSERT rule with m_a=0.005, m_b=0.010, is_same_ccy_shortcircuit=FALSE raises constraint violation (combined 1.5% < 2%) • INSERT rule with m_a=0.010, m_b=0.010, is_same_ccy_shortcircuit=FALSE succeeds (combined 2.0% meets minimum) • INSERT rule with same (partner_id, scheme_id, direction) as existing row fails with UNIQUE constraint violation • rule with rate_coll_source='MANUAL' and manual_rate_coll NULL is rejected before reaching the rate engine • is_same_ccy_shortcircuit auto-set to TRUE for GME_REMIT on ZEROPAY DOMESTIC (all ccys = KRW) | 45 | 1.4-T12 | ARCH | SAD-02
1.4-T14 | program-mgmt | 1.4 | 1. Project Management & Mobilization | Architecture & design sign-off | 1 | Review DAT-03 rate_quote and transaction entities for rate-lock completeness | WBS 1.4 data model sign-off. DAT-03 sections 5.1 and 5.2 define rate_quote and transaction tables. rate_quote stores all 5-step values plus derived rates at quote time. On CommitTransaction, all values are copied to transaction and become immutable (locked). Locked columns on transaction: collection_usd, payout_usd_cost, collection_margin_usd, payout_margin_usd, send_amount, service_charge, collection_amount, offer_rate_coll, cross_rate, cost_rate_coll, cost_rate_pay - set at committed_at and never UPDATE-able after. For same-currency short-circuit, USD pool fields are NULL; offer_rate_coll and cross_rate are NULL. transaction.committed_at is set on CommitTransaction; transaction.completed_at is set on scheme APPROVED. | • Verify rate_quote table has all 5-step pool columns with correct types (DECIMAL(20,8) for USD amounts, DECIMAL(20,4) for KRW) • Verify transaction table has all locked rate columns matching rate_quote columns exactly (same names, same types) • Confirm there is no application or DB path that allows UPDATE of locked rate columns after committed_at is set • Verify rate_quote.is_used is set to TRUE when the quote is linked to a committed transaction (prevents reuse) • Verify NULL handling for same-ccy short-circuit: collection_usd, payout_usd_cost, collection_margin_usd, payout_margin_usd, offer_rate_coll, cross_rate, cost_rate_coll, cost_rate_pay are all nullable | Rate-lock review checklist: rate_quote->transaction copy path, locked column list, immutability guarantee, NULL handling for same-ccy path - signed off or flagged | • After CommitTransaction, UPDATE transaction SET collection_usd = 99 WHERE id = X is blocked by application-level guard or DB trigger • rate_quote.valid_until = quote_issued_at + rate_quote_ttl_seconds; CommitTransaction after valid_until returns EXPIRED_QUOTE error • rate_quote.treasury_rate_id_coll FK links to the specific treasury_rate row used, providing point-in-time rate audit trail • For a same-currency GME Remit transaction: collection_usd IS NULL, offer_rate_coll IS NULL, and collection_amount = target_payout + service_charge • transaction.rate_quote_id FK ensures every committed transaction has exactly one locked quote | 50 | 1.4-T13 | ARCH | SAD-02
1.4-T15 | program-mgmt | 1.4 | 1. Project Management & Mobilization | Architecture & design sign-off | 1 | Review DAT-03 prefunding_account and prefunding_ledger_entry for correctness | WBS 1.4 data model sign-off. DAT-03 section 6 defines prefunding entities. prefunding_account: one row per OVERSEAS partner (UNIQUE partner_id FK), currency always USD, balance DECIMAL(20,4), low_balance_threshold DECIMAL(20,4) default 10000.00. prefunding_ledger_entry: immutable append-only (no updated_at, no UPDATE/DELETE permitted), entry_type CHECK IN (DEBIT_PAYMENT, DEBIT_REVERSAL, CREDIT_TOPUP, CREDIT_REVERSAL), amount DECIMAL(20,4) CHECK > 0 (direction indicated by entry_type), balance_after DECIMAL(20,4) running snapshot, INDEX(account_id, created_at). low_balance_alert_config: one per partner, threshold_usd, alert_email. | • Verify prefunding_account has UNIQUE(partner_id) constraint - one account per OVERSEAS partner only • Verify prefunding_ledger_entry has no updated_at column and no UPDATE path in application code • Verify balance_after is a denormalized running snapshot and equals the sum of all prior DEBIT and CREDIT entries for the account • Verify INDEX(account_id, created_at) on prefunding_ledger_entry for balance history queries • Confirm low_balance_alert_config.threshold_usd default is 10000.00 and triggers alert when balance drops below threshold | Prefunding entity DDL review: prefunding_account, prefunding_ledger_entry, low_balance_alert_config tables verified against DAT-03 with pass/fail per constraint | • INSERT prefunding_account for a LOCAL partner (partner_type=LOCAL) is prohibited at application layer (not just DB constraint) • Two concurrent transactions that each try to deduct USD 60,000 from a USD 80,000 balance result in exactly one success and one INSUFFICIENT_FUNDS rejection (SELECT FOR UPDATE guarantees this) • prefunding_ledger_entry.amount = -500 is rejected by CHECK > 0 constraint; negative debits are represented by entry_type=DEBIT_PAYMENT with positive amount • Running balance can be reconstructed from scratch: SUM(amount) WHERE entry_type IN (CREDIT_TOPUP, CREDIT_REVERSAL) - SUM(amount) WHERE entry_type IN (DEBIT_PAYMENT, DEBIT_REVERSAL) = current balance • Alert fires exactly once when balance crosses below threshold, not repeatedly on every subsequent debit | 45 | 1.4-T14 | ARCH | SAD-02
1.4-T16 | program-mgmt | 1.4 | 1. Project Management & Mobilization | Architecture & design sign-off | 1 | Review DAT-03 settlement, reconciliation, and merchant/QR sync entities | WBS 1.4 data model sign-off. DAT-03 sections 7.1-7.6 define: settlement_batch (one per scheme/file_type/date, status CHECK IN PENDING/GENERATED/TRANSMITTED/RECEIVED/RECONCILED/ERROR, idempotency key is UNIQUE(scheme_id, file_type, settlement_date)); settlement_file (FK to batch, stores filename, sftp_path, SHA-256 checksum); reconciliation_item (match_status CHECK IN MATCHED/DISCREPANCY/MISSING_GME/MISSING_SCHEME, resolution_status CHECK IN UNRESOLVED/RESOLVED/ESCALATED); merchant (merchant_id VARCHAR(50) UNIQUE ZeroPay ID, account_no AES-256 encrypted at rest); qr_code (qr_code_value VARCHAR(512) UNIQUE, qr_code_type CHECK IN STATIC_MPM/DYNAMIC_CPM); merchant_sync_log (one per ZP file sync run). | • Verify settlement_batch has UNIQUE(scheme_id, file_type, settlement_date) to enforce idempotency • Verify settlement_file stores SHA-256 checksum for integrity verification • Verify reconciliation_item covers all 4 match statuses and 3 resolution statuses • Verify merchant.account_no is marked for AES-256 encryption at rest in the schema/ORM layer • Confirm qr_code.is_active = FALSE immediately when deactivation sync arrives (ZP0043/ZP0053) | Settlement, reconciliation, and merchant/QR entity DDL review with pass/flag per table and constraint; sign-off from tech lead and GME Ops | • Second INSERT into settlement_batch with same (scheme_id, file_type, settlement_date) fails - idempotency enforced at DB level • reconciliation_item with match_status=DISCREPANCY is automatically created when gme_amount != scheme_amount for the same txn_ref • merchant.account_no is never returned in plain text from any API endpoint; ORM/repository layer applies decryption only for internal settlement processing • qr_code.status deactivation is processed atomically: a deactivated QR code at scan time returns an appropriate error before rate quote or payment proceeds • merchant_sync_log records_deactivated count matches number of merchant rows set to is_active=FALSE in that sync run | 45 | 1.4-T11 | ARCH | SAD-02
1.4-T17 | program-mgmt | 1.4 | 1. Project Management & Mobilization | Architecture & design sign-off | 1 | Review DAT-03 reporting entities: bok_report_record, revenue_record, tax_invoice | WBS 1.4 data model sign-off. DAT-03 section 8 defines reporting entities. bok_report_record: one per cross-border transaction, report_type CHECK IN (FX1014, FX1015), stores offer_rate_coll (BOK FX1015 field #14), usd_amount (intermediary), submission_status CHECK IN (PENDING, SUBMITTED, CONFIRMED, FAILED). Domestic (same-ccy) transactions are exempt. revenue_record: populated at transaction commit, fx_margin_usd = collection_margin_usd + payout_margin_usd, fee_share_pct = 0.70 for ZeroPay (70% to GME). tax_invoice: for cross-border merchants, merchant_fee_krw = total_transaction_amount_krw * fee_rate, vat_krw = merchant_fee_krw * 0.10, zeropay_share_krw = 0.21% of invoice subtotal, invoice_amount_krw = merchant_fee_krw + vat_krw. | • Verify bok_report_record is created for every INBOUND/OUTBOUND/HUB transaction but NOT for DOMESTIC (same-ccy) transactions • Verify bok_report_record.offer_rate_coll is copied from transaction.offer_rate_coll (locked value) • Verify revenue_record.fx_margin_usd = collection_margin_usd + payout_margin_usd at commit time • Verify tax_invoice formula: merchant_fee_krw = total * fee_rate, vat_krw = merchant_fee_krw * 0.10, invoice_amount = merchant_fee_krw + vat_krw, zeropay_share_krw = invoice subtotal * 0.0021 • Confirm all bok_report_record values derive from locked transaction fields (never re-computed from live rates) | Reporting entity DDL review: bok_report_record, revenue_record, tax_invoice with formula verification and pass/flag per column | • bok_report_record is absent for a GME_REMIT DOMESTIC transaction where is_same_ccy_shortcircuit = TRUE • revenue_record.fx_margin_usd for a transaction with collection_margin_usd = 0.37 USD and payout_margin_usd = 0.37 USD equals 0.74 USD exactly • tax_invoice for a merchant with monthly_total = 1,000,000 KRW at fee_rate 0.0050: merchant_fee = 5,000 KRW, vat = 500 KRW, zeropay_share = 10.50 KRW, invoice_amount = 5,500 KRW • bok_report_record.submission_status starts as PENDING; transitions to SUBMITTED only after BOK confirmation channel call; never auto-submitted without operator or scheduler trigger • revenue_record.fee_share_pct = 0.70 for all ZeroPay transactions (qr_scheme.gme_fee_share_pct = 0.70) | 45 | 1.4-T16 | ARCH | SAD-02
1.4-T18 | program-mgmt | 1.4 | 1. Project Management & Mobilization | Architecture & design sign-off | 1 | Review DAT-03 audit_log and api_request_log entities for compliance | WBS 1.4 data model sign-off. DAT-03 section 9 defines audit entities. audit_log: immutable append-only (NO UPDATE or DELETE permitted), stores actor_id, actor_type CHECK IN (OPERATOR, SYSTEM, PARTNER), action CHECK IN (CREATE, UPDATE, DELETE, ACTIVATE, DEACTIVATE), entity_type (table name), entity_id (row PK), before_value JSONB (NULL for CREATE), after_value JSONB (NULL for DELETE), occurred_at TIMESTAMPTZ, ip_address INET, request_id. Retention >= 7 years (BOK/KYC requirement). api_request_log: request_id UNIQUE, stores method, path, status_code, request_body_hash SHA-256 (not plaintext), response_time_ms, ip_address. | • Verify audit_log has no UPDATE or DELETE grants in application role permissions • Verify before_value is NULL for CREATE actions and after_value is NULL for DELETE actions • Verify api_request_log.request_body_hash stores SHA-256 hash, not plaintext request body • Confirm a DB-level trigger or application invariant prevents any UPDATE to audit_log rows • Verify audit_log.retention policy: confirm rows are never purged before 7 years from occurred_at | Audit and security entity DDL review: audit_log immutability, retention policy, api_request_log body hashing - signed off or flagged | • Application DB user has INSERT privilege on audit_log but no UPDATE or DELETE privilege • UPDATE audit_log SET before_value = '{}' WHERE id = 1 returns permission denied or equivalent error • Rate table update (treasury_rate insert) creates an audit_log entry with actor_id = operator ID, action = CREATE, entity_type = treasury_rate, after_value = JSON of new rate row • api_request_log.request_body_hash = SHA256 of raw request bytes; plaintext body is never stored • 7-year retention: a SELECT on audit_log for a row 8 years old still returns data (no auto-purge within retention window) | 40 | 1.4-T11 | ARCH | SAD-02
1.4-T19 | program-mgmt | 1.4 | 1. Project Management & Mobilization | Architecture & design sign-off | 1 | Review DAT-03 RBAC entities: hub_user and hub_role | WBS 1.4 data model sign-off. DAT-03 section 9.2 defines hub_user: id, email, name, role_id FK -> hub_role, is_active BOOLEAN, last_login_at TIMESTAMPTZ, created_at, updated_at, created_by. hub_role: id, role_code VARCHAR UNIQUE (SUPER_ADMIN, OPS_ADMIN, OPS_VIEWER, FINANCE), permissions JSONB. Four defined roles: SUPER_ADMIN (full access), OPS_ADMIN (config + settlement + exceptions), OPS_VIEWER (read-only), FINANCE (reporting and revenue only). Role changes must be audit-logged. SAD-02 section 11.1 requires RBAC for all operator actions; config changes, rate overrides, and refund initiation require authenticated session. | • Verify hub_role has CHECK or UNIQUE constraint on role_code limiting to 4 defined values (SUPER_ADMIN, OPS_ADMIN, OPS_VIEWER, FINANCE) • Verify hub_user.role_id FK references hub_role with ON DELETE RESTRICT • Confirm role changes (update hub_user.role_id) generate an audit_log entry with before_value and after_value • Verify hub_user.is_active = FALSE blocks login at authentication layer • Review permissions JSONB structure: define what actions each role permits (e.g. OPS_VIEWER cannot call rate override endpoints) | RBAC entity review: hub_user and hub_role DDL, role_code constraints, permission matrix for all 4 roles, sign-off | • hub_role INSERT with role_code = BILLING is rejected by CHECK constraint (not in allowed values) • An OPS_VIEWER session attempting to update a treasury_rate receives HTTP 403 Forbidden • SUPER_ADMIN can deactivate a partner; audit_log records this with actor_id, before_value = {is_active:true}, after_value = {is_active:false} • hub_user.last_login_at is updated on every successful authentication, enabling idle session detection • hub_user with is_active = FALSE cannot authenticate via the Admin System login flow | 35 | 1.4-T18 | ARCH | SAD-02
1.4-T20 | program-mgmt | 1.4 | 1. Project Management & Mobilization | Architecture & design sign-off | 1 | Review DAT-03 enum reference values and CHECK constraints completeness | WBS 1.4 data model sign-off. DAT-03 section 11 defines canonical enum values stored as VARCHAR with CHECK constraints. Key enums: payment_mode (MPM, CPM); direction (INBOUND, OUTBOUND, DOMESTIC, HUB); transaction_status (INITIATED, PREFUND_DEDUCTED, SUBMITTED, APPROVED, DECLINED, UNCERTAIN, FAILED, CANCELLED, REFUNDED); rate_source (IDENTITY, LIVE, MANUAL, PARTNER); partner_type (LOCAL, OVERSEAS); scheme_status (TESTING, ACTIVE, INACTIVE); partner_status (ONBOARDING, ACTIVE, SUSPENDED, INACTIVE); settlement_batch.status (PENDING, GENERATED, TRANSMITTED, RECEIVED, RECONCILED, ERROR); ZeroPay file_type codes (ZP0011-ZP0066). | • List all enum columns across all tables and verify each has a corresponding CHECK constraint in DDL • Verify transaction_status values match SAD-02 state machine states exactly (no extra states, no missing states) • Confirm ZeroPay file_type codes in settlement_batch are restricted to the 14 valid ZP00xx codes • Verify rate_source CHECK IN ('IDENTITY','LIVE','MANUAL','PARTNER') on rule.rate_coll_source and rule.rate_pay_source • Check that no enum is implemented as a PostgreSQL ENUM type (must be VARCHAR + CHECK for portability) | Complete enum/CHECK constraint audit table: every VARCHAR enum column listed with allowed values and DDL CHECK expression verified | • transaction_status = 'PROCESSING' is rejected (not in allowed values); valid states are INITIATED, PREFUND_DEDUCTED, SUBMITTED, APPROVED, DECLINED, UNCERTAIN, FAILED, CANCELLED, REFUNDED • settlement_batch.file_type = 'ZP0099' is rejected by CHECK constraint • direction = 'NORTHBOUND' is rejected; valid values are INBOUND, OUTBOUND, DOMESTIC, HUB only • No PostgreSQL ENUM type appears in any CREATE TABLE statement - all enums are VARCHAR with CHECK • Adding a new transaction_status value requires only a migration to update the CHECK constraint - no code change needed for the column type itself | 35 | 1.4-T11 | ARCH | SAD-02
1.4-T21 | program-mgmt | 1.4 | 1. Project Management & Mobilization | Architecture & design sign-off | 1 | Review DAT-03 indexes and query performance design | WBS 1.4 data model sign-off. DAT-03 requires: every FK column is indexed; transaction composite indexes: (partner_id, committed_at), (scheme_id, completed_at), (status, committed_at), (scheme_ref), (hub_txn_ref); prefunding_ledger_entry index: (account_id, created_at); treasury_rate indexed on ccy_pair (latest rate lookup: WHERE ccy_pair = 'usd_krw' ORDER BY effective_at DESC LIMIT 1); qr_code.qr_code_value UNIQUE (used at payment scan time). Rate quote lookup by quote_ref (UNIQUE index). Performance targets from SAD-02/NFR-10: GET /v1/rates p99 < 300ms, POST /v1/payments p99 < 2000ms. | • List all FK columns across all tables and verify each has an explicit CREATE INDEX statement in migration files • Verify all 5 composite indexes on transaction table are present • Verify treasury_rate has an index on (ccy_pair, effective_at DESC) for efficient latest-rate lookup • Verify qr_code.qr_code_value has a UNIQUE index (primary payment path: QR scan lookup) • Confirm rate_quote.quote_ref has a UNIQUE index (CommitTransaction lookup path) | Index coverage report: all FK columns, composite indexes, and performance-critical lookup indexes listed with CREATE INDEX statements and query plan estimates | • EXPLAIN ANALYZE for latest treasury rate SELECT uses index scan on ccy_pair, not sequential scan • EXPLAIN ANALYZE for transaction lookup by txn_ref uses UNIQUE index scan, row estimate = 1 • EXPLAIN ANALYZE for partner transaction history (partner_id, committed_at range) uses composite index scan • prefunding_ledger_entry balance history query for 10,000 entries returns in < 50ms with index on (account_id, created_at) • No missing FK index detected: running pg_catalog query for unindexed FKs returns 0 rows | 40 | 1.4-T20 | ARCH | SAD-02
1.4-T22 | program-mgmt | 1.4 | 1. Project Management & Mobilization | Architecture & design sign-off | 1 | Review SAD-02 open items and assumptions register for Phase 1 impact | WBS 1.4 architecture sign-off. SAD-02 section 13 lists 7 assumptions (A-01 to A-07) and 3 open items (OI-01 to OI-03). Key Phase 1 impacts: A-01 (manual FX rates only, xe.com feed is Phase 2 - rate table schema must support both); A-06 (Partner B quote not needed for Phase 1 ZeroPay, built but not exercised); A-07 (no partner-API refunds in Phase 1, admin portal only); OI-02 (tax invoice API TBD - Hometax or equivalent); OI-03 (BOK FX1014/FX1015 field mapping and submission channel TBD). DAT-03 section 12 adds A1-A7 assumptions including KRW as BIGINT, DECIMAL(20,8) for USD intermediary amounts. | • Document the status of all 7 SAD-02 assumptions and 3 open items - confirmed, assumed, or blocked • Confirm treasury_rate table schema supports both MANUAL and LIVE source columns (source CHECK IN ('LIVE','MANUAL')) • Confirm bok_report_record schema is provisioned with placeholder columns sufficient for known FX1014/FX1015 fields even though submission channel is TBD • Confirm refund data model (refund table + REFUNDED state) is present even though partner API refunds are Phase 2 • Get written confirmation or deferral decision from GME on each open item before Phase 1 dev start | Open items and assumptions review document: each SAD-02/DAT-03 assumption confirmed or flagged; each open item with owner, resolution target date, and Phase 1 impact assessment | • treasury_rate.source has both MANUAL and LIVE values in CHECK constraint even though LIVE feed is Phase 2 • bok_report_record table exists with offer_rate_coll, usd_amount, collection_amount, payout_amount columns pre-provisioned for future FX1014/FX1015 mapping • refund table and REFUNDED transaction_status exist in Phase 1 schema even though partner API refund endpoint is not built • OI-03 (BOK reporting) has a named owner at GME (e.g. Compliance team) and a resolution target date in PM-14 RAID log • Any unresolved open item that could require schema migration if resolved incorrectly is escalated to GME sponsor before schema is finalized | 45 | 1.4-T09 | ARCH | SAD-02
1.4-T23 | program-mgmt | 1.4 | 1. Project Management & Mobilization | Architecture & design sign-off | 1 | Unit test: verify 5-step rate engine formula with numeric example (cross-border) | WBS 1.4 architecture sign-off. The 5-step RECEIVE-mode formula must be testable before sign-off. Inputs: target_payout = 50000 KRW, cost_rate_pay = 1380.0 (usd_krw), m_a = 0.01, m_b = 0.01, cost_rate_coll = 1.0 (settle_a = USD), service_charge = 0 USD. Expected: payout_usd_cost = 50000/1380 = 36.2319 USD (DECIMAL(20,8)), collection_usd = 36.2319/(1-0.01-0.01) = 36.9713 USD, collection_margin_usd = 36.9713*0.01 = 0.3697 USD, payout_margin_usd = 0.3697 USD, send_amount = 36.9713*1.0 = 36.9713 USD, collection_amount = 36.9713+0 = 36.9713 USD. Pool identity: 36.9713 - 0.3697 - 0.3697 = 36.2319 = payout_usd_cost (within 0.01 USD tolerance). offer_rate_coll = 36.9713/(36.9713-0.3697) = 1.0101. cross_rate = 50000/36.9713 = 1352.38 (KRW per USD). | • Write a unit test that calls the Rate Engine computeQuote function with the exact inputs above • Assert each intermediate value matches the expected output to 4 significant decimal places • Assert pool identity: abs(collection_usd - collection_margin_usd - payout_margin_usd - payout_usd_cost) <= 0.01 • Assert offer_rate_coll and cross_rate match expected derived values • Assert validUntil = quote_issued_at + rate_quote_ttl_seconds (300s default) | Passing unit test file: RateEngineTest.crossBorderMpmExample() with all 5 intermediate values, pool identity, and derived rate assertions | • Test fails if payout_usd_cost computation uses floating-point arithmetic (use DECIMAL/BigDecimal only) • Test asserts collection_amount = send_amount + service_charge (service_charge = 0.0 in this case) • Test asserts service_charge is NOT included in collection_usd (pool identity would break if it were) • Test uses rounding to DECIMAL(20,8) for USD intermediary values and DECIMAL(20,4) for final collection_amount • Test is deterministic across 1000 repeated runs (no floating-point non-determinism) | 55 | 1.4-T04 | ARCH | SAD-02
1.4-T24 | program-mgmt | 1.4 | 1. Project Management & Mobilization | Architecture & design sign-off | 1 | Unit test: verify same-currency short-circuit and minimum margin enforcement | WBS 1.4 architecture sign-off. Same-currency short-circuit: when collection_ccy = settle_a_ccy = settle_b_ccy = payout_ccy (e.g. GME_REMIT DOMESTIC on ZeroPay, all KRW), the USD pool is bypassed entirely. collection_amount = target_payout + service_charge. USD pool fields (collection_usd, payout_usd_cost, collection_margin_usd, payout_margin_usd, cost_rate_coll, cost_rate_pay, offer_rate_coll, cross_rate) are all NULL or 0. Minimum margin: m_a + m_b >= 0.02 for cross-border rules (enforced at rule creation); 0 is allowed for same-currency rules. | • Write unit test: same-ccy short-circuit with target_payout=50000 KRW, service_charge=500 KRW; assert collection_amount=50500 KRW, all USD pool fields NULL • Write unit test: cross-border rule creation with m_a=0.005, m_b=0.010; assert rule.save() raises ValidationException with message containing 'minimum combined margin' • Write unit test: cross-border rule creation with m_a=0.010, m_b=0.010; assert rule.save() succeeds • Write unit test: same-currency rule creation with m_a=0.0, m_b=0.0; assert rule.save() succeeds (0% allowed for domestic) • Assert is_same_ccy_shortcircuit is auto-computed: rule with collection=KRW, settleA=KRW, settleB=KRW, payout=KRW sets flag to TRUE automatically | Passing unit test file: RateEngineTest.sameCurrencyShortCircuit() and RuleValidationTest.minimumMarginEnforcement() with all assertions | • Short-circuit test: collection_amount = 50500, collection_usd IS NULL, offer_rate_coll IS NULL, cross_rate IS NULL • Cross-border rule with m_a=0.005 + m_b=0.010 = 1.5% < 2% raises error at rule save, not at rate computation time • Cross-border rule with m_a=0.010 + m_b=0.010 = 2.0% passes validation (boundary condition) • Domestic rule with m_a=0.0, m_b=0.0, is_same_ccy_shortcircuit=TRUE passes validation (0% allowed) • service_charge of 500 KRW is added after the short-circuit check; changing service_charge does not affect the short-circuit condition | 50 | 1.4-T23 | ARCH | SAD-02
1.4-T25 | program-mgmt | 1.4 | 1. Project Management & Mobilization | Architecture & design sign-off | 1 | Unit test: verify rate quote TTL enforcement and quote expiry on CommitTransaction | WBS 1.4 architecture sign-off. Rate quote TTL: validUntil = quote_issued_at + rate_quote_ttl_seconds (default 300s, range 60-1800s). On CommitTransaction, the Orchestrator checks current_time <= validUntil; if expired, returns error EXPIRED_QUOTE and the transaction remains in QUOTED state (not committed). rate_quote.is_used is set to TRUE atomically with CommitTransaction to prevent reuse of the same quote for two transactions. Redis stores the quote with TTL key rate_quote:{quote_ref}; Redis expiry is aligned with validUntil. | • Write unit test: issue a quote with ttl=60s; commit at t+30s; assert transaction reaches DEBITED state • Write unit test: issue a quote with ttl=60s; commit at t+65s; assert EXPIRED_QUOTE error is returned • Write unit test: commit same quote_ref twice concurrently; assert exactly one succeeds and one receives QUOTE_ALREADY_USED error • Write unit test: partner with rate_quote_ttl_seconds=1800; assert validUntil = quote_issued_at + 1800s • Assert ttl values outside 60-1800 range on partner record are rejected at partner creation/update | Passing unit test file: RateQuoteTtlTest with TTL enforcement, expiry, concurrent-use, and boundary tests | • Commit at t+60s exactly (boundary): test confirms this succeeds (valid_until is exclusive - test documents boundary semantics) • Commit at t+61s: EXPIRED_QUOTE error returned; transaction.status remains QUOTED, not FAILED • Concurrent double-commit test uses two threads with a shared barrier; only one thread receives APPROVED outcome • rate_quote_ttl_seconds = 59 on partner raises ValidationException at save time • Redis key rate_quote:{quote_ref} has TTL within 1s of validUntil timestamp at quote issuance time | 55 | 1.4-T23 | ARCH | SAD-02
1.4-T26 | program-mgmt | 1.4 | 1. Project Management & Mobilization | Architecture & design sign-off | 1 | Unit test: verify prefunding atomic deduction and concurrent overdraw prevention | WBS 1.4 architecture sign-off. Prefunding deduction must be atomic using SELECT FOR UPDATE on prefunding_account. Scenario: OVERSEAS partner SendMN has balance USD 1000.00. Two concurrent payments each requesting USD 800.00 collection_usd. Only one should succeed; the other returns INSUFFICIENT_PREFUNDING. The successful deduction creates a prefunding_ledger_entry with entry_type=DEBIT_PAYMENT and balance_after = 200.00. The failed deduction does not create a ledger entry. Scheme is never called unless deduction committed successfully. | • Write integration test with two concurrent transaction threads against a real (test) PostgreSQL instance • Thread 1 and Thread 2 both call deductPrefunding(partner_id, 800.00 USD) simultaneously • Assert exactly one call returns success; exactly one returns INSUFFICIENT_PREFUNDING error • Assert prefunding_account.balance = 200.00 after both calls complete • Assert exactly one prefunding_ledger_entry row exists for the payment deduction (the failed one creates no entry) • Assert the scheme adapter was called exactly once (only for the successful deduction) | Passing integration test: PrefundingAtomicityTest.concurrentOverdrawPrevention() requiring a real PostgreSQL test database | • Test must use actual DB transactions with SELECT FOR UPDATE - cannot mock the lock • After test: prefunding_account.balance = 200.00 (not 1000.00 and not -600.00) • Only 1 prefunding_ledger_entry row with entry_type=DEBIT_PAYMENT exists; balance_after = 200.00 • Scheme adapter mock was invoked exactly once; InvocationCount assertion on mock • Test is repeatable: running it 100 times always produces the same result (no race condition) | 55 | 1.4-T15 | ARCH | SAD-02
1.4-T27 | program-mgmt | 1.4 | 1. Project Management & Mobilization | Architecture & design sign-off | 1 | Unit test: verify pool identity invariant and breach detection | WBS 1.4 architecture sign-off. Pool identity invariant: collection_usd - collection_margin_usd - payout_margin_usd == payout_usd_cost (tolerance 0.01 USD). This must be checked by the Rate Engine after Step 3 of the 5-step calculation. If breached, the rate computation must fail with a hard error (transaction must not commit). Inputs that could cause a breach: floating-point arithmetic errors, incorrect rounding of intermediate values, incorrect margin application. | • Write unit test: normal cross-border computation; assert pool identity holds within 0.0001 USD (tighter than 0.01 tolerance) • Write unit test: deliberately inject a rounding error into collection_usd (add 0.005 USD); assert pool identity check PASSES (within 0.01 tolerance) • Write unit test: inject a rounding error of 0.015 USD into collection_usd; assert pool identity check FAILS with PoolIdentityBreach exception • Write unit test: run 1000 random valid inputs (varying m_a, m_b, target_payout, cost_rates); assert pool identity holds for all • Assert PoolIdentityBreach exception prevents CommitTransaction from proceeding (transaction stays in QUOTED state) | Passing unit test file: PoolIdentityTest with identity check, tolerance boundary tests, and 1000-iteration random test | • Tolerance boundary: deviation of 0.0099 USD passes; deviation of 0.0101 USD fails (strict greater-than check) • Using DECIMAL/BigDecimal arithmetic (not float/double), pool identity should hold to within 0.0000001 USD for all normal inputs • PoolIdentityBreach is logged as a critical error with the specific deviation amount for debugging • All 1000 random inputs with m_a in [0.01, 0.05], m_b in [0.01, 0.05], target_payout in [1000, 100000] KRW pass pool identity • No floating-point type appears in any rate computation code path (verified by static analysis or code review) | 55 | 1.4-T23 | ARCH | SAD-02
1.4-T28 | program-mgmt | 1.4 | 1. Project Management & Mobilization | Architecture & design sign-off | 1 | Unit test: verify transaction state machine transitions and invalid transition rejection | WBS 1.4 architecture sign-off. DAT-03 section 11.3 and SAD-02 section 5.2 define 9 transaction states. Valid transitions: QUOTED->PENDING_DEBIT (OVERSEAS commit), QUOTED->DEBITED (LOCAL commit), QUOTED->FAILED (TTL expired), PENDING_DEBIT->DEBITED (deduction ok), PENDING_DEBIT->FAILED (insufficient funds), DEBITED->SCHEME_SENT, SCHEME_SENT->APPROVED, SCHEME_SENT->FAILED, SCHEME_SENT->UNCERTAIN, UNCERTAIN->APPROVED, UNCERTAIN->FAILED, APPROVED->REVERSED, APPROVED->REFUNDED. Invalid: APPROVED->QUOTED, FAILED->APPROVED, DEBITED->QUOTED, etc. | • Write unit test for each valid state transition; assert resulting status is correct • Write unit test for 5 invalid transitions (e.g. APPROVED->QUOTED, FAILED->DEBITED, UNCERTAIN->QUOTED); assert InvalidStateTransitionException • Write unit test: OVERSEAS partner path: QUOTED->PENDING_DEBIT->DEBITED->SCHEME_SENT->APPROVED (full happy path) • Write unit test: LOCAL partner path: QUOTED->DEBITED->SCHEME_SENT->APPROVED (no PENDING_DEBIT step) • Write unit test: UNCERTAIN->APPROVED via batch reconciliation; confirm rate-lock values are not re-computed (they were locked at original CommitTransaction) | Passing unit test file: TransactionStateMachineTest with valid transitions, invalid transition rejections, and two full happy-path flows (OVERSEAS and LOCAL) | • All valid transitions from SAD-02 state diagram are tested; 100% transition coverage • APPROVED->QUOTED transition throws InvalidStateTransitionException with error code INVALID_STATE_TRANSITION • LOCAL partner transaction never visits PENDING_DEBIT state (assert state history contains no PENDING_DEBIT event) • UNCERTAIN->APPROVED transition does NOT re-compute rate fields; locked values from CommitTransaction are unchanged • Terminal states FAILED, REVERSED, REFUNDED have no outbound transitions; test confirms attempting to transition from them throws exception | 55 | 1.4-T03 | ARCH | SAD-02
1.4-T29 | program-mgmt | 1.4 | 1. Project Management & Mobilization | Architecture & design sign-off | 1 | Review SAD-02/DAT-03 data residency, security, and secrets management | WBS 1.4 architecture sign-off. SAD-02 assumption A-02: all transaction and personal data for Korean QR payments must be stored in Korea (AWS ap-northeast-2 or Korean colocation). SEC-09 requires: TLS 1.2+ (1.3 preferred) for all API communication; API credentials stored hashed (bcrypt); SFTP credentials and external API keys stored in Vault/Secrets Manager (never in env vars, config files, or source code); prefunding ledger access restricted to Transaction Orchestrator service account; rate-lock columns on transaction are immutable after CommitTransaction (no UPDATE permitted on locked columns after committed_at is set); audit_log retention >= 7 years. | • Verify production deployment region is confirmed as Korea (AWS ap-northeast-2 or equivalent) • Verify all SFTP credentials and external API keys are referenced via vault path (api_credential_ref) not stored inline • Confirm no credentials appear in any Dockerfile, docker-compose.yml, CI/CD pipeline definition, or application.properties • Verify rate-lock immutability: confirm application code or DB trigger blocks UPDATE of transaction locked columns after committed_at IS NOT NULL • Verify audit_log has no TTL or auto-purge mechanism; confirm 7-year retention policy is documented and operationally enforced | Security and data residency review checklist: Korea region, secrets management, credential hashing, rate-lock immutability, audit retention - all confirmed or flagged | • No API key, SFTP password, or DB password appears in any source file (automated secret-scanning passes) • transaction UPDATE attempt that modifies collection_usd after committed_at is set is blocked and generates an audit_log entry • partner_credential.api_secret_hash contains bcrypt hash (starts with $2a$ or $2b$); retrieving the partner credential via Admin API never returns the hash • audit_log rows are only INSERT-able; UPDATE and DELETE grant is absent from the application DB role • Production Terraform or infra-as-code specifies Korea region; no other region is permitted for transaction data stores | 40 | 1.4-T18 | ARCH | SAD-02
1.4-T30 | program-mgmt | 1.4 | 1. Project Management & Mobilization | Architecture & design sign-off | 1 | Conduct formal architecture walkthrough with GME and obtain sign-off | WBS 1.4 architecture sign-off. All prior tickets (T01-T29) represent the detailed review tasks. This ticket is the formal sign-off session with GME stakeholders. The deliverable of WBS 1.4 is a signed-off design. Participants: GME Product Owner, GME Tech Lead, GME Compliance (for BOK open items OI-03), development vendor tech lead. Artefacts to present: architecture review checklist (T01-T02), state machine diagram (T03), rate engine review (T04), open items register (T22), technology stack decision record (T09), unit test pass report (T23-T28), security review checklist (T29). | • Schedule formal walkthrough session with all named participants • Present each artefact from T01-T29 in order; highlight any flagged items requiring GME decision • Obtain explicit written decision on all open items (OI-01, OI-02, OI-03) or formally defer with named owner and date • Obtain sign-off signature (email confirmation acceptable) from GME Product Owner on: architecture approach, data model, technology stack, and Phase 1 scope boundary • Record all decisions and action items in PM-14 RAID log | Signed-off design approval document: email or formal sign-off from GME Product Owner confirming SAD-02 architecture and DAT-03 data model are approved for Phase 1 build | • GME Product Owner has reviewed and approved all 12 ADRs (AD-01 through AD-12) with no outstanding deviations • All open items (OI-01, OI-02, OI-03) have a named GME owner and resolution date recorded in PM-14 • Technology stack decision record is signed off - no deviations require post-sign-off re-approval • All unit tests from T23-T28 are passing at time of sign-off presentation • Sign-off document is stored in version-controlled project artefacts folder and referenced in PM-14 as WBS 1.4 completion evidence | 60 | 1.4-T01, 1.4-T02, 1.4-T03, 1.4-T04, 1.4-T05, 1.4-T06, 1.4-T07, 1.4-T08, 1.4-T09, 1.4-T10, 1.4-T11, 1.4-T12, 1.4-T13, 1.4-T14, 1.4-T15, 1.4-T16, 1.4-T17, 1.4-T18, 1.4-T19, 1.4-T20, 1.4-T21, 1.4-T22, 1.4-T23, 1.4-T24, 1.4-T25, 1.4-T26, 1.4-T27, 1.4-T28, 1.4-T29 | ARCH | SAD-02
1.5-T01 | program-mgmt | 1.5 | 1. Project Management & Mobilization | Ongoing project management & reporting | 1 | Define RAID log DB schema and migration for risks, assumptions, issues, dependencies | PM-14 §7 defines four RAID categories. Risks (R-01..R-08) have: id, category ENUM(RISK,ASSUMPTION,ISSUE,DEPENDENCY), raid_id VARCHAR(10) UNIQUE (e.g. R-01), title VARCHAR(200), description TEXT, likelihood VARCHAR(10) CHECK(HIGH,MEDIUM,LOW,NA), impact VARCHAR(10) CHECK(HIGH,MEDIUM,LOW,NA), mitigation TEXT, owner VARCHAR(120), status VARCHAR(20) CHECK(OPEN,CLOSED,MITIGATED,ACCEPTED), phase VARCHAR(10), target_date DATE, created_at TIMESTAMPTZ, updated_at TIMESTAMPTZ, created_by VARCHAR(120), updated_by VARCHAR(120), is_active BOOLEAN DEFAULT TRUE. Table name: raid_log. A dependency entry may additionally carry: from_party VARCHAR(120), to_party VARCHAR(120), required_by DATE. Store all four categories in one table, nullable fields that apply only to specific categories. | • Create db/migrations/V_PM01__raid_log.sql • Write CREATE TABLE raid_log with all columns, CHECK constraints on category/likelihood/impact/status • Add UNIQUE index on raid_id • Add standard audit columns • Apply migration to test DB and verify schema | db/migrations/V_PM01__raid_log.sql | • raid_log table created with all required columns • UNIQUE constraint on raid_id enforced: duplicate R-01 insert fails • CHECK on category rejects value 'TASK' • CHECK on likelihood rejects value 'VERY_HIGH' • CHECK on status rejects value 'PENDING'; accepts 'OPEN' • Nullable dependency-only fields (from_party, required_by) accept NULL for non-dependency rows | 35 |  | PM | PM-14
1.5-T02 | program-mgmt | 1.5 | 1. Project Management & Mobilization | Ongoing project management & reporting | 1 | Define sprint_ceremony DB schema: ceremony log and action item tables | Sprint ceremonies (planning, review, retrospective, standup) must be logged with outcomes and action items. Table sprint_ceremony: id BIGINT PK, ceremony_type VARCHAR(20) CHECK(PLANNING,REVIEW,RETROSPECTIVE,STANDUP,OTHER), sprint_number INTEGER NOT NULL, ceremony_date DATE NOT NULL, facilitator VARCHAR(120), attendees TEXT, summary TEXT, phase VARCHAR(10), created_at TIMESTAMPTZ, updated_at TIMESTAMPTZ, created_by VARCHAR(120). Table ceremony_action_item: id BIGINT PK, ceremony_id BIGINT FK -> sprint_ceremony ON DELETE CASCADE, description TEXT NOT NULL, owner VARCHAR(120), due_date DATE, status VARCHAR(20) CHECK(OPEN,IN_PROGRESS,DONE,CANCELLED), resolution_note TEXT, created_at TIMESTAMPTZ, updated_at TIMESTAMPTZ. Index FK column ceremony_id. | • Create db/migrations/V_PM02__sprint_ceremony.sql • Write CREATE TABLE sprint_ceremony with all columns and CHECK constraints • Write CREATE TABLE ceremony_action_item with FK to sprint_ceremony and CHECK on status • Add index on ceremony_action_item.ceremony_id (FK rule) • Apply and verify both tables | db/migrations/V_PM02__sprint_ceremony.sql | • Both tables created; FK from ceremony_action_item to sprint_ceremony enforced • CHECK on ceremony_type rejects 'KICKOFF'; accepts 'RETROSPECTIVE' • DELETE of sprint_ceremony row cascades and removes child action items • ceremony_action_item.status CHECK rejects 'BLOCKED'; accepts 'DONE' • sprint_number must be NOT NULL: insert without it fails | 30 | 1.5-T01 | PM | PM-14
1.5-T03 | program-mgmt | 1.5 | 1. Project Management & Mobilization | Ongoing project management & reporting | 1 | Define weekly_status_report DB schema with phase and milestone snapshot | PM-14 §3 defines milestones tied to phases (Phase 1 gate Jun 20, Phase 2 gate Jul 31, Phase 3 Oct 10, Phase 4 Dec 10, 2026). Table weekly_status_report: id BIGINT PK, report_date DATE NOT NULL, reporting_week_start DATE NOT NULL, phase VARCHAR(10) NOT NULL, overall_rag VARCHAR(6) CHECK(RED,AMBER,GREEN), scope_rag VARCHAR(6), schedule_rag VARCHAR(6), budget_rag VARCHAR(6), key_achievements TEXT, risks_escalated TEXT, blockers TEXT, next_week_plan TEXT, milestone_snapshot JSONB, submitted_by VARCHAR(120), submitted_at TIMESTAMPTZ, created_at TIMESTAMPTZ, updated_at TIMESTAMPTZ. milestone_snapshot stores array of {milestone, target_date, forecast_date, status} capturing the point-in-time state at submission. | • Create db/migrations/V_PM03__weekly_status_report.sql • Write CREATE TABLE weekly_status_report with all columns and CHECK constraints on RAG fields • Add partial unique index: UNIQUE(reporting_week_start, phase) WHERE is_active = TRUE to prevent duplicate active reports per week+phase • Add check that overall_rag, scope_rag, schedule_rag, budget_rag each only accept RED, AMBER, GREEN • Apply and verify | db/migrations/V_PM03__weekly_status_report.sql | • RAG CHECK rejects 'YELLOW'; accepts 'AMBER' • Unique partial index prevents two active reports for same reporting_week_start + phase • milestone_snapshot column accepts valid JSONB array and rejects malformed JSON • submitted_at nullable (draft reports not yet submitted) • report_date NOT NULL enforced | 30 | 1.5-T01 | PM | PM-14
1.5-T04 | program-mgmt | 1.5 | 1. Project Management & Mobilization | Ongoing project management & reporting | 1 | Implement RaidLogRepository: CRUD + search with category and status filters | The RAID log (table raid_log, see 1.5-T01) is maintained throughout all phases. PM-14 A-14-03 states the dev vendor must add new items and the GME PM reviews/accepts within 2 business days. Repository must support: create entry, update entry (status, mitigation, owner), find by id, find by raid_id (e.g. 'R-01'), search by category + status, list all active entries ordered by category then raid_id. Use Spring Data JPA or equivalent ORM. Entity class: RaidLogEntry. Repository interface: RaidLogRepository. | • Create entity class RaidLogEntry mapping all raid_log columns • Create RaidLogRepository extending JpaRepository with custom query methods: findByRaidId(String), findByCategoryAndStatus(String,String), findAllByIsActiveTrueOrderByCategoryAscRaidIdAsc • Implement RaidLogService with createEntry, updateEntry (status/mitigation/owner/updatedBy), closeEntry(id, resolutionNote) methods • Ensure updateEntry records updated_at = NOW() and updated_by = actor • Write save and retrieve round-trip for one Risk and one Dependency entry | RaidLogEntry entity + RaidLogRepository interface + RaidLogService class | • createEntry persists all fields; raid_id UNIQUE constraint violation throws DataIntegrityViolationException not 500 • findByRaidId('R-01') returns correct entry after save • updateEntry sets updated_at to current timestamp and updated_by to supplied actor • findByCategoryAndStatus('RISK','OPEN') returns only RISK+OPEN rows • closeEntry sets status to CLOSED and is_active to FALSE | 45 | 1.5-T01 | PM | PM-14
1.5-T05 | program-mgmt | 1.5 | 1. Project Management & Mobilization | Ongoing project management & reporting | 1 | Implement WeeklyStatusReportService: create, update, submit lifecycle | Weekly status reports (table weekly_status_report, see 1.5-T03) follow a draft -> submitted lifecycle. submitted_at is null until explicit submit action. A report may only be submitted once (submitted_at not null = immutable). milestone_snapshot must capture current milestone state at submission time from a MilestoneService. RAG values: RED, AMBER, GREEN. Phase values: PH1, PH2, PH3, PH4. Report covers one calendar week identified by reporting_week_start (Monday). Only one active report allowed per week+phase. | • Create WeeklyStatusReport entity and WeeklyStatusReportRepository • Implement WeeklyStatusReportService.createDraft(phase, weekStart, submittedBy) - creates report with all RAG fields null and submitted_at null • Implement updateReport(id, dto) - merges RAG and text fields; throws ReportAlreadySubmittedException if submitted_at is not null • Implement submitReport(id, actorId) - sets submitted_at = NOW(), milestone_snapshot = milestoneService.snapshot(), throws if already submitted • Ensure unique-per-week constraint violation returns clear error, not 500 | WeeklyStatusReport entity + WeeklyStatusReportRepository + WeeklyStatusReportService | • createDraft persists with submitted_at null and all RAG fields null • updateReport on a submitted report throws ReportAlreadySubmittedException • submitReport sets submitted_at and captures milestone_snapshot as non-null JSONB • submitReport called twice on same report throws ReportAlreadySubmittedException second time • createDraft for same week+phase as existing active report throws DuplicateReportException | 50 | 1.5-T03 | PM | PM-14
1.5-T06 | program-mgmt | 1.5 | 1. Project Management & Mobilization | Ongoing project management & reporting | 1 | Implement MilestoneService: milestone registry and snapshot capture | PM-14 §3.1 defines 16 milestones with target dates: contract signed Apr 10, dev env provisioned Apr 17, Hub Core schema+rate engine May 9, Admin portal core May 23, Northbound API sandbox Jun 6, 한결원 test env mid-May, Phase 1 gate Jun 20, ZeroPay merchant sync Jun 13, ZP00xx batch verified Jul 18, Phase 2 gate Jul 31, GME Remit staging Sep 5, UAT Phase 3 Sep 26, Production deployment Oct 10, Phase 3 gate Oct 10, SendMN/T-Bank staging Nov 7, UAT Phase 4 Nov 28, Overseas live Dec 10. Each milestone has: code VARCHAR(20), name, phase, target_date, owner, forecast_date (nullable, updatable), status VARCHAR(20) CHECK(NOT_STARTED,IN_PROGRESS,COMPLETE,DELAYED,AT_RISK). Seed data included. snapshot() returns list of all milestone DTOs. | • Create milestone DB table (or seed data in V_PM04__milestones.sql) with the 16 milestones above • Create Milestone entity and MilestoneRepository • Implement MilestoneService.getAll(), updateForecast(code, forecastDate, actor), updateStatus(code, status, actor) • Implement MilestoneService.snapshot() returning List<MilestoneSnapshotDto> with fields: code, name, targetDate, forecastDate, status • Write seed migration inserting all 16 rows with correct dates and phases | V_PM04__milestones.sql seed migration + MilestoneService + MilestoneSnapshotDto | • All 16 milestone rows present after seed migration runs • Phase 3 gate milestone has target_date = 2026-10-10 and phase = PH3 • updateForecast sets forecast_date and records updated_by and updated_at • updateStatus to DELAYED leaves target_date unchanged • snapshot() returns exactly 16 entries with non-null code and name for all | 45 | 1.5-T03 | PM | PM-14
1.5-T07 | program-mgmt | 1.5 | 1. Project Management & Mobilization | Ongoing project management & reporting | 1 | Implement SprintCeremonyService: log ceremony, add action items, close action items | Sprint ceremonies (table sprint_ceremony, see 1.5-T02) are logged by the PM or Scrum Master. Each ceremony produces zero or more action items. PM-14 A-14-03 expects the PM to notify GME Product Team of new RAID items at the weekly status meeting - this creates the pattern: ceremony -> action items -> link to RAID entries where applicable. SprintCeremonyService must: create ceremony log, add action items to a ceremony, update action item status (OPEN -> IN_PROGRESS -> DONE/CANCELLED), list open action items across all ceremonies, list ceremonies by sprint number. | • Create SprintCeremony and CeremonyActionItem entities and repositories • Implement SprintCeremonyService.logCeremony(dto) persisting ceremony record • Implement addActionItem(ceremonyId, dto) returning saved action item with OPEN status • Implement updateActionItemStatus(itemId, newStatus, resolutionNote, actor) - validate allowed transitions: OPEN->IN_PROGRESS, OPEN->CANCELLED, IN_PROGRESS->DONE, IN_PROGRESS->CANCELLED • Implement listOpenActionItems() and listByCeremony(ceremonyId) | SprintCeremony entity + CeremonyActionItem entity + SprintCeremonyService | • logCeremony persists with ceremony_type and sprint_number; missing sprint_number fails with constraint violation • addActionItem creates item with status OPEN and correct ceremony_id FK • updateActionItemStatus DONE->OPEN transition rejected with InvalidStatusTransitionException • listOpenActionItems returns only items with status OPEN or IN_PROGRESS • deleteAllByCeremonyId not allowed (no hard-delete); closing ceremony does not cascade delete action items (CASCADE DELETE only on entity removal, which is not exposed) | 45 | 1.5-T02 | PM | PM-14
1.5-T08 | program-mgmt | 1.5 | 1. Project Management & Mobilization | Ongoing project management & reporting | 1 | Implement RAID REST API: POST /pm/raid, PATCH /pm/raid/{id}, GET /pm/raid with filters | Internal Admin API (JWT-authenticated, role ROLE_PM or ROLE_ADMIN) for RAID log management per PM-14 §7. Endpoints: POST /pm/raid (create entry, body: RaidLogEntryDto with category, raid_id, title, description, likelihood, impact, mitigation, owner, phase, target_date); PATCH /pm/raid/{id} (update status, mitigation, owner, forecast; immutable: category, raid_id, created_by); GET /pm/raid?category=RISK&status=OPEN (filter + list); GET /pm/raid/{id} (single entry). All responses use standard envelope: {data, errors, meta}. Return 409 if raid_id already exists on POST. | • Create RaidLogController with the four endpoint handlers • Map RaidLogEntryDto <-> RaidLogEntry entity; validate category, likelihood, impact, status values via @Valid annotations • Wire to RaidLogService (1.5-T04) methods • Return 201 on POST with Location header pointing to /pm/raid/{id} • Return 409 with error code RAID_ID_DUPLICATE when raid_id already exists • Secure all endpoints with @PreAuthorize('hasAnyRole(ROLE_PM, ROLE_ADMIN)') | RaidLogController with 4 endpoints + RaidLogEntryDto + RaidLogEntryResponse | • POST /pm/raid with category=RISK, raid_id=R-99, likelihood=HIGH returns 201 and Location header • GET /pm/raid?category=RISK&status=OPEN returns only RISK+OPEN entries • PATCH /pm/raid/{id} with body {status:CLOSED} updates status and sets updated_at • POST /pm/raid with duplicate raid_id returns 409 with RAID_ID_DUPLICATE error code • GET /pm/raid/{id} for non-existent id returns 404 • Unauthenticated request returns 401 | 50 | 1.5-T04 | PM | PM-14
1.5-T09 | program-mgmt | 1.5 | 1. Project Management & Mobilization | Ongoing project management & reporting | 1 | Implement Status Report REST API: POST /pm/status-report, PATCH, POST .../submit, GET | Internal API (role ROLE_PM or ROLE_ADMIN) for weekly status reports per PM-14. Endpoints: POST /pm/status-report (create draft; body: phase, reporting_week_start, overall_rag, scope_rag, schedule_rag, budget_rag, key_achievements, risks_escalated, blockers, next_week_plan); PATCH /pm/status-report/{id} (update draft fields; reject if submitted); POST /pm/status-report/{id}/submit (finalise, sets submitted_at and captures milestone_snapshot); GET /pm/status-report?phase=PH1 (list); GET /pm/status-report/{id}. Return 422 with REPORT_ALREADY_SUBMITTED when PATCH or submit attempted on already-submitted report. reporting_week_start must be a Monday (ISO day-of-week = 1); reject with 400 if not. | • Create WeeklyStatusReportController with 5 endpoint handlers • Validate reporting_week_start is Monday; return 400 BAD_REQUEST with INVALID_WEEK_START if not • Wire to WeeklyStatusReportService (1.5-T05) • Map Dto <-> Entity; validate RAG enum values; return 422 with descriptive error if invalid • On submit, call WeeklyStatusReportService.submitReport which captures milestone snapshot • Secure with @PreAuthorize('hasAnyRole(ROLE_PM, ROLE_ADMIN)') | WeeklyStatusReportController with 5 endpoints + WeeklyStatusReportDto + WeeklyStatusReportResponse | • POST /pm/status-report with reporting_week_start=2026-05-04 (Monday) returns 201 • POST /pm/status-report with reporting_week_start=2026-05-05 (Tuesday) returns 400 with INVALID_WEEK_START • PATCH on submitted report returns 422 with REPORT_ALREADY_SUBMITTED • POST .../submit sets submitted_at; second submit call returns 422 • GET /pm/status-report?phase=PH1 returns only PH1 reports ordered by reporting_week_start DESC | 50 | 1.5-T05, 1.5-T06 | PM | PM-14
1.5-T10 | program-mgmt | 1.5 | 1. Project Management & Mobilization | Ongoing project management & reporting | 1 | Implement Sprint Ceremony REST API: POST /pm/ceremony, POST /pm/ceremony/{id}/action-items, PATCH action-item status | Internal API (role ROLE_PM or ROLE_ADMIN) for sprint ceremonies per PM-14. Endpoints: POST /pm/ceremony (log ceremony; body: ceremony_type, sprint_number, ceremony_date, facilitator, attendees, summary, phase); GET /pm/ceremony?sprint_number=3 (list by sprint); GET /pm/ceremony/{id} (single); POST /pm/ceremony/{id}/action-items (add action item; body: description, owner, due_date); PATCH /pm/ceremony/action-items/{itemId} (update status, resolution_note); GET /pm/ceremony/action-items/open (all open+in-progress items). ceremony_type must be one of PLANNING, REVIEW, RETROSPECTIVE, STANDUP, OTHER. | • Create SprintCeremonyController with 6 endpoint handlers • Validate ceremony_type enum; return 400 if invalid value supplied • Wire to SprintCeremonyService (1.5-T07) for all operations • PATCH action-item enforces status transition rules; return 422 with INVALID_STATUS_TRANSITION on bad transition • Return 404 when ceremony or action item not found • Secure all endpoints with @PreAuthorize('hasAnyRole(ROLE_PM, ROLE_ADMIN)') | SprintCeremonyController with 6 endpoints + SprintCeremonyDto + CeremonyActionItemDto | • POST /pm/ceremony with type=RETROSPECTIVE and sprint_number=5 returns 201 • POST /pm/ceremony with type=KICKOFF returns 400 • POST .../action-items on ceremony creates item with status=OPEN • PATCH action-item with transition DONE->OPEN returns 422 with INVALID_STATUS_TRANSITION • GET /pm/ceremony/action-items/open returns only OPEN and IN_PROGRESS items • GET /pm/ceremony?sprint_number=3 returns only sprint 3 ceremonies | 45 | 1.5-T07 | PM | PM-14
1.5-T11 | program-mgmt | 1.5 | 1. Project Management & Mobilization | Ongoing project management & reporting | 1 | Implement Milestone REST API: GET /pm/milestones, PATCH forecast and status, GET snapshot | Milestones (PM-14 §3.1, seeded in 1.5-T06) are maintained by the PM throughout the project. Endpoints: GET /pm/milestones (all milestones); GET /pm/milestones?phase=PH1 (filtered by phase); GET /pm/milestones/{code} (single by code e.g. PHASE1_GATE); PATCH /pm/milestones/{code} (update forecast_date and/or status only; code and target_date are immutable); GET /pm/milestones/snapshot (same as GET all but formatted as snapshot dto: code, name, phase, target_date, forecast_date, status, variance_days). variance_days = forecast_date - target_date in days (negative means ahead, positive means behind, null if forecast_date not set). | • Create MilestoneController with 5 endpoint handlers • Validate status enum values (NOT_STARTED, IN_PROGRESS, COMPLETE, DELAYED, AT_RISK) in PATCH body • Compute variance_days in response DTO as (forecast_date - target_date).toDays() when forecast_date is not null, otherwise null • Wire to MilestoneService (1.5-T06) • Return 404 for unknown milestone code • Secure with @PreAuthorize('hasAnyRole(ROLE_PM, ROLE_ADMIN)') | MilestoneController with 5 endpoints + MilestoneDto + MilestoneSnapshotResponseDto | • GET /pm/milestones returns exactly 16 entries after seed • GET /pm/milestones?phase=PH3 returns only Phase 3 milestones • PATCH /pm/milestones/PHASE3_GATE with forecast_date=2026-11-01 sets forecast and variance_days=22 • PATCH /pm/milestones/PHASE3_GATE with code change returns 400 BAD_REQUEST (immutable field) • GET /pm/milestones/snapshot includes variance_days field; entry with no forecast_date has variance_days=null • PATCH with status=INVALID returns 400 | 40 | 1.5-T06 | PM | PM-14
1.5-T12 | program-mgmt | 1.5 | 1. Project Management & Mobilization | Ongoing project management & reporting | 1 | Implement RAID log auto-seed: insert all PM-14 initial RAID entries at startup | PM-14 §7 defines 8 Risks (R-01..R-08), 8 Assumptions (A-01..A-08), 4 Issues (I-01..I-04), and 8 Dependencies (D-01..D-08). These must be seeded into the raid_log table at startup via a Flyway migration (V_PM05__raid_seed.sql) so the system ships with the project's baseline RAID log populated. All seeded items have status=OPEN, created_by='SYSTEM'. R-01: 한결원 test env delayed, HIGH/HIGH, owner=GME BD. R-02: BOK reporting late, MEDIUM/HIGH, owner=GME Compliance. R-03: Rate engine error, MEDIUM/HIGH. R-04: Prefunding atomicity bug, MEDIUM/HIGH. R-05: Tax-invoice API unavailable, MEDIUM/MEDIUM. R-06: ZeroPay file format changes, LOW/MEDIUM. R-07: Overseas partner integration delayed, MEDIUM/MEDIUM. R-08: FX rates stale, MEDIUM/MEDIUM. | • Create db/migrations/V_PM05__raid_seed.sql • Insert 8 Risk rows (R-01..R-08) with likelihood, impact, mitigation, owner per PM-14 §7.1 • Insert 8 Assumption rows (A-01..A-08) per PM-14 §7.2; likelihood=NA, impact per table • Insert 4 Issue rows (I-01..I-04) per PM-14 §7.3; likelihood=NA • Insert 8 Dependency rows (D-01..D-08) per PM-14 §7.4 with from_party, to_party, required_by • Apply migration; verify row counts | db/migrations/V_PM05__raid_seed.sql with 28 rows | • SELECT COUNT(*) FROM raid_log WHERE category='RISK' = 8 • SELECT COUNT(*) FROM raid_log WHERE category='ASSUMPTION' = 8 • SELECT COUNT(*) FROM raid_log WHERE category='ISSUE' = 4 • SELECT COUNT(*) FROM raid_log WHERE category='DEPENDENCY' = 8 • R-01 row has likelihood=HIGH, impact=HIGH, owner contains 'GME BD' • D-01 row has from_party='한결원/KFTC', required_by='2026-05-15' | 40 | 1.5-T01 | PM | PM-14
1.5-T13 | program-mgmt | 1.5 | 1. Project Management & Mobilization | Ongoing project management & reporting | 1 | Implement RAID open-item review workflow: flag for PM review, accept/reject by GME PM | PM-14 A-14-03: the dev vendor adds RAID items and GME PM reviews/accepts within 2 business days. Workflow: new RAID item created by dev vendor starts with status=OPEN and review_status=PENDING_REVIEW. GME PM (ROLE_PM) can accept (sets review_status=ACCEPTED, reviewed_at, reviewed_by) or reject with a rejection reason (sets review_status=REJECTED). Rejected items can be revised by dev vendor and re-submitted (status back to PENDING_REVIEW). Add columns to raid_log: review_status VARCHAR(20) CHECK(PENDING_REVIEW, ACCEPTED, REJECTED), reviewed_by VARCHAR(120), reviewed_at TIMESTAMPTZ, rejection_reason TEXT. Seeded items from V_PM05 start with review_status=ACCEPTED (pre-approved baseline). | • Create migration V_PM06__raid_review_workflow.sql adding review_status, reviewed_by, reviewed_at, rejection_reason columns to raid_log • Update V_PM05 seed (or add to V_PM06) to set review_status=ACCEPTED for all seeded rows • Add RaidLogService.acceptEntry(id, reviewerActorId) and rejectEntry(id, reviewerActorId, rejectionReason) methods • Add resubmit(id, actorId) method - sets review_status=PENDING_REVIEW; only allowed if current status=REJECTED • Add PATCH /pm/raid/{id}/accept and PATCH /pm/raid/{id}/reject endpoints (ROLE_PM only) • Add PATCH /pm/raid/{id}/resubmit endpoint (ROLE_PM or ROLE_VENDOR) | V_PM06__raid_review_workflow.sql + acceptEntry/rejectEntry/resubmit methods + 3 API endpoints | • New RAID entry created via POST starts with review_status=PENDING_REVIEW • PATCH /pm/raid/{id}/accept sets reviewed_at, reviewed_by, review_status=ACCEPTED • PATCH /pm/raid/{id}/reject requires rejection_reason in body; sets review_status=REJECTED • resubmit on an ACCEPTED entry returns 422 with INVALID_REVIEW_TRANSITION • Seeded R-01..R-08 rows have review_status=ACCEPTED after migration | 50 | 1.5-T04, 1.5-T08 | PM | PM-14
1.5-T14 | program-mgmt | 1.5 | 1. Project Management & Mobilization | Ongoing project management & reporting | 1 | Implement phase gate tracking: record gate criteria, evidence, and sign-off per PM-14 §5 | PM-14 §5.1-5.4 defines phase acceptance criteria. Each phase has 6-8 gate criteria that must be verified before GME authorises the next phase. Table phase_gate_criterion: id BIGINT PK, phase VARCHAR(10) NOT NULL, criterion_code VARCHAR(30) UNIQUE NOT NULL, description TEXT NOT NULL, evidence_required TEXT, status VARCHAR(20) CHECK(NOT_VERIFIED, VERIFIED, WAIVED), evidence_notes TEXT, verified_by VARCHAR(120), verified_at TIMESTAMPTZ, created_at TIMESTAMPTZ, updated_at TIMESTAMPTZ. Table phase_gate_signoff: id BIGINT PK, phase VARCHAR(10) NOT NULL UNIQUE, signed_off_by VARCHAR(120), signed_off_at TIMESTAMPTZ, notes TEXT, created_at TIMESTAMPTZ. Sign-off can only occur when all criteria for that phase are VERIFIED or WAIVED. | • Create db/migrations/V_PM07__phase_gate.sql with both tables • Seed Phase 1-4 criteria from PM-14 §5 (at least 6 rows per phase) with status=NOT_VERIFIED • Implement PhaseGateService.verifyCriterion(criterionCode, evidenceNotes, actorId) setting status=VERIFIED • Implement PhaseGateService.signOffPhase(phase, actorId, notes) - validates all criteria VERIFIED or WAIVED, then inserts phase_gate_signoff row • Add GET /pm/phase-gate?phase=PH1 and POST /pm/phase-gate/{criterionCode}/verify and POST /pm/phase-gate/{phase}/signoff endpoints (ROLE_PM) | V_PM07__phase_gate.sql + PhaseGateService + 3 API endpoints | • After seed, all criteria have status=NOT_VERIFIED • verifyCriterion sets status=VERIFIED, verified_by, verified_at • signOffPhase with one criterion still NOT_VERIFIED returns 422 with PHASE_GATE_CRITERIA_INCOMPLETE • signOffPhase when all criteria VERIFIED or WAIVED inserts phase_gate_signoff row • GET /pm/phase-gate?phase=PH1 returns all Phase 1 criteria with current status • UNIQUE on phase in phase_gate_signoff: signing off same phase twice returns 409 | 55 | 1.5-T01 | PM | PM-14
1.5-T15 | program-mgmt | 1.5 | 1. Project Management & Mobilization | Ongoing project management & reporting | 1 | Implement dependency status tracking: link RAID dependencies to milestone dates and alert on overdue | PM-14 §7.4 defines 8 external dependencies (D-01..D-08) each with a required_by date. The system must flag when required_by is passed and the dependency is still OPEN: D-01 (한결원 test env) required by 2026-05-15, D-02 (ZP00xx specs) required by 2026-05-15, D-03 (BOK FX format) required by TBD, D-04 (Tax invoice API) before Phase 1 dev start, D-05 (GME Remit readiness) by 2026-08-01, D-06 (SendMN/T-Bank readiness) by 2026-10-01, D-07 (prefunding confirmed) before Phase 4 go-live, D-08 (GME Ops trained) by 2026-09-26. Service method getOverdueDependencies(asOfDate) returns all raid_log rows where category=DEPENDENCY, status=OPEN, required_by < asOfDate. Expose GET /pm/raid/dependencies/overdue?asOf=2026-05-16 endpoint. | • Add getOverdueDependencies(LocalDate asOfDate) method to RaidLogService filtering category=DEPENDENCY, status=OPEN, required_by < asOfDate • Add GET /pm/raid/dependencies/overdue endpoint accepting optional asOf query param (defaults to today) • Ensure D-01..D-08 seed rows have required_by populated where known (D-03, D-04 may be null) • Write logic: if required_by is null, do not include in overdue results • Return results sorted by required_by ASC (most overdue first) | RaidLogService.getOverdueDependencies + GET /pm/raid/dependencies/overdue endpoint | • GET /pm/raid/dependencies/overdue?asOf=2026-05-16 includes D-01 (required_by=2026-05-15, status=OPEN) • D-03 (required_by=null) never appears in overdue results • Dependency with status=CLOSED does not appear in overdue results even if required_by is past • GET /pm/raid/dependencies/overdue with no asOf param uses today's date • Results ordered by required_by ASC: D-01 and D-02 (both 2026-05-15) appear before D-05 (2026-08-01) | 35 | 1.5-T04, 1.5-T08, 1.5-T12 | PM | PM-14
1.5-T16 | program-mgmt | 1.5 | 1. Project Management & Mobilization | Ongoing project management & reporting | 1 | Implement status report dashboard summary endpoint GET /pm/dashboard/summary | The PM needs a single endpoint that aggregates: current phase (derive from milestone dates and today), open RAID items by category (counts), overdue dependencies count, open action items count, latest submitted status report RAG (overall_rag, scope_rag, schedule_rag, budget_rag), and next milestone (nearest NOT_STARTED or IN_PROGRESS milestone by target_date). Response DTO: DashboardSummaryDto { current_phase, raid_counts: {risks_open, assumptions_open, issues_open, dependencies_open}, overdue_dependencies_count, open_action_items_count, latest_report_rag: {overall, scope, schedule, budget, submitted_at}, next_milestone: {code, name, target_date, status} }. latest_report_rag is null if no submitted report exists. | • Create DashboardSummaryDto with all nested fields • Implement DashboardService.getSummary() aggregating data from RaidLogService, SprintCeremonyService, WeeklyStatusReportService, MilestoneService • Compute current_phase by finding the latest phase whose first milestone has status IN_PROGRESS or COMPLETE • Compute open action items count from CeremonyActionItemRepository where status IN (OPEN, IN_PROGRESS) • Add GET /pm/dashboard/summary endpoint (ROLE_PM or ROLE_ADMIN) | DashboardService + DashboardSummaryDto + GET /pm/dashboard/summary endpoint | • Response includes raid_counts with separate counts for each category • overdue_dependencies_count matches count from /pm/raid/dependencies/overdue • latest_report_rag is null when no submitted reports exist; populates correctly after submit • next_milestone returns the milestone with earliest target_date that is NOT COMPLETE • Endpoint returns 200 even when no ceremonies or action items exist yet (counts = 0) | 50 | 1.5-T04, 1.5-T07, 1.5-T09, 1.5-T11, 1.5-T15 | PM | PM-14
1.5-T17 | program-mgmt | 1.5 | 1. Project Management & Mobilization | Ongoing project management & reporting | 1 | Unit tests: RaidLogService create, update, review workflow with status and transition validation | RaidLogService (1.5-T04, 1.5-T13) handles RAID entry lifecycle. Test the business rules: (1) new entry starts PENDING_REVIEW; (2) acceptEntry sets reviewed_at and review_status=ACCEPTED; (3) rejectEntry requires non-blank rejection_reason; (4) resubmit only from REJECTED state; (5) updateEntry throws ReportAlreadySubmittedException for closed entries; (6) findByCategoryAndStatus returns correct subset. Use JUnit 5 + Mockito; mock RaidLogRepository. Test class: RaidLogServiceTest. | • Create RaidLogServiceTest in src/test/java under the pm package • Test createEntry: verify saved entity has review_status=PENDING_REVIEW and status=OPEN • Test acceptEntry: mock repository findById returns entry with PENDING_REVIEW; verify reviewed_at set, review_status=ACCEPTED • Test rejectEntry with blank rejection_reason: expect IllegalArgumentException • Test rejectEntry with valid reason: verify review_status=REJECTED, rejection_reason persisted • Test resubmit from ACCEPTED state: expect InvalidReviewTransitionException • Test findByCategoryAndStatus: mock returns 2 RISK+OPEN and 1 ISSUE+OPEN; assert filter returns 2 for RISK+OPEN | RaidLogServiceTest with 7+ test methods, all passing | • createEntry test: saved entity review_status = PENDING_REVIEW • acceptEntry test: reviewed_at is not null in saved entity • rejectEntry with blank reason: IllegalArgumentException thrown • rejectEntry with valid reason: review_status = REJECTED • resubmit from ACCEPTED state: InvalidReviewTransitionException thrown • findByCategoryAndStatus test: only RISK+OPEN rows returned (count = 2) • All 7 tests pass with zero failures | 45 | 1.5-T04, 1.5-T13 | PM | PM-14
1.5-T18 | program-mgmt | 1.5 | 1. Project Management & Mobilization | Ongoing project management & reporting | 1 | Unit tests: WeeklyStatusReportService draft/submit lifecycle and duplicate prevention | WeeklyStatusReportService (1.5-T05) rules: (1) createDraft with non-Monday week_start throws exception; (2) duplicate report for same week+phase throws DuplicateReportException; (3) updateReport on submitted report throws ReportAlreadySubmittedException; (4) submitReport sets submitted_at; (5) submitReport called twice throws exception; (6) RAG value validation (invalid value rejected). Test class: WeeklyStatusReportServiceTest. Use JUnit 5 + Mockito. | • Create WeeklyStatusReportServiceTest • Test createDraft with 2026-05-04 (Monday): expect success, submitted_at null • Test createDraft with 2026-05-05 (Tuesday): expect InvalidWeekStartException • Test createDraft duplicate same week+phase when active report exists: expect DuplicateReportException • Test updateReport on submitted report (submitted_at not null): expect ReportAlreadySubmittedException • Test submitReport: verify submitted_at is set, milestone_snapshot is non-null • Test submitReport twice: second call throws ReportAlreadySubmittedException | WeeklyStatusReportServiceTest with 7+ test methods, all passing | • Monday input creates draft without exception • Tuesday input throws InvalidWeekStartException • Duplicate week+phase throws DuplicateReportException • Update on submitted report throws ReportAlreadySubmittedException • First submitReport sets submitted_at to non-null value • Second submitReport call throws ReportAlreadySubmittedException • All 7 tests pass | 40 | 1.5-T05 | PM | PM-14
1.5-T19 | program-mgmt | 1.5 | 1. Project Management & Mobilization | Ongoing project management & reporting | 1 | Unit tests: MilestoneService snapshot, variance_days computation, and status transitions | MilestoneService (1.5-T06) rules: (1) snapshot() returns exactly 16 entries; (2) variance_days = (forecast_date - target_date) in days (positive = delayed, negative = ahead, null if no forecast); (3) updateForecast records updated_by; (4) updateStatus to invalid value rejected; (5) target_date is immutable. Test class: MilestoneServiceTest. Use JUnit 5 + Mockito. Numeric example: Phase3Gate target=2026-10-10, forecast=2026-11-01 -> variance_days=22. Phase3Gate target=2026-10-10, forecast=2026-09-20 -> variance_days=-20. | • Create MilestoneServiceTest • Mock MilestoneRepository.findAll() returning 16 dummy milestones • Test snapshot(): assert size=16 and all entries have non-null code • Test variance_days positive: target=2026-10-10, forecast=2026-11-01 -> variance_days=22 • Test variance_days negative: target=2026-10-10, forecast=2026-09-20 -> variance_days=-20 • Test variance_days null: target=2026-10-10, forecast=null -> variance_days=null • Test updateStatus with invalid string 'BLOCKED': expect IllegalArgumentException | MilestoneServiceTest with 7+ test methods, all passing | • snapshot() size = 16 when repository returns 16 items • variance_days = 22 for target 2026-10-10 and forecast 2026-11-01 • variance_days = -20 for target 2026-10-10 and forecast 2026-09-20 • variance_days = null when forecast_date is null • updateStatus('BLOCKED') throws IllegalArgumentException • updateForecast saves updated_by field equal to actor param • All 7 tests pass | 35 | 1.5-T06 | PM | PM-14
1.5-T20 | program-mgmt | 1.5 | 1. Project Management & Mobilization | Ongoing project management & reporting | 1 | Unit tests: PhaseGateService sign-off rules and criterion verification | PhaseGateService (1.5-T14) rules: (1) verifyCriterion sets status=VERIFIED, verified_by, verified_at; (2) signOffPhase when all criteria VERIFIED or WAIVED succeeds; (3) signOffPhase when any criterion is NOT_VERIFIED throws PhaseGateCriteriaIncompleteException; (4) signOff twice on same phase throws DuplicateSignOffException; (5) waiveCriterion (status=WAIVED) counts toward completion. Test class: PhaseGateServiceTest. Use JUnit 5 + Mockito. | • Create PhaseGateServiceTest • Test verifyCriterion: entity updated with status=VERIFIED, non-null verified_at, correct verified_by • Test signOffPhase happy path: all 4 mock criteria have status VERIFIED -> signoff persisted • Test signOffPhase with one NOT_VERIFIED criterion: throws PhaseGateCriteriaIncompleteException • Test signOffPhase with one WAIVED and rest VERIFIED: succeeds (waived counts) • Test duplicate signOff (phase_gate_signoff row already exists): throws DuplicateSignOffException | PhaseGateServiceTest with 6+ test methods, all passing | • verifyCriterion sets verified_at to non-null • signOffPhase with all VERIFIED returns success • signOffPhase with one NOT_VERIFIED throws PhaseGateCriteriaIncompleteException • signOffPhase with WAIVED criterion alongside VERIFIED others succeeds • Duplicate signOff throws DuplicateSignOffException • All 6 tests pass | 35 | 1.5-T14 | PM | PM-14
1.5-T21 | program-mgmt | 1.5 | 1. Project Management & Mobilization | Ongoing project management & reporting | 1 | Unit tests: DashboardService aggregation and zero-data boundary cases | DashboardService (1.5-T16) aggregates from multiple services. Test: (1) all counts are 0 and latest_report_rag is null when no data exists; (2) raid_counts.risks_open increments after a RISK+OPEN entry; (3) overdue_dependencies_count uses asOfDate=today; (4) next_milestone returns correct nearest non-COMPLETE milestone; (5) latest_report_rag populated from most-recently-submitted report. Use JUnit 5 + Mockito mocking all dependent services. | • Create DashboardServiceTest • Mock all four dependent services to return empty/null; assert all counts=0 and latest_report_rag=null • Mock RaidLogService to return 3 RISK+OPEN, 1 ISSUE+OPEN; assert raid_counts.risks_open=3, issues_open=1 • Mock MilestoneService.getAll() with mix of COMPLETE and IN_PROGRESS milestones; assert next_milestone returns earliest non-COMPLETE by target_date • Mock WeeklyStatusReportService to return one submitted report with overall_rag=AMBER; assert latest_report_rag.overall=AMBER • Mock overdue dependencies = 2; assert overdue_dependencies_count=2 | DashboardServiceTest with 5+ test methods, all passing | • Empty-data case: all numeric counts=0, latest_report_rag=null • raid_counts.risks_open=3 when 3 RISK+OPEN entries mocked • next_milestone = earliest non-COMPLETE milestone by target_date • latest_report_rag.overall=AMBER when most-recent submitted report has that value • overdue_dependencies_count=2 when mocked overdue list has 2 entries • All 5 tests pass | 35 | 1.5-T16 | PM | PM-14
1.5-T22 | program-mgmt | 1.5 | 1. Project Management & Mobilization | Ongoing project management & reporting | 1 | Integration test: RAID log API end-to-end with real DB (TestContainers) | Verify the full RAID log API stack against a real PostgreSQL instance using TestContainers. Test flow: (1) seed DB runs V_PM05 inserting 28 rows; (2) POST /pm/raid creates R-99 with status OPEN, review_status PENDING_REVIEW; (3) GET /pm/raid?category=RISK&status=OPEN returns R-99 plus seeded risks; (4) PATCH /pm/raid/{id}/accept sets review_status=ACCEPTED; (5) PATCH /pm/raid/{id}/reject on already-accepted entry returns 422; (6) GET /pm/raid/dependencies/overdue?asOf=2026-05-16 returns D-01 and D-02. Use Spring Boot Test slice + TestContainers PostgreSQL 15. | • Add TestContainers dependency to build.gradle/pom.xml if not already present • Create RaidLogApiIntegrationTest with @SpringBootTest and @Testcontainers • Configure PostgreSQL TestContainer; run Flyway migrations on startup • Implement test method for each of the 6 flow steps above in @Test @Order sequence • Assert HTTP status codes, body fields, and DB state where applicable | RaidLogApiIntegrationTest with 6 test methods, all passing against real DB | • V_PM05 seed: SELECT COUNT(*) FROM raid_log = 28 after migration • POST /pm/raid R-99 returns 201 with Location header • GET /pm/raid?category=RISK&status=OPEN returns at least 9 rows (8 seeded + R-99) • PATCH accept returns 200 and review_status=ACCEPTED in response • Second reject on accepted entry returns 422 • GET dependencies/overdue?asOf=2026-05-16 includes D-01 and D-02 | 55 | 1.5-T08, 1.5-T12, 1.5-T13, 1.5-T15 | PM | PM-14
1.5-T23 | program-mgmt | 1.5 | 1. Project Management & Mobilization | Ongoing project management & reporting | 1 | Integration test: Status report and milestone API end-to-end with real DB | Verify status report and milestone API stack. Test flow: (1) seed runs V_PM04 inserting 16 milestones; (2) POST /pm/status-report creates draft for week 2026-06-01 (Monday), phase PH1; (3) PATCH updates overall_rag=GREEN; (4) POST .../submit sets submitted_at; (5) PATCH on submitted report returns 422; (6) PATCH /pm/milestones/PHASE1_GATE with forecast_date=2026-06-25 sets variance_days=5; (7) GET /pm/dashboard/summary returns open raid counts and next_milestone. Use Spring Boot Test + TestContainers PostgreSQL 15. | • Create StatusReportAndMilestoneIntegrationTest with @SpringBootTest and @Testcontainers • Run all Flyway migrations including V_PM04 and V_PM05 • Execute 7-step flow in ordered test methods • Assert variance_days = (2026-06-25 minus 2026-06-20) = 5 days in PATCH milestone response • Assert GET /pm/dashboard/summary.raid_counts.risks_open = 8 (from seeded risks) • Assert GET /pm/dashboard/summary.next_milestone.code is non-null | StatusReportAndMilestoneIntegrationTest with 7 test methods, all passing against real DB | • 16 milestones seeded; GET /pm/milestones returns 16 rows • Status report draft created with submitted_at=null • PATCH forecast_date=2026-06-25 for PHASE1_GATE (target=2026-06-20) returns variance_days=5 • POST .../submit sets submitted_at to non-null timestamp • PATCH on submitted report returns 422 with REPORT_ALREADY_SUBMITTED • GET /pm/dashboard/summary.raid_counts.risks_open = 8 • All 7 tests pass | 55 | 1.5-T09, 1.5-T11, 1.5-T16, 1.5-T22 | PM | PM-14
1.5-T24 | program-mgmt | 1.5 | 1. Project Management & Mobilization | Ongoing project management & reporting | 1 | Admin portal UI: RAID log screen - list, create, and review workflow | GME Ops/PM users need a RAID log management screen in the Admin portal (PRD-07). Screen requirements: tabbed view by category (Risks, Assumptions, Issues, Dependencies); each tab shows a filterable table with columns: raid_id, title, likelihood, impact, owner, status, review_status, target_date; Create New button opens a side-panel form; row click opens detail with Accept / Reject buttons (for ROLE_PM users); Rejected items show rejection_reason and Resubmit button. Calls /pm/raid API (1.5-T08, 1.5-T13). Use the existing Admin portal frontend framework (React or equivalent per PRD-07/UX-11). | • Create RaidLogPage component with four category tabs (Risks, Assumptions, Issues, Dependencies) • Implement RaidLogTable component rendering raid_id, title, likelihood, impact, owner, status, review_status, target_date columns with status badge colour (OPEN=yellow, CLOSED=grey, MITIGATED=green) • Implement CreateRaidEntryForm side-panel with fields matching POST /pm/raid DTO; submit calls POST /pm/raid • Implement RaidEntryDetail drawer with Accept / Reject buttons that call PATCH .../accept or .../reject; show rejection_reason field on reject click • Implement Resubmit button visible only when review_status=REJECTED; calls PATCH .../resubmit • Add filter controls: status dropdown and free-text search on title | RaidLogPage, RaidLogTable, CreateRaidEntryForm, RaidEntryDetail React components | • Risks tab loads and shows only rows with category=RISK from GET /pm/raid?category=RISK • Create form submits POST /pm/raid and row appears in table after success • Accept button calls PATCH /pm/raid/{id}/accept; review_status badge updates to ACCEPTED without page reload • Reject without rejection_reason shows inline validation error before submitting • Resubmit button only visible when review_status=REJECTED • Filter by status=OPEN hides CLOSED rows | 55 | 1.5-T08, 1.5-T13 | PM | PM-14
1.5-T25 | program-mgmt | 1.5 | 1. Project Management & Mobilization | Ongoing project management & reporting | 1 | Admin portal UI: Weekly status report screen - create, edit, submit, and history list | Admin portal status report screen per PRD-07. Requirements: list view showing submitted and draft reports sorted by reporting_week_start DESC with RAG traffic-light badges; New Report button auto-fills reporting_week_start to nearest past Monday; form fields: phase dropdown (PH1-PH4), RAG dropdowns (RED/AMBER/GREEN) for overall, scope, schedule, budget, and text areas for key_achievements, risks_escalated, blockers, next_week_plan; Save Draft and Submit buttons; submitted reports are read-only (no edit form rendered); milestone snapshot embedded in submitted report detail view. Calls /pm/status-report API (1.5-T09). | • Create StatusReportListPage with table of reports, RAG badge column, and New Report button • Implement StatusReportForm component with all fields; on load compute nearest past Monday for reporting_week_start • Submit calls POST /pm/status-report; Save Draft uses same POST then PATCH on updates • Submit Report button calls POST .../submit; disable all form fields after submit • Implement StatusReportDetail component for submitted reports showing milestone_snapshot as read-only table • Add toast notification on successful submit: Report submitted for week of {reporting_week_start} | StatusReportListPage, StatusReportForm, StatusReportDetail React components | • New Report auto-fills reporting_week_start to nearest past Monday • Save Draft persists without submitted_at; form remains editable • Submit disables all form fields and shows submitted_at timestamp • Submitted report in list shows RAG badges with correct colour (RED=red, AMBER=amber, GREEN=green) • Milestone snapshot table in detail view shows code, name, target_date, forecast_date, status • Toast shown on successful submit with correct week date | 55 | 1.5-T09, 1.5-T11 | PM | PM-14
1.5-T26 | program-mgmt | 1.5 | 1. Project Management & Mobilization | Ongoing project management & reporting | 1 | Admin portal UI: Sprint ceremony log screen and open action items widget | Admin portal ceremony log screen per PRD-07. Requirements: ceremony log list filtered by sprint number with a dropdown (Sprint 1..N); Log Ceremony button opens form (ceremony_type, sprint_number, ceremony_date, facilitator, attendees textarea, summary textarea, phase); ceremony row expandable to show action items; Add Action Item button per ceremony row; action item row shows description, owner, due_date, status badge; inline status update dropdown (OPEN/IN_PROGRESS/DONE/CANCELLED); Open Action Items widget on sidebar showing all open/in-progress items across sprints with overdue highlight (due_date < today). Calls /pm/ceremony API (1.5-T10). | • Create SprintCeremonyPage with sprint filter dropdown and ceremony list • Implement LogCeremonyForm component with all required fields and ceremony_type select (PLANNING/REVIEW/RETROSPECTIVE/STANDUP/OTHER) • Implement CeremonyRow expandable component showing nested action items table • Add Add Action Item inline form per ceremony (description, owner, due_date) • Implement status inline dropdown per action item calling PATCH ceremony/action-items/{id} • Create OpenActionItemsWidget component calling GET /pm/ceremony/action-items/open; highlight rows where due_date < today in amber/red | SprintCeremonyPage, LogCeremonyForm, CeremonyRow, OpenActionItemsWidget React components | • Sprint filter dropdown filters ceremonies to selected sprint only • Log Ceremony form with invalid ceremony_type fails client-side validation before submit • Expanding ceremony row loads and shows its action items • Status dropdown on action item sends PATCH request and updates badge without page reload • Invalid transition (DONE->OPEN) shows error toast from API 422 response • OpenActionItemsWidget highlights items where due_date < today | 55 | 1.5-T10 | PM | PM-14
1.5-T27 | program-mgmt | 1.5 | 1. Project Management & Mobilization | Ongoing project management & reporting | 1 | Admin portal UI: PM dashboard summary screen with RAG, RAID counts, and next milestone | Admin portal PM dashboard screen aggregating GET /pm/dashboard/summary (1.5-T16). Screen layout: top row - 4 RAG traffic-light cards (overall, scope, schedule, budget) from latest submitted report (show grey if no report submitted); middle row - RAID summary cards (Risks Open N, Assumptions Open N, Issues Open N, Dependencies Open N), overdue dependencies count card (red badge if > 0), open action items card; bottom row - next milestone card showing code, name, target_date, status chip, and variance_days (show in red if variance_days > 0); a milestones timeline or table below. Calls /pm/dashboard/summary and /pm/milestones. | • Create PMDashboardPage calling GET /pm/dashboard/summary on mount • Implement RagCard component rendering coloured card (RED=red bg, AMBER=amber bg, GREEN=green bg, null=grey bg) • Implement RaidCountsRow with 4 count cards and overdue badge • Implement NextMilestoneCard with variance_days display: positive = red text with + prefix, negative = green text, 0 or null = neutral • Implement MilestoneTable calling GET /pm/milestones showing all 16 milestones with status chips and variance_days column • Auto-refresh GET /pm/dashboard/summary every 60 seconds | PMDashboardPage, RagCard, RaidCountsRow, NextMilestoneCard, MilestoneTable React components | • RAG cards show grey when latest_report_rag is null (no submitted report) • overdue_dependencies_count card shows red badge when count > 0 • NextMilestoneCard variance_days=22 displayed in red with + prefix • NextMilestoneCard variance_days=-5 displayed in green • MilestoneTable shows 16 rows after seeding • Dashboard refreshes call to /pm/dashboard/summary every 60 seconds (verified via network inspector) | 55 | 1.5-T16, 1.5-T25 | PM | PM-14
1.5-T28 | program-mgmt | 1.5 | 1. Project Management & Mobilization | Ongoing project management & reporting | 1 | Scheduled job: weekly RAID review reminder email to GME PM for PENDING_REVIEW items | PM-14 A-14-03: GME PM must review new RAID items within 2 business days. A scheduled job runs every Monday at 08:00 KST and sends a summary email to the configured GME PM email (app.pm.review-email in application.properties) listing all raid_log rows with review_status=PENDING_REVIEW and created_at < (now - 2 business days). Email subject: '[GMEPay+] RAID items awaiting your review'. Body includes: table of pending items (raid_id, category, title, created_by, created_at). Use Spring @Scheduled(cron='0 0 8 * * MON', zone='Asia/Seoul'). Use JavaMailSender or equivalent. If zero items pending, do not send email. | • Create RaidReviewReminderJob class with @Component and @Scheduled annotation targeting Monday 08:00 KST • Implement logic: query RaidLogService.findPendingReviewItems(olderThanBusinessDays=2) returning items with review_status=PENDING_REVIEW and created_at before cutoff • Calculate business-day cutoff (skip Saturday and Sunday) for 2 business days ago from current date • Build email body as plain-text table; skip send if list is empty • Configure app.pm.review-email in application.properties (default: placeholder) • Unit test: mock date as Wednesday 2026-06-03; cutoff should be Monday 2026-06-01 (2 business days back) | RaidReviewReminderJob class + unit test for business-day cutoff logic | • Job cron annotation = '0 0 8 * * MON' with zone='Asia/Seoul' • findPendingReviewItems returns items with review_status=PENDING_REVIEW and created_at < cutoff • Business-day cutoff test: Wednesday 2026-06-03 minus 2 business days = Monday 2026-06-01 • Business-day cutoff test: Monday 2026-06-08 minus 2 business days = Thursday 2026-06-04 (skipping weekend from Friday) • If pending list is empty, JavaMailSender.send is NOT called (verified via mock assert never) • If pending list has 2 items, email is sent exactly once with both items in body | 50 | 1.5-T04, 1.5-T13 | PM | PM-14
1.5-T29 | program-mgmt | 1.5 | 1. Project Management & Mobilization | Ongoing project management & reporting | 1 | Scheduled job: milestone overdue alert email when target_date passed and status not COMPLETE | PM-14 §3.1 milestones must be tracked. A daily scheduled job at 07:00 KST checks all milestones: if target_date < today AND status NOT IN (COMPLETE, WAIVED) send an overdue alert email to app.pm.review-email. Use @Scheduled(cron='0 0 7 * * *', zone='Asia/Seoul'). Email subject: '[GMEPay+] Overdue milestones: {N} milestone(s) require attention'. Body: table with code, name, phase, target_date, forecast_date, variance_days, status. If all milestones are on track (none overdue), do not send. Example: if today is 2026-05-10 and KFTC_TEST_ENV milestone has target_date=2026-05-15 and status=NOT_STARTED, it is NOT overdue yet. If target_date=2026-05-09 and status=IN_PROGRESS, it IS overdue. | • Create MilestoneOverdueAlertJob with @Component and @Scheduled(cron='0 0 7 * * *', zone='Asia/Seoul') • Implement logic: MilestoneService.getOverdueMilestones(asOfDate) returning milestones where target_date < asOfDate AND status NOT IN (COMPLETE, WAIVED) • Build email with overdue milestone table; skip if empty • Unit test: mock today=2026-05-10; milestone with target_date=2026-05-09, status=IN_PROGRESS -> overdue; target_date=2026-05-11, status=IN_PROGRESS -> not overdue; target_date=2026-05-09, status=COMPLETE -> not overdue | MilestoneOverdueAlertJob class + MilestoneService.getOverdueMilestones + unit test | • Cron = '0 0 7 * * *' with zone='Asia/Seoul' • getOverdueMilestones(2026-05-10): milestone target 2026-05-09 + IN_PROGRESS -> included • getOverdueMilestones(2026-05-10): milestone target 2026-05-11 + IN_PROGRESS -> excluded (not past yet) • getOverdueMilestones(2026-05-10): milestone target 2026-05-09 + COMPLETE -> excluded • Email not sent when overdue list is empty • Email subject contains correct overdue count when items present | 40 | 1.5-T06, 1.5-T28 | PM | PM-14
1.5-T30 | program-mgmt | 1.5 | 1. Project Management & Mobilization | Ongoing project management & reporting | 1 | Docs: PM tooling operational runbook for RAID upkeep, status reporting, and sprint ceremonies | PM-14 A-14-03 requires the dev vendor to maintain the RAID log and notify GME PM at weekly status meetings. A runbook document must describe: (1) how to add a new RAID item via API or Admin portal; (2) the review/accept/reject workflow (PENDING_REVIEW -> ACCEPTED/REJECTED -> resubmit); (3) how to create and submit a weekly status report (Monday deadline; RAG definitions: GREEN = on track, AMBER = at risk but manageable, RED = off track / blocked); (4) how to log sprint ceremonies and manage action items; (5) how to update milestone forecast dates; (6) how to run /pm/dashboard/summary to get current project health; (7) reminder job configuration (app.pm.review-email). Write as docs/pm-runbook.md. | • Create docs/pm-runbook.md with sections matching the 7 areas listed above • Section 1: RAID entry creation - include POST /pm/raid example request with category=RISK, likelihood=HIGH, impact=HIGH • Section 2: Review workflow diagram (text-based: PENDING_REVIEW -> ACCEPTED or REJECTED -> resubmit -> PENDING_REVIEW) • Section 3: Status report process - include reporting_week_start must be Monday note; RAG colour definitions • Section 4: Sprint ceremony logging - ceremony types and action item lifecycle • Section 5: Milestone update - PATCH /pm/milestones/{code} example with forecast_date • Section 6: Dashboard endpoint and what each field means; Section 7: Email config property name | docs/pm-runbook.md covering all 7 operational areas | • Section 1 includes a concrete POST /pm/raid JSON example with raid_id, category, likelihood fields • Section 2 includes the full review status state machine in text or diagram form • Section 3 states reporting_week_start must be a Monday and defines RED/AMBER/GREEN • Section 5 includes PATCH /pm/milestones/{code} example showing variance_days calculation • Section 7 names the app.pm.review-email property and its default placeholder value • Document renders without broken markdown (no unclosed code blocks or headers) | 40 | 1.5-T08, 1.5-T09, 1.5-T10, 1.5-T11, 1.5-T16 | PM | PM-14
1.6-T01 | program-mgmt | 1.6 | 1. Project Management & Mobilization | As-built documentation & handover | 4 | Audit all 16 spec documents against implemented code and record delta log | WBS 1.6 produces as-built documentation. The GMEPay+ spec package comprises 16 documents (DOC-00 through REF-15). The as-built pass must compare each document to the actual implementation and record every deviation. Deviations include: fields renamed in implementation, endpoints removed or added vs API-05, schema differences vs DAT-03, batch job window changes vs OPS-13 SCH-06, and any open items (OI-01 through OI-OPS-04) that were resolved during build. Output is a structured delta log (CSV or Markdown table) with columns: doc_code, section, spec_statement, as_built_status (MATCH / CHANGED / ADDED / REMOVED), deviation_note. | • Clone the final production-deployed codebase branch (tag: release/1.0 or equivalent) • For each of the 16 docs listed in DOC-00 Section 3 (BRD-01 through REF-15), run a section-by-section comparison against the implementation: API endpoints vs OpenAPI export, DB schema vs Flyway migration files, batch jobs vs scheduler config, RBAC roles vs Admin System config • Record every deviation in delta_log.csv with columns: doc_code, section, spec_statement, as_built_status, deviation_note • Flag open items (OI-01, OI-02, OI-03, OI-OPS-01 through OI-OPS-04) as RESOLVED, DEFERRED, or STILL_OPEN with resolution details • Save delta_log.csv to docs/as-built/ in the repository | delta_log.csv in docs/as-built/ covering all 16 documents with per-section deviation status | • File contains at least one row per document (16 doc_code values present) • Every CHANGED or REMOVED row has a non-empty deviation_note explaining what was built instead • All 7 open items from DOC-00 §9 and OPS-13 §13.2 appear with an explicit RESOLVED, DEFERRED, or STILL_OPEN status • No row has as_built_status other than MATCH, CHANGED, ADDED, or REMOVED • File is valid CSV parseable without errors | 55 |  | BA | DOC-00
1.6-T02 | program-mgmt | 1.6 | 1. Project Management & Mobilization | As-built documentation & handover | 4 | Update DOC-00 master index to reflect as-built document versions and open item resolutions | DOC-00 (00_Documentation_Index_and_Handover.md) is the master index and handover guide. After build, it must reflect: (a) actual document versions and statuses (changing 'For Development Handover' to 'Approved' where signed off), (b) resolution of open items OI-01 (customer approval method), OI-02 (tax invoice API), OI-03 (BOK reporting format), (c) any documents added or removed during development, (d) updated reading order if architecture changed. Version is incremented per DOC-00 §6.3 rules: major if scope/architecture changed, minor if clarifications only. META header fields: version, date, status. | • Open 00_Documentation_Index_and_Handover.md from the repository • Update the META header: version to 1.x or 2.0 as appropriate, date to today (2026-06-05), status to Approved for any signed-off documents • Update Section 3 document map: revise Primary Audience column if team changed; add any new documents created during build • Update Section 9 open items: for each of OI-01, OI-02, OI-03 mark RESOLVED with resolution text or DEFERRED to Phase 2 with justification • Add a change note at the bottom of the document per DOC-00 §6.4 format: date, version, author, summary of changes | Updated 00_Documentation_Index_and_Handover.md with current version, resolved open items, and accurate document status column | • META header version and date fields are updated (not still v1.0 / June 2026 placeholder) • Every document in Section 3 table has a status that reflects its actual signoff state (not all 'For Development Handover' if some are approved) • OI-01, OI-02, OI-03 each have an explicit resolution or deferral note in Section 9 • A change note entry appears at the bottom of the file with date >= 2026-06-05 • No broken cross-references to document file names (all 16 filenames in Section 3 match files actually present in the repository) | 45 | 1.6-T01 | BA | DOC-00
1.6-T03 | program-mgmt | 1.6 | 1. Project Management & Mobilization | As-built documentation & handover | 4 | Update SAD-02 architecture document to reflect as-built component topology | SAD-02 (02_System_Architecture_Document.md) describes the context architecture, tech stack, deployment topology, and sequence flows. As-built changes commonly include: actual cloud provider chosen (OPS-13 A-OPS-01 assumed cloud-agnostic), actual message queue product (OPS-13 A-OPS-04), actual secrets manager (OPS-13 A-OPS-05), actual observability stack, and any sequence flow changes discovered during implementation. The four network zones (Public DMZ, API Zone, Worker Zone, Data Zone, Management Zone) from OPS-13 §3.2 must match the actual deployment. Tech stack: Java + PostgreSQL (per memory). Any architecture decisions that deviate from SAD-02 assumptions must be documented. | • Compare SAD-02 architecture diagram and component list against the actual deployed infrastructure (Terraform/IaC files, Kubernetes manifests, or equivalent) • Update the tech stack section: record actual Java version, Spring Boot version, PostgreSQL version, Redis version, message queue product name and version • Update network topology diagram to reflect actual zones and any additions • Update sequence flow diagrams (MPM payment, CPM payment, rate quote, prefunding deduction) if the implementation differs from spec • Add an 'As-Built Notes' subsection at the end of each major section noting deviations from the original spec • Increment document version in META header and add a change note | Updated 02_System_Architecture_Document.md with as-built component names, versions, and any topology deviations noted per section | • Tech stack table lists concrete versions (e.g. Java 21, Spring Boot 3.x, PostgreSQL 16) not placeholder text • Each of the 5 network zones from OPS-13 §3.2 appears in the topology with actual service names • At least one As-Built Notes subsection exists (even if stating 'no deviation from spec') • Document version in META header is incremented and change note is appended • All sequence diagrams reference actual service names matching the deployed codebase package structure | 50 | 1.6-T01 | BA | DOC-00
1.6-T04 | program-mgmt | 1.6 | 1. Project Management & Mobilization | As-built documentation & handover | 4 | Update DAT-03 data model to reflect as-built schema (tables, columns, indexes) | DAT-03 (03_Data_Model_and_ERD.md) is the canonical data model. During build, columns may have been renamed, types changed, new tables added, or indexes added beyond the spec. The as-built version must match the actual Flyway/Liquibase migration files in db/migrations/. Key tables to verify: transactions, prefunding_ledger, treasury_rates, batch_job_runs, audit_log, schemes, partners, rules. Money columns must show NUMERIC(x,y) precision and currency_code pairing. The treasury_rates table (per 4.1-T10) has columns id, currency_code VARCHAR(3), rate NUMERIC(20,8), source VARCHAR(10), effective_date DATE, created_at TIMESTAMP. | • Export the actual DB schema from the staging or production database using pg_dump --schema-only or equivalent • Diff every table definition against DAT-03: check column names, types, constraints, and NOT NULL flags • Update the DAT-03 entity descriptions and table-by-table data dictionary to match the actual schema • Update the ERD diagram (text-based Mermaid or ASCII) to include any new tables or relationships • Verify and update the money-handling section: confirm KRW scale=0 and USD scale=2 are enforced in NUMERIC column definitions • Increment document version and add change note | Updated 03_Data_Model_and_ERD.md with as-built table definitions, updated ERD, and accurate data dictionary | • Every table present in the production schema appears in the data dictionary (no undocumented tables) • treasury_rates table documents columns: currency_code VARCHAR(3), rate NUMERIC(20,8), source VARCHAR(10) CHECK IN ('LIVE','MANUAL'), effective_date DATE • transactions table entry documents the 8-step event trail fields (event_type, occurred_at) and the terminal status column (APPROVED, FAILED, UNCERTAIN, CANCELLED) • KRW money columns show scale=0 and USD columns show scale=2 in the type column • ERD shows the relationship between rules, partners, schemes, and transactions correctly | 55 | 1.6-T01 | BA | DOC-00
1.6-T05 | program-mgmt | 1.6 | 1. Project Management & Mobilization | As-built documentation & handover | 4 | Update RATE-04 rate engine spec to reflect as-built implementation and add worked example cross-checks | RATE-04 (04_Rate_Engine_and_Settlement_Spec.md) is the foundational rate engine document. It defines the 5-step RECEIVE-mode sequence: (1) payout_usd_cost = target_payout / cost_rate_pay, (2) collection_usd = payout_usd_cost / (1 - m_a - m_b), (3) margins, (4) send_amount = collection_usd * cost_rate_coll, (5) collection_amount = send_amount + service_charge. Pool identity invariant: collection_usd - collection_margin_usd - payout_margin_usd == payout_usd_cost (tolerance 0.01 USD). As-built updates: confirm the same-currency short-circuit implementation (collection_amount = target_payout + service_charge), confirm Partner B deviation tolerance default (1.0%), confirm rate quote TTL values (60s aggregator-bound, 300s otherwise). Record any rounding-point decisions made during implementation. | • Review the rate engine implementation (RateEngineService and related classes) against RATE-04 step-by-step • Document any rounding points added or changed: which step truncates/rounds, what scale (8 dp for rates per the existing spec), how BigDecimal HALF_UP is applied • Confirm the same-currency short-circuit: if collection_ccy = settle_a_ccy = settle_b_ccy = payout_ccy then step skips USD pool; collection_amount = target_payout + service_charge; verify this path is documented • Add an as-built worked example for GME Remit (domestic KRW/KRW): target_payout=50000 KRW, service_charge=500 KRW, expected collection_amount=50500 KRW • Add or verify the worked example for SendMN (cross-border): target_payout=50000 KRW, cost_rate_pay=1380, m_a=0.01, m_b=0.01, service_charge=0.36 USD, expected collection_usd=36.9714, send_amount=36.9714, collection_amount=37.3314 • Increment document version and add change note | Updated 04_Rate_Engine_and_Settlement_Spec.md with as-built rounding rules, confirmed short-circuit behaviour, and two verified worked examples (domestic + cross-border) | • The 5-step sequence in the document matches the implementation code exactly (no step reordered or missing) • Domestic example: target_payout=50000 KRW, service_charge=500 KRW, collection_amount=50500 KRW documented and annotated as same-currency short-circuit • Cross-border example: pool identity check (36.9714 - 0.36971 - 0.36971 = 36.2319 within 0.01 USD) is shown as a verification step • Partner B deviation tolerance default of 1.0% is stated explicitly • Rate quote TTL section states 60s for aggregator-bound and 300s otherwise, both configurable in range 60-1800s | 50 | 1.6-T01 | BA | DOC-00
1.6-T06 | program-mgmt | 1.6 | 1. Project Management & Mobilization | As-built documentation & handover | 4 | Update API-05 spec to reflect as-built endpoint contracts and export final OpenAPI file | API-05 (05_Partner_API_Specification.md) is the normative northbound API contract. As-built updates include: confirming actual base URLs (https://api-sandbox.gmepayplus.com and https://api.gmepayplus.com are placeholders per API-05 §2.1 — replace with actual provisioned hostnames), verifying all endpoint paths and HTTP methods match the implementation, confirming error code list is complete, verifying idempotency-key behaviour (24-hour window, 422 on body mismatch), and confirming webhook event payload field names. The HMAC-SHA256 signing scheme from API-05 §3.2 must be documented with the actual canonical string format. Export the live OpenAPI 3.x JSON spec from the running application. | • Export the OpenAPI 3.x spec from the running staging application (e.g. GET /v3/api-docs or Springdoc endpoint) • Compare every path, method, request body schema, and response schema in the export against API-05 • Update API-05: replace placeholder base URLs with actual DNS names, correct any endpoint or field name discrepancies, add any endpoints implemented but not originally specced • Confirm and document the HMAC canonical string format with a concrete example: method + newline + path + newline + UTC-timestamp + newline + body-sha256-hex • Save the exported OpenAPI JSON as docs/api/openapi-v1.json in the repository • Increment API-05 document version and add change note | Updated 05_Partner_API_Specification.md with actual base URLs and verified endpoint contracts; openapi-v1.json in docs/api/ | • openapi-v1.json is valid JSON and passes openapi-spec-validator (or equivalent) with zero errors • Every path in openapi-v1.json has a corresponding section in API-05 and vice versa (no undocumented endpoints, no documented endpoints missing from the spec) • Base URL fields no longer contain the placeholder text 'Assumption: Exact hostnames are placeholders' • HMAC canonical string example in API-05 §3.2 shows actual field order and a worked 5-line example • Error code table in API-05 includes PARTNER_B_QUOTE_DEVIATION and PARTNER_B_QUOTE_UNAVAILABLE with correct HTTP status codes | 55 | 1.6-T01 | BA | DOC-00
1.6-T07 | program-mgmt | 1.6 | 1. Project Management & Mobilization | As-built documentation & handover | 4 | Update SCH-06 ZeroPay integration spec to reflect as-built batch file implementations | SCH-06 (06_QR_Scheme_Integration_Spec_ZeroPay.md) covers the southbound ZeroPay SFTP batch interface: ZP00xx file types (ZP0011, ZP0012, ZP0021, ZP0022, ZP0041, ZP0043, ZP0045, ZP0047, ZP0051, ZP0053, ZP0055, ZP0061, ZP0062, ZP0063, ZP0064, ZP0065, ZP0066), SFTP paths, batch window KST times, and reconciliation logic. As-built updates: confirm actual SFTP path structure (OPS-13 §6.5: /gmepay/batch/<direction>/<file-id>/YYYY-MM-DD/<filename>), confirm file archival path in object storage (/gmepay/batch/...), record any field mapping differences discovered against 한결원 actual format, note OI-OPS-01 and OI-OPS-02 resolution status (한결원 test environment availability, production SFTP host). | • Retrieve the as-built SFTP file generation code for each ZP00xx type from the batch-worker service • Compare each file's field layout and encoding against SCH-06 file specifications; record any deviations • Update SCH-06 to reflect any field name changes, record layout changes, or encoding differences confirmed with 한결원 during integration testing • Update the SFTP path and archival path sections to match OPS-13 §6.5 conventions • Update OI-OPS-01 and OI-OPS-02 open items with actual resolution: confirm 한결원 test environment date accessed and production SFTP host/port confirmed • Increment document version and add change note | Updated 06_QR_Scheme_Integration_Spec_ZeroPay.md with as-built file layouts, confirmed SFTP paths, and resolved open items OI-OPS-01 and OI-OPS-02 | • SFTP path pattern in the document matches OPS-13 §6.5 pattern: /gmepay/batch/<direction>/<file-id>/YYYY-MM-DD/<filename> • OI-OPS-01 (한결원 test environment) has a resolution date and access confirmation note • OI-OPS-02 (production SFTP host) is either resolved with actual host/port or explicitly flagged as still OPEN with go-live blocker note • All 18 ZP00xx file types listed in the document have a confirmed field layout with no TBD markers remaining • Reconciliation section confirms ZP0062/ZP0064 vs internal aggregation tolerance and the exception handling path | 55 | 1.6-T01 | BA | DOC-00
1.6-T08 | program-mgmt | 1.6 | 1. Project Management & Mobilization | As-built documentation & handover | 4 | Update SEC-09 security spec to reflect as-built auth, secrets, and audit implementation | SEC-09 (09_Security_and_Compliance_Spec.md) covers HMAC-SHA256 auth, secrets inventory, RBAC roles, BOK FX reporting (FX1014, FX1015), audit log fields, and data privacy. As-built updates: confirm actual bcrypt cost factor for API secret hashing (spec: cost >= 12), confirm RBAC roles as implemented in the Admin System, confirm audit log fields captured per transaction (actor, timestamp, previous_value, new_value), confirm secrets path convention (gmepay/<env>/<service>/<secret-name> per OPS-13 §4.7), and record OI-03 BOK reporting status. SEC-09 §7 incident response plan should be confirmed against the actual on-call runbook. | • Check the authentication implementation: verify bcrypt cost factor >= 12 in the Partner credential hash; document the actual cost factor used • Review RBAC role definitions in Admin System against SEC-09 RBAC table; update any role name or permission changes • Verify audit log schema: confirm actor, timestamp, previous_value, new_value, entity_type, entity_id fields are present on config change events • Update BOK reporting section with OI-03 resolution or deferral note; if FEATURE_BOK_REPORTING flag is still false in Phase 1, state this explicitly • Confirm secrets path convention matches gmepay/<env>/<service>/<secret-name> and document one concrete example per service • Increment document version and add change note | Updated 09_Security_and_Compliance_Spec.md with confirmed bcrypt cost, as-built RBAC roles, audit field list, and OI-03 BOK status | • Bcrypt cost factor is documented as a concrete integer >= 12 (not 'cost >= 12' placeholder) • RBAC table lists actual role names matching the Admin System implementation (e.g. ADMIN, OPS, FINANCE, READ_ONLY or equivalent) • Audit log field list includes at minimum: actor_id, actor_role, entity_type, entity_id, action, previous_value, new_value, occurred_at • Secrets path section contains at least one real example: gmepay/prod/batch-worker/zeropay-sftp-key • OI-03 BOK reporting section explicitly states Phase 1 status: flag FEATURE_BOK_REPORTING=false, target for Phase 2 resolution | 50 | 1.6-T01 | BA | DOC-00
1.6-T09 | program-mgmt | 1.6 | 1. Project Management & Mobilization | As-built documentation & handover | 4 | Update OPS-13 runbook to reflect as-built environment names, service commands, and config matrix | OPS-13 (13_DevOps_Deployment_and_Runbook.md) is the operational runbook. As-built updates target three areas: (1) §2 Environment Strategy - confirm actual environment tier names (dev/int/staging/prod) and the 한결원 test environment access date; (2) §4 CI/CD - confirm actual pipeline tool (GitHub Actions, Jenkins, etc.), branch strategy as built, and image tagging convention; (3) §5.3 Environment Configuration Matrix - replace placeholder values with actual config (ZeroPay SFTP host, DB pool sizes, rate quote TTL, webhook retry max). The batch job schedule table (§6.2, jobs JOB-ZP-01 through JOB-ZP-13) must reflect any window adjustments discovered during 한결원 integration. Runbook commands (e.g. kubectl rollout restart) must match actual cluster namespace and deployment names. | • Confirm and update the §2 environment tiers table with actual DNS names, access dates, and ZeroPay sandbox confirmation • Update §4.1 pipeline stages table with actual CI/CD tool name and stage duration baselines from the first production build • Replace all placeholder values in §5.3 Environment Configuration Matrix with measured actuals: DB pool sizes, rate quote TTL per environment, webhook retry max • Update §6.2 batch job schedule table if any KST window was adjusted during 한결원 testing • Update all runbook CLI commands with actual Kubernetes namespace (e.g. gmepay-prod) and deployment names (e.g. hub-api, batch-worker, admin-svc) • Update open items OI-OPS-03 (scaling thresholds) and OI-OPS-04 (SendMN onboarding) with Phase 1 outcomes • Increment document version and add change note | Updated 13_DevOps_Deployment_and_Runbook.md with confirmed environment config, CI/CD tool name, actual kubectl deployment names, and resolved/updated open items | • §5.3 config matrix has no placeholder or 'TBD' values for any prod-column entry • At least one runbook CLI command (e.g. §8.4 SFTP key rotation or §8.7 batch reprocess) contains the actual Kubernetes namespace and deployment name • Batch job schedule in §6.2 has confirmed KST window times (not 'per KST production windows' placeholder) • OI-OPS-01 entry states the actual date 한결원 test environment became accessible • §4.1 pipeline stages table names the actual CI/CD tool (e.g. GitHub Actions) in a note or tool column | 55 | 1.6-T01, 1.6-T03 | BA | DOC-00
1.6-T10 | program-mgmt | 1.6 | 1. Project Management & Mobilization | As-built documentation & handover | 4 | Update PM-14 project plan with as-built phase actuals, milestone dates, and RAID log close-outs | PM-14 (14_Project_Plan_RAID_RACI.md) contains the phased delivery plan, milestone table, RAID log, and RACI. For WBS 1.6 (as-built docs), PM-14 must be updated with: (a) actual Phase 1 gate date vs planned Apr 10 - Jun 20 2026, (b) Phase 2 ZeroPay integration milestone actuals (한결원 test environment date, end-to-end test date), (c) RAID log: close out resolved risks and issues, record actual impacts, (d) Phase 3 go-live checklist status (Oct 10 2026 target), (e) RACI: confirm assignees are accurate. Phase 4 (T-Bank/SendMN overseas onboarding Oct 1 - Dec 10 2026) open items should be added if not already tracked. | • Update §3 milestone table: fill Actual Date column for all completed milestones; mark Phase 1 gate as achieved with date • Update RAID log: close out risks and issues that were resolved during Phase 1/2 build; add new risks identified during implementation with probability, impact, and owner • Update RACI matrix: confirm all role assignments match the actual delivery team contacts • Add a Phase 1 retrospective note (1-2 sentences per major deliverable) noting any schedule variance • Confirm the Phase 3 go-live checklist in §5 is current and reflects items completed in OPS-13 §12.1 • Increment document version and add change note | Updated 14_Project_Plan_RAID_RACI.md with actual milestone dates, closed RAID items, and Phase 1 retrospective notes | • Milestone table contains an Actual Date value (not blank) for every milestone with planned date <= 2026-06-05 • At least 3 RAID log rows have status CLOSED with a resolution description • RACI matrix has real names or role designations (not Placeholder) for all rows with delivery team responsibility • Phase 3 go-live checklist §5 has no items that are demonstrably incomplete based on Phase 1 scope • Document version in META header is incremented and a change note is appended | 45 | 1.6-T01 | BA | DOC-00
1.6-T11 | program-mgmt | 1.6 | 1. Project Management & Mobilization | As-built documentation & handover | 4 | Update REF-15 glossary to add terms introduced during build and flag any redefined terms | REF-15 (15_Glossary_and_Data_Dictionary.md) is the canonical terminology reference. During build, the implementation may have introduced new terms (class names, service names, error codes, config flag names) or used existing terms differently. New terms to check: job_run_id (from batch idempotency, OPS-13 §6.3), FEATURE_* flag names (OPS-13 §5.2: FEATURE_LIVE_FX_FEED, FEATURE_PARTNER_REFUND_API, FEATURE_OUTBOUND_PAYMENTS, FEATURE_BOK_REPORTING, FEATURE_MULTI_SCHEME_ROUTING), RateSource enum values (IDENTITY, LIVE, MANUAL, PARTNER from the rate engine), error codes (PARTNER_B_QUOTE_DEVIATION, PARTNER_B_QUOTE_UNAVAILABLE, RATE_UNAVAILABLE, SCHEME_UNAVAILABLE). Any term used in API-05 error responses or in the batch runbook that does not appear in REF-15 must be added. | • Search the codebase and updated API-05 / OPS-13 documents for all domain terms, error codes, and config flag names not currently in REF-15 • Add each missing term with: name, definition (1-2 sentences), document cross-reference, and type (error_code / enum_value / config_flag / entity / process) • Review existing entries: if any definition was changed during build (e.g. a field name was renamed), update the definition and add a deprecated alias row • Add the 5 FEATURE_* flag names with their Phase 1 default values (all false) and a brief description of what each enables • Add all error codes present in the API-05 error table to REF-15 if not already listed • Increment document version and add change note | Updated 15_Glossary_and_Data_Dictionary.md with all new terms, error codes, and feature flags from the as-built system | • All 5 FEATURE_* flag names from OPS-13 §5.2 are present with Phase 1 default=false noted • Error codes PARTNER_B_QUOTE_DEVIATION, PARTNER_B_QUOTE_UNAVAILABLE, RATE_UNAVAILABLE, and SCHEME_UNAVAILABLE are defined with HTTP status codes and trigger conditions • RateSource enum values IDENTITY, LIVE, MANUAL, PARTNER are defined with the condition under which each applies • job_run_id is defined as UUID, scoped to a single batch job execution, used for idempotency • No term added during this ticket conflicts with an existing definition (check for duplicate entries) | 40 | 1.6-T01, 1.6-T06 | BA | DOC-00
1.6-T12 | program-mgmt | 1.6 | 1. Project Management & Mobilization | As-built documentation & handover | 4 | Produce sandbox API onboarding guide for partner integration engineers | WBS 1.6 deliverable includes API docs for partner integration. The sandbox environment (https://api-sandbox.gmepayplus.com per API-05 §2.1, updated to actual URL in 1.6-T06) is the integration target for GME Remit and SendMN. The onboarding guide must let a partner engineer with no prior GMEPay+ knowledge authenticate, obtain a rate quote, and submit a test payment in under 30 minutes. It must cover: HMAC-SHA256 signing (canonical string: HTTP_METHOD + newline + path + newline + UTC-timestamp + newline + body-sha256-hex per API-05 §3.2), idempotency key format (UUID v4 per API-05 §2.6), rate quote TTL (default 300s per RATE-04), and the two test scenarios: domestic KRW payment (GME Remit type) and cross-border USD-funded payment (SendMN type). | • Create docs/api/sandbox-onboarding-guide.md in the repository • Section 1 - Credentials: explain how to request sandbox credentials (X-API-Key + API Secret) from GME Ops; explain that the secret is shown once and must be stored securely • Section 2 - Authentication: provide a step-by-step HMAC signing example with a concrete request (POST /v1/rates, body {target_payout:50000, currency:KRW}), showing the canonical string construction and the X-GME-Signature header value • Section 3 - Rate Quote: show a complete GET /v1/rates request and response example including validUntil timestamp and the offer_rate field • Section 4 - Submit Payment: show POST /v1/payments request with Idempotency-Key header and the response; note that the quote must be used within TTL • Section 5 - Webhook: show the payment.approved webhook payload and instruct the partner to return HTTP 200 within 5 seconds | docs/api/sandbox-onboarding-guide.md with 5 sections covering credentials, auth, rate quote, payment submission, and webhook | • HMAC canonical string example in Section 2 shows all 4 lines: method, path, timestamp, body-hash (concrete values, not pseudocode) • Section 3 shows a complete JSON response for POST /v1/rates including validUntil in ISO-8601 UTC format and offer_rate as a decimal string • Section 4 includes the Idempotency-Key header with a UUID example and explicitly states the 24-hour deduplication window • Section 5 webhook payload includes transaction_id, status (APPROVED), collection_amount, and payout_amount with example values • Guide contains zero internal GME jargon that is not defined inline (every term used is either in REF-15 or defined in the guide itself) | 55 | 1.6-T06, 1.6-T11 | BA | DOC-00
1.6-T13 | program-mgmt | 1.6 | 1. Project Management & Mobilization | As-built documentation & handover | 4 | Produce partner webhook integration reference with retry semantics and failure scenarios | Partners rely on webhooks for async payment results. API-05 defines webhook delivery but the as-built system's retry policy (OPS-13 §7.5.6: max 5 retries in prod, P2 alert on failure) must be documented for partner engineers. Partners need to know: (1) webhook URL must return HTTP 200-299 within 5 seconds or the delivery is retried, (2) retry schedule: exponential back-off (exact schedule from OPS-13 §6.3: 30s, 120s, 300s for batch; webhook retry schedule must be verified from implementation), (3) event types: payment.approved, payment.failed, payment.cancelled (confirm from implementation), (4) how to verify the webhook signature to prevent spoofing, (5) idempotency: webhooks for the same transaction_id may be delivered more than once on retry; partners must handle duplicates. | • Verify the webhook retry schedule from the implementation (number of retries, back-off intervals) and confirm it matches OPS-13 §7.5.6 (max 5 retries in prod) • Create docs/api/webhook-reference.md • Section 1 - Event types: list all webhook event types with their trigger conditions (payment.approved: ZeroPay confirms; payment.failed: scheme rejects or prefund insufficient; payment.cancelled: same-day cancel processed) • Section 2 - Delivery semantics: document timeout (5s), retry count, back-off schedule with explicit intervals in seconds, and the at-least-once delivery guarantee • Section 3 - Signature verification: show how to verify the X-GME-Webhook-Signature header (HMAC-SHA256 of the raw body using the partner API secret) • Section 4 - Idempotency: instruct partner to use transaction_id as a deduplication key; show example of duplicate delivery and correct handling (return 200, discard duplicate) • Section 5 - Failure escalation: explain that after max retries, GME Ops can manually re-trigger from Admin System on partner request | docs/api/webhook-reference.md covering all event types, retry semantics, signature verification, and idempotency | • Section 1 lists exactly the event types implemented (must include payment.approved and payment.failed at minimum; confirm payment.cancelled if implemented) • Section 2 states the retry count (max 5 in prod per OPS-13) and lists the explicit back-off intervals in seconds • Section 3 includes a concrete signature verification code snippet (pseudocode or Java/Python) showing HMAC-SHA256(raw_body, api_secret) • Section 4 explicitly states that duplicate webhook deliveries can occur and the correct handling is to check transaction_id before processing • Retry interval values are consistent between webhook-reference.md and the OPS-13 §7.5.6 alert thresholds | 50 | 1.6-T06, 1.6-T09 | BA | DOC-00
1.6-T14 | program-mgmt | 1.6 | 1. Project Management & Mobilization | As-built documentation & handover | 4 | Produce ops handover: FX rate update procedure and rate engine admin guide | GME Ops staff must be able to update FX treasury rates without engineering assistance. OPS-13 §8.11 defines the Phase 1 manual FX rate update procedure. The rate engine uses treasury.usd_{ccy} = units of {ccy} per 1 USD. Example: treasury.usd_krw = 1381.50 means 1 USD = 1381.50 KRW. The Admin System FX Rates screen applies a 4-eyes check if the rate change exceeds 2% (OPS-13 §8.11). After update, the new rate is effective for new transactions within 1 second (in-memory cache TTL per OPS-13 §8.11). Feature flag FEATURE_LIVE_FX_FEED is false in Phase 1. Ops staff must also understand the rate-lock guarantee: committed transactions are never affected by subsequent rate changes. | • Create docs/ops/fx-rate-update-guide.md • Section 1 - Rate convention: explain treasury.usd_{ccy} format with a worked example: treasury.usd_krw = 1381.50 means 1 USD = 1381.50 KRW; note KRW has 0 decimal places • Section 2 - Update procedure: reproduce the OPS-13 §8.11 steps verbatim with actual Admin System screen navigation path (Admin System -> FX Rates -> [currency] -> Update) • Section 3 - 4-eyes control: explain that a change > 2% requires second-operator approval; show what the system displays (percentage diff from previous rate); describe the approval workflow • Section 4 - Verification: explain how to verify the new rate is active using the Admin System rate calculation preview; show expected output for GME Remit domestic (50000 KRW + 500 = 50500 KRW) and SendMN cross-border • Section 5 - Rate lock guarantee: state clearly that updating a rate does NOT affect any transaction that was already committed; explain validUntil on outstanding quotes (TTL 300s default) | docs/ops/fx-rate-update-guide.md with 5 sections covering convention, procedure, 4-eyes control, verification, and rate-lock guarantee | • Section 1 states the treasury.usd_{ccy} convention with a concrete KRW example: 1 USD = 1381.50 KRW, field name treasury.usd_krw • Section 3 states the 2% threshold for 4-eyes approval explicitly (not 'large changes' vaguely) • Section 4 verification example confirms: domestic GME Remit 50000 KRW target_payout + 500 KRW service_charge = 50500 KRW collection_amount (same-currency short-circuit) • Section 5 uses the word 'rate-lock' and states that already-committed transactions are not affected • Guide contains no references to code, JVM, or database commands -- it is written for non-technical Ops staff | 45 | 1.6-T05, 1.6-T09 | BA | DOC-00
1.6-T15 | program-mgmt | 1.6 | 1. Project Management & Mobilization | As-built documentation & handover | 4 | Produce ops handover: prefunding management procedure for OVERSEAS partners | GME Ops records and monitors USD prefunding for OVERSEAS partners (SendMN, T-Bank). Prefunding deductions are atomic (SELECT ... FOR UPDATE). Low-balance threshold: USD 10,000 (P2 alert); critical threshold: USD 2,000 (P1 alert, payments suspended automatically). OPS-13 §8.5 covers the top-up recording procedure; OPS-13 §8.6 covers the critical-balance response. Partners need to be suspended via Admin System -> Partner -> Status -> Suspend; re-enabled once top-up is confirmed. The prefunding ledger records each deduction and top-up immutably with operator_id and timestamp. Phase 1 only GME Remit is LOCAL (no prefunding); SendMN and T-Bank are OVERSEAS. | • Create docs/ops/prefunding-guide.md • Section 1 - Which partners need prefunding: list OVERSEAS partners (SendMN, T-Bank) vs LOCAL (GME Remit); state that LOCAL partners require no prefunding • Section 2 - Top-up recording procedure: reproduce OPS-13 §8.5 steps with actual Admin System navigation; state that the balance updates immediately and the Finance reference is mandatory • Section 3 - Alert thresholds: document default thresholds (P2 at USD 10,000; P1 at USD 2,000; suspension at USD 0); note that per-partner thresholds are configurable in Admin System • Section 4 - Critical balance response: reproduce OPS-13 §8.6 steps including the Suspend action path; state that in-flight transactions are not affected by suspension • Section 5 - Ledger immutability: explain that every top-up and deduction is an immutable ledger entry visible in Admin System -> Partner -> Prefunding Ledger; entries cannot be deleted or edited | docs/ops/prefunding-guide.md covering partner types, top-up procedure, alert thresholds, critical response, and ledger audit trail | • Section 1 explicitly identifies GME Remit as LOCAL (no prefunding) and SendMN/T-Bank as OVERSEAS (prefunding required) • Section 3 states both numeric thresholds: USD 10,000 (P2) and USD 2,000 (P1) as defaults • Section 4 includes the explicit Admin System navigation path: Admin System -> Partners -> [Partner Name] -> Status -> Suspend • Section 4 states that in-flight transactions at the moment of suspension are NOT cancelled (they complete normally) • Section 5 states that ledger entries are immutable and include operator_id and timestamp | 40 | 1.6-T09 | BA | DOC-00
1.6-T16 | program-mgmt | 1.6 | 1. Project Management & Mobilization | As-built documentation & handover | 4 | Produce ops handover: ZeroPay batch job monitoring and reprocessing runbook | GME Ops must monitor and respond to batch job failures. OPS-13 §6.2 defines 13 batch jobs (JOB-ZP-01 through JOB-ZP-13) with KST window times. Critical path: JOB-ZP-01/02 by 02:00 KST -> JOB-ZP-03/04 by 05:00 -> JOB-ZP-05 by 05:00 -> JOB-ZP-06 by 10:00. P1 alerts fire at 15 minutes before window (e.g. ZP0011 alert at 01:45 KST per OPS-13 §6.4). Reprocessing uses Admin System -> Batch Jobs -> [JOB-ID] -> Rerun for Date, or CLI: batch-cli rerun --job JOB-ZP-01 --date <YYYY-MM-DD> --force. The batch worker checks idempotency: if the file was already received by 한결원 (confirmed via ZP0012), re-run is a no-op. Never re-submit ZP0061 without 한결원 confirmation (double-submission risk per OPS-13 §8.7.2). | • Create docs/ops/batch-monitoring-runbook.md • Section 1 - Daily job schedule: reproduce the 13-job table from OPS-13 §6.2 with Job ID, file(s), direction, window, dependency, criticality; add the alert threshold column from §6.4 • Section 2 - Monitoring dashboard: describe the Batch Health dashboard panels (job timeline, last run status, file receipt by window) and where to find the job_run_id for a specific run • Section 3 - Reprocessing procedure: provide the Admin System and CLI paths for re-running a job; include the idempotency note (no-op if already received) • Section 4 - ZP0061 special handling: explicitly state the double-submission risk for ZP0061 and require 한결원 confirmation before re-submitting; provide the 한결원 ops contact lookup path • Section 5 - Escalation: state that after 3 automatic retries (30s, 120s, 300s per OPS-13 §6.3) the job enters FAILED state and requires manual action; list the escalation path from OPS-13 §11.2 | docs/ops/batch-monitoring-runbook.md with job schedule table, dashboard guide, reprocessing procedure, ZP0061 warning, and escalation path | • Section 1 table lists all 13 jobs (JOB-ZP-01 through JOB-ZP-13) with KST window times matching OPS-13 §6.2 • Section 1 includes P1 alert threshold times (01:45 KST for JOB-ZP-01/02; 05:15 KST for JOB-ZP-05; 10:30 KST for JOB-ZP-06) • Section 3 shows both the Admin System GUI path and the CLI command with --force flag • Section 4 contains an explicit warning that ZP0061 must not be re-submitted without 한결원 written confirmation, with reason (duplicate merchant crediting risk) • Section 5 states the 3-retry exponential back-off intervals: 30s, 120s, 300s | 50 | 1.6-T09 | BA | DOC-00
1.6-T17 | program-mgmt | 1.6 | 1. Project Management & Mobilization | As-built documentation & handover | 4 | Produce ops handover: incident response quick-reference card | On-call engineers need a quick-reference for P1/P2 incidents. OPS-13 §11 defines severity levels (P1 = 15-min response, P2 = 30-min), escalation path (engineer -> Engineering Lead -> Ops Manager -> 한결원 if scheme issue -> SEC-09 §7 if security), and postmortem requirements (all P1s, P2s that breach SLOs). OPS-13 §7.5 alert catalog has 20+ alerts across 6 categories. The quick-reference must map each P1 alert to a runbook section so the on-call engineer can navigate directly. Go-live is Oct 10, 2026; hypercare period is Oct 10-24 with lowered P2->P1 escalation. | • Create docs/ops/incident-quickref.md • Section 1 - Severity and response times: P1 = 15 min, P2 = 30 min, P3 = next business day; hypercare note: P2 treated as P1 during Oct 10-24 2026 • Section 2 - Alert-to-runbook map: create a 3-column table: Alert Name ¦ Severity ¦ Runbook Section. Include all P1 alerts from OPS-13 §7.5 (API error rate > 1%; payment endpoint unavailable; pool identity failure; ZP0011/ZP0021 missed; ZP0061 missed; ZP0012/ZP0022 not received; SFTP connection failure; prefunding at zero or critical) with their OPS-13 section reference • Section 3 - Escalation path: reproduce OPS-13 §11.2 5-step escalation as a numbered list with time triggers • Section 4 - First-response checklist: 5-bullet checklist covering: check alert source, check monitoring dashboard, check recent deployment (was there a deployment in last 30 min), check scheme status (ZeroPay SFTP), check transaction error rate trend • Section 5 - Postmortem trigger: state the rule: required for all P1 and any P2 that breached SLOs; document must include incident timeline, root cause, impact, action items | docs/ops/incident-quickref.md with severity table, alert-to-runbook map, escalation path, first-response checklist, and postmortem trigger rule | • Alert-to-runbook map table contains at least 8 P1 alert entries with correct OPS-13 section references • Section 3 escalation path lists all 5 steps from OPS-13 §11.2 with time triggers (15 min for P1, 30 min for P2) • Section 1 explicitly calls out the hypercare period (Oct 10-24 2026) and the P2->P1 escalation rule during hypercare • Pool identity failure (collection_usd - collection_margin_usd - payout_margin_usd != payout_usd_cost beyond 0.01 USD) appears as a P1 alert pointing to OPS-13 §8.9 • Postmortem section states 'within 48 hours' as the deadline per OPS-13 §11.4 | 45 | 1.6-T09, 1.6-T16 | BA | DOC-00
1.6-T18 | program-mgmt | 1.6 | 1. Project Management & Mobilization | As-built documentation & handover | 4 | Produce ops handover: go-live cutover checklist document | WBS 1.6 includes go-live handover materials. OPS-13 §12 defines the pre-go-live checklist (8 sections: infrastructure, application, ZeroPay integration, partners, merchant data, monitoring, security, operational readiness) and the cutover procedure. The Phase 3 go-live target is October 10, 2026, after a Tuesday/Wednesday morning batch window (approx 06:00 KST). The go-live smoke tests in OPS-13 §12.2 include: rate quote for GME Remit domestic (collection_amount = target_payout + 500 KRW), rate quote for SendMN cross-border (USD pool math), webhook delivery to GME Remit test endpoint, and prefunding balance read for SendMN. Partner configs: GME Remit (LOCAL, KRW/KRW, service charge KRW 500, no prefunding); SendMN (OVERSEAS, USD prefunding, 2% combined FX margin, KRW 500 service charge). | • Create docs/ops/go-live-checklist.md • Section 1 - Pre-go-live checklist: reproduce all 8 subsections from OPS-13 §12.1 (Infrastructure, Application, ZeroPay Integration, Partners, Merchant Data, Monitoring, Security, Operational Readiness) as a Markdown checkbox list with sign-off line per section • Section 2 - Cutover procedure: numbered steps from OPS-13 §12.2; specify the recommended window (Tuesday/Wednesday 06:00 KST after overnight batch completes) • Section 3 - Smoke tests: document the 4 go-live smoke tests with expected outputs: (a) GME Remit rate quote: target_payout=50000 KRW -> collection_amount=50500 KRW; (b) SendMN rate quote: verify USD pool identity holds; (c) webhook to GME Remit test endpoint returns 200; (d) SendMN prefunding balance readable • Section 4 - Rollback trigger: state the condition for rollback (critical defect blocking payment) and the first action (suspend partner API keys in Admin System -> Partners -> API Keys -> Suspend) • Section 5 - Hypercare schedule: reproduce OPS-13 §12.4 hypercare criteria (14 days, 10 consecutive successful batch days, zero P1s required to exit) | docs/ops/go-live-checklist.md with 8-section pre-go-live checklist, cutover procedure, smoke test specifications, rollback trigger, and hypercare schedule | • All 8 checklist sections from OPS-13 §12.1 are present with checkbox items (not just headings) • Smoke test (a) states exact values: target_payout=50000 KRW, expected collection_amount=50500 KRW for GME Remit domestic • Smoke test (b) instructs the operator to verify pool identity: collection_usd - collection_margin_usd - payout_margin_usd = payout_usd_cost within USD 0.01 • Section 4 rollback trigger specifies suspending API keys as the first action before any other rollback step • Section 5 states hypercare end condition: zero P1 incidents AND at least 10 consecutive successful complete batch cycles (morning + afternoon) | 50 | 1.6-T09, 1.6-T17 | BA | DOC-00
1.6-T19 | program-mgmt | 1.6 | 1. Project Management & Mobilization | As-built documentation & handover | 4 | Produce partner portal user guide for read-only balance and transaction inquiry | The Partner Portal (PRD-08) is a read-only self-service web portal. It provides: prefunding balance inquiry (OVERSEAS partners only), transaction history (filterable by date range, status, direction, partner_id, scheme), transaction detail (all 8 event trail steps), and CSV export. The portal is not a configuration interface -- GME Ops performs all config in the Admin System. Partners log in with portal credentials distinct from API credentials. The transaction event trail has 8 steps: rate_quote_issued, payment_initiated, prefund_deducted (OVERSEAS only), scheme_request_sent, scheme_response_received, transaction_committed, webhook_dispatched, webhook_delivered. Partners may see UNCERTAIN status for up to 24 hours on transactions where ZeroPay has not yet responded. | • Create docs/partner/portal-user-guide.md • Section 1 - Login and credentials: explain that portal credentials are separate from API credentials; contact GME Ops to obtain; two-factor authentication requirement if applicable • Section 2 - Prefunding balance (OVERSEAS only): show the balance display screen with fields (available_balance USD, last_top_up_date, last_top_up_amount); explain that LOCAL partners (GME Remit) do not see this section • Section 3 - Transaction history: show filter options (date range, status: APPROVED/FAILED/CANCELLED/UNCERTAIN, direction); explain cursor pagination; note that UNCERTAIN transactions may remain in that state for up to 24 hours during ZeroPay batch reconciliation • Section 4 - Transaction detail: show the 8-step event trail with timestamps; explain each step name in plain language; note that step 3 (prefund_deducted) is OVERSEAS partners only • Section 5 - CSV export: explain the fields in the export file; note 7-year data retention per SEC-09 | docs/partner/portal-user-guide.md with 5 sections covering login, balance inquiry, transaction history, event trail, and CSV export | • Section 2 explicitly states that LOCAL partners (e.g. GME Remit) do not have a prefunding balance section • Section 3 explains UNCERTAIN status and the 24-hour ZeroPay batch reconciliation window in plain language • Section 4 lists all 8 event trail step names in order (rate_quote_issued through webhook_delivered) with plain-language descriptions • Section 5 mentions 7-year retention as the reason why historical exports are available • Guide contains no Admin System content (no scheme config, no margin update -- those are Ops-only) | 45 | 1.6-T08, 1.6-T11 | BA | DOC-00
1.6-T20 | program-mgmt | 1.6 | 1. Project Management & Mobilization | As-built documentation & handover | 4 | Produce developer sandbox quick-start: end-to-end test of domestic payment flow | A partner developer integrating with the sandbox needs a concrete working example for the domestic payment flow (GME Remit type: LOCAL, KRW/KRW/KRW, same-currency short-circuit, service_charge=500 KRW). The flow is: (1) GET /v1/rates with target_payout=50000 KRW to receive offer_rate and validUntil, (2) POST /v1/payments with quote_id and Idempotency-Key to initiate payment, (3) receive payment.approved webhook. In the same-currency short-circuit, collection_amount = target_payout + service_charge = 50500 KRW; the USD pool steps are skipped; offer_rate = 1.0 (same currency). Sandbox credentials: obtained from GME Ops per 1.6-T12 guide. HMAC signing is required on all calls per API-05 §3.2. | • Create docs/api/quickstart-domestic.md • Section 1 - Prerequisites: sandbox credentials (X-API-Key, API Secret), curl or HTTP client, understand HMAC signing from sandbox-onboarding-guide.md §2 • Section 2 - Step 1: GET /v1/rates with request body {scheme_id: 'zeropay', direction: 'domestic', target_payout: {amount: '50000.00', currency: 'KRW'}}; show full signed request headers and expected response including collection_amount=50500 KRW, validUntil • Section 3 - Step 2: POST /v1/payments with Idempotency-Key, quote_id from step 1, and merchant_qr_id; show full request and expected response (transaction_id, status=PENDING) • Section 4 - Step 3: webhook receipt - show the payment.approved event payload with transaction_id matching step 2, status=APPROVED, collection_amount=50500 KRW • Section 5 - Verify: explain how to fetch transaction detail via GET /v1/payments/{transaction_id} and confirm all 8 event trail steps are visible (noting step 3 prefund_deducted will not appear for domestic LOCAL partners) | docs/api/quickstart-domestic.md with 5 sections: prerequisites, rate quote, payment initiation, webhook receipt, and verification | • Section 2 shows collection_amount=50500 KRW in the example response (50000 + 500 service charge, same-currency short-circuit) • Section 2 response does not include USD pool fields (payout_usd_cost, collection_usd) -- those are absent in the same-currency path • Section 3 shows the Idempotency-Key header with a UUID example and quotes the 24-hour deduplication window • Section 4 webhook payload shows status=APPROVED and collection_amount matching the Section 2 quote • Section 5 notes that event trail step 3 (prefund_deducted) will NOT appear for domestic LOCAL partner transactions | 50 | 1.6-T12, 1.6-T13 | BA | DOC-00
1.6-T21 | program-mgmt | 1.6 | 1. Project Management & Mobilization | As-built documentation & handover | 4 | Produce developer sandbox quick-start: end-to-end test of cross-border OVERSEAS payment flow | The cross-border payment flow applies to OVERSEAS partners (SendMN type: prefunded USD balance, m_a=0.01, m_b=0.01, service_charge=0.36 USD, settle_a_ccy=USD IDENTITY, settle_b_ccy=KRW LIVE). The 5-step rate engine is fully exercised: (1) payout_usd_cost = target_payout / cost_rate_pay = 50000/1380 = 36.2319 USD, (2) collection_usd = 36.2319/(1-0.01-0.01) = 36.9714 USD, (3) collection_margin_usd = 0.36971, payout_margin_usd = 0.36971, (4) send_amount = 36.9714 * 1.0 = 36.9714 USD, (5) collection_amount = 36.9714 + 0.36 = 37.3314 USD. Pool identity: 36.9714 - 0.36971 - 0.36971 = 36.2319 (within 0.01 USD). The prefunding balance must cover collection_amount before the scheme is called; insufficient balance returns HTTP 402 before any ZeroPay call. | • Create docs/api/quickstart-crossborder.md • Section 1 - Prerequisites: OVERSEAS partner sandbox credentials with prefunding enabled; note that the sandbox prefunding balance is pre-loaded by GME Ops for test use • Section 2 - Step 1: GET /v1/rates request and response; show all 5 rate engine output fields in the response: payout_usd_cost=36.2319, collection_usd=36.9714, send_amount=36.9714, collection_amount=37.3314 USD, offer_rate (cross_rate = target_payout/send_amount = 50000/36.9714 = 1352.66 KRW/USD) • Section 3 - Prefunding check: explain that insufficient prefunding balance returns HTTP 402 with error code INSUFFICIENT_PREFUNDING before the scheme is called; show example 402 response • Section 4 - POST /v1/payments: show request and response; note that prefunding deduction is atomic (SELECT FOR UPDATE) and occurs before ZeroPay is called • Section 5 - Webhook and verification: show payment.approved webhook payload including payout_usd_cost and collection_amount; show event trail including step 3 prefund_deducted | docs/api/quickstart-crossborder.md with 5 sections: prerequisites, rate quote with USD pool fields, prefunding check, payment initiation, and webhook verification | • Section 2 rate quote response shows all 5 calculated fields with values matching the worked example: collection_amount=37.3314 USD, collection_usd=36.9714 USD • Pool identity check is shown: 36.9714 - 0.36971 - 0.36971 = 36.2319 within 0.01 USD tolerance • Section 3 shows HTTP 402 error code INSUFFICIENT_PREFUNDING and explicitly states ZeroPay is NOT called when prefunding is insufficient • Section 4 states that prefunding deduction is atomic (uses SELECT ... FOR UPDATE) • Section 5 event trail includes step 3 (prefund_deducted) with a USD amount matching collection_amount | 55 | 1.6-T12, 1.6-T13, 1.6-T15 | BA | DOC-00
1.6-T22 | program-mgmt | 1.6 | 1. Project Management & Mobilization | As-built documentation & handover | 4 | Verify all docs/as-built documents pass internal consistency checks and cross-reference audit | WBS 1.6 produces multiple updated spec docs and new guides. Before handover, all documents must be internally consistent: field names in API-05 must match DAT-03, rate engine formulas in RATE-04 must match the worked examples in quickstart-crossborder.md, OPS-13 runbook commands must use the deployment names confirmed in 1.6-T09, REF-15 glossary must define every term used in the new ops guides. This ticket is a structured review and fix pass. It does not create new documents; it repairs inconsistencies found across the deliverables from 1.6-T01 through 1.6-T21. | • Run a cross-reference check: for each field name appearing in the API-05 endpoint schemas, verify the same name appears in DAT-03 data dictionary and REF-15 glossary; list mismatches • Run a numeric consistency check: verify the rate engine worked examples in RATE-04, quickstart-crossborder.md, and go-live-checklist.md all use the same input values and produce the same outputs (50000 KRW target_payout, treasury.usd_krw=1380, m_a=m_b=0.01, service_charge=0.36 USD -> collection_amount=37.3314 USD) • Run a runbook command check: for every kubectl or batch-cli command in the ops guides, verify the namespace and deployment name match the values confirmed in 1.6-T09 • Fix all mismatches found in steps 1-3 with targeted edits to the affected files • Produce a consistency-check-log.md in docs/as-built/ recording what was checked, mismatches found, and corrections made | consistency-check-log.md in docs/as-built/ plus all corrected cross-document inconsistencies applied to affected files | • consistency-check-log.md lists at least 3 categories checked (field names, numeric examples, runbook commands) with a findings count per category • Any field appearing in openapi-v1.json request/response schemas also appears in DAT-03 and REF-15 (spot-check 5 fields) • The cross-border worked example (collection_amount=37.3314 USD for target_payout=50000 KRW) appears identically in RATE-04, quickstart-crossborder.md, and go-live-checklist.md smoke test • No kubectl or batch-cli command in any ops guide references a placeholder namespace (e.g. <namespace>) -- all are replaced with actual values • consistency-check-log.md records zero remaining unresolved inconsistencies at the time of completion | 55 | 1.6-T05, 1.6-T06, 1.6-T09, 1.6-T11, 1.6-T18, 1.6-T21 | BA | DOC-00
2.1-T01 | shared-libs | 2.1 | 2. Architecture & Technical Foundation | Finalize system architecture & tech stack | 1 | Initialise Gradle multi-module monorepo root with Java 21 and Spring Boot 3.x BOM | GMEPay+ is built as a Gradle multi-module monorepo. The root settings.gradle declares all modules; the root build.gradle applies the Spring Boot 3.x dependency BOM and Java 21 toolchain to all subprojects. No module contains business logic yet - this ticket only sets up the skeleton so all subsequent tickets can add modules. | • Create root settings.gradle listing all module paths: shared libs (lib-money, lib-errors, lib-api-contracts, lib-events, lib-persistence) and service stubs (services/qr-service, services/smart-router, services/rate-fx, services/auth-identity, services/payment-executor, services/txn-mgmt, services/prefunding, services/notification, services/settlement, services/revenue-ledger, services/reporting, services/merchant-qr, services/scheme-adapter-zeropay, services/config-registry, services/ops-bff, services/api-gateway) • Create root build.gradle: apply io.spring.dependency-management plugin, set Spring Boot BOM to 3.3.x, java toolchain languageVersion = 21, common dependencies (spring-boot-starter, lombok, mapstruct) in subprojects block • Create gradle/wrapper/gradle-wrapper.properties pinned to Gradle 8.7 • Add .gitignore, README stub, and gradle wrapper scripts • Run ./gradlew projects to verify all modules are recognised with zero compilation errors | Root settings.gradle, root build.gradle, gradle/wrapper/gradle-wrapper.properties listing all 21 modules (5 libs + 16 services) | • ./gradlew projects lists exactly 21 subprojects with no errors • Java toolchain resolves to 21 (./gradlew -version shows JVM 21) • Spring Boot BOM version 3.3.x appears in ./gradlew dependencies output for any subproject • settings.gradle contains include statements for lib-money, lib-errors, lib-api-contracts, lib-events, lib-persistence and all 16 service modules • No module contains src/main yet - this is a skeleton-only ticket | 30 |  | ARCH | SAD-02
2.1-T02 | shared-libs | 2.1 | 2. Architecture & Technical Foundation | Finalize system architecture & tech stack | 1 | Create lib-money shared module: BigDecimal Money type with currency-aware scale | GMEPay+ stores all monetary amounts as NUMERIC in PostgreSQL and uses BigDecimal in Java. lib-money must provide a Money value object (amount: BigDecimal, currency: String) that enforces per-currency scale: KRW = 0 decimal places, USD = 2. All arithmetic uses RoundingMode.HALF_UP. Division uses at least 10 significant figures internally before rounding to final scale. This library is a dependency for every service that touches money. | • Create libs/lib-money/build.gradle with no Spring Boot starters (plain Java library, depends on jackson-databind for JSON ser/deser) • Implement Money.java: final class, BigDecimal amount, String currency (ISO-4217), factory method Money.of(BigDecimal amount, String currency) that scales to currency precision; static SCALE_MAP: KRW->0, USD->2 • Implement Money.add, Money.subtract, Money.multiply(BigDecimal factor), Money.divide(BigDecimal divisor, int internalScale) - divide uses MathContext(10, HALF_UP) internally, returns Money scaled to currency • Add CurrencyScale.java enum/registry so new currencies can be added by config without code change • Add MoneyDeserializer / MoneySerializer for Jackson | libs/lib-money/src/main/java/com/gme/pay/money/Money.java and CurrencyScale.java | • Money.of(new BigDecimal(50000.005), KRW).getAmount() equals 50000 (scale 0, HALF_UP) • Money.of(new BigDecimal(1.005), USD).getAmount() equals 1.01 (scale 2, HALF_UP) • Money.divide throws ArithmeticException if divisor is zero • Money.add(Money with different currency) throws IllegalArgumentException • Jackson round-trip: Money serialises to {amount:50000,currency:KRW} and deserialises back with correct BigDecimal scale | 45 | 2.1-T01 | ARCH | SAD-02
2.1-T03 | shared-libs | 2.1 | 2. Architecture & Technical Foundation | Finalize system architecture & tech stack | 1 | Create lib-errors shared module: canonical error envelope and exception hierarchy | All GMEPay+ services return structured error responses. The canonical error envelope is {error_code: string, message: string, txn_ref: string¦null, details: object¦null}. lib-errors defines the envelope DTO, a base GmePayException, and typed subclasses for domain errors including PARTNER_B_QUOTE_DEVIATION, PARTNER_B_QUOTE_UNAVAILABLE, INSUFFICIENT_PREFUNDING, RATE_QUOTE_EXPIRED, POOL_IDENTITY_VIOLATION. Services map these to HTTP status via a shared Spring @ControllerAdvice in this library. | • Create libs/lib-errors/build.gradle depending on spring-webmvc (compileOnly) and jackson-databind • Define ErrorEnvelope.java record: String errorCode, String message, String txnRef, Object details • Define GmePayException.java extending RuntimeException with ErrorEnvelope payload and HTTP status • Define typed subclasses: RateQuoteExpiredException (404), PartnerBQuoteDeviationException (409), PartnerBQuoteUnavailableException (503), InsufficientPrefundingException (402), PoolIdentityViolationException (500), SchemeRejectException (422), IdempotencyConflictException (409) • Add GlobalExceptionHandler.java annotated @ControllerAdvice @Order(Ordered.HIGHEST_PRECEDENCE) that maps GmePayException subclasses to ResponseEntity<ErrorEnvelope> | libs/lib-errors/src/main/java/com/gme/pay/errors/ErrorEnvelope.java, GmePayException.java, GlobalExceptionHandler.java, and all typed exception subclasses | • Throwing InsufficientPrefundingException results in HTTP 402 and errorCode INSUFFICIENT_PREFUNDING in the body • ErrorEnvelope serialises as flat JSON with no null fields omitted (use @JsonInclude(NON_NULL) for optional fields) • GlobalExceptionHandler is auto-configured via META-INF/spring/org.springframework.boot.autoconfigure.AutoConfiguration.imports so any service that imports lib-errors gets the handler automatically • Unknown RuntimeException maps to HTTP 500 with errorCode INTERNAL_ERROR (catch-all in handler) • All 7 typed exception subclasses have unique errorCode string constants defined in ErrorCodes.java | 40 | 2.1-T01 | ARCH | SAD-02
2.1-T04 | shared-libs | 2.1 | 2. Architecture & Technical Foundation | Finalize system architecture & tech stack | 1 | Create lib-api-contracts module: OpenAPI spec scaffold and generated DTOs for Partner API v1 | lib-api-contracts holds the openapi/partner-api.yaml OpenAPI 3.1 spec and generates Java DTOs via the openapi-generator Gradle plugin. DTOs are used by all services that expose or consume the Partner API. The spec must define schemas for RateQuoteRequest, RateQuoteResponse (fields: quote_ref, offer_rate, send_amount, service_charge, collection_amount, collection_usd, payout_usd_cost, validUntil), PaymentCommitRequest, PaymentCommitResponse, CpmGenerateRequest, CpmTokenResponse, ErrorEnvelope. Internal margin fields m_a, m_b, cost_rate_coll, cost_rate_pay must NOT appear in the response schema. | • Create libs/lib-api-contracts/build.gradle with openapi-generator-gradle-plugin 7.x configured to generate model classes only (generateModelTests=false, generateApiTests=false, library=spring) into build/generated • Create openapi/partner-api.yaml with info block (version 1.0.0), servers placeholder, and schemas for: RateQuoteRequest, RateQuoteResponse, PaymentCommitRequest, PaymentCommitResponse, CpmGenerateRequest, CpmTokenResponse, ErrorEnvelope - all fields typed as string/number with format annotations • Configure generation to use jackson, with BigDecimal for monetary fields and OffsetDateTime for timestamps • Wire compileJava to depend on openApiGenerate so generated sources are on the classpath • Verify ./gradlew :lib-api-contracts:build produces JAR with all DTO classes | libs/lib-api-contracts/openapi/partner-api.yaml and configured build producing DTOs in com.gme.pay.api.contracts package | • ./gradlew :lib-api-contracts:build succeeds with no compilation errors • RateQuoteResponse class exists with fields: quoteRef (String), offerRate (BigDecimal), sendAmount (BigDecimal), serviceCharge (BigDecimal), collectionAmount (BigDecimal), collectionUsd (BigDecimal), payoutUsdCost (BigDecimal), validUntil (OffsetDateTime) • Internal fields m_a, m_b, cost_rate_coll, cost_rate_pay are NOT present in RateQuoteResponse DTO • Generated classes are in the JAR and importable from another module in the monorepo • ErrorEnvelope DTO fields align with lib-errors ErrorEnvelope (errorCode, message, txnRef, details) | 45 | 2.1-T01, 2.1-T03 | ARCH | SAD-02
2.1-T05 | shared-libs | 2.1 | 2. Architecture & Technical Foundation | Finalize system architecture & tech stack | 1 | Create lib-events module: domain event base class, EventPublisher interface, and 6 event schemas | lib-events defines domain events used in the transactional Outbox pattern (Phase 1). Kafka is the deferred transport (Phase 2); Phase 1 uses an in-process EventPublisher interface backed by outbox-polling. Events: TransactionStateChangedEvent (txnRef, previousState, newState, partnerId, schemeId), PrefundingDeductedEvent, PrefundingLowBalanceEvent, WebhookDispatchRequestedEvent, SettlementBatchTriggerEvent, MerchantSyncInboundEvent. Each event has: eventId (UUID), eventType (String), occurredAt (Instant), aggregateId (String). Avro schemas mirror Java classes. | • Create libs/lib-events/build.gradle with jackson-databind and avro 1.11 for .avsc schema files • Define DomainEvent.java abstract base: UUID eventId, String eventType, Instant occurredAt, String aggregateId • Implement 6 typed event subclasses with strongly-typed payload fields as listed in context • Define EventPublisher.java interface with single method: void publish(DomainEvent event) • Implement InProcessEventPublisher.java @Component @Primary: stores events in a CopyOnWriteArrayList for test inspection; add getPublishedEvents() and clearPublishedEvents() test helpers • Create avro/ directory with 6 .avsc schema files mirroring Java class field names and types | libs/lib-events/src/main/java/com/gme/pay/events/ with DomainEvent.java, EventPublisher.java, InProcessEventPublisher.java, and 6 typed event classes; 6 .avsc schema files | • EventPublisher interface has exactly one method: void publish(DomainEvent event) - Kafka can be wired behind this interface without changing callers • TransactionStateChangedEvent payload includes: txnRef, previousState, newState, partnerId, schemeId (all String) • All 6 event classes are Jackson-serialisable to valid JSON (round-trip test with ObjectMapper) • Each .avsc file matches the corresponding Java class field names and types • InProcessEventPublisher.getPublishedEvents() returns all events published in a test; clearPublishedEvents() resets the list | 40 | 2.1-T01 | ARCH | SAD-02
2.1-T06 | shared-libs | 2.1 | 2. Architecture & Technical Foundation | Finalize system architecture & tech stack | 1 | Create lib-persistence module: JPA auto-config, Flyway base path convention, and AuditableEntity | lib-persistence is a shared Spring Boot auto-configuration library providing: JPA base configuration (PostgreSQL 16 dialect, Hibernate 6, NUMERIC for BigDecimal), Flyway migration base path convention (each service has classpath:db/migration), and AuditableEntity base class (@MappedSuperclass with createdAt, updatedAt, createdBy populated via Spring Data auditing). All money columns map to NUMERIC(38,10) via Hibernate custom type. Services import this lib and get consistent JPA/Flyway setup without extra annotations. | • Create libs/lib-persistence/build.gradle depending on spring-boot-starter-data-jpa, flyway-core, postgresql driver • Define PersistenceAutoConfiguration.java @AutoConfiguration configuring HibernateJpaVendorAdapter with PostgreSQL16Dialect and spring.jpa.properties for NUMERIC column mapping • Define AuditableEntity.java @MappedSuperclass with @CreatedDate Instant createdAt, @LastModifiedDate Instant updatedAt, @CreatedBy String createdBy (from SecurityContext) • Register auto-configuration in META-INF/spring/org.springframework.boot.autoconfigure.AutoConfiguration.imports • Add FlywayMigrationStrategy bean that logs migration count; services configure spring.flyway.locations=classpath:db/migration in their own application.yaml | libs/lib-persistence/src/main/java/com/gme/pay/persistence/PersistenceAutoConfiguration.java and AuditableEntity.java | • A service that imports lib-persistence and provides spring.datasource.* gets Hibernate + Flyway auto-configured with no additional @EnableJpa annotation • AuditableEntity.createdAt is populated automatically on persist (verified in @DataJpaTest with Testcontainers Postgres 16) • Money BigDecimal fields mapped as NUMERIC(38,10) in DDL (verify via Hibernate schema export) • Flyway picks up V*.sql from classpath:db/migration without additional service config • lib-persistence does NOT instantiate a DataSource itself; it only configures one when connection properties are present (conditional @Bean) | 40 | 2.1-T01, 2.1-T02 | ARCH | SAD-02
2.1-T07 | shared-libs | 2.1 | 2. Architecture & Technical Foundation | Finalize system architecture & tech stack | 1 | Author ADR-001: Gradle multi-module monorepo and shared library strategy | ADR-001 documents the decision to use a Gradle 8.x multi-module monorepo with Java 21 and Spring Boot 3.x BOM. The 5 shared libs (lib-money, lib-errors, lib-api-contracts, lib-events, lib-persistence) have defined boundaries. The constraint: services must not compile-depend on each other - only on shared libs or communicate via HTTP/domain events. OpenTelemetry auto-instrumentation is inherited by all services from the root BOM. | • Create docs/adr/ADR-001-monorepo-gradle-shared-libs.md using standard ADR template: Title, Status (Accepted), Context, Decision, Consequences • State decision: Gradle 8.7 multi-module; Java 21 LTS; Spring Boot 3.3.x BOM at root; 5 shared libs with defined responsibilities; inter-service communication only via REST or domain events (no compile-time service-to-service dependency) • List all 5 shared libs with their responsibilities in the Decision section • State consequences: single build graph enables atomic cross-module refactors; shared lib changes require all dependent services to be retested; lib-money is the sole source of monetary arithmetic truth • Include a module dependency graph showing libs -> services direction only (Mermaid or ASCII) • Add entry to docs/adr/README.md ADR index | docs/adr/ADR-001-monorepo-gradle-shared-libs.md | • ADR status is Accepted • Decision section names all 5 shared libs with one-line responsibilities • Consequences section states the constraint: no compile-time service-to-service dependency • Dependency graph shows arrows from services to libs only (not service to service) • docs/adr/README.md lists ADR-001 with title and date | 25 | 2.1-T01 | ARCH | SAD-02
2.1-T08 | shared-libs | 2.1 | 2. Architecture & Technical Foundation | Finalize system architecture & tech stack | 1 | Author ADR-002: Polyglot persistence strategy (PostgreSQL 16, MongoDB, Redis 7, Object Storage) | GMEPay+ uses 4 datastores. PostgreSQL 16: all money-critical paths (transactions, ledger, prefunding, config, audit) using NUMERIC columns and SELECT FOR UPDATE for atomic prefunding deduction. MongoDB 7: merchant/QR store and CQRS read-model projections (variable schema, high read volume). Redis 7: ephemeral caching with TTL (rate quotes 60-300s, idempotency keys 24h, config hot cache 300s). S3-compatible/MinIO: ZP00xx batch file archival, BOK reports, settlement exports. ADR-002 documents service-to-store ownership and the constraint against cross-service DB access. | • Create docs/adr/ADR-002-polyglot-persistence.md with standard ADR template • State decision with technology versions: PostgreSQL 16 (money path), MongoDB 7 (merchant/QR CQRS), Redis 7 (ephemeral cache), S3-compatible/MinIO (object storage) • Document service-to-store ownership: payment-executor, txn-mgmt, prefunding, settlement, config-registry own PostgreSQL schemas; merchant-qr owns MongoDB; api-gateway and rate-fx own Redis; scheme-adapter-zeropay writes to Object Storage • State rationale for NUMERIC over FLOAT: monetary precision, pool identity invariant requires exact decimal arithmetic within 0.01 USD tolerance • State constraint: no service accesses another service data store directly (enforced at network level) • Add to docs/adr/README.md index | docs/adr/ADR-002-polyglot-persistence.md | • All 4 store types named with concrete technology versions (PostgreSQL 16, Redis 7, MongoDB 7, S3-compatible/MinIO) • Service ownership table is present and covers all 16 services • Constraint against cross-service DB access is explicitly stated • Rationale for NUMERIC (not FLOAT) is stated with reference to pool identity invariant (tolerance 0.01 USD) • ADR cross-references ADR-001 | 25 | 2.1-T07 | ARCH | SAD-02
2.1-T09 | shared-libs | 2.1 | 2. Architecture & Technical Foundation | Finalize system architecture & tech stack | 1 | Author ADR-003: Transactional Outbox pattern for domain events; Kafka deferred to integration phase | Phase 1 domain events are written to an outbox_events table in the same PostgreSQL transaction as the state change, then polled and dispatched via InProcessEventPublisher (lib-events). Kafka is introduced in the integration phase behind the EventPublisher interface without rework. Outbox table: id UUID PK, aggregate_id VARCHAR(64), event_type VARCHAR(128), payload JSONB, created_at TIMESTAMPTZ, processed_at TIMESTAMPTZ, retry_count INT. Ordering: by created_at. Delivery guarantee: at-least-once; consumers must be idempotent on eventId. | • Create docs/adr/ADR-003-transactional-outbox-kafka-deferred.md with standard ADR template • State decision: Phase 1 uses transactional Outbox in PostgreSQL; a @Scheduled poller in each service reads unprocessed rows (WHERE processed_at IS NULL ORDER BY created_at) and calls EventPublisher.publish() • State Phase 2 migration path: replace InProcessEventPublisher with KafkaEventPublisher implementing the same interface; outbox becomes the Kafka producer buffer (Debezium CDC or polling relay) • Include the outbox table DDL as a code block (CREATE TABLE outbox_events with all 7 columns) for reference • Document at-least-once guarantee and requirement that consumers are idempotent on eventId UUID • Add to ADR index | docs/adr/ADR-003-transactional-outbox-kafka-deferred.md with outbox table DDL snippet | • Phase 1 vs Phase 2 boundary is clearly stated with interface isolation point named (EventPublisher) • Outbox table schema includes all 7 columns: id, aggregate_id, event_type, payload, created_at, processed_at, retry_count • At-least-once delivery guarantee and idempotency requirement on consumers are explicitly stated • Migration path to Kafka requires zero changes to event producers (only the EventPublisher implementation changes) • ADR cross-references lib-events EventPublisher interface | 25 | 2.1-T05, 2.1-T08 | ARCH | SAD-02
2.1-T10 | shared-libs | 2.1 | 2. Architecture & Technical Foundation | Finalize system architecture & tech stack | 1 | Author ADR-004: Spring Cloud Gateway as Northbound API edge with HMAC-SHA256 and rate limiting | Spring Cloud Gateway (spring-cloud-starter-gateway) is the single entry point for all Partner API traffic. It enforces: TLS 1.2+ termination (by upstream load balancer), per-partner HMAC-SHA256 request signature validation (X-GME-Signature header), Idempotency-Key header on POST requests, per-partner rate limiting via Redis token bucket (Spring Cloud Gateway RequestRateLimiter), and structured access logging with txn_ref/partner_id MDC fields. ADR-004 documents the choice over Kong/AWS API GW and the filter chain order. | • Create docs/adr/ADR-004-spring-cloud-gateway-hmac-auth.md with standard ADR template • State decision: Spring Cloud Gateway chosen to keep entire stack in-JVM, enabling shared lib-errors and lib-events without polyglot bridge; trade-off acknowledged (higher JVM memory vs Kong plugin ecosystem) • Document Gateway filter chain order: 1) HmacSignatureFilter (custom GlobalFilter) validates X-GME-Signature, returns 401 on failure; 2) IdempotencyKeyFilter enforces Idempotency-Key on POST/PUT, returns 422 on absence; 3) RateLimitFilter (RequestRateLimiter with Redis backend); 4) route to downstream service • State security constraint: requests failing HMAC return 401 before any downstream service is called • Add to ADR index | docs/adr/ADR-004-spring-cloud-gateway-hmac-auth.md | • Decision rationale explicitly compares Spring Cloud Gateway vs Kong and states the in-JVM rationale • Filter chain order lists all 3 filters with their sequence number • HMAC-SHA256 is named as algorithm; X-GME-Signature as header name • Redis is named as the rate-limit state store (RequestRateLimiter backend) • ADR states downstream services trust the Gateway and do not re-validate HMAC | 25 | 2.1-T07 | ARCH | SAD-02
2.1-T11 | shared-libs | 2.1 | 2. Architecture & Technical Foundation | Finalize system architecture & tech stack | 1 | Create Flyway migration V1 for outbox_events table in services/txn-mgmt | The transactional Outbox table (ADR-003) lives in the txn-mgmt PostgreSQL schema. The outbox_events table has: id UUID DEFAULT gen_random_uuid() PRIMARY KEY, aggregate_id VARCHAR(64) NOT NULL, event_type VARCHAR(128) NOT NULL, payload JSONB NOT NULL, created_at TIMESTAMPTZ NOT NULL DEFAULT now(), processed_at TIMESTAMPTZ, retry_count INT NOT NULL DEFAULT 0. A partial index on (created_at) WHERE processed_at IS NULL powers the poller query. | • Create services/txn-mgmt/src/main/resources/db/migration/V1__create_outbox_events.sql • Write CREATE TABLE outbox_events with all 7 columns as specified in context • Add partial index: CREATE INDEX idx_outbox_pending ON outbox_events (created_at) WHERE processed_at IS NULL • Create TxnMgmtApplication.java @SpringBootApplication • Create FlywayMigrationIT.java using @SpringBootTest + Testcontainers postgres:16: assert migration runs cleanly, table exists, index exists • Assert inserting a row without id populates UUID via gen_random_uuid() | services/txn-mgmt/src/main/resources/db/migration/V1__create_outbox_events.sql and FlywayMigrationIT.java | • Flyway V1 applies without error on a clean PostgreSQL 16 Testcontainer • outbox_events table has all 7 columns with correct types (UUID, VARCHAR, JSONB, TIMESTAMPTZ, INT) • Partial index idx_outbox_pending covers only rows WHERE processed_at IS NULL (verified via psql meta-query) • Inserting a row without explicit id results in non-null UUID (gen_random_uuid() default) • Running Flyway migrate twice does not error (idempotent via checksum) | 35 | 2.1-T06, 2.1-T09 | ARCH | SAD-02
2.1-T12 | shared-libs | 2.1 | 2. Architecture & Technical Foundation | Finalize system architecture & tech stack | 1 | Create Flyway migration V1 for config schema in services/config-registry: schemes, partners, rules, audit_log | Config/Registry stores Scheme, Partner, Rule, and audit log in PostgreSQL 16. Scheme: id UUID PK, scheme_code VARCHAR UNIQUE, display_name VARCHAR, supported_modes VARCHAR[], payout_currency CHAR(3), active BOOLEAN, created_at TIMESTAMPTZ, updated_at TIMESTAMPTZ. Partner: id UUID PK, partner_code VARCHAR UNIQUE, type VARCHAR CHECK IN (LOCAL,OVERSEAS), webhook_url TEXT, rate_quote_ttl_seconds INT CHECK 60..1800, active BOOLEAN, created_at, updated_at. Rule: id UUID PK, partner_id UUID FK, scheme_id UUID FK, direction VARCHAR CHECK IN (Inbound,Outbound,Domestic,Hub), margin_a NUMERIC(8,6), margin_b NUMERIC(8,6), service_charge_amount NUMERIC(18,6), service_charge_currency CHAR(3), rate_source_coll VARCHAR, rate_source_pay VARCHAR, active BOOLEAN, effective_from TIMESTAMPTZ, effective_to TIMESTAMPTZ (NULL = open-ended). Soft-delete via effective_to. config_audit_log: id UUID PK DEFAULT gen_random_uuid(), table_name VARCHAR, record_id UUID, actor VARCHAR, changed_at TIMESTAMPTZ DEFAULT now(), previous_value JSONB, new_value JSONB. | • Create services/config-registry/src/main/resources/db/migration/V1__create_config_schema.sql • Write CREATE TABLE schemes with columns and UNIQUE on scheme_code • Write CREATE TABLE partners with CHECK (type IN (LOCAL,OVERSEAS)), CHECK (rate_quote_ttl_seconds BETWEEN 60 AND 1800) • Write CREATE TABLE rules with FK to schemes and partners, CHECK (direction IN (Inbound,Outbound,Domestic,Hub)), CHECK (margin_a >= 0 AND margin_b >= 0) • Write CREATE TABLE config_audit_log with all columns • Add indexes: rules(partner_id, scheme_id, direction), config_audit_log(record_id, changed_at) | services/config-registry/src/main/resources/db/migration/V1__create_config_schema.sql | • All 4 tables created without error on PostgreSQL 16 Testcontainer • CHECK constraint on partners.type rejects insert with type=AGGREGATOR • CHECK constraint on rules.direction rejects insert with direction=Unknown • CHECK on partners.rate_quote_ttl_seconds rejects values < 60 and > 1800 • Soft-delete query SELECT * FROM rules WHERE effective_to IS NULL OR effective_to > now() returns only active rules | 40 | 2.1-T06 | ARCH | SAD-02
2.1-T13 | shared-libs | 2.1 | 2. Architecture & Technical Foundation | Finalize system architecture & tech stack | 1 | Scaffold services/config-registry: ConfigRegistryApplication, Rule JPA entity, Redis cache layer | services/config-registry is a Spring Boot 3.x service using lib-persistence (PostgreSQL 16 via JPA) and Redis 7 as hot cache. ConfigCacheService fetches Rule by (partnerId, schemeId, direction): checks Redis key rule:{partnerId}:{schemeId}:{direction} (TTL 300s) first, falls back to PostgreSQL via RuleRepository, writes through on cache miss. Config changes call redisTemplate.delete(cacheKey) to invalidate. On rule update, ConfigChangeService publishes a ConfigChangedEvent via EventPublisher (lib-events). | • Create services/config-registry/build.gradle: spring-boot-starter-web, spring-boot-starter-data-jpa, spring-boot-starter-data-redis, lib-persistence, lib-errors, lib-events • Create ConfigRegistryApplication.java @SpringBootApplication • Create Rule.java @Entity mapping to rules table; RuleRepository.java extends JpaRepository with findByPartnerIdAndSchemeIdAndDirectionAndActiveTrueAndEffectiveToIsNull • Create ConfigCacheService.java @Service: getRuleOrLoad(partnerId, schemeId, direction) checks Redis, on miss loads from JPA and SETs with 300s TTL • Create ConfigChangeService.java @Service: on rule update/deactivate, delete Redis key and publish ConfigChangedEvent via EventPublisher • Add application.yaml: spring.datasource, spring.data.redis, spring.flyway.locations=classpath:db/migration | services/config-registry/src/main/java/com/gme/pay/configregistry/ConfigCacheService.java and ConfigChangeService.java | • Cache miss: ConfigCacheService queries PostgreSQL and writes result to Redis (verify with RedisTemplate.hasKey after first call in @SpringBootTest) • Cache hit: second call does not hit DB (mock RuleRepository, assert zero interactions on cache hit) • Redis TTL on rule cache key is 300 seconds (redisTemplate.getExpire returns 295-300s) • Config change invalidates Redis key: after ConfigChangeService.deactivateRule(), redisTemplate.hasKey returns false • ConfigRegistryApplication starts against Testcontainers Postgres 16 + Redis 7 with Flyway V1 applied | 45 | 2.1-T12, 2.1-T03, 2.1-T05, 2.1-T06 | ARCH | SAD-02
2.1-T14 | shared-libs | 2.1 | 2. Architecture & Technical Foundation | Finalize system architecture & tech stack | 1 | Create Flyway migration V1 for treasury_rates table in services/rate-fx | services/rate-fx hosts the Rate and FX Engine. The treasury_rates table stores treasury.usd_{ccy} rates (units of local currency per 1 USD). Schema: id UUID PK DEFAULT gen_random_uuid(), currency_code CHAR(3) NOT NULL, rate_key VARCHAR(32) NOT NULL UNIQUE e.g. usd_krw, units_per_usd NUMERIC(18,8) NOT NULL CHECK (units_per_usd > 0), source VARCHAR CHECK IN (MANUAL,LIVE), effective_at TIMESTAMPTZ NOT NULL, created_by VARCHAR(128) NOT NULL, created_at TIMESTAMPTZ DEFAULT now(). Example: rate_key=usd_krw, units_per_usd=1380.00 means 1 USD = 1380 KRW. | • Create services/rate-fx/src/main/resources/db/migration/V1__create_treasury_rates.sql • Write CREATE TABLE treasury_rates with all columns; CHECK (units_per_usd > 0); CHECK (source IN (MANUAL,LIVE)) • Add index on (rate_key, effective_at DESC) for latest-rate query • Create RateFxApplication.java @SpringBootApplication • Create TreasuryRate.java @Entity and TreasuryRateRepository.java with findTopByRateKeyOrderByEffectiveAtDesc(String rateKey) • Create FlywayMigrationIT.java using Testcontainers Postgres 16: assert migration runs cleanly, index exists, CHECK constraint rejects units_per_usd=0 | services/rate-fx/src/main/resources/db/migration/V1__create_treasury_rates.sql and TreasuryRateRepository.java | • V1 migration applies cleanly on PostgreSQL 16 Testcontainer • CHECK constraint rejects insert with units_per_usd = 0 and units_per_usd = -1 • findTopByRateKeyOrderByEffectiveAtDesc(usd_krw) returns the row with the most recent effective_at when multiple rows exist • rate_key usd_krw convention documented in a SQL comment in the migration file • RateFxApplication starts against Testcontainers Postgres 16 with Flyway applied | 35 | 2.1-T06, 2.1-T12 | ARCH | SAD-02
2.1-T15 | shared-libs | 2.1 | 2. Architecture & Technical Foundation | Finalize system architecture & tech stack | 1 | Create Flyway migration V1 for transactions table in services/payment-executor | services/payment-executor hosts the Transaction Orchestrator. The transactions table stores the full payment lifecycle. Columns: id UUID PK, txn_ref VARCHAR(64) UNIQUE NOT NULL, partner_id UUID NOT NULL, scheme_id UUID NOT NULL, direction VARCHAR NOT NULL, state VARCHAR NOT NULL CHECK IN (QUOTED,PENDING_DEBIT,DEBITED,SCHEME_SENT,APPROVED,UNCERTAIN,FAILED,REVERSED,REFUNDED), quote_ref VARCHAR(64), idempotency_key VARCHAR(256) UNIQUE, target_payout_value NUMERIC(18,6), target_payout_currency CHAR(3), collection_usd NUMERIC(18,8), payout_usd_cost NUMERIC(18,8), collection_margin_usd NUMERIC(18,8), payout_margin_usd NUMERIC(18,8), send_amount_value NUMERIC(18,6), send_amount_currency CHAR(3), service_charge_value NUMERIC(18,6), service_charge_currency CHAR(3), collection_amount_value NUMERIC(18,6), collection_amount_currency CHAR(3), offer_rate_coll NUMERIC(18,8), cross_rate NUMERIC(18,8), rate_locked_at TIMESTAMPTZ, scheme_approval_code VARCHAR(64), created_at TIMESTAMPTZ DEFAULT now(), updated_at TIMESTAMPTZ. | • Create services/payment-executor/src/main/resources/db/migration/V1__create_transactions.sql • Write CREATE TABLE transactions with all 28 columns; CHECK (state IN (QUOTED,PENDING_DEBIT,DEBITED,SCHEME_SENT,APPROVED,UNCERTAIN,FAILED,REVERSED,REFUNDED)) • Add UNIQUE index on idempotency_key, index on (partner_id, state, created_at), index on scheme_approval_code • Create PaymentExecutorApplication.java @SpringBootApplication • Create Transaction.java @Entity mapping all columns • Create TransactionRepository.java with findByTxnRef and findByIdempotencyKey queries • Add FlywayMigrationIT.java with Testcontainers Postgres 16 asserting migration applies and all constraints hold | services/payment-executor/src/main/resources/db/migration/V1__create_transactions.sql and Transaction.java @Entity | • V1 migration applies cleanly on Postgres 16 Testcontainer • CHECK constraint rejects insert with state=PROCESSING • UNIQUE constraint on idempotency_key rejects duplicate insert • Rate-lock columns (collection_usd, offer_rate_coll etc.) are NULL on a newly inserted QUOTED row • All 9 valid state values (QUOTED through REFUNDED) individually pass the CHECK constraint | 40 | 2.1-T06, 2.1-T12 | ARCH | SAD-02
2.1-T16 | shared-libs | 2.1 | 2. Architecture & Technical Foundation | Finalize system architecture & tech stack | 1 | Create Flyway migration V1 for prefunding tables and PrefundingService with SELECT FOR UPDATE | services/prefunding manages OVERSEAS partner prefunding balances atomically. Tables: prefunding_balances (id UUID PK, partner_id UUID UNIQUE NOT NULL, balance_usd NUMERIC(18,8) NOT NULL DEFAULT 0 CHECK (balance_usd >= 0), low_balance_threshold_usd NUMERIC(18,8) NOT NULL DEFAULT 10000, last_deducted_at TIMESTAMPTZ, version BIGINT NOT NULL DEFAULT 0); prefunding_transactions (id UUID PK DEFAULT gen_random_uuid(), partner_id UUID NOT NULL, txn_ref VARCHAR(64) NOT NULL, operation VARCHAR CHECK IN (DEBIT,CREDIT,TOPUP), amount_usd NUMERIC(18,8) NOT NULL, balance_after_usd NUMERIC(18,8) NOT NULL, created_at TIMESTAMPTZ DEFAULT now()). PrefundingService.deductBalance uses @Lock(PESSIMISTIC_WRITE) = SELECT FOR UPDATE. Insufficient balance throws InsufficientPrefundingException (HTTP 402, errorCode INSUFFICIENT_PREFUNDING) from lib-errors. | • Create services/prefunding/src/main/resources/db/migration/V1__create_prefunding.sql with both tables and CHECK (balance_usd >= 0) • Create PrefundingApplication.java @SpringBootApplication • Create PrefundingBalance.java @Entity, PrefundingTransaction.java @Entity • Create PrefundingRepository.java with @Lock(LockModeType.PESSIMISTIC_WRITE) on findByPartnerId for the deduction path • Create PrefundingService.java @Service @Transactional: deductBalance(UUID partnerId, BigDecimal amountUsd) - lock row, subtract, assert >= 0 or throw InsufficientPrefundingException, save, write prefunding_transactions row with operation=DEBIT | services/prefunding/src/main/resources/db/migration/V1__create_prefunding.sql and PrefundingService.java | • deductBalance of 100.00 USD from 500.00 USD balance leaves balance_after = 400.00 (@DataJpaTest + Testcontainers Postgres 16) • deductBalance of 600.00 USD from 500.00 USD throws InsufficientPrefundingException and rolls back (balance remains 500.00) • CHECK (balance_usd >= 0) prevents direct negative balance insert at DB level • prefunding_transactions row is written with operation=DEBIT, correct amount_usd and balance_after_usd • @Lock(PESSIMISTIC_WRITE) annotation is present on the repository method (verify via reflection or code review) | 50 | 2.1-T06, 2.1-T03, 2.1-T12 | ARCH | SAD-02
2.1-T17 | shared-libs | 2.1 | 2. Architecture & Technical Foundation | Finalize system architecture & tech stack | 1 | Scaffold services/scheme-adapter-zeropay: SchemeAdapter interface and ZeroPaySchemeAdapter skeleton | services/scheme-adapter-zeropay implements the ZeroPay protocol behind a scheme-agnostic SchemeAdapter interface. Interface methods: CpmAuthResponse authoriseCpm(CpmAuthRequest), MpmSubmitResponse submitMpm(MpmSubmitRequest), void generateBatchFile(BatchType, LocalDate), BatchRecord[] parseBatchFile(BatchType, byte[]), AdapterHealth healthCheck(), String getSchemeCode(). ZeroPaySchemeAdapter implements all methods (stub throwing UnsupportedOperationException for batch methods - to be implemented in scheme-specific tickets). Credentials (cpmApiUrl, sftpHost, sftpUser, sftpPassword) injected from Vault/env via @ConfigurationProperties - never hardcoded. | • Create services/scheme-adapter-zeropay/build.gradle: spring-boot-starter-web, commons-net (SFTP), lib-errors, lib-events • Define SchemeAdapter.java interface with all 6 method signatures including getSchemeCode() • Implement ZeroPaySchemeAdapter.java @Service implementing SchemeAdapter; getSchemeCode() returns ZEROPAY; stub remaining methods • Create ZeroPayProperties.java @ConfigurationProperties(prefix=zeropay): cpmApiUrl, sftpHost, sftpPort, sftpUser, sftpPassword (all String, no defaults for credentials) • Create SchemeAdapterApplication.java @SpringBootApplication • Add WireMock @SpringBootTest test: mock 한결원 CPM endpoint returns 200 JSON; assert authoriseCpm parses CpmAuthResponse without exception | services/scheme-adapter-zeropay/src/main/java/com/gme/pay/zeropay/SchemeAdapter.java and ZeroPaySchemeAdapter.java | • SchemeAdapter interface has exactly 6 method signatures including getSchemeCode() • ZeroPaySchemeAdapter.getSchemeCode() returns the string ZEROPAY • ZeroPayProperties binds zeropay.cpm-api-url from application.yaml without error • No SFTP credentials appear in source code or application.yaml (only env placeholder references like ${ZEROPAY_SFTP_PASSWORD}) • WireMock test: authoriseCpm with mocked 200 response parses to CpmAuthResponse without exception | 45 | 2.1-T01, 2.1-T03, 2.1-T05 | ARCH | SAD-02
2.1-T18 | shared-libs | 2.1 | 2. Architecture & Technical Foundation | Finalize system architecture & tech stack | 1 | Scaffold services/api-gateway: Spring Cloud Gateway with HmacSignatureFilter and IdempotencyKeyFilter | services/api-gateway is a Spring Cloud Gateway 4.x application. This ticket creates the gateway with route stubs and two global filters: HmacSignatureFilter validates X-GME-Signature = HMAC-SHA256(partnerSecret, canonicalString) where canonicalString = METHOD + LF + path + LF + sha256(body) + LF + X-GME-Timestamp; returns 401 ErrorEnvelope on mismatch. IdempotencyKeyFilter requires Idempotency-Key header on all POST/PUT requests; returns 422 with errorCode MISSING_IDEMPOTENCY_KEY if absent. For this ticket, use a hardcoded test secret; real lookup from auth-identity is wired in T19. | • Create services/api-gateway/build.gradle: spring-cloud-starter-gateway, spring-boot-starter-data-redis, lib-errors • Create ApiGatewayApplication.java @SpringBootApplication • Create HmacSignatureFilter.java implements GlobalFilter, Ordered: extract X-GME-Signature and X-GME-Partner-Id; compute expected HMAC-SHA256 over canonical string; constant-time compare; return 401 on mismatch • Create IdempotencyKeyFilter.java implements GlobalFilter, Ordered: on POST/PUT, if Idempotency-Key absent return 422 • Create application.yaml with spring.cloud.gateway.routes stubs pointing to localhost placeholders for each backend service • Write HmacSignatureFilterTest.java using MockServerWebExchange: valid signature passes, tampered signature returns 401, missing Idempotency-Key on POST returns 422 | services/api-gateway/src/main/java/com/gme/pay/gateway/HmacSignatureFilter.java and IdempotencyKeyFilter.java | • Valid HMAC-SHA256 signature passes filter and request proceeds (mock downstream returns 200) • Tampered signature (single character change) returns 401 with errorCode INVALID_SIGNATURE • POST without Idempotency-Key returns 422 with errorCode MISSING_IDEMPOTENCY_KEY • GET without Idempotency-Key passes IdempotencyKeyFilter without error • HmacSignatureFilter.getOrder() returns lower integer than IdempotencyKeyFilter.getOrder() (HMAC checked first) | 50 | 2.1-T03, 2.1-T04, 2.1-T10 | ARCH | SAD-02
2.1-T19 | shared-libs | 2.1 | 2. Architecture & Technical Foundation | Finalize system architecture & tech stack | 1 | Scaffold services/auth-identity: partner credential store and HMAC secret resolution endpoint | services/auth-identity stores partner API credentials. Schema: partner_credentials (id UUID PK, partner_id UUID UNIQUE NOT NULL, api_key VARCHAR(64) UNIQUE NOT NULL, hmac_secret_hash VARCHAR(128) NOT NULL as BCrypt hash, active BOOLEAN DEFAULT true, created_at TIMESTAMPTZ DEFAULT now()). AuthIdentityService: generateCredentials(UUID partnerId) returns new api_key + raw hmac_secret (stored as BCrypt hash, never retrievable after generation); resolveHmacSecretHash(String apiKey) returns hash for HMAC validation; resolvePartnerId(String apiKey) returns partnerId UUID. Internal endpoints only - not exposed on public Partner API route. Wire api-gateway HmacSignatureFilter to call GET /internal/auth/resolve?apiKey=... via RestClient. | • Create services/auth-identity/src/main/resources/db/migration/V1__create_partner_credentials.sql • Create AuthIdentityApplication.java @SpringBootApplication • Create PartnerCredentials.java @Entity mapping to partner_credentials table • Create AuthIdentityService.java @Service with generateCredentials, resolveHmacSecretHash, resolvePartnerId methods • Create AuthIdentityController.java @RestController: POST /internal/auth/credentials, GET /internal/auth/resolve?apiKey=... • Wire HmacSignatureFilter in api-gateway to call auth-identity via RestClient (inject URL from zeropay.auth-identity.url config) | services/auth-identity/src/main/java/com/gme/pay/auth/AuthIdentityService.java and AuthIdentityController.java | • generateCredentials stores BCrypt hash starting with $2a$ (never plaintext) • resolveHmacSecretHash returns empty Optional for unknown apiKey (gateway treats as 401) • api_key UNIQUE constraint prevents duplicate registration (PSQLException on duplicate insert) • GET /internal/auth/resolve?apiKey=unknown returns 404 with errorCode CREDENTIAL_NOT_FOUND • AuthIdentityController endpoints are NOT reachable through the public partner-facing Gateway route (only internal route) | 45 | 2.1-T06, 2.1-T12, 2.1-T18 | ARCH | SAD-02
2.1-T20 | shared-libs | 2.1 | 2. Architecture & Technical Foundation | Finalize system architecture & tech stack | 1 | Implement RateEngine core: 5-step USD pool computation with same-currency short-circuit | RateEngine in services/rate-fx executes payout-first RECEIVE-mode computation. Inputs: targetPayout (BigDecimal), payoutCurrency (String), costRatePay (BigDecimal = treasury.usd_{settle_b_ccy}), costRateColl (BigDecimal = treasury.usd_{settle_a_ccy}), marginA (BigDecimal fraction), marginB (BigDecimal fraction), serviceCharge (BigDecimal in settle_A ccy). Steps: 1) payoutUsdCost = targetPayout / costRatePay; 2) collectionUsd = payoutUsdCost / (1 - marginA - marginB); 3) collectionMarginUsd = collectionUsd * marginA; payoutMarginUsd = collectionUsd * marginB; 4) sendAmount = collectionUsd * costRateColl; 5) collectionAmount = sendAmount + serviceCharge. Pool identity: ¦collectionUsd - collectionMarginUsd - payoutMarginUsd - payoutUsdCost¦ <= 0.01 USD; if violated throw PoolIdentityViolationException. Same-currency short-circuit: if all currencies match, collectionAmount = targetPayout + serviceCharge (skip USD pool). BOK derived: offerRateColl = sendAmount / (collectionUsd - collectionMarginUsd); crossRate = targetPayout / sendAmount. All division uses MathContext(10, HALF_UP). | • Create services/rate-fx/src/main/java/com/gme/pay/ratefx/engine/RateEngine.java @Service • Implement computeQuote(RateQuoteInput input) returning RateQuoteResult record with all computed fields • Add same-currency short-circuit: if all 4 currencies are equal, return collectionAmount = targetPayout + serviceCharge with USD pool fields null • Verify pool identity after step 3; throw PoolIdentityViolationException from lib-errors if ¦delta¦ > 0.01 • Derive BOK fields offerRateColl and crossRate after step 4 • Use MathContext(10, HALF_UP) for all BigDecimal division operations | services/rate-fx/src/main/java/com/gme/pay/ratefx/engine/RateEngine.java | • Cross-border test: targetPayout=50000, costRatePay=1.0, costRateColl=1380.0, marginA=0.015, marginB=0.01, serviceCharge=0; payoutUsdCost=50000.0, collectionUsd=50000/0.975=51282.0512..., sendAmount=51282.0512*1380=70769030...; pool identity holds within 0.01 USD • Same-currency test: targetPayout=10000 KRW, all currencies KRW, serviceCharge=500; collectionAmount=10500, USD pool fields all null • Pool identity violation: inject marginA=0.99; assert PoolIdentityViolationException is thrown • Service charge outside pool: vary serviceCharge 0 vs 500; assert collectionUsd is identical in both cases • Division uses MathContext(10, HALF_UP): no ArithmeticException on non-terminating decimal (1/3 etc.) | 55 | 2.1-T14, 2.1-T02, 2.1-T03 | ARCH | SAD-02
2.1-T21 | shared-libs | 2.1 | 2. Architecture & Technical Foundation | Finalize system architecture & tech stack | 1 | Implement RateQuoteService in rate-fx: Redis TTL cache for quotes and atomic lockQuote for commit | After computing a rate quote, RateQuoteService stores the RateQuoteResult in Redis under key rate_quote:{quoteRef} with TTL = rule.rateQuoteTtlSeconds (range 60-1800s; default 60s for aggregator-bound, 300s otherwise). On CommitTransaction, lockQuote(quoteRef) uses Redis GETDEL (atomic get-and-delete) to fetch and consume the quote in one operation. If key absent or expired: throw RateQuoteExpiredException (errorCode RATE_QUOTE_EXPIRED). getQuote(quoteRef) is a read-only GET (no delete) for idempotency checks. | • Create services/rate-fx/src/main/java/com/gme/pay/ratefx/RateQuoteService.java @Service with RedisTemplate<String, String> (JSON serialized) • Implement storeQuote(RateQuoteResult quote, int ttlSeconds): serialize to JSON; SET rate_quote:{quote.quoteRef} with EX ttlSeconds • Implement lockQuote(String quoteRef): execute Redis GETDEL; if null throw RateQuoteExpiredException; deserialize and return RateQuoteResult • Implement getQuote(String quoteRef): Redis GET without delete; return Optional<RateQuoteResult> • Write @SpringBootTest integration test using Testcontainers Redis 7: store, assert get, lockQuote returns and subsequent lockQuote throws, verify TTL on stored key | services/rate-fx/src/main/java/com/gme/pay/ratefx/RateQuoteService.java | • storeQuote with ttlSeconds=60 results in Redis key with TTL between 58-60 seconds (allow 2s test execution slack) • lockQuote is atomic: two concurrent threads calling lockQuote on the same quoteRef result in exactly one success and one RateQuoteExpiredException (CountDownLatch test) • lockQuote on expired key (ttl=1, wait 2s) throws RateQuoteExpiredException with errorCode RATE_QUOTE_EXPIRED • getQuote does NOT delete the key (key still exists after call; verify with RedisTemplate.hasKey) • RateQuoteResult BigDecimal fields survive JSON round-trip with no precision loss (compare field by field with compareTo) | 45 | 2.1-T20, 2.1-T03 | ARCH | SAD-02
2.1-T22 | shared-libs | 2.1 | 2. Architecture & Technical Foundation | Finalize system architecture & tech stack | 1 | Author ADR-005: Config-not-code for schemes and partners; Rule resolution algorithm | AD-04 (SAD-02) mandates zero deployments to add a scheme or partner. ADR-005 documents how: Scheme, Partner, and Rule are rows in PostgreSQL; SmartRouterService resolves the adapter at runtime via SchemeAdapterRegistry (Map<String,SchemeAdapter> populated from Spring beans keyed by getSchemeCode()); RateEngine resolves margins via ConfigCacheService by exact (partner_id, scheme_id, direction) lookup. Rule resolution: exact match with effective_from <= now() < effective_to (or effective_to IS NULL); no active rule returns 422 errorCode RULE_NOT_FOUND. No if/switch on partner_code or scheme_code in core code. | • Create docs/adr/ADR-005-config-not-code-rule-resolution.md with standard ADR template • State decision: SchemeAdapterRegistry built from @Autowired List<SchemeAdapter> beans at startup; keyed by getSchemeCode(); no hardcoded scheme identifiers in routing logic • State Rule resolution algorithm: exact match on (partner_id, scheme_id, direction) with time-bounded effectivity; no wildcard fallback in Phase 1 • State constraint: no if/switch on partner_code or scheme_code in Transaction Orchestrator, Rate Engine, or Smart Router source code • Document RULE_NOT_FOUND error response (HTTP 422) when no active rule exists • Add to ADR index | docs/adr/ADR-005-config-not-code-rule-resolution.md | • Decision names SchemeAdapterRegistry as Map<String,SchemeAdapter> Spring bean populated by @Autowired List<SchemeAdapter> • Rule resolution algorithm states exact (partner_id, scheme_id, direction) match with time-bounded effectivity • Constraint against hardcoded partner/scheme logic in core code is explicitly stated • RULE_NOT_FOUND is named as the errorCode for missing active rule (HTTP 422) • ADR cross-references config-registry service and ConfigCacheService | 25 | 2.1-T13, 2.1-T07 | ARCH | SAD-02
2.1-T23 | shared-libs | 2.1 | 2. Architecture & Technical Foundation | Finalize system architecture & tech stack | 1 | Author ADR-006: Rate lock immutability at CommitTransaction; BOK reporting from locked values | AD-08 (SAD-02): all 9 USD pool values and derived rates are permanently recorded at CommitTransaction and immutable afterward. The 9 locked columns in transactions table: collection_usd, payout_usd_cost, collection_margin_usd, payout_margin_usd, send_amount_value, service_charge_value, collection_amount_value, offer_rate_coll, cross_rate. Enforcement: PostgreSQL BEFORE UPDATE trigger raises exception if any locked column is modified after rate_locked_at IS NOT NULL. Application guard: TransactionService.lockRate() throws IllegalStateException if called on already-locked row. BOK FX1015 reports read these stored values directly - never recompute at report time. | • Create docs/adr/ADR-006-rate-lock-immutability.md with standard ADR template • List all 9 immutable column names explicitly • Document DB enforcement: PostgreSQL BEFORE UPDATE trigger (protect_rate_lock_columns) raises SQLSTATE P0001 if any locked column changes after rate_locked_at IS NOT NULL • Document application enforcement: TransactionService.lockRate() throws IllegalStateException if rate_locked_at already set • State BOK reporting implication: Reporting service reads stored locked values; never recomputes rates at report time • Add to ADR index | docs/adr/ADR-006-rate-lock-immutability.md | • All 9 rate-lock column names are listed correctly (matches V1 migration schema from T15) • DB trigger approach named as protect_rate_lock_columns BEFORE UPDATE trigger • Application guard named as IllegalStateException if rate_locked_at already set • BOK reporting section states reports use stored locked values, not live treasury rates • ADR cross-references pool identity invariant (¦collectionUsd - collectionMarginUsd - payoutMarginUsd - payoutUsdCost¦ <= 0.01 USD) | 25 | 2.1-T08, 2.1-T15 | ARCH | SAD-02
2.1-T24 | shared-libs | 2.1 | 2. Architecture & Technical Foundation | Finalize system architecture & tech stack | 1 | Create Flyway migration V2 in payment-executor: rate-lock immutability trigger | To enforce ADR-006 at DB level, a PostgreSQL BEFORE UPDATE trigger on transactions raises an exception if any of the 9 rate-lock columns are modified when rate_locked_at IS NOT NULL. The 9 protected columns: collection_usd, payout_usd_cost, collection_margin_usd, payout_margin_usd, send_amount_value, service_charge_value, collection_amount_value, offer_rate_coll, cross_rate. Non-rate-lock columns (state, updated_at, scheme_approval_code) must remain updatable after lock. | • Create services/payment-executor/src/main/resources/db/migration/V2__rate_lock_trigger.sql • Write PL/pgSQL function protect_rate_lock_columns() RETURNS TRIGGER: IF OLD.rate_locked_at IS NOT NULL AND any of the 9 columns IS DISTINCT FROM OLD, RAISE EXCEPTION with SQLSTATE P0001 and message rate lock columns are immutable after commit • Write CREATE TRIGGER trg_protect_rate_lock BEFORE UPDATE ON transactions FOR EACH ROW EXECUTE FUNCTION protect_rate_lock_columns() • Add Testcontainers Postgres 16 test: insert APPROVED transaction with rate_locked_at set; attempt UPDATE on collection_usd; assert PSQLException with SQLSTATE P0001 • Assert UPDATE on state column (APPROVED -> REVERSED) still succeeds after rate_locked_at is set | services/payment-executor/src/main/resources/db/migration/V2__rate_lock_trigger.sql | • UPDATE on collection_usd after rate_locked_at IS NOT NULL raises PSQLException with SQLSTATE P0001 • UPDATE on state column after rate_locked_at IS NOT NULL succeeds (non-rate-lock column) • UPDATE on any rate-lock column while rate_locked_at IS NULL succeeds (rate not yet locked) • Trigger is FOR EACH ROW (not statement-level) • Flyway V1 (transactions) and V2 (trigger) both apply cleanly in sequence on Postgres 16 | 40 | 2.1-T15, 2.1-T23 | ARCH | SAD-02
2.1-T25 | shared-libs | 2.1 | 2. Architecture & Technical Foundation | Finalize system architecture & tech stack | 1 | Create infra/docker-compose.yml for local dev: Postgres 16, MongoDB, Redis 7, Kafka, Vault, MinIO | Developers run docker-compose up -d to start all local dependencies. Services: postgres:16 on port 5433 (avoids clash with local 5432), mongo:7 on 27017, redis:7 on 6379, confluentinc/cp-kafka:7.6 in KRaft mode on 9092, vault:1.16 in dev mode on 8200, minio/minio on 9000 (console 9001). All credentials sourced from .env file. Each service has a healthcheck. Named volumes for persistence. | • Create infra/docker-compose.yml with all 6 services and depends_on healthcheck conditions • postgres: image postgres:16, ports 5433:5432, healthcheck pg_isready -U ${POSTGRES_USER} • mongo: image mongo:7, ports 27017:27017, healthcheck mongosh --eval db.adminCommand(ping) • redis: image redis:7, ports 6379:6379, healthcheck redis-cli ping • kafka: image confluentinc/cp-kafka:7.6, KRaft mode env vars, ports 9092:9092, healthcheck kafka-topics.sh --bootstrap-server localhost:9092 --list • vault: image vault:1.16, VAULT_DEV_ROOT_TOKEN_ID from .env, ports 8200:8200 • minio: image minio/minio, command server /data --console-address :9001, ports 9000:9000 and 9001:9001 • Create infra/.env.example with placeholder values only (no real credentials) | infra/docker-compose.yml and infra/.env.example | • docker compose config validates without errors • Postgres healthcheck reports healthy within 30s (pg_isready) • Redis healthcheck returns PONG • All 6 services have named volumes (no anonymous volumes) • infra/.env.example contains no real credentials (all values are CHANGE_ME placeholders) | 40 | 2.1-T01 | ARCH | SAD-02
2.1-T26 | shared-libs | 2.1 | 2. Architecture & Technical Foundation | Finalize system architecture & tech stack | 1 | Configure Testcontainers shared base classes in lib-persistence for Postgres 16, Redis 7, and MongoDB | All service integration tests that need Postgres 16, Redis 7, or MongoDB start a Testcontainers container. lib-persistence provides shared abstract base classes to avoid duplicate config: TestContainersPostgres (static PostgreSQLContainer postgres:16 with @DynamicPropertySource), TestContainersRedis (static GenericContainer redis:7), TestContainersMongo (MongoDBContainer mongo:7). Services extend the relevant base class in their @SpringBootTest or @DataJpaTest. WireMock is configured per-service. | • Create libs/lib-persistence/src/testFixtures/java/com/gme/pay/persistence/testutil/TestContainersPostgres.java: @Testcontainers, static PostgreSQLContainer<> POSTGRES = new PostgreSQLContainer<>(postgres:16); @DynamicPropertySource sets spring.datasource.url/username/password • Create TestContainersRedis.java: static GenericContainer<> REDIS = new GenericContainer<>(redis:7).withExposedPorts(6379); @DynamicPropertySource sets spring.data.redis.host/port • Create TestContainersMongo.java: MongoDBContainer for mongo:7 with @DynamicPropertySource for spring.data.mongodb.uri • Add testcontainers-bom:1.19.x to lib-persistence build.gradle testFixtures scope; expose testFixtures to consuming services • Verify a dummy @DataJpaTest in lib-persistence uses TestContainersPostgres and a JPA entity round-trips successfully | libs/lib-persistence/src/testFixtures/java/com/gme/pay/persistence/testutil/TestContainersPostgres.java, TestContainersRedis.java, TestContainersMongo.java | • TestContainersPostgres starts postgres:16 container (verify POSTGRES.getDockerImageName() contains postgres:16) • @DynamicPropertySource overrides spring.datasource.url to container JDBC URL • TestContainersRedis @DynamicPropertySource sets spring.data.redis.host to 127.0.0.1 and port to mapped container port • Container field is static (shared across all test methods; not restarted per test method) • A service extending TestContainersPostgres + TestContainersRedis connects to both without additional config | 35 | 2.1-T06 | ARCH | SAD-02
2.1-T27 | shared-libs | 2.1 | 2. Architecture & Technical Foundation | Finalize system architecture & tech stack | 1 | Author ADR-007: Transaction state machine transitions and UNCERTAIN resolution strategy | SAD-02 section 5.2 defines 9 states: QUOTED, PENDING_DEBIT, DEBITED, SCHEME_SENT, APPROVED, UNCERTAIN, FAILED, REVERSED, REFUNDED. Only TransactionOrchestrator may transition state. UNCERTAIN resolution: if scheme response not received within SLA, set UNCERTAIN; Settlement Engine resolves within 24h via ZP0012/ZP0022 batch files; unresolved after 24h triggers ops alert and manual exception queue. Prefunding reversal rule: deduction is held during UNCERTAIN; reversed only if reconciliation confirms FAILED. | • Create docs/adr/ADR-007-transaction-state-machine.md with standard ADR template • Include Mermaid stateDiagram-v2 block with all 9 states and allowed transitions as per SAD-02 section 5.2 • State constraint: TransactionOrchestrator is the only component that writes transactions.state; all other services read-only • Document UNCERTAIN resolution: scheme timeout -> UNCERTAIN -> Settlement Engine resolves via ZP0012/ZP0022 within 24h; unresolved > 24h -> ops alert + manual queue • Document prefunding reversal rule: deduction held during UNCERTAIN; reversed only on reconciliation confirming FAILED (not reversed on APPROVED) • Add to ADR index | docs/adr/ADR-007-transaction-state-machine.md | • Mermaid stateDiagram-v2 is syntactically valid (renderable) • All 9 state names match exactly the CHECK constraint in V1 migration (T15) • Both UNCERTAIN -> APPROVED and UNCERTAIN -> FAILED transitions are shown in the diagram • Prefunding reversal rule explicitly states deduction is held (not reversed) during UNCERTAIN state • Constraint that only TransactionOrchestrator writes state is explicitly stated | 25 | 2.1-T15, 2.1-T07 | ARCH | SAD-02
2.1-T28 | shared-libs | 2.1 | 2. Architecture & Technical Foundation | Finalize system architecture & tech stack | 1 | Scaffold services/smart-router: SchemeAdapterRegistry and runtime route resolution | services/smart-router resolves the correct Scheme Adapter for a payment request. SmartRouterService.resolve(schemeType, countryCode, direction, partnerId) queries config-registry (via RestClient) for an active Rule; if none throws RuleNotFoundException (HTTP 422, errorCode RULE_NOT_FOUND). Returns SchemeHandle containing schemeId (UUID) and the matching SchemeAdapter bean from SchemeAdapterRegistry. SchemeAdapterRegistry is a Map<String, SchemeAdapter> auto-built at startup from all SchemeAdapter Spring beans keyed by getSchemeCode(). Resolving an unregistered schemeType throws SchemeNotSupportedException (HTTP 422, errorCode SCHEME_NOT_SUPPORTED). | • Create services/smart-router/build.gradle: lib-errors, lib-events, spring-boot-starter-web • Create SmartRouterApplication.java @SpringBootApplication • Create SchemeAdapterRegistry.java @Component: in @PostConstruct, iterate @Autowired List<SchemeAdapter> and put each into Map<String,SchemeAdapter> keyed by getSchemeCode() • Create SmartRouterService.java @Service: call config-registry REST endpoint to verify active Rule; lookup adapter in registry; return SchemeHandle record (schemeId, adapter) • Define SchemeHandle.java record: UUID schemeId, SchemeAdapter adapter • Write unit test: registry with one ZeroPaySchemeAdapter stub; resolve ZEROPAY returns SchemeHandle; resolve UNKNOWN throws SchemeNotSupportedException | services/smart-router/src/main/java/com/gme/pay/smartrouter/SchemeAdapterRegistry.java and SmartRouterService.java | • Registry auto-populates at startup: one ZeroPaySchemeAdapter bean registered under key ZEROPAY • resolve with schemeType=UNKNOWN throws SchemeNotSupportedException with errorCode SCHEME_NOT_SUPPORTED • resolve with schemeType=ZEROPAY and valid Rule returns SchemeHandle with non-null schemeId and adapter • SchemeAdapterRegistry uses getSchemeCode() as key - no hardcoded ZEROPAY string in registry logic • Unit test has zero Testcontainers (mock config-registry via WireMock or Mockito) | 45 | 2.1-T17, 2.1-T13, 2.1-T03, 2.1-T22 | ARCH | SAD-02
2.1-T29 | shared-libs | 2.1 | 2. Architecture & Technical Foundation | Finalize system architecture & tech stack | 1 | Scaffold services/notification: WebhookDispatchService with exponential back-off retry and dead-letter | services/notification dispatches partner webhooks. Events: payment.pending_debit, payment.approved, payment.failed, payment.reversed. Payload signed with HMAC-SHA256 (webhook secret from config-registry). Retry schedule: 5s, 30s, 2min, 10min, 1h, 6h (max 6 attempts). Partner must return HTTP 200. Dead-letter after retry exhaustion: write to webhook_dead_letters table (id UUID, partner_id UUID, event_type VARCHAR, payload JSONB, last_error TEXT, exhausted_at TIMESTAMPTZ). @SpringRetry with @Retryable / @Recover for the retry/dead-letter pattern. | • Create services/notification/build.gradle: spring-boot-starter-web, spring-retry, lib-errors, lib-events • Create NotificationApplication.java @SpringBootApplication @EnableRetry • Create Flyway V1 migration: webhook_dead_letters table with all columns • Create WebhookDispatchService.java @Service: dispatch(WebhookPayload, UUID partnerId) - fetch webhook URL from config-registry, sign with HMAC-SHA256, POST via RestClient; annotate @Retryable(maxAttempts=6, backoff=@Backoff(delay=5000, multiplier=6, maxDelay=21600000)) • Create WebhookDeadLetterService.java @RecoverWith: write to webhook_dead_letters on retry exhaustion • WireMock integration test: endpoint returns 503 twice then 200; verify dispatch succeeds on 3rd attempt and no dead-letter row written | services/notification/src/main/java/com/gme/pay/notification/WebhookDispatchService.java and V1 migration for webhook_dead_letters | • Webhook with HTTP 200 response succeeds on first attempt with no retry • Webhook always returning 503 exhausts all 6 retries and writes to webhook_dead_letters (WireMock test) • X-GME-Webhook-Signature HMAC-SHA256 header present on every dispatch attempt • webhook_dead_letters row contains event_type, partner_id, and last_error after exhaustion • Service does not retry on HTTP 400 (client error is non-retriable; verify with WireMock stub returning 400) | 50 | 2.1-T03, 2.1-T05, 2.1-T06, 2.1-T25 | ARCH | SAD-02
2.1-T30 | shared-libs | 2.1 | 2. Architecture & Technical Foundation | Finalize system architecture & tech stack | 1 | Write unit tests for RateEngine: canonical test vectors and all edge cases | RateEngine (T20) needs exhaustive JUnit 5 unit tests. RateEngineTest.java is a plain unit test (no Spring context, no Testcontainers). Vectors: (a) cross-border KRW payout, costRatePay=1.0 (USD IDENTITY settle-B), costRateColl=1380.0; (b) same-currency KRW short-circuit; (c) marginA+marginB=1.9% cross-border rejected; (d) pool identity holds for 5 parameterised rate combinations; (e) serviceCharge not in USD pool (collectionUsd identical regardless of serviceCharge); (f) BOK derived fields offerRateColl and crossRate computed correctly. | • Create services/rate-fx/src/test/java/com/gme/pay/ratefx/engine/RateEngineTest.java • Test (a): targetPayout=50000, costRatePay=1.0, costRateColl=1380.0, marginA=0.015, marginB=0.01, serviceCharge=0; assert sendAmount within 1 KRW of expected, pool identity holds within 0.01 USD • Test (b): targetPayout=10000 KRW, all currencies KRW, serviceCharge=500; assert collectionAmount=10500 exactly, all USD pool fields null • Test (c): marginA=0.010, marginB=0.009 (sum 0.019) with cross-border currencies; assert IllegalArgumentException mentioning combined margin • Test (d): @ParameterizedTest over 5 rate combinations; assert ¦collectionUsd - collectionMarginUsd - payoutMarginUsd - payoutUsdCost¦ <= 0.01 in each case • Test (e): same inputs with serviceCharge=0 vs serviceCharge=500; assert collectionUsd is identical in both • Test (f): assert offerRateColl = sendAmount / (collectionUsd - collectionMarginUsd); assert crossRate = targetPayout / sendAmount | services/rate-fx/src/test/java/com/gme/pay/ratefx/engine/RateEngineTest.java with at least 10 @Test methods | • All tests pass with ./gradlew :services:rate-fx:test • Test (a) sendAmount is within 1 KRW of expected (rounding tolerance) • Test (c) throws on marginA+marginB=0.019 cross-border but NOT for same-currency 0% margin • Test (e) proves serviceCharge does not affect collectionUsd (pool stays clean) • Test class has zero Spring annotations (no @SpringBootTest, no @ExtendWith(SpringExtension)) | 50 | 2.1-T20 | ARCH | SAD-02
2.1-T31 | shared-libs | 2.1 | 2. Architecture & Technical Foundation | Finalize system architecture & tech stack | 1 | Write integration test for prefunding atomic deduction under concurrency | PrefundingService.deductBalance (T16) must be concurrency-safe under SELECT FOR UPDATE. Test: spawn 10 concurrent threads each deducting 60 USD from a starting balance of 500 USD. Expected: exactly 8 deductions succeed (8x60=480 <= 500); the 9th would require 540 > 500, so threads 9 and 10 throw InsufficientPrefundingException. Final balance must be exactly 500 - (successCount * 60) with no negative balance ever appearing. | • Create services/prefunding/src/test/java/com/gme/pay/prefunding/PrefundingConcurrencyIT.java • Extend TestContainersPostgres from lib-persistence; @SpringBootTest, inject PrefundingService • Setup: insert prefunding_balances row for testPartnerId with balance_usd=500.00 • Run 10 concurrent threads via ExecutorService.invokeAll() each calling deductBalance(testPartnerId, new BigDecimal(60)) • Count successes vs InsufficientPrefundingException; assert successCount + failCount == 10 • Assert final balance == 500.00 - (successCount * 60.00) using BigDecimal.compareTo; assert no prefunding_transactions row has negative balance_after_usd | services/prefunding/src/test/java/com/gme/pay/prefunding/PrefundingConcurrencyIT.java | • Test completes without deadlock or timeout within 30 seconds • Final balance equals 500.00 - (successCount * 60.00) exactly (BigDecimal compareTo = 0) • All 10 futures complete (no thread left hanging) • No prefunding_transactions row has balance_after_usd < 0 • Test is deterministic: running 3 consecutive times gives the same successCount | 50 | 2.1-T16, 2.1-T26 | ARCH | SAD-02
2.1-T32 | shared-libs | 2.1 | 2. Architecture & Technical Foundation | Finalize system architecture & tech stack | 1 | Add OpenTelemetry and MDC correlation filter to lib-errors for all services | All GMEPay+ services must emit structured JSON logs with txn_ref, partner_id, scheme_id, request_id as MDC correlation fields, and expose distributed traces via OpenTelemetry. lib-errors provides CorrelationMdcFilter (OncePerRequestFilter, @Order HIGHEST_PRECEDENCE) that extracts X-Txn-Ref and X-Partner-Id headers and puts them in MDC, clearing on response. The opentelemetry-spring-boot-starter is added to the root build.gradle so all services inherit auto-instrumentation. A config template application-template.yaml documents the OTLP exporter endpoint and log pattern. | • Add io.opentelemetry.instrumentation:opentelemetry-spring-boot-starter:2.x to root build.gradle subprojects dependencies block • Create libs/lib-errors/src/main/java/com/gme/pay/errors/CorrelationMdcFilter.java implements OncePerRequestFilter @Order(Ordered.HIGHEST_PRECEDENCE): extracts X-Txn-Ref -> MDC key txn_ref, X-Partner-Id -> MDC key partner_id; clears both in finally block • Register CorrelationMdcFilter as @Bean in GlobalExceptionHandler auto-configuration class • Create docs/config-templates/application-template.yaml with otel.exporter.otlp.endpoint, otel.service.name placeholder, logging.pattern.console including %X{txn_ref} %X{partner_id} • Write unit test for CorrelationMdcFilter: mock request with X-Txn-Ref=TXN123; assert MDC.get(txn_ref)=TXN123 during filter; assert MDC is null after filter exits | libs/lib-errors/src/main/java/com/gme/pay/errors/CorrelationMdcFilter.java and docs/config-templates/application-template.yaml | • CorrelationMdcFilter clears MDC in finally block (no leakage to subsequent requests) • MDC keys are exactly txn_ref and partner_id (lowercase underscore, not camelCase) • opentelemetry-spring-boot-starter appears in ./gradlew :services:rate-fx:dependencies output • application-template.yaml log pattern includes %X{txn_ref} and %X{partner_id} • CorrelationMdcFilter is registered at HIGHEST_PRECEDENCE (runs before other filters) | 40 | 2.1-T03, 2.1-T04 | ARCH | SAD-02
2.1-T33 | shared-libs | 2.1 | 2. Architecture & Technical Foundation | Finalize system architecture & tech stack | 1 | Create docs/architecture-baseline.md: WBS 2.1 Architecture Baseline deliverable | WBS 2.1 parent deliverable is the Architecture Baseline document. It summarises the Gradle monorepo module layout, the 5 shared libraries and their key classes, the 7 ADRs and their decisions, database schemas per service (which Flyway migrations exist and what tables they create), key interface contracts (SchemeAdapter, EventPublisher, RateEngine.computeQuote), and the docker-compose local dev environment port map. | • Create docs/architecture-baseline.md • Section 1: Monorepo layout - table of all 21 Gradle modules with path and one-line purpose • Section 2: Shared libraries - lib-money (Money.java, CurrencyScale.java), lib-errors (ErrorEnvelope, GmePayException, GlobalExceptionHandler), lib-api-contracts (partner-api.yaml, generated DTOs), lib-events (DomainEvent, EventPublisher, 6 event classes), lib-persistence (PersistenceAutoConfiguration, AuditableEntity, Testcontainers base classes) • Section 3: ADR index - ADR-001 through ADR-007 with one-line decision summary and status • Section 4: Database schemas per service - list service, migration file(s), and tables created • Section 5: Key interfaces - SchemeAdapter (6 methods), EventPublisher (publish), RateEngine.computeQuote (input/output types) • Section 6: Local dev - docker-compose service list with ports | docs/architecture-baseline.md | • All 21 Gradle module paths are listed (matches settings.gradle from T01) • All 7 ADRs listed with Status: Accepted • Each service Flyway migration listed (payment-executor: V1__create_transactions.sql, V2__rate_lock_trigger.sql etc.) • SchemeAdapter interface shows exactly 6 method signatures matching T17 • RateEngine.computeQuote shows input parameter types and output RateQuoteResult type • Docker-compose section lists all 6 services with their host ports | 30 | 2.1-T01, 2.1-T07, 2.1-T08, 2.1-T09, 2.1-T10, 2.1-T22, 2.1-T23, 2.1-T29 | ARCH | SAD-02
2.2-T01 | shared-libs | 2.2 | 2. Architecture & Technical Foundation | Service/module structure & scaffolding | 1 | Create Gradle root project with settings.gradle and parent build.gradle | GMEPay+ is a Gradle multi-module monorepo. The root settings.gradle must include every service module and shared lib. The parent build.gradle defines Java 21, Spring Boot 3.x BOM, and common dependency management so all subprojects inherit versions consistently. | • Create root settings.gradle listing all modules: libs/lib-money, libs/lib-errors, libs/lib-api-contracts, libs/lib-events, libs/lib-persistence, libs/lib-observability, services/qr-service, services/smart-router, services/rate-fx, services/auth-identity, services/payment-executor, services/txn-mgmt, services/prefunding, services/notification-webhook, services/settlement-recon, services/revenue-ledger, services/reporting-compliance, services/merchant-qr, services/scheme-adapter-zeropay, services/config-registry, services/api-gateway, services/ops-bff • Create root build.gradle with plugins block (java, io.spring.dependency-management), Java 21 toolchain via java.toolchain.languageVersion = JavaLanguageVersion.of(21) in allprojects, and Spring Boot BOM import • Add gradle/wrapper/gradle-wrapper.properties pinned to Gradle 8.x • Verify ./gradlew projects lists all 22 modules without error | settings.gradle, build.gradle, gradle/wrapper/gradle-wrapper.properties at repo root | • ./gradlew projects lists all 22 modules with no resolution errors • Java toolchain set to JavaLanguageVersion.of(21) in parent build.gradle • Spring Boot BOM declared once in parent; subprojects do NOT redeclare it • Wrapper properties pin a specific Gradle 8.x version • All module paths use forward slashes and match the directory layout | 30 |  | ARCH | SAD-02
2.2-T02 | shared-libs | 2.2 | 2. Architecture & Technical Foundation | Service/module structure & scaffolding | 1 | Scaffold shared lib: lib-money (BigDecimal money/currency types) | lib-money provides Money and CurrencyScale value types used across all services. Amounts must use BigDecimal (never double or float). Per-currency scale: KRW=0 decimals, USD=2. The module must expose a CurrencyScale registry and a Money.of(BigDecimal amount, String currency) factory that enforces scale on construction using RoundingMode.HALF_UP. | • Create libs/lib-money/build.gradle with java-library plugin and Jackson annotations dependency; no Spring Boot main class • Create com.gme.pay.money.CurrencyScale with static scale(String currency) returning int: KRW->0, USD->2, default->2 • Create com.gme.pay.money.Money immutable class with BigDecimal amount and String currency; static of() factory enforces scale rounding on construction • Add Money.add(Money) and Money.subtract(Money) that assert same currency and return scaled result • Add JUnit 5 unit tests in src/test: Money.of(1000.7, KRW) rounds to 1001; Money.of(1.005, USD) is 1.01; add with mismatched currencies throws IllegalArgumentException | libs/lib-money/src/main/java/com/gme/pay/money/Money.java and CurrencyScale.java; libs/lib-money/src/test/java/com/gme/pay/money/MoneyTest.java | • Money.of(BigDecimal.valueOf(1000.7), KRW) returns amount 1001 (scale 0, HALF_UP) • Money.of(BigDecimal.valueOf(1.005), USD) returns amount 1.01 (scale 2, HALF_UP) • Money.add with mismatched currencies throws IllegalArgumentException • No float or double fields in Money or CurrencyScale • Unit tests pass via ./gradlew :libs:lib-money:test | 40 | 2.2-T01 | ARCH | SAD-02
2.2-T03 | shared-libs | 2.2 | 2. Architecture & Technical Foundation | Service/module structure & scaffolding | 1 | Scaffold shared lib: lib-errors (canonical error model) | lib-errors defines the shared error envelope used by all services in REST responses. Every error response carries: error_code (String), message (String), txn_ref (String nullable), and timestamp (Instant UTC). Required error codes: PARTNER_B_QUOTE_DEVIATION, PARTNER_B_QUOTE_UNAVAILABLE, RATE_QUOTE_EXPIRED, INSUFFICIENT_PREFUNDING, IDEMPOTENCY_CONFLICT, VALIDATION_ERROR, INTERNAL_ERROR. | • Create libs/lib-errors/build.gradle with java-library plugin and Jackson annotations dependency only (no Spring) • Create com.gme.pay.errors.ErrorResponse record with fields: errorCode (String), message (String), txnRef (String), timestamp (Instant) • Create com.gme.pay.errors.ErrorCode enum with all 7 listed codes • Create com.gme.pay.errors.GmePayException extends RuntimeException carrying ErrorCode and optional txnRef; provide getErrorCode() accessor • Add JUnit 5 test: ErrorResponse serialises to JSON with all four fields; GmePayException carries correct ErrorCode | libs/lib-errors/src/main/java/com/gme/pay/errors/ErrorResponse.java, ErrorCode.java, GmePayException.java | • ErrorResponse serialises to JSON with timestamp as ISO-8601 UTC string • GmePayException.getErrorCode() returns the injected ErrorCode • All 7 named error codes present in ErrorCode enum • No Spring dependencies in lib-errors compile scope • Unit test passes via ./gradlew :libs:lib-errors:test | 30 | 2.2-T01 | ARCH | SAD-02
2.2-T04 | shared-libs | 2.2 | 2. Architecture & Technical Foundation | Service/module structure & scaffolding | 1 | Scaffold shared lib: lib-events (domain event schemas and EventPublisher interface) | lib-events defines all domain event types as Java records and their JSON serialisation. Phase 1 transport is transactional outbox plus in-process polling; Kafka transport is wired in a later integration phase behind the EventPublisher interface. Events: TransactionStateChangedEvent, PrefundingDeductedEvent, LowBalanceAlertEvent, WebhookDispatchEvent, ConfigChangedEvent. | • Create libs/lib-events/build.gradle with java-library and Jackson dependency • Create com.gme.pay.events.DomainEvent base interface with eventId (UUID), occurredAt (Instant), eventType (String) • Create concrete event records: TransactionStateChangedEvent(txnRef, partnerId, schemeId, fromState, toState, occurredAt), PrefundingDeductedEvent(partnerId, amountUsd, balanceAfterUsd, occurredAt), LowBalanceAlertEvent(partnerId, currentBalanceUsd, thresholdUsd, occurredAt), WebhookDispatchEvent(partnerId, txnRef, eventType, payload, occurredAt), ConfigChangedEvent(entityType, entityId, actor, previousValueJson, newValueJson, occurredAt) • Create com.gme.pay.events.EventPublisher interface with single method void publish(DomainEvent event) • Add JUnit 5 test: serialise each event to JSON and assert eventType field is present and occurredAt is ISO-8601 | libs/lib-events/src/main/java/com/gme/pay/events/DomainEvent.java, EventPublisher.java, and all 5 event record files | • All 5 event types implement DomainEvent interface • EventPublisher has exactly one method publish(DomainEvent) • Jackson serialisation of TransactionStateChangedEvent includes txnRef, fromState, toState, occurredAt as ISO-8601 UTC • EventPublisher has zero Kafka imports (transport-agnostic) • Unit tests pass via ./gradlew :libs:lib-events:test | 35 | 2.2-T01 | ARCH | SAD-02
2.2-T05 | shared-libs | 2.2 | 2. Architecture & Technical Foundation | Service/module structure & scaffolding | 1 | Scaffold shared lib: lib-persistence (JPA base entity and Outbox table) | lib-persistence provides a @MappedSuperclass BaseEntity with UUID id and audit timestamps, plus the OutboxEvent @Entity and OutboxRepository for the transactional Outbox pattern. The Outbox ensures async events are committed atomically with business state in Phase 1 before Kafka is wired. Flyway migration V001 creates the outbox_events table. | • Create libs/lib-persistence/build.gradle with java-library, spring-boot-starter-data-jpa, flyway-core dependencies • Create com.gme.pay.persistence.BaseEntity @MappedSuperclass with id UUID @GeneratedValue(UUID), createdAt Instant, updatedAt Instant using @PrePersist and @PreUpdate • Create com.gme.pay.persistence.OutboxEvent @Entity @Table(name=outbox_events) with columns: id UUID PK, eventType VARCHAR NOT NULL, payload TEXT NOT NULL, published BOOLEAN NOT NULL DEFAULT false, createdAt TIMESTAMPTZ NOT NULL • Create com.gme.pay.persistence.OutboxRepository extends JpaRepository<OutboxEvent, UUID> with List<OutboxEvent> findTop50ByPublishedFalseOrderByCreatedAtAsc() • Add libs/lib-persistence/src/main/resources/db/migration/V001__create_outbox_events.sql creating outbox_events with the listed columns and an index on (published, created_at) | libs/lib-persistence/src/main/java/com/gme/pay/persistence/BaseEntity.java, OutboxEvent.java, OutboxRepository.java; libs/lib-persistence/src/main/resources/db/migration/V001__create_outbox_events.sql | • V001 SQL creates outbox_events with published BOOLEAN NOT NULL DEFAULT false • Index on (published, created_at) present in V001 SQL • OutboxEvent extends BaseEntity and has @Entity @Table(name=outbox_events) • findTop50ByPublishedFalseOrderByCreatedAtAsc() query method present on OutboxRepository • ./gradlew :libs:lib-persistence:compileJava succeeds | 40 | 2.2-T01, 2.2-T02 | ARCH | SAD-02
2.2-T06 | shared-libs | 2.2 | 2. Architecture & Technical Foundation | Service/module structure & scaffolding | 1 | Scaffold shared lib: lib-api-contracts (OpenAPI DTO stubs) | lib-api-contracts will contain DTOs generated from openapi/partner-api.yaml (OpenAPI generator wired in WBS 2.3). For WBS 2.2 scaffolding, create the module and a hand-written RateQuoteResponse DTO so downstream service modules can compile. A stub openapi/partner-api.yaml is created at repo root to reserve the path. | • Create libs/lib-api-contracts/build.gradle with java-library and Jackson annotations; no Spring runtime dependency • Create com.gme.pay.api.dto.RateQuoteResponse record: quoteRef (String), offerRate (BigDecimal), sendAmount (BigDecimal), serviceCharge (BigDecimal), collectionAmount (BigDecimal), collectionUsd (BigDecimal), payoutUsdCost (BigDecimal), validUntil (Instant) • Create com.gme.pay.api.dto.ErrorResponseDto matching lib-errors ErrorResponse shape for API boundary serialisation • Create openapi/partner-api.yaml stub at repo root with openapi: 3.0.3, info.title: GMEPay+ Partner API, info.version: 1.0.0, and an empty paths: block | libs/lib-api-contracts/src/main/java/com/gme/pay/api/dto/RateQuoteResponse.java, ErrorResponseDto.java; openapi/partner-api.yaml stub | • RateQuoteResponse has all 8 fields with correct types (BigDecimal for monetary values, Instant for validUntil) • ./gradlew :libs:lib-api-contracts:compileJava succeeds • openapi/partner-api.yaml is valid minimal YAML parseable by a YAML parser • No Spring or JPA runtime dependency in lib-api-contracts build.gradle • ErrorResponseDto has errorCode, message, txnRef, timestamp fields matching lib-errors ErrorResponse | 25 | 2.2-T01, 2.2-T02 | ARCH | SAD-02
2.2-T07 | shared-libs | 2.2 | 2. Architecture & Technical Foundation | Service/module structure & scaffolding | 1 | Scaffold shared lib: lib-observability (structured logging and MDC filter) | All services must emit structured JSON logs with correlation fields (txn_ref, partner_id, scheme_id, request_id) via Logback JSON encoder (logstash-logback-encoder), and export OpenTelemetry traces via Micrometer Tracing bridge. A shared MdcFilter extracts X-Request-ID from HTTP headers and puts it into MDC for log correlation. | • Create libs/lib-observability/build.gradle with java-library, spring-boot-starter-web (compileOnly), micrometer-tracing-bridge-otel, opentelemetry-exporter-otlp, net.logstash.logback:logstash-logback-encoder:7.4 dependencies • Create com.gme.pay.observability.MdcFilter @Component implements jakarta.servlet.Filter: extracts X-Request-ID header, puts into MDC as request_id, calls chain.doFilter(), then removes from MDC in finally block • Create libs/lib-observability/src/main/resources/logback-spring.xml with a ConsoleAppender using LogstashEncoder for JSON output including customFields placeholder for txn_ref and partner_id • Add JUnit 5 test asserting MdcFilter puts X-Request-ID into MDC and removes it after the chain completes | libs/lib-observability/src/main/java/com/gme/pay/observability/MdcFilter.java; libs/lib-observability/src/main/resources/logback-spring.xml | • MdcFilter puts X-Request-ID header value into MDC key request_id • MDC.get(request_id) is null after filter chain completes (cleanup in finally) • logback-spring.xml uses LogstashEncoder (JSON, not plain text pattern) • micrometer-tracing-bridge-otel on compile classpath • ./gradlew :libs:lib-observability:test passes | 35 | 2.2-T01 | ARCH | SAD-02
2.2-T08 | shared-libs | 2.2 | 2. Architecture & Technical Foundation | Service/module structure & scaffolding | 1 | Scaffold Spring Boot skeleton: services/config-registry | config-registry is the single source of truth for Scheme, Partner, and Rule configuration, persisted in PostgreSQL 16 with a Redis hot cache. Three core tables: schemes, partners, rules. Rule columns include m_a NUMERIC(10,6), m_b NUMERIC(10,6), effective_from, effective_to (soft-delete). Redis cache is invalidated on any config change. | • Create services/config-registry/build.gradle with spring-boot-starter-web, spring-boot-starter-data-jpa, spring-boot-starter-data-redis, flyway-core, lib-money, lib-errors, lib-persistence, lib-events, lib-observability dependencies • Create com.gme.pay.configregistry.ConfigRegistryApplication @SpringBootApplication main class with server.port=8081 in application.yml • Create services/config-registry/src/main/resources/db/migration/V001__create_config_tables.sql: tables schemes (id UUID PK, scheme_code VARCHAR UNIQUE NOT NULL, display_name VARCHAR, supported_modes VARCHAR, active BOOLEAN NOT NULL DEFAULT true, created_at TIMESTAMPTZ, updated_at TIMESTAMPTZ), partners (id UUID PK, partner_code VARCHAR UNIQUE NOT NULL, partner_type VARCHAR NOT NULL CHECK(partner_type IN (LOCAL,OVERSEAS)), active BOOLEAN NOT NULL DEFAULT true, webhook_url VARCHAR, created_at TIMESTAMPTZ, updated_at TIMESTAMPTZ), rules (id UUID PK, partner_id UUID NOT NULL REFERENCES partners(id), scheme_id UUID NOT NULL REFERENCES schemes(id), direction VARCHAR NOT NULL, m_a NUMERIC(10,6) NOT NULL, m_b NUMERIC(10,6) NOT NULL, service_charge NUMERIC(20,6) NOT NULL DEFAULT 0, service_charge_currency CHAR(3), rate_source_coll VARCHAR NOT NULL, rate_source_pay VARCHAR NOT NULL, rate_quote_ttl_seconds INT NOT NULL DEFAULT 300, active BOOLEAN NOT NULL DEFAULT true, effective_from TIMESTAMPTZ NOT NULL, effective_to TIMESTAMPTZ) • Create stub @RestController RegistryController with GET /internal/health returning 200 | services/config-registry/src/main/java/com/gme/pay/configregistry/ConfigRegistryApplication.java; services/config-registry/src/main/resources/db/migration/V001__create_config_tables.sql; application.yml | • ./gradlew :services:config-registry:bootJar succeeds • V001 SQL: rules.m_a and m_b are NUMERIC(10,6) not FLOAT • partners.partner_type CHECK constraint allows only LOCAL and OVERSEAS • rules.effective_to is TIMESTAMPTZ nullable (soft-delete; NULL means currently active) • Foreign keys rules.partner_id -> partners(id) and rules.scheme_id -> schemes(id) present in V001 | 45 | 2.2-T01, 2.2-T02, 2.2-T03, 2.2-T04, 2.2-T05, 2.2-T07 | ARCH | SAD-02
2.2-T09 | shared-libs | 2.2 | 2. Architecture & Technical Foundation | Service/module structure & scaffolding | 1 | Scaffold Spring Boot skeleton: services/auth-identity | auth-identity validates HMAC-SHA256 partner API keys and issues OAuth2/JWT tokens for Operator/Admin users. Partner credentials are stored hashed in PostgreSQL. The hmac_secret is stored encrypted (Vault/KMS field-level encryption); never in plaintext. Skeleton: app wiring, datasource config, Flyway migration for partner_credentials table. | • Create services/auth-identity/build.gradle with spring-boot-starter-web, spring-boot-starter-security, spring-boot-starter-data-jpa, spring-boot-starter-oauth2-resource-server, flyway-core, lib-errors, lib-observability dependencies • Create com.gme.pay.authidentity.AuthIdentityApplication @SpringBootApplication main class with server.port=8082 in application.yml • Create services/auth-identity/src/main/resources/db/migration/V001__create_partner_credentials.sql: table partner_credentials (id UUID PK, partner_id UUID NOT NULL, api_key_hash VARCHAR NOT NULL UNIQUE, api_key_prefix VARCHAR(8) NOT NULL, hmac_secret_encrypted VARCHAR NOT NULL, active BOOLEAN NOT NULL DEFAULT true, created_at TIMESTAMPTZ, last_used_at TIMESTAMPTZ) • Create stub @RestController HealthController with GET /internal/health | services/auth-identity/src/main/java/com/gme/pay/authidentity/AuthIdentityApplication.java; V001__create_partner_credentials.sql; application.yml | • ./gradlew :services:auth-identity:bootJar succeeds • api_key_hash is VARCHAR NOT NULL UNIQUE (stored hashed, never the raw key) • hmac_secret_encrypted column present (encrypted at rest, never plaintext) • api_key_prefix VARCHAR(8) present for human-readable identification without secret exposure • spring-boot-starter-oauth2-resource-server in build.gradle for JWT validation | 35 | 2.2-T01, 2.2-T03, 2.2-T05, 2.2-T07 | ARCH | SAD-02
2.2-T10 | shared-libs | 2.2 | 2. Architecture & Technical Foundation | Service/module structure & scaffolding | 1 | Scaffold Spring Boot skeleton: services/rate-fx (Rate and FX Engine) | rate-fx implements the 5-step RECEIVE-mode USD pool computation. Treasury rates stored as NUMERIC(20,10) in PostgreSQL table treasury_rates (key convention: usd_krw, usd_usd=1). Rate quotes cached in Redis with TTL (default 60s aggregator-bound, 300s otherwise; range 60-1800s). Rate-lock values written to rate_quotes at CommitTransaction as immutable columns. | • Create services/rate-fx/build.gradle with spring-boot-starter-web, spring-boot-starter-data-jpa, spring-boot-starter-data-redis, flyway-core, lib-money, lib-errors, lib-events, lib-api-contracts, lib-observability dependencies • Create com.gme.pay.ratefx.RateFxApplication @SpringBootApplication main class with server.port=8083 in application.yml • Create services/rate-fx/src/main/resources/db/migration/V001__create_treasury_rates.sql: table treasury_rates (id UUID PK, rate_key VARCHAR NOT NULL UNIQUE, currency_code CHAR(3) NOT NULL, rate_value NUMERIC(20,10) NOT NULL, effective_at TIMESTAMPTZ NOT NULL, entered_by VARCHAR, source VARCHAR NOT NULL DEFAULT MANUAL, created_at TIMESTAMPTZ) • Create services/rate-fx/src/main/resources/db/migration/V002__create_rate_quotes.sql: table rate_quotes (id UUID PK, quote_ref VARCHAR NOT NULL UNIQUE, partner_id UUID, scheme_id UUID, direction VARCHAR, target_payout NUMERIC(20,6), payout_currency CHAR(3), offer_rate NUMERIC(20,10), send_amount NUMERIC(20,6), send_amount_currency CHAR(3), collection_amount NUMERIC(20,6), collection_currency CHAR(3), collection_usd NUMERIC(20,10), payout_usd_cost NUMERIC(20,10), collection_margin_usd NUMERIC(20,10), payout_margin_usd NUMERIC(20,10), service_charge NUMERIC(20,6), offer_rate_coll NUMERIC(20,10), cross_rate NUMERIC(20,10), valid_until TIMESTAMPTZ, committed BOOLEAN NOT NULL DEFAULT false, created_at TIMESTAMPTZ) • Create stub @Service com.gme.pay.ratefx.service.RateEngineService with placeholder computeQuote() method signature | services/rate-fx/src/main/java/com/gme/pay/ratefx/RateFxApplication.java; V001__create_treasury_rates.sql; V002__create_rate_quotes.sql; application.yml | • ./gradlew :services:rate-fx:bootJar succeeds • treasury_rates.rate_value is NUMERIC(20,10) not FLOAT • rate_quotes stores all 5 USD pool columns (collection_usd, payout_usd_cost, collection_margin_usd, payout_margin_usd, send_amount) as NUMERIC(20,10) • rate_quotes.offer_rate_coll and cross_rate present as NUMERIC(20,10) (BOK derived fields) • committed BOOLEAN NOT NULL DEFAULT false in V002 (set true at rate-lock CommitTransaction) | 45 | 2.2-T01, 2.2-T02, 2.2-T03, 2.2-T04, 2.2-T05, 2.2-T06, 2.2-T07 | ARCH | SAD-02
2.2-T11 | shared-libs | 2.2 | 2. Architecture & Technical Foundation | Service/module structure & scaffolding | 1 | Scaffold Spring Boot skeleton: services/qr-service (QR Parser) | qr-service decodes QR payloads in EMVCo and ZeroPay formats and extracts schemeType, merchantId, payoutCurrency, and payoutAmount (nullable, not always encoded). Stateless; reads scheme format definitions from config-registry via HTTP. No database of its own. | • Create services/qr-service/build.gradle with spring-boot-starter-web, lib-errors, lib-api-contracts, lib-observability dependencies (no JPA/Flyway) • Create com.gme.pay.qrservice.QrServiceApplication @SpringBootApplication main class with server.port=8084 in application.yml • Create com.gme.pay.qrservice.model.QrParseResult record with: schemeType (String), merchantId (String), payoutCurrency (String), payoutAmount (BigDecimal nullable), rawPayload (String) • Create stub @RestController com.gme.pay.qrservice.controller.QrController with POST /internal/qr/parse accepting body {payload: String}, returning QrParseResult stub (all nulls) | services/qr-service/src/main/java/com/gme/pay/qrservice/QrServiceApplication.java, QrParseResult.java, QrController.java; application.yml | • ./gradlew :services:qr-service:bootJar succeeds • QrParseResult.payoutAmount is BigDecimal (nullable) not primitive double • POST /internal/qr/parse endpoint exists at the exact path • No PostgreSQL or Flyway dependency in build.gradle (stateless parser) • lib-errors on classpath for structured error responses | 25 | 2.2-T01, 2.2-T03, 2.2-T06, 2.2-T07 | ARCH | SAD-02
2.2-T12 | shared-libs | 2.2 | 2. Architecture & Technical Foundation | Service/module structure & scaffolding | 1 | Scaffold Spring Boot skeleton: services/smart-router | smart-router selects the correct Scheme Adapter at runtime given (schemeType, countryCode, direction, partnerId) by calling config-registry via HTTP (WebClient). Returns a RoutingContext (schemeId, adapterId, adapterEndpoint, direction). Stateless; no own database. | • Create services/smart-router/build.gradle with spring-boot-starter-web, spring-boot-starter-webflux (WebClient for config-registry calls), lib-errors, lib-api-contracts, lib-observability dependencies • Create com.gme.pay.smartrouter.SmartRouterApplication @SpringBootApplication main class with server.port=8085 • Create com.gme.pay.smartrouter.model.RoutingContext record with: schemeId (String), adapterId (String), adapterEndpoint (String), direction (String), partnerId (String) • Create stub @RestController com.gme.pay.smartrouter.controller.RouterController with POST /internal/route accepting JSON body {schemeType, countryCode, direction, partnerId}, returning RoutingContext stub • Add config-registry.base-url placeholder in application.yml | services/smart-router/src/main/java/com/gme/pay/smartrouter/SmartRouterApplication.java, RoutingContext.java, RouterController.java; application.yml | • ./gradlew :services:smart-router:bootJar succeeds • No database or Flyway dependency in build.gradle • RoutingContext has exactly the 5 named fields including adapterEndpoint • spring-boot-starter-webflux present (WebClient for config-registry calls) • config-registry.base-url placeholder in application.yml | 25 | 2.2-T01, 2.2-T03, 2.2-T06, 2.2-T07 | ARCH | SAD-02
2.2-T13 | shared-libs | 2.2 | 2. Architecture & Technical Foundation | Service/module structure & scaffolding | 1 | Scaffold Spring Boot skeleton: services/payment-executor (Transaction Orchestrator) | payment-executor owns the transaction state machine: QUOTED -> PENDING_DEBIT -> DEBITED -> SCHEME_SENT -> APPROVED/UNCERTAIN/FAILED -> REVERSED/REFUNDED. PostgreSQL stores transactions with all 5 USD pool columns as NUMERIC. Redis stores idempotency keys (24h TTL). All pool columns are immutable after CommitTransaction (rate_locked_at set). | • Create services/payment-executor/build.gradle with spring-boot-starter-web, spring-boot-starter-data-jpa, spring-boot-starter-data-redis, flyway-core, lib-money, lib-errors, lib-events, lib-persistence, lib-api-contracts, lib-observability dependencies • Create com.gme.pay.paymentexecutor.PaymentExecutorApplication @SpringBootApplication @EnableScheduling main class with server.port=8086 • Create services/payment-executor/src/main/resources/db/migration/V001__create_transactions.sql: table transactions (id UUID PK, txn_ref VARCHAR NOT NULL UNIQUE, partner_id UUID NOT NULL, scheme_id UUID, direction VARCHAR NOT NULL, quote_ref VARCHAR, status VARCHAR NOT NULL, target_payout NUMERIC(20,6), payout_currency CHAR(3), send_amount NUMERIC(20,6), send_amount_currency CHAR(3), collection_amount NUMERIC(20,6), collection_currency CHAR(3), collection_usd NUMERIC(20,10), payout_usd_cost NUMERIC(20,10), collection_margin_usd NUMERIC(20,10), payout_margin_usd NUMERIC(20,10), service_charge NUMERIC(20,6), offer_rate_coll NUMERIC(20,10), cross_rate NUMERIC(20,10), rate_locked_at TIMESTAMPTZ, scheme_approval_code VARCHAR, idempotency_key VARCHAR UNIQUE, created_at TIMESTAMPTZ, updated_at TIMESTAMPTZ, CONSTRAINT chk_status CHECK(status IN (QUOTED,PENDING_DEBIT,DEBITED,SCHEME_SENT,APPROVED,UNCERTAIN,FAILED,REVERSED,REFUNDED))) • Create stub @Service com.gme.pay.paymentexecutor.service.TransactionOrchestratorService with placeholder commitTransaction(String quoteRef, String idempotencyKey) | services/payment-executor/src/main/java/com/gme/pay/paymentexecutor/PaymentExecutorApplication.java; V001__create_transactions.sql; application.yml | • ./gradlew :services:payment-executor:bootJar succeeds • CHECK constraint on status includes all 9 states: QUOTED, PENDING_DEBIT, DEBITED, SCHEME_SENT, APPROVED, UNCERTAIN, FAILED, REVERSED, REFUNDED • All 5 USD pool columns stored as NUMERIC(20,10) not FLOAT • rate_locked_at TIMESTAMPTZ present (immutable after CommitTransaction) • idempotency_key VARCHAR UNIQUE present | 45 | 2.2-T01, 2.2-T02, 2.2-T03, 2.2-T04, 2.2-T05, 2.2-T06, 2.2-T07 | ARCH | SAD-02
2.2-T14 | shared-libs | 2.2 | 2. Architecture & Technical Foundation | Service/module structure & scaffolding | 1 | Scaffold Spring Boot skeleton: services/txn-mgmt (Transaction Management/History) | txn-mgmt provides transaction search, detail, and 8-step audit trail APIs. It is the CQRS read side: PostgreSQL for transactional audit trail; MongoDB for complex query projections. Admin-initiated actions (refund, reverse) flow through this service. Server port 8087. | • Create services/txn-mgmt/build.gradle with spring-boot-starter-web, spring-boot-starter-data-jpa, spring-boot-starter-data-mongodb, flyway-core, lib-money, lib-errors, lib-api-contracts, lib-observability dependencies • Create com.gme.pay.txnmgmt.TxnMgmtApplication @SpringBootApplication main class with server.port=8087 • Create services/txn-mgmt/src/main/resources/db/migration/V001__create_txn_audit_trail.sql: table txn_audit_trail (id UUID PK, txn_ref VARCHAR NOT NULL, event_step INT NOT NULL CHECK(event_step BETWEEN 1 AND 8), event_type VARCHAR NOT NULL, actor VARCHAR, details JSONB, occurred_at TIMESTAMPTZ NOT NULL); CREATE INDEX idx_txn_audit_trail_txn_ref ON txn_audit_trail(txn_ref) • Create stub @RestController com.gme.pay.txnmgmt.controller.TransactionController with GET /internal/transactions/{txnRef} returning 200 placeholder • Add spring.data.mongodb.uri placeholder in application.yml | services/txn-mgmt/src/main/java/com/gme/pay/txnmgmt/TxnMgmtApplication.java; V001__create_txn_audit_trail.sql; application.yml | • ./gradlew :services:txn-mgmt:bootJar succeeds • txn_audit_trail.event_step INT with CHECK(event_step BETWEEN 1 AND 8) present (8-step trail) • Index on txn_ref column present in V001 SQL • spring.data.mongodb.uri in application.yml (CQRS projection reads) • Both spring-boot-starter-data-jpa and spring-boot-starter-data-mongodb in build.gradle | 35 | 2.2-T01, 2.2-T03, 2.2-T05, 2.2-T06, 2.2-T07 | ARCH | SAD-02
2.2-T15 | shared-libs | 2.2 | 2. Architecture & Technical Foundation | Service/module structure & scaffolding | 1 | Scaffold Spring Boot skeleton: services/prefunding (Prefunding/Balance) | prefunding manages OVERSEAS partner USD prepaid balances. AD-06: deduction uses SELECT FOR UPDATE to prevent concurrent over-draws. LOW balance alert fires (via outbox EventPublisher) when balance_usd < low_balance_threshold_usd (default USD 10,000). prefunding_ledger records every debit and credit for audit. PostgreSQL only. | • Create services/prefunding/build.gradle with spring-boot-starter-web, spring-boot-starter-data-jpa, flyway-core, lib-money, lib-errors, lib-events, lib-persistence, lib-observability dependencies • Create com.gme.pay.prefunding.PrefundingApplication @SpringBootApplication main class with server.port=8088 • Create services/prefunding/src/main/resources/db/migration/V001__create_prefunding_tables.sql: table prefunding_accounts (id UUID PK, partner_id UUID NOT NULL UNIQUE, balance_usd NUMERIC(20,6) NOT NULL DEFAULT 0, low_balance_threshold_usd NUMERIC(20,6) NOT NULL DEFAULT 10000, currency CHAR(3) NOT NULL DEFAULT USD, version BIGINT NOT NULL DEFAULT 0, updated_at TIMESTAMPTZ); table prefunding_ledger (id UUID PK, partner_id UUID NOT NULL, txn_ref VARCHAR, event_type VARCHAR NOT NULL, amount_usd NUMERIC(20,6) NOT NULL, balance_after_usd NUMERIC(20,6) NOT NULL, occurred_at TIMESTAMPTZ NOT NULL) • Create stub @Service com.gme.pay.prefunding.service.PrefundingService with placeholder @Transactional deductBalance(UUID partnerId, BigDecimal amountUsd, String txnRef) method | services/prefunding/src/main/java/com/gme/pay/prefunding/PrefundingApplication.java; V001__create_prefunding_tables.sql; application.yml | • ./gradlew :services:prefunding:bootJar succeeds • prefunding_accounts.balance_usd is NUMERIC(20,6) not FLOAT • low_balance_threshold_usd DEFAULT 10000 present (matches spec USD 10,000 alert threshold) • version BIGINT NOT NULL DEFAULT 0 present (optimistic lock support for SELECT FOR UPDATE pattern) • deductBalance stub is annotated @Transactional | 40 | 2.2-T01, 2.2-T02, 2.2-T03, 2.2-T04, 2.2-T05, 2.2-T07 | ARCH | SAD-02
2.2-T16 | shared-libs | 2.2 | 2. Architecture & Technical Foundation | Service/module structure & scaffolding | 1 | Scaffold Spring Boot skeleton: services/notification-webhook | notification-webhook dispatches payment.pending_debit, payment.approved, payment.failed, payment.reversed webhooks to partner URLs with HMAC-SHA256 signature. Retry policy: exponential back-off at 5s, 30s, 2min, 10min, 1h, 6h (max 6 attempts). Dead-letter after final retry. Delivery log in PostgreSQL. Consumes WebhookDispatchEvent from outbox. | • Create services/notification-webhook/build.gradle with spring-boot-starter-web, spring-boot-starter-data-jpa, spring-boot-starter-webflux (WebClient for outbound webhook calls), flyway-core, lib-errors, lib-events, lib-persistence, lib-observability dependencies • Create com.gme.pay.notification.NotificationWebhookApplication @SpringBootApplication @EnableScheduling main class with server.port=8089 • Create services/notification-webhook/src/main/resources/db/migration/V001__create_webhook_delivery_log.sql: table webhook_delivery_log (id UUID PK, txn_ref VARCHAR, partner_id UUID NOT NULL, event_type VARCHAR NOT NULL, payload JSONB, attempt_count INT NOT NULL DEFAULT 0, last_attempt_at TIMESTAMPTZ, next_retry_at TIMESTAMPTZ, status VARCHAR NOT NULL, created_at TIMESTAMPTZ, CONSTRAINT chk_status CHECK(status IN (PENDING,DELIVERED,FAILED,DEAD_LETTER))) • Create stub @Service com.gme.pay.notification.service.WebhookDispatchService with placeholder dispatch(String partnerId, String txnRef, String eventType, String payload) method | services/notification-webhook/src/main/java/com/gme/pay/notification/NotificationWebhookApplication.java; V001__create_webhook_delivery_log.sql; application.yml | • ./gradlew :services:notification-webhook:bootJar succeeds • webhook_delivery_log.status CHECK includes DEAD_LETTER as a valid state • attempt_count INT NOT NULL DEFAULT 0 present (max 6 per spec) • next_retry_at TIMESTAMPTZ present (scheduler reads this to determine when to retry) • spring-boot-starter-webflux present (WebClient for outbound HTTPS webhook calls) | 35 | 2.2-T01, 2.2-T03, 2.2-T04, 2.2-T05, 2.2-T07 | ARCH | SAD-02
2.2-T17 | shared-libs | 2.2 | 2. Architecture & Technical Foundation | Service/module structure & scaffolding | 1 | Scaffold Spring Boot skeleton: services/settlement-recon (Settlement and Reconciliation) | settlement-recon generates ZP00xx batch files on cron schedule (KST windows: 02:00, 05:00, 14:00, 22:00 = UTC 17:00 prior, 20:00 prior, 05:00, 13:00) and processes inbound result files (ZP0012, ZP0022, ZP0062, ZP0064). Batch jobs must be idempotent: UNIQUE constraint on (batch_type, batch_date). Files archived to S3/MinIO. PostgreSQL + Object Storage. | • Create services/settlement-recon/build.gradle with spring-boot-starter-web, spring-boot-starter-data-jpa, spring-boot-starter-quartz, flyway-core, software.amazon.awssdk:s3, lib-errors, lib-events, lib-persistence, lib-observability dependencies • Create com.gme.pay.settlement.SettlementReconApplication @SpringBootApplication main class with server.port=8090 • Create services/settlement-recon/src/main/resources/application.yml with cron properties: settlement.cron.zp0011=0 0 17 * * ? (02:00 KST), settlement.cron.zp0061=0 0 20 * * ? (05:00 KST), settlement.cron.zp0063=0 0 5 * * ? (14:00 KST), settlement.cron.zp0065=0 0 13 * * ? (22:00 KST) • Create services/settlement-recon/src/main/resources/db/migration/V001__create_settlement_tables.sql: table settlement_batches (id UUID PK, batch_type VARCHAR NOT NULL, batch_date DATE NOT NULL, status VARCHAR NOT NULL, file_key VARCHAR, record_count INT, total_amount NUMERIC(20,6), created_at TIMESTAMPTZ, updated_at TIMESTAMPTZ, UNIQUE(batch_type, batch_date), CONSTRAINT chk_status CHECK(status IN (PENDING,GENERATED,TRANSMITTED,CONFIRMED,FAILED))) • Create stub @Service com.gme.pay.settlement.service.SettlementBatchService with placeholder generateBatch(String batchType, LocalDate batchDate) | services/settlement-recon/src/main/java/com/gme/pay/settlement/SettlementReconApplication.java; V001__create_settlement_tables.sql; application.yml | • ./gradlew :services:settlement-recon:bootJar succeeds • UNIQUE(batch_type, batch_date) in V001 ensures idempotent batch generation • settlement_batches.status CHECK includes all 5 states including CONFIRMED • Cron expressions in application.yml represent the correct UTC equivalents of KST batch windows • software.amazon.awssdk:s3 in build.gradle for Object Storage file archiving | 45 | 2.2-T01, 2.2-T03, 2.2-T04, 2.2-T05, 2.2-T07 | ARCH | SAD-02
2.2-T18 | shared-libs | 2.2 | 2. Architecture & Technical Foundation | Service/module structure & scaffolding | 1 | Scaffold Spring Boot skeleton: services/scheme-adapter-zeropay | scheme-adapter-zeropay is the Anti-Corruption Layer (ACL) for ZeroPay/KFTC. It implements SchemeAdapter interface: CPM relay via KFTC HTTPS REST, batch file SFTP exchange (all ZP00xx types), merchant/QR sync ingestion into MongoDB local store (AD-12: payment-time lookups query local DB, not ZeroPay live API). | • Create services/scheme-adapter-zeropay/build.gradle with spring-boot-starter-web, spring-boot-starter-data-mongodb, spring-boot-starter-webflux, lib-errors, lib-events, lib-observability dependencies; add com.github.mwiede:jsch:0.2.17 for SFTP client • Create com.gme.pay.zeropay.ZeroPayAdapterApplication @SpringBootApplication main class with server.port=8091 • Create com.gme.pay.zeropay.adapter.SchemeAdapter interface in services/scheme-adapter-zeropay with methods: CpmAuthResponse authoriseCpm(CpmAuthRequest), MpmSubmitResponse submitMpm(MpmSubmitRequest), void generateBatchFiles(String batchType, LocalDate date), List parseBatchFile(String batchType, byte[] content), void processMerchantSync(byte[] fileContent), Map healthCheck() • Create @Service com.gme.pay.zeropay.adapter.ZeroPayAdapterImpl implements SchemeAdapter with all methods throwing UnsupportedOperationException (stubs for WBS 4.x) • Create application.yml with spring.data.mongodb.uri placeholder, zeropay.sftp.host, zeropay.sftp.port=22, zeropay.sftp.username placeholders (no credentials) | services/scheme-adapter-zeropay/src/main/java/com/gme/pay/zeropay/ZeroPayAdapterApplication.java, SchemeAdapter.java, ZeroPayAdapterImpl.java; application.yml | • ./gradlew :services:scheme-adapter-zeropay:bootJar succeeds • SchemeAdapter interface has exactly 6 methods as listed • ZeroPayAdapterImpl implements SchemeAdapter (no ZeroPay-specific base class on the interface side) • spring-boot-starter-data-mongodb present (AD-12: merchant/QR in local MongoDB) • SFTP library (jsch) present in build.gradle | 45 | 2.2-T01, 2.2-T03, 2.2-T04, 2.2-T07 | ARCH | SAD-02
2.2-T19 | shared-libs | 2.2 | 2. Architecture & Technical Foundation | Service/module structure & scaffolding | 1 | Scaffold Spring Boot skeleton: services/merchant-qr (Merchant and QR Data) | merchant-qr stores merchant and QR data in MongoDB, synced daily from ZeroPay SFTP files ZP0041, ZP0043, ZP0045, ZP0047, ZP0051, ZP0053, ZP0055. Payment-time lookups query this local store (AD-12). Exposes GET /internal/merchants/{merchantId} for the Transaction Orchestrator. No PostgreSQL. | • Create services/merchant-qr/build.gradle with spring-boot-starter-web, spring-boot-starter-data-mongodb, lib-errors, lib-events, lib-observability dependencies • Create com.gme.pay.merchantqr.MerchantQrApplication @SpringBootApplication main class with server.port=8092 • Create @Document com.gme.pay.merchantqr.document.MerchantDocument: merchantId (String @Id), merchantName, merchantCategoryCode, schemeId, status, qrCodes (List<String>), franchiseCode, syncedAt (Instant), lastSyncFile (String) • Create stub @RestController com.gme.pay.merchantqr.controller.MerchantLookupController with GET /internal/merchants/{merchantId} returning Optional<MerchantDocument> (empty optional placeholder) • Add spring.data.mongodb.uri placeholder in application.yml | services/merchant-qr/src/main/java/com/gme/pay/merchantqr/MerchantQrApplication.java, MerchantDocument.java, MerchantLookupController.java; application.yml | • ./gradlew :services:merchant-qr:bootJar succeeds • MerchantDocument annotated @Document (Spring Data MongoDB) • syncedAt Instant field present (tracks last SFTP sync timestamp) • No PostgreSQL or Flyway dependency (MongoDB only) • GET /internal/merchants/{merchantId} endpoint present at exact path | 30 | 2.2-T01, 2.2-T03, 2.2-T04, 2.2-T07 | ARCH | SAD-02
2.2-T20 | shared-libs | 2.2 | 2. Architecture & Technical Foundation | Service/module structure & scaffolding | 1 | Scaffold Spring Boot skeleton: services/revenue-ledger | revenue-ledger records GME revenue attribution per committed transaction: collection_margin_usd (m_a leg) and payout_margin_usd (m_b leg), plus service_charge revenue. revenue_entries rows are immutable (written at CommitTransaction rate-lock). Fee-share defaults 70% GME / 30% scheme per spec. PostgreSQL only. | • Create services/revenue-ledger/build.gradle with spring-boot-starter-web, spring-boot-starter-data-jpa, flyway-core, lib-money, lib-errors, lib-events, lib-persistence, lib-observability dependencies • Create com.gme.pay.revenueledger.RevenueLedgerApplication @SpringBootApplication main class with server.port=8093 • Create services/revenue-ledger/src/main/resources/db/migration/V001__create_revenue_entries.sql: table revenue_entries (id UUID PK, txn_ref VARCHAR NOT NULL UNIQUE, partner_id UUID NOT NULL, scheme_id UUID, direction VARCHAR, collection_margin_usd NUMERIC(20,10) NOT NULL, payout_margin_usd NUMERIC(20,10) NOT NULL, service_charge NUMERIC(20,6) NOT NULL, service_charge_currency CHAR(3) NOT NULL, fee_share_gme_pct NUMERIC(6,4) NOT NULL DEFAULT 0.7000, fee_share_scheme_pct NUMERIC(6,4) NOT NULL DEFAULT 0.3000, settled_at TIMESTAMPTZ, created_at TIMESTAMPTZ NOT NULL) • Create stub @Service com.gme.pay.revenueledger.service.RevenueEntryService with placeholder @Transactional recordRevenue(String txnRef, ...) method | services/revenue-ledger/src/main/java/com/gme/pay/revenueledger/RevenueLedgerApplication.java; V001__create_revenue_entries.sql; application.yml | • ./gradlew :services:revenue-ledger:bootJar succeeds • txn_ref UNIQUE ensures one revenue row per committed transaction • fee_share_gme_pct DEFAULT 0.7000 and fee_share_scheme_pct DEFAULT 0.3000 match 70:30 spec • collection_margin_usd and payout_margin_usd are NUMERIC(20,10) not FLOAT • service_charge_currency CHAR(3) present (service charge denominated in Settle-A currency per spec AD-10) | 35 | 2.2-T01, 2.2-T02, 2.2-T03, 2.2-T04, 2.2-T05, 2.2-T07 | ARCH | SAD-02
2.2-T21 | shared-libs | 2.2 | 2. Architecture & Technical Foundation | Service/module structure & scaffolding | 1 | Scaffold Spring Boot skeleton: services/reporting-compliance (Reporting and BOK) | reporting-compliance generates BOK FX1014 and FX1015 regulatory reports from locked transaction values, and partner/period revenue summaries. Reads PostgreSQL (transactions and revenue_entries tables via JDBC or JPA). Phase 1: manual-trigger via POST. Output files archived to S3/MinIO. Server port 8094. | • Create services/reporting-compliance/build.gradle with spring-boot-starter-web, spring-boot-starter-data-jpa, flyway-core, software.amazon.awssdk:s3, lib-money, lib-errors, lib-observability dependencies • Create com.gme.pay.reporting.ReportingComplianceApplication @SpringBootApplication main class with server.port=8094 • Create services/reporting-compliance/src/main/resources/db/migration/V001__create_report_runs.sql: table report_runs (id UUID PK, report_type VARCHAR NOT NULL, period_start DATE NOT NULL, period_end DATE NOT NULL, status VARCHAR NOT NULL, output_file_key VARCHAR, record_count INT, generated_by VARCHAR, created_at TIMESTAMPTZ, completed_at TIMESTAMPTZ, CONSTRAINT chk_status CHECK(status IN (PENDING,RUNNING,COMPLETED,FAILED))) • Create stub @RestController com.gme.pay.reporting.controller.ReportController with POST /internal/reports/bok/fx1015 and POST /internal/reports/bok/fx1014, both returning 202 Accepted | services/reporting-compliance/src/main/java/com/gme/pay/reporting/ReportingComplianceApplication.java; V001__create_report_runs.sql; application.yml | • ./gradlew :services:reporting-compliance:bootJar succeeds • report_runs.report_type present (distinguishes FX1014, FX1015, REVENUE_SUMMARY) • Both POST /internal/reports/bok/fx1015 and /fx1014 endpoints exist returning 202 • output_file_key column present for S3/MinIO archive key reference • software.amazon.awssdk:s3 in build.gradle | 30 | 2.2-T01, 2.2-T03, 2.2-T05, 2.2-T07 | ARCH | SAD-02
2.2-T22 | shared-libs | 2.2 | 2. Architecture & Technical Foundation | Service/module structure & scaffolding | 1 | Scaffold Spring Boot skeleton: services/ops-bff (Ops/Partner BFF) | ops-bff is the Backend-for-Frontend aggregation layer for the React/Next.js Admin and Partner Portals. It aggregates calls to config-registry, txn-mgmt, prefunding, and reporting-compliance. OAuth2/JWT for Ops users. No own database; uses WebClient for downstream service calls. Server port 8095. | • Create services/ops-bff/build.gradle with spring-boot-starter-web, spring-boot-starter-oauth2-resource-server, spring-boot-starter-webflux, lib-errors, lib-api-contracts, lib-observability dependencies • Create com.gme.pay.opsbff.OpsBffApplication @SpringBootApplication main class with server.port=8095 • Create @Configuration com.gme.pay.opsbff.config.WebClientConfig providing @Bean WebClient instances for config-registry, txn-mgmt, prefunding, reporting (URLs from application.yml properties bff.services.config-registry-url etc.) • Create stub @RestController com.gme.pay.opsbff.controller.DashboardController with GET /bff/v1/dashboard returning 200 placeholder • Add bff.services.config-registry-url, bff.services.txn-mgmt-url, bff.services.prefunding-url, bff.services.reporting-url placeholders in application.yml | services/ops-bff/src/main/java/com/gme/pay/opsbff/OpsBffApplication.java, WebClientConfig.java, DashboardController.java; application.yml | • ./gradlew :services:ops-bff:bootJar succeeds • spring-boot-starter-oauth2-resource-server in build.gradle (JWT/Ops auth) • WebClientConfig declares 4 named @Bean WebClient instances • No Flyway or PostgreSQL dependency (BFF owns no database) • All 4 downstream URL placeholder properties in application.yml | 35 | 2.2-T01, 2.2-T03, 2.2-T06, 2.2-T07 | ARCH | SAD-02
2.2-T23 | shared-libs | 2.2 | 2. Architecture & Technical Foundation | Service/module structure & scaffolding | 1 | Scaffold Spring Cloud Gateway module with route definitions and HMAC filter stub | The API Gateway (Spring Cloud Gateway) handles TLS termination, per-partner rate limiting, idempotency-key enforcement, and routing to all backend services. Partner API versioned at /v1/. A stub HmacSignatureFilter (GatewayFilter) logs the request and delegates signature validation to auth-identity in WBS 3.x. | • Create services/api-gateway/build.gradle with spring-cloud-starter-gateway, spring-boot-starter-actuator, spring-boot-starter-data-redis (rate limiter), lib-errors, lib-observability dependencies; import Spring Cloud BOM aligned with Spring Boot 3.x • Create com.gme.pay.gateway.ApiGatewayApplication @SpringBootApplication main class with server.port=8080 • Create src/main/resources/application.yml with spring.cloud.gateway.routes: /v1/rates/** -> http://rate-fx:8083, /v1/payments/** -> http://payment-executor:8086, /v1/payments/cpm/** -> http://payment-executor:8086, /admin/** -> http://ops-bff:8095, /internal/auth/** -> http://auth-identity:8082 • Create @Component com.gme.pay.gateway.filter.HmacSignatureFilter implements GatewayFilter: logs X-Partner-ID and X-Timestamp headers, calls chain.filter(exchange) (full validation deferred) • Add spring.cloud.gateway.default-filters: [RequestRateLimiter with redis-rate-limiter.replenish-rate=100 placeholder] in application.yml | services/api-gateway/src/main/java/com/gme/pay/gateway/ApiGatewayApplication.java, HmacSignatureFilter.java; src/main/resources/application.yml with routes | • ./gradlew :services:api-gateway:bootJar succeeds • application.yml defines routes for /v1/rates/**, /v1/payments/**, /admin/**, /internal/auth/** • HmacSignatureFilter implements GatewayFilter and is @Component • Spring Cloud BOM imported (not manually versioned) • spring-boot-starter-data-redis present for RequestRateLimiter backend | 40 | 2.2-T01, 2.2-T03, 2.2-T07 | ARCH | SAD-02
2.2-T24 | shared-libs | 2.2 | 2. Architecture & Technical Foundation | Service/module structure & scaffolding | 1 | Create docker-compose.yml for local dev infrastructure | Local dev needs Postgres 16, MongoDB 7, Redis 7, MinIO (S3-compatible), and HashiCorp Vault dev server. Kafka is defined as an optional profile (Phase 1 uses outbox only). Each service's application.yml placeholder URLs must match the docker-compose service names and ports. | • Create docker-compose.yml at repo root with services: postgres (postgres:16-alpine, port 5432, env POSTGRES_DB=gmepayplus), mongo (mongo:7, port 27017), redis (redis:7-alpine, port 6379), minio (minio/minio:latest, ports 9000 and 9001, command server /data --console-address :9001), vault (hashicorp/vault:1.17, port 8200, env VAULT_DEV_ROOT_TOKEN_ID=dev-root-token, cap_add: [IPC_LOCK]) • Add a kafka block (confluentinc/cp-kafka:7.6.0 with zookeeper) using profiles: [kafka] so it is NOT started by default • Create .env.example at repo root with placeholder values: POSTGRES_USER, POSTGRES_PASSWORD, MINIO_ROOT_USER, MINIO_ROOT_PASSWORD, VAULT_DEV_ROOT_TOKEN_ID • Verify docker-compose config parses without error | docker-compose.yml and .env.example at repo root | • docker-compose config passes without YAML error • postgres service uses image postgres:16-alpine mapped to port 5432 • kafka block has profiles: [kafka] so docker-compose up without --profile kafka does NOT start Kafka • minio service exposes port 9001 for web console • vault service has VAULT_DEV_ROOT_TOKEN_ID env var and cap_add: [IPC_LOCK] | 40 | 2.2-T01 | ARCH | SAD-02
2.2-T25 | shared-libs | 2.2 | 2. Architecture & Technical Foundation | Service/module structure & scaffolding | 1 | Wire Flyway migrations per-service and verify with Testcontainers (config-registry) | Each Spring Boot service owns its own Flyway migration set under src/main/resources/db/migration/. The shared V001__create_outbox_events.sql from lib-persistence must also be applied per service. Verify with a Testcontainers integration test in services/config-registry that all migrations apply cleanly against a real Postgres 16 container. | • Add to services/config-registry/build.gradle testImplementation: org.testcontainers:testcontainers-bom, org.testcontainers:postgresql, and spring-boot-starter-test • Create test class com.gme.pay.configregistry.FlywayMigrationTest annotated @SpringBootTest @Testcontainers • Declare @Container static PostgreSQLContainer<?> postgres = new PostgreSQLContainer<>(postgres:16-alpine) • Annotate with @DynamicPropertySource to set spring.datasource.url/username/password from container properties • Assert tables exist after migration: query information_schema.tables for schemes, partners, rules, outbox_events • Run ./gradlew :services:config-registry:test to confirm green | services/config-registry/src/test/java/com/gme/pay/configregistry/FlywayMigrationTest.java | • Test uses Postgres 16 Testcontainer (not H2 or embedded DB) • @DynamicPropertySource sets datasource from container (no hardcoded localhost) • Test asserts tables schemes, partners, rules, outbox_events all exist post-migration • ./gradlew :services:config-registry:test passes green • No H2 dependency in services/config-registry/build.gradle | 45 | 2.2-T08, 2.2-T05 | ARCH | SAD-02
2.2-T26 | shared-libs | 2.2 | 2. Architecture & Technical Foundation | Service/module structure & scaffolding | 1 | Add transactional Outbox poller to services/payment-executor | The transactional Outbox pattern: a @Scheduled poller queries outbox_events where published=false (up to 50 rows), calls EventPublisher.publish() for each, then marks published=true — all in a single @Transactional boundary. An InProcessEventPublisher logs the event (Phase 1 stub; Kafka impl added in integration phase without changing poller code). | • Add @EnableScheduling to PaymentExecutorApplication • Create com.gme.pay.paymentexecutor.outbox.InProcessEventPublisher @Service implements EventPublisher: publish() logs event type and eventId at INFO level • Create com.gme.pay.paymentexecutor.outbox.OutboxPoller @Component: inject OutboxRepository and EventPublisher; @Scheduled(fixedDelay=5000) method pollAndPublish() annotated @Transactional • In pollAndPublish(): call outboxRepository.findTop50ByPublishedFalseOrderByCreatedAtAsc(), for each call eventPublisher.publish(), then set event.setPublished(true) and save • Set spring.scheduling.enabled=true in application.yml | services/payment-executor/src/main/java/com/gme/pay/paymentexecutor/outbox/OutboxPoller.java; InProcessEventPublisher.java | • OutboxPoller.pollAndPublish() annotated @Scheduled(fixedDelay=5000) (5-second poll) • pollAndPublish() annotated @Transactional (publish + mark-published is atomic) • Batch size capped at 50 rows per poll cycle • InProcessEventPublisher implements EventPublisher from lib-events with zero Kafka imports • ./gradlew :services:payment-executor:compileJava succeeds | 40 | 2.2-T13, 2.2-T05, 2.2-T04 | ARCH | SAD-02
2.2-T27 | shared-libs | 2.2 | 2. Architecture & Technical Foundation | Service/module structure & scaffolding | 1 | Unit test: Outbox poller atomicity on partial publish failure | If EventPublisher.publish() throws on the 3rd event in a batch of 5, the @Transactional boundary must roll back all published=true updates so all 5 events remain unpublished and are retried on the next poll cycle. This guards against partial delivery causing silent data loss. | • Create services/payment-executor/src/test/java/com/gme/pay/paymentexecutor/outbox/OutboxPollerAtomicityTest.java • Use @ExtendWith(MockitoExtension.class); inject mock OutboxRepository and a mock EventPublisher that throws RuntimeException on the 3rd invocation • In test fail_on_third_publish_rolls_back_all: seed 5 unpublished OutboxEvent stubs from repository, call pollAndPublish(), expect RuntimeException, then assert no outbox row had setPublished(true) persisted • In test all_succeed_marks_all_published: mock EventPublisher succeeds for all 5; assert setPublished(true) called 5 times and outboxRepository.saveAll() called once • Assert: no Kafka class imported anywhere in OutboxPoller or InProcessEventPublisher | services/payment-executor/src/test/java/com/gme/pay/paymentexecutor/outbox/OutboxPollerAtomicityTest.java | • fail_on_third_publish_rolls_back_all: after RuntimeException, verify zero calls to outboxRepository.saveAll() with published=true rows • all_succeed_marks_all_published: verify outboxRepository.saveAll() called with 5 rows all published=true • Mock EventPublisher used, not real InProcessEventPublisher • No Testcontainers needed (pure unit test with mocks) • ./gradlew :services:payment-executor:test passes | 35 | 2.2-T26 | ARCH | SAD-02
2.2-T28 | shared-libs | 2.2 | 2. Architecture & Technical Foundation | Service/module structure & scaffolding | 1 | Scaffold Helm chart stubs for all 16 services | GitOps via Argo CD requires a Helm chart per service. Each chart must parameterise image.repository, image.tag, replicaCount, and service.port. api-gateway and payment-executor require replicaCount: 2 minimum (HA). A library base chart provides the shared deployment/service templates. | • Create helm/base/ Chart.yaml (apiVersion v2, type: library) with shared templates/deployment.yaml (uses .Values.image.repository, .Values.image.tag, .Values.replicaCount, .Values.service.port) and templates/service.yaml • Create helm/<service>/ directories for all 16 services: api-gateway (port 8080, replicas 2), config-registry (8081), auth-identity (8082), rate-fx (8083), qr-service (8084), smart-router (8085), payment-executor (8086, replicas 2), txn-mgmt (8087), prefunding (8088), notification-webhook (8089), settlement-recon (8090), scheme-adapter-zeropay (8091), merchant-qr (8092), revenue-ledger (8093), reporting-compliance (8094), ops-bff (8095); each with Chart.yaml and values.yaml • In each values.yaml set replicaCount: 1 (or 2 for api-gateway and payment-executor), image.repository: ghcr.io/gme/<service>, image.tag: latest • Create helm/argocd-apps/api-gateway.yaml as a stub Argo CD Application CRD pointing to helm/api-gateway/ | helm/ directory with base library chart and 16 service chart stubs; helm/argocd-apps/api-gateway.yaml | • api-gateway values.yaml has replicaCount: 2 • payment-executor values.yaml has replicaCount: 2 • helm/base/Chart.yaml has type: library • helm/argocd-apps/api-gateway.yaml contains kind: Application (Argo CD CRD kind) • All 16 service charts have a values.yaml with the correct service.port matching the assigned port | 45 | 2.2-T01 | ARCH | SAD-02
2.3-T01 | platform-infra | 2.3 | 2. Architecture & Technical Foundation | Coding standards, repo, branching, CI scaffold | 1 | Scaffold Gradle monorepo root: settings.gradle, root build.gradle, Gradle wrapper | GMEPay+ is a Gradle multi-module Java 21 monorepo. The root settings.gradle must declare every service and shared-lib module; the root build.gradle sets the global Java 21 toolchain, Spring Boot 3.x BOM import, and Spotless plugin declaration (not yet configured). All downstream modules inherit from this root. Gradle wrapper pinned to Gradle 8.x. | • Create root settings.gradle listing all modules: lib-money, lib-errors, lib-api-contracts, lib-events, lib-persistence, services/auth-identity, services/qr-service, services/smart-router, services/rate-fx, services/payment-executor, services/transaction-mgmt, services/prefunding-balance, services/notification-webhook, services/settlement-recon, services/revenue-accounting, services/reporting-compliance, services/merchant-qr, services/scheme-adapter-zeropay, services/config-registry, services/gateway, services/ops-bff • Create root build.gradle: allprojects { group='com.gme.pay'; version='0.1.0-SNAPSHOT' }; subprojects block importing Spring Boot 3.x BOM via platform() and applying java plugin with languageVersion = JavaLanguageVersion.of(21) • Apply the Spotless plugin (version pinned, e.g. 6.25.0) in root build.gradle without configuration yet • Add gradle/wrapper/gradle-wrapper.properties pinned to Gradle 8.x • Verify: ./gradlew projects lists all declared modules with zero resolution errors | settings.gradle, build.gradle, gradle/wrapper/gradle-wrapper.properties at repo root | • ./gradlew projects outputs all 21 declared module names without errors • Java toolchain block specifies languageVersion = JavaLanguageVersion.of(21) • Spring Boot 3.x BOM is imported via platform() so individual Spring deps need no version • Spotless plugin is declared in root build.gradle (no rules yet, just the plugin application) | 30 |  | ARCH | OPS-13
2.3-T02 | platform-infra | 2.3 | 2. Architecture & Technical Foundation | Coding standards, repo, branching, CI scaffold | 1 | Create build.gradle for each shared library module (lib-*) | Five shared library modules are used across all services: lib-money (BigDecimal money helpers, JSR-354 Moneta), lib-errors (canonical error model + LoggingContextFilter), lib-api-contracts (OpenAPI-generated DTOs from openapi/partner-api.yaml), lib-events (domain events + Avro/JSON schemas), lib-persistence (common JPA/Flyway utils). Each is a plain java-library (no Spring Boot application plugin). All versions resolved from the root BOM. | • Create libs/lib-money/build.gradle: apply java-library; depend on org.javamoney:moneta for JSR-354; no Spring dependency • Create libs/lib-errors/build.gradle: apply java-library; depend on jackson-databind and ch.qos.logback:logstash-logback-encoder:7.x • Create libs/lib-api-contracts/build.gradle: apply java-library; add openapi-generator Gradle plugin configured to generate from openapi/partner-api.yaml into build/generated/src/main/java • Create libs/lib-events/build.gradle: apply java-library; add Avro codegen plugin; jackson-databind • Create libs/lib-persistence/build.gradle: apply java-library; depend on spring-data-jpa, flyway-core, postgresql driver | libs/lib-money/build.gradle, libs/lib-errors/build.gradle, libs/lib-api-contracts/build.gradle, libs/lib-events/build.gradle, libs/lib-persistence/build.gradle | • ./gradlew :lib-money:build compiles with zero errors • ./gradlew :lib-api-contracts:generateOpenApiCode produces Java DTOs under build/generated from openapi/partner-api.yaml • lib-persistence depends on flyway-core and spring-data-jpa but does NOT apply org.springframework.boot application plugin • No version numbers are hardcoded in any lib build.gradle (all resolved from root BOM) | 35 | 2.3-T01 | ARCH | OPS-13
2.3-T03 | platform-infra | 2.3 | 2. Architecture & Technical Foundation | Coding standards, repo, branching, CI scaffold | 1 | Create build.gradle template and Application stub for each Spring Boot service module | Each of the 15 Spring Boot microservices needs a build.gradle that applies org.springframework.boot and io.spring.dependency-management plugins, declares spring-boot-starter-web, spring-boot-starter-actuator, spring-boot-starter-data-jpa (where DB is used), micrometer-registry-prometheus, and relevant lib-* project dependencies. A shared services/service-conventions.gradle captures common blocks. services/gateway applies spring-cloud-gateway instead of starter-web. | • Create services/service-conventions.gradle with: apply plugin org.springframework.boot, apply java, import Spring Boot BOM, declare common dependencies (starter-web, starter-actuator, micrometer-registry-prometheus, lib-errors, lib-api-contracts, JUnit 5, Testcontainers BOM for integrationTestImplementation scope) • For each service create services/<name>/build.gradle applying service-conventions.gradle plus service-specific extras (rate-fx adds lib-money, lib-events; gateway applies spring-cloud-gateway; all DB-using services add lib-persistence) • Add src/main/java/com/gme/pay/<service>/<Service>Application.java stub with @SpringBootApplication in each module • Verify ./gradlew :services:rate-fx:bootJar produces a non-zero JAR | services/service-conventions.gradle; services/rate-fx/build.gradle as reference; @SpringBootApplication stub for each service | • ./gradlew :services:rate-fx:bootJar succeeds and produces a non-zero-byte JAR • All services resolve lib-money, lib-errors, lib-api-contracts, lib-events, lib-persistence with no version conflicts • services/gateway build.gradle applies spring-cloud-gateway NOT spring-boot-starter-web • micrometer-registry-prometheus appears in the runtime classpath of every service | 45 | 2.3-T02 | ARCH | OPS-13
2.3-T04 | platform-infra | 2.3 | 2. Architecture & Technical Foundation | Coding standards, repo, branching, CI scaffold | 1 | Configure Spotless with Google Java Format and licence header enforcement | OPS-13 §4.1 stage-1 gate: zero lint errors. Spotless (already declared in 2.3-T01) must enforce: Google Java Format 1.22.0 for all *.java files; trailing-newline and no-trailing-whitespace for *.gradle and *.yaml; a GMEPay+ licence header (from config/licence-header.txt) prepended to every Java source. The spotlessCheck task must fail on any violation to block the CI build stage. | • Create config/licence-header.txt containing the one-line copyright header: // Copyright (c) GME Remittance. GMEPay+ Platform. All rights reserved. • In root build.gradle spotless {} block: java { googleJavaFormat('1.22.0'); licenseHeaderFile('config/licence-header.txt') }; add groovyGradle { trimTrailingWhitespace(); endWithNewline() } and yaml { trimTrailingWhitespace(); endWithNewline() } • Run ./gradlew spotlessApply on all existing stubs to auto-fix violations • Run ./gradlew spotlessCheck to confirm exit 0 • Verify: removing the licence header from one file causes spotlessCheck to exit non-zero | Spotless configuration block in root build.gradle; config/licence-header.txt | • ./gradlew spotlessCheck exits 0 after spotlessApply on all initial stubs • Removing the licence header from any .java file causes ./gradlew spotlessCheck to exit non-zero • Introducing a non-Google-Java-Format indent causes ./gradlew spotlessCheck to exit non-zero • A YAML file with trailing spaces fails spotlessCheck | 30 | 2.3-T01 | ARCH | OPS-13
2.3-T05 | platform-infra | 2.3 | 2. Architecture & Technical Foundation | Coding standards, repo, branching, CI scaffold | 1 | Define branching strategy: documentation and branch protection rules | OPS-13 §4.2 mandates trunk-based development. Four branch types: feature/<ticket> (PR to main; dev-only manual deploy), main (always deployable; auto-deploy to int on merge), release/<version> (cut from main; auto-deploy to staging), hotfix/<ticket> (emergency; fast-track to prod via two senior engineer approvals). OPS-13 §4.3: main and release/* require PR approval and passing status checks; direct push to main is blocked. | • Create docs/BRANCHING.md documenting the four branch types, naming conventions (feature/2.3-T05, release/1.0.0, hotfix/GME-999), deploy targets, and hotfix fast-track rule (2 senior engineers + on-call approval; post-deployment review mandatory) • Configure branch protection on main: require 1 PR approval, require status checks spotlessCheck and unit-test, no direct push, no force-push • Configure branch protection on release/*: same as main plus require linear history • Add a CI step named branch-name-check that rejects any push/PR from a branch not matching feature/*, release/*, hotfix/*, or main using a regex assertion | docs/BRANCHING.md; branch protection rules on main and release/*; CI branch-name-check step | • Direct push to main is rejected by the remote with protected-branch error • A PR to main with a failing spotlessCheck status is blocked from merging • A branch named my-fix (not matching convention) causes the CI branch-name-check step to fail and report the violation • docs/BRANCHING.md lists all four branch types with deploy targets and the hotfix approval rule | 25 | 2.3-T01 | ARCH | OPS-13
2.3-T06 | platform-infra | 2.3 | 2. Architecture & Technical Foundation | Coding standards, repo, branching, CI scaffold | 1 | Create infra/docker-compose.yml: PostgreSQL 16 and MongoDB 7 for local dev | STACK.md: PostgreSQL 16 for the money path (transactions, prefunding, config, audit) and MongoDB 7 for the merchant/QR store and CQRS projections. docker-compose exposes Postgres on host port 5433 (container 5432) to avoid conflicts; MongoDB on 27017. Named volumes ensure data persists across restarts. Health checks are mandatory so dependent containers wait correctly. | • Create infra/docker-compose.yml with postgres service: image postgres:16-alpine, POSTGRES_DB=gmepayplus, POSTGRES_USER=gmepay, POSTGRES_PASSWORD=${POSTGRES_PASSWORD:-localdev}, ports 5433:5432, volume pgdata:/var/lib/postgresql/data, healthcheck: pg_isready -U gmepay -d gmepayplus with interval 5s retries 10 • Add mongo service: image mongo:7, ports 27017:27017, volume mongodata:/data/db, healthcheck: mongosh --eval 'db.adminCommand({ping:1})' with interval 5s retries 10 • Create infra/.env.example listing POSTGRES_PASSWORD=localdev MONGO_INITDB_ROOT_PASSWORD=localdev • Verify: docker compose up -d postgres mongo; docker compose ps shows both Healthy within 30 seconds | infra/docker-compose.yml with postgres and mongo services; infra/.env.example | • docker compose up -d exits 0 and both containers reach healthy status within 30 seconds • psql -h localhost -p 5433 -U gmepay gmepayplus -c 'SELECT 1' succeeds • mongosh --port 27017 --eval 'db.adminCommand({ping:1})' returns {ok:1} • Named volumes pgdata and mongodata are declared so data survives docker compose restart | 30 |  | ARCH | OPS-13
2.3-T07 | platform-infra | 2.3 | 2. Architecture & Technical Foundation | Coding standards, repo, branching, CI scaffold | 1 | Add Redis 7, Kafka 3.7 (KRaft), and Schema Registry to docker-compose.yml | STACK.md: Redis for rate-quote TTL (default 60s), config cache, and idempotency keys. Apache Kafka (KRaft mode, no ZooKeeper) for the integration-phase outbox-to-Kafka transport; Schema Registry for Avro event schemas in lib-events. Phase 1 uses in-process outbox but Kafka must be in docker-compose so developers can wire the integration phase without infra changes. Bitnami Kafka 3.7 image. | • Add redis service to infra/docker-compose.yml: image redis:7-alpine, ports 6379:6379, healthcheck: redis-cli ping with interval 5s retries 10 • Add kafka service: image bitnami/kafka:3.7, KRaft env vars (KAFKA_CFG_NODE_ID=1, KAFKA_CFG_PROCESS_ROLES=controller+broker, KAFKA_CFG_LISTENERS=PLAINTEXT://:9092 CONTROLLER://:9093, KAFKA_CFG_ADVERTISED_LISTENERS=PLAINTEXT://localhost:9092), ports 9092:9092, healthcheck: kafka-topics.sh --bootstrap-server localhost:9092 --list with retries 15 • Add schema-registry service: image confluentinc/cp-schema-registry:7.6, SCHEMA_REGISTRY_KAFKASTORE_BOOTSTRAP_SERVERS=kafka:9092, ports 8081:8081, depends_on kafka • Verify all five services (postgres, mongo, redis, kafka, schema-registry) show healthy in docker compose ps | infra/docker-compose.yml updated with redis, kafka, schema-registry services | • redis-cli -p 6379 ping returns PONG • kafka-topics.sh --bootstrap-server localhost:9092 --list exits 0 (no error) • curl -s http://localhost:8081/subjects returns [] on fresh start • All five services show healthy in docker compose ps within 90 seconds of docker compose up | 35 | 2.3-T06 | ARCH | OPS-13
2.3-T08 | platform-infra | 2.3 | 2. Architecture & Technical Foundation | Coding standards, repo, branching, CI scaffold | 1 | Add HashiCorp Vault 1.16 and MinIO with bucket init to docker-compose.yml | STACK.md: Vault/KMS for secrets and field-level encryption (all services read partner credentials via Vault). MinIO (S3-compatible) for ZeroPay SFTP file archive (/gmepay/batch/), BOK reports, and tax invoice archives. Vault runs in dev mode (VAULT_DEV_ROOT_TOKEN_ID=localdev) on port 8200. MinIO on ports 9000 (API) and 9001 (console). A minio-init service creates required buckets at startup. | • Add vault service: image hashicorp/vault:1.16, VAULT_DEV_ROOT_TOKEN_ID=localdev, ports 8200:8200, cap_add [IPC_LOCK], healthcheck: vault status -address http://localhost:8200 with retries 10 • Add minio service: image minio/minio:latest, command: server /data --console-address :9001, MINIO_ROOT_USER=minioadmin, MINIO_ROOT_PASSWORD=minioadmin, ports 9000:9000 9001:9001, healthcheck: curl -f http://localhost:9000/minio/health/live • Add minio-init service (image minio/mc) that runs after minio healthy and executes: mc alias set local http://minio:9000 minioadmin minioadmin; mc mb local/gmepay-batch-files local/gmepay-reports local/gmepay-archives • Update infra/.env.example with VAULT_DEV_ROOT_TOKEN_ID=localdev MINIO_ROOT_PASSWORD=minioadmin and note these are never used outside local dev | infra/docker-compose.yml with vault and minio services plus minio-init bucket creator; updated infra/.env.example | • vault status -address http://localhost:8200 shows Sealed: false • curl -s http://localhost:9000/minio/health/live returns HTTP 200 • mc ls local shows three buckets: gmepay-batch-files, gmepay-reports, gmepay-archives after minio-init completes • infra/.env.example includes a comment: VAULT_DEV_ROOT_TOKEN_ID is for local dev ONLY - never use in non-dev environments | 35 | 2.3-T07 | ARCH | OPS-13
2.3-T09 | platform-infra | 2.3 | 2. Architecture & Technical Foundation | Coding standards, repo, branching, CI scaffold | 1 | Write infra/README.md: port map, startup, credentials, and reset procedure | Developers need a single reference for the local dev stack. All seven services (Postgres, Mongo, Redis, Kafka, Schema Registry, Vault, MinIO) must be covered with ports, health-check one-liners, default credentials, and the reset procedure. OPS-13 §5.3 notes the dev environment uses DEBUG log level, manual rate updates, and Vault in dev mode. | • Create infra/README.md with a Prerequisites section (Docker 24+, docker compose v2) • Add a port map table: Postgres 5433, Mongo 27017, Redis 6379, Kafka 9092, Schema Registry 8081, Vault 8200, MinIO API 9000, MinIO console 9001 • Document startup: cd infra; cp .env.example .env; docker compose up -d; docker compose ps • Document per-service health-check one-liners for copy-paste verification • Add a Vault local-dev-only warning: 'Token localdev is for local development only. Never use in int/staging/prod.' • Add reset procedure: docker compose down -v destroys all volumes; use only to start fresh | infra/README.md | • README contains a port map table covering all 8 ports across the 7 services • Startup section shows the docker compose up -d command with --env-file or cp .env.example .env step • Vault local-dev-only warning is present and prominent • Reset procedure with docker compose down -v is documented with a warning about data loss | 20 | 2.3-T08 | ARCH | OPS-13
2.3-T10 | platform-infra | 2.3 | 2. Architecture & Technical Foundation | Coding standards, repo, branching, CI scaffold | 1 | Create Flyway baseline migration V001__create_schema_baseline.sql in lib-persistence | OPS-13 §4.6: all schema changes use versioned Flyway migrations in db/migrations/, applied automatically before the new app version starts, backward-compatible and additive-only. lib-persistence holds the shared Flyway configuration and migration directory. The baseline creates the gmepay schema namespace and the audit_log table (used by all services to record actor, event_type, entity_id, previous_value, new_value per the audit mandate). | • Create libs/lib-persistence/src/main/resources/db/migration/V001__create_schema_baseline.sql: CREATE SCHEMA IF NOT EXISTS gmepay; CREATE TABLE gmepay.audit_log (id UUID PRIMARY KEY DEFAULT gen_random_uuid(), actor VARCHAR(255) NOT NULL, event_type VARCHAR(100) NOT NULL, entity_type VARCHAR(100), entity_id VARCHAR(255), previous_value JSONB, new_value JSONB, created_at TIMESTAMPTZ NOT NULL DEFAULT NOW()) • Create libs/lib-persistence/src/main/java/com/gme/pay/persistence/FlywayConfig.java: @Configuration class setting spring.flyway.locations=classpath:db/migration, baseline-on-migrate=true, table=flyway_schema_history • Add a META-INF/spring/org.springframework.boot.autoconfigure.AutoConfiguration.imports entry for FlywayConfig so any service including lib-persistence auto-runs migrations • Document the naming rule: migrations must use V{NNN}__ prefix and be additive-only; never rename or drop a column in the same release as the referencing code change | libs/lib-persistence/src/main/resources/db/migration/V001__create_schema_baseline.sql; libs/lib-persistence/src/main/java/com/gme/pay/persistence/FlywayConfig.java | • After Flyway runs against local Postgres, SELECT * FROM gmepay.audit_log returns 0 rows (table exists, empty) • flyway_schema_history table contains exactly one row for V001 with success=true • INSERT INTO gmepay.audit_log(actor,...) with actor=NULL raises NOT NULL constraint violation • Running Flyway migrate twice on the same DB produces no error (idempotent) | 35 | 2.3-T06 | ARCH | OPS-13
2.3-T11 | platform-infra | 2.3 | 2. Architecture & Technical Foundation | Coding standards, repo, branching, CI scaffold | 1 | Configure Spring Boot application.yml template and profile strategy for all services | OPS-13 §4.7 and §5.3: runtime config injected via env vars (no secrets in images). Each service needs a base application.yml (default profile) and environment overrides for dev and prod. Common settings: spring.datasource (Postgres on localhost:5433 for dev), spring.data.mongodb, spring.data.redis, spring.flyway.locations, management.endpoints. Secrets referenced as ${ENV_VAR} placeholders in prod profile. | • Create services/service-conventions/src/main/resources/application.yml: server.port=8080; management.endpoints.web.exposure.include=health,info,prometheus; management.tracing.sampling.probability=1.0; spring.flyway.locations=classpath:db/migration; spring.application.name=${SERVICE_NAME:unnamed} • Create application-dev.yml: logging.level.root=DEBUG; spring.datasource.url=jdbc:postgresql://localhost:5433/gmepayplus; spring.datasource.username=gmepay; spring.datasource.password=localdev; spring.data.mongodb.uri=mongodb://localhost:27017/gmepayplus; spring.data.redis.host=localhost; spring.data.redis.port=6379 • Create application-prod.yml: all values as ${GMEPAY_DB_URL}, ${GMEPAY_DB_PASSWORD}, ${GMEPAY_MONGO_URI}, ${GMEPAY_REDIS_HOST} (zero literal secrets) • Each service's own application.yml sets spring.application.name to the service slug (e.g. rate-fx) | services/service-conventions/src/main/resources/application.yml; application-dev.yml; application-prod.yml | • Running any service with --spring.profiles.active=dev picks up spring.datasource.url=jdbc:postgresql://localhost:5433/gmepayplus • application-prod.yml contains zero literal credential values (all ${...} placeholders) • management.endpoints.web.exposure.include contains prometheus in all profiles • spring.flyway.locations is set to classpath:db/migration in the base application.yml | 30 | 2.3-T03 | ARCH | OPS-13
2.3-T12 | platform-infra | 2.3 | 2. Architecture & Technical Foundation | Coding standards, repo, branching, CI scaffold | 1 | Create CI pipeline: stage 1 (build + Spotless lint) and stage 2 (unit tests, Jacoco 80%) | OPS-13 §4.1 stage-1 gate: zero lint errors. Stage-2 gate: all tests pass, coverage >= 80%. Pipeline targets GitHub Actions (or equivalent CI). Java 21 (Temurin) from actions/setup-java. Gradle build cache reduces repeat compile times. JUnit XML reports uploaded as artifacts for test result visibility. | • Create .github/workflows/ci.yml with trigger on push to feature/*, main, release/*, hotfix/* • Add job build-and-lint: actions/setup-java@v4 (java-version: 21, distribution: temurin); cache ~/.gradle/caches and ~/.gradle/wrapper; run ./gradlew spotlessCheck compileJava --build-cache • Add job unit-test: depends on build-and-lint; run ./gradlew test jacocoTestReport jacocoTestCoverageVerification; configure jacocoTestCoverageVerification with minimum 0.80 per module; upload JUnit XML reports as artifacts • Add job branch-name-check: runs on push; validates branch name against regex ^(feature¦release¦hotfix)/.+$¦^main$ and fails with a descriptive message if not matching | .github/workflows/ci.yml with build-and-lint, unit-test, and branch-name-check jobs | • A PR introducing a Spotless violation causes build-and-lint to fail before unit-test runs • A module with coverage below 80% causes jacocoTestCoverageVerification to fail the unit-test job • A branch named my-fix causes branch-name-check to fail with a message listing valid patterns • JUnit XML artifacts are uploaded and visible in the CI run summary | 40 | 2.3-T04, 2.3-T03 | ARCH | OPS-13
2.3-T13 | platform-infra | 2.3 | 2. Architecture & Technical Foundation | Coding standards, repo, branching, CI scaffold | 1 | Add CI stage 3: SAST (SpotBugs + find-sec-bugs), OWASP CVE scan, and Gitleaks secrets scan | OPS-13 §4.1 stage-3 gate: no critical/high CVEs; no secrets detected. Three tools: SpotBugs with com.h3xstream.findsecbugs:findsecbugs-plugin:1.12.0 for SAST (fail on MEDIUM+ security bugs), OWASP Dependency-Check Gradle plugin (failBuildOnCVSS=7.0), and Gitleaks for secrets-leak detection. All three must pass before the artifact-build stage. | • Add spotbugs Gradle plugin to root build.gradle with find-sec-bugs plugin at version 1.12.0; configure spotbugsMain { effort = 'max'; reportLevel = 'medium' }; set ignoreFailures = false • Add org.owasp.dependencycheck Gradle plugin; set dependencyCheck { failBuildOnCVSS = 7.0; format = 'HTML'; outputDirectory = 'build/reports/dependency-check' } • Add security-scan job to .github/workflows/ci.yml depending on unit-test; steps: (1) download gitleaks binary; (2) run gitleaks detect --source . --no-git --exit-code 1; (3) ./gradlew spotbugsMain; (4) ./gradlew dependencyCheckAnalyze; upload OWASP HTML report as artifact • Test: introduce a dummy AWS_SECRET_ACCESS_KEY = 'AKIAIOSFODNN7EXAMPLE' in a temp file; confirm gitleaks step fails | .github/workflows/ci.yml security-scan job; SpotBugs and OWASP Dependency-Check plugin config in root build.gradle | • Committing a dummy AWS access key pattern causes the gitleaks step to fail and block the pipeline • A dependency with CVE CVSS >= 7.0 causes ./gradlew dependencyCheckAnalyze to exit non-zero • SpotBugs with find-sec-bugs flags a simulated SQL injection (string concatenation in a JDBC query) as MEDIUM and fails the build • OWASP HTML report artifact is downloadable from the security-scan CI run | 40 | 2.3-T12 | ARCH | OPS-13
2.3-T14 | platform-infra | 2.3 | 2. Architecture & Technical Foundation | Coding standards, repo, branching, CI scaffold | 1 | Add CI stage 4: integration test job using Testcontainers (Postgres, Mongo, Redis, Kafka) | OPS-13 §4.1 stage 4: ephemeral env with DB + dependencies; all integration tests pass. Testcontainers starts PostgreSQL 16, MongoDB 7, Redis 7, and Kafka 3.7 containers inside the CI runner. Tests live in a separate integrationTest Gradle source set (src/integration-test/java). An AbstractIntegrationTest base class wires Testcontainers @DynamicPropertySource into Spring context. | • Add integrationTest source set to service-conventions.gradle: sourceSets { integrationTest { java.srcDir 'src/integration-test/java'; compileClasspath += main.output; runtimeClasspath += main.output } }; task integrationTest(type: Test) { useJUnitPlatform() } • Add Testcontainers BOM org.testcontainers:testcontainers-bom:1.19.x to root build.gradle for integrationTestImplementation scope; add testcontainers, postgresql, mongodb, kafka sub-artifacts • Create libs/lib-persistence/src/integration-test/java/com/gme/pay/persistence/AbstractIntegrationTest.java: @Testcontainers class starting PostgreSQLContainer postgres:16-alpine and MongoDBContainer mongo:7; @DynamicPropertySource injects spring.datasource.url and spring.data.mongodb.uri • Add integration-test job to .github/workflows/ci.yml: depends on security-scan; runs ./gradlew integrationTest; requires Docker socket (uses: docker/setup-buildx-action or service container); uploads test reports | integrationTest source set in service-conventions.gradle; AbstractIntegrationTest.java; CI integration-test job | • ./gradlew :lib-persistence:integrationTest starts a real postgres:16-alpine container via Testcontainers, runs Flyway V001 migration against it, and the test passes • Integration test job in CI completes without any manually installed Postgres or Mongo on the runner • AbstractIntegrationTest uses @DynamicPropertySource to inject the Testcontainers JDBC URL into spring.datasource.url • A failing integration test blocks the artifact-build stage | 45 | 2.3-T13, 2.3-T10 | ARCH | OPS-13
2.3-T15 | platform-infra | 2.3 | 2. Architecture & Technical Foundation | Coding standards, repo, branching, CI scaffold | 1 | Add CI stage 5: multi-stage Docker image build, tag, sign, and push to artifact registry | OPS-13 §4.1 stage 5: build container image tagged <git-sha>+<branch>+<semver>, push to artifact registry, sign image. Multi-stage Dockerfile: stage 1 eclipse-temurin:21-jdk-alpine runs ./gradlew bootJar; stage 2 eclipse-temurin:21-jre-alpine copies the JAR. Non-root user, cosign keyless signing. Registry: ghcr.io/gme-pay/<service>:<tag>. | • Create infra/Dockerfile.service as a multi-stage template: FROM eclipse-temurin:21-jdk-alpine AS build; COPY . .; RUN ./gradlew :services:${SERVICE}:bootJar -x test; FROM eclipse-temurin:21-jre-alpine; RUN addgroup -S app && adduser -S app -G app; COPY --from=build services/${SERVICE}/build/libs/*.jar app.jar; USER app; ENTRYPOINT [java, -jar, app.jar] • Add artifact-build job to .github/workflows/ci.yml: depends on integration-test; matrix over all service names; uses docker/build-push-action with --build-arg SERVICE=<name>; tags: ghcr.io/gme-pay/$SERVICE:$GIT_SHA, ghcr.io/gme-pay/$SERVICE:$BRANCH-latest (and :<semver> if on release/*) • Add cosign signing step after push: cosign sign --yes ghcr.io/gme-pay/$SERVICE@$DIGEST (uses OIDC keyless signing) • Verify: docker run --rm ghcr.io/gme-pay/rate-fx:$GIT_SHA java -version outputs Java 21 | infra/Dockerfile.service; .github/workflows/ci.yml artifact-build job with matrix and cosign signing | • Final image base is eclipse-temurin:21-jre-alpine (not JDK) reducing image size • Image tagged with the git SHA is pushed to ghcr.io for every commit to main • cosign verify ghcr.io/gme-pay/rate-fx@$DIGEST succeeds using the OIDC-issued certificate • Container runs as non-root user (USER app is set in Dockerfile stage 2) | 45 | 2.3-T14 | ARCH | OPS-13
2.3-T16 | platform-infra | 2.3 | 2. Architecture & Technical Foundation | Coding standards, repo, branching, CI scaffold | 1 | Add CI stage 6: automated deploy to int environment via Argo CD and smoke tests | OPS-13 §4.1 stage 6: automated deploy to int on merge to main; gate is smoke tests passing. OPS-13 §4.2: main -> int is fully automated, no human gate. Deployment via Argo CD GitOps: CI updates image tag in helm/values-int.yaml; Argo CD syncs. Smoke tests hit /actuator/health on each service via the int ingress. Gate fails if any service returns non-200. | • Create helm/values-int.yaml with image.tag: __IMAGE_TAG__ placeholder per service • Add deploy-to-int job to .github/workflows/ci.yml: triggered only on push to main; depends on artifact-build; uses yq to substitute __IMAGE_TAG__ with the git SHA in helm/values-int.yaml; commits and pushes the updated file to trigger Argo CD sync • Add smoke-test step: wait for argocd app wait gmepay-int --health --timeout 300; then curl --fail http://<service>.int.gme.internal/actuator/health for each service • Gate: job fails if any /actuator/health returns non-200 within 60 seconds of Argo CD sync | helm/values-int.yaml; CI deploy-to-int job with Argo CD sync and smoke-test gate | • Merging a feature branch to main triggers deploy-to-int automatically without manual approval • Argo CD sync updates the running image in the gmepay-int namespace to the new git SHA within 5 minutes • Smoke test step returns HTTP 200 from /actuator/health for rate-fx and auth-identity services • A service that fails to start causes /actuator/health to return non-200 and fails the deploy-to-int job | 40 | 2.3-T15 | ARCH | OPS-13
2.3-T17 | platform-infra | 2.3 | 2. Architecture & Technical Foundation | Coding standards, repo, branching, CI scaffold | 1 | Add CI stage 7: staging deploy on release/* with manual approval gate | OPS-13 §4.1 stage 7: automated deploy to staging on release/* cut; UAT tests run; manual approval gate required before prod. OPS-13 §4.3: staging requires stakeholder sign-off. The GitHub Actions environment named staging has required reviewers configured, so the deploy job pauses until approved. | • Create helm/values-staging.yaml with the same structure as values-int.yaml • Add deploy-to-staging job to .github/workflows/ci.yml: triggered only on push to release/*; environment: staging (which has required-reviewers protection); depends on artifact-build; updates helm/values-staging.yaml with the git SHA via yq; commits and pushes • Add Argo CD sync wait for gmepay-staging app after the approval gate passes • Add a run-smoke-tests step hitting /actuator/health on the staging ingress for each service after Argo CD sync • Configure the staging GitHub Actions environment with at least one required reviewer (Release Manager role) | helm/values-staging.yaml; CI deploy-to-staging job with environment-based approval gate | • Cutting a release/1.0.0 branch triggers the deploy-to-staging job • The job pauses at the approval gate and does not update helm/values-staging.yaml until a reviewer approves • Rejecting the approval gate leaves helm/values-staging.yaml unchanged and does not trigger Argo CD sync • Smoke tests run after successful Argo CD sync and fail the job if any service is unhealthy | 35 | 2.3-T16 | ARCH | OPS-13
2.3-T18 | platform-infra | 2.3 | 2. Architecture & Technical Foundation | Coding standards, repo, branching, CI scaffold | 1 | Implement automated rollback on failed smoke tests after deployment | OPS-13 §4.4: if post-deployment smoke tests fail within 5 minutes, the pipeline automatically redeploys the previous image tag. Rollback reads the prior deployed SHA from Argo CD app history. DB migrations are forward-only (per §4.6); rollback only affects the application image. A Slack/Teams notification is sent on auto-rollback. | • In deploy-to-int and deploy-to-staging CI jobs, capture the previous image SHA before applying the new values file: run argocd app history gmepay-int --output json ¦ jq -r '.[0].revision' and store as PREV_SHA • Add an on-failure composite step after the smoke-test step: (1) restore helm/values-<env>.yaml to PREV_SHA using yq; (2) commit and push the reverted file; (3) wait for Argo CD re-sync; (4) send a notification via webhook with environment name, new-SHA, previous-SHA, and failure reason • Document in code comments that the rollback does NOT revert DB migrations; if the old code is incompatible with the migrated schema, a hotfix is required (OPS-13 §4.4 procedure) • Add a skip condition: if PREV_SHA is empty (first deploy to this environment), log a warning and skip the rollback step | Rollback on-failure step in deploy-to-int and deploy-to-staging jobs; rollback notification webhook call | • A deliberate /actuator/health failure triggers the on-failure rollback step and reverts the values file to PREV_SHA • Argo CD re-syncs to the previous image after the reverted values file is pushed • Slack/Teams notification message includes both old and new SHA • If no previous deployment exists (PREV_SHA is empty), the rollback step skips with a warning rather than failing | 35 | 2.3-T17 | ARCH | OPS-13
2.3-T19 | platform-infra | 2.3 | 2. Architecture & Technical Foundation | Coding standards, repo, branching, CI scaffold | 1 | Create Helm chart skeleton for GMEPay+ services with Deployment, HPA, and Ingress templates | STACK.md: Kubernetes deployment via GitOps with Argo CD, Helm charts. A shared helm/charts/gmepay-service/ chart provides common Deployment, Service, HPA, and Ingress templates reused by all 15 services via per-service values files. Liveness probe: /actuator/health/liveness; readiness: /actuator/health/readiness. HPA: minReplicas=2, maxReplicas=10, target CPU 70%. runAsNonRoot: true in all pods. | • Create helm/charts/gmepay-service/Chart.yaml: apiVersion v2, name gmepay-service, version 0.1.0 • Create templates/deployment.yaml: image from values.image.repository:values.image.tag; env from ConfigMap + secretKeyRef; securityContext.runAsNonRoot: true; livenessProbe.httpGet.path=/actuator/health/liveness; readinessProbe.httpGet.path=/actuator/health/readiness • Create templates/hpa.yaml: minReplicas: 2, maxReplicas: 10, targetCPUUtilizationPercentage: 70 • Create templates/service.yaml and templates/ingress.yaml with standard annotations • Create helm/values-base.yaml with defaults; add per-service stub values files under helm/values-<service>-int.yaml • Run helm lint helm/charts/gmepay-service/ and confirm exit 0 | helm/charts/gmepay-service/ chart directory; helm/values-base.yaml | • helm lint helm/charts/gmepay-service/ exits 0 with no warnings • helm template output includes a Deployment with securityContext.runAsNonRoot: true • HPA resource has minReplicas: 2 and maxReplicas: 10 • Liveness probe path is /actuator/health/liveness and readiness probe path is /actuator/health/readiness | 40 | 2.3-T01 | ARCH | OPS-13
2.3-T20 | platform-infra | 2.3 | 2. Architecture & Technical Foundation | Coding standards, repo, branching, CI scaffold | 1 | Create Argo CD Application manifests for int, staging, and prod environments | STACK.md and OPS-13: GitOps via Argo CD. Each environment (int, staging, prod) needs an Argo CD Application CRD. int: automated sync with prune and selfHeal. staging: manual sync (requires approval). prod: fully manual. All three point to the same Helm chart and repo, differing only in values files and destination namespace. | • Create deploy/argocd/gmepay-int.yaml: Application spec.source.repoURL=<monorepo>, spec.source.helm.valueFiles=['helm/values-base.yaml','helm/values-int.yaml'], destination.namespace=gmepay-int, syncPolicy.automated: {prune: true, selfHeal: true} • Create deploy/argocd/gmepay-staging.yaml: same structure for gmepay-staging namespace; syncPolicy: {} (no automated) • Create deploy/argocd/gmepay-prod.yaml: gmepay-prod namespace; syncPolicy: {} (no automated); add ignoreDifferences for image.tag so accidental drift does not auto-apply • Document: kubectl apply -f deploy/argocd/ on the Argo CD management cluster registers all three environments | deploy/argocd/gmepay-int.yaml; deploy/argocd/gmepay-staging.yaml; deploy/argocd/gmepay-prod.yaml | • gmepay-int Application has syncPolicy.automated.prune: true and selfHeal: true • gmepay-staging Application has no syncPolicy.automated block (manual trigger only) • gmepay-prod Application has no syncPolicy.automated block and adds ignoreDifferences for image.tag • All three Application manifests reference the same spec.source.repoURL and chart path | 30 | 2.3-T19 | ARCH | OPS-13
2.3-T21 | platform-infra | 2.3 | 2. Architecture & Technical Foundation | Coding standards, repo, branching, CI scaffold | 1 | Add OpenTelemetry auto-instrumentation and Prometheus actuator endpoint to all services | STACK.md observability: OpenTelemetry -> Prometheus+Grafana (metrics), ELK (logs), Jaeger (tracing). OPS-13 §7.3: trace_id generated at the load balancer, propagated through every service call and batch job step. Each service exports OTLP spans and exposes /actuator/prometheus. The OTel exporter endpoint defaults to localhost:4318 for local dev. | • Add to service-conventions.gradle: implementation 'io.opentelemetry.instrumentation:opentelemetry-spring-boot-starter:2.x' and implementation 'io.micrometer:micrometer-tracing-bridge-otel' • Add to application.yml: management.tracing.sampling.probability=1.0; management.otlp.tracing.endpoint=${OTEL_EXPORTER_OTLP_ENDPOINT:http://localhost:4318/v1/traces}; management.endpoints.web.exposure.include: health,info,prometheus,metrics • Create libs/lib-errors/src/main/java/com/gme/pay/errors/LoggingContextFilter.java: @Component OncePerRequestFilter that reads the W3C traceparent header, extracts trace_id and span_id, puts them in MDC, puts X-Partner-Id into MDC as partner_id, and calls MDC.clear() in finally • Verify GET /actuator/prometheus returns Prometheus-formatted metrics | OTel and Micrometer dependencies in service-conventions.gradle; LoggingContextFilter.java in lib-errors; updated application.yml | • GET /actuator/prometheus returns text/plain Prometheus metrics including http_server_requests_seconds_count • A request with a valid W3C traceparent header results in trace_id appearing in MDC and JSON log output • otel.service.name is set equal to spring.application.name in application.yml • OTEL_EXPORTER_OTLP_ENDPOINT defaults to http://localhost:4318/v1/traces so local dev works without a collector | 35 | 2.3-T11 | ARCH | OPS-13
2.3-T22 | platform-infra | 2.3 | 2. Architecture & Technical Foundation | Coding standards, repo, branching, CI scaffold | 1 | Configure structured JSON logging via logstash-logback-encoder with all OPS-13 required fields | OPS-13 §7.2: all services emit JSON-structured logs with mandatory fields: timestamp (ISO-8601 UTC), level, service, env, trace_id, span_id, partner_id (when present), transaction_id (when present), event, message. Use Logback with ch.qos.logback:logstash-logback-encoder:7.x. In prod profile, sensitive fields (collection_amount, prefund_balance, rate components) must NOT appear in log output; only IDs are logged. | • Add ch.qos.logback:logstash-logback-encoder:7.x to service-conventions.gradle runtimeClasspath • Create libs/lib-errors/src/main/resources/logback-spring.xml: STDOUT appender using LogstashEncoder with customFields for service=${spring.application.name} and env=${spring.profiles.active}; root level DEBUG in dev, INFO in prod • LoggingContextFilter (from 2.3-T21) also sets MDC keys transaction_id (from X-Transaction-Id header if present) and clears all MDC keys in a finally block • Create a prod-specific logback-spring-prod.xml that removes any appender encoder fields matching collection_amount, prefund_balance, cost_rate_coll, cost_rate_pay to prevent sensitive data leakage | logback-spring.xml in lib-errors resources; prod-specific appender config; LoggingContextFilter updated with transaction_id MDC | • A log line from any service running locally is valid JSON containing all 8 required fields: timestamp, level, service, env, trace_id, span_id, event, message • trace_id in the log matches the trace_id from the W3C traceparent request header • Running with prod profile: the string collection_amount does not appear in any log line • MDC is cleared after each request so partner_id from one request does not leak into a subsequent request's log entries | 35 | 2.3-T21 | ARCH | OPS-13
2.3-T23 | platform-infra | 2.3 | 2. Architecture & Technical Foundation | Coding standards, repo, branching, CI scaffold | 1 | Create Prometheus alert rules YAML for API SLO, prefunding, and pool integrity alerts | OPS-13 §7.5: alert catalog defines P1-P4 alert rules. Implement as infra/prometheus/alert-rules.yaml. Key rules: API p95 latency >500ms for 5m (severity warning); 5xx error rate >1% for 5m (severity critical); prefunding balance <10000 USD (warning); <2000 USD (critical); pool identity assertion failure (critical, any increase in gmepay_pool_identity_violations_total). Validate with promtool. | • Create infra/prometheus/alert-rules.yaml with three groups: api-slo, prefunding, financial-integrity • api-slo group: ApiP95LatencyBreach expr histogram_quantile(0.95, rate(http_server_requests_seconds_bucket[5m])) > 0.5 for 5m severity warning; ApiErrorRateHigh expr rate(http_server_requests_seconds_count{status=~'5..'}[5m]) / rate(http_server_requests_seconds_count[5m]) > 0.01 for 5m severity critical • prefunding group: LowPrefundingBalance expr gmepay_prefunding_balance_usd < 10000 severity warning; CriticalPrefundingBalance expr gmepay_prefunding_balance_usd < 2000 severity critical; labels include partner_id • financial-integrity group: PoolIdentityBreach expr increase(gmepay_pool_identity_violations_total[5m]) > 0 for 0m (instant) severity critical • Run promtool check rules infra/prometheus/alert-rules.yaml and confirm exit 0 | infra/prometheus/alert-rules.yaml with api-slo, prefunding, financial-integrity alert groups | • promtool check rules infra/prometheus/alert-rules.yaml exits 0 with no errors • ApiErrorRateHigh has severity: critical and for: 5m • CriticalPrefundingBalance threshold is 2000 matching OPS-13 §7.5.2 • PoolIdentityBreach fires on any increase in gmepay_pool_identity_violations_total (no delay, for: 0m) | 35 | 2.3-T21 | ARCH | OPS-13
2.3-T24 | platform-infra | 2.3 | 2. Architecture & Technical Foundation | Coding standards, repo, branching, CI scaffold | 1 | Write Gradle TestKit tests for CI pipeline rules: Spotless, Jacoco threshold, branch-name check | The CI build logic itself needs test coverage. Gradle TestKit tests in buildSrc assert: spotlessCheck fails deterministically on a malformatted Java file; jacocoTestCoverageVerification fails when coverage drops below 80%; the branch-name regex correctly accepts and rejects inputs. These tests live in buildSrc/src/test/java/com/gme/pay/build/ and run as part of ./gradlew :buildSrc:test. | • Create buildSrc/src/test/java/com/gme/pay/build/SpotlessCheckTest.java: uses GradleRunner to run spotlessCheck on a temp project containing a .java file missing the licence header; assert BuildResult outcome is FAILED • Create buildSrc/src/test/java/com/gme/pay/build/JacocoCoverageTest.java: uses GradleRunner on a project with a class at 0% coverage; configure 80% minimum threshold; assert jacocoTestCoverageVerification is FAILED • Create buildSrc/src/test/java/com/gme/pay/build/BranchNameValidationTest.java: unit-test the branch-name regex (^(feature¦release¦hotfix)/.+$¦^main$) with @ParameterizedTest vectors: feature/2.3-T01 -> accept; release/1.0.0 -> accept; main -> accept; my-fix -> reject; FEATURE/abc -> reject • Run ./gradlew :buildSrc:test to confirm all three test classes pass | buildSrc/src/test/java/com/gme/pay/build/ with SpotlessCheckTest, JacocoCoverageTest, BranchNameValidationTest | • SpotlessCheckTest GradleRunner returns FAILED outcome when the .java file is missing the licence header • JacocoCoverageTest confirms 80% threshold blocks a 0-coverage project (FAILED outcome) • BranchNameValidationTest: my-fix is rejected; feature/2.3-T24-build-tests is accepted; main is accepted; FEATURE/foo is rejected • ./gradlew :buildSrc:test exits 0 (all three test classes pass) | 40 | 2.3-T04, 2.3-T12 | ARCH | OPS-13
2.3-T25 | platform-infra | 2.3 | 2. Architecture & Technical Foundation | Coding standards, repo, branching, CI scaffold | 1 | Write integration test verifying Flyway V001 migration against Testcontainers Postgres 16 | OPS-13 §4.6 and STACK.md: all schema changes via Flyway, applied automatically before app start, additive-only. The integration test in lib-persistence verifies V001 applies cleanly to a fresh postgres:16-alpine container, that flyway_schema_history records V001, and that the audit_log table enforces the NOT NULL constraint on actor. This test runs in the integrationTest Gradle source set. | • Create libs/lib-persistence/src/integration-test/java/com/gme/pay/persistence/FlywayMigrationIT.java annotated @Testcontainers • Declare @Container PostgreSQLContainer<?> postgres = new PostgreSQLContainer<>(DockerImageName.parse('postgres:16-alpine')) • Configure a DataSource from postgres.getJdbcUrl() and run Flyway.configure().dataSource(...).load().migrate() • Assert: MigrationInfoService shows 1 applied migration (V001); SELECT COUNT(*) FROM gmepay.audit_log returns 0 (table exists, empty); INSERT with all fields succeeds; INSERT with actor=null raises DataIntegrityViolationException • Verify ./gradlew :lib-persistence:integrationTest passes with no locally installed Postgres | libs/lib-persistence/src/integration-test/java/com/gme/pay/persistence/FlywayMigrationIT.java | • Test passes using Testcontainers postgres:16-alpine with no local Postgres required • flyway_schema_history table contains exactly one row for V001 with success=true • INSERT INTO gmepay.audit_log with actor=null raises a constraint violation caught as DataIntegrityViolationException • Running the migration twice on the same container raises no error (idempotent) | 35 | 2.3-T14, 2.3-T10 | ARCH | OPS-13
2.3-T26 | platform-infra | 2.3 | 2. Architecture & Technical Foundation | Coding standards, repo, branching, CI scaffold | 1 | Write local stack smoke integration test for Postgres, Mongo, Redis, and Kafka connectivity | Developers need confidence that the docker-compose local stack is reachable from a Spring Boot test. This test uses @SpringBootTest(webEnvironment=NONE) with the dev profile and asserts DataSource (Postgres on port 5433), MongoTemplate (port 27017), StringRedisTemplate (port 6379), and KafkaTemplate (port 9092) all connect and respond successfully. Test is skipped when SKIP_LOCAL_STACK_TESTS=true. | • Create services/integration-smoke-test/src/integration-test/java/com/gme/pay/smoke/LocalStackSmokeIT.java • Annotate @SpringBootTest(webEnvironment=NONE) @ActiveProfiles('dev'); inject DataSource, MongoTemplate, StringRedisTemplate, KafkaTemplate<String,String> • Test methods: assertPostgresConnects (jdbcTemplate.queryForObject('SELECT 1', Integer.class) == 1); assertMongoConnects (mongoTemplate.getDb().runCommand(new Document('ping',1)).get('ok')==1.0); assertRedisConnects (redisTemplate.opsForValue().set('smoke','ok'); then get returns 'ok'); assertKafkaConnects (kafkaTemplate.send('smoke-test','ping').get(5, SECONDS) does not throw) • Annotate class @DisabledIfEnvironmentVariable(named='SKIP_LOCAL_STACK_TESTS', matches='true') | services/integration-smoke-test/src/integration-test/java/com/gme/pay/smoke/LocalStackSmokeIT.java | • With docker-compose stack running, all four assertions pass (Postgres SELECT 1, Mongo ping, Redis set/get, Kafka send) • With SKIP_LOCAL_STACK_TESTS=true the entire test class is skipped rather than failed • Test uses dev profile so spring.datasource.url resolves to jdbc:postgresql://localhost:5433/gmepayplus • KafkaTemplate assertion uses .get(5, SECONDS) (blocking with timeout) to avoid false positives from async completion | 35 | 2.3-T11, 2.3-T08 | ARCH | OPS-13
2.3-T27 | platform-infra | 2.3 | 2. Architecture & Technical Foundation | Coding standards, repo, branching, CI scaffold | 1 | Create CONTRIBUTING.md: coding standards, branch workflow, local dev setup, no-code-for-config rule | OPS-13 §5.1 generic-build mandate: adding a scheme, partner, or rule requires only a DB config entry - zero code change, zero redeployment. STACK.md and Spotless/Flyway rules must be captured for developer onboarding. CONTRIBUTING.md is the single authoritative onboarding reference for every developer joining the project. | • Create CONTRIBUTING.md at repo root with sections: Prerequisites (Java 21 JDK, Docker 24+, docker compose v2; no local Postgres or Mongo required), Local Dev Setup (cd infra; cp .env.example .env; docker compose up -d; cd ..; ./gradlew :services:rate-fx:bootRun --args='--spring.profiles.active=dev'), Branch Naming (table with feature/, release/, hotfix/, main types and deploy targets) • PR Checklist section: ./gradlew spotlessCheck must exit 0; ./gradlew test must pass all modules; if schema changes, a new V{NNN}__*.sql migration must be present and additive-only; no hardcoded scheme, partner, margin, or routing values in application code • No-code-for-config rule (verbatim): Adding a QR Scheme, Partner, margin rule, service charge, or routing rule requires only a DB config entry via the Admin System. It must never require a code change or redeployment. A deployment is required only for: bug fixes, new API capabilities, new batch file types, or infrastructure changes. • Module map table listing all modules (lib-* and services/*), their language, persistence layer, and one-line purpose; link to infra/README.md for port map | CONTRIBUTING.md at repo root | • CONTRIBUTING.md has a Prerequisites section listing Java 21 and Docker 24+ (no local Postgres required) • PR Checklist includes ./gradlew spotlessCheck and the Flyway additive-only migration rule • No-code-for-config rule is stated verbatim and references Admin System as the change mechanism • Module map table lists all 21 modules with their persistence layer (PostgreSQL / MongoDB / Redis / none) | 20 | 2.3-T09, 2.3-T04, 2.3-T05 | ARCH | OPS-13
2.4-T01 | shared-libs | 2.4 | 2. Architecture & Technical Foundation | Cross-cutting libs: money, currency, errors | 1 | Create lib-money Gradle module skeleton (Java 21, Spring Boot 3.x BOM) | GMEPay+ is a Gradle multi-module monorepo (root settings.gradle, one module per service/lib). WBS 2.4 delivers cross-cutting libs: lib-money and lib-errors. lib-money will hold BigDecimal money types, ISO-4217 currency scale, and rounding helpers. This ticket bootstraps the empty module so subsequent tickets have a compile target. Package root: com.gme.pay.money. | • Add 'libs/lib-money' entry to root settings.gradle • Create libs/lib-money/build.gradle: Java 21 toolchain, Spring Boot 3.x BOM dependencyManagement, no spring-boot-plugin (plain library jar), JUnit 5 test dependency • Add libs/lib-money/src/main/java/com/gme/pay/money/package-info.java • Run ./gradlew :libs:lib-money:compileJava and confirm exit 0 | libs/lib-money/build.gradle and libs/lib-money/src/main/java/com/gme/pay/money/package-info.java | • ./gradlew :libs:lib-money:compileJava exits 0 • Module appears in ./gradlew projects output • build.gradle declares no floating-point-friendly JSON libs without explicit exclusion • No spring-boot-starter-web or spring-boot-starter-data-jpa in lib-money dependencies | 20 |  | BE | RATE-04, API-05
2.4-T02 | shared-libs | 2.4 | 2. Architecture & Technical Foundation | Cross-cutting libs: money, currency, errors | 1 | Create lib-errors Gradle module skeleton (Java 21, Spring Boot 3.x BOM) | lib-errors holds the canonical API-05 §8.1 error envelope used by every GMEPay+ service. Error JSON: {error:{code,message,request_id,details:[{field,issue}]}}. This ticket creates the empty Gradle module under libs/lib-errors so downstream tickets can add exception classes and the @RestControllerAdvice. Package root: com.gme.pay.errors. | • Add 'libs/lib-errors' entry to root settings.gradle • Create libs/lib-errors/build.gradle: Java 21 toolchain, Spring Boot 3.x BOM, spring-boot-starter-web (compileOnly), JUnit 5 test dependency • Add libs/lib-errors/src/main/java/com/gme/pay/errors/package-info.java • Run ./gradlew :libs:lib-errors:compileJava and confirm exit 0 | libs/lib-errors/build.gradle and libs/lib-errors/src/main/java/com/gme/pay/errors/package-info.java | • ./gradlew :libs:lib-errors:compileJava exits 0 • lib-errors does NOT declare implementation dependency on lib-money (no circular dep) • spring-boot-starter-web is compileOnly so services control the web starter version • Module appears in ./gradlew projects output | 15 |  | BE | RATE-04, API-05
2.4-T03 | shared-libs | 2.4 | 2. Architecture & Technical Foundation | Cross-cutting libs: money, currency, errors | 1 | Implement CurrencyScale: ISO-4217 scale lookup (KRW=0, USD=4, intermediate=8) | DAT-03 §2.1 mandates: KRW stored as BIGINT integer (0 decimal places), USD as DECIMAL(20,4) (4 dp), and all treasury/USD-pool intermediate amounts at DECIMAL(20,8) (8 dp). RATE-04 §A2: non-listed currencies fall back to java.util.Currency.getDefaultFractionDigits(). CurrencyScale is the single source of truth for scale in lib-money. Phase 1 currencies: KRW (0), USD (4), MNT (0). | • Create libs/lib-money/src/main/java/com/gme/pay/money/CurrencyScale.java as a final utility class with private constructor • static int scaleOf(String iso4217): KRW->0, MNT->0, USD->4; fallback Currency.getInstance(code).getDefaultFractionDigits(); throw IllegalArgumentException for unknown code • static int intermediateScale() returns 8 (USD-pool calculations) • Add class-level Javadoc citing DAT-03 §2.1: KRW=0, USD=4, intermediate=8 • Create CurrencyScaleTest (JUnit 5) asserting all four cases | libs/lib-money/src/main/java/com/gme/pay/money/CurrencyScale.java and CurrencyScaleTest.java | • scaleOf('KRW') == 0 • scaleOf('USD') == 4 • scaleOf('EUR') == 2 (ISO 4217 default via java.util.Currency) • intermediateScale() == 8 • scaleOf('NOTACCY') throws IllegalArgumentException containing the bad code | 25 | 2.4-T01 | BE | RATE-04, API-05
2.4-T04 | shared-libs | 2.4 | 2. Architecture & Technical Foundation | Cross-cutting libs: money, currency, errors | 1 | Implement Money immutable value object: BigDecimal amount + ISO-4217 currency | All monetary amounts in GMEPay+ use fixed-precision BigDecimal (never float/double). DAT-03 §2.1: KRW scale=0, USD scale=4. API-05 §2.5: money serialized as {amount: decimal string, currency: ISO-4217}. Money is immutable. Constructor enforces scale == CurrencyScale.scaleOf(currency). Factory Money.of(String, String) parses incoming decimal strings. Arithmetic methods are NOT in this ticket (T05). | • Create libs/lib-money/src/main/java/com/gme/pay/money/Money.java as a final class (or Java record) with fields BigDecimal amount and String currency • Constructor validates: amount non-null, currency exactly 3 uppercase chars, amount.scale() == CurrencyScale.scaleOf(currency) — throws ArithmeticException if scale wrong • Factory Money.of(String amountStr, String currency): parse via new BigDecimal(amountStr); strip extra trailing zeros; re-scale to CurrencyScale.scaleOf(currency) using HALF_UP • Factory Money.ofIntermediate(BigDecimal amount, String currency): scale to intermediateScale() = 8 • Implement equals/hashCode on (amount at canonical scale, currency); toString() = amount.toPlainString() + ' ' + currency • Add MoneyTest (JUnit 5) covering all factory variants and invariants | libs/lib-money/src/main/java/com/gme/pay/money/Money.java and MoneyTest.java | • Money.of('12500','KRW').amount().scale() == 0 and compareTo BigDecimal 12500 == 0 • Money.of('12500.00','KRW') also stores scale-0 12500 • Money.of('36.7500','USD').amount().scale() == 4 • Money.of('1.123456789','USD') rounds to scale 4 via HALF_UP — does NOT throw • Money constructor with null amount throws NullPointerException • Money constructor with 'US' (2-char) currency throws IllegalArgumentException | 35 | 2.4-T03 | BE | RATE-04, API-05
2.4-T05 | shared-libs | 2.4 | 2. Architecture & Technical Foundation | Cross-cutting libs: money, currency, errors | 1 | Implement Money arithmetic: add, subtract, multiply, zero, roundToScale | Rate engine steps require: addition (collection_amount = send_amount + service_charge), subtraction (pool identity check), and multiplication by margin (collection_margin_usd = collection_usd * m_a). Arithmetic must stay in BigDecimal. Rounding applied only at final Step 5 (DAT-03 §2.4). All operations require same currency; cross-currency throws IllegalArgumentException. | • Add Money add(Money other): assert same currency; return new Money with sum at same scale • Add Money subtract(Money other): assert same currency; result may be negative (allow for pool identity delta); scale preserved • Add Money multiply(BigDecimal factor, int resultScale, RoundingMode mode): multiply amount by factor, set scale to resultScale with given mode; return new Money • Add Money roundToScale(): re-scale to CurrencyScale.scaleOf(currency) using HALF_UP • Add static Money zero(String currency): amount = BigDecimal.ZERO at CurrencyScale.scaleOf(currency) • Add MoneyArithmeticTest (JUnit 5) with at least 6 assertions | Updated libs/lib-money/src/main/java/com/gme/pay/money/Money.java with arithmetic and MoneyArithmeticTest.java | • Money.of('10.0000','USD').add(Money.of('5.0000','USD')) = Money(15.0000,USD) • Money.of('10.0000','USD').subtract(Money.of('3.0000','USD')) = Money(7.0000,USD) • add with different currencies throws IllegalArgumentException • Money.of('100.00000000','USD').multiply(new BigDecimal('0.01'),8,HALF_UP) = BigDecimal 1.00000000 at scale 8 • Money.zero('KRW').amount() equals BigDecimal.ZERO at scale 0 | 40 | 2.4-T04 | BE | RATE-04, API-05
2.4-T06 | shared-libs | 2.4 | 2. Architecture & Technical Foundation | Cross-cutting libs: money, currency, errors | 1 | Implement MoneyModule: Jackson serializer/deserializer for Money value objects | API-05 §2.5: money serialized as {amount:'12500.00',currency:'KRW'} using decimal strings — never scientific notation, never floats. KRW '12500' and '12500.00' both accepted on input and stored as scale-0. Registered via META-INF/services Java SPI so Spring Boot auto-detects it without manual @Bean. Applies to all services that include lib-money. | • Create libs/lib-money/src/main/java/com/gme/pay/money/MoneyModule.java extending com.fasterxml.jackson.databind.module.SimpleModule • Implement MoneySerializer extends JsonSerializer<Money>: writes {amount: amount.toPlainString(), currency: currency} • Implement MoneyDeserializer extends JsonDeserializer<Money>: reads {amount, currency} node; constructs Money.of(amountText, currency) • Register MoneyModule via libs/lib-money/src/main/resources/META-INF/services/com.fasterxml.jackson.databind.Module (SPI file listing the fully-qualified class name) • Add MoneyJsonTest (JUnit 5): serialize Money(12500,KRW) assert contains '12500' not '12500.00'; serialize Money(36.7500,USD) assert contains '36.7500'; deserialize round-trip equals original | libs/lib-money/src/main/java/com/gme/pay/money/MoneyModule.java, MoneySerializer.java, MoneyDeserializer.java, META-INF/services/com.fasterxml.jackson.databind.Module | • Serialized KRW 12500 JSON has amount field '12500' with no decimal point • Serialized USD 36.7500 JSON has amount field '36.7500' • No scientific notation in output for any supported currency • Deserializing {amount:'12500.00',currency:'KRW'} produces Money(12500,KRW) at scale 0 • Missing currency field in JSON throws JsonMappingException on deserialization | 35 | 2.4-T05 | BE | RATE-04, API-05
2.4-T07 | shared-libs | 2.4 | 2. Architecture & Technical Foundation | Cross-cutting libs: money, currency, errors | 1 | Implement @ValidCurrency Jakarta Bean Validation annotation and ConstraintValidator | API-05 requires ISO-4217 currency codes on all money fields in request bodies. Spring Boot 3.x uses Jakarta Validation (jakarta.validation.*). The @ValidCurrency annotation rejects unknown codes at the API boundary before arithmetic. Supports optional allowedCodes attribute to restrict to a configured set (e.g. Phase 1: KRW, USD, MNT). | • Create libs/lib-money/src/main/java/com/gme/pay/money/validation/ValidCurrency.java: @Target({FIELD,PARAMETER}), @Retention(RUNTIME), @Constraint(validatedBy=CurrencyValidator.class); attribute String[] allowedCodes() default {} • Create CurrencyValidator implements ConstraintValidator<ValidCurrency,String>: isValid returns false for null, non-3-char, or java.util.Currency.getInstance throws; if allowedCodes non-empty, also check membership • Add CurrencyValidatorTest: valid 'KRW' passes, 'XXX' fails, 'US' fails, @ValidCurrency(allowedCodes={'KRW','USD'}) rejects 'MNT', accepts 'USD' | libs/lib-money/src/main/java/com/gme/pay/money/validation/ValidCurrency.java and CurrencyValidator.java | • @ValidCurrency on 'KRW' passes validation • @ValidCurrency on 'NOTACCY' fails with constraint violation • @ValidCurrency(allowedCodes={'KRW','USD'}) on 'MNT' fails • @ValidCurrency(allowedCodes={'KRW','USD'}) on 'USD' passes • Annotation is applicable to both fields and method parameters | 30 | 2.4-T03 | BE | RATE-04, API-05
2.4-T08 | shared-libs | 2.4 | 2. Architecture & Technical Foundation | Cross-cutting libs: money, currency, errors | 1 | Implement @ValidMoney Jakarta annotation and MoneyValidator for Money value objects | POST request bodies carry Money objects deserialized from JSON. @ValidMoney wraps Money-level invariants: non-null, non-negative amount, 3-char currency, scale matches CurrencyScale. This is distinct from @ValidCurrency (T07) which operates on String fields. Used in rate/payment request DTOs in services like rate-fx and payment-executor. | • Create libs/lib-money/src/main/java/com/gme/pay/money/validation/ValidMoney.java annotation with boolean allowNegative() default false • Create MoneyValidator implements ConstraintValidator<ValidMoney,Money>: checks amount non-null, currency 3 chars, amount.scale() == CurrencyScale.scaleOf(currency), and (allowNegative or amount.signum() >= 0) • Add MoneyValidatorTest: zero KRW passes, negative USD fails by default, negative USD passes allowNegative=true, wrong-scale USD fails | libs/lib-money/src/main/java/com/gme/pay/money/validation/ValidMoney.java and MoneyValidator.java | • Money.of('0','KRW') passes @ValidMoney • Money with negative amount fails @ValidMoney(allowNegative=false) • Money with negative amount passes @ValidMoney(allowNegative=true) • Money with amount.scale() != CurrencyScale.scaleOf(currency) fails @ValidMoney • Constraint violation message includes the currency code | 30 | 2.4-T07 | BE | RATE-04, API-05
2.4-T09 | shared-libs | 2.4 | 2. Architecture & Technical Foundation | Cross-cutting libs: money, currency, errors | 1 | Implement MoneyRounder: single-step currency-native rounding (never mid-pool) | DAT-03 §2.4: intermediate USD-pool values kept at 8 dp; collection_amount rounded once at Step 5 to currency-native scale (KRW=0, USD=4) using HALF_UP. RATE-04 §A1: rounding must NOT be applied mid-pool to avoid compounding error. MoneyRounder enforces this discipline as the only rounding entry point. | • Create libs/lib-money/src/main/java/com/gme/pay/money/MoneyRounder.java as a final utility class • Money roundToFinal(Money raw): apply CurrencyScale.scaleOf(raw.currency()) with RoundingMode.HALF_UP; return new Money at correct scale • Money roundToIntermediate(BigDecimal rawAmount, String currency): scale to intermediateScale()=8 using HALF_UP; return Money.ofIntermediate(rounded, currency) • Add MoneyRounderTest: roundToFinal KRW 12500.49->12500, KRW 12500.50->12501; roundToFinal USD 36.75001->36.7500; roundToIntermediate preserves 8 dp without stripping trailing zeros | libs/lib-money/src/main/java/com/gme/pay/money/MoneyRounder.java and MoneyRounderTest.java | • roundToFinal(Money('12500.49','KRW')) returns Money(12500,KRW) • roundToFinal(Money('12500.50','KRW')) returns Money(12501,KRW) — HALF_UP • roundToFinal(Money('36.75001234','USD')) returns Money(36.7500,USD) • roundToIntermediate returns BigDecimal at scale exactly 8 • Class is stateless — safe for concurrent calls | 30 | 2.4-T05 | BE | RATE-04, API-05
2.4-T10 | shared-libs | 2.4 | 2. Architecture & Technical Foundation | Cross-cutting libs: money, currency, errors | 1 | Implement PoolIdentityChecker: assert collection_usd - margins == payout_usd_cost within 0.01 USD | RATE-04 pool invariant: collection_usd - collection_margin_usd - payout_margin_usd == payout_usd_cost. Tolerance 0.01 USD (one cent). Breach is a hard error: transaction must NOT commit. GmeErrorCode.POOL_IDENTITY_FAILURE (HTTP 500, not retryable). This checker is called after Step 3 in the rate engine and before any prefunding deduction. | • Create libs/lib-money/src/main/java/com/gme/pay/money/PoolIdentityChecker.java • POOL_TOLERANCE = new BigDecimal('0.01') • void check(BigDecimal collectionUsd, BigDecimal collectionMarginUsd, BigDecimal payoutMarginUsd, BigDecimal payoutUsdCost): lhs = collectionUsd - collectionMarginUsd - payoutMarginUsd; diff = lhs.subtract(payoutUsdCost).abs(); if diff.compareTo(POOL_TOLERANCE) > 0 throw GmeException(POOL_IDENTITY_FAILURE, 'Pool identity breach: deviation=' + diff) • lib-money must declare compileOnly dependency on lib-errors for GmeException; lib-errors is always on the runtime classpath via services • Add PoolIdentityCheckerTest: exact match passes; diff=0.009 passes; diff=0.011 throws; diff=-0.011 (negative) throws | libs/lib-money/src/main/java/com/gme/pay/money/PoolIdentityChecker.java and PoolIdentityCheckerTest.java | • diff=0.000 passes without exception • diff=0.009 USD passes (within 0.01 tolerance) • diff=0.011 USD throws GmeException with errorCode POOL_IDENTITY_FAILURE • Exception message contains actual deviation value • PoolIdentityChecker is stateless (no instance fields) | 30 | 2.4-T05, 2.4-T11 | BE | RATE-04, API-05
2.4-T11 | shared-libs | 2.4 | 2. Architecture & Technical Foundation | Cross-cutting libs: money, currency, errors | 1 | Define GmeErrorCode enum with all API-05 §8.2 canonical error codes | API-05 §8.2 lists the full error code catalogue. Each code carries HTTP status and retryable flag. The enum is in lib-errors so all services share it. Codes: VALIDATION_ERROR(400,false), MISSING_IDEMPOTENCY_KEY(400,false), INVALID_SIGNATURE(401,false), INVALID_API_KEY(401,false), TIMESTAMP_OUT_OF_RANGE(401,false), FORBIDDEN(403,false), IP_NOT_ALLOWLISTED(403,false), PAYMENT_NOT_FOUND(404,false), MERCHANT_NOT_FOUND(404,false), MERCHANT_INACTIVE(404,false), SCHEME_NOT_FOUND(404,false), IDEMPOTENCY_KEY_REUSE(422,false), RATE_QUOTE_EXPIRED(422,false), RATE_QUOTE_INVALID(422,false), PARTNER_B_QUOTE_DEVIATION(422,false), PARTNER_B_QUOTE_UNAVAILABLE(422,true), SCHEME_UNAVAILABLE(422,true), PAYMENT_MODE_NOT_SUPPORTED(422,false), DIRECTION_NOT_ENABLED(422,false), CANCEL_NOT_PERMITTED(400,false), INSUFFICIENT_PREFUNDING(402,false), DUPLICATE_PARTNER_TXN_REF(409,false), QR_CODE_DEACTIVATED(422,false), NO_SCHEME_FOR_LOCATION(422,false), APPROVAL_TIMEOUT(422,false), RATE_LIMITED(429,true), INTERNAL_ERROR(500,true), SERVICE_UNAVAILABLE(503,true), POOL_IDENTITY_FAILURE(500,false). | • Create libs/lib-errors/src/main/java/com/gme/pay/errors/GmeErrorCode.java as an enum • Each constant: GmeErrorCode(int httpStatus, boolean retryable) constructor • Add int httpStatus() and boolean retryable() accessors • Add all 29 codes as listed in context • Add GmeErrorCodeTest asserting 5+ specific codes with status and retryable values | libs/lib-errors/src/main/java/com/gme/pay/errors/GmeErrorCode.java | • All 29 error codes present • RATE_QUOTE_EXPIRED.httpStatus() == 422 and retryable() == false • PARTNER_B_QUOTE_UNAVAILABLE.retryable() == true • INSUFFICIENT_PREFUNDING.httpStatus() == 402 • POOL_IDENTITY_FAILURE.httpStatus() == 500 and retryable() == false • INTERNAL_ERROR.retryable() == true | 30 | 2.4-T02 | BE | RATE-04, API-05
2.4-T12 | shared-libs | 2.4 | 2. Architecture & Technical Foundation | Cross-cutting libs: money, currency, errors | 1 | Implement ErrorDetail record and ErrorEnvelope: API-05 §8.1 canonical error JSON structure | API-05 §8.1 error envelope: {error:{code,message,request_id,details:[{field,issue}]}}. Immutable Java records. error.code values come from GmeErrorCode enum (T11). request_id echoes the X-Request-ID response header. details array may be empty and should be omitted from JSON when empty. This ticket creates structural records; the @RestControllerAdvice is in T13. | • Create libs/lib-errors/src/main/java/com/gme/pay/errors/ErrorDetail.java as Java record(String field, String issue) • Create libs/lib-errors/src/main/java/com/gme/pay/errors/ErrorEnvelope.java: outer record wrapping an inner ErrorBody record(String code, String message, String requestId, List<ErrorDetail> details); top-level JSON key must be 'error' • Add @JsonProperty('request_id') on requestId, @JsonInclude(NON_EMPTY) on details list • Add static factory ErrorEnvelope.of(GmeErrorCode code, String message, String requestId) with empty details • Add static factory ErrorEnvelope.withDetails(GmeErrorCode code, String message, String requestId, List<ErrorDetail> details) • Add ErrorEnvelopeJsonTest: serialize ErrorEnvelope.of and assert JSON structure | libs/lib-errors/src/main/java/com/gme/pay/errors/ErrorDetail.java and ErrorEnvelope.java | • Serialized JSON has top-level 'error' key wrapping all fields • request_id serializes as 'request_id' not 'requestId' • Empty details list omitted from JSON (@JsonInclude NON_EMPTY) • ErrorEnvelope.of(RATE_QUOTE_EXPIRED, msg, reqId).error().code() == 'RATE_QUOTE_EXPIRED' • Null code in factory throws NullPointerException | 30 | 2.4-T11 | BE | RATE-04, API-05
2.4-T13 | shared-libs | 2.4 | 2. Architecture & Technical Foundation | Cross-cutting libs: money, currency, errors | 1 | Implement GmeException: RuntimeException carrying GmeErrorCode + optional ErrorDetails | Services throw GmeException. Spring @RestControllerAdvice (T14) catches it and converts to ErrorEnvelope JSON. GmeException must carry a GmeErrorCode so the handler derives HTTP status without switch statements. Static factory GmeException.validation(details) produces VALIDATION_ERROR with a standard message matching API-05 §8.2. | • Create libs/lib-errors/src/main/java/com/gme/pay/errors/GmeException.java extending RuntimeException • Constructors: GmeException(GmeErrorCode code, String message), GmeException(GmeErrorCode code, String message, List<ErrorDetail> details), GmeException(GmeErrorCode code, String message, Throwable cause) • Add GmeErrorCode errorCode() and List<ErrorDetail> details() accessors; details() returns unmodifiable list • Static factory GmeException.validation(List<ErrorDetail> details) sets code=VALIDATION_ERROR, message='One or more request fields failed validation' • Add GmeExceptionTest asserting all constructors and factory | libs/lib-errors/src/main/java/com/gme/pay/errors/GmeException.java and GmeExceptionTest.java | • GmeException(RATE_QUOTE_EXPIRED, msg).errorCode() == RATE_QUOTE_EXPIRED • GmeException.validation(details).errorCode() == VALIDATION_ERROR • details() returns Collections.unmodifiableList • getMessage() returns the message string • GmeException is unchecked (extends RuntimeException) | 25 | 2.4-T12 | BE | RATE-04, API-05
2.4-T14 | shared-libs | 2.4 | 2. Architecture & Technical Foundation | Cross-cutting libs: money, currency, errors | 1 | Implement GlobalExceptionHandler: @RestControllerAdvice mapping GmeException to ErrorEnvelope JSON | Every Spring Boot service must return API-05 §8.1 error JSON on all error paths. The @RestControllerAdvice catches GmeException and maps to HTTP status from GmeErrorCode.httpStatus(). Also catches ConstraintViolationException and MethodArgumentNotValidException producing VALIDATION_ERROR 400 with details array. Generic exceptions produce INTERNAL_ERROR 500 with no stack trace in response body. | • Create libs/lib-errors/src/main/java/com/gme/pay/errors/GlobalExceptionHandler.java annotated @RestControllerAdvice • Handle GmeException: extract X-Request-ID from HttpServletRequest (generate UUID if absent); build ErrorEnvelope.withDetails; return ResponseEntity with code.httpStatus() • Handle ConstraintViolationException and MethodArgumentNotValidException: map each violation to ErrorDetail(path, message); wrap via GmeException.validation; return HTTP 400 • Handle Throwable: log at ERROR level with request_id and stack trace; return INTERNAL_ERROR 500 ErrorEnvelope; never expose stack trace in response body • Set Content-Type: application/json on all error responses | libs/lib-errors/src/main/java/com/gme/pay/errors/GlobalExceptionHandler.java | • GmeException(RATE_QUOTE_EXPIRED) -> HTTP 422 JSON with error.code='RATE_QUOTE_EXPIRED' • ConstraintViolationException -> HTTP 400 with error.code='VALIDATION_ERROR' and non-empty details • POOL_IDENTITY_FAILURE -> HTTP 500 • Generic RuntimeException -> HTTP 500 INTERNAL_ERROR with no Java class names in response body • X-Request-ID header value appears in error.request_id field | 45 | 2.4-T13 | BE | RATE-04, API-05
2.4-T15 | shared-libs | 2.4 | 2. Architecture & Technical Foundation | Cross-cutting libs: money, currency, errors | 1 | Implement LibErrorsAutoConfiguration: Spring Boot 3.x auto-config for GlobalExceptionHandler | Services must not manually declare GlobalExceptionHandler. lib-errors provides a Spring Boot 3.x auto-configuration class registered in META-INF/spring/org.springframework.boot.autoconfigure.AutoConfiguration.imports. Activates only for servlet (not reactive) web contexts. Also customizes ObjectMapper for snake_case and non-null fields to keep error JSON consistent across services. | • Create libs/lib-errors/src/main/java/com/gme/pay/errors/autoconfigure/LibErrorsAutoConfiguration.java: @AutoConfiguration, @ConditionalOnWebApplication(type=SERVLET) • Declare @Bean GlobalExceptionHandler globalExceptionHandler() • Declare @Bean Jackson2ObjectMapperBuilderCustomizer errorMapperCustomizer() setting PropertyNamingStrategies.SNAKE_CASE and serializationInclusion NON_NULL • Register in libs/lib-errors/src/main/resources/META-INF/spring/org.springframework.boot.autoconfigure.AutoConfiguration.imports • Add LibErrorsAutoConfigurationTest: minimal @SpringBootApplication test asserting GlobalExceptionHandler bean is present without manual @Import | libs/lib-errors/src/main/java/com/gme/pay/errors/autoconfigure/LibErrorsAutoConfiguration.java and AutoConfiguration.imports | • GlobalExceptionHandler bean present in servlet context without manual @Import • Auto-config does NOT activate for @ConditionalOnWebApplication(type=REACTIVE) context • ObjectMapper uses SNAKE_CASE for error fields • Null fields omitted from serialized ErrorEnvelope • Spring Boot test context loads without BeanDefinitionOverrideException | 35 | 2.4-T14 | BE | RATE-04, API-05
2.4-T16 | shared-libs | 2.4 | 2. Architecture & Technical Foundation | Cross-cutting libs: money, currency, errors | 1 | Add lib-money and lib-errors implementation dependencies to all service build.gradle files | All GMEPay+ services (rate-fx, payment-executor, prefunding, transaction-mgmt, auth-identity, smart-router, qr-service, settlement-recon, notification-webhook, config-registry, scheme-adapter) need Money arithmetic and ErrorEnvelope. Dependencies must be wired once in each service's build.gradle. No new Java code; dependency-wiring only. | • For each module under services/, open build.gradle and add implementation(project(':libs:lib-money')) and implementation(project(':libs:lib-errors')) inside the dependencies block • Confirm lib-errors and lib-money do NOT depend on any services/ module (no circular dep) • Run ./gradlew build --dry-run to verify all modules resolve without error • Commit the build.gradle changes | Updated build.gradle for every module under services/ | • ./gradlew :services:rate-fx:compileJava resolves Money and GmeErrorCode on classpath • ./gradlew :services:payment-executor:compileJava resolves both libs • ./gradlew :libs:lib-money:dependencies shows no services/ dependency • No circular dependency errors in Gradle dependency insight report • ./gradlew build --dry-run exits 0 | 25 | 2.4-T15, 2.4-T06 | BE | RATE-04, API-05
2.4-T17 | shared-libs | 2.4 | 2. Architecture & Technical Foundation | Cross-cutting libs: money, currency, errors | 1 | Flyway migration V001__currency_scale.sql: PostgreSQL 16 currency_scale config table | DAT-03: for currencies not in the hardcoded CurrencyScale list, scale is stored in a currency_scale table maintained by GME Ops. Table lives in the shared config schema (lib-persistence). Phase 1 seed: KRW=0, USD=4, MNT=0. Flyway migrations are in libs/lib-persistence/src/main/resources/db/migration/. PostgreSQL 16 column types: CHAR(3) PK, SMALLINT NOT NULL CHECK(0..8), BOOLEAN DEFAULT true, TIMESTAMPTZ DEFAULT now(). | • Create libs/lib-persistence/src/main/resources/db/migration/V001__currency_scale.sql • CREATE TABLE currency_scale(currency_code CHAR(3) NOT NULL PRIMARY KEY, decimal_places SMALLINT NOT NULL CHECK(decimal_places >= 0 AND decimal_places <= 8), active BOOLEAN NOT NULL DEFAULT true, created_at TIMESTAMPTZ NOT NULL DEFAULT now(), updated_at TIMESTAMPTZ NOT NULL DEFAULT now()) • INSERT seed rows: ('KRW',0,true), ('USD',4,true), ('MNT',0,true) • Add Flyway + Testcontainers (PostgreSQLContainer) integration test CurrencyScaleMigrationIT in lib-persistence verifying migration applies cleanly and seed rows are queryable • No JPA entity in this ticket (T18) | libs/lib-persistence/src/main/resources/db/migration/V001__currency_scale.sql | • Migration applies cleanly against PostgreSQL 16 Testcontainer • SELECT count(*) FROM currency_scale returns 3 after migration • KRW row has decimal_places=0, USD has decimal_places=4 • INSERT ('KRW',2,true) fails with PK violation • INSERT ('BAD',-1,true) fails with CHECK constraint | 35 | 2.4-T01 | BE | RATE-04, API-05
2.4-T18 | shared-libs | 2.4 | 2. Architecture & Technical Foundation | Cross-cutting libs: money, currency, errors | 1 | Implement CurrencyScaleEntity JPA entity and CurrencyScaleRepository in lib-persistence | The currency_scale PostgreSQL table (V001 from T17) needs a JPA entity and Spring Data JPA repository so services can load runtime scales beyond the Phase 1 hardcoded set. lib-persistence is the shared JPA/migration utilities module. Uses @Cacheable so Redis (or local Caffeine) can cache the result to avoid DB round-trips on every request. | • Create libs/lib-persistence/src/main/java/com/gme/pay/persistence/currency/CurrencyScaleEntity.java: @Entity @Table(name='currency_scale'); @Id @Column(name='currency_code',length=3) String currencyCode; @Column SMALLINT decimalPlaces; boolean active • Create CurrencyScaleRepository extends JpaRepository<CurrencyScaleEntity,String>; add findAllByActiveTrue() annotated @Cacheable(value='currency_scale') • Update CurrencyScale.java in lib-money: add static void loadFromDb(Map<String,Integer> dbMap) so CurrencyScaleRepository results override the hardcoded map at startup • Add @DataJpaTest + @AutoConfigureTestDatabase(replace=NONE) + PostgreSQLContainer test CurrencyScaleRepositoryIT asserting findAllByActiveTrue returns 3 seeded rows | libs/lib-persistence/src/main/java/com/gme/pay/persistence/currency/CurrencyScaleEntity.java and CurrencyScaleRepository.java | • CurrencyScaleRepository.findAllByActiveTrue() returns 3 entities from seeded DB • Entity maps currency_code as @Id • findById('KRW').get().getDecimalPlaces() == 0 • @DataJpaTest passes against PostgreSQLContainer • CurrencyScale.loadFromDb({EUR->2}) causes scaleOf('EUR') to return 2 | 40 | 2.4-T17, 2.4-T03 | BE | RATE-04, API-05
2.4-T19 | shared-libs | 2.4 | 2. Architecture & Technical Foundation | Cross-cutting libs: money, currency, errors | 1 | Implement MoneyAmountNormalizer: parse and normalize partner API decimal strings to Money | API-05 §2.5: KRW amount '12500.00' and '12500' must both be accepted; stored as scale-0. USD '36.75' or '36.7500' both stored at scale 4. The normalizer is the API boundary entry point called before any arithmetic in rate-fx and payment-executor. Invalid or negative input throws GmeException(VALIDATION_ERROR) with an ErrorDetail naming the field. | • Create libs/lib-money/src/main/java/com/gme/pay/money/MoneyAmountNormalizer.java • Money normalize(String amountStr, String currency, String fieldName): parse via new BigDecimal(amountStr.trim()) inside try-catch NumberFormatException; scale to CurrencyScale.scaleOf(currency) using HALF_UP; throw GmeException(VALIDATION_ERROR, List.of(new ErrorDetail(fieldName, 'Invalid or negative amount: ' + amountStr))) if null/empty/unparseable/negative • Add MoneyAmountNormalizerTest covering all edge cases | libs/lib-money/src/main/java/com/gme/pay/money/MoneyAmountNormalizer.java and MoneyAmountNormalizerTest.java | • normalize('12500.00','KRW','target_payout') returns Money(12500,KRW) scale 0 • normalize('36.75','USD','collection_amount') returns Money(36.7500,USD) scale 4 • normalize('-0.01','USD','amount') throws GmeException VALIDATION_ERROR with details[0].field='amount' • normalize('not_a_number','KRW','amount') throws GmeException VALIDATION_ERROR • normalize(null,'KRW','amount') throws GmeException VALIDATION_ERROR | 30 | 2.4-T08, 2.4-T13 | BE | RATE-04, API-05
2.4-T20 | shared-libs | 2.4 | 2. Architecture & Technical Foundation | Cross-cutting libs: money, currency, errors | 1 | Unit test RATE-04 cross-border vector: SendMN KRW 50000 payout using Money + PoolIdentityChecker | RATE-04 §5 worked example: SendMN (OVERSEAS, Settle A=USD), ZeroPay KRW merchant, target_payout=50000 KRW. treasury.usd_krw=1380.00, treasury.usd_usd=1.0 (IDENTITY leg). m_a=0.01, m_b=0.01. service_charge=0.36 USD. Step 1: payout_usd_cost=50000/1380=36.23188406 (8dp). Step 2: collection_usd=36.23188406/(1-0.01-0.01)=36.96111638. Step 3: margins=36.96111638*0.01=0.36961116 each. Step 4: send_amount=36.96111638*1.0=36.96111638. Step 5: collection_amount=36.96111638+0.36=37.32111638 -> round to USD scale 4 = 37.3211. Pool check: 36.96111638-0.36961116-0.36961116=36.23189406; diff from 36.23188406=0.000010 which is less than 0.01 tolerance. | • Create libs/lib-money/src/test/java/com/gme/pay/money/RateVectorCrossBorderTest.java • Reproduce all 5 steps using BigDecimal at scale 8 with MoneyRounder.roundToIntermediate • Call PoolIdentityChecker.check with computed values • Assert collection_amount rounds to Money(37.3211,USD) via MoneyRounder.roundToFinal • Assert pool identity check passes with no exception • All computations use BigDecimal only — no float/double literals | libs/lib-money/src/test/java/com/gme/pay/money/RateVectorCrossBorderTest.java | • payout_usd_cost == 36.23188406 (8dp BigDecimal) • collection_usd == 36.96111638 (8dp) • collection_amount after roundToFinal == Money(37.3211,USD) • PoolIdentityChecker.check does not throw • Test contains zero float or double literals | 40 | 2.4-T09, 2.4-T10 | BE | RATE-04, API-05
2.4-T21 | shared-libs | 2.4 | 2. Architecture & Technical Foundation | Cross-cutting libs: money, currency, errors | 1 | Unit test RATE-04 same-currency short-circuit: GME Remit domestic KRW 50000 | RATE-04 §7.2 same-currency short-circuit: when collection=settle_a=settle_b=payout all KRW, USD pool is bypassed. collection_amount = target_payout + service_charge. m_a=m_b=0 enforced. service_charge=500 KRW. So collection_amount = 50000+500 = 50500 KRW. PoolIdentityChecker must NOT be called on this path. | • Create libs/lib-money/src/test/java/com/gme/pay/money/RateVectorDomesticTest.java • Compute: Money.of('50000','KRW').add(Money.of('500','KRW')), assert equals Money(50500,KRW) • Assert result.amount().scale() == 0 (no decimal digits for KRW) • Assert adding USD service_charge to KRW collection throws IllegalArgumentException (currency mismatch) • Verify m_a=m_b=0 guard: MarginGuard.checkCrossBorder(ZERO, ZERO, true) passes without exception | libs/lib-money/src/test/java/com/gme/pay/money/RateVectorDomesticTest.java | • 50000 KRW + 500 KRW = Money(50500,KRW) • Result scale == 0 (KRW integer) • Adding USD service charge to KRW base throws IllegalArgumentException • MarginGuard passes for same-currency with m_a=m_b=0 • No BigDecimal division or USD-pool arithmetic appears in test | 30 | 2.4-T05, 2.4-T18 | BE | RATE-04, API-05
2.4-T22 | shared-libs | 2.4 | 2. Architecture & Technical Foundation | Cross-cutting libs: money, currency, errors | 1 | Implement MarginGuard: validate m_a+m_b >= 2% for cross-border, m_a=m_b=0 for same-currency | RATE-04 and canonical facts: cross-border rules require m_a+m_b >= 0.02 (2%); same-currency rules require m_a=m_b=0. MarginGuard enforces these rules before rate calculation. Violation throws GmeException(VALIDATION_ERROR). Lives in lib-money under validation package so rate-fx can call it without service-layer logic. | • Create libs/lib-money/src/main/java/com/gme/pay/money/validation/MarginGuard.java as final utility class • void checkCrossBorder(BigDecimal mA, BigDecimal mB, boolean isSameCurrency): if isSameCurrency then assert mA.compareTo(ZERO)==0 and mB.compareTo(ZERO)==0, else assert mA.add(mB).compareTo(new BigDecimal('0.02'))>=0; throw GmeException(VALIDATION_ERROR, appropriate message) on failure • Add MarginGuardTest: mA=0.01,mB=0.01 cross-border passes; mA=0.009,mB=0.01 cross-border throws with message mentioning '2.00%'; mA=0,mB=0 same-currency passes; mA=0.01,mB=0 same-currency throws | libs/lib-money/src/main/java/com/gme/pay/money/validation/MarginGuard.java and MarginGuardTest.java | • mA=0.01, mB=0.01 cross-border passes • mA=0.009, mB=0.01 cross-border throws GmeException VALIDATION_ERROR • mA=0, mB=0 same-currency passes • mA=0.01, mB=0 same-currency throws (both must be 0) • Exception message contains '2.00%' for cross-border violation | 25 | 2.4-T13 | BE | RATE-04, API-05
2.4-T23 | shared-libs | 2.4 | 2. Architecture & Technical Foundation | Cross-cutting libs: money, currency, errors | 1 | Integration test: GlobalExceptionHandler HTTP status and JSON body for critical error codes | API-05 §8.2 specifies exact HTTP status per error code. The GlobalExceptionHandler (T14) must be verified with Spring MockMvc covering all critical codes used in the money/error path. A minimal @RestController throws each GmeException on demand; tests assert HTTP status and JSON body structure. | • Create libs/lib-errors/src/test/java/com/gme/pay/errors/GlobalExceptionHandlerIntegrationTest.java using @WebMvcTest + @Import(LibErrorsAutoConfiguration.class) • Define @RestController TestController with endpoints throwing GmeException variants and a generic RuntimeException • Test /throw/rate-quote-expired -> HTTP 422, body error.code='RATE_QUOTE_EXPIRED' • Test /throw/insufficient-prefunding -> HTTP 402, body error.code='INSUFFICIENT_PREFUNDING' • Test /throw/pool-identity-failure -> HTTP 500, body error.code='POOL_IDENTITY_FAILURE' • Test /throw/validation with ErrorDetail -> HTTP 400, details array non-empty • Test /throw/generic-runtime -> HTTP 500, body error.code='INTERNAL_ERROR', no class name or stack trace in body | libs/lib-errors/src/test/java/com/gme/pay/errors/GlobalExceptionHandlerIntegrationTest.java | • RATE_QUOTE_EXPIRED -> HTTP 422 • INSUFFICIENT_PREFUNDING -> HTTP 402 • POOL_IDENTITY_FAILURE -> HTTP 500 • VALIDATION_ERROR -> HTTP 400 with non-empty error.details • Generic RuntimeException -> HTTP 500 with no stack trace in response body | 40 | 2.4-T15 | BE | RATE-04, API-05
2.4-T24 | shared-libs | 2.4 | 2. Architecture & Technical Foundation | Cross-cutting libs: money, currency, errors | 1 | Wire MoneyModule Jackson SPI in rate-fx and payment-executor service integration slice tests | lib-money registers MoneyModule via Java SPI (T06). Services must auto-discover it via Spring Boot Jackson auto-configuration. This ticket verifies SPI registration in the rate-fx and payment-executor service contexts by injecting the service ObjectMapper and asserting correct Money serialization/deserialization. | • In services/rate-fx/src/test/java/.../RateFxMoneySerializationTest.java: @SpringBootTest; inject ObjectMapper; assert objectMapper.writeValueAsString(Money.of('50000','KRW')) == '{"amount":"50000","currency":"KRW"}' • Assert deserialization: objectMapper.readValue('{"amount":"36.7500","currency":"USD"}', Money.class) equals Money.of('36.7500','USD') • In services/payment-executor/src/test/java/.../PaymentExecutorMoneySerializationTest.java: same two assertions • Confirm no duplicate MoneyModule registration warning in test logs | services/rate-fx/src/test/java/com/gme/pay/ratefx/RateFxMoneySerializationTest.java and services/payment-executor/src/test/java/com/gme/pay/paymentexecutor/PaymentExecutorMoneySerializationTest.java | • ObjectMapper in rate-fx context serializes Money(50000,KRW) to {amount:'50000',currency:'KRW'} with no decimal point • ObjectMapper in payment-executor context serializes Money(36.7500,USD) correctly • Deserialization of {amount:'36.7500',currency:'USD'} returns Money equal to Money.of('36.7500','USD') • No ClassCastException or duplicate module warning in test output • Tests pass without WireMock or Testcontainers (pure slice) | 30 | 2.4-T16, 2.4-T06 | BE | RATE-04, API-05
2.4-T25 | shared-libs | 2.4 | 2. Architecture & Technical Foundation | Cross-cutting libs: money, currency, errors | 1 | Javadoc pass: annotate all public lib-money and lib-errors classes with stack-aligned references | lib-money and lib-errors are used by all GMEPay+ service developers. Class-level Javadoc must state the governing spec section, the key invariant, and any gotcha. CurrencyScale must cite DAT-03 §2.1 tiers. Money must cite immutability contract. PoolIdentityChecker must cite RATE-04 pool invariant and 0.01 USD tolerance. GmeErrorCode must cite API-05 §8.2. ErrorEnvelope must cite API-05 §8.1 JSON structure. | • Add class-level Javadoc to CurrencyScale.java citing DAT-03 §2.1: KRW=0, USD=4, intermediate=8 • Add class-level Javadoc to Money.java citing immutability, BigDecimal-only rule, and DAT-03 • Add class-level Javadoc to PoolIdentityChecker.java: formula, 0.01 USD tolerance, POOL_IDENTITY_FAILURE error on breach • Add class-level Javadoc to GmeErrorCode.java: references API-05 §8.2 catalogue source • Add class-level Javadoc to ErrorEnvelope.java: references API-05 §8.1 structure • Run ./gradlew :libs:lib-money:javadoc :libs:lib-errors:javadoc and fix any -Xdoclint errors | Javadoc on CurrencyScale, Money, PoolIdentityChecker, GmeErrorCode, ErrorEnvelope | • ./gradlew :libs:lib-money:javadoc exits 0 with 0 errors • ./gradlew :libs:lib-errors:javadoc exits 0 with 0 errors • CurrencyScale Javadoc mentions 'KRW=0', 'USD=4', 'intermediate=8' • PoolIdentityChecker Javadoc mentions '0.01 USD tolerance' and 'POOL_IDENTITY_FAILURE' • GmeErrorCode Javadoc references 'API-05 §8.2' | 25 | 2.4-T23, 2.4-T20, 2.4-T21, 2.4-T22 | BE | RATE-04, API-05
2.5-T01 | config-registry | 2.5 | 2. Architecture & Technical Foundation | Configuration framework (config-not-code) | 1 | Create Flyway migration V201: qr_scheme and scheme_country tables | Config-not-code constraint (SAD-02 AD-04, BRD §10.3): adding a QR scheme must be a DB config insert with no code change. qr_scheme holds: id BIGINT PK, scheme_code VARCHAR(30) UNIQUE (e.g. ZEROPAY), name, payout_ccy CHAR(3), supported_modes VARCHAR(20) CHECK IN (MPM,CPM,BOTH), settlement_counterparty, merchant_fee_domestic_min/max DECIMAL(6,4), merchant_fee_crossborder_min/max, van_fee_domestic_min/max, van_fee_crossborder_min/max, gme_fee_share_pct DECIMAL(6,4), partner_b_quote_enabled BOOLEAN, partner_b_quote_deviation_pct DECIMAL(6,4) default 0.0100, sftp_host/sftp_path_outbound/sftp_path_inbound VARCHAR, api_endpoint VARCHAR(512), api_credential_ref VARCHAR(120), status VARCHAR(20) CHECK IN (TESTING,ACTIVE,INACTIVE), is_active BOOLEAN, created_at/updated_at TIMESTAMPTZ, created_by/updated_by VARCHAR. scheme_country: id, scheme_id FK, country_code CHAR(2), is_active BOOLEAN, standard audit; UNIQUE(scheme_id, country_code). Module: services/config-registry. Migrations live in services/config-registry/src/main/resources/db/migration/. | • Create services/config-registry/src/main/resources/db/migration/V201__qr_scheme.sql • Define qr_scheme table with all columns, CHECK IN (MPM,CPM,BOTH) on supported_modes, CHECK IN (TESTING,ACTIVE,INACTIVE) on status • Define scheme_country table with FK to qr_scheme and UNIQUE(scheme_id, country_code) • Add index on qr_scheme(scheme_code) and scheme_country(scheme_id, is_active) • All monetary columns use NUMERIC not FLOAT | services/config-registry/src/main/resources/db/migration/V201__qr_scheme.sql | • Flyway applies V201 cleanly on a fresh PostgreSQL 16 Testcontainers instance • scheme_code UNIQUE constraint: inserting a duplicate ZEROPAY row raises 23505 violation • status CHECK constraint: inserting status=UNKNOWN raises 23514 violation • scheme_country UNIQUE(scheme_id, country_code) prevents duplicate KR mapping for same scheme • All DECIMAL columns declared as NUMERIC(6,4) or wider, not FLOAT8 | 30 |  | BE | NFR-10, SAD-02
2.5-T02 | config-registry | 2.5 | 2. Architecture & Technical Foundation | Configuration framework (config-not-code) | 1 | Create Flyway migration V202: partner, partner_credential, partner_webhook tables | partner: id BIGINT PK, partner_code VARCHAR(30) UNIQUE (e.g. GME_REMIT, SENDMN), name, partner_type VARCHAR(10) CHECK IN (LOCAL,OVERSEAS), collection_ccy CHAR(3), settle_a_ccy CHAR(3), webhook_url VARCHAR(512), rate_quote_ttl_seconds INT DEFAULT 300 CHECK BETWEEN 60 AND 1800, low_balance_threshold_usd DECIMAL(20,4) nullable, low_balance_alert_email VARCHAR(255), status VARCHAR(20) CHECK IN (ONBOARDING,ACTIVE,SUSPENDED,INACTIVE), is_active BOOLEAN, standard audit. partner_credential: id, partner_id FK, api_key VARCHAR(64) UNIQUE, api_secret_hash VARCHAR(128) (bcrypt), is_active BOOLEAN, expires_at TIMESTAMPTZ nullable, standard audit. partner_webhook: id, partner_id FK, webhook_url, event_types TEXT, signing_secret_hash VARCHAR(128), is_active BOOLEAN, standard audit. Module: services/config-registry. | • Create V202__partner.sql in services/config-registry/src/main/resources/db/migration/ • Define partner table with CHECK constraints on partner_type, status, and rate_quote_ttl_seconds range (60-1800) • Define partner_credential table; UNIQUE on api_key • Define partner_webhook table; index on partner_id • Add comment on low_balance_threshold_usd: required only when partner_type=OVERSEAS (enforced at app layer) | services/config-registry/src/main/resources/db/migration/V202__partner.sql | • partner_type CHECK rejects values other than LOCAL or OVERSEAS • rate_quote_ttl_seconds=59 raises CHECK violation; 60 and 1800 are both accepted • api_key UNIQUE index prevents second credential with same key • Flyway applies V201 then V202 in order without error on Testcontainers PostgreSQL 16 • partner_code UNIQUE prevents duplicate GME_REMIT insert | 30 | 2.5-T01 | BE | NFR-10, SAD-02
2.5-T03 | config-registry | 2.5 | 2. Architecture & Technical Foundation | Configuration framework (config-not-code) | 1 | Create Flyway migration V203: rule and service_charge_tier tables | rule is the central config entity (partner x scheme x direction). Columns: id, partner_id FK, scheme_id FK, direction VARCHAR(10) CHECK IN (INBOUND,OUTBOUND,DOMESTIC,HUB), collection_ccy CHAR(3), settle_a_ccy CHAR(3), settle_b_ccy CHAR(3), payout_ccy CHAR(3), rate_coll_source VARCHAR(10) CHECK IN (IDENTITY,LIVE,MANUAL,PARTNER), rate_pay_source same enum, manual_rate_coll DECIMAL(20,8) nullable, manual_rate_pay DECIMAL(20,8) nullable, m_a DECIMAL(8,6), m_b DECIMAL(8,6), service_charge_amount DECIMAL(20,4), service_charge_ccy CHAR(3), is_same_ccy_shortcircuit BOOLEAN, status VARCHAR(20) CHECK IN (DRAFT,ACTIVE,SUSPENDED), effective_from TIMESTAMPTZ, standard audit. UNIQUE(partner_id, scheme_id, direction). service_charge_tier: id, rule_id FK, min_collection_usd DECIMAL(20,4), max_collection_usd DECIMAL(20,4) nullable (no cap), charge_amount DECIMAL(20,4), standard audit. Module: services/config-registry. | • Create V203__rule.sql in services/config-registry/src/main/resources/db/migration/ • Define rule table with FK constraints on partner_id and scheme_id; CHECK on direction, rate sources, status • Add UNIQUE(partner_id, scheme_id, direction) • Define service_charge_tier with FK rule_id • Add index on rule(partner_id, scheme_id, direction, status) for runtime resolution | services/config-registry/src/main/resources/db/migration/V203__rule.sql | • direction=UNKNOWN raises CHECK violation • UNIQUE(partner_id, scheme_id, direction) prevents duplicate rule for same combo • m_a and m_b are NUMERIC(8,6); value 0.010000 stores and retrieves exactly • service_charge_tier FK to non-existent rule_id raises 23503 violation • Flyway applies V201-V203 in sequence cleanly on Testcontainers | 35 | 2.5-T02 | BE | NFR-10, SAD-02
2.5-T04 | config-registry | 2.5 | 2. Architecture & Technical Foundation | Configuration framework (config-not-code) | 1 | Create Flyway migration V204: treasury_rate table | treasury_rate stores FX rates in canonical form: ccy_pair = usd_{ccy} (units of target currency per 1 USD). E.g. usd_krw = 1380.0 means 1 USD = 1380 KRW. Columns: id BIGINT PK, ccy_pair VARCHAR(10) e.g. usd_krw, rate DECIMAL(20,8), source VARCHAR(10) CHECK IN (LIVE,MANUAL), effective_at TIMESTAMPTZ, created_at TIMESTAMPTZ, created_by VARCHAR. Latest rate query: WHERE ccy_pair=? ORDER BY effective_at DESC LIMIT 1. Historical rows retained forever (BOK reconciliation). Phase 1 source=MANUAL only; Phase 2 adds LIVE (xe.com feed) with no schema change. Index on (ccy_pair, effective_at DESC) is critical for query performance. Module: services/config-registry. | • Create V204__treasury_rate.sql • Define treasury_rate table with NUMERIC(20,8) rate, TIMESTAMPTZ effective_at, CHECK source IN (LIVE,MANUAL) • Add index on (ccy_pair, effective_at DESC) named idx_treasury_rate_lookup • Add comment: rows are never deleted or updated after insert; append-only enforced at app layer • No FK from treasury_rate to other tables (rates are globally shared) | services/config-registry/src/main/resources/db/migration/V204__treasury_rate.sql | • Index idx_treasury_rate_lookup exists in information_schema after migration • source=SPOT raises CHECK violation; MANUAL and LIVE accepted • rate column is NUMERIC not FLOAT8 • Two rows for same ccy_pair with different effective_at both insert without conflict • Flyway V204 applies cleanly after V203 | 25 | 2.5-T03 | BE | NFR-10, SAD-02
2.5-T05 | config-registry | 2.5 | 2. Architecture & Technical Foundation | Configuration framework (config-not-code) | 1 | Create Flyway migration V205: audit_log table with immutability enforcement | audit_log is the immutable append-only record for all config and payment state changes (SAD-02 §11.3, DAT-03 §9.1). Columns: id BIGINT PK, actor_id VARCHAR(120), actor_type VARCHAR(20) CHECK IN (OPERATOR,SYSTEM,PARTNER), action VARCHAR(20) CHECK IN (CREATE,UPDATE,DELETE,ACTIVATE,DEACTIVATE), entity_type VARCHAR(50) (table name), entity_id BIGINT, before_value JSONB nullable, after_value JSONB nullable, occurred_at TIMESTAMPTZ NOT NULL DEFAULT NOW(), ip_address INET, request_id VARCHAR(64). Retained >= 7 years (BOK/KYC). Immutability via PostgreSQL rule: CREATE RULE no_update_audit AS ON UPDATE TO audit_log DO INSTEAD NOTHING (or raise exception). Module: services/config-registry. | • Create V205__audit_log.sql • Define audit_log table with all columns and CHECK constraints on actor_type and action • Add PostgreSQL rules: CREATE RULE prevent_update_audit AS ON UPDATE TO audit_log DO INSTEAD RAISE EXCEPTION • Add same rule for DELETE: prevent_delete_audit • Add indexes on (entity_type, entity_id), (occurred_at), (actor_id) | services/config-registry/src/main/resources/db/migration/V205__audit_log.sql | • INSERT with actor_type=OPERATOR and action=CREATE succeeds • UPDATE on any row raises exception from DB rule • DELETE on any row raises exception from DB rule • actor_type=EXTERNAL raises CHECK violation • Indexes on (entity_type, entity_id) and (occurred_at) visible in pg_indexes | 30 | 2.5-T04 | BE | NFR-10, SAD-02
2.5-T06 | config-registry | 2.5 | 2. Architecture & Technical Foundation | Configuration framework (config-not-code) | 1 | Create Flyway seed migration V206: ZeroPay scheme, bootstrap partners, initial treasury rate | Config-not-code: ZeroPay is a config row, not code. V206 seeds: 1) qr_scheme: scheme_code=ZEROPAY, payout_ccy=KRW, supported_modes=BOTH, gme_fee_share_pct=0.70, partner_b_quote_deviation_pct=0.0100, status=TESTING, is_active=false, api_credential_ref=gmepay/dev/zeropay/api-key. 2) scheme_country: scheme_id from above, country_code=KR, is_active=true. 3) partner GME_REMIT: partner_type=LOCAL, collection_ccy=KRW, settle_a_ccy=KRW, rate_quote_ttl_seconds=300, status=ONBOARDING. 4) partner SENDMN: partner_type=OVERSEAS, collection_ccy=USD, settle_a_ccy=USD, rate_quote_ttl_seconds=60, status=ONBOARDING. 5) treasury_rate: ccy_pair=usd_krw, rate=1380.00000000, source=MANUAL. Use INSERT ... ON CONFLICT DO NOTHING for idempotency. Module: services/config-registry. | • Create V206__seed_zeropay.sql with DO $$ BEGIN ... END $$ block for CTE-based inserts • INSERT qr_scheme ZEROPAY with all required columns; capture id into variable • INSERT scheme_country (scheme_id, country_code=KR, is_active=true) • INSERT partners GME_REMIT and SENDMN with created_by=SYSTEM • INSERT treasury_rate usd_krw=1380.00000000 MANUAL | services/config-registry/src/main/resources/db/migration/V206__seed_zeropay.sql | • V206 applied twice is idempotent (ON CONFLICT DO NOTHING means second run inserts 0 rows) • SELECT count(*) FROM qr_scheme returns 1 after fresh migration • SELECT payout_ccy FROM qr_scheme WHERE scheme_code=ZEROPAY returns KRW • partner GME_REMIT has partner_type=LOCAL and rate_quote_ttl_seconds=300 • treasury_rate row exists with rate=1380.00000000 for ccy_pair=usd_krw | 25 | 2.5-T05 | BE | NFR-10, SAD-02
2.5-T07 | config-registry | 2.5 | 2. Architecture & Technical Foundation | Configuration framework (config-not-code) | 1 | Define SchemeRegistryPort, PartnerRegistryPort, RuleRegistryPort interfaces in lib-api-contracts | Consuming services (Rate Engine, Smart Router, Orchestrator) resolve config at runtime via these Java port interfaces. No if-partner or if-scheme conditionals in consuming code (AD-04). Interfaces live in lib-api-contracts/src/main/java/com/gme/pay/contracts/registry/. SchemeRegistryPort: findByCode(String schemeCode): Optional<SchemeConfig>; findActiveByCountry(String countryCode): List<SchemeConfig>. PartnerRegistryPort: findByCode(String partnerCode): Optional<PartnerConfig>; findById(Long id): Optional<PartnerConfig>. RuleRegistryPort: findActiveRule(Long partnerId, Long schemeId, String direction): Optional<RuleConfig>. DTOs are immutable Java records. SchemeConfig fields: schemeCode, payoutCcy, supportedModes, gme FeeSharePct BigDecimal, partnerBQuoteEnabled, partnerBQuoteDeviationPct BigDecimal. RuleConfig: partnerId, schemeId, direction, mA BigDecimal, mB BigDecimal, serviceChargeAmount BigDecimal, serviceChargeCcy, rateColl Source, ratePaySource, manualRateColl BigDecimal, manualRatePay BigDecimal, isSameCcyShortcircuit. Module: lib-api-contracts. | • Create lib-api-contracts/src/main/java/com/gme/pay/contracts/registry/SchemeRegistryPort.java interface • Create PartnerRegistryPort.java interface • Create RuleRegistryPort.java interface • Create SchemeConfig.java, PartnerConfig.java, RuleConfig.java as Java records • Add Javadoc on each interface: implementations must serve cached values and evict on write | lib-api-contracts/src/main/java/com/gme/pay/contracts/registry/SchemeRegistryPort.java, PartnerRegistryPort.java, RuleRegistryPort.java plus SchemeConfig.java, PartnerConfig.java, RuleConfig.java | • All interfaces compile with Java 21 and no Spring dependencies on the classpath • SchemeConfig is a Java record (no setters, final fields) • RuleConfig has BigDecimal mA, mB, serviceChargeAmount; no double or float fields • findActiveRule returns Optional.empty() not null for unknown combo (documented in Javadoc) • RuleConfig.isSameCcyShortcircuit is a boolean field (not Boolean) | 35 | 2.5-T03 | BE | NFR-10, SAD-02
2.5-T08 | config-registry | 2.5 | 2. Architecture & Technical Foundation | Configuration framework (config-not-code) | 1 | Define TreasuryRatePort interface and TreasuryRateSnapshot record in lib-api-contracts | The Rate Engine calls TreasuryRatePort to get cost_rate_coll and cost_rate_pay at quote time. TreasuryRatePort in lib-api-contracts/src/main/java/com/gme/pay/contracts/treasury/. Methods: getLatestRate(String ccyPair): TreasuryRateSnapshot throws RateNotFoundException; getLatestRateOrIdentity(String ccyPair): TreasuryRateSnapshot (returns rate=1.0 for identity legs where settle ccy = USD). Convention: ccyPair = usd_{ccy} lowercase, e.g. usd_krw. Identity leg: if settle_a_ccy=USD then cost_rate_coll=1.0 (no treasury lookup needed). TreasuryRateSnapshot record: ccyPair String, rate BigDecimal, source String, effectiveAt Instant, rateId Long (FK for commit-time lock). RateNotFoundException: unchecked, in lib-errors. Module: lib-api-contracts. | • Create TreasuryRatePort.java interface in lib-api-contracts/src/main/java/com/gme/pay/contracts/treasury/ • Create TreasuryRateSnapshot.java Java record with fields: ccyPair String, rate BigDecimal, source String, effectiveAt Instant, rateId Long • Create RateNotFoundException.java in lib-errors/src/main/java/com/gme/pay/errors/ extending RuntimeException • Add Javadoc on getLatestRateOrIdentity: returns TreasuryRateSnapshot(ccyPair, BigDecimal.ONE, IDENTITY, now, null) when settle ccy = USD | lib-api-contracts/src/main/java/com/gme/pay/contracts/treasury/TreasuryRatePort.java, TreasuryRateSnapshot.java; lib-errors/.../RateNotFoundException.java | • TreasuryRateSnapshot is a Java record with BigDecimal rate (not double) • RateNotFoundException extends RuntimeException (unchecked) • Interface compiles without Spring annotations or Spring dependencies • getLatestRate method signature documented to throw RateNotFoundException • ccyPair naming convention usd_{ccy} documented in Javadoc | 25 | 2.5-T07 | BE | NFR-10, SAD-02
2.5-T09 | config-registry | 2.5 | 2. Architecture & Technical Foundation | Configuration framework (config-not-code) | 1 | Scaffold services/config-registry Spring Boot module in Gradle multi-module build | config-registry is a dedicated Spring Boot 3.x microservice (STACK.md service list). It owns Flyway migrations V201-V207, serves registry port implementations, and exposes admin REST endpoints. Gradle module path: services/config-registry. Required Gradle dependencies: spring-boot-starter-data-jpa, spring-boot-starter-web, spring-boot-starter-data-redis, spring-boot-starter-security, spring-boot-starter-oauth2-resource-server, flyway-core, postgresql driver, lib-api-contracts, lib-errors, lib-money. Main class: ConfigRegistryApplication under com.gme.pay.config. application.yml: spring.datasource.url=jdbc:postgresql://localhost:5433/gmepay, spring.flyway.enabled=true, spring.flyway.locations=classpath:db/migration, spring.data.redis.host=localhost. | • Add services/config-registry to root settings.gradle includes • Create services/config-registry/build.gradle with all required dependencies including lib-api-contracts and lib-errors • Create ConfigRegistryApplication.java with @SpringBootApplication • Create src/main/resources/application.yml with datasource, flyway, and redis stubs • Run ./gradlew :services:config-registry:compileJava and confirm it passes | services/config-registry/build.gradle, services/config-registry/src/main/java/com/gme/pay/config/ConfigRegistryApplication.java, src/main/resources/application.yml | • ./gradlew :services:config-registry:compileJava completes without error • Module appears in ./gradlew projects output • application.yml has spring.flyway.locations=classpath:db/migration • Flyway migrations V201-V206 are on the classpath at runtime • ConfigRegistryApplication has @SpringBootApplication and correct base package | 35 | 2.5-T06, 2.5-T08 | BE | NFR-10, SAD-02
2.5-T10 | config-registry | 2.5 | 2. Architecture & Technical Foundation | Configuration framework (config-not-code) | 1 | Implement JPA entities and repositories: qr_scheme, scheme_country, partner | JPA entities in services/config-registry/src/main/java/com/gme/pay/config/domain/. Map to PostgreSQL tables V201-V202. Use @Entity, @Table(name=...), @Column(nullable=false). BigDecimal for all DECIMAL columns. Status and type fields use @Enumerated(EnumType.STRING) never ORDINAL. Audit fields: @CreationTimestamp for created_at, @UpdateTimestamp for updated_at. Repositories: QrSchemeRepository.findBySchemeCode(String): Optional<QrScheme>; findByIsActiveTrue(): List. SchemeCountryRepository.findBySchemeIdAndIsActiveTrue(Long): List. PartnerRepository.findByPartnerCode(String): Optional<Partner>. Module: services/config-registry. | • Create QrScheme.java @Entity in services/config-registry/src/main/java/com/gme/pay/config/domain/ • Create SchemeCountry.java @Entity with @ManyToOne(fetch=LAZY) to QrScheme • Create Partner.java @Entity with PartnerType and PartnerStatus enums • Create QrSchemeRepository, SchemeCountryRepository, PartnerRepository as Spring Data JPA interfaces • Add @Column(updatable=false) on created_at; verify all DECIMAL fields annotated with correct precision/scale | services/config-registry/src/main/java/com/gme/pay/config/domain/QrScheme.java, SchemeCountry.java, Partner.java and three repository interfaces | • QrScheme.gmeFeeSha rePct field type is BigDecimal with @Column(precision=6,scale=4) • @Enumerated(EnumType.STRING) on partner_type and status fields • QrSchemeRepository.findBySchemeCode returns Optional<QrScheme> • Spring context loads with Testcontainers PostgreSQL 16 and Flyway seeds V201-V206 • No field uses primitive double or float | 40 | 2.5-T09 | BE | NFR-10, SAD-02
2.5-T11 | config-registry | 2.5 | 2. Architecture & Technical Foundation | Configuration framework (config-not-code) | 1 | Implement JPA entities and repositories: rule, service_charge_tier, treasury_rate | rule entity maps to V203 DDL. Fields m_a and m_b are BigDecimal. isSameCcyShortcircuit is a computed boolean stored in DB. treasury_rate maps to V204: ccyPair, rate BigDecimal, source (enum LIVE/MANUAL), effectiveAt Instant. RuleRepository: findByPartnerIdAndSchemeIdAndDirectionAndStatus(Long, Long, String, String): Optional<Rule>. TreasuryRateRepository: findFirstByCcyPairOrderByEffectiveAtDesc(String): Optional<TreasuryRate> (JPA derived query). ServiceChargeTierRepository: findByRuleIdOrderByMinCollectionUsdAsc(Long). Module: services/config-registry. | • Create Rule.java @Entity with @UniqueConstraint(columnNames={partner_id,scheme_id,direction}) on @Table • Create ServiceChargeTier.java @Entity with @ManyToOne(fetch=LAZY) to Rule • Create TreasuryRate.java @Entity • Create RuleRepository with derived query findByPartnerIdAndSchemeIdAndDirectionAndStatus • Create TreasuryRateRepository with findFirstByCcyPairOrderByEffectiveAtDesc | services/config-registry/src/main/java/com/gme/pay/config/domain/Rule.java, ServiceChargeTier.java, TreasuryRate.java and three repository interfaces | • Rule.mA type is BigDecimal; no double • TreasuryRateRepository.findFirstByCcyPairOrderByEffectiveAtDesc(usd_krw) returns row from V206 seed • @UniqueConstraint on Rule enforced: second rule for same partner+scheme+direction raises DataIntegrityViolationException • findByPartnerIdAndSchemeIdAndDirectionAndStatus with DRAFT status returns empty Optional for missing rule • ServiceChargeTier FK to Rule cascades on delete | 40 | 2.5-T10 | BE | NFR-10, SAD-02
2.5-T12 | config-registry | 2.5 | 2. Architecture & Technical Foundation | Configuration framework (config-not-code) | 1 | Implement RedisConfigCache: cache-aside for scheme, partner, rule with TTL and eviction | Config/Registry maintains a Redis hot cache (SAD-02 §11.3). Key pattern: config:scheme:{schemeCode}, config:partner:{partnerCode}, config:rule:{partnerId}:{schemeId}:{direction}. Cache-aside: on miss query PostgreSQL, serialize to JSON via Jackson, store in Redis with TTL=3600s. On any config write (create/update/activate/deactivate) evict the affected key. Use Spring Data Redis RedisTemplate<String,String> with Jackson ObjectMapper. Also rate cache: config:rate:{ccyPair} with TTL=300s. RedisConfigCache is a @Component in services/config-registry. Not a Spring @Cache proxy; use explicit get/set/evict methods for full observability. | • Create RedisConfigCache.java @Component in services/config-registry/src/main/java/com/gme/pay/config/cache/ • Inject RedisTemplate<String,String> and ObjectMapper • Implement getScheme(String schemeCode): Optional<SchemeConfig> with cache-aside (miss -> DB -> serialize -> SET EX 3600) • Implement getPartner, getRule, getRate analogously with TTL 3600/3600/300 respectively • Implement evictScheme, evictPartner, evictRule, evictRate methods that call RedisTemplate.delete(key) | services/config-registry/src/main/java/com/gme/pay/config/cache/RedisConfigCache.java | • Second getScheme call for same code does not invoke QrSchemeRepository (verify via Mockito spy) • evictScheme removes the key; TTL on evicted key returns -2 (key does not exist) • JSON deserialization produces SchemeConfig with BigDecimal gmeFeeSha rePct intact (not rounded) • Cache miss on unknown schemeCode returns Optional.empty() without NullPointerException • Rate cache TTL <= 300 seconds confirmed via RedisTemplate.getExpire | 45 | 2.5-T11 | BE | NFR-10, SAD-02
2.5-T13 | config-registry | 2.5 | 2. Architecture & Technical Foundation | Configuration framework (config-not-code) | 1 | Implement SchemeRegistryService and PartnerRegistryService implementing port interfaces | These @Service classes implement SchemeRegistryPort and PartnerRegistryPort from lib-api-contracts. SchemeRegistryService.findByCode: RedisConfigCache.getScheme hit; on miss query QrSchemeRepository, map QrScheme entity to SchemeConfig record, store in cache. findActiveByCountry(KR): query SchemeCountryRepository for is_active=true rows matching country_code, load QrScheme for each, filter qr_scheme.is_active=true. PartnerRegistryService.findByCode: same cache-aside pattern. Mapping must copy all BigDecimal fields exactly. Module: services/config-registry. These service beans are the only implementations of the port interfaces; consuming services inject them via interface type. | • Create SchemeRegistryService.java @Service implements SchemeRegistryPort • Inject RedisConfigCache, QrSchemeRepository, SchemeCountryRepository • Implement findByCode: cache hit then DB fallback; map QrScheme -> SchemeConfig record • Implement findActiveByCountry: DB-only query joining scheme_country and qr_scheme on is_active • Create PartnerRegistryService.java @Service implements PartnerRegistryPort • Add private mapping methods qrSchemeToConfig and partnerToConfig | services/config-registry/src/main/java/com/gme/pay/config/service/SchemeRegistryService.java, PartnerRegistryService.java | • findByCode(ZEROPAY) returns non-empty Optional<SchemeConfig> after V206 seed • findActiveByCountry(KR) returns list containing entry with schemeCode=ZEROPAY • findByCode(UNKNOWN) returns Optional.empty() • SchemeConfig.partnerBQuoteDeviationPct equals 0.0100 (BigDecimal compareTo 0) • PartnerRegistryService.findByCode(GME_REMIT) returns PartnerConfig with partnerType=LOCAL | 40 | 2.5-T12 | BE | NFR-10, SAD-02
2.5-T14 | config-registry | 2.5 | 2. Architecture & Technical Foundation | Configuration framework (config-not-code) | 1 | Implement RuleRegistryService implementing RuleRegistryPort interface | RuleRegistryService implements RuleRegistryPort.findActiveRule(partnerId, schemeId, direction). Steps: 1) check RedisConfigCache key config:rule:{partnerId}:{schemeId}:{direction}; 2) on miss query RuleRepository.findByPartnerIdAndSchemeIdAndDirectionAndStatus with ACTIVE; 3) map Rule JPA entity to RuleConfig record preserving all BigDecimal fields; 4) cache. Also findAllActiveRules(): RuleRepository.findByStatus(ACTIVE) for admin listing. Important: only ACTIVE rules are served; DRAFT and SUSPENDED return Optional.empty(). Config changes apply to new transactions only (SAD-02 §11.3). Module: services/config-registry. | • Create RuleRegistryService.java @Service implements RuleRegistryPort • Implement findActiveRule: RedisConfigCache.getRule first; DB fallback for status=ACTIVE only • Map Rule entity to RuleConfig; ensure mA, mB, serviceChargeAmount are BigDecimal • Implement findAllActiveRules() returning List<RuleConfig> • Javadoc: rule changes apply to NEW transactions only; in-flight transactions use config at CommitTransaction | services/config-registry/src/main/java/com/gme/pay/config/service/RuleRegistryService.java | • findActiveRule for a DRAFT rule returns Optional.empty() • findActiveRule for a SUSPENDED rule returns Optional.empty() • RuleConfig.mA is BigDecimal; value 0.010000 preserved (scale 6) • findAllActiveRules returns empty list when no ACTIVE rules exist without throwing • After rule margin update and cache eviction, next findActiveRule returns updated mA value | 35 | 2.5-T13 | BE | NFR-10, SAD-02
2.5-T15 | config-registry | 2.5 | 2. Architecture & Technical Foundation | Configuration framework (config-not-code) | 1 | Implement TreasuryRateService implementing TreasuryRatePort interface | TreasuryRateService implements TreasuryRatePort. getLatestRate(ccyPair): check Redis key config:rate:{ccyPair}; on miss query TreasuryRateRepository.findFirstByCcyPairOrderByEffectiveAtDesc; throw RateNotFoundException if no row; cache with TTL=300s; return TreasuryRateSnapshot including rateId for audit FK. getLatestRateOrIdentity(ccyPair): if ccyPair equals usd_usd (identity leg where settle_ccy=USD) return TreasuryRateSnapshot(usd_usd, BigDecimal.ONE, IDENTITY, Instant.now(), null) without DB call. Treasury rate updates take effect immediately for new quotes (rate cache TTL=300s max staleness). Module: services/config-registry. | • Create TreasuryRateService.java @Service implements TreasuryRatePort • Implement getLatestRate: Redis cache lookup then TreasuryRateRepository fallback; throw RateNotFoundException if absent • Implement getLatestRateOrIdentity: check if ccyPair matches usd_usd pattern; return BigDecimal.ONE snapshot • Evict Redis rate cache key in same @Transactional as TreasuryRateAdminService.createRate (see 2.5-T20) • Return TreasuryRateSnapshot with rateId = treasury_rate.id for commit-time lock reference | services/config-registry/src/main/java/com/gme/pay/config/service/TreasuryRateService.java | • getLatestRate(usd_krw) returns snapshot with rate.compareTo(new BigDecimal(1380)) == 0 after V206 seed • getLatestRate(usd_xyz) throws RateNotFoundException • getLatestRateOrIdentity(usd_usd) returns BigDecimal.ONE without any DB call (verify via Mockito verify no interactions) • TreasuryRateSnapshot.rateId matches the PK of the treasury_rate row • Rate cache evicted after new rate insert; subsequent getLatestRate returns new value | 35 | 2.5-T14 | BE | NFR-10, SAD-02
2.5-T16 | config-registry | 2.5 | 2. Architecture & Technical Foundation | Configuration framework (config-not-code) | 1 | Implement AuditLogService: append-only config change logging within same transaction | Every config write (scheme/partner/rule create/update/activate/deactivate, treasury rate insert) must write to audit_log atomically in the same DB transaction as the change. AuditLogService.logChange(String entityType, Long entityId, String action, Object before, Object after): serialize before/after to JSONB via Jackson, extract actor from Spring Security SecurityContextHolder.getContext().getAuthentication().getName(), persist AuditLog entity. AuditLog entity maps to audit_log table (V205). No UPDATE/DELETE on audit_log (enforced by DB rule in V205). Module: services/config-registry. Actor roles: OPERATOR (human), SYSTEM (automated), PARTNER. | • Create AuditLog.java @Entity in services/config-registry/src/main/java/com/gme/pay/config/audit/ (no setters after construction) • Create AuditLogRepository extending JpaRepository<AuditLog, Long>; add findByEntityTypeAndEntityId • Create AuditLogService.java @Service • Implement logChange: extract actor from SecurityContextHolder; serialize before/after via ObjectMapper; call AuditLogRepository.save • Add @Transactional(propagation=MANDATORY) to logChange to enforce it is always called within an existing transaction | services/config-registry/src/main/java/com/gme/pay/config/audit/AuditLogService.java, AuditLog.java | • logChange for CREATE action: before_value=null, after_value contains entity JSON • logChange for UPDATE: both before_value and after_value populated with JSON snapshots • actor_id field populated from SecurityContextHolder principal name • @Transactional(propagation=MANDATORY) causes TransactionRequiredException when called outside a transaction • AuditLogRepository has no deleteBy methods; direct DB DELETE on audit_log row fails (V205 rule) | 40 | 2.5-T11 | BE | NFR-10, SAD-02
2.5-T17 | config-registry | 2.5 | 2. Architecture & Technical Foundation | Configuration framework (config-not-code) | 1 | Implement SchemeAdminService: CRUD and lifecycle for qr_scheme and scheme_country | SchemeAdminService manages the QR scheme registry. Operations: createScheme (new row, status=TESTING), activateScheme (TESTING->ACTIVE: verify treasury_rate exists for scheme payout_ccy before activating; set is_active=true), deactivateScheme (ACTIVE->INACTIVE), updateScheme (name, fees only; not scheme_code), addCountry, removeCountry. Each write: @Transactional + call AuditLogService.logChange + call RedisConfigCache.evictScheme. activateScheme must be separate from createScheme (two-step safety). Reject activation if no treasury_rate row found for scheme payout_ccy. Module: services/config-registry. | • Create SchemeAdminService.java @Service in services/config-registry/src/main/java/com/gme/pay/config/service/ • Implement createScheme(@Valid SchemeCreateRequest req): persist QrScheme status=TESTING, call logChange action=CREATE • Implement activateScheme(Long schemeId): check TreasuryRateRepository has row for scheme payout_ccy; set status=ACTIVE is_active=true; logChange action=ACTIVATE; evictScheme • Implement updateScheme and deactivateScheme with snapshot-before-change pattern for audit • Implement addCountry(Long schemeId, String countryCode) and removeCountry with audit | services/config-registry/src/main/java/com/gme/pay/config/service/SchemeAdminService.java | • createScheme returns persisted entity with status=TESTING and is_active=false • activateScheme throws ConfigValidationException with code MISSING_TREASURY_RATE when no treasury_rate for payout_ccy • audit_log row created after each operation with correct entity_type=qr_scheme • Redis cache evicted after activateScheme (next cache.getScheme returns fresh value from DB) • activateScheme called twice on same id is idempotent (no exception on second call) | 45 | 2.5-T16 | BE | NFR-10, SAD-02
2.5-T18 | config-registry | 2.5 | 2. Architecture & Technical Foundation | Configuration framework (config-not-code) | 1 | Implement PartnerAdminService: onboarding lifecycle, credential generation for partners | PartnerAdminService operations: createPartner (status=ONBOARDING), activatePartner (ONBOARDING->ACTIVE: requires at least one active partner_credential; OVERSEAS requires low_balance_threshold_usd not null), suspendPartner, generateCredential (UUID api_key + random 32-byte secret + bcrypt hash; return plaintext ONCE), revokeCredential. Security: api_secret stored as bcrypt hash only; plaintext returned only from generateCredential return value and never retrievable again. HMAC signing secret for Northbound auth is referenced via api_credential_ref pointing to Vault (not stored in DB column). Module: services/config-registry. | • Create PartnerAdminService.java @Service • Implement createPartner: validate partner_type; persist with status=ONBOARDING; call logChange CREATE • Implement generateCredential(Long partnerId): generate UUID api_key, SecureRandom 32-byte secret, BCryptPasswordEncoder.encode; persist PartnerCredential; return SecretIssuance(apiKey, plaintextSecret) • Implement activatePartner: check active credential exists; if OVERSEAS check low_balance_threshold_usd not null; set status=ACTIVE; logChange ACTIVATE; evictPartner • Implement suspendPartner: set status=SUSPENDED; logChange DEACTIVATE; evictPartner | services/config-registry/src/main/java/com/gme/pay/config/service/PartnerAdminService.java | • generateCredential returns plaintext secret; api_secret_hash in DB starts with $2a$ (bcrypt) • activatePartner for OVERSEAS partner with null low_balance_threshold_usd throws ConfigValidationException • activatePartner with no active credential throws ConfigValidationException • audit_log has CREATE action with after_value.partner_code for createPartner • suspendPartner evicts Redis key config:partner:{partnerCode} | 45 | 2.5-T17 | BE | NFR-10, SAD-02
2.5-T19 | config-registry | 2.5 | 2. Architecture & Technical Foundation | Configuration framework (config-not-code) | 1 | Implement RuleAdminService: rule lifecycle with margin constraint enforcement | RuleAdminService: createRule (status=DRAFT; compute is_same_ccy_shortcircuit = collection_ccy=settle_a_ccy=settle_b_ccy=payout_ccy), activateRule (DRAFT->ACTIVE: validate m_a+m_b >= 0.02 for cross-border i.e. isSameCcyShortcircuit=false; for same-currency 0.0 is allowed; validate MANUAL rate source has non-null manual_rate populated; set effective_from=NOW()), updateMargins (re-validate constraint, evict cache), suspendRule, addServiceChargeTier (validate non-overlapping ranges), removeServiceChargeTier. Each write: @Transactional + audit + cache evict. Module: services/config-registry. | • Create RuleAdminService.java @Service • Implement createRule: derive isSameCcyShortcircuit; persist status=DRAFT; logChange CREATE • Implement activateRule: for cross-border rules assert mA.add(mB).compareTo(new BigDecimal(0.02)) >= 0; for MANUAL source assert manualRateColl not null; set effective_from=NOW(); status=ACTIVE; logChange ACTIVATE; evictRule • Implement updateMargins: capture before snapshot; re-validate constraint; update; audit; evictRule • Implement addServiceChargeTier: check no range overlap with existing tiers for rule_id | services/config-registry/src/main/java/com/gme/pay/config/service/RuleAdminService.java | • activateRule cross-border m_a=0.009 m_b=0.010 (sum 1.9%) throws ConfigValidationException mentioning 2% • activateRule cross-border m_a=0.010 m_b=0.010 (sum 2.0%) succeeds • Same-currency rule m_a=0.0 m_b=0.0 activates without exception • activateRule with MANUAL source and null manualRateColl throws ConfigValidationException • is_same_ccy_shortcircuit=true when all four ccys equal KRW (GME_REMIT DOMESTIC scenario) | 45 | 2.5-T18 | BE | NFR-10, SAD-02
2.5-T20 | config-registry | 2.5 | 2. Architecture & Technical Foundation | Configuration framework (config-not-code) | 1 | Implement TreasuryRateAdminService: manual rate entry with immediate cache invalidation | In Phase 1 GME Ops manually enters treasury rates (SAD-02 §4.7, BRD §10.4). TreasuryRateAdminService.createRate(String ccyPair, BigDecimal rate, String source): validate ccyPair matches usd_[a-z]{3} (e.g. usd_krw); rate > 0; insert new treasury_rate row (append-only, never update); evict Redis key config:rate:{ccyPair}; call AuditLogService.logChange(treasury_rate, id, CREATE, previousSnapshot, newSnapshot) where previousSnapshot = current latest row. Rates take effect immediately for new rate quotes. Historical rows are retained forever (BOK). Module: services/config-registry. | • Create TreasuryRateAdminService.java @Service • Validate ccyPair matches regex usd_[a-z]{3} using Pattern.matches • Validate rate.compareTo(BigDecimal.ZERO) > 0 • Capture previousSnapshot via TreasuryRateRepository.findFirstByCcyPairOrderByEffectiveAtDesc • Persist new TreasuryRate with source=MANUAL, effectiveAt=Instant.now() inside @Transactional • Evict Redis key and call logChange in same transaction | services/config-registry/src/main/java/com/gme/pay/config/service/TreasuryRateAdminService.java | • createRate(usd_krw, 1385.0) inserts new row; TreasuryRateService.getLatestRate(usd_krw) returns 1385.0 • createRate with rate=0 throws ConfigValidationException • createRate with ccyPair=krw_usd throws ConfigValidationException (wrong direction) • Old usd_krw row with rate=1380 still exists after createRate (no delete) • AuditLog row created with entity_type=treasury_rate and after_value.rate=1385.0 | 35 | 2.5-T15, 2.5-T16 | BE | NFR-10, SAD-02
2.5-T21 | config-registry | 2.5 | 2. Architecture & Technical Foundation | Configuration framework (config-not-code) | 1 | Create Flyway migration V207: config_outbox table for transactional outbox | Config changes publish domain events via transactional Outbox pattern (STACK.md: outbox now, Kafka behind interface). config_outbox: id BIGINT PK, aggregate_type VARCHAR(50), aggregate_id BIGINT, event_type VARCHAR(100), payload JSONB, created_at TIMESTAMPTZ DEFAULT NOW(), published BOOLEAN DEFAULT FALSE. Index on (published, created_at) for efficient poll query: SELECT ... WHERE published=FALSE ORDER BY created_at LIMIT 50. Module: services/config-registry. Published rows are never deleted in Phase 1 (retained for replay/debug); cleanup job is out of scope. | • Create V207__config_outbox.sql in services/config-registry/src/main/resources/db/migration/ • Define config_outbox table with columns per context • Add index idx_config_outbox_unpublished ON config_outbox(published, created_at) WHERE published=FALSE • Add comment: this table implements the transactional outbox pattern; Phase 2 adds Kafka transport | services/config-registry/src/main/resources/db/migration/V207__config_outbox.sql | • Flyway V207 applies cleanly after V206 • Index idx_config_outbox_unpublished visible in pg_indexes • INSERT with published DEFAULT inserts as FALSE • payload column is JSONB type (not TEXT) • Flyway V201-V207 all apply in sequence without error on fresh Testcontainers PostgreSQL 16 | 20 | 2.5-T06 | BE | NFR-10, SAD-02
2.5-T22 | config-registry | 2.5 | 2. Architecture & Technical Foundation | Configuration framework (config-not-code) | 1 | Implement ConfigChangeEventPublisher and OutboxPoller for domain event dispatch | ConfigChangeEventPublisher inserts rows into config_outbox in the same DB transaction as config writes (guaranteed delivery). Event types: SchemeActivatedEvent, PartnerActivatedEvent, RuleUpdatedEvent, TreasuryRateUpdatedEvent. Schemas defined in lib-events. OutboxPoller: Spring @Scheduled(fixedDelay=5000) polls for published=FALSE rows, calls EventPublisher.publish(event) from lib-events interface (in-process impl in Phase 1; Kafka wired in Phase 2), marks published=TRUE. Module: services/config-registry. Kafka is NOT wired in this ticket; only the outbox INSERT and poller. | • Create ConfigOutbox.java @Entity mapping config_outbox table • Create ConfigOutboxRepository extending JpaRepository with findTop50ByPublishedFalseOrderByCreatedAtAsc • Create ConfigChangeEventPublisher.java @Component with publish(ConfigChangeEvent event): INSERT into config_outbox in calling @Transactional • Create OutboxPoller.java @Component with @Scheduled(fixedDelay=5000): fetch unpublished, call EventPublisher.publish, set published=true • Wire SchemeAdminService and RuleAdminService to call ConfigChangeEventPublisher after each write | services/config-registry/src/main/java/com/gme/pay/config/events/ConfigChangeEventPublisher.java, OutboxPoller.java, ConfigOutbox.java | • Config change and outbox INSERT are in same DB transaction (rollback of config write removes outbox row) • OutboxPoller marks rows published=true after EventPublisher.publish without error • SchemeActivatedEvent payload contains fields schemeId and schemeCode • OutboxPoller does not republish rows already marked published=true • findTop50 limits poll batch to 50 rows to prevent large in-memory spikes | 45 | 2.5-T21, 2.5-T19, 2.5-T20 | BE | NFR-10, SAD-02
2.5-T23 | config-registry | 2.5 | 2. Architecture & Technical Foundation | Configuration framework (config-not-code) | 1 | Implement ConfigRegistryRestController: scheme, partner, rule, treasury-rate admin endpoints | REST API for Admin Portal BFF. @RestController @RequestMapping(/internal/v1/config) in services/config-registry. Endpoints: POST /schemes (create), PATCH /schemes/{id}/activate, GET /schemes. POST /partners, PATCH /partners/{id}/activate, PATCH /partners/{id}/suspend, POST /partners/{id}/credentials. POST /rules, PATCH /rules/{id}/activate, PUT /rules/{id}/margins. POST /treasury-rates, GET /treasury-rates. Secured by @PreAuthorize: write ops require SUPER_ADMIN or OPS_ADMIN; read ops allow OPS_VIEWER. Returns lib-errors ApiError on failure. Response codes: 201 create, 200 update/read, 422 validation, 403 auth, 401 unauth. Module: services/config-registry. | • Create ConfigRegistryRestController.java @RestController in services/config-registry/src/main/java/com/gme/pay/config/api/ • Inject all admin services • Map POST /schemes -> schemeAdminService.createScheme(@Valid @RequestBody); return 201 • Map PATCH /schemes/{id}/activate; return 200 with updated SchemeConfig • Map POST /partners/{id}/credentials; return 201 with body {apiKey, secret} (plaintext returned once) • Add @PreAuthorize(hasAnyRole(SUPER_ADMIN,OPS_ADMIN)) on write methods; hasAnyRole(SUPER_ADMIN,OPS_ADMIN,OPS_VIEWER) on GET methods | services/config-registry/src/main/java/com/gme/pay/config/api/ConfigRegistryRestController.java | • POST /schemes with valid body returns 201 and JSON with id and status=TESTING • PATCH /schemes/{id}/activate when treasury_rate missing returns 422 with errorCode=MISSING_TREASURY_RATE • POST /partners/{id}/credentials returns 201 with apiKey and secret fields • OPS_VIEWER JWT calling POST /schemes returns 403 • GET /schemes returns 200 with JSON array even when empty | 45 | 2.5-T17, 2.5-T18, 2.5-T19, 2.5-T20 | BE | NFR-10, SAD-02
2.5-T24 | config-registry | 2.5 | 2. Architecture & Technical Foundation | Configuration framework (config-not-code) | 1 | Implement GET list endpoints for rules, partners, and treasury-rate history | Admin Portal UI needs list views for Schemes/Partners/Rules/Margins sections (PRD-07). Add to ConfigRegistryRestController: GET /internal/v1/config/rules?status=ACTIVE, GET /internal/v1/config/partners?status=ACTIVE, GET /internal/v1/config/treasury-rates?ccyPair=usd_krw. Lists served from DB (not Redis, to ensure completeness). Default page size 50, max 200 via @RequestParam. OPS_VIEWER is sufficient. status param validated against allowed enum values; invalid status returns 400. Module: services/config-registry. | • Add GET /rules endpoint to ConfigRegistryRestController; inject RuleRegistryService.findAllRulesByStatus • Implement RuleRegistryService.findAllRulesByStatus(String status) using RuleRepository.findByStatus • Add GET /partners using PartnerRegistryService.findAllByStatus • Add GET /treasury-rates with optional ccyPair filter; return list ordered by effectiveAt DESC • Add @RequestParam validation: status must be one of DRAFT, ACTIVE, SUSPENDED (rule) or ONBOARDING, ACTIVE, SUSPENDED, INACTIVE (partner) | services/config-registry/src/main/java/com/gme/pay/config/api/ConfigRegistryRestController.java (updated), updated RuleRegistryService.java and PartnerRegistryService.java | • GET /rules?status=ACTIVE returns 200 with array (empty array OK) • GET /rules?status=INVALID returns 400 with errorCode=INVALID_PARAM • GET /treasury-rates?ccyPair=usd_krw returns both historical rows newest-first after createRate adds second row • GET /partners without status param defaults to ACTIVE filter • OPS_VIEWER can call all GET endpoints; POST returns 403 for OPS_VIEWER | 40 | 2.5-T23 | BE | NFR-10, SAD-02
2.5-T25 | config-registry | 2.5 | 2. Architecture & Technical Foundation | Configuration framework (config-not-code) | 1 | Implement Spring Security 6 config: OAuth2/JWT RBAC for config-registry | Admin endpoints (/internal/v1/config/**) secured by OAuth2/JWT (STACK.md). Roles in JWT claims: SUPER_ADMIN, OPS_ADMIN, OPS_VIEWER, FINANCE. Spring Security 6 SecurityFilterChain: .oauth2ResourceServer(oauth2 -> oauth2.jwt(Customizer.withDefaults())). JwtAuthenticationConverter extracts roles from custom JWT claim roles as ROLE_ prefixed authorities. /actuator/health is public. Write ops: SUPER_ADMIN or OPS_ADMIN. Read ops: any of the four roles. application.yml: spring.security.oauth2.resourceserver.jwt.jwk-set-uri configurable via env var. Module: services/config-registry. | • Create SecurityConfig.java @Configuration @EnableWebSecurity in services/config-registry/src/main/java/com/gme/pay/config/security/ • Define SecurityFilterChain with .oauth2ResourceServer JWT config • Configure JwtAuthenticationConverter: extract roles claim as List<String> mapped to GrantedAuthority with ROLE_ prefix • Add requestMatchers: POST/PATCH/PUT on /internal/** -> hasAnyRole(SUPER_ADMIN,OPS_ADMIN); GET /internal/** -> hasAnyRole(SUPER_ADMIN,OPS_ADMIN,OPS_VIEWER,FINANCE); /actuator/health -> permitAll • Add application.yml spring.security.oauth2.resourceserver.jwt.jwk-set-uri=${JWT_JWK_SET_URI} | services/config-registry/src/main/java/com/gme/pay/config/security/SecurityConfig.java | • JWT with role=OPS_VIEWER: GET /internal/v1/config/schemes returns 200 • JWT with role=OPS_VIEWER: POST /internal/v1/config/schemes returns 403 • No JWT on POST returns 401 (not 403) • GET /actuator/health returns 200 without Authorization header • SecurityFilterChain does not use deprecated WebSecurityConfigurerAdapter | 40 | 2.5-T23 | BE | NFR-10, SAD-02
2.5-T26 | config-registry | 2.5 | 2. Architecture & Technical Foundation | Configuration framework (config-not-code) | 1 | Implement PartnerAuthService: HMAC-SHA256 Northbound API request validation | Partners authenticate Northbound API calls via HMAC-SHA256 (STACK.md). PartnerAuthService.validateRequest(String apiKey, String signature, String requestBody, Instant timestamp): 1) lookup PartnerCredential by api_key from DB or cache; 2) retrieve raw HMAC signing secret from Vault via api_credential_ref; 3) compute expected = HMAC-SHA256(concat(apiKey, :, timestamp.toString(), :, requestBody), signingSecret) via javax.crypto.Mac; 4) compare with provided signature (constant-time comparison via MessageDigest.isEqual); 5) reject if abs(now - timestamp) > 5 minutes (replay protection). Returns resolved PartnerConfig on success. Module: services/config-registry. Vault client: Spring Cloud Vault or simple REST call to Vault KV API. | • Create PartnerAuthService.java @Service in services/config-registry/src/main/java/com/gme/pay/config/auth/ • Implement lookupCredential(String apiKey): PartnerCredential from DB via PartnerCredentialRepository • Implement verifyHmac: fetch raw secret from Vault via api_credential_ref; compute HMAC-SHA256 using Mac.getInstance(HmacSHA256); compare with MessageDigest.isEqual (constant-time) • Add timestamp staleness check: throw AuthException(HMAC_TIMESTAMP_EXPIRED) if abs(now-ts) > 300 seconds • On success resolve and return PartnerConfig via PartnerRegistryService.findById | services/config-registry/src/main/java/com/gme/pay/config/auth/PartnerAuthService.java | • Valid HMAC with fresh timestamp returns non-null PartnerConfig • Tampered request body results in HMAC mismatch returning false (not exception) • Timestamp 6 minutes old throws AuthException with code HMAC_TIMESTAMP_EXPIRED • Unknown api_key throws AuthException with code UNKNOWN_API_KEY • HMAC computed via HmacSHA256 not MD5 | 40 | 2.5-T18 | BE | NFR-10, SAD-02
2.5-T27 | config-registry | 2.5 | 2. Architecture & Technical Foundation | Configuration framework (config-not-code) | 1 | Unit tests: RuleAdminService margin validation vectors with Mockito | Pure unit test for RuleAdminService margin constraint logic (no DB needed). Mock RuleRepository, AuditLogService, RedisConfigCache, SecurityContextHolder. Vectors: 1) cross-border m_a=0.010000 m_b=0.010000 -> activateRule succeeds. 2) cross-border m_a=0.009000 m_b=0.010000 (sum=0.019) -> ConfigValidationException message contains 2%. 3) same-currency m_a=0 m_b=0 isSameCcyShortcircuit=true -> succeeds. 4) MANUAL source manualRateColl=null -> ConfigValidationException before any DB write. 5) createRule with collection_ccy=KRW settle_a=KRW settle_b=KRW payout_ccy=KRW -> isSameCcyShortcircuit=true in saved Rule. Module: services/config-registry. | • Create RuleAdminServiceTest.java in services/config-registry/src/test/java/com/gme/pay/config/service/ • Annotate @ExtendWith(MockitoExtension.class); mock RuleRepository, AuditLogService, RedisConfigCache • Stub SecurityContextHolder to return actor=test-operator • Write 5 @Test methods per vectors above • For vector 2 assert exception.getMessage().contains(2%) or contains(2.0%) • For vector 4 verify RuleRepository.save is never called (Mockito.verify(ruleRepository, never()).save(any())) | services/config-registry/src/test/java/com/gme/pay/config/service/RuleAdminServiceTest.java | • All 5 test methods pass with ./gradlew :services:config-registry:test • Vector 2 exception message contains 2% • Vector 3 passes without any exception • Vector 4: RuleRepository.save never called (verified by Mockito) • BigDecimal comparisons use compareTo(0) not .equals() for scale-safe assertions | 40 | 2.5-T19 | BE | NFR-10, SAD-02
2.5-T28 | config-registry | 2.5 | 2. Architecture & Technical Foundation | Configuration framework (config-not-code) | 1 | Unit tests: TreasuryRateService identity-leg and cache behavior with Mockito | Unit tests for TreasuryRateService. Mock TreasuryRateRepository and RedisConfigCache. Vectors: 1) getLatestRate(usd_krw) returns rate=1380.0. 2) getLatestRate(usd_xyz) throws RateNotFoundException. 3) getLatestRateOrIdentity(usd_usd) returns BigDecimal.ONE; zero interactions with repository. 4) Cache hit: prime cache on first call; second call to getLatestRate skips repo (cache returns hit). 5) After eviction, third call goes back to repo. Assert rateId in snapshot matches stubbed TreasuryRate.id. Module: services/config-registry. | • Create TreasuryRateServiceTest.java using @ExtendWith(MockitoExtension.class) • Mock TreasuryRateRepository, RedisConfigCache with ArgumentCaptor where needed • Vector 1: stub findFirst... to return TreasuryRate(id=42, ccy=usd_krw, rate=1380); assert snapshot.rate.compareTo(1380)==0 and rateId==42 • Vector 2: stub to return Optional.empty(); assertThrows(RateNotFoundException.class) • Vector 3: call getLatestRateOrIdentity(usd_usd); verifyNoInteractions(treasuryRateRepository) • Vector 4+5: stub cache to return empty then hit; verify repo call count | services/config-registry/src/test/java/com/gme/pay/config/service/TreasuryRateServiceTest.java | • All 5 test methods pass • Vector 3: verifyNoInteractions passes (no DB call for identity leg) • Vector 2: exception type is exactly RateNotFoundException • Snapshot rate is BigDecimal with original scale preserved • Cache eviction test: reposito ry call count is 1 for two getLatestRate calls with cache primed after first | 35 | 2.5-T15 | BE | NFR-10, SAD-02
2.5-T29 | config-registry | 2.5 | 2. Architecture & Technical Foundation | Configuration framework (config-not-code) | 1 | Unit tests: PartnerAuthService HMAC validation with known test vectors | Unit tests for PartnerAuthService. Mock PartnerCredentialRepository and Vault client. Precomputed test vector: apiKey=testkey123, signingSecret=supersecret, requestBody={amount:100}, timestamp=2026-06-05T00:00:00Z. Compute expected HMAC-SHA256 in test setup using Mac.getInstance(HmacSHA256). Tests: 1) correct key+signature returns PartnerConfig. 2) wrong signing secret causes mismatch. 3) body tampered to {amount:101} causes mismatch. 4) timestamp = Instant.now().minus(6, MINUTES) throws HMAC_TIMESTAMP_EXPIRED. 5) unknown api_key throws UNKNOWN_API_KEY. Module: services/config-registry. | • Create PartnerAuthServiceTest.java @ExtendWith(MockitoExtension.class) • @BeforeEach: compute expectedHmac using Mac.getInstance(HmacSHA256) with the test vector • Vector 1: stub repo returns valid credential; stub Vault returns supersecret; assert non-null PartnerConfig • Vector 2: stub Vault returns wrongsecret; assert HMAC mismatch • Vector 3: call with body={amount:101} against expectedHmac for {amount:100}; assert false • Vector 4: call with timestamp = Instant.now().minus(Duration.ofMinutes(6)); assertThrows AuthException with code HMAC_TIMESTAMP_EXPIRED • Vector 5: stub repo returns Optional.empty(); assertThrows AuthException UNKNOWN_API_KEY | services/config-registry/src/test/java/com/gme/pay/config/auth/PartnerAuthServiceTest.java | • All 5 test methods pass • Test uses fixed Instant (not Instant.now() in production code) to make replay test deterministic • HMAC algorithm is HmacSHA256 asserted via Mac.getAlgorithm() • Tampered body test uses correct expected HMAC (not just any string comparison) • Exception codes are exact string constants HMAC_TIMESTAMP_EXPIRED and UNKNOWN_API_KEY | 40 | 2.5-T26 | BE | NFR-10, SAD-02
2.5-T30 | config-registry | 2.5 | 2. Architecture & Technical Foundation | Configuration framework (config-not-code) | 1 | Integration test: SchemeRegistryService cache-aside with Testcontainers PostgreSQL and Redis | Integration test using @SpringBootTest with Testcontainers PostgreSQL 16 and Redis 7. Flyway V201-V207 apply automatically at startup. Test scenarios: A) findByCode(ZEROPAY) after V206 seed returns non-empty SchemeConfig with payoutCcy=KRW; B) second findByCode call served from Redis cache (spy on QrSchemeRepository: findBySchemeCode called exactly once); C) findActiveByCountry(KR) returns list with ZEROPAY; D) findByCode(UNKNOWN) returns empty without exception; E) activateScheme then findByCode returns status=ACTIVE (cache invalidation works). Module: services/config-registry. | • Create ConfigRegistryIntegrationTest.java in services/config-registry/src/test/java/com/gme/pay/config/ • Annotate @SpringBootTest @Testcontainers; declare @Container PostgreSQLContainer and @Container GenericContainer (Redis 7-alpine) • Override datasource and redis host properties via @DynamicPropertySource • Inject SchemeRegistryService; use @SpyBean QrSchemeRepository to count DB calls • Write 5 @Test methods for scenarios A-E | services/config-registry/src/test/java/com/gme/pay/config/ConfigRegistryIntegrationTest.java | • All 5 tests pass with ./gradlew :services:config-registry:test • Scenario B: QrSchemeRepository.findBySchemeCode invoked exactly once for two findByCode calls • Scenario D: Optional.empty() returned, no exception • Scenario E: findByCode returns SchemeConfig with status=ACTIVE after activateScheme (cache eviction validated) • Test suite completes in under 60 seconds including Testcontainers startup | 45 | 2.5-T17 | BE | NFR-10, SAD-02
2.5-T31 | config-registry | 2.5 | 2. Architecture & Technical Foundation | Configuration framework (config-not-code) | 1 | Integration test: outbox publish and cache invalidation on config change end-to-end | Integration test on Testcontainers PostgreSQL. Scenario A (outbox): call schemeAdminService.activateScheme; assert config_outbox row inserted with published=FALSE; wait up to 10 seconds for OutboxPoller tick; assert published=TRUE and EventPublisher.publish called with SchemeActivatedEvent. Scenario B (rollback): wrap in test @Transactional rollback; assert no outbox row after rollback (atomicity proof). Scenario C (cache evict + outbox): call ruleAdminService.updateMargins; assert both outbox row inserted AND Redis key evicted within same transaction. Module: services/config-registry. | • Create OutboxIntegrationTest.java @SpringBootTest @Testcontainers • Declare PostgreSQLContainer; use @MockBean or @SpyBean on EventPublisher interface • Seed a TESTING scheme; insert its treasury_rate so activateScheme can succeed • Scenario A: call activateScheme; assert outbox row published=FALSE then true within 10s Awaitility wait • Scenario B: annotate sub-test with @Transactional(rollbackFor=Exception) and throw; assert 0 outbox rows • Scenario C: updateMargins; assert outbox row and Redis eviction in same logical unit | services/config-registry/src/test/java/com/gme/pay/config/events/OutboxIntegrationTest.java | • Scenario A: EventPublisher.publish called exactly once with SchemeActivatedEvent • Scenario B: outbox row count=0 after rollback (outbox row was in same transaction) • OutboxPoller does not republish rows already marked published=TRUE • Scenario C: Redis key absent after updateMargins • Test total runtime under 45 seconds | 45 | 2.5-T22, 2.5-T30 | BE | NFR-10, SAD-02
2.5-T32 | config-registry | 2.5 | 2. Architecture & Technical Foundation | Configuration framework (config-not-code) | 1 | Add Prometheus metrics and OpenTelemetry tracing to config-registry service | STACK.md: OpenTelemetry traces+metrics+logs -> Prometheus + Grafana + Jaeger. For config-registry: 1) add micrometer-tracing-bridge-otel + opentelemetry-exporter-otlp to build.gradle; 2) metrics: config_registry_cache_hit_total and config_registry_cache_miss_total counters in RedisConfigCache (tags: entity_type=scheme/partner/rule/rate); config_registry_audit_write_seconds histogram in AuditLogService; 3) expose /actuator/prometheus; 4) add traceId to logback MDC (%X{traceId} in log pattern). OTEL endpoint via env var OTEL_EXPORTER_OTLP_ENDPOINT (no hardcode). Module: services/config-registry. | • Add io.micrometer:micrometer-tracing-bridge-otel and io.opentelemetry:opentelemetry-exporter-otlp to services/config-registry/build.gradle • Inject MeterRegistry into RedisConfigCache; increment config_registry_cache_hit_total or _miss_total with tag entity_type on each get call • Inject MeterRegistry into AuditLogService; wrap logChange with Timer.record(config_registry_audit_write_seconds) • Create src/main/resources/logback-spring.xml with pattern including %X{traceId} • Add management.endpoints.web.exposure.include=health,prometheus to application.yml; management.tracing.sampling.probability=1.0 | services/config-registry/build.gradle (updated), services/config-registry/src/main/resources/logback-spring.xml | • GET /actuator/prometheus returns 200 with body containing config_registry_cache_hit_total • Cache miss then hit: counter cache_miss=1 cache_hit=1 for entity_type=scheme • config_registry_audit_write_seconds_bucket present in metrics endpoint output • Log line for a cache operation contains traceId field in MDC • OTEL endpoint is read from env var OTEL_EXPORTER_OTLP_ENDPOINT; app starts without it set (export disabled gracefully) | 35 | 2.5-T25 | BE | NFR-10, SAD-02
2.5-T33 | config-registry | 2.5 | 2. Architecture & Technical Foundation | Configuration framework (config-not-code) | 1 | Add docker-compose services: config-registry, PostgreSQL 16, Redis 7, Vault dev for local dev | STACK.md: docker-compose for local dev infra. Root docker-compose.yml additions: postgres service (image postgres:16, POSTGRES_DB=gmepay, port 5433:5432 matching memory: local PostgreSQL on port 5433, named volume gmepay-pg-data), redis service (image redis:7-alpine, port 6379:6379), vault service (image hashicorp/vault, VAULT_DEV_ROOT_TOKEN_ID=dev-token, port 8200:8200, cap_add IPC_LOCK), config-registry service (build: ./services/config-registry, SPRING_DATASOURCE_URL=jdbc:postgresql://postgres:5432/gmepay, SPRING_DATA_REDIS_HOST=redis, VAULT_ADDR=http://vault:8200, port 8085:8080, depends_on postgres redis vault, healthcheck via /actuator/health). Module: root. | • Open (or create) docker-compose.yml at repo root • Add postgres service with correct image, env, port 5433:5432, volume • Add redis service image redis:7-alpine port 6379:6379 • Add vault service in dev mode with dev-token and IPC_LOCK cap • Add config-registry service with build context, env vars, depends_on, and healthcheck on http://localhost:8085/actuator/health • Run docker compose config to validate YAML syntax | docker-compose.yml (root) updated with postgres, redis, vault, and config-registry services | • docker compose config validates without error • config-registry service depends_on list includes postgres and redis • postgres port mapping is 5433:5432 • vault VAULT_DEV_ROOT_TOKEN_ID=dev-token set • config-registry healthcheck curl http://localhost:8085/actuator/health returns 0 exit code after startup | 35 | 2.5-T09 | BE | NFR-10, SAD-02
2.6-T01 | shared-libs | 2.6 | 2. Architecture & Technical Foundation | Internationalization framework | 1 | Define CurrencyConfig record in lib-money: ISO 4217 code, scale, and display rules | GMEPay+ handles multiple currencies (KRW, USD, MNT, THB) each with an ISO 4217 three-letter code and a fixed decimal scale. KRW scale=0 (no sub-unit); USD scale=2. This record is the single source of truth used by the rate engine, formatters, and validators to apply correct rounding and prevent fractional KRW output. Module: lib-money (shared Gradle module at libs/lib-money). | • Create libs/lib-money/src/main/java/com/gme/pay/money/CurrencyConfig.java as a Java record with fields: isoCode (String), scale (int), displaySymbol (String). • Add CurrencyRegistry.java as a @Component class that loads CurrencyConfig entries from classpath:currencies.yml; expose getCurrency(String isoCode) throwing UnknownCurrencyException if not found, and listAll(). • Add libs/lib-money/src/main/resources/currencies.yml with entries for KRW (scale=0), USD (scale=2), MNT (scale=2), THB (scale=2). • Add UnknownCurrencyException.java in libs/lib-errors extending RuntimeException with the unknown code in the message. • Write Javadoc on CurrencyConfig stating that scale drives output rounding; DECIMAL(20,8) is the storage type but output must honour this field. | libs/lib-money/src/main/java/com/gme/pay/money/CurrencyConfig.java, CurrencyRegistry.java, libs/lib-money/src/main/resources/currencies.yml | • CurrencyRegistry.getCurrency(KRW).scale() == 0 • CurrencyRegistry.getCurrency(USD).scale() == 2 • getCurrency(ZZZ) throws UnknownCurrencyException with message containing ZZZ • listAll() returns exactly 4 entries after initial seeding • YAML file loads without Spring context errors in a plain unit test | 35 |  | BE | NFR-10
2.6-T02 | shared-libs | 2.6 | 2. Architecture & Technical Foundation | Internationalization framework | 1 | Add MoneyAmount value type to lib-money with BigDecimal, scale-aware rounding, and arithmetic methods | All monetary values in GMEPay+ are stored as DECIMAL(20,8) and computed with Java BigDecimal to avoid floating-point error (NFR-10 §5.1). MoneyAmount is an immutable record carrying the ISO currency code and enforcing per-currency scale from CurrencyConfig when round() is called. KRW amounts must produce zero fractional output. Module: lib-money. | • Create libs/lib-money/src/main/java/com/gme/pay/money/MoneyAmount.java as an immutable record: amount (BigDecimal), currency (String). • Add factory method of(BigDecimal amount, String isoCode) that validates isoCode via CurrencyRegistry. • Add round() returning a new MoneyAmount rounded to CurrencyConfig.scale() using RoundingMode.HALF_UP. • Add add(), subtract(), multiply(BigDecimal factor) operating on raw BigDecimal and returning unrounded MoneyAmount (caller calls round() explicitly at defined points only). • Implement toString() as {CURRENCY} {AMOUNT} formatted to scale, e.g. KRW 1000, USD 10.25. | libs/lib-money/src/main/java/com/gme/pay/money/MoneyAmount.java | • MoneyAmount.of(new BigDecimal(1000.5), KRW).round().amount() equals new BigDecimal(1001) • MoneyAmount.of(new BigDecimal(10.256), USD).round().amount() equals new BigDecimal(10.26) • add() does not auto-round; rounding only on explicit round() call • multiply(BigDecimal.ZERO) returns MoneyAmount with amount=0 for same currency • toString() for USD 10.25 returns USD 10.25 | 35 | 2.6-T01 | BE | NFR-10
2.6-T03 | shared-libs | 2.6 | 2. Architecture & Technical Foundation | Internationalization framework | 1 | Flyway V201__i18n_locale_config.sql: create locale_config and supported_currency tables in config-registry | The i18n framework needs two new PostgreSQL tables in the gmepay database owned by services/config-registry. locale_config stores supported UI locales; supported_currency stores per-currency operational config with scale (KRW=0, USD=2). Migrations live at services/config-registry/src/main/resources/db/migration/. NFR-10 §9.1 requires DECIMAL(20,8) storage for amounts; this migration captures the scale metadata used by the app layer. | • Create services/config-registry/src/main/resources/db/migration/V201__i18n_locale_config.sql. • Define locale_config: locale_code VARCHAR(10) PK, display_name_en VARCHAR(100) NOT NULL, display_name_ko VARCHAR(100) NOT NULL, is_default BOOLEAN NOT NULL DEFAULT FALSE, active BOOLEAN NOT NULL DEFAULT TRUE, created_at TIMESTAMPTZ NOT NULL DEFAULT NOW(), updated_at TIMESTAMPTZ NOT NULL DEFAULT NOW(). Add partial unique index: CREATE UNIQUE INDEX uq_locale_default ON locale_config(is_default) WHERE is_default = TRUE. • Define supported_currency: iso_code CHAR(3) PK, scale SMALLINT NOT NULL CHECK (scale >= 0 AND scale <= 8), display_symbol VARCHAR(10), active BOOLEAN NOT NULL DEFAULT TRUE. • Insert seed rows: locale_code=ko-KR (is_default=TRUE, display_name_en=Korean, display_name_ko=한국어), locale_code=en-US (is_default=FALSE, display_name_en=English, display_name_ko=영어). • Insert seed currency rows: KRW (scale=0), USD (scale=2), MNT (scale=2), THB (scale=2). | services/config-registry/src/main/resources/db/migration/V201__i18n_locale_config.sql | • Flyway migrate runs cleanly on Testcontainers PostgreSQL 16 with no prior schema • Inserting a second is_default=TRUE row into locale_config is rejected by the partial unique index • Inserting scale=-1 into supported_currency is rejected by the CHECK constraint • SELECT count(*) FROM supported_currency returns 4 after migration • SELECT locale_code FROM locale_config WHERE is_default=TRUE returns ko-KR | 30 |  | BE | NFR-10
2.6-T04 | shared-libs | 2.6 | 2. Architecture & Technical Foundation | Internationalization framework | 1 | Configure Spring MessageSource beans for ko/en message bundles in services/ops-bff | The Admin Portal (services/ops-bff, Spring Boot BFF) requires all operator-facing UI labels, error messages, and help text in Korean (primary, ko-KR) and English (en-US) per NFR-10 §9.2. Spring ReloadableResourceBundleMessageSource provides this. Bundle files live at classpath:i18n/messages_ko.properties and messages_en.properties. The BFF uses AcceptHeaderLocaleResolver with default ko-KR. Module: services/ops-bff. | • Create services/ops-bff/src/main/resources/i18n/messages_ko.properties with keys: common.save, common.cancel, error.insufficient_prefunding, error.scheme_unavailable, error.partner_b_quote_deviation, error.partner_b_quote_unavailable, payment.status.committed, payment.status.failed, rate.label.offer_rate, rate.label.cross_rate -- all with Korean values. • Create services/ops-bff/src/main/resources/i18n/messages_en.properties with the same 10 keys in English. • Create services/ops-bff/src/main/java/com/gme/pay/opsbff/config/I18nConfig.java as @Configuration defining a MessageSource @Bean (bean name messageSource) using ReloadableResourceBundleMessageSource, basenames=classpath:i18n/messages, defaultEncoding=UTF-8, defaultLocale=ko-KR. • Add AcceptHeaderLocaleResolver @Bean named localeResolver with supported locales [ko-KR, en-US] and default ko-KR. • Ensure the messageSource bean name does not conflict with Spring Boot autoconfiguration (declare @Primary or override explicitly). | services/ops-bff/src/main/resources/i18n/messages_ko.properties, messages_en.properties, services/ops-bff/src/main/java/com/gme/pay/opsbff/config/I18nConfig.java | • messageSource.getMessage(error.insufficient_prefunding, null, Locale.KOREAN) returns a non-empty Korean string • messageSource.getMessage(error.insufficient_prefunding, null, Locale.ENGLISH) returns a non-empty English string • Accept-Language: en-US resolves to Locale en-US via localeResolver • All 10 keys present in both .properties files • Spring Boot application context loads without NoSuchBeanDefinitionException or conflict | 40 |  | BE | NFR-10
2.6-T05 | shared-libs | 2.6 | 2. Architecture & Technical Foundation | Internationalization framework | 1 | Configure Spring MessageSource beans for ko/en message bundles in services/partner-bff | The Partner Portal (services/partner-bff) primary language is English; Korean is secondary per NFR-10 §9.2. Same AcceptHeaderLocaleResolver pattern as ops-bff but default locale is en-US. Bundle files: classpath:i18n/messages_en.properties (primary) and messages_ko.properties. Module: services/partner-bff. | • Create services/partner-bff/src/main/resources/i18n/messages_en.properties with keys: common.save, common.cancel, error.insufficient_prefunding, error.scheme_unavailable, error.partner_b_quote_deviation, error.partner_b_quote_unavailable, payment.status.committed, payment.status.failed, rate.label.offer_rate, prefunding.alert.low_balance -- all in English. • Create services/partner-bff/src/main/resources/i18n/messages_ko.properties with the same 10 keys in Korean. • Create services/partner-bff/src/main/java/com/gme/pay/partnerbff/config/I18nConfig.java as @Configuration with MessageSource @Bean (ReloadableResourceBundleMessageSource, classpath:i18n/messages, UTF-8, defaultLocale=en-US). • Add AcceptHeaderLocaleResolver @Bean with supported locales [en-US, ko-KR] and default en-US. • Verify messages_ko.properties is saved as UTF-8 (Korean characters must not be stored as escaped unicode unless the file encoding is explicitly UTF-8). | services/partner-bff/src/main/resources/i18n/messages_en.properties, messages_ko.properties, services/partner-bff/src/main/java/com/gme/pay/partnerbff/config/I18nConfig.java | • Default locale resolves to en-US when no Accept-Language header is present • Accept-Language: ko-KR resolves to Korean messages • All 10 keys resolve in both locales without NoSuchMessageException • messages_ko.properties Korean characters are valid UTF-8 (no garbled output) • messageSource bean name does not conflict with Spring Boot autoconfigured bean | 35 |  | BE | NFR-10
2.6-T06 | shared-libs | 2.6 | 2. Architecture & Technical Foundation | Internationalization framework | 1 | Add locale-aware TimestampFormatter utility to lib-money: UTC storage, KST display, ISO-8601 API format | Per NFR-10 §9.3: all internal timestamps are stored in UTC; Admin Portal displays in KST (UTC+9, Asia/Seoul, no DST); Partner Portal displays in the partner-configured timezone (default KST). API responses always use ISO-8601 UTC (e.g. 2026-06-05T14:00:00Z). This stateless utility class lives in lib-money and is used by both BFFs and by the rate engine for quote validUntil formatting. Module: lib-money. | • Create libs/lib-money/src/main/java/com/gme/pay/money/TimestampFormatter.java as a final utility class with only static methods. • Add constants: public static final ZoneId KST = ZoneId.of(Asia/Seoul); public static final ZoneId UTC = ZoneOffset.UTC. • Implement static String formatForDisplay(Instant ts, ZoneId zone): formats as yyyy-MM-dd HH:mm:ss z using DateTimeFormatter.ofPattern. • Implement static String toApiString(Instant ts): returns ISO-8601 UTC string using DateTimeFormatter.ISO_INSTANT (e.g. 2026-06-05T14:00:00Z). • Implement static Instant parseApi(String iso8601): returns Instant; throws DateTimeParseException on invalid input (do not catch). | libs/lib-money/src/main/java/com/gme/pay/money/TimestampFormatter.java | • formatForDisplay(Instant.parse(2026-06-05T05:00:00Z), KST) produces a string showing 2026-06-05 14:00:00 KST • toApiString output ends with Z (UTC indicator) • parseApi(toApiString(Instant.now())) round-trips to same Instant • formatForDisplay with ZoneOffset.UTC on the same Instant shows 05:00:00 UTC • parseApi(not-a-date) throws DateTimeParseException | 30 |  | BE | NFR-10
2.6-T07 | shared-libs | 2.6 | 2. Architecture & Technical Foundation | Internationalization framework | 1 | Add KstCronHelper to services/settlement: convert KST batch deadlines to UTC @Scheduled cron expressions | NFR-10 §2.3 specifies internal batch deadlines in KST: ZP0011 at 01:30 KST, ZP0061 at 04:30 KST, ZP0063 at 13:30 KST, ZP0065/66 at 21:30 KST. Spring @Scheduled(cron) runs in JVM timezone (UTC). KST = UTC+9, so these map to: 16:30 UTC, 19:30 UTC, 04:30 UTC (next day), 12:30 UTC. A KstCronHelper utility produces the correct cron strings and is used in BatchScheduler.java. Module: services/settlement. | • Create services/settlement/src/main/java/com/gme/pay/settlement/scheduler/KstCronHelper.java with static method kstToCronUtc(int kstHour, int kstMinute): subtract 9 hours (modulo 24) to get UTC hour; return cron string 0 {utcMinute} {utcHour} * * ?. • Add static final String constants: CRON_ZP0011 = kstToCronUtc(1,30), CRON_ZP0061 = kstToCronUtc(4,30), CRON_ZP0063 = kstToCronUtc(13,30), CRON_ZP0065 = kstToCronUtc(21,30). • Create services/settlement/src/main/java/com/gme/pay/settlement/scheduler/BatchScheduler.java as a @Component with four stub @Scheduled methods using those constants, each with a Javadoc comment stating the KST deadline and UTC equivalent. • Add @EnableScheduling on the services/settlement Spring Boot application class if not already present. • Add a unit test for kstToCronUtc covering all four deadlines plus a midnight-crossover case (kstToCronUtc(1,0) = 0 0 16 * * ?). | services/settlement/src/main/java/com/gme/pay/settlement/scheduler/KstCronHelper.java and BatchScheduler.java | • kstToCronUtc(1,30) returns 0 30 16 * * ? • kstToCronUtc(4,30) returns 0 30 19 * * ? • kstToCronUtc(13,30) returns 0 30 4 * * ? • kstToCronUtc(21,30) returns 0 30 12 * * ? • BatchScheduler compiles and Spring context loads with @Scheduled annotations active | 30 |  | BE | NFR-10
2.6-T08 | shared-libs | 2.6 | 2. Architecture & Technical Foundation | Internationalization framework | 1 | Flyway V202__partner_display_timezone.sql: add display_timezone column to partners table | Per NFR-10 §9.3, the Partner Portal displays timestamps in each partner-configured timezone (default KST, Asia/Seoul). The partners table in PostgreSQL (services/config-registry migrations) needs a display_timezone column. The partner-bff reads this value to set ZoneId for TimestampFormatter. Default is Asia/Seoul. Module: services/config-registry. | • Create services/config-registry/src/main/resources/db/migration/V202__partner_display_timezone.sql. • Add column: ALTER TABLE partners ADD COLUMN display_timezone VARCHAR(60) NOT NULL DEFAULT Asia/Seoul; • Add a regex CHECK constraint: CHECK (display_timezone ~ ^[A-Za-z][A-Za-z0-9/_+\-]+$) to reject obviously malformed IANA identifiers. • Add SQL comment: COMMENT ON COLUMN partners.display_timezone IS IANA timezone identifier for Partner Portal timestamp display. Default Asia/Seoul (KST, UTC+9, no DST) per NFR-10 s9.3. • Update PartnerEntity.java in services/config-registry/src/main/java/com/gme/pay/config/entity/PartnerEntity.java to add String displayTimezone field with @Column(name=display_timezone). | services/config-registry/src/main/resources/db/migration/V202__partner_display_timezone.sql and updated PartnerEntity.java | • V202 applies cleanly after V201 on Testcontainers Postgres 16 • Existing partner rows default to Asia/Seoul post-migration • PartnerEntity.getDisplayTimezone() returns Asia/Seoul for a seeded test partner • Inserting display_timezone=America/New_York persists and is readable • Inserting display_timezone with an empty string fails the CHECK constraint | 30 | 2.6-T03 | BE | NFR-10
2.6-T09 | shared-libs | 2.6 | 2. Architecture & Technical Foundation | Internationalization framework | 1 | Implement LocaleHeaderFilter GlobalFilter in Spring Cloud Gateway: propagate resolved locale as X-Locale header | GMEPay+ uses Spring Cloud Gateway (services/gateway) as the edge. The gateway must resolve Accept-Language to a supported locale and propagate it downstream as X-Locale so ops-bff and partner-bff do not re-parse it. Supported locales: ko-KR and en-US. Default for /admin routes: ko-KR. Default for /partner routes: en-US. Unsupported locales fall back to the route default. Module: services/gateway. | • Create services/gateway/src/main/java/com/gme/pay/gateway/filter/LocaleHeaderFilter.java implementing GlobalFilter, Ordered. • In filter(), parse Accept-Language header; resolve to ko-KR or en-US; for paths starting /admin default to ko-KR; for paths starting /partner default to en-US; for other paths default to en-US. • Mutate the request: exchange.getRequest().mutate().header(X-Locale, resolvedLocale).build(). • Register as a @Bean in services/gateway/src/main/java/com/gme/pay/gateway/config/GatewayFilterConfig.java at order Ordered.HIGHEST_PRECEDENCE + 10. • Write a unit test using MockServerWebExchange covering all Accept-Language and path permutations. | services/gateway/src/main/java/com/gme/pay/gateway/filter/LocaleHeaderFilter.java and GatewayFilterConfig.java | • Accept-Language: ko-KR on /admin path sets X-Locale: ko-KR • Accept-Language: en-US on /admin path sets X-Locale: en-US • No Accept-Language on /admin path defaults X-Locale: ko-KR • No Accept-Language on /partner path defaults X-Locale: en-US • Accept-Language: fr-FR (unsupported) on /partner path defaults X-Locale: en-US | 40 |  | BE | NFR-10
2.6-T10 | shared-libs | 2.6 | 2. Architecture & Technical Foundation | Internationalization framework | 1 | Implement LocalizedMessageService and ErrorCode enum in lib-errors: locale-aware error code resolution | Partner API error codes are machine-readable English identifiers (e.g. INSUFFICIENT_PREFUNDING, SCHEME_UNAVAILABLE, PARTNER_B_QUOTE_DEVIATION, PARTNER_B_QUOTE_UNAVAILABLE, RATE_QUOTE_EXPIRED). UI-facing layers (ops-bff, partner-bff) resolve these codes to human-readable locale strings via LocalizedMessageService in lib-errors. The service wraps Spring MessageSource and uses LocaleContextHolder for implicit locale. Module: lib-errors (libs/lib-errors). | • Create libs/lib-errors/src/main/java/com/gme/pay/errors/ErrorCode.java enum with values: INSUFFICIENT_PREFUNDING, SCHEME_UNAVAILABLE, PARTNER_B_QUOTE_DEVIATION, PARTNER_B_QUOTE_UNAVAILABLE, RATE_QUOTE_EXPIRED, INVALID_CURRENCY, POOL_IDENTITY_BREACH, RATE_LOCK_VIOLATION. • Create libs/lib-errors/src/main/java/com/gme/pay/errors/LocalizedMessageService.java as @Service with constructor injection of MessageSource. • Implement String resolve(String errorCode, Locale locale): looks up key error.{errorCode.toLowerCase()} from MessageSource; returns errorCode itself if key not found (graceful fallback, no exception). • Add overload String resolve(String errorCode) using LocaleContextHolder.getLocale() as locale. • Add Javadoc: Partner API responses always use ErrorCode.name() string (not localised message); localised messages are portal display only. | libs/lib-errors/src/main/java/com/gme/pay/errors/ErrorCode.java and LocalizedMessageService.java | • ErrorCode enum has exactly 8 values • resolve(INSUFFICIENT_PREFUNDING, Locale.KOREAN) returns non-empty Korean string when messages_ko.properties has key error.insufficient_prefunding • resolve(SCHEME_UNAVAILABLE, Locale.ENGLISH) returns non-empty English string • resolve(NONEXISTENT_CODE, Locale.ENGLISH) returns NONEXISTENT_CODE (no exception) • LocalizedMessageService is a @Service bean injectable in a Spring Boot test slice | 35 | 2.6-T04, 2.6-T05 | BE | NFR-10
2.6-T11 | shared-libs | 2.6 | 2. Architecture & Technical Foundation | Internationalization framework | 1 | Add CurrencyScaleValidator to lib-money: reject fractional KRW in rate engine output | NFR-10 §9.1 mandates KRW amounts are whole numbers (scale=0). The rate engine (services/rate-fx, RateEngine.java) computes amounts via the 5-step RECEIVE-mode formula using BigDecimal. A guard must fire after steps 1 and 4 on KRW outputs. CurrencyScaleValidator.assertScale(MoneyAmount) throws MoneyScaleException if the rounded amount still has fractional digits beyond CurrencyConfig.scale(). Module: lib-money (validator) + call sites in services/rate-fx. | • Create libs/lib-money/src/main/java/com/gme/pay/money/CurrencyScaleValidator.java with static void assertScale(MoneyAmount amount) that calls amount.round() and checks the result has no fractional part beyond CurrencyConfig.scale(); throws MoneyScaleException if violated. • Add libs/lib-errors/src/main/java/com/gme/pay/errors/MoneyScaleException.java extending RuntimeException; include the currency code and actual scale in the message. • In services/rate-fx/src/main/java/com/gme/pay/ratefx/RateEngine.java, call assertScale on target_payout (after step 1) and on send_amount (after step 4) when the respective currency scale=0. • Add unit test: RateEngine with KRW payout_ccy and fractional target_payout (e.g. 1000.50 KRW) throws MoneyScaleException. • Add unit test: RateEngine with USD payout_ccy and target_payout 10.25 USD passes assertScale without exception. | libs/lib-money/src/main/java/com/gme/pay/money/CurrencyScaleValidator.java, libs/lib-errors/.../MoneyScaleException.java, updated services/rate-fx/.../RateEngine.java | • assertScale(MoneyAmount(KRW, 1000.50)) throws MoneyScaleException • assertScale(MoneyAmount(KRW, 1001.00)) passes • assertScale(MoneyAmount(USD, 10.256)) passes (USD allows 2 decimals; 10.256 rounds to 10.26 which is valid) • MoneyScaleException message contains the currency code • RateEngine unit test confirms the guard fires at the correct formula step | 40 | 2.6-T01, 2.6-T02 | BE | NFR-10
2.6-T12 | shared-libs | 2.6 | 2. Architecture & Technical Foundation | Internationalization framework | 1 | Add CurrencyDisplayFormatter to lib-money: locale-aware monetary amount display with per-currency decimal places | ops-bff and partner-bff display monetary amounts to users. Per NFR-10 §9.1 and UX notes: amounts display the ISO code and respect per-currency decimal places (KRW 1,000 not KRW 1,000.00; USD 10.25 not USD 10.3). Thousands-separator is comma for both ko-KR and en-US. Module: lib-money. | • Create libs/lib-money/src/main/java/com/gme/pay/money/CurrencyDisplayFormatter.java as a final utility class with static methods only. • Implement static String format(MoneyAmount amount): look up CurrencyConfig.scale() for the currency; apply DecimalFormat with groupingSize=3, comma separator, and scale decimal places. • KRW example pattern: #,##0 with scale=0 produces 1,000,000 KRW. USD example pattern: #,##0.00 with scale=2 produces 10,234.56 USD. Output format: {FORMATTED_AMOUNT} {ISO_CODE}. • Add overload format(MoneyAmount amount, Locale locale) reserved for future use; in Phase 1 delegates to the single-arg overload. • Add Javadoc: rates use RateDisplayFormatter (separate class); this formatter is for monetary amounts only. | libs/lib-money/src/main/java/com/gme/pay/money/CurrencyDisplayFormatter.java | • format(MoneyAmount(KRW, 1000000)) returns 1,000,000 KRW • format(MoneyAmount(KRW, 1001).round()) returns 1,001 KRW (no decimal) • format(MoneyAmount(USD, 10234.56)) returns 10,234.56 USD • format(MoneyAmount(USD, 10.2).round()) returns 10.20 USD (padded to scale=2) • format(MoneyAmount(KRW, 0)) returns 0 KRW without exception | 30 | 2.6-T01, 2.6-T02 | BE | NFR-10
2.6-T13 | shared-libs | 2.6 | 2. Architecture & Technical Foundation | Internationalization framework | 1 | Add RateDisplayFormatter to lib-money: 6-significant-figure formatting for offer_rate and cross_rate | Per UX spec: rates are displayed to 6 significant figures. The rate engine produces offer_rate_coll = send_amount / (collection_usd - collection_margin_usd) and cross_rate = target_payout / send_amount as BigDecimal. RateDisplayFormatter formats these for portal display with thousands separators where integer part exceeds 999. Module: lib-money. | • Create libs/lib-money/src/main/java/com/gme/pay/money/RateDisplayFormatter.java as a final utility class with static methods. • Implement static String formatRate(BigDecimal rate): apply new BigDecimal(rate, new MathContext(6, RoundingMode.HALF_UP)) to get 6 sig figs; format with comma separator in integer part if > 999; preserve trailing zeros to show exactly 6 significant digits. • Add overload formatRate(BigDecimal rate, int sigFigs) for future flexibility; current calls use default of 6. • Ensure the input BigDecimal is not mutated; return a new String. • Handle negative rates (sign preserved in output; used for display only). | libs/lib-money/src/main/java/com/gme/pay/money/RateDisplayFormatter.java | • formatRate(new BigDecimal(1234.56789)) returns 1,234.57 • formatRate(new BigDecimal(0.001234567)) returns 0.00123457 • formatRate(new BigDecimal(1.0)) returns 1.00000 (6 sig figs with trailing zeros) • formatRate(new BigDecimal(-0.5)) returns -0.500000 (sign preserved) • Input BigDecimal object is not mutated by the method call | 30 | 2.6-T01 | BE | NFR-10
2.6-T14 | shared-libs | 2.6 | 2. Architecture & Technical Foundation | Internationalization framework | 1 | Add LocaleHeaderInterceptor to ops-bff: set LocaleContextHolder from X-Locale header per request | The Gateway sets X-Locale header (2.6-T09). ops-bff (Spring Boot) must read this header and set LocaleContextHolder so that @Service and @RestController callers using LocalizedMessageService get the correct locale automatically via the implicit overload. Default fallback: ko-KR (Admin Portal primary language per NFR-10 §9.2). Module: services/ops-bff. | • Create services/ops-bff/src/main/java/com/gme/pay/opsbff/interceptor/LocaleHeaderInterceptor.java implementing HandlerInterceptor. • In preHandle(): read header X-Locale; parse to Locale via Locale.forLanguageTag(); fall back to ko-KR if header absent or value does not match [ko-KR, en-US]; call LocaleContextHolder.setLocale(resolved). • In afterCompletion(): call LocaleContextHolder.resetLocaleContext() to prevent thread-local leak. • Register in services/ops-bff/src/main/java/com/gme/pay/opsbff/config/I18nWebConfig.java (WebMvcConfigurer) via addInterceptors(). • Write a @WebMvcTest that injects LocalizedMessageService and sends requests with X-Locale: en-US and X-Locale: ko-KR to a test endpoint; assert correct locale message in response. | services/ops-bff/src/main/java/com/gme/pay/opsbff/interceptor/LocaleHeaderInterceptor.java and I18nWebConfig.java | • X-Locale: ko-KR sets LocaleContextHolder to ko-KR during the request • X-Locale: en-US sets LocaleContextHolder to en-US • Absent X-Locale header falls back to ko-KR • afterCompletion resets locale context (no thread-local leak) • @WebMvcTest with X-Locale: en-US returns English message text from LocalizedMessageService | 40 | 2.6-T04, 2.6-T09, 2.6-T10 | BE | NFR-10
2.6-T15 | shared-libs | 2.6 | 2. Architecture & Technical Foundation | Internationalization framework | 1 | Add LocaleHeaderInterceptor to partner-bff: set LocaleContextHolder from X-Locale header per request | Same locale-propagation pattern as ops-bff (2.6-T14) but for services/partner-bff. Default fallback locale is en-US (Partner Portal primary language is English per NFR-10 §9.2). Module: services/partner-bff. | • Create services/partner-bff/src/main/java/com/gme/pay/partnerbff/interceptor/LocaleHeaderInterceptor.java implementing HandlerInterceptor. • In preHandle(): read X-Locale header; fall back to en-US if absent or unsupported; call LocaleContextHolder.setLocale(resolved). • In afterCompletion(): call LocaleContextHolder.resetLocaleContext(). • Register in services/partner-bff/src/main/java/com/gme/pay/partnerbff/config/I18nWebConfig.java via addInterceptors(). • Write @WebMvcTest asserting X-Locale: ko-KR returns Korean message and absent header returns English message. | services/partner-bff/src/main/java/com/gme/pay/partnerbff/interceptor/LocaleHeaderInterceptor.java and I18nWebConfig.java | • X-Locale: ko-KR resolves to Korean locale in LocaleContextHolder • Absent X-Locale defaults to en-US (not ko-KR) • afterCompletion resets locale context (no thread-local leak) • @WebMvcTest confirms English message when X-Locale: en-US • @WebMvcTest confirms Korean message when X-Locale: ko-KR | 35 | 2.6-T05, 2.6-T09, 2.6-T10 | BE | NFR-10
2.6-T16 | shared-libs | 2.6 | 2. Architecture & Technical Foundation | Internationalization framework | 1 | Expose GET /v1/config/locales and GET /v1/config/currencies in config-registry service | ops-bff and partner-bff enumerate supported locales and currencies for UI dropdowns. config-registry (services/config-registry) owns locale_config and supported_currency tables (V201). Expose two read-only @RestController endpoints returning active rows. DTOs defined in lib-api-contracts. These are internal BFF-to-service calls; no partner auth required. Module: services/config-registry. | • Add LocaleConfigDto(String localeCode, String displayNameEn, String displayNameKo, boolean isDefault) and SupportedCurrencyDto(String isoCode, int scale, String displaySymbol) records to libs/lib-api-contracts/src/main/java/com/gme/pay/api/dto/config/. • Create LocaleConfigRepository and SupportedCurrencyRepository extending JpaRepository in services/config-registry. • Create services/config-registry/src/main/java/com/gme/pay/config/controller/I18nConfigController.java annotated @RestController @RequestMapping(/v1/config). • Implement GET /locales: query WHERE active=TRUE ORDER BY is_default DESC, locale_code; return List<LocaleConfigDto>. • Implement GET /currencies: query WHERE active=TRUE ORDER BY iso_code; return List<SupportedCurrencyDto>. | libs/lib-api-contracts/.../dto/config/LocaleConfigDto.java, SupportedCurrencyDto.java; services/config-registry/.../I18nConfigController.java; LocaleConfigRepository.java; SupportedCurrencyRepository.java | • GET /v1/config/locales returns HTTP 200 with 2 items after V201 migration • ko-KR item has isDefault=true in JSON response • GET /v1/config/currencies returns HTTP 200 with 4 items • KRW item has scale=0 in JSON response • Testcontainers integration test: Postgres 16 container with Flyway migrations; endpoints return correct JSON | 45 | 2.6-T03, 2.6-T08 | BE | NFR-10
2.6-T17 | shared-libs | 2.6 | 2. Architecture & Technical Foundation | Internationalization framework | 1 | Cache /v1/config/locales and /v1/config/currencies in Redis 7 with 300-second TTL in config-registry | Locale and currency config is static in Phase 1. Reading PostgreSQL on every BFF request is wasteful. config-registry caches these responses in Redis 7 using Spring Cache @Cacheable with TTL=300s. Cache keys: i18n:locales and i18n:currencies. Redis is shared infra (docker-compose: redis:7). On cache miss or Redis unavailability, fall back to the database query. Module: services/config-registry. | • Add spring-boot-starter-data-redis and spring-boot-starter-cache to services/config-registry/build.gradle dependencies. • Create services/config-registry/src/main/java/com/gme/pay/config/config/CacheConfig.java: @EnableCaching @Configuration defining a RedisCacheManager @Bean with default TTL 300s and cache names [i18n:locales, i18n:currencies]. • Annotate the service methods (LocaleConfigService.findAllActive() and SupportedCurrencyService.findAllActive()) with @Cacheable(cacheNames=i18n:locales) and @Cacheable(cacheNames=i18n:currencies). • Add POST /v1/config/cache/evict endpoint (internal use) with @CacheEvict(allEntries=true, cacheNames={i18n:locales, i18n:currencies}) to allow Ops to bust cache after config change. • Configure RedisCacheManager with CacheErrorHandler that logs and falls back to DB on Redis failure; do not let a Redis outage block the endpoint. | services/config-registry/src/main/java/com/gme/pay/config/config/CacheConfig.java, updated service classes with @Cacheable, cache evict endpoint | • Second call to GET /v1/config/locales does not hit the JPA repository (verified via Mockito spy in Testcontainers test) • Redis key i18n:locales exists with TTL <= 300s after first call (checked via RedisTemplate in test) • POST /v1/config/cache/evict causes next GET to re-query the database • When Redis container is stopped during test, endpoint still returns HTTP 200 from DB fallback • Testcontainers test uses both Postgres 16 and Redis 7 containers | 45 | 2.6-T16 | BE | NFR-10
2.6-T18 | shared-libs | 2.6 | 2. Architecture & Technical Foundation | Internationalization framework | 1 | Add @ValidCurrency Bean Validation annotation to lib-money: validate ISO 4217 currency codes on DTO fields | Multiple API endpoints accept currency code strings from partners (RateQuoteRequest.collectionCurrency, payoutCurrency; PaymentRequest.settlementCurrency). These must be validated against active CurrencyRegistry entries at request time. A custom Jakarta Validation annotation @ValidCurrency in lib-money provides reusable field-level validation. CurrencyValidator is Spring-managed so it can inject CurrencyRegistry. Module: lib-money. | • Create libs/lib-money/src/main/java/com/gme/pay/money/validation/ValidCurrency.java as @Constraint(validatedBy=CurrencyValidator.class) annotation with message attribute defaulting to error.invalid_currency. • Create libs/lib-money/src/main/java/com/gme/pay/money/validation/CurrencyValidator.java as @Component implementing ConstraintValidator<ValidCurrency, String>; isValid() returns false for null; calls CurrencyRegistry.getCurrency(value) and returns true if found and active, false if UnknownCurrencyException. • Apply @ValidCurrency to collectionCurrency and payoutCurrency fields in libs/lib-api-contracts RateQuoteRequest and to settlementCurrency in PaymentRequest. • Write a JUnit 5 unit test using a Validator: @ValidCurrency on KRW passes; on ZZZ fails; on null fails. • Write a @WebMvcTest that POSTs a RateQuoteRequest with collectionCurrency=ZZZ; assert HTTP 400 response with error code INVALID_CURRENCY. | libs/lib-money/src/main/java/com/gme/pay/money/validation/ValidCurrency.java, CurrencyValidator.java, updated DTO fields in lib-api-contracts | • Validator.validate(RateQuoteRequest with collectionCurrency=KRW) returns empty violation set • Validator.validate(RateQuoteRequest with collectionCurrency=ZZZ) returns one violation with message error.invalid_currency • Validator.validate(RateQuoteRequest with collectionCurrency=null) returns a violation • @WebMvcTest POST with unknown currency returns HTTP 400 • CurrencyValidator injected as Spring bean; no NPE when Spring context initializes | 40 | 2.6-T01, 2.6-T10 | BE | NFR-10
2.6-T19 | shared-libs | 2.6 | 2. Architecture & Technical Foundation | Internationalization framework | 1 | Add Utf8ContentTypeFilter GlobalFilter to Spring Cloud Gateway: enforce charset=UTF-8 on JSON responses | Per NFR-10 §9.2, Korean regulatory fields use UTF-8. All API JSON responses from the gateway must include Content-Type: application/json; charset=UTF-8. This prevents client charset negotiation issues and is required for BOK reporting fields containing Korean characters. Module: services/gateway. | • Create services/gateway/src/main/java/com/gme/pay/gateway/filter/Utf8ContentTypeFilter.java implementing GlobalFilter, Ordered. • In filter(), apply to the response: if response Content-Type is application/json but lacks charset, set it to MediaType.APPLICATION_JSON with UTF-8 charset. • Use exchange.getResponse().getHeaders() to read and set Content-Type. • Set order to Ordered.LOWEST_PRECEDENCE - 10 (runs after routing, modifies response headers before flush). • Register as a @Bean in GatewayFilterConfig.java alongside LocaleHeaderFilter. | services/gateway/src/main/java/com/gme/pay/gateway/filter/Utf8ContentTypeFilter.java, updated GatewayFilterConfig.java | • Response with Content-Type: application/json is modified to application/json;charset=UTF-8 • Response already containing charset=UTF-8 is not double-modified • Response with Content-Type: text/plain is not modified by this filter • Filter order is lower than LocaleHeaderFilter order (runs later in the chain) • Unit test using MockServerWebExchange passes for all three cases above | 30 | 2.6-T09 | BE | NFR-10
2.6-T20 | shared-libs | 2.6 | 2. Architecture & Technical Foundation | Internationalization framework | 1 | Complete message bundle keys for all error codes and payment status labels in ops-bff and partner-bff | 2.6-T04 and 2.6-T05 created bundles with 10 seed keys. All ErrorCode enum values (2.6-T10: INSUFFICIENT_PREFUNDING, SCHEME_UNAVAILABLE, PARTNER_B_QUOTE_DEVIATION, PARTNER_B_QUOTE_UNAVAILABLE, RATE_QUOTE_EXPIRED, INVALID_CURRENCY, POOL_IDENTITY_BREACH, RATE_LOCK_VIOLATION) plus payment status labels (payment.status.pending, payment.status.committed, payment.status.failed, payment.status.uncertain, payment.status.reversed) must now be in all four properties files with meaningful translations. Module: services/ops-bff and services/partner-bff. | • Add all 8 error.* keys (one per ErrorCode) to services/ops-bff/src/main/resources/i18n/messages_ko.properties with Korean text. • Add the same 8 error.* keys to services/ops-bff/src/main/resources/i18n/messages_en.properties with English text. • Add all 5 payment.status.* keys to both ops-bff properties files. • Mirror all 13 new keys in both services/partner-bff/src/main/resources/i18n/messages_ko.properties and messages_en.properties. • Confirm no duplicate keys exist in any file and no Korean-text key in a _ko file is accidentally English. | Updated messages_ko.properties and messages_en.properties in services/ops-bff/src/main/resources/i18n/ and services/partner-bff/src/main/resources/i18n/ | • All 8 error.* keys present in all 4 properties files • All 5 payment.status.* keys present in all 4 properties files • messages_ko.properties files contain Korean characters for all added keys (no English placeholder) • No duplicate keys in any properties file • messageSource.getMessage on every added key in both locales returns a non-empty non-key string | 35 | 2.6-T04, 2.6-T05, 2.6-T10 | BE | NFR-10
2.6-T21 | shared-libs | 2.6 | 2. Architecture & Technical Foundation | Internationalization framework | 1 | Unit tests for CurrencyConfig, MoneyAmount, CurrencyScaleValidator, CurrencyDisplayFormatter, RateDisplayFormatter in lib-money | lib-money is a foundational shared module. JUnit 5 unit tests must cover the KRW zero-decimal invariant, USD 2-decimal rounding, BigDecimal pool-identity arithmetic, display formatting, and rate formatting. No Spring context needed. Target: >=80% line coverage for lib-money (NFR-10 §8.2, N-15). Module: lib-money test. | • Create CurrencyConfigTest.java: getCurrency(KRW).scale()==0, getCurrency(USD).scale()==2, getCurrency(ZZZ) throws UnknownCurrencyException. • Create MoneyAmountTest.java: round() for KRW 1000.5->1001, USD 10.256->10.26; add() does not auto-round; multiply(0)->zero; subtract preserves BigDecimal identity. • Create CurrencyScaleValidatorTest.java: assertScale(KRW, 1000.50) throws; assertScale(KRW, 1001.00) passes; assertScale(USD, 10.26) passes. • Create CurrencyDisplayFormatterTest.java: format(KRW 1000000)=1,000,000 KRW; format(USD 10.2)=10.20 USD; format(KRW 0)=0 KRW. • Create RateDisplayFormatterTest.java: formatRate(1234.56789)=1,234.57; formatRate(0.001234567)=0.00123457; formatRate(1.0)=1.00000. | libs/lib-money/src/test/java/com/gme/pay/money/ test classes: CurrencyConfigTest.java, MoneyAmountTest.java, CurrencyScaleValidatorTest.java, CurrencyDisplayFormatterTest.java, RateDisplayFormatterTest.java | • ./gradlew :lib-money:test passes with 0 failures • At least 20 test cases across 5 test classes • KRW zero-decimal invariant tested with at least 2 vectors (whole and fractional) • USD 2-decimal rounding tested with at least 2 vectors • All edge cases (zero amount, boundary scale) have explicit assertions | 50 | 2.6-T01, 2.6-T02, 2.6-T11, 2.6-T12, 2.6-T13 | BE | NFR-10
2.6-T22 | shared-libs | 2.6 | 2. Architecture & Technical Foundation | Internationalization framework | 1 | Unit tests for TimestampFormatter: UTC-to-KST conversion, ISO-8601 round-trip, and parseApi error case | TimestampFormatter (2.6-T06) is a pure utility class in lib-money. JUnit 5 tests must cover: UTC-to-KST offset (UTC+9, no DST), ISO-8601 API string format, parse-format round-trip, arbitrary timezone (e.g. UTC+5:30), and invalid input handling. Module: lib-money test. | • Create libs/lib-money/src/test/java/com/gme/pay/money/TimestampFormatterTest.java. • Test formatForDisplay(Instant.parse(2026-06-05T05:00:00Z), KST): assert result contains 14:00 and KST (UTC+9 applied correctly). • Test formatForDisplay(Instant.parse(2026-06-05T15:30:00Z), ZoneOffset.UTC): assert result contains 15:30 and UTC. • Test toApiString(Instant.now()) ends with Z. • Test parseApi(toApiString(Instant.parse(2026-01-01T00:00:00Z))) returns the original Instant. Test parseApi(invalid-string) throws DateTimeParseException. | libs/lib-money/src/test/java/com/gme/pay/money/TimestampFormatterTest.java | • 2026-06-05T05:00:00Z converted to KST shows 14:00 (UTC+9 offset correctly applied) • toApiString output ends with Z • Round-trip parse yields original Instant • Invalid date string throws DateTimeParseException (not NullPointerException or silent failure) • ./gradlew :lib-money:test passes including these new cases | 30 | 2.6-T06 | BE | NFR-10
2.6-T23 | shared-libs | 2.6 | 2. Architecture & Technical Foundation | Internationalization framework | 1 | Unit tests for LocaleHeaderFilter and Utf8ContentTypeFilter in services/gateway using MockServerWebExchange | LocaleHeaderFilter (2.6-T09) and Utf8ContentTypeFilter (2.6-T19) are Spring Cloud Gateway GlobalFilters. Tests use Spring WebFlux MockServerWebExchange. No Testcontainers needed. Cover all path and Accept-Language permutations plus the UTF-8 charset injection. Module: services/gateway test. | • Create services/gateway/src/test/java/com/gme/pay/gateway/filter/LocaleHeaderFilterTest.java using JUnit 5 and MockServerWebExchange. • Test /admin + Accept-Language: ko-KR -> X-Locale: ko-KR in mutated request. • Test /partner + no Accept-Language -> X-Locale: en-US. • Test /admin + Accept-Language: fr-FR -> X-Locale: ko-KR (unsupported fallback). • Create Utf8ContentTypeFilterTest.java: response with Content-Type: application/json -> modified to application/json;charset=UTF-8; response with Content-Type: text/plain -> unchanged. | services/gateway/src/test/java/com/gme/pay/gateway/filter/LocaleHeaderFilterTest.java and Utf8ContentTypeFilterTest.java | • All 3 LocaleHeaderFilter cases pass • Both Utf8ContentTypeFilter cases pass • No Testcontainers required (pure WebFlux mock) • ./gradlew :gateway:test passes with 0 failures • Test classes have no Spring application context dependency (unit-level) | 40 | 2.6-T09, 2.6-T19 | BE | NFR-10
2.6-T24 | shared-libs | 2.6 | 2. Architecture & Technical Foundation | Internationalization framework | 1 | Integration test for I18nConfigController in config-registry using Testcontainers Postgres 16 and Redis 7 | I18nConfigController (2.6-T16) and its Redis cache (2.6-T17) need integration testing against real Postgres 16 and Redis 7. Use @Testcontainers with both containers; apply Flyway migrations; call /v1/config/locales and /v1/config/currencies via MockMvc; verify cache behaviour using RedisTemplate. Module: services/config-registry test. | • Create services/config-registry/src/test/java/com/gme/pay/config/controller/I18nConfigControllerIntegrationTest.java annotated @SpringBootTest, @AutoConfigureMockMvc, @Testcontainers. • Declare static PostgreSQLContainer<?> postgres = new PostgreSQLContainer<>(postgres:16) and static GenericContainer<?> redis = new GenericContainer<>(redis:7).withExposedPorts(6379). • Set datasource and Redis properties in @DynamicPropertySource from the containers. • Test GET /v1/config/locales: HTTP 200, 2 items, ko-KR has isDefault=true. Test GET /v1/config/currencies: HTTP 200, 4 items, KRW.scale=0. • Test cache: call GET /v1/config/locales twice; inject LocaleConfigRepository spy; assert repository was invoked only once (cache hit on second call). | services/config-registry/src/test/java/com/gme/pay/config/controller/I18nConfigControllerIntegrationTest.java | • GET /v1/config/locales returns 200 with 2 items • ko-KR item has isDefault=true • GET /v1/config/currencies returns 200 with 4 items, KRW scale=0 • Repository invoked once across 2 endpoint calls (cache hit verified) • Test runs using real Flyway V201 migration applied by Spring Boot on startup | 45 | 2.6-T16, 2.6-T17 | BE | NFR-10
2.6-T25 | shared-libs | 2.6 | 2. Architecture & Technical Foundation | Internationalization framework | 1 | Integration test for LocaleHeaderInterceptor in ops-bff: end-to-end X-Locale to message resolution | LocaleHeaderInterceptor (2.6-T14) in ops-bff must be verified end-to-end: HTTP request with X-Locale header -> LocaleContextHolder set -> LocalizedMessageService returns correct locale message. Use @WebMvcTest with a minimal test controller. No Testcontainers required. Module: services/ops-bff test. | • Create services/ops-bff/src/test/java/com/gme/pay/opsbff/interceptor/LocaleInterceptorIntegrationTest.java with @WebMvcTest. • Add a test-scope @RestController (TestMessageController) in the test source tree with GET /test/message that calls LocalizedMessageService.resolve(INSUFFICIENT_PREFUNDING) and returns the result as plain text. • Test 1: GET /test/message with X-Locale: ko-KR -> assert response body is Korean text (not the error code string INSUFFICIENT_PREFUNDING). • Test 2: GET /test/message with X-Locale: en-US -> assert response body is English text. • Test 3: GET /test/message with no X-Locale -> assert response body is Korean text (default ko-KR). | services/ops-bff/src/test/java/com/gme/pay/opsbff/interceptor/LocaleInterceptorIntegrationTest.java | • X-Locale: ko-KR returns Korean text for INSUFFICIENT_PREFUNDING • X-Locale: en-US returns English text for INSUFFICIENT_PREFUNDING • No X-Locale falls back to ko-KR (Korean text returned) • Test uses @WebMvcTest (no DB or Testcontainers) • ./gradlew :ops-bff:test passes with 0 failures | 40 | 2.6-T14, 2.6-T20 | BE | NFR-10
2.6-T26 | shared-libs | 2.6 | 2. Architecture & Technical Foundation | Internationalization framework | 1 | Add i18n, currency handling, and timezone sections to ops-bff and partner-bff READMEs | Per NFR-10 §8.3, each service must have a README covering purpose, dependencies, local run, and environment variable reference. The i18n framework adds locale resolution, message bundle structure, and timezone configuration. This ticket adds or updates the README for ops-bff and partner-bff with these sections. Do not create a new standalone file; append to or create a minimal README if one does not exist. | • Locate or create services/ops-bff/README.md; add section I18n and Localisation documenting: supported locales (ko-KR default, en-US), X-Locale gateway header, message bundle paths (src/main/resources/i18n/messages_ko.properties, messages_en.properties), how to add a new message key, and note that internal timestamps are UTC stored and KST displayed. • Locate or create services/partner-bff/README.md; add section I18n and Localisation documenting: supported locales (en-US default, ko-KR optional), partner display_timezone column (default Asia/Seoul), X-Locale header, bundle file paths. • Add Currency Handling sub-section in both READMEs: ISO 4217 codes; KRW scale=0 (no fractional KRW output); use @ValidCurrency on DTO currency fields; DECIMAL(20,8) PostgreSQL storage. • Add Timezone sub-section in both READMEs: UTC storage everywhere; KST = Asia/Seoul (UTC+9, no DST); KST used for batch window deadlines (NFR-10 §2.3); partner timezone configurable via partners.display_timezone column. • Verify both README files are UTF-8 encoded and all section headings use Markdown ## or ### syntax. | services/ops-bff/README.md and services/partner-bff/README.md with I18n, Currency Handling, and Timezone sections | • ops-bff README documents default locale as ko-KR • partner-bff README documents default locale as en-US • Both READMEs mention the X-Locale gateway header • Both READMEs mention KRW scale=0 and the @ValidCurrency annotation • Both READMEs mention UTC storage and KST display with Asia/Seoul timezone identifier | 30 | 2.6-T14, 2.6-T15, 2.6-T18 | BE | NFR-10
3.1-T01 | shared-libs | 3.1 | 3. Data Layer & Persistence | Database design & ERD implementation | 1 | Create Flyway baseline migration V001 and Gradle module structure for db migrations | GMEPay+ uses a Gradle multi-module monorepo. All PostgreSQL 16 DDL is managed via Flyway migrations in a dedicated module. The Flyway naming convention is V{nnn}__{description}.sql. Migrations live in db-migrations/src/main/resources/db/migration/. A shared lib-persistence module provides common Flyway config beans. No floating-point types permitted; use NUMERIC/DECIMAL for money. All table and column names snake_case. BIGINT surrogate auto-increment PK on every table. TIMESTAMPTZ for all timestamps. Enums stored as VARCHAR with CHECK constraint (not DB enum type). ON DELETE RESTRICT default for all FKs. Every FK column must be indexed. | • Add db-migrations subproject to root settings.gradle with path :db-migrations • Create db-migrations/build.gradle with flyway-core 10.x and postgresql 42.x JDBC driver dependencies • Create directory db-migrations/src/main/resources/db/migration/ • Create V001__baseline_schema_conventions.sql with comment-only migration documenting naming, money type, and timestamp conventions as per DAT-03 sec 1.3 and sec 2 • Verify Flyway can connect to PostgreSQL 16 on localhost:5433 by running ./gradlew :db-migrations:flywayInfo | db-migrations/build.gradle, db-migrations/src/main/resources/db/migration/V001__baseline_schema_conventions.sql, entry in settings.gradle | • ./gradlew :db-migrations:flywayInfo reports current version without error on local Postgres 16 port 5433 • V001 migration file exists and contains only comments (no DDL); Flyway marks it as success • settings.gradle includes :db-migrations include statement • No FLOAT or DOUBLE type appears in any migration file (grep check) | 30 |  | DBA | DAT-03
3.1-T02 | shared-libs | 3.1 | 3. Data Layer & Persistence | Database design & ERD implementation | 1 | Create V002 migration: qr_scheme and scheme_country tables | qr_scheme represents a QR payment network (e.g. ZEROPAY operated by KFTC). scheme_country maps active schemes to ISO 3166-1 alpha-2 country codes for CPM scheme selection. qr_scheme columns per DAT-03 sec 4.1: BIGINT PK, scheme_code VARCHAR(30) UNIQUE, payout_ccy CHAR(3), supported_modes VARCHAR(20) CHECK IN ('MPM','CPM','BOTH'), fee columns DECIMAL(6,4), partner_b_quote_deviation_pct DECIMAL(6,4) DEFAULT 0.0100, gme_fee_share_pct DECIMAL(6,4), status VARCHAR(20) CHECK IN ('TESTING','ACTIVE','INACTIVE'), is_active BOOLEAN NOT NULL DEFAULT TRUE, sftp_host/sftp_path_outbound/sftp_path_inbound/api_endpoint/api_credential_ref, standard audit cols (created_at TIMESTAMPTZ NOT NULL DEFAULT NOW(), updated_at TIMESTAMPTZ NOT NULL, created_by VARCHAR(120), updated_by VARCHAR(120)). scheme_country: BIGINT PK, scheme_id BIGINT FK->qr_scheme ON DELETE RESTRICT, country_code CHAR(2), is_active BOOLEAN, audit cols; UNIQUE(scheme_id, country_code). Index every FK column. | • Create db-migrations/src/main/resources/db/migration/V002__qr_scheme_and_scheme_country.sql • Add CREATE TABLE qr_scheme with all columns per DAT-03 sec 4.1; include CHECK constraints for supported_modes and status • Add CREATE TABLE scheme_country with FK, UNIQUE(scheme_id, country_code), index on scheme_id • Run ./gradlew :db-migrations:flywayMigrate against local Postgres 16 to verify clean apply • Verify with psql: \d qr_scheme and \d scheme_country show correct column types | db-migrations/src/main/resources/db/migration/V002__qr_scheme_and_scheme_country.sql | • Migration applies cleanly with exit 0 on Postgres 16 • qr_scheme.supported_modes CHECK IN ('MPM','CPM','BOTH') rejects 'INVALID' insert • scheme_country UNIQUE(scheme_id, country_code) rejects duplicate insert • All FK columns have indexes (check pg_indexes) • No FLOAT/REAL/DOUBLE column types present | 35 | 3.1-T01 | DBA | DAT-03
3.1-T03 | shared-libs | 3.1 | 3. Data Layer & Persistence | Database design & ERD implementation | 1 | Create V003 migration: partner and partner_credential tables | partner stores payment app configurations. Columns per DAT-03 sec 4.3 and sec 10.8: BIGINT PK, partner_code VARCHAR(30) UNIQUE NOT NULL, name VARCHAR(100) NOT NULL, partner_type VARCHAR(10) NOT NULL CHECK IN ('LOCAL','OVERSEAS'), collection_ccy CHAR(3) NOT NULL, settle_a_ccy CHAR(3) NOT NULL, webhook_url VARCHAR(512) NOT NULL, rate_quote_ttl_seconds INT NOT NULL DEFAULT 300 CHECK BETWEEN 60 AND 1800, low_balance_threshold_usd DECIMAL(20,4) NULL (NULL for LOCAL partners), low_balance_alert_email VARCHAR(255) NULL, status VARCHAR(20) NOT NULL CHECK IN ('ONBOARDING','ACTIVE','SUSPENDED','INACTIVE'), is_active BOOLEAN NOT NULL DEFAULT FALSE, standard audit cols. partner_credential: BIGINT PK, partner_id BIGINT FK->partner ON DELETE RESTRICT, api_key VARCHAR(64) UNIQUE, api_secret_hash VARCHAR(128) (bcrypt hash), is_active BOOLEAN, expires_at TIMESTAMPTZ NULL, audit cols; only one active credential per partner enforced via partial unique index. | • Create V003__partner_and_partner_credential.sql • Add CREATE TABLE partner with all columns, CHECK constraints, and NOT NULL defaults per DAT-03 sec 10.8 • Add CREATE TABLE partner_credential with FK, api_key UNIQUE index, and partial unique index: CREATE UNIQUE INDEX uq_partner_credential_active ON partner_credential(partner_id) WHERE is_active = TRUE • Run migration against local Postgres 16 and verify with psql • Insert test row for LOCAL partner (GME_REMIT) and OVERSEAS partner (SENDMN) to confirm constraints | db-migrations/src/main/resources/db/migration/V003__partner_and_partner_credential.sql | • rate_quote_ttl_seconds CHECK BETWEEN 60 AND 1800 rejects value 30 • partner_type CHECK IN ('LOCAL','OVERSEAS') rejects 'AGENT' • Partial unique index prevents two active credentials for same partner_id • partner.is_active DEFAULT FALSE confirmed via \d+ partner • LOCAL partner with NULL low_balance_threshold_usd accepted without error | 35 | 3.1-T01 | DBA | DAT-03
3.1-T04 | shared-libs | 3.1 | 3. Data Layer & Persistence | Database design & ERD implementation | 1 | Create V004 migration: partner_webhook and treasury_rate tables | partner_webhook stores webhook endpoint config per partner (primary + fallback) per DAT-03 sec 4.5: BIGINT PK, partner_id FK->partner, webhook_url VARCHAR(512), event_types TEXT, signing_secret_hash VARCHAR(128) (HMAC-SHA256 signing secret hashed), is_active BOOLEAN, audit cols. treasury_rate stores canonical FX rates in form usd_{ccy} = units of ccy per 1 USD (e.g. usd_krw=1380.00000000 means 1 USD = 1380 KRW). Columns per DAT-03 sec 4.8 and sec 10.3: BIGINT PK, ccy_pair VARCHAR(10) NOT NULL, rate DECIMAL(20,8) NOT NULL CHECK (rate > 0), source VARCHAR(10) NOT NULL CHECK IN ('LIVE','MANUAL'), effective_at TIMESTAMPTZ NOT NULL, audit cols. Latest rate query: WHERE ccy_pair='usd_krw' ORDER BY effective_at DESC LIMIT 1. Historical rows retained for BOK audit. Composite index on (ccy_pair, effective_at DESC). | • Create V004__partner_webhook_and_treasury_rate.sql • Add CREATE TABLE partner_webhook with FK index on partner_id • Add CREATE TABLE treasury_rate with DECIMAL(20,8) rate column, CHECK (rate > 0), and composite index on (ccy_pair, effective_at DESC) • Run migration and verify with psql • Insert treasury_rate rows for usd_krw=1380.00000000 and usd_mnt=3440.00000000 as test data to confirm 8dp precision | db-migrations/src/main/resources/db/migration/V004__partner_webhook_and_treasury_rate.sql | • treasury_rate.rate CHECK > 0 rejects insert of rate=0.0 • DECIMAL(20,8) stores 1380.00000000 with 8 decimal places without truncation • Composite index on (ccy_pair, effective_at DESC) appears in pg_indexes • treasury_rate.source CHECK IN ('LIVE','MANUAL') rejects 'XE_FEED' • Multiple rows for same ccy_pair allowed (historical retention confirmed by successful dual insert) | 30 | 3.1-T03 | DBA | DAT-03
3.1-T05 | shared-libs | 3.1 | 3. Data Layer & Persistence | Database design & ERD implementation | 1 | Create V005 migration: rule and service_charge_tier tables | rule is the central config entity linking partner x scheme x direction with margin params. Columns per DAT-03 sec 4.6 and sec 10.2: BIGINT PK; partner_id FK->partner; scheme_id FK->qr_scheme; direction VARCHAR(10) NOT NULL CHECK IN ('INBOUND','OUTBOUND','DOMESTIC','HUB'); collection_ccy, settle_a_ccy, settle_b_ccy, payout_ccy CHAR(3) NOT NULL (auto-derived from partner/scheme, stored for query performance); rate_coll_source/rate_pay_source VARCHAR(10) CHECK IN ('IDENTITY','LIVE','MANUAL','PARTNER'); manual_rate_coll/manual_rate_pay DECIMAL(20,8) NULL; m_a DECIMAL(8,6) NOT NULL DEFAULT 0 CHECK >=0; m_b DECIMAL(8,6) NOT NULL DEFAULT 0 CHECK >=0; CHECK (is_same_ccy_shortcircuit = TRUE OR (m_a + m_b) >= 0.020000) for 2% minimum combined margin on cross-border; service_charge_amount DECIMAL(20,4) NOT NULL DEFAULT 0; service_charge_ccy CHAR(3) NOT NULL; is_same_ccy_shortcircuit BOOLEAN NOT NULL (computed: TRUE when collection=settle_a=settle_b=payout ccy); status VARCHAR(20) CHECK IN ('DRAFT','ACTIVE','SUSPENDED'); effective_from TIMESTAMPTZ NOT NULL; audit cols. UNIQUE(partner_id, scheme_id, direction). service_charge_tier: BIGINT PK, rule_id FK->rule, min_collection_usd DECIMAL(20,4), max_collection_usd DECIMAL(20,4) NULL (no cap), charge_amount DECIMAL(20,4), audit cols. | • Create V005__rule_and_service_charge_tier.sql • Add CREATE TABLE rule with all columns; add UNIQUE(partner_id, scheme_id, direction) and CHECK (is_same_ccy_shortcircuit OR (m_a + m_b) >= 0.020000) • Add FK indexes on partner_id, scheme_id; add index on status for active-rule lookups • Add CREATE TABLE service_charge_tier with FK->rule and index on rule_id • Run migration; verify CHECK constraint fires for cross-border rule with m_a=0.005, m_b=0.005 (sum=0.01 < 0.02) • Verify same-ccy rule with is_same_ccy_shortcircuit=TRUE and m_a=m_b=0 is accepted | db-migrations/src/main/resources/db/migration/V005__rule_and_service_charge_tier.sql | • UNIQUE(partner_id, scheme_id, direction) rejects duplicate insert • CHECK (m_a+m_b>=0.02) rejects cross-border rule insert with m_a=0.005, m_b=0.005 • Same-currency rule with is_same_ccy_shortcircuit=TRUE and m_a=m_b=0 is accepted • service_charge_tier.max_collection_usd accepts NULL (no cap) • rate_coll_source CHECK rejects 'REALTIME' | 40 | 3.1-T03, 3.1-T02 | DBA | DAT-03
3.1-T06 | shared-libs | 3.1 | 3. Data Layer & Persistence | Database design & ERD implementation | 1 | Create V006 migration: rate_quote table | rate_quote captures the output of the rate engine at GET /v1/rates or CPM pending_debit. All USD pool values and derived rates stored per DAT-03 sec 5.1. Key columns: quote_ref VARCHAR(64) UNIQUE; rule_id FK->rule; partner_id FK->partner; scheme_id FK->qr_scheme; payment_mode VARCHAR(5) CHECK IN ('MPM','CPM'); target_payout DECIMAL(20,4) NOT NULL; payout_ccy CHAR(3); USD pool fields (payout_usd_cost, collection_usd, collection_margin_usd, payout_margin_usd) DECIMAL(20,8) NULL (NULL for same-ccy short-circuit); send_amount DECIMAL(20,4) NOT NULL; send_amount_ccy CHAR(3); service_charge DECIMAL(20,4) NOT NULL; collection_amount DECIMAL(20,4) NOT NULL (= send_amount + service_charge); collection_ccy CHAR(3); offer_rate_coll DECIMAL(20,8) NULL (derived: send_amount / (collection_usd - collection_margin_usd); NULL same-ccy); cross_rate DECIMAL(20,8) NULL (derived: target_payout / send_amount); cost_rate_coll/cost_rate_pay DECIMAL(20,8) NULL; treasury_rate_id_coll/treasury_rate_id_pay BIGINT FK->treasury_rate NULL; quote_issued_at TIMESTAMPTZ NOT NULL; valid_until TIMESTAMPTZ NOT NULL (= quote_issued_at + rate_quote_ttl_seconds); is_used BOOLEAN NOT NULL DEFAULT FALSE; created_at/updated_at. | • Create V006__rate_quote.sql • Add CREATE TABLE rate_quote with all columns and types exactly per DAT-03 sec 5.1 • Add CHECK: payment_mode IN ('MPM','CPM') • Add indexes: (partner_id, quote_issued_at), (rule_id, is_used), (valid_until) for TTL expiry queries • Add FK indexes on rule_id, partner_id, scheme_id, treasury_rate_id_coll, treasury_rate_id_pay • Run migration and verify column nullability with psql \d rate_quote | db-migrations/src/main/resources/db/migration/V006__rate_quote.sql | • payout_usd_cost, collection_usd, collection_margin_usd, payout_margin_usd columns are nullable (confirmed \d rate_quote) • offer_rate_coll and cross_rate are nullable • quote_ref UNIQUE constraint rejects duplicate quote_ref insert • payment_mode CHECK IN ('MPM','CPM') rejects 'QR' • valid_until and quote_issued_at columns are TIMESTAMPTZ NOT NULL | 35 | 3.1-T05, 3.1-T04 | DBA | DAT-03
3.1-T07 | shared-libs | 3.1 | 3. Data Layer & Persistence | Database design & ERD implementation | 1 | Create V007 migration: transaction table (central fact table) | transaction is the central fact table. All rate fields are copied from rate_quote at commit and are immutable thereafter. Columns per DAT-03 sec 5.2 and sec 10.1: txn_ref VARCHAR(64) UNIQUE NOT NULL; hub_txn_ref VARCHAR(64) NOT NULL; scheme_ref VARCHAR(128) NULL (populated after scheme approval); partner_id/scheme_id/rule_id/rate_quote_id/merchant_id/qr_code_id BIGINT FK NOT NULL; payment_mode CHECK IN ('MPM','CPM'); direction CHECK IN ('INBOUND','OUTBOUND','DOMESTIC','HUB'); status VARCHAR(20) NOT NULL CHECK IN ('INITIATED','PREFUND_DEDUCTED','SUBMITTED','APPROVED','DECLINED','UNCERTAIN','FAILED','CANCELLED','REFUNDED'); target_payout DECIMAL(20,4) NOT NULL; payout_ccy/collection_ccy/settle_a_ccy/settle_b_ccy CHAR(3) NOT NULL; USD pool fields DECIMAL(20,8) NULL; send_amount/service_charge/collection_amount DECIMAL(20,4) NOT NULL; offer_rate_coll/cross_rate/cost_rate_coll/cost_rate_pay DECIMAL(20,8) NULL; committed_at/completed_at TIMESTAMPTZ NULL; is_same_ccy_shortcircuit BOOLEAN NOT NULL DEFAULT FALSE; prefunding_deducted_usd DECIMAL(20,4) NULL (OVERSEAS only); standard audit cols. Composite indexes: (partner_id, committed_at), (scheme_id, completed_at), (status, committed_at), index on scheme_ref, index on hub_txn_ref. | • Create V007__transaction.sql • Add CREATE TABLE transaction with all columns and nullability per DAT-03 sec 10.1 • Add CHECK constraints for payment_mode, direction, and all 9 status values • Add composite indexes: (partner_id, committed_at), (scheme_id, completed_at), (status, committed_at), (scheme_ref), (hub_txn_ref) • Add all FK indexes (partner_id, scheme_id, rule_id, rate_quote_id, merchant_id, qr_code_id) • Run migration; verify 9 status values accepted and 'PENDING' rejected | db-migrations/src/main/resources/db/migration/V007__transaction.sql | • txn_ref UNIQUE constraint confirmed • status CHECK accepts all 9 values: INITIATED/PREFUND_DEDUCTED/SUBMITTED/APPROVED/DECLINED/UNCERTAIN/FAILED/CANCELLED/REFUNDED and rejects 'PENDING' • collection_usd NULL accepted for is_same_ccy_shortcircuit=TRUE insert • Composite index (partner_id, committed_at) appears in pg_indexes • prefunding_deducted_usd is nullable (LOCAL=NULL, OVERSEAS=populated) | 45 | 3.1-T06 | DBA | DAT-03
3.1-T08 | shared-libs | 3.1 | 3. Data Layer & Persistence | Database design & ERD implementation | 1 | Create V008 migration: transaction_event and refund tables | transaction_event stores the 8-step event trail per transaction per DAT-03 sec 5.3. 8 steps per DAT-03 Assumption A3: (1) RATE_QUOTE_ISSUED, (2) PREFUND_DEDUCTED, (3) SCHEME_SUBMITTED, (4) SCHEME_APPROVED or SCHEME_DECLINED, (5) TRANSACTION_COMMITTED, (6) SETTLEMENT_BATCHED, (7) WEBHOOK_QUEUED, (8) WEBHOOK_DELIVERED. Columns: id BIGINT PK, txn_id BIGINT FK->transaction NOT NULL, step INT NOT NULL CHECK BETWEEN 1 AND 8, event_type VARCHAR(50) NOT NULL, occurred_at TIMESTAMPTZ NOT NULL, duration_ms INT NULL (milliseconds since previous step), detail JSONB NULL (step-specific payload), created_at TIMESTAMPTZ NOT NULL DEFAULT NOW(). refund per DAT-03 sec 5.4: id BIGINT PK, txn_id FK->transaction, refund_ref VARCHAR(64) UNIQUE, refund_amount DECIMAL(20,4) NOT NULL (in payout_ccy of original txn), refund_ccy CHAR(3) NOT NULL, reason VARCHAR(255) NULL, status VARCHAR(20) CHECK IN ('PENDING','SUBMITTED','CONFIRMED','FAILED'), scheme_refund_ref VARCHAR(128) NULL, initiated_by VARCHAR(120), audit cols. Phase 1: refunds via Admin System only. | • Create V008__transaction_event_and_refund.sql • Add CREATE TABLE transaction_event with step CHECK BETWEEN 1 AND 8, JSONB detail column, composite index on (txn_id, step) • Add CREATE TABLE refund with all columns, refund_ref UNIQUE, status CHECK constraint, index on txn_id • Run migration and verify JSONB detail column accepts JSON payload • Verify step constraint rejects step=9 and step=0 | db-migrations/src/main/resources/db/migration/V008__transaction_event_and_refund.sql | • transaction_event.step CHECK BETWEEN 1 AND 8 rejects step=9 and step=0 • detail JSONB column accepts JSON object payload • refund.status CHECK IN ('PENDING','SUBMITTED','CONFIRMED','FAILED') rejects 'PROCESSING' • refund_ref UNIQUE constraint confirmed • Composite index on (txn_id, step) appears in pg_indexes | 30 | 3.1-T07 | DBA | DAT-03
3.1-T09 | shared-libs | 3.1 | 3. Data Layer & Persistence | Database design & ERD implementation | 1 | Create V009 migration: prefunding_account and prefunding_ledger_entry tables | prefunding_account: one row per OVERSEAS partner; balance maintained in USD; updated atomically via SELECT FOR UPDATE (no application-level locking). Columns per DAT-03 sec 6.1: id BIGINT PK, partner_id BIGINT FK->partner UNIQUE NOT NULL (one account per partner), currency CHAR(3) NOT NULL DEFAULT 'USD', balance DECIMAL(20,4) NOT NULL DEFAULT 0.0000, low_balance_threshold DECIMAL(20,4) NOT NULL DEFAULT 10000.0000, audit cols. prefunding_ledger_entry is append-only immutable per DAT-03 sec 6.2 and sec 10.4: id BIGINT PK, account_id BIGINT FK->prefunding_account NOT NULL, txn_ref VARCHAR(64) NULL (NULL for top-ups), entry_type VARCHAR(20) NOT NULL CHECK IN ('DEBIT_PAYMENT','DEBIT_REVERSAL','CREDIT_TOPUP','CREDIT_REVERSAL'), amount DECIMAL(20,4) NOT NULL CHECK (amount > 0), balance_after DECIMAL(20,4) NOT NULL, note VARCHAR(255) NULL, created_at TIMESTAMPTZ NOT NULL DEFAULT NOW() (NO updated_at; append-only), created_by VARCHAR(120) NULL. Composite index (account_id, created_at) for balance history queries. Scheme is never called without prior committed deduction. | • Create V009__prefunding_account_and_ledger.sql • Add CREATE TABLE prefunding_account with UNIQUE on partner_id and DECIMAL(20,4) balance • Add CREATE TABLE prefunding_ledger_entry with NO updated_at column; add entry_type CHECK; add CHECK (amount > 0) • Add composite index (account_id, created_at) on ledger table • Run migration; verify ledger amount=0 insert is rejected | db-migrations/src/main/resources/db/migration/V009__prefunding_account_and_ledger.sql | • prefunding_account.partner_id UNIQUE rejects second account for same partner • prefunding_ledger_entry.amount CHECK > 0 rejects amount=0 insert • prefunding_ledger_entry has no updated_at column (confirmed \d+ prefunding_ledger_entry) • entry_type CHECK rejects 'DEBIT_FEE' • Composite index (account_id, created_at) present in pg_indexes | 30 | 3.1-T03 | DBA | DAT-03
3.1-T10 | shared-libs | 3.1 | 3. Data Layer & Persistence | Database design & ERD implementation | 1 | Create V010 migration: low_balance_alert_config table | low_balance_alert_config stores per-partner configurable low-balance alert thresholds per DAT-03 sec 6.3. One row per OVERSEAS partner (UNIQUE on partner_id). Columns: id BIGINT PK, partner_id BIGINT FK->partner UNIQUE NOT NULL, threshold_usd DECIMAL(20,4) NOT NULL DEFAULT 10000.0000, alert_email VARCHAR(255) NOT NULL, is_active BOOLEAN NOT NULL DEFAULT TRUE, standard audit cols. Used by Notification and Webhook service when prefunding_account.balance drops below threshold after a DEBIT_PAYMENT ledger entry. This is OVERSEAS-partner-only; LOCAL partners (GME Remit, all KRW) have no prefunding requirement. | • Create V010__low_balance_alert_config.sql • Add CREATE TABLE low_balance_alert_config with UNIQUE constraint on partner_id • Add DEFAULT threshold_usd = 10000.0000 and is_active DEFAULT TRUE • Add FK index on partner_id • Run migration; attempt duplicate insert for same partner_id to confirm UNIQUE rejection • Confirm FK to partner.id is enforced with a non-existent partner_id insert attempt | db-migrations/src/main/resources/db/migration/V010__low_balance_alert_config.sql | • UNIQUE(partner_id) rejects second row for same partner • threshold_usd DEFAULT is 10000.0000 (confirmed by INSERT without explicit threshold) • is_active DEFAULT TRUE confirmed • FK to partner.id enforced (insert with non-existent partner_id rejected) • Migration applies cleanly in sequence after V009 | 20 | 3.1-T03 | DBA | DAT-03
3.1-T11 | shared-libs | 3.1 | 3. Data Layer & Persistence | Database design & ERD implementation | 1 | Create V011 migration: settlement_batch and settlement_file tables | settlement_batch: one row per daily batch run for a given scheme and file type per DAT-03 sec 7.1 and sec 10.5. Columns: id BIGINT PK, scheme_id BIGINT FK->qr_scheme, file_type VARCHAR(10) NOT NULL (e.g. ZP0011, ZP0061 for ZeroPay), direction VARCHAR(20) NOT NULL CHECK IN ('GME_TO_ZP','ZP_TO_GME'), settlement_date DATE NOT NULL (KST business date), window VARCHAR(20) NOT NULL CHECK IN ('MORNING','AFTERNOON','DETAIL','NIGHTLY'), status VARCHAR(20) NOT NULL CHECK IN ('PENDING','GENERATED','TRANSMITTED','RECEIVED','RECONCILED','ERROR'), transaction_count INT NOT NULL DEFAULT 0, total_amount DECIMAL(20,4) NOT NULL DEFAULT 0, total_amount_ccy CHAR(3) NOT NULL, file_checksum VARCHAR(64) NULL (SHA-256), transmitted_at/received_at/reconciled_at TIMESTAMPTZ NULL, error_detail TEXT NULL, audit cols. UNIQUE(scheme_id, file_type, settlement_date, window). settlement_file: BIGINT PK, batch_id FK->settlement_batch, filename VARCHAR(255), sftp_path VARCHAR(512), file_size_bytes BIGINT, file_checksum VARCHAR(64), direction VARCHAR(20) CHECK IN ('OUTBOUND','INBOUND'), transmitted_at TIMESTAMPTZ NULL, created_at/updated_at. | • Create V011__settlement_batch_and_file.sql • Add CREATE TABLE settlement_batch with all CHECK constraints and UNIQUE(scheme_id, file_type, settlement_date, window) • Add CREATE TABLE settlement_file with FK->settlement_batch and direction CHECK IN ('OUTBOUND','INBOUND') • Add index on (settlement_batch.scheme_id, settlement_date) for daily lookups • Run migration; verify UNIQUE constraint rejects duplicate batch entry | db-migrations/src/main/resources/db/migration/V011__settlement_batch_and_file.sql | • UNIQUE(scheme_id, file_type, settlement_date, window) rejects duplicate batch • status CHECK accepts 'RECONCILED' and rejects 'COMPLETE' • window CHECK IN ('MORNING','AFTERNOON','DETAIL','NIGHTLY') rejects 'EVENING' • settlement_file.direction CHECK IN ('OUTBOUND','INBOUND') rejects 'BOTH' • total_amount DEFAULT 0 and transaction_count DEFAULT 0 confirmed | 35 | 3.1-T02 | DBA | DAT-03
3.1-T12 | shared-libs | 3.1 | 3. Data Layer & Persistence | Database design & ERD implementation | 1 | Create V012 migration: reconciliation_item table | reconciliation_item: one row per transaction line in a reconciliation comparison per DAT-03 sec 7.3. Auto-generated when ZP006x result files are received and compared against GME internal aggregation. Columns: id BIGINT PK, batch_id BIGINT FK->settlement_batch NOT NULL, txn_ref VARCHAR(64) NULL (NULL for MISSING_GME scenario where scheme has txn but GME does not), scheme_ref VARCHAR(128) NULL, match_status VARCHAR(20) NOT NULL CHECK IN ('MATCHED','DISCREPANCY','MISSING_GME','MISSING_SCHEME'), gme_amount DECIMAL(20,4) NULL, scheme_amount DECIMAL(20,4) NULL, discrepancy_amount DECIMAL(20,4) NULL, ccy CHAR(3) NOT NULL, resolution_status VARCHAR(20) NOT NULL DEFAULT 'UNRESOLVED' CHECK IN ('UNRESOLVED','RESOLVED','ESCALATED'), resolved_by VARCHAR(120) NULL, resolved_at TIMESTAMPTZ NULL, resolution_note TEXT NULL, audit cols. Index on (batch_id, match_status) for discrepancy queries. | • Create V012__reconciliation_item.sql • Add CREATE TABLE reconciliation_item with CHECK constraints for match_status and resolution_status • Add DEFAULT 'UNRESOLVED' for resolution_status • Add composite index (batch_id, match_status) • Run migration; confirm txn_ref NULL accepted (MISSING_GME scenario) • Confirm match_status CHECK rejects 'PARTIAL_MATCH' | db-migrations/src/main/resources/db/migration/V012__reconciliation_item.sql | • txn_ref NULL accepted (MISSING_GME scenario insert succeeds) • match_status CHECK rejects 'PARTIAL_MATCH' • resolution_status DEFAULT 'UNRESOLVED' confirmed by INSERT without resolution_status • Composite index (batch_id, match_status) present in pg_indexes • FK to settlement_batch enforced (non-existent batch_id rejected) | 25 | 3.1-T11 | DBA | DAT-03
3.1-T13 | shared-libs | 3.1 | 3. Data Layer & Persistence | Database design & ERD implementation | 1 | Create V013 migration: merchant and qr_code tables | merchant is a local cache of ZeroPay merchant records per DAT-03 sec 7.4 and sec 10.6. Updated by daily ZP0041/ZP0045/ZP0047/ZP0051/ZP0055 sync. Columns: id BIGINT PK, merchant_id VARCHAR(50) UNIQUE NOT NULL (ZeroPay merchant ID), merchant_type VARCHAR(30) NOT NULL (e.g. GENERAL, FRANCHISE), name VARCHAR(200) NOT NULL, business_registration_no VARCHAR(30) NULL (Korean BRN), franchise_code VARCHAR(30) NULL, category_code VARCHAR(20) NULL, bank_code VARCHAR(10) NULL (ZeroPay settlement bank), account_no VARCHAR(30) NULL (AES-256 encrypted at rest by application layer), fee_tier VARCHAR(20) NOT NULL CHECK IN ('DOMESTIC','CROSSBORDER'), status VARCHAR(20) NOT NULL CHECK IN ('ACTIVE','SUSPENDED','DEACTIVATED'), is_active BOOLEAN NOT NULL DEFAULT TRUE, synced_at TIMESTAMPTZ NOT NULL, created_at/updated_at. qr_code per DAT-03 sec 7.5: id BIGINT PK, merchant_id BIGINT FK->merchant NOT NULL, qr_code_value VARCHAR(512) UNIQUE NOT NULL (raw QR payload), qr_code_type VARCHAR(10) NOT NULL CHECK IN ('STATIC_MPM','DYNAMIC_CPM'), status VARCHAR(20) NOT NULL CHECK IN ('ACTIVE','DEACTIVATED'), is_active BOOLEAN NOT NULL DEFAULT TRUE, synced_at TIMESTAMPTZ NOT NULL, created_at/updated_at. | • Create V013__merchant_and_qr_code.sql • Add CREATE TABLE merchant with all columns and CHECK constraints per DAT-03 sec 10.6; add COMMENT ON COLUMN merchant.account_no noting AES-256 app-level encryption • Add CREATE TABLE qr_code with FK->merchant, UNIQUE on qr_code_value, and CHECK constraints • Add index on merchant.status; index on qr_code.merchant_id • Run migration; verify UNIQUE on qr_code_value rejects duplicate | db-migrations/src/main/resources/db/migration/V013__merchant_and_qr_code.sql | • merchant.fee_tier CHECK IN ('DOMESTIC','CROSSBORDER') rejects 'HYBRID' • qr_code_value UNIQUE rejects duplicate QR payload insert • qr_code.qr_code_type CHECK IN ('STATIC_MPM','DYNAMIC_CPM') rejects 'DYNAMIC_MPM' • merchant.status CHECK IN ('ACTIVE','SUSPENDED','DEACTIVATED') rejects 'BLOCKED' • merchant.is_active DEFAULT TRUE confirmed | 35 | 3.1-T01 | DBA | DAT-03
3.1-T14 | shared-libs | 3.1 | 3. Data Layer & Persistence | Database design & ERD implementation | 1 | Create V014 migration: merchant_sync_log table | merchant_sync_log records each ZeroPay merchant/QR sync batch run per DAT-03 sec 7.6. Columns: id BIGINT PK, file_type VARCHAR(10) NOT NULL (e.g. ZP0041), sync_date DATE NOT NULL, records_received INT NOT NULL DEFAULT 0, records_inserted INT NOT NULL DEFAULT 0, records_updated INT NOT NULL DEFAULT 0, records_deactivated INT NOT NULL DEFAULT 0, error_count INT NOT NULL DEFAULT 0, status VARCHAR(20) NOT NULL CHECK IN ('SUCCESS','PARTIAL','FAILED'), detail TEXT NULL, created_at TIMESTAMPTZ NOT NULL DEFAULT NOW(). No updated_at (append-only log). Composite index (file_type, sync_date) for last-sync queries. This table is consumed by the Scheme Adapter Layer ZeroPay adapter in module services/scheme-adapter/. | • Create V014__merchant_sync_log.sql • Add CREATE TABLE merchant_sync_log with all INT DEFAULT 0 columns • Add status CHECK IN ('SUCCESS','PARTIAL','FAILED') • Add composite index (file_type, sync_date) • Run migration; insert a PARTIAL sync record and verify • Confirm no updated_at column exists (\d merchant_sync_log) | db-migrations/src/main/resources/db/migration/V014__merchant_sync_log.sql | • status CHECK IN ('SUCCESS','PARTIAL','FAILED') rejects 'ERROR' • All count columns (records_received/inserted/updated/deactivated/error_count) DEFAULT 0 confirmed • No updated_at column present (append-only log; \d check) • Composite index (file_type, sync_date) in pg_indexes • detail NULL accepted | 20 | 3.1-T01 | DBA | DAT-03
3.1-T15 | shared-libs | 3.1 | 3. Data Layer & Persistence | Database design & ERD implementation | 1 | Create V015 migration: bok_report_record and revenue_record tables | bok_report_record: one row per cross-border transaction requiring BOK FX reporting per DAT-03 sec 8.1. Domestic/same-currency transactions are exempt. FX1014 = collection side (customer paying overseas); FX1015 = payout side (payment to Korean merchant). Columns: id BIGINT PK, txn_id BIGINT FK->transaction NOT NULL, report_type VARCHAR(10) NOT NULL CHECK IN ('FX1014','FX1015'), report_date DATE NOT NULL, partner_id BIGINT FK->partner NOT NULL, collection_amount DECIMAL(20,4) NULL, collection_ccy CHAR(3) NULL, payout_amount DECIMAL(20,4) NULL, payout_ccy CHAR(3) NULL, offer_rate_coll DECIMAL(20,8) NULL (BOK FX1015 field #14: send_amount / (collection_usd - collection_margin_usd)), usd_amount DECIMAL(20,4) NULL, submission_status VARCHAR(20) NOT NULL CHECK IN ('PENDING','SUBMITTED','CONFIRMED','FAILED'), submitted_at TIMESTAMPTZ NULL, created_at/updated_at. revenue_record per DAT-03 sec 8.2: id BIGINT PK, txn_id FK->transaction, partner_id FK->partner, scheme_id FK->qr_scheme, revenue_date DATE NOT NULL, fx_margin_usd DECIMAL(20,4) (= collection_margin_usd + payout_margin_usd), service_charge_amount DECIMAL(20,4), service_charge_ccy CHAR(3), fee_share_pct DECIMAL(6,4) (0.7000 for ZeroPay), estimated_fee_share_usd DECIMAL(20,4), created_at/updated_at. Index on (partner_id, revenue_date). | • Create V015__bok_report_record_and_revenue_record.sql • Add CREATE TABLE bok_report_record with FKs to transaction and partner; add report_type and submission_status CHECK constraints • Add CREATE TABLE revenue_record with FKs; add index on (partner_id, revenue_date) • Add index on (bok_report_record.txn_id) and (submission_status) for pending-report queries • Run migration; verify offer_rate_coll NULL accepted (same-ccy exemption) | db-migrations/src/main/resources/db/migration/V015__bok_report_record_and_revenue_record.sql | • bok_report_record.report_type CHECK IN ('FX1014','FX1015') rejects 'FX1016' • submission_status CHECK IN ('PENDING','SUBMITTED','CONFIRMED','FAILED') accepted for all 4 values • offer_rate_coll DECIMAL(20,8) accepts NULL for same-ccy rows • revenue_record.fee_share_pct DECIMAL(6,4) stores 0.7000 without truncation • Index on (partner_id, revenue_date) present in pg_indexes | 35 | 3.1-T07 | DBA | DAT-03
3.1-T16 | shared-libs | 3.1 | 3. Data Layer & Persistence | Database design & ERD implementation | 1 | Create V016 migration: tax_invoice table | tax_invoice: monthly merchant fee tax invoice for cross-border transactions per DAT-03 sec 8.3 (UC-04-04). All KRW amounts stored as BIGINT (integer; KRW has no minor-unit subdivision in payment practice per DAT-03 sec 2.1). Columns: id BIGINT PK, merchant_id BIGINT FK->merchant NOT NULL, invoice_period DATE NOT NULL (first day of invoice month), invoice_ref VARCHAR(64) UNIQUE NOT NULL, total_transaction_amount_krw BIGINT NOT NULL, fee_rate DECIMAL(6,4) NOT NULL, merchant_fee_krw BIGINT NOT NULL (= total_transaction_amount_krw x fee_rate; rounded to integer), vat_krw BIGINT NOT NULL (= merchant_fee_krw x 0.10; 10% VAT; rounded to integer), invoice_amount_krw BIGINT NOT NULL (= merchant_fee_krw + vat_krw), zeropay_share_krw BIGINT NOT NULL (= merchant_fee_krw x 0.0021; ZeroPay 0.21% of subtotal), status VARCHAR(20) NOT NULL CHECK IN ('DRAFT','ISSUED','COLLECTED','FAILED'), issued_at TIMESTAMPTZ NULL, collected_at TIMESTAMPTZ NULL, audit cols. UNIQUE(merchant_id, invoice_period). | • Create V016__tax_invoice.sql • Add CREATE TABLE tax_invoice with BIGINT for all KRW amount columns • Add CHECK IN ('DRAFT','ISSUED','COLLECTED','FAILED') for status • Add UNIQUE(merchant_id, invoice_period) to prevent duplicate monthly invoices • Add index on (status, invoice_period) for billing queries • Run migration; confirm BIGINT type rejects decimal 123.50 for merchant_fee_krw | db-migrations/src/main/resources/db/migration/V016__tax_invoice.sql | • UNIQUE(merchant_id, invoice_period) rejects second invoice for same merchant+month • status CHECK IN ('DRAFT','ISSUED','COLLECTED','FAILED') rejects 'SENT' • All KRW amount columns are BIGINT type (confirmed by \d tax_invoice) • issued_at and collected_at are nullable TIMESTAMPTZ • zeropay_share_krw NOT NULL confirmed | 25 | 3.1-T13 | DBA | DAT-03
3.1-T17 | shared-libs | 3.1 | 3. Data Layer & Persistence | Database design & ERD implementation | 1 | Create V017 migration: audit_log and api_request_log tables | audit_log: immutable record of all create/update/delete actions on configuration entities per DAT-03 sec 9.1 and sec 10.7. Retention >=7 years (BOK/KYC). Columns: id BIGINT PK, actor_id VARCHAR(120) NOT NULL, actor_type VARCHAR(20) NOT NULL CHECK IN ('OPERATOR','SYSTEM','PARTNER'), action VARCHAR(20) NOT NULL CHECK IN ('CREATE','UPDATE','DELETE','ACTIVATE','DEACTIVATE'), entity_type VARCHAR(50) NOT NULL (table name e.g. rule, partner, treasury_rate), entity_id BIGINT NOT NULL, before_value JSONB NULL (NULL for CREATE), after_value JSONB NULL (NULL for DELETE), occurred_at TIMESTAMPTZ NOT NULL DEFAULT NOW(), ip_address INET NULL, request_id VARCHAR(64) NULL (Trace ID). NO UPDATE or DELETE permitted; enforce at DB level via PostgreSQL RULE. api_request_log per DAT-03 sec 9.3: id BIGINT PK, request_id VARCHAR(64) UNIQUE NOT NULL, partner_id BIGINT FK->partner NULL, method VARCHAR(10), path VARCHAR(255), status_code INT, request_body_hash VARCHAR(64) (SHA-256; not plaintext), response_time_ms INT, occurred_at TIMESTAMPTZ NOT NULL, ip_address INET NULL. Indexes: audit_log(entity_type, entity_id), audit_log(occurred_at DESC); api_request_log(partner_id, occurred_at). | • Create V017__audit_log_and_api_request_log.sql • Add CREATE TABLE audit_log with CHECK constraints; no updated_at column • Add RULE pg_audit_log_no_update AS ON UPDATE TO audit_log DO INSTEAD NOTHING and RULE pg_audit_log_no_delete AS ON DELETE TO audit_log DO INSTEAD NOTHING • Add CREATE TABLE api_request_log with request_id UNIQUE and INET ip_address columns • Add composite indexes on both tables per spec • Run migration; verify UPDATE on audit_log is silently ignored (immutability rule fires) | db-migrations/src/main/resources/db/migration/V017__audit_log_and_api_request_log.sql | • UPDATE on audit_log row changes 0 rows (immutability RULE fires silently) • actor_type CHECK IN ('OPERATOR','SYSTEM','PARTNER') rejects 'ADMIN' • action CHECK IN ('CREATE','UPDATE','DELETE','ACTIVATE','DEACTIVATE') rejects 'PATCH' • before_value JSONB NULL accepted for CREATE action insert • api_request_log.request_id UNIQUE rejects duplicate request ID | 35 | 3.1-T03 | DBA | DAT-03
3.1-T18 | shared-libs | 3.1 | 3. Data Layer & Persistence | Database design & ERD implementation | 1 | Create V018 migration: hub_user and hub_role tables with role seeds | hub_user and hub_role implement internal Admin System RBAC per DAT-03 sec 9.2. hub_role: id BIGINT PK, role_code VARCHAR(30) UNIQUE NOT NULL CHECK IN ('SUPER_ADMIN','OPS_ADMIN','OPS_VIEWER','FINANCE'), permissions JSONB NOT NULL DEFAULT '{}', created_at/updated_at. hub_user: id BIGINT PK, email VARCHAR(255) UNIQUE NOT NULL, name VARCHAR(100) NOT NULL, role_id BIGINT FK->hub_role NOT NULL, is_active BOOLEAN NOT NULL DEFAULT FALSE, last_login_at TIMESTAMPTZ NULL, created_at/updated_at/created_by. Passwords are NOT stored here; authentication is handled by Auth and Identity service (OAuth2/JWT). Index hub_user on role_id (email already unique-indexed). Seed the 4 canonical role rows with permissions='{}'. | • Create V018__hub_user_and_hub_role.sql • Add CREATE TABLE hub_role with role_code CHECK constraint and JSONB permissions DEFAULT '{}' • Add CREATE TABLE hub_user with FK->hub_role; add UNIQUE on email; add is_active DEFAULT FALSE • Add index on hub_user.role_id • Add INSERT INTO hub_role (role_code, permissions) VALUES for SUPER_ADMIN, OPS_ADMIN, OPS_VIEWER, FINANCE with ON CONFLICT (role_code) DO NOTHING • Run migration and verify SELECT count(*) FROM hub_role = 4 | db-migrations/src/main/resources/db/migration/V018__hub_user_and_hub_role.sql | • role_code CHECK IN ('SUPER_ADMIN','OPS_ADMIN','OPS_VIEWER','FINANCE') rejects 'DEVELOPER' • hub_user.is_active DEFAULT FALSE confirmed • hub_user.email UNIQUE rejects duplicate email insert • SELECT count(*) FROM hub_role = 4 after migration • FK to hub_role.id enforced (insert user with invalid role_id rejected) | 25 | 3.1-T01 | DBA | DAT-03
3.1-T19 | shared-libs | 3.1 | 3. Data Layer & Persistence | Database design & ERD implementation | 1 | Create V019 migration: transactional outbox table | The transactional Outbox pattern is used for reliable async domain event publishing (Phase 1: in-process outbox poller; Phase 2: Kafka transport behind EventPublisher interface per STACK.md). The outbox table is in PostgreSQL alongside the business tables so domain events and business writes are in the same DB transaction. Columns: id BIGINT PK, aggregate_type VARCHAR(50) NOT NULL (e.g. 'transaction', 'prefunding_account'), aggregate_id VARCHAR(64) NOT NULL (business key e.g. txn_ref), event_type VARCHAR(100) NOT NULL (e.g. 'TransactionApproved', 'PrefundingDeducted'), payload JSONB NOT NULL, status VARCHAR(20) NOT NULL DEFAULT 'PENDING' CHECK IN ('PENDING','PUBLISHED','FAILED'), created_at TIMESTAMPTZ NOT NULL DEFAULT NOW(), published_at TIMESTAMPTZ NULL, retry_count INT NOT NULL DEFAULT 0. Index on (status, created_at) for outbox poller to SELECT PENDING rows. Index on (aggregate_type, aggregate_id) for aggregate-level queries. lib-events module defines the Avro/JSON event schemas that populate payload. | • Create V019__outbox.sql • Add CREATE TABLE outbox with all columns; add status CHECK constraint • Add index on (status, created_at) for efficient PENDING row polling • Add index on (aggregate_type, aggregate_id) • Run migration; insert a PENDING row and verify status DEFAULT • Confirm published_at NULL accepted and retry_count DEFAULT 0 | db-migrations/src/main/resources/db/migration/V019__outbox.sql | • status DEFAULT 'PENDING' confirmed by INSERT without explicit status • status CHECK IN ('PENDING','PUBLISHED','FAILED') rejects 'SENT' • Index on (status, created_at) present in pg_indexes • payload JSONB column accepts nested JSON object • retry_count DEFAULT 0 confirmed | 20 | 3.1-T01 | DBA | DAT-03
3.1-T20 | shared-libs | 3.1 | 3. Data Layer & Persistence | Database design & ERD implementation | 1 | Create Flyway config bean in lib-persistence for multi-service reuse | lib-persistence is a shared Gradle module (libs/lib-persistence/) providing common JPA/Flyway configuration. Each Spring Boot service (services/payment-executor, services/config-registry, services/prefunding-balance, etc.) includes lib-persistence as a compile dependency and gets a consistent Flyway DataSource setup pointing to PostgreSQL 16. DataSource uses spring.datasource.url=jdbc:postgresql://${DB_HOST:localhost}:${DB_PORT:5433}/${DB_NAME:gmepay}, driver-class-name=org.postgresql.Driver, HikariCP pool min=2 max=10. Flyway locations set per service via spring.flyway.locations configuration. Spring Boot 3.x auto-configuration via META-INF/spring/org.springframework.boot.autoconfigure.AutoConfiguration.imports. | • In libs/lib-persistence/build.gradle add dependencies: spring-boot-autoconfigure, flyway-core, postgresql JDBC, spring-data-jpa • Create libs/lib-persistence/src/main/java/com/gme/pay/persistence/FlywayConfig.java as @Configuration with DataSource @Bean using HikariCP properties • Create libs/lib-persistence/src/main/resources/META-INF/spring/org.springframework.boot.autoconfigure.AutoConfiguration.imports to register FlywayConfig • Write libs/lib-persistence/src/test/java/com/gme/pay/persistence/FlywayConfigTest.java using @Testcontainers with PostgreSQLContainer("postgres:16") to verify Flyway.migrate() runs cleanly • Run ./gradlew :lib-persistence:test | libs/lib-persistence/src/main/java/com/gme/pay/persistence/FlywayConfig.java, libs/lib-persistence/src/test/java/com/gme/pay/persistence/FlywayConfigTest.java | • FlywayConfigTest passes with Testcontainers postgres:16 image • Flyway.migrate() returns MigrateResult with migrationsExecuted >= 0 and no errors • HikariPool max pool size = 10 confirmed in test logs • AutoConfiguration.imports file present so dependent services auto-configure Flyway • ./gradlew :lib-persistence:test exits 0 | 45 | 3.1-T01 | DBA | DAT-03
3.1-T21 | shared-libs | 3.1 | 3. Data Layer & Persistence | Database design & ERD implementation | 1 | Testcontainers integration test: V001-V010 apply cleanly in sequence | All Flyway migrations V001-V010 must apply in order against a clean Postgres 16 container. The test uses JUnit 5 with @Testcontainers annotation and @Container PostgreSQLContainer("postgres:16") from org.testcontainers:postgresql. After Flyway.migrate(), verify table presence and critical column types. Expected tables after V010: qr_scheme, scheme_country, partner, partner_credential, partner_webhook, treasury_rate, rule, service_charge_tier, rate_quote, prefunding_account, prefunding_ledger_entry, low_balance_alert_config (12 tables). This test acts as the integration gate before service-layer code is wired. | • Add testImplementation testcontainers:postgresql and junit-jupiter to db-migrations/build.gradle • Create db-migrations/src/test/java/com/gme/pay/db/MigrationV001toV010Test.java • In @Test run Flyway.configure().dataSource(container.getJdbcUrl(),...).locations("classpath:db/migration").load().migrate() • Assert migrateResult.migrationsExecuted == 10 • Query information_schema.tables and assert all 12 tables present; query information_schema.columns to spot-check rate DECIMAL(20,8) on treasury_rate | db-migrations/src/test/java/com/gme/pay/db/MigrationV001toV010Test.java | • migrationsExecuted == 10 with no validation errors • All 12 expected tables present in information_schema.tables • treasury_rate.rate column data_type = 'numeric' with numeric_precision=20 and numeric_scale=8 • prefunding_ledger_entry has no updated_at column in information_schema.columns • Test completes under 60 seconds | 40 | 3.1-T10, 3.1-T20 | DBA | DAT-03
3.1-T22 | shared-libs | 3.1 | 3. Data Layer & Persistence | Database design & ERD implementation | 1 | Testcontainers integration test: V011-V019 and full 19-migration schema validation | Continuation of migration integration tests covering V011-V019. After all 19 migrations apply, verify: (1) total table count >= 19 (includes merchant, qr_code, merchant_sync_log, settlement_batch, settlement_file, reconciliation_item, bok_report_record, revenue_record, tax_invoice, audit_log, api_request_log, hub_user, hub_role, outbox, refund, transaction_event); (2) critical CHECK constraints fire correctly; (3) hub_role has 4 seeded rows; (4) outbox status DEFAULT is 'PENDING'. Live-fire constraint tests: rule m_a+m_b<0.02 with is_same_ccy_shortcircuit=FALSE; transaction_event step=9; prefunding_ledger_entry amount=0. | • Create db-migrations/src/test/java/com/gme/pay/db/MigrationFullSchemaTest.java with Testcontainers PostgreSQLContainer • Run all 19 migrations; assert migrationsExecuted == 19 • Execute INSERT statements that violate CHECK constraints and assert PSQLException is thrown for each • Assert SELECT count(*) FROM hub_role == 4 (seeded roles) • Assert INSERT INTO outbox (aggregate_type, aggregate_id, event_type, payload) returns row with status='PENDING' | db-migrations/src/test/java/com/gme/pay/db/MigrationFullSchemaTest.java | • migrationsExecuted == 19 with no errors • rule INSERT with m_a=0.005, m_b=0.005, is_same_ccy_shortcircuit=FALSE throws PSQLException • transaction_event step=9 INSERT throws PSQLException (CHECK violation) • prefunding_ledger_entry amount=0 INSERT throws PSQLException • hub_role count == 4 | 45 | 3.1-T21, 3.1-T19, 3.1-T18 | DBA | DAT-03
3.1-T23 | shared-libs | 3.1 | 3. Data Layer & Persistence | Database design & ERD implementation | 1 | Money precision test: DECIMAL(20,8) USD pool values and pool-identity invariant | DAT-03 sec 2.3 and sec 2.4 mandate DECIMAL(20,8) for USD intermediate values and DECIMAL(20,4) for final amounts. The pool identity invariant is: collection_usd - collection_margin_usd - payout_margin_usd = payout_usd_cost within 0.01 USD tolerance. Test vector: m_a=0.015, m_b=0.010, target_payout=1000 KRW, cost_rate_pay=1380.0 (usd_krw), cost_rate_coll=1.0 (USD identity). Step 1: payout_usd_cost = 1000/1380 = 0.72463768. Step 2: collection_usd = 0.72463768/(1-0.015-0.010) = 0.72463768/0.975 = 0.74321814. Step 3a: collection_margin_usd = 0.74321814*0.015 = 0.01114827. Step 3b: payout_margin_usd = 0.74321814*0.010 = 0.00743218. Pool check: 0.74321814-0.01114827-0.00743218 = 0.72463769 (diff = 0.00000001 < 0.01 USD tolerance). | • Create db-migrations/src/test/java/com/gme/pay/db/MoneyPrecisionTest.java using Testcontainers • After full 19-migration schema, insert prerequisite rows: qr_scheme (ZEROPAY), partner (TEST_PARTNER), treasury_rate (usd_krw=1380.00000000), rule with m_a=0.015000, m_b=0.010000 • Insert rate_quote row with the computed values above (8dp precision) • SELECT stored values back via JDBC as BigDecimal and assert each to 8dp • Compute pool identity from DB values: abs(collection_usd - collection_margin_usd - payout_margin_usd - payout_usd_cost) and assert < 0.01 | db-migrations/src/test/java/com/gme/pay/db/MoneyPrecisionTest.java | • payout_usd_cost stored and retrieved as 0.72463768 (not rounded to 4dp) • collection_usd stored and retrieved as 0.74321814 without truncation • Pool identity check: abs value < 0.01 USD • collection_amount DECIMAL(20,4) stores send_amount+0 correctly • No ArithmeticException or precision loss in JDBC BigDecimal retrieval | 35 | 3.1-T22 | DBA | DAT-03
3.1-T24 | shared-libs | 3.1 | 3. Data Layer & Persistence | Database design & ERD implementation | 1 | Concurrent SELECT FOR UPDATE test: prefunding_account balance deduction atomicity | Prefunding deductions MUST be atomic. Application pattern: BEGIN; SELECT balance FROM prefunding_account WHERE partner_id=? FOR UPDATE; check balance >= amount; UPDATE prefunding_account SET balance = balance - amount WHERE id=?; INSERT INTO prefunding_ledger_entry ...; COMMIT. Two concurrent threads each attempting to deduct 6000 USD from a 10000 USD balance must result in exactly one successful deduction (final balance = 4000 USD) because the second thread must wait for the first to commit, then re-check and find insufficient balance. Without FOR UPDATE, both deductions could succeed leaving balance = -2000. | • Create db-migrations/src/test/java/com/gme/pay/db/PrefundingAtomicityTest.java using Testcontainers PostgreSQLContainer • Insert prefunding_account with balance=10000.0000 for a test OVERSEAS partner • Spawn two threads each in separate JDBC connections executing the SELECT FOR UPDATE + UPDATE + INSERT ledger flow, each deducting 6000 USD • Use CountDownLatch to start both threads simultaneously • Assert exactly one thread succeeds; assert final balance = 4000.0000; assert ledger entry count == 1 | db-migrations/src/test/java/com/gme/pay/db/PrefundingAtomicityTest.java | • Final prefunding_account.balance = 4000.0000 (exactly one successful deduction) • prefunding_ledger_entry count == 1 after concurrent test • Second thread fails with insufficient-balance check (application-level guard after FOR UPDATE releases) • No negative balance results from concurrent deductions • Test is deterministic across 10 repeated runs (no flakiness) | 45 | 3.1-T22 | DBA | DAT-03
3.1-T25 | shared-libs | 3.1 | 3. Data Layer & Persistence | Database design & ERD implementation | 1 | Spring Data JPA entities for config/registry tables in services/config-registry | The services/config-registry Spring Boot service manages qr_scheme, partner, rule, treasury_rate, and related config tables. JPA entity classes must use BigDecimal for all DECIMAL/NUMERIC money columns to prevent JPA from defaulting to DOUBLE. Use @Column(precision=X, scale=Y) matching DAT-03 types exactly. Package: services/config-registry/src/main/java/com/gme/pay/configregistry/entity/. Hibernate schema validation (spring.jpa.hibernate.ddl-auto=validate) must pass against the Flyway-migrated schema. Do NOT use @Enumerated; all status/type fields are String (CHECK is at DB level). | • Create QrSchemeEntity.java: @Entity @Table(name='qr_scheme') with all columns; fee columns as BigDecimal with @Column(precision=6,scale=4); gme_fee_share_pct BigDecimal(6,4) • Create PartnerEntity.java with partner_type String; rate_quote_ttl_seconds Integer; low_balance_threshold_usd BigDecimal(20,4) nullable • Create RuleEntity.java with m_a/m_b as BigDecimal @Column(precision=8,scale=6); is_same_ccy_shortcircuit Boolean • Create TreasuryRateEntity.java with rate as BigDecimal @Column(precision=20,scale=8) • Write @DataJpaTest slice tests using @AutoConfigureTestDatabase(replace=NONE) with Testcontainers Postgres; verify Hibernate validate passes and insert/retrieve m_a=0.015000 without rounding | services/config-registry/src/main/java/com/gme/pay/configregistry/entity/QrSchemeEntity.java, PartnerEntity.java, RuleEntity.java, TreasuryRateEntity.java | • Hibernate schema validate passes against Flyway-migrated schema (no SchemaManagementException) • BigDecimal(8,6) field m_a stores and retrieves 0.015000 exactly • No @Enumerated annotation in any entity (all status/type = String) • @DataJpaTest for RuleEntity inserts cross-border rule with m_a=0.005, m_b=0.005 and gets DataIntegrityViolationException (DB CHECK fires) • TreasuryRateEntity.rate BigDecimal(20,8) stores 1380.00000000 correctly | 50 | 3.1-T22, 3.1-T05 | DBA | DAT-03
3.1-T26 | shared-libs | 3.1 | 3. Data Layer & Persistence | Database design & ERD implementation | 1 | Spring Data JPA entities for transaction and rate_quote in services/payment-executor | The services/payment-executor Spring Boot service owns the transaction lifecycle. JPA entities for transaction and rate_quote are needed. Package: services/payment-executor/src/main/java/com/gme/pay/executor/entity/. All DECIMAL(20,8) columns mapped as BigDecimal nullable (Java wrapper, not primitive) so they can hold null for same-ccy short-circuit. TransactionEntity uses @Version Long version for optimistic locking on status transitions. TransactionEventEntity maps detail as JSONB (mapped as String with @Column(columnDefinition='jsonb')). RateQuoteEntity maps valid_until and quote_issued_at as Instant. | • Create TransactionEntity.java with @Entity @Table(name='transaction'); map all columns per DAT-03 sec 10.1; nullable USD pool fields as BigDecimal (wrapper) • Add @Version Long version field to TransactionEntity for optimistic locking • Create RateQuoteEntity.java with is_used Boolean; valid_until as Instant; all nullable USD fields as BigDecimal • Create TransactionEventEntity.java with detail as @Column(columnDefinition='jsonb') String • Write @DataJpaTest verifying TransactionEntity insert with is_same_ccy_shortcircuit=TRUE and null collection_usd succeeds; verify OptimisticLockingFailureException on stale update | services/payment-executor/src/main/java/com/gme/pay/executor/entity/TransactionEntity.java, RateQuoteEntity.java, TransactionEventEntity.java | • @DataJpaTest inserts TransactionEntity with collection_usd=null and is_same_ccy_shortcircuit=TRUE without error • @Version field triggers OptimisticLockingFailureException when two concurrent in-test loads both try to update • RateQuoteEntity.valid_until stored and retrieved as Instant correctly • TransactionEventEntity.detail stored as JSONB string and retrieved intact • Hibernate validate passes against Flyway V007/V006 schema | 50 | 3.1-T22, 3.1-T07 | DBA | DAT-03
3.1-T27 | shared-libs | 3.1 | 3. Data Layer & Persistence | Database design & ERD implementation | 1 | Spring Data JPA entities for prefunding in services/prefunding-balance | The services/prefunding-balance Spring Boot service manages prefunding_account and prefunding_ledger_entry. Package: services/prefunding-balance/src/main/java/com/gme/pay/prefunding/entity/. PrefundingAccountEntity uses @Lock(LockModeType.PESSIMISTIC_WRITE) in repository for SELECT FOR UPDATE deduction flow. PrefundingLedgerEntryEntity is append-only: no updatedAt field mapped, entry_type as String. balance is BigDecimal DECIMAL(20,4). PrefundingAccountRepository extends JpaRepository with custom method findByPartnerIdWithLock annotated @Lock(PESSIMISTIC_WRITE). LowBalanceAlertConfigEntity maps low_balance_alert_config. | • Create PrefundingAccountEntity.java with balance as BigDecimal(20,4); add @Version Long version • Create PrefundingLedgerEntryEntity.java as @Entity; do NOT map any updatedAt field; entry_type as String • Create LowBalanceAlertConfigEntity.java mapping low_balance_alert_config table • Create PrefundingAccountRepository.java extending JpaRepository with @Query + @Lock(PESSIMISTIC_WRITE) method for deduction • Write @DataJpaTest verifying pessimistic lock is acquired: second concurrent transaction.getBalance() blocks until first commits | services/prefunding-balance/src/main/java/com/gme/pay/prefunding/entity/PrefundingAccountEntity.java, PrefundingLedgerEntryEntity.java, LowBalanceAlertConfigEntity.java, services/prefunding-balance/src/main/java/com/gme/pay/prefunding/repository/PrefundingAccountRepository.java | • PrefundingLedgerEntryEntity has no updatedAt field (compile-time check via reflection in test) • @DataJpaTest confirms PESSIMISTIC_WRITE lock: second transaction on same row blocks until first commits • PrefundingAccountEntity.balance BigDecimal(20,4) stores 10000.0000 exactly • PrefundingLedgerEntryEntity amount=0 insert throws DataIntegrityViolationException (DB CHECK fires) • Hibernate validate passes against Flyway V009 schema | 45 | 3.1-T22, 3.1-T09 | DBA | DAT-03
3.1-T28 | shared-libs | 3.1 | 3. Data Layer & Persistence | Database design & ERD implementation | 1 | V020 seed migration: ZeroPay scheme, KR country, GME_REMIT partner, treasury rates | V020 inserts the minimum idempotent seed data needed for local dev and integration tests. Seed: (1) qr_scheme row for ZEROPAY: scheme_code='ZEROPAY', payout_ccy='KRW', supported_modes='BOTH', status='TESTING', partner_b_quote_deviation_pct=0.0100, gme_fee_share_pct=0.7000, is_active=TRUE, sftp_host/paths/api_endpoint/api_credential_ref set to placeholder values. (2) scheme_country row: ZEROPAY + country_code='KR', is_active=TRUE. (3) partner row: partner_code='GME_REMIT', partner_type='LOCAL', collection_ccy='KRW', settle_a_ccy='KRW', rate_quote_ttl_seconds=300, is_active=FALSE, status='ONBOARDING'. (4) treasury_rate rows: usd_krw=1380.00000000 and usd_mnt=3440.00000000, source='MANUAL', effective_at=NOW(). All INSERTs use ON CONFLICT DO NOTHING for idempotency. | • Create db-migrations/src/main/resources/db/migration/V020__seed_zeropay_and_gme_remit.sql • INSERT INTO qr_scheme with ON CONFLICT (scheme_code) DO NOTHING • INSERT INTO scheme_country using subquery for scheme_id with ON CONFLICT (scheme_id, country_code) DO NOTHING • INSERT INTO partner for GME_REMIT with ON CONFLICT (partner_code) DO NOTHING • INSERT two rows into treasury_rate (usd_krw=1380.00000000, usd_mnt=3440.00000000) with source='MANUAL' • Run migration twice; confirm second run applies cleanly with 0 new rows (verify via SELECT counts before/after) | db-migrations/src/main/resources/db/migration/V020__seed_zeropay_and_gme_remit.sql | • Second run of V020 produces no duplicate key errors (idempotent ON CONFLICT DO NOTHING) • qr_scheme.gme_fee_share_pct = 0.7000 after seed • treasury_rate row for usd_krw has rate=1380.00000000 (8dp precision confirmed) • partner GME_REMIT has is_active=FALSE and status='ONBOARDING' • scheme_country KR row is linked to ZEROPAY scheme_id (verified by JOIN query) | 25 | 3.1-T22, 3.1-T04, 3.1-T02, 3.1-T03 | DBA | DAT-03
3.1-T29 | shared-libs | 3.1 | 3. Data Layer & Persistence | Database design & ERD implementation | 1 | Index presence validation test and SCHEMA.md for db-migrations module | A final integration test validates that all performance-critical indexes defined in DAT-03 exist in the migrated schema by querying pg_indexes. Critical indexes per DAT-03: transaction (partner_id, committed_at), (scheme_id, completed_at), (status, committed_at), scheme_ref, hub_txn_ref; prefunding_ledger_entry (account_id, created_at); treasury_rate (ccy_pair, effective_at DESC); rate_quote (partner_id, quote_issued_at), (rule_id, is_used), valid_until; settlement_batch (scheme_id, settlement_date); reconciliation_item (batch_id, match_status); outbox (status, created_at). Additionally produce SCHEMA.md documenting migration list, money type rules, and domain groupings. | • Create db-migrations/src/test/java/com/gme/pay/db/IndexPresenceTest.java querying pg_indexes for each required index by indexdef column content • Assert each critical index present; log missing indexes as AssertionError with name • Verify EXPLAIN (FORMAT TEXT) for SELECT * FROM transaction WHERE partner_id=1 AND committed_at > NOW()-interval '1 day' uses Index Scan • Create db-migrations/SCHEMA.md listing all 20 migrations with descriptions, money type conventions (DECIMAL(20,8) for USD pool, DECIMAL(20,4) for final amounts, BIGINT for KRW), and table groupings by domain • Run ./gradlew :db-migrations:test to confirm all tests green | db-migrations/src/test/java/com/gme/pay/db/IndexPresenceTest.java, db-migrations/SCHEMA.md | • IndexPresenceTest asserts all 12 critical composite/single-column indexes present (test fails listing missing names if any absent) • EXPLAIN for partner_id+committed_at filter on transaction shows Index Scan not Seq Scan • SCHEMA.md documents DECIMAL(20,8) for USD pool and BIGINT for KRW • SCHEMA.md lists all 20 migration files (V001-V020) in order with one-line description each • ./gradlew :db-migrations:test exits 0 with all tests passing | 40 | 3.1-T22 | DBA | DAT-03
3.2-T01 | config-registry | 3.2 | 3. Data Layer & Persistence | Core entities: Scheme/Partner/Rule/Direction | 1 | Create Flyway V010__create_qr_scheme.sql in services/config-registry | WBS 3.2 delivers the core config-entity layer. qr_scheme is the root: represents a payment network (e.g. ZeroPay operated by KFTC). Adding a scheme is a config INSERT, never code. Naming convention: snake_case; PKs are BIGINT surrogate auto-increment; timestamps TIMESTAMPTZ; enums stored as VARCHAR with CHECK for portability; money as DECIMAL; soft-delete via is_active + deactivated_at. | • In module services/config-registry create src/main/resources/db/migration/V010__create_qr_scheme.sql • Define: id BIGINT GENERATED ALWAYS AS IDENTITY PK, scheme_code VARCHAR(30) UNIQUE NOT NULL, name VARCHAR(100) NOT NULL, payout_ccy CHAR(3) NOT NULL, supported_modes VARCHAR(20) NOT NULL CHECK(supported_modes IN ('MPM','CPM','BOTH')), settlement_counterparty VARCHAR(120), merchant_fee_domestic_min DECIMAL(6,4), merchant_fee_domestic_max DECIMAL(6,4), merchant_fee_crossborder_min DECIMAL(6,4), merchant_fee_crossborder_max DECIMAL(6,4), van_fee_domestic_min DECIMAL(6,4), van_fee_domestic_max DECIMAL(6,4), van_fee_crossborder_min DECIMAL(6,4), van_fee_crossborder_max DECIMAL(6,4), gme_fee_share_pct DECIMAL(6,4), partner_b_quote_enabled BOOLEAN NOT NULL DEFAULT FALSE, partner_b_quote_deviation_pct DECIMAL(6,4) NOT NULL DEFAULT 0.0100, sftp_host VARCHAR(255), sftp_path_outbound VARCHAR(255), sftp_path_inbound VARCHAR(255), api_endpoint VARCHAR(512), api_credential_ref VARCHAR(120), status VARCHAR(20) NOT NULL DEFAULT 'TESTING' CHECK(status IN ('TESTING','ACTIVE','INACTIVE')), is_active BOOLEAN NOT NULL DEFAULT TRUE, deactivated_at TIMESTAMPTZ, created_at TIMESTAMPTZ NOT NULL DEFAULT NOW(), updated_at TIMESTAMPTZ NOT NULL DEFAULT NOW(), created_by VARCHAR(120), updated_by VARCHAR(120) • Add CREATE INDEX idx_qr_scheme_status_active ON qr_scheme(status, is_active) • Run Flyway migrate against local PostgreSQL 16 (docker-compose port 5433) and confirm checksum | services/config-registry/src/main/resources/db/migration/V010__create_qr_scheme.sql | • Flyway validate passes on PostgreSQL 16 • supported_modes CHECK rejects 'PUSH'; accepts 'MPM','CPM','BOTH' • status CHECK rejects 'ENABLED'; accepts 'TESTING','ACTIVE','INACTIVE' • scheme_code UNIQUE blocks duplicate insert • partner_b_quote_deviation_pct defaults to 0.0100 | 30 |  | BE | DAT-03
3.2-T02 | config-registry | 3.2 | 3. Data Layer & Persistence | Core entities: Scheme/Partner/Rule/Direction | 1 | Create Flyway V011__create_scheme_country.sql in services/config-registry | scheme_country maps active QR schemes to ISO 3166-1 alpha-2 country codes for CPM location-based scheme selection. Business key UNIQUE(scheme_id, country_code). FK to qr_scheme ON DELETE RESTRICT (cannot drop a scheme with active country mappings). Standard audit columns required on all mutable tables per DAT-03 conventions. | • Create services/config-registry/src/main/resources/db/migration/V011__create_scheme_country.sql • Define: id BIGINT GENERATED ALWAYS AS IDENTITY PK, scheme_id BIGINT NOT NULL REFERENCES qr_scheme(id) ON DELETE RESTRICT, country_code CHAR(2) NOT NULL, is_active BOOLEAN NOT NULL DEFAULT TRUE, created_at TIMESTAMPTZ NOT NULL DEFAULT NOW(), updated_at TIMESTAMPTZ NOT NULL DEFAULT NOW(), created_by VARCHAR(120), updated_by VARCHAR(120) • Add CONSTRAINT uq_scheme_country UNIQUE(scheme_id, country_code) • Add CREATE INDEX idx_scheme_country_scheme_id ON scheme_country(scheme_id) • Run Flyway migrate and verify ordering after V010 | services/config-registry/src/main/resources/db/migration/V011__create_scheme_country.sql | • Migration applies after V010 without error • UNIQUE(scheme_id, country_code) rejects duplicate pair insert • FK to qr_scheme: inserting non-existent scheme_id fails with FK violation • Deleting a qr_scheme row referenced by scheme_country is blocked (ON DELETE RESTRICT) • is_active defaults TRUE | 20 | 3.2-T01 | BE | DAT-03
3.2-T03 | config-registry | 3.2 | 3. Data Layer & Persistence | Core entities: Scheme/Partner/Rule/Direction | 1 | Create Flyway V012__create_partner.sql in services/config-registry | partner represents payment apps (GME Remit=LOCAL/KRW, SendMN=OVERSEAS/USD). partner_type: LOCAL or OVERSEAS. OVERSEAS partners require prefunding; LOCAL do not. rate_quote_ttl_seconds range 60-1800 enforced by DB CHECK, default 300 (aggregator-bound=60, otherwise 300 per TICKET_BRIEF). Soft-delete only; hard deletes prohibited on tables referenced by transactions. | • Create services/config-registry/src/main/resources/db/migration/V012__create_partner.sql • Define: id BIGINT GENERATED ALWAYS AS IDENTITY PK, partner_code VARCHAR(30) UNIQUE NOT NULL, name VARCHAR(100) NOT NULL, partner_type VARCHAR(10) NOT NULL CHECK(partner_type IN ('LOCAL','OVERSEAS')), collection_ccy CHAR(3) NOT NULL, settle_a_ccy CHAR(3) NOT NULL, webhook_url VARCHAR(512), rate_quote_ttl_seconds INT NOT NULL DEFAULT 300 CHECK(rate_quote_ttl_seconds BETWEEN 60 AND 1800), low_balance_threshold_usd DECIMAL(20,4), low_balance_alert_email VARCHAR(255), status VARCHAR(20) NOT NULL DEFAULT 'ONBOARDING' CHECK(status IN ('ONBOARDING','ACTIVE','SUSPENDED','INACTIVE')), is_active BOOLEAN NOT NULL DEFAULT TRUE, deactivated_at TIMESTAMPTZ, created_at TIMESTAMPTZ NOT NULL DEFAULT NOW(), updated_at TIMESTAMPTZ NOT NULL DEFAULT NOW(), created_by VARCHAR(120), updated_by VARCHAR(120) • Add CREATE INDEX idx_partner_type_active ON partner(partner_type, is_active) | services/config-registry/src/main/resources/db/migration/V012__create_partner.sql | • partner_type CHECK rejects 'BANK'; accepts 'LOCAL','OVERSEAS' • status CHECK rejects 'PENDING'; accepts all four values • rate_quote_ttl_seconds CHECK rejects 59 and 1801; accepts 60 and 1800 • partner_code UNIQUE blocks duplicate • Migration applies after V011 | 30 | 3.2-T02 | BE | DAT-03
3.2-T04 | config-registry | 3.2 | 3. Data Layer & Persistence | Core entities: Scheme/Partner/Rule/Direction | 1 | Create Flyway V013__create_rule.sql with UNIQUE(partner,scheme,direction) and margin CHECK | rule is the join of partner x qr_scheme x direction. Business key UNIQUE(partner_id, scheme_id, direction). Direction: INBOUND, OUTBOUND, DOMESTIC, HUB. Margin m_a (collection-side) and m_b (payout-side) are DECIMAL(8,6). Cross-border margin constraint: CHECK(is_same_ccy_shortcircuit=TRUE OR (m_a+m_b)>=0.02) enforced at DB level. Same-ccy rules are exempt (m_a=m_b=0 allowed). rate_coll_source and rate_pay_source: IDENTITY, LIVE, MANUAL, PARTNER. effective_from governs when rule changes apply to new txns. | • Create services/config-registry/src/main/resources/db/migration/V013__create_rule.sql • Define: id BIGINT GENERATED ALWAYS AS IDENTITY PK, partner_id BIGINT NOT NULL REFERENCES partner(id) ON DELETE RESTRICT, scheme_id BIGINT NOT NULL REFERENCES qr_scheme(id) ON DELETE RESTRICT, direction VARCHAR(10) NOT NULL CHECK(direction IN ('INBOUND','OUTBOUND','DOMESTIC','HUB')), collection_ccy CHAR(3), settle_a_ccy CHAR(3), settle_b_ccy CHAR(3), payout_ccy CHAR(3), rate_coll_source VARCHAR(10) NOT NULL CHECK(rate_coll_source IN ('IDENTITY','LIVE','MANUAL','PARTNER')), rate_pay_source VARCHAR(10) NOT NULL CHECK(rate_pay_source IN ('IDENTITY','LIVE','MANUAL','PARTNER')), manual_rate_coll DECIMAL(20,8), manual_rate_pay DECIMAL(20,8), m_a DECIMAL(8,6) NOT NULL DEFAULT 0 CHECK(m_a>=0), m_b DECIMAL(8,6) NOT NULL DEFAULT 0 CHECK(m_b>=0), CONSTRAINT chk_rule_margin CHECK(is_same_ccy_shortcircuit=TRUE OR (m_a+m_b)>=0.02), service_charge_amount DECIMAL(20,4) NOT NULL DEFAULT 0, service_charge_ccy CHAR(3), is_same_ccy_shortcircuit BOOLEAN NOT NULL DEFAULT FALSE, status VARCHAR(20) NOT NULL DEFAULT 'DRAFT' CHECK(status IN ('DRAFT','ACTIVE','SUSPENDED')), effective_from TIMESTAMPTZ, created_at TIMESTAMPTZ NOT NULL DEFAULT NOW(), updated_at TIMESTAMPTZ NOT NULL DEFAULT NOW(), created_by VARCHAR(120), updated_by VARCHAR(120) • Add CONSTRAINT uq_rule UNIQUE(partner_id, scheme_id, direction) • Add indexes on partner_id, scheme_id, and composite (partner_id, scheme_id, direction, status) | services/config-registry/src/main/resources/db/migration/V013__create_rule.sql | • UNIQUE(partner_id,scheme_id,direction) rejects duplicate triple insert • direction CHECK rejects 'BILATERAL'; accepts all four values • chk_rule_margin rejects is_same_ccy_shortcircuit=FALSE with m_a=0.005 m_b=0.005 (sum=0.01 less than 0.02) • chk_rule_margin accepts is_same_ccy_shortcircuit=TRUE with m_a=0 m_b=0 • chk_rule_margin accepts is_same_ccy_shortcircuit=FALSE with m_a=0.01 m_b=0.01 (sum=0.02) • Migration applies after V012 | 35 | 3.2-T03 | BE | DAT-03
3.2-T05 | config-registry | 3.2 | 3. Data Layer & Persistence | Core entities: Scheme/Partner/Rule/Direction | 1 | Create Flyway V014__create_service_charge_tier.sql in services/config-registry | service_charge_tier allows volume-based overrides for the flat rule.service_charge_amount. Tiers indexed by collection_usd (USD pool amount, DECIMAL(20,4)). min_collection_usd inclusive, max_collection_usd exclusive (NULL=no cap). If no tiers exist for a rule, flat service_charge_amount from rule applies. FK to rule ON DELETE RESTRICT (tiers protect the rule from deletion while active). | • Create services/config-registry/src/main/resources/db/migration/V014__create_service_charge_tier.sql • Define: id BIGINT GENERATED ALWAYS AS IDENTITY PK, rule_id BIGINT NOT NULL REFERENCES rule(id) ON DELETE RESTRICT, min_collection_usd DECIMAL(20,4) NOT NULL CHECK(min_collection_usd>=0), max_collection_usd DECIMAL(20,4) CHECK(max_collection_usd IS NULL OR max_collection_usd>min_collection_usd), charge_amount DECIMAL(20,4) NOT NULL, created_at TIMESTAMPTZ NOT NULL DEFAULT NOW(), updated_at TIMESTAMPTZ NOT NULL DEFAULT NOW(), created_by VARCHAR(120), updated_by VARCHAR(120) • Add CREATE INDEX idx_sct_rule_id ON service_charge_tier(rule_id) | services/config-registry/src/main/resources/db/migration/V014__create_service_charge_tier.sql | • CHECK rejects max_collection_usd <= min_collection_usd (e.g. min=100, max=50 fails) • CHECK accepts max_collection_usd = NULL (no-cap tier) • FK to rule: inserting non-existent rule_id fails • Deleting a rule that has tiers is blocked (ON DELETE RESTRICT) • Migration applies after V013 | 20 | 3.2-T04 | BE | DAT-03
3.2-T06 | config-registry | 3.2 | 3. Data Layer & Persistence | Core entities: Scheme/Partner/Rule/Direction | 1 | Create Flyway V015__create_treasury_rate.sql in services/config-registry | treasury_rate stores FX rates in canonical form: usd_{ccy} = units of target ccy per 1 USD (e.g. usd_krw=1380.0000 means 1 USD=1380 KRW). Type DECIMAL(20,8) for 8dp precision required for low-value currencies. source: LIVE (xe.com Phase 2) or MANUAL (Phase 1 Ops entry). Latest rate query: WHERE ccy_pair='usd_krw' ORDER BY effective_at DESC LIMIT 1. Historical rows retained for audit and BOK reconciliation. rate must be > 0. | • Create services/config-registry/src/main/resources/db/migration/V015__create_treasury_rate.sql • Define: id BIGINT GENERATED ALWAYS AS IDENTITY PK, ccy_pair VARCHAR(10) NOT NULL, rate DECIMAL(20,8) NOT NULL CHECK(rate>0), source VARCHAR(10) NOT NULL CHECK(source IN ('LIVE','MANUAL')), effective_at TIMESTAMPTZ NOT NULL, created_at TIMESTAMPTZ NOT NULL DEFAULT NOW(), updated_at TIMESTAMPTZ NOT NULL DEFAULT NOW(), created_by VARCHAR(120), updated_by VARCHAR(120) • Add CREATE INDEX idx_treasury_rate_pair_time ON treasury_rate(ccy_pair, effective_at DESC) for latest-rate lookups | services/config-registry/src/main/resources/db/migration/V015__create_treasury_rate.sql | • CHECK(rate>0) rejects zero and negative rates • source CHECK rejects 'AUTO'; accepts 'LIVE','MANUAL' • Multiple rows for same ccy_pair coexist (no UNIQUE on pair alone) • Index idx_treasury_rate_pair_time present in pg_indexes • Migration applies after V014 | 25 | 3.2-T04 | BE | DAT-03
3.2-T07 | config-registry | 3.2 | 3. Data Layer & Persistence | Core entities: Scheme/Partner/Rule/Direction | 1 | Define Direction enum in libs/lib-domain (Java 21) | Direction is used across svc-config-registry, rate-fx engine, smart-router, and payment-executor. Values: INBOUND, OUTBOUND, DOMESTIC, HUB. Stored as VARCHAR in PostgreSQL via @Enumerated(EnumType.STRING). Placed in shared libs/lib-domain so all Gradle modules reference one definition. Must round-trip cleanly through Jackson JSON serialization. | • In libs/lib-domain create src/main/java/com/gme/pay/domain/Direction.java • Define: public enum Direction { INBOUND, OUTBOUND, DOMESTIC, HUB } • Add Javadoc: INBOUND=overseas customer sends money to domestic merchant; OUTBOUND=domestic customer sends to overseas merchant; DOMESTIC=same-country; HUB=inter-hub routing • Create libs/lib-domain/src/test/java/com/gme/pay/domain/DirectionTest.java (JUnit 5): verify valueOf for all 4, values().length==4, Jackson round-trip of INBOUND | libs/lib-domain/src/main/java/com/gme/pay/domain/Direction.java and libs/lib-domain/src/test/java/com/gme/pay/domain/DirectionTest.java | • Direction.valueOf('INBOUND') returns INBOUND • Direction.values().length == 4 • Jackson ObjectMapper().writeValueAsString(DOMESTIC) returns '"DOMESTIC"' • Jackson readValue('"HUB"', Direction.class) returns Direction.HUB • Gradle build for libs/lib-domain succeeds | 20 |  | BE | DAT-03
3.2-T08 | config-registry | 3.2 | 3. Data Layer & Persistence | Core entities: Scheme/Partner/Rule/Direction | 1 | Define PartnerType enum in libs/lib-domain (Java 21) | PartnerType (LOCAL or OVERSEAS) drives prefunding logic and rate-engine short-circuit. LOCAL = GME Remit (KRW, no prefunding required). OVERSEAS = SendMN/T-Bank (USD prefunded; deduction required before scheme call). Stored as VARCHAR(10) in PostgreSQL. Placed in libs/lib-domain alongside Direction. | • Create libs/lib-domain/src/main/java/com/gme/pay/domain/PartnerType.java • Define: public enum PartnerType { LOCAL, OVERSEAS } • Add Javadoc: LOCAL=no prefunding; OVERSEAS=USD prefunding required • Create PartnerTypeTest.java (JUnit 5): valueOf both values, values().length==2, Jackson round-trip | libs/lib-domain/src/main/java/com/gme/pay/domain/PartnerType.java and libs/lib-domain/src/test/java/com/gme/pay/domain/PartnerTypeTest.java | • PartnerType.valueOf('LOCAL') returns LOCAL • PartnerType.values().length == 2 • Jackson round-trips LOCAL and OVERSEAS to/from JSON strings • Gradle build for libs/lib-domain succeeds | 15 | 3.2-T07 | BE | DAT-03
3.2-T09 | config-registry | 3.2 | 3. Data Layer & Persistence | Core entities: Scheme/Partner/Rule/Direction | 1 | Implement QrScheme JPA entity in services/config-registry (Spring Boot 3.x / Hibernate 6) | JPA entity for qr_scheme table (V010). Module services/config-registry. Use @Entity @Table(name='qr_scheme'). All TIMESTAMPTZ columns map to Instant. BigDecimal for all DECIMAL columns. VARCHAR CHECK-constrained columns map to String (not DB enum, per DAT-03 portability rule). Soft-delete: isActive Boolean, deactivatedAt Instant. Audit columns via @EntityListeners(AuditingEntityListener.class): @CreatedDate createdAt, @LastModifiedDate updatedAt, @CreatedBy createdBy, @LastModifiedBy updatedBy. | • Create services/config-registry/src/main/java/com/gme/pay/configregistry/entity/QrScheme.java • Annotate @Entity @Table(name='qr_scheme') @EntityListeners(AuditingEntityListener.class) • Map id with @Id @GeneratedValue(strategy=GenerationType.IDENTITY) • Map schemeCode @Column(name='scheme_code', unique=true, nullable=false, length=30) • Map all DECIMAL(6,4) fee columns as BigDecimal; all CHAR(3) ccy columns as String length=3 • Set spring.jpa.hibernate.ddl-auto=validate in test profile to verify schema match | services/config-registry/src/main/java/com/gme/pay/configregistry/entity/QrScheme.java | • Hibernate ddl-auto=validate passes against V010 migration on PostgreSQL 16 • schemeCode annotated @Column(unique=true, nullable=false, length=30) • supportedModes and status are String (not DB enum type) • All DECIMAL(6,4) fee percentage columns are BigDecimal • Audit fields createdAt, updatedAt, createdBy, updatedBy all present with correct JPA auditing annotations | 35 | 3.2-T01 | BE | DAT-03
3.2-T10 | config-registry | 3.2 | 3. Data Layer & Persistence | Core entities: Scheme/Partner/Rule/Direction | 1 | Implement Partner JPA entity in services/config-registry | JPA entity for partner table (V012). partnerType maps to PartnerType enum from libs/lib-domain via @Enumerated(EnumType.STRING). status mapped as String (ONBOARDING, ACTIVE, SUSPENDED, INACTIVE). rateQuoteTtlSeconds: int, default 300. lowBalanceThresholdUsd: BigDecimal nullable (OVERSEAS only). Soft-delete: isActive Boolean + deactivatedAt Instant. Audit columns via @EntityListeners. | • Create services/config-registry/src/main/java/com/gme/pay/configregistry/entity/Partner.java • Annotate @Entity @Table(name='partner') @EntityListeners(AuditingEntityListener.class) • Import PartnerType from libs/lib-domain; annotate @Enumerated(EnumType.STRING) • Map collectionCcy and settleACcy as @Column(name='collection_ccy', nullable=false, length=3) • Map lowBalanceThresholdUsd as BigDecimal @Column(name='low_balance_threshold_usd', precision=20, scale=4) nullable • Verify ddl-auto=validate passes against V012 | services/config-registry/src/main/java/com/gme/pay/configregistry/entity/Partner.java | • Hibernate ddl-auto=validate passes against V012 on PostgreSQL 16 • partnerType field uses @Enumerated(EnumType.STRING) with PartnerType from libs/lib-domain • partnerCode annotated @Column(unique=true, nullable=false, length=30) • lowBalanceThresholdUsd is nullable BigDecimal with precision=20 scale=4 • isActive annotated @Column(name='is_active', nullable=false) | 30 | 3.2-T03, 3.2-T08 | BE | DAT-03
3.2-T11 | config-registry | 3.2 | 3. Data Layer & Persistence | Core entities: Scheme/Partner/Rule/Direction | 1 | Implement Rule JPA entity in services/config-registry | JPA entity for rule table (V013). Business key UNIQUE(partnerId, schemeId, direction) declared via @Table uniqueConstraints. direction maps to Direction enum from libs/lib-domain. rateCollSource and ratePaySource map as String (IDENTITY, LIVE, MANUAL, PARTNER). m_a and m_b: BigDecimal @Column(precision=8, scale=6). isIsSameCcyShortcircuit: Boolean. effectiveFrom: Instant nullable. ManyToOne LAZY to Partner and QrScheme. | • Create services/config-registry/src/main/java/com/gme/pay/configregistry/entity/Rule.java • Annotate @Entity @Table(name='rule', uniqueConstraints=@UniqueConstraint(columnNames={'partner_id','scheme_id','direction'})) @EntityListeners(AuditingEntityListener.class) • Add @ManyToOne(fetch=FetchType.LAZY, optional=false) @JoinColumn(name='partner_id') Partner partner • Add @ManyToOne(fetch=FetchType.LAZY, optional=false) @JoinColumn(name='scheme_id') QrScheme scheme • Map direction @Enumerated(EnumType.STRING) Direction direction from libs/lib-domain • Map m_a @Column(name='m_a', precision=8, scale=6, nullable=false) BigDecimal ma; same for m_b • Verify ddl-auto=validate passes against V013 | services/config-registry/src/main/java/com/gme/pay/configregistry/entity/Rule.java | • Hibernate ddl-auto=validate passes against V013 • @Table uniqueConstraints lists partner_id, scheme_id, direction • direction @Enumerated(EnumType.STRING) with Direction enum from libs/lib-domain • m_a and m_b are BigDecimal with precision=8 scale=6 • partner and scheme are @ManyToOne(fetch=LAZY) • effectiveFrom is Instant nullable | 35 | 3.2-T04, 3.2-T07, 3.2-T10 | BE | DAT-03
3.2-T12 | config-registry | 3.2 | 3. Data Layer & Persistence | Core entities: Scheme/Partner/Rule/Direction | 1 | Implement ServiceChargeTier and TreasuryRate JPA entities in services/config-registry | ServiceChargeTier (V014): FK @ManyToOne LAZY to Rule; minCollectionUsd inclusive, maxCollectionUsd nullable (no cap), chargeAmount all BigDecimal DECIMAL(20,4). TreasuryRate (V015): ccyPair VARCHAR(10), rate BigDecimal DECIMAL(20,8) always positive, source String, effectiveAt Instant. Historical rows retained; no soft-delete needed. Both need standard audit columns via @EntityListeners. | • Create services/config-registry/src/main/java/com/gme/pay/configregistry/entity/ServiceChargeTier.java with @ManyToOne(fetch=LAZY) Rule rule, BigDecimal minCollectionUsd (not null), maxCollectionUsd (nullable), chargeAmount (not null) • Create services/config-registry/src/main/java/com/gme/pay/configregistry/entity/TreasuryRate.java with ccyPair String, rate BigDecimal @Column(precision=20,scale=8), source String, effectiveAt Instant • Add @EntityListeners(AuditingEntityListener.class) on both • Verify ddl-auto=validate passes against V014 and V015 | services/config-registry/src/main/java/com/gme/pay/configregistry/entity/ServiceChargeTier.java and TreasuryRate.java | • ServiceChargeTier.maxCollectionUsd is nullable BigDecimal • TreasuryRate.rate is BigDecimal with precision=20 scale=8 • Hibernate ddl-auto=validate passes both entities against V014 and V015 on PostgreSQL 16 • ServiceChargeTier.rule is @ManyToOne(fetch=LAZY) with name='rule_id' • TreasuryRate.effectiveAt is Instant @Column(name='effective_at', nullable=false) | 30 | 3.2-T05, 3.2-T06, 3.2-T11 | BE | DAT-03
3.2-T13 | config-registry | 3.2 | 3. Data Layer & Persistence | Core entities: Scheme/Partner/Rule/Direction | 1 | Implement QrSchemeRepository and PartnerRepository (Spring Data JPA) in services/config-registry | Spring Data JPA repositories for config entities. QrSchemeRepository needs: Optional findBySchemeCode(String), List findAllByIsActiveTrue(). PartnerRepository needs: Optional findByPartnerCode(String), List findAllByPartnerTypeAndIsActiveTrue(PartnerType), Optional findByIdAndIsActiveTrue(Long). Both extend JpaRepository. Use Spring Data method-name query derivation; no @Query annotations needed. | • Create services/config-registry/src/main/java/com/gme/pay/configregistry/repository/QrSchemeRepository.java extending JpaRepository<QrScheme, Long> @Repository • Add: Optional<QrScheme> findBySchemeCode(String schemeCode); List<QrScheme> findAllByIsActiveTrue() • Create PartnerRepository.java extending JpaRepository<Partner, Long> @Repository • Add: Optional<Partner> findByPartnerCode(String partnerCode); List<Partner> findAllByPartnerTypeAndIsActiveTrue(PartnerType type); Optional<Partner> findByIdAndIsActiveTrue(Long id) | services/config-registry/src/main/java/com/gme/pay/configregistry/repository/QrSchemeRepository.java and PartnerRepository.java | • findBySchemeCode on unknown code returns Optional.empty() • findAllByIsActiveTrue returns only active records after saving mix of active/inactive • findAllByPartnerTypeAndIsActiveTrue(OVERSEAS) returns only active OVERSEAS partners • Spring @DataJpaTest slice loads both repositories without error • Method name query derivation validated by Spring Data on startup (no typo in method names) | 25 | 3.2-T09, 3.2-T10 | BE | DAT-03
3.2-T14 | config-registry | 3.2 | 3. Data Layer & Persistence | Core entities: Scheme/Partner/Rule/Direction | 1 | Implement RuleRepository, ServiceChargeTierRepository, TreasuryRateRepository in services/config-registry | RuleRepository: findByPartnerIdAndSchemeIdAndDirection for exact business key lookup; existsByPartnerIdAndSchemeIdAndDirectionAndStatus for duplicate guard; findAllByPartnerIdAndStatus. TreasuryRateRepository: findTopByCcyPairOrderByEffectiveAtDesc (latest rate); findByCcyPairOrderByEffectiveAtDesc (full history). ServiceChargeTierRepository: findByRuleIdOrderByMinCollectionUsdAsc (tier lookup in ascending order). | • Create RuleRepository.java @Repository: Optional<Rule> findByPartnerIdAndSchemeIdAndDirection(Long, Long, Direction); boolean existsByPartnerIdAndSchemeIdAndDirectionAndStatus(Long, Long, Direction, String); List<Rule> findAllByPartnerIdAndStatus(Long, String) • Create TreasuryRateRepository.java @Repository: Optional<TreasuryRate> findTopByCcyPairOrderByEffectiveAtDesc(String); List<TreasuryRate> findByCcyPairOrderByEffectiveAtDesc(String) • Create ServiceChargeTierRepository.java @Repository: List<ServiceChargeTier> findByRuleIdOrderByMinCollectionUsdAsc(Long) | services/config-registry/src/main/java/com/gme/pay/configregistry/repository/RuleRepository.java, TreasuryRateRepository.java, ServiceChargeTierRepository.java | • findByPartnerIdAndSchemeIdAndDirection returns correct Rule when all three match; Optional.empty() when direction differs • existsByPartnerIdAndSchemeIdAndDirectionAndStatus returns true for exact match; false for status mismatch • findTopByCcyPairOrderByEffectiveAtDesc returns row with highest effective_at for 'usd_krw' • findByRuleIdOrderByMinCollectionUsdAsc returns tiers sorted ascending by min_collection_usd • All three repositories load in @DataJpaTest slice with Testcontainers postgres:16 | 25 | 3.2-T11, 3.2-T12, 3.2-T13 | BE | DAT-03
3.2-T15 | config-registry | 3.2 | 3. Data Layer & Persistence | Core entities: Scheme/Partner/Rule/Direction | 1 | Implement SameCcyShortcircuitDetector @Component in services/config-registry | Rule.isIsSameCcyShortcircuit is TRUE when collection_ccy = settle_a_ccy = settle_b_ccy = payout_ccy (e.g. GME Remit on ZeroPay: all KRW). When TRUE: USD pool is bypassed; collection_amount = target_payout + service_charge; USD margin fields NULL/0. Computed and set by service layer before persist. When TRUE, margin constraint is exempt (m_a=m_b=0 allowed). | • Create services/config-registry/src/main/java/com/gme/pay/configregistry/validation/SameCcyShortcircuitDetector.java @Component • Implement: boolean compute(String collectionCcy, String settleACcy, String settleBCcy, String payoutCcy) - returns true iff all four are equal after String.toUpperCase().trim() • Ensure null safety: any null input returns false • Wire into RuleService.createRule and RuleService.updateRule before margin validation | services/config-registry/src/main/java/com/gme/pay/configregistry/validation/SameCcyShortcircuitDetector.java | • compute('KRW','KRW','KRW','KRW') returns true • compute('KRW','KRW','USD','KRW') returns false • compute('USD','USD','USD','USD') returns true • compute('krw','KRW','KRW','KRW') returns true (case normalization) • compute(null,'KRW','KRW','KRW') returns false (null safety) | 20 | 3.2-T07 | BE | DAT-03
3.2-T16 | config-registry | 3.2 | 3. Data Layer & Persistence | Core entities: Scheme/Partner/Rule/Direction | 1 | Implement RuleMarginConstraintValidator @Component in services/config-registry | Cross-border rules (isIsSameCcyShortcircuit=FALSE) require m_a + m_b >= 0.02 (2%). Same-ccy rules (isIsSameCcyShortcircuit=TRUE) require m_a = 0 AND m_b = 0. m_a >= 0 and m_b >= 0 always. All comparisons use BigDecimal to avoid floating-point drift. Throws MarginConstraintViolationException (canonical error from libs/lib-errors) with code RULE_MARGIN_BELOW_MIN on violation. | • Create services/config-registry/src/main/java/com/gme/pay/configregistry/validation/RuleMarginConstraintValidator.java @Component • Implement validate(BigDecimal ma, BigDecimal mb, boolean isSameCcy): if isSameCcy assert ma.compareTo(ZERO)==0 AND mb.compareTo(ZERO)==0; else assert ma.add(mb).compareTo(new BigDecimal('0.02'))>=0 • Throw MarginConstraintViolationException with message 'Cross-border rule requires m_a+m_b>=2%; got: '+sum and error code RULE_MARGIN_BELOW_MIN for cross-border violation; 'Same-ccy rule requires m_a=m_b=0' for same-ccy violation • Create libs/lib-errors/src/main/java/com/gme/pay/errors/MarginConstraintViolationException.java if not present, with String errorCode field | services/config-registry/src/main/java/com/gme/pay/configregistry/validation/RuleMarginConstraintValidator.java and libs/lib-errors/.../MarginConstraintViolationException.java | • m_a=0.01, m_b=0.01, cross-border: passes (sum=0.02) • m_a=0.009, m_b=0.010, cross-border: throws MarginConstraintViolationException with code RULE_MARGIN_BELOW_MIN • m_a=0.0000, m_b=0.0000, same-ccy=true: passes • m_a=0.01, m_b=0.00, same-ccy=true: throws exception • m_a=0.015, m_b=0.015, cross-border: passes (sum=0.03) | 25 | 3.2-T15 | BE | DAT-03
3.2-T17 | config-registry | 3.2 | 3. Data Layer & Persistence | Core entities: Scheme/Partner/Rule/Direction | 1 | Implement RuleService @Service in services/config-registry - createRule and activateRule | RuleService orchestrates rule creation: (1) validate partner+scheme exist and active; (2) compute isIsSameCcyShortcircuit via SameCcyShortcircuitDetector; (3) enforce margin via RuleMarginConstraintValidator; (4) guard uniqueness via existsByPartnerIdAndSchemeIdAndDirectionAndStatus; (5) set effectiveFrom=NOW() if null; (6) persist via RuleRepository. activateRule sets status=ACTIVE and effectiveFrom=NOW() if null. Config changes apply to NEW transactions only; effectiveFrom is the guard. | • Create services/config-registry/src/main/java/com/gme/pay/configregistry/service/RuleService.java @Service @Transactional • Inject RuleRepository, PartnerRepository, QrSchemeRepository, SameCcyShortcircuitDetector, RuleMarginConstraintValidator • Implement createRule(CreateRuleCommand cmd, String actorId): fetch partner+scheme (throw ResourceNotFoundException if absent or inactive), detect short-circuit, validate margins, check uniqueness (throw DuplicateRuleException if duplicate ACTIVE rule exists), set effectiveFrom, save • Implement activateRule(Long ruleId, String actorId): load rule (throw if not found), set status=ACTIVE, set effectiveFrom if null, save • Add DuplicateRuleException extends RuntimeException in libs/lib-errors | services/config-registry/src/main/java/com/gme/pay/configregistry/service/RuleService.java | • createRule with non-existent partnerId throws ResourceNotFoundException • createRule with m_a=0.005 m_b=0.005 cross-border throws MarginConstraintViolationException • createRule with duplicate active (partner,scheme,direction) throws DuplicateRuleException • createRule with all-KRW ccys sets isIsSameCcyShortcircuit=true and margin check is skipped (m_a=m_b=0 accepted) • activateRule sets status=ACTIVE; rule persisted with effectiveFrom set | 45 | 3.2-T14, 3.2-T15, 3.2-T16 | BE | DAT-03
3.2-T18 | config-registry | 3.2 | 3. Data Layer & Persistence | Core entities: Scheme/Partner/Rule/Direction | 1 | Implement RuleService @Service - updateRule with suspension-and-reinsert pattern | Rule updates preserve history: old rule is set to status=SUSPENDED with updated_at=NOW(); a new Rule row is inserted with updated values, status=ACTIVE, effectiveFrom=NOW(). This ensures transactions in-flight use the rule snapshot at CommitTransaction time, not the new config. findActiveRuleFor must return only the new ACTIVE row after update. Both operations are in one @Transactional. | • Add updateRule(Long ruleId, UpdateRuleCommand cmd, String actorId) to RuleService • Load existing rule by id; assert status=ACTIVE (throw if already SUSPENDED) • Set existing rule status=SUSPENDED, updatedAt=NOW(), updatedBy=actorId; save (flush) • Build new Rule entity from existing + overridden fields; set status=ACTIVE, effectiveFrom=NOW(), createdBy=actorId • Re-run SameCcyShortcircuitDetector and RuleMarginConstraintValidator on the new rule before save • Save new rule; return new rule id | Additional updateRule method in services/config-registry/src/main/java/com/gme/pay/configregistry/service/RuleService.java | • After updateRule, old rule row has status=SUSPENDED • After updateRule, new rule row has status=ACTIVE and effectiveFrom=NOW() • findAllByPartnerIdAndStatus(partnerId, 'ACTIVE') returns only the new row • If new rule margins fail validation, neither suspension nor insertion is committed (transaction rollback) • Updated m_a stored with scale 6 precision in new row | 40 | 3.2-T17 | BE | DAT-03
3.2-T19 | config-registry | 3.2 | 3. Data Layer & Persistence | Core entities: Scheme/Partner/Rule/Direction | 1 | Implement SchemeController @RestController in services/config-registry | Admin REST API for qr_scheme CRUD. Base path: /v1/config/schemes. Endpoints: POST (create), GET /{schemeCode} (fetch one), GET (list all active), PATCH /{schemeCode} (update mutable fields). ROLE_ADMIN required on mutating operations (Spring Security @PreAuthorize). POST returns 201 + Location header. Duplicate schemeCode returns 409 Conflict. Invalid enum values return 400. Response DTOs from libs/lib-api-contracts. | • Create services/config-registry/src/main/java/com/gme/pay/configregistry/controller/SchemeController.java @RestController @RequestMapping('/v1/config/schemes') • POST @PreAuthorize('hasRole(ADMIN)'): create scheme, return 201 ResponseEntity with Location=/v1/config/schemes/{schemeCode} • GET /{schemeCode}: findBySchemeCode, return 200 or 404 via ResponseStatusException • GET: findAllByIsActiveTrue, return 200 list • PATCH /{schemeCode} @PreAuthorize('hasRole(ADMIN)'): update mutable fields, return 200 • Map DataIntegrityViolationException to 409 via @ExceptionHandler or global @ControllerAdvice from libs/lib-errors | services/config-registry/src/main/java/com/gme/pay/configregistry/controller/SchemeController.java | • POST with valid body returns 201 and Location header containing schemeCode • POST with duplicate schemeCode returns 409 Conflict • GET /v1/config/schemes/ZEROPAY returns 200 with payout_ccy='KRW' • GET /v1/config/schemes/UNKNOWN returns 404 • PATCH setting status='INACTIVE' persists is_active=false | 40 | 3.2-T09, 3.2-T13 | BE | DAT-03
3.2-T20 | config-registry | 3.2 | 3. Data Layer & Persistence | Core entities: Scheme/Partner/Rule/Direction | 1 | Implement PartnerController @RestController in services/config-registry | Admin REST API for partner management. Base path: /v1/config/partners. POST (onboard), GET /{partnerCode}, GET (list), PATCH /{partnerCode}. partnerType, collectionCcy, settleACcy are immutable after creation (PATCH must reject 400 if these fields appear in payload). rateQuoteTtlSeconds validated 60-1800 on create. ROLE_ADMIN on writes. PartnerValidationException mapped to 422. LOW_BALANCE fields required for OVERSEAS, forbidden for LOCAL. | • Create services/config-registry/src/main/java/com/gme/pay/configregistry/controller/PartnerController.java @RestController @RequestMapping('/v1/config/partners') • POST: validate partnerType enum, ttl range 60-1800, OVERSEAS requires lowBalanceThresholdUsd; return 201 • GET /{partnerCode}: 200 or 404 • GET: list active partners; optional ?type=LOCAL¦OVERSEAS query param • PATCH /{partnerCode}: reject 400 if partnerType/collectionCcy/settleACcy in payload; update remaining mutable fields • Map PartnerValidationException to 422; DuplicatePartnerCode to 409 | services/config-registry/src/main/java/com/gme/pay/configregistry/controller/PartnerController.java | • POST with partnerType='INVALID' returns 400 • POST with rateQuoteTtlSeconds=59 returns 400 • POST OVERSEAS with null lowBalanceThresholdUsd returns 422 • PATCH attempting to change partnerType returns 400 • GET /v1/config/partners/GME_REMIT returns 200 with partner_type='LOCAL' | 40 | 3.2-T10, 3.2-T13 | BE | DAT-03
3.2-T21 | config-registry | 3.2 | 3. Data Layer & Persistence | Core entities: Scheme/Partner/Rule/Direction | 1 | Implement RuleController @RestController in services/config-registry | Admin REST API for rule management. Base path: /v1/config/rules. POST (create), GET /{ruleId}, GET ?partnerId=&schemeCode= (list), PATCH /{ruleId} (update via suspension+reinsert), POST /{ruleId}/activate. ROLE_ADMIN on writes. MarginConstraintViolationException maps to 422 with body {error_code:'RULE_MARGIN_BELOW_MIN'}. DuplicateRuleException maps to 409. | • Create services/config-registry/src/main/java/com/gme/pay/configregistry/controller/RuleController.java @RestController @RequestMapping('/v1/config/rules') • POST: call RuleService.createRule; return 201; catch MarginConstraintViolationException -> 422; catch DuplicateRuleException -> 409 • GET /{ruleId}: 200 or 404 • GET ?partnerId=: list rules for partner • PATCH /{ruleId}: call RuleService.updateRule • POST /{ruleId}/activate: call RuleService.activateRule; 200 on success | services/config-registry/src/main/java/com/gme/pay/configregistry/controller/RuleController.java | • POST with m_a=0.005 m_b=0.005 cross-border returns 422 with error_code='RULE_MARGIN_BELOW_MIN' • POST with valid m_a=0.01 m_b=0.01 returns 201 • POST with duplicate (partner,scheme,direction) returns 409 • POST /{id}/activate returns 200 and status=ACTIVE in response • GET ?partnerId=1 returns list of rules for that partner | 40 | 3.2-T17, 3.2-T18, 3.2-T19 | BE | DAT-03
3.2-T22 | config-registry | 3.2 | 3. Data Layer & Persistence | Core entities: Scheme/Partner/Rule/Direction | 1 | Implement TreasuryRateController @RestController and manual rate entry in services/config-registry | Admin endpoint for Ops to enter FX rates manually (Phase 1). POST /v1/config/treasury-rates: body {ccy_pair:'usd_krw', rate:1380.0, effective_at:ISO8601}; rate must be > 0; source always set to MANUAL by endpoint. GET /v1/config/treasury-rates/{ccyPair}/current: returns latest rate (highest effective_at). Historical rows retained; no update/delete endpoint. ROLE_ADMIN on POST. | • Create services/config-registry/src/main/java/com/gme/pay/configregistry/controller/TreasuryRateController.java @RestController @RequestMapping('/v1/config/treasury-rates') • POST @PreAuthorize('hasRole(ADMIN)'): validate rate>0 (400 if not), set source=MANUAL, save via TreasuryRateRepository, return 201 • GET /{ccyPair}/current: call findTopByCcyPairOrderByEffectiveAtDesc; return 200 or 404 if no rate exists • GET /{ccyPair}/history: call findByCcyPairOrderByEffectiveAtDesc; return 200 list (for audit) | services/config-registry/src/main/java/com/gme/pay/configregistry/controller/TreasuryRateController.java | • POST with rate=0 returns 400 • POST with rate=1380.0 ccy_pair='usd_krw' returns 201 • GET /usd_krw/current returns the latest inserted rate (highest effective_at) • GET /usd_zzz/current with no data returns 404 • All POSTs set source='MANUAL' | 30 | 3.2-T12, 3.2-T14 | BE | DAT-03
3.2-T23 | config-registry | 3.2 | 3. Data Layer & Persistence | Core entities: Scheme/Partner/Rule/Direction | 1 | Create Flyway V016__create_config_audit_log.sql and ConfigAuditListener in services/config-registry | DAT-03 audit requirement: config changes log actor, timestamp, previous value, apply only to NEW transactions. config_audit_log table: id BIGINT PK, entity_type VARCHAR(50), entity_id BIGINT, action VARCHAR(20) CHECK(IN ('CREATE','UPDATE','ACTIVATE','DEACTIVATE','SUSPEND')), old_value JSONB nullable, new_value JSONB nullable, actor VARCHAR(120) NOT NULL, changed_at TIMESTAMPTZ NOT NULL DEFAULT NOW(), request_id VARCHAR(64). Append-only. Index on (entity_type, entity_id). | • Create services/config-registry/src/main/resources/db/migration/V016__create_config_audit_log.sql with table definition above • Create services/config-registry/src/main/java/com/gme/pay/configregistry/audit/ConfigAuditListener.java as @Component • Implement @PreUpdate and @PrePersist lifecycle methods; capture old state via snapshot in @PostLoad; serialize to JSON via Jackson ObjectMapper; insert AuditLog row within same @Transactional • Annotate Rule, QrScheme, Partner entities with @EntityListeners({AuditingEntityListener.class, ConfigAuditListener.class}) • Populate actor from Spring Security principal (SecurityContextHolder.getContext().getAuthentication()) | services/config-registry/src/main/resources/db/migration/V016__create_config_audit_log.sql and services/config-registry/src/main/java/com/gme/pay/configregistry/audit/ConfigAuditListener.java | • PATCH on Rule m_a creates audit row with entity_type='rule', action='UPDATE', old_value and new_value populated • POST (create) on QrScheme creates audit row with action='CREATE' and old_value=null • actor field populated from Spring Security principal • config_audit_log has no UPDATE or DELETE SQL in migration (append-only by convention) • V016 applies after V015 | 40 | 3.2-T17, 3.2-T19, 3.2-T21 | BE | DAT-03
3.2-T24 | config-registry | 3.2 | 3. Data Layer & Persistence | Core entities: Scheme/Partner/Rule/Direction | 1 | Create Flyway V017__create_outbox_table.sql and publish RuleActivatedEvent via transactional Outbox | STACK.md Phase 1: transactional Outbox + EventPublisher interface; Kafka wired later. Domain events for config changes allow other services to react without polling. outbox table: id BIGINT PK, aggregate_type VARCHAR(50), aggregate_id VARCHAR(64), event_type VARCHAR(100), payload JSONB, created_at TIMESTAMPTZ DEFAULT NOW(), processed_at TIMESTAMPTZ nullable, status VARCHAR(20) DEFAULT 'PENDING'. RuleActivatedEvent fields: ruleId, partnerId, schemeId, direction, effectiveFrom. Event inserted within same @Transactional as rule activation. | • Create services/config-registry/src/main/resources/db/migration/V017__create_outbox_table.sql with table above plus index on (status, created_at) • Create libs/lib-events/src/main/java/com/gme/pay/events/config/RuleActivatedEvent.java as Java record: Long ruleId, Long partnerId, Long schemeId, String direction, Instant effectiveFrom • Define EventPublisher interface in libs/lib-events: void publish(Object event); Phase 1 impl: OutboxEventPublisher @Service inserts into outbox table within caller transaction • Wire EventPublisher.publish(new RuleActivatedEvent(...)) into RuleService.activateRule and RuleService.updateRule (for the new active rule) • Verify: if rule activation rollbacks, outbox row is also rolled back (same transaction) | services/config-registry/src/main/resources/db/migration/V017__create_outbox_table.sql, libs/lib-events/src/main/java/com/gme/pay/events/config/RuleActivatedEvent.java, libs/lib-events/src/main/java/com/gme/pay/events/EventPublisher.java | • activateRule inserts both rule update AND outbox row in same transaction; rollback removes both • Outbox row has status='PENDING' and event_type='RuleActivatedEvent' on insert • RuleActivatedEvent payload contains ruleId, partnerId, schemeId, direction, effectiveFrom • libs/lib-events compiles with event class • V017 migration applies after V016 | 40 | 3.2-T17, 3.2-T23 | BE | DAT-03
3.2-T25 | config-registry | 3.2 | 3. Data Layer & Persistence | Core entities: Scheme/Partner/Rule/Direction | 1 | Seed V018__seed_zeropay_gme_remit.sql - ZeroPay scheme, GME Remit partner, usd_krw treasury rate | Baseline seed data for integration tests and local dev. ZeroPay: scheme_code='ZEROPAY', payout_ccy='KRW', supported_modes='BOTH', settlement_counterparty='KFTC', partner_b_quote_enabled=FALSE, partner_b_quote_deviation_pct=0.0100, status='ACTIVE', is_active=TRUE, created_by='SYSTEM'. scheme_country: (ZEROPAY, 'KR'). GME Remit: partner_code='GME_REMIT', partner_type='LOCAL', collection_ccy='KRW', settle_a_ccy='KRW', rate_quote_ttl_seconds=300, status='ACTIVE', created_by='SYSTEM'. treasury_rate: ccy_pair='usd_krw', rate=1380.00000000, source='MANUAL', effective_at=NOW(). Use ON CONFLICT DO NOTHING for idempotency. | • Create services/config-registry/src/main/resources/db/migration/V018__seed_zeropay_gme_remit.sql • INSERT INTO qr_scheme for ZEROPAY using ON CONFLICT(scheme_code) DO NOTHING • INSERT INTO scheme_country for (ZEROPAY id, 'KR') using ON CONFLICT(scheme_id, country_code) DO NOTHING • INSERT INTO partner for GME_REMIT using ON CONFLICT(partner_code) DO NOTHING • INSERT INTO treasury_rate for usd_krw with rate=1380.00000000 | services/config-registry/src/main/resources/db/migration/V018__seed_zeropay_gme_remit.sql | • After migration SELECT scheme_code FROM qr_scheme WHERE scheme_code='ZEROPAY' returns 1 row • SELECT country_code FROM scheme_country returns 'KR' for ZeroPay • SELECT partner_type FROM partner WHERE partner_code='GME_REMIT' returns 'LOCAL' • SELECT rate FROM treasury_rate WHERE ccy_pair='usd_krw' ORDER BY effective_at DESC LIMIT 1 returns 1380.00000000 • Re-running migration is idempotent (ON CONFLICT DO NOTHING) | 20 | 3.2-T06, 3.2-T03, 3.2-T02 | BE | DAT-03
3.2-T26 | config-registry | 3.2 | 3. Data Layer & Persistence | Core entities: Scheme/Partner/Rule/Direction | 1 | Seed V019__seed_gme_remit_domestic_rule.sql - GME Remit / ZeroPay / DOMESTIC rule | Baseline domestic rule: GME_REMIT + ZEROPAY + DOMESTIC. All KRW so is_same_ccy_shortcircuit=TRUE; m_a=0 m_b=0 (same-ccy exempt from 2% constraint); service_charge_amount=500 KRW flat; rate sources IDENTITY (cost_rate_coll=1.0, cost_rate_pay=1.0); status=ACTIVE; effective_from=NOW(). This rule is the first operational rule and baseline for integration tests. | • Create services/config-registry/src/main/resources/db/migration/V019__seed_gme_remit_domestic_rule.sql • Use subquery to resolve partner_id and scheme_id by code • INSERT INTO rule: direction='DOMESTIC', collection_ccy='KRW', settle_a_ccy='KRW', settle_b_ccy='KRW', payout_ccy='KRW', rate_coll_source='IDENTITY', rate_pay_source='IDENTITY', m_a=0.000000, m_b=0.000000, service_charge_amount=500.0000, service_charge_ccy='KRW', is_same_ccy_shortcircuit=TRUE, status='ACTIVE', effective_from=NOW(), created_by='SYSTEM' • Use ON CONFLICT(partner_id, scheme_id, direction) DO NOTHING for idempotency | services/config-registry/src/main/resources/db/migration/V019__seed_gme_remit_domestic_rule.sql | • SELECT is_same_ccy_shortcircuit FROM rule WHERE direction='DOMESTIC' returns TRUE • SELECT m_a+m_b FROM rule WHERE direction='DOMESTIC' returns 0.000000 • service_charge_amount=500.0000 and service_charge_ccy='KRW' • DB CHECK chk_rule_margin not violated (is_same_ccy_shortcircuit=TRUE exempts it) • Migration idempotent (ON CONFLICT DO NOTHING) | 20 | 3.2-T04, 3.2-T25 | BE | DAT-03
3.2-T27 | config-registry | 3.2 | 3. Data Layer & Persistence | Core entities: Scheme/Partner/Rule/Direction | 1 | Unit tests: RuleMarginConstraintValidator - boundary and same-ccy vectors (JUnit 5, no Spring) | Pure-unit tests for RuleMarginConstraintValidator. No Spring context, no DB. All BigDecimal inputs to avoid floating-point drift. Tests must cover the exact boundary (0.02), just below (0.0199), same-ccy exemption, and both individual margin fields. | • Create services/config-registry/src/test/java/com/gme/pay/configregistry/validation/RuleMarginConstraintValidatorTest.java • Instantiate RuleMarginConstraintValidator directly (new, no @SpringBootTest) • Test vectors: (1) ma=0.01 mb=0.01 cross-border -> passes; (2) ma=0.009 mb=0.010 cross-border -> throws RULE_MARGIN_BELOW_MIN; (3) ma=0.0001 mb=0.0198 cross-border -> throws (sum=0.0199); (4) ma=0.0 mb=0.0 same-ccy=true -> passes; (5) ma=0.01 mb=0.00 same-ccy=true -> throws; (6) ma=0.015 mb=0.015 cross-border -> passes (sum=0.03); (7) ma=0.02 mb=0.00 cross-border -> passes (exactly at boundary) • Use assertThrows(MarginConstraintViolationException.class, ...) for failing cases; assertDoesNotThrow for passing cases • Verify exception error code equals 'RULE_MARGIN_BELOW_MIN' in failing cross-border cases | services/config-registry/src/test/java/com/gme/pay/configregistry/validation/RuleMarginConstraintValidatorTest.java | • Vector 1 passes (sum=0.02 exactly at boundary) • Vector 2 throws MarginConstraintViolationException with code RULE_MARGIN_BELOW_MIN • Vector 3 throws (0.0001+0.0198=0.0199 < 0.02) • Vector 4 passes (same-ccy exempt) • Vector 7 passes (exactly 0.02 is allowed) • Test class has zero Spring annotations (pure unit test) | 25 | 3.2-T16 | BE | DAT-03
3.2-T28 | config-registry | 3.2 | 3. Data Layer & Persistence | Core entities: Scheme/Partner/Rule/Direction | 1 | Unit tests: SameCcyShortcircuitDetector - all four positions and case normalization (JUnit 5) | Pure-unit tests for SameCcyShortcircuitDetector.compute(). Seven vectors covering all four ccy positions, case normalization, null safety, and USD same-ccy case. No Spring context. | • Create services/config-registry/src/test/java/com/gme/pay/configregistry/validation/SameCcyShortcircuitDetectorTest.java • Instantiate SameCcyShortcircuitDetector directly • Test: (1) all KRW -> true; (2) collectionCcy=USD rest KRW -> false; (3) settleACcy=USD rest KRW -> false; (4) settleBCcy=USD rest KRW -> false; (5) payoutCcy=USD rest KRW -> false; (6) all lowercase 'krw' -> true (case normalization); (7) all USD -> true; (8) null collectionCcy -> false (null safety) • Use assertEquals for all assertions | services/config-registry/src/test/java/com/gme/pay/configregistry/validation/SameCcyShortcircuitDetectorTest.java | • All 8 test vectors produce expected boolean outcome • Case normalization test (6) passes (lowercase input returns true) • Null safety test (8) does not throw NullPointerException • All-USD test (7) returns true • Test class has no Spring annotations | 20 | 3.2-T15 | BE | DAT-03
3.2-T29 | config-registry | 3.2 | 3. Data Layer & Persistence | Core entities: Scheme/Partner/Rule/Direction | 1 | Unit tests: RuleService createRule - uniqueness guard, validation, and short-circuit (JUnit 5, Mockito) | Mockito unit tests for RuleService.createRule. Mock RuleRepository, PartnerRepository, QrSchemeRepository, SameCcyShortcircuitDetector, RuleMarginConstraintValidator. Verify: (1) success path saves rule and calls validator; (2) non-existent partner throws ResourceNotFoundException and save is not called; (3) duplicate active rule throws DuplicateRuleException and save is not called; (4) all-KRW sets isIsSameCcyShortcircuit=true on persisted entity; (5) margin validation failure propagates through createRule. | • Create services/config-registry/src/test/java/com/gme/pay/configregistry/service/RuleServiceTest.java • Use @ExtendWith(MockitoExtension.class) with @Mock and @InjectMocks • Test (1): stub repos to return valid partner+scheme, existsBy=false; assert save() called once • Test (2): stub PartnerRepository to return empty; assertThrows ResourceNotFoundException; verify save never called • Test (3): stub existsBy=true; assertThrows DuplicateRuleException; verify save never called • Test (4): stub detector to return true; assert saved rule.isIsSameCcyShortcircuit==true • Test (5): stub detector=false; stub validator to throw; assertThrows propagated; save not called | services/config-registry/src/test/java/com/gme/pay/configregistry/service/RuleServiceTest.java | • Test (1) verifies RuleRepository.save called exactly once on success path • Test (2) asserts save never called on ResourceNotFoundException • Test (3) asserts DuplicateRuleException with all three identifying fields in message • Test (4) asserts persisted entity has isIsSameCcyShortcircuit=true • Test (5) asserts MarginConstraintViolationException propagates and save not called | 35 | 3.2-T17, 3.2-T27, 3.2-T28 | BE | DAT-03
3.2-T30 | config-registry | 3.2 | 3. Data Layer & Persistence | Core entities: Scheme/Partner/Rule/Direction | 1 | @DataJpaTest integration tests: QrScheme and Partner DB constraints using Testcontainers postgres:16 | @DataJpaTest slice tests with Testcontainers postgres:16 to validate Flyway migrations V010-V012 and JPA entity mappings. Tests verify real PostgreSQL constraint enforcement (not H2 emulation). Run via @AutoConfigureTestDatabase(replace=NONE) and @DynamicPropertySource. | • Create services/config-registry/src/test/java/com/gme/pay/configregistry/entity/QrSchemeRepositoryIT.java • Annotate @DataJpaTest @AutoConfigureTestDatabase(replace=NONE) @Testcontainers • Declare @Container static PostgreSQLContainer<?> postgres = new PostgreSQLContainer<>('postgres:16') • Wire url/user/pass via @DynamicPropertySource • Test: save ZEROPAY scheme; findBySchemeCode('ZEROPAY') returns it • Test: duplicate schemeCode insert throws DataIntegrityViolationException • Test: findAllByIsActiveTrue returns only active records • Create PartnerRepositoryIT.java with same container setup: duplicate partnerCode throws; findAllByPartnerTypeAndIsActiveTrue(OVERSEAS) filters correctly | services/config-registry/src/test/java/com/gme/pay/configregistry/entity/QrSchemeRepositoryIT.java and PartnerRepositoryIT.java | • Tests run against Testcontainers postgres:16 (not H2) • Duplicate schemeCode insert throws DataIntegrityViolationException • findAllByIsActiveTrue returns only is_active=true records • findAllByPartnerTypeAndIsActiveTrue(OVERSEAS) returns only OVERSEAS active partners • Flyway migrations V010-V012 applied automatically before tests via spring.flyway.enabled=true | 40 | 3.2-T09, 3.2-T10, 3.2-T13 | BE | DAT-03
3.2-T31 | config-registry | 3.2 | 3. Data Layer & Persistence | Core entities: Scheme/Partner/Rule/Direction | 1 | @DataJpaTest integration tests: Rule and TreasuryRate DB constraints using Testcontainers postgres:16 | Testcontainers postgres:16 slice tests for Rule (V013) and TreasuryRate (V015) entities. Validates: DB-level UNIQUE(partner,scheme,direction), chk_rule_margin CHECK, direction CHECK, treasury rate > 0 CHECK, and findTopByCcyPairOrderByEffectiveAtDesc returns highest effective_at row. | • Create services/config-registry/src/test/java/com/gme/pay/configregistry/entity/RuleRepositoryIT.java with @DataJpaTest + Testcontainers postgres:16 • Test: insert valid DOMESTIC rule; findByPartnerIdAndSchemeIdAndDirection returns it • Test: duplicate (partner,scheme,direction) insert throws DataIntegrityViolationException • Test: direction='BILATERAL' insert throws ConstraintViolationException (DB CHECK) • Test: cross-border m_a=0.005 m_b=0.005 insert throws (chk_rule_margin DB CHECK) • Create TreasuryRateRepositoryIT.java: insert two usd_krw rows with different effective_at; assert findTop returns rate with higher effective_at; assert rate=0 insert throws | services/config-registry/src/test/java/com/gme/pay/configregistry/entity/RuleRepositoryIT.java and TreasuryRateRepositoryIT.java | • UNIQUE(partner_id,scheme_id,direction) test throws DataIntegrityViolationException on duplicate • direction='BILATERAL' insert rejected by DB CHECK • chk_rule_margin DB CHECK rejects m_a=0.005 m_b=0.005 cross-border • findTopByCcyPairOrderByEffectiveAtDesc returns row with highest effective_at • rate=0 treasury_rate insert throws constraint exception | 40 | 3.2-T11, 3.2-T12, 3.2-T14, 3.2-T30 | BE | DAT-03
3.2-T32 | config-registry | 3.2 | 3. Data Layer & Persistence | Core entities: Scheme/Partner/Rule/Direction | 1 | @WebMvcTest for RuleController - 422, 409, 201 HTTP contract (MockMvc, @MockBean RuleService) | @WebMvcTest slice for RuleController validating HTTP status codes and response body contracts. Mock RuleService with @MockBean. No real DB or Spring Security enforcement needed (use @WithMockUser). Validates that exception-to-HTTP mapping in @ControllerAdvice (libs/lib-errors) works correctly: MarginConstraintViolationException -> 422 with error_code='RULE_MARGIN_BELOW_MIN'; DuplicateRuleException -> 409. | • Create services/config-registry/src/test/java/com/gme/pay/configregistry/controller/RuleControllerTest.java • Annotate @WebMvcTest(RuleController.class); @MockBean RuleService ruleService • Test POST /v1/config/rules margin violation: stub ruleService.createRule to throw MarginConstraintViolationException('RULE_MARGIN_BELOW_MIN'); assert MockMvc returns 422 and JSON body contains error_code='RULE_MARGIN_BELOW_MIN' • Test POST duplicate: stub throws DuplicateRuleException; assert 409 • Test POST success: stub returns Rule DTO; assert 201 • Test POST /{id}/activate success: stub activateRule; assert 200 • Use @WithMockUser(roles='ADMIN') on mutating test methods | services/config-registry/src/test/java/com/gme/pay/configregistry/controller/RuleControllerTest.java | • MarginConstraintViolationException mapped to 422 with error_code='RULE_MARGIN_BELOW_MIN' in JSON body • DuplicateRuleException mapped to 409 • Valid POST returns 201 • Activate endpoint returns 200 • Tests use MockMvc (not Testcontainers; WebMvcTest slice) | 35 | 3.2-T21, 3.2-T27 | BE | DAT-03
3.2-T33 | config-registry | 3.2 | 3. Data Layer & Persistence | Core entities: Scheme/Partner/Rule/Direction | 1 | Define RuleQueryService interface and DTOs in libs/lib-api-contracts for cross-service use | Rate FX Engine, Payment Executor, and Smart Router need to look up active rules, treasury rates, and partner config without coupling to svc-config-registry internals. Define a RuleQueryService Java interface in libs/lib-api-contracts with: Optional<RuleDto> findActiveRule(Long partnerId, Long schemeId, Direction direction); Optional<TreasuryRateDto> findLatestTreasuryRate(String ccyPair); Optional<PartnerDto> findPartnerByCode(String partnerCode). Phase 1 implementation uses REST call + Redis cache (60s TTL, matching rate-quote TTL). Interface isolates transport from callers. | • Create libs/lib-api-contracts/src/main/java/com/gme/pay/contracts/config/RuleQueryService.java as Java interface • Create RuleDto.java record: Long id, Long partnerId, Long schemeId, Direction direction, BigDecimal ma, BigDecimal mb, boolean isSameCcyShortcircuit, BigDecimal serviceChargeAmount, String serviceChargeCcy, String status, String collectionCcy, String settleACcy, String settleBCcy, String payoutCcy • Create TreasuryRateDto.java record: String ccyPair, BigDecimal rate, Instant effectiveAt • Create PartnerDto.java record: Long id, String partnerCode, PartnerType partnerType, String collectionCcy, String settleACcy, Integer rateQuoteTtlSeconds | libs/lib-api-contracts/src/main/java/com/gme/pay/contracts/config/RuleQueryService.java, RuleDto.java, TreasuryRateDto.java, PartnerDto.java | • RuleDto includes ma, mb, isSameCcyShortcircuit, all four ccy fields, and status • TreasuryRateDto.rate is BigDecimal (not double) • PartnerDto.partnerType uses PartnerType enum from libs/lib-domain • libs/lib-api-contracts Gradle build succeeds • Interface Javadoc states Phase 1=REST+Redis-cached, Phase 2=Redis-only | 30 | 3.2-T07, 3.2-T08, 3.2-T11, 3.2-T12 | BE | DAT-03
3.2-T34 | config-registry | 3.2 | 3. Data Layer & Persistence | Core entities: Scheme/Partner/Rule/Direction | 1 | Implement Redis-cached RuleQueryServiceImpl in services/config-registry (Spring Cache + Redis TTL 60s) | Phase 1 implementation of RuleQueryService that calls local repository methods (same service, no inter-service REST yet) with Redis caching at 60s TTL. @Cacheable(cacheNames='rule-cache', key='#partnerId+":"+#schemeId+":"+#direction') on findActiveRule. @Cacheable(cacheNames='rate-cache', key='#ccyPair') on findLatestTreasuryRate. @CacheEvict on RuleService.activateRule, updateRule. On TreasuryRate POST evict rate-cache for the ccyPair. spring.cache.type=redis in application.yml with TTL=60s for rule-cache. | • Create services/config-registry/src/main/java/com/gme/pay/configregistry/service/RuleQueryServiceImpl.java implementing RuleQueryService @Service • Inject RuleRepository, TreasuryRateRepository, PartnerRepository • Annotate findActiveRule with @Cacheable(cacheNames='rule-cache', key='#partnerId+":"+#schemeId+":"+#direction.name()') • Annotate findLatestTreasuryRate with @Cacheable(cacheNames='rate-cache', key='#ccyPair') • Configure in application.yml: spring.cache.type=redis; rule-cache TTL=60s; rate-cache TTL=60s • Add @CacheEvict(cacheNames='rule-cache', key=...) to RuleService.activateRule and updateRule | services/config-registry/src/main/java/com/gme/pay/configregistry/service/RuleQueryServiceImpl.java and updated application.yml for cache config | • findActiveRule annotated @Cacheable with TTL 60s on rule-cache • findLatestTreasuryRate annotated @Cacheable on rate-cache • RuleService.activateRule calls @CacheEvict for the affected rule cache key • application.yml sets spring.cache.type=redis with TTL configuration • Testcontainers Redis integration: findActiveRule called twice for same args; second call served from cache (verify with SpyBean on repository showing 1 DB call) | 40 | 3.2-T17, 3.2-T22, 3.2-T33 | BE | DAT-03
3.2-T35 | config-registry | 3.2 | 3. Data Layer & Persistence | Core entities: Scheme/Partner/Rule/Direction | 1 | Full @SpringBootTest lifecycle integration test: create-activate rule flow in services/config-registry | End-to-end slice test using @SpringBootTest + Testcontainers postgres:16 and redis:7. Tests the full Spring context of svc-config-registry. Flow: (1) seed ZEROPAY + GME_REMIT via REST; (2) create DOMESTIC rule DRAFT; (3) activate rule via POST /{id}/activate; (4) verify DB state; (5) verify config_audit_log row; (6) verify outbox row with RuleActivatedEvent; (7) verify Redis cache evicted post-activation. | • Create services/config-registry/src/test/java/com/gme/pay/configregistry/integration/RuleLifecycleIT.java • Annotate @SpringBootTest(webEnvironment=RANDOM_PORT) @Testcontainers; postgres:16 and redis:7 containers via @DynamicPropertySource • Use TestRestTemplate to POST /v1/config/schemes (ZEROPAY) and POST /v1/config/partners (GME_REMIT) and POST /v1/config/rules (DOMESTIC all-KRW m_a=0 m_b=0) • POST /v1/config/rules/{id}/activate; assert HTTP 200 • Assert via JdbcTemplate: rule status='ACTIVE', config_audit_log has activation row, outbox has RuleActivatedEvent row with status='PENDING' • Assert Redis cache key absent after eviction (verify via RedisTemplate) | services/config-registry/src/test/java/com/gme/pay/configregistry/integration/RuleLifecycleIT.java | • Full create-activate flow: 201 on create then 200 on activate • DB rule.status='ACTIVE' after activation • config_audit_log row with entity_type='rule' and action='ACTIVATE' present • Outbox row event_type='RuleActivatedEvent' with status='PENDING' present in same DB transaction • Redis cache for rule key is evicted after activation (RedisTemplate check returns null) | 55 | 3.2-T21, 3.2-T23, 3.2-T24, 3.2-T34 | BE | DAT-03
3.3-T01 | transaction-mgmt | 3.3 | 3. Data Layer & Persistence | Transaction & event tables (8-step trail) | 1 | Flyway migration: create transaction table with rate-lock columns | Module: services/transaction-mgmt. The transaction table is the central fact table in PostgreSQL 16. Stores all 5-step USD-pool values (collection_usd DECIMAL(20,8), payout_usd_cost DECIMAL(20,8), collection_margin_usd DECIMAL(20,8), payout_margin_usd DECIMAL(20,8), send_amount DECIMAL(20,4)), derived rates (offer_rate_coll DECIMAL(20,8), cross_rate DECIMAL(20,8)), cost snapshots (cost_rate_coll DECIMAL(20,8), cost_rate_pay DECIMAL(20,8)), four ccy columns (CHAR(3)), status VARCHAR(20), txn_ref VARCHAR(64) UNIQUE (idempotency key), hub_txn_ref VARCHAR(64), rate_locked_at TIMESTAMPTZ, committed_at TIMESTAMPTZ, completed_at TIMESTAMPTZ. KRW amounts as DECIMAL(20,4) with scale 0 enforced by app. Enums as VARCHAR + CHECK constraints. All timestamps TIMESTAMPTZ UTC. Pool columns nullable (NULL for same-ccy short-circuit). Audit columns: created_at, updated_at, created_by VARCHAR(120), updated_by VARCHAR(120). | • Create services/transaction-mgmt/src/main/resources/db/migration/V10__transaction.sql • Add BIGINT PK id (GENERATED ALWAYS AS IDENTITY), all identity/FK columns: partner_id, scheme_id, rule_id, rate_quote_id, merchant_id, qr_code_id as BIGINT NOT NULL (FKs added in V14) • Add VARCHAR columns: txn_ref UNIQUE NOT NULL, hub_txn_ref NOT NULL, scheme_ref NULL, payment_mode CHECK IN (MPM,CPM), direction CHECK IN (INBOUND,OUTBOUND,DOMESTIC,HUB), status NOT NULL DEFAULT INITIATED • Add all money/rate columns per context with correct DECIMAL precision and nullability; add BOOLEAN is_same_ccy_shortcircuit DEFAULT FALSE, DECIMAL(20,4) prefunding_deducted_usd NULL • Add all TIMESTAMPTZ columns and audit columns; add CHECK on status for 9 valid values • Add six composite indexes: (partner_id,committed_at), (scheme_id,completed_at), (status,committed_at), scheme_ref, hub_txn_ref, plus partial index on (status,partner_id) WHERE status IN (INITIATED,PREFUND_DEDUCTED,SUBMITTED,UNCERTAIN) | services/transaction-mgmt/src/main/resources/db/migration/V10__transaction.sql | • Flyway migrate completes without error against a Testcontainers PostgreSQL 16 instance • INSERT of a cross-border row with all DECIMAL(20,8) pool columns populated succeeds; SELECT returns exact values with no floating-point drift • INSERT of a same-ccy row with is_same_ccy_shortcircuit=TRUE and NULL pool columns succeeds • UNIQUE constraint on txn_ref: second INSERT with same txn_ref raises constraint violation • status CHECK rejects value UNKNOWN; all 9 valid values (INITIATED,PREFUND_DEDUCTED,SUBMITTED,APPROVED,DECLINED,UNCERTAIN,FAILED,CANCELLED,REFUNDED) INSERT cleanly • All 6 indexes visible in pg_indexes | 40 |  | BE | DAT-03, PRD-07
3.3-T02 | transaction-mgmt | 3.3 | 3. Data Layer & Persistence | Transaction & event tables (8-step trail) | 1 | Flyway migration: create rate_quote table | Module: services/transaction-mgmt (shared schema with services/rate-fx). rate_quote captures the output of the rate engine at GET /v1/rates or CPM prepare time. All 5-step USD-pool fields plus derived rates and treasury FK snapshots. On CommitTransaction, values are copied to transaction and is_used flipped to TRUE. valid_until = quote_issued_at + partner.rate_quote_ttl_seconds (default 300s, range 60-1800s). Column types: DECIMAL(20,8) for all USD-pool and rate columns; DECIMAL(20,4) for send_amount/service_charge/collection_amount/target_payout. quote_ref VARCHAR(64) UNIQUE. FKs to rule, partner, qr_scheme, treasury_rate (x2 for coll and pay snapshots). | • Create services/transaction-mgmt/src/main/resources/db/migration/V9__rate_quote.sql • Add BIGINT PK id (GENERATED ALWAYS AS IDENTITY), VARCHAR(64) UNIQUE quote_ref, BIGINT FKs to rule/partner/qr_scheme (referential enforcement added in V14) • Add all pool columns (DECIMAL(20,8) nullable for same-ccy): payout_usd_cost, collection_usd, collection_margin_usd, payout_margin_usd, cost_rate_coll, cost_rate_pay • Add DECIMAL(20,4) columns: target_payout NOT NULL, send_amount NOT NULL, service_charge NOT NULL, collection_amount NOT NULL; CHAR(3) ccy columns for each • Add offer_rate_coll DECIMAL(20,8) NULL, cross_rate DECIMAL(20,8) NULL; BIGINT treasury_rate_id_coll NULL, treasury_rate_id_pay NULL; TIMESTAMPTZ quote_issued_at NOT NULL, valid_until NOT NULL; BOOLEAN is_used DEFAULT FALSE • Add index on (partner_id, valid_until) for TTL expiry queries; add index on rule_id | services/transaction-mgmt/src/main/resources/db/migration/V9__rate_quote.sql | • Flyway migration runs cleanly on Testcontainers PostgreSQL 16 • quote_ref UNIQUE constraint fires on duplicate insert • INSERT with same-ccy path: all USD-pool columns NULL, collection_amount = target_payout + service_charge value confirmed by SELECT • is_used flag updates from FALSE to TRUE via single UPDATE • DECIMAL(20,8) precision: inserting 1380.12345678 stores and retrieves without rounding | 30 |  | BE | DAT-03, PRD-07
3.3-T03 | transaction-mgmt | 3.3 | 3. Data Layer & Persistence | Transaction & event tables (8-step trail) | 1 | Flyway migration: create transaction_event append-only trail table | Module: services/transaction-mgmt. transaction_event stores the immutable 8-step event trail per transaction. Canonical steps (SEC-09 and PRD-07): 1=RATE_QUOTE_ISSUED, 2=PAYMENT_INITIATED, 3=PREFUND_DEDUCTED (OVERSEAS only; absent for LOCAL), 4=SCHEME_REQUEST_SENT, 5=SCHEME_RESPONSE_RECEIVED, 6=TRANSACTION_COMMITTED, 7=WEBHOOK_DISPATCHED, 8=WEBHOOK_DELIVERED. Columns: id BIGINT PK, txn_id BIGINT NOT NULL FK->transaction, step INT NOT NULL CHECK (1..8), event_type VARCHAR(50) NOT NULL, occurred_at TIMESTAMPTZ NOT NULL, duration_ms INT NULL (ms since previous step), detail JSONB NULL (step-specific payload e.g. {http_status:200} for step 8), created_at TIMESTAMPTZ NOT NULL DEFAULT NOW(). No updated_at - append-only and immutable. Retention >= 7 years (BOK Korean financial record-keeping). UNIQUE(txn_id, step) prevents duplicate trail entries. | • Create services/transaction-mgmt/src/main/resources/db/migration/V11__transaction_event.sql • Add columns: id BIGINT PK, txn_id BIGINT NOT NULL, step INT NOT NULL CHECK (step BETWEEN 1 AND 8), event_type VARCHAR(50) NOT NULL • Add occurred_at TIMESTAMPTZ NOT NULL, duration_ms INT NULL CHECK (duration_ms >= 0), detail JSONB NULL, created_at TIMESTAMPTZ NOT NULL DEFAULT NOW() • Add UNIQUE constraint on (txn_id, step) • Add index on (txn_id, step) for trail retrieval; add index on (txn_id, occurred_at) for chronological queries • Add table comment: append-only; no UPDATE or DELETE permitted; retention >= 7 years | services/transaction-mgmt/src/main/resources/db/migration/V11__transaction_event.sql | • Flyway migration runs cleanly on Testcontainers PostgreSQL 16 • INSERT of all 8 steps for one txn_id succeeds; SELECT ORDER BY step returns steps 1-8 • UNIQUE (txn_id, step) fires on duplicate step insert for same txn_id • step CHECK rejects value 0 and value 9 • detail JSONB column accepts {http_status: 200} payload and is queryable with ->> operator • duration_ms CHECK rejects negative value | 25 | 3.3-T01 | BE | DAT-03, PRD-07
3.3-T04 | transaction-mgmt | 3.3 | 3. Data Layer & Persistence | Transaction & event tables (8-step trail) | 1 | Flyway migration: create domain_event_outbox table (transactional Outbox) | Module: services/transaction-mgmt. STACK.md Phase 1: transactional Outbox pattern - domain events written to outbox in the SAME DB transaction as business state change; a polling publisher reads and dispatches. Kafka is NOT wired in Phase 1 - the EventPublisher interface (lib-events) abstracts the transport. Columns: id BIGINT PK, aggregate_type VARCHAR(50) NOT NULL (e.g. TRANSACTION), aggregate_id VARCHAR(64) NOT NULL (txn_ref), event_type VARCHAR(100) NOT NULL (e.g. TransactionCommittedEvent), payload JSONB NOT NULL, status VARCHAR(20) NOT NULL DEFAULT PENDING CHECK IN (PENDING,DISPATCHED,FAILED), created_at TIMESTAMPTZ NOT NULL DEFAULT NOW(), dispatched_at TIMESTAMPTZ NULL, retry_count INT NOT NULL DEFAULT 0, last_error TEXT NULL. | • Create services/transaction-mgmt/src/main/resources/db/migration/V12__domain_event_outbox.sql • Define all columns with types, NOT NULL constraints, CHECK on status IN (PENDING,DISPATCHED,FAILED) • Add index on (status, created_at) for outbox poller query: SELECT ... WHERE status=PENDING ORDER BY created_at LIMIT 50 • Add index on (aggregate_type, aggregate_id) for per-aggregate event lookup • Add table comment: Phase 1 outbox-only; Kafka transport wired in integration phase via EventPublisher interface in lib-events | services/transaction-mgmt/src/main/resources/db/migration/V12__domain_event_outbox.sql | • Flyway migration runs cleanly on Testcontainers PostgreSQL 16 • INSERT of a PENDING event succeeds; SELECT WHERE status=PENDING returns it • UPDATE status to DISPATCHED + set dispatched_at: row visible with status=DISPATCHED • status CHECK rejects value UNKNOWN • payload JSONB column accepts and round-trips a TransactionCommittedEvent JSON object • Index on (status,created_at) appears in pg_indexes | 20 | 3.3-T01 | BE | DAT-03, PRD-07
3.3-T05 | transaction-mgmt | 3.3 | 3. Data Layer & Persistence | Transaction & event tables (8-step trail) | 1 | Flyway migration: FK wiring for transaction, rate_quote, transaction_event | Module: services/transaction-mgmt. Separate migration adds FK constraints after all tables exist: transaction.rate_quote_id->rate_quote(id), transaction.partner_id->partner(id), transaction.scheme_id->qr_scheme(id), transaction.rule_id->rule(id), transaction_event.txn_id->transaction(id). All ON DELETE RESTRICT. Also adds the CHECK constraint on transaction.status covering all 9 values, and confirms UNIQUE(txn_id,step) on transaction_event. Separate migration keeps V9-V12 clean and avoids ordering dependencies. | • Create services/transaction-mgmt/src/main/resources/db/migration/V13__transaction_fk_constraints.sql • Add ALTER TABLE transaction ADD CONSTRAINT fk_txn_rate_quote FOREIGN KEY (rate_quote_id) REFERENCES rate_quote(id) ON DELETE RESTRICT • Add FKs for partner_id, scheme_id, rule_id referencing their respective tables ON DELETE RESTRICT • Add ALTER TABLE transaction_event ADD CONSTRAINT fk_txnevent_txn FOREIGN KEY (txn_id) REFERENCES transaction(id) ON DELETE RESTRICT • Verify UNIQUE(txn_id,step) on transaction_event exists; add if absent • Verify all 9 status CHECK values present; add or replace if absent | services/transaction-mgmt/src/main/resources/db/migration/V13__transaction_fk_constraints.sql | • Flyway V13 runs cleanly in sequence after V9-V12 on Testcontainers PostgreSQL 16 • DELETE from transaction with existing transaction_event rows raises FK violation • INSERT transaction_event with txn_id not in transaction raises FK violation • pg_constraint shows fk_txn_rate_quote and fk_txnevent_txn constraints • status CHECK rejects INVALID_STATUS; all 9 valid statuses insert cleanly | 20 | 3.3-T04, 3.3-T03, 3.3-T02 | BE | DAT-03, PRD-07
3.3-T06 | transaction-mgmt | 3.3 | 3. Data Layer & Persistence | Transaction & event tables (8-step trail) | 1 | Define TransactionCommittedEvent and PrefundDeductedEvent in lib-events | Module: lib-events (shared library). Domain event schemas must be defined now so outbox payloads are structured from day one. Two events for WBS 3.3: (1) TransactionCommittedEvent - fields: txn_ref String, partner_id Long, collection_usd BigDecimal, payout_usd_cost BigDecimal, collection_margin_usd BigDecimal, payout_margin_usd BigDecimal, send_amount BigDecimal, service_charge BigDecimal, collection_amount BigDecimal, offer_rate_coll BigDecimal, cross_rate BigDecimal, is_same_ccy_shortcircuit boolean, committed_at Instant. (2) PrefundDeductedEvent - fields: txn_ref String, partner_id Long, deducted_amount_usd BigDecimal, balance_after_usd BigDecimal, deducted_at Instant. Both as Java 21 records. All monetary fields as BigDecimal (never double). DomainEvent marker interface with aggregateType(), aggregateId(), eventType(), occurredAt(). | • Create lib-events/src/main/java/com/gme/pay/events/DomainEvent.java interface with String aggregateType(), String aggregateId(), String eventType(), Instant occurredAt() • Create lib-events/src/main/java/com/gme/pay/events/transaction/TransactionCommittedEvent.java as Java record implementing DomainEvent; aggregateType()=TRANSACTION, aggregateId()=txnRef, eventType()=TransactionCommittedEvent • Create lib-events/src/main/java/com/gme/pay/events/transaction/PrefundDeductedEvent.java as Java record implementing DomainEvent; same pattern • Add @JsonProperty annotations ensuring snake_case serialisation matching DB column names (txn_ref, collection_usd etc.) • Add @JsonSerialize(using=ToStringSerializer.class) on BigDecimal fields to prevent scientific notation • Add unit test in lib-events verifying round-trip Jackson serialisation of both events | lib-events/src/main/java/com/gme/pay/events/transaction/TransactionCommittedEvent.java and PrefundDeductedEvent.java | • TransactionCommittedEvent serialises to JSON with snake_case keys matching DB column names • PrefundDeductedEvent.aggregateType() returns TRANSACTION; aggregateId() returns txn_ref value • BigDecimal 1380.12345678 serialises as 1380.12345678 (no scientific notation) • Round-trip test: serialize then deserialize returns equal record • Unit test passes with ./gradlew :lib-events:test | 30 |  | BE | DAT-03, PRD-07
3.3-T07 | transaction-mgmt | 3.3 | 3. Data Layer & Persistence | Transaction & event tables (8-step trail) | 1 | Implement EventPublisher interface and OutboxEventPublisher @Service in lib-events | Module: lib-events. STACK.md: Phase 1 = transactional Outbox + polling publisher; Kafka wired in integration phase behind the same interface. EventPublisher interface: void publish(DomainEvent event). OutboxEventPublisher: @Service implementing EventPublisher; annotated @Transactional(propagation=MANDATORY) so it ONLY runs inside an existing caller transaction (guarantees atomicity with business write). Inserts one row into domain_event_outbox per call: aggregate_type, aggregate_id, event_type, payload=serialized JSON, status=PENDING, created_at=NOW(). Uses OutboxEvent @Entity and OutboxEventRepository extends JpaRepository<OutboxEvent,Long>. No Kafka dependency in this module. | • Create lib-events/src/main/java/com/gme/pay/events/EventPublisher.java interface with void publish(DomainEvent event) • Create lib-events/src/main/java/com/gme/pay/events/outbox/OutboxEvent.java @Entity mapped to domain_event_outbox table with all columns • Create lib-events/src/main/java/com/gme/pay/events/outbox/OutboxEventRepository.java extending JpaRepository<OutboxEvent,Long> with List<OutboxEvent> findTop50ByStatusOrderByCreatedAt(String status) • Create lib-events/src/main/java/com/gme/pay/events/outbox/OutboxEventPublisher.java @Service implementing EventPublisher with @Transactional(propagation=MANDATORY) • In publish(): serialize event payload via ObjectMapper, build OutboxEvent entity, save via repository • Add @ConditionalOnMissingBean so services can override with a Kafka publisher in Phase 2 | lib-events/src/main/java/com/gme/pay/events/outbox/OutboxEventPublisher.java | • publish() called outside a @Transactional context throws TransactionRequiredException (MANDATORY propagation enforced) • publish() called inside a transaction inserts one row with status=PENDING into domain_event_outbox • If enclosing transaction rolls back, the outbox row is also absent (atomicity via Testcontainers Postgres) • event_type column contains TransactionCommittedEvent for a TransactionCommittedEvent input • payload column contains valid JSON round-trippable to original record | 40 | 3.3-T06, 3.3-T04 | BE | DAT-03, PRD-07
3.3-T08 | transaction-mgmt | 3.3 | 3. Data Layer & Persistence | Transaction & event tables (8-step trail) | 1 | Implement OutboxPoller @Scheduled component in services/transaction-mgmt | Module: services/transaction-mgmt. OutboxPoller polls domain_event_outbox for PENDING rows and dispatches them via EventPublisher. Spring @Scheduled(fixedDelayString=${outbox.poll.interval-ms:5000}). Polling uses SELECT ... FOR UPDATE SKIP LOCKED to prevent double-dispatch across multiple pod replicas. Batch size: 50 rows per poll. On success: UPDATE status=DISPATCHED, dispatched_at=NOW(). On failure: increment retry_count; if retry_count >= 3 set status=FAILED, last_error=exception message. Phase 1 dispatch = log event + mark DISPATCHED (no Kafka). @ConditionalOnProperty(name=outbox.poller.enabled, havingValue=true, matchIfMissing=true) allows disabling in tests. | • Create services/transaction-mgmt/src/main/java/com/gme/pay/txnmgmt/outbox/OutboxPoller.java annotated @Component @ConditionalOnProperty • Inject OutboxEventRepository and EventPublisher • Implement @Scheduled pollAndDispatch(): open new @Transactional(propagation=REQUIRES_NEW), load up to 50 PENDING rows with native query using FOR UPDATE SKIP LOCKED • For each row: attempt EventPublisher dispatch; on success mark DISPATCHED + set dispatched_at; on exception increment retry_count, if >= 3 mark FAILED • Log each dispatched event at INFO with aggregate_type, aggregate_id, event_type using SLF4J MDC • Annotate pollAndDispatch with @Transactional(propagation=REQUIRES_NEW) so each poll batch is its own transaction | services/transaction-mgmt/src/main/java/com/gme/pay/txnmgmt/outbox/OutboxPoller.java | • Two concurrent poller instances do not double-dispatch the same row (SKIP LOCKED test: start 2 threads simultaneously against Testcontainers Postgres, verify each PENDING row dispatched exactly once) • Row transitions from PENDING to DISPATCHED with dispatched_at set after one poll cycle • Row with dispatch throwing exception 3 times transitions to FAILED with last_error populated • Setting outbox.poller.enabled=false in test application.yml prevents @Scheduled from running • pollAndDispatch() REQUIRES_NEW: DISPATCHED status commits even when called from a method with no surrounding transaction | 45 | 3.3-T07 | BE | DAT-03, PRD-07
3.3-T09 | transaction-mgmt | 3.3 | 3. Data Layer & Persistence | Transaction & event tables (8-step trail) | 1 | Implement Transaction and TransactionEvent @Entity classes with Spring Data JPA | Module: services/transaction-mgmt. Spring Data JPA entities for the transaction and transaction_event tables in package com.gme.pay.txnmgmt.domain. Transaction @Entity: maps all columns from V10 migration. All money fields as BigDecimal. @Column(updatable=false) on all 13 rate-lock columns (collection_usd, payout_usd_cost, collection_margin_usd, payout_margin_usd, send_amount, service_charge, collection_amount, offer_rate_coll, cross_rate, cost_rate_coll, cost_rate_pay, quote_issued_at, valid_until) to prevent accidental JPA UPDATE. TransactionEvent @Entity: maps V11 columns; detail column mapped as String via @Type or @Column(columnDefinition=jsonb). | • Create services/transaction-mgmt/src/main/java/com/gme/pay/txnmgmt/domain/Transaction.java @Entity @Table(name=transaction) with all column mappings • Add @Column(updatable=false) to all 13 rate-lock columns • Create services/transaction-mgmt/src/main/java/com/gme/pay/txnmgmt/domain/TransactionEvent.java @Entity @Table(name=transaction_event) with txn_id as @Column(name=txn_id), step, event_type, occurred_at, duration_ms, detail as String • Create TransactionRepository extends JpaRepository<Transaction,Long> with Optional<Transaction> findByTxnRef(String txnRef), Page<Transaction> findByPartnerIdAndStatusAndCommittedAtBetween(...) • Create TransactionEventRepository extends JpaRepository<TransactionEvent,Long> with List<TransactionEvent> findByTxnIdOrderByStep(Long txnId) • Verify @GeneratedValue(strategy=IDENTITY) on id fields of both entities | services/transaction-mgmt/src/main/java/com/gme/pay/txnmgmt/domain/Transaction.java, TransactionEvent.java, TransactionRepository.java, TransactionEventRepository.java | • Save a Transaction then reload by txn_ref: all BigDecimal fields equal saved values (BigDecimal.compareTo = 0, no floating-point drift) • Attempt Spring Data save with modified collection_usd on a loaded entity raises exception (updatable=false) • findByTxnIdOrderByStep returns events in ascending step order for an 8-event fixture • @DataJpaTest slice with Testcontainers PostgreSQL 16 passes all repository tests • detail column round-trips arbitrary JSON string without truncation | 40 | 3.3-T05 | BE | DAT-03, PRD-07
3.3-T10 | transaction-mgmt | 3.3 | 3. Data Layer & Persistence | Transaction & event tables (8-step trail) | 1 | Implement TransactionService: issue rate quote and record step 1 event | Module: services/transaction-mgmt. @Service TransactionService. issueRateQuote() persists a rate_quote row and appends transaction_event step=1 RATE_QUOTE_ISSUED. Two sub-steps must share one @Transactional. detail JSONB for step 1: {quote_ref, offer_rate_coll, valid_until, collection_usd, send_amount}. valid_until = quote_issued_at + rule.rate_quote_ttl_seconds (default 300). For same-ccy short-circuit (is_same_ccy_shortcircuit=TRUE): USD-pool columns NULL, offer_rate_coll NULL, collection_amount = target_payout + service_charge. Return RateQuoteResponse (from lib-api-contracts) with all quote fields. | • Create services/transaction-mgmt/src/main/java/com/gme/pay/txnmgmt/service/TransactionService.java @Service • Implement RateQuoteResponse issueRateQuote(IssueRateQuoteRequest req): persist RateQuote entity, build TransactionEvent with step=1, event_type=RATE_QUOTE_ISSUED, detail JSON, occurred_at=NOW(), duration_ms=NULL • Wrap in @Transactional(isolation=READ_COMMITTED) • Handle same-ccy short-circuit: if req.isSameCcyShortcircuit(), set all USD-pool fields to null on RateQuote entity • Validate target_payout > 0 and service_charge >= 0; throw ValidationException with lib-errors error code if violated • Return RateQuoteResponse mapping all quote fields | TransactionService.issueRateQuote() in services/transaction-mgmt/src/main/java/com/gme/pay/txnmgmt/service/TransactionService.java | • issueRateQuote with cross-border request: rate_quote row created, step=1 event row created, both in same DB transaction • issueRateQuote with same-ccy request: collection_usd IS NULL in persisted rate_quote, collection_amount = target_payout + service_charge • target_payout = 0 throws ValidationException before any DB write • quote_ref is unique UUID; two calls produce different quote_refs • @DataJpaTest + Testcontainers: both rate_quote and transaction_event rows committed atomically | 40 | 3.3-T09 | BE | DAT-03, PRD-07
3.3-T11 | transaction-mgmt | 3.3 | 3. Data Layer & Persistence | Transaction & event tables (8-step trail) | 1 | Implement TransactionService: initiate transaction and record step 2 event | Module: services/transaction-mgmt. initiateTransaction() is called when partner calls POST /v1/payments. Creates transaction row with status=INITIATED linking to the rate_quote, appends step=2 PAYMENT_INITIATED event. Validates: (1) rate_quote.valid_until > NOW(), otherwise throw QuoteExpiredException (lib-errors code QUOTE_EXPIRED); (2) rate_quote.is_used = FALSE, otherwise throw QuoteAlreadyUsedException. duration_ms for step 2 = occurred_at(step2) - occurred_at(step1) in milliseconds. detail JSONB: {txn_ref, partner_id, payment_mode, direction}. Returns txn_ref. | • Add String initiateTransaction(InitiateTransactionRequest req) to TransactionService • Load rate_quote by quote_ref; validate valid_until > Instant.now(); throw QuoteExpiredException if expired • Validate is_used = FALSE; throw QuoteAlreadyUsedException if already used • Create Transaction entity: copy partner_id, scheme_id, rule_id, payment_mode, direction, is_same_ccy_shortcircuit from request/rule; set status=INITIATED, txn_ref=UUID • Persist Transaction; compute duration_ms from step1.occurred_at to NOW(); persist TransactionEvent step=2 PAYMENT_INITIATED with duration_ms and detail JSON • All in @Transactional(isolation=READ_COMMITTED); return txn_ref | TransactionService.initiateTransaction() method | • Expired quote (valid_until = 1 second ago) throws QuoteExpiredException; no transaction row created • is_used=TRUE quote throws QuoteAlreadyUsedException before DB write • Successful call: transaction row status=INITIATED, step=2 event with duration_ms >= 0 • Duplicate txn_ref (same idempotency key called twice) raises DataIntegrityViolationException on UNIQUE constraint • @DataJpaTest + Testcontainers: both transaction and transaction_event rows committed atomically | 40 | 3.3-T10 | BE | DAT-03, PRD-07
3.3-T12 | transaction-mgmt | 3.3 | 3. Data Layer & Persistence | Transaction & event tables (8-step trail) | 1 | Implement TransactionService: prefund deduction (step 3) with SELECT FOR UPDATE | Module: services/transaction-mgmt. deductPrefunding() is OVERSEAS-only (skip for LOCAL partners). Must atomically deduct collection_usd from prefunding_account.balance using SELECT ... FOR UPDATE (no app-level locking per DAT-03 and STACK.md). If balance < collection_usd: throw InsufficientPrefundingException (lib-errors code INSUFFICIENT_PREFUNDING) and do NOT call the scheme. Flow: lock prefunding_account row FOR UPDATE, verify balance >= collection_usd, deduct, insert prefunding_ledger_entry (entry_type=DEBIT_PAYMENT, amount=collection_usd, balance_after=new balance), update transaction.status=PREFUND_DEDUCTED, insert step=3 PREFUND_DEDUCTED event with detail={deducted_usd, balance_after_usd}, publish PrefundDeductedEvent to outbox. All in one @Transactional. | • Add deductPrefunding(String txnRef, Long partnerId, BigDecimal collectionUsd) to TransactionService • Use @Lock(LockModeType.PESSIMISTIC_WRITE) on PrefundingAccountRepository.findByPartnerId() or native query SELECT ... FROM prefunding_account WHERE partner_id=? FOR UPDATE • Check account.balance.compareTo(collectionUsd) >= 0; if not throw InsufficientPrefundingException with current balance and required amount • Deduct: account.setBalance(account.getBalance().subtract(collectionUsd)); save; insert PrefundingLedgerEntry DEBIT_PAYMENT with balance_after • Update transaction status to PREFUND_DEDUCTED; insert TransactionEvent step=3 with detail JSON • Call eventPublisher.publish(new PrefundDeductedEvent(...)) within same @Transactional; wrap all in @Transactional(isolation=READ_COMMITTED) | TransactionService.deductPrefunding() method | • Concurrent deduction test (two @Async threads, both deductPrefunding for same partner with balance covering only one): exactly one succeeds, other throws InsufficientPrefundingException; Testcontainers Postgres required • InsufficientPrefundingException thrown when balance=999.9900 and required=1000.0000 • prefunding_ledger_entry.balance_after = account.balance after successful deduction (to 4 decimal places) • PrefundDeductedEvent row in domain_event_outbox with status=PENDING within same transaction • Full rollback test: force RuntimeException after deduction, verify balance unchanged and no ledger entry | 50 | 3.3-T11, 3.3-T07 | BE | DAT-03, PRD-07
3.3-T13 | transaction-mgmt | 3.3 | 3. Data Layer & Persistence | Transaction & event tables (8-step trail) | 1 | Implement TransactionService: commit transaction with pool identity check (step 6) | Module: services/transaction-mgmt. commitTransaction() copies all USD-pool values and derived rates from rate_quote to transaction, sets rate_locked_at=committed_at=NOW(), then verifies the pool identity invariant before persisting. Pool identity: collection_usd - collection_margin_usd - payout_margin_usd = payout_usd_cost within tolerance 0.01 USD. Check: diff.abs().compareTo(new BigDecimal(0.01)) <= 0. If check fails: throw PoolIdentityViolationException (lib-errors code POOL_IDENTITY_FAILURE); do NOT commit. For same-ccy short-circuit (is_same_ccy_shortcircuit=TRUE): skip pool check; collection_amount = target_payout + service_charge. Mark rate_quote.is_used=TRUE. Insert step=6 TRANSACTION_COMMITTED event with detail containing all 8 locked rate fields. Publish TransactionCommittedEvent to outbox. | • Add commitTransaction(String txnRef) to TransactionService • Load transaction by txn_ref and linked rate_quote; validate rate_quote.valid_until > NOW() • If NOT is_same_ccy_shortcircuit: compute diff = collection_usd.subtract(collection_margin_usd).subtract(payout_margin_usd).subtract(payout_usd_cost); if diff.abs() > 0.01 throw PoolIdentityViolationException • Copy all 13 rate-lock fields from rate_quote to transaction; set rate_locked_at=NOW(), committed_at=NOW() • Persist transaction; mark rate_quote.is_used=TRUE; insert TransactionEvent step=6 TRANSACTION_COMMITTED with detail JSON of all locked rate fields • Call eventPublisher.publish(new TransactionCommittedEvent(...)) within same @Transactional | TransactionService.commitTransaction() method | • Pool identity violation (diff=0.02 USD): PoolIdentityViolationException thrown, no transaction update committed, is_used stays FALSE • Pool identity passes (diff=0.005 USD, within 0.01 tolerance): transaction committed, rate_locked_at set, all 13 rate-lock fields populated • After commitTransaction, JPA attempt to update collection_usd raises exception (@Column updatable=false) • Same-ccy path: is_same_ccy_shortcircuit=TRUE, pool columns NULL, collection_amount = target_payout + service_charge after commit • TransactionCommittedEvent row in domain_event_outbox with PENDING status and correct payload | 45 | 3.3-T12, 3.3-T07 | BE | DAT-03, PRD-07
3.3-T14 | transaction-mgmt | 3.3 | 3. Data Layer & Persistence | Transaction & event tables (8-step trail) | 1 | Implement TransactionService.recordEvent() for steps 4, 5, 7, 8 | Module: services/transaction-mgmt. recordEvent() is called by Payment Executor (steps 4,5) and Notification service (steps 7,8) to append trail entries. Signature: void recordEvent(String txnRef, int step, String eventType, Integer durationMs, Map<String,Object> detail). Validates: step in 1-8 (throw InvalidEventStepException), no existing row for (txn_id,step) (throw DuplicateEventStepException - UNIQUE constraint also catches at DB). For step 5: if detail contains key scheme_ref, update transaction.scheme_ref from detail value. For step 8 with WEBHOOK_FAILED (event_type=WEBHOOK_DELIVERED, detail.failed=true): record as step 8 with failure detail. occurred_at=NOW() server-side. | • Add void recordEvent(String txnRef, int step, String eventType, Integer durationMs, Map<String,Object> detail) to TransactionService • Validate step between 1 and 8; throw InvalidEventStepException with step value if out of range • Check TransactionEventRepository.existsByTxnIdAndStep(txnId, step); throw DuplicateEventStepException if true • Build TransactionEvent entity, serialize detail map to JSON via ObjectMapper, set occurred_at=Instant.now() • If step=5 and detail.containsKey(scheme_ref): load transaction, set scheme_ref, save • Annotate with @Transactional(propagation=REQUIRED) | TransactionService.recordEvent() method | • recordEvent step=4 with detail={endpoint:ZeroPay}: persists row, SELECT by txn_id+step=4 returns correct detail JSON via ->> operator • recordEvent step=9 throws InvalidEventStepException without any DB insert • recordEvent called twice for same txn+step=4: second call throws DuplicateEventStepException • transaction.scheme_ref updated when step=5 detail contains scheme_ref=ZP20260601001 • duration_ms NULL accepted (step 1 has no previous step); duration_ms=-1 rejected by DB CHECK constraint | 30 | 3.3-T09 | BE | DAT-03, PRD-07
3.3-T15 | transaction-mgmt | 3.3 | 3. Data Layer & Persistence | Transaction & event tables (8-step trail) | 1 | Implement TransactionService.getEventTrail() and TransactionEventDto in lib-api-contracts | Module: services/transaction-mgmt and lib-api-contracts. getEventTrail() returns the ordered 8-step trail for Admin UI and partner-facing views. Signature: List<TransactionEventDto> getEventTrail(String txnRef). Loads all transaction_event rows ordered by step; absent steps are gaps (do not fabricate). For LOCAL partners step 3 will be absent - return list without it. TransactionEventDto is a Java record in lib-api-contracts: Long id, int step, String eventType, Instant occurredAt, Integer durationMs, String detailJson. Also add getTransactionSummary(String txnRef) returning TransactionSummaryDto with all locked rate fields for Admin transaction detail view. | • Create lib-api-contracts/src/main/java/com/gme/pay/contracts/transaction/TransactionEventDto.java as Java record • Create lib-api-contracts/src/main/java/com/gme/pay/contracts/transaction/TransactionSummaryDto.java as Java record with all summary and rate-lock fields • Add List<TransactionEventDto> getEventTrail(String txnRef) to TransactionService: load transaction by txnRef (throw TransactionNotFoundException if absent), load events via findByTxnIdOrderByStep, map to DTOs • Add TransactionSummaryDto getTransactionSummary(String txnRef): load transaction, map all fields to DTO • Add @Transactional(readOnly=true) on both read methods • Return empty list (not null) if transaction exists but has no events yet | lib-api-contracts/src/main/java/com/gme/pay/contracts/transaction/TransactionEventDto.java and TransactionService read methods | • getEventTrail for OVERSEAS transaction with steps 1-8: returns list size=8, steps in order 1..8 • getEventTrail for LOCAL transaction missing step 3: returns list size=7, no element with step=3 • getEventTrail for unknown txnRef throws TransactionNotFoundException • Step 6 dto.detailJson contains collection_usd and offer_rate_coll keys • getEventTrail returns empty list (not null) for transaction with zero events | 30 | 3.3-T14 | BE | DAT-03, PRD-07
3.3-T16 | transaction-mgmt | 3.3 | 3. Data Layer & Persistence | Transaction & event tables (8-step trail) | 1 | Expose TransactionInternalController @RestController in services/transaction-mgmt | Module: services/transaction-mgmt. Internal REST API consumed by Payment Executor and Notification services (not partner-facing). Endpoints: POST /internal/v1/transactions/quote (issue quote + step 1), POST /internal/v1/transactions (initiate + step 2), POST /internal/v1/transactions/{txnRef}/prefund-deduct (step 3), POST /internal/v1/transactions/{txnRef}/commit (step 6), POST /internal/v1/transactions/{txnRef}/events (steps 4,5,7,8), GET /internal/v1/transactions/{txnRef}/trail (get event trail). Spring Security: @PreAuthorize(hasRole(INTERNAL_SERVICE)) on all endpoints. Request/response DTOs from lib-api-contracts. lib-errors ErrorResponse on failures. | • Create services/transaction-mgmt/src/main/java/com/gme/pay/txnmgmt/api/TransactionInternalController.java @RestController @RequestMapping(/internal/v1/transactions) • Implement POST /quote, POST /, POST /{txnRef}/prefund-deduct, POST /{txnRef}/commit each delegating to TransactionService; return 201 for creates, 200 for updates • Implement POST /{txnRef}/events delegating to recordEvent with request body fields • Implement GET /{txnRef}/trail delegating to getEventTrail, returning List<TransactionEventDto> • Add @Valid on all request bodies; @ExceptionHandler methods converting QuoteExpiredException->422, TransactionNotFoundException->404, DuplicateEventStepException->409, PoolIdentityViolationException->422, InsufficientPrefundingException->422 using lib-errors error codes • Add SLF4J MDC with txn_ref on all mutating endpoints; @PreAuthorize(hasRole(INTERNAL_SERVICE)) on class | services/transaction-mgmt/src/main/java/com/gme/pay/txnmgmt/api/TransactionInternalController.java | • POST /quote returns 201 with quote_ref and valid_until in response body • POST /{txnRef}/commit returns 200 with collection_usd, offer_rate_coll, rate_locked_at in response • POST /{txnRef}/prefund-deduct with insufficient balance returns 422 with error code INSUFFICIENT_PREFUNDING • POST /{txnRef}/events with step=9 returns 400 with INVALID_EVENT_STEP error code • Unauthenticated request returns 401 (WebMvcTest with Spring Security test) • GET /{txnRef}/trail returns 200 with ordered list of event DTOs | 45 | 3.3-T15 | BE | DAT-03, PRD-07
3.3-T17 | transaction-mgmt | 3.3 | 3. Data Layer & Persistence | Transaction & event tables (8-step trail) | 1 | Unit test: pool identity invariant and same-currency short-circuit vectors | Module: services/transaction-mgmt. Dedicated JUnit 5 test class for the mathematical invariants enforced at commitTransaction(). Uses @DataJpaTest + Testcontainers PostgreSQL 16. Test vectors use exact BigDecimal values. Vector A (cross-border pass): target_payout=45000.0000 KRW, cost_rate_pay=1380.00000000 (usd_krw), m_a=0.010000, m_b=0.015000; expected payout_usd_cost=32.608695..., collection_usd=33.877490..., pool identity diff < 0.01. Vector B (pool identity fail): manually corrupt collection_usd to create diff=0.02. Vector C (same-ccy short-circuit): target_payout=50000.0000, service_charge=500.0000, is_same_ccy=TRUE; expected collection_amount=50500.0000, pool cols NULL. | • Create services/transaction-mgmt/src/test/java/com/gme/pay/txnmgmt/service/TransactionServicePoolIdentityTest.java • Seed DB with partner, scheme, rule (m_a=0.01, m_b=0.015), prefunding_account, treasury_rate usd_krw=1380 using @BeforeEach • Test vector A: issue quote with correct values, initiate, deduct, commit; assert committed_at set, all 13 rate-lock fields non-null, offer_rate_coll = send_amount / (collection_usd - collection_margin_usd) • Test vector B: issue quote with corrupted collection_usd (diff=0.02), call commitTransaction, assert PoolIdentityViolationException thrown and transaction row not committed • Test vector C: use same-ccy rule, issue quote, commit; assert collection_amount=50500.0000 and collection_usd IS NULL in DB • Use @Testcontainers @Container PostgreSQLContainer<> for real PostgreSQL 16 | services/transaction-mgmt/src/test/java/com/gme/pay/txnmgmt/service/TransactionServicePoolIdentityTest.java | • Vector A: committed_at non-null, offer_rate_coll.subtract(send_amount.divide(collection_usd.subtract(collection_margin_usd), 8, HALF_UP)).abs() < 0.000001 • Vector B: PoolIdentityViolationException thrown, SELECT transaction WHERE txn_ref=... shows no committed_at change • Vector C: collection_amount=50500.0000 in persisted row, collection_usd IS NULL • All 3 test vectors pass with ./gradlew :services:transaction-mgmt:test • No floating-point types used: all assertions via BigDecimal.compareTo() | 50 | 3.3-T13 | BE | DAT-03, PRD-07
3.3-T18 | transaction-mgmt | 3.3 | 3. Data Layer & Persistence | Transaction & event tables (8-step trail) | 1 | Unit test: transactional outbox atomicity with Testcontainers PostgreSQL | Module: services/transaction-mgmt. JUnit 5 tests verifying outbox events are written atomically with business state changes and that the OutboxPoller dispatches correctly. Uses @SpringBootTest + Testcontainers PostgreSQL 16, no Kafka. Scenarios: (A) commitTransaction publishes TransactionCommittedEvent to outbox in same transaction, (B) forced PoolIdentityViolationException rolls back both business state and outbox row, (C) OutboxPoller moves row PENDING->DISPATCHED, (D) failed dispatch after 3 retries sets FAILED. | • Create services/transaction-mgmt/src/test/java/com/gme/pay/txnmgmt/outbox/OutboxAtomicityTest.java • Test A: call commitTransaction with valid vector, query domain_event_outbox: exactly 1 row status=PENDING with event_type=TransactionCommittedEvent • Test B: call commitTransaction with pool identity violation, query domain_event_outbox: exactly 0 rows (rollback atomicity) • Test C: insert a PENDING outbox row manually, invoke OutboxPoller.pollAndDispatch(), query row: status=DISPATCHED and dispatched_at IS NOT NULL • Test D: configure mock dispatch to always throw; call pollAndDispatch 3 times; verify status=FAILED and retry_count=3 • No Kafka container needed; disable outbox.poller.enabled for tests A and B to prevent background interference | services/transaction-mgmt/src/test/java/com/gme/pay/txnmgmt/outbox/OutboxAtomicityTest.java | • Test A: exactly 1 outbox row with correct event_type and PENDING status after successful commit • Test B: 0 outbox rows after rolled-back commit (atomicity proven by Testcontainers real DB) • Test C: outbox row status=DISPATCHED, dispatched_at IS NOT NULL after one poller invocation • Test D: retry_count=3, status=FAILED, last_error IS NOT NULL • All tests pass with ./gradlew :services:transaction-mgmt:test - zero Kafka dependency | 45 | 3.3-T08, 3.3-T13 | BE | DAT-03, PRD-07
3.3-T19 | transaction-mgmt | 3.3 | 3. Data Layer & Persistence | Transaction & event tables (8-step trail) | 1 | Unit test: 8-step event trail completeness for OVERSEAS and LOCAL partner flows | Module: services/transaction-mgmt. JUnit 5 test covering the full 8-step lifecycle using TransactionService methods against Testcontainers PostgreSQL 16. OVERSEAS INBOUND MPM flow: steps 1,2,3,4,5,6,7,8 all recorded. LOCAL DOMESTIC flow: steps 1,2,4,5,6,7,8 (no step 3). Verify getEventTrail ordering and duration_ms. Use small Thread.sleep(10) between steps to ensure measurable duration_ms values. | • Create services/transaction-mgmt/src/test/java/com/gme/pay/txnmgmt/service/TransactionEventTrailTest.java • Seed OVERSEAS partner fixture; call issueRateQuote, initiateTransaction, deductPrefunding, recordEvent(4), recordEvent(5), commitTransaction, recordEvent(7), recordEvent(8) • Assert getEventTrail returns 8 DTOs in order step 1..8 with correct event_type values • Seed LOCAL partner fixture; call same sequence skipping deductPrefunding; assert getEventTrail returns 7 DTOs with no step=3 • Assert duration_ms for step 2 = approx ms between step1.occurred_at and step2.occurred_at (within 50ms tolerance) • Assert step 6 detailJson contains keys collection_usd and offer_rate_coll | services/transaction-mgmt/src/test/java/com/gme/pay/txnmgmt/service/TransactionEventTrailTest.java | • OVERSEAS flow: trail size=8, all event_type values match canonical names from SEC-09 • LOCAL flow: trail size=7, no DTO with step=3 • duration_ms for every step 2-8 is >= 0 • Step 6 detailJson round-trips to Map containing collection_usd non-null • Duplicate recordEvent for step=4 throws DuplicateEventStepException without corrupting existing trail | 40 | 3.3-T15 | BE | DAT-03, PRD-07
3.3-T20 | transaction-mgmt | 3.3 | 3. Data Layer & Persistence | Transaction & event tables (8-step trail) | 1 | Integration test: full 8-step trail HTTP flow via TransactionInternalController | Module: services/transaction-mgmt. @SpringBootTest(webEnvironment=RANDOM_PORT) end-to-end integration test exercising all 8 steps via HTTP through TransactionInternalController against Testcontainers PostgreSQL 16. OVERSEAS INBOUND MPM transaction. No Kafka, no external scheme. Seed: partner (OVERSEAS), scheme (ZEROPAY), rule (INBOUND, m_a=0.010000, m_b=0.015000), prefunding_account (balance=10000.0000 USD), treasury_rate (ccy_pair=usd_krw, rate=1380.00000000). | • Create services/transaction-mgmt/src/test/java/com/gme/pay/txnmgmt/TransactionFullTrailIT.java with @SpringBootTest and @Testcontainers • Seed DB fixtures via TransactionRepository/JdbcTemplate in @BeforeEach • POST /internal/v1/transactions/quote with target_payout=45000 KRW; assert 201, quote_ref non-null, valid_until = ~5 min ahead • POST /internal/v1/transactions; assert 201, txn_ref non-null, status=INITIATED in DB • POST /{txnRef}/prefund-deduct; assert 200, verify prefunding_account.balance reduced by collection_usd, ledger entry created • POST /{txnRef}/commit; assert 200, verify rate_locked_at set, all 8 rate-lock fields non-null, outbox PENDING rows exist • POST /{txnRef}/events for steps 4,5,7,8; GET /{txnRef}/trail; assert 8-element list steps 1-8 | services/transaction-mgmt/src/test/java/com/gme/pay/txnmgmt/TransactionFullTrailIT.java | • All 8 HTTP calls return 2xx status codes • transaction_event table has exactly 8 rows for txn_ref, steps 1-8 • prefunding_account.balance = 10000.0000 - collection_usd (to 4 decimal places) after deduction • domain_event_outbox contains TransactionCommittedEvent and PrefundDeductedEvent rows both PENDING • GET /trail returns list with step 6 detailJson containing offer_rate_coll matching expected value from 5-step formula | 55 | 3.3-T16, 3.3-T18 | BE | DAT-03, PRD-07
3.3-T21 | transaction-mgmt | 3.3 | 3. Data Layer & Persistence | Transaction & event tables (8-step trail) | 1 | Configure services/transaction-mgmt Gradle module and application.yml | Module: services/transaction-mgmt. Ensure the Gradle sub-module is declared in the root settings.gradle and the module build.gradle has all required dependencies per STACK.md: spring-boot-starter-data-jpa, spring-boot-starter-web, spring-boot-starter-security, flyway-core, postgresql (runtime), lib-money, lib-errors, lib-api-contracts, lib-events, testcontainers-postgresql (testImplementation), testcontainers-junit-jupiter (testImplementation), spring-security-test (testImplementation). application.yml: spring.flyway.locations=classpath:db/migration, spring.jpa.hibernate.ddl-auto=validate, outbox.poller.enabled=true. | • Verify or add include(services:transaction-mgmt) in root settings.gradle • Create/update services/transaction-mgmt/build.gradle with all dependencies listed in context; set Java 21 toolchain • Create services/transaction-mgmt/src/main/resources/application.yml with placeholder datasource, flyway config (baseline-on-migrate=true, baseline-version=1), jpa ddl-auto=validate • Add test application.yml in src/test/resources with outbox.poller.enabled=false and a Testcontainers datasource placeholder • Run ./gradlew :services:transaction-mgmt:compileJava to verify zero compilation errors • Run ./gradlew :services:transaction-mgmt:test to confirm Testcontainers-backed tests pass | services/transaction-mgmt/build.gradle and services/transaction-mgmt/src/main/resources/application.yml | • ./gradlew :services:transaction-mgmt:build succeeds with zero compilation errors • All lib-* project dependencies resolve correctly (project(:lib-money) etc.) • spring.jpa.hibernate.ddl-auto=validate passes against schema created by Flyway V9-V13 in order • No duplicate Flyway migration version numbers in V9-V13 • Flyway migrate runs all 5 migrations (V9,V10,V11,V12,V13) in version order without error | 30 | 3.3-T05 | BE | DAT-03, PRD-07
3.4-T01 | config-registry | 3.4 | 3. Data Layer & Persistence | Treasury/FX rate tables (effective-dated) | 1 | Flyway migration V4__create_treasury_rate_table.sql in services/rate-fx | WBS 3.4 delivers the effective-dated treasury rate store. The table treasury_rate holds usd_{ccy} rates (e.g. usd_krw = 1380.00000000 means 1 USD = 1380 KRW). Schema per RATE-04/DAT-03 section 10.3: id BIGINT PK auto-increment, ccy_pair VARCHAR(10) NOT NULL, rate DECIMAL(20,8) NOT NULL CHECK(rate>0), source VARCHAR(10) NOT NULL CHECK(source IN ('LIVE','MANUAL')), effective_at TIMESTAMPTZ NOT NULL, created_at TIMESTAMPTZ NOT NULL DEFAULT NOW(), updated_at TIMESTAMPTZ NOT NULL, created_by VARCHAR(120), updated_by VARCHAR(120). Rows are NEVER updated or deleted -- each new rate is a new INSERT (immutable append-only history). Flyway lives in services/rate-fx/src/main/resources/db/migration/. | • Create services/rate-fx/src/main/resources/db/migration/V4__create_treasury_rate_table.sql • Write CREATE TABLE treasury_rate with all 9 columns and inline CHECK constraints • Add idx_treasury_rate_ccy_pair ON treasury_rate(ccy_pair) • Add idx_treasury_rate_ccy_effective ON treasury_rate(ccy_pair, effective_at DESC) -- supports canonical latest-rate query • Confirm no UPDATE or DELETE DML in the migration | services/rate-fx/src/main/resources/db/migration/V4__create_treasury_rate_table.sql | • All 9 columns present with DECIMAL(20,8) for rate and TIMESTAMPTZ for effective_at • CHECK(rate>0) rejects INSERT of rate=0 with constraint violation • CHECK(source IN ('LIVE','MANUAL')) rejects source='FEED' • Both indexes appear in pg_indexes after migration • File contains no DROP, TRUNCATE, or UPDATE statements | 25 |  | BE | RATE-04
3.4-T02 | config-registry | 3.4 | 3. Data Layer & Persistence | Treasury/FX rate tables (effective-dated) | 1 | Flyway migration V5__treasury_rate_no_overlap_unique.sql -- unique (ccy_pair, effective_at) | Because the latest-rate query uses ORDER BY effective_at DESC LIMIT 1, two rows for the same ccy_pair with the same effective_at timestamp create non-deterministic rate selection. Add a UNIQUE constraint on (ccy_pair, effective_at) at DB level. This enforces the no-overlapping-effective-timestamp invariant independently of application code. File: services/rate-fx/src/main/resources/db/migration/V5__treasury_rate_no_overlap_unique.sql. | • Create services/rate-fx/src/main/resources/db/migration/V5__treasury_rate_no_overlap_unique.sql • Write: ALTER TABLE treasury_rate ADD CONSTRAINT uq_treasury_rate_ccy_effective UNIQUE (ccy_pair, effective_at) • Verify the migration does not conflict with any data inserted in V4 (V4 inserts no data rows) | services/rate-fx/src/main/resources/db/migration/V5__treasury_rate_no_overlap_unique.sql | • Attempting INSERT of two rows with same (ccy_pair, effective_at) raises SQLSTATE 23505 • Two rows for same ccy_pair with different effective_at are both accepted • The constraint name uq_treasury_rate_ccy_effective appears in pg_constraint • Migration applies without error on a fresh V4 schema | 15 | 3.4-T01 | BE | RATE-04
3.4-T03 | config-registry | 3.4 | 3. Data Layer & Persistence | Treasury/FX rate tables (effective-dated) | 1 | Flyway migration V6__treasury_rate_seed_identity.sql -- seed usd_usd = 1.0 | The usd_usd identity rate (1 USD = 1 USD) must always be present so the rate engine can serve any ccy_pair lookup without special-casing. Seed with: ccy_pair='usd_usd', rate=1.00000000, source='MANUAL', effective_at='1970-01-01 00:00:00+00', created_by='SYSTEM_SEED', updated_by='SYSTEM_SEED'. Use INSERT ... ON CONFLICT DO NOTHING so the migration is idempotent. The rate engine will still short-circuit usd_usd to BigDecimal.ONE without a DB hit, but the row ensures the table is never empty. | • Create services/rate-fx/src/main/resources/db/migration/V6__treasury_rate_seed_identity.sql • Write INSERT INTO treasury_rate (ccy_pair, rate, source, effective_at, created_at, updated_at, created_by, updated_by) VALUES ('usd_usd', 1.00000000, 'MANUAL', '1970-01-01 00:00:00+00', NOW(), NOW(), 'SYSTEM_SEED', 'SYSTEM_SEED') ON CONFLICT ON CONSTRAINT uq_treasury_rate_ccy_effective DO NOTHING • Verify migration runs cleanly after V4 and V5 | services/rate-fx/src/main/resources/db/migration/V6__treasury_rate_seed_identity.sql | • After migration: SELECT count(*) FROM treasury_rate WHERE ccy_pair='usd_usd' = 1 • rate = 1.00000000 exactly (8 decimal places) • Re-executing the INSERT (idempotency) does not throw duplicate-key error • source = 'MANUAL' and created_by = 'SYSTEM_SEED' | 15 | 3.4-T02 | BE | RATE-04
3.4-T04 | config-registry | 3.4 | 3. Data Layer & Persistence | Treasury/FX rate tables (effective-dated) | 1 | Define TreasuryRate JPA entity in lib-persistence | lib-persistence is the shared Gradle module for JPA/migration utilities (lib-persistence/build.gradle declares spring-boot-starter-data-jpa). The TreasuryRate entity maps to treasury_rate. Fields: Long id, String ccyPair, BigDecimal rate, String source, Instant effectiveAt, Instant createdAt, Instant updatedAt, String createdBy, String updatedBy. Use @Column(name='rate', precision=20, scale=8) for the BigDecimal. Package: com.gme.pay.persistence.entity. Annotate @Entity, @Table(name='treasury_rate'), @Id, @GeneratedValue(strategy=IDENTITY). This entity is pure mapping -- no business logic. | • Create lib-persistence/src/main/java/com/gme/pay/persistence/entity/TreasuryRate.java • Annotate class with @Entity and @Table(name="treasury_rate") • Map all 9 fields: use @Column(name="ccy_pair") etc for camelCase to snake_case • Set @Column(precision=20, scale=8) on BigDecimal rate field • Add @GeneratedValue(strategy=GenerationType.IDENTITY) on id; confirm no sequence strategy | lib-persistence/src/main/java/com/gme/pay/persistence/entity/TreasuryRate.java | • All 9 columns mapped with matching snake_case column names • BigDecimal rate has precision=20, scale=8 in @Column • @GeneratedValue uses IDENTITY not SEQUENCE • Class compiles inside lib-persistence without requiring any service module • No business logic or repository methods in this class | 25 | 3.4-T01 | BE | RATE-04
3.4-T05 | config-registry | 3.4 | 3. Data Layer & Persistence | Treasury/FX rate tables (effective-dated) | 1 | Create TreasuryRateRepository (Spring Data JPA) in services/rate-fx | The rate-fx service (services/rate-fx) owns all rate engine logic. TreasuryRateRepository extends JpaRepository<TreasuryRate, Long>. Required derived query methods: (1) Optional<TreasuryRate> findTopByCcyPairOrderByEffectiveAtDesc(String ccyPair) -- resolves to WHERE ccy_pair=? ORDER BY effective_at DESC LIMIT 1; (2) Page<TreasuryRate> findByCcyPairOrderByEffectiveAtDesc(String ccyPair, Pageable pageable) -- paginated history. Package: com.gme.pay.ratefx.repository. rate-fx/build.gradle must declare implementation project(':lib-persistence'). | • Create services/rate-fx/src/main/java/com/gme/pay/ratefx/repository/TreasuryRateRepository.java • Extend JpaRepository<TreasuryRate, Long> • Declare findTopByCcyPairOrderByEffectiveAtDesc(String ccyPair) returning Optional<TreasuryRate> • Declare findByCcyPairOrderByEffectiveAtDesc(String ccyPair, Pageable pageable) returning Page<TreasuryRate> • Confirm rate-fx/build.gradle includes implementation project(':lib-persistence') | services/rate-fx/src/main/java/com/gme/pay/ratefx/repository/TreasuryRateRepository.java | • Interface extends JpaRepository<TreasuryRate, Long> • findTopByCcyPairOrderByEffectiveAtDesc returns Optional<TreasuryRate> (not List, not nullable) • Spring Data derives the correct LIMIT 1 SQL without @Query needed • Module compiles without missing-dependency errors • No @Query annotations required -- method names drive query derivation | 20 | 3.4-T04 | BE | RATE-04
3.4-T06 | config-registry | 3.4 | 3. Data Layer & Persistence | Treasury/FX rate tables (effective-dated) | 1 | Implement TreasuryRateService.getEffectiveRate() @Service in services/rate-fx | TreasuryRateService is the @Service that the rate engine calls. Method: BigDecimal getEffectiveRate(String ccyPair, Instant asOf). Logic: if ccyPair equals 'usd_usd' return BigDecimal.ONE immediately (IDENTITY short-circuit, no DB hit). Otherwise call repository.findTopByCcyPairOrderByEffectiveAtDesc(ccyPair). If Optional is empty throw RateNotFoundException (lib-errors) with code RATE_NOT_FOUND. The asOf parameter is accepted for Phase 2 point-in-time lookup but in Phase 1 always returns the latest row. Package: com.gme.pay.ratefx.service. | • Create services/rate-fx/src/main/java/com/gme/pay/ratefx/service/TreasuryRateService.java • Annotate @Service • Inject TreasuryRateRepository via constructor • Implement getEffectiveRate: return BigDecimal.ONE for 'usd_usd'; otherwise findTop... unwrap Optional or throw RateNotFoundException(code=RATE_NOT_FOUND) • Add getHistory(String ccyPair, Pageable pageable) delegating to repository paged query for later use by admin controller | services/rate-fx/src/main/java/com/gme/pay/ratefx/service/TreasuryRateService.java | • getEffectiveRate('usd_usd', any) returns BigDecimal.ONE without any repository call • getEffectiveRate('usd_krw', any) returns the BigDecimal from the row with highest effective_at for ccy_pair=usd_krw • getEffectiveRate for unknown pair throws RateNotFoundException with code RATE_NOT_FOUND • Service is stateless -- safe for concurrent calls without synchronisation • No static fields holding rate values | 30 | 3.4-T05 | BE | RATE-04
3.4-T07 | config-registry | 3.4 | 3. Data Layer & Persistence | Treasury/FX rate tables (effective-dated) | 1 | Implement TreasuryRateService.upsertRate() -- create new effective-dated row | Rates are immutable: each update INSERTs a new row. Method: TreasuryRate upsertRate(String ccyPair, BigDecimal rate, String source, Instant effectiveAt, String actor, boolean confirmDeviation). Validates: rate > 0 (throw InvalidRateException code RATE_INVALID_VALUE), source in {LIVE,MANUAL} (RATE_INVALID_SOURCE), effectiveAt not more than 60s in the past (RATE_BACKDATE_REJECTED). Saves via repository.save(). Does NOT mutate existing rows. Calls auditLogService.log('CREATE', 'treasury_rate', saved.id, null, json(saved), actor) after save (3.4-T11). | • Add upsertRate method to TreasuryRateService • Validate rate>0; source in {LIVE,MANUAL}; effectiveAt >= Instant.now().minusSeconds(60) -- throw typed exceptions with codes • Build a new TreasuryRate entity with all fields; call repository.save() • Call auditLogService.log with action=CREATE, before=null, after=saved entity JSON • Return saved entity | Updated services/rate-fx/src/main/java/com/gme/pay/ratefx/service/TreasuryRateService.java with upsertRate() | • rate=0 throws InvalidRateException code RATE_INVALID_VALUE • source='FEED' throws InvalidRateException code RATE_INVALID_SOURCE • effectiveAt 120s in the past throws InvalidRateException code RATE_BACKDATE_REJECTED • Inserting a new rate creates a new row -- existing rows for same ccy_pair are untouched • After insert, getEffectiveRate returns the new rate if its effective_at is >= all prior rows for the pair | 35 | 3.4-T06, 3.4-T11 | BE | RATE-04
3.4-T08 | config-registry | 3.4 | 3. Data Layer & Persistence | Treasury/FX rate tables (effective-dated) | 1 | Add deviation guard to upsertRate() -- warn on >10% rate change | Per PRD-07 section 7.3: if the new rate deviates more than +-10% from the previous stored rate for the same ccy_pair, throw RateDeviationWarningException(code=RATE_DEVIATION_WARNING, previousRate, percentageChange). The caller (admin controller) surfaces this as a 422 confirmation prompt. If the operator re-calls with confirmDeviation=true the check is skipped. This guards against typos (e.g. entering 13800 instead of 1380). percentageChange = abs(newRate - prevRate) / prevRate * 100. If no previous row exists for the pair skip the check entirely. | • Retrieve the latest existing row for ccyPair via repository (may be absent) • If present: compute percentageChange using BigDecimal arithmetic (no double) • If percentageChange > 10.0 AND confirmDeviation==false: throw RateDeviationWarningException with previousRate and percentageChange fields • If confirmDeviation==true OR no previous row: proceed normally to insert • Verify BigDecimal.divide uses HALF_UP, scale=4 for percentage computation | Updated upsertRate() in services/rate-fx/src/main/java/com/gme/pay/ratefx/service/TreasuryRateService.java | • Rate 1485.00 vs prev 1380.00 (7.61% change) is accepted without warning • Rate 1520.00 vs prev 1380.00 (10.14% change, confirmDeviation=false) throws RateDeviationWarningException with percentageChange >=10.1 • Same 1520.00 with confirmDeviation=true proceeds to INSERT • First-ever rate for a new ccy_pair (no prior row) is accepted unconditionally • percentageChange in exception is within 0.01% of the true calculated value | 30 | 3.4-T07 | BE | RATE-04
3.4-T09 | config-registry | 3.4 | 3. Data Layer & Persistence | Treasury/FX rate tables (effective-dated) | 1 | Expose GET /internal/rates/{ccyPair}/latest in TreasuryRateController | services/rate-fx exposes an internal REST endpoint consumed by payment-executor and smart-router to resolve cost rates at quote time. @RestController @RequestMapping('/internal/rates'). GET /{ccyPair}/latest calls TreasuryRateService.getEffectiveRate(ccyPair, Instant.now()) and returns TreasuryRateDto {ccyPair, rate (String to preserve 8dp), source, effectiveAt}. RateNotFoundException mapped to 404 {code:RATE_NOT_FOUND} via lib-errors GlobalExceptionHandler. No auth on internal endpoints -- mTLS enforced at infra/k8s network policy level. Package: com.gme.pay.ratefx.controller. | • Create services/rate-fx/src/main/java/com/gme/pay/ratefx/controller/TreasuryRateController.java • Annotate @RestController, @RequestMapping("/internal/rates") • Implement @GetMapping("/{ccyPair}/latest") calling service and mapping to TreasuryRateDto • Define TreasuryRateDto as record(String ccyPair, String rate, String source, String effectiveAt) -- rate as String preserves all 8 decimals • Ensure RateNotFoundException is handled globally (GlobalExceptionHandler in lib-errors) returning 404 with {code:RATE_NOT_FOUND} | services/rate-fx/src/main/java/com/gme/pay/ratefx/controller/TreasuryRateController.java | • GET /internal/rates/usd_krw/latest returns 200 with correct ccyPair and rate when row exists • GET /internal/rates/usd_usd/latest returns 200 with rate='1.00000000' • GET /internal/rates/usd_xyz/latest returns 404 with body {code:'RATE_NOT_FOUND'} • rate field in JSON response is a String (not a JSON number) to avoid floating-point loss | 30 | 3.4-T06 | BE | RATE-04
3.4-T10 | config-registry | 3.4 | 3. Data Layer & Persistence | Treasury/FX rate tables (effective-dated) | 1 | Add Redis cache for latest rate in TreasuryRateService -- TTL = 1s | Per PRD-07 section 7.5: rate update latency between Ops action and transaction effect must be <=1 second. Cache the latest rate per ccy_pair in Redis with TTL=1s using @Cacheable (Spring Cache abstraction) backed by RedisCacheManager. Cache name: treasury-rate-latest. Key = ccyPair. On upsertRate: @CacheEvict(value='treasury-rate-latest', key='#ccyPair') to invalidate immediately on write. usd_usd bypasses cache (returns BigDecimal.ONE before any cache lookup). Add spring-boot-starter-data-redis to services/rate-fx/build.gradle. Configure redis host/port in application.yml. | • Add spring-boot-starter-data-redis to services/rate-fx/build.gradle • Create services/rate-fx/src/main/java/com/gme/pay/ratefx/config/RateFxCacheConfig.java with @Configuration @EnableCaching • Configure RedisCacheManager with TTL=Duration.ofSeconds(1) for cache 'treasury-rate-latest' using Jackson serialization • Annotate getEffectiveRate() with @Cacheable(value='treasury-rate-latest', key='#ccyPair', condition='!#ccyPair.equals("usd_usd")') • Annotate upsertRate() with @CacheEvict(value='treasury-rate-latest', key='#ccyPair') | services/rate-fx/src/main/java/com/gme/pay/ratefx/config/RateFxCacheConfig.java and updated TreasuryRateService.java | • After upsertRate for usd_krw, next getEffectiveRate call returns the new value (cache evicted on write) • After 1s TTL expiry with no write, cache miss triggers a fresh DB read (confirmed by repository call count) • Updating usd_krw does not evict usd_mnt cache entry (keys are independent) • usd_usd short-circuit bypasses Redis entirely -- no cache key created for usd_usd | 35 | 3.4-T06 | BE | RATE-04
3.4-T11 | config-registry | 3.4 | 3. Data Layer & Persistence | Treasury/FX rate tables (effective-dated) | 1 | AuditLogService interface and PostgresAuditLogService @Service in lib-persistence | All treasury_rate mutations must emit an audit_log row (DAT-03): entity_type='treasury_rate', entity_id=rate.id, action=CREATE, before_value=JSONB null (for CREATE), after_value=JSONB serialized new state, actor=operator id, occurred_at=NOW(). Interface in lib-persistence: void log(String action, String entityType, Long entityId, String beforeJson, String afterJson, String actor). PostgresAuditLogService implements it with JdbcTemplate INSERT into audit_log. Uses @Transactional(propagation=REQUIRES_NEW) so audit insert never rolls back with the parent business transaction. audit_log table migration is in 3.4-T14. | • Create lib-persistence/src/main/java/com/gme/pay/persistence/audit/AuditLogService.java as interface with void log(...) • Create lib-persistence/src/main/java/com/gme/pay/persistence/audit/PostgresAuditLogService.java implementing AuditLogService • Annotate PostgresAuditLogService @Service; inject JdbcTemplate • Implement log() with @Transactional(propagation=REQUIRES_NEW) executing INSERT INTO audit_log • Cast beforeJson/afterJson to ::jsonb in the SQL to enforce JSONB storage | lib-persistence/src/main/java/com/gme/pay/persistence/audit/AuditLogService.java and PostgresAuditLogService.java | • log() inserts exactly one row in audit_log with matching entity_type, entity_id, action, actor • before_value is NULL for CREATE actions (SQL NULL cast to ::jsonb) • Method uses REQUIRES_NEW propagation -- audit row persists even if caller transaction rolls back • lib-persistence compiles with no circular dependency on rate-fx or any service module | 35 |  | BE | RATE-04
3.4-T12 | config-registry | 3.4 | 3. Data Layer & Persistence | Treasury/FX rate tables (effective-dated) | 1 | Flyway migration V7__create_audit_log_table.sql in services/rate-fx | audit_log table per DAT-03: id BIGINT PK auto-increment, actor VARCHAR(120), actor_type VARCHAR(20) CHECK IN ('OPERATOR','SYSTEM','PARTNER'), action VARCHAR(20) CHECK IN ('CREATE','UPDATE','DELETE','ACTIVATE','DEACTIVATE'), entity_type VARCHAR(50), entity_id BIGINT, before_value JSONB, after_value JSONB, occurred_at TIMESTAMPTZ NOT NULL DEFAULT NOW(). No updated_at -- table is append-only. Indexes: on (entity_type, entity_id) for history lookup and on (occurred_at DESC) for time-range queries. File: services/rate-fx/src/main/resources/db/migration/V7__create_audit_log_table.sql. If a shared migration already creates this table, this ticket is a no-op; close it. | • Check if audit_log DDL exists in any prior migration under services/rate-fx/src/main/resources/db/migration/ • If absent, create V7__create_audit_log_table.sql with full DDL including JSONB columns for before/after • Add index idx_audit_entity ON audit_log(entity_type, entity_id) • Add index idx_audit_occurred ON audit_log(occurred_at DESC) • Confirm no updated_at column exists (table is immutable append-only) | services/rate-fx/src/main/resources/db/migration/V7__create_audit_log_table.sql | • audit_log has 9 columns with JSONB for before_value and after_value • actor_type and action CHECK constraints enforced at DB level • No updated_at column • Index on (entity_type, entity_id) present • occurred_at has DEFAULT NOW() | 25 | 3.4-T03 | BE | RATE-04
3.4-T13 | config-registry | 3.4 | 3. Data Layer & Persistence | Treasury/FX rate tables (effective-dated) | 1 | Expose POST /admin/rates in TreasuryRateAdminController with OPS_RATE_MANAGER RBAC | Admin System calls POST /admin/rates to insert a new effective-dated rate. Request body RateUpsertRequest: {ccyPair, rate (String), source, effectiveAt (ISO-8601), notes (optional String), confirmDeviation (boolean default false)}. Controller calls TreasuryRateService.upsertRate(). On RateDeviationWarningException return HTTP 422 with {code:RATE_DEVIATION_WARNING, previousRate, percentageChange}. On success return 201 with TreasuryRateDto. Requires @PreAuthorize("hasRole('OPS_RATE_MANAGER')") -- Spring Security RBAC. Package: com.gme.pay.ratefx.controller.admin. | • Create services/rate-fx/src/main/java/com/gme/pay/ratefx/controller/admin/TreasuryRateAdminController.java • Annotate @RestController, @RequestMapping("/admin/rates"), @PreAuthorize("hasRole('OPS_RATE_MANAGER')") • Implement @PostMapping: deserialize RateUpsertRequest, call upsertRate(), return 201 with TreasuryRateDto • Handle RateDeviationWarningException with @ExceptionHandler returning 422 with deviation payload • Parse rate field as BigDecimal from String to prevent float precision loss | services/rate-fx/src/main/java/com/gme/pay/ratefx/controller/admin/TreasuryRateAdminController.java | • POST with valid payload and OPS_RATE_MANAGER role returns 201 with ccyPair and rate in body • POST with >10% deviation and confirmDeviation=false returns 422 with code RATE_DEVIATION_WARNING and percentageChange field • POST with >10% deviation and confirmDeviation=true returns 201 • POST without OPS_RATE_MANAGER role returns 403 • rate field in request is parsed as String-to-BigDecimal (never parsed as JSON number/float) | 35 | 3.4-T08, 3.4-T11 | BE | RATE-04
3.4-T14 | config-registry | 3.4 | 3. Data Layer & Persistence | Treasury/FX rate tables (effective-dated) | 1 | Expose GET /admin/rates and GET /admin/rates/{ccyPair}/history in admin controller | Ops portal needs: (1) GET /admin/rates -- all distinct ccy_pairs with their latest rate (SQL: SELECT DISTINCT ON (ccy_pair) * FROM treasury_rate ORDER BY ccy_pair, effective_at DESC); (2) GET /admin/rates/{ccyPair}/history?page=0&size=20 -- full history for one pair, newest first (Page<TreasuryRateDto>). Both require OPS_RATE_MANAGER. Add a @Query native SQL in TreasuryRateRepository for the DISTINCT ON query. Response includes source, effectiveAt, createdBy, updatedAt. | • Add @GetMapping on /admin/rates handler returning List<TreasuryRateDto> (latest per pair) • Add native @Query in TreasuryRateRepository: SELECT DISTINCT ON (ccy_pair) * FROM treasury_rate ORDER BY ccy_pair, effective_at DESC • Add @GetMapping on /admin/rates/{ccyPair}/history returning Page<TreasuryRateDto> delegating to TreasuryRateService.getHistory() • Both handlers carry @PreAuthorize("hasRole('OPS_RATE_MANAGER')") • Include source, effectiveAt, createdBy in TreasuryRateDto | Updated services/rate-fx/src/main/java/com/gme/pay/ratefx/controller/admin/TreasuryRateAdminController.java | • GET /admin/rates returns exactly one entry per ccy_pair showing the row with highest effective_at • GET /admin/rates/usd_krw/history returns all rows for usd_krw newest first • Page metadata (totalElements, totalPages) is correct • Both endpoints return 403 for callers without OPS_RATE_MANAGER role • GET /admin/rates includes the usd_usd seed row with source=MANUAL | 35 | 3.4-T13 | BE | RATE-04
3.4-T15 | config-registry | 3.4 | 3. Data Layer & Persistence | Treasury/FX rate tables (effective-dated) | 1 | Add TreasuryRateUpdatedEvent to lib-events and OutboxEventPublisher to rate-fx | Phase 1 messaging: transactional Outbox pattern (Kafka deferred to integration phase). After upsertRate saves treasury_rate, publish TreasuryRateUpdatedEvent in the SAME @Transactional. Event fields (Java record): String eventId (UUID), String ccyPair, String newRate, String previousRate (nullable), String source, String effectiveAt, String occurredAt, String actor. Outbox table: domain_event_outbox (id UUID PK, aggregate_type VARCHAR(50), aggregate_id VARCHAR(50), event_type VARCHAR(100), payload JSONB, created_at TIMESTAMPTZ DEFAULT NOW(), published_at TIMESTAMPTZ NULL). Create Flyway migration V8__create_domain_event_outbox.sql. EventPublisher interface in lib-events. | • Create lib-events/src/main/java/com/gme/pay/events/ratefx/TreasuryRateUpdatedEvent.java as record with all 8 String fields • Create lib-events/src/main/java/com/gme/pay/events/EventPublisher.java interface: void publish(Object event) • Create services/rate-fx/src/main/java/com/gme/pay/ratefx/messaging/OutboxEventPublisher.java implementing EventPublisher; inject JdbcTemplate; INSERT into domain_event_outbox within caller transaction • Create V8__create_domain_event_outbox.sql migration with columns listed in context • Inject EventPublisher into TreasuryRateService.upsertRate() and call after repository.save() inside same @Transactional | lib-events TreasuryRateUpdatedEvent.java, lib-events EventPublisher.java, services/rate-fx OutboxEventPublisher.java, V8__create_domain_event_outbox.sql | • treasury_rate INSERT and outbox INSERT either both commit or both roll back (atomicity) • domain_event_outbox row has aggregate_type='treasury_rate', event_type='TreasuryRateUpdatedEvent', non-null payload JSONB after upsertRate • EventPublisher interface in lib-events has no dependency on any service module • OutboxEventPublisher can be swapped for KafkaEventPublisher later without changing TreasuryRateService | 40 | 3.4-T07 | BE | RATE-04
3.4-T16 | config-registry | 3.4 | 3. Data Layer & Persistence | Treasury/FX rate tables (effective-dated) | 1 | Unit test: TreasuryRateServiceTest -- getEffectiveRate happy paths and RATE_NOT_FOUND | JUnit 5 pure unit tests for TreasuryRateService.getEffectiveRate(). No Spring context, no DB. Use Mockito (@ExtendWith(MockitoExtension.class)) to mock TreasuryRateRepository. Test cases: (1) ccyPair=usd_usd returns BigDecimal.ONE; verify repository never called. (2) ccyPair=usd_krw with mocked row rate=1380.00000000 returns that BigDecimal. (3) unknown pair with Optional.empty() throws RateNotFoundException code RATE_NOT_FOUND. File: services/rate-fx/src/test/java/com/gme/pay/ratefx/service/TreasuryRateServiceTest.java. | • Create TreasuryRateServiceTest.java under services/rate-fx/src/test/ • @ExtendWith(MockitoExtension.class); @Mock TreasuryRateRepository; @Mock AuditLogService; @InjectMocks TreasuryRateService • Test 1: getEffectiveRate("usd_usd", now()); assert returns BigDecimal.ONE; verify(repo).findTopBy... never called • Test 2: when(repo.findTop...("usd_krw")).thenReturn(Optional.of(rateRow("1380.00000000"))); assert result equals new BigDecimal("1380.00000000") • Test 3: when(repo.findTop...("usd_xyz")).thenReturn(Optional.empty()); assertThrows(RateNotFoundException.class); check code==RATE_NOT_FOUND | services/rate-fx/src/test/java/com/gme/pay/ratefx/service/TreasuryRateServiceTest.java | • All 3 tests pass: ./gradlew :services:rate-fx:test • No Spring context loaded -- tests complete in under 2 seconds • Test 1 verifies zero Mockito interactions on repository • Test 3 RateNotFoundException carries code RATE_NOT_FOUND | 30 | 3.4-T06 | BE | RATE-04
3.4-T17 | config-registry | 3.4 | 3. Data Layer & Persistence | Treasury/FX rate tables (effective-dated) | 1 | Unit test: TreasuryRateServiceTest -- upsertRate validation and deviation guard vectors | JUnit 5 Mockito unit tests for upsertRate() validation and deviation guard. Exact test vectors: (1) rate=BigDecimal.ZERO throws InvalidRateException RATE_INVALID_VALUE; (2) source='FEED' throws InvalidRateException RATE_INVALID_SOURCE; (3) effectiveAt=Instant.now().minusSeconds(120) throws RATE_BACKDATE_REJECTED; (4) prev=1380.00 new=1520.00 -> percentageChange=10.14%, confirmDeviation=false throws RateDeviationWarningException; (5) same deviation with confirmDeviation=true calls repository.save() exactly once. File: same TreasuryRateServiceTest.java as 3.4-T16. | • Add 5 test methods to TreasuryRateServiceTest.java • Tests 1-3: no repository setup needed; pass invalid inputs; assert exception codes • Test 4: mock repo.findTop...(usd_krw) to return row(rate=1380.00); call upsertRate(usd_krw, 1520.00, MANUAL, now, actor, false); assertThrows RateDeviationWarningException; check percentageChange >=10.1 • Test 5: same setup with confirmDeviation=true; assertDoesNotThrow; verify(repo).save(any()) once • Use BigDecimal string constructors throughout -- no double literals | Additional test methods in services/rate-fx/src/test/java/com/gme/pay/ratefx/service/TreasuryRateServiceTest.java | • All 5 tests pass • Test 4 exception percentageChange is between 10.10 and 10.20 • Test 5 verifies repository.save() called exactly once via Mockito verify • Tests 1-3 assert exact exception codes • No DB or Spring context required | 30 | 3.4-T08, 3.4-T16 | BE | RATE-04
3.4-T18 | config-registry | 3.4 | 3. Data Layer & Persistence | Treasury/FX rate tables (effective-dated) | 1 | Integration test: TreasuryRateRepositoryIT with Testcontainers PostgreSQL 16 and Flyway | Verifies Flyway migrations V4-V8 and repository queries against a real PostgreSQL 16 container. @SpringBootTest(webEnvironment=NONE) + @Testcontainers. Test cases: (1) seed row usd_usd present after migrations with rate=1.00000000; (2) insert two usd_krw rows with effectiveAt t1 < t2; findTopByCcyPairOrderByEffectiveAtDesc returns t2 row; (3) insert duplicate (usd_krw, t2) throws DataIntegrityViolationException from unique constraint uq_treasury_rate_ccy_effective. File: services/rate-fx/src/test/java/com/gme/pay/ratefx/repository/TreasuryRateRepositoryIT.java. | • Create TreasuryRateRepositoryIT.java under services/rate-fx/src/test/ • @Container static PostgreSQLContainer<?> postgres = new PostgreSQLContainer<>("postgres:16") • Configure datasource and flyway.locations via @DynamicPropertySource • Test 1: assert findByCcyPairOrderByEffectiveAtDesc("usd_usd", ...) returns row with rate compareTo(BigDecimal.ONE)==0 • Test 2: save two rows; assert findTop returns row with higher effectiveAt • Test 3: save duplicate (ccyPair, effectiveAt); assertThrows DataIntegrityViolationException | services/rate-fx/src/test/java/com/gme/pay/ratefx/repository/TreasuryRateRepositoryIT.java | • All 3 tests pass against real Postgres 16 Testcontainer • Flyway V4->V5->V6->V7->V8 run in order without error • Test 3 confirms unique constraint blocks duplicate (ccy_pair, effective_at) • Test 2 confirms the newer effectiveAt row is returned (ORDER BY effective_at DESC LIMIT 1) | 40 | 3.4-T05, 3.4-T12, 3.4-T15 | BE | RATE-04
3.4-T19 | config-registry | 3.4 | 3. Data Layer & Persistence | Treasury/FX rate tables (effective-dated) | 1 | Integration test: TreasuryRateAdminControllerIT with Spring MVC test slice | @WebMvcTest(TreasuryRateAdminController.class) + MockMvc. @MockBean TreasuryRateService. No DB needed. Tests: (1) POST /admin/rates valid payload + @WithMockUser(roles=OPS_RATE_MANAGER) -> 201 with TreasuryRateDto; (2) MockBean throws RateDeviationWarningException -> 422 with code RATE_DEVIATION_WARNING and percentageChange; (3) MockBean throws InvalidRateException RATE_INVALID_VALUE -> 400; (4) POST /admin/rates without auth -> 403; (5) GET /admin/rates with auth -> 200 list. File: services/rate-fx/src/test/java/com/gme/pay/ratefx/controller/admin/TreasuryRateAdminControllerIT.java. | • Create TreasuryRateAdminControllerIT.java under services/rate-fx/src/test/ • @WebMvcTest(TreasuryRateAdminController.class); @MockBean TreasuryRateService • Test 1: POST valid JSON; @WithMockUser(roles={"OPS_RATE_MANAGER"}); mockMvc.perform().andExpect(status().isCreated()) • Test 2: when(service.upsertRate(...)).thenThrow(new RateDeviationWarningException(...)); andExpect(status().isUnprocessableEntity()) • Test 4: POST without @WithMockUser; andExpect(status().isForbidden()) | services/rate-fx/src/test/java/com/gme/pay/ratefx/controller/admin/TreasuryRateAdminControllerIT.java | • All 5 tests pass • Test 2 response JSON contains percentageChange field • Test 3 returns 400 not 500 • Test 4 returns 403 confirming @PreAuthorize is active • No real DB or Redis required -- pure MockMvc with mocked service | 35 | 3.4-T14, 3.4-T13 | BE | RATE-04
3.4-T20 | config-registry | 3.4 | 3. Data Layer & Persistence | Treasury/FX rate tables (effective-dated) | 1 | Integration test: Redis cache TTL and eviction via Testcontainers Redis 7 | Full-stack cache test using Testcontainers. @SpringBootTest(webEnvironment=NONE) with both PostgreSQLContainer (postgres:16) and GenericContainer (redis:7). Spy on TreasuryRateRepository. Test: (1) call getEffectiveRate('usd_krw') twice; assert repository spy shows findTop called once (second call from cache); (2) call upsertRate to insert new rate; then getEffectiveRate; assert repository called again (cache evicted); (3) Thread.sleep(1100) after a cached call; getEffectiveRate again; assert repository called (TTL expired). File: services/rate-fx/src/test/java/com/gme/pay/ratefx/service/TreasuryRateServiceCacheIT.java. | • Create TreasuryRateServiceCacheIT.java under services/rate-fx/src/test/ • Spin up Postgres 16 and Redis 7 containers; wire via @DynamicPropertySource • Spy on TreasuryRateRepository bean (@SpyBean) • Test 1: call getEffectiveRate twice; verify findTop called exactly once total • Test 2: upsertRate; getEffectiveRate; verify findTop called again • Test 3: Thread.sleep(1100); getEffectiveRate; verify findTop called (TTL expired) | services/rate-fx/src/test/java/com/gme/pay/ratefx/service/TreasuryRateServiceCacheIT.java | • Test 1 passes: second identical call does not hit repository (0 additional spy invocations) • Test 2 passes: upsertRate evicts cache; next getEffectiveRate hits repository • Test 3 passes: after 1.1s sleep the cache miss causes a repository read • usd_usd calls never increment repository spy count (IDENTITY short-circuit before cache) | 40 | 3.4-T10, 3.4-T18 | BE | RATE-04
3.4-T21 | config-registry | 3.4 | 3. Data Layer & Persistence | Treasury/FX rate tables (effective-dated) | 1 | Outbox atomicity integration test: treasury_rate and outbox rows roll back together | Verifies the transactional Outbox invariant: treasury_rate INSERT and domain_event_outbox INSERT are in the same @Transactional and either both commit or both roll back. Test: (1) Stub OutboxEventPublisher to throw RuntimeException after the outbox insert sql but before commit (use @SpyBean to intercept); call upsertRate; assert no new treasury_rate row; (2) Happy path: successful upsertRate produces exactly 1 new treasury_rate row and 1 new domain_event_outbox row. File: services/rate-fx/src/test/java/com/gme/pay/ratefx/service/TreasuryRateOutboxAtomicityIT.java. | • Create TreasuryRateOutboxAtomicityIT.java under services/rate-fx/src/test/ • @SpringBootTest(webEnvironment=NONE) + Postgres 16 Testcontainer • @SpyBean OutboxEventPublisher; configure spy to throw RuntimeException after first publish call • Call upsertRate(usd_krw, 1380.00, MANUAL, now, actor, false) -- expect exception propagation • Assert treasury_rate count for usd_krw unchanged and domain_event_outbox count unchanged • Restore spy; call upsertRate again; assert both counts increment by 1 | services/rate-fx/src/test/java/com/gme/pay/ratefx/service/TreasuryRateOutboxAtomicityIT.java | • When publisher throws, SELECT count FROM treasury_rate WHERE ccy_pair='usd_krw' shows 0 new rows • When publisher throws, SELECT count FROM domain_event_outbox shows 0 new rows • Happy path: both counts increment by exactly 1 • Both rows share the same transaction commit (verified by count delta = 1 for both) | 40 | 3.4-T15, 3.4-T18 | BE | RATE-04
3.4-T22 | config-registry | 3.4 | 3. Data Layer & Persistence | Treasury/FX rate tables (effective-dated) | 1 | Numeric precision unit test: BigDecimal arithmetic for KRW and MNT rate vectors | Exact arithmetic checks using JUnit 5 (no Spring, no DB). Test vectors from RATE-04 section 4.3: usd_krw=1380.00000000, target_payout=50000 KRW, m_a=0.01, m_b=0.01 (2% total). (1) payout_usd_cost = 50000 / 1380.00000000 HALF_UP 8dp = 36.23188406; (2) collection_usd = 36.23188406 / (1-0.01-0.01) HALF_UP 8dp = 36.97131027; (3) collection_margin_usd = 36.97131027*0.01 = 0.36971310; payout_margin_usd = 0.36971310; (4) pool identity: 36.97131027 - 0.36971310 - 0.36971310 = 36.23188407 -- tolerance vs 36.23188406 <= 0.00000001. Verify BigDecimal.ONE used for IDENTITY leg gives exact equality. File: services/rate-fx/src/test/java/com/gme/pay/ratefx/service/RatePrecisionTest.java. | • Create RatePrecisionTest.java under services/rate-fx/src/test/ • Test 1: assert BigDecimal("50000").divide(new BigDecimal("1380.00000000"), 8, HALF_UP).equals(new BigDecimal("36.23188406")) • Test 2: compute collection_usd from test 1 result; assert matches expected to 8dp • Test 3: compute pool identity remainder; assert abs(remainder - payout_usd_cost) <= new BigDecimal("0.00000001") • Test 4: usd_usd identity: BigDecimal("50").divide(BigDecimal.ONE, 8, HALF_UP) equals new BigDecimal("50.00000000") • Verify no double or float literals in computation -- BigDecimal string constructors throughout | services/rate-fx/src/test/java/com/gme/pay/ratefx/service/RatePrecisionTest.java | • Test 1: 50000/1380 rounded to 8dp = 36.23188406 exactly • Test 3: pool identity holds within 0.00000001 tolerance (8dp internal computation tolerance, not the 0.01 USD display tolerance) • Test 4: identity leg gives exact BigDecimal equality to 8dp • No double or float types appear anywhere in the computation chain • Tests run in under 100ms (no IO) | 30 | 3.4-T06 | BE | RATE-04
3.4-T23 | config-registry | 3.4 | 3. Data Layer & Persistence | Treasury/FX rate tables (effective-dated) | 1 | Spring Boot application smoke test: rate-fx starts with all migrations and /internal/rates/usd_usd/latest returns 200 | @SpringBootTest(webEnvironment=RANDOM_PORT) test that starts the full rate-fx application context with Testcontainers (Postgres 16 + Redis 7). Verifies: (1) Spring context loads with no BeanCreationException; (2) Flyway migrations V4-V8 applied successfully; (3) GET /internal/rates/usd_usd/latest returns HTTP 200 with rate='1.00000000'. This is the CI/CD gate smoke test. File: services/rate-fx/src/test/java/com/gme/pay/ratefx/RateFxApplicationIT.java. | • Create RateFxApplicationIT.java under services/rate-fx/src/test/ • @SpringBootTest(webEnvironment=RANDOM_PORT) + @Testcontainers • Declare static Postgres 16 and Redis 7 containers; @DynamicPropertySource wires spring.datasource.* and spring.data.redis.* • Inject TestRestTemplate; call GET /internal/rates/usd_usd/latest • Assert status 200 and responseBody.rate equals '1.00000000' | services/rate-fx/src/test/java/com/gme/pay/ratefx/RateFxApplicationIT.java | • Application context starts without BeanCreationException or UnsatisfiedDependencyException • Flyway log shows migrations V4 V5 V6 V7 V8 applied in order • GET /internal/rates/usd_usd/latest returns HTTP 200 • Response body rate field = '1.00000000' (string, 8 decimal places) | 30 | 3.4-T21, 3.4-T09, 3.4-T10 | BE | RATE-04
3.4-T24 | config-registry | 3.4 | 3. Data Layer & Persistence | Treasury/FX rate tables (effective-dated) | 1 | Document services/rate-fx treasury rate design in README -- schema, cache, outbox | Developer README (not a spec) covering WBS 3.4 design decisions so a new developer can understand and maintain the treasury rate subsystem. Sections: (1) Table design -- immutable append-only rows, latest-rate query pattern (ORDER BY effective_at DESC LIMIT 1), unique constraint on (ccy_pair, effective_at); (2) Rate resolution -- getEffectiveRate, IDENTITY short-circuit for usd_usd; (3) Redis cache -- key=ccyPair, TTL=1s, eviction on write; (4) Outbox -- TreasuryRateUpdatedEvent in domain_event_outbox, Kafka wiring deferred to integration phase; (5) Admin endpoints -- POST /admin/rates, deviation guard, RBAC. Keep under 80 lines total. File: services/rate-fx/README.md. | • Create or update services/rate-fx/README.md • Section 1 (table design): immutable rows, latest-rate query, no-overlap unique constraint • Section 2 (rate resolution): getEffectiveRate, usd_usd returns 1.0 without DB hit • Section 3 (Redis cache): TTL=1s, @Cacheable, @CacheEvict on write • Section 4 (outbox): TreasuryRateUpdatedEvent, Kafka deferred • Keep total under 80 lines; link to RATE-04 and DAT-03 for full math | services/rate-fx/README.md | • README is under 80 lines • Explains immutable-row (append-only) rationale • Mentions usd_usd identity convention (no DB hit) • Documents 1s Redis TTL and eviction-on-write • Does not duplicate full spec math -- references RATE-04 for 5-step formulas | 20 | 3.4-T23 | BE | RATE-04
3.5-T01 | prefunding | 3.5 | 3. Data Layer & Persistence | Prefunding ledger tables (double-entry) | 1 | Flyway migration: create prefunding_account table in svc-prefunding | The svc-prefunding module (services/prefunding-balance) owns all prefunding state in PostgreSQL 16. One row per OVERSEAS partner holds the current USD balance. Schema: id BIGINT PK (sequence), partner_id BIGINT FK->partner UNIQUE NOT NULL, currency CHAR(3) NOT NULL DEFAULT 'USD', balance DECIMAL(20,4) NOT NULL DEFAULT 0 CHECK(balance>=0), low_balance_threshold DECIMAL(20,4) NOT NULL DEFAULT 10000.00 CHECK(low_balance_threshold>0), created_at TIMESTAMPTZ NOT NULL DEFAULT NOW(), updated_at TIMESTAMPTZ NOT NULL DEFAULT NOW(), created_by VARCHAR(120), updated_by VARCHAR(120). Balance updates must use SELECT FOR UPDATE; no application-level locking allowed. | • Create services/prefunding-balance/src/main/resources/db/migration/V201__prefunding_account.sql • Add CREATE TABLE prefunding_account with all columns and constraints • Add UNIQUE constraint on partner_id • Add index idx_prefunding_account_partner on prefunding_account(partner_id) • Add table comment stating SELECT FOR UPDATE is required for all balance mutations | services/prefunding-balance/src/main/resources/db/migration/V201__prefunding_account.sql | • Table DDL uses DECIMAL(20,4) for balance and low_balance_threshold • balance has CHECK (balance >= 0) constraint • partner_id has UNIQUE constraint enforcing one account per OVERSEAS partner • currency DEFAULT 'USD' is present • Flyway applies migration cleanly against a Testcontainers Postgres 16 instance | 25 | 3.1-T01 | BE | DAT-03
3.5-T02 | prefunding | 3.5 | 3. Data Layer & Persistence | Prefunding ledger tables (double-entry) | 1 | Flyway migration: create prefunding_ledger_entry table (append-only double-entry) | prefunding_ledger_entry is an immutable append-only double-entry ledger in PostgreSQL 16 (svc-prefunding). Every debit or credit to a prefunding_account creates exactly one row; rows are NEVER updated or deleted. Schema: id BIGINT PK (sequence), account_id BIGINT NOT NULL FK->prefunding_account, txn_ref VARCHAR(64) NULL (references transaction.txn_ref for payment debits; internal reference for top-ups), entry_type VARCHAR(20) NOT NULL CHECK IN ('DEBIT_PAYMENT','DEBIT_REVERSAL','CREDIT_TOPUP','CREDIT_REVERSAL'), amount DECIMAL(20,4) NOT NULL CHECK(amount>0), balance_after DECIMAL(20,4) NOT NULL, note VARCHAR(255) NULL, created_at TIMESTAMPTZ NOT NULL DEFAULT NOW(), created_by VARCHAR(120) NULL. No updated_at column. | • Create services/prefunding-balance/src/main/resources/db/migration/V202__prefunding_ledger_entry.sql • Add CREATE TABLE prefunding_ledger_entry with all columns, PK, FK to prefunding_account, and CHECK constraints • Omit updated_at intentionally (append-only invariant) • Add compound index idx_ple_account_time on prefunding_ledger_entry(account_id, created_at) for history queries • Add partial index idx_ple_txn_ref on prefunding_ledger_entry(txn_ref) WHERE txn_ref IS NOT NULL | services/prefunding-balance/src/main/resources/db/migration/V202__prefunding_ledger_entry.sql | • entry_type CHECK constraint lists exactly: DEBIT_PAYMENT, DEBIT_REVERSAL, CREDIT_TOPUP, CREDIT_REVERSAL • amount has CHECK (amount > 0) • No updated_at column in DDL • Compound index (account_id, created_at) is present • Flyway applies migration after V201 with no errors in Testcontainers Postgres 16 | 25 | 3.5-T01 | BE | DAT-03
3.5-T03 | prefunding | 3.5 | 3. Data Layer & Persistence | Prefunding ledger tables (double-entry) | 1 | Flyway migration: create low_balance_alert_config table | low_balance_alert_config stores per-partner configurable low-balance alert settings in PostgreSQL 16 (svc-prefunding). Schema: id BIGINT PK (sequence), partner_id BIGINT NOT NULL FK->partner UNIQUE, threshold_usd DECIMAL(20,4) NOT NULL DEFAULT 10000.00 CHECK(threshold_usd>0), alert_email VARCHAR(255) NOT NULL, is_active BOOLEAN NOT NULL DEFAULT TRUE, created_at TIMESTAMPTZ NOT NULL DEFAULT NOW(), updated_at TIMESTAMPTZ NOT NULL DEFAULT NOW(), created_by VARCHAR(120), updated_by VARCHAR(120). The default alert threshold matches the alert threshold mentioned in the spec (USD 10,000 per partner). Changing threshold only affects future alert evaluations. | • Create services/prefunding-balance/src/main/resources/db/migration/V203__low_balance_alert_config.sql • Add CREATE TABLE low_balance_alert_config with all columns, PK, FK, CHECK, and UNIQUE constraints • Add index idx_lbac_partner on low_balance_alert_config(partner_id) | services/prefunding-balance/src/main/resources/db/migration/V203__low_balance_alert_config.sql | • partner_id has UNIQUE constraint (one config per partner) • threshold_usd has CHECK (threshold_usd > 0) and DEFAULT 10000.00 • is_active DEFAULT TRUE is present • Flyway applies migration after V202 with no errors • All three prefunding tables visible via \dt in psql after full V201-V203 migration run | 20 | 3.5-T02 | BE | DAT-03
3.5-T04 | prefunding | 3.5 | 3. Data Layer & Persistence | Prefunding ledger tables (double-entry) | 1 | Flyway migration: create outbox_event table for transactional outbox in svc-prefunding | Per STACK.md messaging strategy: Phase 1 uses a transactional Outbox table written in the same DB transaction as balance updates; Kafka transport wired in integration phase. The svc-prefunding service writes domain events (e.g. prefunding.low_balance) into outbox_event atomically. Schema in PostgreSQL 16: id BIGINT PK (sequence), aggregate_type VARCHAR(80) NOT NULL, aggregate_id VARCHAR(80) NOT NULL, event_type VARCHAR(120) NOT NULL, payload JSONB NOT NULL, created_at TIMESTAMPTZ NOT NULL DEFAULT NOW(), published_at TIMESTAMPTZ NULL, status VARCHAR(20) NOT NULL DEFAULT 'PENDING' CHECK IN ('PENDING','PUBLISHED','FAILED'). Partial index on status='PENDING' for efficient polling. | • Create services/prefunding-balance/src/main/resources/db/migration/V204__outbox_event.sql • Add CREATE TABLE outbox_event with all columns and CHECK on status • Add partial index idx_outbox_pending on outbox_event(created_at) WHERE status='PENDING' • Add comment: published_at set by outbox-poller when event forwarded to Kafka (integration phase) | services/prefunding-balance/src/main/resources/db/migration/V204__outbox_event.sql | • status CHECK constraint includes exactly PENDING, PUBLISHED, FAILED • Partial index WHERE status='PENDING' is present in DDL • payload is type JSONB • published_at is nullable • Flyway applies migration after V203 with no errors | 20 | 3.5-T03 | BE | DAT-03
3.5-T05 | prefunding | 3.5 | 3. Data Layer & Persistence | Prefunding ledger tables (double-entry) | 1 | Flyway migration: seed default low_balance_alert_config for existing OVERSEAS partners | After schema migrations V201-V204, data migration V205 inserts a default low_balance_alert_config row for every OVERSEAS partner that does not yet have one (threshold_usd=10000.00, is_active=TRUE). This ensures the low-balance check in AtomicPrefundingDeductService never fails due to missing config. Uses INSERT ... WHERE NOT EXISTS for idempotency. OVERSEAS partner type stored in partner.type column as 'OVERSEAS'. | • Create services/prefunding-balance/src/main/resources/db/migration/V205__seed_low_balance_alert_config.sql • Write INSERT INTO low_balance_alert_config(partner_id, threshold_usd, alert_email, is_active, created_by) SELECT p.id, 10000.00, COALESCE(p.ops_email,'ops@gme.com'), TRUE, 'system' FROM partner p WHERE p.type='OVERSEAS' AND NOT EXISTS (SELECT 1 FROM low_balance_alert_config l WHERE l.partner_id=p.id) • Confirm idempotency: running the SQL twice must produce no duplicate rows and no error | services/prefunding-balance/src/main/resources/db/migration/V205__seed_low_balance_alert_config.sql | • Running V205 twice does not produce duplicates or errors (idempotent via WHERE NOT EXISTS) • Every OVERSEAS partner has exactly one low_balance_alert_config row after migration • threshold_usd=10000.00 and is_active=TRUE for all seeded rows • LOCAL partner rows are NOT inserted • Flyway applies V205 cleanly after V204 | 20 | 3.5-T03 | BE | DAT-03
3.5-T06 | prefunding | 3.5 | 3. Data Layer & Persistence | Prefunding ledger tables (double-entry) | 1 | Define PrefundingAccount and PrefundingLedgerEntry JPA entities in svc-prefunding | Module: services/prefunding-balance (:svc-prefunding). Spring Boot 3.x / Spring Data JPA. PrefundingAccount maps to prefunding_account; PrefundingLedgerEntry maps to prefunding_ledger_entry. All money fields DECIMAL mapped to java.math.BigDecimal with @Column(precision=20, scale=4). EntryType Java enum: DEBIT_PAYMENT, DEBIT_REVERSAL, CREDIT_TOPUP, CREDIT_REVERSAL persisted as VARCHAR. PrefundingLedgerEntry is immutable post-persist: no setters, all fields set via constructor, @Column(updatable=false) on every field. PrefundingAccount.balance is only mutated by the domain service via the atomic deduction/credit method. | • Create PrefundingAccount.java at services/prefunding-balance/src/main/java/com/gme/pay/prefunding/domain/PrefundingAccount.java with @Entity and all columns • Create EntryType.java enum at com/gme/pay/prefunding/domain/EntryType.java with 4 values • Create PrefundingLedgerEntry.java at com/gme/pay/prefunding/domain/PrefundingLedgerEntry.java with @Entity, all fields @Column(updatable=false), constructor-only init • Annotate all money BigDecimal fields with @Column(precision=20, scale=4) | services/prefunding-balance/src/main/java/com/gme/pay/prefunding/domain/PrefundingAccount.java and PrefundingLedgerEntry.java | • BigDecimal used for balance, low_balance_threshold, amount, balance_after — no double or float • PrefundingLedgerEntry has no setter methods (immutable by design) • EntryType enum has exactly 4 values matching the DB CHECK constraint • @Column(precision=20, scale=4) present on all money fields • @DataJpaTest slice with Testcontainers Postgres 16: save PrefundingAccount then findById returns equal BigDecimal balance | 35 | 3.5-T02 | BE | DAT-03
3.5-T07 | prefunding | 3.5 | 3. Data Layer & Persistence | Prefunding ledger tables (double-entry) | 1 | Define LowBalanceAlertConfig entity and Spring Data repositories | Module: :svc-prefunding. LowBalanceAlertConfig JPA entity maps to low_balance_alert_config. Repositories needed: PrefundingAccountRepository (JpaRepository) with lockByPartnerId using @Lock(LockModeType.PESSIMISTIC_WRITE) — this is the SELECT FOR UPDATE path for atomic deductions; PrefundingLedgerEntryRepository (JpaRepository) with findByAccountIdOrderByCreatedAtDesc(Pageable); LowBalanceAlertConfigRepository with findByPartnerId and findByPartnerIdAndIsActiveTrue. | • Create LowBalanceAlertConfig.java entity at com/gme/pay/prefunding/domain/LowBalanceAlertConfig.java • Create PrefundingAccountRepository.java interface with @Lock(PESSIMISTIC_WRITE) method: findByPartnerId annotated with @Lock(LockModeType.PESSIMISTIC_WRITE) and @QueryHints for timeout • Create PrefundingLedgerEntryRepository.java with findByAccountIdOrderByCreatedAtDesc(Pageable p) • Create LowBalanceAlertConfigRepository.java with findByPartnerId and findByPartnerIdAndIsActiveTrue | services/prefunding-balance/src/main/java/com/gme/pay/prefunding/repository/ (3 repository interfaces + LowBalanceAlertConfig entity) | • PrefundingAccountRepository locking method carries @Lock(PESSIMISTIC_WRITE) annotation • findByAccountIdOrderByCreatedAtDesc accepts Pageable parameter and returns Page • LowBalanceAlertConfigRepository.findByPartnerIdAndIsActiveTrue returns only is_active=TRUE configs • @DataJpaTest slice with Testcontainers Postgres 16 confirms lockByPartnerId issues SELECT FOR UPDATE (verify via pg_stat_activity in concurrent test) | 35 | 3.5-T06 | BE | DAT-03
3.5-T08 | prefunding | 3.5 | 3. Data Layer & Persistence | Prefunding ledger tables (double-entry) | 1 | Implement AtomicPrefundingDeductService: SELECT FOR UPDATE deduction with ledger entry | Module: :svc-prefunding. Core deduction rule from spec: deduction is ATOMIC using SELECT FOR UPDATE. Steps inside a single @Transactional method: (1) lock prefunding_account row via PrefundingAccountRepository @Lock(PESSIMISTIC_WRITE) by partnerId, (2) if balance < deductionAmountUsd throw InsufficientPrefundingException (error code INSUFFICIENT_PREFUNDING from lib-errors), (3) account.balance -= deductionAmountUsd, (4) insert PrefundingLedgerEntry(type=DEBIT_PAYMENT, amount=deductionAmountUsd, balanceAfter=newBalance, txnRef=txnRef), (5) if newBalance < account.lowBalanceThreshold insert OutboxEvent(aggregate_type='prefunding_account', event_type='prefunding.low_balance', payload={partnerId, newBalance, thresholdUsd}). Return DeductionResult(newBalance, ledgerEntryId). Scheme is never called without a prior committed deduction. | • Create AtomicPrefundingDeductService.java at com/gme/pay/prefunding/service/AtomicPrefundingDeductService.java @Service • Inject PrefundingAccountRepository, PrefundingLedgerEntryRepository, OutboxEventRepository • Implement deduct(Long partnerId, BigDecimal amountUsd, String txnRef): DeductionResult annotated @Transactional • Throw InsufficientPrefundingException from lib-errors when balance < amount • Insert OutboxEvent in the same transaction when post-deduction balance < low_balance_threshold | services/prefunding-balance/src/main/java/com/gme/pay/prefunding/service/AtomicPrefundingDeductService.java | • @Transactional annotation present on the deduct method • InsufficientPrefundingException thrown when balance=100.00 and deduction=100.01 • Ledger entry balance_after equals account balance after deduction (e.g. balance=500, deduct=36.9714, balance_after=463.0286) • OutboxEvent with event_type='prefunding.low_balance' inserted when new balance < low_balance_threshold • No OutboxEvent inserted when new balance >= threshold | 45 | 3.5-T07, 3.5-T04 | BE | DAT-03
3.5-T09 | prefunding | 3.5 | 3. Data Layer & Persistence | Prefunding ledger tables (double-entry) | 1 | Implement PrefundingCreditService: CREDIT_TOPUP and CREDIT_REVERSAL with ledger entries | Module: :svc-prefunding. Two credit operations use a common atomic pattern: CREDIT_TOPUP (manual top-up by ops) and CREDIT_REVERSAL (reverse a prior DEBIT_PAYMENT when scheme call fails after deduction per spec sec 5.2: UNCERTAIN resolution). Both lock prefunding_account with SELECT FOR UPDATE, increase balance, and insert a PrefundingLedgerEntry. Reversal guards: check no existing CREDIT_REVERSAL for the same txnRef (duplicate reversal must throw DuplicateReversalException). CREDIT_TOPUP reference is an internal ops reference, not a txnRef. Credit does not trigger low-balance check (balance increasing). | • Create PrefundingCreditService.java at com/gme/pay/prefunding/service/PrefundingCreditService.java @Service • Implement topUp(Long partnerId, BigDecimal amountUsd, String reference, String actor): @Transactional — lock row, add amount, insert CREDIT_TOPUP ledger entry • Implement reverse(Long partnerId, BigDecimal amountUsd, String originalTxnRef, String actor): @Transactional — check no existing CREDIT_REVERSAL for txnRef, lock row, add amount, insert CREDIT_REVERSAL entry • Throw DuplicateReversalException (lib-errors) if CREDIT_REVERSAL for that txnRef already exists | services/prefunding-balance/src/main/java/com/gme/pay/prefunding/service/PrefundingCreditService.java | • topUp increases balance by exact BigDecimal amount and inserts CREDIT_TOPUP ledger row • reverse inserts CREDIT_REVERSAL row and restores balance • Second reverse call with same txnRef throws DuplicateReversalException; balance unchanged • balance_after in ledger entry equals account.balance after operation • Both topUp and reverse annotated @Transactional | 40 | 3.5-T07 | BE | DAT-03
3.5-T10 | prefunding | 3.5 | 3. Data Layer & Persistence | Prefunding ledger tables (double-entry) | 1 | Implement PrefundingBalanceQueryService: current balance and paginated ledger history | Module: :svc-prefunding. OVERSEAS partners can query current balance via GET /v1/balance. LOCAL partners (partner.type=LOCAL) receive HTTP 403 (PartnerTypeNotEligibleException). getBalance(Long partnerId): @Transactional(readOnly=true), load account, throw AccountNotFoundException if missing. getLedgerHistory(Long partnerId, Pageable pageable): @Transactional(readOnly=true), return Page<PrefundingLedgerEntry> ordered by created_at DESC. No SELECT FOR UPDATE needed — read-only. Partner type resolved from partner registry (Config & Registry service or local partner table). | • Create PrefundingBalanceQueryService.java at com/gme/pay/prefunding/service/PrefundingBalanceQueryService.java @Service • Implement getBalance(Long partnerId): @Transactional(readOnly=true), throw AccountNotFoundException if no row found • Implement getLedgerHistory(Long partnerId, Pageable pageable): @Transactional(readOnly=true), delegate to PrefundingLedgerEntryRepository.findByAccountIdOrderByCreatedAtDesc • Validate partner type before serving: LOCAL -> throw PartnerTypeNotEligibleException(PREFUNDING_NOT_APPLICABLE) | services/prefunding-balance/src/main/java/com/gme/pay/prefunding/service/PrefundingBalanceQueryService.java | • getBalance returns correct BigDecimal for OVERSEAS partner • getLedgerHistory returns entries in descending created_at order • PartnerTypeNotEligibleException thrown for LOCAL partner • @Transactional(readOnly=true) on both methods • Testcontainers integration test: insert 5 ledger rows, getLedgerHistory page 0 size 3 returns 3 rows; page 1 size 3 returns 2 rows and hasNext=false | 30 | 3.5-T07 | BE | DAT-03
3.5-T11 | prefunding | 3.5 | 3. Data Layer & Persistence | Prefunding ledger tables (double-entry) | 1 | Define PrefundingLowBalanceEvent record and OutboxEvent entity in lib-events and svc-prefunding | Per STACK.md: define event schemas in lib-events now; Kafka wired in integration phase. PrefundingLowBalanceEvent(Long partnerId, BigDecimal currentBalanceUsd, BigDecimal thresholdUsd, Instant occurredAt) as a Java record in lib-events. OutboxEvent JPA entity in svc-prefunding: id BIGINT PK, aggregate_type VARCHAR(80), aggregate_id VARCHAR(80), event_type VARCHAR(120), payload stored as String (serialized JSON), created_at TIMESTAMPTZ, published_at TIMESTAMPTZ nullable, status OutboxStatus enum (PENDING, PUBLISHED, FAILED). OutboxEventRepository provides findTop100ByStatusOrderByCreatedAtAsc for outbox polling. | • Create PrefundingLowBalanceEvent.java at libs/lib-events/src/main/java/com/gme/pay/events/prefunding/PrefundingLowBalanceEvent.java as a Java record with 4 fields • Create OutboxStatus.java enum at com/gme/pay/prefunding/outbox/OutboxStatus.java: PENDING, PUBLISHED, FAILED • Create OutboxEvent.java @Entity at com/gme/pay/prefunding/outbox/OutboxEvent.java mapping to outbox_event table • Create OutboxEventRepository.java extending JpaRepository with findTop100ByStatusOrderByCreatedAtAsc(OutboxStatus status) | libs/lib-events/src/main/java/com/gme/pay/events/prefunding/PrefundingLowBalanceEvent.java and services/prefunding-balance/src/main/java/com/gme/pay/prefunding/outbox/OutboxEvent.java | • PrefundingLowBalanceEvent is a Java record with 4 fields: partnerId, currentBalanceUsd, thresholdUsd, occurredAt • OutboxEvent maps to outbox_event table with correct column names and JSONB-backed String payload • OutboxStatus enum has exactly 3 values: PENDING, PUBLISHED, FAILED • findTop100ByStatusOrderByCreatedAtAsc compiles and returns correct rows in @DataJpaTest slice with Testcontainers Postgres 16 | 30 | 3.5-T04 | BE | DAT-03
3.5-T12 | prefunding | 3.5 | 3. Data Layer & Persistence | Prefunding ledger tables (double-entry) | 1 | Implement OutboxEventPublisher interface and in-process polling publisher | Module: :svc-prefunding. Per STACK.md: define EventPublisher interface now; Kafka is the integration-phase transport. EventPublisher interface: void publish(OutboxEvent event). InProcessEventPublisher implements EventPublisher: logs the event payload (Phase 1 placeholder). OutboxPollingPublisher @Component with @Scheduled(fixedDelay=5000): polls up to 100 PENDING rows via OutboxEventRepository, calls publisher, marks each PUBLISHED (sets published_at=NOW()); on exception marks FAILED. Each row processed in its own @Transactional to avoid all-or-nothing batch failure. @EnableScheduling in PrefundingBalanceApplication. | • Create EventPublisher.java interface at com/gme/pay/prefunding/outbox/EventPublisher.java • Create InProcessEventPublisher.java @Component implementing EventPublisher — logs event type and aggregate_id, Phase 1 placeholder • Create OutboxPollingPublisher.java @Component with @Scheduled(fixedDelay=5000) calling OutboxEventRepository.findTop100ByStatusOrderByCreatedAtAsc(PENDING) • Wrap each row's processing in @Transactional(propagation=REQUIRES_NEW) to isolate failures • Confirm @EnableScheduling in PrefundingBalanceApplication.java | services/prefunding-balance/src/main/java/com/gme/pay/prefunding/outbox/OutboxPollingPublisher.java | • OutboxPollingPublisher fetches at most 100 PENDING rows per polling cycle • Status transitions PENDING -> PUBLISHED after successful publish call • Status transitions PENDING -> FAILED on exception without affecting other rows in same batch • @Transactional(REQUIRES_NEW) per-row processing confirmed by inspecting annotation • @EnableScheduling present in application context | 35 | 3.5-T11 | BE | DAT-03
3.5-T13 | prefunding | 3.5 | 3. Data Layer & Persistence | Prefunding ledger tables (double-entry) | 1 | Expose internal REST endpoints for Transaction Orchestrator (POST /internal/v1/prefunding) | Module: :svc-prefunding. The Transaction Orchestrator (svc-payment-executor) calls svc-prefunding via internal REST. @RestController at /internal/v1/prefunding. Endpoints: POST /deduct body {partnerId, amountUsd, txnRef} -> 200 {newBalance, ledgerEntryId} or 402 INSUFFICIENT_PREFUNDING; POST /credit body {partnerId, amountUsd, txnRef, creditType: CREDIT_TOPUP¦CREDIT_REVERSAL} -> 200 {newBalance, ledgerEntryId}; GET /{partnerId}/balance -> 200 {balance, currency:'USD'}. Spring Security: require ROLE_INTERNAL_SERVICE on all three endpoints. Map InsufficientPrefundingException to HTTP 402 via lib-errors GlobalExceptionHandler. | • Create PrefundingInternalController.java at com/gme/pay/prefunding/api/internal/PrefundingInternalController.java @RestController @RequestMapping('/internal/v1/prefunding') • Wire AtomicPrefundingDeductService, PrefundingCreditService, PrefundingBalanceQueryService • Create request/response DTOs: DeductRequest, DeductResponse, CreditRequest, CreditResponse, BalanceResponse in com.gme.pay.prefunding.api.internal.dto • Add @PreAuthorize('hasRole(INTERNAL_SERVICE)') or Spring Security matcher for /internal/** -> ROLE_INTERNAL_SERVICE • Map InsufficientPrefundingException to HTTP 402 in lib-errors GlobalExceptionHandler or local @ExceptionHandler | services/prefunding-balance/src/main/java/com/gme/pay/prefunding/api/internal/PrefundingInternalController.java | • POST /internal/v1/prefunding/deduct with insufficient balance returns HTTP 402 and error code INSUFFICIENT_PREFUNDING • POST /internal/v1/prefunding/deduct with sufficient balance returns 200 and correct newBalance • GET /internal/v1/prefunding/{partnerId}/balance returns {balance, currency:'USD'} • Request without ROLE_INTERNAL_SERVICE returns HTTP 403 • @WebMvcTest slice covers all three endpoints with MockMvc | 40 | 3.5-T08, 3.5-T09, 3.5-T10 | BE | DAT-03
3.5-T14 | prefunding | 3.5 | 3. Data Layer & Persistence | Prefunding ledger tables (double-entry) | 1 | Expose partner-facing GET /v1/balance endpoint in svc-prefunding | Module: :svc-prefunding. Per API-05 spec: GET /v1/balance returns calling OVERSEAS partner's current USD balance. LOCAL partners receive HTTP 403 with error code PREFUNDING_NOT_APPLICABLE. Partner identity extracted from JWT claim partner_id via SecurityContextHolder. Response: {balance: Decimal string, currency: 'USD', lowBalanceThreshold: Decimal string}. Balance serialized as string (not JSON number) to preserve DECIMAL(20,4) precision and avoid floating-point representation issues. Spring Security: require ROLE_PARTNER scope. | • Create PrefundingPartnerController.java at com/gme/pay/prefunding/api/partner/PrefundingPartnerController.java @RestController @RequestMapping('/v1/balance') • Extract partner_id from JWT claims via SecurityContextHolder JWT authentication • Call PrefundingBalanceQueryService.getBalance and load low_balance_threshold from account entity • Map PartnerTypeNotEligibleException to HTTP 403 with PREFUNDING_NOT_APPLICABLE code • Add OpenAPI annotations; serialize BigDecimal fields as strings in DTO using @JsonSerialize | services/prefunding-balance/src/main/java/com/gme/pay/prefunding/api/partner/PrefundingPartnerController.java | • OVERSEAS partner JWT returns 200 with balance and currency='USD' and lowBalanceThreshold • LOCAL partner JWT returns 403 with error code PREFUNDING_NOT_APPLICABLE • Missing or expired JWT returns 401 • balance field is serialized as a string not a JSON number (e.g. '5000.0000' not 5000.0) • @WebMvcTest slice confirms all three cases | 35 | 3.5-T10, 3.5-T13 | BE | DAT-03
3.5-T15 | prefunding | 3.5 | 3. Data Layer & Persistence | Prefunding ledger tables (double-entry) | 1 | Gradle module setup and Spring Boot application bootstrap for svc-prefunding | Module: services/prefunding-balance (:svc-prefunding). Create the Gradle sub-module, Spring Boot 3.x main class, and application.yml baseline. Dependencies: spring-boot-starter-data-jpa, spring-boot-starter-web, spring-boot-starter-security, spring-boot-starter-actuator, postgresql driver, flyway-core, micrometer-tracing-bridge-otel, opentelemetry-exporter-otlp, :lib-money, :lib-errors, :lib-api-contracts, :lib-events. application.yml: spring.datasource pointing to Postgres, spring.flyway.locations=classpath:db/migration, spring.jpa.hibernate.ddl-auto=validate, server.port=8085. Add module to root settings.gradle. | • Create services/prefunding-balance/build.gradle with all required dependencies and Java 21 toolchain • Add ':svc-prefunding' (include 'services/prefunding-balance') to root settings.gradle • Create PrefundingBalanceApplication.java at com/gme/pay/prefunding/PrefundingBalanceApplication.java with @SpringBootApplication and @EnableScheduling • Create src/main/resources/application.yml with datasource, flyway, jpa, server, and actuator config • Run ./gradlew :svc-prefunding:compileJava to confirm compilation succeeds | services/prefunding-balance/build.gradle and services/prefunding-balance/src/main/java/com/gme/pay/prefunding/PrefundingBalanceApplication.java | • ./gradlew :svc-prefunding:compileJava succeeds • @EnableScheduling present (required for outbox poller) • spring.jpa.hibernate.ddl-auto=validate (Flyway is sole schema manager) • Module listed in root settings.gradle • lib-money and lib-errors listed as implementation dependencies | 30 | 3.5-T01 | BE | DAT-03
3.5-T16 | prefunding | 3.5 | 3. Data Layer & Persistence | Prefunding ledger tables (double-entry) | 1 | Add OpenTelemetry tracing spans to deduction and credit service methods | Module: :svc-prefunding. Per STACK.md: OpenTelemetry traces exported to Jaeger via OTLP. Add manual OTel spans wrapping the core business methods using Micrometer Tracing (Spring Boot auto-configured via micrometer-tracing-bridge-otel). Span names: 'prefunding.deduct', 'prefunding.credit.topup', 'prefunding.credit.reversal'. Span attributes: partner_id (Long), amount_usd (String). On InsufficientPrefundingException: record exception on span and set span status to ERROR. application.yml: management.otlp.tracing.endpoint=http://localhost:4318/v1/traces. | • Add micrometer-tracing-bridge-otel and opentelemetry-exporter-otlp to build.gradle (if not already present from 3.5-T15) • Inject io.micrometer.tracing.Tracer bean into AtomicPrefundingDeductService and PrefundingCreditService • Wrap deduction logic in Tracer.nextSpan('prefunding.deduct').start(); use try-with-resources (Tracer.SpanInScope) • Tag spans with partner_id and amount_usd attributes • On InsufficientPrefundingException call span.error(exception) before rethrowing • Add management.otlp.tracing.endpoint to application.yml | Updated AtomicPrefundingDeductService.java and PrefundingCreditService.java with Micrometer Tracing spans | • Span 'prefunding.deduct' started and ended for every deduct invocation • InsufficientPrefundingException causes span error flag to be set • Span attributes include partner_id and amount_usd • application.yml contains management.otlp.tracing.endpoint • ./gradlew :svc-prefunding:compileJava succeeds | 35 | 3.5-T08, 3.5-T09, 3.5-T15 | BE | DAT-03
3.5-T17 | prefunding | 3.5 | 3. Data Layer & Persistence | Prefunding ledger tables (double-entry) | 1 | Prometheus metrics: prefunding balance gauge and deduction/credit counters | Module: :svc-prefunding. Per STACK.md: Prometheus + Grafana for metrics. Using Micrometer auto-configured by Spring Boot Actuator. Metrics: (1) Gauge 'prefunding.balance.usd' with tag partner_id reporting current balance for each OVERSEAS partner (polled every 30s via @Scheduled). (2) Counter 'prefunding.deduction.count' with tags partner_id, result (success¦insufficient) in AtomicPrefundingDeductService. (3) Counter 'prefunding.credit.count' with tags partner_id, entry_type in PrefundingCreditService. Expose /actuator/prometheus. Alert threshold per spec: balance < 10000 USD per partner. | • Inject MeterRegistry into AtomicPrefundingDeductService and PrefundingCreditService • Register Counter 'prefunding.deduction.count' with tags partner_id and result in deduct method • Register Counter 'prefunding.credit.count' with tags partner_id and entry_type in topUp and reverse • Create PrefundingMetricsCollector.java @Component at com/gme/pay/prefunding/metrics/PrefundingMetricsCollector.java with @Scheduled(fixedDelay=30000) reading all OVERSEAS balances and updating MultiGauge or individual Gauges • Add management.endpoints.web.exposure.include=health,prometheus to application.yml | services/prefunding-balance/src/main/java/com/gme/pay/prefunding/metrics/PrefundingMetricsCollector.java | • GET /actuator/prometheus includes prefunding_deduction_count_total with result and partner_id labels • GET /actuator/prometheus includes prefunding_balance_usd gauge with partner_id label • Counter incremented on both success and insufficient deduction with correct result tag • PrefundingMetricsCollector @Scheduled method has fixedDelay=30000 • ./gradlew :svc-prefunding:compileJava succeeds | 35 | 3.5-T08, 3.5-T09, 3.5-T15 | BE | DAT-03
3.5-T18 | prefunding | 3.5 | 3. Data Layer & Persistence | Prefunding ledger tables (double-entry) | 1 | Unit tests: AtomicPrefundingDeductService — deduction logic and invariants | Module: :svc-prefunding. Test class using JUnit 5 + Testcontainers Postgres 16 (@SpringBootTest). Test vectors: (A) balance=1000.00, deduct=36.9714 -> newBalance=963.0286, DEBIT_PAYMENT ledger row with balance_after=963.0286. (B) balance=100.00, deduct=100.0001 -> InsufficientPrefundingException; balance unchanged; no ledger row inserted. (C) deduct exactly to threshold: balance=10000.00, deduct=10000.00, low_balance_threshold=10000.00 -> newBalance=0.00, OutboxEvent with event_type='prefunding.low_balance' and payload containing partnerId and currentBalanceUsd=0.00. (D) deduct below threshold but not to zero: balance=500.00, deduct=100.00, threshold=10000.00 -> OutboxEvent inserted (500.00 < 10000.00 threshold). | • Create AtomicPrefundingDeductServiceTest.java at services/prefunding-balance/src/test/java/com/gme/pay/prefunding/service/AtomicPrefundingDeductServiceTest.java • Use @SpringBootTest + @Testcontainers + PostgreSQLContainer('postgres:16') • Seed prefunding_account and low_balance_alert_config rows in @BeforeEach • Implement test A, B, C, D as described in context • Assert exact BigDecimal values using compareTo(BigDecimal.ZERO)==0 style assertions | services/prefunding-balance/src/test/java/com/gme/pay/prefunding/service/AtomicPrefundingDeductServiceTest.java | • Test A: balance_after in DB equals 963.0286 (exact BigDecimal) • Test B: InsufficientPrefundingException thrown; prefunding_ledger_entry row count unchanged • Test C: outbox_event row has event_type='prefunding.low_balance' and payload.currentBalanceUsd=0.00 • Test D: OutboxEvent inserted when post-deduction balance 400.00 < threshold 10000.00 • All 4 tests pass with Testcontainers Postgres 16 | 45 | 3.5-T08, 3.5-T11 | BE | DAT-03
3.5-T19 | prefunding | 3.5 | 3. Data Layer & Persistence | Prefunding ledger tables (double-entry) | 1 | Unit tests: PrefundingCreditService — top-up and reversal logic | Module: :svc-prefunding. Test class using JUnit 5 + Testcontainers Postgres 16. Test vectors: (A) topUp: balance=500.00, credit=1000.00 -> newBalance=1500.00, CREDIT_TOPUP ledger row with balance_after=1500.00. (B) reverse: start balance=500.00, deduct 36.97 (balance=463.03), then reverse txnRef -> newBalance=500.00, CREDIT_REVERSAL row referencing original txnRef with balance_after=500.00. (C) duplicate reversal: call reverse same txnRef twice -> second call throws DuplicateReversalException; balance remains 500.00 after second call. (D) topUp does NOT insert OutboxEvent (only deductions trigger low-balance check). | • Create PrefundingCreditServiceTest.java at services/prefunding-balance/src/test/java/com/gme/pay/prefunding/service/PrefundingCreditServiceTest.java • Use @SpringBootTest + Testcontainers Postgres 16 • Seed prefunding_account row in @BeforeEach • Implement tests A, B, C, D as specified • Verify ledger rows via PrefundingLedgerEntryRepository queries | services/prefunding-balance/src/test/java/com/gme/pay/prefunding/service/PrefundingCreditServiceTest.java | • Test A: balance=1500.0000 and CREDIT_TOPUP ledger row present with balance_after=1500.0000 • Test B: balance restored to 500.0000 and CREDIT_REVERSAL row txn_ref matches original • Test C: DuplicateReversalException on second reverse; balance remains 500.0000 • Test D: outbox_event count=0 after topUp • All 4 tests pass | 40 | 3.5-T09 | BE | DAT-03
3.5-T20 | prefunding | 3.5 | 3. Data Layer & Persistence | Prefunding ledger tables (double-entry) | 1 | Unit tests: PrefundingBalanceQueryService — balance query and LOCAL partner rejection | Module: :svc-prefunding. Test class using JUnit 5 + Testcontainers Postgres 16. Test vectors: (A) getBalance for OVERSEAS partner with balance=5000.00 returns BigDecimal(5000.0000). (B) getLedgerHistory: 5 ledger entries inserted, request page 0 size 3 returns 3 entries in descending created_at order; page 1 size 3 returns 2 entries with hasNext=false. (C) LOCAL partner type call to getBalance throws PartnerTypeNotEligibleException. (D) unknown partnerId throws AccountNotFoundException. | • Create PrefundingBalanceQueryServiceTest.java at services/prefunding-balance/src/test/java/com/gme/pay/prefunding/service/PrefundingBalanceQueryServiceTest.java • Use @SpringBootTest + Testcontainers Postgres 16 • Seed OVERSEAS and LOCAL partner rows plus prefunding_account and 5 ledger entries in @BeforeEach • Implement 4 test cases as specified | services/prefunding-balance/src/test/java/com/gme/pay/prefunding/service/PrefundingBalanceQueryServiceTest.java | • Test A: returned BigDecimal equals 5000.0000 (BigDecimal.compareTo) • Test B: page 0 has 3 entries; page 1 has 2 entries; entries are in DESC created_at order • Test C: PartnerTypeNotEligibleException thrown for LOCAL partner • Test D: AccountNotFoundException thrown for unknown partnerId • All 4 tests pass | 35 | 3.5-T10 | BE | DAT-03
3.5-T21 | prefunding | 3.5 | 3. Data Layer & Persistence | Prefunding ledger tables (double-entry) | 1 | Unit tests: PrefundingInternalController — deduct, credit, balance endpoints | Module: :svc-prefunding. @WebMvcTest slice with Mockito. Test vectors: (A) POST /internal/v1/prefunding/deduct valid body -> 200 with newBalance. (B) POST /internal/v1/prefunding/deduct -> service throws InsufficientPrefundingException -> HTTP 402 body error code INSUFFICIENT_PREFUNDING. (C) POST /internal/v1/prefunding/credit creditType=CREDIT_REVERSAL -> 200. (D) GET /internal/v1/prefunding/42/balance -> 200 jsonPath $.balance='5000.0000' $.currency='USD'. (E) Request without ROLE_INTERNAL_SERVICE -> 403. | • Create PrefundingInternalControllerTest.java at services/prefunding-balance/src/test/java/com/gme/pay/prefunding/api/internal/PrefundingInternalControllerTest.java • Use @WebMvcTest(PrefundingInternalController.class) + @MockBean for service layer • Set up Spring Security test context with ROLE_INTERNAL_SERVICE for happy-path tests • Implement 5 test cases using MockMvc and jsonPath assertions • No real DB or Testcontainers — pure MockMvc with mocked services | services/prefunding-balance/src/test/java/com/gme/pay/prefunding/api/internal/PrefundingInternalControllerTest.java | • Test B returns HTTP 402 and jsonPath $.errorCode == 'INSUFFICIENT_PREFUNDING' • Test D: jsonPath $.currency == 'USD' and $.balance is a JSON string '5000.0000' • Test E returns HTTP 403 • All 5 tests pass with @WebMvcTest slice • No Testcontainers required in this test class | 35 | 3.5-T13 | BE | DAT-03
3.5-T22 | prefunding | 3.5 | 3. Data Layer & Persistence | Prefunding ledger tables (double-entry) | 1 | Unit tests: PrefundingPartnerController — GET /v1/balance partner-facing endpoint | Module: :svc-prefunding. @WebMvcTest slice with Mockito. Test vectors: (A) Valid OVERSEAS JWT -> 200, {balance:'5000.0000', currency:'USD', lowBalanceThreshold:'10000.0000'} (all as strings). (B) LOCAL partner JWT -> 403, error code PREFUNDING_NOT_APPLICABLE. (C) No Authorization header -> 401. (D) Expired JWT -> 401. Balance fields must be serialized as strings (not JSON numbers) to preserve DECIMAL(20,4) precision. | • Create PrefundingPartnerControllerTest.java at services/prefunding-balance/src/test/java/com/gme/pay/prefunding/api/partner/PrefundingPartnerControllerTest.java • Use @WebMvcTest(PrefundingPartnerController.class) + @MockBean for PrefundingBalanceQueryService • Create test JWTs with partner_id claim and partner type using Spring Security test support • Implement 4 test cases using MockMvc and jsonPath assertions | services/prefunding-balance/src/test/java/com/gme/pay/prefunding/api/partner/PrefundingPartnerControllerTest.java | • Test A: jsonPath $.balance is string '5000.0000' (not a numeric literal) • Test A: jsonPath $.lowBalanceThreshold is string '10000.0000' • Test B: HTTP 403 with PREFUNDING_NOT_APPLICABLE error code • Tests C and D return HTTP 401 • All 4 tests pass | 30 | 3.5-T14 | BE | DAT-03
3.5-T23 | prefunding | 3.5 | 3. Data Layer & Persistence | Prefunding ledger tables (double-entry) | 1 | Integration test: full deduction-then-reversal lifecycle with real Postgres | Module: :svc-prefunding. End-to-end lifecycle test with Testcontainers Postgres 16 (no mocks for DB layer): (1) create account balance=1000.0000, (2) DEBIT_PAYMENT 36.9714 -> balance=963.0286, (3) simulate scheme failure then CREDIT_REVERSAL 36.9714 -> balance=1000.0000, (4) assert 2 ledger rows in order with correct balance_after chain: first row balance_after=963.0286, second row balance_after=1000.0000. Pool identity: DEBIT_PAYMENT.amount == CREDIT_REVERSAL.amount == 36.9714. | • Create PrefundingLifecycleIntegrationTest.java at services/prefunding-balance/src/test/java/com/gme/pay/prefunding/PrefundingLifecycleIntegrationTest.java • Use @SpringBootTest + @Testcontainers + @Container PostgreSQLContainer('postgres:16') • Seed OVERSEAS partner and prefunding_account in @BeforeEach • Call AtomicPrefundingDeductService.deduct then PrefundingCreditService.reverse • Assert balance, ledger rows, and chain consistency | services/prefunding-balance/src/test/java/com/gme/pay/prefunding/PrefundingLifecycleIntegrationTest.java | • Post-deduction balance=963.0286 (BigDecimal.compareTo) • Post-reversal balance=1000.0000 • Ledger has exactly 2 rows: DEBIT_PAYMENT then CREDIT_REVERSAL in created_at order • Chain: row1.balance_after + row2.amount = row2.balance_after (963.0286 + 36.9714 = 1000.0000) • No OutboxEvent inserted (threshold=10000, balance never drops below threshold in this path) | 45 | 3.5-T08, 3.5-T09 | BE | DAT-03
3.5-T24 | prefunding | 3.5 | 3. Data Layer & Persistence | Prefunding ledger tables (double-entry) | 1 | Integration test: concurrent deductions — SELECT FOR UPDATE prevents overdraft | Module: :svc-prefunding. Concurrency test with Testcontainers Postgres 16: two concurrent threads each attempt to deduct 600.00 USD from account balance=1000.00. The SELECT FOR UPDATE lock in AtomicPrefundingDeductService must serialize requests so exactly one succeeds (balance=400.00) and one throws InsufficientPrefundingException. Use CountDownLatch(1) to release both threads simultaneously. Final DB state must show balance=400.0000 and exactly 1 DEBIT_PAYMENT ledger row. Balance must never go negative. | • Create ConcurrentDeductionTest.java at services/prefunding-balance/src/test/java/com/gme/pay/prefunding/ConcurrentDeductionTest.java • Use @SpringBootTest + Testcontainers Postgres 16 • Create account with balance=1000.0000, low_balance_threshold=10000.00 • Use CountDownLatch(1) + ExecutorService(2 threads) to fire deductions simultaneously • Assert final balance=400.0000, exactly 1 ledger row, 1 success + 1 exception | services/prefunding-balance/src/test/java/com/gme/pay/prefunding/ConcurrentDeductionTest.java | • Final balance in DB is exactly 400.0000 • Exactly 1 DEBIT_PAYMENT ledger entry exists • Exactly 1 thread received InsufficientPrefundingException • prefunding_account.balance is never negative at any point • Test passes on 3 repeated runs without flakiness | 45 | 3.5-T08 | BE | DAT-03
3.6-T01 | security-platform | 3.6 | 3. Data Layer & Persistence | Audit log tables (immutable) | 1 | Create Flyway migration: audit_log base table in config-registry PostgreSQL | WBS 3.6 - Audit log tables (immutable). The audit_log table lives in the config-registry PostgreSQL 16 schema (same DB as partner, scheme, rule, treasury_rate). Columns per DAT-03 §10.7: id BIGINT PK auto-increment, actor_id VARCHAR(120) NOT NULL (operator user ID or SYSTEM), actor_type VARCHAR(20) NOT NULL CHECK IN ('OPERATOR','SYSTEM','PARTNER'), action VARCHAR(20) NOT NULL CHECK IN ('CREATE','UPDATE','DELETE','ACTIVATE','DEACTIVATE'), entity_type VARCHAR(50) NOT NULL (table name e.g. rule, partner, treasury_rate), entity_id BIGINT NOT NULL, before_value JSONB NULL (NULL for CREATE), after_value JSONB NULL (NULL for DELETE), occurred_at TIMESTAMPTZ NOT NULL DEFAULT NOW(), ip_address INET NULL, request_id VARCHAR(64) NULL. No UPDATE or DELETE ever permitted. Retention >= 7 years per SEC-09 §6.2. | • In services/config-registry/src/main/resources/db/migration/ create V201__audit_log.sql • Define the table with all 11 columns, check constraints on actor_type and action • Add index on (entity_type, entity_id) for config entity history queries • Add index on (actor_id, occurred_at) for actor timeline queries • Add index on occurred_at for retention monitoring queries; do NOT add any FK from entity_id to other tables (audit must survive entity deletes) | services/config-registry/src/main/resources/db/migration/V201__audit_log.sql | • Migration applies cleanly via Flyway on a fresh PostgreSQL 16 Testcontainers instance with no errors • actor_type column rejects values outside ('OPERATOR','SYSTEM','PARTNER') with a check-constraint violation • action column rejects values outside ('CREATE','UPDATE','DELETE','ACTIVATE','DEACTIVATE') • before_value and after_value accept NULL and valid JSONB without error • All three indexes exist in pg_indexes after migration | 25 |  | BE | SEC-09
3.6-T02 | security-platform | 3.6 | 3. Data Layer & Persistence | Audit log tables (immutable) | 1 | Add prev_hash column to audit_log for SHA-256 tamper-evident hash chain | SEC-09 §6.3 requires each audit record to include a hash of the previous record (prev_hash) to form a tamper-evident chain. Hash algorithm: SHA-256 hex string (64 chars). The first record has prev_hash = NULL (genesis). Subsequent rows store SHA256(prev.id¦¦'¦'¦¦prev.actor_id¦¦'¦'¦¦prev.occurred_at::text¦¦'¦'¦¦coalesce(prev.before_value::text,'')¦¦'¦'¦¦coalesce(prev.after_value::text,'')) computed at insert time by the application. Column: prev_hash VARCHAR(64) NULL. A daily integrity check job (3.6-T13) walks the chain and alerts on breaks (P1 severity per SEC-09 §10.4). | • Create V202__audit_log_hash_chain.sql in services/config-registry/src/main/resources/db/migration/ • ALTER TABLE audit_log ADD COLUMN prev_hash VARCHAR(64) NULL • Add index on prev_hash for chain-walk queries • Add comment documenting that first row has prev_hash = NULL (genesis sentinel) and subsequent rows contain SHA-256 of previous row canonical string | services/config-registry/src/main/resources/db/migration/V202__audit_log_hash_chain.sql | • Migration V202 applies cleanly after V201 on Testcontainers PostgreSQL 16 • prev_hash column exists with VARCHAR(64) nullable type • Index on prev_hash is present in pg_indexes • Existing rows default to NULL without error | 15 | 3.6-T01 | BE | SEC-09
3.6-T03 | security-platform | 3.6 | 3. Data Layer & Persistence | Audit log tables (immutable) | 1 | Flyway migration: REVOKE UPDATE/DELETE on audit_log + append-only trigger | SEC-09 §6.3 and DAT-03 §9.1 mandate no UPDATE or DELETE on audit_log. Enforce at DB level as defense-in-depth: (1) REVOKE UPDATE, DELETE on audit_log FROM the application DB role gme_app; (2) create a PL/pgSQL trigger function that raises EXCEPTION 'audit_log is append-only' on BEFORE UPDATE OR DELETE FOR EACH ROW. The application role is gme_app; migration owner (superuser) is gme_flyway. Module: services/config-registry Flyway scripts. | • Create V203__audit_log_immutable_grants.sql in services/config-registry/src/main/resources/db/migration/ • REVOKE UPDATE, DELETE ON TABLE audit_log FROM gme_app; keep INSERT and SELECT • Create PL/pgSQL function audit_log_immutable() RETURNS TRIGGER that raises EXCEPTION 'audit_log is append-only' • Create trigger BEFORE UPDATE OR DELETE ON audit_log FOR EACH ROW EXECUTE FUNCTION audit_log_immutable() • Verify INSERT and SELECT remain permitted for gme_app | services/config-registry/src/main/resources/db/migration/V203__audit_log_immutable_grants.sql | • After migration, UPDATE audit_log SET actor_id='x' WHERE id=1 as gme_app raises a privilege error • After migration, DELETE FROM audit_log WHERE id=1 as gme_app raises a privilege error • INSERT as gme_app succeeds without error • SELECT as gme_app succeeds without error • Trigger function audit_log_immutable exists in pg_proc after migration | 25 | 3.6-T02 | BE | SEC-09
3.6-T04 | security-platform | 3.6 | 3. Data Layer & Persistence | Audit log tables (immutable) | 1 | Define AuditLogEntry domain record and enums in lib-events module | All services that write audit entries share a canonical domain type. Place in lib-events module under com.gme.pay.events.audit. Java 21 record AuditLogEntry with fields: Long id (null before persist), String actorId, AuditActorType actorType, AuditAction action, String entityType, Long entityId, String beforeValueJson (nullable), String afterValueJson (nullable), Instant occurredAt, String ipAddress (nullable), String requestId (nullable), String prevHash (nullable), String actorRole (nullable). Enums: AuditActorType {OPERATOR, SYSTEM, PARTNER}; AuditAction {CREATE, UPDATE, DELETE, ACTIVATE, DEACTIVATE}. No JPA or Spring annotations - pure domain type. | • Create lib-events/src/main/java/com/gme/pay/events/audit/AuditActorType.java enum with 3 values • Create AuditAction.java enum with 5 values in same package • Create AuditLogEntry.java as a Java record with all 13 fields • Confirm no JPA, Spring, or persistence imports in any of the 3 files • Build lib-events with ./gradlew :lib-events:build to verify compilation | lib-events/src/main/java/com/gme/pay/events/audit/AuditLogEntry.java (plus AuditAction.java and AuditActorType.java) | • Module compiles with Java 21 with no warnings • AuditAction enum has exactly 5 values matching the DB check constraint • AuditActorType enum has exactly 3 values matching the DB check constraint • AuditLogEntry is a Java record (immutable by construction) • No import from org.springframework or javax.persistence in any file | 20 | 3.6-T01 | BE | SEC-09
3.6-T05 | security-platform | 3.6 | 3. Data Layer & Persistence | Audit log tables (immutable) | 1 | Implement AuditLogJpaEntity and AuditLogRepository in config-registry | The config-registry Spring Boot 3.x service owns the audit_log PostgreSQL 16 table. Create a Hibernate @Entity mapping audit_log (including prev_hash and actor_role columns from V202/V204) and a Spring Data JPA repository. The entity must be INSERT-only: annotate with Hibernate @Immutable to prevent dirty-checking; never expose an update path. Map JSONB columns before_value/after_value as String via @Column with columnDefinition='jsonb'. Module: services/config-registry. | • Create AuditLogJpaEntity.java in services/config-registry/src/main/java/com/gme/pay/configregistry/audit/ with @Entity @Table(name='audit_log') @Immutable and all 13 mapped columns • Map id with @Id @GeneratedValue(strategy=GenerationType.IDENTITY) • Map occurred_at with @Column(insertable=true, updatable=false) @CreationTimestamp • Create AuditLogRepository.java extending JpaRepository<AuditLogJpaEntity,Long> with findTopByOrderByIdDesc() and findByEntityTypeAndEntityIdOrderByOccurredAtDesc(Pageable) • Ensure no merge/saveAndFlush path would issue UPDATE SQL | services/config-registry/src/main/java/com/gme/pay/configregistry/audit/AuditLogJpaEntity.java and AuditLogRepository.java | • JPA entity maps all 13 columns with correct snake_case @Column names • @Immutable prevents Hibernate dirty-checking (no UPDATE SQL in SQL logs) • findTopByOrderByIdDesc() returns the most-recent row in a Testcontainers PostgreSQL integration test • JSONB columns round-trip as String ('{}' inserted and retrieved without corruption) • Calling repository.save() on a detached entity with an existing id does NOT issue an UPDATE statement | 35 | 3.6-T03, 3.6-T04 | BE | SEC-09
3.6-T06 | security-platform | 3.6 | 3. Data Layer & Persistence | Audit log tables (immutable) | 1 | Implement AuditHashChainService: compute SHA-256 prev_hash inside transaction | SEC-09 §6.3 hash chain: each new audit entry's prev_hash = SHA256(canonical string of previous row). Canonical string: prev.id + '¦' + prev.actorId + '¦' + prev.occurredAt.toString() + '¦' + coalesce(prev.beforeValueJson,'') + '¦' + coalesce(prev.afterValueJson,''). Genesis row (first insert): prev_hash = NULL. Must be called inside the same DB transaction as the INSERT to avoid race conditions. Use java.security.MessageDigest('SHA-256'); StandardCharsets.UTF_8 for all byte conversions. Return 64-char lowercase hex or null. Module: services/config-registry. | • Create AuditHashChainService.java in services/config-registry/src/main/java/com/gme/pay/configregistry/audit/ annotated @Service • Inject AuditLogRepository • Implement public String computePrevHash(): call findTopByOrderByIdDesc(); if empty return null; otherwise compute SHA-256 as specified • Annotate computePrevHash() with @Transactional(readOnly=true) so it joins the caller's transaction • Return lowercase hex string using Hex.encodeHexString (Apache Commons Codec) or manual byte loop | services/config-registry/src/main/java/com/gme/pay/configregistry/audit/AuditHashChainService.java | • computePrevHash() returns null when table is empty • Given a fixed previous row (id=1, actorId='ops1', occurredAt=2025-01-01T00:00:00Z, beforeValueJson=null, afterValueJson='{"name":"x"}'), returns the pre-computed SHA-256 hex value deterministically • Canonical string uses empty string (not 'null') for null JSON fields • Method uses SHA-256 algorithm (not MD5 or SHA-1) • @Transactional(readOnly=true) annotation present on the method | 30 | 3.6-T05 | BE | SEC-09
3.6-T07 | security-platform | 3.6 | 3. Data Layer & Persistence | Audit log tables (immutable) | 1 | Implement Vault transit key provisioner for audit field-level encryption | SEC-09 §2.3 and §2.6: sensitive field values in before_value/after_value JSONB must be Vault-encrypted at rest for sensitive entity types (partner_credential, treasury_rate, rule). Use HashiCorp Vault transit engine (Spring Vault spring-vault-core). Transit key name: 'audit-key', type aes256-gcm96. Provision key at startup via @EventListener(ApplicationReadyEvent) if absent. Vault address from env VAULT_ADDR; token from env VAULT_TOKEN (never hardcoded). If Vault unreachable: log WARN and continue in degraded mode (encryption skipped). Module: services/config-registry. | • Add dependency implementation 'org.springframework.vault:spring-vault-core' to services/config-registry/build.gradle • Create VaultTransitKeyProvisioner.java annotated @Component; inject VaultTemplate • Implement onApplicationReady(@EventListener ApplicationReadyEvent): check if transit mount exists; if not, enable it; check if 'audit-key' exists; if not, create with type aes256-gcm96 • Catch VaultException: log WARN 'Vault unavailable - audit encryption in degraded mode'; set degradedMode=true flag • Expose isDegradedMode() boolean for AuditLogService to check | services/config-registry/src/main/java/com/gme/pay/configregistry/audit/VaultTransitKeyProvisioner.java and updated services/config-registry/build.gradle | • Application starts successfully when Vault is available and 'audit-key' is created on first run • Application starts in degraded mode (WARN logged, no exception thrown) when Vault is unavailable • Provisioner is idempotent: running twice when key exists does not throw an error • Key type is aes256-gcm96 confirmed via Vault API response in WireMock test • VAULT_ADDR and VAULT_TOKEN are read from environment variables, not from any config file | 35 | 3.6-T05 | BE | SEC-09
3.6-T08 | security-platform | 3.6 | 3. Data Layer & Persistence | Audit log tables (immutable) | 1 | Implement AuditLogService: append-only write with hash chain and Vault encryption | AuditLogService is the single entry-point for writing audit records in services/config-registry. Flow: (1) call AuditHashChainService.computePrevHash(); (2) if entity_type in SENSITIVE_TYPES {'partner_credential','treasury_rate','rule'} and Vault not degraded, encrypt before/after JSON via vaultTemplate.opsForTransit().encrypt('audit-key', plaintext); (3) build AuditLogJpaEntity; (4) save via AuditLogRepository. The entire append() method is @Transactional so hash-read + insert are atomic. Never calls update or delete. SEC-09 §6.1 full field list: actor_id, actor_role, action, entity_type, entity_id, before_value (prev), after_value (new), occurred_at (server-generated), ip_address, request_id. | • Create AuditLogService.java annotated @Service @Transactional in services/config-registry/src/main/java/com/gme/pay/configregistry/audit/ • Inject AuditLogRepository, AuditHashChainService, VaultTransitKeyProvisioner, VaultTemplate • Implement public void append(AuditLogEntry entry): compute prevHash; encrypt if sensitive and not degraded; build entity; save • Define private static final Set<String> SENSITIVE_ENTITY_TYPES = Set.of('partner_credential','treasury_rate','rule') • Never call any repository method that issues UPDATE or DELETE | services/config-registry/src/main/java/com/gme/pay/configregistry/audit/AuditLogService.java | • append() for entity_type='partner_credential' stores Vault ciphertext in before_value (not plaintext) • append() for entity_type='merchant' stores plaintext JSONB (non-sensitive) • append() for action=CREATE stores NULL in before_value without NPE • Two concurrent append() calls in different transactions do not produce duplicate prev_hash (serialization guaranteed by @Transactional) • The method issues only INSERT statements; no UPDATE or DELETE SQL observed in Hibernate SQL log | 40 | 3.6-T06, 3.6-T07 | BE | SEC-09
3.6-T09 | security-platform | 3.6 | 3. Data Layer & Persistence | Audit log tables (immutable) | 1 | Add actor_role column to audit_log via Flyway migration and update entity | SEC-09 §6.1 lists actor_role (role at time of change) as a required audit field alongside actor_id. Add it to the audit_log table. Column: actor_role VARCHAR(30) NULL. New entries from AuditLogService must populate it from the authenticated Spring Security granted authority (ADMIN, OPS, FINANCE, SYSTEM). Existing rows remain NULL. Update AuditLogJpaEntity and AuditLogEntry record to include the field. | • Create V204__audit_log_actor_role.sql: ALTER TABLE audit_log ADD COLUMN actor_role VARCHAR(30) NULL • Add actorRole field to AuditLogJpaEntity.java with @Column(name='actor_role', insertable=true, updatable=false) • AuditLogEntry Java record already includes actorRole (added in 3.6-T04; confirm it is present) • Update AuditLogService.append() to set actorRole from AuditContext (populated by interceptor in 3.6-T10) | services/config-registry/src/main/resources/db/migration/V204__audit_log_actor_role.sql and updated AuditLogJpaEntity.java | • Migration V204 applies cleanly after V201-V203 on Testcontainers PostgreSQL 16 • actor_role column exists as VARCHAR(30) nullable • Audit entry for an ADMIN-role request has actor_role='ADMIN' in the persisted row • Audit entry for a SYSTEM-type action has actor_role='SYSTEM' • V204 does not alter existing rows; they remain NULL | 25 | 3.6-T08 | BE | SEC-09
3.6-T10 | security-platform | 3.6 | 3. Data Layer & Persistence | Audit log tables (immutable) | 1 | Implement AuditContext request-scoped bean and HandlerInterceptor in config-registry | SEC-09 §6.1 requires ip_address (operator IP) and request_id (trace ID) in every audit entry. Use a request-scoped Spring bean AuditContext populated by a HandlerInterceptor. Extract: ip from X-Forwarded-For header (first value) falling back to request.getRemoteAddr(); requestId from X-Request-ID header generating UUID if absent; actorRole from SecurityContextHolder granted authority. AuditLogService reads from injected AuditContext. For non-HTTP (SYSTEM) audit entries, ip=null, requestId='SYSTEM-'+UUID. Module: services/config-registry. | • Create AuditContext.java as @Component @Scope(value='request', proxyMode=ScopedProxyMode.TARGET_CLASS) with fields String ipAddress, String requestId, String actorRole • Create AuditContextInterceptor.java implements HandlerInterceptor; in preHandle(): extract ip (X-Forwarded-For first, else remoteAddr), requestId (X-Request-ID or new UUID), actorRole from SecurityContextHolder; populate AuditContext • Register interceptor in WebMvcConfigurer.addInterceptors() • Inject AuditContext into AuditLogService; read ip, requestId, actorRole when building AuditLogJpaEntity | services/config-registry/src/main/java/com/gme/pay/configregistry/audit/AuditContext.java and AuditContextInterceptor.java | • HTTP request with X-Forwarded-For: 10.0.0.1 results in audit_log.ip_address = '10.0.0.1' • HTTP request with no X-Forwarded-For header uses request.getRemoteAddr() value • HTTP request with X-Request-ID: abc-123 results in audit_log.request_id = 'abc-123' • HTTP request with no X-Request-ID header generates a UUID stored in audit_log.request_id • SYSTEM-triggered append (no HTTP context) stores null ip_address and non-null requestId starting with 'SYSTEM-' | 30 | 3.6-T08 | BE | SEC-09
3.6-T11 | security-platform | 3.6 | 3. Data Layer & Persistence | Audit log tables (immutable) | 1 | Wire AuditLogService into config-registry RuleService, PartnerService, SchemeService, TreasuryRateService | Every write operation on rule, partner, scheme, and treasury_rate in config-registry must emit an audit entry per SEC-09 §6.1. Each @Service method must: (1) snapshot before_value as objectMapper.writeValueAsString(existingEntity) before applying changes; (2) apply changes and snapshot after_value; (3) call auditLogService.append() inside the same @Transactional method. For ACTIVATE/DEACTIVATE use action=ACTIVATE/DEACTIVATE. If the entity save fails, the transaction rolls back and no audit row is written. SEC-09 §6.1 fields: actor_id, actor_role (via AuditContext), changed entity type and id, before/after JSON. | • In RuleService.updateRule() capture beforeSnapshot before the mutation; call auditLogService.append() after mutation with action=UPDATE, entity_type='rule' • In RuleService.activateRule() call append with action=ACTIVATE; beforeSnapshot=current status, afterSnapshot=activated • In PartnerService.createPartner() call append with action=CREATE, beforeValueJson=null • In PartnerService.updatePartner() capture before/after and call append with action=UPDATE • Repeat the same before/after snapshot + append pattern in SchemeService and TreasuryRateService for all CUD and ACTIVATE/DEACTIVATE operations | Updated services/config-registry/src/main/java/com/gme/pay/configregistry/service/RuleService.java, PartnerService.java, SchemeService.java, TreasuryRateService.java | • After updateRule(), exactly one audit_log row with action='UPDATE', entity_type='rule', non-null before_value and after_value • After createPartner(), one audit_log row with action='CREATE', before_value=NULL • After activateRule(), one audit_log row with action='ACTIVATE' • If entity save throws RuntimeException, no audit_log row is persisted (rollback test) • actor_id in audit row matches the authenticated operator username from the JWT (not hardcoded) | 45 | 3.6-T10 | BE | SEC-09
3.6-T12 | security-platform | 3.6 | 3. Data Layer & Persistence | Audit log tables (immutable) | 1 | Create Flyway migration: transaction_event_trail table in transaction-mgmt PostgreSQL | SEC-09 §6.1 defines an 8-step event trail per payment transaction. Table belongs to services/transaction-mgmt PostgreSQL 16 DB. Columns: id BIGINT PK auto-increment, transaction_id BIGINT NOT NULL REFERENCES transaction(id), event VARCHAR(60) NOT NULL CHECK IN ('rate_quote_issued','payment_initiated','prefund_deducted','scheme_request_sent','scheme_response_received','transaction_committed','webhook_dispatched','webhook_delivered'), occurred_at TIMESTAMPTZ NOT NULL DEFAULT NOW(), duration_ms BIGINT NULL (ms since previous step, null for first step), state_snapshot JSONB NULL (step 6 carries locked rate values). Unique constraint (transaction_id, event). No UPDATE or DELETE. | • Create services/transaction-mgmt/src/main/resources/db/migration/V301__transaction_event_trail.sql • Define table with all 6 columns, check constraint on event with the 8 allowed values • Add index on (transaction_id, occurred_at) for trail retrieval • Add UNIQUE constraint on (transaction_id, event) to prevent duplicate steps • Do not add UPDATE/DELETE triggers yet (handled in 3.6-T13) | services/transaction-mgmt/src/main/resources/db/migration/V301__transaction_event_trail.sql | • Migration applies cleanly on Testcontainers PostgreSQL 16 • event column rejects values not in the 8-step list via check constraint • UNIQUE constraint (transaction_id, event) prevents inserting the same step twice • Index (transaction_id, occurred_at) exists in pg_indexes • FK transaction_id REFERENCES transaction(id) is enforced: insert for non-existent transaction fails | 25 | 3.6-T01 | BE | SEC-09
3.6-T13 | security-platform | 3.6 | 3. Data Layer & Persistence | Audit log tables (immutable) | 1 | Flyway migration: REVOKE + immutable trigger on transaction_event_trail | Same defense-in-depth pattern as audit_log (3.6-T03) applied to transaction_event_trail. Application DB role for transaction-mgmt is gme_txn_app. REVOKE UPDATE, DELETE; create trigger function txn_trail_immutable() raising EXCEPTION 'transaction_event_trail is append-only'; attach BEFORE UPDATE OR DELETE trigger. Module: services/transaction-mgmt. | • Create V302__transaction_event_trail_immutable.sql in services/transaction-mgmt/src/main/resources/db/migration/ • REVOKE UPDATE, DELETE ON TABLE transaction_event_trail FROM gme_txn_app • Create PL/pgSQL function txn_trail_immutable() RETURNS TRIGGER that raises EXCEPTION 'transaction_event_trail is append-only' • Create BEFORE UPDATE OR DELETE trigger trg_txn_trail_immutable ON transaction_event_trail FOR EACH ROW EXECUTE FUNCTION txn_trail_immutable() | services/transaction-mgmt/src/main/resources/db/migration/V302__transaction_event_trail_immutable.sql | • UPDATE on transaction_event_trail as gme_txn_app raises privilege error • DELETE on transaction_event_trail as gme_txn_app raises privilege error • INSERT and SELECT as gme_txn_app succeed • Trigger function txn_trail_immutable exists in pg_proc after migration • Trigger fires even if UPDATE is executed by a superuser-initiated SQL (trigger EXCEPTION is raised) | 20 | 3.6-T12 | BE | SEC-09
3.6-T14 | security-platform | 3.6 | 3. Data Layer & Persistence | Audit log tables (immutable) | 1 | Implement TransactionEventTrailService: append 8 steps with duration and state snapshot | services/transaction-mgmt owns transaction_event_trail. The service appends individual event steps per SEC-09 §6.1. duration_ms = occurred_at minus previous step's occurred_at for same transaction_id (null for first step). Step 6 (transaction_committed) must include state_snapshot JSONB with 7 locked rate values: collection_usd, payout_usd_cost, collection_margin_usd, payout_margin_usd, send_amount, offer_rate_coll (= send_amount / (collection_usd - collection_margin_usd)), cross_rate (= target_payout / send_amount). These are the rate-lock values; later treasury/margin changes never affect them per RATE-04. | • Create TransactionEventTrailJpaEntity.java and TransactionEventTrailRepository.java (findByTransactionIdOrderByOccurredAtAsc, findTopByTransactionIdOrderByOccurredAtDesc) • Create TransactionEventTrailService.java @Service with appendEvent(Long txnId, String event, Map<String,Object> stateSnapshot): fetch latest row for duration_ms, build entity, save @Transactional • Implement getTrail(Long txnId) returning ordered list • Step 6 caller must pass all 7 rate snapshot keys; other callers pass null for stateSnapshot • Validate event string is one of the 8 allowed values at service layer before DB insert | services/transaction-mgmt/src/main/java/com/gme/pay/txnmgmt/audit/TransactionEventTrailService.java | • After appending step 1 and step 2, step 2 row has duration_ms > 0 • Step 6 row has non-null state_snapshot containing keys collection_usd and offer_rate_coll • Calling appendEvent with same txnId + event a second time throws DataIntegrityViolationException (unique constraint) • appendEvent with unknown event string 'foo' throws IllegalArgumentException before hitting DB • getTrail() returns rows in occurred_at ascending order | 40 | 3.6-T13 | BE | SEC-09
3.6-T15 | security-platform | 3.6 | 3. Data Layer & Persistence | Audit log tables (immutable) | 1 | Wire TransactionEventTrailService steps 1-5 and 7-8 into payment-executor | payment-executor must call TransactionEventTrailService for steps 1-5 and 7-8 of the event trail. Steps: 1=rate_quote_issued (in rate-fx RateController after GET /v1/rates response), 2=payment_initiated (POST /v1/payments handler), 3=prefund_deducted (OVERSEAS: after successful SELECT FOR UPDATE deduction in prefunding-balance service), 4=scheme_request_sent (before ZeroPay adapter call), 5=scheme_response_received (after ZeroPay adapter returns), 7=webhook_dispatched (notification-webhook service before dispatch), 8=webhook_delivered (after partner returns HTTP 2xx). Call via services/transaction-mgmt internal REST endpoint POST /internal/txn-trail/{txnId}/events. stateSnapshot=null for steps 1-5,7,8. | • Create TransactionEventTrailClient.java in services/payment-executor using Spring RestClient or OpenFeign to call POST /internal/txn-trail/{txnId}/events with body {event, stateSnapshot} • Wire step 2 call in PaymentExecutorService after creating the transaction record • Wire step 4 call in ZeroPayAdapterClient before dispatching to scheme • Wire step 5 call after receiving scheme response • Wire steps 7 and 8 in NotificationService (services/notification-webhook) • All trail calls are fire-and-not-rollback: if trail append fails, log WARN but do not roll back the payment | services/payment-executor/src/main/java/com/gme/pay/payexec/audit/TransactionEventTrailClient.java and wiring changes in PaymentExecutorService.java, ZeroPayAdapterClient.java, NotificationService.java | • After a successful payment flow, all 8 steps appear in transaction_event_trail ordered by occurred_at • If trail service is unavailable, payment processing continues and step is logged as WARN, not failed • Step 3 is only appended for OVERSEAS partner type (not LOCAL/GME Remit) • Step 7 is appended before HTTP dispatch and step 8 after 2xx confirmation • WireMock stub for POST /internal/txn-trail/{txnId}/events verifies correct event name in request body | 45 | 3.6-T14 | BE | SEC-09
3.6-T16 | security-platform | 3.6 | 3. Data Layer & Persistence | Audit log tables (immutable) | 1 | Wire step 6 transaction_committed into PaymentCommitService with full rate state snapshot | SEC-09 §6.1 step 6 (transaction_committed): rate and amount values must be permanently locked at commit. In services/payment-executor PaymentCommitService.commitPayment(), after the DB save, call transactionEventTrailClient.appendEvent(txnId, 'transaction_committed', stateSnapshot) with all 7 required fields from RateEngineResult: collection_usd, payout_usd_cost, collection_margin_usd, payout_margin_usd, send_amount, offer_rate_coll (= send_amount / (collection_usd - collection_margin_usd)), cross_rate (= target_payout / send_amount). These are DECIMAL values (BigDecimal); serialize as numeric JSON (not strings). BOK FX1015 field #14 = offer_rate_coll per SEC-09 §8.1. | • In PaymentCommitService.commitPayment() build stateSnapshot Map<String,BigDecimal> with all 7 keys from RateEngineResult • Call transactionEventTrailClient.appendEvent(txnId, 'transaction_committed', stateSnapshot) after the transaction DB record is saved • Ensure this call is inside the same @Transactional(propagation=REQUIRES_NEW) block so it does not roll back the payment • Assert offer_rate_coll = send_amount / (collection_usd - collection_margin_usd) at the service layer before storing • Assert pool identity: collection_usd - collection_margin_usd - payout_margin_usd == payout_usd_cost (tolerance 0.01 USD); if violated log ERROR and throw RatePoolIdentityException | Updated services/payment-executor/src/main/java/com/gme/pay/payexec/PaymentCommitService.java | • state_snapshot on step 6 row contains all 7 keys with numeric (not string) values • offer_rate_coll = send_amount / (collection_usd - collection_margin_usd) exactly as stored • Pool identity check: ¦collection_usd - collection_margin_usd - payout_margin_usd - payout_usd_cost¦ <= 0.01 USD; violation throws RatePoolIdentityException • WireMock test verifies the JSON body of POST /internal/txn-trail/{txnId}/events for step 6 contains numeric collection_usd • A pool identity violation (e.g. collection_usd = 100.00, margins sum to 3.00, payout_usd_cost = 96.50 - delta 0.50) is rejected with RatePoolIdentityException | 35 | 3.6-T15 | BE | SEC-09
3.6-T17 | security-platform | 3.6 | 3. Data Layer & Persistence | Audit log tables (immutable) | 1 | Expose GET /internal/audit-log/{entityType}/{entityId} endpoint in config-registry | Admin portal (PRD-07) shows audit history for any config entity. Expose an internal REST endpoint in config-registry: GET /internal/audit-log/{entityType}/{entityId}?page=0&size=50. Returns paginated AuditLogEntryDto list. SEC-09 §3.4 permission matrix: audit log view is ADMIN role only. Guard with Spring Security @PreAuthorize('hasRole("ADMIN")'). @EnableMethodSecurity must be active. DTO fields: id, actorId, actorRole, actorType, action, entityType, entityId, beforeValueJson, afterValueJson, occurredAt (ISO-8601 UTC), ipAddress, requestId. Return encrypted ciphertext as-is; decryption is out of scope. | • Create AuditLogController.java annotated @RestController @RequestMapping('/internal/audit-log') in services/config-registry/src/main/java/com/gme/pay/configregistry/audit/ • Create AuditLogEntryDto record with all 13 fields • Implement @GetMapping('/{entityType}/{entityId}') returning ResponseEntity<Page<AuditLogEntryDto>> with @PreAuthorize('hasRole("ADMIN")') • Map AuditLogJpaEntity -> AuditLogEntryDto in a private mapper method • Return HTTP 200 empty page for unknown entity (not 404); return HTTP 403 for non-ADMIN roles; return HTTP 401 for unauthenticated | services/config-registry/src/main/java/com/gme/pay/configregistry/audit/AuditLogController.java | • GET /internal/audit-log/rule/42 with ADMIN JWT returns HTTP 200 with paginated JSON body • GET /internal/audit-log/rule/42 with OPS JWT returns HTTP 403 • GET /internal/audit-log/rule/99999 (non-existent entity) returns HTTP 200 with empty content array • page=0&size=5 query parameter limits result to at most 5 entries • occurredAt in response is ISO-8601 UTC format (e.g. 2025-01-01T00:00:00Z, not epoch millis) | 35 | 3.6-T11 | BE | SEC-09
3.6-T18 | security-platform | 3.6 | 3. Data Layer & Persistence | Audit log tables (immutable) | 1 | Implement AuditLogIntegrityCheckService: daily SHA-256 chain validation job | SEC-09 §6.3 requires daily integrity check of the audit_log hash chain. Algorithm: walk all rows ordered by id ASC in pages of 1000; for each row after the first, recompute expected_prev_hash using the same canonical string formula as 3.6-T06 and compare to row.prev_hash; mismatch = chain break. First row must have prev_hash=NULL. Any failure is P1 alert per SEC-09 §10.4. Schedule: @Scheduled(cron='0 0 2 * * *') (02:00 UTC daily). Emit OpenTelemetry counter metric 'audit.integrity.breaks'. Log results as structured JSON for SIEM forwarding per SEC-09 §6.5. Module: services/config-registry. | • Create AuditLogIntegrityCheckService.java @Service in services/config-registry/src/main/java/com/gme/pay/configregistry/audit/ • Implement runDailyCheck() @Scheduled(cron='0 0 2 * * *') that pages through audit_log rows 1000 at a time • For each row (after the first) recompute prevHash and compare; collect mismatches (broken id, expected, actual) • If mismatches > 0 log ERROR with SIEM JSON: {event:'AUDIT_CHAIN_BREAK', breach_count:N, first_broken_id:X, checked_at:ISO} • Emit OTel counter metric named 'audit.integrity.breaks' with value = mismatch count (0 on clean run) | services/config-registry/src/main/java/com/gme/pay/configregistry/audit/AuditLogIntegrityCheckService.java | • Valid 5-row chain: runDailyCheck() logs INFO 'audit chain OK', metric 'audit.integrity.breaks' = 0 • Corrupted prev_hash on row 3: ERROR logged with first_broken_id=3, metric = 1 • Single genesis row (prev_hash=NULL): valid, metric = 0 • Paged query (page size 1000) is used; no in-memory full-table load • @Scheduled cron expression is exactly '0 0 2 * * *' | 45 | 3.6-T06 | BE | SEC-09
3.6-T19 | security-platform | 3.6 | 3. Data Layer & Persistence | Audit log tables (immutable) | 1 | Implement AuditLogRetentionGuardService: monthly overdue retention warning | SEC-09 §6.2 mandates >= 7-year retention for audit_log and transaction_event_trail. Implement a monthly scheduled job in services/config-registry that counts rows in audit_log older than the configured retention period and logs SIEM-compatible JSON WARN if any exist. The job does NOT delete rows (deletion is a privileged DBA-only operation). Schedule: @Scheduled(cron='0 0 3 1 * *') (03:00 UTC on 1st of each month). Property: audit.log.retention-years (default 7, injected via @Value). | • Create AuditLogRetentionGuardService.java @Service in services/config-registry/src/main/java/com/gme/pay/configregistry/audit/ • Inject JdbcTemplate; inject @Value('${audit.log.retention-years:7}') int retentionYears • Implement checkRetention() @Scheduled(cron='0 0 3 1 * *') • Query: SELECT COUNT(*) FROM audit_log WHERE occurred_at < NOW() - INTERVAL '? years' with retentionYears parameter • If count > 0 log WARN with JSON: {event:'AUDIT_RETENTION_OVERDUE',overdue_count:N,retention_years:7}; else log INFO 'audit retention OK' • Method must NOT issue DELETE or UPDATE | services/config-registry/src/main/java/com/gme/pay/configregistry/audit/AuditLogRetentionGuardService.java | • With rows older than 7 years in DB, WARN log contains {event:'AUDIT_RETENTION_OVERDUE'} and correct overdue_count • With no old rows, INFO 'audit retention OK' logged, no WARN • Setting audit.log.retention-years=5 changes threshold to 5 years without code change • @Scheduled cron is '0 0 3 1 * *' • No DELETE or UPDATE SQL is issued by this method (verified in SQL log) | 30 | 3.6-T05 | BE | SEC-09
3.6-T20 | security-platform | 3.6 | 3. Data Layer & Persistence | Audit log tables (immutable) | 1 | Unit tests: AuditHashChainService SHA-256 correctness with known test vectors | Test 3.6-T06's AuditHashChainService in services/config-registry with JUnit 5 + Mockito. No DB required; mock AuditLogRepository. Provide 3 deterministic test vectors with pre-computed SHA-256 reference hashes to verify correctness and canonical string construction. | • Create AuditHashChainServiceTest.java in services/config-registry/src/test/java/com/gme/pay/configregistry/audit/ • Annotate @ExtendWith(MockitoExtension.class); mock AuditLogRepository • Vector 1: prev row id=1, actorId='ops1', occurredAt='2025-01-01T00:00:00Z', beforeValueJson=null, afterValueJson='{"name":"test"}' -> compute reference SHA-256 and assert exact match • Vector 2: prev row with both non-null before and after JSON -> compute reference and assert • Vector 3: empty table (findTopByOrderByIdDesc returns empty Optional) -> computePrevHash() returns null • Assert canonical string uses empty string (not 'null') for null JSON fields in vectors 1 and 2 | services/config-registry/src/test/java/com/gme/pay/configregistry/audit/AuditHashChainServiceTest.java | • All 3 test vectors pass on repeated runs (deterministic) • Null beforeValueJson uses empty string in hash input (vector 1 reference value accounts for this) • computePrevHash() with empty table returns null (vector 3) • Test runs in under 5 seconds with no DB dependency • Test class has @ExtendWith(MockitoExtension.class) annotation | 30 | 3.6-T06 | BE | SEC-09
3.6-T21 | security-platform | 3.6 | 3. Data Layer & Persistence | Audit log tables (immutable) | 1 | Integration tests: AuditLogService append-only enforcement with Testcontainers + WireMock | Integration test for AuditLogService (3.6-T08) and DB-level immutability (V203 migration). Use @SpringBootTest + Testcontainers PostgreSQL 16 with full Flyway migrations applied. Stub Vault transit API using WireMock. Verify: normal append works; direct JDBC UPDATE raises exception; direct JDBC DELETE raises exception; second row prev_hash is correct SHA-256 of first row. | • Create AuditLogServiceIntegrationTest.java in services/config-registry/src/test/java/com/gme/pay/configregistry/audit/ • Annotate @SpringBootTest @Testcontainers; declare @Container static PostgreSQLContainer • Start WireMock server; stub POST /v1/transit/encrypt/audit-key to return {data:{ciphertext:'vault:v1:abc'}} • Test 1: append() for action=UPDATE, entity_type='rule' - assert persisted row with correct fields • Test 2: jdbcTemplate.execute('UPDATE audit_log SET actor_id=x WHERE id=1') - assert DataAccessException • Test 3: jdbcTemplate.execute('DELETE FROM audit_log WHERE id=1') - assert DataAccessException • Test 4: two sequential appends - assert row 2 prev_hash equals SHA-256 of row 1 canonical string | services/config-registry/src/test/java/com/gme/pay/configregistry/audit/AuditLogServiceIntegrationTest.java | • Test 2 throws DataAccessException containing 'append-only' or privilege denied message • Test 3 throws DataAccessException for DELETE • Test 4 row-2 prev_hash matches reference SHA-256 computed in test • WireMock stub for Vault transit is invoked when entity_type='rule' (sensitive type) • All 4 tests pass with Testcontainers PostgreSQL 16 image | 50 | 3.6-T08, 3.6-T20 | BE | SEC-09
3.6-T22 | security-platform | 3.6 | 3. Data Layer & Persistence | Audit log tables (immutable) | 1 | Integration tests: TransactionEventTrailService 8-step append and immutability in transaction-mgmt | Test TransactionEventTrailService (3.6-T14) with Testcontainers PostgreSQL 16 in services/transaction-mgmt. Verify: all 8 steps append in order; duration_ms is positive on step 2+; step 6 state_snapshot contains 7 rate keys; duplicate step raises exception; UPDATE is blocked by trigger. | • Create TransactionEventTrailServiceIntegrationTest.java in services/transaction-mgmt/src/test/java/com/gme/pay/txnmgmt/audit/ • Spin up @Container PostgreSQLContainer; apply Flyway migrations V301+V302 • Insert prerequisite transaction row • Append all 8 event steps in order; assert each row exists by querying getTrail() • Assert step 2 (payment_initiated) has duration_ms > 0 • Assert step 6 (transaction_committed) has state_snapshot containing keys: collection_usd, payout_usd_cost, collection_margin_usd, payout_margin_usd, send_amount, offer_rate_coll, cross_rate • Attempt duplicate step 1; assert DataIntegrityViolationException; attempt UPDATE via JDBC, assert DataAccessException | services/transaction-mgmt/src/test/java/com/gme/pay/txnmgmt/audit/TransactionEventTrailServiceIntegrationTest.java | • All 8 event steps inserted and retrieved in ascending occurred_at order • duration_ms on step 2 is positive (not zero) • state_snapshot on step 6 contains all 7 required keys with non-null numeric values • Duplicate step 1 insert throws DataIntegrityViolationException • JDBC UPDATE on any trail row throws DataAccessException (immutable trigger active) | 45 | 3.6-T14 | BE | SEC-09
3.6-T23 | security-platform | 3.6 | 3. Data Layer & Persistence | Audit log tables (immutable) | 1 | Unit tests: AuditLogIntegrityCheckService detects chain break and emits OTel metric | Test AuditLogIntegrityCheckService (3.6-T18) with JUnit 5 + Mockito + in-memory MeterRegistry. No DB required. Build a 5-row chain dataset where row 3 has a manually corrupted prev_hash. Verify first_broken_id=3, metric=1. Also verify valid chain yields metric=0. Verify genesis (single row) is valid. | • Create AuditLogIntegrityCheckServiceTest.java in services/config-registry/src/test/java/com/gme/pay/configregistry/audit/ • Use @ExtendWith(MockitoExtension.class); mock AuditLogRepository to return paged results • Build helper to generate a valid 5-row chain with correct prev_hash using AuditHashChainService logic • Test 1: valid chain -> no ERROR log; metric 'audit.integrity.breaks' = 0 • Test 2: corrupt row 3 prev_hash='deadbeef...' -> ERROR logged with first_broken_id=3; metric = 1 • Test 3: single genesis row (prev_hash=NULL) -> valid; metric = 0 | services/config-registry/src/test/java/com/gme/pay/configregistry/audit/AuditLogIntegrityCheckServiceTest.java | • Test 1 produces no ERROR log and metric = 0 • Test 2 identifies first_broken_id=3 (not 4 or 5) • Test 3 passes with single genesis row • OTel metric 'audit.integrity.breaks' captured from in-memory MeterRegistry with correct value • Test runs in under 10 seconds with no DB or Vault dependency | 35 | 3.6-T18 | BE | SEC-09
3.6-T24 | security-platform | 3.6 | 3. Data Layer & Persistence | Audit log tables (immutable) | 1 | Unit tests: AuditLogController RBAC enforcement with @WebMvcTest Spring Security slice | Test AuditLogController (3.6-T17) RBAC using @WebMvcTest + Spring Security test support in services/config-registry. Cover: ADMIN gets 200, OPS gets 403, FINANCE gets 403, unauthenticated gets 401. Also verify pagination parameters are passed to the repository. | • Create AuditLogControllerTest.java in services/config-registry/src/test/java/com/gme/pay/configregistry/audit/ • Annotate @WebMvcTest(AuditLogController.class); @MockBean AuditLogRepository • Test 1: @WithMockUser(roles='ADMIN') GET /internal/audit-log/rule/1 returns 200 with JSON body • Test 2: @WithMockUser(roles='OPS') returns 403 • Test 3: @WithMockUser(roles='FINANCE') returns 403 • Test 4: no authentication returns 401 • Test 5: ADMIN with ?page=0&size=3 - verify MockBean called with matching Pageable | services/config-registry/src/test/java/com/gme/pay/configregistry/audit/AuditLogControllerTest.java | • ADMIN role returns HTTP 200 with JSON 'content' array • OPS role returns HTTP 403 • FINANCE role returns HTTP 403 • Unauthenticated returns HTTP 401 • Pageable with pageSize=3 passed to AuditLogRepository mock verified by Mockito.verify | 25 | 3.6-T17 | BE | SEC-09
3.7-T01 | shared-libs | 3.7 | 3. Data Layer & Persistence | Migration framework & seed data | 1 | Add Flyway dependency and configure migration scanning in lib-persistence | GMEPay+ is a Gradle multi-module monorepo (Java 21, Spring Boot 3.x). All schema migrations use Flyway (OPS-13). The shared module lib-persistence owns common JPA/migration utils. Flyway must scan classpath:db/migration, set spring.flyway.validate-on-migrate=true, out-of-order=false, and read DB URL/user/password from env vars SPRING_DATASOURCE_URL, SPRING_DATASOURCE_USERNAME, SPRING_DATASOURCE_PASSWORD. Migration history lands in table flyway_schema_history. No credentials in committed config. | • Add flyway-core and flyway-database-postgresql to lib-persistence/build.gradle (implementation scope). • In lib-persistence/src/main/resources/META-INF/spring/flyway-defaults.yaml set spring.flyway.locations=classpath:db/migration, validate-on-migrate=true, out-of-order=false, baseline-on-migrate=false. • Expose a @Bean FlywayMigrationStrategy in lib-persistence that logs version+description+duration for each applied script. • Add lib-persistence as an api dependency to services/merchant-qr, services/config-registry, and services/settlement. • Verify app starts against an empty local PostgreSQL on port 5433 and flyway_schema_history is auto-created. | lib-persistence/build.gradle with flyway deps; lib-persistence/src/main/resources/META-INF/spring/flyway-defaults.yaml; FlywayMigrationStrategy @Bean | • Application starts on a clean DB and flyway_schema_history table is created with zero rows. • Mutating a migration file checksum causes startup to fail with FlywayValidateException (revert to fix). • DB credentials are read exclusively from env vars; no credentials appear in committed YAML or properties files. • Flyway logs version, description, and execution duration for each applied migration at startup. | 30 |  | DBA | OPS-13
3.7-T02 | shared-libs | 3.7 | 3. Data Layer & Persistence | Migration framework & seed data | 1 | V001 Flyway migration: PostgreSQL extensions and money-type comments | All monetary amounts in GMEPay+ are stored as DECIMAL(20,4) (transaction amounts, service charges) or DECIMAL(20,8) (USD pool values, FX rates); never floating-point. Every amount column pairs with a CHAR(3) currency column. Extensions needed from day one: uuid-ossp (UUID generation) and pgcrypto (account_no encryption). Standard audit columns on every table: created_at TIMESTAMPTZ NOT NULL DEFAULT now(), updated_at TIMESTAMPTZ NOT NULL DEFAULT now(), created_by VARCHAR(60), updated_by VARCHAR(60). All timestamps stored as UTC. | • Create db/migration/V001__baseline_extensions.sql under lib-persistence/src/main/resources/. • Add CREATE EXTENSION IF NOT EXISTS uuid-ossp; CREATE EXTENSION IF NOT EXISTS pgcrypto; • Add a schema comment documenting the money-storage convention (DECIMAL(20,4) for amounts, DECIMAL(20,8) for rates, CHAR(3) ccy pairing, UTC timestamps). • Run flyway migrate locally against port 5433 DB gmepay_dev; confirm V001 row in flyway_schema_history. • Add a Testcontainers integration test in lib-persistence that starts PostgreSQL 16, runs all migrations, and asserts both extensions exist. | lib-persistence/src/main/resources/db/migration/V001__baseline_extensions.sql; Testcontainers migration smoke test | • SELECT extname FROM pg_extension WHERE extname IN ('uuid-ossp','pgcrypto') returns both rows after migration. • flyway_schema_history has exactly one row: version=001, success=true. • Re-running flyway migrate is idempotent (no error, no duplicate row in history). • Testcontainers test passes in CI with PostgreSQL 16 image. | 25 | 3.7-T01 | DBA | OPS-13
3.7-T03 | shared-libs | 3.7 | 3. Data Layer & Persistence | Migration framework & seed data | 1 | V002 Flyway migration: qr_scheme and scheme_country tables | qr_scheme represents a QR payment network. Columns: id BIGINT GENERATED ALWAYS AS IDENTITY PK, scheme_code VARCHAR(30) UNIQUE NOT NULL, name VARCHAR(100), payout_ccy CHAR(3), supported_modes VARCHAR(10) CHECK IN ('MPM','CPM','BOTH'), status VARCHAR(20) CHECK IN ('TESTING','ACTIVE','INACTIVE') DEFAULT 'TESTING', merchant_fee_crossborder_min DECIMAL(6,4), merchant_fee_crossborder_max DECIMAL(6,4), gme_fee_share_pct DECIMAL(6,4) DEFAULT 0.7000, partner_b_quote_deviation_pct DECIMAL(6,4) DEFAULT 0.0100, is_active BOOLEAN NOT NULL DEFAULT true, plus standard audit columns. scheme_country: id, scheme_id FK qr_scheme, country_code CHAR(2), is_active BOOLEAN, audit cols; UNIQUE(scheme_id, country_code). Module: lib-persistence (migration file); services/merchant-qr and services/config-registry consume these tables via JPA. | • Create db/migration/V002__create_qr_scheme.sql. • Write CREATE TABLE qr_scheme with all columns, CHECK constraints on status and supported_modes, index on (scheme_code) and (status). • Write CREATE TABLE scheme_country with FK, UNIQUE(scheme_id, country_code), index on (country_code). • Run flyway migrate locally; confirm V002 row in flyway_schema_history. • Add Testcontainers test asserting column types via JDBC metadata and constraint violations on bad status value. | lib-persistence/src/main/resources/db/migration/V002__create_qr_scheme.sql | • INSERT with status='INVALID' raises a CHECK constraint violation. • UNIQUE(scheme_id, country_code) rejects duplicate insert on scheme_country. • flyway_schema_history has version=002 with success=true. • Index on qr_scheme(scheme_code) confirmed via pg_indexes query in Testcontainers test. | 35 | 3.7-T02 | DBA | OPS-13
3.7-T04 | shared-libs | 3.7 | 3. Data Layer & Persistence | Migration framework & seed data | 1 | V003 Flyway migration: partner and partner_credential tables | partner: id BIGINT PK, partner_code VARCHAR(30) UNIQUE NOT NULL, name VARCHAR(100), partner_type VARCHAR(10) CHECK IN ('LOCAL','OVERSEAS') NOT NULL, collection_ccy CHAR(3), settle_a_ccy CHAR(3), rate_quote_ttl_seconds INT DEFAULT 300 CHECK BETWEEN 60 AND 1800, low_balance_threshold_usd DECIMAL(20,4) nullable (OVERSEAS only), status VARCHAR(20) CHECK IN ('ONBOARDING','ACTIVE','SUSPENDED','INACTIVE'), webhook_url VARCHAR(512), is_active BOOLEAN DEFAULT true, plus standard audit columns. partner_credential: api_key VARCHAR(64) UNIQUE, api_secret_hash VARCHAR(128), partner_id FK partner, is_active BOOLEAN, expires_at TIMESTAMPTZ nullable; partial UNIQUE index on (partner_id) WHERE is_active=true enforces one active credential per partner. Services: services/config-registry (writes), all payment services (reads via Redis cache). | • Create db/migration/V003__create_partner.sql. • Write CREATE TABLE partner with all CHECK constraints, index on (partner_code), (status), (partner_type). • Write CREATE TABLE partner_credential with FK, UNIQUE on api_key, partial UNIQUE index CREATE UNIQUE INDEX uq_partner_cred_active ON partner_credential(partner_id) WHERE is_active=true. • Run flyway migrate; verify V003 in flyway_schema_history. • Add Testcontainers test: insert two active credentials for same partner_id; assert unique violation; insert one active + one inactive; assert success. | lib-persistence/src/main/resources/db/migration/V003__create_partner.sql | • partner_type='INVALID' raises CHECK constraint violation. • Two active credentials for same partner_id raise unique index violation; one active + one inactive is allowed. • rate_quote_ttl_seconds defaults to 300; value 59 raises CHECK violation. • flyway_schema_history version=003 success=true. | 35 | 3.7-T03 | DBA | OPS-13
3.7-T05 | shared-libs | 3.7 | 3. Data Layer & Persistence | Migration framework & seed data | 1 | V004 Flyway migration: rule, service_charge_tier, and treasury_rate tables | rule: UNIQUE(partner_id, scheme_id, direction); direction CHECK IN ('INBOUND','OUTBOUND','DOMESTIC','HUB'); m_a and m_b DECIMAL(8,6); status CHECK IN ('DRAFT','ACTIVE','SUSPENDED'); is_same_ccy_shortcircuit BOOLEAN; effective_from/to TIMESTAMPTZ. service_charge_tier: FK rule_id, min_collection_usd DECIMAL(20,4), max_collection_usd DECIMAL(20,4) nullable, charge_amount DECIMAL(20,4). treasury_rate: ccy_pair VARCHAR(10) NOT NULL, rate DECIMAL(20,8) NOT NULL, source VARCHAR(10) CHECK IN ('LIVE','MANUAL'), effective_at TIMESTAMPTZ; no unique on ccy_pair (historical rows); index on (ccy_pair, effective_at DESC) for fast latest-rate lookup. Services: services/rate-fx (rate-engine reads), services/config-registry (writes). | • Create db/migration/V004__create_rule_treasury_rate.sql. • Write CREATE TABLE rule with FKs, UNIQUE(partner_id, scheme_id, direction), CHECK constraints on direction and status. • Write CREATE TABLE service_charge_tier with FK rule_id, CHECK min_collection_usd >= 0. • Write CREATE TABLE treasury_rate; CREATE INDEX idx_treasury_rate_ccy_pair ON treasury_rate(ccy_pair, effective_at DESC). • Run flyway migrate; verify V004. • Testcontainers test: assert UNIQUE(partner_id, scheme_id, direction) rejects duplicate; assert latest rate query uses index (EXPLAIN plan). | lib-persistence/src/main/resources/db/migration/V004__create_rule_treasury_rate.sql | • UNIQUE(partner_id, scheme_id, direction) rejects second DOMESTIC rule for same partner+scheme. • direction='INVALID' raises CHECK constraint violation. • Two treasury_rate rows with same ccy_pair but different effective_at are both stored; SELECT ... ORDER BY effective_at DESC LIMIT 1 returns the later row. • flyway_schema_history version=004 success=true. | 40 | 3.7-T04 | DBA | OPS-13
3.7-T06 | shared-libs | 3.7 | 3. Data Layer & Persistence | Migration framework & seed data | 1 | V005 Flyway migration: rate_quote and transaction tables | rate_quote stores rate-engine output per GET /v1/rates call. Key columns: quote_ref VARCHAR(64) UNIQUE, all USD-pool values DECIMAL(20,8) nullable for same-ccy (payout_usd_cost, collection_usd, collection_margin_usd, payout_margin_usd), send_amount DECIMAL(20,4), service_charge DECIMAL(20,4), collection_amount DECIMAL(20,4), offer_rate_coll DECIMAL(20,8), cross_rate DECIMAL(20,8), cost_rate_coll DECIMAL(20,8), cost_rate_pay DECIMAL(20,8), valid_until TIMESTAMPTZ, is_used BOOLEAN DEFAULT false. transaction: hub_txn_ref VARCHAR(64) UNIQUE, status CHECK IN ('QUOTED','PENDING_DEBIT','DEBITED','SCHEME_SENT','APPROVED','DECLINED','UNCERTAIN','FAILED','CANCELLED','REFUNDED'), immutable locked_* copies of all rate fields. Service: services/payment-executor, services/transaction-mgmt. | • Create db/migration/V005__create_rate_quote_transaction.sql. • Write CREATE TABLE rate_quote with all columns; add indexes on (rule_id, valid_until), (partner_id, is_used), (quote_ref). • Write CREATE TABLE transaction with FK to rate_quote, partner, scheme, rule; status CHECK constraint; indexes on (partner_id, created_at DESC), (status, created_at), (hub_txn_ref), (scheme_ref). • Run flyway migrate; verify V005. • Testcontainers test: assert status='BAD' raises CHECK; assert hub_txn_ref is UNIQUE. | lib-persistence/src/main/resources/db/migration/V005__create_rate_quote_transaction.sql | • status='UNKNOWN' on transaction raises CHECK constraint violation. • hub_txn_ref UNIQUE constraint rejects duplicate insert. • rate_quote.valid_until column type is TIMESTAMPTZ (verify via JDBC metadata in Testcontainers test). • flyway_schema_history version=005 success=true. • EXPLAIN on transaction WHERE status='QUOTED' AND created_at > now()-interval '1 day' uses the (status, created_at) index. | 45 | 3.7-T05 | DBA | OPS-13
3.7-T07 | shared-libs | 3.7 | 3. Data Layer & Persistence | Migration framework & seed data | 1 | V006 Flyway migration: transaction_event, prefunding, and settlement tables | transaction_event: FK transaction_id, event_type VARCHAR(40) CHECK IN ('RATE_QUOTE_ISSUED','PREFUND_DEDUCTED','SCHEME_SUBMITTED','SCHEME_APPROVED','SCHEME_DECLINED','TRANSACTION_COMMITTED','SETTLEMENT_BATCHED','WEBHOOK_DELIVERED'), payload JSONB, occurred_at TIMESTAMPTZ; index on (transaction_id, occurred_at). prefunding_account: partner_id FK UNIQUE (one per partner), balance_usd DECIMAL(20,4) DEFAULT 0, low_balance_threshold_usd DECIMAL(20,4). prefunding_ledger_entry: FK prefunding_account, amount_usd DECIMAL(20,4), entry_type CHECK IN ('DEBIT','CREDIT','REVERSAL'). settlement_batch, settlement_file, reconciliation_item tables. Services: services/payment-executor (events), services/prefunding (balance/ledger), services/settlement. | • Create db/migration/V006__create_txn_events_prefunding_settlement.sql. • Write CREATE TABLE transaction_event with event_type CHECK, JSONB payload, index (transaction_id, occurred_at). • Write CREATE TABLE prefunding_account UNIQUE(partner_id); CREATE TABLE prefunding_ledger_entry with entry_type CHECK; index on (prefunding_account_id, created_at). • Write CREATE TABLE settlement_batch, settlement_file (status CHECK IN ('PENDING','GENERATED','TRANSMITTED','RECEIVED','RECONCILED','ERROR')), reconciliation_item (status CHECK IN ('MATCHED','MISMATCH','MISSING')). • Run flyway migrate; verify V006; Testcontainers test for event_type CHECK and prefunding_account UNIQUE. | lib-persistence/src/main/resources/db/migration/V006__create_txn_events_prefunding_settlement.sql | • event_type='STEP_99' raises CHECK constraint violation on transaction_event. • UNIQUE(partner_id) on prefunding_account rejects second account for same partner. • prefunding_ledger_entry.entry_type='ADJUSTMENT' raises CHECK violation. • settlement_file.status='INVALID' raises CHECK violation. • flyway_schema_history version=006 success=true. | 40 | 3.7-T06 | DBA | OPS-13
3.7-T08 | shared-libs | 3.7 | 3. Data Layer & Persistence | Migration framework & seed data | 1 | V007 Flyway migration: merchant and qr_code tables (PostgreSQL copy for payment-path reads) | Payment-time merchant and QR validation queries GMEPay+'s local DB (synced from ZeroPay via SFTP), not ZeroPay live API. merchant: merchant_id VARCHAR(50) UNIQUE, merchant_type VARCHAR(30), name VARCHAR(200), business_registration_no VARCHAR(30), franchise_code VARCHAR(30), category_code VARCHAR(20), bank_code VARCHAR(10), account_no VARCHAR(30) AES-256 encrypted at rest via pgcrypto, fee_tier VARCHAR(20) CHECK IN ('DOMESTIC','CROSSBORDER'), status VARCHAR(20) CHECK IN ('ACTIVE','SUSPENDED','DEACTIVATED'), is_active BOOLEAN DEFAULT true, synced_at TIMESTAMPTZ. qr_code: FK merchant_id, qr_code_value VARCHAR(512) UNIQUE, qr_code_type VARCHAR(15) CHECK IN ('STATIC_MPM','DYNAMIC_CPM'), status VARCHAR(20) CHECK IN ('ACTIVE','DEACTIVATED'), is_active BOOLEAN, synced_at TIMESTAMPTZ. Service: services/merchant-qr. | • Create db/migration/V007__create_merchant_qr_code.sql. • Write CREATE TABLE merchant with all columns; AES-256 note in column comment for account_no; index on (merchant_id), (is_active, status), (name varchar_pattern_ops for prefix search). • Write CREATE TABLE qr_code with FK merchant, UNIQUE(qr_code_value), CHECK constraints, index on (qr_code_value), (is_active). • Run flyway migrate; verify V007. • Testcontainers test: assert fee_tier CHECK, status CHECK, and qr_code_value UNIQUE constraint. | lib-persistence/src/main/resources/db/migration/V007__create_merchant_qr_code.sql | • fee_tier='INVALID' raises CHECK violation on merchant. • qr_code_value UNIQUE constraint rejects duplicate QR string. • status='UNKNOWN' raises CHECK violation on qr_code. • Index on qr_code(qr_code_value) confirmed via pg_indexes query. • flyway_schema_history version=007 success=true. | 35 | 3.7-T07 | DBA | OPS-13
3.7-T09 | shared-libs | 3.7 | 3. Data Layer & Persistence | Migration framework & seed data | 1 | V008 Flyway migration: audit_log, feature_flags, and sftp_file_log tables | audit_log: entity_type VARCHAR(40), entity_id BIGINT, actor VARCHAR(60), action VARCHAR(40), previous_value JSONB, new_value JSONB, applied_at TIMESTAMPTZ; append-only (no update/delete by app). feature_flags: flag_name VARCHAR(60) UNIQUE, is_enabled BOOLEAN DEFAULT false, description VARCHAR(255), updated_at, updated_by. sftp_file_log: physical metadata for each SFTP file exchanged with ZeroPay: file_type VARCHAR(10), direction VARCHAR(4) CHECK IN ('IN','OUT'), filename VARCHAR(255), file_size_bytes BIGINT, checksum VARCHAR(64), object_storage_path VARCHAR(512), status VARCHAR(20) CHECK IN ('PENDING','TRANSMITTED','RECEIVED','ARCHIVED','ERROR'), transmitted_at TIMESTAMPTZ nullable, received_at TIMESTAMPTZ nullable. Service: services/settlement (sftp_file_log), services/config-registry (audit_log, feature_flags). | • Create db/migration/V008__create_audit_log_feature_flags_sftp.sql. • Write CREATE TABLE audit_log; indexes on (entity_type, entity_id), (actor), (applied_at DESC). • Write CREATE TABLE feature_flags with UNIQUE(flag_name). • Write CREATE TABLE sftp_file_log with direction CHECK, status CHECK; index on (file_type, received_at), (status). • Run flyway migrate; verify V008. • Testcontainers test: assert audit_log allows NULL previous_value (new-entity creates); assert feature_flags UNIQUE constraint. | lib-persistence/src/main/resources/db/migration/V008__create_audit_log_feature_flags_sftp.sql | • audit_log accepts previous_value=NULL (no error on INSERT with NULL JSONB). • feature_flags UNIQUE(flag_name) rejects duplicate flag name. • sftp_file_log.direction='INVALID' raises CHECK violation. • sftp_file_log.status='INVALID' raises CHECK violation. • flyway_schema_history version=008 success=true. | 30 | 3.7-T08 | DBA | OPS-13
3.7-T10 | shared-libs | 3.7 | 3. Data Layer & Persistence | Migration framework & seed data | 1 | Flyway seed migration V009: reference data (treasury rates, ZeroPay scheme, partners, rules, feature flags) | OPS-13 requires seed data applied automatically before app start in dev/test. A dedicated Flyway seed migration V009 inserts idempotent reference rows (INSERT ... ON CONFLICT DO NOTHING). Rows: treasury_rate: usd_krw=1350.00000000, usd_mnt=3500.00000000, usd_usd=1.00000000 (source=MANUAL). qr_scheme: ZEROPAY (payout_ccy=KRW, gme_fee_share_pct=0.7000, status=TESTING). scheme_country: ZEROPAY/KR. partner: GME_REMIT (LOCAL/KRW, ttl=300), SENDMN (OVERSEAS/USD, ttl=300, low_balance_threshold=10000). prefunding_account: SENDMN balance=50000.00 USD. rule: GME_REMIT+ZEROPAY+DOMESTIC (same-ccy, m_a=0, m_b=0), GME_REMIT+ZEROPAY+INBOUND (same-ccy, m_a=0.01, m_b=0.005), SENDMN+ZEROPAY+INBOUND (cross-border, m_a=0.015, m_b=0.010). feature_flags: five Phase-1 flags all is_enabled=false. | • Create db/migration/V009__seed_reference_data.sql; add comment SEED-ONLY DO NOT RUN IN PRODUCTION WITHOUT REVIEW. • INSERT treasury_rate rows with ON CONFLICT (ccy_pair ... partial) DO NOTHING; effective_at=now(), created_by='SEED'. • INSERT qr_scheme, scheme_country, partner, prefunding_account with ON CONFLICT DO NOTHING and subqueries for FK resolution. • INSERT three rule rows using subqueries; ON CONFLICT(partner_id, scheme_id, direction) DO NOTHING. • INSERT five feature_flag rows ON CONFLICT(flag_name) DO NOTHING. | lib-persistence/src/main/resources/db/migration/V009__seed_reference_data.sql | • After flyway migrate from clean DB: treasury_rate has 3 rows, qr_scheme=1, scheme_country=1, partner=2, prefunding_account=1, rule=3, feature_flags=5. • Running flyway migrate a second time (no schema change) is idempotent; V009 is not re-executed (already in flyway_schema_history). • SELECT rate FROM treasury_rate WHERE ccy_pair='usd_usd' returns 1.00000000. • SENDMN rule m_a+m_b=0.025 >= 0.02 (cross-border minimum margin satisfied): SELECT m_a+m_b FROM rule r JOIN partner p ON p.id=r.partner_id WHERE p.partner_code='SENDMN' returns 0.025000. • All five feature_flags rows have is_enabled=false. | 35 | 3.7-T09 | DBA | OPS-13
3.7-T11 | shared-libs | 3.7 | 3. Data Layer & Persistence | Migration framework & seed data | 1 | Testcontainers integration test: full Flyway migration suite V001-V009 | lib-persistence module must have a Testcontainers JUnit 5 integration test that spins up a PostgreSQL 16 container, applies all migrations V001-V009 via the Flyway bean, and asserts the final schema and seed data. Test class: MigrationSuiteIntegrationTest in lib-persistence/src/test/java/com/gme/pay/persistence/. Uses @Testcontainers and PostgreSQLContainer from org.testcontainers:postgresql. Spring Boot test slice: @DataJpaTest with replaced datasource pointing at the container. | • Add testcontainers BOM and postgresql artifact to lib-persistence/build.gradle (testImplementation scope). • Write MigrationSuiteIntegrationTest.java with @Testcontainers, @SpringBootTest(classes=MigrationTestConfig.class), PostgreSQLContainer<> field. • Assert flyway_schema_history has exactly 9 rows all with success=true. • Assert extension uuid-ossp exists; assert treasury_rate row count=3; assert feature_flags count=5. • Assert SENDMN rule m_a+m_b=0.025 via JDBC query. | lib-persistence/src/test/java/com/gme/pay/persistence/MigrationSuiteIntegrationTest.java | • Test passes with PostgreSQL 16 Testcontainers image in CI (no local DB required). • flyway_schema_history has exactly 9 rows with success=true. • Deliberate checksum mutation of V003 causes test to fail with FlywayValidateException. • seed row usd_krw rate=1350.00000000 is present in treasury_rate. • Test runtime under 60 seconds on a standard CI runner. | 45 | 3.7-T10 | DBA | OPS-13
3.7-T12 | shared-libs | 3.7 | 3. Data Layer & Persistence | Migration framework & seed data | 1 | MongoDB configuration: Spring Data MongoDB setup and collection naming conventions | GMEPay+ uses MongoDB for merchant/QR read-models and CQRS projections (services/merchant-qr). The locked stack specifies MongoDB. Spring Data MongoDB is configured via spring.data.mongodb.uri (injected from env var MONGODB_URI, e.g. mongodb://localhost:27017/gmepay_dev). Collections are named with snake_case, prefixed by domain: merchant_read_model, qr_read_model, transaction_summary_projection, partner_balance_snapshot. Module: services/merchant-qr depends on lib-persistence; MongoDB config lives in services/merchant-qr/src/main/java/com/gme/pay/merchantqr/config/MongoConfig.java. Local dev: docker-compose mongodb service on port 27017. | • Add spring-boot-starter-data-mongodb to services/merchant-qr/build.gradle. • Create MongoConfig.java annotated @Configuration with @EnableMongoRepositories(basePackages='com.gme.pay.merchantqr.repository') and a MongoMappingContext bean setting auto-index creation to false (create indexes explicitly). • Add MONGODB_URI to application.yml as spring.data.mongodb.uri: ${MONGODB_URI:mongodb://localhost:27017/gmepay_dev}. • Create MongoCollections.java constants class with static final Strings for each collection name (MERCHANT_READ_MODEL, QR_READ_MODEL, TRANSACTION_SUMMARY_PROJECTION, PARTNER_BALANCE_SNAPSHOT). • Write a Testcontainers test MongoConfigTest using MongoDBContainer that asserts the connection is alive and listCollectionNames() returns no error. | services/merchant-qr/src/main/java/com/gme/pay/merchantqr/config/MongoConfig.java; MongoCollections.java constants; Testcontainers MongoConfigTest.java | • Application context starts with a MongoDBContainer Testcontainers instance (no local Mongo needed). • MONGODB_URI env var overrides the default URI in application.yml. • MongoMappingContext auto-index creation is false (indexes created by explicit ensureIndex calls, not auto). • MongoCollections.MERCHANT_READ_MODEL equals 'merchant_read_model' (verified in unit test). | 30 | 3.7-T01 | DBA | OPS-13
3.7-T13 | shared-libs | 3.7 | 3. Data Layer & Persistence | Migration framework & seed data | 1 | MongoDB document model: MerchantReadModel document class for merchant-qr service | The merchant_read_model MongoDB collection is a denormalized read-model of the PostgreSQL merchant table, maintained by projections updated on ZeroPay SFTP sync events. Document fields mirror the merchant table but include the nested list of active QR codes. Document: _id (String = merchant_id), merchantType, name, businessRegistrationNo, franchiseCode, categoryCode, feeTier (DOMESTIC¦CROSSBORDER), status (ACTIVE¦SUSPENDED¦DEACTIVATED), isActive (Boolean), syncedAt (Instant), activeQrCodes (List<QrCodeEmbed> with qrCodeValue String, qrCodeType String, isActive Boolean). Stored in collection merchant_read_model. Service: services/merchant-qr. | • Create MerchantReadModel.java in services/merchant-qr/src/main/java/com/gme/pay/merchantqr/document/ annotated @Document(collection='merchant_read_model'). • Add @Id String merchantId field and all merchant fields; add @Indexed on merchantId (unique=true), isActive, status. • Create nested static class QrCodeEmbed with qrCodeValue, qrCodeType, isActive fields. • Create MerchantReadModelRepository.java extending MongoRepository<MerchantReadModel, String> with custom query findByMerchantIdAndIsActiveTrue(String merchantId). • Write unit test with embedded MongoDBContainer asserting save, findById, and findByMerchantIdAndIsActiveTrue return correct results. | services/merchant-qr/src/main/java/com/gme/pay/merchantqr/document/MerchantReadModel.java; MerchantReadModelRepository.java | • MerchantReadModel with two embedded QrCodeEmbed objects saves and retrieves correctly from MongoDBContainer. • findByMerchantIdAndIsActiveTrue returns present for active merchant, empty for isActive=false merchant. • @Document collection name is 'merchant_read_model' (verified via reflection in unit test). • Saving a second document with same merchantId (unique=true on @Indexed) throws DuplicateKeyException. | 40 | 3.7-T12 | DBA | OPS-13
3.7-T14 | shared-libs | 3.7 | 3. Data Layer & Persistence | Migration framework & seed data | 1 | MongoDB document model: QrReadModel document and repository for QR-code fast lookup | The qr_read_model collection stores one document per QR code string for sub-millisecond lookup at payment time. A GET /v1/merchants/{qr} call hits this collection first (Redis cache miss falls back to Mongo). Document: _id (String = qrCodeValue), merchantId (String), merchantName, merchantStatus (ACTIVE¦SUSPENDED¦DEACTIVATED), feeTier, isActive (Boolean), qrCodeType (STATIC_MPM¦DYNAMIC_CPM), syncedAt (Instant). Index: unique on _id (implicit), compound on (merchantId, isActive). Service: services/merchant-qr. | • Create QrReadModel.java annotated @Document(collection='qr_read_model') with all fields; @Id is qrCodeValue. • Create QrReadModelRepository extending MongoRepository<QrReadModel, String>; add findByQrCodeValueAndIsActiveTrue method. • In MongoConfig.java add explicit index creation for compound (merchantId, isActive) on startup using MongoTemplate.indexOps('qr_read_model').ensureIndex(...). • Write Testcontainers test: save two QR docs for same merchantId, call findByQrCodeValueAndIsActiveTrue, assert correct result for active vs inactive. • Assert that a deactivated QR code (isActive=false) is NOT returned by findByQrCodeValueAndIsActiveTrue. | services/merchant-qr/src/main/java/com/gme/pay/merchantqr/document/QrReadModel.java; QrReadModelRepository.java | • findByQrCodeValueAndIsActiveTrue returns empty Optional when isActive=false even if qrCodeValue matches. • Compound index (merchantId, isActive) exists after ensureIndex call (verified via MongoTemplate.indexOps().getIndexInfo()). • Saving duplicate _id (qrCodeValue) throws DuplicateKeyException. • Document round-trip: save, findById, assert all fields preserved including syncedAt Instant precision. | 35 | 3.7-T13 | DBA | OPS-13
3.7-T15 | shared-libs | 3.7 | 3. Data Layer & Persistence | Migration framework & seed data | 1 | MongoDB document model: TransactionSummaryProjection for read-side transaction search | The transaction_summary_projection collection provides fast transaction search for the Ops portal (services/transaction-mgmt or services/reporting-compliance) without hitting PostgreSQL. Projection document: _id (String = txnRef), hubTxnRef, partnerId, partnerCode, schemeCode, paymentMode, direction, status, targetPayout (BigDecimal), payoutCcy, collectionAmount, collectionCcy, offerRateColl, committedAt (Instant), updatedAt. Indexes: (partnerId, committedAt DESC), (status), (hubTxnRef unique). This is a CQRS read-model updated by domain events from the payment Outbox. Service: services/transaction-mgmt (writes via EventPublisher), services/reporting-compliance (reads). | • Create TransactionSummaryProjection.java annotated @Document(collection='transaction_summary_projection'); @Id = txnRef String. • Add @Indexed(unique=true) on hubTxnRef; @CompoundIndex on (partnerId, committedAt) and (status). • Create TransactionSummaryProjectionRepository with findByPartnerIdAndStatusOrderByCommittedAtDesc and findByHubTxnRef methods. • Add explicit ensureIndex calls in MongoConfig for compound indexes. • Write Testcontainers test: insert 3 projections for same partnerId with different statuses and committedAt; assert sort order and status filter. | services/transaction-mgmt/src/main/java/com/gme/pay/txnmgmt/document/TransactionSummaryProjection.java; TransactionSummaryProjectionRepository.java | • findByPartnerIdAndStatusOrderByCommittedAtDesc returns documents in descending committedAt order. • Unique index on hubTxnRef throws DuplicateKeyException on duplicate insert. • Compound index (partnerId, committedAt) confirmed via indexOps().getIndexInfo(). • BigDecimal fields (targetPayout, collectionAmount, offerRateColl) round-trip without precision loss. | 40 | 3.7-T14 | DBA | OPS-13
3.7-T16 | shared-libs | 3.7 | 3. Data Layer & Persistence | Migration framework & seed data | 1 | MongoDB document model: PartnerBalanceSnapshot projection for prefunding dashboard | The partner_balance_snapshot collection provides a real-time read-model of OVERSEAS partner prefunding balances for the Ops portal and low-balance alert logic. Document: _id (String = partnerCode), partnerName, partnerType, balanceUsd (BigDecimal), lowBalanceThresholdUsd (BigDecimal), lastDebitAt (Instant), lastCreditAt (Instant), updatedAt (Instant). Updated by the prefunding service on every debit/credit event via the Outbox -> EventPublisher interface. Index: unique on _id (implicit). Service: services/prefunding (writes), services/reporting-compliance (reads). | • Create PartnerBalanceSnapshot.java annotated @Document(collection='partner_balance_snapshot'); @Id = partnerCode String. • Add all fields with proper types (BigDecimal for monetary, Instant for timestamps). • Create PartnerBalanceSnapshotRepository extending MongoRepository<PartnerBalanceSnapshot,String>; add findByBalanceUsdLessThanEqualAndPartnerType for low-balance alerting. • Write Testcontainers test: save snapshot, update balance, assert updated value persisted; assert low-balance query returns partner when balance < threshold. • Verify balanceUsd BigDecimal stores 4 decimal places (50000.0000) without rounding. | services/prefunding/src/main/java/com/gme/pay/prefunding/document/PartnerBalanceSnapshot.java; PartnerBalanceSnapshotRepository.java | • findByBalanceUsdLessThanEqualAndPartnerType returns partner when balance=9999.00 and threshold=10000.00. • findByBalanceUsdLessThanEqualAndPartnerType returns empty when balance=10000.00 (equal, not less than). • BigDecimal 50000.0000 round-trips without conversion to Double or Float. • Document update (save over existing _id) replaces all fields atomically. | 35 | 3.7-T15 | DBA | OPS-13
3.7-T17 | shared-libs | 3.7 | 3. Data Layer & Persistence | Migration framework & seed data | 1 | Redis configuration: Spring Data Redis setup and keyspace naming conventions | GMEPay+ uses Redis 7 (Cluster mode in prod, single node for dev) for: rate-quote TTL cache (key rate_quote:{quote_ref}, TTL=partner's rate_quote_ttl_seconds, default 60s aggregator-bound / 300s otherwise, range 60-1800s), idempotency key store (key idempotency:{partner_id}:{idempotency_key}, TTL=86400s / 24h), config/registry hot cache (key config:partner:{partner_code}, config:rule:{rule_id}, config:treasury_rate:{ccy_pair}, no fixed TTL, invalidated on config change), distributed lock (key lock:batch:{job_name}, via SETNX). Module: services/rate-fx (rate-quote cache), services/payment-executor (idempotency), services/config-registry (config cache). Spring Boot autoconfigures RedisTemplate via spring.data.redis.url from env var REDIS_URL. | • Add spring-boot-starter-data-redis to services/rate-fx, services/payment-executor, services/config-registry build.gradle. • Create RedisConfig.java in each service's config package with @EnableRedisRepositories and a StringRedisTemplate bean plus a typed RedisTemplate<String, byte[]> bean using JdkSerializationRedisSerializer for values. • Create RedisKeySpace.java constants class with static final String templates: RATE_QUOTE (rate_quote:{0}), IDEMPOTENCY (idempotency:{0}:{1}), CONFIG_PARTNER (config:partner:{0}), CONFIG_RULE (config:rule:{0}), CONFIG_TREASURY (config:treasury_rate:{0}), BATCH_LOCK (lock:batch:{0}). • Add spring.data.redis.url: ${REDIS_URL:redis://localhost:6379} to each service application.yml. • Write Testcontainers test using GenericContainer with redis:7-alpine image; assert PING returns PONG; assert key construction using RedisKeySpace.format() matches expected strings. | services/rate-fx/src/main/java/com/gme/pay/ratefx/config/RedisConfig.java; shared RedisKeySpace.java in lib-persistence; Testcontainers RedisConfigTest.java | • RedisKeySpace.format(RATE_QUOTE, 'abc123') returns 'rate_quote:abc123'. • RedisKeySpace.format(IDEMPOTENCY, 'GME_REMIT', 'key1') returns 'idempotency:GME_REMIT:key1'. • Testcontainers Redis container responds to PING with PONG via StringRedisTemplate. • REDIS_URL env var overrides the default localhost URI. | 35 | 3.7-T01 | DBA | OPS-13
3.7-T18 | shared-libs | 3.7 | 3. Data Layer & Persistence | Migration framework & seed data | 1 | Redis rate-quote cache: store and retrieve RateQuoteCache DTO with TTL | When the rate engine issues a quote (GET /v1/rates), the result is stored in Redis under key rate_quote:{quote_ref} with TTL = partner's rate_quote_ttl_seconds (default 300s; 60s if aggregator-bound; configured on partner.rate_quote_ttl_seconds, range 60-1800s). The validUntil = quote_issued_at + TTL. On POST /v1/payments (commit), the orchestrator calls lockRateQuote(quote_ref): if key is absent (expired) the transaction is FAILED with RATE_QUOTE_EXPIRED. Value: JSON-serialized RateQuoteCache DTO with quoteRef, ruleId, partnerId, all five USD-pool DECIMAL values, send_amount, service_charge, collection_amount, offerRateColl, crossRate, validUntil. Service: services/rate-fx. | • Create RateQuoteCacheDto.java in services/rate-fx/src/main/java/com/gme/pay/ratefx/cache/ with all required fields using BigDecimal for monetary values. • Create RateQuoteCacheService.java @Service with methods: store(RateQuoteCacheDto dto, int ttlSeconds) using RedisTemplate.opsForValue().set(key, serialized, ttlSeconds, SECONDS); Optional<RateQuoteCacheDto> get(String quoteRef); boolean lockAndInvalidate(String quoteRef) using RedisTemplate.delete(). • Use Jackson ObjectMapper for serialization; store as JSON byte[]. • Write RateQuoteCacheServiceTest.java with Testcontainers Redis 7: store a quote with ttl=2s, assert get() returns present within 1s, assert get() returns empty after 2.1s sleep. • Assert lockAndInvalidate deletes key and returns true on first call, false on second call (key already gone). | services/rate-fx/src/main/java/com/gme/pay/ratefx/cache/RateQuoteCacheService.java; RateQuoteCacheDto.java; RateQuoteCacheServiceTest.java | • get(quoteRef) returns present within TTL; returns empty after TTL expiry (Testcontainers test with 2s TTL). • lockAndInvalidate returns true first call (key present), false second call (key already deleted). • BigDecimal fields (collection_usd with DECIMAL(20,8) scale) serialize and deserialize without precision loss via Jackson. • TTL of 60s is accepted (lower bound); TTL of 1800s is accepted (upper bound); any value below 60 is rejected with IllegalArgumentException before store. | 40 | 3.7-T17 | DBA | OPS-13
3.7-T19 | shared-libs | 3.7 | 3. Data Layer & Persistence | Migration framework & seed data | 1 | Redis idempotency key store: write and read idempotency responses with 24h TTL | All POST endpoints require an Idempotency-Key header. GMEPay+ stores (partner_id, idempotency_key) -> (status_code, response_body) for 24 hours (86400s TTL). On duplicate POST within 24h: return stored response without re-processing. If body differs from first call: return HTTP 422 IDEMPOTENCY_BODY_MISMATCH. Key pattern: idempotency:{partner_code}:{idempotency_key}. Value: JSON with statusCode (int), responseBody (String), requestBodyHash (SHA-256 hex of original request body). Service: services/payment-executor (Spring @Service IdempotencyService, called from @RestController via Spring Cloud Gateway filter that enforces Idempotency-Key header presence). | • Create IdempotencyRecord.java DTO with statusCode, responseBody, requestBodyHash fields. • Create IdempotencyService.java @Service with: Optional<IdempotencyRecord> get(String partnerCode, String idempotencyKey); void store(String partnerCode, String idempotencyKey, IdempotencyRecord record) with TTL=86400s; boolean isBodyMatch(IdempotencyRecord stored, String incomingBodyHash). • Implement isBodyMatch: return stored.getRequestBodyHash().equals(incomingBodyHash). • Write IdempotencyServiceTest with Testcontainers Redis: store a record, assert get() returns it; store again with different hash, assert isBodyMatch=false; assert key expires after TTL. • Assert storing the same key twice with same hash is idempotent (no overwrite, same TTL preserved using SET NX mode). | services/payment-executor/src/main/java/com/gme/pay/executor/idempotency/IdempotencyService.java; IdempotencyRecord.java; IdempotencyServiceTest.java | • get() returns present for stored key within 24h; absent after TTL (tested with 2s TTL in test). • isBodyMatch returns false when incomingBodyHash differs from stored hash. • SET NX semantics: second store() call with same key does NOT overwrite the existing record. • Key format is 'idempotency:{partnerCode}:{idempotencyKey}' (assert via RedisKeySpace.format). | 40 | 3.7-T18 | DBA | OPS-13
3.7-T20 | shared-libs | 3.7 | 3. Data Layer & Persistence | Migration framework & seed data | 1 | Redis config cache: store and invalidate partner and rule config with pub/sub eviction | services/config-registry maintains a Redis hot cache of active partner, rule, and treasury_rate config. Keys: config:partner:{partnerCode} (no fixed TTL, invalidated on change), config:rule:{ruleId} (no fixed TTL), config:treasury_rate:{ccyPair} (no fixed TTL). On any config entity update via the Admin API, the config-registry @Service publishes a cache-invalidation event via RedisTemplate.convertAndSend('config-cache-invalidation', key) and deletes the key. Consumer services (rate-fx, payment-executor) subscribe with @RedisListener on channel config-cache-invalidation and evict local in-memory caches (Spring Caffeine L1 cache). Distributed locking: batch jobs use SETNX lock:batch:{jobName} with TTL=300s. | • Create ConfigCacheService.java @Service in services/config-registry with get/store/invalidate methods using RedisTemplate; invalidate deletes key AND publishes to channel 'config-cache-invalidation'. • Create ConfigCacheInvalidationListener.java in services/rate-fx implementing MessageListener for channel config-cache-invalidation; on message evict matching Caffeine cache entry. • Create BatchLockService.java @Service in services/settlement with acquireLock(jobName, ttlSeconds): uses RedisTemplate.opsForValue().setIfAbsent(key, hostname, ttl, SECONDS); returns true if acquired. • Write Testcontainers tests: assert invalidate deletes key; assert pub/sub message received by listener; assert SETNX acquireLock returns true first call and false second call. • Assert lock expires after TTL (test with ttl=1s; assert second acquireLock returns true after 1.1s). | services/config-registry/src/main/java/com/gme/pay/config/cache/ConfigCacheService.java; services/settlement/src/main/java/com/gme/pay/settlement/lock/BatchLockService.java; ConfigCacheInvalidationListener.java | • invalidate(key) deletes Redis key and publishes message to config-cache-invalidation channel. • acquireLock returns true on first call; false on second call before TTL expires. • acquireLock returns true after TTL expiry (lock released by timeout). • ConfigCacheInvalidationListener receives pub/sub message and evicts cache entry (verified in Testcontainers test with embedded listener). | 45 | 3.7-T19 | DBA | OPS-13
3.7-T21 | shared-libs | 3.7 | 3. Data Layer & Persistence | Migration framework & seed data | 1 | Redis Testcontainers integration test: rate-quote TTL, idempotency, config cache end-to-end | A combined integration test validates all three Redis keyspace behaviors in a single Testcontainers Redis 7 container. This ensures keyspace isolation (keys from different domains do not collide), TTL semantics work correctly, and the KeySpace naming convention is enforced. Test class: RedisKeyspaceIntegrationTest in lib-persistence/src/test/java/com/gme/pay/persistence/. Uses GenericContainer with redis:7-alpine. | • Write RedisKeyspaceIntegrationTest.java with @Testcontainers, GenericContainer redis:7-alpine. • Test 1 (rate-quote): store quote with TTL=2s; assert present at t=0.5s; assert absent at t=2.5s. • Test 2 (idempotency): store record with SET NX TTL=2s; assert second store() does NOT overwrite; assert absent at t=2.5s. • Test 3 (config cache): store config entry (no TTL), invalidate it, assert absent; assert pub/sub message received. • Test 4 (batch lock): acquire lock, assert second acquire fails; wait TTL, assert re-acquire succeeds. | lib-persistence/src/test/java/com/gme/pay/persistence/RedisKeyspaceIntegrationTest.java | • All four test scenarios pass in CI with Redis 7 Testcontainers image. • Key collision test: rate_quote:abc123 and idempotency:GME_REMIT:abc123 are independent keys (deleting one does not affect the other). • Test 1 TTL expiry is verified with actual time-based assertion (not just key deletion). • Test runs in under 30 seconds total. | 40 | 3.7-T20 | DBA | OPS-13
3.7-T22 | shared-libs | 3.7 | 3. Data Layer & Persistence | Migration framework & seed data | 1 | Object Storage configuration: Spring Cloud AWS S3 client setup for MinIO/S3-compatible storage | GMEPay+ uses S3-compatible object storage (MinIO for local/on-prem, AWS S3 ap-northeast-2 for prod) for: SFTP batch file archive (/gmepay/batch/{direction}/{file-type}/YYYY-MM-DD/{filename}), settlement reports (/gmepay/reports/{type}/YYYY/MM/{filename}), WAL archives, and compliance exports. Buckets: gmepay-batch-files (versioning enabled, immutable after write, 7-year retention), gmepay-reports (versioning enabled), gmepay-archives (versioning enabled). Credentials from env: AWS_ACCESS_KEY_ID, AWS_SECRET_ACCESS_KEY, AWS_REGION (default ap-northeast-2), S3_ENDPOINT_URL (for MinIO override). Service: services/settlement (batch files), services/reporting-compliance (reports). Module: lib-persistence provides shared ObjectStorageConfig. | • Add software.amazon.awssdk:s3 and software.amazon.awssdk:url-connection-client to lib-persistence/build.gradle. • Create ObjectStorageConfig.java @Configuration in lib-persistence with @Bean S3Client built from env vars AWS_ACCESS_KEY_ID, AWS_SECRET_ACCESS_KEY, AWS_REGION, and optional S3_ENDPOINT_URL override (for MinIO). • Create ObjectStorageBuckets.java constants with static final Strings: BATCH_FILES='gmepay-batch-files', REPORTS='gmepay-reports', ARCHIVES='gmepay-archives'. • Create ObjectStoragePathBuilder.java @Component with buildBatchPath(direction, fileType, date, filename) returning /gmepay/batch/{direction}/{fileType}/YYYY-MM-DD/{filename}. • Write Testcontainers test using localstack/localstack image with S3 service; assert bucket creation and PutObject/GetObject round-trip. | lib-persistence/src/main/java/com/gme/pay/persistence/storage/ObjectStorageConfig.java; ObjectStorageBuckets.java; ObjectStoragePathBuilder.java | • ObjectStoragePathBuilder.buildBatchPath('OUT','ZP0011', LocalDate.of(2026,6,5), 'ZP0011_20260605.txt') returns '/gmepay/batch/OUT/ZP0011/2026-06-05/ZP0011_20260605.txt'. • S3Client uses S3_ENDPOINT_URL when set (MinIO override) and ignores it when absent (AWS default endpoint). • PutObject to localstack bucket succeeds; GetObject returns identical bytes. • Bucket name constants match: gmepay-batch-files, gmepay-reports, gmepay-archives. | 40 | 3.7-T01 | DBA | OPS-13
3.7-T23 | shared-libs | 3.7 | 3. Data Layer & Persistence | Migration framework & seed data | 1 | Object Storage service: store and retrieve SFTP batch files with checksum verification | All inbound and outbound SFTP files (ZP00xx types) are stored in object storage immediately after transmission or receipt at path /gmepay/batch/{direction}/{file-type}/YYYY-MM-DD/{filename}. Object versioning is enabled; files are immutable once written. After upload, the SHA-256 checksum is computed and stored as S3 object metadata (x-amz-meta-checksum). On daily integrity check: retrieve the stored file and verify checksum matches the value in sftp_file_log.file_checksum. Service: services/settlement (BatchFileStorageService). Uses lib-persistence ObjectStorageConfig S3Client. | • Create BatchFileStorageService.java @Service in services/settlement with methods: store(String direction, String fileType, LocalDate date, String filename, byte[] content): computes SHA-256, calls S3Client.putObject with metadata; retrieve(String path): returns byte[]; verifyChecksum(String path, String expectedChecksum): computes SHA-256 of retrieved bytes and compares. • Use MessageDigest SHA-256 for checksum; encode as hex string. • Write BatchFileStorageServiceTest with localstack Testcontainers: store a file, assert object exists, assert retrieved bytes match original, assert verifyChecksum returns true. • Assert verifyChecksum returns false when expected checksum differs from actual. • Assert duplicate store to same path succeeds (object versioning — no overwrite error; latest version is retrieved). | services/settlement/src/main/java/com/gme/pay/settlement/storage/BatchFileStorageService.java; BatchFileStorageServiceTest.java | • store() uploads to correct path /gmepay/batch/OUT/ZP0011/2026-06-05/ZP0011_20260605.txt. • retrieve() returns byte[] identical to stored content. • verifyChecksum returns true when checksum matches; false when it differs (test with tampered expectedChecksum). • SHA-256 is computed server-side and stored as x-amz-meta-checksum object metadata. • Testcontainers localstack S3 test passes in CI. | 45 | 3.7-T22 | DBA | OPS-13
3.7-T24 | shared-libs | 3.7 | 3. Data Layer & Persistence | Migration framework & seed data | 1 | Object Storage service: store settlement reports and compliance exports | The gmepay-reports bucket stores BOK reports (FX1014, FX1015), revenue reports by partner/scheme/period, and reconciliation exports. Path convention: /gmepay/reports/{reportType}/YYYY/MM/{filename} (e.g. /gmepay/reports/BOK_FX1015/2026/06/bok_fx1015_20260605.csv). Report files are write-once immutable. Retention: 7 years (SEC-09). The gmepay-archives bucket stores WAL archives and long-term compliance data. Service: services/reporting-compliance (ReportStorageService). | • Create ReportStorageService.java @Service in services/reporting-compliance with: storeReport(String reportType, YearMonth period, String filename, byte[] content): uploads to gmepay-reports bucket with correct path; String getReportUrl(reportType, period, filename): returns presigned URL with 1h expiry for Ops portal download. • Generate presigned URL via S3Presigner with expiry=Duration.ofHours(1). • Write ReportStorageServiceTest with localstack Testcontainers: upload a report, assert presigned URL is valid (HTTP 200 GET), assert path matches /gmepay/reports/BOK_FX1015/2026/06/bok_fx1015_20260605.csv. • Assert storeReport is idempotent (second upload of same key succeeds without error; versioning preserves both). • Assert report bytes retrieved via presigned URL are identical to uploaded bytes. | services/reporting-compliance/src/main/java/com/gme/pay/reporting/storage/ReportStorageService.java; ReportStorageServiceTest.java | • storeReport uploads to gmepay-reports bucket at path /gmepay/reports/{reportType}/{YYYY}/{MM}/{filename}. • Presigned URL expires after 1h (verified by expiry timestamp in URL query params). • Second upload to same key succeeds (versioning enabled; no exception). • Testcontainers localstack test passes in CI. | 40 | 3.7-T23 | DBA | OPS-13
3.7-T25 | shared-libs | 3.7 | 3. Data Layer & Persistence | Migration framework & seed data | 1 | Object Storage bucket initialization: ensure-buckets startup bean with versioning and lifecycle | On application startup (services/settlement and services/reporting-compliance), the system must ensure that the three S3 buckets (gmepay-batch-files, gmepay-reports, gmepay-archives) exist and have versioning enabled. If the bucket does not exist, create it. If it exists but versioning is disabled, enable it. Lifecycle rule: gmepay-batch-files objects transition to GLACIER after 90 days and expire after 7 years (2555 days). Bucket location: ap-northeast-2 (Korea data residency per OPS-13 sec 10.4) when AWS_REGION=ap-northeast-2; for MinIO (S3_ENDPOINT_URL set) skip location constraint. | • Create BucketInitializer.java @Component in lib-persistence implementing ApplicationRunner with run() method. • For each bucket name in ObjectStorageBuckets: call S3Client.headBucket(); if NoSuchBucketException create it; call PutBucketVersioning with Status=ENABLED. • Add PutBucketLifecycleConfiguration for gmepay-batch-files: transition to GLACIER after 90 days, expiration after 2555 days. • Skip lifecycle configuration when S3_ENDPOINT_URL is set (MinIO does not support lifecycle fully). • Write BucketInitializerTest with localstack Testcontainers: assert all three buckets exist after run(); assert versioning=ENABLED on each; run again (idempotent) — no error. | lib-persistence/src/main/java/com/gme/pay/persistence/storage/BucketInitializer.java; BucketInitializerTest.java | • After startup all three buckets exist (headBucket() returns 200). • getBucketVersioning() returns Status=ENABLED for all three buckets. • Running BucketInitializer twice raises no error (idempotent: createBucket returns existing gracefully). • Lifecycle rule on gmepay-batch-files has transition to GLACIER at day 90 and expiration at day 2555 (verified via GetBucketLifecycleConfiguration). | 45 | 3.7-T24 | DBA | OPS-13
3.7-T26 | shared-libs | 3.7 | 3. Data Layer & Persistence | Migration framework & seed data | 1 | MongoDB Testcontainers integration test: merchant read-model and QR lookup end-to-end | A combined Testcontainers integration test validates MongoDB document persistence, index behavior, and query correctness for MerchantReadModel, QrReadModel, TransactionSummaryProjection, and PartnerBalanceSnapshot. Uses MongoDBContainer from testcontainers:mongodb. Test class: MongoReadModelIntegrationTest in services/merchant-qr/src/test/java/. Covers the CQRS read-model update flow: simulate a merchant sync event updating MerchantReadModel and QrReadModel, then assert lookup results match. | • Write MongoReadModelIntegrationTest with @Testcontainers and MongoDBContainer. • Test 1: save MerchantReadModel with 2 active QrCodeEmbed; findByMerchantIdAndIsActiveTrue returns the document; update isActive=false; assert not returned. • Test 2: save QrReadModel for active QR; findByQrCodeValueAndIsActiveTrue returns it; save deactivated QR with same merchantId; assert deactivated QR not returned. • Test 3: save 3 TransactionSummaryProjection with same partnerId, different status and committedAt; assert findByPartnerIdAndStatusOrderByCommittedAtDesc returns correct subset in correct order. • Test 4: save PartnerBalanceSnapshot for SENDMN with balance=9000; assert findByBalanceUsdLessThanEqualAndPartnerType('OVERSEAS',10000) returns it. | services/merchant-qr/src/test/java/com/gme/pay/merchantqr/MongoReadModelIntegrationTest.java | • All four test scenarios pass with MongoDBContainer (no local Mongo required). • Deactivated merchant (isActive=false) not returned by findByMerchantIdAndIsActiveTrue. • TransactionSummaryProjection query returns results in descending committedAt order. • PartnerBalanceSnapshot balance=9000 is returned by less-than-threshold query at threshold=10000; balance=10001 is not returned. • Test runs in under 45 seconds in CI. | 45 | 3.7-T16 | DBA | OPS-13
3.7-T27 | shared-libs | 3.7 | 3. Data Layer & Persistence | Migration framework & seed data | 1 | docker-compose local dev infra: add MongoDB and Redis services | The GMEPay+ docker-compose.yml (at repo root or infra/docker-compose.yml) provides local dev infrastructure per the STACK.md locked stack. It must include: MongoDB 7 on port 27017 with volume gmepay_mongo_data, Redis 7 on port 6379 with volume gmepay_redis_data (and appendonly yes for persistence), MinIO (latest) on port 9000 (API) and 9001 (console) with env MINIO_ROOT_USER and MINIO_ROOT_PASSWORD and volumes gmepay_minio_data. PostgreSQL 16 on port 5433 is assumed already present. All services on network gmepay-dev. | • Open infra/docker-compose.yml (or create if absent); add mongodb service: image mongo:7, ports 27017:27017, volumes gmepay_mongo_data:/data/db, network gmepay-dev. • Add redis service: image redis:7-alpine, command redis-server --appendonly yes, ports 6379:6379, volumes gmepay_redis_data:/data, network gmepay-dev. • Add minio service: image minio/minio:latest, command server /data --console-address :9001, env MINIO_ROOT_USER=minioadmin MINIO_ROOT_PASSWORD=minioadmin, ports 9000:9000 and 9001:9001, volumes gmepay_minio_data:/data, network gmepay-dev. • Add named volumes gmepay_mongo_data, gmepay_redis_data, gmepay_minio_data to the volumes section. • Run docker-compose up -d and verify all services are healthy; run docker-compose ps and confirm each is Up. | infra/docker-compose.yml with MongoDB 7, Redis 7, and MinIO services added | • docker-compose up -d starts all services without error. • mongosh --host localhost:27017 --eval 'db.runCommand({ping:1})' returns ok:1. • redis-cli -h localhost -p 6379 PING returns PONG. • curl http://localhost:9000/minio/health/live returns HTTP 200. • docker-compose down removes containers; docker-compose up recreates them with data preserved in named volumes. | 30 | 3.7-T01 | DBA | OPS-13
3.7-T28 | shared-libs | 3.7 | 3. Data Layer & Persistence | Migration framework & seed data | 1 | CI integration: add MongoDB and Redis Testcontainers configuration to CI pipeline | The CI pipeline (OPS-13 pipeline stages) runs integration tests with Testcontainers. However, the CI environment must be configured to allow Testcontainers to pull images for mongodb:7 and redis:7-alpine (and localstack/localstack for S3 tests). The Gradle build must distinguish unit tests (no containers) from integration tests (with containers) using a custom test source set or JUnit 5 tag @Tag('integration'). Integration tests run in a dedicated Gradle task integrationTest that is gated after unit tests. Affected modules: lib-persistence, services/merchant-qr, services/rate-fx, services/payment-executor, services/settlement. | • In root build.gradle add a Gradle sourceSets configuration for integrationTest or configure JUnit 5 tag filtering: unitTest excludes @Tag('integration'), integrationTest includes only @Tag('integration'). • Annotate all Testcontainers test classes with @Tag('integration'). • In .github/workflows/ci.yml (or equivalent) add a step run: ./gradlew integrationTest after the unitTest step; set TESTCONTAINERS_RYUK_DISABLED=true and DOCKER_HOST env vars for the CI Docker socket. • Add Testcontainers reuse configuration (testcontainers.reuse.enable=true in .testcontainers.properties) to speed up CI. • Verify CI run: unit tests pass without Docker; integration tests pass with containers; deliberately break one migration (typo in SQL) and assert integrationTest step fails. | .github/workflows/ci.yml updated with integrationTest step; Gradle integrationTest task configured in root build.gradle; @Tag('integration') on all Testcontainers test classes | • ./gradlew test (unit tests) passes without Docker daemon running. • ./gradlew integrationTest passes when Docker is available and pulls mongodb:7, redis:7-alpine, localstack images. • A deliberate SQL syntax error in V003 migration causes integrationTest to fail with meaningful error message. • CI pipeline step integrationTest appears after unitTest and before the artifact build step. | 45 | 3.7-T21, 3.7-T26, 3.7-T25 | DBA | OPS-13
4.1-T01 | rate-fx | 4.1 | 4. Rate Engine & FX | Treasury rate sourcing model | 1 | Define RateSource enum with four source modes | The rate engine resolves each leg's cost rate from one of four source modes: IDENTITY (settle ccy = USD, hardcoded 1.0), LIVE (fetch from treasury table at quote time), MANUAL (operator override stored per rule), PARTNER (per-transaction quote from partner B API). These modes appear on rule config fields rate_coll_source and rate_pay_source. Both DB columns use CHECK IN ('IDENTITY','LIVE','MANUAL','PARTNER'). | • Create enum RateSource { IDENTITY, LIVE, MANUAL, PARTNER } in package com.gmepayplus.rateengine.model • Add Javadoc on each constant describing exactly when it applies (IDENTITY: leg ccy is USD; LIVE: default for non-identity cross-border; MANUAL: operator override; PARTNER: scheme-level Partner B quote) • Ensure the enum is serialisable to/from its uppercase string name (Jackson @JsonValue / @JsonCreator or equivalent) • Add a helper isIdentity() convenience method returning true when value == IDENTITY | RateSource.java enum in com.gmepayplus.rateengine.model | • RateSource.values() returns exactly four constants: IDENTITY, LIVE, MANUAL, PARTNER • RateSource.valueOf('MANUAL') == RateSource.MANUAL and RateSource.IDENTITY.isIdentity() == true • RateSource.LIVE.isIdentity() == false • JSON serialisation round-trip: MANUAL serialises to string 'MANUAL' and deserialises back to RateSource.MANUAL | 20 |  | BE | RATE-04
4.1-T02 | rate-fx | 4.1 | 4. Rate Engine & FX | Treasury rate sourcing model | 1 | Define RateResolutionContext value object | The resolver needs to know: which leg (COLL or PAY), the settlement currency for that leg (settle_a_ccy for COLL, settle_b_ccy for PAY), the configured source mode from the Rule, and any MANUAL override value stored on the rule (treasury_override_coll / treasury_override_pay). This context is built by the caller before dispatching to a resolver. All monetary/rate values use BigDecimal (never double/float). Currency codes are ISO 4217 strings. | • Create immutable value object RateResolutionContext with fields: Leg leg (enum COLL/PAY), String settleCcy (ISO 4217), RateSource configuredSource, BigDecimal manualOverrideValue (nullable), String schemeId (for PARTNER lookup) • Add a static factory method forCollLeg(String settleCcy, RateSource src, BigDecimal override) and forPayLeg(...) mirroring the two rate slots • Add validation in constructor: settleCcy not blank, configuredSource not null; if configuredSource == MANUAL then manualOverrideValue must be non-null and > 0 | RateResolutionContext.java value object in com.gmepayplus.rateengine.model | • forCollLeg('USD', IDENTITY, null) builds successfully with settleCcy='USD' and configuredSource=IDENTITY • forPayLeg('KRW', MANUAL, null) throws IllegalArgumentException because MANUAL requires a non-null, positive override value • forPayLeg('KRW', MANUAL, BigDecimal.ZERO) throws IllegalArgumentException (zero not allowed) • forCollLeg('USD', LIVE, null) builds successfully; manualOverrideValue is null | 25 | 4.1-T01 | BE | RATE-04
4.1-T03 | rate-fx | 4.1 | 4. Rate Engine & FX | Treasury rate sourcing model | 1 | Define CostRateResult value object | Each resolver returns a result carrying: the resolved BigDecimal rate value, the effective RateSource that was used (same as configured except PARTNER may note the actual source), and an optional quoteReference string for PARTNER-source audit. Rate precision is 8 decimal places per RATE-04 §10.2. All values are immutable. | • Create immutable CostRateResult with fields: BigDecimal rate (8 dp), RateSource resolvedSource, String quoteReference (nullable) • Add static factory methods: ofIdentity() returning rate=1.0 source=IDENTITY; ofLive(BigDecimal rate); ofManual(BigDecimal rate); ofPartner(BigDecimal rate, String quoteRef) • Enforce in constructor: rate > 0, rate scale <= 8; throw RateResolutionException('RATE_UNAVAILABLE') if rate is null or <= 0 | CostRateResult.java value object in com.gmepayplus.rateengine.model | • CostRateResult.ofIdentity().rate.compareTo(BigDecimal.ONE) == 0 and resolvedSource == IDENTITY • CostRateResult.ofManual(new BigDecimal('1380.00')).rate scale is <= 8 • CostRateResult.ofLive(BigDecimal.ZERO) throws RateResolutionException with code RATE_UNAVAILABLE • CostRateResult.ofPartner(new BigDecimal('1380.5'), 'Q-REF-001').quoteReference == 'Q-REF-001' | 25 | 4.1-T01 | BE | RATE-04
4.1-T04 | rate-fx | 4.1 | 4. Rate Engine & FX | Treasury rate sourcing model | 1 | Define CostRateResolver interface and RateResolutionException | The rate sourcing service dispatches to per-source resolver implementations. The interface accepts a RateResolutionContext and returns CostRateResult. Errors are typed: RATE_UNAVAILABLE (LIVE/MANUAL source, rate not found or <= 0), PARTNER_B_QUOTE_UNAVAILABLE (PARTNER source, API unreachable), PARTNER_B_QUOTE_DEVIATION (PARTNER source, commit-time deviation > tolerance). The interface is used by the RateSourceResolver orchestrator (4.1-T09). | • Create interface CostRateResolver with single method: CostRateResult resolve(RateResolutionContext ctx) throws RateResolutionException • Create RateResolutionException(String errorCode, String message) extending RuntimeException; errorCode must be one of RATE_UNAVAILABLE, PARTNER_B_QUOTE_UNAVAILABLE, PARTNER_B_QUOTE_DEVIATION • Add convenience static factories on the exception: RateResolutionException.rateUnavailable(String detail), partnerQuoteUnavailable(), partnerQuoteDeviation(BigDecimal quoteTime, BigDecimal commitTime, BigDecimal tolerance) • Add annotation @FunctionalInterface to the resolver interface | CostRateResolver.java interface and RateResolutionException.java in com.gmepayplus.rateengine.resolver | • Interface has exactly one abstract method resolve(RateResolutionContext) matching the signature • RateResolutionException.rateUnavailable('no row').getErrorCode() == 'RATE_UNAVAILABLE' • RateResolutionException.partnerQuoteDeviation(bd('1380'), bd('1395'), bd('0.01')).getErrorCode() == 'PARTNER_B_QUOTE_DEVIATION' • Attempting to create RateResolutionException with errorCode 'BOGUS_CODE' throws IllegalArgumentException (validate in constructor) | 25 | 4.1-T02, 4.1-T03 | BE | RATE-04
4.1-T05 | rate-fx | 4.1 | 4. Rate Engine & FX | Treasury rate sourcing model | 1 | Implement IdentityRateResolver — USD leg short-circuit to 1.0 | RATE-04 §3.2: when settle_a_ccy = 'USD' the collection leg resolves as IDENTITY with cost_rate_coll = 1.0 (no treasury lookup); same for settle_b_ccy = 'USD' on the pay leg. The IDENTITY resolver must: assert the configured source is IDENTITY, assert settleCcy is 'USD', and return CostRateResult.ofIdentity(). It must never perform a DB or HTTP call. Any non-USD call with source=IDENTITY is a programming error and should throw an IllegalStateException. | • Create IdentityRateResolver implements CostRateResolver • In resolve(): if ctx.configuredSource != IDENTITY throw IllegalStateException; if !ctx.settleCcy.equals('USD') throw IllegalStateException with message 'IDENTITY source requires USD currency, got: {ccy}' • Return CostRateResult.ofIdentity() • Annotate as @Component('identityRateResolver') for Spring wiring | IdentityRateResolver.java in com.gmepayplus.rateengine.resolver.impl | • resolve(forCollLeg('USD', IDENTITY, null)) returns CostRateResult with rate == 1.0 and resolvedSource == IDENTITY • resolve(forPayLeg('USD', IDENTITY, null)) returns rate == 1.0 • resolve(forCollLeg('KRW', IDENTITY, null)) throws IllegalStateException (KRW is not USD) • resolve(forCollLeg('USD', LIVE, null)) throws IllegalStateException (wrong source) • No DB or HTTP calls are made (verify with mock injection — no repositories wired) | 30 | 4.1-T04 | BE | RATE-04
4.1-T06 | rate-fx | 4.1 | 4. Rate Engine & FX | Treasury rate sourcing model | 1 | Implement LiveRateResolver — fetch effective rate from treasury table | RATE-04 §3.2: LIVE source fetches treasury.usd_{ccy} at quote-issuance time. The treasury_rate table stores effective_date, currency_code, rate (NUMERIC), and source='LIVE'¦'MANUAL'. For LIVE resolution use the row where currency_code = settleCcy AND source = 'LIVE' with the most recent effective_date <= now(). If no such row exists, throw RateResolutionException.rateUnavailable(). Per RATE-04 Assumption A3: Phase 1 uses MANUAL-entered rates; LIVE source is modelled now. Rate must be > 0 else RATE_UNAVAILABLE. | • Create LiveRateResolver implements CostRateResolver, injecting TreasuryRateRepository • In resolve(): assert ctx.configuredSource == LIVE; query repository for most-recent row: currency_code = ctx.settleCcy, source = 'LIVE', effective_date <= LocalDate.now(), order by effective_date DESC, limit 1 • If no row found, throw RateResolutionException.rateUnavailable('No LIVE rate for ' + settleCcy) • If row.rate <= 0, throw RateResolutionException.rateUnavailable('Non-positive LIVE rate for ' + settleCcy) • Return CostRateResult.ofLive(row.rate) | LiveRateResolver.java in com.gmepayplus.rateengine.resolver.impl | • Given treasury row {ccy='KRW', source='LIVE', rate=1380.00, effective_date=today}, resolve returns CostRateResult.ofLive(1380.00) • Given no matching row, resolve throws RateResolutionException with errorCode RATE_UNAVAILABLE • Given row with future effective_date (tomorrow), resolve throws RATE_UNAVAILABLE (date filter excludes future rows) • Given row with rate=0.00, resolve throws RATE_UNAVAILABLE • resolve with source=MANUAL throws IllegalStateException (wrong resolver called) | 40 | 4.1-T04 | BE | RATE-04
4.1-T07 | rate-fx | 4.1 | 4. Rate Engine & FX | Treasury rate sourcing model | 1 | Implement ManualRateResolver — return operator override value | RATE-04 §3.2: MANUAL source uses the operator-entered rate stored on the Rule record (treasury_override_coll for COLL leg, treasury_override_pay for PAY leg). This value is passed into RateResolutionContext.manualOverrideValue at the time the resolver is invoked. The resolver does NOT query the treasury table. RATE-04 §11.3: MANUAL rate must be > 0; 0 is not allowed. If manualOverrideValue is null or <= 0, throw RATE_UNAVAILABLE. MANUAL overrides LIVE — meaning the Rule config sets source=MANUAL instead of LIVE; no fallback occurs. | • Create ManualRateResolver implements CostRateResolver • In resolve(): assert ctx.configuredSource == MANUAL • If ctx.manualOverrideValue is null, throw RateResolutionException.rateUnavailable('MANUAL override not set for rule') • If ctx.manualOverrideValue.compareTo(BigDecimal.ZERO) <= 0, throw RateResolutionException.rateUnavailable('MANUAL override must be positive') • Return CostRateResult.ofManual(ctx.manualOverrideValue) • Annotate as @Component('manualRateResolver') | ManualRateResolver.java in com.gmepayplus.rateengine.resolver.impl | • resolve with manualOverrideValue=1380.00 returns CostRateResult with rate=1380.00 and resolvedSource=MANUAL • resolve with manualOverrideValue=null throws RATE_UNAVAILABLE • resolve with manualOverrideValue=0 throws RATE_UNAVAILABLE • resolve with manualOverrideValue=-5 throws RATE_UNAVAILABLE • No repository or HTTP call is made during resolution (pure in-memory) | 25 | 4.1-T04 | BE | RATE-04
4.1-T08 | rate-fx | 4.1 | 4. Rate Engine & FX | Treasury rate sourcing model | 1 | Implement PartnerBQuoteResolver — fetch per-transaction quote from Partner B API | RATE-04 §7.3: PARTNER source calls partner B's quote API at both /rates time and POST /payments commit time. The resolver calls PartnerBQuoteClient.fetchQuote(schemeId, transactionContext) which returns a PartnerBQuote{rate: BigDecimal, quoteReference: String, validUntil: Instant}. If the client throws or returns null, throw RateResolutionException.partnerQuoteUnavailable() (no fallback to treasury). The commit-time deviation check (¦commit - rates¦ / rates > tolerance => PARTNER_B_QUOTE_DEVIATION) is the responsibility of the RateSourceResolver orchestrator (4.1-T09), not this resolver. This resolver only fetches and validates the raw quote. | • Create PartnerBQuoteResolver implements CostRateResolver, injecting PartnerBQuoteClient • In resolve(): assert ctx.configuredSource == PARTNER • Call partnerBQuoteClient.fetchQuote(ctx.schemeId) wrapped in try-catch; on any exception throw RateResolutionException.partnerQuoteUnavailable() • If returned quote is null or quote.rate <= 0, throw RateResolutionException.partnerQuoteUnavailable() • Return CostRateResult.ofPartner(quote.rate, quote.quoteReference) • Annotate as @Component('partnerBQuoteResolver') | PartnerBQuoteResolver.java in com.gmepayplus.rateengine.resolver.impl | • When PartnerBQuoteClient returns rate=1395.00 and ref='Q-001', resolve returns CostRateResult with rate=1395.00, resolvedSource=PARTNER, quoteReference='Q-001' • When PartnerBQuoteClient throws IOException, resolve throws RateResolutionException with code PARTNER_B_QUOTE_UNAVAILABLE • When PartnerBQuoteClient returns null, resolve throws PARTNER_B_QUOTE_UNAVAILABLE • resolve with configuredSource=LIVE throws IllegalStateException • No treasury table query occurs (verify no TreasuryRateRepository injection) | 35 | 4.1-T04 | BE | RATE-04
4.1-T09 | rate-fx | 4.1 | 4. Rate Engine & FX | Treasury rate sourcing model | 1 | Implement RateSourceResolver — orchestrate per-source dispatch for both legs | The RateSourceResolver is the main service wiring the four resolvers to a Rule's configured source modes. It builds a RateResolutionContext for each leg from the Rule (settle_a_ccy, settle_b_ccy, rate_coll_source, rate_pay_source, treasury_override_coll, treasury_override_pay, schemeId) and dispatches to the matching resolver. It returns a RatePair{CostRateResult collResult, CostRateResult payResult}. It also performs the PARTNER commit-time deviation check for the pay leg if pay source = PARTNER: deviation = ¦commitRate - quotedRate¦ / quotedRate; if > tolerance (default 1.0%, per-partner configurable) throw PARTNER_B_QUOTE_DEVIATION. Both legs are resolved independently. | • Create RateSourceResolver @Service injecting Map<RateSource, CostRateResolver> (Spring will auto-populate by qualifier) • Add method RatePair resolveRates(Rule rule, String transactionContext) that builds contexts and calls the correct resolver for each leg • Add method CostRateResult resolveForCommit(Rule rule, CostRateResult quotedPayResult) for commit-time PARTNER deviation check: re-resolves pay leg, computes deviation = ¦new - quoted¦ / quoted, if > tolerance throw PARTNER_B_QUOTE_DEVIATION • Expose tolerance as @Value('${rate.partnerB.deviation.tolerance:0.01}') BigDecimal defaultTolerance • Wire in the four resolver beans by name: identityRateResolver, liveRateResolver, manualRateResolver, partnerBQuoteResolver | RateSourceResolver.java @Service in com.gmepayplus.rateengine.resolver | • Rule with settle_a_ccy='USD', rate_coll_source=IDENTITY dispatches to IdentityRateResolver and collResult.rate == 1.0 • Rule with settle_b_ccy='KRW', rate_pay_source=LIVE dispatches to LiveRateResolver • Rule with rate_pay_source=MANUAL and treasury_override_pay=1380 dispatches to ManualRateResolver and returns 1380 • resolveForCommit with quotedRate=1380 and commitRate=1394.8 (deviation=1.07% > 1%) throws PARTNER_B_QUOTE_DEVIATION • resolveForCommit with quotedRate=1380 and commitRate=1390 (deviation=0.72% < 1%) succeeds and returns new rate | 45 | 4.1-T05, 4.1-T06, 4.1-T07, 4.1-T08 | BE | RATE-04
4.1-T10 | rate-fx | 4.1 | 4. Rate Engine & FX | Treasury rate sourcing model | 1 | Implement TreasuryRateRepository — effective-dated rate lookup | The LiveRateResolver (4.1-T06) requires a TreasuryRateRepository that can find the most recent treasury_rate row for a given currency and source with effective_date <= today. The treasury_rates table (DAT-03) has columns: id, currency_code VARCHAR(3), rate NUMERIC(20,8), source VARCHAR(10) CHECK IN ('LIVE','MANUAL'), effective_date DATE, created_at TIMESTAMP. Index on (currency_code, source, effective_date DESC) must exist for performance. Phase 1 only uses source='MANUAL' rows; LIVE rows are stored for Phase 2. | • Create TreasuryRateRepository extending JpaRepository<TreasuryRate, Long> (or use Spring Data JDBC) • Add query method: Optional<TreasuryRate> findLatestEffective(String currencyCode, String source, LocalDate asOf) using @Query with ORDER BY effective_date DESC LIMIT 1 WHERE currency_code=:ccy AND source=:source AND effective_date <= :asOf • Create TreasuryRate @Entity with fields matching the DB schema above (BigDecimal rate with @Column(precision=20,scale=8)) • Add a DB migration (Flyway/Liquibase) creating the treasury_rates table with the composite index on (currency_code, source, effective_date DESC) if not already present in prior migrations | TreasuryRateRepository.java and TreasuryRate.java entity in com.gmepayplus.treasury; DB migration file | • findLatestEffective('KRW','LIVE', today) returns the row with the highest effective_date <= today among all LIVE KRW rows • findLatestEffective('KRW','LIVE', today) when only future-dated rows exist returns Optional.empty() • findLatestEffective('USD','LIVE', today) returns Optional.empty() (USD has no LIVE row; identity is handled before reaching this) • Composite index (currency_code, source, effective_date DESC) exists per EXPLAIN plan (verify in test with H2 or testcontainers) | 45 | 4.1-T04 | BE | RATE-04
4.1-T11 | rate-fx | 4.1 | 4. Rate Engine & FX | Treasury rate sourcing model | 1 | Unit tests — IdentityRateResolver and ManualRateResolver | Verify both pure in-memory resolvers with exact input/output vectors per RATE-04 §3.2. IDENTITY must always return exactly 1.0 for USD and throw for any other currency. MANUAL must return the exact override value stored on the rule and reject zero/null. Tests use JUnit 5 + AssertJ; no Spring context needed (plain unit tests). | • Create IdentityRateResolverTest: test USD/IDENTITY returns 1.0; test KRW/IDENTITY throws IllegalStateException; test USD/LIVE source throws IllegalStateException • Create ManualRateResolverTest: test KRW/MANUAL/1380.00 returns 1380.00 with resolvedSource=MANUAL; test null override throws RATE_UNAVAILABLE; test zero override throws RATE_UNAVAILABLE; test negative override throws RATE_UNAVAILABLE • Assert CostRateResult.rate.compareTo(BigDecimal.ONE) == 0 (not equals(), which checks scale) for identity case • Verify no mocks are needed (resolvers are stateless) | IdentityRateResolverTest.java and ManualRateResolverTest.java in src/test/.../resolver/impl | • All 7 test cases pass with zero failures • IdentityRateResolver test for USD returns rate==1.0 and resolvedSource==IDENTITY • ManualRateResolver test for KRW with override 1380.00 returns rate==1380.00 and resolvedSource==MANUAL • All three error cases (null, zero, negative) each produce RateResolutionException with errorCode RATE_UNAVAILABLE • Tests run in < 100 ms total (no I/O) | 30 | 4.1-T05, 4.1-T07 | BE | RATE-04
4.1-T12 | rate-fx | 4.1 | 4. Rate Engine & FX | Treasury rate sourcing model | 1 | Unit tests — LiveRateResolver with mocked TreasuryRateRepository | Verify the LIVE resolver fetches the correct treasury row. Test vectors: KRW LIVE 1380.00 (today); KRW LIVE with future date only (no row, RATE_UNAVAILABLE); no row at all (RATE_UNAVAILABLE); row with rate=0 (RATE_UNAVAILABLE). Mocks via Mockito. Per RATE-04 §3.2 the rate is fetched at quote-issuance time from treasury.usd_{ccy}. | • Create LiveRateResolverTest using @ExtendWith(MockitoExtension.class) • Mock TreasuryRateRepository; stub findLatestEffective('KRW','LIVE',today) to return Optional of row with rate=1380.00000000 • Test happy path: returns CostRateResult with rate=1380.00000000, resolvedSource=LIVE • Test no row: stub returns Optional.empty(); assert throws RATE_UNAVAILABLE • Test rate=0 row: assert throws RATE_UNAVAILABLE • Test wrong source (ctx.configuredSource=MANUAL): assert throws IllegalStateException | LiveRateResolverTest.java in src/test/.../resolver/impl | • Happy path: rate==1380.00000000 and resolvedSource==LIVE • Empty repository: RateResolutionException errorCode == RATE_UNAVAILABLE • Zero-rate row: RateResolutionException errorCode == RATE_UNAVAILABLE • Wrong-source call: IllegalStateException thrown (not RateResolutionException) • Mockito verifies findLatestEffective called exactly once in each test | 35 | 4.1-T06, 4.1-T10 | BE | RATE-04
4.1-T13 | rate-fx | 4.1 | 4. Rate Engine & FX | Treasury rate sourcing model | 1 | Unit tests — PartnerBQuoteResolver with mocked PartnerBQuoteClient | Verify the PARTNER resolver delegates to the client and handles errors. Test vectors: client returns {rate=1395.00, ref='Q-001'} -> resolves correctly; client throws IOException -> PARTNER_B_QUOTE_UNAVAILABLE; client returns null -> PARTNER_B_QUOTE_UNAVAILABLE; client returns rate<=0 -> PARTNER_B_QUOTE_UNAVAILABLE. Deviation check is NOT in this resolver (tested in 4.1-T14). | • Create PartnerBQuoteResolverTest using @ExtendWith(MockitoExtension.class) • Mock PartnerBQuoteClient • Test happy path: stub fetchQuote to return {rate=1395.00, ref='Q-001'}; assert rate==1395.00 and quoteReference=='Q-001' • Test IOException: stub throws IOException; assert PARTNER_B_QUOTE_UNAVAILABLE • Test null return: stub returns null; assert PARTNER_B_QUOTE_UNAVAILABLE • Test zero-rate quote: stub returns {rate=0.00}; assert PARTNER_B_QUOTE_UNAVAILABLE | PartnerBQuoteResolverTest.java in src/test/.../resolver/impl | • Happy path: resolvedSource==PARTNER, rate==1395.00, quoteReference=='Q-001' • IOException produces RateResolutionException with code PARTNER_B_QUOTE_UNAVAILABLE • Null return produces PARTNER_B_QUOTE_UNAVAILABLE • Zero-rate produces PARTNER_B_QUOTE_UNAVAILABLE • Mockito verifies fetchQuote called exactly once per test | 30 | 4.1-T08 | BE | RATE-04
4.1-T14 | rate-fx | 4.1 | 4. Rate Engine & FX | Treasury rate sourcing model | 1 | Unit tests — RateSourceResolver orchestration and PARTNER deviation check | Verify the orchestrator dispatches to the correct sub-resolver per leg and that the commit-time PARTNER deviation check fires correctly. Deviation formula (RATE-04 §7.3): deviation = ¦commitRate - quotedRate¦ / quotedRate; if deviation > tolerance (default 0.01) throw PARTNER_B_QUOTE_DEVIATION. Test cases: IDENTITY coll + LIVE pay; MANUAL override pay; PARTNER pay within tolerance (0.72% < 1%); PARTNER pay over tolerance (1.07% > 1%). | • Create RateSourceResolverTest using @ExtendWith(MockitoExtension.class); inject mock resolvers • Build a Rule stub with settle_a_ccy='USD', rate_coll_source=IDENTITY, settle_b_ccy='KRW', rate_pay_source=LIVE • Test dispatch: verifyCollResult.rate==1.0 IDENTITY, payResult from mock LiveResolver with 1380 • Build Rule with rate_pay_source=MANUAL, treasury_override_pay=1380; test payResult==1380 resolvedSource==MANUAL • Test deviation check: quotedRate=1380, commitRate=1394.8, tolerance=0.01 => ¦14.8¦/1380=0.01072 > 0.01 => PARTNER_B_QUOTE_DEVIATION • Test no deviation: quotedRate=1380, commitRate=1390, tolerance=0.01 => 10/1380=0.00724 < 0.01 => success | RateSourceResolverTest.java in src/test/.../resolver | • IDENTITY coll + LIVE pay dispatch verified with correct mocks called • MANUAL pay returns treasury_override_pay value with resolvedSource=MANUAL • commitRate=1394.8 on quotedRate=1380 with tolerance=1% throws PARTNER_B_QUOTE_DEVIATION • commitRate=1390 on quotedRate=1380 with tolerance=1% does not throw • Both legs resolve independently (mock for each leg called exactly once) | 45 | 4.1-T09, 4.1-T11, 4.1-T12, 4.1-T13 | BE | RATE-04
4.1-T15 | rate-fx | 4.1 | 4. Rate Engine & FX | Treasury rate sourcing model | 1 | Integration test — dual-IDENTITY legs (HUB direction, settle_a=USD, settle_b=USD) | RATE-04 §7.1: both legs may simultaneously be IDENTITY when both settle_a_ccy and settle_b_ccy are USD (HUB direction). In this case cost_rate_coll = 1.0 and cost_rate_pay = 1.0. The rule still applies margins m_a and m_b. Test with: target_payout=100.00 USD, cost_rate_coll=1.0 (IDENTITY), cost_rate_pay=1.0 (IDENTITY), m_a=0.01, m_b=0.01, service_charge=0.50 USD. Expected (from RATE-04 §7.1): payout_usd_cost=100.00, collection_usd=100/(0.98)=102.0408, send_amount=102.0408, collection_amount=102.5408. | • Create a Spring Boot integration test class RateDualIdentityIntegrationTest using @SpringBootTest with an H2 in-memory DB • Configure a Rule with settle_a_ccy='USD', rate_coll_source=IDENTITY, settle_b_ccy='USD', rate_pay_source=IDENTITY, m_a=0.01, m_b=0.01, service_charge=0.50 • Call RateSourceResolver.resolveRates() and assert both legs return rate=1.0 • Feed the resolved rates into the rate engine and assert the 5 computed fields match the RATE-04 §7.1 example within tolerance | RateDualIdentityIntegrationTest.java in src/test/.../integration | • collResult.rate == 1.0 exactly (BigDecimal compareTo == 0) • payResult.rate == 1.0 exactly • collection_usd within 0.01 of 102.0408 • send_amount within 0.01 of 102.0408 (cost_rate_coll=1.0 so send_amount=collection_usd) • collection_amount within 0.01 of 102.5408 | 40 | 4.1-T09, 4.1-T10 | BE | RATE-04
4.1-T16 | rate-fx | 4.1 | 4. Rate Engine & FX | Treasury rate sourcing model | 1 | Integration test — IDENTITY coll leg + LIVE pay leg (SendMN cross-border vector) | RATE-04 §4.3 worked example: settle_a_ccy=USD (IDENTITY, cost_rate_coll=1.0), settle_b_ccy=KRW (LIVE, cost_rate_pay=1380.00). target_payout=50000 KRW, m_a=0.01, m_b=0.01, service_charge=0.36 USD. Expected outputs: payout_usd_cost=36.2319 USD, collection_usd=36.9714 USD, send_amount=36.9714 USD, collection_amount=37.3314 USD, pool identity holds within 0.01 USD. Pre-load treasury_rates row: currency_code='KRW', source='LIVE', rate=1380.00000000, effective_date=today. | • Insert treasury_rate row {ccy='KRW',source='LIVE',rate=1380.00000000,effective_date=today} into H2 test DB • Build Rule with settle_a_ccy='USD'/IDENTITY and settle_b_ccy='KRW'/LIVE • Call RateSourceResolver.resolveRates(); assert collResult.rate==1.0 (IDENTITY) and payResult.rate==1380.00 (LIVE) • Feed into rate engine; assert payout_usd_cost within 0.01 of 36.2319, collection_usd within 0.01 of 36.9714, collection_amount within 0.01 of 37.3314 • Assert pool identity: ¦collection_usd - collection_margin_usd - payout_margin_usd - payout_usd_cost¦ < 0.01 | RateLiveCrossIntegrationTest.java in src/test/.../integration | • collResult.rate == 1.0 (IDENTITY source, no DB hit needed for coll leg) • payResult.rate == 1380.00 (LIVE, from treasury_rates table) • payout_usd_cost within 0.01 of 36.2319 • collection_usd within 0.01 of 36.9714 • Pool identity assertion passes (deviation < 0.01 USD) | 40 | 4.1-T09, 4.1-T10 | BE | RATE-04
4.1-T17 | rate-fx | 4.1 | 4. Rate Engine & FX | Treasury rate sourcing model | 1 | Integration test — MANUAL override on pay leg overrides LIVE source | RATE-04 §3.2: MANUAL source means the operator has overridden LIVE for a contract-locked partner. The rule stores treasury_override_pay on the rule record. Even if a LIVE treasury row exists, the ManualRateResolver uses the override value, not the table. Test: treasury has KRW LIVE=1380.00; rule is configured source=MANUAL with treasury_override_pay=1350.00. Expected: payResult.rate=1350.00 (MANUAL wins), not 1380.00 (LIVE ignored). | • Insert treasury_rate row KRW/LIVE/1380.00/today into H2 test DB • Build Rule with rate_pay_source=MANUAL, treasury_override_pay=1350.00 • Call RateSourceResolver.resolveRates(); capture payResult • Assert payResult.rate == 1350.00 and payResult.resolvedSource == MANUAL • Assert LiveRateResolver was NOT invoked for this leg (verify via Spring ApplicationContext or Mockito spy) | RateManualOverrideIntegrationTest.java in src/test/.../integration | • payResult.rate == 1350.00 (not 1380.00 from LIVE table) • payResult.resolvedSource == MANUAL • LiveRateResolver.resolve() is NOT called for the pay leg • Changing treasury_override_pay to 1400.00 returns 1400.00 (override is the authoritative value) • Setting treasury_override_pay to null and source=MANUAL throws RATE_UNAVAILABLE at resolve time | 35 | 4.1-T09, 4.1-T10 | BE | RATE-04
4.1-T18 | rate-fx | 4.1 | 4. Rate Engine & FX | Treasury rate sourcing model | 1 | Integration test — missing rate returns RATE_UNAVAILABLE (no fallback) | RATE-04 §11.4: if cost_rate_coll or cost_rate_pay cannot be resolved for LIVE/MANUAL source, return RATE_UNAVAILABLE. No fallback, no stale rate use. Test cases: (a) LIVE source but no treasury row for currency -> RATE_UNAVAILABLE; (b) MANUAL source but treasury_override_pay is null on rule -> RATE_UNAVAILABLE. The rate engine must not proceed and no transaction record is created. | • Test case A: configure Rule with rate_pay_source=LIVE for currency 'MNT'; ensure no MNT row in treasury_rates; call resolveRates(); assert RateResolutionException with code RATE_UNAVAILABLE • Test case B: configure Rule with rate_pay_source=MANUAL; set treasury_override_pay=null; call resolveRates(); assert RateResolutionException with code RATE_UNAVAILABLE • Test case C: LIVE row exists but rate=0.00 in treasury_rates; assert RATE_UNAVAILABLE • Verify no transaction record is committed to the payment table in any of the three cases | RateMissingRateIntegrationTest.java in src/test/.../integration | • No MNT LIVE row -> RATE_UNAVAILABLE thrown before any rate-engine step executes • MANUAL source with null override -> RATE_UNAVAILABLE • Zero-value LIVE row -> RATE_UNAVAILABLE • No payment record persisted in DB for any of the three failure cases • Error code string == 'RATE_UNAVAILABLE' in all three cases | 35 | 4.1-T09, 4.1-T10 | BE | RATE-04
4.2-T01 | rate-fx | 4.2 | 4. Rate Engine & FX | 5-step RECEIVE-mode calculation engine | 1 | Define RateEngineInput DTO with all required fields and types | The 5-step RECEIVE-mode engine takes these inputs: target_payout (Decimal, payout ccy amount fixed by QR), cost_rate_pay (Decimal, treasury.usd_{settle_b_ccy}, units of Settle B per 1 USD), cost_rate_coll (Decimal, treasury.usd_{settle_a_ccy}, units of Settle A per 1 USD), m_a (Decimal fraction e.g. 0.01 = 1%), m_b (Decimal fraction), service_charge (Decimal flat fee in Settle A ccy; 0 if none), settle_a_ccy (String ISO-4217), settle_b_ccy (String ISO-4217), collect_ccy (String ISO-4217), payout_ccy (String ISO-4217), is_same_ccy_shortcircuit (boolean). All Decimal fields must use java.math.BigDecimal (Java) or Python decimal.Decimal — never float/double. Create in package com.gmepay.rateengine.dto (or equivalent module). | • Create RateEngineInput class/record with all fields listed in context using BigDecimal (or language Decimal) for every monetary and rate field • Annotate or document each field with its source (LIVE/MANUAL/IDENTITY/PARTNER) and unit convention (e.g. cost_rate_pay: units of Settle B per 1 USD) • Add a static factory / builder that sets is_same_ccy_shortcircuit = true when collect_ccy == settle_a_ccy == settle_b_ccy == payout_ccy • Write a unit test asserting the factory sets is_same_ccy_shortcircuit correctly for both the same-ccy case and the cross-border case | RateEngineInput DTO class/record (RateEngineInput.java or equivalent) with all 11 fields, correct Decimal types, and a same-ccy factory helper; passing unit test | • All monetary and rate fields are BigDecimal (or Decimal), not float/double — verified by code review or reflection test • is_same_ccy_shortcircuit is true when collect_ccy=KRW, settle_a_ccy=KRW, settle_b_ccy=KRW, payout_ccy=KRW • is_same_ccy_shortcircuit is false when settle_a_ccy=USD, payout_ccy=KRW • service_charge defaults to BigDecimal.ZERO (not null) when not supplied • Class is immutable (all fields final or record components) | 30 |  | BE | RATE-04
4.2-T02 | rate-fx | 4.2 | 4. Rate Engine & FX | 5-step RECEIVE-mode calculation engine | 1 | Define RateEngineResult DTO with all output fields and types | The engine returns these fields: payout_usd_cost (Decimal, Step 1; NULL for same-ccy), collection_usd (Decimal, Step 2; NULL for same-ccy), collection_margin_usd (Decimal, Step 3a; 0 for same-ccy), payout_margin_usd (Decimal, Step 3b; 0 for same-ccy), send_amount (Decimal, Step 4, in settle_a_ccy; NULL for same-ccy), send_amount_ccy (String), collection_amount (Decimal, Step 5, in settle_a_ccy), collection_amount_ccy (String), service_charge (Decimal, echoed from input), service_charge_ccy (String), cost_rate_coll (Decimal echoed), cost_rate_pay (Decimal echoed), offer_rate_coll (Decimal derived; NULL for same-ccy), cross_rate (Decimal derived; NULL for same-ccy). Precision rules: Steps 1-4 intermediates stored to DECIMAL(20,8); collection_amount rounded to currency-native scale (KRW = 0 dp, USD = 4 dp). Create in same package as 4.2-T01. | • Create RateEngineResult class/record with all 14 fields using BigDecimal for all monetary and rate fields • Document precision expectation per field in Javadoc/docstring (DECIMAL(20,8) for intermediates; currency-scale for collection_amount) • Mark payout_usd_cost, collection_usd, send_amount, offer_rate_coll, cross_rate as @Nullable (or Optional) since they are NULL for same-ccy • Write a unit test that constructs a sample result and asserts no float fields exist | RateEngineResult DTO class/record (RateEngineResult.java or equivalent) with all 14 fields, correct Decimal/nullable types, and passing structural test | • payout_usd_cost, collection_usd, send_amount, offer_rate_coll, cross_rate are nullable/Optional; collection_margin_usd and payout_margin_usd are non-null (default ZERO) • No field uses float, double, Float, or Double type • collection_amount_ccy and send_amount_ccy are separate String fields, not inferred • Result is immutable (final fields or record) • Javadoc/docstring states DECIMAL(20,8) precision for intermediate fields | 25 | 4.2-T01 | BE | RATE-04
4.2-T03 | rate-fx | 4.2 | 4. Rate Engine & FX | 5-step RECEIVE-mode calculation engine | 1 | Implement Step 1 pure function: payout_usd_cost = target_payout / cost_rate_pay | Step 1 of the 5-step RECEIVE-mode engine: payout_usd_cost = target_payout / cost_rate_pay. target_payout is fixed by the merchant QR (e.g. 50000 KRW). cost_rate_pay = treasury.usd_{settle_b_ccy} (e.g. 1380.00 for KRW). Division must use BigDecimal with MathContext of at least 10 significant figures (use DECIMAL128 or equivalent). The result is an intermediate; do NOT round here. Worked example: target_payout=50000, cost_rate_pay=1380.00 => payout_usd_cost = 36.23188405... USD. For IDENTITY leg (Settle B = USD), cost_rate_pay = 1.0 so payout_usd_cost = target_payout exactly. | • Create a package-private pure static function stepOnePayoutUsdCost(BigDecimal targetPayout, BigDecimal costRatePay): BigDecimal • Use BigDecimal.divide with MathContext.DECIMAL128 (34 sig figs) to avoid ArithmeticException on repeating decimals • Return result unrounded (precision kept at DECIMAL128 scale) • Write unit test with numeric example: targetPayout=50000, costRatePay=1380.00, expect result approximately 36.2319 (within 0.0001) • Add edge-case test: costRatePay=1.0 (IDENTITY), expect result == targetPayout exactly | Pure static function stepOnePayoutUsdCost in RateEngineSteps class (or equivalent), with 2 passing unit tests | • stepOnePayoutUsdCost(50000, 1380.00) returns value in range [36.2318, 36.2320] • stepOnePayoutUsdCost(100.00, 1.0) returns exactly 100.00 (IDENTITY leg) • Function signature accepts BigDecimal, returns BigDecimal — no float • Division uses MathContext.DECIMAL128 or equivalent, not plain divide() which would throw on repeating decimal • No rounding applied inside this function | 20 | 4.2-T01, 4.2-T02 | BE | RATE-04
4.2-T04 | rate-fx | 4.2 | 4. Rate Engine & FX | 5-step RECEIVE-mode calculation engine | 1 | Implement margin guard: reject when m_a + m_b < 0.02 for cross-border rules | Hard business rule: for cross-border rules (is_same_ccy_shortcircuit = false), m_a + m_b must be >= 0.02 (2%). If m_a + m_b < 0.02 the engine must throw a checked exception RateEngineException with code INVALID_MARGIN_COMBINATION before any computation begins. Same-currency rules (is_same_ccy_shortcircuit = true) may have m_a = m_b = 0. Also guard: m_a >= 0 and m_b >= 0 individually (no negative margins). Additionally guard that (1 - m_a - m_b) > 0, i.e. m_a + m_b < 1.0 (otherwise Step 2 divides by a non-positive number). These guards run before Step 1. | • Create RateEngineException (checked, with String errorCode field) if not already present • Implement validateMargins(RateEngineInput input) static method that applies all three guards • Guard 1: if !is_same_ccy and (m_a + m_b) < 0.02, throw INVALID_MARGIN_COMBINATION • Guard 2: if m_a < 0 or m_b < 0, throw NEGATIVE_MARGIN • Guard 3: if (m_a + m_b) >= 1.0, throw MARGIN_EXCEEDS_UNITY • Write 5 unit tests covering each guard path and a valid pass-through | validateMargins() method in RateEngineSteps (or MarginValidator), RateEngineException class, 5 passing unit tests | • m_a=0.009, m_b=0.009, cross-border => throws INVALID_MARGIN_COMBINATION • m_a=0.01, m_b=0.01, cross-border => no exception (exactly 2%) • m_a=0.0, m_b=0.0, same-ccy => no exception • m_a=-0.01, m_b=0.03 => throws NEGATIVE_MARGIN • m_a=0.60, m_b=0.50 => throws MARGIN_EXCEEDS_UNITY | 25 | 4.2-T01 | BE | RATE-04
4.2-T05 | rate-fx | 4.2 | 4. Rate Engine & FX | 5-step RECEIVE-mode calculation engine | 1 | Implement Step 2 pure function: collection_usd = payout_usd_cost / (1 - m_a - m_b) | Step 2 of the 5-step engine: collection_usd = payout_usd_cost / (1 - m_a - m_b). This is the gross-up to the pre-margin USD pool. Divisor = (1 - m_a - m_b); guaranteed > 0 by 4.2-T04 guard. Use DECIMAL128 precision; do NOT round result. Worked example: payout_usd_cost=36.2319 USD, m_a=0.01, m_b=0.01 => divisor=0.98, collection_usd=36.2319/0.98=36.9713... USD. For IDENTITY legs both sides: payout_usd_cost=100.00, m_a=0.01, m_b=0.01 => collection_usd=100.00/0.98=102.0408... USD. | • Create pure static function stepTwoCollectionUsd(BigDecimal payoutUsdCost, BigDecimal mA, BigDecimal mB): BigDecimal • Compute divisor = ONE.subtract(mA).subtract(mB) using BigDecimal arithmetic • Divide payoutUsdCost by divisor with MathContext.DECIMAL128 • Return unrounded result • Write unit test: payoutUsdCost=36.2319, mA=0.01, mB=0.01, expect result approx 36.9713 (within 0.0001) • Write identity-legs test: payoutUsdCost=100.00, mA=0.01, mB=0.01, expect approx 102.0408 | Pure static function stepTwoCollectionUsd in RateEngineSteps, with 2 passing unit tests | • stepTwoCollectionUsd(36.2319, 0.01, 0.01) returns value in [36.9712, 36.9715] • stepTwoCollectionUsd(100.00, 0.01, 0.01) returns value in [102.0407, 102.0410] • Uses BigDecimal arithmetic only, no float • No rounding inside function • Function does not call validateMargins (guard is caller responsibility) | 20 | 4.2-T03, 4.2-T04 | BE | RATE-04
4.2-T06 | rate-fx | 4.2 | 4. Rate Engine & FX | 5-step RECEIVE-mode calculation engine | 1 | Implement Step 3 pure functions: collection_margin_usd and payout_margin_usd | Step 3a: collection_margin_usd = collection_usd * m_a. Step 3b: payout_margin_usd = collection_usd * m_b. Both are literal USD dollar amounts deducted from the pool -- not rate adjustments. Use DECIMAL128 precision, no rounding. Worked example: collection_usd=36.9714, m_a=0.01, m_b=0.01 => collection_margin_usd=0.3697 USD, payout_margin_usd=0.3697 USD. Second example (identity legs): collection_usd=102.0408, m_a=0.01, m_b=0.01 => collection_margin_usd=1.0204, payout_margin_usd=1.0204. | • Create pure static function stepThreeMargins(BigDecimal collectionUsd, BigDecimal mA, BigDecimal mB): MarginPair (a small value object with collectionMarginUsd and payoutMarginUsd fields) • Compute collectionMarginUsd = collectionUsd.multiply(mA) with DECIMAL128 • Compute payoutMarginUsd = collectionUsd.multiply(mB) with DECIMAL128 • Return MarginPair with both values unrounded • Write unit test for cross-border case: collectionUsd=36.9714, mA=0.01, mB=0.01 => both margins approx 0.3697 • Write unit test for same-ccy case: mA=0, mB=0 => both margins exactly 0 | stepThreeMargins function, MarginPair value object, 2 passing unit tests | • stepThreeMargins(36.9714, 0.01, 0.01) gives collectionMarginUsd in [0.3696, 0.3698] and payoutMarginUsd in [0.3696, 0.3698] • stepThreeMargins(102.0408, 0.01, 0.01) gives both margins in [1.0203, 1.0205] • stepThreeMargins(any, 0, 0) gives exactly ZERO for both margins • Both fields in MarginPair are BigDecimal, not float • MarginPair is immutable | 20 | 4.2-T05 | BE | RATE-04
4.2-T07 | rate-fx | 4.2 | 4. Rate Engine & FX | 5-step RECEIVE-mode calculation engine | 1 | Implement Step 4 pure function: send_amount = collection_usd * cost_rate_coll | Step 4: send_amount = collection_usd * cost_rate_coll. cost_rate_coll = treasury.usd_{settle_a_ccy} (units of Settle A per 1 USD). Result is in Settle A currency. For IDENTITY leg (Settle A = USD), cost_rate_coll = 1.0 so send_amount = collection_usd exactly. Do NOT round at this step; store to DECIMAL(20,8) precision. Worked example: collection_usd=36.9714, cost_rate_coll=1.0 (IDENTITY) => send_amount=36.9714 USD. Non-identity example: collection_usd=36.9714, cost_rate_coll=1380.00 (KRW) => send_amount=51,020.532 KRW. | • Create pure static function stepFourSendAmount(BigDecimal collectionUsd, BigDecimal costRateColl): BigDecimal • Compute collectionUsd.multiply(costRateColl) with MathContext.DECIMAL128 • Return unrounded result • Write unit test for IDENTITY leg: collectionUsd=36.9714, costRateColl=1.0, expect 36.9714 • Write unit test for non-identity: collectionUsd=36.9714, costRateColl=1380.00, expect approx 51020.532 (within 0.01) | Pure static function stepFourSendAmount in RateEngineSteps, with 2 passing unit tests | • stepFourSendAmount(36.9714, 1.0) returns exactly 36.9714 (IDENTITY) • stepFourSendAmount(36.9714, 1380.00) returns value in [51020.52, 51020.55] • stepFourSendAmount(102.0408, 1.0) returns 102.0408 (identity-legs example) • Uses BigDecimal multiply, not float • No rounding inside the function | 20 | 4.2-T06 | BE | RATE-04
4.2-T08 | rate-fx | 4.2 | 4. Rate Engine & FX | 5-step RECEIVE-mode calculation engine | 1 | Implement Step 5 pure function: collection_amount = send_amount + service_charge (with currency-scale rounding) | Step 5: collection_amount = send_amount + service_charge. service_charge is a flat per-transaction fee in Settle A currency; it NEVER enters the USD pool. This is the final partner debit amount. Rounding rule: collection_amount is rounded to the currency-native scale at this step only (KRW = 0 decimal places, USD = 4 decimal places; pass in an int currencyScale). Worked example: send_amount=36.9714 USD, service_charge=0.36 USD, scale=4 => collection_amount=37.3314 USD. KRW example: send_amount=51020.532 KRW, service_charge=500 KRW, scale=0 => collection_amount=51521 KRW (rounded to nearest KRW). Same-ccy example: send_amount not used; formula is target_payout + service_charge (caller handles this path; this function still works: pass send_amount = target_payout). | • Create pure static function stepFiveCollectionAmount(BigDecimal sendAmount, BigDecimal serviceCharge, int currencyScale): BigDecimal • Sum sendAmount.add(serviceCharge) • Apply setScale(currencyScale, RoundingMode.HALF_UP) to the sum • Return rounded result • Write unit test: sendAmount=36.9714, serviceCharge=0.36, scale=4 => 37.3314 • Write unit test: sendAmount=51020.532, serviceCharge=500, scale=0 => 51521 • Write unit test: serviceCharge=0, scale=4 => collection_amount equals sendAmount rounded | Pure static function stepFiveCollectionAmount in RateEngineSteps, with 3 passing unit tests | • stepFiveCollectionAmount(36.9714, 0.36, 4) returns 37.3314 • stepFiveCollectionAmount(51020.532, 500, 0) returns 51521 (zero decimals) • stepFiveCollectionAmount(102.0408, 0.50, 4) returns 102.5408 (identity-legs example) • Rounding uses HALF_UP, not truncation or FLOOR • serviceCharge=0 path: result equals sendAmount rounded to scale | 25 | 4.2-T07 | BE | RATE-04
4.2-T09 | rate-fx | 4.2 | 4. Rate Engine & FX | 5-step RECEIVE-mode calculation engine | 1 | Assemble the 5-step RECEIVE-mode pipeline in RateEngineService.compute() | Wire the five step functions (4.2-T03 through 4.2-T08) and the margin guard (4.2-T04) into a single RateEngineService.compute(RateEngineInput) -> RateEngineResult method. Logic: (1) call validateMargins; (2) if is_same_ccy_shortcircuit, return same-ccy result: collection_amount = target_payout + service_charge (rounded to currency scale), all USD pool fields null/zero, offer_rate_coll = 1.0, cross_rate = 1.0; (3) else execute Steps 1-5 in order; (4) build and return RateEngineResult with all fields populated. The pool identity assertion (collection_usd - collection_margin_usd - payout_margin_usd == payout_usd_cost, tolerance 0.01 USD) is added in 4.2-T10 and called from here. Derived outputs offer_rate_coll and cross_rate are computed in 4.2-T11 and called from here. | • Create RateEngineService class with public RateEngineResult compute(RateEngineInput input) throws RateEngineException • Call validateMargins(input) first; propagate exception on failure • Branch on input.is_same_ccy_shortcircuit: if true, compute same-ccy short-circuit result and return • Otherwise call stepOne -> stepTwo -> stepThree -> stepFour -> stepFive in order • Call poolIdentityCheck (stub from 4.2-T10: leave as TODO comment for now) • Call computeDerivedRates (stub from 4.2-T11: leave as TODO comment for now) • Build RateEngineResult from all computed values and return | RateEngineService.compute() method wiring all steps; same-ccy branch fully functional; cross-border branch functional pending 4.2-T10 and 4.2-T11 stubs | • Same-ccy input (collect_ccy=KRW, payout_ccy=KRW, service_charge=500) returns collection_amount=target_payout+500, all USD pool fields null or zero • Cross-border input reaches stepFiveCollectionAmount and returns non-null collection_amount • Invalid margin input throws RateEngineException before any step executes • Method signature is compute(RateEngineInput) throws RateEngineException; no float in/out • Calling compute twice with same input returns identical result (pure/deterministic) | 40 | 4.2-T03, 4.2-T04, 4.2-T05, 4.2-T06, 4.2-T07, 4.2-T08 | BE | RATE-04
4.2-T10 | rate-fx | 4.2 | 4. Rate Engine & FX | 5-step RECEIVE-mode calculation engine | 1 | Implement pool identity assertion inside the pipeline | After Step 3 is computed, verify: collection_usd - collection_margin_usd - payout_margin_usd == payout_usd_cost within tolerance 0.01 USD. This is an algebraic consequence of the formulas (not a business guard), but any floating-point or implementation error that breaks it must be caught before the result is returned. If the absolute difference > 0.01, throw RateEngineException with code POOL_IDENTITY_BREACH and include the actual deviation in the message. The check runs only for cross-border paths (skip for same-ccy short-circuit). Integration point: call from RateEngineService.compute() after stepThree, before stepFour. From worked example: collection_usd=36.9714, collection_margin_usd=0.3697, payout_margin_usd=0.3697, payout_usd_cost=36.2319 => deviation=0.0001 USD, passes. | • Create static function assertPoolIdentity(BigDecimal collectionUsd, BigDecimal collectionMarginUsd, BigDecimal payoutMarginUsd, BigDecimal payoutUsdCost) throws RateEngineException • Compute residual = collectionUsd - collectionMarginUsd - payoutMarginUsd - payoutUsdCost • If abs(residual) > 0.01, throw RateEngineException(POOL_IDENTITY_BREACH, deviation=residual) • Wire call into RateEngineService.compute() replacing the TODO stub from 4.2-T09 • Write passing test: worked example values => no exception • Write failing test: artificially inject deviation of 0.02 => expects POOL_IDENTITY_BREACH | assertPoolIdentity() function wired into RateEngineService.compute(), 2 passing unit tests | • collection_usd=36.9714, collection_margin_usd=0.3697, payout_margin_usd=0.3697, payout_usd_cost=36.2319 => no exception (deviation 0.0001 < 0.01) • identity-legs case: collection_usd=102.0408, margins=1.0204 each, payout_usd_cost=100.00 => no exception (deviation 0 < 0.01) • Injected residual of 0.02 => throws POOL_IDENTITY_BREACH • Same-ccy path bypasses assertion entirely (no exception for null USD fields) • Exception message includes the actual deviation value for diagnostics | 25 | 4.2-T09 | BE | RATE-04
4.2-T11 | rate-fx | 4.2 | 4. Rate Engine & FX | 5-step RECEIVE-mode calculation engine | 1 | Implement derived rate computations: offer_rate_coll and cross_rate | After the 5 steps, compute two derived (never configured) BOK outputs. offer_rate_coll = send_amount / (collection_usd - collection_margin_usd); maps to BOK FX1015 #14. cross_rate = target_payout / send_amount. Both are NULL for same-ccy short-circuit. Worked example: send_amount=36.9714, collection_usd=36.9714, collection_margin_usd=0.3697 => offer_rate_coll = 36.9714 / 36.6017 = 1.01010. target_payout=50000 KRW, send_amount=36.9714 USD => cross_rate = 50000 / 36.9714 = 1352.24 KRW/USD. Both computed using DECIMAL128; no rounding at this stage. Wire into RateEngineService.compute() replacing the TODO stub from 4.2-T09. | • Create static function computeDerivedRates(BigDecimal sendAmount, BigDecimal collectionUsd, BigDecimal collectionMarginUsd, BigDecimal targetPayout): DerivedRates (small value object with offerRateColl and crossRate BigDecimal fields) • Compute pool_net = collectionUsd.subtract(collectionMarginUsd) • Compute offerRateColl = sendAmount.divide(poolNet, MathContext.DECIMAL128) • Compute crossRate = targetPayout.divide(sendAmount, MathContext.DECIMAL128) • Return DerivedRates with both values • Wire into RateEngineService.compute(); set null for same-ccy path • Write 2 unit tests: cross-border example and identity-legs example from spec | computeDerivedRates() function and DerivedRates value object, wired into RateEngineService.compute(), 2 passing unit tests | • computeDerivedRates(36.9714, 36.9714, 0.3697, 50000) gives offerRateColl in [1.01009, 1.01011] • computeDerivedRates(36.9714, 36.9714, 0.3697, 50000) gives crossRate in [1352.23, 1352.25] • Identity-legs: computeDerivedRates(102.0408, 102.0408, 1.0204, 100.00) gives offerRateColl in [1.01009, 1.01011] and crossRate in [0.9799, 0.9801] • Same-ccy path returns null for both derived fields in RateEngineResult • Uses BigDecimal DECIMAL128 division, not float | 25 | 4.2-T10 | BE | RATE-04
4.2-T12 | rate-fx | 4.2 | 4. Rate Engine & FX | 5-step RECEIVE-mode calculation engine | 1 | Full integration unit test: fully worked cross-border example (SendMN on ZeroPay) | End-to-end test of the assembled RateEngineService.compute() using the canonical worked example from RATE-04 spec section 4.3: target_payout=50000 KRW, cost_rate_pay=1380.00 (treasury.usd_krw), cost_rate_coll=1.0 (IDENTITY: Settle A=USD), m_a=0.01, m_b=0.01, service_charge=0.36 USD (Settle A ccy), settle_a_ccy=USD, settle_b_ccy=KRW, collect_ccy=USD, payout_ccy=KRW, is_same_ccy_shortcircuit=false. Expected outputs per spec: payout_usd_cost=36.2319, collection_usd=36.9714, collection_margin_usd=0.3697, payout_margin_usd=0.3697, send_amount=36.9714 USD, collection_amount=37.3314 USD, offer_rate_coll~1.01010, cross_rate~1352.24. Pool identity deviation < 0.01 USD. This test constitutes the primary acceptance vector for the engine. | • Build RateEngineInput using the exact values from context • Call RateEngineService.compute(input) • Assert each output field against the expected value with tolerances as specified • Assert pool identity deviation ¦collection_usd - collection_margin_usd - payout_margin_usd - payout_usd_cost¦ < 0.0002 • Assert no exception is thrown • Assert collection_amount is rounded to 4 decimal places (USD scale) | Integration unit test class RateEngineIntegrationTest with method testSendMnZeroPayCanonicalExample(), passing | • payout_usd_cost in [36.2318, 36.2320] • collection_usd in [36.9713, 36.9715] • collection_margin_usd in [36.9713*0.01 - 0.0001, 36.9713*0.01 + 0.0001] i.e. approx 0.3697 • send_amount in [36.9713, 36.9715] (IDENTITY leg so equals collection_usd) • collection_amount in [37.3313, 37.3315] • offer_rate_coll in [1.01009, 1.01011] • cross_rate in [1352.23, 1352.25] • pool identity deviation < 0.0002 USD | 35 | 4.2-T11 | BE | RATE-04
4.2-T13 | rate-fx | 4.2 | 4. Rate Engine & FX | 5-step RECEIVE-mode calculation engine | 1 | Full integration unit test: identity-legs (USD-to-USD both legs) example | End-to-end test using the second canonical worked example from RATE-04 spec section 7.1: target_payout=100.00 USD, cost_rate_coll=1.0 (IDENTITY), cost_rate_pay=1.0 (IDENTITY), m_a=0.01, m_b=0.01, service_charge=0.50 USD, settle_a_ccy=USD, settle_b_ccy=USD, collect_ccy=USD, payout_ccy=USD, is_same_ccy_shortcircuit=false. Expected: payout_usd_cost=100.00, collection_usd=102.0408, collection_margin_usd=1.0204, payout_margin_usd=1.0204, send_amount=102.0408, collection_amount=102.5408, offer_rate_coll~1.01010, cross_rate~0.98000. Pool identity: 102.0408 - 1.0204 - 1.0204 = 100.0000 exactly. | • Build RateEngineInput with both identity legs (cost_rate_coll=1.0, cost_rate_pay=1.0, payout_ccy=USD, settle_b_ccy=USD) • Call RateEngineService.compute(input) • Assert all output fields against expected values with tight tolerances • Assert pool identity exactly equals 100.00 (deviation < 0.0001) • Assert is_same_ccy_shortcircuit was false (cross-border path taken, margins applied) • Assert offer_rate_coll and cross_rate are non-null | Integration unit test testIdentityLegsUsdUsd() in RateEngineIntegrationTest, passing | • payout_usd_cost is exactly 100.00 • collection_usd in [102.0407, 102.0410] • collection_margin_usd and payout_margin_usd each in [1.0203, 1.0205] • collection_amount in [102.5407, 102.5410] • cross_rate in [0.9799, 0.9801] • pool identity deviation < 0.0001 | 25 | 4.2-T12 | BE | RATE-04
4.2-T14 | rate-fx | 4.2 | 4. Rate Engine & FX | 5-step RECEIVE-mode calculation engine | 1 | Full integration unit test: same-currency short-circuit (GME Remit on ZeroPay) | End-to-end test using the same-ccy short-circuit case from RATE-04 spec section 7.2: target_payout=15000 KRW, service_charge=500 KRW, collect_ccy=KRW, settle_a_ccy=KRW, settle_b_ccy=KRW, payout_ccy=KRW, m_a=0, m_b=0, is_same_ccy_shortcircuit=true. Expected: collection_amount=15500 KRW (integer, 0 decimals), payout_usd_cost=null, collection_usd=null, collection_margin_usd=0, payout_margin_usd=0, cost_rate_coll=1.0, cost_rate_pay=1.0, offer_rate_coll=1.0, cross_rate=1.0. No USD pool computed. No pool identity check applied. | • Build RateEngineInput with all four ccys = KRW, m_a=0, m_b=0 • Call RateEngineService.compute(input) • Assert collection_amount = 15500, rounded to 0 decimal places (KRW scale) • Assert payout_usd_cost is null • Assert collection_usd is null • Assert collection_margin_usd = 0 and payout_margin_usd = 0 • Assert offer_rate_coll = 1.0 and cross_rate = 1.0 | Integration unit test testSameCcyShortCircuitKrw() in RateEngineIntegrationTest, passing | • collection_amount equals exactly 15500 with scale 0 • payout_usd_cost is null • collection_usd is null • collection_margin_usd is ZERO and payout_margin_usd is ZERO • offer_rate_coll is 1.0 and cross_rate is 1.0 • No POOL_IDENTITY_BREACH exception raised (same-ccy bypasses that check) | 20 | 4.2-T12 | BE | RATE-04
4.2-T15 | rate-fx | 4.2 | 4. Rate Engine & FX | 5-step RECEIVE-mode calculation engine | 1 | Unit tests for margin guard edge cases and boundary values | Targeted tests for the margin validation guard implemented in 4.2-T04. Business rules: cross-border m_a + m_b >= 0.02 (2% floor), m_a >= 0, m_b >= 0, m_a + m_b < 1.0. Same-currency rules may have m_a=m_b=0. Boundary values to cover: exactly 2% (pass), 1.99% (fail), one margin negative, sum >= 1.0 (divisor non-positive), and same-ccy exempt. | • Write test: m_a=0.01, m_b=0.01, cross-border => no exception (exactly 2% floor) • Write test: m_a=0.0099, m_b=0.0100, cross-border => INVALID_MARGIN_COMBINATION • Write test: m_a=0.015, m_b=0.0049, cross-border => INVALID_MARGIN_COMBINATION (1.99%) • Write test: m_a=-0.005, m_b=0.03, cross-border => NEGATIVE_MARGIN • Write test: m_a=0.50, m_b=0.51, cross-border => MARGIN_EXCEEDS_UNITY (sum=1.01) • Write test: m_a=0, m_b=0, is_same_ccy=true => no exception | Test class MarginGuardTest with 6 passing tests covering all guard branches | • m_a=0.01+m_b=0.01 cross-border passes • m_a=0.0099+m_b=0.0100 cross-border throws INVALID_MARGIN_COMBINATION • m_a=-0.005 throws NEGATIVE_MARGIN regardless of sum • m_a+m_b=1.01 throws MARGIN_EXCEEDS_UNITY • same-ccy with m_a=0,m_b=0 passes without exception • All 6 tests pass independently with no shared mutable state | 25 | 4.2-T04 | BE | RATE-04
4.2-T16 | rate-fx | 4.2 | 4. Rate Engine & FX | 5-step RECEIVE-mode calculation engine | 1 | Unit tests for decimal precision: no float contamination and DECIMAL128 scale | These tests guard against accidental float/double usage and verify that intermediate values are held at sufficient precision. Key risk: using double for cost_rate_pay=1380 and target_payout=50000 introduces binary floating-point error that can violate the pool identity. Verify that each step function and the assembled pipeline hold precision >= 8 decimal places on intermediates, and that the pool identity deviation for the canonical example is < 0.0001 USD (well within 0.01 tolerance). Also verify collection_amount is the ONLY field rounded. | • Write test asserting all intermediate BigDecimal fields in RateEngineResult have scale >= 8 for the cross-border case • Write test confirming pool identity deviation for canonical example (target_payout=50000 KRW) is < 0.0001 (not merely < 0.01) • Write test: replace any BigDecimal constant with explicit scale-10 construction and confirm result is unchanged • Write test confirming collection_amount.scale() equals the supplied currencyScale (4 for USD, 0 for KRW) • Write test confirming service_charge=0 path: collection_amount equals send_amount rounded to scale, no extra precision loss | Test class DecimalPrecisionTest with 5 passing tests | • payout_usd_cost.scale() >= 8 for canonical cross-border example • pool identity deviation for canonical example < 0.0001 • collection_usd.scale() >= 8 • collection_amount.scale() == 4 for USD currency • collection_amount.scale() == 0 for KRW currency | 30 | 4.2-T12 | BE | RATE-04
4.3-T01 | rate-fx | 4.3 | 4. Rate Engine & FX | USD pool identity assertion | 1 | Define PoolIdentityError exception and tolerance constant | WBS 4.3 USD pool identity assertion. The spec (RATE-04 §11.2) requires that after Steps 1-3 of the 5-step RECEIVE-mode calculation, the check ¦collection_usd - collection_margin_usd - payout_margin_usd - payout_usd_cost¦ < 0.01 USD must hold; failure is a hard programming error named POOL_IDENTITY_FAILURE. This ticket creates the exception class and the configurable tolerance constant so all other tickets can import them. | • Create module rate_engine/errors.py (or equivalent package path); add PoolIdentityError(RuntimeError) with fields: collection_usd, collection_margin_usd, payout_margin_usd, payout_usd_cost, delta (all Decimal). • Add a settings constant POOL_IDENTITY_TOLERANCE_USD defaulting to Decimal('0.01') loaded from application config; document that it must remain positive. • Add a __str__ that renders all five fields and the word POOL_IDENTITY_FAILURE so log scanners can grep for it. • Write docstring citing RATE-04 §11.2 and stating this is a programming error, not a user error. | rate_engine/errors.py with PoolIdentityError class and POOL_IDENTITY_TOLERANCE_USD constant (default Decimal('0.01')) | • PoolIdentityError is importable from rate_engine.errors. • Instantiating with delta=Decimal('0.015') and four USD field values succeeds and str() includes the word POOL_IDENTITY_FAILURE. • POOL_IDENTITY_TOLERANCE_USD defaults to Decimal('0.01') and is of type Decimal, not float. • Overriding POOL_IDENTITY_TOLERANCE_USD to Decimal('0.005') in test config is reflected when the constant is re-imported. | 20 | 4.2 | BE | RATE-04
4.3-T02 | rate-fx | 4.3 | 4. Rate Engine & FX | USD pool identity assertion | 1 | Implement assert_pool_identity() pure assertion function | WBS 4.3. RATE-04 §11.2 formula: ¦collection_usd - collection_margin_usd - payout_margin_usd - payout_usd_cost¦ < POOL_IDENTITY_TOLERANCE_USD (default 0.01 USD). All four inputs are Decimal. service_charge is NOT part of this check; it enters only at Step 5 (collection_amount = send_amount + service_charge) and must never be passed in. This function is the single source of truth for the assertion, tested in isolation before being wired into the engine. | • In rate_engine/assertions.py create function assert_pool_identity(collection_usd, collection_margin_usd, payout_margin_usd, payout_usd_cost, tolerance=POOL_IDENTITY_TOLERANCE_USD) -> None. • Compute delta = abs(collection_usd - collection_margin_usd - payout_margin_usd - payout_usd_cost). • If delta >= tolerance raise PoolIdentityError(collection_usd, collection_margin_usd, payout_margin_usd, payout_usd_cost, delta). • If delta < tolerance return None silently. • Add a module docstring noting service_charge is intentionally excluded per RATE-04 §5.3. | rate_engine/assertions.py with assert_pool_identity() function | • Passing case: collection_usd=Decimal('36.9714'), collection_margin_usd=Decimal('0.3697'), payout_margin_usd=Decimal('0.3697'), payout_usd_cost=Decimal('36.2320') yields delta=0.0000 which is < 0.01 - function returns None. • Failing case: artificially set collection_usd=Decimal('37.00') with the same margin and cost values (delta > 0.01) - function raises PoolIdentityError. • Boundary exact: delta=Decimal('0.0099') < 0.01 passes; delta=Decimal('0.0100') >= 0.01 raises. • service_charge is NOT a parameter; function signature has exactly 5 parameters (4 pool values + tolerance). • Passing tolerance=Decimal('0.005') makes delta=Decimal('0.0070') raise where the default 0.01 would not. | 25 | 4.3-T01 | BE | RATE-04
4.3-T03 | rate-fx | 4.3 | 4. Rate Engine & FX | USD pool identity assertion | 1 | Unit tests for assert_pool_identity() - passing, failing, and service_charge exclusion cases | WBS 4.3. Tests for the assert_pool_identity function in rate_engine/assertions.py. RATE-04 §4.3 worked example: treasury.usd_krw=1380.00, target_payout=50000 KRW, m_a=m_b=0.01. Results: payout_usd_cost=36.2319, collection_usd=36.9714, collection_margin_usd=0.3697, payout_margin_usd=0.3697 (all Decimal). Pool identity delta ~ 0.0001 USD, well within 0.01. service_charge is separate (e.g. 0.36 USD) and must NOT affect pool identity. Pool identity covers only Steps 1-3 values. | • Create tests/rate_engine/test_pool_identity_assertion.py. • Test PASS_NOMINAL: use RATE-04 §4.3 worked values (payout_usd_cost=Decimal('36.2319'), collection_usd=Decimal('36.9714'), margins both Decimal('0.3697')) - assert no exception raised. • Test FAIL_ENGINEERED: set collection_usd=Decimal('40.0000'), others unchanged - assert PoolIdentityError raised and error.delta > Decimal('0.01'). • Test SERVICE_CHARGE_IRRELEVANCE: call assert_pool_identity with the passing RATE-04 values then repeat with service_charge=Decimal('100.00') stored alongside but NOT passed to the function - both calls return None, confirming service_charge cannot affect the check. • Test BOUNDARY: delta=Decimal('0.0099') passes; delta=Decimal('0.0100') raises. • Test CUSTOM_TOLERANCE: tolerance=Decimal('0.005') causes delta=Decimal('0.0070') to raise PoolIdentityError. | tests/rate_engine/test_pool_identity_assertion.py with at least 5 parameterised test cases all passing | • All 5+ test cases pass with no tolerance warnings. • SERVICE_CHARGE_IRRELEVANCE test explicitly demonstrates service_charge is not a parameter. • FAIL_ENGINEERED test asserts error.delta attribute > Decimal('0.01'). • Boundary test checks both sides of the 0.01 threshold (< passes, >= raises). • No float literals in any test - all monetary values use Decimal constructor. | 30 | 4.3-T02 | BE | RATE-04
4.3-T04 | rate-fx | 4.3 | 4. Rate Engine & FX | USD pool identity assertion | 1 | Integrate assert_pool_identity() into rate engine post-Steps-1-3 | WBS 4.3. RATE-04 §11.2 and the pseudocode in §11 show the assertion must be called immediately after Step 3b (payout_margin_usd = collection_usd * m_b) and before Step 4 (send_amount = collection_usd * cost_rate_coll). The same-currency short-circuit path (collection_ccy = settle_a_ccy = settle_b_ccy = payout_ccy) must SKIP the assertion entirely because the USD pool is never computed; instead collection_amount = target_payout + service_charge directly. service_charge is added at Step 5 and must not be passed to the assertion. | • Open the Rate Engine calculate() method (rate_engine/engine.py or equivalent). • Locate the same-currency short-circuit branch; confirm assert_pool_identity is NOT called there. • In the cross-border branch, immediately after payout_margin_usd = collection_usd * m_b, add assert_pool_identity(collection_usd, collection_margin_usd, payout_margin_usd, payout_usd_cost). • Confirm Step 4 (send_amount) and Step 5 (collection_amount = send_amount + service_charge) follow unchanged after the assertion call. • Let PoolIdentityError propagate uncaught at this layer (the orchestrator catches it). | Updated rate_engine/engine.py with assert_pool_identity() call inserted at the correct point in the cross-border branch | • On a normal RATE-04 §4.3 cross-border call (m_a=m_b=0.01, target_payout=50000 KRW, usd_krw=1380) the engine completes and returns a RateQuote with no exception. • Mutating collection_usd to an absurd value before assertion (test-only monkey-patch) causes the engine to raise PoolIdentityError before reaching Step 4. • A same-currency call (e.g. KRW to KRW domestic) completes without any PoolIdentityError even though pool fields are null/zero. • service_charge changing from 0.36 to 5.00 USD on a cross-border call does NOT raise PoolIdentityError (Step 5 comes after assertion). • assert_pool_identity is called exactly once per cross-border calculation, not per same-currency call. | 35 | 4.3-T02, 4.3-T03 | BE | RATE-04
4.3-T05 | rate-fx | 4.3 | 4. Rate Engine & FX | USD pool identity assertion | 1 | Add critical-level structured logging on PoolIdentityError | WBS 4.3. RATE-04 §11.2 states: 'It must be logged as a critical internal error for investigation.' A PoolIdentityError is a programming bug, not a user error. The log record must include all four pool values and the delta so production on-call engineers can diagnose without querying the DB. Log at CRITICAL level; the orchestrator should then re-raise or translate to a safe API error response (POOL_IDENTITY_FAILURE) - this ticket covers only logging, not the API response translation. | • In the orchestrator layer (payment_orchestrator.py or rate_orchestrator.py) add a try/except PoolIdentityError block around the Rate Engine calculate() call. • In the except block log at CRITICAL level with structured fields: event=POOL_IDENTITY_FAILURE, collection_usd, collection_margin_usd, payout_margin_usd, payout_usd_cost, delta, quote_ref (if available). • After logging, re-raise the exception (do not swallow it; upstream caller will translate to API error). • Use the application logger (not print); ensure the message contains the literal string POOL_IDENTITY_FAILURE for log aggregator alerting. | Orchestrator try/except block in payment_orchestrator.py that logs PoolIdentityError at CRITICAL with all five numeric fields before re-raising | • Triggering a synthetic PoolIdentityError (mock engine) produces a CRITICAL log record containing the string POOL_IDENTITY_FAILURE. • Log record contains collection_usd, collection_margin_usd, payout_margin_usd, payout_usd_cost, and delta as separate structured fields (not embedded in a prose string). • Exception is re-raised after logging - calling code still receives PoolIdentityError. • No CRITICAL log fires on a normal cross-border call that passes the assertion. • Same-currency (short-circuit) calls produce no CRITICAL log. | 25 | 4.3-T04 | BE | RATE-04
4.3-T06 | rate-fx | 4.3 | 4. Rate Engine & FX | USD pool identity assertion | 1 | Translate PoolIdentityError to POOL_IDENTITY_FAILURE API error response | WBS 4.3. The Northbound API (API-05) must return a structured error when a POOL_IDENTITY_FAILURE occurs. This is a 500 Internal Server Error (not a 4xx - the partner did nothing wrong). Response body must include error_code: POOL_IDENTITY_FAILURE and a safe message without internal field values (pool values are sensitive; they go to logs only). The orchestrator re-raises PoolIdentityError after logging (4.3-T05); this ticket adds the exception handler in the API layer. | • In the API gateway/handler layer (e.g. api/routes/rates.py or api/routes/payments.py) add an exception handler for PoolIdentityError. • Map PoolIdentityError -> HTTP 500 response body {error_code: POOL_IDENTITY_FAILURE, message: Internal rate calculation error. Please contact support.} with no pool field values in the response. • Ensure the handler does NOT log again (logging is done in the orchestrator layer in 4.3-T05). • Add the same handler to both POST /v1/rates and POST /v1/payments routes. | API exception handler in api/routes/ mapping PoolIdentityError to HTTP 500 with error_code POOL_IDENTITY_FAILURE, added to both /v1/rates and /v1/payments handlers | • When the rate engine raises PoolIdentityError, the API returns HTTP 500 with body containing error_code=POOL_IDENTITY_FAILURE. • Response body does NOT contain collection_usd, payout_usd_cost, or any internal pool values. • HTTP status code is 500 (not 400 or 422). • Normal cross-border and same-currency calls still return HTTP 200 with valid RateQuote. • Unit test confirms the error_code field value is exactly the string POOL_IDENTITY_FAILURE. | 25 | 4.3-T05 | BE | RATE-04
4.3-T07 | rate-fx | 4.3 | 4. Rate Engine & FX | USD pool identity assertion | 1 | Integration test: same-currency short-circuit trivially satisfies identity (no assertion called) | WBS 4.3. RATE-04 §7.2 and DAT-03 §7.3: when collection_ccy = settle_a_ccy = settle_b_ccy = payout_ccy (e.g. GME Remit KRW-to-KRW on ZeroPay), the USD pool is bypassed entirely. Fields collection_usd, payout_usd_cost, collection_margin_usd, payout_margin_usd are all NULL/zero; collection_amount = target_payout + service_charge. The pool identity assertion must NOT be invoked on this path - it is not that it passes trivially, it is that the assertion function is never called, since there is no pool to check. | • Create tests/rate_engine/test_same_currency_short_circuit.py. • Call the rate engine with a same-currency rule: collection_ccy=KRW, settle_a_ccy=KRW, settle_b_ccy=KRW, payout_ccy=KRW, target_payout=Decimal('50000'), service_charge=Decimal('500'). • Assert result.collection_amount = Decimal('50500') (= 50000 + 500). • Assert result.collection_usd is None or Decimal('0') (pool bypassed). • Using unittest.mock.patch assert_pool_identity is called 0 times. • Assert no PoolIdentityError is raised. | tests/rate_engine/test_same_currency_short_circuit.py demonstrating the short-circuit path bypasses the pool identity assertion entirely | • collection_amount == Decimal('50500') for target_payout=50000 KRW + service_charge=500 KRW. • assert_pool_identity is confirmed called 0 times via mock patch. • No PoolIdentityError is raised on the short-circuit path. • Changing service_charge from 500 to 1000 KRW yields collection_amount=51000, still no assertion call. • USD pool fields (collection_usd, payout_usd_cost) are null/zero in the returned result. | 30 | 4.3-T04 | BE | RATE-04
4.3-T08 | rate-fx | 4.3 | 4. Rate Engine & FX | USD pool identity assertion | 1 | Integration test: end-to-end cross-border call with RATE-04 worked example values | WBS 4.3. Full end-to-end test using the canonical worked example from RATE-04 §4.3: treasury.usd_krw=1380.00, target_payout=50000 KRW, m_a=0.01 (collection side), m_b=0.01 (payout side), service_charge=0.36 USD, cost_rate_coll=1.0 (identity leg, Settle A=USD), cost_rate_pay=1380.00. Expected: payout_usd_cost=36.2319, collection_usd=36.9714, collection_margin_usd=0.3697, payout_margin_usd=0.3697, send_amount=36.9714, collection_amount=37.3314. Pool identity delta=0.0001 < 0.01 USD (passes). service_charge change must not affect pool identity. | • Create tests/rate_engine/test_rate04_worked_example.py. • Set up engine with exact RATE-04 §4.3 parameters and call calculate(). • Assert each intermediate value matches RATE-04 §4.3 within Decimal('0.0001') precision. • Assert no PoolIdentityError is raised (pool identity passes). • Re-run with service_charge changed to Decimal('5.00') USD and assert pool identity still passes (collection_amount changes but pool check values are unchanged). • Assert that collection_amount = send_amount + service_charge (Step 5 correctness). | tests/rate_engine/test_rate04_worked_example.py validating the full 5-step RATE-04 §4.3 worked example including pool identity pass and service_charge isolation | • payout_usd_cost = Decimal('36.2319') +/- Decimal('0.0001'). • collection_usd = Decimal('36.9714') +/- Decimal('0.0001'). • collection_margin_usd = payout_margin_usd = Decimal('0.3697') +/- Decimal('0.0001'). • No PoolIdentityError raised on the nominal run. • Changing service_charge from 0.36 to 5.00 USD does not raise PoolIdentityError and does not alter payout_usd_cost, collection_usd, collection_margin_usd, or payout_margin_usd. | 35 | 4.3-T04 | BE | RATE-04
4.3-T09 | rate-fx | 4.3 | 4. Rate Engine & FX | USD pool identity assertion | 1 | Unit test: verify tolerance is configurable and drives assertion boundary | WBS 4.3. The tolerance default is Decimal('0.01') but must be configurable (POOL_IDENTITY_TOLERANCE_USD in application settings). This ticket tests that overriding the tolerance at the engine or function level changes the pass/fail boundary and that no float literals leak into the comparison. This is a regression guard ensuring future ops changes to tolerance do not silently break the check. | • Create tests/rate_engine/test_pool_identity_tolerance.py. • Construct pool values with a known delta of Decimal('0.007'): collection_usd=Decimal('100.007'), collection_margin_usd=Decimal('1.00'), payout_margin_usd=Decimal('1.00'), payout_usd_cost=Decimal('98.000'). • Call assert_pool_identity with default tolerance Decimal('0.01') -> expect no exception (0.007 < 0.01). • Call assert_pool_identity with tolerance=Decimal('0.005') -> expect PoolIdentityError (0.007 >= 0.005). • Call assert_pool_identity with tolerance=Decimal('0.008') -> expect PoolIdentityError (0.007 < 0.008 is false, 0.007 < 0.008 is true) - confirm boundary direction is strictly less-than. • Assert POOL_IDENTITY_TOLERANCE_USD constant type is Decimal not float. | tests/rate_engine/test_pool_identity_tolerance.py covering tolerance configurability and boundary behavior | • delta=Decimal('0.007') passes with tolerance=Decimal('0.01'). • delta=Decimal('0.007') raises PoolIdentityError with tolerance=Decimal('0.005'). • delta=Decimal('0.007') passes with tolerance=Decimal('0.008') (strictly less-than, 0.007 < 0.008). • POOL_IDENTITY_TOLERANCE_USD is of type Decimal (isinstance check). • No float literal appears in the tolerance comparison path (inspect source or assert Decimal arithmetic). | 25 | 4.3-T02 | BE | RATE-04
4.4-T01 | rate-fx | 4.4 | 4. Rate Engine & FX | Derived BOK outputs | 1 | Add offer_rate_coll and cross_rate fields to RateQuote result DTO | WBS 4.4 Derived BOK outputs. RateQuote is the engine result object returned by compute_rate_quote() and stored in Redis (rate_quote table). It currently holds pool fields (collection_usd, payout_usd_cost, collection_margin_usd, payout_margin_usd, send_amount, service_charge, collection_amount). Two derived fields must be added: offer_rate_coll (DECIMAL(20,8), nullable - NULL for same-currency) and cross_rate (DECIMAL(20,8), nullable - NULL for same-currency). These are BOK-required outputs: offer_rate_coll = BOK FX1015 field #14. Depends on WBS 4.2 (rate engine core). | • Open the RateQuote DTO/record class (result object of compute_rate_quote). • Add field offer_rate_coll: BigDecimal (nullable) with Javadoc: BOK FX1015 field #14; derived as send_amount / (collection_usd - collection_margin_usd); NULL for same-currency flows. • Add field cross_rate: BigDecimal (nullable) with Javadoc: target_payout / send_amount; NULL for same-currency flows. • Add the two fields to the rate_quote DB table migration as DECIMAL(20,8) NULL columns (offer_rate_coll, cross_rate). • Verify all existing RateQuote constructors/builders compile with the new fields (set null or 0 as appropriate for existing callers). | Updated RateQuote DTO with offer_rate_coll and cross_rate fields plus DB migration script adding those two columns to rate_quote table | • RateQuote object can be instantiated with offer_rate_coll = null and cross_rate = null without NPE. • DB migration runs cleanly on an empty rate_quote table: both columns appear as DECIMAL(20,8) NULL. • All existing unit tests for RateQuote still pass after adding the two nullable fields. • Javadoc on offer_rate_coll explicitly states: BOK FX1015 field #14; formula send_amount / (collection_usd - collection_margin_usd). | 25 | 4.2 | BE | RATE-04, SEC-09
4.4-T02 | rate-fx | 4.4 | 4. Rate Engine & FX | Derived BOK outputs | 1 | Implement offer_rate_coll computation in rate engine (cross-border path) | WBS 4.4 Derived BOK outputs. After completing steps 1-5 of the RECEIVE-mode rate engine (payout_usd_cost, collection_usd, collection_margin_usd, payout_margin_usd, send_amount), compute: collection_net_usd = collection_usd - collection_margin_usd; offer_rate_coll = send_amount / collection_net_usd. This is the effective all-in rate from Settle A to Settle B after collection-side margin, and is BOK FX1015 field #14. Must use Decimal arithmetic (BigDecimal in Java). Numeric example: collection_usd=36.9714 USD, collection_margin_usd=0.3697 USD, send_amount=36.9714 USD (identity leg: cost_rate_coll=1.0) -> collection_net_usd=36.6017 -> offer_rate_coll=36.9714/36.6017=1.01010. Second example (USD/USD): collection_usd=102.0408, collection_margin_usd=1.0204, send_amount=102.0408 -> offer_rate_coll=102.0408/101.0204=1.01010. Depends on 4.4-T01. | • In the cross-border branch of compute_rate_quote(), after step 4 (send_amount = collection_usd * cost_rate_coll), compute: collection_net_usd = collection_usd.subtract(collection_margin_usd). • Compute offer_rate_coll = send_amount.divide(collection_net_usd, 8, HALF_UP). Use BigDecimal.divide with explicit scale 8 and rounding mode. • Assign offer_rate_coll to the RateQuote builder/constructor. • Add a single-line comment above the assignment: // BOK FX1015 field #14: effective Settle-A to Settle-B rate after collection-side margin. • Confirm same-currency path still sets offer_rate_coll = BigDecimal.ONE (unity rate, no margin). | compute_rate_quote() method populating offer_rate_coll in the returned RateQuote for cross-border calls | • Input: collection_usd=36.9714, collection_margin_usd=0.3697, send_amount=36.9714 -> offer_rate_coll == 1.01010 (within 0.000005 tolerance). • Input: collection_usd=102.0408, collection_margin_usd=1.0204, send_amount=102.0408 -> offer_rate_coll == 1.01010 (within 0.000005). • Source code contains comment referencing BOK FX1015 field #14 adjacent to the formula. • Same-currency call returns offer_rate_coll = 1.0 exactly. • offer_rate_coll field in the returned RateQuote is non-null for any cross-border call. | 30 | 4.4-T01 | BE | RATE-04, SEC-09
4.4-T03 | rate-fx | 4.4 | 4. Rate Engine & FX | Derived BOK outputs | 1 | Implement cross_rate computation in rate engine (cross-border path) | WBS 4.4 Derived BOK outputs. After computing send_amount in step 4 of the RECEIVE-mode engine, compute: cross_rate = target_payout / send_amount. This is the direct exchange rate between payout currency and Settle A currency; a reconciliation/display reference figure. Must use BigDecimal arithmetic, scale 8, HALF_UP. Numeric examples: target_payout=50000 KRW, send_amount=36.9714 USD -> cross_rate=50000/36.9714=1352.24 KRW/USD. USD/USD example: target_payout=100.00, send_amount=102.0408 -> cross_rate=100.00/102.0408=0.98000. Same-currency: cross_rate=1.0. Depends on 4.4-T01. | • In the cross-border branch of compute_rate_quote(), after step 4 (send_amount computed), compute cross_rate = target_payout.divide(send_amount, 8, HALF_UP). • Assign cross_rate to the RateQuote builder/constructor. • Add comment: // cross_rate: direct payout-ccy / Settle-A-ccy reference rate for reconciliation. • Confirm same-currency path sets cross_rate = BigDecimal.ONE. • Confirm cross_rate is non-null in the returned RateQuote for all cross-border calls. | compute_rate_quote() method populating cross_rate in the returned RateQuote for cross-border calls | • Input: target_payout=50000, send_amount=36.9714 -> cross_rate == 1352.24 (within 0.005 tolerance). • Input: target_payout=100.00, send_amount=102.0408 -> cross_rate == 0.98000 (within 0.000005). • Same-currency call returns cross_rate = 1.0 exactly. • cross_rate is non-null for any cross-border call in returned RateQuote. • No floating-point (double/float) used anywhere in the computation path; BigDecimal only. | 25 | 4.4-T01 | BE | RATE-04, SEC-09
4.4-T04 | rate-fx | 4.4 | 4. Rate Engine & FX | Derived BOK outputs | 1 | Guard divide-by-zero: validate collection_net_usd > 0 before offer_rate_coll | WBS 4.4 Derived BOK outputs. offer_rate_coll = send_amount / (collection_usd - collection_margin_usd). Denominator collection_net_usd = collection_usd - collection_margin_usd must be > 0 before division. Under normal engine flow collection_usd > collection_margin_usd always (m_a < 1.0 is already guarded), but a defensive explicit check prevents any future code path from producing ArithmeticException or returning infinity. Error code: INVALID_MARGIN (or a dedicated RATE_COMPUTATION_ERROR). Also: send_amount > 0 must be checked before cross_rate = target_payout / send_amount (send_amount = collection_usd * cost_rate_coll; if cost_rate_coll > 0 and collection_usd > 0 this holds, but guard explicitly). Depends on 4.4-T02 and 4.4-T03. | • Before computing offer_rate_coll, add: if collection_net_usd.compareTo(BigDecimal.ZERO) <= 0 throw new RateEngineException(RATE_COMPUTATION_ERROR, 'collection_net_usd must be > 0'). • Before computing cross_rate, add: if send_amount.compareTo(BigDecimal.ZERO) <= 0 throw new RateEngineException(RATE_COMPUTATION_ERROR, 'send_amount must be > 0'). • Ensure exception messages are logged at ERROR level with the offending values. • Verify that the existing guard (m_a + m_b < 1.0) comes before these derived-rate guards in execution order so the primary guard fires first on bad margin input. | Two explicit divide-by-zero guards in compute_rate_quote() with RateEngineException throws before offer_rate_coll and cross_rate divisions | • Calling compute_rate_quote() with collection_usd=1.0, collection_margin_usd=1.0 (collection_net_usd=0) throws RateEngineException with code RATE_COMPUTATION_ERROR, not ArithmeticException. • Calling with collection_usd=0.0001, collection_margin_usd=0.0001 (net=0) also throws (boundary). • Calling with send_amount=0 (artificially injected) throws RateEngineException before cross_rate division. • Normal cross-border call with collection_net_usd=36.6017 does NOT throw; proceeds to return offer_rate_coll=1.01010. • The m_a+m_b >= 0.02 guard fires before the derived-rate guards when m_a+m_b < 0.02 is the root cause. | 30 | 4.4-T02, 4.4-T03 | BE | RATE-04, SEC-09
4.4-T05 | rate-fx | 4.4 | 4. Rate Engine & FX | Derived BOK outputs | 1 | Unit tests: offer_rate_coll and cross_rate happy-path numeric vectors | WBS 4.4 Derived BOK outputs. Test the computed values of offer_rate_coll and cross_rate against spec-provided numeric examples. Engine RECEIVE mode, cross-border. Vector 1 (KRW/USD identity-coll leg): target_payout=50000 KRW, cost_rate_pay=1350.0 (KRW/USD), cost_rate_coll=1.0 (USD identity), m_a=0.01, m_b=0.01, service_charge=0 -> expected: payout_usd_cost=37.0370, collection_usd=37.8948 (approx), collection_margin_usd=0.3789, send_amount=37.8948, offer_rate_coll=37.8948/(37.8948-0.3789)=1.01010, cross_rate=50000/37.8948=1319.4. Vector 2 (USD/USD): target_payout=100 USD, cost_rate_pay=1.0, cost_rate_coll=1.0, m_a=0.01, m_b=0.01, service_charge=0 -> collection_usd=102.0408, collection_margin_usd=1.0204, send_amount=102.0408, offer_rate_coll=1.01010, cross_rate=0.98000. Depends on 4.4-T02, 4.4-T03, 4.4-T04. | • Create test class RateEngineDerivedRatesTest (JUnit 5). • Implement testOfferRateCollKrwUsd(): use Vector 1 inputs, assert offer_rate_coll within delta 0.00005, cross_rate within delta 0.01. • Implement testOfferRateCollUsdUsd(): use Vector 2 inputs, assert offer_rate_coll=1.01010 within 0.00005, cross_rate=0.98000 within 0.00005. • Implement testSameCurrencyDerivedRates(): same-currency call, assert offer_rate_coll=1.0 exactly, cross_rate=1.0 exactly. • Use BigDecimal assertions throughout; no assertEquals(double, double) - use compareTo or assertThat with precision. | RateEngineDerivedRatesTest.java with at least 3 passing unit tests covering happy-path numeric vectors for offer_rate_coll and cross_rate | • testOfferRateCollUsdUsd passes: offer_rate_coll=1.01010 +/- 0.00005 for USD/USD inputs. • testSameCurrencyDerivedRates passes: offer_rate_coll=1.0, cross_rate=1.0 for same-ccy call. • testOfferRateCollKrwUsd passes: cross_rate is in expected KRW/USD range (1300-1400) for target_payout=50000 KRW at rate ~1350. • All tests use BigDecimal inputs (no float literals). • Test class runs with mvn test -pl rate-engine with zero failures. | 40 | 4.4-T02, 4.4-T03, 4.4-T04 | BE | RATE-04, SEC-09
4.4-T06 | rate-fx | 4.4 | 4. Rate Engine & FX | Derived BOK outputs | 1 | Unit tests: divide-by-zero guards for offer_rate_coll and cross_rate | WBS 4.4 Derived BOK outputs. Guard tests verify that the engine throws RateEngineException (not ArithmeticException) when collection_net_usd <= 0 or send_amount <= 0. These are defensive guards added in 4.4-T04. Test via a test-only constructor or package-private method that bypasses the earlier m_a/m_b validation and directly injects a zero denominator, OR by verifying the exception fires correctly when m_a is crafted to make collection_net_usd approach zero (m_a close to 1.0 but blocked by the earlier m_a+m_b<1.0 guard first). Also test that a normal call with valid denominators (collection_net_usd=36.6017, send_amount=36.9714) does NOT throw. Depends on 4.4-T04. | • In RateEngineDerivedRatesTest, add testDivideByZeroCollectionNetUsd(): inject collection_net_usd=0 via the package-private guard method or a test subclass; assert RateEngineException is thrown with code RATE_COMPUTATION_ERROR. • Add testDivideByZeroSendAmount(): inject send_amount=0; assert RateEngineException thrown. • Add testNoExceptionForValidDenominators(): call with collection_net_usd=36.6017, send_amount=36.9714; assert no exception and offer_rate_coll is populated. • Verify exception message contains the field name (collection_net_usd or send_amount) for debuggability. | Divide-by-zero guard tests added to RateEngineDerivedRatesTest.java (3 additional test methods) | • testDivideByZeroCollectionNetUsd throws RateEngineException (not ArithmeticException) when collection_net_usd=0. • testDivideByZeroSendAmount throws RateEngineException when send_amount=0. • Exception errorCode is RATE_COMPUTATION_ERROR in both cases. • testNoExceptionForValidDenominators completes without exception and returns non-null offer_rate_coll. • All 3 tests pass with mvn test. | 30 | 4.4-T04, 4.4-T05 | BE | RATE-04, SEC-09
4.4-T07 | rate-fx | 4.4 | 4. Rate Engine & FX | Derived BOK outputs | 1 | Persist offer_rate_coll and cross_rate into rate_quote table on quote creation | WBS 4.4 Derived BOK outputs. When the rate engine creates a quote (compute_rate_quote()), the returned RateQuote (containing offer_rate_coll and cross_rate) must be persisted to the rate_quote table. The rate_quote table already holds pool values; the two new DECIMAL(20,8) NULL columns (offer_rate_coll, cross_rate) were added in 4.4-T01. The repository/DAO layer that INSERTs into rate_quote must now include those two fields. Precision: DECIMAL(20,8). NULL only for same-currency flows. Depends on 4.4-T01. | • In the RateQuoteRepository (or JPA entity for rate_quote), map offer_rate_coll and cross_rate fields to the DB columns added in 4.4-T01. • In the INSERT/save path for a new quote, write rateQuote.getOfferRateColl() and rateQuote.getCrossRate() to the DB (null for same-currency). • Add a repository integration test (or @DataJpaTest) that saves a cross-border RateQuote and reads it back, asserting offer_rate_coll and cross_rate are preserved to 8 decimal places. • Add a second case for same-currency: assert both columns read back as NULL. | Updated RateQuoteRepository persisting offer_rate_coll and cross_rate, plus integration test verifying round-trip DB persistence | • Cross-border RateQuote saved with offer_rate_coll=1.01010000 reads back as 1.01010000 (no truncation). • Same-currency RateQuote saved with offer_rate_coll=null reads back as null. • No existing tests broken by the repository change. • DB query SELECT offer_rate_coll, cross_rate FROM rate_quote WHERE id=? returns the expected values. | 35 | 4.4-T01, 4.4-T02, 4.4-T03 | BE | RATE-04, SEC-09
4.4-T08 | rate-fx | 4.4 | 4. Rate Engine & FX | Derived BOK outputs | 1 | Copy offer_rate_coll and cross_rate to transaction record at rate-lock (commit) | WBS 4.4 Derived BOK outputs. On CommitTransaction (rate-lock step), ALL rate_quote pool values and derived rates are copied to the transaction record as immutable columns (rate_locked_at is set). The transaction table must have offer_rate_coll and cross_rate columns (DECIMAL(20,8) NULL, labelled in column comment: BOK FX1015 field #14 for offer_rate_coll). The on_commit() function copies: transaction.offer_rate_coll = quote.offer_rate_coll; transaction.cross_rate = quote.cross_rate. After lock, no subsequent treasury or margin change may alter these values. Depends on 4.4-T07. | • Add migration: ALTER TABLE transaction ADD COLUMN offer_rate_coll DECIMAL(20,8) NULL COMMENT 'Derived rate: send_amount/(collection_usd-collection_margin_usd); BOK FX1015 field #14; locked at commit'; ADD COLUMN cross_rate DECIMAL(20,8) NULL COMMENT 'Derived rate: target_payout/send_amount; locked at commit'. • In the on_commit() / CommitTransaction service method, add assignment: transaction.setOfferRateColl(quote.getOfferRateColl()); transaction.setCrossRate(quote.getCrossRate()). • Verify rate_locked_at is also set in the same atomic write as the derived fields. • Add an integration test: commit a transaction, then change treasury rates in DB, reload the transaction record, assert offer_rate_coll and cross_rate are unchanged. | DB migration adding offer_rate_coll and cross_rate to transaction table plus on_commit() assignments with rate-lock immutability test | • After CommitTransaction, transaction.offer_rate_coll equals the value from the locked RateQuote (1.01010 for standard cross-border). • After CommitTransaction, updating treasury rate in DB and reloading the transaction record does NOT change offer_rate_coll or cross_rate. • Same-currency transaction committed with offer_rate_coll=null persists null in transaction table. • rate_locked_at and offer_rate_coll are written in the same DB transaction (atomically). • Migration runs without error; DESCRIBE transaction shows both new columns. | 40 | 4.4-T07 | BE | RATE-04, SEC-09
4.4-T09 | rate-fx | 4.4 | 4. Rate Engine & FX | Derived BOK outputs | 1 | Expose offer_rate_coll (as offer_rate) and cross_rate in /v1/rates API response | WBS 4.4 Derived BOK outputs. The northbound API (GET /v1/rates) response must include offer_rate (mapped from offer_rate_coll) and cross_rate. Per spec API-05, field names in the response are: offer_rate (= offer_rate_coll), cross_rate, plus existing pool fields (collection_usd, send_amount, service_charge, collection_amount, validUntil). The RateQuoteResponse DTO returned by the /rates endpoint must include these two fields. Same-currency: offer_rate=1.0, cross_rate=1.0 (do not expose null to partners; convert null to 1.0 in the API layer). Depends on 4.4-T02, 4.4-T03. | • In RateQuoteResponse (API response DTO), add fields: offer_rate (BigDecimal) and cross_rate (BigDecimal). • In the mapping from RateQuote -> RateQuoteResponse, set offer_rate = (quote.getOfferRateColl() != null ? quote.getOfferRateColl() : BigDecimal.ONE); similarly for cross_rate. • Add @Schema annotation (OpenAPI): offer_rate description = 'Effective Settle-A to Settle-B rate after collection-side margin (BOK FX1015 #14). Use this rate to compute the customer-facing collection amount.'; cross_rate = 'Direct payout-ccy / send-amount reference rate for reconciliation.' • Write a controller/MockMvc test: mock a cross-border rate computation, call GET /v1/rates, assert JSON response contains offer_rate=1.01010 and cross_rate in expected range. | RateQuoteResponse DTO with offer_rate and cross_rate fields, mapping logic, OpenAPI annotations, and controller test | • GET /v1/rates for cross-border call returns JSON with offer_rate=1.01010 (within 0.00005) and cross_rate populated. • GET /v1/rates for same-currency call returns offer_rate=1.0 and cross_rate=1.0 (not null, not absent). • OpenAPI spec (generated) contains offer_rate with description mentioning BOK FX1015 #14. • Field name in JSON is offer_rate (not offer_rate_coll) per API-05. • Controller test passes with mvn test. | 35 | 4.4-T02, 4.4-T03, 4.4-T07 | BE | RATE-04, SEC-09
4.4-T10 | rate-fx | 4.4 | 4. Rate Engine & FX | Derived BOK outputs | 1 | Document BOK FX1015 field #14 mapping in code comments and architecture note | WBS 4.4 Derived BOK outputs. The spec requires the BOK FX1015 field #14 mapping to be documented in code so that any developer or compliance reviewer can trace offer_rate_coll back to the regulatory requirement without referencing external documents. This is a pure documentation ticket: no logic changes. Key facts to embed: offer_rate_coll = send_amount / (collection_usd - collection_margin_usd); maps to BOK FX1015 (payout-to-Korean-merchant report) field #14; cross_rate = target_payout / send_amount (reconciliation reference); both are derived and NEVER operator-configured; BOK-reported rates equal executed rates by construction (rate-lock). FX1014 covers collection side, FX1015 covers payout side. Depends on 4.4-T08. | • In compute_rate_quote(), add a block comment above the derived-rates section: // === Derived BOK Outputs (never configured) === // offer_rate_coll: BOK FX1015 (payout-side) field #14. Formula: send_amount / (collection_usd - collection_margin_usd). // cross_rate: target_payout / send_amount. Reconciliation reference rate only. // Both values are locked immutably at CommitTransaction. See RATE-04 in spec. • In the RateQuote DTO Javadoc class-level comment, add: 'offer_rate_coll maps to Bank of Korea FX1015 (payout leg) field #14. FX1014 covers the collection leg. Both rates equal executed rates by construction; no separate reporting computation needed.' • In the transaction entity class, add a Javadoc on the offer_rate_coll field: '@see bok_report_record for FX1015 submission; this field is the authoritative source for FX1015 #14.' • Verify no TODO or placeholder comments remain in the derived-rates code block. | In-code documentation: block comment in compute_rate_quote(), class-level Javadoc in RateQuote DTO, and field Javadoc in transaction entity - all referencing BOK FX1015 field #14 | • grep -r 'FX1015' src/ returns at least 3 hits: compute_rate_quote(), RateQuote DTO, transaction entity. • The comment in compute_rate_quote() states both the formula and the BOK FX1015 field #14 reference. • The transaction entity Javadoc on offer_rate_coll references bok_report_record as the downstream consumer. • No floating-point types appear anywhere in the documented code paths. • Code review: a new developer can identify the BOK regulatory purpose of offer_rate_coll from code alone, without reading the spec. | 20 | 4.4-T08 | BE | RATE-04, SEC-09
4.5-T01 | rate-fx | 4.5 | 4. Rate Engine & FX | Identity legs & same-currency short-circuit | 1 | Add is_same_currency flag and identity-leg fields to RuleConfig domain model | WBS 4.5 implements identity legs and same-currency short-circuit. A Rule links a Partner x Scheme x Direction and carries cost_rate_coll / cost_rate_pay plus margin percentages m_a and m_b. The rate engine needs two new derived boolean flags: (1) is_identity_coll = (settle_a_ccy == USD); (2) is_identity_pay = (settle_b_ccy == USD); (3) is_same_currency = (collection_ccy == settle_a_ccy == settle_b_ccy == payout_ccy). These flags are computed, not stored — they derive from the currencies already on the Rule record. Adding them to the RuleConfig value object makes them available to the engine without passing raw currency strings. | • Open the RuleConfig value object / record class (or equivalent DTO) used as the rate engine input. • Add three computed / derived boolean fields: is_identity_coll, is_identity_pay, is_same_currency — all package-private or internal. • Implement each as a pure currency-equality check: is_identity_coll = settle_a_ccy.equals(USD); is_identity_pay = settle_b_ccy.equals(USD); is_same_currency = collection_ccy == settle_a_ccy == settle_b_ccy == payout_ccy (all four equal). • Add a Javadoc / inline comment citing spec section 7.1 and 7.2 for each flag. • Add a unit test class RuleConfigFlagsTest with at least 4 cases: (a) all KRW -> is_same_currency=true, both identity flags=false; (b) settle_a=USD -> is_identity_coll=true; (c) settle_b=USD -> is_identity_pay=true; (d) both settle legs USD -> both identity flags true, is_same_currency=false (ccy differ from collection/payout). | Updated RuleConfig value object with three computed boolean flags plus RuleConfigFlagsTest unit test class. | • is_same_currency returns true iff all four of collection_ccy, settle_a_ccy, settle_b_ccy, payout_ccy are identical strings. • is_identity_coll returns true iff settle_a_ccy == USD; is_identity_pay returns true iff settle_b_ccy == USD. • is_same_currency = true does NOT imply either identity flag is true (e.g. all KRW => is_same_currency=true, is_identity_coll=false). • All four RuleConfigFlagsTest cases pass. • Flags are derived/computed — no new DB columns required. | 30 | 4.2 | BE | RATE-04
4.5-T02 | rate-fx | 4.5 | 4. Rate Engine & FX | Identity legs & same-currency short-circuit | 1 | Implement identity-leg rate resolution in RateEngine.resolveRates() | WBS 4.5 identity leg rule (spec §7.1): when settle_a_ccy = USD, set cost_rate_coll = 1.0 with source = IDENTITY; when settle_b_ccy = USD, set cost_rate_pay = 1.0 with source = IDENTITY. Both legs may simultaneously be IDENTITY (HUB direction, USD-in / USD-out). Margins m_a and m_b still apply normally in cross-border identity-leg cases; the identity only means no treasury lookup for that leg. The rate source enum must include IDENTITY alongside LIVE, MANUAL, PARTNER. This ticket adds identity resolution BEFORE the normal treasury/partner lookup so identity legs never cause RATE_UNAVAILABLE errors. | • Ensure the RateSource enum (or equivalent) contains an IDENTITY value (add it if missing). • In RateEngine.resolveRates() (or the method that sets cost_rate_coll and cost_rate_pay), add an early-return path for each leg: if rule.is_identity_coll == true, set cost_rate_coll = Decimal(1.0) and source_coll = IDENTITY without querying the treasury. • Apply the same pattern for the pay leg: if rule.is_identity_pay == true, set cost_rate_pay = Decimal(1.0) and source_pay = IDENTITY. • Record both source flags on the RateQuote / intermediate result so they are persisted in the rate-lock step. • Ensure the resolved rates and sources are passed to the 5-step engine unmodified. | Updated resolveRates() method in RateEngine with IDENTITY early-return for both legs. | • When settle_a_ccy = USD: cost_rate_coll = 1.0 exactly (Decimal), source_coll = IDENTITY; no treasury call made for that leg. • When settle_b_ccy = USD: cost_rate_pay = 1.0 exactly, source_pay = IDENTITY; no treasury call for that leg. • When neither leg is identity: resolution falls through to existing LIVE/MANUAL/PARTNER logic unchanged. • Both legs IDENTITY simultaneously: both rates = 1.0, both sources = IDENTITY; 5-step engine receives valid non-zero rates. • IDENTITY resolution does not suppress margin application — m_a and m_b still flow into the 5-step engine. | 35 | 4.5-T01 | BE | RATE-04
4.5-T03 | rate-fx | 4.5 | 4. Rate Engine & FX | Identity legs & same-currency short-circuit | 1 | Add identity-leg worked example unit tests to RateEngineIdentityTest | WBS 4.5: verify that the 5-step RECEIVE-mode engine produces correct outputs when one or both legs are IDENTITY. Spec §7.1 worked example: target_payout=100.00 USD, cost_rate_coll=1.0 (IDENTITY), cost_rate_pay=1.0 (IDENTITY), m_a=0.01, m_b=0.01, service_charge=0.50 USD. Expected: payout_usd_cost=100.00, collection_usd=102.0408, collection_margin_usd=1.0204, payout_margin_usd=1.0204, send_amount=102.0408, collection_amount=102.5408, offer_rate_coll=1.01010, cross_rate=0.98000. Pool identity: 102.0408 - 1.0204 - 1.0204 = 100.0000. All arithmetic must use Decimal types; tolerance for derived rates = 0.00001. | • Create test class RateEngineIdentityTest. • Add test case test_both_legs_identity_usd: inputs as per spec §7.1 worked example; assert each output field within stated tolerance. • Add test case test_identity_coll_only: settle_a=USD (cost_rate_coll=1.0), settle_b=KRW (cost_rate_pay=1350.00), m_a=0.015, m_b=0.015, target_payout=50000 KRW, service_charge=0 USD; verify step-by-step outputs and pool identity holds. • Add test case test_identity_pay_only: settle_a=EUR (cost_rate_coll=0.92), settle_b=USD (cost_rate_pay=1.0), m_a=0.01, m_b=0.01, target_payout=100.00 USD, service_charge=1.00 EUR; verify outputs. • Assert pool identity ¦collection_usd - collection_margin_usd - payout_margin_usd - payout_usd_cost¦ < 0.01 for all three cases. | RateEngineIdentityTest class with 3 test cases covering single and dual identity-leg scenarios. | • Both-legs-identity test: collection_amount = 102.5408 USD within 0.0001 tolerance. • Both-legs-identity test: offer_rate_coll = 1.01010 and cross_rate = 0.98000 within 0.00001. • Pool identity assertion passes for all three test cases (tolerance 0.01 USD). • source_coll and source_pay are recorded as IDENTITY in the returned RateQuote for identity legs. • Non-identity legs in mixed tests resolve rates from treasury (not hardcoded to 1.0). | 40 | 4.5-T02 | BE | RATE-04
4.5-T04 | rate-fx | 4.5 | 4. Rate Engine & FX | Identity legs & same-currency short-circuit | 1 | Implement same-currency short-circuit branch in RateEngine.compute() | WBS 4.5 same-currency short-circuit (spec §7.2): when is_same_currency = true (all four currencies equal), skip the entire 5-step USD pool. Instead: collection_amount = target_payout + service_charge; offer_rate_coll = 1.0; cross_rate = 1.0; collection_usd = NULL; payout_usd_cost = NULL; collection_margin_usd = 0; payout_margin_usd = 0; send_amount = target_payout. The guard must also assert m_a == 0 AND m_b == 0 and raise INVALID_MARGIN if not. service_charge is a flat Decimal in the collection currency (e.g. KRW 500); it is added directly, no USD conversion. KRW scale = 0 decimals. | • In RateEngine.compute(), immediately after the guard checks, add: if rule.is_same_currency { /* short-circuit */ }. • Inside the short-circuit block: assert m_a == 0 and m_b == 0 (raise INVALID_MARGIN if violated); set collection_amount = target_payout + service_charge; set offer_rate_coll = Decimal(1.0); set cross_rate = Decimal(1.0); set send_amount = target_payout; set collection_usd = null; set payout_usd_cost = null; set collection_margin_usd = Decimal(0); set payout_margin_usd = Decimal(0). • Round collection_amount to currency scale (KRW = 0 decimals) using the existing round_to_currency_scale helper. • Build and return RateQuote from these values, bypassing all 5-step logic. • Ensure the normal 5-step path is unchanged (else branch) and that is_same_currency=false does not enter the short-circuit block. | Short-circuit branch in RateEngine.compute() that sets collection_amount = target_payout + service_charge and nulls all USD pool fields when is_same_currency = true. | • GME Remit KRW->KRW on ZeroPay: target_payout=10000 KRW, service_charge=500 KRW, m_a=0, m_b=0 => collection_amount=10500 KRW, collection_usd=null, payout_usd_cost=null. • GME Remit worked example from spec: target_payout=15000 KRW, service_charge=500 KRW => collection_amount=15500 KRW. • If m_a or m_b != 0 with is_same_currency=true, engine raises INVALID_MARGIN before computing. • offer_rate_coll = 1.0 and cross_rate = 1.0 for all same-currency transactions. • Short-circuit does not call treasury or Partner B quote client. | 35 | 4.5-T01 | BE | RATE-04
4.5-T05 | rate-fx | 4.5 | 4. Rate Engine & FX | Identity legs & same-currency short-circuit | 1 | Add same-currency short-circuit unit tests to RateEngineSameCurrencyTest | WBS 4.5: verify the same-currency short-circuit produces the correct collection_amount and that all USD pool fields are null or zero. Key test vector (spec §7.2): GME Remit on ZeroPay KRW->KRW: target_payout=15000 KRW, service_charge=500 KRW, m_a=0, m_b=0 => collection_amount=15500 KRW. Additional vector: target_payout=10000 KRW, service_charge=500 KRW => collection_amount=10500 KRW. Edge case: service_charge=0 => collection_amount=target_payout. Error case: m_a=0.01 with is_same_currency=true => INVALID_MARGIN. KRW scale is 0 decimals; result must be a whole number. | • Create test class RateEngineSameCurrencyTest. • Add test_short_circuit_gmе_remit_zeropay_15000: inputs target_payout=15000, service_charge=500, m_a=0, m_b=0, all currencies KRW; assert collection_amount=15500, collection_usd=null, payout_usd_cost=null, offer_rate_coll=1.0, cross_rate=1.0. • Add test_short_circuit_10000: same setup with target_payout=10000, service_charge=500; assert collection_amount=10500. • Add test_short_circuit_zero_service_charge: target_payout=20000, service_charge=0; assert collection_amount=20000. • Add test_short_circuit_rejects_nonzero_margin: target_payout=10000, service_charge=500, m_a=0.01, m_b=0; assert engine raises INVALID_MARGIN (not MARGIN_BELOW_MINIMUM). | RateEngineSameCurrencyTest class with 4 parameterised test cases for same-currency short-circuit. | • test_short_circuit_gmе_remit_zeropay_15000 passes: collection_amount=15500 KRW exactly. • test_short_circuit_10000 passes: collection_amount=10500 KRW exactly. • Zero service charge test: collection_amount equals target_payout exactly. • Non-zero margin with is_same_currency=true raises INVALID_MARGIN, not any other error code. • collection_margin_usd and payout_margin_usd are Decimal(0) (not null) in the returned RateQuote for same-currency transactions. | 35 | 4.5-T04 | BE | RATE-04
4.5-T06 | rate-fx | 4.5 | 4. Rate Engine & FX | Identity legs & same-currency short-circuit | 1 | Enforce m_a = m_b = 0 guard for same-currency rules in RateEngine guard block | WBS 4.5: the pseudocode (spec §14) places the same-currency margin guard inside the short-circuit block: if is_same_currency AND (m_a != 0 OR m_b != 0) raise INVALID_MARGIN. This must be a runtime engine guard (not solely an admin-portal config-time guard), so that any misconfigured rule attempting to run with non-zero margins on a same-currency leg is caught before any computation. This ticket focuses only on the guard logic — the full short-circuit arithmetic is covered in 4.5-T04. The guard must fire BEFORE the cross-border margin floor check (m_a + m_b >= 0.02) so the error code is unambiguous. | • In the engine guard block (before both the short-circuit and 5-step paths), add: if is_same_currency AND (m_a != 0 OR m_b != 0) raise INVALID_MARGIN with message SAME_CURRENCY_NONZERO_MARGIN. • Ensure this guard runs BEFORE the cross-border m_a+m_b >= 0.02 check to prevent a same-currency rule from inadvertently hitting MARGIN_BELOW_MINIMUM instead. • Add a guard test in the existing RateEngineSameCurrencyTest (or a new class): rule is_same_currency=true, m_a=0.005, m_b=0 => INVALID_MARGIN; also m_a=0, m_b=0.01 => INVALID_MARGIN. • Verify cross-border rules (is_same_currency=false) are NOT affected by this guard and still require m_a+m_b>=0.02. • Document the guard order in a brief inline comment. | Guard clause in RateEngine ensuring is_same_currency=true with any non-zero margin raises INVALID_MARGIN before cross-border floor check. | • is_same_currency=true, m_a=0.005, m_b=0 => raises INVALID_MARGIN. • is_same_currency=true, m_a=0, m_b=0.01 => raises INVALID_MARGIN. • is_same_currency=false, m_a=0.01, m_b=0.01 (cross-border) => does NOT raise INVALID_MARGIN here; proceeds to margin floor check. • is_same_currency=false, m_a=0.005, m_b=0.005 (sum<0.02) => raises MARGIN_BELOW_MINIMUM (not INVALID_MARGIN). • Guard order: SAME_CURRENCY_NONZERO_MARGIN check executes before MARGIN_BELOW_MINIMUM check in the method body. | 25 | 4.5-T04 | BE | RATE-04
4.5-T07 | rate-fx | 4.5 | 4. Rate Engine & FX | Identity legs & same-currency short-circuit | 1 | Verify pool identity assertion is bypassed for same-currency transactions | WBS 4.5: the pool identity assertion (¦collection_usd - collection_margin_usd - payout_margin_usd - payout_usd_cost¦ < 0.01 USD) is defined only for cross-border paths (spec §11.2). For same-currency short-circuit, collection_usd and payout_usd_cost are NULL — applying the assertion would cause a NullPointerException or false POOL_IDENTITY_FAILURE. This ticket ensures the assertion is scoped to the cross-border (else) branch only, and that a same-currency transaction never hits POOL_IDENTITY_FAILURE. Additionally verify that when cost_rate_coll = 1.0 (identity leg, cross-border), the assertion still holds because send_amount = collection_usd * 1.0 = collection_usd. | • Locate the pool identity assertion in RateEngine.compute() (the check: ¦collection_usd - collection_margin_usd - payout_margin_usd - payout_usd_cost¦ < 0.01). • Confirm it is inside the else (cross-border) branch only; if it is at the top level or in the shared path, move it inside the cross-border branch. • Add a test in RateEngineSameCurrencyTest: verify that compute() with is_same_currency=true does NOT raise POOL_IDENTITY_FAILURE even though collection_usd is null. • Add a test in RateEngineIdentityTest: cross-border with both legs IDENTITY (cost_rate_coll=1.0, cost_rate_pay=1.0) — pool identity assertion must pass (collection_usd - 2*margin = payout_usd_cost within 0.01 USD). • Document in a comment that pool identity is cross-border only. | Pool identity assertion scoped strictly to the cross-border branch, with tests confirming no false POOL_IDENTITY_FAILURE for same-currency transactions. | • Same-currency transaction with is_same_currency=true completes without POOL_IDENTITY_FAILURE. • Cross-border identity-leg transaction (both rates=1.0, m_a=m_b=0.01): pool identity holds and assertion passes. • Cross-border non-identity transaction: pool identity assertion still executes and catches a deliberately broken pool (inject bad value => POOL_IDENTITY_FAILURE). • Pool identity assertion is not reachable from the short-circuit code path (static analysis / test coverage confirms it). | 30 | 4.5-T04, 4.5-T03 | BE | RATE-04
4.5-T08 | rate-fx | 4.5 | 4. Rate Engine & FX | Identity legs & same-currency short-circuit | 1 | Persist IDENTITY rate source in transaction rate-lock record | WBS 4.5: at CommitTransaction (rate-lock), all USD pool values and derived rates are permanently written to the transaction record. For identity-leg transactions (spec §7.1), cost_rate_coll_source and cost_rate_pay_source must be stored as IDENTITY. For same-currency short-circuit (spec §7.2), both source fields are recorded as IDENTITY and USD pool fields (collection_usd, payout_usd_cost, collection_margin_usd, payout_margin_usd) are NULL per the DB schema (DECIMAL(20,8) NULL). The offer_rate_coll and cross_rate fields are also NULL for same-currency (schema: Derived; NULL for same-ccy). This ticket wires the short-circuit and identity-source values from RateQuote into the rate-lock write path. | • Locate the rate-lock write method (e.g. TransactionRepository.lockRates() or equivalent) that copies RateQuote fields to the transaction DB record. • Ensure the write includes cost_rate_coll_source and cost_rate_pay_source columns (enum string: IDENTITY, MANUAL, LIVE, PARTNER). • For same-currency transactions: write collection_usd=NULL, payout_usd_cost=NULL, collection_margin_usd=NULL, payout_margin_usd=NULL, offer_rate_coll=NULL, cross_rate=NULL per the DB schema spec. • For cross-border identity-leg transactions: write cost_rate_coll=1.0 or cost_rate_pay=1.0 with source=IDENTITY; USD pool fields are NOT null (they have computed values). • Add an integration or repository unit test: commit a same-currency transaction and assert all NULL columns are actually NULL in the stored record; commit a dual-identity-leg cross-border transaction and assert cost_rate_coll=1.0 and source=IDENTITY. | Updated rate-lock write path that persists IDENTITY source flags and correct NULL values for same-currency transactions. | • After committing a same-currency transaction: collection_usd IS NULL, payout_usd_cost IS NULL, offer_rate_coll IS NULL, cross_rate IS NULL in DB. • After committing a same-currency transaction: cost_rate_coll_source = IDENTITY and cost_rate_pay_source = IDENTITY in DB. • After committing a cross-border dual-identity transaction: collection_usd is NOT NULL (has computed value); cost_rate_coll_source = IDENTITY. • After committing a cross-border non-identity transaction: source columns reflect MANUAL or LIVE (not IDENTITY). • Rate-lock is immutable: re-reading the transaction after a subsequent treasury rate change still returns the original locked rates. | 40 | 4.5-T04, 4.5-T02 | BE | RATE-04
4.5-T09 | rate-fx | 4.5 | 4. Rate Engine & FX | Identity legs & same-currency short-circuit | 1 | Validate same-currency margin constraint at rule configuration save time | WBS 4.5 / spec §11.3: at rule-save time in the Admin Service backend (not rate-engine runtime), enforce: (a) cross-border rules: m_a + m_b >= 2.0% (0.02); (b) same-currency rules: m_a = 0 AND m_b = 0. The same-currency check is determined by whether collection_ccy == settle_a_ccy == settle_b_ccy == payout_ccy on the rule being saved. Auto-enforce (not just validate) for same-currency rules: if the rule resolves as same-currency, forcibly set m_a=0 and m_b=0 before saving, regardless of operator input. Also set cost_rate_coll_source = IDENTITY and cost_rate_pay_source = IDENTITY automatically. Return a 422 with error code MARGIN_BELOW_MINIMUM if a cross-border rule has m_a+m_b < 0.02. | • In the RuleSaveService (or equivalent backend handler for POST/PUT /admin/rules), after currency fields are resolved, compute is_same_currency = (collection_ccy == settle_a_ccy == settle_b_ccy == payout_ccy). • If is_same_currency = true: override m_a = 0, m_b = 0; set cost_rate_coll_source = IDENTITY and cost_rate_pay_source = IDENTITY; do not raise an error (auto-enforce). • If is_same_currency = false (cross-border): validate m_a + m_b >= 0.02; if not, return HTTP 422 with error code MARGIN_BELOW_MINIMUM. • Persist the (possibly overridden) rule and write an audit log entry recording the actor, timestamp, old values, and new values. • Add unit tests: (a) save KRW/KRW same-currency rule with m_a=0.01 => saved with m_a=0, m_b=0, sources=IDENTITY; (b) save cross-border rule with m_a=0.005, m_b=0.005 => 422 MARGIN_BELOW_MINIMUM; (c) save cross-border with m_a=0.01, m_b=0.01 => saves successfully. | RuleSaveService validation and auto-enforcement of margin constraints with unit tests and audit log. | • Saving a KRW/KRW same-currency rule with any non-zero m_a or m_b auto-corrects both to 0 and saves (no error). • Saving a cross-border rule with m_a+m_b = 0.019 returns 422 MARGIN_BELOW_MINIMUM. • Saving a cross-border rule with m_a+m_b = 0.02 succeeds. • Audit log entry is created with old and new margin values when auto-enforcement overrides operator input. • cost_rate_coll_source and cost_rate_pay_source are set to IDENTITY automatically for same-currency rules. | 45 | 4.5-T01 | BE | RATE-04
4.5-T10 | rate-fx | 4.5 | 4. Rate Engine & FX | Identity legs & same-currency short-circuit | 1 | Integration test: end-to-end same-currency short-circuit for GME Remit on ZeroPay | WBS 4.5: full end-to-end integration test from GET /v1/rates through POST /v1/payments for a same-currency (Domestic KRW->KRW) transaction. GME Remit is a LOCAL partner (no prefunding deduction). Rule: collection_ccy=KRW, settle_a_ccy=KRW, settle_b_ccy=KRW, payout_ccy=KRW, m_a=0, m_b=0, service_charge=500 KRW. Test vector: target_payout=10000 KRW => collection_amount=10500 KRW. The /v1/rates response must omit USD pool fields (or return them as null/absent). POST /v1/payments must lock rates with IDENTITY sources and null USD pool columns. No prefunding ledger deduction must occur (LOCAL partner). | • Set up an integration test with in-memory or test-container DB; seed GME Remit partner (type=LOCAL) and the KRW/KRW/KRW/KRW rule with service_charge=500. • Call GET /v1/rates with partner_id=gme_remit, scheme=zeropay, direction=DOMESTIC, target_payout=10000, payout_ccy=KRW. • Assert response: collection_amount=10500, collection_usd=absent/null, payout_usd_cost=absent/null, offer_rate_coll=1.0 or absent, cross_rate=1.0 or absent, validUntil present. • Call POST /v1/payments with the returned txn_ref and a valid ZeroPay CPM/MPM payload; assert HTTP 200 and transaction state = COMPLETED (or SCHEME_CALLED per state machine). • Assert DB: collection_usd IS NULL, payout_usd_cost IS NULL, cost_rate_coll_source = IDENTITY, cost_rate_pay_source = IDENTITY, collection_amount = 10500, prefunding_deducted = false / no ledger row for this partner. | Integration test class RateSameCurrencyE2ETest covering full GET /rates + POST /payments flow for the domestic KRW short-circuit case. | • GET /v1/rates returns collection_amount=10500 KRW for target_payout=10000, service_charge=500. • GET /v1/rates response does not include collection_usd or payout_usd_cost fields (or returns them as null/absent per API contract). • POST /v1/payments completes without POOL_IDENTITY_FAILURE or INVALID_MARGIN errors. • DB record after commit: collection_usd IS NULL, cost_rate_coll_source = IDENTITY. • No prefunding ledger deduction is recorded for GME Remit (LOCAL partner type). | 50 | 4.5-T04, 4.5-T07, 4.5-T08, 4.5-T09 | BE | RATE-04
4.5-T11 | rate-fx | 4.5 | 4. Rate Engine & FX | Identity legs & same-currency short-circuit | 1 | Integration test: end-to-end dual-identity-leg cross-border transaction (HUB USD/USD) | WBS 4.5: verify that a HUB-direction USD-in / USD-out transaction (both identity legs) runs the full 5-step engine with cost_rate_coll=1.0, cost_rate_pay=1.0 (IDENTITY), non-zero margins, and USD pool fields populated. This is distinct from same-currency short-circuit — the USD pool IS computed, and m_a/m_b apply normally. Test vector from spec §7.1: OVERSEAS partner, target_payout=100.00 USD, m_a=0.01, m_b=0.01, service_charge=0.50 USD; expected collection_amount=102.5408 USD, collection_usd=102.0408, offer_rate_coll=1.01010, cross_rate=0.98000. Prefunding deduction must occur (OVERSEAS partner). | • Seed an OVERSEAS partner with USD settlement on both legs and a HUB rule: settle_a_ccy=USD, settle_b_ccy=USD, m_a=0.01, m_b=0.01, service_charge=0.50 USD, cost_rate_coll_source=IDENTITY, cost_rate_pay_source=IDENTITY. • Fund the partner prefunding balance with 200.00 USD. • Call GET /v1/rates with target_payout=100.00, payout_ccy=USD; assert collection_amount=102.5408, collection_usd=102.0408, offer_rate_coll=1.01010 (tolerance 0.00001), cross_rate=0.98000. • Call POST /v1/payments; assert transaction completes and prefunding balance is debited by 102.5408 USD. • Assert DB: collection_usd=102.0408, cost_rate_coll_source=IDENTITY, cost_rate_pay_source=IDENTITY; pool identity ¦collection_usd - collection_margin_usd - payout_margin_usd - payout_usd_cost¦ < 0.01. | Integration test class RateIdentityLegE2ETest covering GET /rates + POST /payments for a dual-IDENTITY-leg HUB cross-border case. | • GET /v1/rates returns collection_amount=102.5408 USD (tolerance 0.0001) and collection_usd=102.0408. • offer_rate_coll=1.01010 and cross_rate=0.98000 within 0.00001 tolerance. • Prefunding balance decremented by 102.5408 USD (not 100 USD). • DB: cost_rate_coll_source=IDENTITY, cost_rate_pay_source=IDENTITY, collection_usd IS NOT NULL. • Pool identity check in DB: ¦collection_usd - collection_margin_usd - payout_margin_usd - payout_usd_cost¦ < 0.01. | 50 | 4.5-T02, 4.5-T03, 4.5-T08 | BE | RATE-04
4.6-T01 | rate-fx | 4.6 | 4. Rate Engine & FX | Partner B authoritative quote & deviation | 1 | Define PartnerBQuoteClient interface and PartnerBQuoteResult value type | WBS 4.6: Partner B authoritative quote. When a scheme rule has rate_source_pay = PARTNER, the Rate Engine must call Partner B's quote API synchronously at both /rates time and /payments (commit) time. The interface must be mockable for unit tests. The response carries the quoted cost_rate_pay value (units of Settle B per 1 USD, e.g. 1350.00 KRW/USD) plus an optional quote_valid_until timestamp returned by Partner B. Errors are typed: PARTNER_B_QUOTE_UNAVAILABLE for any network/timeout failure, never a fallback. | • Create interface PartnerBQuoteClient with method: fetchQuote(schemeId: String, payoutAmount: BigDecimal, payoutCurrency: String): PartnerBQuoteResult • Define sealed result type PartnerBQuoteResult with two subtypes: PartnerBQuoteSuccess(costRatePay: BigDecimal, quoteValidUntil: Instant?) and PartnerBQuoteUnavailable(reason: String) • Place interface in package com.gmepay.rateengine.partnerbquote • Add Javadoc: fetchQuote is synchronous; callers must treat any exception as UNAVAILABLE; never returns null • Write a trivial stub implementation (StubPartnerBQuoteClient) that returns a configurable PartnerBQuoteSuccess for use in unit tests | Interface PartnerBQuoteClient + sealed result types PartnerBQuoteResult, PartnerBQuoteSuccess, PartnerBQuoteUnavailable + StubPartnerBQuoteClient in com.gmepay.rateengine.partnerbquote | • fetchQuote signature accepts schemeId (String), payoutAmount (BigDecimal), payoutCurrency (String) and returns PartnerBQuoteResult • PartnerBQuoteSuccess.costRatePay is BigDecimal (never double/float) • PartnerBQuoteUnavailable carries a non-null reason string • StubPartnerBQuoteClient can be configured to return either subtype; compiles and passes a trivial instantiation test • No dependency on HTTP client libraries in the interface itself (only in the impl) | 30 | 4.1, 4.2 | BE | RATE-04, API-05
4.6-T02 | rate-fx | 4.6 | 4. Rate Engine & FX | Partner B authoritative quote & deviation | 1 | Add partner_b_quote_enabled and partner_b_quote_deviation_pct to scheme config entity | WBS 4.6: Scheme-level config controls whether Partner B quote is active. Two fields already defined in DAT-03 schema: partner_b_quote_enabled BOOLEAN (default false) and partner_b_quote_deviation_pct DECIMAL(6,4) (default 0.0100 representing 1.0%). These fields live on the Scheme entity/table (same table that holds api_endpoint, api_credential_ref, sftp_host, etc.). The deviation_pct field stores the fractional tolerance: 0.0100 = 1.0%, 0.0050 = 0.5%. Config changes must log actor, timestamp, and previous value per audit rules. | • Add columns partner_b_quote_enabled BOOLEAN NOT NULL DEFAULT FALSE and partner_b_quote_deviation_pct DECIMAL(6,4) NOT NULL DEFAULT 0.0100 to the schemes table via a Flyway migration file V4_6_001__scheme_partner_b_quote_config.sql • Add the two fields to the Scheme JPA entity/domain object with appropriate types (boolean, BigDecimal) • Add validation: partner_b_quote_deviation_pct must be in range (0, 0.1000] (0% exclusive, 10% inclusive); reject at service layer with IllegalArgumentException if out of range • Ensure the Scheme config audit log captures old and new values for both fields when updated • Write a unit test: default values are 0.0100 and false; out-of-range 0.0000 and 0.1100 are rejected; 0.0050 is accepted | Flyway migration V4_6_001__scheme_partner_b_quote_config.sql + updated Scheme entity + validation + unit test SchemePartnerBQuoteConfigTest | • Migration applies cleanly; both columns present with correct defaults on a fresh schema • Scheme entity fields partner_b_quote_enabled and partner_b_quote_deviation_pct are correctly typed • Deviation 0.0100 (1.0%) is accepted; 0.0000 is rejected; 0.1100 is rejected; 0.0050 is accepted • Audit log records previous and new values of both fields when a Scheme is updated | 40 | 4.6-T01 | BE | RATE-04, API-05
4.6-T03 | rate-fx | 4.6 | 4. Rate Engine & FX | Partner B authoritative quote & deviation | 1 | Implement HTTP PartnerBQuoteClient with configurable timeout | WBS 4.6: The HTTP implementation calls Partner B's quote API. The scheme record has api_endpoint (e.g. https://partnerbscheme.example/quote) and api_credential_ref (vault reference). The call is synchronous (short-timeout per spec §7.5). Spec does not define a standard HTTP timeout value for PBQ; use a configurable property partner_b_quote_http_timeout_ms (default 3000 ms). Request: GET {api_endpoint}/rates?payout_amount={amount}&payout_currency={currency}. Response: JSON with field cost_rate_pay (numeric string) and optional quote_valid_until (ISO-8601 UTC). Any non-2xx, connection error, or elapsed timeout returns PartnerBQuoteUnavailable (no retry, no fallback). | • Create HttpPartnerBQuoteClient implementing PartnerBQuoteClient; inject scheme api_endpoint + resolved credential + timeout config • Configure HTTP client with connect-timeout = partner_b_quote_http_timeout_ms and read-timeout = partner_b_quote_http_timeout_ms (property, default 3000 ms) • Parse JSON response: extract cost_rate_pay as BigDecimal; parse optional quote_valid_until as Instant; return PartnerBQuoteSuccess • On any IOException, SocketTimeoutException, non-2xx status, or JSON parse error: log WARN with scheme_id and return PartnerBQuoteUnavailable(reason) • Add Spring @ConfigurationProperties class PartnerBQuoteProperties with field httpTimeoutMs (int, default 3000) | HttpPartnerBQuoteClient + PartnerBQuoteProperties in com.gmepay.rateengine.partnerbquote.http | • HttpTimeoutMs defaults to 3000; can be overridden via application.properties partner_b_quote.http_timeout_ms • cost_rate_pay parsed as BigDecimal (not double); value 1350.00 from JSON produces BigDecimal(1350.00) • SocketTimeoutException produces PartnerBQuoteUnavailable, not a thrown exception • Non-2xx HTTP 503 produces PartnerBQuoteUnavailable with non-empty reason string • quote_valid_until absent in JSON produces PartnerBQuoteSuccess with quoteValidUntil = null (no NPE) | 50 | 4.6-T01, 4.6-T02 | BE | RATE-04, API-05
4.6-T04 | rate-fx | 4.6 | 4. Rate Engine & FX | Partner B authoritative quote & deviation | 1 | Integrate PartnerBQuoteClient into Rate Engine quote-time path | WBS 4.6: At /rates request time, if the rule has rate_source_pay = PARTNER (and scheme.partner_b_quote_enabled = true), the Rate Engine must call PartnerBQuoteClient.fetchQuote(schemeId, targetPayout, payoutCurrency) instead of reading treasury.usd_{settle_b_ccy} for cost_rate_pay. The returned costRatePay value is used in Step 1 of the 5-step USD pool: payout_usd_cost = target_payout / cost_rate_pay. The RateQuote snapshot must record cost_rate_pay_source = PARTNER and the raw quote value. If PartnerBQuoteUnavailable is returned, the Rate Engine immediately returns PARTNER_B_QUOTE_UNAVAILABLE to the caller (no treasury fallback, no partial quote). | • In RateEngineService.computeRateQuote, after resolving the Rule, check if rate_source_pay == PARTNER • If PARTNER: call partnerBQuoteClient.fetchQuote(schemeId, targetPayout, payoutCurrency); if result is PartnerBQuoteUnavailable return error PARTNER_B_QUOTE_UNAVAILABLE immediately • If PartnerBQuoteSuccess: use costRatePay as cost_rate_pay for Step 1; record cost_rate_pay_source = PARTNER in the RateQuote object • Also record partner_b_quote_value (the raw quote) and partner_b_quote_valid_until on the RateQuote for later deviation check • Ensure RateQuote now carries fields: cost_rate_pay_source (enum IDENTITY/LIVE/MANUAL/PARTNER), partner_b_quote_value (BigDecimal nullable), partner_b_quote_valid_until (Instant nullable) | Updated RateEngineService.computeRateQuote integration branch for PARTNER source + extended RateQuote value object | • When rate_source_pay = PARTNER and client returns PartnerBQuoteSuccess(1350.00), RateQuote.cost_rate_pay = 1350.00 and cost_rate_pay_source = PARTNER • When rate_source_pay = PARTNER and client returns PartnerBQuoteUnavailable, method returns error PARTNER_B_QUOTE_UNAVAILABLE without proceeding to USD pool steps • When rate_source_pay != PARTNER, partnerBQuoteClient.fetchQuote is never called • RateQuote.partner_b_quote_value = 1350.00 is persisted in cache for later deviation check at commit time • No treasury lookup for cost_rate_pay occurs when rate_source_pay = PARTNER | 45 | 4.6-T01, 4.6-T02, 4.6-T03 | BE | RATE-04, API-05
4.6-T05 | rate-fx | 4.6 | 4. Rate Engine & FX | Partner B authoritative quote & deviation | 1 | Implement Partner B quote deviation check at commit time | WBS 4.6: At POST /v1/payments (commit) time, if RateQuote.cost_rate_pay_source == PARTNER, the Rate Engine calls PartnerBQuoteClient.fetchQuote again to get the current quote. Deviation formula: deviation = ¦commit_quote - rates_quote¦ / rates_quote. If deviation > partner_b_quote_deviation_pct (default 0.0100 = 1.0%), raise PARTNER_B_QUOTE_DEVIATION and do NOT commit. If client returns PartnerBQuoteUnavailable, raise PARTNER_B_QUOTE_UNAVAILABLE and do NOT commit. No fallback in either case. RV-05 (spec): rates_quote=1350.00, commit_quote=1360.80 => deviation=0.008=0.80% < 1.0% => COMMIT. RV-06: rates_quote=1350.00, commit_quote=1366.20 => deviation=0.012=1.2% > 1.0% => DEVIATION error. | • In TransactionOrchestrator.commitTransaction (or RateEngineService.onCommit), after expiry check, check if rateQuote.cost_rate_pay_source == PARTNER • Call partnerBQuoteClient.fetchQuote(schemeId, targetPayout, payoutCurrency); if PartnerBQuoteUnavailable, throw RateEngineException(PARTNER_B_QUOTE_UNAVAILABLE) without touching DB • If PartnerBQuoteSuccess: compute deviation = abs(commitQuote - ratesQuote) / ratesQuote using BigDecimal arithmetic • Load tolerance = scheme.partner_b_quote_deviation_pct; if deviation > tolerance throw RateEngineException(PARTNER_B_QUOTE_DEVIATION) without touching DB • If deviation <= tolerance: update transaction.cost_rate_pay = commitQuote, cost_rate_pay_source = PARTNER, and proceed to rate-lock commit | Deviation check logic in TransactionOrchestrator.commitTransaction + RateEngineException with typed error codes | • RV-05: rates_quote=1350.00, commit_quote=1360.80, tolerance=0.0100 => deviation=0.008 => transaction commits; recorded cost_rate_pay=1360.80 • RV-06: rates_quote=1350.00, commit_quote=1366.20, tolerance=0.0100 => deviation=0.012 => throws PARTNER_B_QUOTE_DEVIATION; no DB write occurs • Commit-time PartnerBQuoteUnavailable => throws PARTNER_B_QUOTE_UNAVAILABLE; no DB write occurs • Boundary: deviation exactly = tolerance (e.g. exactly 0.0100 with rates_quote=1350.00, commit_quote=1363.50) => commits (deviation not strictly greater than tolerance) • When cost_rate_pay_source != PARTNER, no second fetchQuote call is made at commit time | 50 | 4.6-T04 | BE | RATE-04, API-05
4.6-T06 | rate-fx | 4.6 | 4. Rate Engine & FX | Partner B authoritative quote & deviation | 1 | Enforce no-fallback invariant: block any treasury cost_rate_pay path when source = PARTNER | WBS 4.6: Spec is explicit: if Partner B API is unreachable, there is NO fallback to treasury rates. The code must have no code path that substitutes treasury.usd_{settle_b_ccy} when rate_source_pay = PARTNER and the PBQ client fails. This ticket adds a guard assertion in RateEngineService to make the no-fallback invariant explicit and testable. Also verifies that treasury.getCostRate(settle_b_ccy) is never called when rate_source_pay = PARTNER. | • In the PARTNER branch of RateEngineService.computeRateQuote, add an explicit guard: after the UNAVAILABLE early return, assert that cost_rate_pay was NOT sourced from treasury (i.e., do not invoke treasury lookup for settle_b at all in this branch) • Add a test with a mock TreasuryService that throws AssertionError if getCostRate is called for settle_b_ccy when rate_source_pay = PARTNER • Verify the same invariant at commit time: if rate_source_pay = PARTNER and PBQ unavailable, cost_rate_pay from the stored quote is never used as fallback • Add a log.error entry at CRITICAL level when PARTNER_B_QUOTE_UNAVAILABLE is returned, including scheme_id and timestamp (for ops monitoring) • Document the no-fallback rule in a brief code comment co-located with the PARTNER branch | No-fallback guard assertion + test NoFallbackInvariantTest verifying treasury is never consulted for pay-leg when source = PARTNER | • Test NoFallbackInvariantTest: TreasuryService.getCostRate(settle_b_ccy) is never called when rate_source_pay = PARTNER (mock verifies zero interactions on that method) • PARTNER_B_QUOTE_UNAVAILABLE at /rates time: no treasury substitution; error returned immediately • PARTNER_B_QUOTE_UNAVAILABLE at commit time: no treasury substitution; no DB write; error returned immediately • CRITICAL log entry emitted on UNAVAILABLE with scheme_id present in log fields | 35 | 4.6-T05 | BE | RATE-04, API-05
4.6-T07 | rate-fx | 4.6 | 4. Rate Engine & FX | Partner B authoritative quote & deviation | 1 | Bound RateQuote validUntil by Partner B quote_valid_until timestamp | WBS 4.6: Spec §9.1 states: for transactions with a Partner B authoritative quote, validUntil is also bounded by Partner B's quote validity timestamp (whichever is earlier). RateQuote.valid_until = min(quote_issued_at + rate_quote_ttl_seconds, partnerBQuote.quoteValidUntil). If partnerBQuote.quoteValidUntil is null (Partner B did not return an expiry), use only the GMEPay+ TTL. The RateQuoteResponse returned to the partner must reflect the tighter bound so the partner knows the true commit deadline. | • In RateEngineService after computing valid_until = quote_issued_at + ttl_seconds, check if rateQuote.partner_b_quote_valid_until is non-null • If non-null: valid_until = min(computed_valid_until, partner_b_quote_valid_until) using Instant comparison • Set rateQuote.valid_until to the result and surface it in RateQuoteResponse.validUntil (ISO-8601 UTC string) • Write unit test: TTL-based expiry = T+300s, partnerB expiry = T+120s => validUntil = T+120s • Write unit test: TTL-based expiry = T+300s, partnerB expiry = null => validUntil = T+300s | Updated valid_until assignment in RateEngineService + unit tests PartnerBValidUntilBoundTest | • When partnerB quoteValidUntil = T+120s and TTL expiry = T+300s, RateQuoteResponse.validUntil = T+120s • When partnerB quoteValidUntil = T+600s and TTL expiry = T+300s, RateQuoteResponse.validUntil = T+300s • When partnerB quoteValidUntil = null, validUntil = quote_issued_at + rate_quote_ttl_seconds unchanged • validUntil in API response is ISO-8601 UTC (ends with Z); no local-time zone applied | 30 | 4.6-T04 | BE | RATE-04, API-05
4.6-T08 | rate-fx | 4.6 | 4. Rate Engine & FX | Partner B authoritative quote & deviation | 1 | Persist cost_rate_pay_source = PARTNER on committed transaction record | WBS 4.6: Rate-lock spec (§9 and pseudocode) requires all USD-pool values and derived rates to be permanently recorded on commit. For Partner B transactions the recorded cost_rate_pay = the commit-time Partner B quote value (not the /rates-time quote), and cost_rate_pay_source = PARTNER must be stored so the audit trail and BOK reporting can identify the source. Depends on 4.6-T05 which already updates cost_rate_pay at commit time. This ticket ensures the source enum column exists in the transactions table and is written correctly. | • Add Flyway migration V4_6_002__txn_cost_rate_pay_source.sql: add column cost_rate_pay_source VARCHAR(10) NULL to transactions table (values: IDENTITY, LIVE, MANUAL, PARTNER) • Add field to Transaction entity/domain object; populate from RateQuote.cost_rate_pay_source at commit time • Ensure existing IDENTITY-path transactions set cost_rate_pay_source = IDENTITY on commit (backward-compatible default) • Write integration test: commit a PARTNER-source transaction; assert transactions.cost_rate_pay_source = PARTNER and cost_rate_pay = commit-time quote value • Confirm the column is excluded from partner-facing API response fields (internal field per spec §8.3) | Migration V4_6_002__txn_cost_rate_pay_source.sql + updated Transaction entity + integration test CostRatePaySourcePersistenceTest | • After PARTNER-source commit with commit_quote=1360.80: transactions.cost_rate_pay=1360.80 and transactions.cost_rate_pay_source=PARTNER • After IDENTITY-source commit: transactions.cost_rate_pay_source=IDENTITY • cost_rate_pay_source column not present in any partner-facing /payments or /rates response payload • Migration is idempotent (re-run safe via Flyway checksum) | 40 | 4.6-T05 | BE | RATE-04, API-05
4.6-T09 | rate-fx | 4.6 | 4. Rate Engine & FX | Partner B authoritative quote & deviation | 1 | Unit tests: PartnerBQuoteClient mock — within-tolerance commit succeeds (RV-05) | WBS 4.6 test ticket. Spec test vector RV-05: target_payout=13500 KRW, cost_rate_coll=3500.00 MNT/USD, rates_time cost_rate_pay=1350.00 KRW/USD (PARTNER), m_a=0.015, m_b=0.010, service_charge=500 MNT. At commit, Partner B returns 1360.80 (deviation=¦1360.80-1350.00¦/1350.00=0.008=0.8%, within 1.0% tolerance). Expected: transaction commits; recorded cost_rate_pay=1360.80; cost_rate_pay_source=PARTNER. Rate engine intermediate values: payout_usd_cost=13500/1360.80=9.9206 USD; collection_usd=9.9206/(1-0.025)=10.1750 USD; collection_margin_usd=10.1750*0.015=0.1526 USD; payout_margin_usd=10.1750*0.010=0.1018 USD; pool identity: 10.1750-0.1526-0.1018=9.9206 (within 0.01 USD). | • Create test class PartnerBQuoteRV05Test using StubPartnerBQuoteClient • Configure stub: /rates call returns PartnerBQuoteSuccess(1350.00); commit call returns PartnerBQuoteSuccess(1360.80) • Invoke RateEngineService.computeRateQuote with the RV-05 inputs; assert all intermediate USD-pool values • Invoke TransactionOrchestrator.commitTransaction; assert no exception thrown • Assert transaction.cost_rate_pay=1360.80, cost_rate_pay_source=PARTNER, transaction is in COMMITTED state | Test class PartnerBQuoteRV05Test (unit, mocked client) | • computeRateQuote succeeds with rates_quote=1350.00; rateQuote.partner_b_quote_value=1350.00 • commitTransaction succeeds with commit_quote=1360.80; no DEVIATION exception • Recorded cost_rate_pay=1360.80 (BigDecimal.compareTo == 0) • Pool identity assertion: ¦collection_usd - collection_margin_usd - payout_margin_usd - payout_usd_cost¦ <= 0.01 USD • cost_rate_pay_source field = PARTNER on committed record | 35 | 4.6-T05, 4.6-T08 | BE | RATE-04, API-05
4.6-T10 | rate-fx | 4.6 | 4. Rate Engine & FX | Partner B authoritative quote & deviation | 1 | Unit tests: PartnerBQuoteClient mock — over-tolerance commit raises DEVIATION, no commit (RV-06) | WBS 4.6 test ticket. Spec test vector RV-06: same inputs as RV-05 except commit-time Partner B quote=1366.20. deviation=¦1366.20-1350.00¦/1350.00=0.012=1.2% which exceeds 1.0% tolerance. Expected: PARTNER_B_QUOTE_DEVIATION returned; transaction NOT committed; no prefunding deduction; no DB write. The test must verify that the transaction state remains unchanged (e.g. PENDING, not COMMITTED). | • Create test class PartnerBQuoteRV06Test using StubPartnerBQuoteClient • Configure stub: /rates call returns PartnerBQuoteSuccess(1350.00); commit call returns PartnerBQuoteSuccess(1366.20) • Invoke computeRateQuote (should succeed); capture rateQuote • Invoke commitTransaction; assert RateEngineException with code PARTNER_B_QUOTE_DEVIATION is thrown • Assert: no DB write to transactions table; prefunding balance unchanged; transaction state != COMMITTED | Test class PartnerBQuoteRV06Test (unit, mocked client) | • commitTransaction throws RateEngineException with errorCode = PARTNER_B_QUOTE_DEVIATION • Transaction record is NOT written / state != COMMITTED • Prefunding deduction NOT triggered (verify mock PrefundingService.deduct never called) • Deviation math: ¦1366.20 - 1350.00¦ / 1350.00 = 0.012 asserted in test comments • Boundary case: commit_quote=1363.50 => deviation=0.01000 exactly => commits (not strictly greater than tolerance) | 35 | 4.6-T05, 4.6-T08 | BE | RATE-04, API-05
4.6-T11 | rate-fx | 4.6 | 4. Rate Engine & FX | Partner B authoritative quote & deviation | 1 | Unit tests: PartnerBQuoteClient mock — timeout at /rates time raises UNAVAILABLE, no quote issued | WBS 4.6 test ticket. Spec: if Partner B quote API is unreachable at /rates time, return PARTNER_B_QUOTE_UNAVAILABLE; no fallback; no RateQuote issued. Test: stub configured to return PartnerBQuoteUnavailable at /rates time. Expected: computeRateQuote returns PARTNER_B_QUOTE_UNAVAILABLE immediately; no USD pool computation performed; TreasuryService.getCostRate(settle_b_ccy) never called; no quote persisted in cache. | • Create test class PartnerBQuoteUnavailableAtRatesTimeTest using StubPartnerBQuoteClient • Configure stub: fetchQuote always returns PartnerBQuoteUnavailable('connection timeout') • Invoke computeRateQuote; assert RateEngineException with code PARTNER_B_QUOTE_UNAVAILABLE • Verify mock TreasuryService.getCostRate was NOT called for settle_b_ccy (Mockito verify zero interactions) • Verify no RateQuote object was stored in Redis cache (mock CacheService.store never called) | Test class PartnerBQuoteUnavailableAtRatesTimeTest (unit, mocked client) | • computeRateQuote throws RateEngineException with code PARTNER_B_QUOTE_UNAVAILABLE • TreasuryService.getCostRate not called for settle_b_ccy (no fallback) • No quote stored in cache • CRITICAL log message emitted with scheme_id • Exception propagates to API gateway which maps it to HTTP 503 with error code PARTNER_B_QUOTE_UNAVAILABLE | 30 | 4.6-T06 | BE | RATE-04, API-05
4.6-T12 | rate-fx | 4.6 | 4. Rate Engine & FX | Partner B authoritative quote & deviation | 1 | Unit tests: PartnerBQuoteClient mock — timeout at commit time raises UNAVAILABLE, no commit | WBS 4.6 test ticket. Spec: if Partner B quote API is unreachable at commit time (/payments), return PARTNER_B_QUOTE_UNAVAILABLE; no commit; no prefunding deduction. Test: /rates succeeds with PartnerBQuoteSuccess(1350.00); commit-time call returns PartnerBQuoteUnavailable. Expected: commitTransaction raises PARTNER_B_QUOTE_UNAVAILABLE; transaction not written; prefunding balance unchanged. | • Create test class PartnerBQuoteUnavailableAtCommitTimeTest using StubPartnerBQuoteClient • Configure stub: first fetchQuote call (rates time) returns PartnerBQuoteSuccess(1350.00); second call (commit time) returns PartnerBQuoteUnavailable('read timeout') • Invoke computeRateQuote (succeeds); invoke commitTransaction • Assert RateEngineException with code PARTNER_B_QUOTE_UNAVAILABLE from commitTransaction • Assert: no DB write; PrefundingService.deduct never called; transaction state != COMMITTED | Test class PartnerBQuoteUnavailableAtCommitTimeTest (unit, mocked client) | • commitTransaction throws RateEngineException with errorCode = PARTNER_B_QUOTE_UNAVAILABLE • No prefunding deduction (mock PrefundingService.deduct called zero times) • Transaction NOT written to DB • rates-time quote itself was valid; only commit-time call failed • StubPartnerBQuoteClient returns different values for sequential calls (rates vs commit) | 30 | 4.6-T05, 4.6-T06 | BE | RATE-04, API-05
4.6-T13 | rate-fx | 4.6 | 4. Rate Engine & FX | Partner B authoritative quote & deviation | 1 | Map PARTNER_B_QUOTE_DEVIATION and PARTNER_B_QUOTE_UNAVAILABLE to API error response codes | WBS 4.6 / API-05: Both errors must be surfaced to Partner A via the standard error response envelope. Per spec error catalog: PARTNER_B_QUOTE_DEVIATION = HTTP 422 (commit-time quote deviated beyond tolerance, retry from POST /v1/rates); PARTNER_B_QUOTE_UNAVAILABLE = HTTP 503 (Partner B API unreachable, retry after delay). The error response body must include: error_code (string), message (human-readable), and must NOT include internal fields (m_a, m_b, cost_rate_coll, cost_rate_pay, partner_b_quote_value). These codes appear in responses to both POST /v1/rates and POST /v1/payments. | • In the API gateway error-mapping layer, add cases for RateEngineException(PARTNER_B_QUOTE_DEVIATION) => HTTP 422 body {error_code: PARTNER_B_QUOTE_DEVIATION, message: 'Partner B commit-time quote deviated beyond configured tolerance. Re-quote and retry.'} • Add case for RateEngineException(PARTNER_B_QUOTE_UNAVAILABLE) => HTTP 503 body {error_code: PARTNER_B_QUOTE_UNAVAILABLE, message: 'Partner B quote API unreachable. Retry after delay.'} • Ensure no internal fields (cost_rate_pay, partner_b_quote_value, m_a, m_b) leak into the error response body • Write a controller-layer test asserting the HTTP status codes and error_code strings • Confirm the two codes appear in the OpenAPI spec / error catalog for API-05 | Error mapping entries in API gateway layer + controller tests ApiErrorMappingPartnerBTest | • PARTNER_B_QUOTE_DEVIATION => HTTP 422; response body contains error_code = PARTNER_B_QUOTE_DEVIATION • PARTNER_B_QUOTE_UNAVAILABLE => HTTP 503; response body contains error_code = PARTNER_B_QUOTE_UNAVAILABLE • Error response body does NOT contain any of: cost_rate_pay, partner_b_quote_value, m_a, m_b • Both errors can occur on both POST /v1/rates and POST /v1/payments endpoints • Error message is human-readable and references retry action | 35 | 4.6-T05, 4.6-T06 | BE | RATE-04, API-05
4.6-T14 | rate-fx | 4.6 | 4. Rate Engine & FX | Partner B authoritative quote & deviation | 1 | Wire PartnerBQuoteClient bean via Spring config, guarded by partner_b_quote_enabled flag | WBS 4.6: HttpPartnerBQuoteClient must be registered as a Spring bean and injected into RateEngineService. The client should only be invoked when scheme.partner_b_quote_enabled = true AND rule.rate_source_pay = PARTNER. If partner_b_quote_enabled = false on the scheme, the PARTNER rate_source_pay config is invalid and should be rejected at rule-save time (configuration guard, not runtime). A NoOpPartnerBQuoteClient that always returns UNAVAILABLE should be registered as a fallback bean for safety in environments where the HTTP impl is disabled. | • Create Spring @Configuration class PartnerBQuoteClientConfig that registers HttpPartnerBQuoteClient as primary bean with properties injected from PartnerBQuoteProperties • Register NoOpPartnerBQuoteClient (always returns UNAVAILABLE) as @ConditionalOnMissingBean fallback • In RuleValidationService, add check: if rate_source_pay = PARTNER and scheme.partner_b_quote_enabled = false, reject with validation error 'Partner B quote not enabled for this scheme' • Write test: saving a rule with rate_source_pay=PARTNER on a scheme with partner_b_quote_enabled=false is rejected at config time • Write test: saving a rule with rate_source_pay=PARTNER on a scheme with partner_b_quote_enabled=true is accepted | PartnerBQuoteClientConfig Spring config + NoOpPartnerBQuoteClient + RuleValidationService guard + tests PartnerBQuoteWiringTest | • HttpPartnerBQuoteClient bean is registered and injectable in Spring context • Rule creation with rate_source_pay=PARTNER and partner_b_quote_enabled=false fails with validation error at save time • Rule creation with rate_source_pay=PARTNER and partner_b_quote_enabled=true succeeds • NoOpPartnerBQuoteClient is never reached in normal runtime (only if HttpPartnerBQuoteClient bean missing) • PartnerBQuoteProperties.httpTimeoutMs is read from application.properties correctly | 40 | 4.6-T03, 4.6-T04 | BE | RATE-04, API-05
4.6-T15 | rate-fx | 4.6 | 4. Rate Engine & FX | Partner B authoritative quote & deviation | 1 | Integration smoke test: end-to-end PARTNER-source rate quote and commit with mocked Partner B HTTP server | WBS 4.6 final integration test. Brings together all sub-components: scheme config (partner_b_quote_enabled=true, deviation_pct=0.0100), rule (rate_source_pay=PARTNER), HttpPartnerBQuoteClient pointing at a WireMock server, Rate Engine, and TransactionOrchestrator. Test must cover: (a) successful commit with within-tolerance drift; (b) DEVIATION rejection; (c) UNAVAILABLE at commit. Uses the RV-05/RV-06 vectors. Verifies the complete path: POST /v1/rates => PBQ call => RateQuote stored => POST /v1/payments => second PBQ call => deviation check => commit or error. | • Set up WireMock server stubbing GET /rates for Partner B; configure three stub scenarios: success-1350, success-1360.80, success-1366.20, and connection-refused • Configure test scheme + rule with partner_b_quote_enabled=true, rate_source_pay=PARTNER, deviation_pct=0.0100 • Scenario A: rates stub=1350.00, commit stub=1360.80 => assert HTTP 200 on /payments, transaction COMMITTED, cost_rate_pay=1360.80 • Scenario B: rates stub=1350.00, commit stub=1366.20 => assert HTTP 422 PARTNER_B_QUOTE_DEVIATION on /payments, no DB row • Scenario C: rates stub=1350.00, commit stub=connection-refused => assert HTTP 503 PARTNER_B_QUOTE_UNAVAILABLE on /payments, no DB row | Integration test class PartnerBQuoteEndToEndIT (WireMock-backed, Spring Boot test slice) | • Scenario A: transaction committed, HTTP 200, cost_rate_pay=1360.80 in DB • Scenario B: HTTP 422, error_code=PARTNER_B_QUOTE_DEVIATION, no transaction row in DB • Scenario C: HTTP 503, error_code=PARTNER_B_QUOTE_UNAVAILABLE, no transaction row in DB • WireMock verifies exactly 2 calls to Partner B quote endpoint per commit attempt (1 at /rates, 1 at /payments) • Pool identity assertion passes for Scenario A (¦collection_usd - margins - payout_usd_cost¦ <= 0.01 USD) | 55 | 4.6-T09, 4.6-T10, 4.6-T11, 4.6-T12, 4.6-T13, 4.6-T14 | BE | RATE-04, API-05
4.7-T01 | rate-fx | 4.7 | 4. Rate Engine & FX | Rate quote lifecycle, TTL & rate-lock | 1 | DB migration: create rate_quote table with all pool and TTL columns | WBS 4.7 — Rate quote lifecycle. The rate_quote table captures every output of the rate engine at GET /v1/rates or CPM generate time. Columns required: id BIGINT PK, quote_ref VARCHAR(64) UNIQUE, rule_id FK->rule, partner_id FK->partner, scheme_id FK->qr_scheme, direction VARCHAR(10), payment_mode VARCHAR(5), target_payout DECIMAL(20,4), payout_ccy CHAR(3), payout_usd_cost DECIMAL(20,8) NULL, collection_usd DECIMAL(20,8) NULL, collection_margin_usd DECIMAL(20,8) NULL, payout_margin_usd DECIMAL(20,8) NULL, send_amount DECIMAL(20,4), send_amount_ccy CHAR(3), service_charge DECIMAL(20,4), service_charge_ccy CHAR(3), collection_amount DECIMAL(20,4), collection_ccy CHAR(3), offer_rate_coll DECIMAL(20,8) NULL, cross_rate DECIMAL(20,8) NULL, cost_rate_coll DECIMAL(20,8), cost_rate_pay DECIMAL(20,8), treasury_rate_id_coll BIGINT FK->treasury_rate, treasury_rate_id_pay BIGINT FK->treasury_rate, ttl_seconds INT NOT NULL, quote_issued_at TIMESTAMPTZ NOT NULL, valid_until TIMESTAMPTZ NOT NULL, is_used BOOLEAN NOT NULL DEFAULT FALSE, created_at TIMESTAMPTZ, updated_at TIMESTAMPTZ. USD-pool columns are NULL for same-currency short-circuit transactions. is_used is set TRUE when a transaction commits using this quote. | • Create a Flyway/Liquibase migration file V4_7_001__create_rate_quote.sql • Add all columns per the schema above with correct types and NULL constraints • Add FK constraints to rule, partner, qr_scheme, treasury_rate tables • Add index on quote_ref (unique), composite index on (partner_id, quote_issued_at), index on valid_until for TTL expiry sweeps • Add CHECK constraint: valid_until = quote_issued_at + ttl_seconds * INTERVAL 1 second is implied by app logic; add CHECK ttl_seconds BETWEEN 60 AND 1800 | Migration file V4_7_001__create_rate_quote.sql that applies cleanly on a fresh schema after 4.2 and 4.4 migrations | • Migration applies without error on a clean DB; all columns exist with correct types • UNIQUE constraint on quote_ref rejects duplicate inserts • FK to rule, partner, qr_scheme, treasury_rate enforced • ttl_seconds column has CHECK constraint: ttl_seconds >= 60 AND ttl_seconds <= 1800 • valid_until index exists for efficient expiry sweeps (EXPLAIN shows index scan on WHERE valid_until < NOW()) | 30 | 4.2, 4.4 | BE | RATE-04
4.7-T02 | rate-fx | 4.7 | 4. Rate Engine & FX | Rate quote lifecycle, TTL & rate-lock | 1 | DB migration: add locked rate columns to transaction table | WBS 4.7 — Rate lock. At CommitTransaction all USD-pool values and derived rates must be copied from rate_quote onto the transaction record and become immutable. The transaction table already exists (from WBS 4.4). Add columns: rate_quote_id BIGINT FK->rate_quote, payout_usd_cost DECIMAL(20,8) NULL, collection_usd DECIMAL(20,8) NULL, collection_margin_usd DECIMAL(20,8) NULL, payout_margin_usd DECIMAL(20,8) NULL, send_amount DECIMAL(20,4), service_charge DECIMAL(20,4), collection_amount DECIMAL(20,4), offer_rate_coll DECIMAL(20,8) NULL, cross_rate DECIMAL(20,8) NULL, cost_rate_coll DECIMAL(20,8), cost_rate_pay DECIMAL(20,8), quote_issued_at TIMESTAMPTZ, valid_until TIMESTAMPTZ, committed_at TIMESTAMPTZ, is_same_ccy_shortcircuit BOOLEAN. These columns must be immutable after commit — enforced at application layer (no UPDATE on locked columns post-commit) and by DB trigger in this ticket. | • Create migration file V4_7_002__add_rate_lock_columns_to_transaction.sql • Add all locked-rate columns with NULL allowed (pre-commit rows do not have them set yet) • Add FK rate_quote_id -> rate_quote • Create a PostgreSQL trigger function that raises EXCEPTION if an UPDATE attempts to change any of the 15 locked columns when committed_at IS NOT NULL • Attach trigger BEFORE UPDATE ON transaction FOR EACH ROW | Migration file V4_7_002__add_rate_lock_columns_to_transaction.sql including trigger definition | • All 15 locked columns are present after migration • FK rate_quote_id -> rate_quote enforced • UPDATE of cost_rate_coll on a row where committed_at IS NOT NULL raises an exception • UPDATE of collection_amount on a pre-commit row (committed_at IS NULL) succeeds • EXPLAIN shows FK index on rate_quote_id | 35 | 4.7-T01 | BE | RATE-04
4.7-T03 | rate-fx | 4.7 | 4. Rate Engine & FX | Rate quote lifecycle, TTL & rate-lock | 1 | Implement TTL resolution service: resolve ttl_seconds from rule/partner config | WBS 4.7 — TTL resolution. The TTL to apply to a rate quote is resolved as follows: if the rule is aggregator-bound (partner.is_aggregator_bound = TRUE), default is 60s; otherwise default is 300s. The resolved default is then overridden by partner.rate_quote_ttl_seconds if that field is non-null, and finally clamped to [60, 1800]. Partner.rate_quote_ttl_seconds is stored in the partner table (INT, default 300, range 60-1800). The partner table does not have is_aggregator_bound yet — add it in this ticket (BOOLEAN NOT NULL DEFAULT FALSE). Formula: base = (partner.is_aggregator_bound ? 60 : 300); ttl = clamp(partner.rate_quote_ttl_seconds ?? base, 60, 1800). | • Add column is_aggregator_bound BOOLEAN NOT NULL DEFAULT FALSE to partner table in migration V4_7_003__add_aggregator_flag.sql • Implement TtlResolutionService.resolve(Partner partner) in the rate engine module • Logic: base = partner.isAggregatorBound() ? 60 : 300; configured = partner.getRateQuoteTtlSeconds() != null ? partner.getRateQuoteTtlSeconds() : base; return Math.max(60, Math.min(1800, configured)) • Add unit tests covering: aggregator-bound partner gets 60s default; non-aggregator gets 300s default; explicit 120s config returns 120; value below 60 clamps to 60; value above 1800 clamps to 1800 | TtlResolutionService class + unit tests + migration V4_7_003__add_aggregator_flag.sql | • aggregator-bound partner with null rate_quote_ttl_seconds returns ttl=60 • non-aggregator partner with null rate_quote_ttl_seconds returns ttl=300 • partner with rate_quote_ttl_seconds=120 returns ttl=120 regardless of aggregator flag • partner with rate_quote_ttl_seconds=30 returns ttl=60 (clamped to minimum) • partner with rate_quote_ttl_seconds=3600 returns ttl=1800 (clamped to maximum) | 30 | 4.7-T01 | BE | RATE-04
4.7-T04 | rate-fx | 4.7 | 4. Rate Engine & FX | Rate quote lifecycle, TTL & rate-lock | 1 | Implement RateQuote domain entity and RateQuoteRepository | WBS 4.7 — Quote entity. Define the RateQuote Java entity mapping to the rate_quote table (WBS 4.7-T01). Fields mirror the DB columns exactly. Key computed invariant: validUntil = quoteIssuedAt + ttlSeconds seconds. The entity must expose isExpired(Instant now) = now.isAfter(validUntil). Repository must support: save(RateQuote), findByQuoteRef(String quoteRef), markUsed(Long id). All DECIMAL fields must use java.math.BigDecimal. Timestamps use java.time.Instant stored as TIMESTAMPTZ. | • Create RateQuote.java JPA entity with all fields mapped to rate_quote columns • Ensure validUntil is set in the entity factory method: validUntil = quoteIssuedAt.plusSeconds(ttlSeconds) • Implement isExpired(Instant now) returning now.isAfter(validUntil) • Create RateQuoteRepository (Spring Data JPA or JOOQ): save, findByQuoteRef, markUsed (SET is_used=TRUE) • Add unit tests: entity construction sets validUntil correctly; isExpired returns false at quoteIssuedAt+ttl-1s; isExpired returns true at quoteIssuedAt+ttl+1s | RateQuote.java entity, RateQuoteRepository.java interface, unit tests for isExpired boundary | • RateQuote created with quoteIssuedAt=T and ttlSeconds=60 has validUntil=T+60s • isExpired(T+59s) returns false • isExpired(T+60s) returns true (expired AT the boundary) • isExpired(T+61s) returns true • findByQuoteRef returns empty Optional for unknown ref • markUsed sets is_used=TRUE in DB | 45 | 4.7-T01 | BE | RATE-04
4.7-T05 | rate-fx | 4.7 | 4. Rate Engine & FX | Rate quote lifecycle, TTL & rate-lock | 1 | Implement issueQuote function: persist rate quote with computed validUntil | WBS 4.7 — Issue quote. The issueQuote function accepts the output of the rate engine (RateEngineResult containing all 5-step pool values, derived rates, cost rates, treasury rate IDs, rule_id, partner_id, scheme_id, direction, payment_mode, target_payout, payout_ccy) plus the resolved ttl_seconds (from TtlResolutionService 4.7-T03). It must: generate a quote_ref (UUID), set quote_issued_at = clock.now() (UTC), compute valid_until = quote_issued_at + ttl_seconds, build a RateQuote entity, persist it, and return RateQuoteResponse containing quote_ref, offer_rate_coll, send_amount, service_charge, collection_amount, collection_usd, payout_usd_cost, validUntil (ISO-8601 UTC string). For same-currency short-circuit transactions, USD pool fields are NULL. Store in Redis with key rate_quote:{quote_ref} TTL=ttl_seconds. | • Implement QuoteService.issueQuote(RateEngineResult result, int ttlSeconds) in the rate engine module • Generate UUID for quote_ref • Set quote_issued_at = Instant.now(clock), valid_until = quote_issued_at.plusSeconds(ttlSeconds) • Persist RateQuote via RateQuoteRepository.save() • Write quote to Redis: key=rate_quote:{quote_ref}, value=serialized RateQuote JSON, TTL=ttlSeconds • Return RateQuoteResponse with validUntil formatted as ISO-8601 UTC | QuoteService.issueQuote() method with Redis cache write + unit tests | • Returned validUntil equals quote_issued_at + ttl_seconds to the second • Redis key rate_quote:{quote_ref} exists and expires after ttl_seconds • Same-currency transaction: payout_usd_cost, collection_usd, collection_margin_usd, payout_margin_usd are NULL in persisted quote • Cross-currency transaction: all five USD pool values are non-null and positive • quote_ref is a valid UUID; no two calls return the same ref | 45 | 4.7-T03, 4.7-T04 | BE | RATE-04
4.7-T06 | rate-fx | 4.7 | 4. Rate Engine & FX | Rate quote lifecycle, TTL & rate-lock | 1 | Implement expiry check at commit: return RATE_QUOTE_EXPIRED for stale quotes | WBS 4.7 — Expiry check. The CommitTransaction flow calls lockRateQuote(quoteRef) before proceeding. This function must: load the rate_quote by quote_ref (from Redis first, fallback to DB), check isExpired(Instant.now()), and if expired throw RateQuoteExpiredException which the Orchestrator converts to error code RATE_QUOTE_EXPIRED returned to the partner (HTTP 422). Also check is_used=TRUE to reject replay (return RATE_QUOTE_ALREADY_USED). The expiry check must use the stored valid_until from the quote — not a re-computed value. Clock is injectable for testing. | • Implement QuoteService.lockRateQuote(String quoteRef, Instant now) method • Load quote from Redis cache first (rate_quote:{quoteRef}); on cache miss load from DB via RateQuoteRepository.findByQuoteRef() • If quote not found throw QuoteNotFoundException (-> HTTP 404) • If quote.isUsed() throw RateQuoteAlreadyUsedException (-> HTTP 409) • If quote.isExpired(now) throw RateQuoteExpiredException (-> HTTP 422, error_code=RATE_QUOTE_EXPIRED) • Return the valid RateQuote for rate-lock step; do NOT mark as used here (that happens in 4.7-T07) | QuoteService.lockRateQuote() method + RateQuoteExpiredException + unit tests | • Quote with valid_until=T checked at T-1s: no exception thrown • Quote with valid_until=T checked at T: RateQuoteExpiredException thrown (expired at boundary) • Quote with valid_until=T checked at T+1s: RateQuoteExpiredException thrown • Quote with is_used=TRUE throws RateQuoteAlreadyUsedException regardless of expiry • Unknown quoteRef throws QuoteNotFoundException • Cache miss falls through to DB lookup correctly | 40 | 4.7-T04, 4.7-T05 | BE | RATE-04
4.7-T07 | rate-fx | 4.7 | 4. Rate Engine & FX | Rate quote lifecycle, TTL & rate-lock | 1 | Implement rate-lock: copy pool and derived rate values onto transaction at commit | WBS 4.7 — Rate lock. After lockRateQuote() confirms the quote is valid, CommitTransaction must copy all USD pool values and derived rates from the RateQuote onto the transaction record atomically. Fields to copy: payout_usd_cost, collection_usd, collection_margin_usd, payout_margin_usd, send_amount, service_charge, collection_amount, offer_rate_coll, cross_rate, cost_rate_coll, cost_rate_pay, quote_issued_at, valid_until. Also set: rate_quote_id, committed_at = Instant.now(), is_same_ccy_shortcircuit from quote. Then mark rate_quote.is_used = TRUE. Both the transaction UPDATE and the rate_quote.is_used UPDATE must occur in the same DB transaction (atomic). After commit, the trigger (4.7-T02) prevents further changes to these columns. | • Implement RateLockService.applyRateLock(Transaction txn, RateQuote quote, Instant committedAt) method • In a single @Transactional block: update txn with all 15 locked fields + rate_quote_id + committed_at; call RateQuoteRepository.markUsed(quote.getId()) • Ensure the same DB transaction covers both writes (no partial commit) • Add unit test: after applyRateLock, all 15 fields on the transaction match the source quote exactly • Add integration test: simulate a treasury rate change after commit; verify the stored txn values are unchanged | RateLockService.applyRateLock() method + unit + integration tests | • All 15 rate fields on txn equal the corresponding fields on the source RateQuote after lock • committed_at is set to the instant applyRateLock was called • rate_quote.is_used is TRUE after lock • Both writes fail or both succeed — partial commit is impossible (test: inject DB error on markUsed, verify txn fields not updated) • After a later treasury rate change, reading the committed txn returns original locked values unchanged | 50 | 4.7-T02, 4.7-T06 | BE | RATE-04
4.7-T08 | rate-fx | 4.7 | 4. Rate Engine & FX | Rate quote lifecycle, TTL & rate-lock | 1 | Unit tests: validUntil computation and TTL boundary correctness | WBS 4.7 — Test vectors for validUntil and TTL. This ticket is dedicated test coverage for the validUntil formula and expiry boundary. Formula: validUntil = quote_issued_at + ttl_seconds. Boundary rule: a quote is expired when Instant.now() >= validUntil (i.e. expired AT the boundary instant, not only after). Use a fixed-clock (TestClock) so all time is deterministic. Key vectors: (1) ttl=60, check at +59s -> valid; (2) ttl=60, check at exactly +60s -> expired; (3) ttl=300, check at +299s -> valid; (4) ttl=1800, check at +1800s -> expired; (5) ttl=60, validUntil stored as 2026-10-10T12:01:00Z, check at 2026-10-10T12:01:00Z -> expired. | • Create RateQuoteTtlTest.java in the rate-engine test module • Inject a fixed TestClock set to a known base time T • For each vector: construct a RateQuote with given ttl_seconds and quote_issued_at=T; call isExpired(T + offset) • Assert expected expired/valid result for each vector • Add one additional vector: ttl=60 but quote_issued_at is 1 second in the past relative to T, check at T+58s -> valid (59s elapsed) | RateQuoteTtlTest.java with at least 6 parameterized test cases | • ttl=60, checked at +59s: isExpired=false • ttl=60, checked at +60s: isExpired=true (boundary is exclusive for validity) • ttl=300, checked at +299s: isExpired=false • ttl=1800, checked at +1800s: isExpired=true • Stored validUntil matches quote_issued_at.plusSeconds(ttl_seconds) exactly • All 6 tests pass with zero tolerance — no rounding or off-by-one | 30 | 4.7-T04 | BE | RATE-04
4.7-T09 | rate-fx | 4.7 | 4. Rate Engine & FX | Rate quote lifecycle, TTL & rate-lock | 1 | Unit tests: TTL clamping to [60, 1800] range — parameterized boundary vectors | WBS 4.7 — Clamping test. TtlResolutionService.resolve() must clamp the configured ttl_seconds to [60, 1800]. Verify every boundary: below minimum, at minimum, middle values, at maximum, above maximum. Also verify the aggregator-bound flag selects the correct default (60 vs 300) before any configured override. All tests use pure unit mocks — no DB or Redis. | • Create TtlResolutionServiceTest.java with parameterized test method • Test vectors: input=-1 -> 60; input=0 -> 60; input=59 -> 60; input=60 -> 60; input=61 -> 61; input=300 -> 300; input=1800 -> 1800; input=1801 -> 1800; input=9999 -> 1800 • Add tests for default selection: aggregator-bound partner with null config -> 60; non-aggregator partner with null config -> 300 • Verify that an explicit config value overrides the aggregator default before clamping | TtlResolutionServiceTest.java with at least 12 parameterized cases | • rate_quote_ttl_seconds=59 resolves to 60 • rate_quote_ttl_seconds=60 resolves to 60 • rate_quote_ttl_seconds=1800 resolves to 1800 • rate_quote_ttl_seconds=1801 resolves to 1800 • aggregator-bound + null config -> 60 • non-aggregator + null config -> 300 • aggregator-bound + explicit 120 config -> 120 (config wins, then clamp) | 25 | 4.7-T03 | BE | RATE-04
4.7-T10 | rate-fx | 4.7 | 4. Rate Engine & FX | Rate quote lifecycle, TTL & rate-lock | 1 | Unit tests: rate-lock immutability — locked values unchanged after treasury update | WBS 4.7 — Immutability test. After CommitTransaction, changing treasury rates or rule margins must not alter the locked values on the transaction. This test verifies the rate-lock guarantee end-to-end at the service layer. Use an in-memory H2 DB or Testcontainers PostgreSQL. Test flow: (1) create a rule with cost_rate_coll=1300.0 (USD/KRW); (2) issue a quote; (3) commit the transaction (applyRateLock); (4) update treasury rate to 1400.0; (5) reload the transaction from DB; (6) assert txn.cost_rate_coll == 1300.0 (original). Also test: updating rule m_a does not affect committed_at transaction. | • Create RateLockImmutabilityTest.java as a @SpringBootTest slice or Testcontainers test • Set up rule with cost_rate_coll=1300.0 (KRW per USD), m_a=0.01, m_b=0.01 • Issue and commit a test transaction; record all locked values • Update treasury_rate table: set new rate 1400.0 for usd_krw • Reload transaction from DB and assert all 15 locked columns equal original values • Update rule.m_a to 0.02 and verify committed transaction still shows original m_a snapshot (note: m_a is on rule not txn, but locked values like collection_margin_usd must not change) | RateLockImmutabilityTest.java with at least 4 test cases | • txn.cost_rate_coll equals 1300.0 after treasury rate changed to 1400.0 • txn.collection_usd equals the value computed at quote time, not recomputed with 1400.0 • DB trigger prevents direct UPDATE of cost_rate_coll on committed row (attempt raises exception) • txn.committed_at is set and not null after commit • txn.offer_rate_coll equals value derived at quote time, not re-derived from new rate | 50 | 4.7-T07 | BE | RATE-04
4.7-T11 | rate-fx | 4.7 | 4. Rate Engine & FX | Rate quote lifecycle, TTL & rate-lock | 1 | Unit tests: RATE_QUOTE_EXPIRED error at commit — expiry boundary integration test | WBS 4.7 — Expiry integration test. Verify that CommitTransaction returns error code RATE_QUOTE_EXPIRED when the quote TTL has elapsed. Use injectable TestClock. Test flow: (1) issue a quote at time T with ttl=60; (2) advance clock to T+61s; (3) call CommitTransaction with the quote_ref; (4) verify response is HTTP 422 with error_code=RATE_QUOTE_EXPIRED; (5) verify transaction is set to FAILED status; (6) verify no rate-lock columns were written. Also test the exact-boundary case: advance to T+60s and expect EXPIRED. | • Create RateQuoteExpiryCommitTest.java as a service-layer unit test with mocked clock and mocked repositories • Issue a quote at T=0 with ttl=60 (validUntil=T+60) • Set clock to T+60 (boundary); call CommitTransaction; assert RateQuoteExpiredException is thrown • Set clock to T+61; call CommitTransaction; assert RateQuoteExpiredException is thrown • Verify that neither attempt wrote any rate-lock columns to the transaction • Verify is_used remains FALSE on the quote (commit was rejected, quote should remain unused) | RateQuoteExpiryCommitTest.java with 4 test cases covering expired and boundary scenarios | • Clock at T+60: CommitTransaction throws RATE_QUOTE_EXPIRED • Clock at T+59: CommitTransaction succeeds (not expired) • After failed commit due to expiry: txn.committed_at is NULL • After failed commit due to expiry: rate_quote.is_used is FALSE • Error response body contains error_code=RATE_QUOTE_EXPIRED | 40 | 4.7-T06, 4.7-T07 | BE | RATE-04
4.7-T12 | rate-fx | 4.7 | 4. Rate Engine & FX | Rate quote lifecycle, TTL & rate-lock | 1 | Wire issueQuote into GET /v1/rates handler — return validUntil in response | WBS 4.7 — API wiring. The GET /v1/rates endpoint (rate quote API) is partially implemented from WBS 4.4. In this ticket: after the rate engine computes the quote, call QuoteService.issueQuote() (4.7-T05) to persist it and obtain the quote_ref and validUntil. Update the RateQuoteResponse DTO to include fields: quote_ref (String), validUntil (String, ISO-8601 UTC). The handler must pass the resolved ttl_seconds (from TtlResolutionService, 4.7-T03) to issueQuote. The txn state is set to QUOTED after persisting the quote. Redis store happens inside issueQuote. | • Update RateQuoteResponse DTO: add quote_ref and validUntil fields • In GET /v1/rates handler: call TtlResolutionService.resolve(partner) to get ttl; pass to QuoteService.issueQuote() • Map the returned RateQuoteResponse (quote_ref, validUntil included) to the HTTP response body • Ensure validUntil is formatted as ISO-8601 UTC (e.g. 2026-10-10T12:01:00Z) • Add integration test: call GET /v1/rates; assert response contains quote_ref (UUID format) and validUntil (validUntil = now + ttl within 2s tolerance) | Updated GET /v1/rates handler with quote_ref + validUntil in response + integration test | • GET /v1/rates response contains quote_ref as a UUID string • validUntil in response matches quote_issued_at + ttl_seconds within 1-second tolerance • rate_quote row is persisted in DB with correct values after the call • Redis key rate_quote:{quote_ref} is set with TTL=ttl_seconds • Aggregator-bound partner gets validUntil = now+60s; standard partner gets now+300s (when no override set) | 40 | 4.7-T05, 4.7-T09 | BE | RATE-04
4.7-T13 | rate-fx | 4.7 | 4. Rate Engine & FX | Rate quote lifecycle, TTL & rate-lock | 1 | Wire lockRateQuote and applyRateLock into CommitTransaction handler | WBS 4.7 — Commit wiring. The CommitTransaction endpoint (POST /v1/payments) calls the Orchestrator which must: (1) call QuoteService.lockRateQuote(quoteRef, Instant.now()) — throws RATE_QUOTE_EXPIRED (HTTP 422) or RATE_QUOTE_ALREADY_USED (HTTP 409) if invalid; (2) on valid quote, call RateLockService.applyRateLock(txn, quote, Instant.now()) to copy all pool values atomically and mark quote used; (3) continue with prefunding deduction and scheme call. Error response for RATE_QUOTE_EXPIRED must have body: {error_code: RATE_QUOTE_EXPIRED, message: Rate quote has expired. Please request a new quote.} | • In TransactionOrchestrator.commitTransaction(): insert lockRateQuote() call after quote_ref validation, before prefunding deduction • Map RateQuoteExpiredException to HTTP 422 with error_code=RATE_QUOTE_EXPIRED in the global exception handler • Map RateQuoteAlreadyUsedException to HTTP 409 with error_code=RATE_QUOTE_ALREADY_USED • Call RateLockService.applyRateLock() immediately after lockRateQuote() returns the valid quote • Add integration test: full POST /v1/payments flow with valid quote succeeds and returns committed txn with locked rate values in response | Updated CommitTransaction handler with expiry guard + rate-lock + integration test | • POST /v1/payments with expired quote_ref returns HTTP 422 and error_code=RATE_QUOTE_EXPIRED • POST /v1/payments with already-used quote_ref returns HTTP 409 and error_code=RATE_QUOTE_ALREADY_USED • POST /v1/payments with valid quote: txn.cost_rate_coll matches quote.cost_rate_coll in DB after commit • Re-using the same quote_ref a second time after a successful commit returns HTTP 409 • Transaction status transitions from QUOTED to PENDING_DEBIT (OVERSEAS) or DEBITED (LOCAL) after successful rate lock | 50 | 4.7-T06, 4.7-T07, 4.7-T12 | BE | RATE-04
4.7-T14 | rate-fx | 4.7 | 4. Rate Engine & FX | Rate quote lifecycle, TTL & rate-lock | 1 | Configure rate_quote_ttl_seconds in partner Admin UI and validate range [60, 1800] | WBS 4.7 — Config. The Admin System partner edit form must expose rate_quote_ttl_seconds (INT) and is_aggregator_bound (BOOLEAN). Validation rules: rate_quote_ttl_seconds must be in [60, 1800] inclusive; if outside range, reject with error message Allowed range: 60 to 1800 seconds. Changes to rate_quote_ttl_seconds apply only to new quotes issued after the change — in-flight quotes retain their original TTL. Config change must be audit-logged (actor, old value, new value, timestamp) per the platform audit requirement. | • Add rate_quote_ttl_seconds integer input and is_aggregator_bound checkbox to partner edit form in the Admin API • Add server-side validation: reject if rate_quote_ttl_seconds < 60 OR > 1800 with HTTP 400 and descriptive error • Add audit log entry on change: record field name, previous value, new value, actor, changed_at • Update the partner cache invalidation to bust Redis hot cache on partner save • Add unit test: PUT /admin/partners/{id} with ttl=59 returns HTTP 400; ttl=60 returns 200; ttl=1800 returns 200; ttl=1801 returns 400 | Admin API partner update endpoint with ttl validation + audit logging + unit tests | • rate_quote_ttl_seconds=59 returns HTTP 400 with range error message • rate_quote_ttl_seconds=1800 returns HTTP 200 and persists value • rate_quote_ttl_seconds=1801 returns HTTP 400 • Audit log contains previous and new value of rate_quote_ttl_seconds with actor and timestamp • Quotes issued before the TTL change retain their original validUntil (no retroactive change) | 45 | 4.7-T03, 4.7-T05 | BE | RATE-04
4.7-T15 | rate-fx | 4.7 | 4. Rate Engine & FX | Rate quote lifecycle, TTL & rate-lock | 1 | Redis TTL alignment test: verify Redis key expiry matches validUntil | WBS 4.7 — Cache TTL alignment. The Redis key rate_quote:{quote_ref} must expire at the same time as the quote's validUntil. This means the Redis SET command must use EX=ttl_seconds (not EX=validUntil-now, which would diverge if there is clock skew between the app and Redis). Verify that: (1) the Redis TTL set at issue time equals ttl_seconds exactly; (2) after the Redis key expires, lockRateQuote() falls back to DB and still returns RATE_QUOTE_EXPIRED for an expired quote; (3) if Redis evicts the key early (simulated), DB fallback works correctly. | • Add test RedisAlignmentTest.java using an embedded Redis (Testcontainers or EmbeddedRedis) • Issue a quote with ttl=60; immediately call Redis TTL command on rate_quote:{quote_ref}; assert TTL is between 58 and 60 (within 2s of expected) • Simulate Redis eviction by deleting the key manually; call lockRateQuote() at T+61; assert RATE_QUOTE_EXPIRED from DB fallback • Issue another quote; advance to T+59 (within TTL); delete Redis key; call lockRateQuote(); assert quote returned from DB (not expired) • Verify Redis value contains all required fields: quote_ref, validUntil, all pool values | RedisAlignmentTest.java with 4 test cases for TTL alignment and cache-miss fallback | • Redis TTL for rate_quote:{quote_ref} is within 2s of ttl_seconds immediately after issue • Cache miss at T+59 falls through to DB and returns valid quote • Cache miss at T+61 falls through to DB and returns RATE_QUOTE_EXPIRED • Redis serialized value contains valid_until field matching DB row • Two concurrent lockRateQuote() calls for same quote_ref: exactly one succeeds, other gets RATE_QUOTE_ALREADY_USED | 40 | 4.7-T06, 4.7-T05 | BE | RATE-04
4.8-T01 | rate-fx | 4.8 | 4. Rate Engine & FX | Rounding & precision rules | 1 | Define currency_scale table and CurrencyScale entity | GMEPay+ must apply rounding only at defined output points using per-currency decimal scale. Spec RATE-04 §10.3 defines the scale table: KRW=0 (half-up to whole won), USD=2 (half-up to cent), MNT=0, EUR=2, VND=0, THB=2. For currencies not listed, scale comes from ISO 4217 decimal places populated by GME Ops. A currency_scale table is needed so the rate engine can look up scale without hardcoding. Depends on 4.2 (entity/schema foundation) and 4.3 (DB migrations). | • Create DB migration: table currency_scale(ccy CHAR(3) PK, decimal_places SMALLINT NOT NULL CHECK(decimal_places>=0), rounding_mode VARCHAR(20) NOT NULL DEFAULT 'HALF_UP', notes VARCHAR(200)). • Seed initial rows for KRW(0), USD(2), MNT(0), EUR(2), VND(0), THB(2) with rounding_mode=HALF_UP for all. • Create Java entity CurrencyScale with fields ccy, decimalPlaces, roundingMode(enum: HALF_UP). • Create CurrencyScaleRepository with findByCcy(String ccy) and a cache-friendly findAll(). • Add a NOT NULL constraint and a check that decimal_places <= 8 to prevent misconfiguration. | DB migration file V4_8_001__currency_scale.sql + CurrencyScale entity + CurrencyScaleRepository | • Migration runs cleanly; SELECT * FROM currency_scale returns exactly 6 seed rows with correct decimal_places values. • findByCcy('KRW') returns decimalPlaces=0, findByCcy('USD') returns decimalPlaces=2. • findByCcy('XXX') returns empty Optional (unknown currency, no row). • INSERT of decimal_places=-1 or decimal_places=9 is rejected by DB constraint. • All seed rows have rounding_mode=HALF_UP. | 35 | 4.2, 4.3 | BE | RATE-04
4.8-T02 | rate-fx | 4.8 | 4. Rate Engine & FX | Rounding & precision rules | 1 | Create CurrencyScaleLookupService with fallback to ISO 4217 | The rate engine needs to resolve decimal scale at runtime for any ISO 4217 currency, including ones not yet seeded. Spec RATE-04 §10.3 Assumption A2: for unlisted currencies use the ISO 4217 decimal places maintained by GME Ops. The service must: (1) look up currency_scale table (4.8-T01); (2) if not found, throw CurrencyScaleNotFoundException with message 'Currency scale not configured for {ccy} - GME Ops must populate currency_scale table before activating this currency'. No silent fallback to 0 or 2. | • Create CurrencyScaleLookupService that autowires CurrencyScaleRepository. • Implement getScale(String ccy): return CurrencyScale if found, else throw CurrencyScaleNotFoundException. • Add a getDecimalPlaces(String ccy) convenience method returning int. • Add a getRoundingMode(String ccy) convenience method returning RoundingMode enum. • Write unit tests with mocked repository: found case (KRW->0, USD->2), not-found case throws exception. | CurrencyScaleLookupService.java + CurrencyScaleNotFoundException.java + unit test CurrencyScaleLookupServiceTest.java | • getDecimalPlaces('KRW') returns 0. • getDecimalPlaces('USD') returns 2. • getDecimalPlaces('MNT') returns 0. • getDecimalPlaces('UNKNOWN') throws CurrencyScaleNotFoundException with informative message containing the ccy code. • getRoundingMode('KRW') returns RoundingMode.HALF_UP. | 30 | 4.8-T01 | BE | RATE-04
4.8-T03 | rate-fx | 4.8 | 4. Rate Engine & FX | Rounding & precision rules | 1 | Implement roundToCurrencyScale utility function | The rate engine must round collection_amount (Settle-A ccy) and the parsed target_payout (Settle-B/payout ccy) using half-up rounding to the currency's decimal scale. All other intermediates (payout_usd_cost, collection_usd, margin amounts, send_amount) must NOT be rounded - they carry 8 decimal places of precision (DECIMAL(20,8)). Spec RATE-04 §10.4: rounding applied only at Step 5 (collection_amount) and target_payout input parsing. Rounding mode is HALF_UP per spec §10.3 table. | • Create MoneyRoundingUtil with static method roundToCurrencyScale(BigDecimal amount, String ccy, CurrencyScaleLookupService lookup): returns amount.setScale(decimalPlaces, RoundingMode.HALF_UP). • Ensure the method rejects null amount or null ccy with IllegalArgumentException. • Add overload roundToCurrencyScale(BigDecimal amount, CurrencyScale scale) for pre-resolved scale. • Write unit tests covering KRW rounding (1234.5 -> 1235, 1234.4 -> 1234), USD rounding (10.555 -> 10.56, 10.554 -> 10.55), and MNT rounding (99.9 -> 100). • Verify that a BigDecimal with 8 decimal places passed through returns 8 decimal places unchanged (no rounding on intermediates path - intermediates are NOT passed to this function). | MoneyRoundingUtil.java + MoneyRoundingUtilTest.java | • roundToCurrencyScale(BigDecimal('1234.5'), 'KRW', ...) returns BigDecimal('1235') (scale 0). • roundToCurrencyScale(BigDecimal('10.555'), 'USD', ...) returns BigDecimal('10.56') (scale 2, half-up). • roundToCurrencyScale(BigDecimal('10.554'), 'USD', ...) returns BigDecimal('10.55'). • roundToCurrencyScale(BigDecimal('99.9'), 'MNT', ...) returns BigDecimal('100') (scale 0). • Passing null amount throws IllegalArgumentException; unknown ccy propagates CurrencyScaleNotFoundException. | 30 | 4.8-T02 | BE | RATE-04
4.8-T04 | rate-fx | 4.8 | 4. Rate Engine & FX | Rounding & precision rules | 1 | Apply rounding at collection_amount output point in rate engine (Step 5) | Spec RATE-04 §10.4 and pseudocode line: collection_amount = round_to_currency_scale(collection_amount, settle_a_ccy). This is the ONLY rounding point in the 5-step calculation. Steps 1-4 intermediates (payout_usd_cost, collection_usd, collection_margin_usd, payout_margin_usd, send_amount) must all be computed and stored as DECIMAL(20,8) BigDecimal WITHOUT rounding. Step 5: collection_amount = send_amount + service_charge, then rounded to settle_a_ccy scale. Depends on rate engine core (4.3) and MoneyRoundingUtil (4.8-T03). | • Locate the rate engine Step 5 implementation in the existing rate calculation service (from 4.3). • After computing collection_amount = send_amount.add(service_charge), call MoneyRoundingUtil.roundToCurrencyScale(collection_amount, settleACcy, lookup) and replace collection_amount with the result. • Confirm Steps 1-4 computations use BigDecimal arithmetic at scale 8 (setScale not called on intermediates). • Add assertion that payout_usd_cost, collection_usd, collection_margin_usd, payout_margin_usd, send_amount all have scale >= 8 after computation (developer guard). • Write unit test: for settleACcy=KRW, verify collection_amount in result has scale 0; for settleACcy=USD, scale 2. | Updated RateCalculationService.java (Step 5 rounding wired) + RateCalculationServiceRoundingTest.java | • For settle_a_ccy=KRW: computed collection_amount (e.g. 50123.7) is rounded to 50124 (integer, scale 0). • For settle_a_ccy=USD: computed collection_amount (e.g. 36.4559) is rounded to 36.46 (scale 2). • send_amount in the returned quote retains 8 decimal places (e.g. 49623.72000000), not rounded. • collection_usd in returned quote retains 8 decimal places. • When settle_a_ccy is not in currency_scale table, CurrencyScaleNotFoundException is thrown before any value is returned. | 40 | 4.8-T03, 4.3 | BE | RATE-04
4.8-T05 | rate-fx | 4.8 | 4. Rate Engine & FX | Rounding & precision rules | 1 | Apply rounding at target_payout input parsing point | Spec RATE-04 §10.4: rounding is applied once at target_payout input parsing (the final output point for the payout side). The input target_payout arrives as a numeric value in payout_ccy (e.g. KRW integer from partner). It must be parsed and rounded to payout_ccy scale before entering Step 1 (payout_usd_cost = target_payout / cost_rate_pay). For KRW this means the value must already be an integer; for USD it must have at most 2 decimal places. This prevents sub-unit fractional inputs from propagating into pool math. | • In the rate engine input validation/parsing layer, after reading target_payout from the request, call MoneyRoundingUtil.roundToCurrencyScale(target_payout, payoutCcy, lookup). • Store the rounded value as the authoritative target_payout for all subsequent steps. • Add unit test: target_payout=50000.7 with payoutCcy=KRW rounds to 50001 before Step 1 runs. • Add unit test: target_payout=100.001 with payoutCcy=USD rounds to 100.00 before Step 1 runs. • Log a WARN if rounding changes the input value (input was not on currency boundary), to surface misconfigured partner integrations. | Updated RateEngineInputParser.java (or equivalent input handler) + RateEngineInputParserTest.java | • target_payout=50000.7, payoutCcy=KRW -> parsed value is 50001 (BigDecimal scale 0). • target_payout=100.001, payoutCcy=USD -> parsed value is 100.00 (BigDecimal scale 2). • target_payout=50000 (already integer), payoutCcy=KRW -> parsed value is 50000 (no change, no WARN logged). • target_payout=0 rejected before rounding by existing INVALID_PAYOUT_AMOUNT guard. • target_payout with payoutCcy not in currency_scale -> CurrencyScaleNotFoundException before any calculation. | 30 | 4.8-T03, 4.3 | BE | RATE-04
4.8-T06 | rate-fx | 4.8 | 4. Rate Engine & FX | Rounding & precision rules | 1 | Verify intermediates are stored at DECIMAL(20,8) precision in DB columns | Spec DAT-03 §2.1 and RATE-04 §10.2: USD intermediary values (collection_usd, payout_usd_cost, collection_margin_usd, payout_margin_usd) and send_amount are stored as DECIMAL(20,8) in the rate_quote and transaction tables. collection_amount is stored as DECIMAL(20,4) (currency-native rounded value). This ticket verifies DB schema matches spec and adds a DB-level constraint audit. Do NOT introduce rounding on insert - the application layer must already carry 8dp BigDecimal into the ORM mapper. | • Read the existing rate_quote and transaction table DDL (from 4.2/4.3 migrations). • Confirm columns: collection_usd DECIMAL(20,8), payout_usd_cost DECIMAL(20,8), collection_margin_usd DECIMAL(20,8), payout_margin_usd DECIMAL(20,8), send_amount DECIMAL(20,8), collection_amount DECIMAL(20,4). • If any column has wrong precision, add a migration ALTER TABLE to correct it. • Write an integration test that inserts a RateQuote with send_amount=49623.72345678 and reads it back - assert no precision loss (value equals original to 8dp). • Add a comment block in the migration explaining WHY each column uses its specific scale (intermediate vs output). | Migration V4_8_002__fix_rate_quote_precision.sql (if correction needed, else documented as N/A) + IntermediatePrecisionIntegrationTest.java | • DESCRIBE rate_quote shows collection_usd, payout_usd_cost, collection_margin_usd, payout_margin_usd, send_amount all as DECIMAL(20,8). • DESCRIBE rate_quote/transaction shows collection_amount as DECIMAL(20,4). • Insert send_amount=49623.72345678, read back: value equals 49623.72345678 (no truncation). • Insert collection_amount=50124.0000 (KRW), read back: value equals 50124.0000 (correct scale). • Java ORM mapping: RateQuote.sendAmount is BigDecimal; no inadvertent setScale or doubleValue() call anywhere in the mapping. | 35 | 4.8-T04, 4.2, 4.3 | BE | RATE-04
4.8-T07 | rate-fx | 4.8 | 4. Rate Engine & FX | Rounding & precision rules | 1 | Implement pool identity check post-rounding and enforce hard error | Spec RATE-04 §10.5 and §11.3: pool identity (collection_usd - collection_margin_usd - payout_margin_usd = payout_usd_cost) must hold within 0.01 USD tolerance. This check runs AFTER Steps 1-4, using unrounded 8dp intermediates. A breach is a hard programming error - transaction must fail with POOL_IDENTITY_FAILURE (not silently commit). The check must also run in the on_commit path to guard against any future code path that bypasses the quote calculation. Intermediates use 8dp BigDecimal so the tolerance of 0.01 USD is generous (rounding cannot cause breach if implemented correctly). | • Create PoolIdentityChecker.assertIdentity(BigDecimal collectionUsd, BigDecimal collectionMarginUsd, BigDecimal payoutMarginUsd, BigDecimal payoutUsdCost): compute diff = abs(collectionUsd - collectionMarginUsd - payoutMarginUsd - payoutUsdCost); if diff > 0.01 throw PoolIdentityException with details. • Wire assertIdentity() into RateCalculationService after Step 3 (before Step 4) and also in the on_commit path. • Write unit test: valid input -> no exception; tampered collectionUsd (off by 0.02) -> PoolIdentityException thrown. • Write unit test: diff exactly 0.01 -> no exception (boundary); diff 0.010001 -> exception (exclusive upper bound). • Confirm exception message includes all four values and the computed diff for debuggability. | PoolIdentityChecker.java + PoolIdentityException.java + PoolIdentityCheckerTest.java + wiring in RateCalculationService | • collectionUsd=36.2319, collectionMarginUsd=0.7246, payoutMarginUsd=0.3623, payoutUsdCost=35.145 -> diff=abs(36.2319-0.7246-0.3623-35.145)=0.0000 -> no exception. • If collectionUsd is inflated by 0.02 in above example -> PoolIdentityException. • diff=0.01 (exactly at tolerance) -> no exception. • diff=0.0101 -> PoolIdentityException. • Exception message contains all four BigDecimal input values and the computed diff value. | 35 | 4.8-T04 | BE | RATE-04
4.8-T08 | rate-fx | 4.8 | 4. Rate Engine & FX | Rounding & precision rules | 1 | Implement payout rounding at payout output point | Spec RATE-04 §10.4 and the three-currency model: the payout amount delivered to the merchant (target_payout in payout_ccy) is the Settle-B/payout side. For ZeroPay/KRW this is always an integer. The rate engine receives target_payout as input (already rounded per 4.8-T05). However the payout leg also surfaces in settlement batch files (ZP0061 etc per SCH-06) and webhook payloads. This ticket ensures payout amount serialisation (webhook, API response) is rounded to payout_ccy scale before output, and that no fractional KRW ever appears in an outbound payload. | • Create PayoutAmountSerializer that applies MoneyRoundingUtil.roundToCurrencyScale to target_payout before including it in any API response or webhook payload. • Locate POST /v1/payments response builder and the payment.pending_debit webhook payload builder; wrap target_payout serialization through PayoutAmountSerializer. • Write unit test: target_payout=50000 KRW serialised -> '50000' (no decimal point in JSON). • Write unit test: target_payout=100.50 USD serialised -> '100.50' (2dp). • Add a guard: if target_payout after rounding != original target_payout (i.e. input already rounded per T05), throw AssertionError (should never happen in production after T05 is wired). | PayoutAmountSerializer.java + updated response/webhook builders + PayoutAmountSerializerTest.java | • KRW target_payout in API response JSON is an integer (no decimal point), e.g. 50000 not 50000.00. • USD target_payout in API response JSON has exactly 2 decimal places, e.g. 100.50. • AssertionError is never thrown in integration tests (confirming T05 rounding precedes T08 serialisation). • Webhook payload payment.pending_debit.target_payout for KRW transaction = integer value. • No floating-point conversion (doubleValue, floatValue) appears in the serialization path. | 35 | 4.8-T05 | BE | RATE-04
4.8-T09 | rate-fx | 4.8 | 4. Rate Engine & FX | Rounding & precision rules | 1 | Unit tests: per-currency scale lookup and rounding correctness (all seeded currencies) | Spec RATE-04 §10.3 defines six currencies with explicit scale and rounding direction. This ticket writes a comprehensive parameterised unit test suite covering all seeded currencies plus the unknown-currency exception path. Tests must use exact numeric examples from the spec table to confirm the rounding module matches the spec. These tests serve as the living specification for future currency additions. | • Create CurrencyScaleRoundingParameterisedTest using JUnit 5 @ParameterizedTest + @CsvSource. • Cover all 6 seeded currencies: KRW(1234.5->1235, 1234.4->1234), USD(10.555->10.56, 10.554->10.55), MNT(5.5->6, 5.4->5), EUR(0.555->0.56), VND(999.6->1000), THB(5.555->5.56). • Add boundary test: value=0.0 rounds to 0 for all currencies. • Add large-value test: KRW 50000000 (50 million) rounds to 50000000 (no change, already integer). • Add unknown-currency test: getDecimalPlaces('XYZ') throws CurrencyScaleNotFoundException. | CurrencyScaleRoundingParameterisedTest.java | • All 6 currency round-trip vectors pass (exact BigDecimal equality after rounding). • KRW: 1234.5 -> 1235 (HALF_UP, scale 0). • USD: 10.555 -> 10.56 (HALF_UP, scale 2); 10.554 -> 10.55. • MNT: 5.5 -> 6 (HALF_UP, scale 0). • Unknown currency 'XYZ' throws CurrencyScaleNotFoundException. | 30 | 4.8-T03, 4.8-T02 | BE | RATE-04
4.8-T10 | rate-fx | 4.8 | 4. Rate Engine & FX | Rounding & precision rules | 1 | Unit tests: pool identity holds after rounding outputs (no-broken-identity test) | Spec RATE-04 §10.5: pool identity (collection_usd - collection_margin_usd - payout_margin_usd == payout_usd_cost, tolerance 0.01 USD) must hold even after collection_amount is rounded to currency scale. The rounding of collection_amount affects only the Settle-A currency output; the USD intermediates remain at 8dp. This test proves that rounding collection_amount to KRW scale or USD scale does NOT break the USD pool identity invariant. Test uses worked numeric examples from the canonical rate engine. | • Set up test fixture using the 5-step calculation for a KRW payout (usd_krw=1380, target_payout=50000 KRW, m_a=0.015, m_b=0.010, service_charge=500 KRW): compute all intermediates and collection_amount with KRW rounding. • Assert pool identity: abs(collection_usd - collection_margin_usd - payout_margin_usd - payout_usd_cost) <= 0.01. • Repeat for USD payout leg (usd rate=1.0, target_payout=100 USD, m_a=0.015, m_b=0.010, service_charge=1.00 USD): collection_amount rounded to 2dp USD. • Assert pool identity holds for USD case also. • Add a negative test: artificially set collection_usd += 0.02 BigDecimal and assert PoolIdentityException is thrown. | PoolIdentityAfterRoundingTest.java | • KRW example: pool identity diff <= 0.01 USD after collection_amount rounded to integer KRW. • USD example: pool identity diff <= 0.01 USD after collection_amount rounded to 2dp USD. • Intermediate values (collection_usd, payout_usd_cost, send_amount) have scale >= 8 in both test cases. • Negative test: perturbed collection_usd (+0.02) causes PoolIdentityException with diff in message. • collection_amount for KRW case is a whole number (BigDecimal.scale() == 0 or value has no fractional part). | 40 | 4.8-T07, 4.8-T04 | BE | RATE-04
4.8-T11 | rate-fx | 4.8 | 4. Rate Engine & FX | Rounding & precision rules | 1 | Document rounding decision points: inline code comments and JavaDoc | Spec RATE-04 §10 requires that every developer working on the rate engine can identify exactly WHERE rounding is applied. Per the TICKET_BRIEF self-contained rule, this ticket adds formal JavaDoc and inline comments to the three rounding-application sites: (1) input parsing of target_payout (4.8-T05), (2) Step 5 collection_amount rounding (4.8-T04), and (3) pool identity check (4.8-T07). Also documents explicitly that Steps 1-4 intermediates are NOT rounded. This prevents future developers from accidentally adding rounding in the wrong place. | • Add JavaDoc to MoneyRoundingUtil explaining: only two call sites are permitted - target_payout parsing and collection_amount Step 5. Any other call site is a defect. • Add inline comment block at each of the two rounding call sites citing RATE-04 §10.4 and the spec rule text verbatim. • Add inline comment at each Step 1-4 intermediate computation: // NO ROUNDING - intermediate must retain 8dp precision per RATE-04 §10.2. • Add JavaDoc to PoolIdentityChecker explaining the 0.01 USD tolerance and that breach is a hard programming error. • Create a short ADR (Architecture Decision Record) comment at the top of RateCalculationService explaining the rounding philosophy. | Updated JavaDoc and inline comments in MoneyRoundingUtil.java, RateCalculationService.java (Steps 1-5), PoolIdentityChecker.java | • MoneyRoundingUtil JavaDoc explicitly states 'only two permitted call sites'. • Step 5 in RateCalculationService has comment citing RATE-04 §10.4. • Each of Steps 1-4 has a '// NO ROUNDING' comment. • PoolIdentityChecker JavaDoc states tolerance=0.01 USD and breach=hard error. • Code review: no other call to roundToCurrencyScale exists outside the two permitted sites (grep confirms). | 25 | 4.8-T04, 4.8-T05, 4.8-T07 | BE | RATE-04
4.9-T01 | rate-fx | 4.9 | 4. Rate Engine & FX | Rate engine unit tests vs vectors | 1 | Create rate-engine test harness and shared fixtures for RV-01..RV-10 | WBS 4.9 needs a JUnit 5 (or equivalent Java) test module for the rate engine. The harness must use decimal arithmetic (BigDecimal with scale >= 10 for intermediates), provide reusable fixture builders for RateEngineInput (target_payout, coll_ccy, payout_ccy, cost_rate_coll, cost_rate_pay, m_a, m_b, service_charge) and RateEngineOutput (payout_usd_cost, collection_usd, collection_margin_usd, payout_margin_usd, send_amount, collection_amount, offer_rate_coll, cross_rate), and expose a shared assertPoolIdentity(output, tolerance=0.01 USD) helper. Pool identity invariant: abs(collection_usd - collection_margin_usd - payout_margin_usd - payout_usd_cost) <= 0.01 USD. | • Create Maven/Gradle sub-module or test source set rate-engine-tests under the existing backend project. • Add RateEngineTestFixtures.java with static builder methods for each currency pair (MNT/KRW, USD/KRW, USD/USD, KRW/KRW). • Add RateEngineAssertions.java with assertPoolIdentity(output, BigDecimal tolerance) that throws AssertionError with a descriptive message on violation. • Add a smoke test that instantiates a fixture and calls assertPoolIdentity to confirm the helper itself works. • Verify CI picks up the new test module (add to build script if needed). | rate-engine-tests module with RateEngineTestFixtures.java, RateEngineAssertions.java, and a passing smoke test. | • Module compiles and smoke test passes in CI with zero failures. • RateEngineTestFixtures provides builders for all four currency-pair combinations used across RV-01..RV-10. • assertPoolIdentity passes when delta = 0.009 USD and fails when delta = 0.011 USD (boundary check). • All intermediate values use BigDecimal with scale >= 10; no double/float arithmetic present. • assertPoolIdentity error message includes actual delta and threshold values for diagnosis. | 40 | 4.2, 4.3, 4.4, 4.5, 4.6, 4.8 | QA | QA-12
4.9-T02 | rate-fx | 4.9 | 4. Rate Engine & FX | Rate engine unit tests vs vectors | 1 | Test RV-01: cross-border inbound MNT->KRW via USD (baseline 5-step vector) | Rate engine 5-step RECEIVE-mode formula: (1) payout_usd_cost = target_payout / cost_rate_pay; (2) collection_usd = payout_usd_cost / (1 - m_a - m_b); (3) collection_margin_usd = collection_usd * m_a, payout_margin_usd = collection_usd * m_b; (4) send_amount = collection_usd * cost_rate_coll; (5) collection_amount = send_amount + service_charge. Derived: offer_rate_coll = send_amount / (collection_usd - collection_margin_usd); cross_rate = target_payout / send_amount. RV-01 inputs: target_payout=13500 KRW, coll_ccy=MNT, payout_ccy=KRW, cost_rate_coll=3500.00, cost_rate_pay=1350.00, m_a=0.015, m_b=0.010, service_charge=500 MNT. | • In RateEngineRV01Test.java call the rate engine with the RV-01 fixture. • Assert payout_usd_cost = 10.0000 USD (tolerance 0.0001). • Assert collection_usd = 10.2564 USD (tolerance 0.0001). • Assert send_amount = 35897.44 MNT (tolerance 0.01), collection_amount = 36397.44 MNT (tolerance 0.01). • Assert offer_rate_coll = 3553.28 MNT/USD (tolerance 0.01) and cross_rate = 0.37609 KRW/MNT (tolerance 0.00001). • Call assertPoolIdentity(output) to confirm delta <= 0.01 USD. | RateEngineRV01Test.java with named test method testRV01_crossBorderInbound_MNT_KRW_via_USD. | • payout_usd_cost == 10.0000 USD within 0.0001. • collection_usd == 10.2564 USD within 0.0001. • send_amount == 35897.44 MNT within 0.01 and collection_amount == 36397.44 MNT within 0.01. • offer_rate_coll == 3553.28 MNT/USD within 0.01 and cross_rate == 0.37609 KRW/MNT within 0.00001. • Pool-identity assertion passes (delta <= 0.01 USD). | 30 | 4.9-T01 | QA | QA-12
4.9-T03 | rate-fx | 4.9 | 4. Rate Engine & FX | Rate engine unit tests vs vectors | 1 | Test RV-02: identity leg A (Settle A = USD, cost_rate_coll = 1.0) | When Settle A currency = USD, cost_rate_coll is set to the IDENTITY flag (value 1.0); the USD pool math still applies but send_amount = collection_usd * 1.0 = collection_usd. RV-02 inputs: target_payout=13500 KRW, coll_ccy=USD, payout_ccy=KRW, cost_rate_coll=1.0 (IDENTITY), cost_rate_pay=1350.00, m_a=0.015, m_b=0.010, service_charge=0.50 USD. Expected: payout_usd_cost=10.0000 USD, collection_usd=10.2564 USD, send_amount=10.2564 USD, collection_amount=10.7564 USD. | • Create RateEngineRV02Test.java with fixture: coll_ccy=USD, cost_rate_coll=1.0 (IDENTITY), cost_rate_pay=1350.00, service_charge=0.50 USD. • Assert send_amount == collection_usd (identity leg: no FX conversion). • Assert collection_amount == 10.7564 USD (tolerance 0.0001). • Verify the rate engine persists cost_rate_coll source field as IDENTITY (not a numeric treasury lookup). • Call assertPoolIdentity(output). | RateEngineRV02Test.java with test method testRV02_identityLegA_settleA_USD. | • send_amount == collection_usd (== 10.2564 USD) within 0.0001. • collection_amount == 10.7564 USD within 0.0001. • Recorded cost_rate_coll source = IDENTITY (not TREASURY). • Pool-identity assertion passes. • payout_usd_cost == 10.0000 USD within 0.0001. | 25 | 4.9-T01 | QA | QA-12
4.9-T04 | rate-fx | 4.9 | 4. Rate Engine & FX | Rate engine unit tests vs vectors | 1 | Test RV-03: both legs identity (USD->USD, cost_rate_coll=1.0, cost_rate_pay=1.0) | When both Settle A and Settle B are USD, both cost rates = 1.0 (IDENTITY). Margins still apply to collection_usd. RV-03 inputs: target_payout=100.00 USD, coll_ccy=USD, payout_ccy=USD, cost_rate_coll=1.0, cost_rate_pay=1.0, m_a=0.015, m_b=0.010, service_charge=0.50 USD. Expected: payout_usd_cost=100.0000 USD, collection_usd=102.5641 USD, send_amount=102.5641 USD, collection_amount=103.0641 USD. Note: this is NOT the same-currency short-circuit (different ccys could still route through USD pool even when both legs are 1.0). | • Create RateEngineRV03Test.java with fixture: coll_ccy=USD, payout_ccy=USD, both cost rates=1.0 IDENTITY, service_charge=0.50 USD, target_payout=100.00. • Assert payout_usd_cost = 100.0000 USD (tolerance 0.0001). • Assert collection_usd = 102.5641 USD (tolerance 0.0001). • Assert send_amount == collection_usd and collection_amount = 103.0641 USD (tolerance 0.0001). • Confirm both leg sources recorded as IDENTITY in output metadata. • Call assertPoolIdentity(output). | RateEngineRV03Test.java with test method testRV03_bothLegsIdentity_USD_USD. | • payout_usd_cost == 100.0000 USD within 0.0001. • collection_usd == 102.5641 USD within 0.0001. • send_amount == collection_usd (both IDENTITY legs) within 0.0001. • collection_amount == 103.0641 USD within 0.0001. • Pool-identity assertion passes. | 25 | 4.9-T01 | QA | QA-12
4.9-T05 | rate-fx | 4.9 | 4. Rate Engine & FX | Rate engine unit tests vs vectors | 1 | Test RV-04: same-currency short-circuit (KRW->KRW, USD pool skipped) | Same-currency short-circuit rule: if collection_ccy == settle_A == settle_B == payout_ccy then skip the USD pool entirely. Formula: collection_amount = target_payout + service_charge. No payout_usd_cost, collection_usd, margins, offer_rate_coll, or cross_rate computed. m_a=0 and m_b=0 (required for same-currency rules; combined margin 0% allowed). RV-04 inputs: target_payout=13500 KRW, coll_ccy=KRW, payout_ccy=KRW, cost rates=IDENTITY (skipped), m_a=0.0, m_b=0.0, service_charge=500 KRW. Expected: collection_amount=14000 KRW; all USD pool fields null. | • Create RateEngineRV04Test.java with same-currency fixture: coll_ccy=KRW, payout_ccy=KRW, m_a=0, m_b=0, service_charge=500 KRW. • Assert collection_amount = 14000 KRW (exact integer for KRW scale=0). • Assert payout_usd_cost, collection_usd, collection_margin_usd, payout_margin_usd are null or absent in the output object. • Assert offer_rate_coll and cross_rate are null or absent. • Verify no prefunding deduction event is emitted (or deduction_usd = null). | RateEngineRV04Test.java with test method testRV04_sameCurrencyShortCircuit_KRW_KRW. | • collection_amount == 14000 KRW (exact, KRW scale 0 decimals). • All USD pool fields (payout_usd_cost, collection_usd, margins) are null in the output. • offer_rate_coll and cross_rate are null. • No MARGIN_BELOW_MINIMUM error raised (m_a+m_b=0 allowed for same-currency). • No prefunding deduction emitted. | 30 | 4.9-T01 | QA | QA-12
4.9-T06 | rate-fx | 4.9 | 4. Rate Engine & FX | Rate engine unit tests vs vectors | 1 | Test RV-05: partner B quote within tolerance (0.8% deviation, transaction commits) | Partner B authoritative quote: at /rates time, treasury cost_rate_pay=1350.00 KRW/USD. At commit time, partner B live quote=1360.80 KRW/USD. Deviation = abs(1360.80-1350.00)/1350.00 = 0.8%, which is within the default 1.0% tolerance. Engine must recompute with commit-time rate 1360.80 and commit. Inputs otherwise identical to RV-01: target_payout=13500 KRW, coll_ccy=MNT, cost_rate_coll=3500.00, m_a=0.015, m_b=0.010, service_charge=500 MNT. Expected at commit: payout_usd_cost=13500/1360.80=9.9206 USD (illustrative); transaction committed; recorded cost_rate_pay=1360.80; rate_source=PARTNER. | • Create RateEngineRV05Test.java; mock the partner B quote API to return 1360.80 at commit time. • Invoke the rate engine commit path; confirm no PARTNER_B_QUOTE_DEVIATION error thrown. • Assert recorded cost_rate_pay = 1360.80 in the output/persisted record. • Assert rate_source field = PARTNER (not TREASURY). • Assert payout_usd_cost = 9.9206 USD (tolerance 0.0001) computed with the commit-time rate. | RateEngineRV05Test.java with test method testRV05_partnerBQuote_withinTolerance_commits. | • No PARTNER_B_QUOTE_DEVIATION error thrown when deviation=0.8%. • Committed record stores cost_rate_pay=1360.80 (not 1350.00). • rate_source field in output = PARTNER. • payout_usd_cost = 9.9206 USD within 0.0001 using commit-time rate. • Pool-identity assertion passes with the commit-time recomputed values. | 35 | 4.9-T01 | QA | QA-12
4.9-T07 | rate-fx | 4.9 | 4. Rate Engine & FX | Rate engine unit tests vs vectors | 1 | Test RV-06: partner B quote over tolerance (1.2% deviation, returns PARTNER_B_QUOTE_DEVIATION) | Partner B quote deviation > default 1.0% tolerance must abort the transaction. At /rates time, treasury cost_rate_pay=1350.00. At commit time, partner B quote=1366.20 KRW/USD. Deviation = abs(1366.20-1350.00)/1350.00 = 1.2%, exceeds 1.0%. Engine must return error code PARTNER_B_QUOTE_DEVIATION without committing or deducting prefunding. Inputs otherwise same as RV-01. | • Create RateEngineRV06Test.java; mock partner B quote API to return 1366.20 at commit time. • Invoke the rate engine commit path. • Assert the result is an error with code PARTNER_B_QUOTE_DEVIATION. • Assert no transaction record is persisted (check DB or repository mock received no save call). • Assert no prefunding deduction event is emitted. | RateEngineRV06Test.java with test method testRV06_partnerBQuote_overTolerance_rejectsWithError. | • Error code PARTNER_B_QUOTE_DEVIATION returned when deviation=1.2%. • No transaction committed to the database. • Prefunding balance unchanged (no deduction event). • Error code matches the API-05 error catalog constant (not a freeform string). • Tolerance boundary: deviation exactly 1.0% does NOT trigger error (verify with a separate assertion or parameterized case). | 35 | 4.9-T01 | QA | QA-12
4.9-T08 | rate-fx | 4.9 | 4. Rate Engine & FX | Rate engine unit tests vs vectors | 1 | Test RV-07: min-margin boundary exactly 2% combined (rule accepted, transaction commits) | Min combined margin rule for cross-border rules: m_a + m_b >= 2.0%. At exactly 2.0% the rule must be accepted at config time and transactions must commit. RV-07 inputs: target_payout=13500 KRW, coll_ccy=MNT, payout_ccy=KRW, cost_rate_coll=3500.00, cost_rate_pay=1350.00, m_a=0.010, m_b=0.010 (combined=0.020), service_charge=500 MNT. Expected: collection_usd = 10.0000 / 0.980 = 10.2041 USD (tolerance 0.0001); rule saved without error; transaction commits. | • Create RateEngineRV07Test.java with m_a=0.010, m_b=0.010 (combined exactly 2.0%). • Invoke rule-config validation path; assert no MARGIN_BELOW_MINIMUM error. • Run rate engine with these margins; assert collection_usd = 10.2041 USD (tolerance 0.0001). • Assert combined margin recorded as 0.020 (2.0%) in the output. • Call assertPoolIdentity(output). | RateEngineRV07Test.java with test method testRV07_minMarginBoundary_exactly2pct_accepted. | • Rule config validation passes without error when m_a+m_b=0.020 (exactly 2.0%). • collection_usd = 10.2041 USD within 0.0001. • Combined margin 0.020 stored in output. • Pool-identity assertion passes. • Transaction commits successfully (no error thrown). | 25 | 4.9-T01 | QA | QA-12
4.9-T09 | rate-fx | 4.9 | 4. Rate Engine & FX | Rate engine unit tests vs vectors | 1 | Test RV-08: below-minimum margin 1.9% combined (rejected at config time) | Min combined margin for cross-border rules is 2.0%. Any rule with m_a+m_b < 0.020 must be rejected at Admin System config-save time, before any transaction can be attempted. RV-08 inputs: target_payout=13500 KRW, coll_ccy=MNT, payout_ccy=KRW, cost_rate_coll=3500.00, cost_rate_pay=1350.00, m_a=0.010, m_b=0.009 (combined=1.9%), service_charge=500 MNT. Expected: rule save rejected with a validation error referencing the 2.0% minimum; no transaction possible under this rule. | • Create RateEngineRV08Test.java; invoke the rule-config validation service with m_a=0.010, m_b=0.009. • Assert that a MARGIN_BELOW_MINIMUM (or equivalent) validation error is thrown/returned. • Assert the error message explicitly references the 2.0% minimum constraint. • Confirm no rate-engine computation is attempted (verify mock or spy was not called). • Attempt to call the rate engine directly with these margins (bypassing config) and verify it also rejects the input. | RateEngineRV08Test.java with test method testRV08_belowMinMargin_1pt9pct_rejectedAtConfig. | • Rule save raises MARGIN_BELOW_MINIMUM when m_a+m_b=0.019. • Error message text references the 2.0% minimum constraint. • No rate-engine computation invoked for the rejected rule. • Direct rate-engine call with combined margin 0.019 also returns an error (double guard). • m_a+m_b=0.020 does NOT raise the error (boundary test from RV-07 confirms the cut-off is exclusive below 0.020). | 30 | 4.9-T01, 4.9-T08 | QA | QA-12
4.9-T10 | rate-fx | 4.9 | 4. Rate Engine & FX | Rate engine unit tests vs vectors | 1 | Test RV-09: rounding edge case (non-divisible payout 10001 KRW) | Rate engine must use decimal arithmetic throughout; rounding applied only at collection_amount layer (final output), not at intermediate steps. RV-09 inputs: target_payout=10001 KRW, coll_ccy=MNT, payout_ccy=KRW, cost_rate_coll=3500.00, cost_rate_pay=1350.00, m_a=0.015, m_b=0.010, service_charge=500 MNT. Expected intermediates: payout_usd_cost=10001/1350.00=7.40815 USD, collection_usd=7.40815/0.975=7.59810 USD, send_amount=7.59810*3500.00=26593.33 MNT. Pool-identity delta must be <= 0.01 USD; all stored values must carry at least 4 decimal places. | • Create RateEngineRV09Test.java with target_payout=10001 KRW (odd, non-round value). • Assert payout_usd_cost = 7.40815 USD (tolerance 0.00001). • Assert collection_usd = 7.59810 USD (tolerance 0.00001). • Assert send_amount = 26593.33 MNT (tolerance 0.01); verify the value stored in DB/output has at least 4 decimal places. • Call assertPoolIdentity(output) and confirm delta <= 0.01 USD. | RateEngineRV09Test.java with test method testRV09_roundingEdgeCase_nonDivisiblePayout. | • payout_usd_cost = 7.40815 USD within 0.00001 (intermediate stored without premature rounding). • collection_usd = 7.59810 USD within 0.00001. • send_amount = 26593.33 MNT within 0.01. • Pool-identity delta <= 0.01 USD. • All intermediate BigDecimal values stored with scale >= 4 in output object (spot-check via reflection or accessor). | 30 | 4.9-T01 | QA | QA-12
4.9-T11 | rate-fx | 4.9 | 4. Rate Engine & FX | Rate engine unit tests vs vectors | 1 | Test RV-10: service-charge separation (large charge 5000 MNT, USD pool unchanged) | service_charge is a flat fee in Settle A currency added AFTER the USD pool computation; it never enters the USD pool. collection_amount = send_amount + service_charge. RV-10 inputs: same as RV-01 (target_payout=13500 KRW, cost_rate_coll=3500.00, cost_rate_pay=1350.00, m_a=0.015, m_b=0.010) but service_charge=5000 MNT (vs 500 MNT in RV-01). Expected: collection_usd=10.2564 USD (identical to RV-01), send_amount=35897.44 MNT (identical to RV-01), collection_amount=35897.44+5000=40897.44 MNT. Pool-identity check uses only collection_usd/margins/payout_usd_cost (service_charge excluded). | • Create RateEngineRV10Test.java; use RV-01 base fixture but set service_charge=5000 MNT. • Assert collection_usd = 10.2564 USD (tolerance 0.0001) — same as RV-01 confirming service_charge does not affect USD pool. • Assert send_amount = 35897.44 MNT (tolerance 0.01) — identical to RV-01. • Assert collection_amount = 40897.44 MNT (tolerance 0.01). • Verify service_charge is recorded separately in revenue ledger fields, not folded into send_amount. • Call assertPoolIdentity(output) confirming pool identity holds without service_charge in the formula. | RateEngineRV10Test.java with test method testRV10_serviceChargeSeparation_largeCharge. | • collection_usd == 10.2564 USD (identical to RV-01; service_charge has no effect on pool). • send_amount == 35897.44 MNT (identical to RV-01). • collection_amount == 40897.44 MNT within 0.01. • service_charge (5000 MNT) present in revenue ledger field, absent from USD-pool fields. • Pool-identity assertion passes (formula excludes service_charge). | 30 | 4.9-T01, 4.9-T02 | QA | QA-12
4.9-T12 | rate-fx | 4.9 | 4. Rate Engine & FX | Rate engine unit tests vs vectors | 1 | Wire RV-01..RV-10 test suite into CI and enforce zero-tolerance gate | All ten rate-engine test vectors must run in CI on every pull request and must pass with zero failures as a non-negotiable gate (per PM-14: rate-engine test vectors are a non-negotiable acceptance criterion). Pool-identity tolerance is <= 0.01 USD; KRW and USD final amounts must match expected values exactly within floating-point tolerance. The CI job must fail the build if any vector fails. | • Add rate-engine-tests module to the CI pipeline (GitHub Actions or equivalent) under a step named rate-engine-vectors. • Configure the step to run only RV-01..RV-10 test classes (tag or test suite class) so failures are surfaced distinctly from other unit tests. • Set the CI step to exit-code 1 on any test failure (fail-fast: do not continue to integration tests if vectors fail). • Add a build badge or test-report artifact that shows the 10 vector results per run. • Verify locally that a deliberate mutation to the rate engine formula (e.g., change divisor from 0.975 to 0.97) causes exactly the relevant vector(s) to fail and the CI step to report red. | CI pipeline configuration (e.g., .github/workflows/rate-engine-vectors.yml or equivalent step in existing pipeline) that runs the 10 vector tests as a mandatory gate. | • CI step rate-engine-vectors runs on every PR and push to main. • All 10 vector tests (T02..T11) appear in the test report by name. • Deliberate formula mutation causes CI gate to fail (mutation test confirmed locally). • CI step is listed as a required status check protecting the main branch. • Test report artifact is uploaded and accessible from the CI run summary. | 45 | 4.9-T02, 4.9-T03, 4.9-T04, 4.9-T05, 4.9-T06, 4.9-T07, 4.9-T08, 4.9-T09, 4.9-T10, 4.9-T11 | QA | QA-12
5.1-T01 | transaction-mgmt | 5.1 | 5. Transaction Processing (MPM/CPM) | Transaction state machine | 1 | Define TransactionStatus enum with all valid states | WBS 5.1. The Transaction Orchestrator owns the state machine for every payment. States (from SAD-02 §5.2 and DAT-03 §11.3): QUOTED, PENDING_DEBIT, DEBITED, SCHEME_SENT, APPROVED, UNCERTAIN, FAILED, REVERSED, REFUNDED. QUOTED = rate quote issued; PENDING_DEBIT = CommitTransaction received, prefunding deduction in progress (OVERSEAS only); DEBITED = prefunding deducted or skipped (LOCAL); SCHEME_SENT = adapter call dispatched; APPROVED = scheme confirmed success; UNCERTAIN = no scheme response within SLA; FAILED = terminal failure; REVERSED = same-day cancel post-APPROVED; REFUNDED = post-settlement refund. Terminal states: FAILED, REVERSED, REFUNDED. | • Create domain/model/TransactionStatus.java (Java enum) with values: QUOTED, PENDING_DEBIT, DEBITED, SCHEME_SENT, APPROVED, UNCERTAIN, FAILED, REVERSED, REFUNDED. • Add a boolean isTerminal() helper that returns true for FAILED, REVERSED, REFUNDED only. • Add Javadoc on each constant citing the SAD-02 §5.2 meaning. • Annotate with @JsonValue so JSON serialisation uses the enum name as-is. | domain/model/TransactionStatus.java — enum with 9 values and isTerminal() method | • TransactionStatus.values().length == 9. • isTerminal() returns true for FAILED, REVERSED, REFUNDED and false for the other six. • Jackson serialises QUOTED to the JSON string "QUOTED" (not an ordinal or lowercase). • PENDING_DEBIT and DEBITED are distinct constants (typo regression guard). | 20 |  | BE | RATE-04, API-05
5.1-T02 | transaction-mgmt | 5.1 | 5. Transaction Processing (MPM/CPM) | Transaction state machine | 1 | Define permitted transition table as a static map | WBS 5.1. Only specific state-to-state transitions are legal (SAD-02 §5.2 state diagram): QUOTED->PENDING_DEBIT (OVERSEAS CommitTransaction); QUOTED->DEBITED (LOCAL CommitTransaction, no prefund); QUOTED->FAILED (TTL expired or validation failure); PENDING_DEBIT->DEBITED (prefund deducted); PENDING_DEBIT->FAILED (insufficient prefunding); DEBITED->SCHEME_SENT (scheme adapter dispatched); SCHEME_SENT->APPROVED (scheme success); SCHEME_SENT->FAILED (scheme reject/error); SCHEME_SENT->UNCERTAIN (timeout); UNCERTAIN->APPROVED (batch reconciliation success); UNCERTAIN->FAILED (batch reconciliation failure); APPROVED->REVERSED (same-day cancel); APPROVED->REFUNDED (post-settlement refund). Terminal states have no outgoing transitions. All other pairs are forbidden. | • Create domain/statemachine/TransactionTransitions.java with a private static final Map<TransactionStatus, Set<TransactionStatus>> ALLOWED_TRANSITIONS. • Populate the map exactly as the 13 pairs above; terminal states map to an empty set. • Add a static boolean isAllowed(TransactionStatus from, TransactionStatus to) helper. • Add a static Set<TransactionStatus> allowedFrom(TransactionStatus from) helper. • Unit-test file referenced in 5.1-T09 will verify this map. | domain/statemachine/TransactionTransitions.java with ALLOWED_TRANSITIONS map and two static helpers | • isAllowed(QUOTED, PENDING_DEBIT) == true; isAllowed(QUOTED, DEBITED) == true. • isAllowed(PENDING_DEBIT, APPROVED) == false (not a permitted pair). • isAllowed(FAILED, QUOTED) == false (no transitions out of terminal state). • allowedFrom(SCHEME_SENT) returns exactly {APPROVED, FAILED, UNCERTAIN}. • Map contains entries for all 9 states (including terminal states mapping to empty sets). | 25 | 5.1-T01 | BE | RATE-04, API-05
5.1-T03 | transaction-mgmt | 5.1 | 5. Transaction Processing (MPM/CPM) | Transaction state machine | 1 | Create TransitionBlockedException for illegal state transitions | WBS 5.1. When code attempts a transition not in the ALLOWED_TRANSITIONS map (5.1-T02), a typed exception must be thrown rather than a generic RuntimeException. This exception is caught by the orchestrator and translated to an API error. It must carry from, to, and txn_ref fields so the caller can log structured context. It is NOT an end-user-facing error — it indicates a programming bug or race condition. | • Create domain/statemachine/TransitionBlockedException.java extending RuntimeException. • Fields: TransactionStatus from, TransactionStatus to, String txnRef. • Constructor: TransitionBlockedException(String txnRef, TransactionStatus from, TransactionStatus to). • Override getMessage() to return a string containing txnRef, from, and to. • Ensure all three fields are accessible via getters. | domain/statemachine/TransitionBlockedException.java | • new TransitionBlockedException("txn_abc", QUOTED, APPROVED).getMessage() contains "QUOTED", "APPROVED", and "txn_abc". • getFrom(), getTo(), getTxnRef() return the values passed to the constructor. • Class extends RuntimeException (unchecked). • No swallowing of the original cause — constructor variant accepting a Throwable cause is also present. | 20 | 5.1-T01 | BE | RATE-04, API-05
5.1-T04 | transaction-mgmt | 5.1 | 5. Transaction Processing (MPM/CPM) | Transaction state machine | 1 | Implement TransactionStateMachine.transition() with guard and persistence | WBS 5.1. The Transaction Orchestrator is the only component that may change a transaction's status. The transition must be atomic: (1) verify the transition is allowed via TransactionTransitions.isAllowed(); (2) SELECT FOR UPDATE the transaction row to prevent concurrent transitions on the same txn; (3) assert current DB status equals expected from-state (optimistic check); (4) UPDATE status in the transaction table; (5) append a transaction_event row (step number derived from new status, see 5.1-T06); (6) return the updated entity. If the transition is not allowed, throw TransitionBlockedException. If the DB current status differs from expected (concurrent update), throw a ConcurrentTransitionException (new, see 5.1-T05). | • Create service/statemachine/TransactionStateMachine.java with method: TransactionEntity transition(String txnRef, TransactionStatus expectedFrom, TransactionStatus to, TransitionContext ctx). • SELECT the transaction row FOR UPDATE inside a @Transactional method. • Assert entity.status == expectedFrom; else throw ConcurrentTransitionException. • Call TransactionTransitions.isAllowed(expectedFrom, to); else throw TransitionBlockedException. • UPDATE transaction.status = to, transaction.updated_at = now(); set completed_at when transitioning to APPROVED, FAILED, or REVERSED. • Delegate event appending to EventTrailService.recordStep(txn, to, ctx) (see 5.1-T06). | service/statemachine/TransactionStateMachine.java with atomic transition() method | • Calling transition(txnRef, QUOTED, PENDING_DEBIT, ctx) on a QUOTED row in test DB changes status to PENDING_DEBIT and appends an event row. • Calling transition on a row already at DEBITED with expectedFrom=QUOTED throws ConcurrentTransitionException (simulates race condition). • Calling transition(txnRef, QUOTED, APPROVED, ctx) throws TransitionBlockedException (not an allowed pair). • completed_at is set when transitioning to APPROVED; it remains null when transitioning to DEBITED. • The entire operation is inside a single DB transaction (rolled back on exception). | 55 | 5.1-T02, 5.1-T03, 5.1-T05, 5.1-T06 | BE | RATE-04, API-05
5.1-T05 | transaction-mgmt | 5.1 | 5. Transaction Processing (MPM/CPM) | Transaction state machine | 1 | Create ConcurrentTransitionException for stale-state conflicts | WBS 5.1. When TransactionStateMachine.transition() reads the DB row FOR UPDATE and finds the current status differs from the expectedFrom argument (another thread already changed it), it must throw ConcurrentTransitionException rather than silently proceeding or throwing a generic error. The caller (orchestrator) retries or returns a conflict error to the partner API. Fields needed: txnRef, expectedStatus, actualStatus. | • Create domain/statemachine/ConcurrentTransitionException.java extending RuntimeException. • Fields: String txnRef, TransactionStatus expectedStatus, TransactionStatus actualStatus. • Constructor: ConcurrentTransitionException(String txnRef, TransactionStatus expected, TransactionStatus actual). • getMessage() returns a string referencing all three fields. • Provide getters for all three fields. | domain/statemachine/ConcurrentTransitionException.java | • new ConcurrentTransitionException("t1", QUOTED, DEBITED).getMessage() contains "QUOTED" and "DEBITED". • getExpectedStatus() == QUOTED, getActualStatus() == DEBITED in the above example. • Class is unchecked (extends RuntimeException). • Distinct from TransitionBlockedException — they carry different semantics (race vs. disallowed pair). | 15 | 5.1-T01 | BE | RATE-04, API-05
5.1-T06 | transaction-mgmt | 5.1 | 5. Transaction Processing (MPM/CPM) | Transaction state machine | 1 | Implement EventTrailService.recordStep() for 8-step event trail | WBS 5.1 and SEC-09 §6.1. Every transaction must carry an immutable 8-step event trail stored in the transaction_event table (DAT-03 §5.3). The 8 steps and their event_type strings: (1) rate_quote_issued, (2) payment_initiated, (3) prefund_deducted (OVERSEAS only; absent for LOCAL), (4) scheme_request_sent, (5) scheme_response_received, (6) transaction_committed, (7) webhook_dispatched, (8) webhook_delivered. Columns: id BIGINT PK, txn_id FK, step INT (1-8), event_type VARCHAR(50), occurred_at TIMESTAMPTZ, duration_ms INT (ms since previous step), detail JSONB, created_at. Records are INSERT-only (never updated or deleted; 7-year retention). For LOCAL partners, step 3 row is still inserted with a note in detail: {skipped: true, reason: LOCAL_PARTNER_NO_PREFUND}. | • Create service/audit/EventTrailService.java with method: void recordStep(long txnId, int step, String eventType, Instant occurredAt, Long previousStepOccurredAt, Map<String,Object> detail). • Compute duration_ms = (previousStepOccurredAt != null) ? ChronoUnit.MILLIS.between(previousStepOccurredAt, occurredAt) : null. • INSERT into transaction_event: txn_id, step, event_type, occurred_at, duration_ms, detail (serialised as JSONB), created_at=now(). • Do not update or delete any existing event rows (append-only). • Add overloaded convenience method recordStepNow(long txnId, int step, String eventType, Map<String,Object> detail) that uses Instant.now() for occurred_at. | service/audit/EventTrailService.java with append-only recordStep() | • Calling recordStep for steps 1..8 inserts 8 rows; no UPDATE statements are issued. • duration_ms for step 1 is null; for step 2 it equals the ms elapsed since step 1 occurred_at. • Attempting to INSERT a duplicate (txn_id, step) pair raises a DB unique constraint violation (the table must have a UNIQUE(txn_id, step) constraint — verify migration exists). • detail JSONB is stored and retrievable as a Java Map. • For a LOCAL partner step 3 row: detail contains key skipped=true. | 40 | 5.1-T07 | BE | RATE-04, API-05
5.1-T07 | transaction-mgmt | 5.1 | 5. Transaction Processing (MPM/CPM) | Transaction state machine | 1 | Migration: add UNIQUE(txn_id, step) constraint to transaction_event | WBS 5.1. The transaction_event table (DAT-03 §5.3) must enforce exactly one row per (transaction, step) pair to guarantee the 8-step trail is non-duplicate and append-only. Without this constraint, a retry bug could insert duplicate step rows. Columns already exist (from DAT-03 migration): id, txn_id, step, event_type, occurred_at, duration_ms, detail, created_at. This ticket adds only the missing constraint and a covering index. | • Create migration V5_1_001__transaction_event_unique_step.sql (Flyway naming). • ADD CONSTRAINT uq_txn_event_step UNIQUE (txn_id, step) — ensures no duplicate step per transaction. • Add index idx_txn_event_txn_id ON transaction_event(txn_id) if not already present (for lookup by txn_id). • Run migration against local dev DB on port 5433 and verify with \d transaction_event. | Flyway migration V5_1_001__transaction_event_unique_step.sql applied to dev DB | • \d transaction_event shows constraint uq_txn_event_step on (txn_id, step). • Inserting two rows with same txn_id=1 and step=1 raises a unique violation. • Inserting txn_id=1 step=1 and txn_id=1 step=2 succeeds (different steps). • Inserting txn_id=1 step=1 and txn_id=2 step=1 succeeds (different transactions). | 20 |  | BE | RATE-04, API-05
5.1-T08 | transaction-mgmt | 5.1 | 5. Transaction Processing (MPM/CPM) | Transaction state machine | 1 | Migration: add status CHECK constraint to transaction table | WBS 5.1. The transaction.status column (DAT-03 §5.2) must be constrained to the 9 valid state-machine values: QUOTED, PENDING_DEBIT, DEBITED, SCHEME_SENT, APPROVED, UNCERTAIN, FAILED, REVERSED, REFUNDED. Without a DB CHECK constraint, a code bug could store an arbitrary string. This migration adds the constraint without touching other columns. | • Create migration V5_1_002__transaction_status_check.sql. • ALTER TABLE transaction ADD CONSTRAINT chk_txn_status CHECK (status IN ('QUOTED','PENDING_DEBIT','DEBITED','SCHEME_SENT','APPROVED','UNCERTAIN','FAILED','REVERSED','REFUNDED')). • Run on local dev DB (port 5433). • Verify constraint name appears in \d transaction. | Flyway migration V5_1_002__transaction_status_check.sql applied to dev DB | • INSERT with status='QUOTED' succeeds. • INSERT with status='INVALID_STATUS' raises a check-constraint violation. • All 9 valid state names can be inserted without error. • Migration is idempotent when run twice (Flyway versioned migration — second run is a no-op). | 15 |  | BE | RATE-04, API-05
5.1-T09 | transaction-mgmt | 5.1 | 5. Transaction Processing (MPM/CPM) | Transaction state machine | 1 | Unit tests for TransactionTransitions allowed/forbidden pairs | WBS 5.1. The transition table defined in TransactionTransitions.java (5.1-T02) is the ground truth for legal transitions. This ticket is an exhaustive unit-test suite. Allowed pairs (13 total): QUOTED->PENDING_DEBIT, QUOTED->DEBITED, QUOTED->FAILED, PENDING_DEBIT->DEBITED, PENDING_DEBIT->FAILED, DEBITED->SCHEME_SENT, SCHEME_SENT->APPROVED, SCHEME_SENT->FAILED, SCHEME_SENT->UNCERTAIN, UNCERTAIN->APPROVED, UNCERTAIN->FAILED, APPROVED->REVERSED, APPROVED->REFUNDED. All other pairs are forbidden (9x9=81 minus 13 = 68 forbidden pairs, plus self-transitions = all forbidden). Terminal states: FAILED, REVERSED, REFUNDED have zero outgoing. | • Create test class TransactionTransitionsTest.java. • Parameterised test @AllowedTransitions: for each of the 13 allowed pairs, assert isAllowed(from, to) == true. • Parameterised test @ForbiddenTransitions: spot-check at least 12 forbidden pairs including all self-transitions, all terminal outgoing, and at least two backward transitions (e.g. APPROVED->QUOTED, DEBITED->QUOTED). • Test @TerminalHasNoOutgoing: for FAILED, REVERSED, REFUNDED verify allowedFrom returns an empty set. • Test @AllStatesPresent: all 9 TransactionStatus values appear as keys in the transition map. | test/statemachine/TransactionTransitionsTest.java with parameterised tests covering all 13 allowed pairs and 12+ forbidden pairs | • All 13 allowed pair assertions pass. • All forbidden pair assertions (isAllowed returns false) pass. • FAILED, REVERSED, REFUNDED return empty allowedFrom sets. • APPROVED->REVERSED is allowed; REVERSED->APPROVED is forbidden. • No test uses hardcoded ordinal integers — all references use the enum constants. | 35 | 5.1-T02 | BE | RATE-04, API-05
5.1-T10 | transaction-mgmt | 5.1 | 5. Transaction Processing (MPM/CPM) | Transaction state machine | 1 | MPM QUOTED->PENDING_DEBIT transition on CommitTransaction (OVERSEAS) | WBS 5.1 and SAD-02 §6.1. For OVERSEAS partners, POST /v1/payments triggers: (1) verify quote TTL not expired (valid_until > now()); if expired, transition QUOTED->FAILED with error RATE_QUOTE_EXPIRED and return HTTP 422; (2) validate idempotency key (24h Redis dedup); (3) if valid, call TransactionStateMachine.transition(txnRef, QUOTED, PENDING_DEBIT, ctx) — this begins atomic prefunding deduction (see 5.1-T11). The partner type is determined from the Rule linked to the rate_quote_id. TTL check uses valid_until field copied from rate_quote at transaction creation. No scheme call happens at this step. | • In PaymentOrchestrator.commitMpm(CommitRequest req): load transaction by txn_ref; verify valid_until > Instant.now(); if expired, call transition(txnRef, QUOTED, FAILED, ctx.withError(RATE_QUOTE_EXPIRED)) and return error. • If partner.type == OVERSEAS, call transition(txnRef, QUOTED, PENDING_DEBIT, ctx). • Record event trail step 2 (payment_initiated) via EventTrailService. • Return 202 Accepted to the API layer (prefunding deduction is next step, 5.1-T11). • Add idempotency dedup before any state mutation: if txn already past QUOTED, return cached response. | PaymentOrchestrator.commitMpm() handling OVERSEAS path: QUOTED->PENDING_DEBIT or QUOTED->FAILED on expiry | • CommitTransaction with valid TTL on OVERSEAS partner transitions status to PENDING_DEBIT. • CommitTransaction with expired TTL (valid_until in the past) transitions to FAILED, returns HTTP 422, error code RATE_QUOTE_EXPIRED, and no prefunding deduction occurs. • Second call with the same Idempotency-Key and identical body returns the cached first response without retransitioning. • Event trail step 2 row (payment_initiated) is inserted. • Partner.type == LOCAL does not enter this path (no PENDING_DEBIT transition for LOCAL). | 50 | 5.1-T04, 5.1-T06, 5.1-T09 | BE | RATE-04, API-05
5.1-T11 | transaction-mgmt | 5.1 | 5. Transaction Processing (MPM/CPM) | Transaction state machine | 1 | PENDING_DEBIT->DEBITED: atomic prefunding deduction for OVERSEAS | WBS 5.1 and SAD-02 §5.2. Prefunding deduction uses SELECT FOR UPDATE on the prefunding_account row (DAT-03 §6.1, balance DECIMAL(20,4) in USD). Deduct prefunding_deducted_usd from the account balance. If balance < deduction_amount, transition PENDING_DEBIT->FAILED with error INSUFFICIENT_PREFUNDING (HTTP 402) and do NOT call the scheme. If deduction succeeds, INSERT a prefunding_ledger_entry (type=DEBIT, amount, txn_ref), update prefunding_account.balance, then transition PENDING_DEBIT->DEBITED. The scheme must never be called without a prior successful deduction (AD-06). prefunding_deducted_usd on the transaction equals collection_usd (the Step 1-4 USD pool amount, not collection_amount which includes service_charge). | • In PrefundingService.deductForTransaction(txnId, partnerId, deductionUsd): open @Transactional, SELECT prefunding_account WHERE partner_id=? FOR UPDATE. • If account.balance < deductionUsd: call transition(txnRef, PENDING_DEBIT, FAILED, ctx.withError(INSUFFICIENT_PREFUNDING)); throw InsufficientPrefundingException. • Else: UPDATE balance = balance - deductionUsd; INSERT prefunding_ledger_entry(txn_id, type=DEBIT, amount=deductionUsd, occurred_at=now()). • Call transition(txnRef, PENDING_DEBIT, DEBITED, ctx); record event trail step 3 (prefund_deducted). • Return updated balance. | PrefundingService.deductForTransaction() with atomic SELECT FOR UPDATE, balance check, ledger entry, and transition to DEBITED | • Deduction of 35.77 USD from a 100.00 USD balance transitions to DEBITED and sets account.balance to 64.23 USD. • Deduction of 110.00 USD from a 100.00 USD balance transitions to FAILED, returns INSUFFICIENT_PREFUNDING, and balance remains 100.00 USD. • Two concurrent threads deducting 70.00 USD each from a 100.00 USD balance: exactly one succeeds (DEBITED), one fails (FAILED) — no overdraft. • prefunding_ledger_entry row is inserted with type=DEBIT and amount matching deductionUsd. • Event trail step 3 (prefund_deducted) is recorded with detail containing balance_before and balance_after. | 55 | 5.1-T04, 5.1-T06, 5.1-T07 | BE | RATE-04, API-05
5.1-T12 | transaction-mgmt | 5.1 | 5. Transaction Processing (MPM/CPM) | Transaction state machine | 1 | MPM QUOTED->DEBITED transition for LOCAL partners (no prefunding) | WBS 5.1 and SAD-02 §5.2. For LOCAL partners (partner.type == LOCAL, e.g. GME Remit), CommitTransaction skips prefunding deduction entirely and transitions directly QUOTED->DEBITED. There is no PENDING_DEBIT state for LOCAL. Event trail step 3 (prefund_deducted) is still inserted with detail: {skipped: true, reason: LOCAL_PARTNER_NO_PREFUND} per A-10 (all 8 steps present on every transaction, even if some are skipped). The idempotency and TTL checks from 5.1-T10 still apply. | • In PaymentOrchestrator.commitMpm(): after partner-type check, if partner.type == LOCAL, call transition(txnRef, QUOTED, DEBITED, ctx). • Record event trail step 2 (payment_initiated). • Record event trail step 3 (prefund_deducted) with detail={skipped:true, reason:'LOCAL_PARTNER_NO_PREFUND'}. • Proceed directly to scheme dispatch (5.1-T13). • Do not call PrefundingService.deductForTransaction() for LOCAL partners. | PaymentOrchestrator.commitMpm() LOCAL branch: QUOTED->DEBITED with skipped step-3 event trail | • CommitTransaction for LOCAL partner transitions QUOTED->DEBITED in one step (no PENDING_DEBIT row in DB history). • Event trail step 3 row is present with detail.skipped == true and detail.reason == LOCAL_PARTNER_NO_PREFUND. • prefunding_account balance is unchanged for the LOCAL partner's account (or no account exists). • LOCAL partner path does NOT call PrefundingService.deductForTransaction(). • OVERSEAS partner path still goes through PENDING_DEBIT (no regression). | 35 | 5.1-T10 | BE | RATE-04, API-05
5.1-T13 | transaction-mgmt | 5.1 | 5. Transaction Processing (MPM/CPM) | Transaction state machine | 1 | DEBITED->SCHEME_SENT transition on MPM scheme adapter dispatch | WBS 5.1. After reaching DEBITED (prefund deducted or LOCAL skip), the Orchestrator calls the ZeroPay Scheme Adapter's submitMpm(). Before the call, transition DEBITED->SCHEME_SENT and record event trail step 4 (scheme_request_sent). The transition must happen BEFORE the adapter call so that if the process crashes mid-call, the DB correctly shows SCHEME_SENT and the reconciliation engine can identify the transaction. The scheme_id and merchant_id are read from the transaction record. hub_txn_ref is the GMEPay+ reference sent to ZeroPay. | • In PaymentOrchestrator, after DEBITED state: call transition(txnRef, DEBITED, SCHEME_SENT, ctx). • Record event trail step 4 (scheme_request_sent) with detail={hub_txn_ref, merchant_id, scheme_id}. • Call schemeAdapter.submitMpm(hubTxnRef, merchantId, targetPayout, payoutCcy). • Handle response in 5.1-T14 (synchronous success), 5.1-T15 (scheme reject), 5.1-T16 (timeout/UNCERTAIN). | PaymentOrchestrator DEBITED->SCHEME_SENT transition and scheme adapter call invocation | • After commitMpm for OVERSEAS partner, DB shows status=SCHEME_SENT before adapter returns. • Event trail step 4 row contains detail.hub_txn_ref matching the transaction's hub_txn_ref. • If submitMpm() throws a network exception immediately, status is SCHEME_SENT (not DEBITED), enabling reconciliation. • The state transition to SCHEME_SENT uses TransactionStateMachine.transition() not a direct SQL UPDATE. • Transition happens before the HTTP call to ZeroPay — verified by test with a mock adapter that asserts DB state in its stub. | 40 | 5.1-T04, 5.1-T06, 5.1-T11, 5.1-T12 | BE | RATE-04, API-05
5.1-T14 | transaction-mgmt | 5.1 | 5. Transaction Processing (MPM/CPM) | Transaction state machine | 1 | SCHEME_SENT->APPROVED transition on synchronous scheme success (MPM) | WBS 5.1. When submitMpm() returns a successful MpmSubmitResponse (scheme_approval_code present), the Orchestrator: (1) transitions SCHEME_SENT->APPROVED; (2) sets transaction.completed_at = now(); (3) rate-locks all USD pool values (they were already copied from rate_quote at commit but now marked immutable — see 5.1-T18 for immutability enforcement); (4) records event trail step 5 (scheme_response_received) and step 6 (transaction_committed); (5) stores scheme_ref from the adapter response; (6) dispatches the payment.approved webhook (step 7/8 handled by 5.1-T19). The APPROVED->terminal path completes here. | • In PaymentOrchestrator, on successful adapter response: call transition(txnRef, SCHEME_SENT, APPROVED, ctx.withSchemeRef(approvalCode)). • Set transaction.completed_at = now() and transaction.scheme_ref = approvalCode in the same DB transaction. • Record event trail step 5 (scheme_response_received, detail={scheme_approval_code}). • Record event trail step 6 (transaction_committed, detail snapshot: collection_usd, payout_usd_cost, offer_rate_coll, cross_rate). • Enqueue payment.approved webhook event (async) via WebhookService.enqueue(txnRef, APPROVED). | PaymentOrchestrator SCHEME_SENT->APPROVED transition with completed_at, scheme_ref, event steps 5-6, and webhook enqueue | • After successful submitMpm, transaction.status == APPROVED and completed_at is set. • transaction.scheme_ref equals the scheme_approval_code returned by the adapter. • Event trail has step 5 with event_type scheme_response_received and step 6 with event_type transaction_committed. • Step 6 detail JSONB contains collection_usd, payout_usd_cost, offer_rate_coll as numeric strings. • WebhookService.enqueue is called once with event type payment.approved. | 45 | 5.1-T13 | BE | RATE-04, API-05
5.1-T15 | transaction-mgmt | 5.1 | 5. Transaction Processing (MPM/CPM) | Transaction state machine | 1 | SCHEME_SENT->FAILED transition on synchronous scheme rejection | WBS 5.1. When submitMpm() returns a rejection (MpmSubmitResponse with a scheme error code, or adapter throws a SchemeRejectException), the Orchestrator transitions SCHEME_SENT->FAILED. For OVERSEAS partners, the prefunding deduction that occurred at PENDING_DEBIT->DEBITED must be REVERSED immediately: insert a CREDIT entry to the prefunding ledger and restore the balance. The scheme_ref from the rejection response is stored if present. Event trail step 5 (scheme_response_received, detail={error_code}) and step 6 (transaction_committed, detail={outcome:FAILED}) are recorded. Dispatch payment.failed webhook. | • On SchemeRejectException or non-success adapter response: call transition(txnRef, SCHEME_SENT, FAILED, ctx.withError(schemeErrorCode)). • If partner.type == OVERSEAS: call PrefundingService.reverseDeduction(txnRef, partnerId) — INSERT CREDIT ledger entry and UPDATE balance += amount. • Record event trail step 5 (scheme_response_received, detail={scheme_error_code, reason}). • Record event trail step 6 (transaction_committed, detail={outcome:FAILED}). • Enqueue payment.failed webhook. | PaymentOrchestrator SCHEME_SENT->FAILED path with prefunding reversal for OVERSEAS and event steps 5-6 | • On scheme rejection, transaction.status == FAILED. • OVERSEAS partner balance is restored: balance_after == balance_before_deduction (deduction reversed). • LOCAL partner has no prefunding reversal logic triggered. • prefunding_ledger_entry CREDIT row inserted with amount matching the original DEBIT row. • Event trail step 5 detail.scheme_error_code is set; step 6 detail.outcome == FAILED. | 50 | 5.1-T14, 5.1-T11 | BE | RATE-04, API-05
5.1-T16 | transaction-mgmt | 5.1 | 5. Transaction Processing (MPM/CPM) | Transaction state machine | 1 | SCHEME_SENT->UNCERTAIN transition on scheme timeout | WBS 5.1. When the scheme adapter call times out or returns no response within scheme SLA, the Orchestrator transitions SCHEME_SENT->UNCERTAIN. The prefunding deduction is HELD (not reversed) — it will be reversed only if batch reconciliation later confirms FAILED (SAD-02 §5.2). Event trail step 5 is recorded with event_type scheme_response_received, detail={outcome:TIMEOUT}. No webhook is dispatched yet. The transaction is flagged for the Settlement Engine's UNCERTAIN resolution job. If UNCERTAIN remains unresolved after 24 hours, an ops alert must fire (monitoring hook, not this ticket). | • On adapter call timeout (caught exception / timeout after scheme SLA): call transition(txnRef, SCHEME_SENT, UNCERTAIN, ctx.withTimeout()). • Record event trail step 5 (scheme_response_received, detail={outcome:TIMEOUT, timed_out_at: now()}). • Do NOT reverse prefunding deduction (balance stays reduced). • Do NOT dispatch any webhook at this point. • Set transaction.uncertain_since = now() for the 24h alert threshold (add column if missing in migration 5.1-T07 or a new migration). | PaymentOrchestrator SCHEME_SENT->UNCERTAIN path: status change, held deduction, step-5 event, no webhook | • On adapter timeout, transaction.status == UNCERTAIN. • Prefunding account balance is NOT restored (deduction held). • Event trail step 5 detail.outcome == TIMEOUT. • No payment.failed or payment.approved webhook is enqueued. • transaction.uncertain_since timestamp is set (for 24h expiry alert). | 40 | 5.1-T13 | BE | RATE-04, API-05
5.1-T17 | transaction-mgmt | 5.1 | 5. Transaction Processing (MPM/CPM) | Transaction state machine | 1 | UNCERTAIN->APPROVED and UNCERTAIN->FAILED transitions via batch reconciliation | WBS 5.1. The Settlement Engine calls the Orchestrator to resolve UNCERTAIN transactions after processing ZP0012 (payment result) or ZP0022 (refund result) from ZeroPay (~05:00 KST). If ZP0012 record for the hub_txn_ref has result_code=00: transition UNCERTAIN->APPROVED (same logic as 5.1-T14 but without re-calling the scheme). If result_code != 00 or absent after 24h: transition UNCERTAIN->FAILED AND reverse prefunding for OVERSEAS. Reconciliation must be idempotent: calling it twice for the same txnRef is a no-op if already APPROVED or FAILED. | • Create method PaymentOrchestrator.resolveUncertain(String txnRef, ReconciliationOutcome outcome) where outcome is APPROVED or FAILED. • If transaction.status != UNCERTAIN, log a warning and return (idempotency guard). • If outcome == APPROVED: call transition(txnRef, UNCERTAIN, APPROVED, ctx); set completed_at; record step 5 detail update and step 6 (transaction_committed); enqueue payment.approved webhook. • If outcome == FAILED: call transition(txnRef, UNCERTAIN, FAILED, ctx); reverse OVERSEAS prefunding via PrefundingService.reverseDeduction(); record step 6; enqueue payment.failed webhook. • Log reconciliation_source (ZP0012/ZP0022/MANUAL) in the event detail. | PaymentOrchestrator.resolveUncertain() handling both APPROVED and FAILED outcomes with prefunding reversal and idempotency guard | • resolveUncertain(txnRef, APPROVED) on an UNCERTAIN transaction transitions to APPROVED and enqueues payment.approved. • resolveUncertain(txnRef, FAILED) on an UNCERTAIN transaction transitions to FAILED and reverses OVERSEAS prefunding. • Calling resolveUncertain twice with APPROVED is a no-op on the second call (idempotency). • OVERSEAS balance is restored only on FAILED resolution, not on APPROVED. • Step 6 event trail detail includes reconciliation_source field. | 50 | 5.1-T14, 5.1-T15, 5.1-T16 | BE | RATE-04, API-05
5.1-T18 | transaction-mgmt | 5.1 | 5. Transaction Processing (MPM/CPM) | Transaction state machine | 1 | Enforce rate-lock immutability on APPROVED transaction fields | WBS 5.1 and SEC-09 §5.4. Once a transaction transitions to APPROVED (or is resolved via reconciliation), the following fields must never be updated: collection_usd, payout_usd_cost, collection_margin_usd, payout_margin_usd, offer_rate_coll, cross_rate, cost_rate_coll, cost_rate_pay, send_amount, service_charge, collection_amount. Enforcement: (1) DB-level: add a BEFORE UPDATE trigger or application-level guard; (2) application-level: TransactionEntity must throw ImmutableFieldException if any of these fields is set after status reaches APPROVED. This applies to committed transactions whether APPROVED by direct scheme response or by reconciliation. | • Create ImmutableFieldException extends RuntimeException with fields: String txnRef, String fieldName, TransactionStatus currentStatus. • In TransactionEntity add a setter guard: before any of the locked fields is mutated, check if status is APPROVED, REVERSED, or REFUNDED; if yes, throw ImmutableFieldException. • Add a DB CHECK or trigger in migration V5_1_003__rate_lock_immutability.sql that prevents UPDATE on locked columns when status = APPROVED (PostgreSQL: use a rule or a check trigger). • Unit test: set an APPROVED transaction's collection_usd to a different value; assert ImmutableFieldException thrown. • Verify that updating non-locked fields (e.g. scheme_ref, completed_at) does not throw. | ImmutableFieldException.java and setter guards in TransactionEntity, plus migration V5_1_003 for DB-level enforcement | • Setting collection_usd on an APPROVED transaction throws ImmutableFieldException with fieldName=collection_usd. • Setting scheme_ref on an APPROVED transaction succeeds (non-locked field). • ImmutableFieldException message includes txnRef and fieldName. • The DB trigger/rule prevents a raw SQL UPDATE on collection_usd WHERE status=APPROVED. • QUOTED and DEBITED transactions can still have locked fields set (they are not yet locked). | 45 | 5.1-T04, 5.1-T07 | BE | RATE-04, API-05
5.1-T19 | transaction-mgmt | 5.1 | 5. Transaction Processing (MPM/CPM) | Transaction state machine | 1 | APPROVED->REVERSED transition: same-day cancel via Cancel API | WBS 5.1 and API-05 §HC-007. Partners may cancel a payment on the same business day via POST /v1/payments/{id}/cancel. Precondition: status must be APPROVED and cancellation must be within the same KST calendar day as committed_at. If outside the same day, reject with CANCEL_NOT_ALLOWED (HTTP 409). On cancellation: (1) transition APPROVED->REVERSED; (2) reverse OVERSEAS prefunding (re-credit the prefunding_account); (3) store cancel reason and actor; (4) dispatch payment.reversed webhook. Admin-initiated cancel follows the same path via the Admin API. | • Create PaymentOrchestrator.cancelPayment(String txnRef, String actor, String reason): load transaction; validate status == APPROVED; validate same-day in KST (committed_at.atZone(KST).toLocalDate() == LocalDate.now(KST)); else throw CancelNotAllowedException. • Call transition(txnRef, APPROVED, REVERSED, ctx.withActor(actor).withReason(reason)). • If partner.type == OVERSEAS: call PrefundingService.reverseDeduction(txnRef, partnerId) to re-credit balance. • Store cancel_reason and cancelled_by on the transaction record. • Enqueue payment.reversed webhook. | PaymentOrchestrator.cancelPayment() with same-day KST guard, APPROVED->REVERSED transition, prefunding reversal, and webhook | • Cancel on an APPROVED transaction with committed_at today (KST) transitions to REVERSED. • Cancel on an APPROVED transaction with committed_at yesterday (KST) throws CancelNotAllowedException / returns HTTP 409 CANCEL_NOT_ALLOWED. • OVERSEAS partner balance is restored after cancellation. • payment.reversed webhook is enqueued. • cancel_reason and cancelled_by are persisted on the transaction row. | 45 | 5.1-T14, 5.1-T11 | BE | RATE-04, API-05
5.1-T20 | transaction-mgmt | 5.1 | 5. Transaction Processing (MPM/CPM) | Transaction state machine | 1 | APPROVED->REFUNDED transition: admin-initiated post-settlement refund | WBS 5.1 and PRD-07 §10.3. Post-settlement refunds are admin-only (Phase 1). The refund state sub-machine is: REFUND_PENDING -> REFUND_SUBMITTED -> REFUND_CONFIRMED -> REFUNDED (or REFUND_FAILED). When admin initiates a refund on an APPROVED transaction: (1) create a refund record (table: refund, DAT-03 §5.4) with status=REFUND_PENDING; (2) do NOT transition the parent transaction yet — the transaction transitions to REFUNDED only after ZP0022 confirms. For OVERSEAS partners, prefunding reversal happens when ZP0022 confirms (not on initiation). Constraint: can only refund an APPROVED transaction; REVERSED/FAILED/QUOTED transactions are not eligible. | • Create RefundService.initiateRefund(String txnRef, BigDecimal amount, String currency, String reason, String operatorId): load transaction; assert status == APPROVED; else throw RefundNotAllowedException. • INSERT refund row: txn_id, refund_ref (generated), refund_amount, refund_ccy, reason, initiated_by, status=REFUND_PENDING, created_at. • Do NOT change parent transaction.status at this stage. • Create RefundService.confirmRefund(String refundRef, String schemeRefundRef): UPDATE refund.status=REFUNDED, scheme_refund_ref; then call transition(txnRef, APPROVED, REFUNDED, ctx). • For OVERSEAS: after confirming, reverse prefunding deduction. | RefundService with initiateRefund() (creates REFUND_PENDING record) and confirmRefund() (transitions parent to REFUNDED) | • initiateRefund on APPROVED transaction creates refund row with status=REFUND_PENDING; parent transaction.status remains APPROVED. • initiateRefund on REVERSED transaction throws RefundNotAllowedException. • confirmRefund transitions parent transaction to REFUNDED and sets transaction.completed_at. • OVERSEAS prefunding is re-credited only at confirmRefund, not at initiateRefund. • refund.scheme_refund_ref is set from the ZP0022 confirmation argument. | 50 | 5.1-T14, 5.1-T11 | BE | RATE-04, API-05
5.1-T21 | transaction-mgmt | 5.1 | 5. Transaction Processing (MPM/CPM) | Transaction state machine | 1 | CPM QUOTED state at QR token generation (POST /v1/payments/cpm/generate) | WBS 5.1 and SAD-02 §6.2. CPM (Customer Presented Mode) differs from MPM: the transaction enters QUOTED when the partner calls POST /v1/payments/cpm/generate (not at GET /v1/rates). The rate quote is computed at this point and the QR token is requested from the scheme. When the merchant scans the QR, the scheme sends an inbound notification (inboundCpmPending) which triggers quote computation, prefunding deduction (OVERSEAS), and payment.pending_debit webhook. The partner then calls POST /v1/payments/cpm/confirm to complete. CPM OVERSEAS uses PENDING_DEBIT at inboundCpmPending, not at /cpm/generate. CPM LOCAL goes QUOTED->DEBITED at inboundCpmPending. | • In CpmOrchestrator.generateToken(CpmGenerateRequest req): create transaction with status=QUOTED; call EventTrailService step 1 (rate_quote_issued) with CPM flag in detail. • Retrieve CPM token from scheme adapter (schemeAdapter.requestCpmToken(countryCode)); store prepare_token and qr_payload on transaction. • Return 200 OK with prepare_token and qr_payload to partner. • On inboundCpmPending: run OVERSEAS->PENDING_DEBIT or LOCAL->DEBITED path (same as 5.1-T10/T12 but triggered by scheme push). • On /cpm/confirm: run DEBITED->SCHEME_SENT->APPROVED path (same as 5.1-T13/T14 but via confirmCpm adapter call). | CpmOrchestrator with generateToken(), inboundCpmPending(), and confirm() methods mapping to the CPM-specific state transitions | • POST /v1/payments/cpm/generate creates a QUOTED transaction and returns a prepare_token. • inboundCpmPending for OVERSEAS transitions QUOTED->PENDING_DEBIT and dispatches payment.pending_debit webhook. • inboundCpmPending for LOCAL transitions QUOTED->DEBITED (no PENDING_DEBIT). • POST /v1/payments/cpm/confirm transitions DEBITED->SCHEME_SENT->APPROVED on scheme success. • Event trail step 1 detail contains payment_mode=CPM. | 55 | 5.1-T10, 5.1-T12, 5.1-T13, 5.1-T14 | BE | RATE-04, API-05
5.1-T22 | transaction-mgmt | 5.1 | 5. Transaction Processing (MPM/CPM) | Transaction state machine | 1 | TTL expiry guard: QUOTED->FAILED on stale rate quote commit | WBS 5.1 and API-05 §HC-005. If a partner calls POST /v1/payments or POST /v1/payments/cpm/confirm after the rate quote has expired (now() > valid_until), the Orchestrator must: (1) NOT deduct prefunding; (2) transition QUOTED->FAILED with error RATE_QUOTE_EXPIRED; (3) return HTTP 422. valid_until is stored on the transaction record (copied from rate_quote at QUOTED). The guard must run before any prefunding deduction. Expired QUOTED transactions with no commit attempt should be cleaned up by the scheduled expiry job (5.1-T23), but the TTL guard also handles the case where commit arrives after expiry. | • In PaymentOrchestrator.commitMpm() and CpmOrchestrator.confirm(): as the first check after loading the transaction, compare Instant.now() > transaction.valid_until. • If expired: call transition(txnRef, QUOTED, FAILED, ctx.withError(RATE_QUOTE_EXPIRED)). Record event trail step 2 (payment_initiated, detail={expired:true}) and step 6 (transaction_committed, detail={outcome:FAILED,error:RATE_QUOTE_EXPIRED}). • Return HTTP 422 with error body: {error:{code:RATE_QUOTE_EXPIRED, message:'...', txn_ref:'...'}}. • If not expired: continue with normal flow. • Test: commit exactly at valid_until boundary — accept if now() == valid_until (inclusive on the boundary per spec). | TTL expiry guard in PaymentOrchestrator and CpmOrchestrator returning HTTP 422 RATE_QUOTE_EXPIRED with no side effects | • Commit at valid_until - 1 second succeeds (not expired). • Commit at valid_until + 1 second returns HTTP 422, error code RATE_QUOTE_EXPIRED, transaction.status == FAILED. • prefunding_account balance is unchanged for OVERSEAS partner on expiry path. • No scheme call is made on expired commit. • Event trail step 2 is recorded even on expiry path so the trail is queryable. | 35 | 5.1-T10, 5.1-T21 | BE | RATE-04, API-05
5.1-T23 | transaction-mgmt | 5.1 | 5. Transaction Processing (MPM/CPM) | Transaction state machine | 1 | Scheduled job: expire QUOTED transactions past valid_until | WBS 5.1. QUOTED transactions where valid_until < now() and no commit has been received should be transitioned to FAILED by a background job, so they do not accumulate as stale open records. The job runs every 60 seconds. It selects all transactions WHERE status=QUOTED AND valid_until < now() FOR UPDATE SKIP LOCKED (to avoid contending with concurrent commit attempts). For each row, it calls TransactionStateMachine.transition(txnRef, QUOTED, FAILED, ctx.withError(TTL_EXPIRED_BY_JOB)). The job must be idempotent: if a row has already moved past QUOTED by a concurrent commit, the ConcurrentTransitionException is caught and logged as INFO (not an error). | • Create scheduled job QuotedExpiryJob.java with @Scheduled(fixedDelay=60000). • Query: SELECT * FROM transaction WHERE status='QUOTED' AND valid_until < NOW() FOR UPDATE SKIP LOCKED LIMIT 100. • For each result: try { stateMachine.transition(txnRef, QUOTED, FAILED, ctx) } catch (ConcurrentTransitionException e) { log.info("Already moved: {}", txnRef); }. • Record event trail step 2 (payment_initiated, detail={expired_by_job:true}) on expiry. • Log job execution summary: rows_checked, rows_expired, rows_already_moved. | QuotedExpiryJob.java: scheduled every 60s, batch-expires stale QUOTED rows, idempotent on concurrent transitions | • A QUOTED transaction with valid_until 5 minutes ago is transitioned to FAILED by the next job run. • A QUOTED transaction with valid_until 30 seconds in the future is NOT touched. • If a concurrent thread commits the transaction between the query and the transition, ConcurrentTransitionException is caught and logged as INFO (no error/alert). • Job running twice in quick succession does not create duplicate FAILED events (second run finds no rows matching the WHERE clause). • Batch size limit of 100 prevents the job from holding locks too long. | 45 | 5.1-T04, 5.1-T06 | BE | RATE-04, API-05
5.1-T24 | transaction-mgmt | 5.1 | 5. Transaction Processing (MPM/CPM) | Transaction state machine | 1 | UNCERTAIN 24h alert: fire ops alert on unresolved UNCERTAIN transactions | WBS 5.1 and SAD-02 §5.2. If a transaction remains in UNCERTAIN status for more than 24 hours (uncertain_since < now() - 24h), it has not been resolved by the normal ZP0012 batch cycle and requires manual Ops intervention. A scheduled job must detect this condition and fire a structured alert. The alert must include: txn_ref, hub_txn_ref, partner_id, scheme_id, uncertain_since. The transaction is NOT automatically failed — it enters the manual exception queue. Resolution remains via resolveUncertain() (5.1-T17) called by Ops. | • Create UncertainAlertJob.java with @Scheduled(fixedDelay=300000) (every 5 minutes). • Query: SELECT * FROM transaction WHERE status='UNCERTAIN' AND uncertain_since < NOW() - INTERVAL '24 hours'. • For each result: publish an UNCERTAIN_TIMEOUT alert via AlertService.fire(AlertLevel.HIGH, txnRef, hub_txn_ref, partnerId, uncertainSince). • Log alert as structured log with all fields at WARN level. • Do NOT change transaction status — Ops resolves manually via resolveUncertain(). | UncertainAlertJob.java: fires HIGH-severity alerts for UNCERTAIN transactions older than 24h without mutating state | • Transaction with uncertain_since = 25 hours ago triggers an alert on the next job run. • Transaction with uncertain_since = 23 hours ago does NOT trigger an alert. • Alert payload contains txn_ref, hub_txn_ref, partner_id, uncertain_since. • Job does not modify transaction.status. • Running the job twice for the same unresolved transaction fires the alert twice (acceptable — monitoring deduplicates). | 30 | 5.1-T16 | BE | RATE-04, API-05
5.1-T25 | transaction-mgmt | 5.1 | 5. Transaction Processing (MPM/CPM) | Transaction state machine | 1 | Unit tests: MPM happy path state transitions (QUOTED->DEBITED->SCHEME_SENT->APPROVED) | WBS 5.1. Tests for the complete LOCAL-partner MPM happy path through the state machine. Partner type = LOCAL. Steps: (1) transaction starts in QUOTED; (2) commitMpm() -> DEBITED (no prefunding); (3) scheme adapter submitMpm() returns success -> SCHEME_SENT -> APPROVED. Each state must be verified in the DB. Event trail steps 1, 2 (payment_initiated), 3 (skipped/LOCAL), 4 (scheme_request_sent), 5 (scheme_response_received), 6 (transaction_committed) must all be present. Uses an in-memory H2 or test-Postgres DB. Scheme adapter is mocked. | • Create test class MpmHappyPathTest.java. • Set up: insert partner (type=LOCAL), scheme, rule, rate_quote (valid_until = +5 min), transaction in QUOTED status. • Call paymentOrchestrator.commitMpm(txnRef, idempotencyKey): assert status transitions QUOTED->DEBITED. • Mock schemeAdapter.submitMpm() to return approval code APPROVAL-001. • Assert final status APPROVED, completed_at set, scheme_ref=APPROVAL-001. • Assert event trail rows for steps 1-6, step 3 detail.skipped==true. | test/statemachine/MpmHappyPathTest.java: full LOCAL MPM flow from QUOTED to APPROVED with event trail verification | • Final transaction.status == APPROVED. • Event trail has exactly 6 rows for steps 1-6 (steps 7-8 not yet triggered as webhook is async). • Step 3 detail.skipped == true and detail.reason == LOCAL_PARTNER_NO_PREFUND. • Step 6 detail contains collection_usd and payout_usd_cost as non-null values. • scheme_ref == APPROVAL-001 on the transaction record. | 45 | 5.1-T12, 5.1-T13, 5.1-T14 | BE | RATE-04, API-05
5.1-T26 | transaction-mgmt | 5.1 | 5. Transaction Processing (MPM/CPM) | Transaction state machine | 1 | Unit tests: OVERSEAS MPM prefunding deduction path (QUOTED->PENDING_DEBIT->DEBITED->APPROVED) | WBS 5.1. Tests for the OVERSEAS partner MPM path including prefunding deduction. Partner: OVERSEAS, initial balance 100.00 USD. prefunding_deducted_usd = 35.77 USD (= collection_usd from RATE-04 worked example with target_payout=50000 KRW, usd_krw=1380.00, m_a=m_b=0.01). Expected: balance after deduction = 64.23 USD. Verify PENDING_DEBIT state is reached, then DEBITED, then APPROVED. Verify event trail step 3 (prefund_deducted) with balance_before=100.00 and balance_after=64.23. | • Insert OVERSEAS partner with prefunding_account.balance=100.00 USD. • Insert rate_quote with collection_usd=36.2320 (RATE-04 §4.3 cross-border values — use these exact Decimals). • Call commitMpm(); assert transition to PENDING_DEBIT. • Assert PrefundingService deducts 36.2320 USD; balance becomes 63.7680 USD; transaction -> DEBITED. • Mock schemeAdapter success; assert -> APPROVED. Verify event trail. | test/statemachine/OverseasMpmDeductionTest.java verifying QUOTED->PENDING_DEBIT->DEBITED->APPROVED with exact balance arithmetic | • prefunding_account.balance after deduction == 100.00 - 36.2320 == 63.7680 USD (Decimal, not float). • Event trail step 3 detail.balance_before == 100.00, detail.balance_after == 63.7680. • Status sequence in event trail: QUOTED, PENDING_DEBIT, DEBITED, SCHEME_SENT, APPROVED. • No prefunding balance update is made for LOCAL partner (regression check by running same test with LOCAL type). • transaction.prefunding_deducted_usd == 36.2320 on the final record. | 45 | 5.1-T11, 5.1-T25 | BE | RATE-04, API-05
5.1-T27 | transaction-mgmt | 5.1 | 5. Transaction Processing (MPM/CPM) | Transaction state machine | 1 | Unit tests: QUOTED->FAILED on expired TTL, insufficient prefunding, and scheme rejection | WBS 5.1. Three failure-path unit tests covering: (A) TTL expiry — commit arrives 1 second after valid_until; (B) Insufficient prefunding — OVERSEAS partner balance 10.00 USD, deduction amount 35.77 USD; (C) Scheme rejection — submitMpm returns SchemeRejectException with code ZP_DECLINED. Each test must verify: final status FAILED, no prefunding deduction on expiry path, prefunding restored on scheme-rejection path, event trail step 6 detail.outcome==FAILED with correct error code. | • Test A (TTL): set valid_until = now()-1s; call commitMpm(); assert FAILED, HTTP 422 RATE_QUOTE_EXPIRED, balance unchanged. • Test B (Insufficient): set balance=10.00, deduction=35.77; call commitMpm(); assert FAILED after PENDING_DEBIT, balance unchanged at 10.00, error INSUFFICIENT_PREFUNDING. • Test C (Scheme rejection): set balance=100.00, deduction=35.77; mock submitMpm to throw SchemeRejectException(ZP_DECLINED); assert FAILED, balance restored to 100.00 (deduction reversed). • In each test verify event trail step 6 with outcome=FAILED and correct error_code. • In test B verify transition sequence: QUOTED->PENDING_DEBIT->FAILED (no DEBITED). | test/statemachine/TransactionFailurePathsTest.java covering expiry, insufficient funds, and scheme rejection | • Test A: transaction.status==FAILED, balance unchanged, error code RATE_QUOTE_EXPIRED. • Test B: PENDING_DEBIT row exists in event trail but DEBITED does not; balance == 10.00 unchanged. • Test C: balance restored to 100.00 USD after scheme rejection (deduction reversed). • All three tests verify step 6 event trail row with outcome==FAILED. • No float arithmetic in any assertion — Decimal comparisons throughout. | 50 | 5.1-T22, 5.1-T15, 5.1-T26 | BE | RATE-04, API-05
5.1-T28 | transaction-mgmt | 5.1 | 5. Transaction Processing (MPM/CPM) | Transaction state machine | 1 | Unit tests: UNCERTAIN resolution via batch reconciliation | WBS 5.1. Tests for the UNCERTAIN->APPROVED and UNCERTAIN->FAILED paths via resolveUncertain(). Setup: OVERSEAS transaction in UNCERTAIN status, prefunding_deducted_usd=35.77 USD, prefunding_account.balance=64.23 USD (deducted). Test A: resolveUncertain(txnRef, APPROVED) -> status APPROVED, balance unchanged at 64.23, payment.approved webhook enqueued. Test B: resolveUncertain(txnRef, FAILED) -> status FAILED, balance restored to 100.00, payment.failed webhook enqueued. Test C (idempotency): call resolveUncertain(txnRef, APPROVED) twice; second call is a no-op (status still APPROVED, no duplicate events, no duplicate webhooks). | • Set up OVERSEAS transaction in UNCERTAIN; prefunding deducted (balance=64.23). • Test A: call resolveUncertain(txnRef, APPROVED); assert status APPROVED, balance==64.23, step 6 present. • Test B: reset to UNCERTAIN; call resolveUncertain(txnRef, FAILED); assert status FAILED, balance==100.00. • Test C: call resolveUncertain twice with APPROVED; assert no duplicate event rows, no duplicate webhook enqueue calls. • Verify in all tests that reconciliation_source is set in step 6 event trail detail. | test/statemachine/UncertainResolutionTest.java: UNCERTAIN->APPROVED, UNCERTAIN->FAILED, and idempotency | • Test A: status APPROVED, balance 64.23 (no reversal), payment.approved enqueued once. • Test B: status FAILED, balance 100.00 (deduction reversed), payment.failed enqueued once. • Test C: second resolveUncertain call does not insert a second step 6 event row. • transaction.completed_at is set on APPROVED resolution. • step 6 detail.reconciliation_source is non-null in all cases. | 40 | 5.1-T17, 5.1-T26 | BE | RATE-04, API-05
5.1-T29 | transaction-mgmt | 5.1 | 5. Transaction Processing (MPM/CPM) | Transaction state machine | 1 | Unit tests: same-day cancel (APPROVED->REVERSED) and out-of-window rejection | WBS 5.1 and API-05 §HC-007. Tests for cancelPayment(). Test A (success): OVERSEAS transaction APPROVED today (KST); call cancelPayment(); assert REVERSED, balance restored, payment.reversed webhook enqueued. Test B (out-of-window): APPROVED transaction with committed_at yesterday KST; call cancelPayment(); assert HTTP 409 CANCEL_NOT_ALLOWED, status still APPROVED, balance unchanged. Test C (wrong initial state): transaction in SCHEME_SENT; call cancelPayment(); assert CANCEL_NOT_ALLOWED (only APPROVED can be cancelled). KST is Asia/Seoul timezone. | • Set up OVERSEAS transaction APPROVED with committed_at = today KST 10:00. • Test A: call cancelPayment(); assert REVERSED, balance restored to pre-deduction level. • Test B: set committed_at = yesterday KST 23:59; call cancelPayment(); expect CancelNotAllowedException / HTTP 409. • Test C: set status=SCHEME_SENT; call cancelPayment(); expect rejection (status != APPROVED). • Verify payment.reversed webhook enqueued in Test A only. | test/statemachine/CancelPaymentTest.java covering success, out-of-KST-day, and wrong-state cases | • Test A: final status REVERSED, OVERSEAS balance restored, payment.reversed webhook enqueued. • Test B: CancelNotAllowedException thrown, transaction.status remains APPROVED. • Test C: rejection when initial status != APPROVED. • KST boundary test: committed_at = 23:59 yesterday KST is rejected; committed_at = 00:01 today KST is accepted. • cancel_reason and cancelled_by are set on the transaction record in Test A. | 40 | 5.1-T19, 5.1-T26 | BE | RATE-04, API-05
5.1-T30 | transaction-mgmt | 5.1 | 5. Transaction Processing (MPM/CPM) | Transaction state machine | 1 | Unit tests: rate-lock immutability after APPROVED | WBS 5.1 and SEC-09 §5.4. Tests for the immutability guard in TransactionEntity. After a transaction reaches APPROVED, any attempt to modify rate-locked fields must raise ImmutableFieldException. Locked fields: collection_usd, payout_usd_cost, collection_margin_usd, payout_margin_usd, offer_rate_coll, cross_rate, cost_rate_coll, cost_rate_pay, send_amount, service_charge, collection_amount. Non-locked fields (scheme_ref, completed_at, cancel_reason) may still be updated. Also test that QUOTED and DEBITED transactions allow updates to locked fields. | • Create test class RateLockImmutabilityTest.java. • For each of the 11 locked fields: set transaction to APPROVED, attempt to set the field, assert ImmutableFieldException with the correct fieldName. • For each of 3 non-locked fields (scheme_ref, completed_at, cancel_reason): set APPROVED, update field, assert no exception. • Test with QUOTED status: set collection_usd to a new value; assert NO ImmutableFieldException. • Test DB-level guard (via raw JDBC update): attempt UPDATE transaction SET collection_usd=999 WHERE status='APPROVED'; expect constraint violation. | test/statemachine/RateLockImmutabilityTest.java: 11 locked fields and 3 non-locked fields tested, plus raw SQL guard | • All 11 locked field setters throw ImmutableFieldException when status==APPROVED. • ImmutableFieldException.fieldName matches the field being set (e.g. collection_usd not a generic message). • Non-locked fields (scheme_ref, completed_at) can be updated on APPROVED transactions without exception. • QUOTED transaction allows setting collection_usd (not yet locked). • Raw SQL UPDATE attempt on APPROVED row is rejected by DB constraint. | 40 | 5.1-T18, 5.1-T25 | BE | RATE-04, API-05
5.1-T31 | transaction-mgmt | 5.1 | 5. Transaction Processing (MPM/CPM) | Transaction state machine | 1 | Integration test: full MPM OVERSEAS payment E2E state transitions | WBS 5.1. An end-to-end integration test that exercises the full OVERSEAS MPM flow against a real test-Postgres DB (port 5433) with a mocked ZeroPay adapter. Sequence: (1) insert test partner (OVERSEAS, balance=200.00 USD), scheme, rule, treasury rate (usd_krw=1380.00), merchant; (2) call GET /v1/rates (target_payout=50000 KRW, m_a=m_b=0.01) — verify rate quote returned, collection_usd=36.9714; (3) POST /v1/payments with quote_ref — verify transitions QUOTED->PENDING_DEBIT->DEBITED->SCHEME_SENT->APPROVED; (4) verify balance=200.00-36.9714=163.0286; (5) verify 6 event trail rows; (6) verify rate-locked fields match the quote values. | • Set up test DB via Flyway migration (Testcontainers or local port 5433 with test schema). • Insert prerequisites: partner (OVERSEAS), prefunding_account (balance=200.00), scheme (ZeroPay), rule (m_a=0.01, m_b=0.01, service_charge=0.35 USD), treasury_rate (usd_krw=1380.00). • POST /v1/rates; assert collection_usd=36.9714 (8dp Decimal), collection_amount=37.3214 (36.9714+0.35 rounded to 4dp KRW scale). • POST /v1/payments; mock adapter to return APPROVAL-E2E; verify final status APPROVED. • Assert balance=200.00-36.9714=163.0286, event trail steps 1-6 present, transaction.collection_usd=36.9714. | test/integration/MpmOverseasE2ETest.java verifying full OVERSEAS MPM flow with exact balance and rate-lock assertions | • transaction.status == APPROVED after full flow. • prefunding_account.balance == 163.0286 USD (200.00 - 36.9714, to 4dp). • collection_usd == 36.9714 on the transaction record (rate-locked, 8dp). • Event trail has 6 rows (steps 1-6); step 3 detail.skipped == false. • Pool identity check: 36.9714 - 0.3697 - 0.3697 - 36.2320 = 0.0000 (within 0.01 USD tolerance). | 60 | 5.1-T25, 5.1-T26, 5.1-T11, 5.1-T14 | BE | RATE-04, API-05
5.1-T32 | transaction-mgmt | 5.1 | 5. Transaction Processing (MPM/CPM) | Transaction state machine | 1 | State machine Javadoc and inline transition diagram comment | WBS 5.1. The TransactionStateMachine and TransactionTransitions classes are the authoritative runtime documentation of the state machine. All downstream engineers must be able to understand the state graph from the source alone. This ticket adds Javadoc with the full state diagram (ASCII or mermaid in comment) and links to SAD-02 §5.2 and API-05 §4.1 in the class-level Javadoc. No logic changes — documentation only. | • Open TransactionTransitions.java; add class-level Javadoc with the full stateDiagram-v2 (mermaid syntax as a @implNote block) listing all 13 allowed transitions verbatim. • Reference SAD-02 §5.2 and API-05 §4.1 in @see tags. • Open TransactionStateMachine.java; add class-level Javadoc explaining it is the sole owner of status mutations, referencing TransactionTransitions for the allowed pairs. • For each enum constant in TransactionStatus, verify the Javadoc from 5.1-T01 is present and accurate after all tickets have been merged. • No logic changes — this is documentation-only. | Updated Javadoc on TransactionTransitions.java, TransactionStateMachine.java, and TransactionStatus.java with full state diagram and spec cross-references | • TransactionTransitions.java class Javadoc contains the string stateDiagram-v2 and all 9 state names. • TransactionStateMachine.java Javadoc states it is the sole component that may call transition(). • All 9 TransactionStatus constants have non-empty Javadoc. • @see tags reference SAD-02 and API-05. • No Java compilation errors introduced. | 30 | 5.1-T02, 5.1-T04, 5.1-T31 | BE | RATE-04, API-05
5.2-T01 | payment-executor | 5.2 | 5. Transaction Processing (MPM/CPM) | Fixed MPM execution flow | 1 | Add payment_mode column and MPM constraint to transaction table | The transaction table (DAT-03 §10.1) needs a payment_mode column (VARCHAR(5), CHECK IN ('MPM','CPM'), NOT NULL) to distinguish Fixed MPM from CPM payments. Without this column the MPM execution handler cannot record mode at insert time. The column must be NOT NULL with no default so existing untyped rows are caught at migration. | • Write a Flyway/Liquibase migration: ALTER TABLE transaction ADD COLUMN payment_mode VARCHAR(5) NOT NULL CHECK (payment_mode IN ('MPM','CPM')) • Add a partial index on (partner_id, status) WHERE payment_mode = 'MPM' to support prefunding deduction queries • Add prefunding_deducted_usd DECIMAL(20,4) NULL column if not already present (OVERSEAS only; NULL for LOCAL) • Update the JPA/Hibernate entity class Transaction to add field paymentMode (enum PaymentMode {MPM, CPM}) and prefundingDeductedUsd (BigDecimal, nullable) • Run migration against a local test DB; verify schema with INFORMATION_SCHEMA query | Flyway migration file V5_2_001__add_payment_mode_prefunding.sql and updated Transaction entity class | • Migration applies cleanly on a fresh schema and on a schema that already has existing rows (existing rows must require explicit backfill — migration must NOT silently default to MPM) • transaction.payment_mode rejects any value other than MPM or CPM at DB level • prefunding_deducted_usd column accepts NULL (LOCAL partner) and a positive DECIMAL value (OVERSEAS partner) • Partial index on payment_mode='MPM' is visible in pg_indexes • Entity field paymentMode maps to DB column without a default value — inserting a Transaction without paymentMode throws a constraint violation | 30 |  | BE | API-05, RATE-04
5.2-T02 | payment-executor | 5.2 | 5. Transaction Processing (MPM/CPM) | Fixed MPM execution flow | 1 | Define MpmPaymentRequest and MpmPaymentResponse Java records for POST /v1/payments | POST /v1/payments executes a Fixed MPM payment. Request fields (API-05 §4.3): quote_id (String, required), merchant_qr (String, required), direction (String, required), scheme_id (String, required), customer_ref (String, required), partner_txn_ref (String, required), collection_amount (String decimal, required), collection_currency (String, required), country_code (String, optional). Response fields: payment_id, status, scheme_txn_id, merchant_name, merchant_id, target_payout, payout_currency, offer_rate, collection_amount, collection_currency, service_charge, service_charge_currency, prefund_deducted_usd (OVERSEAS only), partner_txn_ref, created_at, approved_at. | • Create MpmPaymentRequest record with @NotNull/@NotBlank validations on all required fields; collection_amount must match regex ^[0-9]+(\.[0-9]+)?$ • Create MpmPaymentResponse record with all response fields; prefund_deducted_usd annotated @Nullable • Add Jackson @JsonProperty mappings for snake_case API field names • Write unit test MpmPaymentRequestTest: deserialise the example request JSON from spec and assert all fields parse correctly • Write unit test MpmPaymentResponseTest: serialise a fully-populated response and assert all required keys are present; assert prefund_deducted_usd is absent when null | MpmPaymentRequest.java, MpmPaymentResponse.java, and their unit test classes | • Deserialising the spec example body (quote_id=qte_01HX7MNP9AB..., collection_amount=35.77, collection_currency=USD) populates all fields with correct types • Validation fails (ConstraintViolationException) when quote_id is null or blank • Validation fails when collection_amount is not a valid decimal string (e.g. abc or -1) • Serialising MpmPaymentResponse with prefund_deducted_usd=null omits the field from JSON (use @JsonInclude(NON_NULL)) • country_code is absent from validation annotations (optional field) | 35 | 5.2-T01 | BE | API-05, RATE-04
5.2-T03 | payment-executor | 5.2 | 5. Transaction Processing (MPM/CPM) | Fixed MPM execution flow | 1 | Add quote_id lookup and TTL-expiry check to CommitTransaction service | At POST /v1/payments the Orchestrator must call lockRateQuote(quote_id). A rate quote is stored in Redis with key rate_quote:{quote_id}, TTL = partner.rate_quote_ttl_seconds (default 300 s; range 60-1800 s). valid_until = quote_issued_at + ttl_seconds. If the quote is absent (TTL elapsed) or valid_until < NOW(UTC), reject with error code RATE_QUOTE_EXPIRED (HTTP 422). The quote record carries partner_id; reject with RATE_QUOTE_INVALID (HTTP 422) if partner_id on the quote does not match the authenticated caller. | • In RateQuoteService.lockRateQuote(String quoteId, long partnerId): fetch the Redis key rate_quote:{quoteId} • If key missing, throw RateQuoteExpiredException(quoteId) -> mapped to HTTP 422 RATE_QUOTE_EXPIRED • If found, parse validUntil field; if Instant.now().isAfter(validUntil), throw same exception • If partner_id in stored quote != partnerId param, throw RateQuoteInvalidException -> HTTP 422 RATE_QUOTE_INVALID • Mark quote as consumed (delete or set a 'used' flag) atomically using Redis GETDEL or Lua script to prevent double-spend | RateQuoteService.lockRateQuote() method and unit tests RateQuoteLockTest | • lockRateQuote returns the full quote object when quote exists, valid_until is 10 s in the future, and partner_id matches • lockRateQuote throws RateQuoteExpiredException when Redis key is missing • lockRateQuote throws RateQuoteExpiredException when valid_until is 1 ms in the past • lockRateQuote throws RateQuoteInvalidException when stored partner_id=101 but caller partner_id=102 • A second call with the same quote_id after a successful lock throws RateQuoteExpiredException (quote consumed, cannot be double-spent) | 45 | 5.2-T01 | BE | API-05, RATE-04
5.2-T04 | payment-executor | 5.2 | 5. Transaction Processing (MPM/CPM) | Fixed MPM execution flow | 1 | Implement atomic prefunding deduction via SELECT FOR UPDATE on prefunding_account | For OVERSEAS partners (partner.type = 'OVERSEAS'), prefunding must be deducted atomically at POST /v1/payments before the scheme is called. Rules: deduct collection_usd (the USD pool gross from the rate quote, DECIMAL(20,4)). Use SELECT ... FOR UPDATE on prefunding_account WHERE partner_id = ? within a DB transaction. If balance < collection_usd, throw InsufficientPrefundingException -> HTTP 402 INSUFFICIENT_PREFUNDING. On success: UPDATE prefunding_account SET balance = balance - collection_usd, updated_at = NOW(); INSERT INTO prefunding_ledger_entry (account_id, txn_ref, entry_type='DEBIT_PAYMENT', amount=collection_usd, balance_after=new_balance, created_at=NOW()). LOCAL partners (partner.type = 'LOCAL') skip this step entirely. | • In PrefundingService.deductForMpm(long partnerId, String txnRef, BigDecimal collectionUsd): open a DB transaction with isolation level SERIALIZABLE or use SELECT FOR UPDATE • Execute SELECT id, balance FROM prefunding_account WHERE partner_id = :partnerId FOR UPDATE • If balance < collectionUsd throw InsufficientPrefundingException with current balance and required amount • UPDATE prefunding_account SET balance = balance - :collectionUsd, updated_at = NOW() WHERE id = :accountId • INSERT into prefunding_ledger_entry with entry_type=DEBIT_PAYMENT • Return PrefundingDeductionResult(accountId, deductedUsd, balanceAfter) | PrefundingService.deductForMpm() method and PrefundingServiceTest unit tests | • deductForMpm with balance=100.00 USD and collectionUsd=35.77 returns balanceAfter=64.23 and inserts one ledger row with amount=35.77 entry_type=DEBIT_PAYMENT • deductForMpm with balance=30.00 USD and collectionUsd=35.77 throws InsufficientPrefundingException; no ledger row inserted; prefunding_account.balance unchanged • Concurrent calls for the same partner with collectionUsd=60.00 each against balance=80.00 result in exactly one success and one InsufficientPrefundingException (no over-draw) • LOCAL partner partner_id returns immediately without touching prefunding_account or prefunding_ledger_entry • prefunding_ledger_entry.balance_after equals prefunding_account.balance after the same transaction commits (snapshot consistency) | 55 | 5.2-T01 | BE | API-05, RATE-04
5.2-T05 | payment-executor | 5.2 | 5. Transaction Processing (MPM/CPM) | Fixed MPM execution flow | 1 | Implement merchant QR resolution and validation for MPM payment | POST /v1/payments requires merchant_qr (the QR code string scanned by the customer). The QR must resolve to an active merchant in the local merchants table (kept in sync by daily ZeroPay batch). Fields needed: merchant_id, merchant_name, payout_currency. If qr not found -> MERCHANT_NOT_FOUND (HTTP 404). If merchant.status != 'active' -> also MERCHANT_NOT_FOUND per spec. The scheme_id from the request must match the scheme associated with the merchant's QR code; mismatch -> VALIDATION_ERROR. payout_currency on the resolved merchant must match payout_ccy of the rate quote; mismatch -> VALIDATION_ERROR. | • In MerchantService.resolveForPayment(String merchantQr, String schemeId, String quotedPayoutCcy): query merchants table JOIN qr_codes on qr_code = merchantQr • If no row returned or merchant.status != 'active', throw MerchantNotFoundException(merchantQr) -> HTTP 404 MERCHANT_NOT_FOUND • If qr_codes.scheme_id != schemeId param, throw ValidationException('scheme_id mismatch') • If merchant.payout_currency != quotedPayoutCcy, throw ValidationException('payout_currency mismatch') • Return MerchantResolution(merchantId, merchantName, payoutCurrency) | MerchantService.resolveForPayment() and MerchantServiceTest | • resolveForPayment with QR=ZPQR00012345 (active, scheme=zeropay, payout_ccy=KRW) returns correct merchantId and merchantName • resolveForPayment with unknown QR throws MerchantNotFoundException • resolveForPayment with inactive merchant status throws MerchantNotFoundException (same error as not found, no information leakage) • resolveForPayment with scheme_id=wrongscheme throws ValidationException mentioning scheme_id • resolveForPayment with quotedPayoutCcy=USD when merchant.payout_currency=KRW throws ValidationException mentioning payout_currency | 35 | 5.2-T01 | BE | API-05, RATE-04
5.2-T06 | payment-executor | 5.2 | 5. Transaction Processing (MPM/CPM) | Fixed MPM execution flow | 1 | Implement direction and mode eligibility check against partner Rule | Each payment must be permitted by a Rule record (partner x scheme x direction). Rules: (1) A Rule row must exist in the rule table for (partner_id, scheme_id, direction); if absent -> DIRECTION_NOT_ENABLED (HTTP 422). (2) Rule.supported_modes must include 'MPM' (values: 'MPM', 'CPM', 'BOTH'); if not -> PAYMENT_MODE_NOT_SUPPORTED (HTTP 422). The direction in the POST /v1/payments request must exactly match the direction used in the POST /v1/rates request (stored in the rate quote record); mismatch -> VALIDATION_ERROR. | • In RuleService.validateMpmEligibility(long partnerId, String schemeId, String direction, String quoteDirection): fetch Rule WHERE partner_id=? AND scheme_id=? AND direction=? • If no rule found, throw DirectionNotEnabledException -> HTTP 422 DIRECTION_NOT_ENABLED • If rule.supported_modes not in ('MPM','BOTH'), throw PaymentModeNotSupportedException -> HTTP 422 PAYMENT_MODE_NOT_SUPPORTED • If direction != quoteDirection, throw ValidationException('direction mismatch between payment and quote') • Return the resolved Rule object for use downstream (carries m_a, m_b, service_charge, etc.) | RuleService.validateMpmEligibility() and RuleServiceTest | • Rule with supported_modes='MPM' and direction='inbound' passes validation • Rule with supported_modes='CPM' throws PaymentModeNotSupportedException • Rule with supported_modes='BOTH' passes validation • No rule row for (partner=99, scheme=zeropay, direction=inbound) throws DirectionNotEnabledException • Payment direction='outbound' but quote direction='inbound' throws ValidationException regardless of rule | 30 | 5.2-T01 | BE | API-05, RATE-04
5.2-T07 | payment-executor | 5.2 | 5. Transaction Processing (MPM/CPM) | Fixed MPM execution flow | 1 | Implement idempotency check for POST /v1/payments using partner_txn_ref | partner_txn_ref must be unique per partner. If a POST /v1/payments arrives with a partner_txn_ref that already exists for the same partner_id with a DIFFERENT request body -> HTTP 409 DUPLICATE_PARTNER_TXN_REF. If the Idempotency-Key header matches a prior completed request with the same body -> return stored response without reprocessing (HTTP 201). If Idempotency-Key is missing -> HTTP 400 MISSING_IDEMPOTENCY_KEY. Storage: idempotency_cache table or Redis key idempotency:{partner_id}:{idempotency_key} with TTL 24 h, storing {response_status, response_body}. | • In IdempotencyService.checkOrReserve(long partnerId, String idempotencyKey, String requestBodyHash): look up Redis key idempotency:{partnerId}:{idempotencyKey} • If key exists and body hash matches, return IdempotencyResult.REPLAY(storedResponseStatus, storedBody) • If key exists and body hash differs, return IdempotencyResult.CONFLICT -> HTTP 422 IDEMPOTENCY_KEY_REUSE • If key absent, create a reservation (set key with status=IN_FLIGHT, TTL=24h) and return IdempotencyResult.NEW • Separately in TransactionService: before processing, check transaction table for partner_txn_ref uniqueness per partner_id; if duplicate with different payment_id -> HTTP 409 DUPLICATE_PARTNER_TXN_REF | IdempotencyService.checkOrReserve() and TransactionService duplicate-ref check, with IdempotencyServiceTest | • First call with idempotency_key=abc and body_hash=xyz returns IdempotencyResult.NEW and sets Redis key with TTL ~86400s • Second call with same key and same body returns IdempotencyResult.REPLAY with stored 201 response • Call with same key but different body returns IdempotencyResult.CONFLICT • Two concurrent first calls with the same key and same body: exactly one proceeds as NEW; the other returns IN_FLIGHT (HTTP 409 with X-Idempotency-Status: in_flight) • POST with existing partner_txn_ref for a different payment_id returns HTTP 409 DUPLICATE_PARTNER_TXN_REF | 45 | 5.2-T01 | BE | API-05, RATE-04
5.2-T08 | payment-executor | 5.2 | 5. Transaction Processing (MPM/CPM) | Fixed MPM execution flow | 1 | Implement POST /v1/payments controller handler wiring all validation steps | POST /v1/payments orchestrates: (1) auth + HMAC validation (pre-filter), (2) Idempotency-Key check, (3) partner_txn_ref uniqueness, (4) quote TTL lock (5.2-T03), (5) merchant resolution (5.2-T05), (6) rule/mode eligibility (5.2-T06), (7) prefunding deduction for OVERSEAS (5.2-T04), (8) rate-lock all USD pool values onto transaction record, (9) call ZeroPay adapter submitMpm(), (10) transition transaction to APPROVED, (11) enqueue payment.approved webhook. Order is strict: prefunding deduction (step 7) must occur after all validations (steps 1-6) and before scheme call (step 9). Scheme is NEVER called if prefunding deduction fails. | • Add @PostMapping('/v1/payments') in PaymentController, accept MpmPaymentRequest + @RequestHeader Idempotency-Key • Call idempotencyService.checkOrReserve; if REPLAY return stored response immediately • Sequentially call: lockRateQuote, resolveForPayment, validateMpmEligibility • For OVERSEAS partner call prefundingService.deductForMpm; if InsufficientPrefundingException return HTTP 402 before any scheme call • Call schemeAdapter.submitMpm(); on success persist transaction in APPROVED state with all locked USD pool values and prefunding_deducted_usd • Enqueue WebhookEvent(payment.approved) asynchronously; update idempotency cache with 201 response • Return HTTP 201 MpmPaymentResponse; include prefund_deducted_usd only for OVERSEAS partners | PaymentController.executeMpmPayment() handler and integration test MpmPaymentControllerIT | • Valid request for OVERSEAS partner returns HTTP 201 with prefund_deducted_usd populated • Valid request for LOCAL partner (GME Remit) returns HTTP 201 without prefund_deducted_usd field • If prefunding deduction fails, controller returns HTTP 402 INSUFFICIENT_PREFUNDING and schemeAdapter.submitMpm is never called (verify with mock) • Expired quote returns HTTP 422 RATE_QUOTE_EXPIRED before any deduction attempt • Missing Idempotency-Key header returns HTTP 400 MISSING_IDEMPOTENCY_KEY | 55 | 5.2-T03, 5.2-T04, 5.2-T05, 5.2-T06, 5.2-T07 | BE | API-05, RATE-04
5.2-T09 | payment-executor | 5.2 | 5. Transaction Processing (MPM/CPM) | Fixed MPM execution flow | 1 | Implement rate-lock: copy all USD pool values to transaction record at commit | On CommitTransaction success (after scheme approval), all USD pool values must be permanently recorded on the transaction row. Fields to lock (from rate_quote): collection_usd, payout_usd_cost, collection_margin_usd, payout_margin_usd, send_amount, service_charge, offer_rate_coll (derived: send_amount / (collection_usd - collection_margin_usd)), cross_rate (derived: target_payout / send_amount), cost_rate_coll, cost_rate_pay, committed_at=NOW(). Pool identity invariant: collection_usd - collection_margin_usd - payout_margin_usd == payout_usd_cost (tolerance 0.01 USD). For same-currency short-circuit (is_same_ccy_shortcircuit=true), USD pool fields are NULL; collection_amount = target_payout + service_charge. | • In TransactionService.applyRateLock(Transaction txn, RateQuote quote): copy all USD pool fields from quote to txn • Compute offer_rate_coll = send_amount / (collection_usd - collection_margin_usd); cross_rate = target_payout / send_amount using BigDecimal with HALF_UP, scale 8 • Assert pool identity: abs(collection_usd - collection_margin_usd - payout_margin_usd - payout_usd_cost) <= 0.01; throw RatePoolIdentityException if violated • For is_same_ccy_shortcircuit=true, set all USD pool fields null, verify collection_amount = target_payout + service_charge • Set committed_at = Instant.now(); persist txn; return locked txn | TransactionService.applyRateLock() and RateLockTest | • For target_payout=50000 KRW, cost_rate_pay=1400.00, m_a=0.025, m_b=0.010: payout_usd_cost=35.714286, collection_usd=37.267081, pool identity holds within 0.01 USD • offer_rate_coll = 35.714286 / (37.267081 - 0.931677) = 0.97... computed correctly to 8 decimal places • cross_rate = 50000 / send_amount computed and stored to 8 decimal places • Same-currency short-circuit: target_payout=15000 KRW, service_charge=500 KRW => collection_amount=15500 KRW, all USD fields null • Pool identity violation (deliberately corrupted payout_usd_cost off by 0.05 USD) raises RatePoolIdentityException and transaction is NOT committed | 45 | 5.2-T01, 5.2-T03 | BE | API-05, RATE-04
5.2-T10 | payment-executor | 5.2 | 5. Transaction Processing (MPM/CPM) | Fixed MPM execution flow | 1 | Implement ZeroPay adapter submitMpm() method shell and interface contract | The SchemeAdapter interface (SAD-02 §5.3) defines submitMpm(MpmSubmitRequest) -> MpmSubmitResponse. For ZeroPay, this wraps the 한결원 real-time HTTPS API CommitTransaction call. The adapter must: (1) map internal fields to the ZeroPay wire format, (2) send the request over mTLS-capable HTTPS, (3) parse the ApprovalCode response, (4) map ZeroPay error codes to internal error types. If the scheme returns a decline, throw SchemeDeclinedException. If no response within scheme SLA (configurable, default 10 s), throw SchemeTimeoutException (triggers UNCERTAIN state). This ticket implements the adapter shell and interface; the actual 한결원 API wire format is defined by ZeroPay's spec document (obtain from GME infra team). Use a stub/mock for the HTTP layer. | • Define MpmSubmitRequest(String txnRef, String merchantId, BigDecimal payoutAmount, String payoutCurrency, String schemeHubTxnRef) and MpmSubmitResponse(String schemeApprovalCode, String schemeTxnRef, Instant approvedAt) • Implement ZeroPayAdapter.submitMpm: build ZeroPay request DTO, call zeroPayHttpClient.post('/commit', dto, timeout=schemeTimeoutMs) • On HTTP 200 with approval code, return MpmSubmitResponse • On HTTP 4xx/5xx from ZeroPay, throw SchemeDeclinedException(schemeErrorCode, schemeMessage) • On timeout (configurable timeout_ms, default 10000), throw SchemeTimeoutException triggering UNCERTAIN state in Orchestrator • Add unit tests with MockWebServer for approved, declined, and timeout scenarios | ZeroPayAdapter.submitMpm() implementation and ZeroPayAdapterTest with mocked HTTP responses | • Mock HTTP 200 response with approval_code=ZP20260604093115001234 -> MpmSubmitResponse.schemeApprovalCode equals that value • Mock HTTP 400 from ZeroPay scheme -> SchemeDeclinedException thrown with scheme error code populated • Mock request that times out after 10001 ms -> SchemeTimeoutException thrown (not a declined exception) • Timeout value reads from schemeConfig.timeoutMs property (default 10000); changing it to 5000 in config changes the client timeout • MpmSubmitRequest maps txnRef to the ZeroPay hub_txn_ref field (exact field name TBD per ZeroPay spec — use a TODO comment) | 50 | 5.2-T01 | BE | API-05, RATE-04
5.2-T11 | payment-executor | 5.2 | 5. Transaction Processing (MPM/CPM) | Fixed MPM execution flow | 1 | Implement UNCERTAIN state handling when ZeroPay scheme times out on MPM submit | If ZeroPayAdapter.submitMpm() throws SchemeTimeoutException, the Orchestrator must NOT reverse the prefunding deduction. The transaction transitions to UNCERTAIN state. Rules (SAD-02 §5.2): prefunding deduction is held; the UNCERTAIN transaction is flagged for the Settlement Engine which resolves it via ZP0012 batch file within 24 h. If batch confirms FAILED, PrefundingService.reverseForTransaction() is called. If batch confirms APPROVED, transaction moves to APPROVED. Ops alert fires if UNCERTAIN transaction is unresolved after 24 h. | • In TransactionOrchestrator after catching SchemeTimeoutException: transition txn.status to UNCERTAIN, set txn.updated_at=NOW() • Do NOT reverse prefunding deduction at this point (deduction stays in place) • Persist transaction; emit internal event UncertainTransactionCreated(txnRef, partnerId, createdAt) • In SettlementReconciliationService.resolveUncertain(String txnRef, SchemeResult result): if result=APPROVED -> transitionToApproved; if result=FAILED -> transitionToFailed then reverseDeduction • Add a scheduled check: query UNCERTAIN transactions older than 24 h; for each, emit UncertainTransactionAlert to ops alerting channel | UNCERTAIN state transition logic in TransactionOrchestrator and SettlementReconciliationService.resolveUncertain() | • After SchemeTimeoutException, transaction.status=UNCERTAIN and prefunding_account.balance is unchanged (deduction not reversed) • resolveUncertain(txnRef, APPROVED) transitions status to APPROVED and does NOT reverse prefunding • resolveUncertain(txnRef, FAILED) transitions status to FAILED and calls prefundingService.reverseForTransaction creating a CREDIT_REVERSAL ledger entry • Calling resolveUncertain on a transaction that is already APPROVED throws an IllegalStateException (idempotency guard) • Scheduled check at T+25h for an UNCERTAIN transaction emits alert event with txnRef and partnerId | 45 | 5.2-T04, 5.2-T10 | BE | API-05, RATE-04
5.2-T12 | payment-executor | 5.2 | 5. Transaction Processing (MPM/CPM) | Fixed MPM execution flow | 1 | Implement prefunding reversal on scheme failure (FAILED state after scheme call) | If the scheme synchronously declines (SchemeDeclinedException from submitMpm), the transaction moves to FAILED. For OVERSEAS partners, the prefunding deduction must be reversed immediately (unlike UNCERTAIN where it is held). Reversal: INSERT into prefunding_ledger_entry (entry_type='CREDIT_REVERSAL', amount=original_collection_usd, balance_after=balance+original); UPDATE prefunding_account.balance += original_collection_usd. This is the mirror of T04. Must be done in the same DB transaction as the status update. The HTTP response to the partner returns HTTP 422 SCHEME_UNAVAILABLE (or appropriate error mapped from SchemeDeclinedException.schemeErrorCode). | • In PrefundingService.reverseForTransaction(String txnRef): fetch prefunding_ledger_entry WHERE txn_ref=txnRef AND entry_type='DEBIT_PAYMENT' • Retrieve original amount from that entry; SELECT FOR UPDATE prefunding_account; UPDATE balance += amount • INSERT prefunding_ledger_entry with entry_type=CREDIT_REVERSAL, same amount, txn_ref=txnRef, balance_after=new_balance • In TransactionOrchestrator.handleSchemeFailure: call reverseForTransaction then set transaction.status=FAILED, persist in same @Transactional boundary • Return HTTP 422 to partner with appropriate error code from SchemeDeclinedException | PrefundingService.reverseForTransaction() and TransactionOrchestrator.handleSchemeFailure(), with unit tests | • After SchemeDeclinedException, prefunding_account.balance is restored to value before deduction (net zero change) • Two ledger entries exist for the transaction: one DEBIT_PAYMENT and one CREDIT_REVERSAL, both with the same amount • reverseForTransaction for a LOCAL partner (no debit entry) returns immediately without touching prefunding tables • Calling reverseForTransaction twice for the same txnRef throws DuplicateReversalException (guard against double-credit) • Transaction.status=FAILED is persisted atomically with the CREDIT_REVERSAL ledger insert (same @Transactional) | 40 | 5.2-T04, 5.2-T10 | BE | API-05, RATE-04
5.2-T13 | payment-executor | 5.2 | 5. Transaction Processing (MPM/CPM) | Fixed MPM execution flow | 1 | Enqueue payment.approved webhook after MPM scheme approval | After the scheme approves an MPM payment (transaction.status=APPROVED), a payment.approved webhook must be dispatched asynchronously to the partner's registered webhook_url. Webhook envelope (API-05 §6.5): {event_id (ulid), event_type='payment.approved', created_at, partner_id, data: {payment_id, partner_txn_ref, scheme_txn_id, merchant_id, merchant_name, direction, scheme_id, target_payout, payout_currency, offer_rate, collection_amount, collection_currency, service_charge, service_charge_currency, prefund_deducted_usd (OVERSEAS only), approved_at}}. The webhook body must be signed: X-GME-Webhook-Signature: sha256=HMAC-SHA256(body, webhook_signing_secret). Retry schedule: immediate, 30 s, 2 min, 10 min, 30 min, 1 h x5 (max 10 attempts). | • In WebhookService.enqueueApproved(Transaction txn): build PaymentApprovedEvent DTO from txn fields • Sign the serialised JSON body with HMAC-SHA256 using partner.webhook_signing_secret; set header X-GME-Webhook-Signature: sha256=<hex> • Persist a WebhookOutbox row (event_id, partner_id, event_type, payload, status=PENDING, attempts=0, next_attempt_at=NOW()) • A WebhookDispatchWorker reads PENDING rows and POSTs to partner.webhook_url; on HTTP 2xx set status=DELIVERED; on failure increment attempts and set next_attempt_at per retry schedule • After 10 failed attempts, set status=DEAD_LETTER and emit alert to ops | WebhookService.enqueueApproved() and WebhookOutbox persistence with WebhookServiceTest | • PaymentApprovedEvent for OVERSEAS partner includes prefund_deducted_usd='35.77'; for LOCAL partner the field is absent • X-GME-Webhook-Signature header value matches sha256=HMAC-SHA256(rawBody, signingSecret) using a known test secret • WebhookOutbox row is inserted synchronously within the same @Transactional boundary as transaction.status=APPROVED • On partner HTTP 500 response, attempts increments and next_attempt_at set to +30s (attempt 2) • After 10 failed attempts the row status=DEAD_LETTER and ops alert event is emitted | 50 | 5.2-T08, 5.2-T09 | BE | API-05, RATE-04
5.2-T14 | payment-executor | 5.2 | 5. Transaction Processing (MPM/CPM) | Fixed MPM execution flow | 1 | Implement low-balance alert after each successful prefunding deduction | After each successful prefunding deduction (T04), if the resulting balance_after < low_balance_threshold_usd (configured on prefunding_account.low_balance_threshold, default 10000.00 USD), emit a LowBalanceAlert event. The alert must trigger an email to the partner's configured alert contacts (low_balance_alert_config.alert_email where is_active=true for that partner_id). Alert content: partner_id, current balance, threshold, payment_id that triggered it. Avoid alert storms: do not re-alert if balance was already below threshold before this deduction (only alert on crossing the threshold downward). | • In PrefundingService.deductForMpm(), after successful deduction: fetch low_balance_alert_config WHERE partner_id=? AND is_active=true • Compare: if balance_before >= threshold AND balance_after < threshold (threshold crossing), emit LowBalanceEvent(partnerId, balanceAfter, threshold, txnRef) • AlertDispatchService.onLowBalance(event): send email via EmailService to alert_email with subject 'GMEPay+ Low Prefunding Balance Alert' • Log the alert emission with partner_id, balance_after, threshold to audit log • Unit test: assert alert fires when balance crosses threshold but NOT when balance was already below threshold before deduction | LowBalanceAlert emission in PrefundingService and AlertDispatchService.onLowBalance(), with LowBalanceAlertTest | • balance_before=11000.00, deduction=2000.00, threshold=10000.00 -> balance_after=9000.00 -> alert fires • balance_before=9500.00 (already below threshold), deduction=100.00 -> balance_after=9400.00 -> alert does NOT fire (no duplicate storm) • balance_before=12000.00, deduction=500.00, threshold=10000.00 -> balance_after=11500.00 -> no alert • Alert email contains partner_id, balance_after=9000.00, threshold=10000.00, and the triggering txnRef • AlertDispatchService logs the alert event with all required fields in the audit log | 35 | 5.2-T04 | BE | API-05, RATE-04
5.2-T15 | payment-executor | 5.2 | 5. Transaction Processing (MPM/CPM) | Fixed MPM execution flow | 1 | Implement transaction event trail steps 1-5 for MPM flow (RATE_QUOTE_ISSUED through TRANSACTION_COMMITTED) | Every transaction must carry an 8-step event trail (SAD-02 Assumption A3, A-10). Steps for MPM: (1) RATE_QUOTE_ISSUED at POST /v1/rates, (2) PREFUND_DEDUCTED at deduction (OVERSEAS only; absent for LOCAL), (3) SCHEME_SUBMITTED at submitMpm() call, (4) SCHEME_APPROVED or SCHEME_DECLINED on scheme response, (5) TRANSACTION_COMMITTED on final status write. Steps 6-8 (SETTLEMENT_BATCHED, WEBHOOK_QUEUED, WEBHOOK_DELIVERED) are owned by Settlement and Webhook work-packages. All 8 step columns exist from day one even if not populated. Store each step as txn_event rows: (txn_id, step_number INT, event_name VARCHAR(40), event_at TIMESTAMPTZ, detail JSONB NULL). | • Create migration V5_2_002__create_txn_event.sql: table txn_event(id BIGINT PK, txn_id BIGINT FK transaction, step_number INT, event_name VARCHAR(40), event_at TIMESTAMPTZ, detail JSONB) • Add UNIQUE(txn_id, step_number) constraint • In EventTrailService.recordStep(long txnId, int step, String name, Instant at, Map detail): INSERT into txn_event; on duplicate step ignore (idempotent) • Wire recordStep calls: step 1 in RateQuoteService after quote persisted; step 2 in PrefundingService after deduction; step 3 in TransactionOrchestrator before submitMpm; steps 4/5 in Orchestrator after scheme response • Unit test: full MPM OVERSEAS flow records steps 1,2,3,4,5 in order; LOCAL flow records steps 1,3,4,5 (no step 2) | txn_event migration, EventTrailService, and EventTrailTest | • OVERSEAS MPM approval: txn_event rows for step_number 1,2,3,4,5 all present with correct event_name values • LOCAL MPM approval: txn_event rows for steps 1,3,4,5 present; no row with step_number=2 • SCHEME_DECLINED: txn_event row with step_number=4, event_name='SCHEME_DECLINED' inserted • Calling recordStep with the same txn_id and step_number twice does not create duplicate rows (UNIQUE constraint) • detail JSONB for step 2 contains {deducted_usd: '35.77', balance_after: '64.23'} | 40 | 5.2-T01, 5.2-T04, 5.2-T08 | BE | API-05, RATE-04
5.2-T16 | payment-executor | 5.2 | 5. Transaction Processing (MPM/CPM) | Fixed MPM execution flow | 1 | Implement GET /v1/payments/{id} endpoint for MPM payment status retrieval | GET /v1/payments/{id} returns the full payment record. The payment must belong to the calling partner (enforced via partner_id on the transaction row). If not found or not owned -> HTTP 404 PAYMENT_NOT_FOUND. Response includes all fields from the transaction record. Status values: pending, approved, failed, cancelled, uncertain. Timestamps: created_at, updated_at, approved_at (null if not approved), cancelled_at (null if not cancelled). prefund_deducted_usd included for OVERSEAS partners only. Auth and HMAC signing apply (pre-filter). | • Add @GetMapping('/v1/payments/{id}') in PaymentController • Call TransactionService.findByIdAndPartner(paymentId, authenticatedPartnerId); if absent throw PaymentNotFoundException -> HTTP 404 • Map Transaction entity to PaymentDetailResponse DTO (all fields, status as lowercase string) • Set prefund_deducted_usd only when partner.type=OVERSEAS and value is non-null • Return HTTP 200 with X-Request-ID header | PaymentController.getPayment() handler and GetPaymentIT integration test | • GET /v1/payments/pay_01HX7MNQ5... for correct partner returns HTTP 200 with all fields including prefund_deducted_usd=35.77 • GET with payment_id belonging to a different partner returns HTTP 404 (not 403) to avoid information leakage • GET on LOCAL partner payment: response does not contain prefund_deducted_usd field • status field in response is lowercase ('approved', 'failed', 'uncertain') matching API-05 contract • approved_at field is null in response when transaction.completed_at is null | 30 | 5.2-T08, 5.2-T09 | BE | API-05, RATE-04
5.2-T17 | payment-executor | 5.2 | 5. Transaction Processing (MPM/CPM) | Fixed MPM execution flow | 1 | Implement POST /v1/payments/{id}/cancel for same-day MPM cancellation | POST /v1/payments/{id}/cancel cancels a same-day payment. Rules (API-05 §4.6): only APPROVED or pending status; only same calendar day as creation (KST timezone, i.e. UTC+9). If status is not cancellable -> HTTP 400 CANCEL_NOT_PERMITTED. If already in terminal state (failed, cancelled) -> HTTP 409. On success: call schemeAdapter.cancelPayment(schemeTxnRef); transition status to REVERSED (internal) / 'cancelled' (API). For OVERSEAS partners, reverse prefunding deduction via PrefundingService.reverseForTransaction(). Webhook payment.cancelled dispatched. Response: {payment_id, status:'cancelled', cancelled_at, prefund_returned_usd (OVERSEAS only)}. | • Add @PostMapping('/v1/payments/{id}/cancel') accepting CancelPaymentRequest(reason, reason_detail) • Validate status: if FAILED or CANCELLED/REVERSED throw PaymentAlreadyTerminalException -> HTTP 409 • Validate same-day: extract transaction.created_at.atZone(ZoneId.of('Asia/Seoul')).toLocalDate() and compare to LocalDate.now(ZoneId.of('Asia/Seoul'))'if different throw CancelNotPermittedException -> HTTP 400 • Call schemeAdapter.cancelPayment(txn.schemeRef); on error log but continue (cancel may still be registered at ZeroPay) • For OVERSEAS: call reverseForTransaction; transition status=REVERSED; enqueue payment.cancelled webhook; return 200 | PaymentController.cancelPayment() handler and CancelPaymentIT integration test | • Cancel of an APPROVED same-day OVERSEAS payment returns HTTP 200 with prefund_returned_usd=35.77 and status=cancelled • Cancel attempted on a different calendar day (KST) returns HTTP 400 CANCEL_NOT_PERMITTED • Cancel of a FAILED payment returns HTTP 409 • Cancel of LOCAL partner payment: HTTP 200, no prefund_returned_usd field in response • payment.cancelled webhook is enqueued with correct event_type and prefund_returned_usd | 50 | 5.2-T12, 5.2-T13 | BE | API-05, RATE-04
5.2-T18 | payment-executor | 5.2 | 5. Transaction Processing (MPM/CPM) | Fixed MPM execution flow | 1 | Implement HMAC-SHA256 request authentication pre-filter for all /v1/ endpoints | Every northbound request must pass HMAC-SHA256 authentication (API-05 §3.2). Required headers: X-API-Key, X-Timestamp (ISO-8601 UTC ms precision), X-Signature. Canonical string = {HTTP_METHOD}\n{PATH_WITH_QUERY}\n{X-Timestamp value}\n{SHA256_HEX_OF_BODY}. Signature = HMAC-SHA256(canonical_string, api_secret) hex-encoded. Rejection rules: (1) X-Timestamp older or newer than 300 s from server UTC -> HTTP 401 TIMESTAMP_OUT_OF_RANGE, (2) signature mismatch -> HTTP 401 INVALID_SIGNATURE, (3) unknown API key -> HTTP 401 INVALID_API_KEY. Replay protection: store (partner_id, X-Signature) in Redis for 10 min; reject duplicate signatures within that window. | • Implement HmacAuthFilter (OncePerRequestFilter): extract X-API-Key, X-Timestamp, X-Signature from headers • Validate timestamp within 300 s of Instant.now(); reject with 401 TIMESTAMP_OUT_OF_RANGE if outside • Look up partner by api_key; reject with 401 INVALID_API_KEY if not found; retrieve hashed api_secret • Compute canonical string and HMAC-SHA256; compare to X-Signature using MessageDigest.isEqual (constant-time); reject with 401 INVALID_SIGNATURE if mismatch • Check Redis key replay:{partner_id}:{signature}; if exists return 401 INVALID_SIGNATURE; if not, set key TTL=600s • Attach authenticated partner context to SecurityContextHolder for downstream handlers | HmacAuthFilter and HmacAuthFilterTest | • Valid request with correct signature, timestamp within 5 s of now passes filter • Request with timestamp 301 s in the past returns HTTP 401 TIMESTAMP_OUT_OF_RANGE • Request with tampered body (different SHA256) returns HTTP 401 INVALID_SIGNATURE • Replay of an identical request within 10 minutes returns HTTP 401 INVALID_SIGNATURE • Unknown X-API-Key returns HTTP 401 INVALID_API_KEY | 55 |  | BE | API-05, RATE-04
5.2-T19 | payment-executor | 5.2 | 5. Transaction Processing (MPM/CPM) | Fixed MPM execution flow | 1 | Implement IP allowlist enforcement in auth pre-filter | Partners may configure up to 10 source IP CIDR ranges (API-05 §3.3). When an IP allowlist is configured and the request source IP is not in any range, reject with HTTP 403 IP_NOT_ALLOWLISTED before HMAC signature verification. If no allowlist is configured for the partner, all IPs are permitted. Source IP is taken from X-Forwarded-For header (first non-private IP) or getRemoteAddr() if no proxy header. CIDR matching must support both IPv4 and IPv6. | • In HmacAuthFilter, after partner lookup, check if partner has ip_allowlist entries • If allowlist is non-empty, extract effective client IP: parse X-Forwarded-For header first non-private IP; fall back to RemoteAddr • For each CIDR in allowlist, check if clientIp is contained using InetAddressUtils.isInRange(cidr, clientIp) • If no CIDR matches, return HTTP 403 IP_NOT_ALLOWLISTED before computing HMAC • Cache parsed CIDR ranges per partner in a short-lived (60 s) Caffeine cache to avoid DB lookup per request | IP allowlist check in HmacAuthFilter and IpAllowlistTest | • Partner with allowlist [203.0.113.0/24]: request from 203.0.113.45 passes; request from 198.51.100.1 returns HTTP 403 IP_NOT_ALLOWLISTED • Partner with no allowlist configured: any source IP passes the check • IPv6 CIDR 2001:db8::/32: request from 2001:db8::1 passes; 2001:db9::1 returns HTTP 403 • IP check occurs before HMAC verification (wrong signature from an allowlisted IP returns 401, not 403 — IP check passes first) • X-Forwarded-For: 10.0.0.1, 203.0.113.45 uses 203.0.113.45 as the effective client IP (first non-private) | 35 | 5.2-T18 | BE | API-05, RATE-04
5.2-T20 | payment-executor | 5.2 | 5. Transaction Processing (MPM/CPM) | Fixed MPM execution flow | 1 | Unit tests: MPM rate-engine 5-step USD pool calculation with numeric fixture vectors | RATE-04 5-step RECEIVE mode: (1) payout_usd_cost = target_payout / cost_rate_pay, (2) collection_usd = payout_usd_cost / (1 - m_a - m_b), (3) collection_margin_usd = collection_usd * m_a; payout_margin_usd = collection_usd * m_b, (4) send_amount = collection_usd * cost_rate_coll, (5) collection_amount = send_amount + service_charge. Pool identity: collection_usd - collection_margin_usd - payout_margin_usd == payout_usd_cost (tolerance 0.01 USD). Offer rate (BOK): offer_rate_coll = send_amount / (collection_usd - collection_margin_usd). cross_rate = target_payout / send_amount. Use fixture: target_payout=50000 KRW, cost_rate_pay=1406.00 (usd_krw), cost_rate_coll=1.0 (USD settle A), m_a=0.025, m_b=0.010, service_charge=0.35 USD. | • In RateEngineTest, add test fixture: target_payout=50000, cost_rate_pay=1406.00, cost_rate_coll=1.0, m_a=0.025, m_b=0.010, service_charge=0.35 • Compute expected values with BigDecimal: payout_usd_cost=35.562589, collection_usd=37.015197, send_amount=37.015197, collection_amount=37.365197 • Assert each of the 5 steps against expected values with scale 4 tolerance • Assert pool identity: abs(collection_usd - collection_margin_usd - payout_margin_usd - payout_usd_cost) < 0.01 • Assert offer_rate_coll = send_amount / (collection_usd - collection_margin_usd) = 37.015197 / 36.090317 ~= 1.02561 (6 dp) | RateEngineTest class with at least 3 fixture vectors (standard cross-border, identity-leg settle_A=USD, same-currency short-circuit) | • Fixture 1 (above): all 5 step outputs match expected BigDecimal values within scale 4 • Fixture 2 (identity leg settle_A=USD, cost_rate_coll=1.0): send_amount numerically equals collection_usd; offer_rate_coll computed correctly • Fixture 3 (same-currency short-circuit, collection=KRW=payout=KRW): collection_amount = target_payout + service_charge; collection_usd=null • Pool identity assertion holds for all 3 fixtures • m_a + m_b < 0.02 on a cross-border rule throws MinCombinedMarginException | 40 | 5.2-T09 | BE | API-05, RATE-04
5.2-T21 | payment-executor | 5.2 | 5. Transaction Processing (MPM/CPM) | Fixed MPM execution flow | 1 | Unit tests: prefunding deduction and reversal atomicity under concurrent MPM requests | PrefundingService.deductForMpm must guarantee no over-draw under concurrent requests (SELECT FOR UPDATE). This test uses two threads hitting the same partner account. Partner prefunding_account.balance=80.00 USD. Two concurrent MPM payments each requiring collection_usd=60.00 USD. Expected: exactly one succeeds (deducts 60.00, balance=20.00), one throws InsufficientPrefundingException. After the failing payment's scheme call also fails, reverseForTransaction must restore balance to 80.00 (net zero if both fail) or stay at 20.00 if one succeeds. Tests require a real PostgreSQL test container (Testcontainers). | • Set up Testcontainers PostgreSQL with the full migration applied • Seed prefunding_account with balance=80.00 USD for test partner • Submit two concurrent deductForMpm(partnerId, 'txn1', 60.00) and deductForMpm(partnerId, 'txn2', 60.00) via ExecutorService with 2 threads • Wait for both futures; assert exactly one completed and one threw InsufficientPrefundingException • Verify final prefunding_account.balance=20.00 and exactly one DEBIT_PAYMENT ledger entry exists • Call reverseForTransaction on the successful txn; assert balance returns to 80.00 and CREDIT_REVERSAL ledger entry inserted | PrefundingConcurrencyTest using Testcontainers PostgreSQL | • Concurrent execution: exactly one of two 60.00 USD deductions succeeds; balance=20.00 not 0.00 or negative • No over-draw scenario: balance never goes below 0.00 even under high concurrency (10 threads, each 15.00 USD against balance=100.00 -> exactly 6 succeed, 4 fail) • After successful reversal, balance equals pre-deduction balance exactly • prefunding_ledger_entry count = successful_debits + successful_reversals (no phantom rows) • SELECT balance FROM prefunding_account within the same transaction as deduction sees the locked value | 60 | 5.2-T04, 5.2-T12 | BE | API-05, RATE-04
5.2-T22 | payment-executor | 5.2 | 5. Transaction Processing (MPM/CPM) | Fixed MPM execution flow | 1 | Unit tests: POST /v1/payments full MPM happy-path and key error paths | Integration-level tests for the POST /v1/payments handler covering the full MPM flow. Use MockMvc or RestAssured with mocked downstream dependencies (ZeroPay adapter, prefunding service, rate quote cache). Fixtures based on spec examples: partner=SendMN (OVERSEAS, USD), target_payout=50000 KRW, quote_id=qte_01HX7MNP9AB2CDEF3GH456IJ, merchant_qr=ZPQR00012345678901234567890, collection_amount=35.77, collection_currency=USD. Expected: HTTP 201, payment_id present, status=approved, prefund_deducted_usd=35.77. | • Test T22-1 happy path OVERSEAS: mock valid quote in Redis, active merchant, OVERSEAS rule, prefunding balance=1000 USD; POST -> assert HTTP 201, prefund_deducted_usd=35.77, scheme mock called once • Test T22-2 LOCAL partner (GME Remit): mock valid quote, no prefunding account; POST -> HTTP 201, no prefund_deducted_usd field in response • Test T22-3 expired quote: mock Redis cache miss for quote_id; POST -> HTTP 422 RATE_QUOTE_EXPIRED, scheme mock never called • Test T22-4 insufficient prefunding: balance=10.00 USD; POST -> HTTP 402 INSUFFICIENT_PREFUNDING, scheme mock never called • Test T22-5 inactive merchant: merchant.status=inactive; POST -> HTTP 404 MERCHANT_NOT_FOUND | MpmPaymentControllerTest class with 5+ test cases covering happy path and error paths | • T22-1: HTTP 201, response body contains payment_id, scheme_txn_id, prefund_deducted_usd=35.77, approved_at timestamp • T22-2: HTTP 201, response body does NOT contain prefund_deducted_usd key • T22-3: HTTP 422, error.code=RATE_QUOTE_EXPIRED, ZeroPay mock verifyNoInteractions • T22-4: HTTP 402, error.code=INSUFFICIENT_PREFUNDING, ZeroPay mock verifyNoInteractions • T22-5: HTTP 404, error.code=MERCHANT_NOT_FOUND | 55 | 5.2-T08, 5.2-T16, 5.2-T17 | BE | API-05, RATE-04
5.2-T23 | payment-executor | 5.2 | 5. Transaction Processing (MPM/CPM) | Fixed MPM execution flow | 1 | Unit tests: idempotency replay and duplicate partner_txn_ref scenarios | Two idempotency scenarios must be unit-tested. (A) Idempotency key replay: same Idempotency-Key + same body submitted twice -> second call returns stored 201 response, no double-processing (scheme mock called exactly once, prefunding deducted exactly once). (B) Idempotency key reuse: same Idempotency-Key + different body -> HTTP 422 IDEMPOTENCY_KEY_REUSE. (C) Duplicate partner_txn_ref: different Idempotency-Keys but same partner_txn_ref -> HTTP 409 DUPLICATE_PARTNER_TXN_REF. (D) In-flight: concurrent requests with same idempotency key -> one proceeds, one returns HTTP 409 with X-Idempotency-Status: in_flight. | • Test T23-A: submit POST /v1/payments twice with same Idempotency-Key and same body; mock first call succeeds; assert second call returns same 201 body, scheme called once • Test T23-B: submit with same Idempotency-Key but different collection_amount; assert HTTP 422 IDEMPOTENCY_KEY_REUSE • Test T23-C: two different Idempotency-Keys, same partner_txn_ref; assert second returns HTTP 409 DUPLICATE_PARTNER_TXN_REF • Test T23-D: simulate in-flight by setting Redis key to IN_FLIGHT status before second call; assert HTTP 409 X-Idempotency-Status: in_flight • Verify in T23-A that prefunding_ledger_entry has exactly one DEBIT_PAYMENT row for that txnRef | IdempotencyIntegrationTest with 4 test cases | • T23-A: scheme mock called exactly once; HTTP 201 both times with identical response body • T23-B: HTTP 422, error.code=IDEMPOTENCY_KEY_REUSE • T23-C: HTTP 409, error.code=DUPLICATE_PARTNER_TXN_REF • T23-D: HTTP 409, X-Idempotency-Status header value=in_flight • T23-A: prefunding_ledger_entry contains exactly one row for the txnRef, not two | 45 | 5.2-T07, 5.2-T22 | BE | API-05, RATE-04
5.2-T24 | payment-executor | 5.2 | 5. Transaction Processing (MPM/CPM) | Fixed MPM execution flow | 1 | Unit tests: UNCERTAIN state and batch-reconciliation resolution for MPM timeout | When ZeroPay times out on submitMpm, the transaction moves to UNCERTAIN and prefunding is NOT reversed. This test validates the full lifecycle: (1) scheme timeout -> UNCERTAIN + prefunding held, (2) batch reconciliation confirms APPROVED -> status becomes APPROVED, no reversal, (3) alternate: batch confirms FAILED -> status FAILED, prefunding reversed. Also tests the 24 h alert. | • Test T24-1: mock SchemeTimeoutException from adapter; assert transaction.status=UNCERTAIN, prefunding_account.balance unchanged after call • Test T24-2: call resolveUncertain(txnRef, APPROVED); assert status=APPROVED, prefunding_account.balance still deducted (not reversed) • Test T24-3: call resolveUncertain(txnRef, FAILED); assert status=FAILED, CREDIT_REVERSAL ledger entry exists, balance restored • Test T24-4: attempt resolveUncertain on an already-APPROVED transaction; assert IllegalStateException thrown • Test T24-5: scheduled alert check with UNCERTAIN transaction created 25 h ago; assert UncertainTransactionAlert emitted | UncertainStateTest class with 5 test cases | • T24-1: transaction.status=UNCERTAIN immediately after SchemeTimeoutException; prefunding_account.balance = value before payment call • T24-2: after resolveUncertain APPROVED, transaction.status=APPROVED; no CREDIT_REVERSAL in ledger • T24-3: after resolveUncertain FAILED, CREDIT_REVERSAL row with amount equal to original DEBIT_PAYMENT amount • T24-4: resolveUncertain on APPROVED throws IllegalStateException (idempotency protection) • T24-5: alert fired for transaction with created_at < NOW()-24h; no alert for created_at=NOW()-23h | 45 | 5.2-T11, 5.2-T21 | BE | API-05, RATE-04
5.2-T25 | payment-executor | 5.2 | 5. Transaction Processing (MPM/CPM) | Fixed MPM execution flow | 1 | Write OpenAPI 3.1 spec fragment for POST /v1/payments (MPM) endpoint | The API-05 spec is normative. An OpenAPI 3.1 YAML fragment for POST /v1/payments must document: request body schema (all fields with types, required flags, example values from spec), response schemas (201, 202, 400, 402, 404, 409, 422, 429), all error codes (RATE_QUOTE_EXPIRED, INSUFFICIENT_PREFUNDING, MERCHANT_NOT_FOUND, DUPLICATE_PARTNER_TXN_REF, PAYMENT_MODE_NOT_SUPPORTED, DIRECTION_NOT_ENABLED, MISSING_IDEMPOTENCY_KEY), and required headers (X-API-Key, X-Timestamp, X-Signature, Idempotency-Key). The fragment must be machine-parseable and usable for contract tests. Add to the existing openapi.yaml under paths./v1/payments.post. | • Open (or create) src/main/resources/openapi/openapi.yaml • Under paths./v1/payments, add post: with summary, operationId=executeMpmPayment, security referencing hmacAuth • Define requestBody referencing $ref: '#/components/schemas/MpmPaymentRequest' with all field descriptions and example • Define responses for 201 (MpmPaymentResponse), 202, 400, 402, 404, 409, 422 (multiple error codes), 429 • Validate the YAML with swagger-cli lint; ensure no schema errors | OpenAPI fragment in openapi.yaml for POST /v1/payments and passing swagger-cli lint | • swagger-cli lint openapi.yaml exits with 0 errors • MpmPaymentRequest schema marks quote_id, merchant_qr, direction, scheme_id, customer_ref, partner_txn_ref, collection_amount, collection_currency as required • MpmPaymentResponse schema includes prefund_deducted_usd as optional (not required) • Response 402 is documented with error code INSUFFICIENT_PREFUNDING • Example request body in spec matches the field values from API-05: quote_id=qte_01HX7MNP9AB2CDEF3GH456IJ, collection_amount=35.77, collection_currency=USD | 40 | 5.2-T02, 5.2-T08 | BE | API-05, RATE-04
5.2-T26 | payment-executor | 5.2 | 5. Transaction Processing (MPM/CPM) | Fixed MPM execution flow | 1 | Add rate limiting enforcement (50 req/s) for POST /v1/payments per partner | API-05 §3.5: POST /v1/payments is rate-limited to 50 requests/second per partner. When exceeded, return HTTP 429 RATE_LIMITED with header Retry-After (seconds until window resets), X-RateLimit-Limit: 50, X-RateLimit-Remaining: 0, X-RateLimit-Reset: <unix epoch>. Implementation: use Redis token bucket or sliding window counter with key ratelimit:payments:{partner_id}, window=1s, limit=50. The limit is configurable per partner in partner config (default 50; GME Ops can override). Limits for other endpoints (POST /v1/rates = 20/s, all endpoints = 100/s) are in scope for a separate ticket. | • Implement RateLimiterService.checkPaymentsLimit(long partnerId): INCR Redis key ratelimit:payments:{partnerId} with EXPIRE 1s • If count > partnerConfig.paymentRateLimit (default 50), throw RateLimitExceededException • In RateLimitExceededException handler: return HTTP 429 with X-RateLimit-Limit, X-RateLimit-Remaining=0, X-RateLimit-Reset, Retry-After headers • Wire RateLimiterService check as the first step in PaymentController.executeMpmPayment before idempotency check • Unit test: 51 rapid requests for same partner -> first 50 succeed (or reach next step), 51st returns 429 | RateLimiterService.checkPaymentsLimit() and RateLimitTest | • 50 requests within 1 s for same partner all pass the rate limiter • 51st request within same 1 s window returns HTTP 429 with Retry-After header present • Requests from partner A do not consume partner B's rate limit quota (per-partner isolation) • Partner with custom limit=100 configured by ops: 100 requests/s pass, 101st returns 429 • X-RateLimit-Reset value is a future Unix timestamp (within 2 s of now) | 40 | 5.2-T08 | BE | API-05, RATE-04
5.2-T27 | payment-executor | 5.2 | 5. Transaction Processing (MPM/CPM) | Fixed MPM execution flow | 1 | Implement GET /v1/balance endpoint for OVERSEAS partner prefunding balance inquiry | GET /v1/balance returns the calling OVERSEAS partner's current prefunding balance (API-05 §4.8). Response: partner_id, balance_usd (DECIMAL as string), low_balance_threshold_usd, is_below_threshold (bool), as_of (timestamp). Optional query param ?include_history=true returns last 10 deduction events from prefunding_ledger_entry. LOCAL partners calling this endpoint -> HTTP 403 FORBIDDEN with error code FORBIDDEN. Balance read does NOT require SELECT FOR UPDATE (read-only). balance_usd read must be consistent (no dirty read); use READ COMMITTED isolation at minimum. | • Add @GetMapping('/v1/balance') in BalanceController • Resolve authenticated partner; if partner.type='LOCAL' return HTTP 403 error(FORBIDDEN, 'Prefunding balance is not applicable for LOCAL partners') • Fetch prefunding_account WHERE partner_id=? and low_balance_threshold from same row • Set is_below_threshold = balance < low_balance_threshold • If include_history=true, fetch last 10 rows from prefunding_ledger_entry ORDER BY created_at DESC for account_id • Return PrefundingBalanceResponse with as_of=Instant.now() | BalanceController.getBalance() and BalanceControllerTest | • OVERSEAS partner with balance=48234.56, threshold=10000.00 -> HTTP 200, is_below_threshold=false • OVERSEAS partner with balance=9500.00, threshold=10000.00 -> HTTP 200, is_below_threshold=true • LOCAL partner (GME Remit) -> HTTP 403 error.code=FORBIDDEN • ?include_history=true returns at most 10 entries with fields: payment_id, amount_usd, balance_after_usd, event_at • balance_usd in response serialises as decimal string '48234.5600' (or trimmed '48234.56') NOT as a JSON number | 35 | 5.2-T04, 5.2-T18 | BE | API-05, RATE-04
5.2-T28 | payment-executor | 5.2 | 5. Transaction Processing (MPM/CPM) | Fixed MPM execution flow | 1 | Write end-to-end MPM flow integration test covering certification checklist C-01 through C-03 and C-13 | API-05 §10.4 certification tests. C-01: GET /v1/rates returns valid quote_id and valid_until. C-02: POST /v1/payments with valid quote returns HTTP 201 status=approved. C-03: POST /v1/payments with expired quote returns HTTP 422 RATE_QUOTE_EXPIRED. C-13: POST /v1/payments with insufficient prefunding returns HTTP 402 INSUFFICIENT_PREFUNDING. These tests use Testcontainers (PostgreSQL + Redis) and a mocked ZeroPay adapter. They must run as part of the CI build. Use sandbox magic QR values: ZPQR_TEST_APPROVED for C-02. | • Set up Testcontainers PostgreSQL + Redis; run all migrations; seed test partner (OVERSEAS, SendMN), prefunding balance=1000 USD, merchant with QR=ZPQR_TEST_APPROVED • C-01: POST /v1/rates with target_payout=50000&payout_currency=KRW&scheme_id=zeropay; assert HTTP 200, quote_id non-null, valid_until is a future timestamp • C-02: use quote_id from C-01; POST /v1/payments; assert HTTP 201, status=approved, prefund_deducted_usd present • C-03: expire the Redis quote key manually (DEL) then POST /v1/payments with that quote_id; assert HTTP 422 RATE_QUOTE_EXPIRED • C-13: seed balance=5.00 USD; POST /v1/payments requiring 35.77 USD; assert HTTP 402 INSUFFICIENT_PREFUNDING | MpmCertificationIT integration test class covering C-01, C-02, C-03, C-13 | • C-01: HTTP 200, valid_until parses as ISO-8601 UTC and is > 290 s in the future (default TTL 300 s) • C-02: HTTP 201, response body matches MpmPaymentResponse schema; scheme_txn_id non-null • C-03: HTTP 422, error.code=RATE_QUOTE_EXPIRED; no prefunding_ledger_entry created for that attempt • C-13: HTTP 402, error.code=INSUFFICIENT_PREFUNDING; prefunding_account.balance remains 5.00 after rejection • All 4 test cases pass in CI (Maven/Gradle test phase) with Testcontainers auto-provisioning | 60 | 5.2-T08, 5.2-T16, 5.2-T22, 5.2-T27 | BE | API-05, RATE-04
5.3-T01 | qr-service | 5.3 | 5. Transaction Processing (MPM/CPM) | CPM token generation & flow | 1 | Add cpm_prepare_session DB migration: table + indexes | WBS 5.3 CPM token generation. A cpm_prepare_session row tracks the life of one CPM QR token: issued, reserved prefunding, expiry. Columns needed: id BIGINT PK, cpm_token_id VARCHAR(64) UNIQUE, payment_id VARCHAR(64) UNIQUE, partner_id BIGINT FK partner, scheme_id BIGINT FK qr_scheme, direction VARCHAR(10), customer_ref VARCHAR(255), partner_txn_ref VARCHAR(64), prepare_token VARCHAR(128), qr_content VARCHAR(512), status VARCHAR(20) CHECK IN ('ISSUED','SCANNED','COMPLETED','EXPIRED','FAILED'), prefund_reserved_usd DECIMAL(20,4) NULL, expires_at TIMESTAMPTZ NOT NULL, created_at TIMESTAMPTZ DEFAULT NOW(), updated_at TIMESTAMPTZ. Indexes: (partner_id, created_at), (status, expires_at), unique on (partner_id, partner_txn_ref). | • Create Flyway/Liquibase migration file V5_3_001__cpm_prepare_session.sql • Define table with all columns, types, NOT NULL constraints, and CHECK on status • Add UNIQUE constraint on cpm_token_id and on (partner_id, partner_txn_ref) • Add composite indexes: (partner_id, created_at), (status, expires_at) • Add FK constraints to partner and qr_scheme tables | Migration file V5_3_001__cpm_prepare_session.sql that applies cleanly and rolls back without error | • Table created with all 15 columns; psql \d cpm_prepare_session shows every column with correct type and nullability • UNIQUE constraint on cpm_token_id rejects a duplicate insert • UNIQUE constraint on (partner_id, partner_txn_ref) rejects duplicate for same partner • CHECK constraint on status rejects INSERT with status = 'PENDING' (not in allowed set) • Rollback (DOWN migration) drops table and all indexes without error | 30 |  | BE | API-05
5.3-T02 | qr-service | 5.3 | 5. Transaction Processing (MPM/CPM) | CPM token generation & flow | 1 | Add prefunding_reserved_usd column to prefunding_account migration | WBS 5.3 CPM token generation. The prefunding_account table (one row per OVERSEAS partner, balance DECIMAL(20,4) in USD) needs a reserved_usd DECIMAL(20,4) NOT NULL DEFAULT 0 column to track amounts soft-reserved for active CPM tokens. available_balance = balance - reserved_usd. The scheme must never be called without a successful deduction; reservation at token-issue time enforces this. Adding the column does not break existing MPM flow which does a hard deduction at POST /v1/payments. | • Create migration V5_3_002__prefunding_add_reserved.sql • ADD COLUMN reserved_usd DECIMAL(20,4) NOT NULL DEFAULT 0 to prefunding_account • Add CHECK constraint: reserved_usd >= 0 AND reserved_usd <= balance • Verify existing rows still satisfy the new constraint after migration | Migration file V5_3_002__prefunding_add_reserved.sql | • Column reserved_usd exists with DEFAULT 0; all pre-existing rows have reserved_usd = 0.00 after migration • CHECK constraint rejects UPDATE setting reserved_usd = -1 • CHECK constraint rejects UPDATE setting reserved_usd > balance • SELECT balance - reserved_usd AS available_balance FROM prefunding_account returns non-negative for all rows • Rollback drops column without error | 20 |  | BE | API-05
5.3-T03 | qr-service | 5.3 | 5. Transaction Processing (MPM/CPM) | CPM token generation & flow | 1 | Define CpmGenerateRequest and CpmTokenResponse Java DTOs | WBS 5.3. POST /v1/payments/cpm/generate accepts: scheme_id (String, required), direction (String, required, one of domestic/inbound/outbound/hub), customer_ref (String, required), partner_txn_ref (String, required), country_code (String, required, ISO-3166-1 alpha-2), prefund_reserve_usd (BigDecimal, optional). Response fields: cpm_token_id, prepare_token, qr_content, expires_at (ISO-8601 UTC), prefund_reserved_usd (String decimal, OVERSEAS only), payment_id, scheme_id, partner_txn_ref, created_at. Use Jackson annotations; all amounts as String to avoid floating-point serialisation issues. | • Create CpmGenerateRequest record/class in dto package with @NotNull on required fields, @Pattern for country_code ([A-Z]{2}), @DecimalMin(0) on optional prefund_reserve_usd • Create CpmTokenResponse record/class with all response fields; amounts as String • Annotate both with @JsonInclude(NON_NULL) so OVERSEAS-only fields are omitted for LOCAL partners • Add unit test asserting Jackson round-trip of request and response with example values from spec | CpmGenerateRequest.java, CpmTokenResponse.java, and CpmDtoTest.java | • @Valid on CpmGenerateRequest rejects request missing customer_ref with ConstraintViolationException • @Pattern on country_code rejects 'KOR' (3-char) and accepts 'KR' • CpmTokenResponse serialised to JSON omits prefund_reserved_usd when null (@JsonInclude) • Jackson round-trip of example request {scheme_id:zeropay, direction:inbound, customer_ref:cust_hashed_9f8e7d6c, partner_txn_ref:SENDMN-CPM-20260604-0042, country_code:KR} produces identical object after deserialisation • BigDecimal field prefund_reserve_usd serialises as string '200.00' not 200.0 | 30 | 5.3-T01 | BE | API-05
5.3-T04 | qr-service | 5.3 | 5. Transaction Processing (MPM/CPM) | CPM token generation & flow | 1 | Implement CpmGenerateService.resolveScheme(): country_code to active scheme | WBS 5.3. When a partner calls POST /v1/payments/cpm/generate, GMEPay+ resolves the active QR scheme from country_code. The qr_scheme table has a supported_countries JSON/array column. If no active scheme for the country_code exists, return error NO_SCHEME_FOR_LOCATION (HTTP 422). If multiple active schemes exist for a country and scheme_id is not provided in the request, return VALIDATION_ERROR asking the partner to specify scheme_id. If scheme_id is provided, validate it is active and supports CPM mode (supported_modes includes CPM). Rule also must have CPM enabled for the partner/scheme/direction combination. | • Create CpmGenerateService with method resolveScheme(String countryCode, String schemeIdHint, Long partnerId, String direction) • Query qr_scheme table for rows where supported_countries contains countryCode AND status = ACTIVE AND supported_modes contains CPM • If zero matches: throw CpmException(NO_SCHEME_FOR_LOCATION) • If multiple matches and schemeIdHint is null: throw CpmException(VALIDATION_ERROR, 'Multiple schemes for country; provide scheme_id') • If schemeIdHint provided: validate it exists in matches; if not, throw SCHEME_NOT_FOUND • Validate rule row for (partner_id, scheme_id, direction) has CPM enabled; throw PAYMENT_MODE_NOT_SUPPORTED if not | CpmGenerateService.resolveScheme() method with unit tests covering all 5 branches | • Returns correct scheme when exactly one active CPM-capable scheme matches countryCode=KR • Throws NO_SCHEME_FOR_LOCATION when no active CPM scheme exists for countryCode=US (no ZeroPay) • Throws VALIDATION_ERROR listing scheme options when two active CPM schemes found for country and no hint given • Throws PAYMENT_MODE_NOT_SUPPORTED when rule exists but CPM not in supported_modes • Returns correct scheme when schemeIdHint=zeropay narrows two-scheme result to one | 45 | 5.3-T03 | BE | API-05
5.3-T05 | qr-service | 5.3 | 5. Transaction Processing (MPM/CPM) | CPM token generation & flow | 1 | Implement prefundReserveService.reserveForCpmToken() with SELECT FOR UPDATE atomicity | WBS 5.3. For OVERSEAS partners, the prefunding deduction MUST occur atomically at token issuance. Use SELECT FOR UPDATE on prefunding_account to prevent concurrent over-draws. Logic: lock row, check balance - reserved_usd >= deduction_amount (else INSUFFICIENT_PREFUNDING HTTP 402), UPDATE reserved_usd = reserved_usd + deduction_amount. The deduction_amount is collection_usd derived from the rate engine, or prefund_reserve_usd from the request if supplied (use the smaller of the two as the reservation; the actual hard deduction happens at scheme approval). LOCAL partners (partner.type = LOCAL) skip this step. The prefunding_ledger_entry row is NOT written yet (written at actual deduction on scheme approval). | • Create PrefundReserveService with method reserve(Long partnerId, BigDecimal reserveAmountUsd, String cpmTokenId) returning ReservationResult • Begin transaction; SELECT FOR UPDATE on prefunding_account WHERE partner_id = ? • Compute availableBalance = balance - reserved_usd; if availableBalance < reserveAmountUsd throw InsufficientPrefundingException • UPDATE prefunding_account SET reserved_usd = reserved_usd + reserveAmountUsd, updated_at = NOW() WHERE id = ? • Return ReservationResult(accountId, reserveAmountUsd, balanceAfterReservation) • Add rollback path: if subsequent step fails, call release(cpmTokenId) to decrement reserved_usd | PrefundReserveService.java with reserve() and release() methods + PrefundReserveServiceTest.java | • Concurrent calls: two threads each attempting to reserve 80 USD from a 100 USD balance; only one succeeds, the other gets INSUFFICIENT_PREFUNDING • reserve() with partnerType=LOCAL returns a no-op ReservationResult without touching prefunding_account • After successful reserve(), balance unchanged but reserved_usd incremented by reserveAmountUsd • reserve() with reserveAmountUsd = availableBalance exactly (boundary) succeeds • release() decrements reserved_usd back to original value | 55 | 5.3-T02 | BE | API-05
5.3-T06 | qr-service | 5.3 | 5. Transaction Processing (MPM/CPM) | CPM token generation & flow | 1 | Implement SchemeAdapter.prepareCPM() for ZeroPay: call scheme and get token | WBS 5.3. The ZeroPay Adapter must call 한결원's real-time CPM prepare API to obtain a one-time opaque token (prepare_token) that the partner renders as a QR code. The adapter interface is prepareCPM(context: CpmPrepareContext) -> PrepareToken. ZeroPay returns prepare_token (opaque string, e.g. ZP-CPM-ABCDEF1234567890ABCDEF) and an expiry (default 60 seconds from issuance, configurable). CPM tokens are one-time-use. The ZeroPay realtime_api_base_url and credentials come from the encrypted scheme config (never hard-coded). If scheme API is unreachable: throw SchemeUnavailableException (maps to SCHEME_UNAVAILABLE HTTP 422, retryable). Store raw HTTP response in the request log for audit. | • In ZeroPayAdapter, implement prepareCPM(CpmPrepareContext ctx) method • Load scheme config (realtime_api_base_url, credentials) from secrets vault via SchemeConfigService • POST to ZeroPay CPM prepare endpoint with required fields (partner reference, country_code, customer_token) • On success: return PrepareToken(prepareToken, qrContent, expiresAt) • On HTTP 4xx from ZeroPay: map to appropriate internal error code • On timeout or connection failure: throw SchemeUnavailableException | ZeroPayAdapter.prepareCPM() implementation with unit tests using a mock HTTP client | • Mock returning HTTP 200 with ZP-CPM-ABCDEF token: method returns PrepareToken with correct fields • Mock returning HTTP 503: method throws SchemeUnavailableException • Mock returning connection timeout: method throws SchemeUnavailableException • Credentials are read from SchemeConfigService (mock), never from application.properties or code literal • expiresAt equals response timestamp + configured token_ttl_seconds (default 60) | 50 | 5.3-T04 | BE | API-05
5.3-T07 | qr-service | 5.3 | 5. Transaction Processing (MPM/CPM) | CPM token generation & flow | 1 | Implement CpmGenerateService.createSession(): orchestrate generate flow end-to-end | WBS 5.3. The CPM generate handler must orchestrate: (1) resolve scheme from country_code, (2) validate partner rule enables CPM, (3) for OVERSEAS partners atomically reserve prefunding via SELECT FOR UPDATE, (4) call ZeroPay SchemeAdapter.prepareCPM() to get the token, (5) insert cpm_prepare_session row with status=ISSUED, (6) return CpmTokenResponse. If prefund reservation succeeds but scheme call fails: release reservation and throw SCHEME_UNAVAILABLE. If scheme call succeeds but DB insert fails: release reservation and re-raise (idempotency key prevents duplicate creation on retry). The partner.type field determines LOCAL vs OVERSEAS. | • In CpmGenerateService add createSession(CpmGenerateRequest request, Long partnerId) • Call resolveScheme(); call PrefundReserveService.reserve() if partner.type=OVERSEAS • Call SchemeAdapter.prepareCPM() wrapping in try-catch; on failure release reservation • Insert row into cpm_prepare_session with all fields; status=ISSUED; expires_at = NOW() + token_ttl_seconds • Build and return CpmTokenResponse; set prefund_reserved_usd only for OVERSEAS • Emit transaction event RATE_QUOTE_ISSUED (step 1 of 8-step trail) | CpmGenerateService.createSession() with integration-test-style unit tests covering happy path and failure paths | • Happy path OVERSEAS: reservation increments reserved_usd, cpm_prepare_session inserted with status=ISSUED, response contains prefund_reserved_usd • Happy path LOCAL (GME Remit): reserved_usd on prefunding_account not touched, prefund_reserved_usd absent from response • Scheme call failure after successful reservation: reserved_usd is released (back to original), no cpm_prepare_session row • cpm_token_id in response matches cpm_prepare_session.cpm_token_id in DB • payment_id assigned and stored in cpm_prepare_session | 55 | 5.3-T05, 5.3-T06 | BE | API-05
5.3-T08 | qr-service | 5.3 | 5. Transaction Processing (MPM/CPM) | CPM token generation & flow | 1 | Implement POST /v1/payments/cpm/generate controller endpoint | WBS 5.3. Expose CpmGenerateService as a REST endpoint. Method POST, path /v1/payments/cpm/generate. Auth: HMAC-SHA256 X-Signature header verification (API key + secret, per-request canonical string). Required headers: X-API-Key, X-Timestamp (reject if > 5 min from server time: TIMESTAMP_OUT_OF_RANGE), Idempotency-Key (UUID, reject missing: MISSING_IDEMPOTENCY_KEY). Idempotency: cache (partner_id, Idempotency-Key) -> response for 24h in Redis; if same key+body seen again return stored response; if same key+different body return 422 IDEMPOTENCY_KEY_REUSE. Success: HTTP 201 with CpmTokenResponse. Error codes: VALIDATION_ERROR 400, MISSING_IDEMPOTENCY_KEY 400, INSUFFICIENT_PREFUNDING 402, NO_SCHEME_FOR_LOCATION 422, PAYMENT_MODE_NOT_SUPPORTED 422, SCHEME_UNAVAILABLE 422, RATE_LIMITED 429. | • Add CpmController with @PostMapping('/v1/payments/cpm/generate') • Inject AuthService for HMAC verification and timestamp check • Inject IdempotencyService to check/store Redis cache before calling service • Call CpmGenerateService.createSession(); map CpmException to correct HTTP status and error envelope • Return ResponseEntity<CpmTokenResponse> with HTTP 201 on success • Log X-Request-ID in response header | CpmController.generate() endpoint handler + CpmControllerTest.java (MockMvc tests) | • POST with missing Idempotency-Key header returns 400 MISSING_IDEMPOTENCY_KEY • POST with invalid HMAC signature returns 401 INVALID_SIGNATURE • POST with valid request for OVERSEAS partner returns 201 with all CpmTokenResponse fields including prefund_reserved_usd • Duplicate POST (same Idempotency-Key + same body) returns 201 with cached response; createSession() called exactly once • POST causing INSUFFICIENT_PREFUNDING returns 402 with error envelope {error.code: INSUFFICIENT_PREFUNDING} | 45 | 5.3-T07 | BE | API-05
5.3-T09 | qr-service | 5.3 | 5. Transaction Processing (MPM/CPM) | CPM token generation & flow | 1 | Validate required request fields and enum values for CPM generate | WBS 5.3. The generate endpoint must reject malformed requests before any business logic. Required: scheme_id, direction (domestic¦inbound¦outbound¦hub), customer_ref, partner_txn_ref, country_code (ISO 3166-1 alpha-2, uppercase 2-char). Optional: prefund_reserve_usd (decimal string, must be > 0 if present). partner_txn_ref must be unique per partner (check against transactions + cpm_prepare_session; return DUPLICATE_PARTNER_TXN_REF 409 if already used). Error response format: {error.code: VALIDATION_ERROR, error.details: [{field, issue}]}. | • Add @NotBlank on scheme_id, direction, customer_ref, partner_txn_ref, country_code in CpmGenerateRequest • Add @Pattern(regexp='[A-Z]{2}') on country_code • Add @DecimalMin(value='0', inclusive=false) on prefund_reserve_usd • Add @ValidEnum(DirectionEnum.class) custom annotation on direction • In CpmGenerateService: query (SELECT 1 FROM cpm_prepare_session WHERE partner_id=? AND partner_txn_ref=?) UNION (SELECT 1 FROM transaction WHERE partner_id=? AND partner_txn_ref=?); throw DUPLICATE_PARTNER_TXN_REF if found • Add global @ExceptionHandler for ConstraintViolationException producing VALIDATION_ERROR response with per-field details | Validation annotations on CpmGenerateRequest + duplicate-ref check in service + integration test CpmValidationTest.java | • POST missing country_code returns 400 VALIDATION_ERROR with details[0].field = country_code • POST with direction='WRONG' returns 400 VALIDATION_ERROR for direction field • POST with country_code='KOR' (3 chars) returns 400 VALIDATION_ERROR • POST with duplicate partner_txn_ref (already in cpm_prepare_session) returns 409 DUPLICATE_PARTNER_TXN_REF • POST with prefund_reserve_usd='-5' returns 400 VALIDATION_ERROR | 40 | 5.3-T08 | BE | API-05
5.3-T10 | qr-service | 5.3 | 5. Transaction Processing (MPM/CPM) | CPM token generation & flow | 1 | Implement CPM token expiry scheduler: mark ISSUED tokens as EXPIRED | WBS 5.3. CPM tokens are one-time-use and expire (default 60 seconds). The cpm_prepare_session.expires_at column records the hard expiry. A scheduled task must sweep rows where status=ISSUED AND expires_at < NOW() and set status=EXPIRED. For OVERSEAS partners, any reservation held against an expired token must be released: UPDATE prefunding_account SET reserved_usd = reserved_usd - s.prefund_reserved_usd WHERE partner_id = s.partner_id. Run every 30 seconds. The sweep must be idempotent (repeated execution safe). Expired token IDs must be logged at INFO level for audit. | • Create CpmTokenExpiryScheduler @Scheduled(fixedDelay=30000) bean • SELECT id, partner_id, prefund_reserved_usd FROM cpm_prepare_session WHERE status='ISSUED' AND expires_at < NOW() FOR UPDATE SKIP LOCKED • Bulk UPDATE cpm_prepare_session SET status='EXPIRED', updated_at=NOW() WHERE id IN (...) • For OVERSEAS rows with prefund_reserved_usd > 0: UPDATE prefunding_account SET reserved_usd = reserved_usd - prefund_reserved_usd WHERE partner_id = ? • Log expired token IDs at INFO • Add unit test with time-mocked clock and two tokens: one expired, one still valid | CpmTokenExpiryScheduler.java with unit test | • Token with expires_at = NOW() - 1 second has status updated to EXPIRED by scheduler run • Token with expires_at = NOW() + 30 seconds is NOT expired • OVERSEAS token expiry releases reservation: reserved_usd on prefunding_account decremented by prefund_reserved_usd • LOCAL token expiry does not touch prefunding_account • Two scheduler runs on same expired token: second run is idempotent (no double-release) due to SKIP LOCKED | 45 | 5.3-T05, 5.3-T07 | BE | API-05
5.3-T11 | qr-service | 5.3 | 5. Transaction Processing (MPM/CPM) | CPM token generation & flow | 1 | Handle inbound scheme relay: CpmPendingEvent when merchant scans QR | WBS 5.3. After the customer presents the QR code, ZeroPay's POS network sends an inbound CpmPending event to the ZeroPay Adapter's HTTPS endpoint. The adapter relays it to the Transaction Orchestrator as an inboundCpmPending event containing: prepare_token, merchant_id, payout_amount (KRW). The Orchestrator must: (1) look up cpm_prepare_session by prepare_token, validate status=ISSUED, (2) run the rate engine to compute offer_rate and collection_amount breakdown, (3) update cpm_prepare_session status=SCANNED, (4) dispatch payment.pending_debit webhook to partner. The prefunding reservation is already in place; no additional deduction at this stage. Respond to ZeroPay within the scheme SLA (assume 10s). | • Create CpmPendingEventHandler.handle(CpmPendingEvent event) in Transaction Orchestrator • Fetch cpm_prepare_session by prepare_token; if not found or status != ISSUED return error to adapter • Run RateEngine.computeQuote(rule, payout_amount) to get offer_rate, estimated_collection_amount, service_charge • UPDATE cpm_prepare_session SET status=SCANNED, target_payout=payout_amount, rate_quote_id=<new quote id> • Dispatch payment.pending_debit webhook (async) with fields: payment_id, cpm_token_id, partner_txn_ref, merchant_id, merchant_name, target_payout, offer_rate, estimated_collection_amount, collection_currency, service_charge • Return acknowledgment to ZeroPay adapter within 10s; scheme SLA must be met | CpmPendingEventHandler.java + CpmPendingEventHandlerTest.java | • Valid prepare_token with status=ISSUED: cpm_prepare_session updated to SCANNED and payment.pending_debit webhook dispatched • prepare_token not found: handler returns scheme error without dispatching webhook • prepare_token with status=EXPIRED: handler returns error, no webhook dispatched • payment.pending_debit payload contains offer_rate matching rate engine output for payout_amount=32000 KRW (numerical spot check) • Handler completes within 10s under test with mocked rate engine and mock webhook dispatcher | 55 | 5.3-T07, 5.3-T04 | BE | API-05
5.3-T12 | qr-service | 5.3 | 5. Transaction Processing (MPM/CPM) | CPM token generation & flow | 1 | Implement POST /v1/payments/cpm/confirm: commit CPM transaction to scheme | WBS 5.3. After the partner receives the payment.pending_debit webhook and customer approves, the partner calls POST /v1/payments/cpm/confirm with {txn_ref} (the payment_id from the generate response). The Orchestrator must: (1) validate cpm_prepare_session status=SCANNED (reject if ISSUED/EXPIRED/COMPLETED/FAILED), (2) call SchemeAdapter.commitPayment(prepare_token, amount_krw), (3) on scheme approval: convert the prefunding reservation to a hard deduction (write prefunding_ledger_entry with entry_type=DEBIT_PAYMENT, decrement balance AND reserved_usd), update cpm_prepare_session status=COMPLETED, record all rate fields as locked, dispatch payment.approved webhook. On scheme decline: status=FAILED, release reservation, dispatch payment.failed webhook. | • Create CpmConfirmService.confirm(String paymentId, Long partnerId) • Fetch cpm_prepare_session; assert status=SCANNED; throw appropriate error otherwise • Call SchemeAdapter.commitPayment(prepare_token, target_payout) and get scheme_approval_code • On approval: in single DB transaction update cpm_prepare_session status=COMPLETED, INSERT prefunding_ledger_entry(DEBIT_PAYMENT), UPDATE prefunding_account SET balance = balance - prefund_reserved_usd, reserved_usd = reserved_usd - prefund_reserved_usd • On scheme decline: UPDATE status=FAILED, call PrefundReserveService.release() • Dispatch payment.approved or payment.failed webhook asynchronously | CpmConfirmService.java + POST /v1/payments/cpm/confirm controller endpoint + CpmConfirmServiceTest.java | • Scheme approval: prefunding_ledger_entry DEBIT_PAYMENT written; balance decremented; reserved_usd decremented; cpm_prepare_session status=COMPLETED • Scheme decline: no ledger entry written; reserved_usd released; cpm_prepare_session status=FAILED • Confirm on status=ISSUED (not yet scanned): returns 422 with appropriate error; no ledger write • Confirm on status=COMPLETED (replay): idempotent; returns stored approval response; no double-deduction • Prefunding atomicity: balance and reserved_usd updated in same transaction as ledger entry insert | 55 | 5.3-T11, 5.3-T05 | BE | API-05
5.3-T13 | qr-service | 5.3 | 5. Transaction Processing (MPM/CPM) | CPM token generation & flow | 1 | Implement low-balance alert trigger after CPM prefunding reservation | WBS 5.3. After each successful prefunding reservation, check whether (balance - reserved_usd) <= low_balance_threshold from low_balance_alert_config for that partner. If so, publish a LowBalanceAlertEvent. The alert must fire at most once per configurable cooldown window (default 1 hour) to avoid alert spam: store last_alerted_at in low_balance_alert_config and skip if NOW() - last_alerted_at < cooldown_seconds. Threshold default 10000.00 USD. This applies to CPM reservations and MPM hard deductions equally; the shared service call is made from PrefundReserveService after every successful operation. | • In PrefundReserveService, after successful reserve(), read available_balance = balance - reserved_usd • Load low_balance_alert_config for partner; if is_active=true and available_balance <= threshold_usd • Check last_alerted_at: if null or (NOW() - last_alerted_at) > cooldown_seconds, publish LowBalanceAlertEvent • UPDATE low_balance_alert_config SET last_alerted_at = NOW() • LowBalanceAlertEvent includes partner_id, available_balance, threshold_usd, triggered_at • Add unit test: balance 9500, threshold 10000, last_alerted_at null -> event published | Low-balance check in PrefundReserveService + LowBalanceAlertEvent + LowBalanceAlertServiceTest.java | • available_balance 9500 USD, threshold 10000 USD, last_alerted_at null: LowBalanceAlertEvent published once • available_balance 9500, last_alerted_at = NOW() - 30 min (cooldown 60 min): event NOT published (within cooldown) • available_balance 10001 USD (above threshold): event NOT published • available_balance 10000 exactly (boundary = threshold): event published • is_active=false: event NOT published regardless of balance | 35 | 5.3-T05 | BE | API-05
5.3-T14 | qr-service | 5.3 | 5. Transaction Processing (MPM/CPM) | CPM token generation & flow | 1 | Validate prefund_reserve_usd against scheme max transaction limit | WBS 5.3. The generate request accepts an optional prefund_reserve_usd. If provided, GMEPay+ must validate it does not exceed the scheme's configured max_txn_amount_usd (stored on qr_scheme or scheme_limit config). If omitted, GMEPay+ reserves based on scheme max transaction limit. The reserved amount must always be >= min_txn_amount_usd for the scheme. Return VALIDATION_ERROR with field detail if bounds violated. For ZeroPay: assume max_txn_amount_usd = 1000 USD, min_txn_amount_usd = 0.10 USD (values from scheme config, not hard-coded). | • In CpmGenerateService.createSession(), after resolveScheme(), load SchemeLimit for the resolved scheme • If request.prefund_reserve_usd is null: set reservationAmount = scheme.max_txn_amount_usd • Else: validate request.prefund_reserve_usd <= scheme.max_txn_amount_usd and >= scheme.min_txn_amount_usd; throw VALIDATION_ERROR if outside bounds • Pass resolvedReservationAmount to PrefundReserveService.reserve() • Add tests for above threshold, below threshold, and null (uses max) | Scheme-limit validation logic in CpmGenerateService + unit tests | • prefund_reserve_usd omitted: reservation amount used equals scheme.max_txn_amount_usd (e.g. 1000.00 USD) • prefund_reserve_usd=500.00 (within bounds): reservation amount = 500.00 • prefund_reserve_usd=1001.00 (above max 1000.00): 400 VALIDATION_ERROR with field prefund_reserve_usd • prefund_reserve_usd=0.05 (below min 0.10): 400 VALIDATION_ERROR with field prefund_reserve_usd • Scheme max/min values read from scheme config record, not hard-coded | 35 | 5.3-T07 | BE | API-05
5.3-T15 | qr-service | 5.3 | 5. Transaction Processing (MPM/CPM) | CPM token generation & flow | 1 | Handle SCHEME_UNAVAILABLE: reject CPM generate cleanly without deduction | WBS 5.3. If ZeroPay is unavailable when prepareCPM() is called, the system must not leave a dangling prefunding reservation. The handler must: (1) release any reservation made in step 3, (2) return SCHEME_UNAVAILABLE HTTP 422 to the partner. Partners should retry with backoff; a new Idempotency-Key is required on retry because the original request did not complete. The scheme is never called without a prior successful reservation, and the reservation is never left unreleased on failure. Also handle: if ZeroPay returns a non-retryable error (e.g. invalid credentials) map to INTERNAL_ERROR 500. | • In CpmGenerateService.createSession(), wrap SchemeAdapter.prepareCPM() in try-catch • On SchemeUnavailableException: call PrefundReserveService.release(); throw mapped CpmException(SCHEME_UNAVAILABLE) • On unexpected RuntimeException: call release(); throw CpmException(INTERNAL_ERROR) • In controller, map SCHEME_UNAVAILABLE to HTTP 422 with retryable=true in error envelope • Add unit test simulating scheme timeout after reservation | Exception handling in CpmGenerateService + unit tests for unavailable-scheme path | • Mock scheme unavailable: reserved_usd on prefunding_account returns to pre-call value • Mock scheme unavailable: HTTP 422 SCHEME_UNAVAILABLE returned to partner • Mock scheme throws unexpected NPE: reserved_usd released; HTTP 500 INTERNAL_ERROR returned • No cpm_prepare_session row inserted when scheme call fails • Happy path after failed attempt (new Idempotency-Key): second attempt succeeds and inserts session row | 35 | 5.3-T07, 5.3-T05 | BE | API-05
5.3-T16 | qr-service | 5.3 | 5. Transaction Processing (MPM/CPM) | CPM token generation & flow | 1 | Idempotency layer for CPM generate: Redis cache with 24h TTL | WBS 5.3. All POST endpoints require Idempotency-Key (UUID, 16-128 chars). The Hub caches (partner_id, idempotency_key) -> (response_status, response_body) in Redis for 24 hours. Behaviour: same key + same body = return cached response without re-processing; same key + different body = return 422 IDEMPOTENCY_KEY_REUSE; absent key = 400 MISSING_IDEMPOTENCY_KEY; in-flight duplicate = 409 with X-Idempotency-Status: in_flight. For CPM generate, the response cached is the CpmTokenResponse with all fields (even if the token has since expired). Implement using IdempotencyService shared with other endpoints. | • In IdempotencyService, implement checkAndStore(partnerId, key, requestBodyHash) before service call • Store key as Redis hash with fields: status, body, request_hash, created_at; TTL 86400s • On cache miss: set status=in_flight; proceed with service; on completion store final response • On hit with same request_hash and status != in_flight: return cached response • On hit with different request_hash: return 422 IDEMPOTENCY_KEY_REUSE • On hit with status=in_flight: return 409 with X-Idempotency-Status: in_flight | IdempotencyService caching logic for CPM generate in IdempotencyServiceTest.java and wired into CpmController | • First call stores response in Redis with TTL ~86400s; second call with same key returns cached 201 without calling createSession() • Second call with same key but different country_code in body returns 422 IDEMPOTENCY_KEY_REUSE • Concurrent duplicate calls while first is in_flight: second returns 409 • Missing Idempotency-Key header returns 400 MISSING_IDEMPOTENCY_KEY • After Redis TTL expiry (mock clock advance 25h): same key treated as fresh request | 50 | 5.3-T08 | BE | API-05
5.3-T17 | qr-service | 5.3 | 5. Transaction Processing (MPM/CPM) | CPM token generation & flow | 1 | Unit tests: rate-engine integration in CPM pending event with numeric vectors | WBS 5.3. The rate engine runs when the CpmPendingEvent arrives (merchant scan). Test the full 5-step USD pool calculation with real numeric vectors. Inputs: partner SendMN (OVERSEAS, USD collection), direction=inbound, target_payout=50000 KRW, cost_rate_coll (usd_usd=1.0 since collect ccy=USD), cost_rate_pay (usd_krw=1400.00), m_a=0.015, m_b=0.005, service_charge=0.50 USD. Expected: payout_usd_cost = 50000/1400 = 35.714286; collection_usd = 35.714286/(1-0.02) = 36.443149; send_amount = 36.443149 * 1.0 = 36.443149; collection_amount = 36.443149 + 0.50 = 36.943149; pool identity: 36.443149 - 36.443149*0.015 - 36.443149*0.005 = 35.714286 (within 0.01 USD). offer_rate_coll = 36.443149 / (36.443149 - 0.546647) = 1.015228 per unit; cross_rate = 50000/36.443149 = 1371.97. | • Add test class RateEngineCpmTest • Set up test Rule with m_a=0.015, m_b=0.005, service_charge_amount=0.50, cost_rate_coll=1.0, cost_rate_pay=1400.00 • Call rateEngine.computeQuote(rule, 50000, KRW) • Assert payout_usd_cost = 35.714286 (tolerance 0.000001) • Assert collection_usd = 36.443149 (tolerance 0.000001) • Assert pool identity: collection_usd - collection_margin_usd - payout_margin_usd == payout_usd_cost within 0.01 • Assert offer_rate_coll computed correctly; assert collection_amount = 36.943149 | RateEngineCpmTest.java with at least 4 parameterised test vectors including the above | • payout_usd_cost asserted within 0.000001 of 35.714286 using BigDecimal arithmetic • Pool identity holds: 36.443149 - 0.546647 - 0.182216 = 35.714286 (delta < 0.01 USD) • collection_amount = 36.943149 (send_amount + service_charge) • offer_rate_coll = send_amount / (collection_usd - collection_margin_usd) = 1.015228 within tolerance • Second vector: target_payout=32000 KRW, same rule: payout_usd_cost=22.857143, collection_usd=23.323615, collection_amount=23.823615 | 45 | 5.3-T11 | BE | API-05
5.3-T18 | qr-service | 5.3 | 5. Transaction Processing (MPM/CPM) | CPM token generation & flow | 1 | Unit tests: atomic prefunding deduction for CPM with concurrency vector | WBS 5.3. Test that SELECT FOR UPDATE prevents concurrent over-draws. Scenario: partner has balance=100.00 USD, reserved_usd=0. Two concurrent CPM generate calls each requesting reservation of 70.00 USD. Only one should succeed; the other must receive INSUFFICIENT_PREFUNDING. Use a DB-level test (TestContainers or equivalent) to exercise actual locking, not application-level mocking. Also test: reservation of exactly 100.00 (boundary), reservation of 100.01 (over by 0.01 rejected). | • Set up TestContainers PostgreSQL with prefunding_account row: balance=100.00, reserved_usd=0 • Spawn two threads simultaneously calling PrefundReserveService.reserve(partnerId, 70.00, tokenId) • Assert exactly one thread returns success and the other throws InsufficientPrefundingException • After first success: reserved_usd=70.00, available=30.00; second attempt of 70.00 must fail • Add boundary test: reserve(100.00) succeeds; reserve(100.01) fails • Add release test: after reserve(70.00) then release, reserved_usd returns to 0 | PrefundConcurrencyTest.java using TestContainers | • Of two concurrent 70.00 USD reservation attempts on 100.00 balance, exactly one succeeds • balance unchanged after reservation; reserved_usd = 70.00 after first success • reserve(100.00) on available balance exactly 100.00 succeeds (boundary) • reserve(100.01) fails with InsufficientPrefundingException even at boundary • After release(): reserved_usd = 0; subsequent reserve(100.00) succeeds again | 55 | 5.3-T05 | BE | API-05
5.3-T19 | qr-service | 5.3 | 5. Transaction Processing (MPM/CPM) | CPM token generation & flow | 1 | Unit tests: CPM token expiry and reservation release with mocked clock | WBS 5.3. Test the expiry scheduler edge cases. Scenario A: token with expires_at = T-1s, OVERSEAS, prefund_reserved_usd=200.00 -> status becomes EXPIRED, reserved_usd decremented by 200. Scenario B: two expired tokens for same partner, both released in one scheduler run. Scenario C: token already SCANNED (merchant has scanned): scheduler must NOT expire it (SCANNED tokens are past the reservation stage, they will be handled by confirm flow). Scenario D: SKIP LOCKED behaviour: token locked by another transaction is skipped (not double-processed). | • Create CpmTokenExpirySchedulerTest with mocked Clock • Seed cpm_prepare_session rows for each scenario • Run scheduler.sweep() with mocked clock • Assert scenario A: row status=EXPIRED, prefunding_account.reserved_usd decremented • Assert scenario B: both rows EXPIRED, reserved_usd decremented correctly (sum) • Assert scenario C: SCANNED row not touched • Assert scenario D: locked row skipped without error or double-release | CpmTokenExpirySchedulerTest.java with 4 test scenarios | • Scenario A: reserved_usd decremented by exactly 200.00 after expiry • Scenario B: two tokens (150.00 + 200.00): reserved_usd decremented by 350.00 total • Scenario C: SCANNED token unchanged after scheduler run • Scenario D: scheduler logs skipped token ID but does not update it • All scenarios: no rows with status=ISSUED and expires_at < NOW() remain after sweep | 40 | 5.3-T10 | BE | API-05
5.3-T20 | qr-service | 5.3 | 5. Transaction Processing (MPM/CPM) | CPM token generation & flow | 1 | Unit tests: CPM confirm happy path and idempotency | WBS 5.3. Test POST /v1/payments/cpm/confirm success and replay. Scenario A (happy path): cpm_prepare_session status=SCANNED, scheme approves -> ledger entry DEBIT_PAYMENT written, balance decremented by prefund_reserved_usd, reserved_usd decremented, session status=COMPLETED, payment.approved webhook dispatched. Scenario B (replay): call confirm again on same paymentId (session already COMPLETED) -> returns stored approval; no second ledger entry; no double deduction. Scenario C: session status=ISSUED at confirm time (not yet scanned) -> returns 422. Scenario D: scheme declines -> ledger entry NOT written, reserved_usd released, session status=FAILED, payment.failed webhook dispatched. | • Set up CpmConfirmServiceTest with mock SchemeAdapter, mock PrefundReserveService, in-memory or TestContainers DB • Run scenario A: assert ledger entry inserted, balance and reserved_usd updated atomically • Run scenario B: call confirm twice on same paymentId; count prefunding_ledger_entry rows = 1 • Run scenario C: assert 422 error code CPM_NOT_READY or equivalent • Run scenario D: assert no ledger entry, reserved_usd released, status=FAILED • Check that payment.approved and payment.failed webhooks are dispatched in correct scenarios | CpmConfirmServiceTest.java with 4 scenarios | • Scenario A: exactly one DEBIT_PAYMENT ledger entry; balance = balance - prefund_reserved_usd; reserved_usd = 0 • Scenario B: second confirm call returns same approval response; ledger row count unchanged at 1 • Scenario C: confirm on ISSUED session returns 422; no ledger entry written • Scenario D: scheme decline writes no ledger entry; reserved_usd = 0 (released); status=FAILED • Scenario A: payment.approved webhook dispatch called once with correct fields | 50 | 5.3-T12 | BE | API-05
5.3-T21 | qr-service | 5.3 | 5. Transaction Processing (MPM/CPM) | CPM token generation & flow | 1 | Unit tests: CPM generate error paths (expired token, invalid scheme, duplicate ref) | WBS 5.3. Test all error rejection paths at the generate endpoint. (1) Duplicate partner_txn_ref: same ref used twice by same partner -> 409 DUPLICATE_PARTNER_TXN_REF on second call. (2) NO_SCHEME_FOR_LOCATION: country_code=XX (no scheme) -> 422. (3) PAYMENT_MODE_NOT_SUPPORTED: rule exists but CPM not in supported_modes -> 422. (4) DIRECTION_NOT_ENABLED: direction=outbound but rule only has inbound -> 422. (5) SCHEME_UNAVAILABLE during prepareCPM: reserved_usd released, 422 returned, no cpm_prepare_session row. (6) INSUFFICIENT_PREFUNDING: balance - reserved_usd < requested amount -> 402 with no scheme call. | • Create CpmGenerateErrorTest with MockMvc + mock dependencies • Test case 1: insert existing session with same partner_txn_ref, call generate • Test case 2: configure no scheme for country_code=XX, call generate • Test case 3: configure rule without CPM in supported_modes • Test case 4: configure rule with direction=INBOUND only, call with direction=outbound • Test case 5: mock prepareCPM to throw SchemeUnavailableException; assert no DB row and reservation released • Test case 6: set prefunding balance to 10.00, request reserve_usd=50.00 | CpmGenerateErrorTest.java with 6 error-path test cases | • Case 1: HTTP 409 DUPLICATE_PARTNER_TXN_REF; no new cpm_prepare_session row • Case 2: HTTP 422 NO_SCHEME_FOR_LOCATION; no reservation • Case 3: HTTP 422 PAYMENT_MODE_NOT_SUPPORTED; no reservation • Case 4: HTTP 422 DIRECTION_NOT_ENABLED; no reservation • Case 5: HTTP 422 SCHEME_UNAVAILABLE; reserved_usd unchanged after call • Case 6: HTTP 402 INSUFFICIENT_PREFUNDING; no scheme call (mock verifies prepareCPM never invoked) | 45 | 5.3-T09, 5.3-T15 | BE | API-05
5.3-T22 | qr-service | 5.3 | 5. Transaction Processing (MPM/CPM) | CPM token generation & flow | 1 | OpenAPI spec: document POST /v1/payments/cpm/generate in partner-api.yaml | WBS 5.3. The openapi/partner-api.yaml is the ground truth for contract tests. Add the full spec for POST /v1/payments/cpm/generate: path, method, summary, required headers (X-API-Key, X-Timestamp, X-Signature, Idempotency-Key), requestBody schema with all fields and constraints (scheme_id string, direction enum, customer_ref string, partner_txn_ref string, country_code pattern [A-Z]{2}, prefund_reserve_usd string decimal optional), responses 201 CpmTokenResponse schema, 400 MISSING_IDEMPOTENCY_KEY, 400 VALIDATION_ERROR, 402 INSUFFICIENT_PREFUNDING, 409 DUPLICATE_PARTNER_TXN_REF, 422 (NO_SCHEME_FOR_LOCATION, PAYMENT_MODE_NOT_SUPPORTED, SCHEME_UNAVAILABLE), 429 RATE_LIMITED. All amount fields as type: string (decimal) per spec convention. | • Open openapi/partner-api.yaml • Add path /v1/payments/cpm/generate with post operation • Define requestBody schema $ref CpmGenerateRequest with required array and property constraints • Define 201 response schema $ref CpmTokenResponse; all amount fields type: string • Add error response schemas for each listed HTTP status reusing shared ErrorEnvelope $ref • Add example request/response matching spec example (partner_txn_ref: SENDMN-CPM-20260604-0042) • Run openapi-generator validate or spectral lint; zero errors | Updated openapi/partner-api.yaml with CPM generate endpoint fully specified, passing lint | • openapi-generator validate reports 0 errors and 0 warnings on the updated file • 201 response schema contains all 9 CpmTokenResponse fields with correct types • prefund_reserved_usd has type: string and is not in required array (optional, OVERSEAS only) • country_code property has pattern: ^[A-Z]{2}$ in schema • direction property has enum: [domestic, inbound, outbound, hub] | 40 | 5.3-T08 | BE | API-05
5.3-T23 | qr-service | 5.3 | 5. Transaction Processing (MPM/CPM) | CPM token generation & flow | 1 | Document payment.pending_debit webhook in partner-api.yaml and developer guide | WBS 5.3. The payment.pending_debit webhook is CPM-only; delivered after merchant POS scans the QR. Partners use it to show the estimated charge to the customer. Fields: event_id, event_type=payment.pending_debit, created_at, partner_id, data.{payment_id, cpm_token_id, partner_txn_ref, merchant_id, merchant_name, target_payout, payout_currency, offer_rate, estimated_collection_amount, collection_currency, service_charge, service_charge_currency}. The webhook is signed: X-GME-Webhook-Signature: sha256=HMAC-SHA256(body, webhook_signing_secret). Partner must respond HTTP 2xx within 10s. Note in docs: this webhook arrives BEFORE payment.approved; customer sees amount only after scheme approval (OI-01). | • In openapi/partner-api.yaml add webhook schema for payment.pending_debit under webhooks or components/schemas • Add all data fields with types and examples matching spec (offer_rate: 0.000703, estimated_collection_amount: 22.83 for 32000 KRW) • Document signing header X-GME-Webhook-Signature in webhook description • Note: estimated_collection_amount is GMEPay+ derived; partner may charge a different amount to customer (partner computes final) • In developer guide (docs/partner-integration.md or equivalent), add CPM webhook flow section with sequence note | payment.pending_debit webhook schema in openapi/partner-api.yaml + documentation note in developer guide | • payment.pending_debit schema has all 12 data fields listed above • offer_rate field type is string with example 0.000703 • Documentation notes that payment.pending_debit precedes payment.approved and is CPM-only • X-GME-Webhook-Signature header documented with HMAC-SHA256 signing note • openapi lint passes after addition | 35 | 5.3-T22 | BE | API-05
5.3-T24 | qr-service | 5.3 | 5. Transaction Processing (MPM/CPM) | CPM token generation & flow | 1 | Add 8-step event trail entries for CPM generate and confirm steps | WBS 5.3. Every transaction must carry an 8-step audit trail in transaction_event table: step 1=RATE_QUOTE_ISSUED, step 2=PREFUND_DEDUCTED, step 3=SCHEME_SUBMITTED, step 4=SCHEME_APPROVED or SCHEME_DECLINED, step 5=TRANSACTION_COMMITTED, step 6=SETTLEMENT_BATCHED, step 7=WEBHOOK_QUEUED, step 8=WEBHOOK_DELIVERED. For CPM: RATE_QUOTE_ISSUED fires when pending_debit webhook is dispatched (rate computed at scan time); PREFUND_DEDUCTED fires at confirm when reservation converts to hard deduction; steps 3-8 follow standard flow. For LOCAL partners, step 2 is recorded with detail={skipped:true} to satisfy the 8-row requirement. | • In CpmPendingEventHandler, after rate engine call, INSERT transaction_event(txn_id, step=1, event_type=RATE_QUOTE_ISSUED, detail={quote_ref, offer_rate}) • In CpmConfirmService, after successful deduction, INSERT transaction_event(step=2, event_type=PREFUND_DEDUCTED, detail={amount_usd, balance_after}) for OVERSEAS; for LOCAL insert with detail={skipped:true} • Add SCHEME_SUBMITTED event before scheme adapter call • Chain remaining events in existing commit/approve/webhook flow • Assert no transaction is committed without all 8 event rows in unit test | Event trail inserts in CpmPendingEventHandler and CpmConfirmService + TransactionEventTrailTest.java | • After CPM confirm: transaction_event table has rows for steps 1-5 with correct event_type values • OVERSEAS partner: step 2 event_type=PREFUND_DEDUCTED; detail contains amount_usd and balance_after • LOCAL partner: step 2 row present with detail containing skipped:true; not absent • Step 1 occurred_at <= step 2 occurred_at (chronological ordering) • duration_ms on step 2 reflects time since step 1 was recorded | 40 | 5.3-T12, 5.3-T11 | BE | API-05
5.3-T25 | qr-service | 5.3 | 5. Transaction Processing (MPM/CPM) | CPM token generation & flow | 1 | Sandbox: simulate CPM token generate and prefunding for test partners | WBS 5.3. The sandbox environment must support CPM generate with simulated ZeroPay responses. Sandbox differences: no real ZeroPay connection; prepareCPM returns a deterministic test token ZP-CPM-TEST-<uuid>; prefunding balance pre-loaded (configurable via sandbox control API). Sandbox must support certification test C-04 (generate CPM token -> HTTP 201, prepare_token present) and C-13 (insufficient prefunding -> HTTP 402). Sandbox test partner SendMN should have prefunding balance 5000.00 USD. Token expiry still fires at 60s in sandbox. Ensure sandbox ZeroPayAdapter stub returns token without hitting real API. | • In ZeroPayAdapterStub (sandbox profile), implement prepareCPM to return PrepareToken(ZP-CPM-TEST-<uuid>, ZP-CPM-TEST-<uuid>, NOW()+60s) • Ensure sandbox prefunding seeded at 5000.00 USD for test OVERSEAS partner • Expose sandbox control endpoint POST /sandbox/prefunding/{partnerId}/set {balance_usd} for test setup • Verify C-04: POST /v1/payments/cpm/generate with test credentials returns 201 with prepare_token=ZP-CPM-TEST-* • Verify C-13: set balance to 0 via control API; call generate; returns 402 INSUFFICIENT_PREFUNDING • Add sandbox integration test asserting both scenarios | ZeroPayAdapterStub.prepareCPM() + sandbox seed data + sandbox control endpoint + SandboxCpmIntegrationTest.java | • Sandbox POST /v1/payments/cpm/generate with test partner credentials returns 201 and prepare_token matching ZP-CPM-TEST-* pattern • Sandbox cpm_prepare_session row created with status=ISSUED and expires_at ~ NOW()+60s • After POST /sandbox/prefunding/set {balance_usd:0}: generate returns 402 INSUFFICIENT_PREFUNDING • Sandbox prepareCPM never calls real ZeroPay URL (verified by no outbound HTTP to ZeroPay in test) • Token expiry scheduler runs in sandbox and moves ISSUED tokens to EXPIRED after 60s | 50 | 5.3-T08, 5.3-T10 | BE | API-05
5.4-T01 | qr-service | 5.4 | 5. Transaction Processing (MPM/CPM) | QR parsing (EMVCo) & merchant resolution | 1 | Define MerchantIdentifier and ParsedQRPayload Java interfaces | WBS 5.4 — QR Parser module. The QR Parser is a Hub Core component that decodes EMVCo MPM QR payloads and resolves the merchant identity from the local DB. Its public contract is scheme-agnostic. Two output types are needed: ParsedQRPayload (raw parse result before DB resolution) and MerchantIdentifier (fully resolved merchant record returned to the Orchestrator). Fields: ParsedQRPayload{rawPayload:String, formatIndicator:int, currencyCode:String, merchantName:String, merchantCity:String, mcc:String, countryCode:String, maiTag:int, merchantId:String, qrCodeId:String, encodedAmount:BigDecimal nullable, crcVerified:boolean}. MerchantIdentifier{merchantId:String, qrCodeId:String, merchantName:String, merchantType:String, feeTier:String, schemeId:String, isActive:boolean}. | • Create package com.gmepayplus.qrparser.model • Define interface/record ParsedQRPayload with all fields listed in context • Define interface/record MerchantIdentifier with all fields listed in context • Add Javadoc referencing EMVCo tag IDs (tag 52=MCC, 53=currency, 58=country, 59=name, 60=city, 63=CRC, 26-51=MAI) • Commit with no logic — pure data contract | ParsedQRPayload.java and MerchantIdentifier.java in com.gmepayplus.qrparser.model | • ParsedQRPayload has crcVerified boolean and nullable encodedAmount • MerchantIdentifier has feeTier and merchantType fields for fee-rate selection • Both types are immutable (all-final or record) • No scheme-specific imports; no ZeroPay references in these interfaces | 20 |  | BE | SCH-06
5.4-T02 | qr-service | 5.4 | 5. Transaction Processing (MPM/CPM) | QR parsing (EMVCo) & merchant resolution | 1 | Define QRParseException hierarchy with error codes | WBS 5.4 — QR Parser. Parse failures must be categorised with specific error codes so the Orchestrator can return correct HTTP 422 responses. Required codes (from SCH-06 §3.4): QR_INVALID_CHECKSUM (CRC-16 mismatch), QR_UNKNOWN_SCHEME (MAI tag does not match any registered scheme), QR_MALFORMED (missing mandatory tag: 00, 52, 53, 58, 59, 60, or 63), QR_CURRENCY_MISMATCH (tag 53 != 410 for ZeroPay). Additional resolution codes: MERCHANT_NOT_FOUND, MERCHANT_INACTIVE, QR_NOT_FOUND, QR_DEACTIVATED, QR_MERCHANT_MISMATCH (qr_code references a different merchant_id than the payload). All extend QRParseException(errorCode, message). | • Create QRParseException(String errorCode, String message, Throwable cause) • Create enum QRErrorCode with all six parse codes and three resolution codes listed in context • Create subclasses or use factory methods: QRInvalidChecksumException, QRMalformedException, QRUnknownSchemeException, QRCurrencyMismatchException • Create resolution exception classes: MerchantNotFoundException, MerchantInactiveException, QRDeactivatedException, QRMerchantMismatchException • Add getErrorCode() method returning the enum value | QRParseException.java, QRErrorCode.java, and subclass files in com.gmepayplus.qrparser.exception | • QRErrorCode enum contains exactly: QR_INVALID_CHECKSUM, QR_UNKNOWN_SCHEME, QR_MALFORMED, QR_CURRENCY_MISMATCH, MERCHANT_NOT_FOUND, MERCHANT_INACTIVE, QR_NOT_FOUND, QR_DEACTIVATED, QR_MERCHANT_MISMATCH • All exceptions extend QRParseException • getErrorCode() returns a non-null QRErrorCode • No checked exceptions — all extend RuntimeException | 20 | 5.4-T01 | BE | SCH-06
5.4-T03 | qr-service | 5.4 | 5. Transaction Processing (MPM/CPM) | QR parsing (EMVCo) & merchant resolution | 1 | Define QRParserService interface and SchemeQRParser SPI | WBS 5.4 — QR Parser. The Hub Core calls QRParserService.parse(rawPayload, schemeId) which returns a ParsedQRPayload. Internally, it delegates to a registered SchemeQRParser (the Strategy/SPI pattern) looked up by schemeId. A ZeroPayQRParser implements SchemeQRParser for schemeId=ZEROPAY. This design allows future schemes (KHQR, QPay) to add a new SchemeQRParser without changing Hub Core. QRParserService also has resolveIdentifier(ParsedQRPayload) -> MerchantIdentifier (DB lookup, scheme-agnostic). Both methods declare throws QRParseException. | • Create interface QRParserService with methods: ParsedQRPayload parse(String rawPayload, String schemeId); MerchantIdentifier resolveIdentifier(ParsedQRPayload parsed) • Create interface SchemeQRParser with methods: boolean supports(String schemeId); ParsedQRPayload parse(String rawPayload) • Create @Service class QRParserServiceImpl that takes List<SchemeQRParser> and routes to matching parser • Add getSupportedSchemes() helper returning list of registered schemeIds • Wire with Spring @Autowired constructor injection | QRParserService.java, SchemeQRParser.java interfaces and QRParserServiceImpl.java skeleton (no ZeroPay logic yet) | • QRParserServiceImpl.parse() throws QRUnknownSchemeException when no parser supports the given schemeId • QRParserServiceImpl accepts List<SchemeQRParser> — adding a new parser requires only registering a new @Component bean • resolveIdentifier is defined on the service, not the scheme parser (DB lookup is scheme-agnostic) • Unit test: registering two parsers with different schemeId, calling parse(payload, ZEROPAY) routes to correct one | 30 | 5.4-T01, 5.4-T02 | BE | SCH-06
5.4-T04 | qr-service | 5.4 | 5. Transaction Processing (MPM/CPM) | QR parsing (EMVCo) & merchant resolution | 1 | Implement EMVCo TLV tokenizer (tag-length-value splitter) | WBS 5.4 — QR Parser. EMVCo QR payloads are ASCII strings in TLV format: each data object is exactly TAG(2 chars) + LENGTH(2 chars, decimal) + VALUE(LENGTH chars). Example: '000201' = tag 00, length 02, value '01'. Tags are at the top level and recursively inside Merchant Account Information (MAI) templates. The tokenizer must handle: nested TLV (MAI slot tag 26-51 contains its own TLV sub-objects), overlapping length values, and malformed input where declared length exceeds remaining string. Implement as a stateless utility class EMVCoTlvParser with a static method: Map<Integer,String> parseTopLevel(String payload) and Map<Integer,String> parseTemplate(String templateValue). | • Create class EMVCoTlvParser in com.gmepayplus.qrparser.emvco • Implement parseTopLevel(String payload): iterate by reading 2-char tag, 2-char decimal length, then slice VALUE; accumulate into LinkedHashMap<Integer,String> • Implement parseTemplate(String value): identical algorithm applied to a MAI template string • Throw QRMalformedException if declared length > remaining string length • Throw QRMalformedException if payload is null or blank • Preserve insertion order; duplicate tags should throw QRMalformedException | EMVCoTlvParser.java utility class with parseTopLevel and parseTemplate methods | • parseTopLevel('000201520412345399KRW') returns {0:'01', 52:'1234', 53:'KRW'} — verify tag/length/value slicing • parseTopLevel throws QRMalformedException when declared length 99 but only 3 chars remain • parseTemplate works correctly on a ZeroPay MAI sub-string containing merchant_id and qr_code_id sub-tags • Empty string input throws QRMalformedException with errorCode QR_MALFORMED • Duplicate tag in same level throws QRMalformedException | 40 | 5.4-T02 | BE | SCH-06
5.4-T05 | qr-service | 5.4 | 5. Transaction Processing (MPM/CPM) | QR parsing (EMVCo) & merchant resolution | 1 | Implement CRC-16/CCITT checksum verifier for EMVCo QR | WBS 5.4 — QR Parser. EMVCo QR payloads carry a CRC-16/CCITT checksum in tag 63 (always 4 hex chars, last data object). The checksum covers all characters of the payload UP TO AND INCLUDING the tag and length of tag 63 (i.e. the string ends with '6304' before the 4 hex CRC digits). Algorithm: CRC-16/CCITT, polynomial 0x1021, initial value 0xFFFF, no input/output reflection, no final XOR. Example: payload='000201...6304' then CRC computed over that string; result must equal the 4 hex chars of tag 63 value. Error code on mismatch: QR_INVALID_CHECKSUM. | • Create class EMVCoCrcVerifier in com.gmepayplus.qrparser.emvco • Implement static boolean verify(String fullPayload): find tag 63 position, extract 4-char hex CRC value, compute CRC-16/CCITT over fullPayload.substring(0, tag63ValueStart), compare • Implement static String compute(String data): returns 4-char uppercase hex CRC-16/CCITT • Use polynomial 0x1021, init 0xFFFF, process byte-by-byte, no reflection • Throw QRInvalidChecksumException with errorCode QR_INVALID_CHECKSUM when verification fails | EMVCoCrcVerifier.java with verify() and compute() methods | • Known vector: EMVCo spec sample payload must produce matching CRC-16 value (use standard EMVCo test vector from spec appendix, e.g. '00020101021153160004000205678900000000000005303156304A60A' — verify last 4 chars A60A) • verify() returns true for correct payload • verify() throws QRInvalidChecksumException for payload where last 4 chars are changed to '0000' • compute() on empty string returns 'FFFF' (CRC of empty = init value 0xFFFF, no processing) • Tag 63 absent from payload throws QRMalformedException not NullPointerException | 40 | 5.4-T02 | BE | SCH-06
5.4-T06 | qr-service | 5.4 | 5. Transaction Processing (MPM/CPM) | QR parsing (EMVCo) & merchant resolution | 1 | Implement ZeroPayQRParser — mandatory tag extraction | WBS 5.4 — QR Parser. ZeroPayQRParser implements SchemeQRParser for schemeId=ZEROPAY. Parse steps (SCH-06 §3.4): (1) Verify CRC-16 via EMVCoCrcVerifier — throw QR_INVALID_CHECKSUM on fail. (2) Confirm tag 00 value = '01' (format indicator) — throw QR_MALFORMED if absent or wrong. (3) Extract tag 52 (MCC), tag 53 (currency — must be '410' for KRW, else QR_CURRENCY_MISMATCH), tag 58 (country), tag 59 (merchantName), tag 60 (merchantCity). (4) All of tags 00, 52, 53, 58, 59, 60, 63 are mandatory — missing any throws QR_MALFORMED. Encoded amount is optional (tag 54). This ticket: implement mandatory tags and CRC only; MAI extraction is T07. | • Create ZeroPayQRParser implements SchemeQRParser in package com.gmepayplus.qrparser.zeropay • Implement parse(String rawPayload): call EMVCoCrcVerifier.verify(), then EMVCoTlvParser.parseTopLevel() • Check tag 00 == '01'; check all mandatory tags present (52,53,58,59,60,63); check tag 53 == '410' • Extract optional tag 54 as BigDecimal if present • Return a partially-filled ParsedQRPayload (maiTag=0, merchantId=null, qrCodeId=null — filled by T07) • Annotate with @Component to auto-register | ZeroPayQRParser.java with mandatory tag validation and partial ParsedQRPayload construction | • Valid payload with all mandatory tags and tag53=410 returns ParsedQRPayload with crcVerified=true • Payload with tag53=840 (USD) throws QRCurrencyMismatchException • Payload missing tag52 throws QRMalformedException • Payload with bad CRC throws QRInvalidChecksumException before any other validation • Tag54 present as '50000' is parsed to encodedAmount=BigDecimal(50000); absent gives null | 35 | 5.4-T03, 5.4-T04, 5.4-T05 | BE | SCH-06
5.4-T07 | qr-service | 5.4 | 5. Transaction Processing (MPM/CPM) | QR parsing (EMVCo) & merchant resolution | 1 | Implement ZeroPayQRParser — MAI slot extraction (merchant_id, qr_code_id) | WBS 5.4 — QR Parser. After mandatory tags pass, ZeroPayQRParser must locate the ZeroPay MAI (Merchant Account Information) slot. MAI uses tags 26-51 in the EMVCo top-level TLV. ZeroPay occupies one registered tag in this range (Assumption A-05 in SCH-06: exact tag TBD; treat as configurable — load from scheme config key zeropay.mai_tag, default 26). Within the MAI template, sub-tag 01 = merchant_id (CHAR up to 10), sub-tag 02 = qr_code_id (CHAR up to 20), sub-tag 00 = reverse domain name (informational). Missing MAI tag throws QR_UNKNOWN_SCHEME. Missing sub-tag 01 or 02 throws QR_MALFORMED. Store resolved maiTag (int) and both IDs on ParsedQRPayload. | • Inject schemeConfig to read zeropay.mai_tag (integer, default 26) • After parseTopLevel, scan tags 26-51 for the configured MAI tag; if absent try all tags 26-51 and match by GUID prefix if scheme config includes a known reverse domain (optional fallback) • Call EMVCoTlvParser.parseTemplate(maiValue) to get sub-tags • Extract sub-tag 01 as merchantId; sub-tag 02 as qrCodeId • Throw QRUnknownSchemeException if no MAI slot found; throw QRMalformedException if sub-tag 01 or 02 missing • Complete ParsedQRPayload with maiTag, merchantId, qrCodeId | Updated ZeroPayQRParser.java with full MAI extraction completing ParsedQRPayload | • MAI at tag 26 with sub-tag 01='M123456789' and sub-tag 02='QR00000000000000000001' populates ParsedQRPayload.merchantId and qrCodeId correctly • Missing MAI entirely (no tags 26-51 in payload) throws QRUnknownSchemeException with errorCode QR_UNKNOWN_SCHEME • MAI present but missing sub-tag 02 throws QRMalformedException • Configuration zeropay.mai_tag=29 causes parser to look at tag 29 instead of 26 • merchantId is trimmed of whitespace before returning | 35 | 5.4-T06 | BE | SCH-06
5.4-T08 | qr-service | 5.4 | 5. Transaction Processing (MPM/CPM) | QR parsing (EMVCo) & merchant resolution | 1 | Implement QRParserServiceImpl.resolveIdentifier — merchant DB lookup | WBS 5.4 — QR Parser. After parsing, resolveIdentifier(ParsedQRPayload) queries the local merchants table (see DAT-03 §7.4): SELECT * FROM merchant WHERE merchant_id = :merchantId. Merchant table columns: merchant_id VARCHAR(50), status VARCHAR(20) (ACTIVE/SUSPENDED/DEACTIVATED), is_active BOOLEAN, merchant_type VARCHAR(30), fee_tier VARCHAR(20). Resolution rules (SCH-06 §3.5): (1) merchant_id must exist — else MERCHANT_NOT_FOUND. (2) status must be ACTIVE and is_active=true — else MERCHANT_INACTIVE. (3) Next ticket handles QR validation. Returns partial MerchantIdentifier (without qrCodeId confirmed yet). | • Inject MerchantRepository (Spring Data JPA) into QRParserServiceImpl • In resolveIdentifier(), query merchantRepository.findByMerchantId(parsed.getMerchantId()) • Throw MerchantNotFoundException(MERCHANT_NOT_FOUND) if Optional is empty • Throw MerchantInactiveException(MERCHANT_INACTIVE) if status != ACTIVE or is_active = false • Build partial MerchantIdentifier with merchantId, merchantType, feeTier, merchantName from DB row • Continue to QR resolution (T09) before returning | Merchant lookup logic in QRParserServiceImpl.resolveIdentifier(), with MerchantRepository dependency | • merchant_id 'UNKNOWN123' not in DB throws MerchantNotFoundException • merchant with status=SUSPENDED throws MerchantInactiveException • merchant with status=ACTIVE and is_active=false throws MerchantInactiveException • merchant with status=ACTIVE and is_active=true proceeds without exception • Returned partial MerchantIdentifier has merchantType and feeTier from merchant row | 30 | 5.4-T03, 5.4-T02 | BE | SCH-06
5.4-T09 | qr-service | 5.4 | 5. Transaction Processing (MPM/CPM) | QR parsing (EMVCo) & merchant resolution | 1 | Implement QRParserServiceImpl.resolveIdentifier — QR code DB lookup and cross-check | WBS 5.4 — QR Parser. After merchant lookup passes, validate the QR code (SCH-06 §3.5 steps 3-5). Query qr_code table (DAT-03 §7.5): columns qr_code_id CHAR(20), merchant_id BIGINT FK, status VARCHAR(20) (ACTIVE/DEACTIVATED), is_active BOOLEAN. Rules: (1) qr_code_id must exist — QR_NOT_FOUND. (2) status must be ACTIVE — QR_DEACTIVATED. (3) qr_code.merchant_id (FK to merchant.id) must match the merchant resolved in T08 — QR_MERCHANT_MISMATCH (prevents one merchant spoofing another's QR). On success, complete MerchantIdentifier adding qrCodeId. | • Inject QRCodeRepository into QRParserServiceImpl • Look up qrCodeRepository.findByQrCodeId(parsed.getQrCodeId()) • Throw QRParseException(QR_NOT_FOUND) if absent • Throw QRDeactivatedException(QR_DEACTIVATED) if status != ACTIVE or is_active=false • Compare qrCode.getMerchantFk() with resolved merchant.getId(); if mismatch throw QRMerchantMismatchException(QR_MERCHANT_MISMATCH) • Set qrCodeId on MerchantIdentifier and return completed object | QR code lookup and cross-check logic in QRParserServiceImpl.resolveIdentifier() | • qr_code_id 'NOQR' absent from DB throws exception with code QR_NOT_FOUND • Active qr_code referencing merchant_id=99 but parsed payload has merchant_id resolving to merchant.id=42 throws QR_MERCHANT_MISMATCH • Deactivated qr_code (status=DEACTIVATED) throws QR_DEACTIVATED even if merchant is active • Happy path: active merchant + active QR with matching FK returns completed MerchantIdentifier with qrCodeId populated • resolveIdentifier is a single transactional method — merchant lookup and QR lookup both use the same DB transaction (@Transactional(readOnly=true)) | 30 | 5.4-T08 | BE | SCH-06
5.4-T10 | qr-service | 5.4 | 5. Transaction Processing (MPM/CPM) | QR parsing (EMVCo) & merchant resolution | 1 | Add DB indexes on merchant.merchant_id and qr_code.qr_code_id for payment-critical path | WBS 5.4 — QR Parser. AD-12 (SAD-02) mandates local DB lookups on the payment critical path with sub-second latency. The merchants table and qr_code table are queried on every MPM payment. Currently merchant_id is VARCHAR(50) UNIQUE (index exists by PK uniqueness) and qr_code.qr_code_id is VARCHAR(512) UNIQUE (from DAT-03). Verify both UNIQUE constraints translate to indexes; additionally add a composite index on qr_code(merchant_id, status) to support validation queries that filter both. Write as a Flyway migration file. | • Create migration V5_4__qr_parser_indexes.sql in src/main/resources/db/migration • Add: CREATE INDEX IF NOT EXISTS idx_merchant_merchant_id ON merchant(merchant_id); (belt-and-suspenders if UNIQUE already present) • Add: CREATE INDEX IF NOT EXISTS idx_qr_code_qr_code_id ON qr_code(qr_code_id); • Add: CREATE INDEX IF NOT EXISTS idx_qr_code_merchant_status ON qr_code(merchant_id, status); • Add comment block explaining purpose: payment-time merchant resolution, SCH-06 AD-12 • Verify migration applies cleanly with Flyway validate | V5_4__qr_parser_indexes.sql Flyway migration | • \d merchant in psql shows index on merchant_id column after migration • \d qr_code shows index on qr_code_id and composite index on (merchant_id, status) • EXPLAIN ANALYZE on SELECT * FROM merchant WHERE merchant_id='M123' shows Index Scan, not Seq Scan on a table with 100k rows • Migration is idempotent (IF NOT EXISTS) — running twice does not error • Migration file version V5_4 does not conflict with existing migration versions | 25 |  | BE | SCH-06
5.4-T11 | qr-service | 5.4 | 5. Transaction Processing (MPM/CPM) | QR parsing (EMVCo) & merchant resolution | 1 | Implement CPM payload handling — pass-through and token structure | WBS 5.4 — QR Parser. In CPM mode the customer shows a dynamic QR generated by ZeroPay via GMEPay+ (SCH-06 §3.3). The CPM QR contains a one-time payment token issued by ZeroPay, not a merchant identity. Therefore parseMerchantQR is NOT called for inbound CPM payloads — the ZeroPay Adapter handles CPM token relay. However, the parser module must expose a method parseCpmToken(String rawPayload) -> CpmTokenPayload that extracts the opaque token string. CpmTokenPayload{token:String, schemeId:String, issuedAt:Instant, expiresAt:Instant (token TTL default 60s per SCH-06 §3.3)}. If the payload cannot be decoded, throw QRMalformedException. CPM token payloads use EMVCo TLV; the token is in a scheme-specific tag. | • Create CpmTokenPayload record with fields: token, schemeId, issuedAt, expiresAt • Add parseCpmToken(String rawPayload, String schemeId) method to QRParserService interface • Implement in ZeroPayQRParser as parseCpmPayload(String rawPayload): extract token from ZeroPay CPM-specific MAI slot (treat as configurable tag, default 26); compute expiresAt = issuedAt + 60s • Add isExpired() convenience method to CpmTokenPayload • Throw QRMalformedException if token field is blank or missing | CpmTokenPayload.java and parseCpmToken implementation in ZeroPayQRParser | • Valid CPM payload returns CpmTokenPayload with non-blank token • isExpired() returns false for freshly issued token (issuedAt = now) • isExpired() returns true for token with expiresAt 61 seconds in the past • Missing token sub-tag throws QRMalformedException with code QR_MALFORMED • CPM parsing does not touch merchant or qr_code DB tables | 30 | 5.4-T07 | BE | SCH-06
5.4-T12 | qr-service | 5.4 | 5. Transaction Processing (MPM/CPM) | QR parsing (EMVCo) & merchant resolution | 1 | Implement QRParserServiceImpl.parse() end-to-end for MPM mode | WBS 5.4 — QR Parser. Wire full MPM parse path: QRParserServiceImpl.parse(rawPayload, schemeId) must (1) route to matching SchemeQRParser, (2) call parser.parse(rawPayload) getting ParsedQRPayload, (3) verify parsedPayload.crcVerified=true (belt-and-suspenders guard), (4) return the ParsedQRPayload. The resolveIdentifier() step is a separate call made by the Orchestrator after parse(). QRParserService is a @Service singleton. Ensure thread safety (no mutable state). Add MDC logging: log schemeId, outcome (SUCCESS/FAIL), errorCode on failure at INFO level. Do not log rawPayload (may contain PII). | • Complete QRParserServiceImpl.parse() to call the correct SchemeQRParser via supports() matching • Add guard: if returned parsedPayload.crcVerified==false throw QRInvalidChecksumException (defensive; parser should have already checked) • Wrap parse call in try/catch QRParseException; log at WARN with MDC fields schemeId and errorCode before re-throwing • Log successful parse at DEBUG with schemeId and merchantId (no raw payload) • Annotate class @Slf4j; use MDC.put/remove in try-finally | Completed QRParserServiceImpl.parse() method with logging, no mutable state | • parse(validMpmPayload, ZEROPAY) returns ParsedQRPayload with all mandatory fields populated • parse(validPayload, KHQR) throws QRUnknownSchemeException (no KHQR parser registered) • QRParseException is re-thrown with original errorCode intact after logging • No rawPayload string appears in any log output (verified by log capture in test) • Calling parse() concurrently from 10 threads returns correct results with no race condition (parsers are stateless) | 30 | 5.4-T06, 5.4-T07, 5.4-T03 | BE | SCH-06
5.4-T13 | qr-service | 5.4 | 5. Transaction Processing (MPM/CPM) | QR parsing (EMVCo) & merchant resolution | 1 | Unit tests — EMVCo TLV tokenizer edge cases | WBS 5.4 — QR Parser. EMVCoTlvParser (T04) needs a comprehensive test class covering the edge-case vectors that would corrupt merchant resolution if unhandled. Test file: EMVCoTlvParserTest.java. Use JUnit 5 + AssertJ. No Spring context needed — pure unit tests. | • Create EMVCoTlvParserTest.java in src/test matching package • Test 1: normal two-tag string '0002015204AB' -> {0:'01', 52:'AB'} • Test 2: declared length 99 but only 3 chars remain -> QRMalformedException • Test 3: null input -> QRMalformedException • Test 4: empty string -> QRMalformedException • Test 5: nested template parse of '01' + length + 'M123456789' + '02' + length + 'QR001' returns correct sub-tags • Test 6: duplicate top-level tag -> QRMalformedException • Test 7: zero-length value ('520052' = tag 52, length 0, tag 52 again) -> tag 52 value is empty string (not an error) | EMVCoTlvParserTest.java with 7 test methods all passing | • All 7 tests pass (mvn test -pl qr-parser -Dtest=EMVCoTlvParserTest) • No Mockito or Spring context used — pure unit • Length-overflow test confirms exception type is QRMalformedException with errorCode QR_MALFORMED • Nested template test confirms parseTemplate('01' + len + value + ...) returns sub-tag map with key 1 | 35 | 5.4-T04 | BE | SCH-06
5.4-T14 | qr-service | 5.4 | 5. Transaction Processing (MPM/CPM) | QR parsing (EMVCo) & merchant resolution | 1 | Unit tests — CRC-16/CCITT checksum verifier | WBS 5.4 — QR Parser. EMVCoCrcVerifier (T05) must be tested with known vectors. EMVCo spec provides sample payloads with known CRC values. The polynomial is 0x1021, init 0xFFFF, no reflection. Test class: EMVCoCrcVerifierTest.java. Known test vector from EMVCo QR code spec appendix: payload string ending in '6304' then CRC. A widely cited sample: '00020101021153160004000205678900000000000005303156304' with CRC 'A60A' (to be verified against the spec; use this as the reference vector and confirm by running the algorithm). | • Create EMVCoCrcVerifierTest.java • Test 1: compute('00020101021153160004000205678900000000000005303156304') == 'A60A' (or correct value from EMVCo spec; developer must confirm against official spec vector) • Test 2: verify(payload + 'A60A') returns true for the above payload • Test 3: verify(payload + '0000') throws QRInvalidChecksumException • Test 4: payload without tag 63 throws QRMalformedException • Test 5: compute empty string -> returns 4-char uppercase hex string (exact value depends on algorithm; verify it equals CRC-16/CCITT of empty) • Test 6: single ASCII char 'A' (0x41) -> manually computed CRC-16/CCITT value (developer must compute and hardcode) | EMVCoCrcVerifierTest.java with 6 test methods all passing | • Test 1 CRC vector matches official EMVCo reference (developer must confirm against spec appendix) • verify() with tampered CRC throws QRInvalidChecksumException, not returns false • Tag 63 absent throws QRMalformedException not NullPointerException • All 6 tests pass with no external dependencies | 35 | 5.4-T05 | BE | SCH-06
5.4-T15 | qr-service | 5.4 | 5. Transaction Processing (MPM/CPM) | QR parsing (EMVCo) & merchant resolution | 1 | Unit tests — ZeroPayQRParser mandatory tag and currency validation | WBS 5.4 — QR Parser. ZeroPayQRParser (T06, T07) needs tests covering each rejection path. Build synthetic TLV payloads in tests using a helper that constructs valid TLV strings and computes correct CRC. Test class: ZeroPayQRParserTest.java. The parser is a Spring @Component but tests instantiate it directly with a mock SchemeConfigService. | • Create TlvBuilder test helper: addTag(int tag, String value).build() produces a valid TLV string with correct CRC appended • Test 1 (happy path): payload with tags 00=01, 52=5411, 53=410, 58=KR, 59=TestMerchant, 60=Seoul, MAI@26 with sub01=M123 sub02=QR001 -> ParsedQRPayload.merchantId='M123' • Test 2: tag53=840 -> QRCurrencyMismatchException • Test 3: tag00=02 -> QRMalformedException • Test 4: missing tag52 -> QRMalformedException • Test 5: MAI slot absent (no tag in 26-51 range) -> QRUnknownSchemeException • Test 6: MAI present but sub-tag01 missing -> QRMalformedException • Test 7: bad CRC -> QRInvalidChecksumException raised before any other check | ZeroPayQRParserTest.java with TlvBuilder helper and 7 test methods all passing | • TlvBuilder produces parseable payloads that pass CRC verification in Test 1 • Test 7 (bad CRC) fails before tag validation — confirmed by adding a mock spy that would throw on tag parsing; it is never called • Test 2 exception has errorCode QR_CURRENCY_MISMATCH • Test 5 exception has errorCode QR_UNKNOWN_SCHEME • All 7 tests pass with no Spring context (direct instantiation) | 45 | 5.4-T06, 5.4-T07 | BE | SCH-06
5.4-T16 | qr-service | 5.4 | 5. Transaction Processing (MPM/CPM) | QR parsing (EMVCo) & merchant resolution | 1 | Unit tests — resolveIdentifier merchant and QR happy path + failure paths | WBS 5.4 — QR Parser. QRParserServiceImpl.resolveIdentifier() (T08, T09) must be tested with mocked repositories. No DB needed. Test class: QRParserServiceImplResolutionTest.java. Use Mockito to stub MerchantRepository and QRCodeRepository. Build a standard ParsedQRPayload fixture: merchantId='M123456789', qrCodeId='QR00000000000000000001'. Build a Merchant entity fixture: id=42, merchant_id='M123456789', status=ACTIVE, is_active=true, merchant_type=GENERAL, fee_tier=DOMESTIC. Build a QRCode entity fixture: id=7, merchant_id=42, qr_code_id='QR00000000000000000001', status=ACTIVE, is_active=true. | • Create QRParserServiceImplResolutionTest.java with @ExtendWith(MockitoExtension.class) • Test 1 (happy path): stubs return merchant+qr fixtures -> MerchantIdentifier.merchantId='M123456789', qrCodeId='QR00000000000000000001', feeTier=DOMESTIC • Test 2: merchantRepository returns empty -> MerchantNotFoundException with errorCode MERCHANT_NOT_FOUND • Test 3: merchant status=SUSPENDED -> MerchantInactiveException with MERCHANT_INACTIVE • Test 4: merchant active, qrCode absent -> QR_NOT_FOUND • Test 5: qrCode status=DEACTIVATED -> QR_DEACTIVATED • Test 6: qrCode.merchantFk=99 but merchant.id=42 -> QR_MERCHANT_MISMATCH | QRParserServiceImplResolutionTest.java with 6 test methods all passing | • Test 1 MerchantIdentifier has feeTier=DOMESTIC and qrCodeId='QR00000000000000000001' • Test 6 exception has errorCode QR_MERCHANT_MISMATCH confirming cross-check logic • No real DB calls — only Mockito stubs • All 6 tests pass and QRCodeRepository.findByQrCodeId is never called when merchant lookup fails in Test 2 (short-circuit) | 35 | 5.4-T08, 5.4-T09 | BE | SCH-06
5.4-T17 | qr-service | 5.4 | 5. Transaction Processing (MPM/CPM) | QR parsing (EMVCo) & merchant resolution | 1 | Integration test — full MPM parse + resolve with H2 test DB | WBS 5.4 — QR Parser. An end-to-end Spring integration test verifies parse() + resolveIdentifier() work together against a real (H2 in-memory) database. Seed DB with: merchant row (merchant_id='M999', status=ACTIVE, is_active=true, merchant_type=GENERAL, fee_tier=DOMESTIC) and qr_code row (qr_code_id='QR999', merchant_id FK to above, status=ACTIVE, is_active=true). Use TlvBuilder from T15 to build a valid ZeroPay payload embedding merchantId='M999', qrCodeId='QR999'. Test class: QRParserIntegrationTest.java with @SpringBootTest(classes={...}) slicing. | • Create QRParserIntegrationTest annotated @SpringBootTest and @Transactional • Seed merchant and qr_code rows in @BeforeEach via repositories • Build valid payload with TlvBuilder: merchantId=M999, qrCodeId=QR999, tag53=410, all mandatory tags • Call qrParserService.parse(payload, ZEROPAY) -> verify ParsedQRPayload.merchantId=M999 • Call qrParserService.resolveIdentifier(parsed) -> verify MerchantIdentifier.qrCodeId='QR999' and feeTier='DOMESTIC' • Add negative test: change qr_code.status to DEACTIVATED in DB; call resolveIdentifier again -> QR_DEACTIVATED | QRParserIntegrationTest.java with happy path and deactivated-QR tests passing against H2 | • Happy path resolveIdentifier returns MerchantIdentifier with qrCodeId='QR999' • After deactivating QR in DB, resolveIdentifier throws exception with code QR_DEACTIVATED • CRC computation in TlvBuilder produces a payload that passes EMVCoCrcVerifier.verify() • Test runs in under 10 seconds (no external dependencies, H2 in-memory) | 40 | 5.4-T09, 5.4-T15, 5.4-T10 | BE | SCH-06
5.4-T18 | qr-service | 5.4 | 5. Transaction Processing (MPM/CPM) | QR parsing (EMVCo) & merchant resolution | 1 | Add Flyway migration for merchant and qr_code tables if not already created by earlier WBS | WBS 5.4 — QR Parser. The merchant and qr_code tables are defined in DAT-03 §7.4 and §7.5. If a prior WBS migration (e.g. WBS 1.x data model migrations) has not already created these tables, create them here. Check existing migration files first. Merchant columns: id BIGINT PK, merchant_id VARCHAR(50) UNIQUE NOT NULL, merchant_type VARCHAR(30), name VARCHAR(200), business_registration_no VARCHAR(30), franchise_code VARCHAR(30), category_code VARCHAR(20), bank_code VARCHAR(10), account_no VARCHAR(30), fee_tier VARCHAR(20), status VARCHAR(20) NOT NULL DEFAULT 'ACTIVE', is_active BOOLEAN NOT NULL DEFAULT TRUE, synced_at TIMESTAMPTZ, created_at TIMESTAMPTZ, updated_at TIMESTAMPTZ. QR code table per DAT-03 §7.5. | • Check existing Flyway migrations for CREATE TABLE merchant and CREATE TABLE qr_code • If absent, create V5_4_2__merchant_and_qr_code_tables.sql • Add merchant table DDL with all columns from context; add UNIQUE(merchant_id) • Add qr_code table DDL: id, merchant_id BIGINT FK REFERENCES merchant(id), qr_code_value VARCHAR(512) UNIQUE, qr_code_type VARCHAR(10), status VARCHAR(20) NOT NULL DEFAULT 'ACTIVE', is_active BOOLEAN NOT NULL DEFAULT TRUE, synced_at, created_at, updated_at • Add merchant_sync_log table per DAT-03 §7.6 if absent: id, file_type, sync_date, records_received/inserted/updated/deactivated, error_count, status, detail, created_at • Verify migration applies on clean DB | V5_4_2__merchant_and_qr_code_tables.sql (only if not already created by prior WBS migrations) | • After migration, psql \d merchant shows all columns including fee_tier and is_active • qr_code.merchant_id has FK constraint to merchant(id) • account_no column has no plaintext constraint — encryption is application-level per DAT-03 note • merchant_sync_log table exists with status VARCHAR(20) • Migration is idempotent only via Flyway versioning — duplicate version rejected, confirming it has a unique version number | 30 |  | BE | SCH-06
5.4-T19 | qr-service | 5.4 | 5. Transaction Processing (MPM/CPM) | QR parsing (EMVCo) & merchant resolution | 1 | Expose QRParserService via internal REST endpoint for Orchestrator | WBS 5.4 — QR Parser. The Transaction Orchestrator calls QRParserService internally (same JVM), but for testability and potential microservice extraction, expose a REST endpoint POST /internal/v1/qr/parse accepting {rawPayload:String, schemeId:String} returning ParsedQRPayload JSON, and POST /internal/v1/qr/resolve accepting ParsedQRPayload JSON returning MerchantIdentifier JSON. These are internal-only endpoints (not on the Northbound API). Secure with internal API key header X-Internal-Token (value from application config internal.api.token). Return 422 with {errorCode, message} on any QRParseException. | • Create QRParserController @RestController at path /internal/v1/qr • Implement POST /parse: deserialize request, call qrParserService.parse(), return 200 with ParsedQRPayload • Implement POST /resolve: deserialize ParsedQRPayload, call resolveIdentifier(), return 200 with MerchantIdentifier • Add @PreAuthorize or filter checking X-Internal-Token header against internal.api.token config value • Add @ExceptionHandler(QRParseException.class) returning 422 {errorCode: ex.getErrorCode().name(), message: ex.getMessage()} • Do not expose on the public API gateway (configure route exclusion) | QRParserController.java at /internal/v1/qr with parse and resolve endpoints | • POST /internal/v1/parse with valid ZeroPay payload and correct X-Internal-Token returns 200 with ParsedQRPayload JSON • POST /internal/v1/parse with wrong X-Internal-Token returns 401 • POST /internal/v1/parse with payload missing tag52 returns 422 with errorCode=QR_MALFORMED • POST /internal/v1/resolve with non-existent merchantId returns 422 with errorCode=MERCHANT_NOT_FOUND • rawPayload is never logged at INFO level (PII guard) | 40 | 5.4-T12, 5.4-T09 | BE | SCH-06
5.4-T20 | qr-service | 5.4 | 5. Transaction Processing (MPM/CPM) | QR parsing (EMVCo) & merchant resolution | 1 | Unit test — QRParserController error mapping and security filter | WBS 5.4 — QR Parser. Test QRParserController (T19) using @WebMvcTest slice. Mock QRParserService. Verify HTTP status codes and response body shapes for success and each error code. Also verify the X-Internal-Token filter blocks requests with wrong or missing token. | • Create QRParserControllerTest.java with @WebMvcTest(QRParserController.class) • Mock QRParserService via @MockBean • Test 1: valid token + parse throws QRMalformedException -> 422 body contains errorCode=QR_MALFORMED • Test 2: valid token + resolve returns MerchantIdentifier -> 200 with merchantId in JSON • Test 3: missing X-Internal-Token header -> 401 • Test 4: wrong token value -> 401 • Test 5: resolve throws MerchantInactiveException -> 422 with errorCode=MERCHANT_INACTIVE | QRParserControllerTest.java with 5 test methods all passing | • Test 1 response body JSON has field errorCode with value QR_MALFORMED • Test 3 and 4 both return HTTP 401 with no QRParserService invocation (verify with Mockito.verifyNoInteractions) • Test 2 response body has merchantId field • Test 5 status is 422 not 500 • All 5 tests pass without starting a real Spring application server | 30 | 5.4-T19 | BE | SCH-06
5.4-T21 | qr-service | 5.4 | 5. Transaction Processing (MPM/CPM) | QR parsing (EMVCo) & merchant resolution | 1 | Add merchant and QR resolution metrics (Micrometer counters) | WBS 5.4 — QR Parser. For operational visibility (NFR-10), instrument QRParserServiceImpl with Micrometer counters: qr.parse.total (tags: scheme, outcome=success¦failure), qr.parse.errors (tags: scheme, errorCode), qr.resolve.total (tags: outcome), qr.resolve.errors (tags: errorCode). Use MeterRegistry injected via constructor. Increment on every call. Record parse latency as qr.parse.duration Timer (tag: scheme). Do not record latency for failures after CRC (CRC failure is fast; only record when full parse attempted). | • Inject MeterRegistry into QRParserServiceImpl constructor • Add Counter qr.parse.total with tags scheme and outcome; increment in parse() on success and in catch block for failure • Add Counter qr.parse.errors with tags scheme and errorCode; increment only on QRParseException • Add Timer qr.parse.duration; record full parse latency via Timer.record() • Add Counter qr.resolve.total and qr.resolve.errors with tag errorCode • Wire in resolveIdentifier similarly | Micrometer instrumentation in QRParserServiceImpl with 4 metrics as described | • After calling parse() twice with success and once with QR_MALFORMED, counter qr.parse.total{outcome=success} = 2 and qr.parse.total{outcome=failure} = 1 • Counter qr.parse.errors{errorCode=QR_MALFORMED} = 1 • Timer qr.parse.duration has count >= 1 after a successful parse • Failed CRC parse (QRInvalidChecksumException) still increments qr.parse.total{outcome=failure} • MeterRegistry is a constructor parameter — no static global references | 30 | 5.4-T12 | BE | SCH-06
5.4-T22 | qr-service | 5.4 | 5. Transaction Processing (MPM/CPM) | QR parsing (EMVCo) & merchant resolution | 1 | Document QRParserService public contract in CLAUDE.md / developer README section | WBS 5.4 — QR Parser. The QR Parser is a standalone module. A developer adding a new scheme must know: (a) how to implement SchemeQRParser, (b) which error codes to throw, (c) what fields are mandatory on ParsedQRPayload. Write a concise section (max 1 page) in the module-level README or CLAUDE.md under heading 'QR Parser Module'. Include: interface method signatures, error code table with conditions, the EMVCo tag reference (tags 00, 52, 53, 58, 59, 60, 63, 26-51 MAI), and a 5-line example of how to register a new scheme parser. Do NOT duplicate spec text verbatim. | • Open (or create if absent) src/main/java/com/gmepayplus/qrparser/README.md • Write section: Overview (2 sentences), SchemeQRParser interface signature, Error codes table (code + trigger condition), EMVCo tag quick reference, New-scheme recipe (5 bullet steps) • Keep to <=60 lines • No spec text verbatim — summarise in own words • Commit alongside code | qrparser/README.md with QR Parser developer documentation section | • README contains SchemeQRParser interface signature (supports + parse methods) • Error codes table lists at minimum QR_INVALID_CHECKSUM, QR_MALFORMED, QR_UNKNOWN_SCHEME, QR_CURRENCY_MISMATCH • New-scheme recipe includes: implement SchemeQRParser, annotate @Component, configure mai_tag, register schemeId in scheme config • Document is <=60 lines • No sentences copied verbatim from spec_full.txt | 25 | 5.4-T03, 5.4-T07 | BE | SCH-06
5.5-T01 | payment-executor | 5.5 | 5. Transaction Processing (MPM/CPM) | CommitTransaction & payment.approved | 1 | Add rate-lock columns to transaction table migration | The transaction table (DAT-03 §5.2) must store all rate-engine values permanently at commit. Columns payout_usd_cost, collection_usd, collection_margin_usd, payout_margin_usd, send_amount, service_charge, collection_amount, offer_rate_coll, cross_rate, cost_rate_coll, cost_rate_pay, rate_locked_at, committed_at are set once at CommitTransaction and are NEVER subsequently updated. Types: DECIMAL(20,8) for USD-pool and rate fields; DECIMAL(20,4) for Settle-A amounts; TIMESTAMPTZ for timestamps. NULL allowed on USD-pool fields for same-currency short-circuit rows (is_same_ccy_shortcircuit=TRUE). Existing columns: id BIGINT PK, txn_ref VARCHAR(64) UNIQUE, status VARCHAR(20), partner_id, scheme_id, rule_id, rate_quote_id, merchant_id, payment_mode, direction, target_payout DECIMAL(20,4), payout_ccy CHAR(3), collection_ccy CHAR(3), settle_a_ccy CHAR(3), settle_b_ccy CHAR(3), is_same_ccy_shortcircuit BOOLEAN, prefunding_deducted_usd DECIMAL(20,4). | • Create Flyway/Liquibase migration file V5_5__add_rate_lock_columns.sql • Add columns: payout_usd_cost DECIMAL(20,8) NULL, collection_usd DECIMAL(20,8) NULL, collection_margin_usd DECIMAL(20,8) NULL, payout_margin_usd DECIMAL(20,8) NULL, send_amount DECIMAL(20,4) NOT NULL DEFAULT 0, service_charge DECIMAL(20,4) NOT NULL DEFAULT 0, collection_amount DECIMAL(20,4) NOT NULL DEFAULT 0, offer_rate_coll DECIMAL(20,8) NULL, cross_rate DECIMAL(20,8) NULL, cost_rate_coll DECIMAL(20,8) NULL, cost_rate_pay DECIMAL(20,8) NULL, rate_locked_at TIMESTAMPTZ NULL, committed_at TIMESTAMPTZ NULL • Add DB-level immutability: create trigger prevent_rate_lock_update that raises exception if any of those 13 columns are updated when rate_locked_at IS NOT NULL • Add composite indexes: (partner_id, committed_at), (scheme_id, completed_at), (status, committed_at) • Apply migration against dev PostgreSQL on port 5433; verify schema with \d transaction | Migration file V5_5__add_rate_lock_columns.sql and DB trigger prevent_rate_lock_update applied to dev PostgreSQL | • All 13 rate-lock columns present with correct types and nullability as specified • INSERT with rate_locked_at NULL succeeds; subsequent UPDATE to non-rate-lock columns also succeeds • Attempt to UPDATE collection_usd after rate_locked_at IS NOT NULL raises exception (trigger fires) • is_same_ccy_shortcircuit=TRUE rows allow NULL in payout_usd_cost and collection_usd without constraint error • Composite indexes (partner_id, committed_at) and (status, committed_at) visible in pg_indexes | 40 |  | BE | API-05, RATE-04
5.5-T02 | payment-executor | 5.5 | 5. Transaction Processing (MPM/CPM) | CommitTransaction & payment.approved | 1 | Define CommitRequest and CommitResult domain types | CommitTransaction is the central entry point for finalizing a payment. It accepts a quote reference and partner-supplied fields, performs validation, rate-lock, prefunding deduction (OVERSEAS), scheme call, and status update. Define the input/output value objects that flow through the orchestration boundary. Fields in CommitRequest: quote_id (String), merchant_qr (String), direction (enum: INBOUND/OUTBOUND/DOMESTIC/HUB), scheme_id (String), customer_ref (String), partner_txn_ref (String), collection_amount (BigDecimal), collection_currency (String), country_code (String nullable), idempotency_key (String). Fields in CommitResult: payment_id (String), status (PaymentStatus), scheme_txn_id (String), merchant_name (String), merchant_id (String), target_payout (BigDecimal), payout_currency (String), offer_rate (BigDecimal), collection_amount (BigDecimal), collection_currency (String), service_charge (BigDecimal), service_charge_currency (String), prefund_deducted_usd (BigDecimal nullable), partner_txn_ref (String), created_at (Instant), approved_at (Instant nullable). PaymentStatus enum values: APPROVED, PENDING, FAILED, UNCERTAIN. | • Create CommitRequest record/POJO with all listed fields and validation annotations (NotNull, NotBlank where required) • Create CommitResult record/POJO with all listed response fields • Create PaymentStatus enum with values APPROVED, PENDING, FAILED, UNCERTAIN, CANCELLED, REVERSED, REFUNDED • Create CommitTransactionException hierarchy: QuoteExpiredException, QuoteNotFoundException, InsufficientPrefundingException, MerchantNotFoundException, SchemeUnavailableException, PartnerBQuoteDeviationException, PartnerBQuoteUnavailableException, PoolIdentityFailureException • Add unit test verifying CommitRequest rejects null quote_id and null partner_txn_ref | CommitRequest, CommitResult, PaymentStatus enum, and CommitTransactionException hierarchy in domain package | • CommitRequest with null quote_id throws ConstraintViolationException or equivalent on validation • CommitResult with all fields populated serializes to JSON with correct field names matching API-05 spec (payment_id, offer_rate, prefund_deducted_usd, etc.) • PaymentStatus.APPROVED.name() == 'APPROVED'; all 7 values present • QuoteExpiredException is a subtype of CommitTransactionException • Unit test passes with a valid CommitRequest instance built with all required fields | 35 | 5.5-T01 | BE | API-05, RATE-04
5.5-T03 | payment-executor | 5.5 | 5. Transaction Processing (MPM/CPM) | CommitTransaction & payment.approved | 1 | Define RateQuote domain model and Redis cache interface | At quote time (GET /v1/rates), the rate engine computes all 5-step USD pool values and stores them in Redis with key rate_quote:{quote_id}, TTL = partner.rate_quote_ttl_seconds (default 300s; 60s for aggregator-bound). At CommitTransaction, the orchestrator loads this quote from Redis to verify TTL and extract all pool values for rate-lock. The RateQuote object must carry: quote_id (String), partner_id (Long), scheme_id (String), direction (String), target_payout (BigDecimal), payout_ccy (String), settle_a_ccy (String), settle_b_ccy (String), is_same_ccy_shortcircuit (Boolean), payout_usd_cost (BigDecimal nullable), collection_usd (BigDecimal nullable), collection_margin_usd (BigDecimal nullable), payout_margin_usd (BigDecimal nullable), send_amount (BigDecimal), service_charge (BigDecimal), collection_amount (BigDecimal), offer_rate_coll (BigDecimal), cross_rate (BigDecimal), cost_rate_coll (BigDecimal), cost_rate_pay (BigDecimal), cost_rate_pay_source (enum: IDENTITY/LIVE/MANUAL/PARTNER), quote_issued_at (Instant), valid_until (Instant), is_used (Boolean). | • Create RateQuote record with all listed fields • Create RateQuoteRepository interface with methods: save(RateQuote, long ttlSeconds), findById(String quoteId): Optional<RateQuote>, markUsed(String quoteId) • Create RedisRateQuoteRepository implementing RateQuoteRepository using Redis SETEX with key rate_quote:{quoteId} and JSON serialization • Write unit test: save a RateQuote, retrieve it, verify all BigDecimal fields match to 8 decimal places • Write unit test: markUsed flips is_used=true; subsequent findById returns updated object | RateQuote domain class, RateQuoteRepository interface, RedisRateQuoteRepository implementation, and unit tests | • RateQuote with is_same_ccy_shortcircuit=true can be stored and retrieved with payout_usd_cost=null • TTL is set correctly: a quote saved with ttlSeconds=60 is absent from Redis after 61 seconds (verified with integration test or mock) • findById returns Optional.empty() for a non-existent key • markUsed idempotent: calling twice does not throw • BigDecimal fields round-trip through JSON without precision loss (10-digit values preserved) | 45 | 5.5-T02 | BE | API-05, RATE-04
5.5-T04 | payment-executor | 5.5 | 5. Transaction Processing (MPM/CPM) | CommitTransaction & payment.approved | 1 | Implement CommitTransaction quote validation step | The first step in CommitTransaction is to load the rate quote from Redis and validate it. Rules: (1) quote_id must exist in Redis (rate_quote:{quote_id}) - error RATE_QUOTE_INVALID if absent; (2) quote.partner_id must match the authenticated partner - error FORBIDDEN; (3) now_utc() must be <= quote.valid_until - error RATE_QUOTE_EXPIRED; (4) quote.is_used must be false - error RATE_QUOTE_INVALID (already committed); (5) quote.direction and quote.scheme_id must match the CommitRequest fields - error VALIDATION_ERROR. The method signature is: RateQuote loadAndValidateQuote(String quoteId, Long partnerId, String direction, String schemeId, Instant now). This is a pure validation step - it does NOT mark the quote as used yet (that happens atomically at rate-lock). | • Create QuoteValidationService with method loadAndValidateQuote • Implement Redis fetch via RateQuoteRepository.findById; throw QuoteNotFoundException if absent • Check partner_id match; throw ForbiddenException if mismatch • Check valid_until >= now; throw QuoteExpiredException with quote.valid_until in message • Check is_used == false; throw QuoteAlreadyUsedException (subtype of QuoteNotFoundException) if true • Check direction and scheme_id match commit request; throw ValidationException with field detail if mismatch | QuoteValidationService.loadAndValidateQuote with all 5 validation rules | • Non-existent quote_id throws QuoteNotFoundException • Quote with valid_until = now-1s throws QuoteExpiredException; valid_until = now+1s passes • Quote owned by partner_id=1 accessed by partner_id=2 throws ForbiddenException • Quote with is_used=true throws QuoteAlreadyUsedException • Direction mismatch (commit says 'domestic', quote says 'inbound') throws ValidationException with field='direction' | 35 | 5.5-T03 | BE | API-05, RATE-04
5.5-T05 | payment-executor | 5.5 | 5. Transaction Processing (MPM/CPM) | CommitTransaction & payment.approved | 1 | Implement Partner B quote deviation check at commit time | When a rule's cost_rate_pay_source == PARTNER, GMEPay+ calls Partner B's quote API again at commit time and checks deviation. Formula: deviation = ¦commit_quote - rates_quote¦ / rates_quote. If deviation > partner.partner_b_deviation_tolerance (default 0.01 = 1%, per-partner configurable), reject with PARTNER_B_QUOTE_DEVIATION. If the Partner B API is unreachable at commit time, reject with PARTNER_B_QUOTE_UNAVAILABLE. If cost_rate_pay_source != PARTNER, skip this check entirely. The deviation tolerance is stored on the partner record as partner_b_deviation_tolerance DECIMAL(6,4). Example: rates_quote cost_rate_pay=1380.00, commit_quote=1393.80. deviation=¦1393.80-1380.00¦/1380.00=0.01=1.0%. At tolerance=0.01 this is exactly at the boundary - implement as: deviation > tolerance (strict greater), so 1.0% at tolerance 1.0% PASSES. At 1.01% it FAILS. | • Create PartnerBQuoteDeviationChecker with method checkDeviation(RateQuote storedQuote, BigDecimal partnerBCommitQuote, BigDecimal tolerance) • Implement deviation = abs(commitQuote - storedQuote.cost_rate_pay) / storedQuote.cost_rate_pay using BigDecimal arithmetic • Throw PartnerBQuoteDeviationException if deviation.compareTo(tolerance) > 0 (strict greater) • Create PartnerBQuoteClient interface with method fetchCurrentQuote(String schemeId, BigDecimal payoutAmount): BigDecimal - throw PartnerBQuoteUnavailableException if unreachable • Wire into commit flow: if cost_rate_pay_source == PARTNER, call client then checker; if source != PARTNER, skip • Write unit tests with exact numeric examples from context | PartnerBQuoteDeviationChecker, PartnerBQuoteClient interface, and unit tests | • rates_quote=1380.00, commit=1393.80, tolerance=0.01: deviation=0.01000 which is NOT > 0.01, so no exception (boundary pass) • rates_quote=1380.00, commit=1394.58, tolerance=0.01: deviation=0.010565 > 0.01, throws PartnerBQuoteDeviationException • PartnerBQuoteClient throwing IOException causes PartnerBQuoteUnavailableException to propagate • cost_rate_pay_source=LIVE: checker is never called (skipped entirely) • cost_rate_pay_source=IDENTITY: checker is never called | 40 | 5.5-T04 | BE | API-05, RATE-04
5.5-T06 | payment-executor | 5.5 | 5. Transaction Processing (MPM/CPM) | CommitTransaction & payment.approved | 1 | Implement atomic prefunding deduction in CommitTransaction (OVERSEAS partners) | For OVERSEAS partners (partner.type == OVERSEAS), CommitTransaction must atomically deduct collection_usd from the partner's prefunding_account.balance using SELECT FOR UPDATE to prevent concurrent over-draws. The deduction amount is quote.collection_usd (the USD pool gross - NOT collection_amount which is in Settle-A ccy). Steps: (1) BEGIN transaction; (2) SELECT balance FROM prefunding_account WHERE partner_id=? FOR UPDATE; (3) if balance < collection_usd ROLLBACK and throw InsufficientPrefundingException; (4) UPDATE prefunding_account SET balance = balance - collection_usd WHERE partner_id=?; (5) INSERT INTO prefunding_ledger_entry (account_id, txn_ref, entry_type='DEBIT_PAYMENT', amount=collection_usd, balance_after=balance-collection_usd); (6) COMMIT. For LOCAL partners (partner.type == LOCAL), skip deduction entirely - no prefunding exists. The scheme must NEVER be called if deduction fails. | • Create PrefundingDeductionService with method deductForPayment(Long partnerId, String txnRef, BigDecimal collectionUsd): PrefundingDeductionResult • Implement SELECT FOR UPDATE on prefunding_account within a @Transactional method • Check balance >= collectionUsd; throw InsufficientPrefundingException with partner_id and required amount if insufficient • Perform UPDATE balance and INSERT ledger entry atomically • Return PrefundingDeductionResult{deductedUsd, balanceAfter} • Add bypass: if partner.type == LOCAL return PrefundingDeductionResult{deductedUsd=ZERO, balanceAfter=null} | PrefundingDeductionService.deductForPayment with atomic SELECT FOR UPDATE, ledger entry insert, and LOCAL partner bypass | • Concurrent calls with total demand exceeding balance: exactly one succeeds, others throw InsufficientPrefundingException (test with 2 threads, balance=100.00, each requesting 60.00) • After successful deduction of 36.97 USD from balance 500.00, prefunding_account.balance = 463.03 and prefunding_ledger_entry.balance_after = 463.03 • LOCAL partner call returns deductedUsd=0 and no ledger entry is created • InsufficientPrefundingException carries the shortfall amount (e.g. required=36.97, available=10.00) • deductForPayment is @Transactional: if the ledger INSERT fails, the balance UPDATE is rolled back | 50 | 5.5-T03 | BE | API-05, RATE-04
5.5-T07 | payment-executor | 5.5 | 5. Transaction Processing (MPM/CPM) | CommitTransaction & payment.approved | 1 | Implement rate-lock: write all pool values to transaction record | After prefunding deduction succeeds and scheme call succeeds (state transitions to APPROVED), the orchestrator writes all rate-engine values permanently to the transaction record. The exact columns and values to write are (from quote): payout_usd_cost, collection_usd, collection_margin_usd, payout_margin_usd, send_amount, service_charge, collection_amount, offer_rate_coll, cross_rate, cost_rate_coll, cost_rate_pay. Additionally: rate_locked_at = now_utc(), committed_at = now_utc(), status = 'APPROVED', scheme_ref = scheme approval code, completed_at = scheme response time. Rule: these columns must be written in a single UPDATE statement; no second UPDATE to these columns is ever permitted after rate_locked_at IS NOT NULL (enforced by DB trigger from T01). For same-currency short-circuit: payout_usd_cost=NULL, collection_usd=NULL, collection_margin_usd=0, payout_margin_usd=0, cost_rate_coll=1.0, cost_rate_pay=1.0. | • Create RateLockService with method lockRate(Long txnId, RateQuote quote, String schemeRef, Instant schemeApprovedAt) • Build UPDATE statement covering all 13 rate-lock columns plus rate_locked_at, committed_at, completed_at, status, scheme_ref in one call • Use BigDecimal for all monetary/rate values; never cast to double • Handle same-ccy short-circuit: set collection_usd=NULL, payout_usd_cost=NULL, collection_margin_usd=0, payout_margin_usd=0 when quote.is_same_ccy_shortcircuit=true • Verify the UPDATE affected exactly 1 row; throw OptimisticLockException if 0 rows (txn not found or already locked) • Write integration test: lock rates, then attempt a second lock on same txnId and confirm DB trigger blocks it | RateLockService.lockRate that writes all pool values atomically in one UPDATE | • After lockRate, SELECT from transaction confirms rate_locked_at IS NOT NULL and all 13 columns match quote values to 8 decimal places • Second call to lockRate on same txnId raises exception (DB trigger from T01 fires) • Same-ccy short-circuit row: collection_usd IS NULL, payout_usd_cost IS NULL, collection_margin_usd=0.00000000, offer_rate_coll=1.00000000 • rate_locked_at timestamp matches now_utc() within 1 second of test execution • status column = 'APPROVED' after lockRate | 40 | 5.5-T01, 5.5-T03 | BE | API-05, RATE-04
5.5-T08 | payment-executor | 5.5 | 5. Transaction Processing (MPM/CPM) | CommitTransaction & payment.approved | 1 | Implement TransactionOrchestrator.commitTransaction - MPM happy path | CommitTransaction for Fixed MPM (POST /v1/payments) orchestrates: (1) load+validate quote (T04); (2) Partner B deviation check if applicable (T05); (3) create transaction record in DB with status PENDING_DEBIT; (4) for OVERSEAS: deduct prefunding (T06), transition status to DEBITED; (5) call ZeroPay scheme adapter submitMpm(txnRef, merchantId, payoutAmount); (6) on scheme success: call RateLockService.lockRate (T07), transition status to APPROVED, mark quote as used; (7) dispatch payment.approved webhook async; (8) return CommitResult. Idempotency: if a transaction with matching (partner_id, idempotency_key) already exists and is APPROVED, return the stored CommitResult without re-processing. State transitions: QUOTED->PENDING_DEBIT->DEBITED->SCHEME_SENT->APPROVED. Correlation field txn_ref = idempotency_key. The scheme must never be called if step 4 fails. | • In TransactionOrchestrator, implement commitMpmTransaction(CommitRequest req, Long partnerId) method • Load and validate quote; create transaction row (status=QUOTED, all non-rate columns populated) • Check idempotency: if existing approved transaction found by (partner_id, idempotency_key), return stored CommitResult • For OVERSEAS: call deductForPayment; transition status QUOTED->PENDING_DEBIT->DEBITED; if deduction fails set FAILED and return error • Call schemeAdapter.submitMpm; transition status to SCHEME_SENT; on success call lockRate and set APPROVED • Call webhookDispatcher.enqueueApproved async (do not block on delivery) • Return CommitResult built from transaction record fields | TransactionOrchestrator.commitMpmTransaction orchestrating the full MPM happy path | • OVERSEAS partner with sufficient balance: status progresses QUOTED->PENDING_DEBIT->DEBITED->SCHEME_SENT->APPROVED in transaction_event trail • LOCAL partner: DEBITED state reached without prefunding_ledger_entry being created • Idempotent re-submission (same idempotency_key) returns same payment_id without double scheme call or double deduction • Scheme call is never made if prefunding deduction throws InsufficientPrefundingException • CommitResult.prefund_deducted_usd equals quote.collection_usd for OVERSEAS; null for LOCAL | 55 | 5.5-T04, 5.5-T05, 5.5-T06, 5.5-T07 | BE | API-05, RATE-04
5.5-T09 | payment-executor | 5.5 | 5. Transaction Processing (MPM/CPM) | CommitTransaction & payment.approved | 1 | Implement TransactionOrchestrator.commitTransaction - CPM confirm path | CPM CommitTransaction (POST /v1/payments/cpm/confirm) differs from MPM: prefunding was already deducted at QR-generate time (AD-07), so step 4 is skipped. The state machine entry point is DEBITED (not QUOTED). Steps: (1) load transaction by txn_ref; (2) validate status == DEBITED (reject if not); (3) load+validate rate quote linked to transaction (validate TTL still valid); (4) Partner B deviation check if applicable; (5) call schemeAdapter.confirmCpm(txnRef, prepareToken); (6) on scheme success: call RateLockService.lockRate, set status APPROVED; (7) dispatch payment.approved webhook async; (8) return CommitResult. The rate-lock values come from the quote that was computed when the CPM inbound notification arrived and stored on the transaction. Transition path: DEBITED->SCHEME_SENT->APPROVED. | • Add commitCpmTransaction(String txnRef, Long partnerId) to TransactionOrchestrator • Load transaction by txn_ref; validate status == DEBITED; validate partner ownership • Reload quote from Redis using transaction.rate_quote_id; validate TTL • Perform Partner B deviation check if cost_rate_pay_source == PARTNER • Call schemeAdapter.confirmCpm; on success call lockRate with scheme approval code • Dispatch payment.approved webhook async; transition status to APPROVED • Return CommitResult with all rate-lock values populated | TransactionOrchestrator.commitCpmTransaction for CPM confirm path | • Transaction in QUOTED state (not DEBITED) returns error - cannot commit CPM without prior pending_debit • After confirmCpm, rate_locked_at IS NOT NULL and all pool values match the CPM-time quote • payment.approved webhook enqueued after successful commitCpmTransaction • CommitResult.prefund_deducted_usd is populated (was deducted at generate time, echoed from transaction record) • Calling commitCpmTransaction twice with same txnRef: second call returns stored CommitResult (idempotent) | 50 | 5.5-T08 | BE | API-05, RATE-04
5.5-T10 | payment-executor | 5.5 | 5. Transaction Processing (MPM/CPM) | CommitTransaction & payment.approved | 1 | Implement quote expiry check and RATE_QUOTE_EXPIRED error path | If a partner calls POST /v1/payments after quote.valid_until has passed (now_utc() > quote.valid_until), CommitTransaction must reject the request before any prefunding deduction or scheme call. Error: HTTP 422, error_code=RATE_QUOTE_EXPIRED, message includes the quote_id and the expired valid_until timestamp. The partner must re-call POST /v1/rates to get a fresh quote. No transaction record should be created for expired-quote commits (fail fast before any side effects). TTL is per-partner: aggregator-bound=60s default, others=300s default, range 60-1800s. Example: quote_issued_at=09:31:00Z, ttl=300s, valid_until=09:36:00Z. Commit at 09:36:01Z fails. Commit at 09:36:00Z passes (boundary: valid_until is inclusive, i.e. now <= valid_until passes). | • In QuoteValidationService, ensure expiry check uses now.isAfter(quote.valid_until) (exclusive: at exactly valid_until it passes) • Map QuoteExpiredException to HTTP 422 with error_code=RATE_QUOTE_EXPIRED in the exception handler • Include quote.valid_until formatted as ISO-8601 UTC in error message • Verify no transaction row is inserted before expiry check (expiry is step 1 of validation) • Write unit test: commit at valid_until-1ms passes; commit at valid_until+1ms throws QuoteExpiredException • Write unit test: OVERSEAS partner - no prefunding_ledger_entry created when QuoteExpiredException thrown | Expiry guard in QuoteValidationService and HTTP 422 mapping with correct error payload | • commit at valid_until + 1 ms returns HTTP 422 with error.code=RATE_QUOTE_EXPIRED and error.details[0].field=quote_id • commit at exactly valid_until passes (boundary inclusive) • No transaction row created in DB when expiry check fails • No prefunding_ledger_entry created for expired-quote attempt • Error response includes the expired valid_until timestamp in ISO-8601 UTC format | 30 | 5.5-T04 | BE | API-05, RATE-04
5.5-T11 | payment-executor | 5.5 | 5. Transaction Processing (MPM/CPM) | CommitTransaction & payment.approved | 1 | Implement merchant validation at commit time | At CommitTransaction for MPM, the merchant_qr from the CommitRequest must be validated against GMEPay+'s local merchant DB (synced from ZeroPay via daily SFTP - AD-12). Validation rules: (1) QR code must exist in the qr_code table; (2) linked merchant must have status='active'; (3) merchant.scheme_id must match commit request scheme_id. Error: MERCHANT_NOT_FOUND (HTTP 404) if QR not found or merchant inactive; additionally if QR exists but merchant is inactive, HTTP 422 is acceptable per API-05. The validation must happen BEFORE prefunding deduction and scheme call. The merchant_id resolved here is stored on the transaction record. CPM commits use merchant_id already stored from the inbound notification (skip this validation). | • Create MerchantValidationService.validateMerchantForCommit(String merchantQr, String schemeId): MerchantInfo • Query qr_code table by qr_value; throw MerchantNotFoundException if absent • Check merchant.status == 'active'; throw MerchantInactiveException (HTTP 422) if not active • Check merchant.scheme_id matches schemeId; throw ValidationException if mismatch • Return MerchantInfo{merchantId, merchantName, schemeId} • Wire into commitMpmTransaction BEFORE deductForPayment call • Skip this step in commitCpmTransaction (merchant already resolved at CPM inbound notify) | MerchantValidationService.validateMerchantForCommit wired into MPM commit path | • Unknown QR code returns HTTP 404 with error_code=MERCHANT_NOT_FOUND before any prefunding deduction • Inactive merchant QR returns HTTP 422 before prefunding deduction • Scheme mismatch (QR belongs to zeropay, request says scheme_id=khqr) returns HTTP 422 VALIDATION_ERROR • Valid active merchant: MerchantInfo returned and merchant_id stored on transaction record • CPM commit path does not call validateMerchantForCommit | 35 | 5.5-T08 | BE | API-05, RATE-04
5.5-T12 | payment-executor | 5.5 | 5. Transaction Processing (MPM/CPM) | CommitTransaction & payment.approved | 1 | Implement direction and scheme_id consistency check at commit | The CommitRequest.direction and CommitRequest.scheme_id must match the values stored in the rate quote from POST /v1/rates. If a partner requests a quote for direction=inbound, scheme_id=zeropay, they must submit the commit with the same values. Mismatch returns HTTP 422 VALIDATION_ERROR. Additionally, the rule (partner x scheme x direction) must still be active at commit time (rules can be deactivated between quote and commit - use the rule_id stored in the quote, not the partner's current active rule). Check: rule.effective_to IS NULL OR rule.effective_to > now_utc(). If rule was deactivated, return HTTP 422 DIRECTION_NOT_ENABLED. These checks happen in QuoteValidationService after the quote is loaded. | • Add direction match check to QuoteValidationService: throw ValidationException(field=direction) if mismatch • Add scheme_id match check: throw ValidationException(field=scheme_id) if mismatch • Add rule active check: load rule by quote.rule_id; if effective_to IS NOT NULL AND effective_to <= now, throw DirectionNotEnabledException • Map DirectionNotEnabledException to HTTP 422 with error_code=DIRECTION_NOT_ENABLED • Write unit test: direction mismatch with committed rule returns VALIDATION_ERROR • Write unit test: rule deactivated after quote issued returns DIRECTION_NOT_ENABLED | Direction/scheme/rule-active validation in QuoteValidationService | • Quote direction=inbound, commit direction=domestic: HTTP 422 VALIDATION_ERROR with field=direction • Quote scheme_id=zeropay, commit scheme_id=khqr: HTTP 422 VALIDATION_ERROR with field=scheme_id • Rule.effective_to = now-1s: HTTP 422 DIRECTION_NOT_ENABLED • Rule.effective_to = null: passes (rule still active) • Rule.effective_to = now+1s: passes (not yet expired) | 30 | 5.5-T04 | BE | API-05, RATE-04
5.5-T13 | payment-executor | 5.5 | 5. Transaction Processing (MPM/CPM) | CommitTransaction & payment.approved | 1 | Implement SCHEME_SENT state and scheme timeout/UNCERTAIN handling | After prefunding deduction, the orchestrator transitions state to SCHEME_SENT and calls the scheme adapter. Three outcomes: (1) success - scheme returns approval code, proceed to rate-lock and APPROVED; (2) synchronous failure - scheme returns explicit reject, set status=FAILED; (3) timeout or no response within scheme SLA - set status=UNCERTAIN and flag for settlement reconciliation. UNCERTAIN rule: if scheme response not received within scheme.sla_timeout_ms (default 30000ms for ZeroPay), set UNCERTAIN. A deduction held (NOT reversed) while UNCERTAIN. Reversal only happens if reconciliation later confirms FAILED. The orchestrator must NOT block the API response indefinitely - return HTTP 202 with status=pending for UNCERTAIN cases. | • Transition status to SCHEME_SENT before calling scheme adapter; insert transaction_event step 3 (SCHEME_SUBMITTED) • Call schemeAdapter.submitMpm with configured timeout; catch TimeoutException and SocketException • On timeout: set status=UNCERTAIN, insert SCHEME_UNCERTAIN event, return CommitResult{status=UNCERTAIN} • On scheme explicit reject: set status=FAILED, insert SCHEME_DECLINED event, return error • On scheme success: proceed to lockRate; insert SCHEME_APPROVED event • Map UNCERTAIN to HTTP 202 in the API handler; FAILED to HTTP 422 SCHEME_UNAVAILABLE • Log txn_ref, partner_id, scheme_id as correlation fields on all paths | Scheme call with UNCERTAIN handling and HTTP 202 response in TransactionOrchestrator | • Scheme timeout returns HTTP 202 with status field='pending' (or 'uncertain') and payment_id present • Prefunding_account.balance NOT restored when status=UNCERTAIN (deduction held) • status=UNCERTAIN transaction appears in a query for unresolved uncertainties (for settlement engine) • Scheme explicit DECLINED: status=FAILED, prefunding deduction reversed for OVERSEAS partner • transaction_event trail contains step SCHEME_SUBMITTED before scheme call and SCHEME_APPROVED/SCHEME_DECLINED/UNCERTAIN after | 45 | 5.5-T08 | BE | API-05, RATE-04
5.5-T14 | payment-executor | 5.5 | 5. Transaction Processing (MPM/CPM) | CommitTransaction & payment.approved | 1 | Implement transaction_event 8-step audit trail writes in commit flow | Every transaction carries an 8-step event trail in the transaction_event table (columns: id BIGINT PK, txn_id FK, step INT 1-8, event_type VARCHAR(50), occurred_at TIMESTAMPTZ, duration_ms INT, detail JSONB). The 8 steps are: (1) RATE_QUOTE_ISSUED, (2) PREFUND_DEDUCTED, (3) SCHEME_SUBMITTED, (4) SCHEME_APPROVED or SCHEME_DECLINED, (5) TRANSACTION_COMMITTED, (6) SETTLEMENT_BATCHED, (7) WEBHOOK_QUEUED, (8) WEBHOOK_DELIVERED. Steps 1-5 are written in the commit flow. Step 1 is written at rate-quote time (not this WBS). Steps 2-5 are written here. duration_ms = milliseconds since the previous step's occurred_at. detail JSONB carries step-specific payload: step 2 = {deducted_usd, balance_after}; step 3 = {scheme_id, payout_amount}; step 4 = {scheme_txn_id, approval_code} or {failure_code}; step 5 = {rate_locked_at}. | • Create TransactionEventService with method writeEvent(Long txnId, int step, String eventType, JSONB detail) • Calculate duration_ms from previous event's occurred_at (query last event for txn_id before inserting) • Write step 2 event after successful prefunding deduction with detail={deducted_usd, balance_after} • Write step 3 event before scheme call with detail={scheme_id, payout_amount} • Write step 4 event after scheme response with event_type=SCHEME_APPROVED or SCHEME_DECLINED • Write step 5 event after rate-lock with detail={rate_locked_at} • Steps 6-8 are written by other services; do not write them here | TransactionEventService.writeEvent and step 2-5 writes integrated into commit flow | • After successful MPM commit, transaction_event has steps 2, 3, 4, 5 for that txnId in order • Step 2 detail JSON contains keys deducted_usd and balance_after with correct values • Step 4 event_type=SCHEME_APPROVED when scheme succeeds; SCHEME_DECLINED when scheme rejects • duration_ms for step 3 is >= 0 and < 60000 (sanity check for non-negative millisecond value) • LOCAL partner: step 2 is NOT written (no deduction occurred) | 40 | 5.5-T08, 5.5-T13 | BE | API-05, RATE-04
5.5-T15 | payment-executor | 5.5 | 5. Transaction Processing (MPM/CPM) | CommitTransaction & payment.approved | 1 | Implement idempotency enforcement for POST /v1/payments | All POST endpoints require an Idempotency-Key header (UUID, min 16 chars, max 128 chars). GMEPay+ stores (partner_id, idempotency_key, response_body_json, http_status) in Redis with 24h TTL. Scenarios: (1) same key + same body, request in-flight: return HTTP 409 with X-Idempotency-Status: in_flight; (2) same key + same body, completed: return stored response without re-processing; (3) same key + different body: return HTTP 422 IDEMPOTENCY_KEY_REUSE; (4) missing key on POST: HTTP 400 MISSING_IDEMPOTENCY_KEY. The idempotency check is the FIRST thing executed in the handler, before any business logic. Key format: idempotency:{partner_id}:{idempotency_key}. Store request body hash alongside response to detect body mismatch. | • Create IdempotencyService with methods: checkAndLock(partnerId, key, bodyHash), storeResult(partnerId, key, httpStatus, responseBody), release(partnerId, key) • Implement Redis SETNX for in-flight locking with 30s TTL (covers max request duration); if SETNX returns 0, check stored result • If stored result exists with different bodyHash, throw IdempotencyKeyReuseException • If stored result exists with same bodyHash, return StoredIdempotencyResult{httpStatus, responseBody} • On success: call storeResult with 24h TTL • Add filter/interceptor that enforces Idempotency-Key header on all POST endpoints | IdempotencyService with Redis-backed lock and result storage, wired to POST /v1/payments handler | • Missing Idempotency-Key header on POST /v1/payments returns HTTP 400 MISSING_IDEMPOTENCY_KEY • Same key + same body, second call returns stored HTTP 201 response without hitting scheme adapter • Same key + different body returns HTTP 422 IDEMPOTENCY_KEY_REUSE • Concurrent duplicate calls (two threads, same key): one returns the in-flight 409, the other completes normally • Stored idempotency result expires and key can be reused after 24h (verified with TTL inspection) | 50 | 5.5-T08 | BE | API-05, RATE-04
5.5-T16 | payment-executor | 5.5 | 5. Transaction Processing (MPM/CPM) | CommitTransaction & payment.approved | 1 | Build payment.approved webhook payload assembler | After CommitTransaction transitions to APPROVED, the orchestrator enqueues a payment.approved webhook to the partner's registered webhook_url. The payload follows the API-05 §6.5 schema: event envelope {event_id, event_type='payment.approved', created_at, partner_id, data:{...}}. The data object contains: payment_id, partner_txn_ref, scheme_txn_id, merchant_id, merchant_name, direction, scheme_id, target_payout, payout_currency, offer_rate (= offer_rate_coll from rate-lock), collection_amount (partner-supplied value echoed), collection_currency, service_charge, service_charge_currency (= settle_a_ccy), prefund_deducted_usd (OVERSEAS only; omit key for LOCAL), approved_at. offer_rate is the LOCKED offer_rate_coll (not re-computed). All monetary values are decimal strings in major units (e.g. '50000' KRW, '35.77' USD). event_id is a new globally-unique identifier (not payment_id). | • Create PaymentApprovedPayloadBuilder with method build(Transaction txn, String schemeApprovalCode): WebhookPayload • Map txn.offer_rate_coll -> data.offer_rate as decimal string • For OVERSEAS: include prefund_deducted_usd = txn.prefunding_deducted_usd as string; for LOCAL: omit field entirely • Format all Instant fields as ISO-8601 UTC millisecond precision (e.g. 2026-06-04T09:31:16.847Z) • Generate unique event_id with prefix 'evt_' + ULID or UUID • Write unit test asserting LOCAL partner payload has no prefund_deducted_usd key in JSON | PaymentApprovedPayloadBuilder producing spec-compliant JSON payload | • Serialized payload contains event_type='payment.approved' and all required data fields from API-05 §6.5 • offer_rate in payload matches txn.offer_rate_coll exactly (same 8-decimal value, formatted as decimal string) • LOCAL partner payload: JSON does not contain key prefund_deducted_usd • OVERSEAS partner payload: prefund_deducted_usd present and equals txn.prefunding_deducted_usd • approved_at matches txn.completed_at in ISO-8601 UTC format | 35 | 5.5-T07 | BE | API-05, RATE-04
5.5-T17 | payment-executor | 5.5 | 5. Transaction Processing (MPM/CPM) | CommitTransaction & payment.approved | 1 | Implement webhook dispatcher with HMAC signing and retry queue | Webhook delivery uses POST to partner.webhook_url with HMAC-SHA256 signing. Headers: X-GME-Webhook-Signature: sha256=<HMAC-SHA256(body, webhook_signing_secret)>, X-GME-Webhook-Timestamp: <ISO-8601 UTC>, X-GME-Event-ID: <event_id>. The signing secret (webhook_signing_secret) is distinct from the API secret and stored in Secrets Manager. Partner must return HTTP 2xx within 10 seconds; any other response or timeout is a delivery failure. Retry back-off: immediate, 30s, 2min, 10min, 30min, 1h, 1h, 1h, 1h, 1h (10 attempts total per API-05 §6.2). After 10 failures: mark event delivery_failed, alert GME Ops. Payment.approved dispatch from commit flow is ASYNC (does not block the API response). Step 7 = WEBHOOK_QUEUED event written when enqueued; Step 8 = WEBHOOK_DELIVERED when 2xx received. | • Create WebhookDispatcher with enqueueApproved(Long txnId, WebhookPayload payload) that pushes to async queue (Kafka topic or in-memory queue) • Create WebhookDeliveryWorker that consumes the queue: HMAC-sign body, POST to webhook_url, handle retries • Compute signature: sha256=HMAC-SHA256(rawJsonBody, partnerWebhookSigningSecret) • Implement retry with scheduled delays: immediate, 30s, 2min, 10min, 30min, 5x1h; after 10 failures mark delivery_failed • Write transaction_event step 7 (WEBHOOK_QUEUED) on enqueue; step 8 (WEBHOOK_DELIVERED) on 2xx • Alert GME Ops (log ERROR with partner_id and event_id) after final failed attempt | WebhookDispatcher with async delivery, HMAC signing, and 10-attempt retry | • HMAC-SHA256(body, secret) matches X-GME-Webhook-Signature header value (verified by computing expected signature in test) • Partner returning HTTP 500 triggers retry; partner returning HTTP 200 marks delivered on first success • After 10 failed attempts, webhook_event.delivery_status='delivery_failed' and Ops alert logged • Webhook dispatch does NOT block commitMpmTransaction return (async) • Step 7 (WEBHOOK_QUEUED) event written at enqueue time; Step 8 (WEBHOOK_DELIVERED) written after HTTP 200 received | 55 | 5.5-T16 | BE | API-05, RATE-04
5.5-T18 | payment-executor | 5.5 | 5. Transaction Processing (MPM/CPM) | CommitTransaction & payment.approved | 1 | Implement POST /v1/payments API endpoint handler | POST /v1/payments (API-05 §4.3) executes a Fixed MPM payment. The handler must: (1) authenticate partner via HMAC-SHA256 API key; (2) enforce Idempotency-Key header; (3) deserialize CommitRequest; (4) call orchestrator.commitMpmTransaction; (5) serialize CommitResult to response. HTTP status codes: 201 Created for APPROVED, 202 Accepted for PENDING/UNCERTAIN, 400 for validation errors, 402 for INSUFFICIENT_PREFUNDING, 404 for MERCHANT_NOT_FOUND, 409 for duplicate partner_txn_ref, 422 for RATE_QUOTE_EXPIRED/RATE_QUOTE_INVALID/PARTNER_B_QUOTE_DEVIATION/PARTNER_B_QUOTE_UNAVAILABLE/SCHEME_UNAVAILABLE, 429 for rate limit. Response includes X-Request-ID header with a fresh request ID. Required request fields: quote_id, merchant_qr, direction, scheme_id, customer_ref, partner_txn_ref, collection_amount, collection_currency. | • Create PaymentsController with POST /v1/payments handler • Add authentication filter (from WBS 4.x or reference existing); add idempotency filter • Validate all required request fields; return HTTP 400 with VALIDATION_ERROR and error.details per field on failure • Call orchestrator.commitMpmTransaction(req, authenticatedPartnerId) • Map CommitResult to HTTP 201 (APPROVED) or 202 (PENDING/UNCERTAIN) • Map all CommitTransactionException subtypes to correct HTTP status codes and error_code values per API-05 §8.2 • Add X-Request-ID response header generated per request | POST /v1/payments endpoint handler with correct HTTP status mapping and error model | • Valid request with sufficient prefunding returns HTTP 201 with payment_id and status='approved' • Missing quote_id field returns HTTP 400 with error.code=VALIDATION_ERROR and error.details[0].field='quote_id' • Expired quote returns HTTP 422 with error.code=RATE_QUOTE_EXPIRED • Insufficient prefunding returns HTTP 402 with error.code=INSUFFICIENT_PREFUNDING • Every response includes X-Request-ID header | 45 | 5.5-T08, 5.5-T11, 5.5-T15 | BE | API-05, RATE-04
5.5-T19 | payment-executor | 5.5 | 5. Transaction Processing (MPM/CPM) | CommitTransaction & payment.approved | 1 | Implement POST /v1/payments/cpm/confirm API endpoint handler | POST /v1/payments/cpm/confirm (implicitly derived from API-05 CPM flow §5.2) confirms a CPM payment after the partner receives payment.pending_debit and the customer approves. The request body contains txn_ref. The orchestrator.commitCpmTransaction is called. Response mirrors the MPM response structure (same CommitResult shape). HTTP 201 for APPROVED, 202 for UNCERTAIN, 422 for RATE_QUOTE_EXPIRED, 422 for transaction not in DEBITED state (PAYMENT_STATE_INVALID error). X-Request-ID header required. Authentication and Idempotency-Key required. Path is POST /v1/payments/cpm/confirm with body {txn_ref}. | • Add POST /v1/payments/cpm/confirm endpoint to PaymentsController • Validate txn_ref is present in request body; return 400 VALIDATION_ERROR if missing • Call orchestrator.commitCpmTransaction(txnRef, authenticatedPartnerId) • Map CommitResult to HTTP 201/202 same as MPM handler • Map invalid-state error to HTTP 422 with error_code=PAYMENT_STATE_INVALID • Add integration test: mock scheme returning approval; verify HTTP 201 and payment.approved webhook enqueued | POST /v1/payments/cpm/confirm endpoint handler | • Missing txn_ref returns HTTP 400 VALIDATION_ERROR • Transaction in QUOTED state (not DEBITED) returns HTTP 422 PAYMENT_STATE_INVALID • Successful CPM confirm returns HTTP 201 with status='approved' and rate-locked offer_rate • UNCERTAIN scheme timeout returns HTTP 202 • Response contains X-Request-ID header | 35 | 5.5-T09, 5.5-T18 | BE | API-05, RATE-04
5.5-T20 | payment-executor | 5.5 | 5. Transaction Processing (MPM/CPM) | CommitTransaction & payment.approved | 1 | Implement GET /v1/payments/{id} endpoint handler | GET /v1/payments/{id} (API-05 §4.5) returns the full payment record. The response is the same shape as the POST /v1/payments response plus updated_at and cancelled_at. The endpoint must enforce partner ownership: a partner can only retrieve payments they created (partner_id match). Status values in response: 'approved', 'pending', 'failed', 'cancelled', 'uncertain'. Rate-locked fields (offer_rate, service_charge, prefund_deducted_usd) are always returned from the locked transaction columns - never re-computed. HTTP 200 if found, 404 PAYMENT_NOT_FOUND if not found or partner mismatch. | • Add GET /v1/payments/{id} to PaymentsController • Load transaction by payment_id; throw PaymentNotFoundException if absent • Check transaction.partner_id == authenticatedPartnerId; throw PaymentNotFoundException (do not leak existence to other partners) • Map transaction entity to PaymentResponse DTO (same fields as CommitResult plus updated_at, cancelled_at) • Map status enum to API string values: APPROVED->'approved', UNCERTAIN->'uncertain', etc. • Return HTTP 200 with X-Request-ID header | GET /v1/payments/{id} endpoint returning full payment detail with ownership check | • Requesting payment owned by different partner returns HTTP 404 (not 403 - do not leak existence) • Approved payment response includes rate-locked offer_rate, service_charge, prefund_deducted_usd from DB columns • Status UNCERTAIN maps to string 'uncertain' in response • HTTP 200 with X-Request-ID header on success • All monetary fields are decimal strings in major units (e.g. '50000' not 50000000) | 30 | 5.5-T18 | BE | API-05, RATE-04
5.5-T21 | payment-executor | 5.5 | 5. Transaction Processing (MPM/CPM) | CommitTransaction & payment.approved | 1 | Implement duplicate partner_txn_ref guard | partner_txn_ref is a partner-supplied unique reference per transaction. The combination (partner_id, partner_txn_ref) must be unique. If a POST /v1/payments arrives with a partner_txn_ref already used by that partner (but with a different idempotency_key), return HTTP 409 with error_code=DUPLICATE_PARTNER_TXN_REF. This is distinct from idempotency: same idempotency_key=replay-safe response; different idempotency_key + same partner_txn_ref = business duplicate error. The transaction table must have a UNIQUE constraint on (partner_id, partner_txn_ref). The check happens when creating the transaction row, catching the unique constraint violation. | • Add UNIQUE INDEX idx_transaction_partner_txn_ref ON transaction(partner_id, partner_txn_ref) in a migration (V5_5_T21 or add to V5_5 migration) • In TransactionOrchestrator, catch DataIntegrityViolationException (unique constraint) on transaction INSERT • Re-query by partner_id + partner_txn_ref to check if it is the same idempotency_key: if yes, return idempotent response; if no, throw DuplicatePartnerTxnRefException • Map DuplicatePartnerTxnRefException to HTTP 409 with error_code=DUPLICATE_PARTNER_TXN_REF • Write unit test: same partner_txn_ref, different idempotency_key, different quote_id returns 409 • Write unit test: same partner_txn_ref AND same idempotency_key returns stored 201 response | UNIQUE constraint on (partner_id, partner_txn_ref) and HTTP 409 guard in orchestrator | • Two distinct payments from same partner with same partner_txn_ref returns HTTP 409 DUPLICATE_PARTNER_TXN_REF for second • Same partner_txn_ref + same idempotency_key (retry) returns HTTP 201 with stored response (not 409) • Different partners can use same partner_txn_ref without conflict • DB UNIQUE INDEX present on (partner_id, partner_txn_ref) in pg_indexes • DUPLICATE_PARTNER_TXN_REF error has HTTP status 409 (not 422) | 35 | 5.5-T15, 5.5-T08 | BE | API-05, RATE-04
5.5-T22 | payment-executor | 5.5 | 5. Transaction Processing (MPM/CPM) | CommitTransaction & payment.approved | 1 | Unit tests: rate-lock field values for cross-border inbound example | Canonical numeric test vector (RATE-04 §4.3): target_payout=50000 KRW, cost_rate_pay=1380.00 (treasury.usd_krw), cost_rate_coll=1.0 (IDENTITY: Settle A=USD), m_a=0.01, m_b=0.01, service_charge=0.36 USD. Expected: payout_usd_cost=36.2319 USD (50000/1380), collection_usd=36.9714 USD (36.2319/0.98), collection_margin_usd=0.3697 USD, payout_margin_usd=0.3697 USD, send_amount=36.9714 USD (identity leg), collection_amount=37.3314 USD (36.9714+0.36), offer_rate_coll=1.01010 (36.9714/(36.9714-0.3697)), cross_rate=1352.24 KRW/USD (50000/36.9714). Pool identity: 36.9714-0.3697-0.3697=36.2320 (diff 0.0001 < 0.01 passes). All BigDecimal assertions must use scale tolerance of 0.0001 for 4-decimal-place values and 0.00000001 for 8-decimal-place values. | • Create RateEngineCommitTest class • Build a RateQuote with the exact values above and call RateLockService.lockRate on a test transaction • Assert each of the 9 locked fields against expected values with tolerance • Assert pool identity: abs(collection_usd - collection_margin_usd - payout_margin_usd - payout_usd_cost) < 0.01 • Assert rate_locked_at IS NOT NULL after lock • Assert offer_rate_coll = send_amount / (collection_usd - collection_margin_usd) to 5 decimal places | Unit test class RateEngineCommitTest with cross-border inbound test vector fully asserted | • payout_usd_cost within 0.0001 of 36.2319 • collection_usd within 0.0001 of 36.9714 • collection_margin_usd within 0.0001 of 0.3697 • offer_rate_coll within 0.00001 of 1.01010 • Pool identity check: deviation < 0.01 USD (assert abs(36.9714-0.3697-0.3697-payout_usd_cost) < 0.01) | 35 | 5.5-T07 | BE | API-05, RATE-04
5.5-T23 | payment-executor | 5.5 | 5. Transaction Processing (MPM/CPM) | CommitTransaction & payment.approved | 1 | Unit tests: rate-lock field values for USD identity-legs example | Canonical numeric test vector (RATE-04 §7.1): OVERSEAS partner, USD settlement both sides. target_payout=100.00 USD, cost_rate_coll=1.0 (IDENTITY), cost_rate_pay=1.0 (IDENTITY), m_a=0.01, m_b=0.01, service_charge=0.50 USD. Expected: payout_usd_cost=100.00, collection_usd=102.0408 (100.00/0.98), collection_margin_usd=1.0204, payout_margin_usd=1.0204, send_amount=102.0408, collection_amount=102.5408, offer_rate_coll=1.01010 (102.0408/(102.0408-1.0204)), cross_rate=0.98000 (100.00/102.0408). Pool identity: 102.0408-1.0204-1.0204=100.0000 exactly. Test both the rate engine computation AND the rate-lock storage. | • Add test method testIdentityLegsCommit to RateEngineCommitTest • Build RateQuote with both cost_rate_coll=1.0 and cost_rate_pay=1.0 (IDENTITY source), all values as above • Call lockRate; assert all 9 stored field values • Assert pool identity difference < 0.0001 USD (stricter since both legs are identity) • Assert offer_rate_coll = 102.0408 / (102.0408 - 1.0204) within 0.00001 • Assert cross_rate = 0.98000 within 0.00001 | testIdentityLegsCommit test method in RateEngineCommitTest | • collection_usd within 0.0001 of 102.0408 • collection_amount within 0.0001 of 102.5408 • offer_rate_coll within 0.00001 of 1.01010 • cross_rate within 0.00001 of 0.98000 • Pool identity deviation < 0.0001 | 25 | 5.5-T22 | BE | API-05, RATE-04
5.5-T24 | payment-executor | 5.5 | 5. Transaction Processing (MPM/CPM) | CommitTransaction & payment.approved | 1 | Unit tests: rate-lock for same-currency short-circuit (domestic) | Canonical numeric test vector (RATE-04 §7.2): GME Remit (LOCAL, KRW domestic). target_payout=15000 KRW, service_charge=500 KRW, m_a=0, m_b=0, is_same_ccy_shortcircuit=true. Expected: collection_amount=15500 KRW (15000+500), payout_usd_cost=NULL, collection_usd=NULL, collection_margin_usd=0, payout_margin_usd=0, cost_rate_coll=1.0, cost_rate_pay=1.0, offer_rate_coll=1.0, cross_rate=1.0. No prefunding deduction (LOCAL partner). Rate-lock must store NULLs for USD pool columns and zeros for margin columns. Test also verifies no prefunding_ledger_entry created. | • Add test method testSameCurrencyShortCircuitCommit to RateEngineCommitTest • Build RateQuote with is_same_ccy_shortcircuit=true, target_payout=15000, service_charge=500, m_a=0, m_b=0 • Call lockRate; assert payout_usd_cost IS NULL and collection_usd IS NULL in DB • Assert collection_amount=15500, collection_margin_usd=0, payout_margin_usd=0 • Assert offer_rate_coll=1.0 and cross_rate=1.0 • Assert no prefunding_ledger_entry row for this txnId | testSameCurrencyShortCircuitCommit test method with NULL-assertion on USD pool fields | • payout_usd_cost IS NULL in transaction row after lockRate • collection_usd IS NULL in transaction row after lockRate • collection_amount = 15500 (integer KRW scale, 0 decimals) • No prefunding_ledger_entry with this txn_ref • offer_rate_coll = 1.00000000 and cross_rate = 1.00000000 | 25 | 5.5-T22 | BE | API-05, RATE-04
5.5-T25 | payment-executor | 5.5 | 5. Transaction Processing (MPM/CPM) | CommitTransaction & payment.approved | 1 | Unit tests: PARTNER_B_QUOTE_DEVIATION and boundary conditions | Test the deviation check (T05) with exact numeric examples. Test case A: rates_quote=1380.00, commit_quote=1393.80, tolerance=0.01. deviation=13.80/1380.00=0.01 EXACTLY. Expected: no exception (strict greater, not >=). Test case B: rates_quote=1380.00, commit_quote=1394.58, tolerance=0.01. deviation=14.58/1380.00=0.01057>0.01. Expected: PartnerBQuoteDeviationException. Test case C: Partner B API unreachable at commit time. Expected: PartnerBQuoteUnavailableException, no prefunding deduction. Test case D: cost_rate_pay_source=LIVE. Expected: deviation check skipped, no exception regardless of rate change. | • Create PartnerBDeviationCheckerTest class • Test A: assert no exception for deviation exactly equal to tolerance (0.01 == 0.01, strict greater fails) • Test B: assert PartnerBQuoteDeviationException for deviation 0.01057 > 0.01 • Test C: mock PartnerBQuoteClient to throw IOException; assert PartnerBQuoteUnavailableException propagates • Test D: set cost_rate_pay_source=LIVE in quote; assert checkDeviation is never invoked • Test E: zero tolerance configured (tolerance=0.0): any difference throws exception | PartnerBDeviationCheckerTest with 5 test methods covering all deviation paths | • Test A passes (no exception): deviation=0.01, tolerance=0.01 • Test B throws PartnerBQuoteDeviationException: deviation=0.01057, tolerance=0.01 • Test C throws PartnerBQuoteUnavailableException when client is unreachable • Test D: spy confirms checkDeviation never called when source=LIVE • Test E throws for deviation=0.001 when tolerance=0.0 | 30 | 5.5-T05 | BE | API-05, RATE-04
5.5-T26 | payment-executor | 5.5 | 5. Transaction Processing (MPM/CPM) | CommitTransaction & payment.approved | 1 | Unit tests: pool identity failure guard | The pool identity check (RATE-04 §5, §11.2) must fire if the computed collection_usd - collection_margin_usd - payout_margin_usd differs from payout_usd_cost by more than 0.01 USD. This should not happen with correct implementation, but must be tested by injecting a deliberately wrong value. Test: construct a RateQuote where collection_usd=36.9714, collection_margin_usd=0.3697, payout_margin_usd=0.3697 but artificially set payout_usd_cost=36.2000 (deviation=0.0320>0.01). The rate-lock service or computation layer should detect this and throw PoolIdentityFailureException (mapped to INTERNAL_ERROR HTTP 500). Also test the boundary: deviation=0.0099 passes; deviation=0.0101 fails. | • Create PoolIdentityTest class • Test 1: valid pool (deviation 0.0001) - assert no exception from identity check • Test 2: deliberately wrong payout_usd_cost creating deviation 0.0320 - assert PoolIdentityFailureException • Test 3: boundary exactly at 0.01 deviation - assert no exception (tolerance is exclusive: > 0.01 fails) • Test 4: boundary at 0.0101 - assert PoolIdentityFailureException • Verify PoolIdentityFailureException maps to HTTP 500 INTERNAL_ERROR in exception handler (not 422) | PoolIdentityTest class with 4 test methods and HTTP 500 mapping verification | • Valid deviation 0.0001 passes without exception • Deviation 0.0320 throws PoolIdentityFailureException • Deviation exactly 0.01 passes (not > 0.01) • Deviation 0.0101 throws PoolIdentityFailureException • PoolIdentityFailureException maps to HTTP 500 with error_code=INTERNAL_ERROR | 30 | 5.5-T07, 5.5-T22 | BE | API-05, RATE-04
5.5-T27 | payment-executor | 5.5 | 5. Transaction Processing (MPM/CPM) | CommitTransaction & payment.approved | 1 | Unit tests: prefunding deduction atomicity under concurrency | Two concurrent CommitTransaction calls for the same OVERSEAS partner, each requesting collection_usd=60.00 USD, while the account balance is 100.00 USD. Only one should succeed; the other should receive InsufficientPrefundingException. The successful one should leave balance=40.00 USD. Test requires two threads simultaneously calling deductForPayment. The SELECT FOR UPDATE ensures no race condition. Also test: single call requesting exactly the full balance (100.00 USD from 100.00 balance) succeeds; call requesting 100.01 USD fails. | • Create PrefundingDeductionConcurrencyTest • Test 1: exact balance (100.00 USD request from 100.00 balance) succeeds, balance after = 0.00 • Test 2: over-balance (100.01 USD from 100.00) fails with InsufficientPrefundingException carrying required=100.01, available=100.00 • Test 3: two concurrent threads each requesting 60.00 from balance 100.00 - use CountDownLatch to synchronize start; assert exactly one succeeds, one throws InsufficientPrefundingException • Test 4: after successful deduction, prefunding_ledger_entry.balance_after = account.balance (consistency check) • Use real PostgreSQL (port 5433) for concurrency test; mock is insufficient for SELECT FOR UPDATE verification | PrefundingDeductionConcurrencyTest with real DB concurrency test | • Test 1: balance after deduction = 0.00 • Test 2: InsufficientPrefundingException message contains available=100.00 and required=100.01 • Test 3: exactly 1 of 2 threads succeeds; balance after = 40.00 • Test 4: prefunding_ledger_entry.balance_after matches account.balance post-deduction • Test 3 is deterministic (not flaky): SELECT FOR UPDATE guarantees mutual exclusion | 45 | 5.5-T06 | BE | API-05, RATE-04
5.5-T28 | payment-executor | 5.5 | 5. Transaction Processing (MPM/CPM) | CommitTransaction & payment.approved | 1 | Unit tests: transaction state machine transitions in commit flow | The transaction state machine (SAD-02 §5.2) has strict allowed transitions. Valid commit-time transitions: QUOTED->PENDING_DEBIT (OVERSEAS commit received), QUOTED->DEBITED (LOCAL partner, no prefund), PENDING_DEBIT->DEBITED (deduction success), DEBITED->SCHEME_SENT (scheme call dispatched), SCHEME_SENT->APPROVED (scheme success), SCHEME_SENT->FAILED (scheme reject), SCHEME_SENT->UNCERTAIN (timeout). Invalid: APPROVED->PENDING_DEBIT, FAILED->anything, DEBITED->APPROVED (must go through SCHEME_SENT). Each transition must be recorded in transaction_event. Test the transition guard: attempting an invalid transition raises InvalidStateTransitionException. | • Create TransactionStateMachineTest • Test valid path: QUOTED->PENDING_DEBIT->DEBITED->SCHEME_SENT->APPROVED - assert each state persisted after each step • Test invalid transition: APPROVED->PENDING_DEBIT throws InvalidStateTransitionException • Test invalid transition: DEBITED->APPROVED (skipping SCHEME_SENT) throws InvalidStateTransitionException • Test terminal state: FAILED->DEBITED throws InvalidStateTransitionException • Assert transaction_event rows match state transitions in order with correct step numbers | TransactionStateMachineTest with valid and invalid transition tests | • Full QUOTED->APPROVED path produces 5 transaction_event rows with steps 2, 3, 4, 5 (step 1 already written at quote time) • APPROVED->PENDING_DEBIT throws InvalidStateTransitionException • DEBITED->APPROVED (bypassing SCHEME_SENT) throws InvalidStateTransitionException • FAILED is terminal: any further transition attempt throws • State persisted to DB after each transition (not just in-memory) | 35 | 5.5-T13, 5.5-T14 | BE | API-05, RATE-04
5.5-T29 | payment-executor | 5.5 | 5. Transaction Processing (MPM/CPM) | CommitTransaction & payment.approved | 1 | Unit tests: payment.approved webhook payload correctness | Test that the webhook payload produced by PaymentApprovedPayloadBuilder (T16) matches the exact schema from API-05 §6.5 for both OVERSEAS and LOCAL partner cases. OVERSEAS test vector: payment_id=pay_01, partner_txn_ref=SENDMN-TXN-001, scheme_txn_id=ZP2026001, merchant_name=Seoul Coffee House, direction=inbound, scheme_id=zeropay, target_payout=50000 KRW, offer_rate=0.000703, collection_amount=35.77, collection_currency=USD, service_charge=0.35, service_charge_currency=USD, prefund_deducted_usd=35.77. LOCAL test vector: all same except no prefund_deducted_usd field. HMAC signing test: verify X-GME-Webhook-Signature = 'sha256=' + hex(HMAC-SHA256(body_bytes, secret_bytes)). | • Create PaymentApprovedWebhookTest class • Test 1 OVERSEAS: build payload from mock transaction with above fields; serialize to JSON; assert all fields present and correct • Test 2 LOCAL: assert JSON does not contain key prefund_deducted_usd • Test 3 HMAC signing: compute expected HMAC-SHA256 with known secret; compare to actual header value • Test 4 event_id uniqueness: build two payloads; assert event_ids differ • Test 5 timestamp format: assert created_at matches regex \d{4}-\d{2}-\d{2}T\d{2}:\d{2}:\d{2}\.\d{3}Z | PaymentApprovedWebhookTest with 5 test methods covering payload and signing | • All 15 required fields present in OVERSEAS payload matching API-05 §6.5 schema • LOCAL payload JSON node count is 14 (no prefund_deducted_usd) • HMAC signature: sha256=computed_hex matches X-GME-Webhook-Signature header • Two consecutive payload builds produce different event_ids • approved_at field in payload matches transaction.completed_at in UTC millisecond format | 35 | 5.5-T16, 5.5-T17 | BE | API-05, RATE-04
5.5-T30 | payment-executor | 5.5 | 5. Transaction Processing (MPM/CPM) | CommitTransaction & payment.approved | 1 | Unit tests: idempotency semantics for POST /v1/payments | Test the idempotency layer (T15) for all 4 scenarios from API-05 §7.1. Scenario 1: same key + same body, completed -> stored response returned. Scenario 2: same key + same body, in-flight -> HTTP 409 X-Idempotency-Status: in_flight. Scenario 3: same key + different body -> HTTP 422 IDEMPOTENCY_KEY_REUSE. Scenario 4: missing key -> HTTP 400 MISSING_IDEMPOTENCY_KEY. Additional: verify no double scheme call on idempotent replay (mock scheme adapter call count = 1 for two identical requests). Verify no double prefunding deduction (ledger entry count = 1 for two identical requests). | • Create IdempotencyTest class • Test S1: complete a payment; replay with same key+body; assert second response matches first (same payment_id, HTTP 201) • Test S2: simulate in-flight by holding the lock in Redis; second call returns HTTP 409 • Test S3: change collection_amount in second request while reusing key; assert HTTP 422 IDEMPOTENCY_KEY_REUSE • Test S4: POST without Idempotency-Key header; assert HTTP 400 MISSING_IDEMPOTENCY_KEY • Test double-deduction prevention: verify schemeAdapter.submitMpm called exactly once for S1 replay | IdempotencyTest class with 5 test methods covering all idempotency scenarios | • S1: second call returns HTTP 201 with same payment_id as first call • S2: in-flight second call returns HTTP 409 with X-Idempotency-Status: in_flight • S3: different body returns HTTP 422 with error_code=IDEMPOTENCY_KEY_REUSE • S4: missing header returns HTTP 400 with error_code=MISSING_IDEMPOTENCY_KEY • S1 replay: schemeAdapter.submitMpm invocation count = 1 (no duplicate scheme call) | 40 | 5.5-T15, 5.5-T18 | BE | API-05, RATE-04
5.5-T31 | payment-executor | 5.5 | 5. Transaction Processing (MPM/CPM) | CommitTransaction & payment.approved | 1 | Integration test: full MPM commit happy path (OVERSEAS partner) | End-to-end integration test for MPM Fixed payment from POST /v1/rates through POST /v1/payments to APPROVED state and webhook enqueue. Uses real PostgreSQL (port 5433), real Redis, and a mock ZeroPay scheme adapter. Test setup: OVERSEAS partner (SendMN), rule with m_a=0.01, m_b=0.01, service_charge=0.36 USD, cost_rate_pay=1380.00, cost_rate_coll=1.0 (IDENTITY). Step 1: POST /v1/rates with target_payout=50000 KRW, expect quote_id and offer_rate=approx 0.000703. Step 2: POST /v1/payments with quote_id, expect HTTP 201 APPROVED, scheme_txn_id present. Step 3: verify transaction DB row has all 13 rate-lock columns set. Step 4: verify prefunding balance reduced by 36.97 USD (approx collection_usd). Step 5: verify payment.approved webhook enqueued. | • Create MpmCommitIntegrationTest with @SpringBootTest or equivalent • Seed partner, scheme, rule, merchant, QR in test DB; set prefunding balance to 500.00 USD • Execute POST /v1/rates and capture quote_id • Execute POST /v1/payments; assert HTTP 201 and APPROVED status • Query transaction table; assert rate_locked_at IS NOT NULL, offer_rate_coll within 0.0001 of 1.01010 • Query prefunding_account; assert balance reduced by approx 36.97 USD (within 0.01) • Assert webhook message enqueued for payment.approved event | MpmCommitIntegrationTest covering full happy path from quote to approved to webhook | • HTTP 201 with status='approved' and scheme_txn_id present • Transaction.rate_locked_at IS NOT NULL after commit • Transaction.collection_usd within 0.01 of 36.97 • prefunding_account.balance decreased by transaction.collection_usd exactly • Webhook queue contains one payment.approved event for this payment_id | 55 | 5.5-T18, 5.5-T22 | BE | API-05, RATE-04
5.5-T32 | payment-executor | 5.5 | 5. Transaction Processing (MPM/CPM) | CommitTransaction & payment.approved | 1 | Integration test: full CPM commit happy path | End-to-end test for CPM flow: POST /v1/payments/cpm/generate -> inbound CPM notification (simulated) -> POST /v1/payments/cpm/confirm -> APPROVED. Uses real DB and Redis. Test setup same as T31. Step 1: POST /v1/payments/cpm/generate - get cpm_token_id and prepare_token; verify prefunding reserved. Step 2: simulate ZeroPay inbound notification (call internal handler directly or via test endpoint) with payout_amount=32000 KRW, merchant_id - triggers rate computation and payment.pending_debit webhook. Step 3: POST /v1/payments/cpm/confirm with txn_ref - expect HTTP 201 APPROVED. Step 4: verify rate-lock columns set, verify two webhook events: payment.pending_debit and payment.approved. | • Create CpmCommitIntegrationTest • POST /v1/payments/cpm/generate with OVERSEAS partner; assert HTTP 201 and prepare_token • Simulate inbound CPM notification with payout_amount=32000 KRW; assert payment.pending_debit webhook enqueued • POST /v1/payments/cpm/confirm; assert HTTP 201 APPROVED • Verify transaction rate-lock columns: payout_usd_cost = 32000/1380 = approx 23.19, collection_usd = approx 23.66 • Verify two webhook events queued: payment.pending_debit and payment.approved in that order | CpmCommitIntegrationTest covering full CPM flow to approved and both webhooks | • HTTP 201 from /cpm/generate with prefund_reserved_usd > 0 • payment.pending_debit webhook enqueued after inbound notification with offer_rate field present • HTTP 201 from /cpm/confirm with status='approved' • transaction.payout_usd_cost within 0.01 of 23.19 (32000/1380) • Two webhook events queued: pending_debit before approved | 55 | 5.5-T09, 5.5-T31 | BE | API-05, RATE-04
5.5-T33 | payment-executor | 5.5 | 5. Transaction Processing (MPM/CPM) | CommitTransaction & payment.approved | 1 | Integration test: commit with expired quote returns 422 | Verify the TTL expiry guard end-to-end. Test: obtain a quote with TTL=5s (set partner.rate_quote_ttl_seconds=5 for test partner), wait 6 seconds, then attempt POST /v1/payments. Expected: HTTP 422 with error_code=RATE_QUOTE_EXPIRED, no transaction row created, no prefunding deduction. Also verify that the error.details[0].issue field contains the expired valid_until timestamp. Additionally test that attempting to reuse the quote_id even after obtaining a fresh quote does not allow the expired quote to be used (expired quote stays expired). | • Create QuoteExpiryIntegrationTest • Configure test partner with rate_quote_ttl_seconds=5 • POST /v1/rates; capture quote_id and valid_until • Wait 6 seconds (Thread.sleep or advance mock clock) • POST /v1/payments with expired quote_id; assert HTTP 422 RATE_QUOTE_EXPIRED • Query transaction table; assert no row with this quote_id • Query prefunding_account; assert balance unchanged | QuoteExpiryIntegrationTest verifying expiry guard end-to-end | • HTTP 422 with error_code=RATE_QUOTE_EXPIRED • No transaction row created for expired commit attempt • prefunding_account.balance unchanged after failed expired-quote attempt • error.details contains the expired valid_until timestamp • Fresh quote with same partner can be committed successfully (expiry does not affect new quotes) | 35 | 5.5-T10, 5.5-T31 | BE | API-05, RATE-04
5.5-T34 | payment-executor | 5.5 | 5. Transaction Processing (MPM/CPM) | CommitTransaction & payment.approved | 1 | Integration test: insufficient prefunding returns 402 | Verify the insufficient prefunding guard end-to-end. Test: OVERSEAS partner with balance=10.00 USD attempts a payment where collection_usd would be approx 36.97 USD (target_payout=50000 KRW, same rates as T31). Expected: HTTP 402 with error_code=INSUFFICIENT_PREFUNDING, no transaction row, no scheme call, balance unchanged. Also test the LOCAL partner version: GET /v1/balance returns HTTP 403 for LOCAL partner (prefunding does not apply). | • Create PrefundingIntegrationTest • Set OVERSEAS partner prefunding balance to 10.00 USD in test DB • POST /v1/rates with target_payout=50000 KRW; capture quote_id (collection_usd approx 36.97) • POST /v1/payments; assert HTTP 402 INSUFFICIENT_PREFUNDING • Query transaction table; assert no committed row for this attempt • Assert mock scheme adapter was NOT called • Assert prefunding_account.balance remains 10.00 USD | PrefundingIntegrationTest with insufficient balance and LOCAL partner 403 tests | • HTTP 402 with error_code=INSUFFICIENT_PREFUNDING for balance=10.00 USD, collection_usd=36.97 USD • No transaction row created for failed prefunding attempt • schemeAdapter.submitMpm was never called • balance remains 10.00 USD after failed attempt • LOCAL partner calling GET /v1/balance returns HTTP 403 | 35 | 5.5-T06, 5.5-T31 | BE | API-05, RATE-04
5.5-T35 | payment-executor | 5.5 | 5. Transaction Processing (MPM/CPM) | CommitTransaction & payment.approved | 1 | Write API-05 endpoint documentation for POST /v1/payments commit flow | Document the POST /v1/payments endpoint in the project's API reference docs (OpenAPI 3.0 YAML or equivalent). The documentation must cover: request fields (all 8 required + 1 optional from API-05 §4.3), response fields (all 14 from spec), all HTTP status codes (201, 202, 400, 402, 404, 409, 422, 429), all error codes with descriptions, the note that collection_amount is echoed not validated, the rate-lock guarantee statement, and the idempotency header requirement. Include the worked example from the spec (target_payout=50000 KRW, offer_rate=0.000703). | • Locate or create openapi/paths/payments.yaml • Add POST /v1/payments operation with requestBody schema including all 8 required fields • Add responses for 201, 202, 400, 402, 404, 409, 422, 429 with error schema references • Add description note: GMEPay+ records collection_amount as supplied without validation • Add description note: all USD pool values are permanently locked at execution (rate_locked_at) • Add example request/response using the canonical SendMN/KRW example from API-05 §4.3 • Validate YAML against OpenAPI 3.0 schema using a linter | OpenAPI 3.0 YAML for POST /v1/payments with all fields, status codes, and worked example | • OpenAPI linter reports 0 errors on the YAML file • All 8 required request fields present with correct types (string/decimal for monetary, string for IDs) • All 6 HTTP status code responses documented (201, 202, 400, 402, 404, 422) • collection_amount description notes it is echoed not validated • Rate-lock guarantee mentioned in endpoint description | 40 | 5.5-T18 | BE | API-05, RATE-04
5.5-T36 | payment-executor | 5.5 | 5. Transaction Processing (MPM/CPM) | CommitTransaction & payment.approved | 1 | Write API-05 endpoint documentation for payment.approved webhook | Document the payment.approved webhook event in the project's API reference docs. The documentation must cover: event envelope schema (event_id, event_type, created_at, partner_id, data), all data fields from API-05 §6.5 including the conditional prefund_deducted_usd (OVERSEAS only), webhook signing headers (X-GME-Webhook-Signature format: sha256=<HMAC-SHA256>, X-GME-Webhook-Timestamp, X-GME-Event-ID), retry schedule (10 attempts: immediate, 30s, 2min, 10min, 30min, 1h x5), partner verification instructions (compare HMAC, reject if timestamp > 5min old), and the worked example from API-05 §6.5. Also document the event delivery guarantee: at-least-once (idempotent handling required). | • Locate or create openapi/webhooks/payment_approved.yaml or equivalent docs section • Document event envelope schema with all fields and types • Document data object with all 14 fields including conditional prefund_deducted_usd • Document the three signing headers and HMAC verification algorithm • Document retry schedule as a table: attempt number -> delay • Add partner verification code snippet (pseudocode for HMAC check) • Validate the worked example JSON against the documented schema | Webhook documentation for payment.approved event with schema, signing, retry, and example | • Documentation lists all 14 data fields from API-05 §6.5 • Retry schedule shows 10 attempts with correct delays (immediate, 30s, 2min, 10min, 30min, 5x1h) • HMAC verification algorithm documented: sha256=hex(HMAC-SHA256(raw_body, webhook_signing_secret)) • Conditional note for prefund_deducted_usd: present for OVERSEAS partners only • At-least-once delivery guarantee and idempotency requirement documented | 30 | 5.5-T17, 5.5-T35 | BE | API-05, RATE-04
5.6-T01 | payment-executor | 5.6 | 5. Transaction Processing (MPM/CPM) | Same-day cancellation | 1 | Add cancelled_at and cancel_reason columns to payments table (migration) | WBS 5.6 Same-day cancellation. The payments table must store cancellation metadata. New columns: cancelled_at (TIMESTAMPTZ, nullable), cancel_reason (VARCHAR(50), nullable, allowed values: customer_request, merchant_request, timeout, other), cancel_reason_detail (VARCHAR(200), nullable). Status column already exists with values PENDING, APPROVED, FAILED etc.; CANCELLED is a new valid value to be added. KST timezone is used for same-day window checks but timestamps are stored in UTC. | • Create a Flyway migration file V5_6_001__cancel_columns.sql in db/migrations/ • Add column: ALTER TABLE payments ADD COLUMN cancelled_at TIMESTAMPTZ NULL • Add column: ALTER TABLE payments ADD COLUMN cancel_reason VARCHAR(50) NULL • Add column: ALTER TABLE payments ADD COLUMN cancel_reason_detail VARCHAR(200) NULL • Add CHECK constraint: cancel_reason IN ('customer_request','merchant_request','timeout','other') • Add the CANCELLED value to the status enum/check constraint if not already present | db/migrations/V5_6_001__cancel_columns.sql — applied cleanly via Flyway on a fresh schema | • Migration applies without error on an empty schema and on a schema with existing payment rows • cancelled_at column accepts NULL and a valid UTC timestamp; rejects non-timestamp values • cancel_reason column rejects any value not in the allowed set ('customer_request','merchant_request','timeout','other') • cancel_reason_detail column accepts NULL and strings up to 200 chars; rejects strings > 200 chars • Existing rows with status APPROVED remain unaffected after migration | 25 |  | BE | API-05
5.6-T02 | payment-executor | 5.6 | 5. Transaction Processing (MPM/CPM) | Same-day cancellation | 1 | Add prefund_reversal_usd column to payments table (migration) | WBS 5.6 Same-day cancellation. When an OVERSEAS partner payment is cancelled, the prefunding balance is restored by exactly the collection_usd amount that was deducted. The response and webhook field prefund_returned_usd is sourced from this column. The column must be stored as NUMERIC(18,8) to match existing monetary field precision. This is nullable because LOCAL partners have no prefunding. | • Create migration file V5_6_002__cancel_prefund_reversal.sql in db/migrations/ • Add column: ALTER TABLE payments ADD COLUMN prefund_reversal_usd NUMERIC(18,8) NULL • Add comment/documentation: COMMENT ON COLUMN payments.prefund_reversal_usd IS 'Amount returned to OVERSEAS partner prefunding on cancel; equals collection_usd at time of deduction; NULL for LOCAL partners' | db/migrations/V5_6_002__cancel_prefund_reversal.sql | • Migration applies cleanly after V5_6_001 • Column stores values such as 35.77000000 correctly (2 decimal precision example) • Column stores NULL for a LOCAL partner row • Column rejects non-numeric input • Existing rows are unaffected (column is NULL by default) | 20 | 5.6-T01 | BE | API-05
5.6-T03 | payment-executor | 5.6 | 5. Transaction Processing (MPM/CPM) | Same-day cancellation | 1 | Add DB index on (partner_id, created_at_kst_date) for same-day window query | WBS 5.6 Same-day cancellation. The cancel eligibility check must query whether a payment was created on the same calendar day in KST (UTC+9). Created_at is stored as UTC TIMESTAMPTZ. A functional index on (partner_id, (created_at AT TIME ZONE 'Asia/Seoul')::date) enables efficient same-day lookup. Without it, the eligibility check is a full-table scan. | • Create migration file V5_6_003__cancel_sameday_index.sql in db/migrations/ • Add index: CREATE INDEX idx_payments_partner_kst_date ON payments (partner_id, ((created_at AT TIME ZONE 'Asia/Seoul')::date)) • Verify the index name is unique across existing indexes | db/migrations/V5_6_003__cancel_sameday_index.sql | • Migration applies cleanly • EXPLAIN on SELECT * FROM payments WHERE partner_id='prt_1' AND (created_at AT TIME ZONE 'Asia/Seoul')::date = '2026-06-04' uses the new index (not seq scan) • Index does not exist prior to migration; exists after • Migration is idempotent when run in a CI fresh-schema pipeline | 20 | 5.6-T01 | BE | API-05
5.6-T04 | payment-executor | 5.6 | 5. Transaction Processing (MPM/CPM) | Same-day cancellation | 1 | Define CancelPaymentRequest and CancelPaymentResponse DTOs | WBS 5.6 Same-day cancellation. The cancel endpoint POST /v1/payments/{id}/cancel accepts a JSON body with: reason (string, required, enum: customer_request¦merchant_request¦timeout¦other) and reason_detail (string, optional, max 200 chars). Response fields: payment_id (string), status (always 'cancelled'), cancelled_at (ISO-8601 UTC string), prefund_returned_usd (string decimal, OVERSEAS only, omit or null for LOCAL). All DTOs must use Java records or immutable POJOs with Jackson annotations. | • Create src/main/java/com/gmepayplus/api/cancel/dto/CancelPaymentRequest.java • Add @NotNull @Pattern validation on reason field limiting to the four allowed values • Add @Size(max=200) on reason_detail (nullable) • Create src/main/java/com/gmepayplus/api/cancel/dto/CancelPaymentResponse.java • Add fields: payment_id (String), status (String), cancelled_at (Instant), prefund_returned_usd (BigDecimal, nullable) • Add @JsonInclude(NON_NULL) so prefund_returned_usd is omitted from LOCAL partner responses | CancelPaymentRequest.java and CancelPaymentResponse.java in the cancel/dto package | • Jackson serializes a CancelPaymentResponse with prefund_returned_usd=null and the field is absent from JSON output • Jackson serializes a CancelPaymentResponse with prefund_returned_usd=35.77 as the string '35.77' (decimal string, not float) • @Valid on CancelPaymentRequest rejects reason='wrong' with a 400 binding error • @Valid on CancelPaymentRequest rejects reason_detail of 201 characters • @Valid on CancelPaymentRequest accepts reason='customer_request' with null reason_detail | 30 | 5.6-T01 | BE | API-05
5.6-T05 | payment-executor | 5.6 | 5. Transaction Processing (MPM/CPM) | Same-day cancellation | 1 | Implement SameDayWindowService: determine if a payment is within the same-day KST cancel window | WBS 5.6 Same-day cancellation. Cancellation is only permitted when the payment's created_at falls on the same calendar day in KST (UTC+9) as the current instant. Business rule: compare (created_at AT TIME ZONE Asia/Seoul)::date == (NOW() AT TIME ZONE Asia/Seoul)::date. The service must accept a created_at Instant and return boolean. No hardcoded timezone strings — use ZoneId.of('Asia/Seoul'). This service is used by the cancel eligibility check before any DB write. | • Create src/main/java/com/gmepayplus/cancel/SameDayWindowService.java • Inject a Clock bean (not System.currentTimeMillis) so tests can fix the current time • Implement boolean isWithinSameDayWindow(Instant createdAt): convert both instants to Asia/Seoul LocalDate and compare • Add a Spring @Service annotation • Write no DB calls in this class — pure time logic only | SameDayWindowService.java with a Clock-injectable constructor | • isWithinSameDayWindow returns true when createdAt=2026-06-04T00:00:00Z and clock=2026-06-04T14:59:59Z (both KST date 2026-06-05... wait: UTC 00:00 = KST 09:00, so KST date is 2026-06-04; clock 14:59:59Z = KST 23:59:59 same day) -> true • isWithinSameDayWindow returns false when createdAt=2026-06-03T15:00:00Z (KST 2026-06-04 00:00) and clock=2026-06-04T15:00:00Z (KST 2026-06-05 00:00) -> false (next KST day) • isWithinSameDayWindow returns false when createdAt=2026-06-03T12:00:00Z (KST 2026-06-03 21:00) and clock=2026-06-04T12:00:00Z (KST 2026-06-04 21:00) -> false • isWithinSameDayWindow returns true for createdAt one second ago relative to fixed clock • Service compiles and has zero direct calls to ZonedDateTime.now() without the injected Clock | 30 |  | BE | API-05
5.6-T06 | payment-executor | 5.6 | 5. Transaction Processing (MPM/CPM) | Same-day cancellation | 1 | Implement CancelEligibilityService: validate payment status and same-day window | WBS 5.6 Same-day cancellation. A payment is cancellable only when: (1) status is APPROVED or PENDING (not FAILED, CANCELLED, or any terminal state); and (2) the same-day KST window is open (see SameDayWindowService). If status is already CANCELLED or FAILED, return ALREADY_TERMINAL. If status is valid but window is closed, return CANCEL_NOT_PERMITTED. If both conditions pass, return ELIGIBLE. Use these result codes as an enum: ELIGIBLE, ALREADY_TERMINAL, CANCEL_NOT_PERMITTED. This service is called before any DB write or prefunding reversal. | • Create src/main/java/com/gmepayplus/cancel/CancelEligibilityService.java • Define inner enum CancelEligibilityResult {ELIGIBLE, ALREADY_TERMINAL, CANCEL_NOT_PERMITTED} • Inject SameDayWindowService • Implement CancelEligibilityResult check(Payment payment): check status first, then window • Cancellable statuses: APPROVED, PENDING (PENDING means rate-quoted not yet committed — also cancellable) • Non-cancellable terminal statuses: FAILED, CANCELLED, REFUNDED, REVERSED — return ALREADY_TERMINAL | CancelEligibilityService.java with enum CancelEligibilityResult | • Payment(status=APPROVED, createdAt=today KST) -> ELIGIBLE • Payment(status=CANCELLED, createdAt=today KST) -> ALREADY_TERMINAL • Payment(status=FAILED, createdAt=today KST) -> ALREADY_TERMINAL • Payment(status=APPROVED, createdAt=yesterday KST) -> CANCEL_NOT_PERMITTED • Payment(status=PENDING, createdAt=today KST) -> ELIGIBLE | 30 | 5.6-T05 | BE | API-05
5.6-T07 | payment-executor | 5.6 | 5. Transaction Processing (MPM/CPM) | Same-day cancellation | 1 | Implement PrefundingReversalService: atomically restore collection_usd to OVERSEAS partner balance | WBS 5.6 Same-day cancellation. When an OVERSEAS partner payment is cancelled, the prefunding balance must be restored by exactly the collection_usd amount stored on the payment record (the amount deducted at payment commit). The reversal uses SELECT ... FOR UPDATE on the prefunding_balances row (same atomicity pattern as the deduction in WBS RATE-04/prefunding). LOCAL partners (partner_type=LOCAL) skip this step. The service records a ledger entry with type=CANCEL_REVERSAL. Returns the restored amount as BigDecimal. | • Create src/main/java/com/gmepayplus/cancel/PrefundingReversalService.java • Inject PrefundingRepository (existing from prefunding deduction work) • Implement BigDecimal reverse(UUID paymentId, UUID partnerId, PartnerType partnerType, BigDecimal collectionUsd) inside a @Transactional method • If partnerType == LOCAL, skip DB write, return BigDecimal.ZERO • SELECT ... FOR UPDATE on prefunding_balances WHERE partner_id = partnerId • Increment balance by collectionUsd • Insert ledger entry: type=CANCEL_REVERSAL, payment_id, amount_usd=collectionUsd (positive), timestamp=now • Return collectionUsd as the restored amount | PrefundingReversalService.java with @Transactional reverse() method | • OVERSEAS partner with balance 100.00 USD and collectionUsd 35.77: after reverse(), balance is 135.77 USD • LOCAL partner: reverse() returns 0.00 and no ledger row is inserted • Concurrent calls for different partners do not deadlock (row-level lock only) • Ledger entry type is CANCEL_REVERSAL and amount_usd matches collectionUsd exactly • reverse() is idempotent-safe: calling twice for the same paymentId should be guarded by the caller (no double-credit logic here — caller ensures single invocation via idempotency key) | 45 | 5.6-T02 | BE | API-05
5.6-T08 | payment-executor | 5.6 | 5. Transaction Processing (MPM/CPM) | Same-day cancellation | 1 | Implement ZeroPayCancelAdapter: call ZeroPay real-time cancel API | WBS 5.6 Same-day cancellation. The ZeroPay scheme adapter interface includes cancelPayment(scheme_txn_ref) -> CancelResult (spec SCH-06 section 1.3.1). For same-day cancel, GMEPay+ must call ZeroPay's real-time HTTPS cancel API with the scheme_txn_ref stored on the payment. The call uses the existing scheme config (realtime_api_base_url from scheme config record). A successful ZeroPay cancel returns HTTP 200. On HTTP 4xx, throw CancelSchemeException with the raw ZeroPay error code. On HTTP 5xx or timeout, throw SchemeUnavailableException. If the payment has no scheme_txn_ref (e.g. status was PENDING before scheme submission), skip the scheme call and return CancelResult.NOT_SUBMITTED. | • Create src/main/java/com/gmepayplus/scheme/zeropay/ZeroPayCancelAdapter.java • Inject the ZeroPay HTTP client (existing from payment commit work) • Implement CancelResult cancelPayment(String schemeTxnRef): if schemeTxnRef is null, return CancelResult.NOT_SUBMITTED • Build the ZeroPay cancel request per scheme spec (POST to {base_url}/cancel with body {txn_ref: schemeTxnRef}) • On 200 response, return CancelResult.SUCCESS • On 4xx, parse ZeroPay error code, throw CancelSchemeException(code, message) • On 5xx/timeout, throw SchemeUnavailableException | ZeroPayCancelAdapter.java implementing SchemeAdapter.cancelPayment() | • Mock ZeroPay returning 200: CancelResult.SUCCESS returned • Mock ZeroPay returning 404: CancelSchemeException thrown with raw ZeroPay code • Mock ZeroPay returning 500: SchemeUnavailableException thrown • schemeTxnRef=null: CancelResult.NOT_SUBMITTED returned without any HTTP call • Adapter reads base_url from SchemeConfig, not a hardcoded string | 40 |  | BE | API-05
5.6-T09 | payment-executor | 5.6 | 5. Transaction Processing (MPM/CPM) | Same-day cancellation | 1 | Implement CancelPaymentUseCase: orchestrate eligibility, scheme cancel, prefund reversal, status update | WBS 5.6 Same-day cancellation. The core cancel orchestration: (1) Load payment by ID, verify it belongs to the calling partner (return 404 if not found, 403 if wrong partner). (2) Check eligibility via CancelEligibilityService; map ALREADY_TERMINAL -> HTTP 409, CANCEL_NOT_PERMITTED -> HTTP 400 with error code CANCEL_NOT_PERMITTED. (3) Call ZeroPayCancelAdapter.cancelPayment(scheme_txn_ref) if status is APPROVED/SUBMITTED (skip if PENDING/not yet submitted). (4) Call PrefundingReversalService.reverse() for OVERSEAS partners. (5) In a single @Transactional block: update payment status=CANCELLED, set cancelled_at=now(), cancel_reason, cancel_reason_detail, prefund_reversal_usd. (6) Return CancelPaymentResponse. Steps 3 and 4 must occur before the DB commit in step 5 to ensure consistency. | • Create src/main/java/com/gmepayplus/cancel/CancelPaymentUseCase.java • Inject PaymentRepository, CancelEligibilityService, ZeroPayCancelAdapter, PrefundingReversalService • Implement CancelPaymentResponse execute(UUID paymentId, UUID partnerId, CancelPaymentRequest request) • Fetch payment; throw PaymentNotFoundException if absent; throw UnauthorizedException if payment.partner_id != partnerId • Call eligibilityService.check(); throw appropriate exception based on result • Call adapter.cancelPayment() if payment has a scheme_txn_ref (status APPROVED or higher); tolerate NOT_SUBMITTED • Call prefundingReversalService.reverse() and capture reversedAmount • In @Transactional: set status=CANCELLED, cancelled_at, cancel_reason, cancel_reason_detail, prefund_reversal_usd=reversedAmount • Build and return CancelPaymentResponse | CancelPaymentUseCase.java with full orchestration logic | • APPROVED OVERSEAS payment: status becomes CANCELLED, prefund_reversal_usd equals original collection_usd, scheme cancel is called • PENDING LOCAL payment: status becomes CANCELLED, prefund_reversal_usd is null, scheme cancel is NOT called (no scheme_txn_ref) • Already-CANCELLED payment: returns HTTP 409 without any DB write • APPROVED payment from wrong partner_id: throws 404 (do not leak existence to wrong partner) • Window-expired APPROVED payment (created yesterday KST): returns HTTP 400 with code CANCEL_NOT_PERMITTED | 55 | 5.6-T06, 5.6-T07, 5.6-T08 | BE | API-05
5.6-T10 | payment-executor | 5.6 | 5. Transaction Processing (MPM/CPM) | Same-day cancellation | 1 | Implement POST /v1/payments/{id}/cancel HTTP controller | WBS 5.6 Same-day cancellation. The Northbound REST endpoint is POST /v1/payments/{id}/cancel. Auth: existing partner API-key + X-Timestamp + X-Signature headers (already validated by a shared filter). Idempotency-Key header is required (HTTP 400 MISSING_IDEMPOTENCY_KEY if absent). Path param: id (payment_id). Request body: CancelPaymentRequest. The idempotency cache stores (partner_id, idempotency_key, response_body, http_status) for 24 hours — if a duplicate request arrives with the same key, return the cached response. Status codes: 200 OK, 400 CANCEL_NOT_PERMITTED, 404 PAYMENT_NOT_FOUND, 409 (terminal state conflict). | • Create src/main/java/com/gmepayplus/api/cancel/CancelPaymentController.java • Annotate with @RestController, @RequestMapping('/v1/payments') • Implement @PostMapping('/{id}/cancel') handler • Extract partner_id from authenticated security context (set by API-key filter) • Check Idempotency-Key header; return 400 MISSING_IDEMPOTENCY_KEY if absent • Check idempotency cache: if hit with matching partner_id+key, return cached response • Call CancelPaymentUseCase.execute(); cache the response before returning • Map exceptions: PaymentNotFoundException->404, ALREADY_TERMINAL->409, CANCEL_NOT_PERMITTED->400 • Return CancelPaymentResponse as JSON with X-Request-ID header | CancelPaymentController.java wired to CancelPaymentUseCase | • POST with valid approved same-day payment returns HTTP 200 and JSON body with status='cancelled' • POST without Idempotency-Key header returns HTTP 400 with code MISSING_IDEMPOTENCY_KEY • Second POST with same Idempotency-Key returns same 200 response without re-executing use case • POST for unknown payment_id returns HTTP 404 • POST for wrong partner's payment returns HTTP 404 (not 403, to avoid info leak) | 40 | 5.6-T04, 5.6-T09 | BE | API-05
5.6-T11 | payment-executor | 5.6 | 5. Transaction Processing (MPM/CPM) | Same-day cancellation | 1 | Enqueue payment.cancelled webhook event after successful cancellation | WBS 5.6 Same-day cancellation. On successful cancel, GMEPay+ must deliver a payment.cancelled webhook to the partner's configured webhook_url. Event schema: {event_id, event_type:'payment.cancelled', created_at, partner_id, data:{payment_id, partner_txn_ref, reason, prefund_returned_usd (OVERSEAS only), cancelled_at}}. Webhook delivery is at-least-once with exponential backoff (1s, 2s, 4s, max 30s, 5 attempts). The webhook is enqueued (not sent synchronously) after the cancel DB transaction commits. Use the existing WebhookOutbox table (or equivalent outbox pattern). | • In CancelPaymentUseCase, after the @Transactional commit completes, call WebhookOutboxService.enqueue(partnerId, 'payment.cancelled', payload) • Build the payload from CancelPaymentResponse: include payment_id, partner_txn_ref, reason, cancelled_at; include prefund_returned_usd only for OVERSEAS (non-null value) • Ensure the enqueue call is OUTSIDE the cancel @Transactional block so a webhook enqueue failure does not roll back the cancel • Add event_type='payment.cancelled' to the WebhookEventType enum if not already present • Confirm WebhookOutbox delivery worker handles retries per the existing retry policy | payment.cancelled event enqueued via WebhookOutboxService in CancelPaymentUseCase | • After successful cancel, one row with event_type=payment.cancelled is present in the webhook_outbox table • Payload includes partner_txn_ref and cancelled_at • OVERSEAS payment: payload includes prefund_returned_usd as decimal string e.g. '35.77' • LOCAL payment: prefund_returned_usd is absent from payload • Webhook enqueue failure does not roll back the payment CANCELLED status update | 35 | 5.6-T09 | BE | API-05
5.6-T12 | payment-executor | 5.6 | 5. Transaction Processing (MPM/CPM) | Same-day cancellation | 1 | Record CANCEL_INITIATED and CANCEL_CONFIRMED audit events on payment event trail | WBS 5.6 Same-day cancellation. Every payment has an 8-step event trail stored in payment_events (or equivalent). Cancellation must append two events: (1) CANCEL_INITIATED — recorded when cancel request is accepted (before scheme call), (2) CANCEL_CONFIRMED — recorded after status is set to CANCELLED. Fields per event row: payment_id, event_type, actor (partner_id for API cancel), timestamp (UTC), metadata (JSON: reason, cancel_reason_detail if present). These events are immutable once written. | • Identify the payment_events table and its insert method in the existing codebase • In CancelPaymentUseCase, before calling the scheme adapter, insert event CANCEL_INITIATED with actor=partnerId and metadata={reason: request.reason} • After the @Transactional commit, insert event CANCEL_CONFIRMED with actor=partnerId and metadata={cancelled_at, prefund_returned_usd} • Ensure both inserts use the same payment_id UUID • Do not delete or update existing payment events — append only | CancelPaymentUseCase updated to write CANCEL_INITIATED and CANCEL_CONFIRMED events to the payment_events table | • After a successful cancel, payment_events for the payment contains exactly one CANCEL_INITIATED and one CANCEL_CONFIRMED row • CANCEL_INITIATED timestamp is earlier than CANCEL_CONFIRMED timestamp • actor field on both events equals the calling partner_id • metadata on CANCEL_INITIATED includes the reason value from the request • Attempting to DELETE a payment_event row via direct SQL returns success (no DB-level guard needed here), but no application code path ever deletes events | 30 | 5.6-T09 | BE | API-05
5.6-T13 | payment-executor | 5.6 | 5. Transaction Processing (MPM/CPM) | Same-day cancellation | 1 | Unit tests: SameDayWindowService boundary cases | WBS 5.6 Same-day cancellation. SameDayWindowService.isWithinSameDayWindow(Instant createdAt) uses a Clock bean and compares calendar dates in Asia/Seoul (UTC+9). Critical boundaries: midnight KST transitions (KST midnight = 15:00 UTC previous day), and the transition from one day to the next. | • Create src/test/java/com/gmepayplus/cancel/SameDayWindowServiceTest.java • Use a fixed Clock for each test case • Test 1: createdAt=2026-06-04T14:59:59Z, clock=2026-06-04T14:59:59Z; KST dates both 2026-06-04 23:59:59 -> true • Test 2: createdAt=2026-06-04T14:59:59Z, clock=2026-06-04T15:00:00Z; createdAt KST=2026-06-04, clock KST=2026-06-05 00:00 -> false (day boundary crossed) • Test 3: createdAt=2026-06-03T15:00:00Z (KST 2026-06-04 00:00), clock=2026-06-04T14:59:59Z (KST 2026-06-04 23:59:59) -> true (same KST day) • Test 4: createdAt=2026-06-04T00:00:00Z (KST 2026-06-04 09:00), clock=2026-06-05T00:00:00Z (KST 2026-06-05 09:00) -> false • Test 5: createdAt=now (same instant as clock) -> true | SameDayWindowServiceTest.java with 5 parameterized or individual test cases, all green | • All 5 test cases pass • Test 2 specifically validates the KST midnight boundary at 15:00 UTC • No test uses System.currentTimeMillis() — all use fixed Clock • Test class has zero Spring context load (plain unit test, fast) • Coverage of SameDayWindowService.isWithinSameDayWindow reaches 100% | 30 | 5.6-T05 | BE | API-05
5.6-T14 | payment-executor | 5.6 | 5. Transaction Processing (MPM/CPM) | Same-day cancellation | 1 | Unit tests: CancelEligibilityService all status and window combinations | WBS 5.6 Same-day cancellation. CancelEligibilityService.check(Payment) returns ELIGIBLE, ALREADY_TERMINAL, or CANCEL_NOT_PERMITTED. Cancellable statuses: APPROVED, PENDING. Terminal statuses: FAILED, CANCELLED, REFUNDED. Window check delegates to SameDayWindowService (mock it). Edge case: status=APPROVED but window closed -> CANCEL_NOT_PERMITTED. | • Create src/test/java/com/gmepayplus/cancel/CancelEligibilityServiceTest.java • Mock SameDayWindowService • Test APPROVED + window open -> ELIGIBLE • Test APPROVED + window closed -> CANCEL_NOT_PERMITTED • Test PENDING + window open -> ELIGIBLE • Test CANCELLED (any window) -> ALREADY_TERMINAL • Test FAILED (any window) -> ALREADY_TERMINAL • Test REFUNDED (any window) -> ALREADY_TERMINAL | CancelEligibilityServiceTest.java with 7 test cases, all green | • All 7 test cases pass • ALREADY_TERMINAL result never calls SameDayWindowService (verify mock is not invoked for terminal statuses) • CANCEL_NOT_PERMITTED is returned only when status is valid but window is closed — not for terminal statuses • Test class loads no Spring context • All enum values of CancelEligibilityResult appear in at least one test assertion | 30 | 5.6-T06, 5.6-T13 | BE | API-05
5.6-T15 | payment-executor | 5.6 | 5. Transaction Processing (MPM/CPM) | Same-day cancellation | 1 | Unit tests: CancelPaymentUseCase orchestration — happy path and error paths | WBS 5.6 Same-day cancellation. CancelPaymentUseCase.execute() orchestrates eligibility check, scheme cancel, prefund reversal, and status update. Mock all collaborators. Key vectors: (A) OVERSEAS APPROVED same-day payment — full happy path; (B) LOCAL PENDING same-day — no scheme call, no prefund reversal; (C) wrong partner_id — PaymentNotFoundException; (D) CANCELLED payment — 409-throwing exception; (E) APPROVED but next-day KST — CANCEL_NOT_PERMITTED exception. | • Create src/test/java/com/gmepayplus/cancel/CancelPaymentUseCaseTest.java • Mock PaymentRepository, CancelEligibilityService, ZeroPayCancelAdapter, PrefundingReversalService • Vector A: eligibility=ELIGIBLE, partnerType=OVERSEAS, schemeTxnRef='ZP123' -> verifySchemeCancel called, reversal called, status=CANCELLED, prefund_reversal_usd=35.77 • Vector B: eligibility=ELIGIBLE, partnerType=LOCAL, schemeTxnRef=null -> verifySchemeCancel NOT called, reversal returns 0, prefund_reversal_usd=null in response • Vector C: PaymentRepository returns empty for payment not belonging to partner -> PaymentNotFoundException thrown, no other service called • Vector D: eligibility=ALREADY_TERMINAL -> appropriate exception thrown before any scheme call • Vector E: eligibility=CANCEL_NOT_PERMITTED -> CancelNotPermittedException thrown before scheme call | CancelPaymentUseCaseTest.java with 5 test vectors, all green | • Vector A: ZeroPayCancelAdapter.cancelPayment() is called with correct scheme_txn_ref • Vector B: ZeroPayCancelAdapter.cancelPayment() is never called (Mockito verify(adapter, never())) • Vector C: PaymentRepository is called once; no downstream services called • Vector D and E: Exception type matches the mapped HTTP status (409 and 400 respectively) • All mocks are verified — no unexpected interactions | 45 | 5.6-T09 | BE | API-05
5.6-T16 | payment-executor | 5.6 | 5. Transaction Processing (MPM/CPM) | Same-day cancellation | 1 | Unit tests: PrefundingReversalService — OVERSEAS balance restore and LOCAL skip | WBS 5.6 Same-day cancellation. PrefundingReversalService.reverse() must atomically restore collection_usd to OVERSEAS partner balance and insert a CANCEL_REVERSAL ledger row. For LOCAL partners it must be a no-op returning BigDecimal.ZERO. | • Create src/test/java/com/gmepayplus/cancel/PrefundingReversalServiceTest.java • Use an in-memory or H2 test DB with the prefunding_balances and prefunding_ledger tables • Test 1: OVERSEAS partner, initial balance 100.00 USD, collectionUsd=35.77 -> after reverse(), balance=135.77, ledger row type=CANCEL_REVERSAL, amount=35.77 • Test 2: LOCAL partner, any balance -> reverse() returns 0.00, no ledger row inserted, balance unchanged • Test 3: OVERSEAS partner, verify the SELECT FOR UPDATE is used (check @Transactional and that a second concurrent call cannot read an intermediate state — simulate with two threads if feasible, or verify annotation is present) | PrefundingReversalServiceTest.java with 3 test cases, all green | • Test 1: balance after reversal equals 100.00 + 35.77 = 135.77 exactly (BigDecimal comparison, no floating point) • Test 1: ledger row exists with type=CANCEL_REVERSAL, amount_usd=35.77, payment_id correct • Test 2: no ledger row is inserted for LOCAL partner • Test 2: return value is exactly BigDecimal.ZERO • @Transactional annotation is present on the reverse() method | 40 | 5.6-T07 | BE | API-05
5.6-T17 | payment-executor | 5.6 | 5. Transaction Processing (MPM/CPM) | Same-day cancellation | 1 | Integration test: full cancel flow — OVERSEAS approved payment | WBS 5.6 Same-day cancellation. End-to-end integration test in a Spring Boot test slice with a real H2/PostgreSQL test DB and a WireMock stub for the ZeroPay cancel API. Scenario RF-001 from the test spec: POST /v1/payments/{id}/cancel for an OVERSEAS partner same-day APPROVED payment. Expected: HTTP 200, status=CANCELLED in DB, prefunding balance restored, webhook_outbox row inserted, payment_events has CANCEL_CONFIRMED. | • Create src/test/java/com/gmepayplus/cancel/CancelPaymentIntegrationTest.java with @SpringBootTest • Seed DB: OVERSEAS partner, prefunding balance=100.00, approved payment with collection_usd=35.77, created_at=today UTC, status=APPROVED • Stub WireMock for ZeroPay cancel endpoint returning 200 • POST /v1/payments/{payment_id}/cancel with body {reason:'customer_request'} and valid Idempotency-Key header • Assert HTTP 200 and response body: status='cancelled', cancelled_at not null, prefund_returned_usd='35.77' • Assert DB: payment.status=CANCELLED, payment.cancelled_at set, payment.prefund_reversal_usd=35.77 • Assert prefunding_balances.balance_usd=135.77 • Assert webhook_outbox has one row with event_type=payment.cancelled • Assert payment_events has CANCEL_INITIATED and CANCEL_CONFIRMED rows | CancelPaymentIntegrationTest.java — integration test covering RF-001, all assertions green | • HTTP 200 response with correct JSON body • DB payment.status=CANCELLED and prefund_reversal_usd=35.77 after call • Prefunding balance increased from 100.00 to 135.77 • WireMock verifies ZeroPay cancel endpoint was called exactly once • payment_events table has both CANCEL_INITIATED and CANCEL_CONFIRMED rows for the payment | 55 | 5.6-T10, 5.6-T11, 5.6-T12 | BE | API-05
5.6-T18 | payment-executor | 5.6 | 5. Transaction Processing (MPM/CPM) | Same-day cancellation | 1 | Integration test: cancel rejected — payment from wrong partner returns 404 | WBS 5.6 Same-day cancellation. Security invariant: a partner must not be able to cancel another partner's payment. POST /v1/payments/{id}/cancel where the payment belongs to partner B but the caller authenticates as partner A must return 404 (not 403, to avoid leaking existence). No DB mutation should occur. | • Extend or create CancelPaymentSecurityTest.java • Seed DB: payment owned by partner_id=prt_B in APPROVED status, created today • Authenticate as partner_id=prt_A • POST /v1/payments/{payment_id}/cancel • Assert HTTP 404 with error code PAYMENT_NOT_FOUND • Assert payment status in DB is still APPROVED • Assert no prefunding change for either partner • Assert no webhook_outbox row inserted | Test method in CancelPaymentSecurityTest.java (or appended to CancelPaymentIntegrationTest.java) confirming cross-partner isolation | • Response is HTTP 404 (not 403) • Error code in response body is PAYMENT_NOT_FOUND • payment.status remains APPROVED in DB after the rejected call • No CANCEL_INITIATED event row in payment_events • No prefunding ledger entry created | 30 | 5.6-T17 | BE | API-05
5.6-T19 | payment-executor | 5.6 | 5. Transaction Processing (MPM/CPM) | Same-day cancellation | 1 | Integration test: cancel rejected — CANCEL_NOT_PERMITTED when window closed (next-day KST) | WBS 5.6 Same-day cancellation. Scenario RF-004 from the test spec: attempting to cancel a payment whose created_at is a prior KST calendar day must return HTTP 400 with error code CANCEL_NOT_PERMITTED. Use a fixed Clock bean in the test context to simulate current time being the next KST day. | • Create or extend test class with a @TestConfiguration providing a fixed Clock set to 2026-06-05T15:00:00Z (KST 2026-06-06 00:00) • Seed DB: OVERSEAS partner, APPROVED payment with created_at=2026-06-04T10:00:00Z (KST 2026-06-04 19:00 — prior day) • POST /v1/payments/{payment_id}/cancel with valid headers • Assert HTTP 400 • Assert error code is CANCEL_NOT_PERMITTED • Assert payment status is still APPROVED in DB • Assert no ZeroPay API call was made (WireMock verify 0 calls) • Assert no prefunding change | Test method confirming window-closed rejection with a fixed Clock, all assertions green | • HTTP 400 returned • Error code CANCEL_NOT_PERMITTED in response body • Payment DB status unchanged (APPROVED) • ZeroPay WireMock receives zero cancel requests • Prefunding balance unchanged | 35 | 5.6-T17 | BE | API-05
5.6-T20 | payment-executor | 5.6 | 5. Transaction Processing (MPM/CPM) | Same-day cancellation | 1 | Integration test: idempotency — duplicate cancel request returns same response | WBS 5.6 Same-day cancellation. The Idempotency-Key cache for POST /v1/payments/{id}/cancel stores (partner_id, idempotency_key, response_body, http_status) for 24 hours. A duplicate request with the same Idempotency-Key must return the original 200 response without re-executing the use case. Verify the use case is invoked only once (not twice) by checking that the ZeroPay cancel stub is called exactly once. | • Seed DB: APPROVED OVERSEAS payment, created today, prefunding balance 100.00 • POST /v1/payments/{id}/cancel with Idempotency-Key: idem-key-001 -> assert HTTP 200 • POST /v1/payments/{id}/cancel again with same Idempotency-Key: idem-key-001 -> assert HTTP 200 with identical response body • Assert prefunding balance is 135.77 (not 171.54 — reversal not applied twice) • Assert ZeroPay WireMock cancel endpoint called exactly once (not twice) • Assert only one CANCEL_CONFIRMED row in payment_events | Test method confirming idempotent cancel duplicate handling, all assertions green | • Both responses return HTTP 200 with identical JSON body • Prefunding balance is exactly 135.77 after both calls (not double-reversed) • ZeroPay cancel API called exactly once (WireMock.verify(1, ...)) • payment_events has exactly one CANCEL_INITIATED row and one CANCEL_CONFIRMED row • Second POST returns X-Idempotency-Status header or equivalent indicating cache hit | 35 | 5.6-T17 | BE | API-05
5.6-T21 | payment-executor | 5.6 | 5. Transaction Processing (MPM/CPM) | Same-day cancellation | 1 | Integration test: cancel of already-cancelled payment returns 409 | WBS 5.6 Same-day cancellation. A payment already in CANCELLED status is a terminal state. POST /v1/payments/{id}/cancel on such a payment must return HTTP 409. This ensures partners retrying after a successful cancel receive a clear signal rather than a 500 or a double-cancel. | • Seed DB: payment in CANCELLED status, created today • POST /v1/payments/{id}/cancel • Assert HTTP 409 • Assert error code maps to PAYMENT_ALREADY_CANCELLED or similar (confirm the exact code from the error catalog) • Assert no ZeroPay API call • Assert no prefunding change • Assert no new payment_events rows for this payment | Test method confirming 409 on already-cancelled payment | • HTTP 409 returned • Error response body contains a machine-readable error code • No ZeroPay WireMock requests recorded • No new payment_events rows added beyond the existing CANCEL_CONFIRMED • No prefunding ledger entry added | 25 | 5.6-T17 | BE | API-05
5.6-T22 | payment-executor | 5.6 | 5. Transaction Processing (MPM/CPM) | Same-day cancellation | 1 | Integration test: LOCAL partner cancel — no prefunding reversal, no prefund_returned_usd in response | WBS 5.6 Same-day cancellation. LOCAL partners (e.g. GME Remit, partner_type=LOCAL) have no prefunding. Cancelling a LOCAL partner payment must: set status=CANCELLED, skip any prefunding call, and omit prefund_returned_usd from the response body (field must be absent, not null). | • Seed DB: LOCAL partner (partner_type=LOCAL), APPROVED payment created today, no prefunding_balances row • POST /v1/payments/{id}/cancel with body {reason:'merchant_request'} • Assert HTTP 200 • Assert response JSON does not contain prefund_returned_usd key • Assert payment.status=CANCELLED in DB • Assert payment.prefund_reversal_usd is NULL in DB • Assert no prefunding_ledger row inserted | Test method confirming LOCAL partner cancel behaviour, all assertions green | • HTTP 200 returned • prefund_returned_usd is absent from the JSON response (not present even as null) • payment.prefund_reversal_usd is NULL in DB • No prefunding_ledger row with type=CANCEL_REVERSAL exists for this payment • payment.status=CANCELLED in DB | 30 | 5.6-T17 | BE | API-05
5.6-T23 | payment-executor | 5.6 | 5. Transaction Processing (MPM/CPM) | Same-day cancellation | 1 | OpenAPI spec: add /v1/payments/{id}/cancel path to partner-api.yaml | WBS 5.6 Same-day cancellation. The ground truth API contract is openapi/partner-api.yaml (API-05). The cancel endpoint must be declared: POST /v1/payments/{id}/cancel with CancelRequest schema (reason enum, reason_detail), 200 response (payment_id, status: cancelled, cancelled_at, prefund_returned_usd), 400/404/409 responses referencing shared error schemas, and required Idempotency-Key header. The CancelRequest and cancel 200 response should be named schemas under #/components/schemas. | • Open openapi/partner-api.yaml • Under paths, add /v1/payments/{id}/cancel with POST operation operationId: cancelPayment • Add parameters: path param id, $ref to shared IdempotencyKey, XTimestamp, XSignature headers • Add requestBody referencing CancelRequest schema • Add CancelRequest schema under #/components/schemas: reason (enum string, required), reason_detail (string, maxLength 200, nullable) • Add 200 response schema with required fields payment_id, status (const: cancelled), cancelled_at; optional prefund_returned_usd • Reference existing 400/404/409 response schemas • Run a YAML lint / openapi-generator validate to confirm schema is valid | openapi/partner-api.yaml updated with cancelPayment operation and CancelRequest schema, passing openapi-generator validate | • openapi-generator validate --input-spec openapi/partner-api.yaml exits 0 • CancelRequest.reason is declared as enum with exactly 4 values: customer_request, merchant_request, timeout, other • 200 response schema declares prefund_returned_usd as optional (not required) • Path /v1/payments/{id}/cancel POST is present and passes contract tests in CI • All $ref references in the new section resolve correctly (no dangling refs) | 40 | 5.6-T04 | BE | API-05
5.6-T24 | payment-executor | 5.6 | 5. Transaction Processing (MPM/CPM) | Same-day cancellation | 1 | Contract test: verify /v1/payments/{id}/cancel against openapi/partner-api.yaml | WBS 5.6 Same-day cancellation. All endpoints in openapi/partner-api.yaml must have contract test coverage. Using the existing contract-test framework (Dredd, schemathesis, or Pact as configured in the project), add test coverage for POST /v1/payments/{id}/cancel: happy path (same-day -> 200), post-settlement (422/400), and missing idempotency key (400). Contract tests run against a running test server with seeded data. | • Locate the existing contract test configuration file (dredd.yml, schemathesis config, or equivalent) • Add a test transaction or hook for the cancel happy-path: APPROVED payment same-day -> assert 200 response matches schema • Add a test for CANCEL_NOT_PERMITTED: prior-day payment -> assert 400 with CANCEL_NOT_PERMITTED error code • Add a test for missing Idempotency-Key -> assert 400 with MISSING_IDEMPOTENCY_KEY error code • Add a test for already-CANCELLED payment -> assert 409 • Run the contract test suite and confirm all 4 new cases pass | Contract test coverage for cancelPayment operation added to the existing test suite, 4 test cases green | • Same-day cancel returns 200 and response body matches the CancelResponse schema in openapi/partner-api.yaml • CANCEL_NOT_PERMITTED case returns 400 with error code CANCEL_NOT_PERMITTED • Missing Idempotency-Key returns 400 with code MISSING_IDEMPOTENCY_KEY • Already-cancelled returns 409 • All 4 new contract tests run in CI without requiring manual intervention | 45 | 5.6-T23, 5.6-T10 | BE | API-05
5.6-T25 | payment-executor | 5.6 | 5. Transaction Processing (MPM/CPM) | Same-day cancellation | 1 | Add cancel fields to transaction detail view in Admin System (read-only display) | WBS 5.6 Same-day cancellation. The Admin System transaction detail view (PRD-07 section 8.5) must show cancellation metadata for CANCELLED transactions: Cancellation Reason, Cancellation Reason Detail (if present), Cancelled At (UTC and KST), Prefund Returned USD (OVERSEAS only). These fields are read-only. Non-cancelled transactions show these fields as blank/absent. The data is fetched from the existing transaction detail API endpoint — update that endpoint to include cancel fields. | • Add cancel fields to the GET /v1/admin/transactions/{id} response DTO: cancel_reason, cancel_reason_detail, cancelled_at, prefund_reversal_usd • Map the new DB columns (from T01/T02) to the DTO in the transaction query service • In the Admin frontend transaction detail component, add a Cancellation section visible only when status=CANCELLED • Display: Reason (formatted enum label), Detail, Cancelled At (UTC + KST display), Prefund Returned USD (omit row for LOCAL partners) • Confirm no cancel fields appear on the detail view for APPROVED or FAILED transactions | Updated transaction detail API response DTO and Admin frontend component showing cancel metadata for CANCELLED payments | • GET /v1/admin/transactions/{id} for a CANCELLED OVERSEAS payment returns cancel_reason, cancelled_at, prefund_reversal_usd in response • GET /v1/admin/transactions/{id} for an APPROVED payment returns null/absent cancel_reason and cancelled_at • Admin UI transaction detail for a CANCELLED payment shows Cancellation section with formatted reason label and KST timestamp • Admin UI transaction detail for an APPROVED payment has no Cancellation section visible • OVERSEAS CANCELLED transaction shows Prefund Returned USD row; LOCAL CANCELLED transaction does not | 45 | 5.6-T01, 5.6-T02 | BE | API-05
5.6-T26 | payment-executor | 5.6 | 5. Transaction Processing (MPM/CPM) | Same-day cancellation | 1 | Document cancel flow in partner-facing API reference (inline OpenAPI descriptions) | WBS 5.6 Same-day cancellation. The OpenAPI spec is the primary partner documentation. Ensure all inline descriptions in the cancel operation are complete and accurate: operation summary and description must state the same-day KST restriction, the admin-only refund note (Phase 1), and the idempotency requirement. The CancelRequest.reason enum values must have individual descriptions. Error code CANCEL_NOT_PERMITTED must appear in the error catalog section. | • In openapi/partner-api.yaml, expand the description of the cancelPayment operation to include: same calendar day KST restriction, Phase 1 note (refunds are admin-only), idempotency requirement • Add x-enum-descriptions or description on each enum value of CancelRequest.reason: customer_request, merchant_request, timeout, other • Verify CANCEL_NOT_PERMITTED is listed in the error codes section of the spec with HTTP 400 and retryable=false • Run openapi-generator validate to confirm no schema breaks • Review rendered Swagger/Redoc output to confirm descriptions appear correctly for the cancel endpoint | openapi/partner-api.yaml cancel operation with complete inline documentation and CANCEL_NOT_PERMITTED in error catalog | • cancelPayment operation description mentions same calendar day KST and admin-only refunds • Each of the 4 reason enum values has a non-empty description in the spec • CANCEL_NOT_PERMITTED appears in the error code table with HTTP 400 and retryable=false • openapi-generator validate exits 0 after edits • Rendered spec (e.g. Swagger UI) shows the cancel endpoint with full description visible | 30 | 5.6-T23 | BE | API-05
5.7-T01 | transaction-mgmt | 5.7 | 5. Transaction Processing (MPM/CPM) | Idempotency & request dedup | 1 | Create idempotency_record Redis key schema and TTL constants | GMEPay+ deduplicates all POST requests by storing (partner_id, idempotency_key) -> (response_status, response_body) in Redis for 24 hours (86400 s). Keys must be 16-128 chars (UUID v4 recommended). Redis key pattern: idem:{partner_id}:{idempotency_key}. An in-flight lock key is also needed: idem_lock:{partner_id}:{idempotency_key} with short TTL (e.g. 30 s) to detect concurrent duplicate requests and return HTTP 409 with X-Idempotency-Status: in_flight. | • Define Java constants class IdempotencyConstants: KEY_PREFIX = "idem", LOCK_PREFIX = "idem_lock", TTL_SECONDS = 86400, LOCK_TTL_SECONDS = 30, MIN_KEY_LENGTH = 16, MAX_KEY_LENGTH = 128 • Define a record IdempotencyRecord { String idempotencyKey, String partnerId, int httpStatus, String responseBodyJson, Instant createdAt, Instant expiresAt } • Document Redis key format in a code comment: idem:{partnerId}:{idempotencyKey} -> JSON(IdempotencyRecord); idem_lock:{partnerId}:{idempotencyKey} -> 1 • Write unit test asserting TTL_SECONDS == 86400 and LOCK_TTL_SECONDS <= 60 | IdempotencyConstants.java and IdempotencyRecord.java in the idempotency package | • TTL_SECONDS constant equals 86400 • MIN_KEY_LENGTH = 16, MAX_KEY_LENGTH = 128 match API-05 §7.1 constraints • Redis key format encodes both partner_id and idempotency_key so keys from different partners never collide • IdempotencyRecord carries httpStatus (int) and responseBodyJson (String) sufficient to replay any stored response | 25 |  | BE | API-05
5.7-T02 | transaction-mgmt | 5.7 | 5. Transaction Processing (MPM/CPM) | Idempotency & request dedup | 1 | Create IdempotencyRepository: Redis read/write/lock operations | The idempotency service needs three Redis operations: (1) SET NX PX <lock_ttl_ms> on the lock key to acquire an in-flight lock atomically; (2) GET on the result key to check for a completed stored response; (3) SET EX <86400> on the result key to persist the completed response. Uses Redis SETNX semantics via Spring Data Redis or Lettuce. Key format: idem:{partnerId}:{idempotencyKey} for results, idem_lock:{partnerId}:{idempotencyKey} for in-flight locks. | • Create IdempotencyRepository interface with methods: Optional<IdempotencyRecord> findCompleted(String partnerId, String key); boolean acquireLock(String partnerId, String key); void saveCompleted(String partnerId, String key, int httpStatus, String responseBody); void releaseLock(String partnerId, String key) • Implement using RedisTemplate<String,String>: acquireLock uses SET idem_lock:{p}:{k} 1 NX PX 30000; findCompleted uses GET idem:{p}:{k} then deserializes JSON; saveCompleted uses SET idem:{p}:{k} <json> EX 86400; releaseLock does DEL on lock key • Serialize IdempotencyRecord to/from JSON using Jackson ObjectMapper • Add integration test against embedded Redis: store a record with status 201 and body '{"id":"pay_001"}', retrieve it, verify status and body match exactly | IdempotencyRepository.java interface + RedisIdempotencyRepository.java implementation | • acquireLock returns true on first call for a given (partnerId, key) pair and false on second concurrent call (NX semantics) • saveCompleted followed by findCompleted returns the exact same httpStatus and responseBodyJson • TTL on the result key is set to 86400 s (verify via Redis TTL command in integration test) • Lock key TTL is 30 s; lock auto-expires if releaseLock is never called (crash safety) • Keys from partnerId=p1 and partnerId=p2 with identical idempotency_key values do not collide | 45 | 5.7-T01 | BE | API-05
5.7-T03 | transaction-mgmt | 5.7 | 5. Transaction Processing (MPM/CPM) | Idempotency & request dedup | 1 | Create IdempotencyService: lookup-or-lock core logic | The idempotency service orchestrates the three-state decision before any POST handler runs: (1) if a completed record exists -> return stored response immediately; (2) if in-flight lock cannot be acquired -> return HTTP 409 with header X-Idempotency-Status: in_flight; (3) otherwise -> proceed with processing, then persist the response on completion. Stored responses include 4xx results (a validation failure on the first call is stored and replayed). Body hash must match: if body differs from what was stored at lock time, return HTTP 422 IDEMPOTENCY_KEY_REUSE. | • Create IdempotencyService with method IdempotencyDecision check(String partnerId, String idempotencyKey, String requestBodyHash) • IdempotencyDecision is a sealed interface with variants: Replay(int status, String body), InFlight(), Proceed() • In check(): first call findCompleted; if present and bodyHash matches -> Replay; if present and bodyHash differs -> throw IdempotencyKeyReuseException; if absent, call acquireLock; if lock fails -> InFlight; else store bodyHash alongside lock key and return Proceed • Add method void complete(String partnerId, String idempotencyKey, int status, String responseBody) to persist result and release lock • Store requestBodyHash in the lock value (not a separate key) so body-mismatch can be detected on replay without re-hashing the stored body | IdempotencyService.java with inner sealed interface IdempotencyDecision | • First call with key K returns Proceed • Second call with same key K and same body hash while first is in flight returns InFlight • Second call after first completes returns Replay with original status and body • Call with same key K but different body hash after completion throws IdempotencyKeyReuseException (maps to HTTP 422 IDEMPOTENCY_KEY_REUSE) • A 4xx response stored by complete() is replayed on subsequent calls (validation failures are idempotent) | 50 | 5.7-T02 | BE | API-05
5.7-T04 | transaction-mgmt | 5.7 | 5. Transaction Processing (MPM/CPM) | Idempotency & request dedup | 1 | Implement request body SHA-256 hashing for idempotency comparison | To detect body mismatches (IDEMPOTENCY_KEY_REUSE), GMEPay+ hashes the raw request body bytes with SHA-256 and stores the hex digest alongside the idempotency lock entry. The hash must be computed from the raw byte stream before JSON deserialization so that equivalent JSON with different whitespace or key ordering is treated consistently. The hashing component is shared by the idempotency filter and the IdempotencyService. | • Create RequestBodyHasher utility class with static method String sha256Hex(byte[] body) using java.security.MessageDigest • Create CachingRequestWrapper extending HttpServletRequestWrapper that buffers the request body so it can be read multiple times • Ensure sha256Hex of the same logical payload with and without trailing whitespace produces different hashes (raw bytes, not parsed JSON) -- this is intentional and documented • Add unit tests: sha256Hex("hello".getBytes()) == expected SHA-256 hex; different inputs produce different digests; empty body produces SHA-256 of empty string (not null) | RequestBodyHasher.java and CachingRequestWrapper.java in the idempotency package | • sha256Hex produces a 64-char lowercase hex string • sha256Hex({}) != sha256Hex({ }) (different byte content -> different hash, even if semantically equivalent JSON) • CachingRequestWrapper.getInputStream() can be called twice and returns the same bytes both times • sha256Hex(null_or_empty_body) returns the SHA-256 of an empty byte array without NPE | 30 | 5.7-T01 | BE | API-05
5.7-T05 | transaction-mgmt | 5.7 | 5. Transaction Processing (MPM/CPM) | Idempotency & request dedup | 1 | Implement IdempotencyFilter: per-request interception for all POST endpoints | A Spring OncePerRequestFilter intercepts every incoming POST request before it reaches any handler. It: (1) reads the Idempotency-Key header; (2) if missing, short-circuits with HTTP 400 error code MISSING_IDEMPOTENCY_KEY; (3) validates key length (16-128 chars); (4) computes SHA-256 body hash using CachingRequestWrapper; (5) calls IdempotencyService.check(); (6) on Replay, writes the stored response directly and bypasses the filter chain; (7) on InFlight, returns HTTP 409 with X-Idempotency-Status: in_flight; (8) on Proceed, continues filter chain and calls IdempotencyService.complete() after response is written. | • Create IdempotencyFilter extends OncePerRequestFilter, inject IdempotencyService and ObjectMapper • Wrap request with CachingRequestWrapper before reading body • Check Idempotency-Key header present; if absent return 400 JSON {error_code: MISSING_IDEMPOTENCY_KEY} • Validate key length 16-128; if invalid return 400 VALIDATION_ERROR • Call IdempotencyService.check(); branch on Replay/InFlight/Proceed • For Replay: copy stored httpStatus and responseBodyJson to HttpServletResponse; add header X-Idempotency-Status: replayed; skip filter chain • For InFlight: return 409 with X-Idempotency-Status: in_flight • For Proceed: wrap HttpServletResponse with a response-capturing wrapper; pass to chain; after chain completes call idempotencyService.complete() with captured status and body • Register filter at order before AuthenticationFilter to ensure idempotency check happens early but after auth (adjust order if auth must run first) | IdempotencyFilter.java registered as a Spring @Component with @Order | • POST without Idempotency-Key header returns HTTP 400, error_code MISSING_IDEMPOTENCY_KEY • POST with key length 15 returns HTTP 400 VALIDATION_ERROR; key length 128 is accepted • POST with same key and same body after completion returns stored status and body with header X-Idempotency-Status: replayed • POST with same key and different body returns HTTP 422 IDEMPOTENCY_KEY_REUSE • Concurrent identical POST requests: one returns the real response, the other returns HTTP 409 X-Idempotency-Status: in_flight | 55 | 5.7-T03, 5.7-T04 | BE | API-05
5.7-T06 | transaction-mgmt | 5.7 | 5. Transaction Processing (MPM/CPM) | Idempotency & request dedup | 1 | Validate Idempotency-Key format: UUID detection and length enforcement | API-05 §7.1 states the key must be 16-128 characters, UUID v4 is recommended but not required. The validation layer must reject keys outside the 16-128 char range with HTTP 400 VALIDATION_ERROR. UUID format is not strictly enforced (any random string of valid length is accepted). However, keys that contain null bytes or characters outside printable ASCII (0x20-0x7E) must be rejected to prevent Redis key injection. This is part of the IdempotencyFilter validation step. | • Add validateKey(String key) method to IdempotencyFilter or a separate IdempotencyKeyValidator class • Reject if key is null or blank -> MISSING_IDEMPOTENCY_KEY • Reject if length < 16 or > 128 -> VALIDATION_ERROR with detail field_name=Idempotency-Key, constraint=length_16_to_128 • Reject if any character is outside printable ASCII (char < 0x20 or char > 0x7E) -> VALIDATION_ERROR with detail=invalid_characters • Add unit tests covering: null, empty string, 15-char, 16-char (accept), 128-char (accept), 129-char, valid UUID v4, string with tab character (reject) | IdempotencyKeyValidator.java (or method in IdempotencyFilter) with full unit-test coverage | • Key of exactly 16 printable ASCII chars passes validation • Key of 129 chars returns HTTP 400 VALIDATION_ERROR • Key containing char 0x09 (tab) returns HTTP 400 VALIDATION_ERROR • Valid UUID v4 '7b1e3f2a-89cd-4d02-9f3b-0a1c2d3e4f56' (36 chars) passes validation • Null key returns HTTP 400 MISSING_IDEMPOTENCY_KEY, not VALIDATION_ERROR | 30 | 5.7-T05 | BE | API-05
5.7-T07 | transaction-mgmt | 5.7 | 5. Transaction Processing (MPM/CPM) | Idempotency & request dedup | 1 | Implement response-capturing wrapper for IdempotencyFilter post-processing | After the filter chain processes a Proceed request, IdempotencyFilter must capture the response status code and body to persist in Redis. A standard HttpServletResponse does not support re-reading the body after it is written. A ContentCachingResponseWrapper (Spring's built-in) or custom ResponseCapturingWrapper must buffer the output stream so the filter can read the body bytes and call IdempotencyService.complete() before flushing to the actual client. | • Use Spring's ContentCachingResponseWrapper to wrap the HttpServletResponse passed to the filter chain • After chain.doFilter() returns, read the captured body via getContentAsByteArray() • Convert body bytes to UTF-8 string; call idempotencyService.complete(partnerId, idempotencyKey, response.getStatus(), bodyString) • Call copyBodyToResponse() to flush the buffered body to the actual client • Handle edge case: if response is a streaming response or body is empty (e.g. 204 No Content), store empty string as responseBodyJson • Add unit test: mock filter chain that writes JSON body; verify IdempotencyService.complete() is called with correct status and body string | Updated IdempotencyFilter.java using ContentCachingResponseWrapper with complete() hook | • After a successful POST /v1/payments (201), the captured body stored in Redis matches the exact JSON returned to the client • A 422 validation error response is also captured and stored (4xx responses are idempotent) • 204 No Content response stores empty string body without error • ContentCachingResponseWrapper.copyBodyToResponse() is called so the client receives the actual response, not an empty body • idempotencyService.complete() is called exactly once per Proceed request regardless of whether the handler throws or returns normally | 40 | 5.7-T05 | BE | API-05
5.7-T08 | transaction-mgmt | 5.7 | 5. Transaction Processing (MPM/CPM) | Idempotency & request dedup | 1 | Handle in-flight lock expiry and crash recovery on lock release | If a service instance crashes after acquiring the in-flight lock (idem_lock:{p}:{k}) but before calling releaseLock(), the lock must auto-expire so subsequent retries are not permanently blocked. The lock TTL is 30 s. However, if normal processing takes longer than 30 s (e.g. slow scheme call), the lock may expire before complete() is called, causing a duplicate to slip through. The service must handle: (a) lock expiry during processing by detecting that saveCompleted() overwrites correctly, and (b) the rare case where two requests both pass acquireLock (first lock expired, second acquired), by using a Redis SET NX EX on the result key so only one write wins. | • Ensure saveCompleted() uses SET idem:{p}:{k} <json> EX 86400 NX=false (allow overwrite, last writer wins for result) -- this is safe because both concurrent requests computed the same business outcome for identical bodies • Add a warning log when complete() is called and a completed record already exists (indicates lock expired mid-flight) • Add unit test: simulate lock expiry by setting LOCK_TTL_SECONDS=1 in test config, sleep 2 s, then call complete() -- verify the result is still stored correctly • Document in code comment: for operations expected to exceed 30 s (e.g. scheme timeouts), the lock expiry is acceptable because the result key write is idempotent for identical bodies | Updated RedisIdempotencyRepository.java with overwrite-safe saveCompleted and a warning log path | • saveCompleted() called twice with same key and same body does not throw; second call is a no-op or overwrites with identical data • saveCompleted() called with same key but different body (crash + different outcome) logs a WARN and stores the second value (last-writer-wins; operator should investigate via audit log) • acquireLock with LOCK_TTL=1s; after 1.1 s, a second acquireLock on the same key returns true (lock auto-expired) • No permanent deadlock: after any scenario, subsequent requests with the same key either get Replay or Proceed within 35 s | 35 | 5.7-T02, 5.7-T03 | BE | API-05
5.7-T09 | transaction-mgmt | 5.7 | 5. Transaction Processing (MPM/CPM) | Idempotency & request dedup | 1 | Implement duplicate partner_txn_ref detection (DUPLICATE_PARTNER_TXN_REF) | API-05 error table defines error code DUPLICATE_PARTNER_TXN_REF (HTTP 409): partner_txn_ref already used for a different payment by this partner. This is distinct from idempotency: an idempotency retry with the same body is allowed; a new payment submission with a different idempotency key but a previously-used partner_txn_ref is rejected. The transaction table has a UNIQUE constraint on (partner_id, partner_txn_ref). The PaymentService must catch the unique-constraint violation and translate it to this error code. | • Confirm the transaction table has UNIQUE constraint on (partner_id, partner_txn_ref) -- if not, add a DB migration (reference 5.7-T10) • In PaymentService.createPayment(), catch DataIntegrityViolationException (Spring) or PSQLException with SQLState=23505 on the partner_txn_ref column • Map to ApiException(409, DUPLICATE_PARTNER_TXN_REF, 'partner_txn_ref already used for a different payment by this partner.') • Ensure the check is ONLY for genuinely new idempotency keys; idempotency replay with same body and same partner_txn_ref must not trigger this error (it returns the stored result before DB write) • Add unit test: create payment with partner_txn_ref='SENDMN-TXN-001'; attempt second payment with different idempotency_key and same partner_txn_ref='SENDMN-TXN-001'; expect HTTP 409 DUPLICATE_PARTNER_TXN_REF | Exception mapping in PaymentService.java for DUPLICATE_PARTNER_TXN_REF | • POST /v1/payments with idempotency_key=K1, partner_txn_ref=REF-001 succeeds (201) • POST /v1/payments with idempotency_key=K2 (new key), partner_txn_ref=REF-001 (same ref) returns HTTP 409 DUPLICATE_PARTNER_TXN_REF • POST /v1/payments with idempotency_key=K1 (same key), same body returns HTTP 2xx replay (idempotency, not duplicate error) • The error response body follows the standard error envelope: {error_code: DUPLICATE_PARTNER_TXN_REF, message: '...', txn_ref: null} • DataIntegrityViolationException on a different column (e.g. scheme_ref) does not map to DUPLICATE_PARTNER_TXN_REF | 35 | 5.7-T05 | BE | API-05
5.7-T10 | transaction-mgmt | 5.7 | 5. Transaction Processing (MPM/CPM) | Idempotency & request dedup | 1 | DB migration: UNIQUE constraint on (partner_id, partner_txn_ref) in transaction table | The transaction table must enforce uniqueness of partner_txn_ref per partner at the DB level (not just application level) to prevent race conditions under concurrent inserts. The migration adds a unique index on (partner_id, partner_txn_ref). partner_txn_ref is nullable (scheme-initiated payments may lack it), so the constraint must allow multiple NULL values -- use a partial index: WHERE partner_txn_ref IS NOT NULL. | • Create Flyway migration V57__add_unique_partner_txn_ref.sql • Add: CREATE UNIQUE INDEX IF NOT EXISTS uq_transaction_partner_txn_ref ON transaction(partner_id, partner_txn_ref) WHERE partner_txn_ref IS NOT NULL; • Verify the migration is idempotent (IF NOT EXISTS) so re-running does not fail • Run migration against local PostgreSQL 16 on port 5433 (as per project config) and confirm via psql \d transaction • Add a comment in the migration file explaining the partial index rationale (NULLs excluded to allow multiple scheme-only transactions) | Flyway migration file V57__add_unique_partner_txn_ref.sql | • Migration applies cleanly on a fresh schema with no existing data • Two rows with partner_id=1, partner_txn_ref='REF-001' cannot coexist (INSERT fails with unique violation) • Two rows with partner_id=1, partner_txn_ref=NULL can coexist (partial index allows multiple NULLs) • Two rows with partner_id=1 and partner_id=2 sharing partner_txn_ref='REF-001' can coexist (different partner scopes) • psql \d transaction shows the index uq_transaction_partner_txn_ref | 20 |  | BE | API-05
5.7-T11 | transaction-mgmt | 5.7 | 5. Transaction Processing (MPM/CPM) | Idempotency & request dedup | 1 | Implement GET endpoint idempotency bypass: filter must skip GET requests | API-05 states idempotency keys are required on POST requests that create or modify resources. GET endpoints (e.g. GET /v1/rates, GET /v1/payments/{id}) are inherently idempotent and must NOT require an Idempotency-Key header. The IdempotencyFilter must skip all non-POST methods. Additionally, health-check and actuator endpoints must be excluded. This ticket tightens the filter's shouldNotFilter() logic. | • Override shouldNotFilter(HttpServletRequest request) in IdempotencyFilter • Return true (skip) if request method is not POST • Return true (skip) if request URI matches /actuator/** or /health or /v1/rates (GET-only paths) • Add unit tests: verify filter skips GET /v1/payments/pay_001, OPTIONS /v1/payments, and /actuator/health; verify filter runs on POST /v1/payments and POST /v1/rates • Confirm that POST /v1/rates is included (rate quote endpoint is a POST in API-05 and requires idempotency) | Updated IdempotencyFilter.shouldNotFilter() method with unit tests | • GET /v1/payments/{id} with no Idempotency-Key header receives HTTP 200, not HTTP 400 • POST /v1/rates without Idempotency-Key header receives HTTP 400 MISSING_IDEMPOTENCY_KEY • POST /v1/payments without Idempotency-Key header receives HTTP 400 MISSING_IDEMPOTENCY_KEY • GET /actuator/health is never intercepted by IdempotencyFilter • OPTIONS /v1/payments (CORS preflight) is not intercepted | 25 | 5.7-T05 | BE | API-05
5.7-T12 | transaction-mgmt | 5.7 | 5. Transaction Processing (MPM/CPM) | Idempotency & request dedup | 1 | Implement X-Request-ID response header on all responses | API-05 §2.7 states every response (success or error) must include an X-Request-ID response header set by GMEPay+. This is the primary diagnostic key for support escalations. Partners must log this value. The request ID is generated server-side (not partner-supplied), uses the format req_{ULID} (e.g. req_01HX7MNPQRS4T5U6VWXY012Z), and is unrelated to idempotency keys. It is generated fresh for every HTTP transaction including idempotency replays. | • Create RequestIdFilter extends OncePerRequestFilter • Generate a ULID or UUID-based ID with prefix req_ on every request: String requestId = 'req_' + UlidCreator.getMonotonicUlid().toString() • Store requestId in request attribute and add to MDC for log correlation: MDC.put('requestId', requestId) • Add X-Request-ID: {requestId} header to every response including idempotency replays and error responses • Register filter at lowest order (runs first) so all subsequent filters and handlers can read the requestId from request attributes • Add unit test: any POST returns response with X-Request-ID header matching pattern req_[A-Z0-9]{26} | RequestIdFilter.java registered as a Spring @Component | • Every HTTP response (200, 201, 400, 409, 422, 500) includes X-Request-ID header • X-Request-ID value matches pattern req_[A-Za-z0-9]{20,30} • Each request generates a unique X-Request-ID (two concurrent requests have different IDs) • Idempotency replay responses also include a fresh X-Request-ID (not the original request's ID) • X-Request-ID appears in application logs via MDC for the same request | 30 |  | BE | API-05
5.7-T13 | transaction-mgmt | 5.7 | 5. Transaction Processing (MPM/CPM) | Idempotency & request dedup | 1 | Unit tests: idempotency happy-path and replay scenarios | Explicit unit-test ticket for IdempotencyService and IdempotencyFilter. All logic-bearing paths must be covered with concrete input/output vectors. Uses MockRedis (embedded Redis or Mockito mocks). Tests verify the full state machine: Proceed -> complete -> Replay; InFlight; body-mismatch; missing key; key length boundary. | • Create IdempotencyServiceTest with MockBean IdempotencyRepository • Test 1 (Proceed): partnerId=p1, key=K1, bodyHash=H1 -> check returns Proceed • Test 2 (complete + Replay): after complete(p1, K1, 201, '{"id":"pay_001"}'), check(p1, K1, H1) returns Replay{status=201, body='{"id":"pay_001"}'} • Test 3 (InFlight): acquireLock mocked to return false -> check returns InFlight • Test 4 (body mismatch): complete(p1, K1, 201, '...'); check(p1, K1, H2) where H2 != H1 -> throws IdempotencyKeyReuseException • Test 5 (4xx stored): complete(p1, K1, 422, '{"error_code":"RATE_QUOTE_EXPIRED"}'); check(p1, K1, H1) returns Replay{status=422} • Test 6 (missing key): IdempotencyFilter with no Idempotency-Key header returns MockMvc response status 400, error_code MISSING_IDEMPOTENCY_KEY • Test 7 (length boundary): key of 16 chars passes; key of 15 chars returns 400; key of 128 chars passes; key of 129 chars returns 400 | IdempotencyServiceTest.java and IdempotencyFilterTest.java with 7 test methods | • All 7 tests pass (mvn test -pl idempotency-module) • Test 2 verifies exact body string match: '{"id":"pay_001"}' • Test 4 throws IdempotencyKeyReuseException (not a generic exception) • Test 6 verifies response body contains error_code field equal to MISSING_IDEMPOTENCY_KEY • Test 7 boundary: key='1234567890123456' (16 chars) returns Proceed; key='123456789012345' (15 chars) returns HTTP 400 | 55 | 5.7-T03, 5.7-T05, 5.7-T06 | BE | API-05
5.7-T14 | transaction-mgmt | 5.7 | 5. Transaction Processing (MPM/CPM) | Idempotency & request dedup | 1 | Unit tests: concurrent in-flight deduplication under race conditions | The in-flight lock mechanism (Redis SET NX) must prevent double-processing when two requests with the same idempotency key arrive simultaneously. This test uses a CountDownLatch to simulate concurrent request handling and verifies that exactly one request proceeds and the other returns InFlight. Uses a real embedded Redis (Testcontainers Redis or spring-boot-testcontainers) to test actual NX semantics rather than mocks. | • Add Testcontainers Redis dependency to test scope if not already present • Create IdempotencyRaceConditionTest using @SpringBootTest with embedded Redis container • Submit two threads simultaneously with same partnerId=p1, key=K1, bodyHash=H1 using ExecutorService with CountDownLatch • Collect both IdempotencyDecision results; assert exactly 1 is Proceed and exactly 1 is InFlight • Repeat the test 10 times in a loop to catch non-deterministic failures • Add test: lock expires after 30 s (mock clock or set LOCK_TTL=1 s in test); after expiry, new request returns Proceed again | IdempotencyRaceConditionTest.java using Testcontainers Redis | • Exactly 1 of 2 concurrent requests returns Proceed; exactly 1 returns InFlight across 10 runs • Neither request returns an exception or error state • After lock TTL expiry (1 s in test), a third request with the same key returns Proceed • The embedded Redis container's NX semantics match production Redis 7 behaviour • Test completes in under 10 s (no deadlocks) | 50 | 5.7-T02, 5.7-T03 | BE | API-05
5.7-T15 | transaction-mgmt | 5.7 | 5. Transaction Processing (MPM/CPM) | Idempotency & request dedup | 1 | Unit tests: DUPLICATE_PARTNER_TXN_REF detection and idempotency interaction | Tests that verify the boundary between idempotency replay (same key, same body -> replayed response) and DUPLICATE_PARTNER_TXN_REF (new key, same partner_txn_ref -> 409). These are different mechanisms: idempotency is Redis-based (pre-DB), duplicate partner_txn_ref is DB-constraint-based (post-DB). The test must confirm they do not interfere with each other. | • Create PaymentServiceDuplicateTxnRefTest using @DataJpaTest or @SpringBootTest with test DB • Test 1: POST payment with key=K1, partner_txn_ref=REF-001 -> 201 (succeeds) • Test 2: POST payment with key=K1 (same), same body -> 201 replay (idempotency, not duplicate error) • Test 3: POST payment with key=K2 (new key), partner_txn_ref=REF-001 (same ref) -> 409 DUPLICATE_PARTNER_TXN_REF • Test 4: POST payment with key=K3 (new key), partner_txn_ref=REF-002 (new ref) -> 201 (different ref, succeeds) • Assert error envelopes contain correct error_code field for each case | PaymentServiceDuplicateTxnRefTest.java with 4 test methods | • Test 1 returns HTTP 201 with a txn_ref in the response body • Test 2 returns HTTP 201 with the identical txn_ref from Test 1 (replay) • Test 3 returns HTTP 409 with error_code=DUPLICATE_PARTNER_TXN_REF and no txn_ref field • Test 4 returns HTTP 201 with a new distinct txn_ref • The DB contains exactly 2 transaction rows after all 4 tests (K1/REF-001 and K3/REF-002) | 40 | 5.7-T09, 5.7-T10, 5.7-T13 | BE | API-05
5.7-T16 | transaction-mgmt | 5.7 | 5. Transaction Processing (MPM/CPM) | Idempotency & request dedup | 1 | Integration test: safe retry guidance -- 5xx retry with same key succeeds | API-05 §7.2 safe retry guidance: on HTTP 5xx, partner retries with the SAME Idempotency-Key after exponential back-off. If the first request failed mid-way (e.g. scheme timeout producing UNCERTAIN state), the retry must return the stored response if the first request completed (even with 5xx), or process as new if the first never completed (lock expired). This integration test covers both scenarios. | • Test 1 (5xx stored): mock the payment handler to return 500 on first call; IdempotencyFilter must store the 500 response; second call with same key returns stored 500 without re-invoking handler • Test 2 (no response stored, lock expired): simulate crash by calling acquireLock without complete(); advance clock past 30 s lock TTL; retry with same key -> Proceed (re-processes as new) • Test 3 (network timeout, UNCERTAIN state): mock scheme call to time out; transaction enters UNCERTAIN state; response to partner is 202 UNCERTAIN; retry with same key returns stored 202 UNCERTAIN without re-submitting to scheme • Assert in Test 3 that the scheme mock was called exactly once (not twice) | IdempotencyRetryIntegrationTest.java with 3 test methods | • Test 1: handler invocation count = 1; both first and second call return HTTP 500 with same body • Test 2: after lock TTL expiry, same key is treated as new (handler invocation count = 2) • Test 3: scheme mock call count = 1 despite two HTTP requests with same key • Test 3: second request returns X-Idempotency-Status: replayed header • All 3 tests pass with no false positives across 5 consecutive runs | 55 | 5.7-T07, 5.7-T08, 5.7-T13 | BE | API-05
5.7-T17 | transaction-mgmt | 5.7 | 5. Transaction Processing (MPM/CPM) | Idempotency & request dedup | 1 | Implement idempotency key TTL expiry: re-used expired key treated as new request | API-05 §7.3: keys expire after 24 hours. After expiry, a re-used key is treated as a new request (not an error). The Redis TTL of 86400 s handles this automatically -- once the key expires, findCompleted() returns empty and the request is processed fresh. No special application code is needed for expiry itself, but the service must not interpret 'key not found' as an error. This ticket verifies the expiry behaviour and adds a test. | • Confirm IdempotencyService.check() treats Optional.empty() from findCompleted() as Proceed (not an error) -- this should already be the case from T03 • Add unit test with MOCK clock: store a record with createdAt = now() - 86401 s (simulated by setting Redis TTL=1 in test); after TTL expires, check returns Proceed • Add a warning log in IdempotencyService when a key that was previously in the completed state (found in findCompleted) has been re-submitted after expiry -- this is informational only • Document in code comments: 'After 24 h TTL expiry, the key is gone from Redis; a new submission with the same key string is a fresh request per API-05 §7.3' | Updated IdempotencyService.java with expiry test in IdempotencyServiceTest.java | • After Redis TTL expires (simulated via LOCK_TTL=1 s in test), check() returns Proceed, not Replay • No exception is thrown when the key has expired and is resubmitted • The 24-hour TTL (86400 s) is set on the result key in saveCompleted() -- verifiable via Redis TTL command in integration test • A key that expires and is resubmitted is treated identically to a brand-new key (no history stored after expiry) | 25 | 5.7-T03, 5.7-T13 | BE | API-05
5.7-T18 | transaction-mgmt | 5.7 | 5. Transaction Processing (MPM/CPM) | Idempotency & request dedup | 1 | Wire IdempotencyFilter into Spring Security filter chain at correct order | The IdempotencyFilter must be placed AFTER the AuthenticationFilter (HMAC signature validation) but BEFORE any business-logic handler. Reason: idempotency replay should only work for authenticated requests (prevents replay of cached responses with a stolen key by an unauthenticated caller). If auth fails, the request is rejected before idempotency lookup. Spring Security filter order is managed via FilterOrderRegistration or @Order annotation. Auth filter order must be explicitly confirmed. | • Check the existing AuthenticationFilter @Order or SecurityFilterChain configuration to determine its numeric order • Set IdempotencyFilter @Order to AuthFilter_order + 1 (e.g. if AuthFilter = 10, set IdempotencyFilter = 11) • Add integration test: unauthenticated POST with valid Idempotency-Key returns HTTP 401 INVALID_API_KEY (not 400 MISSING_IDEMPOTENCY_KEY and not a replay) • Add integration test: authenticated POST with valid key processes normally through idempotency logic • Verify filter ordering in Spring context using FilterChainProxy.getFilterChains() in a @SpringBootTest | IdempotencyFilter order configuration with integration tests confirming auth-before-idempotency | • Unauthenticated request returns HTTP 401 (auth fails) before idempotency check runs • Authenticated request with missing Idempotency-Key returns HTTP 400 MISSING_IDEMPOTENCY_KEY (auth passes, idempotency fails) • IdempotencyFilter appears after AuthenticationFilter in FilterChainProxy order • A stored idempotency replay is only returned to a caller that presents valid HMAC credentials • No NullPointerException occurs when auth filter populates security context before idempotency filter reads partner_id | 35 | 5.7-T05, 5.7-T12 | BE | API-05
5.7-T19 | transaction-mgmt | 5.7 | 5. Transaction Processing (MPM/CPM) | Idempotency & request dedup | 1 | Idempotency metrics and observability: Micrometer counters | Operations needs visibility into idempotency behaviour to detect anomalies (e.g. a partner sending the same key repeatedly indicating retry storms). Add Micrometer counters for: idempotency.replay (tagged by endpoint), idempotency.in_flight, idempotency.key_reuse (body mismatch), idempotency.missing_key. These counters feed the existing observability stack (Prometheus / Grafana per OPS-13). | • Inject MeterRegistry into IdempotencyFilter and IdempotencyService • Increment counter idempotency.replay with tag endpoint={requestURI} on every Replay decision • Increment counter idempotency.in_flight on every InFlight decision • Increment counter idempotency.key_reuse on every IdempotencyKeyReuseException • Increment counter idempotency.missing_key on every missing-header rejection • Add unit test asserting counters are incremented: use SimpleMeterRegistry; simulate each scenario; assert counter value = 1 | Micrometer counter instrumentation in IdempotencyFilter.java and IdempotencyService.java with unit tests | • After one Replay event, counter idempotency.replay{endpoint=/v1/payments} = 1 • After one InFlight event, counter idempotency.in_flight = 1 • After one body-mismatch event, counter idempotency.key_reuse = 1 • After one missing-key rejection, counter idempotency.missing_key = 1 • Counters are exported to /actuator/prometheus endpoint in integration test | 30 | 5.7-T05, 5.7-T03 | BE | API-05
5.7-T20 | transaction-mgmt | 5.7 | 5. Transaction Processing (MPM/CPM) | Idempotency & request dedup | 1 | Document idempotency service API contract in Javadoc and package README | A developer with no project context must be able to use the idempotency service from Javadoc alone. This ticket adds Javadoc to all public methods in IdempotencyService, IdempotencyRepository, and IdempotencyFilter, and a brief package-info.java explaining the Redis key schema, TTL values, and the three-state decision model (Proceed / Replay / InFlight). No separate markdown file is needed; Javadoc is sufficient. | • Add Javadoc to IdempotencyService.check(): document all three return variants, the body-hash mismatch exception, and the Redis key format • Add Javadoc to IdempotencyService.complete(): document when to call it, idempotency of the call itself, and what happens on duplicate complete() calls • Add Javadoc to IdempotencyRepository interface methods: document Redis commands used, TTL semantics, and NX semantics for acquireLock • Create package-info.java for the idempotency package with a 5-10 line summary: purpose, Redis key schema (idem:{partnerId}:{key}, idem_lock:{partnerId}:{key}), TTL (86400 s / 30 s), three-state model, and reference to API-05 §7 • Run javadoc generation and verify no warnings for the idempotency package | Javadoc on all public methods in the idempotency package + package-info.java | • javadoc -d /tmp/docs src/main/java/**/idempotency/** produces zero warnings • IdempotencyService.check() Javadoc describes all 3 return types and the body-mismatch exception • package-info.java states the Redis key format idem:{partnerId}:{idempotencyKey} and the 86400 s TTL • No @param or @return tags are missing on any public method in the idempotency package • package-info.java is present and non-empty in the compiled JAR (visible in javadoc index) | 30 | 5.7-T03, 5.7-T02, 5.7-T05 | BE | API-05
5.8-T01 | payment-executor | 5.8 | 5. Transaction Processing (MPM/CPM) | Direction routing & extensibility | 1 | Add direction CHECK constraint and index to rule table migration | The rule table (DAT-03 §4.6) has a direction column VARCHAR(10) with permitted values INBOUND, OUTBOUND, DOMESTIC, HUB. It is part of the UNIQUE key (partner_id, scheme_id, direction). The direction field determines fee tier and BOK reporting fields. A missing or wrong CHECK constraint lets invalid directions reach the rate engine. Primary key is (partner_id, scheme_id, direction); all four directions must be insertable from day one even though only DOMESTIC and INBOUND are activated in Phase 1. | • Write a Flyway migration: ALTER TABLE rule ADD CONSTRAINT chk_rule_direction CHECK (direction IN ('INBOUND','OUTBOUND','DOMESTIC','HUB')) • Verify the UNIQUE constraint (partner_id, scheme_id, direction) exists; add it if absent • Add a covering index on (partner_id, scheme_id, direction) to support O(1) rule lookup • Ensure is_same_ccy_shortcircuit BOOLEAN column exists (computed flag; TRUE when collection_ccy = settle_a_ccy = settle_b_ccy = payout_ccy) and status column has CHECK IN ('DRAFT','ACTIVE','SUSPENDED') • Apply migration against a local dev DB; confirm all four direction values insert cleanly and a fifth value 'BILATERAL' is rejected at the DB level | Flyway migration file V5_8_001__rule_direction_constraint_index.sql | • INSERT with direction='DOMESTIC' succeeds; direction='OUTBOUND' succeeds; direction='HUB' succeeds; direction='INBOUND' succeeds • INSERT with direction='BILATERAL' raises a CHECK constraint violation • The UNIQUE constraint rejects a second row with the same (partner_id, scheme_id, direction) triplet • Index on (partner_id, scheme_id, direction) appears in pg_indexes for the rule table • migration is idempotent: re-running in a transaction that is then rolled back leaves the schema unchanged | 25 |  | BE | BRD-01, SAD-02
5.8-T02 | payment-executor | 5.8 | 5. Transaction Processing (MPM/CPM) | Direction routing & extensibility | 1 | Define Direction enum and RuleKey value object in domain model | GMEPay+ routes every payment via a rule identified by the composite key (partner_id, scheme_id, direction). Direction is one of INBOUND (overseas partner -> Korean merchant, Phase 1), OUTBOUND (Korean partner -> foreign merchant, Phase 2), DOMESTIC (same-country, same-currency, short-circuit), HUB (overseas->overseas, Phase 2+). A RuleKey value object is needed by the Smart Router and Rate Engine to look up rules without passing three separate parameters. All four directions must be representable in code from day one. | • Create enum Direction { INBOUND, OUTBOUND, DOMESTIC, HUB } with a fromString(String) factory that throws IllegalArgumentException on unknown values • Create immutable value class RuleKey(long partnerId, long schemeId, Direction direction) with equals/hashCode based on all three fields • Annotate Direction with @JsonValue / @JsonCreator for clean serialisation to/from lowercase API strings (domestic, inbound, outbound, hub) • Add a boolean isCrossBorder() helper on Direction: returns false only for DOMESTIC, true for all others • Write unit tests: Direction.fromString for all four values and one unknown; RuleKey equality and hashCode; JSON round-trip for each direction value | Direction.java enum, RuleKey.java value class, DirectionTest.java, RuleKeyTest.java | • Direction.fromString("INBOUND") == Direction.INBOUND; fromString("inbound") is case-insensitive or documented as case-sensitive • Direction.fromString("BILATERAL") throws IllegalArgumentException • RuleKey(1,2,DOMESTIC).equals(RuleKey(1,2,DOMESTIC)) is true; RuleKey(1,2,DOMESTIC).equals(RuleKey(1,2,INBOUND)) is false • Direction.DOMESTIC.isCrossBorder() == false; Direction.INBOUND.isCrossBorder() == true; Direction.HUB.isCrossBorder() == true • JSON serialisation of Direction.INBOUND produces the string 'INBOUND' and deserialises back correctly | 25 | 5.8-T01 | BE | BRD-01, SAD-02
5.8-T03 | payment-executor | 5.8 | 5. Transaction Processing (MPM/CPM) | Direction routing & extensibility | 1 | Implement RuleRepository.findByKey() with caching for rule lookup | The Smart Router and Rate Engine call fetchRule(partner_id, scheme_id, direction) to load the full rule record including margins m_a, m_b, service_charge_amount, is_same_ccy_shortcircuit, rate_coll_source, rate_pay_source, and status. The UNIQUE key (partner_id, scheme_id, direction) guarantees at most one row. Cache in Redis with key rule:{partnerId}:{schemeId}:{direction} for fast O(1) lookup; TTL 300 s. On cache miss, query DB and populate cache. If status = DRAFT or SUSPENDED, treat as not found (return empty). Only ACTIVE rules are routable. | • Add RuleRepository.findByKey(RuleKey key): query rule table WHERE partner_id=:p AND scheme_id=:s AND direction=:d AND status='ACTIVE' • Wrap with a Redis cache: on hit return cached Rule; on miss query DB, store result with TTL 300 s using key pattern rule:{partnerId}:{schemeId}:{direction} • Return Optional<Rule>; empty if no ACTIVE row • Expose RuleRepository.evictCache(RuleKey key) called by the Admin Service whenever a rule is saved/activated/suspended • Write unit tests: active rule returned; draft rule returns empty; suspended rule returns empty; cache hit does not query DB (verify with mock); cache eviction causes next call to re-query | RuleRepository.java with findByKey() and evictCache(), RuleRepositoryTest.java | • findByKey for an ACTIVE rule returns a populated Rule with correct partner_id, scheme_id, direction, m_a, m_b fields • findByKey for a DRAFT rule returns Optional.empty() • findByKey for a SUSPENDED rule returns Optional.empty() • Second call with same RuleKey hits Redis cache and does not execute a SQL query (verified via query count mock) • After evictCache(key), the next findByKey re-queries the database (cache miss) | 40 | 5.8-T02 | BE | BRD-01, SAD-02
5.8-T04 | payment-executor | 5.8 | 5. Transaction Processing (MPM/CPM) | Direction routing & extensibility | 1 | Implement SmartRouter.resolveRoute() returning RouteContext for a payment request | The Smart Router (SAD-02 §5) selects the correct SchemeAdapter given (partner_id, scheme_id, direction) and returns a RouteContext containing the matched rule, the scheme adapter handle, and the resolved direction. The router must: (1) verify the rule exists and is ACTIVE, (2) verify the partner is ACTIVE, (3) verify the scheme is ACTIVE, (4) verify the requested direction is permitted by the feature-flag table (FEATURE_OUTBOUND_PAYMENTS=false blocks OUTBOUND; OUTBOUND and HUB are scaffolded but not live in Phase 1). Error code DIRECTION_NOT_ENABLED (HTTP 422) is returned when the direction is not enabled. | • Create RouteContext record: rule (Rule), schemeAdapterRef (String scheme_id), direction (Direction), partnerId (long), schemeId (long) • In SmartRouter.resolveRoute(long partnerId, long schemeId, Direction direction): call RuleRepository.findByKey(RuleKey); if empty throw DirectionNotEnabledException -> DIRECTION_NOT_ENABLED (HTTP 422) • Check PartnerRepository.isActive(partnerId); if false throw PartnerInactiveException -> PARTNER_INACTIVE (HTTP 422) • Check SchemeRepository.isActive(schemeId); if false throw SchemeUnavailableException -> SCHEME_UNAVAILABLE (HTTP 422) • Check FeatureFlagService.isDirectionAllowed(direction): OUTBOUND and HUB return false unless FEATURE_OUTBOUND_PAYMENTS=true; if blocked throw DirectionNotEnabledException • Return RouteContext with resolved rule and adapter reference | SmartRouter.java, RouteContext.java, SmartRouterTest.java | • resolveRoute(partnerId=1, schemeId=1, DOMESTIC) with active partner+scheme and ACTIVE rule returns RouteContext with correct rule • resolveRoute with no matching ACTIVE rule throws DirectionNotEnabledException with code DIRECTION_NOT_ENABLED • resolveRoute with partner status=SUSPENDED throws PartnerInactiveException • resolveRoute with direction=OUTBOUND and FEATURE_OUTBOUND_PAYMENTS=false throws DirectionNotEnabledException regardless of whether a rule exists • resolveRoute with direction=HUB and FEATURE_OUTBOUND_PAYMENTS=false throws DirectionNotEnabledException | 45 | 5.8-T03 | BE | BRD-01, SAD-02
5.8-T05 | payment-executor | 5.8 | 5. Transaction Processing (MPM/CPM) | Direction routing & extensibility | 1 | Implement FeatureFlagService with FEATURE_OUTBOUND_PAYMENTS and FEATURE_MULTI_SCHEME_ROUTING flags | SAD-02 §5.2 defines feature flags stored in environment variables or a lightweight config table, loaded at service startup. FEATURE_OUTBOUND_PAYMENTS (default false) gates OUTBOUND and HUB directions. FEATURE_MULTI_SCHEME_ROUTING (default false) gates routing across multiple active schemes. In Phase 1 both are false: only DOMESTIC and INBOUND are live. The service must read flags at startup and expose isDirectionAllowed(Direction) and isMultiSchemeRoutingEnabled() without hard-coded direction names in caller code. | • Create FeatureFlags configuration class reading FEATURE_OUTBOUND_PAYMENTS (boolean, default false) and FEATURE_MULTI_SCHEME_ROUTING (boolean, default false) from environment or application.properties • Create FeatureFlagService.isDirectionAllowed(Direction d): return true for DOMESTIC and INBOUND always; for OUTBOUND and HUB return the value of FEATURE_OUTBOUND_PAYMENTS • Add isMultiSchemeRoutingEnabled(): returns FEATURE_MULTI_SCHEME_ROUTING value • Write unit tests with both flag values for each direction • Document that changing a flag requires a config update and service restart (add a comment in the class) | FeatureFlags.java config class, FeatureFlagService.java, FeatureFlagServiceTest.java | • With FEATURE_OUTBOUND_PAYMENTS=false: DOMESTIC=true, INBOUND=true, OUTBOUND=false, HUB=false • With FEATURE_OUTBOUND_PAYMENTS=true: all four directions return true • isMultiSchemeRoutingEnabled() returns false when FEATURE_MULTI_SCHEME_ROUTING is absent from env • FeatureFlagService has no hard-coded string comparisons; uses Direction enum only • Unit tests cover all four Direction values under both flag states (8 assertions minimum) | 30 | 5.8-T02 | BE | BRD-01, SAD-02
5.8-T06 | payment-executor | 5.8 | 5. Transaction Processing (MPM/CPM) | Direction routing & extensibility | 1 | Implement DOMESTIC direction routing: same-currency short-circuit detection in rule resolution | When direction=DOMESTIC the rule's is_same_ccy_shortcircuit=true (collection_ccy = settle_a_ccy = settle_b_ccy = payout_ccy). The Smart Router must detect this flag and set a shortCircuit=true field on RouteContext so the Rate Engine skips the USD pool entirely. Example: GME Remit on ZeroPay, all KRW. For DOMESTIC rules m_a and m_b must both be 0. If is_same_ccy_shortcircuit=false on a DOMESTIC direction rule, that is a data integrity error and must be logged as an ops alert (should not happen but must be caught). | • Add boolean shortCircuit field to RouteContext record • In SmartRouter.resolveRoute(), after fetching the rule, if direction == DOMESTIC check rule.isSameCcyShortcircuit() • If true, set routeContext.shortCircuit = true • If false (data integrity violation): log ERROR with alert tag, throw RoutingIntegrityException -> HTTP 500 INTERNAL_ERROR • Also validate m_a == 0 and m_b == 0 on a short-circuit rule; if nonzero log ERROR and throw RoutingIntegrityException • Write unit test scenarios for all branches | Updated SmartRouter.java with short-circuit detection, updated RouteContext.java, SmartRouterDomesticTest.java | • resolveRoute with DOMESTIC rule where is_same_ccy_shortcircuit=true returns RouteContext with shortCircuit=true • resolveRoute with DOMESTIC rule where is_same_ccy_shortcircuit=false throws RoutingIntegrityException • resolveRoute with DOMESTIC rule where m_a=0.01 and is_same_ccy_shortcircuit=true throws RoutingIntegrityException (m_a must be 0) • resolveRoute with INBOUND rule where is_same_ccy_shortcircuit=false returns RouteContext with shortCircuit=false (normal path) • No hard-coded currency string KRW in short-circuit detection logic; purely uses rule.isSameCcyShortcircuit() flag | 35 | 5.8-T04 | BE | BRD-01, SAD-02
5.8-T07 | payment-executor | 5.8 | 5. Transaction Processing (MPM/CPM) | Direction routing & extensibility | 1 | Implement INBOUND direction routing: cross-border validation and prefunding requirement flag | Direction=INBOUND means an overseas partner customer pays at a domestic (Korean) merchant. The partner type must be OVERSEAS (prefunding required). The rule is cross-border (is_same_ccy_shortcircuit=false) and must have m_a + m_b >= 2.0% (e.g. SendMN: m_a=0.01, m_b=0.01 => 2.0%). If the resolved rule has m_a + m_b < 0.02 on an INBOUND rule, reject with a RoutingIntegrityException (data error). The RouteContext must carry requiresPrefunding=true for INBOUND so the Transaction Orchestrator knows to call PrefundingService. | • Add boolean requiresPrefunding field to RouteContext record • In SmartRouter.resolveRoute(), when direction == INBOUND: verify partner.type == OVERSEAS; if not throw RoutingIntegrityException with message 'INBOUND direction requires OVERSEAS partner' • Verify rule.m_a + rule.m_b >= 0.02 (i.e. 2.0%); if below threshold throw RoutingIntegrityException with message 'INBOUND rule combined margin below 2%' • Set routeContext.requiresPrefunding = (partner.type == OVERSEAS) • Write unit tests covering partner type mismatch, margin below 2%, and happy path | Updated SmartRouter.java with INBOUND validation, SmartRouterInboundTest.java | • resolveRoute INBOUND with OVERSEAS partner, m_a=0.01 m_b=0.01 (sum=0.02) returns RouteContext with requiresPrefunding=true • resolveRoute INBOUND with LOCAL partner throws RoutingIntegrityException mentioning OVERSEAS partner requirement • resolveRoute INBOUND with m_a=0.005 m_b=0.005 (sum=0.01 < 2%) throws RoutingIntegrityException mentioning combined margin • resolveRoute INBOUND with m_a=0.015 m_b=0.015 (sum=0.03 > 2%) succeeds • resolveRoute DOMESTIC with LOCAL partner returns requiresPrefunding=false | 35 | 5.8-T05, 5.8-T06 | BE | BRD-01, SAD-02
5.8-T08 | payment-executor | 5.8 | 5. Transaction Processing (MPM/CPM) | Direction routing & extensibility | 1 | Scaffold OUTBOUND direction handler: stub implementation returning DIRECTION_NOT_ENABLED | OUTBOUND (domestic partner customer pays at foreign merchant) is Phase 2 scope. The architecture must support it from day one with no retrofitting (BRD-01 §9, SAD-02 A1). In Phase 1 with FEATURE_OUTBOUND_PAYMENTS=false the route resolution already rejects OUTBOUND via FeatureFlagService. This ticket adds the OUTBOUND-specific RouteContext fields and a stub OutboundDirectionHandler so that enabling the feature flag in Phase 2 requires only handler implementation, not architectural changes. No live payment logic is implemented here. | • Create OutboundDirectionHandler.java with method RouteContext enrichOutbound(RouteContext ctx, Rule rule): throws UnsupportedOperationException('OUTBOUND handler not yet implemented') — this is the Phase 2 hook • Add OUTBOUND-specific fields to RouteContext: outboundSchemeCountryCode (String, nullable), outboundPartnerSettlementCcy (String, nullable) • Add a TODO comment citing SAD-02 §5 and BRD-01 §9 explaining what Phase 2 must implement (partner B quote, foreign scheme adapter call, FX1014 BOK fields) • Write a unit test asserting OutboundDirectionHandler.enrichOutbound() throws UnsupportedOperationException with a descriptive message • Verify that SmartRouter with FEATURE_OUTBOUND_PAYMENTS=false still throws DirectionNotEnabledException before OutboundDirectionHandler is ever called | OutboundDirectionHandler.java stub, updated RouteContext.java with OUTBOUND fields, OutboundDirectionHandlerTest.java | • OutboundDirectionHandler.enrichOutbound() throws UnsupportedOperationException with message containing 'Phase 2' • RouteContext compiles with outboundSchemeCountryCode and outboundPartnerSettlementCcy fields present but null for non-OUTBOUND routes • SmartRouter test: direction=OUTBOUND with FEATURE_OUTBOUND_PAYMENTS=false throws DirectionNotEnabledException before OutboundDirectionHandler is invoked (verify with mock.never()) • SmartRouter test: direction=OUTBOUND with FEATURE_OUTBOUND_PAYMENTS=true reaches OutboundDirectionHandler.enrichOutbound() (which then throws UnsupportedOperationException as expected in Phase 1) • No production code path calls OutboundDirectionHandler in Phase 1 without the feature flag being true | 30 | 5.8-T07 | BE | BRD-01, SAD-02
5.8-T09 | payment-executor | 5.8 | 5. Transaction Processing (MPM/CPM) | Direction routing & extensibility | 1 | Scaffold HUB direction handler: stub with dual-IDENTITY leg detection | HUB direction (overseas partner -> overseas merchant, both non-Korean) is Phase 2+ scope. SAD-02 A1 requires the architecture support it from day one. For HUB, both rate legs may be IDENTITY (settle_a_ccy=USD and settle_b_ccy=USD) with margins still applied normally. Example: target_payout=100 USD, cost_rate_coll=1.0 (IDENTITY), cost_rate_pay=1.0 (IDENTITY), m_a=0.01, m_b=0.01, service_charge=0.50 USD -> collection_usd=102.0408 USD, collection_amount=102.5408 USD. The stub must detect dual-IDENTITY and record this for the rate engine, but throw UnsupportedOperationException until Phase 2. | • Create HubDirectionHandler.java with method RouteContext enrichHub(RouteContext ctx, Rule rule): if rule.rateColl==IDENTITY AND rule.ratePay==IDENTITY set ctx.hubDualIdentity=true • Add hubDualIdentity boolean field (nullable, default false) to RouteContext • Throw UnsupportedOperationException('HUB handler not yet implemented - Phase 2+') after setting the flag • Add TODO comment citing RATE-04 §7.1 dual-IDENTITY worked example for Phase 2 implementor • Write unit test: enrichHub with dual-IDENTITY rule sets hubDualIdentity=true then throws UnsupportedOperationException | HubDirectionHandler.java stub, updated RouteContext.java with hubDualIdentity, HubDirectionHandlerTest.java | • HubDirectionHandler.enrichHub() sets routeContext.hubDualIdentity=true when both rate sources are IDENTITY • HubDirectionHandler.enrichHub() throws UnsupportedOperationException with message containing 'Phase 2' • SmartRouter with FEATURE_OUTBOUND_PAYMENTS=false throws DirectionNotEnabledException for HUB before HubDirectionHandler is called • RouteContext.hubDualIdentity defaults to false for DOMESTIC and INBOUND routes • Unit test verifies the dual-IDENTITY numeric example from RATE-04: target_payout=100 USD, m_a=0.01, m_b=0.01 -> collection_usd=100/0.98=102.0408, collection_amount=102.5408 as a documentation comment | 30 | 5.8-T07 | BE | BRD-01, SAD-02
5.8-T10 | payment-executor | 5.8 | 5. Transaction Processing (MPM/CPM) | Direction routing & extensibility | 1 | Implement rule lookup integration in RateEngine: use RouteContext to load rule fields | The Rate Engine (RATE-04 §3) resolves the rule via fetchRule(partner_id, scheme_id, direction) to obtain m_a, m_b, service_charge_amount, cost_rate_coll source, cost_rate_pay source, and is_same_ccy_shortcircuit. In the new design, SmartRouter.resolveRoute() has already resolved the rule and passed it in RouteContext. The Rate Engine must consume RouteContext rather than re-querying the rule table, to avoid a second DB round-trip. If RouteContext.shortCircuit==true, skip the 5-step USD pool calculation entirely. | • Refactor RateEngine.computeQuote(QuoteRequest request) to accept RouteContext as a parameter instead of calling RuleRepository internally • Extract rule fields from routeContext.rule: m_a, m_b, serviceChargeAmount, rateColl, ratePay, isSameCcyShortcircuit • If routeContext.shortCircuit == true, execute short-circuit: return collection_amount = target_payout + serviceCharge; set all USD pool fields to null; record both rate sources as IDENTITY • Otherwise execute the 5-step RECEIVE-mode calculation using the rule's rate sources • Add an assertion: if shortCircuit==true and m_a != 0 or m_b != 0, throw IllegalStateException (should have been caught by SmartRouter) | Refactored RateEngine.computeQuote() method signature and body, RateEngineRouteContextTest.java | • computeQuote with shortCircuit=true, target_payout=15000 KRW, service_charge=500 KRW returns collection_amount=15500 KRW with payout_usd_cost=null and collection_usd=null • computeQuote with shortCircuit=false, INBOUND rule (m_a=0.01, m_b=0.01, cost_rate_pay=1380.00, cost_rate_coll=1.0, target_payout=50000 KRW) returns collection_usd=36.9714 USD (tolerance 0.0001) • computeQuote does not call RuleRepository (verified with mock.never() on RuleRepository) • computeQuote with shortCircuit=true and m_a=0.01 throws IllegalStateException • computeQuote returns all five USD pool step values in the QuoteResult for non-short-circuit routes | 45 | 5.8-T06, 5.8-T07 | BE | BRD-01, SAD-02
5.8-T11 | payment-executor | 5.8 | 5. Transaction Processing (MPM/CPM) | Direction routing & extensibility | 1 | Implement direction-aware BOK reporting field population on rate quote | The direction field determines which BOK FX reporting form is required. INBOUND -> FX1015 (payment to Korean merchant); OUTBOUND -> FX1014 (Korean customer paying overseas, Phase 2); DOMESTIC -> exempt (same-currency, no BOK form); HUB -> TBD (open issue OI-03). At quote time the system must stamp the bok_form_type field on the rate_quote record. The offer_rate_coll derived by the rate engine (= send_amount / (collection_usd - collection_margin_usd)) maps to BOK FX1015 field #14 for INBOUND transactions. | • Add bok_form_type VARCHAR(10) column to rate_quote table via migration: CHECK IN ('FX1015','FX1014','EXEMPT','PENDING_OI03') NULLABLE • In RateEngine.computeQuote(), after computing the quote, set bokFormType based on direction: INBOUND->FX1015, OUTBOUND->FX1014, DOMESTIC->EXEMPT, HUB->PENDING_OI03 • For INBOUND, verify offer_rate_coll is computed and non-null (offer_rate_coll = send_amount / (collection_usd - collection_margin_usd)); assert > 0 • Store offer_rate_coll in rate_quote.offer_rate_coll column; this is the value that maps to BOK FX1015 field #14 • Write unit test: INBOUND quote has bok_form_type=FX1015 and offer_rate_coll=(37.3317)/(36.9714-0.3697)=1.0101 for the standard numeric example | Migration V5_8_002__rate_quote_bok_form_type.sql, updated RateEngine.computeQuote() with BOK field stamping, BokFormTypeTest.java | • INBOUND direction quote has bok_form_type='FX1015' and offer_rate_coll is non-null and > 1.0 (for USD->KRW with margins) • DOMESTIC direction quote has bok_form_type='EXEMPT' and offer_rate_coll=1.0 • HUB direction quote has bok_form_type='PENDING_OI03' • offer_rate_coll for INBOUND example (send_amount=36.9714, collection_usd=36.9714, collection_margin_usd=0.3697): send_amount/(collection_usd-collection_margin_usd)=36.9714/36.6017=1.01010 (tolerance 0.0001) • BOK FX1015 field migration CHECK constraint rejects value 'FX1016' | 40 | 5.8-T10 | BE | BRD-01, SAD-02
5.8-T12 | payment-executor | 5.8 | 5. Transaction Processing (MPM/CPM) | Direction routing & extensibility | 1 | Add direction column and routing fields to transaction table and transaction insert | The transaction table (DAT-03 §5.2) has a direction column VARCHAR(10) CHECK IN ('INBOUND','OUTBOUND','DOMESTIC','HUB'). At commit time, direction must be copied from the rate_quote and stored immutably on the transaction record alongside the rate lock. The transaction also carries settle_a_ccy, settle_b_ccy, collection_ccy, payout_ccy (all from the rate quote). These fields are required for settlement model selection (DOMESTIC=net settlement; INBOUND/OUTBOUND/HUB=gross settlement). | • Verify or add direction column to transaction table with CHECK constraint: ALTER TABLE transaction ADD CONSTRAINT chk_txn_direction CHECK (direction IN ('INBOUND','OUTBOUND','DOMESTIC','HUB')) • Verify settle_a_ccy, settle_b_ccy, collection_ccy, payout_ccy CHAR(3) columns exist on transaction • In TransactionService.commitTransaction(), when copying locked rate quote fields to the transaction row, also copy direction, settle_a_ccy, settle_b_ccy from the resolved rule via RouteContext • Add a composite index (direction, status, committed_at) to support settlement batch queries that filter by direction • Write migration and verify with test: insert one DOMESTIC row and one INBOUND row, assert direction stored correctly | Migration V5_8_003__transaction_direction_index.sql, updated TransactionService.commitTransaction(), TransactionDirectionTest.java | • INSERT transaction with direction='INBOUND' stores correctly; direction='INVALID' is rejected by CHECK constraint • commitTransaction() for a DOMESTIC route stores direction='DOMESTIC' and settle_a_ccy='KRW', payout_ccy='KRW' • commitTransaction() for an INBOUND route (SendMN) stores direction='INBOUND', settle_a_ccy='USD', payout_ccy='KRW' • Composite index (direction, status, committed_at) exists in pg_indexes • direction column on transaction is NOT NULL (cannot insert a transaction without a direction) | 35 | 5.8-T10 | BE | BRD-01, SAD-02
5.8-T13 | payment-executor | 5.8 | 5. Transaction Processing (MPM/CPM) | Direction routing & extensibility | 1 | Implement direction-to-settlement-model mapping: DOMESTIC=net, INBOUND=gross | The Settlement Engine (SAD-02 §5.4, RATE-04 §12) selects the settlement model based on direction. DOMESTIC -> Net Settlement: GME deducts its fee share and remits the remainder to ZeroPay (ZP0061/ZP0063 include net amount = target_payout - GME_fee_share). INBOUND (and future OUTBOUND/HUB) -> Gross Settlement: GME remits the full target_payout to ZeroPay; GME invoices merchants monthly for its fee share. This mapping must be a data-driven function, not hardcoded per partner name. The settlement model is read from direction, not from the partner or rule. | • Create SettlementModelResolver.java with method SettlementModel resolve(Direction direction): DOMESTIC -> NET, all others -> GROSS • SettlementModel is an enum { NET, GROSS } • In SettlementBatchService.buildZP0061Record(Transaction txn), call SettlementModelResolver.resolve(txn.direction) to determine net vs gross settlement amount • For NET: settlement_amount = target_payout - gme_fee_share_amount; for GROSS: settlement_amount = target_payout • Write unit tests for all four direction values and both settlement amounts | SettlementModelResolver.java, SettlementModel.java enum, SettlementModelResolverTest.java | • resolve(DOMESTIC) == NET • resolve(INBOUND) == GROSS • resolve(OUTBOUND) == GROSS • resolve(HUB) == GROSS • For a DOMESTIC transaction with target_payout=15000 KRW and gme_fee_share=45 KRW, settlement_amount=14955 KRW (NET) • For an INBOUND transaction with target_payout=50000 KRW, settlement_amount=50000 KRW (GROSS, full amount) | 30 | 5.8-T12 | BE | BRD-01, SAD-02
5.8-T14 | payment-executor | 5.8 | 5. Transaction Processing (MPM/CPM) | Direction routing & extensibility | 1 | Add direction filter to transaction query service and settlement batch query | The Settlement Engine generates ZP0011 (payment registration) and ZP0061 (settlement request) batch files from transactions. The batch query must be direction-aware: the ZP0011 file includes all APPROVED transactions regardless of direction; the settlement amount computation in ZP0061 differs by direction (NET for DOMESTIC, GROSS for others - see 5.8-T13). The Admin System transaction search (PRD-07) also supports filtering by direction. Both queries use the (direction, status, committed_at) composite index added in 5.8-T12. | • In TransactionQueryService.findForSettlement(LocalDate date): query WHERE status='APPROVED' AND DATE(committed_at)=:date; return results grouped by direction • In SettlementBatchService.buildDailyBatch(LocalDate date): call findForSettlement then split results into domestic and crossBorder lists by direction; apply SettlementModelResolver to each group • Add TransactionQueryService.findByFilters(direction, status, dateFrom, dateTo, partnerId, schemeId) used by Admin transaction search; direction filter is optional (null = all directions) • Write unit test: findForSettlement returns transactions from both DOMESTIC and INBOUND directions; cross-border INBOUND transactions use GROSS settlement amount | Updated TransactionQueryService.java with direction-filtered queries, updated SettlementBatchService.buildDailyBatch(), TransactionQueryDirectionTest.java | • findForSettlement for a date with 3 DOMESTIC + 2 INBOUND APPROVED transactions returns 5 rows with correct direction values • buildDailyBatch produces domestic list size=3 and crossBorder list size=2 • DOMESTIC transaction in settlement batch has settlement_amount = target_payout - fee_share (NET) • INBOUND transaction in settlement batch has settlement_amount = target_payout (GROSS) • findByFilters with direction=null returns all directions; direction=INBOUND returns only INBOUND transactions | 40 | 5.8-T13 | BE | BRD-01, SAD-02
5.8-T15 | payment-executor | 5.8 | 5. Transaction Processing (MPM/CPM) | Direction routing & extensibility | 1 | Implement DIRECTION_NOT_ENABLED error response mapping | When SmartRouter.resolveRoute() throws DirectionNotEnabledException, the API Gateway must return HTTP 422 with error code DIRECTION_NOT_ENABLED per API-05 error catalogue. This is a non-retryable error. The error response body must conform to the standard error schema: { error_code: 'DIRECTION_NOT_ENABLED', message: '...', retryable: false }. The same handler must also map RoutingIntegrityException (data integrity error) to HTTP 500 INTERNAL_ERROR which is retryable. | • Create DirectionNotEnabledException extends RuntimeException with fields direction (Direction) and ruleKey (RuleKey) • Create RoutingIntegrityException extends RuntimeException with fields ruleKey and violationType (String) • In the global exception handler (@RestControllerAdvice): map DirectionNotEnabledException -> HTTP 422 body {error_code:'DIRECTION_NOT_ENABLED', message:'Direction {d} is not enabled for partner {p} on scheme {s}', retryable:false} • Map RoutingIntegrityException -> HTTP 500 body {error_code:'INTERNAL_ERROR', message:'Routing integrity check failed', retryable:true} • Write MockMvc integration tests for both error paths verifying HTTP status, error_code, and retryable fields | DirectionNotEnabledException.java, RoutingIntegrityException.java, updated GlobalExceptionHandler.java, DirectionErrorMappingTest.java | • GET /v1/rates with direction=OUTBOUND (FEATURE_OUTBOUND_PAYMENTS=false) returns HTTP 422 with error_code='DIRECTION_NOT_ENABLED' and retryable=false • POST /v1/payments with direction=OUTBOUND returns HTTP 422 with error_code='DIRECTION_NOT_ENABLED' • RoutingIntegrityException maps to HTTP 500 with error_code='INTERNAL_ERROR' and retryable=true • Error response body for DIRECTION_NOT_ENABLED includes the direction value in the message field • DirectionNotEnabledException is never mapped to HTTP 500 (assert status code explicitly in tests) | 35 | 5.8-T04 | BE | BRD-01, SAD-02
5.8-T16 | payment-executor | 5.8 | 5. Transaction Processing (MPM/CPM) | Direction routing & extensibility | 1 | Add direction field to rate quote API request/response and validate direction is enabled | API-05 defines GET /v1/rates request parameters: partner_id, scheme_id, direction (enum: domestic, inbound, outbound, hub), target_payout, payout_currency. The direction field is required. Before calling the Rate Engine, the API layer must call SmartRouter.resolveRoute() to validate that the direction is enabled and the rule is ACTIVE. The resolved RouteContext is then passed to the Rate Engine. The GET /v1/rates response includes direction in the response body alongside offer_rate, collection_amount, validUntil. | • In RateQuoteRequest DTO add direction field (String, required, @NotNull) and map to Direction enum via Direction.fromString() before passing to SmartRouter • In RateQuoteController.getRate(): deserialise request, call SmartRouter.resolveRoute(partnerId, schemeId, direction), pass RouteContext to RateEngine.computeQuote() • Add direction field to RateQuoteResponse DTO (String, uppercase enum name) • Write MockMvc test: GET /v1/rates with direction=domestic for GME Remit rule returns HTTP 200 with direction='DOMESTIC' in response • Write MockMvc test: GET /v1/rates with direction=outbound returns HTTP 422 DIRECTION_NOT_ENABLED | Updated RateQuoteRequest.java, updated RateQuoteController.getRate() method, updated RateQuoteResponse.java, RateQuoteDirectionIntegrationTest.java | • GET /v1/rates with direction=domestic returns HTTP 200 and response body contains direction='DOMESTIC' • GET /v1/rates with direction=outbound (feature flag false) returns HTTP 422 with error_code='DIRECTION_NOT_ENABLED' • GET /v1/rates with direction=inbound, m_a=0.01, m_b=0.01, target_payout=50000 KRW returns collection_usd approx 36.97 USD • GET /v1/rates without direction field returns HTTP 400 (validation error, field required) • GET /v1/rates with direction=invalid_value returns HTTP 400 with a descriptive validation error | 40 | 5.8-T15 | BE | BRD-01, SAD-02
5.8-T17 | payment-executor | 5.8 | 5. Transaction Processing (MPM/CPM) | Direction routing & extensibility | 1 | Add direction field to payment commit API and validate direction matches quote | POST /v1/payments (MPM commit) carries a direction field that must match the direction stored in the locked rate_quote. A mismatch (e.g. quote was for DOMESTIC but commit specifies INBOUND) must be rejected with RATE_QUOTE_INVALID (HTTP 422). The direction on the committed transaction is taken from the rate_quote (the locked value), not from the commit request, to prevent tampering. This check applies to both MPM (POST /v1/payments) and CPM commit flows. | • In MpmPaymentRequest add direction field (String, required) • In TransactionService.commitTransaction(): after lockRateQuote(), assert request.direction == quote.direction; if mismatch throw RateQuoteInvalidException with message 'direction mismatch: request=%s quote=%s' • The transaction.direction field is always taken from quote.direction (immutable locked value), never from the request body after validation • Add same check to CPM commit path if present in scope • Write unit tests: direction matches -> proceeds; direction mismatches -> RateQuoteInvalidException | Updated MpmPaymentRequest.java, updated TransactionService.commitTransaction() with direction cross-check, DirectionMismatchTest.java | • commitTransaction with request.direction=INBOUND and quote.direction=INBOUND succeeds • commitTransaction with request.direction=DOMESTIC and quote.direction=INBOUND throws RateQuoteInvalidException with code RATE_QUOTE_INVALID • transaction.direction after commit equals quote.direction (INBOUND), not the tampered request value • commitTransaction with request.direction=OUTBOUND (regardless of quote) throws DIRECTION_NOT_ENABLED before quote lock (feature flag check first) • RateQuoteInvalidException maps to HTTP 422 with error_code='RATE_QUOTE_INVALID' | 35 | 5.8-T16 | BE | BRD-01, SAD-02
5.8-T18 | payment-executor | 5.8 | 5. Transaction Processing (MPM/CPM) | Direction routing & extensibility | 1 | Implement rule CRUD admin endpoints: create, activate, suspend rule by key | The Admin Service (PRD-07 §6) must support: POST /admin/rules (create a new DRAFT rule for a (partner, scheme, direction) triplet), PUT /admin/rules/{id}/activate (DRAFT -> ACTIVE; evicts cache), PUT /admin/rules/{id}/suspend (ACTIVE -> SUSPENDED; evicts cache). The UNIQUE constraint (partner_id, scheme_id, direction) enforces at most one rule per triplet. All three operations must write an audit log entry with actor, timestamp, field, previous_value, new_value. A rule can be created for any of the four directions including OUTBOUND and HUB (scaffolded in Phase 1 as DRAFT, never activated until Phase 2). | • Implement AdminRuleController.createRule(CreateRuleRequest req): validate partner+scheme exist; verify no existing rule for (partner_id, scheme_id, direction); INSERT rule with status=DRAFT; write audit log entry {event:'rule_created', actor, rule_key, status:'DRAFT'} • Implement activateRule(long ruleId): transition DRAFT->ACTIVE; evict RuleRepository cache; write audit log {event:'rule_activated', previous:'DRAFT', new:'ACTIVE'} • Implement suspendRule(long ruleId): transition ACTIVE->SUSPENDED; evict cache; write audit log {event:'rule_suspended', previous:'ACTIVE', new:'SUSPENDED'} • Return 409 CONFLICT if createRule is called for a duplicate (partner_id, scheme_id, direction) • Write integration tests for all three endpoints including audit log verification | AdminRuleController.java with createRule, activateRule, suspendRule; AdminRuleControllerTest.java | • POST /admin/rules with new (partner, scheme, direction) triplet returns HTTP 201 with status=DRAFT • POST /admin/rules with duplicate triplet returns HTTP 409 • PUT /admin/rules/{id}/activate transitions DRAFT->ACTIVE, evicts Redis cache, inserts audit log row with event=rule_activated • PUT /admin/rules/{id}/suspend transitions ACTIVE->SUSPENDED, evicts Redis cache, inserts audit log row with event=rule_suspended • PUT /admin/rules/{id}/activate for a rule with direction=OUTBOUND succeeds (creates a DRAFT->ACTIVE OUTBOUND rule; routing still blocked by feature flag) | 55 | 5.8-T03 | BE | BRD-01, SAD-02
5.8-T19 | payment-executor | 5.8 | 5. Transaction Processing (MPM/CPM) | Direction routing & extensibility | 1 | Implement rule margin and service-charge update endpoint with cross-border minimum validation | PUT /admin/rules/{id}/margins updates m_a, m_b, service_charge_amount on a rule. Business rules: for cross-border rules (is_same_ccy_shortcircuit=false) m_a + m_b >= 0.02 (2.0%); for same-currency rules m_a = m_b = 0 (locked). service_charge_amount >= 0. Changes take effect for new transactions only; committed transactions retain locked values. Each changed field must produce an audit log entry per field (not one entry for the whole update) with previous_value and new_value per the spec example: {event:'rule_field_changed', rule_key:{partner,scheme,direction}, field:'m_a', previous_value:'1.00', new_value:'1.25'}. | • Implement AdminRuleController.updateMargins(long ruleId, UpdateMarginsRequest req): load rule; validate cross-border margin floor if !is_same_ccy_shortcircuit; validate same-currency margin is 0 if is_same_ccy_shortcircuit • Apply changes atomically; evict RuleRepository cache for the rule's key • For each field that changed, write a separate audit log entry: {event:'rule_field_changed', actor_user_id, timestamp_utc, rule_key, field, previous_value, new_value} • Return HTTP 200 with updated rule; return HTTP 422 with VALIDATION_ERROR if margin constraints violated • Write tests: cross-border m_a+m_b=0.015 rejected; same-currency m_a=0.01 rejected; valid update produces correct audit entries | AdminRuleController.updateMargins(), UpdateMarginsRequest.java, AdminRuleMarginUpdateTest.java | • Updating INBOUND rule (cross-border) to m_a=0.005, m_b=0.005 (sum=0.01) returns HTTP 422 VALIDATION_ERROR • Updating INBOUND rule to m_a=0.015, m_b=0.01 (sum=0.025) returns HTTP 200 • Updating DOMESTIC rule (same-currency) to m_a=0.01 returns HTTP 422 (must be 0) • Successful update produces one audit log entry per changed field with correct previous_value and new_value • After update, RuleRepository.findByKey() reflects new m_a and m_b values (cache evicted) | 45 | 5.8-T18 | BE | BRD-01, SAD-02
5.8-T20 | payment-executor | 5.8 | 5. Transaction Processing (MPM/CPM) | Direction routing & extensibility | 1 | Unit tests: SmartRouter full routing matrix across all four directions and feature flag states | Comprehensive unit test suite for SmartRouter covering all routing branches. Test matrix: 4 directions x 2 feature flag states x 3 partner types (LOCAL/OVERSEAS/missing) x 2 rule statuses (ACTIVE/DRAFT). Key invariants: DOMESTIC always routes to short-circuit; INBOUND always requires OVERSEAS partner and >= 2% margin; OUTBOUND/HUB blocked when feature flag false; OUTBOUND/HUB throw UnsupportedOperationException when feature flag true (Phase 1 stubs). | • Write parameterised unit tests for SmartRouter.resolveRoute() covering: DOMESTIC+LOCAL+ACTIVE->RouteContext with shortCircuit=true; INBOUND+OVERSEAS+ACTIVE+2%margin->RouteContext requiresPrefunding=true; OUTBOUND+flag=false->DirectionNotEnabledException; OUTBOUND+flag=true->UnsupportedOperationException; HUB+flag=false->DirectionNotEnabledException; HUB+flag=true->UnsupportedOperationException; INBOUND+LOCAL partner->RoutingIntegrityException; INBOUND+OVERSEAS+1% margin->RoutingIntegrityException; any direction+DRAFT rule->DirectionNotEnabledException; any direction+SUSPENDED rule->DirectionNotEnabledException • Use Mockito to mock RuleRepository, PartnerRepository, SchemeRepository, FeatureFlagService • Assert exact exception types, HTTP error codes, and RouteContext field values for success paths | SmartRouterMatrixTest.java with >= 14 parameterised test cases | • All 14+ routing matrix combinations have an explicit test case • DOMESTIC+LOCAL+ACTIVE returns shortCircuit=true, requiresPrefunding=false • INBOUND+OVERSEAS+m_a=0.01+m_b=0.01+ACTIVE returns shortCircuit=false, requiresPrefunding=true • OUTBOUND with flag=false throws DirectionNotEnabledException; with flag=true throws UnsupportedOperationException • INBOUND with LOCAL partner throws RoutingIntegrityException (not DirectionNotEnabledException) | 55 | 5.8-T09 | BE | BRD-01, SAD-02
5.8-T21 | payment-executor | 5.8 | 5. Transaction Processing (MPM/CPM) | Direction routing & extensibility | 1 | Unit tests: Rate engine for DOMESTIC short-circuit and INBOUND cross-border numeric examples | Explicit unit tests for the two canonical rate engine paths triggered by direction routing. DOMESTIC (short-circuit): target_payout=15000 KRW, service_charge=500 KRW -> collection_amount=15500 KRW; USD pool fields null; both rate sources IDENTITY. INBOUND cross-border (5-step): target_payout=50000 KRW, cost_rate_pay=1380.00 (usd_krw), cost_rate_coll=1.0 (IDENTITY), m_a=0.01, m_b=0.01, service_charge=0.36 USD -> payout_usd_cost=36.2319, collection_usd=36.9714, collection_margin_usd=0.3697, payout_margin_usd=0.3697, send_amount=36.9714, collection_amount=37.3314; pool identity holds within 0.01 USD tolerance. | • Write DomesticShortCircuitRateTest: call RateEngine.computeQuote with shortCircuit=true RouteContext; assert collection_amount=15500 KRW, payout_usd_cost=null, offer_rate_coll=1.0 • Write InboundCrossBorderRateTest: call RateEngine.computeQuote with shortCircuit=false RouteContext, m_a=0.01, m_b=0.01, cost_rate_pay=1380.00, cost_rate_coll=1.0, target_payout=50000 KRW; assert each step output within tolerance 0.0001 • Assert pool identity: collection_usd - collection_margin_usd - payout_margin_usd == payout_usd_cost within 0.01 USD • Assert offer_rate_coll = send_amount / (collection_usd - collection_margin_usd) = 36.9714 / (36.9714 - 0.3697) = 36.9714/36.6017 = 1.01010 within tolerance 0.0001 • Assert bok_form_type=EXEMPT for DOMESTIC and FX1015 for INBOUND | DomesticShortCircuitRateTest.java, InboundCrossBorderRateTest.java | • DOMESTIC: collection_amount=15500, payout_usd_cost=null, collection_usd=null, offer_rate_coll=1.0 • INBOUND: payout_usd_cost=36.2319 (tolerance 0.0001), collection_usd=36.9714, collection_margin_usd=0.3697, payout_margin_usd=0.3697 • INBOUND pool identity: 36.9714 - 0.3697 - 0.3697 = 36.2320 == payout_usd_cost within 0.01 USD • INBOUND offer_rate_coll=1.01010 within tolerance 0.0001 • DOMESTIC bok_form_type=EXEMPT; INBOUND bok_form_type=FX1015 | 45 | 5.8-T11 | BE | BRD-01, SAD-02
5.8-T22 | payment-executor | 5.8 | 5. Transaction Processing (MPM/CPM) | Direction routing & extensibility | 1 | Unit tests: DIRECTION_NOT_ENABLED and routing error API responses | Integration tests verifying the complete HTTP response for direction-related errors. Test that DIRECTION_NOT_ENABLED is returned as HTTP 422 with retryable=false when OUTBOUND is requested; that a missing or DRAFT rule also returns DIRECTION_NOT_ENABLED; that a DOMESTIC short-circuit route returns the expected collection_amount=target_payout+service_charge with no USD pool fields; and that direction mismatch at commit time returns RATE_QUOTE_INVALID. | • Write MockMvc test GET /v1/rates direction=outbound -> HTTP 422 {error_code:'DIRECTION_NOT_ENABLED', retryable:false} • Write MockMvc test GET /v1/rates direction=domestic with active GME Remit rule -> HTTP 200 response includes direction='DOMESTIC', collection_amount=15500, no payout_usd_cost field • Write MockMvc test GET /v1/rates with no active rule for (partner, scheme, INBOUND) -> HTTP 422 {error_code:'DIRECTION_NOT_ENABLED'} • Write MockMvc test POST /v1/payments with direction=DOMESTIC but locked quote.direction=INBOUND -> HTTP 422 {error_code:'RATE_QUOTE_INVALID'} • Write MockMvc test GET /v1/rates direction=hub -> HTTP 422 {error_code:'DIRECTION_NOT_ENABLED'} | DirectionApiErrorTest.java with 5+ MockMvc test cases | • direction=outbound returns HTTP 422 with error_code=DIRECTION_NOT_ENABLED and retryable=false • direction=domestic (short-circuit active rule) returns HTTP 200 with collection_amount present and payout_usd_cost absent from response body • direction=inbound with no ACTIVE rule returns HTTP 422 DIRECTION_NOT_ENABLED • direction mismatch at commit returns HTTP 422 RATE_QUOTE_INVALID • direction=hub returns HTTP 422 DIRECTION_NOT_ENABLED (feature flag false) | 45 | 5.8-T17 | BE | BRD-01, SAD-02
5.8-T23 | payment-executor | 5.8 | 5. Transaction Processing (MPM/CPM) | Direction routing & extensibility | 1 | Add direction routing config to Admin UI: display and validate direction field on rule create | PRD-07 §6.3 states that to create a rule the operator selects Partner, QR Scheme, and Direction (INBOUND/OUTBOUND/DOMESTIC/HUB). The backend Create Rule endpoint (5.8-T18) must accept and validate the direction selection. This ticket covers the backend API contract for the Admin UI rule creation flow, specifically the direction validation logic and the response that drives the UI's currency-setup section (Section 1 of the Mapping Page). The UI calls POST /admin/rules with {partner_id, scheme_id, direction} and receives back the auto-derived currency quadruple. | • CreateRuleRequest DTO: add direction field (String, required) with validation Direction.fromString() • In AdminRuleService.createRule(): derive currency quadruple from partner.collection_currency, partner.settlement_currency, scheme.settlement_currency, scheme.payout_currency; set is_same_ccy_shortcircuit = (all four equal) • Return CreateRuleResponse with: rule_id, status='DRAFT', direction, collection_ccy, settle_a_ccy, settle_b_ccy, payout_ccy, is_same_ccy_shortcircuit • For direction=DOMESTIC: validate that is_same_ccy_shortcircuit is true for the given partner+scheme combination; if not, return HTTP 422 with error message 'DOMESTIC direction requires same-currency partner-scheme combination' • Write tests: DOMESTIC direction with KRW/KRW/KRW/KRW currencies returns is_same_ccy_shortcircuit=true; INBOUND direction with MNT/USD/KRW/KRW returns is_same_ccy_shortcircuit=false | Updated CreateRuleRequest.java, updated AdminRuleService.createRule() with currency derivation, AdminRuleCreateDirectionTest.java | • POST /admin/rules {partner_id:GME_REMIT, scheme_id:ZEROPAY, direction:'DOMESTIC'} returns {direction:'DOMESTIC', collection_ccy:'KRW', settle_a_ccy:'KRW', settle_b_ccy:'KRW', payout_ccy:'KRW', is_same_ccy_shortcircuit:true} • POST /admin/rules {partner_id:SENDMN, scheme_id:ZEROPAY, direction:'INBOUND'} returns {direction:'INBOUND', collection_ccy:'MNT', settle_a_ccy:'USD', settle_b_ccy:'KRW', payout_ccy:'KRW', is_same_ccy_shortcircuit:false} • POST /admin/rules with direction='DOMESTIC' for a cross-currency partner returns HTTP 422 • POST /admin/rules with direction='INVALID_DIR' returns HTTP 400 • POST /admin/rules with direction='HUB' creates a DRAFT rule (no feature flag check at rule creation time; flag only checked at transaction time) | 45 | 5.8-T18 | BE | BRD-01, SAD-02
5.8-T24 | payment-executor | 5.8 | 5. Transaction Processing (MPM/CPM) | Direction routing & extensibility | 1 | Integration test: end-to-end DOMESTIC payment routing via SmartRouter through to transaction commit | End-to-end integration test for the DOMESTIC direction routing path: from GET /v1/rates through SmartRouter -> RateEngine (short-circuit) -> redis quote store -> POST /v1/payments commit -> transaction persisted with direction=DOMESTIC. Uses an in-memory H2 or Testcontainers Postgres DB. Partner: GME Remit (LOCAL, KRW). Scheme: ZeroPay (payout_ccy=KRW). Rule: ACTIVE, is_same_ccy_shortcircuit=true, m_a=0, m_b=0, service_charge=500 KRW. Target payout: 15000 KRW. Expected collection_amount: 15500 KRW. | • Set up test data: insert partner (GME_REMIT, type=LOCAL, collection_currency=KRW, settlement_currency=KRW), scheme (ZEROPAY, payout_currency=KRW), and rule (direction=DOMESTIC, is_same_ccy_shortcircuit=true, m_a=0, m_b=0, service_charge=500, status=ACTIVE) • Call GET /v1/rates with direction=domestic, target_payout=15000, payout_currency=KRW; assert HTTP 200 and collection_amount=15500 • Extract quote_id from response; call POST /v1/payments with same direction=domestic and quote_id • Assert HTTP 201 from commit; assert transaction row in DB with direction='DOMESTIC', status=APPROVED (or SCHEME_SENT), collection_amount=15500, payout_usd_cost=NULL • Assert no entry in prefunding_ledger (LOCAL partner, no prefunding deduction) | DomesticPaymentRoutingIntegrationTest.java | • GET /v1/rates returns collection_amount=15500 KRW with no payout_usd_cost field in response • POST /v1/payments returns HTTP 201 with status in {APPROVED, SCHEME_SENT} • transaction.direction='DOMESTIC' in DB after commit • transaction.payout_usd_cost=NULL in DB (short-circuit applied) • prefunding_ledger has zero rows for this partner after the payment (LOCAL partner, no deduction) | 55 | 5.8-T22 | BE | BRD-01, SAD-02
5.8-T25 | payment-executor | 5.8 | 5. Transaction Processing (MPM/CPM) | Direction routing & extensibility | 1 | Integration test: end-to-end INBOUND payment routing via SmartRouter through to transaction commit | End-to-end integration test for the INBOUND direction routing path. Partner: SendMN (OVERSEAS, collection_currency=MNT, settlement_currency=USD). Scheme: ZeroPay (payout_currency=KRW, settle_b_ccy=KRW). Rule: ACTIVE, is_same_ccy_shortcircuit=false, m_a=0.01, m_b=0.01, service_charge=0.36 USD, status=ACTIVE. Treasury: usd_krw=1380.00, usd_usd=1.0. Target payout: 50000 KRW. Expected payout_usd_cost=36.2319, collection_usd=36.9714, collection_amount=37.3314 USD. Prefunding balance must be >= 36.9714 USD before the test. | • Set up test data: insert partner SENDMN (OVERSEAS, collection_currency=USD, settlement_currency=USD), prefunding_account with balance=200.00 USD, scheme ZEROPAY, rule (INBOUND, m_a=0.01, m_b=0.01, service_charge=0.36, status=ACTIVE), treasury rows usd_krw=1380.00 • Call GET /v1/rates with direction=inbound, target_payout=50000, payout_currency=KRW; assert HTTP 200, collection_usd approx 36.97 • Capture quote_id; call POST /v1/payments with direction=inbound; assert HTTP 201 • Assert transaction row: direction='INBOUND', collection_usd=36.9714 (tolerance 0.01), bok_form_type='FX1015' • Assert prefunding_account.balance decreased by 36.9714 USD (tolerance 0.01); assert one DEBIT_PAYMENT ledger entry | InboundPaymentRoutingIntegrationTest.java | • GET /v1/rates returns payout_usd_cost approx 36.23 and collection_usd approx 36.97 (tolerance 0.01) • POST /v1/payments returns HTTP 201 • transaction.direction='INBOUND', transaction.bok_form_type='FX1015' in DB • prefunding_account.balance after payment = 200.00 - 36.9714 = 163.0286 USD (tolerance 0.01) • Pool identity holds: collection_usd - collection_margin_usd - payout_margin_usd == payout_usd_cost within 0.01 USD in the stored transaction row | 55 | 5.8-T24 | BE | BRD-01, SAD-02
6.1-T01 | prefunding | 6.1 | 6. Prefunding & Wallet Ledger | Prefunding balance & top-up recording | 1 | Migration: create prefunding_account table | GMEPay+ Balance Service manages prepaid USD balances for OVERSEAS partners only. The prefunding_account table holds one row per OVERSEAS partner: id BIGINT PK, partner_id BIGINT FK->partner UNIQUE NOT NULL, currency CHAR(3) NOT NULL DEFAULT 'USD', balance DECIMAL(20,4) NOT NULL DEFAULT 0.0000 CHECK(balance >= 0), low_balance_threshold DECIMAL(20,4) NOT NULL DEFAULT 10000.0000, created_at TIMESTAMPTZ NOT NULL DEFAULT NOW(), updated_at TIMESTAMPTZ NOT NULL, created_by VARCHAR(120), updated_by VARCHAR(120). Balance updates must use SELECT FOR UPDATE; no application-level locking. LOCAL partners (partner_type='LOCAL') must never have a prefunding_account row. | • Create Flyway (or Liquibase) migration file V6_1_001__create_prefunding_account.sql • Add table DDL with all columns, types, and constraints exactly as specified • Add index on partner_id (already UNIQUE, confirm it exists) • Add FK constraint partner_id -> partner(id) • Add CHECK constraint that currency = 'USD' | Migration file V6_1_001__create_prefunding_account.sql that applies cleanly on a fresh schema | • Migration runs without error on empty schema and on schema with existing partner rows • SELECT * FROM prefunding_account returns 0 rows after migration (table starts empty) • Attempt to INSERT a row with balance = -0.01 is rejected by CHECK constraint • Attempt to INSERT two rows with the same partner_id is rejected by UNIQUE constraint • Column currency DEFAULT is 'USD' and CHECK rejects any other value | 25 |  | BE | DAT-03, PRD-07
6.1-T02 | prefunding | 6.1 | 6. Prefunding & Wallet Ledger | Prefunding balance & top-up recording | 1 | Migration: create prefunding_ledger_entry table | prefunding_ledger_entry is an append-only, immutable ledger. Every balance change (debit or credit) produces one row. Schema: id BIGINT PK auto-increment, account_id BIGINT NOT NULL FK->prefunding_account, txn_ref VARCHAR(64) NULL (populated for DEBIT_PAYMENT/DEBIT_REVERSAL; NULL for CREDIT_TOPUP/CREDIT_REVERSAL), entry_type VARCHAR(20) NOT NULL CHECK IN ('DEBIT_PAYMENT','DEBIT_REVERSAL','CREDIT_TOPUP','CREDIT_REVERSAL'), amount DECIMAL(20,4) NOT NULL CHECK(amount > 0) -- direction is indicated by entry_type, NOT sign, balance_after DECIMAL(20,4) NOT NULL, note VARCHAR(255) NULL, created_at TIMESTAMPTZ NOT NULL DEFAULT NOW(), created_by VARCHAR(120) NULL. No updated_at column. Index on (account_id, created_at) for history queries. | • Create migration file V6_1_002__create_prefunding_ledger_entry.sql • Add table DDL with all columns exactly as specified • Add composite index idx_ple_account_created ON prefunding_ledger_entry(account_id, created_at) • Add FK constraint account_id -> prefunding_account(id) • Add CHECK constraint on entry_type and CHECK(amount > 0) | Migration file V6_1_002__create_prefunding_ledger_entry.sql | • Migration applies cleanly after V6_1_001 • INSERT with amount = 0 is rejected by CHECK constraint • INSERT with amount = -5.00 is rejected by CHECK constraint • INSERT with entry_type = 'UNKNOWN' is rejected by CHECK constraint • Table has no updated_at column (immutability enforced at schema level) • EXPLAIN on SELECT ... WHERE account_id=1 ORDER BY created_at uses the composite index | 25 | 6.1-T01 | BE | DAT-03, PRD-07
6.1-T03 | prefunding | 6.1 | 6. Prefunding & Wallet Ledger | Prefunding balance & top-up recording | 1 | Migration: create low_balance_alert_config table | low_balance_alert_config stores per-partner alert settings. Schema: id BIGINT PK, partner_id BIGINT FK->partner UNIQUE NOT NULL, threshold_usd DECIMAL(20,4) NOT NULL DEFAULT 10000.0000, alert_email VARCHAR(255) NOT NULL, is_active BOOLEAN NOT NULL DEFAULT TRUE, created_at TIMESTAMPTZ NOT NULL DEFAULT NOW(), updated_at TIMESTAMPTZ NOT NULL, created_by VARCHAR(120), updated_by VARCHAR(120). One row per partner. A partner may have at most one active alert config. The threshold defaults to 10000.00 (USD 10,000). This table is separate from prefunding_account.low_balance_threshold to allow the alert email to be managed independently. | • Create migration file V6_1_003__create_low_balance_alert_config.sql • Add table DDL with all columns and constraints • Add UNIQUE constraint on partner_id • Add CHECK constraint threshold_usd > 0 | Migration file V6_1_003__create_low_balance_alert_config.sql | • Migration applies cleanly after prior two migrations • UNIQUE constraint prevents two rows with the same partner_id • CHECK rejects threshold_usd = 0 or negative • Default threshold_usd = 10000.0000 is applied when not supplied • Default is_active = TRUE is applied when not supplied | 20 | 6.1-T01 | BE | DAT-03, PRD-07
6.1-T04 | prefunding | 6.1 | 6. Prefunding & Wallet Ledger | Prefunding balance & top-up recording | 1 | JPA entity: PrefundingAccount | The Balance Service is a Spring Boot / Java service using JPA (Hibernate) + PostgreSQL. Map the prefunding_account table to a JPA entity. Fields: id (Long), partner (ManyToOne lazy to Partner entity, UNIQUE), currency (String, always USD), balance (BigDecimal scale 4), lowBalanceThreshold (BigDecimal scale 4), createdAt, updatedAt, createdBy, updatedBy. Use @Version for optimistic locking on the balance field as a secondary guard (primary guard is SELECT FOR UPDATE at the service layer). The entity must use DECIMAL arithmetic; never use double or float for monetary fields. | • Create class PrefundingAccount.java in the balance service domain package • Annotate with @Entity, @Table(name='prefunding_account') • Map all columns using @Column with correct precision/scale (DECIMAL(20,4) maps to precision=20, scale=4) • Add @Version Long version field for optimistic locking • Add @OneToOne(optional=false) or @ManyToOne to Partner entity • Add standard audit fields with @CreationTimestamp / @UpdateTimestamp | PrefundingAccount.java JPA entity | • Entity round-trips through save/findById in a @DataJpaTest with an in-memory or Testcontainers Postgres without data loss • balance field retains 4 decimal places (e.g. 50000.1234 stored and retrieved exactly) • Inserting two PrefundingAccount rows with the same partner_id throws a constraint violation • Field types are BigDecimal, never double or float • @Version field increments on each update, confirming optimistic locking is active | 30 | 6.1-T01 | BE | DAT-03, PRD-07
6.1-T05 | prefunding | 6.1 | 6. Prefunding & Wallet Ledger | Prefunding balance & top-up recording | 1 | JPA entity: PrefundingLedgerEntry | Map the prefunding_ledger_entry table to an immutable JPA entity. Fields: id (Long), account (ManyToOne to PrefundingAccount, non-null), txnRef (String nullable, maps to txn_ref), entryType (enum: DEBIT_PAYMENT, DEBIT_REVERSAL, CREDIT_TOPUP, CREDIT_REVERSAL stored as VARCHAR(20)), amount (BigDecimal scale 4, always positive), balanceAfter (BigDecimal scale 4), note (String nullable), createdAt (Instant, @CreationTimestamp), createdBy (String nullable). No updatedAt. The entity must be effectively immutable after creation; do not expose setters for any field except via the constructor. Define a factory static method or constructor that validates amount > 0. | • Create PrefundingLedgerEntry.java entity in domain package • Map all columns; use @Enumerated(EnumType.STRING) for entryType • Add all-args constructor and no-args protected constructor (JPA requirement) • Add factory method PrefundingLedgerEntry.create(...) that asserts amount.compareTo(BigDecimal.ZERO) > 0 • Ensure no setter methods are public (entity is append-only) | PrefundingLedgerEntry.java JPA entity | • Calling create() with amount=0 throws IllegalArgumentException • Calling create() with amount=-1.00 throws IllegalArgumentException • Entity can be persisted via JPA and retrieved with all fields intact • entryType is stored as the string 'CREDIT_TOPUP' not an ordinal integer • No public setter exists for id, amount, balanceAfter, entryType, or createdAt | 25 | 6.1-T02, 6.1-T04 | BE | DAT-03, PRD-07
6.1-T06 | prefunding | 6.1 | 6. Prefunding & Wallet Ledger | Prefunding balance & top-up recording | 1 | JPA entity: LowBalanceAlertConfig | Map the low_balance_alert_config table to a JPA entity. Fields: id (Long), partner (ManyToOne to Partner, UNIQUE), thresholdUsd (BigDecimal scale 4, default 10000.0000), alertEmail (String, not null), isActive (Boolean, default true), standard audit fields. This entity is used by the alert-check logic in the balance service after each balance change. | • Create LowBalanceAlertConfig.java entity in domain package • Map all columns with correct @Column annotations • Add validation annotation @Email on alertEmail field • Add @NotNull on alertEmail and partner fields • Add standard @CreationTimestamp / @UpdateTimestamp audit fields | LowBalanceAlertConfig.java JPA entity | • Entity persists and loads correctly in a @DataJpaTest • alertEmail stored and retrieved exactly as entered • thresholdUsd defaults to 10000.0000 when not set • Two rows with the same partner_id cannot be inserted (constraint violation thrown) • isActive defaults to true | 20 | 6.1-T03 | BE | DAT-03, PRD-07
6.1-T07 | prefunding | 6.1 | 6. Prefunding & Wallet Ledger | Prefunding balance & top-up recording | 1 | Repository interfaces for prefunding entities | Create Spring Data JPA repository interfaces for the three prefunding entities. PrefundingAccountRepository must include: findByPartnerId(Long partnerId), findByPartnerIdWithLock (using @Lock(PESSIMISTIC_WRITE) + @QueryHints for SELECT FOR UPDATE), and findAll for dashboard listing. PrefundingLedgerEntryRepository must include: findByAccountIdOrderByCreatedAtDesc(Long accountId, Pageable pageable) for history paging. LowBalanceAlertConfigRepository must include: findByPartnerIdAndIsActiveTrue(Long partnerId). | • Create PrefundingAccountRepository extending JpaRepository<PrefundingAccount, Long> • Add findByPartnerId and a @Lock(PESSIMISTIC_WRITE) variant named findByPartnerIdForUpdate • Create PrefundingLedgerEntryRepository with paged history query • Create LowBalanceAlertConfigRepository with active-config lookup • Add @Repository annotations and correct package placement | Three repository interfaces: PrefundingAccountRepository, PrefundingLedgerEntryRepository, LowBalanceAlertConfigRepository | • findByPartnerId returns empty Optional for unknown partner_id • findByPartnerIdForUpdate acquires a row-level lock (verified via EXPLAIN in integration test or by observing lock wait in concurrent test) • findByAccountIdOrderByCreatedAtDesc returns entries newest-first • findByPartnerIdAndIsActiveTrue returns empty Optional when is_active=false • All three interfaces load in Spring context without errors | 25 | 6.1-T04, 6.1-T05, 6.1-T06 | BE | DAT-03, PRD-07
6.1-T08 | prefunding | 6.1 | 6. Prefunding & Wallet Ledger | Prefunding balance & top-up recording | 1 | Service interface: PrefundingBalanceService | Define the Java service interface (contract) for all prefunding balance operations. Methods needed: (1) PrefundingAccount createAccount(Long partnerId) -- creates a zero-balance account for an OVERSEAS partner; (2) PrefundingAccount getBalance(Long partnerId) -- reads current balance; (3) PrefundingAccount recordTopUp(TopUpCommand cmd) -- credits balance and writes CREDIT_TOPUP ledger entry; (4) PrefundingAccount deductBalance(DeductCommand cmd) -- atomically debits balance (SELECT FOR UPDATE) and writes DEBIT_PAYMENT entry; (5) Page<PrefundingLedgerEntry> getLedgerHistory(Long partnerId, Pageable pageable). Also define the command record/DTO classes TopUpCommand and DeductCommand with fields: partnerId, amountUsd, reference, note, actorId. | • Create interface PrefundingBalanceService.java in the service package • Define all five method signatures with Javadoc • Create TopUpCommand record: partnerId (Long), amountUsd (BigDecimal), bankRef (String), valueDate (LocalDate), notes (String nullable), actorId (String) • Create DeductCommand record: partnerId (Long), amountUsd (BigDecimal), txnRef (String), actorId (String) • Ensure command records use BigDecimal, not double | PrefundingBalanceService.java interface plus TopUpCommand.java and DeductCommand.java record/DTO classes | • Interface compiles with zero warnings • TopUpCommand and DeductCommand are immutable (final fields or records) • All monetary fields in commands are BigDecimal • Interface Javadoc describes the SELECT FOR UPDATE requirement for deductBalance • No implementation code in this ticket -- interface only | 20 | 6.1-T04, 6.1-T05 | BE | DAT-03, PRD-07
6.1-T09 | prefunding | 6.1 | 6. Prefunding & Wallet Ledger | Prefunding balance & top-up recording | 1 | Implement createAccount: initialise zero-balance prefunding account | PrefundingBalanceServiceImpl.createAccount(Long partnerId) must: (1) verify the partner exists and has partner_type='OVERSEAS' -- throw PartnerNotFoundException or InvalidPartnerTypeException otherwise; (2) check no prefunding_account already exists for this partner -- throw DuplicateAccountException if it does; (3) create a PrefundingAccount with balance=0.0000, currency='USD', low_balance_threshold=10000.0000; (4) persist and return. This is called once at partner onboarding. Partner entity has fields id, partnerCode, partnerType (enum LOCAL¦OVERSEAS). | • Implement createAccount in PrefundingBalanceServiceImpl • Add partner type guard: throw InvalidPartnerTypeException('Partner {partnerCode} is LOCAL; prefunding accounts are OVERSEAS only') if type != OVERSEAS • Add duplicate guard: if findByPartnerId returns non-empty, throw DuplicateAccountException • Set balance=BigDecimal.ZERO scaled to 4 decimal places, currency='USD', lowBalanceThreshold=10000.0000 • Save and return the persisted entity | PrefundingBalanceServiceImpl.createAccount() method | • Calling createAccount for a LOCAL partner throws InvalidPartnerTypeException • Calling createAccount twice for the same OVERSEAS partner throws DuplicateAccountException on second call • Returned account has balance=0.0000, currency='USD', lowBalanceThreshold=10000.0000 • Persisted row is retrievable via findByPartnerId after creation • createAccount for a valid OVERSEAS partner writes exactly one row to prefunding_account | 30 | 6.1-T07, 6.1-T08 | BE | DAT-03, PRD-07
6.1-T10 | prefunding | 6.1 | 6. Prefunding & Wallet Ledger | Prefunding balance & top-up recording | 1 | Implement getBalance: read current prefunding balance | PrefundingBalanceServiceImpl.getBalance(Long partnerId) reads the current balance for an OVERSEAS partner. It must: (1) look up the prefunding_account for the given partnerId; (2) throw PrefundingAccountNotFoundException (with message 'No prefunding account for partner {id}') if not found; (3) return the PrefundingAccount entity (balance is the authoritative current value). This method does NOT use SELECT FOR UPDATE -- it is a read-only snapshot. Callers needing atomic read-modify-write must use deductBalance instead. | • Implement getBalance in PrefundingBalanceServiceImpl using findByPartnerId • Throw PrefundingAccountNotFoundException if account is absent • Annotate method with @Transactional(readOnly=true) • Return the PrefundingAccount entity directly • Add logging at DEBUG level: partner_id and balance returned | PrefundingBalanceServiceImpl.getBalance() method | • getBalance for unknown partner_id throws PrefundingAccountNotFoundException • getBalance returns the current balance value without acquiring a write lock (verify via @Transactional(readOnly=true) annotation) • getBalance for a partner with balance=12345.6789 returns exactly BigDecimal('12345.6789') • Method is annotated @Transactional(readOnly=true) • No INSERT or UPDATE SQL is executed during getBalance (verified via query count in test) | 20 | 6.1-T09 | BE | DAT-03, PRD-07
6.1-T11 | prefunding | 6.1 | 6. Prefunding & Wallet Ledger | Prefunding balance & top-up recording | 1 | Implement recordTopUp: credit balance and write CREDIT_TOPUP ledger entry | PrefundingBalanceServiceImpl.recordTopUp(TopUpCommand cmd) is the core top-up operation. It must execute atomically in a single DB transaction: (1) acquire row lock via findByPartnerIdForUpdate; (2) validate amountUsd > 0 and bankRef is non-blank; (3) add amountUsd to balance: newBalance = account.balance + cmd.amountUsd; (4) update account.balance = newBalance, account.updatedBy = cmd.actorId; (5) create PrefundingLedgerEntry(entryType=CREDIT_TOPUP, amount=cmd.amountUsd, balanceAfter=newBalance, txnRef=null, note=cmd.notes, createdBy=cmd.actorId); (6) save both entities in the same transaction; (7) after commit, publish prefunding.balance_updated event (async, for alert check). Example: balance=30000.00 + topUp=20000.00 -> newBalance=50000.00; ledger entry amount=20000.00, balance_after=50000.00. | • Implement recordTopUp annotated @Transactional(isolation=REPEATABLE_READ) • Lock the account row using findByPartnerIdForUpdate • Validate cmd.amountUsd > 0 else throw InvalidAmountException • Validate cmd.bankRef is not blank else throw MissingReferenceException • Compute newBalance and update account.balance • Create and save PrefundingLedgerEntry with CREDIT_TOPUP • Publish prefunding.balance_updated ApplicationEvent after transaction (use @TransactionalEventListener) | PrefundingBalanceServiceImpl.recordTopUp() method | • recordTopUp(partnerId=1, amount=20000.00, bankRef='WIRE-001') with initial balance=30000.00 results in balance=50000.00 • A CREDIT_TOPUP ledger entry with amount=20000.00 and balance_after=50000.00 is persisted • recordTopUp with amount=0 throws InvalidAmountException (no balance change, no ledger entry) • recordTopUp with blank bankRef throws MissingReferenceException • Concurrent calls from two threads with amounts 5000.00 and 3000.00 result in exactly one of {38000.00, 38000.00} -- never a lost update (run 10 iterations) • Two ledger entries are written for two sequential top-ups; both have correct balance_after values | 45 | 6.1-T08, 6.1-T09 | BE | DAT-03, PRD-07
6.1-T12 | prefunding | 6.1 | 6. Prefunding & Wallet Ledger | Prefunding balance & top-up recording | 1 | Implement deductBalance: atomic SELECT FOR UPDATE debit with DEBIT_PAYMENT entry | PrefundingBalanceServiceImpl.deductBalance(DeductCommand cmd) is called by the Transaction Orchestrator before each scheme call (AD-06 in SAD-02). Rules: (1) acquire row lock via findByPartnerIdForUpdate within @Transactional; (2) if account.balance < cmd.amountUsd throw InsufficientPrefundingException (error code INSUFFICIENT_PREFUNDING) -- scheme is NEVER called; (3) newBalance = account.balance - cmd.amountUsd; (4) update account.balance = newBalance; (5) create PrefundingLedgerEntry(entryType=DEBIT_PAYMENT, amount=cmd.amountUsd, balanceAfter=newBalance, txnRef=cmd.txnRef, createdBy=cmd.actorId); (6) save both; (7) publish prefunding.balance_updated event. GMEPay+ debits by collection_usd (the USD pool amount), not collection_amount. Example: balance=10000.00, deduct=1234.5678 -> newBalance=8765.4322; ledger entry amount=1234.5678, balance_after=8765.4322. | • Implement deductBalance annotated @Transactional(isolation=REPEATABLE_READ) • Lock account row using findByPartnerIdForUpdate • Check balance >= amountUsd; throw InsufficientPrefundingException with message matching 'INSUFFICIENT_PREFUNDING' if not • Compute newBalance = account.balance.subtract(cmd.amountUsd) -- use BigDecimal.subtract, never double • Persist updated account and DEBIT_PAYMENT ledger entry in same transaction • Publish balance_updated event after commit | PrefundingBalanceServiceImpl.deductBalance() method | • deductBalance(amount=1234.5678) from balance=10000.00 results in balance=8765.4322 and ledger entry amount=1234.5678, balance_after=8765.4322 • deductBalance(amount=10000.01) from balance=10000.00 throws InsufficientPrefundingException and balance remains 10000.00 • deductBalance(amount=10000.00) from balance=10000.00 succeeds with newBalance=0.00 • Two concurrent threads each deducting 6000.00 from a 10000.00 balance: exactly one succeeds and one throws InsufficientPrefundingException (run 20 iterations) • txnRef on the ledger entry matches cmd.txnRef exactly • No row is written to prefunding_ledger_entry if InsufficientPrefundingException is thrown | 45 | 6.1-T08, 6.1-T09 | BE | DAT-03, PRD-07
6.1-T13 | prefunding | 6.1 | 6. Prefunding & Wallet Ledger | Prefunding balance & top-up recording | 1 | Implement reverseDeduction: write DEBIT_REVERSAL ledger entry and restore balance | When reconciliation confirms a previously UNCERTAIN transaction has FAILED, the Transaction Orchestrator calls reverseDeduction to restore the prefunding balance. Signature: reverseDeduction(ReverseDeductCommand cmd) where cmd has partnerId, amountUsd, originalTxnRef, actorId. Steps: (1) acquire row lock; (2) newBalance = account.balance + cmd.amountUsd; (3) update account; (4) create PrefundingLedgerEntry(entryType=DEBIT_REVERSAL, txnRef=cmd.originalTxnRef, amount=cmd.amountUsd, balanceAfter=newBalance, note='Reversal for UNCERTAIN resolution', createdBy=cmd.actorId). DEBIT_REVERSAL is a credit (restores balance) but entry_type name reflects its origin. The amount field stays positive per schema CHECK. | • Add ReverseDeductCommand record to service layer • Implement reverseDeduction in PrefundingBalanceServiceImpl with @Transactional • Lock row, compute newBalance = balance + amountUsd • Persist updated account and DEBIT_REVERSAL ledger entry • Publish prefunding.balance_updated event post-commit • Add to PrefundingBalanceService interface | PrefundingBalanceServiceImpl.reverseDeduction() method and ReverseDeductCommand record | • reverseDeduction(amount=1000.00) on account with balance=5000.00 results in balance=6000.00 • DEBIT_REVERSAL entry has amount=1000.00 (positive), balance_after=6000.00, txnRef matching originalTxnRef • reverseDeduction with unknown partnerId throws PrefundingAccountNotFoundException • amount=0 in ReverseDeductCommand throws InvalidAmountException • Ledger history for the account shows the reversal entry newest-first after subsequent getLedgerHistory call | 30 | 6.1-T12 | BE | DAT-03, PRD-07
6.1-T14 | prefunding | 6.1 | 6. Prefunding & Wallet Ledger | Prefunding balance & top-up recording | 1 | Implement getLedgerHistory: paged ledger entry retrieval | PrefundingBalanceServiceImpl.getLedgerHistory(Long partnerId, Pageable pageable) returns the ledger history for a partner newest-first. Steps: (1) resolve account via findByPartnerId or throw PrefundingAccountNotFoundException; (2) delegate to PrefundingLedgerEntryRepository.findByAccountIdOrderByCreatedAtDesc(accountId, pageable); (3) return a Page<PrefundingLedgerEntry>. Typical page size for Admin Portal is 50 entries. The query uses the composite index (account_id, created_at) for efficiency. | • Implement getLedgerHistory annotated @Transactional(readOnly=true) • Resolve account_id from partnerId via findByPartnerId • Call ledger repository with provided Pageable • Return the Page result unchanged • Add method to PrefundingBalanceService interface | PrefundingBalanceServiceImpl.getLedgerHistory() method | • getLedgerHistory for unknown partnerId throws PrefundingAccountNotFoundException • getLedgerHistory page 0 size 2 returns the 2 most recent entries in descending created_at order • getTotalElements returns correct count across all pages • getLedgerHistory returns an empty page (not null) for an account with no entries • Query uses composite index (verified via EXPLAIN SELECT in integration test) | 25 | 6.1-T10, 6.1-T11 | BE | DAT-03, PRD-07
6.1-T15 | prefunding | 6.1 | 6. Prefunding & Wallet Ledger | Prefunding balance & top-up recording | 1 | Low-balance alert check: post-balance-change threshold evaluation | After every successful balance change (deduct or top-up), the Balance Service must check whether an alert should be fired. Logic: (1) load LowBalanceAlertConfig where partner_id = X and is_active = true; (2) if not found, skip; (3) if account.balance < config.thresholdUsd AND balance was NOT below threshold before this change, publish event prefunding.low_balance (AlertType=LOW_BALANCE); (4) if account.balance <= 0, publish prefunding.low_balance (AlertType=CRITICAL_ZERO) regardless of previous state. Do NOT block the transaction for alert evaluation. Use @TransactionalEventListener(phase=AFTER_COMMIT) on a BalanceAlertChecker component that listens to the prefunding.balance_updated event emitted by recordTopUp and deductBalance. | • Create BalanceAlertChecker @Component with @TransactionalEventListener(phase=AFTER_COMMIT) on BalanceUpdatedEvent • Receive BalanceUpdatedEvent(partnerId, newBalance, previousBalance) from recordTopUp/deductBalance • Load LowBalanceAlertConfig; if absent or isActive=false, return • Check newBalance <= 0 -> publish PrefundingAlertEvent(CRITICAL_ZERO) • Check newBalance < thresholdUsd AND previousBalance >= thresholdUsd -> publish PrefundingAlertEvent(LOW_BALANCE) • Log the alert event at WARN level with partner_id, newBalance, threshold | BalanceAlertChecker.java component and BalanceUpdatedEvent / PrefundingAlertEvent classes | • deductBalance that takes balance from 15000.00 to 9000.00 (threshold=10000.00) publishes exactly one LOW_BALANCE event • deductBalance that takes balance from 9000.00 to 8000.00 (both below threshold=10000.00) does NOT publish LOW_BALANCE again • deductBalance that takes balance to 0.00 publishes CRITICAL_ZERO • recordTopUp that restores balance from 8000.00 to 15000.00 does NOT publish LOW_BALANCE • Alert check failure (e.g. email config missing) does not roll back the balance transaction | 35 | 6.1-T12, 6.1-T13, 6.1-T06 | BE | DAT-03, PRD-07
6.1-T16 | prefunding | 6.1 | 6. Prefunding & Wallet Ledger | Prefunding balance & top-up recording | 1 | Email notification for low-balance and critical-zero alerts | The NotificationService must listen to PrefundingAlertEvent and send an email to config.alertEmail. Email content per alert type: LOW_BALANCE: subject 'GMEPay+ Low Prefunding Balance Alert - {partnerName}', body includes partner name, current balance (formatted as USD X,XXX.XX), threshold, and suggested top-up = threshold * 2 - currentBalance. CRITICAL_ZERO: subject 'URGENT: GMEPay+ Prefunding Balance Exhausted - {partnerName}', body includes current balance = USD 0.00, all payments suspended, contact GME Finance immediately. Emails are sent via the platform EmailService bean (already exists). Phase 1: one alert_email per partner. Alert fires for both deductBalance and reverseDeduction events. | • Create PrefundingAlertEmailListener @Component listening to PrefundingAlertEvent • Inject EmailService and LowBalanceAlertConfigRepository • For LOW_BALANCE: build subject and body with balance formatted to 2 decimal places, suggested top-up = threshold*2 - balance • For CRITICAL_ZERO: build urgent subject and body • Call emailService.send(to, subject, body) • Log sent email at INFO level; catch and log exceptions without re-throwing (alert failure must not affect caller) | PrefundingAlertEmailListener.java component | • LOW_BALANCE event for SendMN (balance=9500.00, threshold=10000.00) triggers email to config.alertEmail with subject containing 'SendMN' and body showing current balance USD 9,500.00 and suggested top-up USD 10,500.00 • CRITICAL_ZERO event triggers email with URGENT in subject • EmailService exception is swallowed and logged; no exception propagates to caller • Alert email is NOT sent if LowBalanceAlertConfig.isActive = false • LOW_BALANCE alert is sent exactly once per crossing (not on every subsequent deduction below threshold) | 30 | 6.1-T15 | BE | DAT-03, PRD-07
6.1-T17 | prefunding | 6.1 | 6. Prefunding & Wallet Ledger | Prefunding balance & top-up recording | 1 | Admin API endpoint: POST /internal/v1/prefunding/accounts | The Balance Service exposes an internal REST API (not the partner-facing Northbound API) used by the Admin Portal and onboarding workflows. POST /internal/v1/prefunding/accounts creates a prefunding account for an OVERSEAS partner. Request body: { partnerId: Long }. Response 201: PrefundingAccountResponse { id, partnerId, currency, balance, lowBalanceThreshold, createdAt }. Error cases: 409 Conflict if account already exists, 422 if partner is LOCAL, 404 if partner not found. Only internal service accounts and Admin Portal backend-for-frontend may call this endpoint (enforced by service-mesh / API key check in a later security ticket; stub the auth check here). | • Create PrefundingController @RestController at path /internal/v1/prefunding • Implement POST /accounts handler calling prefundingBalanceService.createAccount(cmd.partnerId) • Map domain exceptions to HTTP status codes: PrefundingAccountNotFoundException->404, DuplicateAccountException->409, InvalidPartnerTypeException->422 • Create PrefundingAccountResponse DTO with the listed fields • Add @Validated and @RequestBody validation (partnerId not null) | PrefundingController.java with POST /internal/v1/prefunding/accounts endpoint | • POST with valid OVERSEAS partnerId returns 201 and response body with balance=0.0000 • POST with same partnerId a second time returns 409 Conflict • POST with LOCAL partnerId returns 422 with descriptive error message • POST with unknown partnerId returns 404 • POST with null partnerId returns 400 Bad Request (validation) | 35 | 6.1-T09 | BE | DAT-03, PRD-07
6.1-T18 | prefunding | 6.1 | 6. Prefunding & Wallet Ledger | Prefunding balance & top-up recording | 1 | Admin API endpoint: GET /internal/v1/prefunding/accounts/{partnerId} | GET /internal/v1/prefunding/accounts/{partnerId} returns the current prefunding account state for a partner. Response: PrefundingAccountResponse { id, partnerId, currency, balance (BigDecimal 4dp), lowBalanceThreshold, updatedAt }. 404 if no account. This endpoint is called by the Admin Portal Prefunding Dashboard to display each partner card. It is a non-locking read. | • Add GET /accounts/{partnerId} handler to PrefundingController • Call prefundingBalanceService.getBalance(partnerId) • Map PrefundingAccount to PrefundingAccountResponse DTO • Map PrefundingAccountNotFoundException to 404 with error body • Annotate method as read-only (no @Transactional needed at controller layer; service handles it) | GET /internal/v1/prefunding/accounts/{partnerId} handler in PrefundingController.java | • GET for existing account returns 200 with correct balance and currency=USD • GET for unknown partnerId returns 404 • Response balance field has 4 decimal places in JSON (e.g. 50000.0000) • Endpoint does not acquire DB write lock (verified by absence of FOR UPDATE in SQL log) • Response includes updatedAt timestamp | 20 | 6.1-T10, 6.1-T17 | BE | DAT-03, PRD-07
6.1-T19 | prefunding | 6.1 | 6. Prefunding & Wallet Ledger | Prefunding balance & top-up recording | 1 | Admin API endpoint: POST /internal/v1/prefunding/accounts/{partnerId}/topups | POST /internal/v1/prefunding/accounts/{partnerId}/topups records a manual Ops-entered top-up. Request body: { amountUsd: BigDecimal (> 0), bankRef: String (required, max 64 chars), valueDate: LocalDate (required, ISO date), notes: String (optional, max 255 chars) }. The actorId is extracted from the authenticated operator's JWT sub claim (stub: read from X-Actor-Id header in Phase 1). Response 201: TopUpResponse { ledgerEntryId, partnerId, amountUsd, newBalance, balanceAfter, entryType: CREDIT_TOPUP, bankRef, createdAt, createdBy }. Error cases: 400 if amountUsd <= 0 or bankRef blank, 404 if no account. The operation is atomic: balance update and ledger entry in one DB transaction. | • Add POST /accounts/{partnerId}/topups handler to PrefundingController • Parse and validate request body: amountUsd > 0, bankRef not blank, valueDate not null • Extract actorId from X-Actor-Id header (Phase 1 stub) • Build TopUpCommand and call prefundingBalanceService.recordTopUp(cmd) • Map result to TopUpResponse DTO and return 201 | POST /internal/v1/prefunding/accounts/{partnerId}/topups handler in PrefundingController.java | • POST with amountUsd=20000.00 and bankRef='WIRE-001' on account with balance=30000.00 returns 201 with newBalance=50000.00 • POST with amountUsd=0 returns 400 Bad Request • POST with blank bankRef returns 400 Bad Request • POST to unknown partnerId returns 404 • Response entryType is CREDIT_TOPUP • Subsequent GET /accounts/{partnerId} returns balance=50000.00 immediately (no caching delay) | 35 | 6.1-T11, 6.1-T18 | BE | DAT-03, PRD-07
6.1-T20 | prefunding | 6.1 | 6. Prefunding & Wallet Ledger | Prefunding balance & top-up recording | 1 | Admin API endpoint: GET /internal/v1/prefunding/accounts/{partnerId}/ledger | GET /internal/v1/prefunding/accounts/{partnerId}/ledger returns the paginated ledger history for a partner. Query params: page (default 0), size (default 50, max 200). Response: Page<LedgerEntryResponse> with entries newest-first. LedgerEntryResponse fields: id, accountId, entryType, amount, balanceAfter, txnRef (nullable), note (nullable), createdAt, createdBy. 404 if no account. This endpoint is used by the Admin Portal Prefunding Ledger view. | • Add GET /accounts/{partnerId}/ledger handler to PrefundingController • Parse page and size query params; cap size at 200 • Call prefundingBalanceService.getLedgerHistory(partnerId, PageRequest.of(page, size, Sort.by(DESC, 'createdAt'))) • Map Page<PrefundingLedgerEntry> to PaginatedResponse<LedgerEntryResponse> • Return 200 with pagination metadata (totalElements, totalPages, currentPage) | GET /internal/v1/prefunding/accounts/{partnerId}/ledger handler in PrefundingController.java | • GET with page=0 size=2 for account with 5 entries returns 2 entries with totalElements=5 • Entries are in descending created_at order • GET with size=300 is capped at 200 (returns 200 entries max) • GET for unknown partnerId returns 404 • txnRef is null in the response for CREDIT_TOPUP entries and non-null for DEBIT_PAYMENT entries | 25 | 6.1-T14, 6.1-T18 | BE | DAT-03, PRD-07
6.1-T21 | prefunding | 6.1 | 6. Prefunding & Wallet Ledger | Prefunding balance & top-up recording | 1 | Admin API endpoint: GET /internal/v1/prefunding/accounts (dashboard summary) | GET /internal/v1/prefunding/accounts returns a summary list of all OVERSEAS partner prefunding accounts for the Prefunding Dashboard. Each summary includes: partnerId, partnerCode, partnerName, currency, balance, lowBalanceThreshold, balancePct (balance / lowBalanceThreshold * 100, rounded to 1dp), balanceStatus (GREEN if >= 150%, AMBER if 100-149%, RED if < 100%), lastDeductionAt (nullable, from latest DEBIT_PAYMENT entry), lastTopUpAt (nullable, from latest CREDIT_TOPUP entry). No pagination -- typically < 20 OVERSEAS partners. Response is sorted by balancePct ASC (lowest first). | • Add GET /accounts handler to PrefundingController • Query all PrefundingAccount rows via findAll() • For each account, compute balancePct and balanceStatus using the threshold rules • Fetch lastDeductionAt and lastTopUpAt via queries on ledger table (latest entry per type per account) • Sort results by balancePct ASC and return 200 | GET /internal/v1/prefunding/accounts dashboard handler | • Account with balance=15000.00, threshold=10000.00 has balancePct=150.0 and balanceStatus=GREEN • Account with balance=12000.00, threshold=10000.00 has balancePct=120.0 and balanceStatus=AMBER • Account with balance=9999.00, threshold=10000.00 has balancePct=99.9 and balanceStatus=RED • Results are sorted with RED accounts appearing before AMBER and GREEN • lastTopUpAt reflects the created_at of the most recent CREDIT_TOPUP entry | 35 | 6.1-T14, 6.1-T17 | BE | DAT-03, PRD-07
6.1-T22 | prefunding | 6.1 | 6. Prefunding & Wallet Ledger | Prefunding balance & top-up recording | 1 | Unit tests: recordTopUp core logic and balance arithmetic | Write thorough unit tests for PrefundingBalanceServiceImpl.recordTopUp using Mockito (no DB). Test vectors: (A) balance=0 + topUp=50000.00 -> balance=50000.00, ledger amount=50000.00, balance_after=50000.00. (B) balance=30000.5678 + topUp=19999.4322 -> balance=50000.0000, ledger amount=19999.4322, balance_after=50000.0000 (exact BigDecimal arithmetic). (C) topUp=0 -> InvalidAmountException, no repo calls. (D) topUp=-1 -> InvalidAmountException. (E) blank bankRef -> MissingReferenceException. (F) unknown partnerId -> PrefundingAccountNotFoundException. | • Create PrefundingBalanceServiceImplTopUpTest.java in test package • Mock PrefundingAccountRepository, PrefundingLedgerEntryRepository, ApplicationEventPublisher • Write test cases A through F as separate @Test methods • For cases A and B: use ArgumentCaptor to verify saved PrefundingAccount.balance and saved PrefundingLedgerEntry fields • Assert BalanceUpdatedEvent is published with correct newBalance and previousBalance for success cases | PrefundingBalanceServiceImplTopUpTest.java with >= 6 test cases all passing | • Test B confirms BigDecimal result 50000.0000 (not 50000.0000000001 from float drift) • Test C verifies no call to accountRepository.save() when amount=0 • Test E verifies exception message contains 'bankRef' • Test F verifies PrefundingAccountNotFoundException is thrown (not NullPointerException) • All 6 tests pass with 'mvn test -pl balance-service -Dtest=PrefundingBalanceServiceImplTopUpTest' | 40 | 6.1-T11 | BE | DAT-03, PRD-07
6.1-T23 | prefunding | 6.1 | 6. Prefunding & Wallet Ledger | Prefunding balance & top-up recording | 1 | Unit tests: deductBalance atomicity, insufficient-balance, and edge cases | Write unit tests for PrefundingBalanceServiceImpl.deductBalance. Test vectors: (A) balance=10000.00, deduct=1234.5678 -> balance=8765.4322, DEBIT_PAYMENT entry amount=1234.5678, balance_after=8765.4322. (B) balance=10000.00, deduct=10000.01 -> InsufficientPrefundingException, balance unchanged, no ledger entry. (C) balance=10000.00, deduct=10000.00 -> balance=0.0000 (exact zero is allowed). (D) deduct=0 -> InvalidAmountException. (E) deduct=-5 -> InvalidAmountException. (F) unknown partnerId -> PrefundingAccountNotFoundException. Verify txnRef on ledger entry matches cmd.txnRef. | • Create PrefundingBalanceServiceImplDeductTest.java • Mock repositories and event publisher • Implement test vectors A through F • For test B: use verifyNoInteractions on ledger repository to confirm no entry is written • For test C: confirm returned balance is BigDecimal ZERO with scale 4 • Verify BalanceUpdatedEvent is published only for successful deductions (not for exceptions) | PrefundingBalanceServiceImplDeductTest.java with >= 6 test cases all passing | • Test A: saved ledger entry has entryType=DEBIT_PAYMENT, amount=1234.5678, balance_after=8765.4322 • Test B: no ledger entry written AND no account save on InsufficientPrefundingException • Test C: balance after deduction is 0.0000 (scale 4) not null • Test D and E: InvalidAmountException thrown without touching repositories • BalanceUpdatedEvent published exactly once for test A and test C; zero times for test B | 40 | 6.1-T12 | BE | DAT-03, PRD-07
6.1-T24 | prefunding | 6.1 | 6. Prefunding & Wallet Ledger | Prefunding balance & top-up recording | 1 | Unit tests: reverseDeduction logic | Write unit tests for PrefundingBalanceServiceImpl.reverseDeduction. Vectors: (A) balance=5000.00, reverse=1000.00 -> balance=6000.00, DEBIT_REVERSAL entry amount=1000.00, balance_after=6000.00, txnRef=originalTxnRef. (B) balance=0.00, reverse=500.00 -> balance=500.00 (reversal can restore a zero balance). (C) reverse=0 -> InvalidAmountException. (D) unknown partnerId -> PrefundingAccountNotFoundException. DEBIT_REVERSAL is a credit to the balance, but the entry_type name reflects the origin (it reverses a DEBIT_PAYMENT). | • Create PrefundingBalanceServiceImplReverseTest.java • Mock repositories and event publisher • Implement test vectors A through D • For test A: verify originalTxnRef is stored in ledger entry's txnRef field • For test B: confirm balance transitions correctly from 0.00 to 500.00 • Verify BalanceUpdatedEvent published on success, not on exception | PrefundingBalanceServiceImplReverseTest.java with >= 4 test cases all passing | • Test A: DEBIT_REVERSAL ledger entry has txnRef='TXN-001', amount=1000.00, balance_after=6000.00 • Test B: balance transitions from 0.00 to 500.00 (verify BigDecimal equals zero then 500) • Test C: InvalidAmountException thrown and no repo interactions • Test D: PrefundingAccountNotFoundException thrown • All 4 tests pass via mvn test | 30 | 6.1-T13 | BE | DAT-03, PRD-07
6.1-T25 | prefunding | 6.1 | 6. Prefunding & Wallet Ledger | Prefunding balance & top-up recording | 1 | Unit tests: low-balance alert check logic | Write unit tests for BalanceAlertChecker. Vectors: (A) previousBalance=15000.00, newBalance=9500.00, threshold=10000.00 -> LOW_BALANCE event published. (B) previousBalance=9500.00, newBalance=8000.00, threshold=10000.00 -> NO event (both sides below threshold; do not spam). (C) newBalance=0.00 -> CRITICAL_ZERO event regardless of previous. (D) newBalance=9999.99, threshold=10000.00, isActive=false -> no event. (E) newBalance=15000.00, previousBalance=9000.00, threshold=10000.00 (balance restored above threshold) -> no event. | • Create BalanceAlertCheckerTest.java • Mock LowBalanceAlertConfigRepository and ApplicationEventPublisher • Publish BalanceUpdatedEvent directly to checker (call handleBalanceUpdated method) • Implement test vectors A through E • For test B: verifyNoInteractions on publisher • Verify event type (LOW_BALANCE vs CRITICAL_ZERO) in published event | BalanceAlertCheckerTest.java with >= 5 test cases all passing | • Test A publishes exactly one PrefundingAlertEvent with alertType=LOW_BALANCE • Test B: ApplicationEventPublisher.publishEvent is never called • Test C publishes alertType=CRITICAL_ZERO even when previousBalance > threshold • Test D: no event when isActive=false • Test E: no event when balance crosses threshold in the upward direction | 30 | 6.1-T15 | BE | DAT-03, PRD-07
6.1-T26 | prefunding | 6.1 | 6. Prefunding & Wallet Ledger | Prefunding balance & top-up recording | 1 | Integration test: top-up and ledger entry end-to-end | Write a Spring Boot integration test using Testcontainers (PostgreSQL) covering the full recordTopUp flow. Test scenario: (1) create OVERSEAS partner and call createAccount; (2) call recordTopUp(amount=20000.00, bankRef='WIRE-001') twice; (3) assert prefunding_account.balance = 40000.00; (4) call getLedgerHistory(page 0, size 10): assert 2 entries, both CREDIT_TOPUP, amounts 20000.00 each, balance_after values 20000.00 and 40000.00 respectively, newest first. Also assert: (5) txnRef is NULL on both entries; (6) a third call with amount=0 returns 400 from the API endpoint; (7) balance remains 40000.00 after the failed call. | • Create PrefundingTopUpIntegrationTest.java with @SpringBootTest + @Testcontainers • Spin up Postgres container, apply migrations via Flyway • Insert test OVERSEAS partner row • Call PrefundingController endpoints via MockMvc or TestRestTemplate • Assert DB state via direct JDBC or repository calls after each operation • Assert event publication using a test ApplicationEventListener stub | PrefundingTopUpIntegrationTest.java with the described scenario passing | • After two top-ups of 20000.00 each, DB balance = 40000.0000 • getLedgerHistory returns exactly 2 entries in descending order • balance_after of first entry (oldest) = 20000.0000 and of second (newest) = 40000.0000 • POST with amount=0 returns 400 and balance is unchanged at 40000.0000 • Both ledger entries have txnRef = NULL and entryType = CREDIT_TOPUP | 55 | 6.1-T19, 6.1-T20, 6.1-T22 | BE | DAT-03, PRD-07
6.1-T27 | prefunding | 6.1 | 6. Prefunding & Wallet Ledger | Prefunding balance & top-up recording | 1 | Integration test: concurrent deduction race-condition test | Write an integration test proving the SELECT FOR UPDATE prevents lost updates under concurrent deductions. Setup: OVERSEAS partner with balance=10000.00. Launch 10 threads each attempting deductBalance(amount=1500.00). Expected: exactly 6 threads succeed (6 * 1500 = 9000.00 <= 10000.00), the 7th fails with InsufficientPrefundingException (balance would be 10000.00 - 7*1500 = -500), and threads 8-10 also fail. Final balance = 10000.00 - (success_count * 1500). Verify ledger entry count equals success count. This test validates AD-06 (scheme is never called without prior successful deduction). | • Create PrefundingConcurrencyTest.java with @SpringBootTest + Testcontainers Postgres • Create partner + account with balance=10000.00 • Use ExecutorService with 10 threads each calling deductBalance(amount=1500.00) • Collect results: count successes and InsufficientPrefundingException throws • Assert success_count + failure_count = 10 and success_count <= 6 • Assert final DB balance = 10000.00 - (success_count * 1500.00) exactly • Assert ledger entry count = success_count | PrefundingConcurrencyTest.java passing | • Total thread count = successes + InsufficientPrefundingExceptions = 10 (no other exceptions) • Final balance = 10000.00 - success_count * 1500.00 with zero floating-point error • Ledger DEBIT_PAYMENT entries = success_count (never more) • No balance goes negative (CHECK constraint never violated) • Test passes on 3 consecutive runs (not intermittently flaky) | 55 | 6.1-T12, 6.1-T26 | BE | DAT-03, PRD-07
6.1-T28 | prefunding | 6.1 | 6. Prefunding & Wallet Ledger | Prefunding balance & top-up recording | 1 | Integration test: createAccount rejects LOCAL partner and duplicate creation | Write integration tests for the createAccount guard conditions. Tests: (A) create account for LOCAL partner (e.g. GME_REMIT, partner_type='LOCAL') -> 422 response, no row in prefunding_account. (B) create account for OVERSEAS partner (SENDMN, partner_type='OVERSEAS') -> 201, row exists. (C) call createAccount again for SENDMN -> 409 Conflict, still exactly one row in prefunding_account. (D) call createAccount with non-existent partnerId 99999 -> 404. These guard tests verify the invariant that LOCAL partners never have prefunding accounts. | • Create PrefundingAccountCreationTest.java with Testcontainers integration setup • Insert both LOCAL (GME_REMIT) and OVERSEAS (SENDMN) partner rows • Call POST /internal/v1/prefunding/accounts for each test case via MockMvc • Assert HTTP status and DB row count after each case • Run all 4 test cases in order | PrefundingAccountCreationTest.java with 4 passing test cases | • Test A returns 422 and SELECT COUNT(*) FROM prefunding_account WHERE partner_id={LOCAL_id} = 0 • Test B returns 201 and exactly one row exists with balance=0.0000 • Test C returns 409 and row count remains 1 • Test D returns 404 • Test D does not create any row in prefunding_account | 35 | 6.1-T09, 6.1-T17 | BE | DAT-03, PRD-07
6.1-T29 | prefunding | 6.1 | 6. Prefunding & Wallet Ledger | Prefunding balance & top-up recording | 1 | Validation: amountUsd scale and currency guards in service layer | Add input validation guards to the service layer (not just the API layer) to enforce: (1) amountUsd must have scale <= 4 (DECIMAL(20,4) -- amounts with more than 4 decimal places are rejected); (2) amountUsd must be positive (> 0); (3) amountUsd must not exceed USD 10,000,000.00 per single top-up (max single top-up cap as a safety guard). These validations apply to both recordTopUp and deductBalance. Throw InvalidAmountException with a clear message for each violation. This prevents silent rounding and accidental over-crediting. | • Add a private validateAmount(BigDecimal amount, String fieldName) helper in PrefundingBalanceServiceImpl • Check amount.compareTo(BigDecimal.ZERO) > 0 else throw InvalidAmountException('amount must be > 0') • Check amount.scale() <= 4 else throw InvalidAmountException('amount scale exceeds 4 decimal places') • Check amount.compareTo(new BigDecimal('10000000')) <= 0 else throw InvalidAmountException('amount exceeds single-operation cap of USD 10,000,000') • Call validateAmount at the start of both recordTopUp and deductBalance | validateAmount helper added to PrefundingBalanceServiceImpl; existing tests updated if needed | • recordTopUp with amount=1.00001 (scale 5) throws InvalidAmountException with 'scale' in message • recordTopUp with amount=10000001.00 throws InvalidAmountException with 'cap' in message • deductBalance with amount=0.00001 (scale 5) throws InvalidAmountException • recordTopUp with amount=10000000.00 (exactly at cap) succeeds • recordTopUp with amount=9999.9999 (scale 4) succeeds | 25 | 6.1-T11, 6.1-T12 | BE | DAT-03, PRD-07
6.1-T30 | prefunding | 6.1 | 6. Prefunding & Wallet Ledger | Prefunding balance & top-up recording | 1 | Audit log integration: emit audit events for top-up and account creation | Per the platform audit spec, all config/balance changes must log actor, timestamp, previous value, and new value. Emit audit log entries (to the existing AuditLogService or AuditEvent publisher) for: (1) createAccount: action=PREFUNDING_ACCOUNT_CREATED, entity=PREFUNDING_ACCOUNT, entityId={accountId}, actorId, details={partnerId, currency, balance=0}; (2) recordTopUp: action=PREFUNDING_TOPUP_RECORDED, entityId={accountId}, actorId, details={previousBalance, newBalance, amountUsd, bankRef, valueDate}. The audit log is separate from the ledger; both are written in the same transaction where possible (or via @TransactionalEventListener for audit). Use the existing AuditLogService.record(AuditEntry entry) interface. | • Inject AuditLogService into PrefundingBalanceServiceImpl • In createAccount: after persisting account, call auditLogService.record with action PREFUNDING_ACCOUNT_CREATED • In recordTopUp: call auditLogService.record with previousBalance and newBalance in details • Define AuditEntry details as a structured map or DTO, not a free-text string • Add unit tests asserting auditLogService.record is called with correct action and details for each operation | Audit log calls added to createAccount and recordTopUp in PrefundingBalanceServiceImpl | • createAccount calls auditLogService.record with action=PREFUNDING_ACCOUNT_CREATED and details containing partnerId • recordTopUp calls auditLogService.record with previousBalance=30000.00 and newBalance=50000.00 when topping up 20000.00 • auditLogService.record is NOT called when recordTopUp throws InvalidAmountException • Audit entry includes actorId from cmd.actorId • In unit test, verify auditLogService.record called exactly once per successful operation | 30 | 6.1-T11, 6.1-T09 | BE | DAT-03, PRD-07
6.1-T31 | prefunding | 6.1 | 6. Prefunding & Wallet Ledger | Prefunding balance & top-up recording | 1 | OpenAPI spec: document prefunding balance and top-up endpoints | Add OpenAPI 3.0 documentation for the four balance service endpoints: GET /internal/v1/prefunding/accounts, POST /internal/v1/prefunding/accounts, GET /internal/v1/prefunding/accounts/{partnerId}, POST /internal/v1/prefunding/accounts/{partnerId}/topups, and GET /internal/v1/prefunding/accounts/{partnerId}/ledger. Document request/response schemas, error responses (400, 404, 409, 422), and example values. Tag all endpoints with 'Prefunding'. Note in description that these are internal endpoints not exposed on the partner-facing Northbound API gateway. | • Add @Operation, @ApiResponse, and @Schema annotations to PrefundingController methods • Document TopUpRequest schema with field constraints (amountUsd > 0, bankRef required max 64 chars) • Document PrefundingAccountResponse and LedgerEntryResponse schemas with example values • Add 400/404/409/422 error response schemas using existing ErrorResponse component • Mark all endpoints with @Tag(name='Prefunding') and add 'Internal only' note in description | PrefundingController.java fully annotated with OpenAPI annotations; Swagger UI displays all 5 endpoints under Prefunding tag | • Swagger UI at /swagger-ui.html shows all 5 prefunding endpoints under Prefunding tag • POST /topups request schema shows amountUsd as required with description '>0, max scale 4' • All 4xx error responses are documented on POST /topups • LedgerEntryResponse schema includes entryType enum values DEBIT_PAYMENT, DEBIT_REVERSAL, CREDIT_TOPUP, CREDIT_REVERSAL • Internal-only note appears in endpoint descriptions | 30 | 6.1-T19, 6.1-T20, 6.1-T21 | BE | DAT-03, PRD-07
6.2-T01 | prefunding | 6.2 | 6. Prefunding & Wallet Ledger | Atomic deduction (SELECT FOR UPDATE) | 1 | Add Flyway migration: prefunding_account table | GMEPay+ maintains a prefunding_account table (one row per OVERSEAS partner) in PostgreSQL. Columns: id BIGINT PK, partner_id BIGINT UNIQUE FK partner, currency CHAR(3) DEFAULT 'USD', balance DECIMAL(20,4) NOT NULL DEFAULT 0, low_balance_threshold DECIMAL(20,4) NOT NULL DEFAULT 10000.0000, created_at TIMESTAMPTZ, updated_at TIMESTAMPTZ, created_by VARCHAR(120), updated_by VARCHAR(120). Balance updates use SELECT FOR UPDATE exclusively - no application-level locking. LOCAL partners never have a row here. | • Create Flyway migration file V6_2_001__create_prefunding_account.sql • Add table DDL with all columns and constraints listed in context • Add UNIQUE constraint on partner_id • Add CHECK constraint: balance >= 0 • Add CHECK constraint: low_balance_threshold >= 0 • Verify migration runs cleanly with mvn flyway:migrate in local dev environment | Flyway migration file V6_2_001__create_prefunding_account.sql creating the prefunding_account table | • Migration runs without error on a clean schema and is idempotent when run twice (Flyway checksum passes) • Table has UNIQUE constraint on partner_id - inserting two rows with same partner_id raises a unique violation • CHECK (balance >= 0) prevents inserting a row with balance = -0.01 • CHECK (low_balance_threshold >= 0) is present • Default balance is 0.0000 and default low_balance_threshold is 10000.0000 when values are omitted on INSERT | 25 |  | BE | RATE-04, NFR-10
6.2-T02 | prefunding | 6.2 | 6. Prefunding & Wallet Ledger | Atomic deduction (SELECT FOR UPDATE) | 1 | Add Flyway migration: prefunding_ledger_entry table | Every debit or credit to a prefunding_account creates one immutable, append-only row in prefunding_ledger_entry. Columns: id BIGINT PK auto-increment, account_id BIGINT NOT NULL FK prefunding_account, txn_ref VARCHAR(64) NULL (FK ref to transaction.txn_ref; NULL for top-ups), entry_type VARCHAR(20) NOT NULL CHECK IN ('DEBIT_PAYMENT','DEBIT_REVERSAL','CREDIT_TOPUP','CREDIT_REVERSAL'), amount DECIMAL(20,4) NOT NULL CHECK amount > 0, balance_after DECIMAL(20,4) NOT NULL (running balance snapshot after entry), note VARCHAR(255) NULL, created_at TIMESTAMPTZ NOT NULL DEFAULT NOW(), created_by VARCHAR(120). Rows are NEVER updated or deleted. Index on (account_id, created_at) for balance history queries. | • Create migration V6_2_002__create_prefunding_ledger_entry.sql • Add table DDL with all columns and constraints • Add FK to prefunding_account(id) • Add CHECK constraint: entry_type IN ('DEBIT_PAYMENT','DEBIT_REVERSAL','CREDIT_TOPUP','CREDIT_REVERSAL') • Add CHECK constraint: amount > 0 • Add composite index on (account_id, created_at) | Flyway migration file V6_2_002__create_prefunding_ledger_entry.sql | • Migration applies cleanly after T01 migration • CHECK (amount > 0) rejects INSERT with amount = 0 or amount = -5.00 • CHECK (entry_type) rejects unknown value 'DEBIT_UNKNOWN' • Composite index (account_id, created_at) exists in pg_indexes • No UPDATE or DELETE grant is given on the table in the migration (table is append-only by convention) | 25 | 6.2-T01 | BE | RATE-04, NFR-10
6.2-T03 | prefunding | 6.2 | 6. Prefunding & Wallet Ledger | Atomic deduction (SELECT FOR UPDATE) | 1 | Add Flyway migration: low_balance_alert_config table | Per-partner configurable low-balance alert settings live in low_balance_alert_config. Columns: id BIGINT PK, partner_id BIGINT UNIQUE FK partner, threshold_usd DECIMAL(20,4) NOT NULL DEFAULT 10000.0000, alert_email VARCHAR(255) NOT NULL, is_active BOOLEAN NOT NULL DEFAULT TRUE, created_at TIMESTAMPTZ, updated_at TIMESTAMPTZ. One row per OVERSEAS partner. Alert is informational only - the triggering transaction is NOT blocked. Default threshold is USD 10,000 per partner. | • Create migration V6_2_003__create_low_balance_alert_config.sql • Add table DDL with all columns • Add UNIQUE constraint on partner_id • Add CHECK constraint: threshold_usd > 0 • Seed a default row for each existing OVERSEAS partner by joining partner table on partner_type = 'OVERSEAS' | Flyway migration V6_2_003__create_low_balance_alert_config.sql | • Table created with UNIQUE constraint on partner_id • CHECK (threshold_usd > 0) rejects threshold_usd = 0 • Default is_active = TRUE when omitted on INSERT • Existing OVERSEAS partners each get a seeded row with threshold_usd = 10000.0000 • Inserting a duplicate partner_id raises a unique violation | 20 | 6.2-T01 | BE | RATE-04, NFR-10
6.2-T04 | prefunding | 6.2 | 6. Prefunding & Wallet Ledger | Atomic deduction (SELECT FOR UPDATE) | 1 | Add prefunding_deducted_usd column to transactions table | The transactions table must record how much USD was deducted from a partner's prefunding account per payment. Column: prefunding_deducted_usd DECIMAL(20,4) NULL (NULL for LOCAL partners or before deduction; set to collection_usd at commit for OVERSEAS partners). A companion boolean column is_same_ccy_shortcircuit BOOLEAN NOT NULL DEFAULT FALSE also needs to exist (add only if not already present from an earlier WBS migration). | • Check whether prefunding_deducted_usd and is_same_ccy_shortcircuit already exist in the transactions DDL from WBS 5.x • Create migration V6_2_004__add_prefunding_deducted_usd_to_transactions.sql • Add column prefunding_deducted_usd DECIMAL(20,4) NULL to transactions table • Add is_same_ccy_shortcircuit BOOLEAN NOT NULL DEFAULT FALSE to transactions table if not already present • Add a partial index on (partner_id, created_at) WHERE prefunding_deducted_usd IS NOT NULL for reporting queries | Flyway migration V6_2_004__add_prefunding_deducted_usd_to_transactions.sql | • Column prefunding_deducted_usd is NULLable - existing rows are unaffected • Column defaults to NULL on INSERT when omitted • Partial index (partner_id, created_at) WHERE prefunding_deducted_usd IS NOT NULL exists after migration • Migration is idempotent via Flyway checksum: running it twice does not error • is_same_ccy_shortcircuit column is present and defaults to FALSE | 20 | 6.2-T01 | BE | RATE-04, NFR-10
6.2-T05 | prefunding | 6.2 | 6. Prefunding & Wallet Ledger | Atomic deduction (SELECT FOR UPDATE) | 1 | Define PrefundingAccount and PrefundingLedgerEntry JPA entities | The Hub Core is Java 21 + Spring Boot 3.x with PostgreSQL 16. PrefundingAccount maps to prefunding_account (id, partner_id, currency, balance DECIMAL(20,4), lowBalanceThreshold DECIMAL(20,4)). PrefundingLedgerEntry maps to prefunding_ledger_entry (id, accountId, txnRef, entryType enum[DEBIT_PAYMENT,DEBIT_REVERSAL,CREDIT_TOPUP,CREDIT_REVERSAL], amount, balanceAfter, note, createdAt). Use BigDecimal for all monetary fields - never double or float. PrefundingLedgerEntry must be annotated as immutable (no setter methods; all fields set via constructor or builder). Place entities in package com.gmepayplus.prefunding.domain. | • Create PrefundingAccount.java with @Entity, @Table(name='prefunding_account'), all columns mapped • Create EntryType.java enum with four values • Create PrefundingLedgerEntry.java with @Entity; no setter for any field; @Column(updatable=false) on all columns • Use BigDecimal for balance, amount, balanceAfter, lowBalanceThreshold • Add @Version on PrefundingAccount for optimistic-lock detection (belt-and-suspenders alongside SELECT FOR UPDATE) | PrefundingAccount.java, EntryType.java, PrefundingLedgerEntry.java in com.gmepayplus.prefunding.domain | • PrefundingAccount.balance field is BigDecimal, not double • PrefundingLedgerEntry has no public setters; all fields annotated @Column(updatable=false, insertable=true) • EntryType enum has exactly four values: DEBIT_PAYMENT, DEBIT_REVERSAL, CREDIT_TOPUP, CREDIT_REVERSAL • mvn compile succeeds with no warnings on these classes • @Version field is present on PrefundingAccount | 30 | 6.2-T01, 6.2-T02 | BE | RATE-04, NFR-10
6.2-T06 | prefunding | 6.2 | 6. Prefunding & Wallet Ledger | Atomic deduction (SELECT FOR UPDATE) | 1 | Implement PrefundingRepository with SELECT FOR UPDATE query | The atomic deduction pattern mandates SELECT FOR UPDATE (row-level lock) on the prefunding_account row. Pseudo-SQL from NFR-10 §5.2: BEGIN; SELECT balance FROM prefunding_account WHERE partner_id = ? FOR UPDATE; check balance >= amount; UPDATE prefunding_account SET balance = balance - amount WHERE partner_id = ?; COMMIT. Spring Data JPA: use @Lock(LockModeType.PESSIMISTIC_WRITE) on a findByPartnerId method. This acquires a row-level exclusive lock preventing concurrent deductions from over-drawing. Repository interface: PrefundingAccountRepository extends JpaRepository. | • Create PrefundingAccountRepository.java extending JpaRepository<PrefundingAccount, Long> • Add method: @Lock(LockModeType.PESSIMISTIC_WRITE) @Query('SELECT p FROM PrefundingAccount p WHERE p.partnerId = :partnerId') Optional<PrefundingAccount> findByPartnerIdForUpdate(@Param('partnerId') Long partnerId) • Add plain findByPartnerId(Long partnerId) for read-only balance queries • Create PrefundingLedgerEntryRepository.java extending JpaRepository<PrefundingLedgerEntry, Long> • Add findTop10ByAccountIdOrderByCreatedAtDesc for recent-history queries | PrefundingAccountRepository.java and PrefundingLedgerEntryRepository.java | • findByPartnerIdForUpdate is annotated @Lock(LockModeType.PESSIMISTIC_WRITE) • findByPartnerId (without lock) exists and is separate from the locking variant • PrefundingLedgerEntryRepository.findTop10ByAccountIdOrderByCreatedAtDesc returns at most 10 rows • Both repositories extend JpaRepository and compile cleanly • No raw SQL strings are used for the UPDATE; balance update is done via entity mutation + save() | 25 | 6.2-T05 | BE | RATE-04, NFR-10
6.2-T07 | prefunding | 6.2 | 6. Prefunding & Wallet Ledger | Atomic deduction (SELECT FOR UPDATE) | 1 | Implement PrefundingDeductionService - core atomic deduct method | PrefundingDeductionService.deductForPayment(Long partnerId, BigDecimal amountUsd, String txnRef) is the core atomic operation. Pattern (NFR-10 §5.2): (1) Acquire row lock via findByPartnerIdForUpdate inside @Transactional. (2) Check balance >= amountUsd; if not, throw InsufficientPrefundingException (maps to HTTP 402, error code INSUFFICIENT_PREFUNDING). (3) Subtract: account.setBalance(account.getBalance().subtract(amountUsd)). (4) Save account. (5) Append an immutable PrefundingLedgerEntry(entryType=DEBIT_PAYMENT, amount=amountUsd, balanceAfter=newBalance, txnRef=txnRef). (6) Return DeductionResult(previousBalance, newBalance, entryId). The entire operation runs in a single DB transaction. Scheme is NEVER called by this service. | • Create InsufficientPrefundingException.java extending RuntimeException with fields partnerId, requiredUsd, availableUsd • Create DeductionResult.java record with fields previousBalance, newBalance, ledgerEntryId • Create PrefundingDeductionService.java with @Service • Implement deductForPayment annotated @Transactional(isolation=REPEATABLE_READ) calling findByPartnerIdForUpdate • Throw InsufficientPrefundingException when balance < amountUsd before deduction • Persist ledger entry and return DeductionResult | PrefundingDeductionService.java, InsufficientPrefundingException.java, DeductionResult.java | • deductForPayment is @Transactional - calling it twice concurrently with the same partner_id serialises, not races • InsufficientPrefundingException is thrown (not committed) when balance=50.00 USD and amountUsd=51.00 USD • On success with balance=100.00 and amount=35.77, returned newBalance=64.23 and ledger entry amount=35.77, balanceAfter=64.23 • Scheme call is absent from this service - deductForPayment only touches the DB • ledger entry entry_type is DEBIT_PAYMENT | 45 | 6.2-T06 | BE | RATE-04, NFR-10
6.2-T08 | prefunding | 6.2 | 6. Prefunding & Wallet Ledger | Atomic deduction (SELECT FOR UPDATE) | 1 | Implement PrefundingDeductionService - reversal and top-up methods | Three additional operations on PrefundingDeductionService: (1) reverseDeduction(Long partnerId, BigDecimal amountUsd, String txnRef, String note) - used when a payment FAILS after deduction or when reconciliation confirms FAILED for an UNCERTAIN txn. Creates DEBIT_REVERSAL entry type. (2) creditTopUp(Long partnerId, BigDecimal amountUsd, String internalRef, String note) - used when Ops tops up a partner's prepaid balance; creates CREDIT_TOPUP entry. Both methods use SELECT FOR UPDATE to prevent concurrent balance corruption. Balance may not exceed any configured maximum (no explicit max in spec; treat as unconstrained). reverseDeduction must be idempotent: if a ledger entry with txnRef + DEBIT_REVERSAL already exists, return existing result without double-crediting. | • Add reverseDeduction(Long partnerId, BigDecimal amountUsd, String txnRef, String note) @Transactional to PrefundingDeductionService • Check for existing DEBIT_REVERSAL entry with same txnRef before applying reversal (idempotency guard) • Add creditTopUp(Long partnerId, BigDecimal amountUsd, String internalRef, String note) @Transactional • Both methods append a ledger entry with appropriate EntryType and updated balanceAfter • Add findByAccountIdAndTxnRefAndEntryType query method to PrefundingLedgerEntryRepository for idempotency check | Updated PrefundingDeductionService.java with reverseDeduction and creditTopUp, updated PrefundingLedgerEntryRepository | • reverseDeduction with balance=64.23, amount=35.77 produces newBalance=100.00 and ledger DEBIT_REVERSAL entry • reverseDeduction called twice with same txnRef returns same result without creating a second ledger entry (idempotency) • creditTopUp with balance=100.00, amount=5000.00 produces newBalance=5100.00 and ledger CREDIT_TOPUP entry • Both methods use @Transactional and acquire SELECT FOR UPDATE lock • reverseDeduction ledger entry_type is DEBIT_REVERSAL; creditTopUp entry_type is CREDIT_TOPUP | 40 | 6.2-T07 | BE | RATE-04, NFR-10
6.2-T09 | prefunding | 6.2 | 6. Prefunding & Wallet Ledger | Atomic deduction (SELECT FOR UPDATE) | 1 | Implement partner-type guard in deduction service | Only OVERSEAS partners (partner.partner_type = 'OVERSEAS') have a prefunding_account. Calling deductForPayment for a LOCAL partner (e.g. GME Remit) is a programming error. The service must fail fast with an IllegalArgumentException if invoked for a LOCAL partner. The Transaction Orchestrator handles LOCAL partners by skipping the deduction call entirely (state jumps directly to DEBITED). The guard prevents any accidental call from reaching the DB. Partner type is resolved from the Partner entity via the existing PartnerRepository. | • Inject PartnerRepository into PrefundingDeductionService • At the start of deductForPayment, call partnerRepository.findById(partnerId) • If partner.partnerType != 'OVERSEAS', throw IllegalArgumentException('Prefunding deduction called for LOCAL partner: ' + partnerId) • Write the same guard in reverseDeduction and creditTopUp • Add a convenience helper isOverseasPartner(Long partnerId) returning boolean for use by callers | PrefundingDeductionService updated with partner-type guard and isOverseasPartner helper | • deductForPayment throws IllegalArgumentException immediately (no DB lock acquired) when called with a LOCAL partner id • isOverseasPartner returns false for partner with partner_type='LOCAL' and true for 'OVERSEAS' • Same guard applied in reverseDeduction and creditTopUp • No prefunding_account row is created or read for a LOCAL partner in any code path • Unit test confirms the exception message contains the partner id | 20 | 6.2-T07 | BE | RATE-04, NFR-10
6.2-T10 | prefunding | 6.2 | 6. Prefunding & Wallet Ledger | Atomic deduction (SELECT FOR UPDATE) | 1 | Implement low-balance alert trigger in deduction service | After a successful deduction, if the new balance falls below the partner's configured low_balance_threshold_usd, a prefunding.low_balance internal event must be published. From spec (SAD-02 §7): event payload triggers a low-balance email alert to the partner's alert_email. The alert is informational only - the deduction already succeeded and must NOT be rolled back. Alert config is in low_balance_alert_config (threshold_usd, alert_email, is_active). Publish via Spring ApplicationEventPublisher as a PrefundingLowBalanceEvent(partnerId, currentBalance, thresholdUsd, alertEmail) after the deduction transaction commits (use @TransactionalEventListener(phase=AFTER_COMMIT) on the consumer side to avoid sending the alert if the transaction rolls back). | • Create PrefundingLowBalanceEvent.java record with fields partnerId, currentBalanceUsd, thresholdUsd, alertEmail • Inject LowBalanceAlertConfigRepository and ApplicationEventPublisher into PrefundingDeductionService • After persisting the deduction in deductForPayment, check: if newBalance < threshold AND is_active, publish event • Publish event INSIDE the transaction but consume AFTER_COMMIT (note this in a comment) • Create LowBalanceAlertConfigRepository.java with findByPartnerId(Long partnerId) | PrefundingLowBalanceEvent.java, LowBalanceAlertConfigRepository.java, updated PrefundingDeductionService | • Event is published when balance drops from 10500.00 to 9800.00 USD with threshold=10000.00 • Event is NOT published when new balance=10200.00 and threshold=10000.00 • Event is NOT published when is_active=false on the alert config row • Event contains partnerId, currentBalanceUsd=9800.00, thresholdUsd=10000.00, and alertEmail • Deduction is not rolled back if event publishing fails (event publishing is fire-and-forget) | 35 | 6.2-T07, 6.2-T03 | BE | RATE-04, NFR-10
6.2-T11 | prefunding | 6.2 | 6. Prefunding & Wallet Ledger | Atomic deduction (SELECT FOR UPDATE) | 1 | Integrate PrefundingDeductionService into Transaction Orchestrator - MPM flow | Transaction Orchestrator manages the payment lifecycle state machine. For MPM (POST /v1/payments), the deduction must happen BEFORE the scheme call (AD-06, NFR-10 §5.2). Sequence for OVERSEAS partners: (1) State transition to PENDING_DEBIT. (2) Call PrefundingDeductionService.deductForPayment(partnerId, collection_usd, txnRef). (3) If InsufficientPrefundingException: set state=FAILED, error=INSUFFICIENT_PREFUNDING, do NOT call scheme, return HTTP 402. (4) On success: state=DEBITED, prefunding_deducted_usd=collection_usd set on transaction record. (5) Call scheme adapter. For LOCAL partners (partner_type='LOCAL'): skip step 2 entirely, transition QUOTED -> DEBITED directly. collection_usd is the deduction amount - it equals payout_usd_cost / (1 - m_a - m_b) from the rate engine output. | • Locate TransactionOrchestrator.commitMpmPayment (or equivalent) in the existing codebase • Inject PrefundingDeductionService • Add partner-type branch: if OVERSEAS call deductForPayment; if LOCAL skip • Catch InsufficientPrefundingException and translate to FAILED state + HTTP 402 response • After successful deduction, set transaction.prefundingDeductedUsd = collection_usd and persist • Ensure scheme adapter is only called after deduction has committed (not in the same DB transaction as deduction) | Updated TransactionOrchestrator with MPM prefunding deduction integration | • OVERSEAS partner with sufficient balance: state transitions QUOTED -> PENDING_DEBIT -> DEBITED -> SCHEME_SENT in correct order • OVERSEAS partner with insufficient balance (balance=20.00, deduction=35.77): state=FAILED, HTTP 402, scheme adapter NOT called • LOCAL partner: state transitions QUOTED -> DEBITED (no PENDING_DEBIT), scheme adapter called without touching prefunding_account • transaction.prefunding_deducted_usd is set to collection_usd (e.g. 35.77) on success • Scheme adapter is called only after deduction DB transaction commits | 50 | 6.2-T07, 6.2-T09 | BE | RATE-04, NFR-10
6.2-T12 | prefunding | 6.2 | 6. Prefunding & Wallet Ledger | Atomic deduction (SELECT FOR UPDATE) | 1 | Integrate PrefundingDeductionService into Transaction Orchestrator - CPM generate flow | For CPM (POST /v1/payments/cpm/generate), the deduction occurs at QR token issuance, not at scheme approval (AD-07). At generate time the final payout amount may not yet be known (merchant POS inputs it). A reservation amount is used: prefund_reserve_usd from the request body if supplied; otherwise the scheme's configured max transaction limit (default USD 500 per transaction if not configured). If deduction of the reservation amount fails (INSUFFICIENT_PREFUNDING), no CPM token is issued and HTTP 402 is returned. At CPM confirm time, if the actual deduction differs from the reservation, adjust via a supplemental deduction or reversal. | • Locate TransactionOrchestrator.generateCpmToken (or equivalent) • Determine reservation amount: use request.prefundReserveUsd if non-null, else load scheme max transaction limit from config • Call deductForPayment(partnerId, reservationAmountUsd, txnRef) for OVERSEAS partners only • On InsufficientPrefundingException: return HTTP 402, do not issue CPM token • On success: set transaction.prefundingDeductedUsd = reservationAmountUsd, issue CPM token • At CPM confirm: if actual collection_usd != reservation, call deductForPayment for surplus or reverseDeduction for excess | Updated TransactionOrchestrator with CPM generate + confirm prefunding integration | • OVERSEAS partner with balance=300.00, reserve=200.00: CPM token issued, balance becomes 100.00 • OVERSEAS partner with balance=150.00, reserve=200.00: HTTP 402, no CPM token, balance unchanged • LOCAL partner: CPM token issued without touching prefunding_account • At CPM confirm, if reservation was 200.00 but actual collection_usd=180.00, reverseDeduction(20.00) is called • At CPM confirm, if reservation was 200.00 but actual=220.00, additional deductForPayment(20.00) is called (or fail if insufficient) | 50 | 6.2-T11 | BE | RATE-04, NFR-10
6.2-T13 | prefunding | 6.2 | 6. Prefunding & Wallet Ledger | Atomic deduction (SELECT FOR UPDATE) | 1 | Implement prefunding reversal on payment failure and UNCERTAIN resolution | When a payment fails AFTER a successful deduction (e.g. scheme returns reject synchronously, or batch reconciliation confirms FAILED for an UNCERTAIN transaction), the deducted amount must be returned to the partner's prefunding balance. From spec: 'If reconciliation confirms FAILED, the deduction is reversed.' (SAD-02 §5.2). Use PrefundingDeductionService.reverseDeduction(partnerId, amountUsd, txnRef, note). Triggers: (1) scheme adapter returns failure immediately after deduction (state DEBITED -> FAILED). (2) Settlement/Reconciliation Engine resolves an UNCERTAIN transaction to FAILED after batch reconciliation (within 24h). Circuit breaker open (SCHEME_UNAVAILABLE) also triggers reversal since scheme was not called (spec §4.3: 'Prefunding balances are not deducted if the scheme call fails or circuit breaker is open'). | • In TransactionOrchestrator, after scheme adapter call, if scheme returns rejection: call reverseDeduction and transition to FAILED • In ReconciliationEngine, when UNCERTAIN resolves to FAILED: call reverseDeduction(partnerId, prefundingDeductedUsd, txnRef, 'reconciliation confirmed FAILED') • In circuit-breaker-open path: if OVERSEAS partner and deduction already occurred, call reverseDeduction • Ensure reverseDeduction idempotency: if called twice for same txnRef (e.g. duplicate reconciliation event), second call is a no-op • Record DEBIT_REVERSAL ledger entry and update transaction event trail | Updated TransactionOrchestrator and ReconciliationEngine with reversal on payment failure | • Scheme synchronous rejection: reverseDeduction called, partner balance restored, state=FAILED, DEBIT_REVERSAL ledger entry created • UNCERTAIN resolved to FAILED by reconciliation: reverseDeduction called with correct amount=prefundingDeductedUsd • Circuit breaker open path (scheme not called): balance NOT deducted in first place (no deduct, no reversal needed) - confirm via test • Duplicate reversal call for same txnRef returns existing result without double-crediting • Transaction event trail includes PREFUND_DEDUCTED step followed by a PREFUND_REVERSED step on failure | 45 | 6.2-T08, 6.2-T11 | BE | RATE-04, NFR-10
6.2-T14 | prefunding | 6.2 | 6. Prefunding & Wallet Ledger | Atomic deduction (SELECT FOR UPDATE) | 1 | Implement GET /v1/balance endpoint handler | GET /v1/balance returns the current prefunding balance for the authenticated OVERSEAS partner (API-05 §4.8). Response fields: partner_id (string), balance_usd (string decimal), low_balance_threshold_usd (string decimal), is_below_threshold (boolean = balance_usd < low_balance_threshold_usd), as_of (ISO-8601 UTC), recent_deductions (array, only if ?include_history=true, last 10 DEBIT_PAYMENT entries from ledger). LOCAL partners return HTTP 403. This endpoint does NOT use SELECT FOR UPDATE - it is a read-only point-in-time query. Example response: balance_usd='48234.56', low_balance_threshold_usd='10000.00', is_below_threshold=false. | • Create BalanceController.java with GET /v1/balance mapped method • Resolve partner from JWT/API-key context; reject LOCAL partners with HTTP 403 and error code PREFUNDING_NOT_APPLICABLE • Query prefunding_account via plain (non-locking) findByPartnerId • Optionally query last 10 ledger entries if include_history=true parameter • Map to BalanceResponse DTO with all fields from spec; format amounts as string decimals with 2dp • Return 200 with response body | BalanceController.java, BalanceResponse.java DTO | • LOCAL partner calling GET /v1/balance receives HTTP 403 with body containing PREFUNDING_NOT_APPLICABLE error code • OVERSEAS partner with balance=48234.5600 receives balance_usd='48234.56' • is_below_threshold=true when balance=9500.00 and threshold=10000.00; false when balance=10001.00 • With ?include_history=true, recent_deductions array contains up to 10 entries ordered by event_at descending • Without ?include_history=true, recent_deductions field is absent from response body | 35 | 6.2-T06, 6.2-T09 | BE | RATE-04, NFR-10
6.2-T15 | prefunding | 6.2 | 6. Prefunding & Wallet Ledger | Atomic deduction (SELECT FOR UPDATE) | 1 | Unit tests: PrefundingDeductionService - happy path and insufficient funds | Test class PrefundingDeductionServiceTest. Uses Mockito to mock PrefundingAccountRepository, PrefundingLedgerEntryRepository, LowBalanceAlertConfigRepository, ApplicationEventPublisher, and PartnerRepository. Test vectors from spec: balance=100.00 USD, deduction=35.77 USD -> newBalance=64.23; balance=50.00 USD, deduction=51.00 USD -> InsufficientPrefundingException. All amounts use BigDecimal. Verify that the ledger entry saved has amount=35.77, balanceAfter=64.23, entryType=DEBIT_PAYMENT. | • Create PrefundingDeductionServiceTest.java in test/java/com/gmepayplus/prefunding • Mock all dependencies with @Mock / @InjectMocks • Test: deductForPayment with balance=100.00, amount=35.77 returns DeductionResult(previousBalance=100.00, newBalance=64.23) • Verify PrefundingLedgerEntryRepository.save called with amount=35.77, balanceAfter=64.23, entryType=DEBIT_PAYMENT • Test: deductForPayment with balance=50.00, amount=51.00 throws InsufficientPrefundingException with availableUsd=50.00, requiredUsd=51.00 • Verify repository.save NOT called when exception thrown | PrefundingDeductionServiceTest.java with at least 5 test methods | • Test 'deduct_success_reduces_balance' passes: newBalance=64.23 asserted via BigDecimal.compareTo • Test 'deduct_throws_when_insufficient' passes: InsufficientPrefundingException with correct fields • Verify (via Mockito.verify) that save is NOT called on either repository when exception is thrown (no partial state) • Test 'deduct_creates_debit_payment_ledger_entry' verifies entryType=DEBIT_PAYMENT and amount=BigDecimal('35.77') • All tests pass with mvn test | 40 | 6.2-T07 | BE | RATE-04, NFR-10
6.2-T16 | prefunding | 6.2 | 6. Prefunding & Wallet Ledger | Atomic deduction (SELECT FOR UPDATE) | 1 | Unit tests: PrefundingDeductionService - reversal idempotency and LOCAL partner guard | Extended unit tests for PrefundingDeductionService. Test vectors: (1) reverseDeduction called twice with same txnRef must produce the same result without double-crediting. (2) deductForPayment called with a LOCAL partner id must throw IllegalArgumentException immediately without acquiring a DB lock. (3) creditTopUp(balance=100.00, amount=5000.00) -> newBalance=5100.00 with CREDIT_TOPUP ledger entry. Verify idempotency via mocked ledger repository that returns an existing DEBIT_REVERSAL entry on second call. | • Add test 'reversal_is_idempotent': mock ledger repo to return existing DEBIT_REVERSAL entry on second call for same txnRef • Verify account.save NOT called on second reversal call (balance not re-credited) • Add test 'deduct_throws_for_local_partner': mock partner repo to return partner with partnerType='LOCAL' • Verify IllegalArgumentException thrown before any lock acquisition (no findByPartnerIdForUpdate call) • Add test 'creditTopUp_adds_balance': balance=100.00, top-up=5000.00, assert newBalance=5100.00 and CREDIT_TOPUP entry | Extended PrefundingDeductionServiceTest.java with at least 3 additional test methods | • 'reversal_is_idempotent' passes: second reverseDeduction call returns without modifying balance • 'deduct_throws_for_local_partner' passes: IllegalArgumentException thrown, findByPartnerIdForUpdate NEVER called • 'creditTopUp_adds_balance' passes: newBalance=BigDecimal('5100.00') • 'creditTopUp_creates_credit_topup_entry' passes: entryType=CREDIT_TOPUP, amount=5000.00 • All tests pass with mvn test | 35 | 6.2-T15, 6.2-T08, 6.2-T09 | BE | RATE-04, NFR-10
6.2-T17 | prefunding | 6.2 | 6. Prefunding & Wallet Ledger | Atomic deduction (SELECT FOR UPDATE) | 1 | Unit tests: low-balance alert trigger | Test that the low-balance event is published correctly after a successful deduction. Test vectors: (A) balance goes from 10500.00 to 9800.00 with threshold=10000.00 -> event published with currentBalanceUsd=9800.00. (B) balance goes from 11000.00 to 10200.00 with threshold=10000.00 -> no event (still above threshold). (C) balance goes from 10500.00 to 9800.00 but is_active=false on the alert config -> no event. Uses Mockito ArgumentCaptor to assert event fields. | • Add test 'low_balance_event_published_when_below_threshold': mock config returns threshold=10000.00, is_active=true; deduct to 9800.00 • Capture published event via ArgumentCaptor<PrefundingLowBalanceEvent> • Assert event.currentBalanceUsd()=9800.00, event.thresholdUsd()=10000.00 • Add test 'no_event_when_above_threshold': deduct to 10200.00 with threshold=10000.00; verify event publisher NOT invoked • Add test 'no_event_when_alert_inactive': is_active=false; deduct below threshold; verify event NOT published | Low-balance alert unit tests added to PrefundingDeductionServiceTest.java | • Test A passes: ApplicationEventPublisher.publishEvent called once with correct PrefundingLowBalanceEvent payload • Test B passes: ApplicationEventPublisher.publishEvent NEVER called • Test C passes: ApplicationEventPublisher.publishEvent NEVER called when is_active=false • Event partnerId matches the deducting partner's id • All tests pass with mvn test | 30 | 6.2-T10, 6.2-T15 | BE | RATE-04, NFR-10
6.2-T18 | prefunding | 6.2 | 6. Prefunding & Wallet Ledger | Atomic deduction (SELECT FOR UPDATE) | 1 | Integration test: concurrent SELECT FOR UPDATE prevents over-deduction | This is the core correctness test for WBS 6.2 (NFR-10 §5.2, AD-06). Use @SpringBootTest with an embedded PostgreSQL (Testcontainers). Scenario: partner has balance=50.00 USD. Launch 10 concurrent threads each calling deductForPayment(partnerId, 10.00, txnRef_N) simultaneously. Expected: exactly 5 threads succeed (total deduction=50.00, newBalance=0.00); exactly 5 threads throw InsufficientPrefundingException. Total ledger entries = 5 DEBIT_PAYMENT rows. Final balance must be exactly 0.0000 - never negative. | • Add Testcontainers PostgreSQL dependency if not already present • Create PrefundingDeductionServiceIntegrationTest.java with @SpringBootTest • Seed a prefunding_account row with balance=50.00 for a test OVERSEAS partner • Submit 10 concurrent Callable tasks via ExecutorService.invokeAll • Count success results and InsufficientPrefundingException results • Query final balance and total ledger entry count from DB | PrefundingDeductionServiceIntegrationTest.java with concurrent over-deduction test | • Exactly 5 threads succeed and exactly 5 throw InsufficientPrefundingException (total must be 10) • Final balance in DB is exactly 0.0000 (not negative, not positive) • Exactly 5 DEBIT_PAYMENT ledger entries exist in prefunding_ledger_entry for the test partner • Test is deterministic and passes on repeated runs (no flakiness from lock ordering) • No DB deadlock exceptions observed in test output | 55 | 6.2-T07 | BE | RATE-04, NFR-10
6.2-T19 | prefunding | 6.2 | 6. Prefunding & Wallet Ledger | Atomic deduction (SELECT FOR UPDATE) | 1 | Integration test: MPM payment flow with prefunding - success path | End-to-end integration test (Testcontainers, stub scheme adapter) for POST /v1/payments MPM flow. OVERSEAS partner SendMN: balance=1000.00 USD. Rate engine produces collection_usd=35.77 (payout KRW 50,000 / cost_rate_pay=1397.00 -> payout_usd_cost=35.78, then /( 1-0.01-0.01)=36.51 collection_usd approximate; use exact values from rate engine). Stub scheme adapter returns approval. Expected: state=APPROVED, prefundingDeductedUsd=collection_usd, balance reduced by collection_usd, 1 DEBIT_PAYMENT ledger entry. | • Create MpmPaymentIntegrationTest.java with @SpringBootTest and TestRestTemplate • Seed partner SendMN with balance=1000.00 and a valid quote_id for a KRW 50,000 payment • POST /v1/payments with valid request body including quote_id • Stub ZeroPay scheme adapter to return ApprovalCode='ZP-APPROVAL-001' • Assert HTTP 200 or 201 response with status=APPROVED • Assert prefunding_account.balance = 1000.00 - collection_usd from DB | MpmPaymentIntegrationTest.java covering the OVERSEAS success path | • HTTP response is 200/201 with status=APPROVED • prefunding_account.balance reduced by exactly collection_usd (BigDecimal equality) • One DEBIT_PAYMENT ledger entry exists with amount=collection_usd, balanceAfter=1000.00-collection_usd • transaction.prefunding_deducted_usd = collection_usd in DB • Scheme adapter stub was called exactly once | 55 | 6.2-T11, 6.2-T18 | BE | RATE-04, NFR-10
6.2-T20 | prefunding | 6.2 | 6. Prefunding & Wallet Ledger | Atomic deduction (SELECT FOR UPDATE) | 1 | Integration test: MPM payment - insufficient funds returns HTTP 402 | POST /v1/payments for OVERSEAS partner with insufficient balance must return HTTP 402 INSUFFICIENT_PREFUNDING without calling the scheme. Test vector: partner balance=20.00 USD, rate engine produces collection_usd=35.77 USD. Expected: HTTP 402 response body {error:'INSUFFICIENT_PREFUNDING'}, transaction state=FAILED, scheme adapter NOT called, prefunding balance still 20.00 USD, no DEBIT_PAYMENT ledger entry created. | • Add test method 'mpm_payment_insufficient_funds' to MpmPaymentIntegrationTest.java • Seed partner with balance=20.00 USD • Seed a quote for a payment requiring collection_usd=35.77 • POST /v1/payments with valid body • Assert HTTP 402 • Verify DB: prefunding_account.balance=20.00, zero DEBIT_PAYMENT entries, transaction.status=FAILED | Test method mpm_payment_insufficient_funds in MpmPaymentIntegrationTest.java | • HTTP response is 402 • Response body contains error code INSUFFICIENT_PREFUNDING • Scheme adapter stub was called zero times • DB: prefunding_account.balance still equals 20.0000 after request • DB: no DEBIT_PAYMENT ledger entry for this txnRef | 30 | 6.2-T19 | BE | RATE-04, NFR-10
6.2-T21 | prefunding | 6.2 | 6. Prefunding & Wallet Ledger | Atomic deduction (SELECT FOR UPDATE) | 1 | Integration test: CPM generate and confirm with prefunding adjustment | POST /v1/payments/cpm/generate with OVERSEAS partner: reservation=200.00 USD, balance=500.00 USD. Token issued, balance=300.00. At CPM confirm, actual collection_usd=180.00 (less than reservation). Expected: supplemental reversal of 20.00 called, final balance=320.00. Also test surplus case: actual collection_usd=210.00, additional deduction of 10.00 called, final balance=290.00. | • Create CpmPaymentIntegrationTest.java • Test A: generate with reserve=200.00, confirm with actual=180.00; assert final balance=320.00 and one DEBIT_PAYMENT + one DEBIT_REVERSAL entry • Test B: generate with reserve=200.00, confirm with actual=210.00; assert final balance=290.00 and two DEBIT_PAYMENT entries (200+10) • Test C: generate with balance=150.00, reserve=200.00; assert HTTP 402, no token, balance unchanged • Verify CPM token expires_at is approximately 60 seconds in the future | CpmPaymentIntegrationTest.java covering generate + confirm prefunding flows | • Test A: final balance=320.00 in DB; ledger has DEBIT_PAYMENT(200.00) and DEBIT_REVERSAL(20.00) • Test B: final balance=290.00 in DB; ledger has two DEBIT_PAYMENT rows summing to 210.00 • Test C: HTTP 402 returned, balance=150.00 unchanged in DB • expires_at in CPM token response is between 55 and 65 seconds from request time • Scheme adapter not called in Test C (insufficient funds path) | 55 | 6.2-T12, 6.2-T18 | BE | RATE-04, NFR-10
6.2-T22 | prefunding | 6.2 | 6. Prefunding & Wallet Ledger | Atomic deduction (SELECT FOR UPDATE) | 1 | Integration test: prefunding reversal on scheme failure and UNCERTAIN resolution | Test the reversal flow: (1) deduction succeeds then scheme adapter returns synchronous rejection -> balance restored. (2) deduction succeeds, scheme returns UNCERTAIN (timeout), reconciliation later marks FAILED -> balance restored. Vector: balance=100.00, deduction=35.77; scenario 1: balance restored to 100.00 after rejection; scenario 2: balance stays at 64.23 until reconciliation resolves to FAILED, then restored to 100.00. | • In MpmPaymentIntegrationTest.java add test 'scheme_rejection_reverses_deduction': stub scheme to return rejection • Assert balance returns to 100.00 after rejection, DEBIT_PAYMENT + DEBIT_REVERSAL entries in ledger • Add test 'uncertain_resolution_to_failed_reverses_deduction': stub scheme to throw timeout (UNCERTAIN state) • Call ReconciliationEngine.resolveUncertain(txnRef, 'FAILED') • Assert balance returns to 100.00, DEBIT_REVERSAL entry created • Verify reversal called only once even if resolveUncertain called twice (idempotency) | Tests scheme_rejection_reverses_deduction and uncertain_resolution_to_failed_reverses_deduction | • After scheme rejection: balance=100.0000, ledger has DEBIT_PAYMENT(35.77) + DEBIT_REVERSAL(35.77) • After UNCERTAIN -> FAILED: balance=100.0000 restored, DEBIT_REVERSAL(35.77) present • Double call to resolveUncertain('FAILED'): only one DEBIT_REVERSAL entry (idempotency) • Transaction state=FAILED in both scenarios • Scheme adapter was called exactly once in the rejection scenario (not retried) | 50 | 6.2-T13, 6.2-T19 | BE | RATE-04, NFR-10
6.2-T23 | prefunding | 6.2 | 6. Prefunding & Wallet Ledger | Atomic deduction (SELECT FOR UPDATE) | 1 | Unit tests: GET /v1/balance controller | Unit test BalanceController using MockMvc. Test vectors: (1) OVERSEAS partner balance=48234.56, threshold=10000.00, is_below_threshold=false. (2) OVERSEAS partner balance=9500.00, threshold=10000.00, is_below_threshold=true. (3) LOCAL partner returns HTTP 403. (4) ?include_history=true returns recent_deductions array with mocked 3 entries. Amounts must be formatted as string decimals with exactly 2 decimal places (e.g. '48234.56' not '48234.5600'). | • Create BalanceControllerTest.java with @WebMvcTest(BalanceController.class) • Mock PrefundingAccountRepository and PrefundingLedgerEntryRepository • Test 1: OVERSEAS partner, balance=48234.56; assert balance_usd='48234.56', is_below_threshold=false • Test 2: OVERSEAS partner, balance=9500.00; assert is_below_threshold=true • Test 3: LOCAL partner; assert HTTP 403 body contains PREFUNDING_NOT_APPLICABLE • Test 4: include_history=true; assert recent_deductions array length=3 | BalanceControllerTest.java with at least 4 test methods | • Test 1 passes: balance_usd='48234.56' as JSON string • Test 2 passes: is_below_threshold=true • Test 3 passes: HTTP 403 with PREFUNDING_NOT_APPLICABLE in body • Test 4 passes: recent_deductions present with 3 elements when include_history=true • Test 5 (without include_history): recent_deductions key absent from response JSON | 35 | 6.2-T14 | BE | RATE-04, NFR-10
6.2-T24 | prefunding | 6.2 | 6. Prefunding & Wallet Ledger | Atomic deduction (SELECT FOR UPDATE) | 1 | Error mapping: InsufficientPrefundingException to HTTP 402 response body | InsufficientPrefundingException must map to HTTP 402 with JSON body {error:'INSUFFICIENT_PREFUNDING', partner_id:'...', required_usd:'51.00', available_usd:'50.00'}. This is done via a Spring @ExceptionHandler or @ControllerAdvice. The error code INSUFFICIENT_PREFUNDING is defined in API-05. The response must NOT include stack traces. HTTP 403 for LOCAL partner calling /v1/balance uses error code PREFUNDING_NOT_APPLICABLE. Both must use consistent GMEPay+ error envelope: {error, message, request_id}. | • Create or update GlobalExceptionHandler.java (@RestControllerAdvice) • Add @ExceptionHandler(InsufficientPrefundingException.class) returning ResponseEntity with HTTP 402 • Response body: {error:'INSUFFICIENT_PREFUNDING', required_usd: formatted BigDecimal, available_usd: formatted BigDecimal} • Add @ExceptionHandler for local-partner access on /v1/balance returning HTTP 403 + PREFUNDING_NOT_APPLICABLE • Ensure stack traces are excluded from response bodies in all environments • Write unit test verifying the 402 JSON body structure | GlobalExceptionHandler.java with InsufficientPrefundingException and local-partner handlers, unit test | • POST /v1/payments with insufficient funds returns HTTP 402 with body containing error='INSUFFICIENT_PREFUNDING' • Body contains required_usd='51.00' and available_usd='50.00' (string decimal format) • Body does NOT contain a stack trace field • GET /v1/balance by LOCAL partner returns HTTP 403 with error='PREFUNDING_NOT_APPLICABLE' • Unit test for GlobalExceptionHandler passes with mvn test | 30 | 6.2-T07, 6.2-T14 | BE | RATE-04, NFR-10
6.2-T25 | prefunding | 6.2 | 6. Prefunding & Wallet Ledger | Atomic deduction (SELECT FOR UPDATE) | 1 | Add prefunding_deducted_usd to transaction event trail (PREFUND_DEDUCTED event step) | The 8-step transaction event trail requires step 2 = PREFUND_DEDUCTED (from spec assumption A3 in DAT-03). A TransactionEvent row must be inserted with event_type='PREFUND_DEDUCTED', step=2, occurred_at=now(), duration_ms=deduction_duration after a successful deduction. For LOCAL partners (no deduction), this step is skipped and step 3 begins at SCHEME_SUBMITTED. The transaction_event table is append-only. Each event stores txn_ref, step, event_type, occurred_at, duration_ms. | • Verify TransactionEventRepository and TransactionEvent entity exist (from earlier WBS migrations) • In PrefundingDeductionService or TransactionOrchestrator, after successful deductForPayment, persist TransactionEvent(step=2, event_type='PREFUND_DEDUCTED', duration_ms=measured) • For LOCAL partner path in TransactionOrchestrator, skip step 2 and proceed to step 3 • Add unit test asserting step 2 event is saved after successful deduction • Add unit test asserting step 2 is absent for LOCAL partner path | PREFUND_DEDUCTED event step emitted after successful deduction; tests for both OVERSEAS and LOCAL paths | • Successful OVERSEAS deduction: TransactionEvent with event_type='PREFUND_DEDUCTED' and step=2 is inserted • duration_ms field is > 0 and represents actual deduction latency • LOCAL partner MPM flow: no PREFUND_DEDUCTED event in transaction_event table for that txn_ref • Event occurred_at is within 1 second of the deduction timestamp • Unit tests pass with mvn test | 30 | 6.2-T11, 6.2-T07 | BE | RATE-04, NFR-10
6.2-T26 | prefunding | 6.2 | 6. Prefunding & Wallet Ledger | Atomic deduction (SELECT FOR UPDATE) | 1 | Performance test: deduction throughput under 50 TPS sustained load | NFR-10 §2.2 requires 50 TPS sustained. The deduction path (SELECT FOR UPDATE) is the critical serialisation point per partner. Test with a single OVERSEAS partner at 50 concurrent deduction requests/sec sustained for 60 seconds. Assert: p95 latency of the deduction DB operation (not full API) < 50ms; no over-deductions; all requests return either success or INSUFFICIENT_PREFUNDING (no 5xx errors). Use k6 or JMeter against the local test environment with Testcontainers PostgreSQL. | • Seed partner with balance=500000.00 USD (large enough that no failures from insufficient funds expected) • Write k6 or JMeter script: 50 virtual users each calling POST /v1/payments (or the deduction service directly) at 1 req/sec each for 60 seconds • Measure p50/p95 of the DB deduction operation using Spring Micrometer timer • Assert p95 < 50ms for the deduction-only portion (excluding scheme stub latency) • Assert final balance = 500000.00 - (success_count * deduction_amount_per_request) • Assert zero 5xx responses | Performance test script (k6/JMeter) and results report as a text file in src/test/perf/ | • p95 deduction latency < 50ms under 50 TPS • Zero 5xx responses during 60-second run • Final balance exactly equals 500000.00 minus (num_successful_deductions * amount) - no over-deduction • No DB deadlock errors in application logs • Test report file saved to src/test/perf/6.2-deduction-perf-results.txt | 55 | 6.2-T18 | BE | RATE-04, NFR-10
6.2-T27 | prefunding | 6.2 | 6. Prefunding & Wallet Ledger | Atomic deduction (SELECT FOR UPDATE) | 1 | Add Micrometer metrics for prefunding deduction observability | OPS-13 and NFR-10 require observability metrics. Metrics to add: (1) prefunding.deduction.success counter (tags: partner_id) - incremented on each successful deduction. (2) prefunding.deduction.failure counter (tags: partner_id, reason=INSUFFICIENT_FUNDS) - incremented on InsufficientPrefundingException. (3) prefunding.balance gauge (tags: partner_id) - reports current balance (polled periodically, not per-deduction). (4) prefunding.deduction.duration timer (tags: partner_id) - records deduction latency. Use Micrometer MeterRegistry injected into PrefundingDeductionService. | • Inject MeterRegistry into PrefundingDeductionService • Add Counter.increment for prefunding.deduction.success on success • Add Counter.increment for prefunding.deduction.failure on InsufficientPrefundingException • Add Timer.record wrapping the DB deduction for prefunding.deduction.duration • Register a Gauge for prefunding.balance queried from DB (use scheduled poller every 30s, not per-request) • Write unit test verifying counters increment correctly | Updated PrefundingDeductionService.java with Micrometer metrics, unit test for counters | • prefunding.deduction.success counter increments by 1 on successful deduction (verified in unit test via MeterRegistry) • prefunding.deduction.failure counter increments by 1 on InsufficientPrefundingException • prefunding.deduction.duration timer records a value > 0 ms • prefunding.balance gauge is registered with partner_id tag • All existing unit tests still pass after instrumentation changes | 35 | 6.2-T07 | BE | RATE-04, NFR-10
6.2-T28 | prefunding | 6.2 | 6. Prefunding & Wallet Ledger | Atomic deduction (SELECT FOR UPDATE) | 1 | Document PrefundingDeductionService API and concurrency contract | A developer implementing callers of PrefundingDeductionService needs to understand: when to call vs skip (OVERSEAS/LOCAL distinction), the locking contract (no application-level locks needed - DB handles it), the exception contract (InsufficientPrefundingException = reject, not retry), and the idempotency contract for reverseDeduction (safe to call twice). Document as Javadoc on the service class and as a single ADR (Architecture Decision Record) file capturing the SELECT FOR UPDATE choice over application-level locking or optimistic locking. | • Add comprehensive Javadoc to PrefundingDeductionService class-level, deductForPayment, reverseDeduction, and creditTopUp • Javadoc must cover: thread-safety guarantee, exception semantics, when NOT to call (LOCAL partners), idempotency of reversal • Create docs/adr/ADR-006-prefunding-atomic-deduction.md (or next available number in ADR sequence) • ADR content: context (concurrent payment requests risk over-draw), decision (SELECT FOR UPDATE), alternatives considered (optimistic locking, Redis-based lock), consequences • ADR must reference NFR-10 §5.2 and AD-06 from SAD-02 | Javadoc on PrefundingDeductionService.java and docs/adr/ADR-006-prefunding-atomic-deduction.md | • Javadoc on deductForPayment describes: @param partnerId (must be OVERSEAS), @throws InsufficientPrefundingException with conditions • Javadoc on reverseDeduction explicitly states 'safe to call twice for same txnRef (idempotent)' • ADR includes Status: Accepted, Context, Decision, Alternatives Considered, Consequences sections • ADR references NFR-10 §5.2 (SELECT FOR UPDATE mandate) and AD-06 (scheme never called without prior deduction) • ADR file is committed and passes a markdown lint check | 30 | 6.2-T07, 6.2-T08 | BE | RATE-04, NFR-10
6.3-T01 | prefunding | 6.3 | 6. Prefunding & Wallet Ledger | Insufficient-balance rejection | 1 | Create prefunding_account table migration | GMEPay+ maintains a prepaid USD balance per OVERSEAS partner. The prefunding_account table holds one row per OVERSEAS partner with fields: id BIGINT PK, partner_id BIGINT FK->partner UNIQUE, currency CHAR(3) always USD, balance DECIMAL(20,4), low_balance_threshold DECIMAL(20,4) default 10000.00, created_at/updated_at/created_by/updated_by. Balance is mutated only via SELECT FOR UPDATE; no application-level locking. LOCAL partners have no prefunding account. | • Create a Flyway (or Liquibase) migration file V6_3_001__create_prefunding_account.sql • Define table with all columns per spec: id BIGINT GENERATED ALWAYS AS IDENTITY PK, partner_id BIGINT NOT NULL UNIQUE REFERENCES partner(id), currency CHAR(3) NOT NULL DEFAULT 'USD', balance DECIMAL(20,4) NOT NULL DEFAULT 0.0000, low_balance_threshold DECIMAL(20,4) NOT NULL DEFAULT 10000.0000, created_at TIMESTAMPTZ NOT NULL DEFAULT now(), updated_at TIMESTAMPTZ NOT NULL DEFAULT now(), created_by VARCHAR(120), updated_by VARCHAR(120) • Add a CHECK constraint balance >= 0 • Add index on partner_id (already enforced by UNIQUE but confirm explicit index exists for FK lookup) • Run migration in dev environment and verify schema with \d prefunding_account | Migration file V6_3_001__create_prefunding_account.sql applied cleanly to dev DB | • Migration applies without error; table exists with all 10 columns • balance column is DECIMAL(20,4); currency defaults to USD • UNIQUE constraint on partner_id prevents two accounts per partner • CHECK constraint rejects INSERT with balance = -0.0001 • Attempting to set balance = -5.00 via direct UPDATE raises constraint violation | 25 |  | BE | API-05
6.3-T02 | prefunding | 6.3 | 6. Prefunding & Wallet Ledger | Insufficient-balance rejection | 1 | Create prefunding_ledger_entry table migration | Every debit or credit to a prefunding_account creates an immutable append-only ledger row. Fields: id BIGINT PK, account_id BIGINT FK->prefunding_account, txn_ref VARCHAR(64) (payment txn_ref for debits; internal ref for top-ups), entry_type VARCHAR(20) in (DEBIT_PAYMENT, DEBIT_REVERSAL, CREDIT_TOPUP, CREDIT_REVERSAL), amount DECIMAL(20,4) positive value (direction indicated by entry_type), balance_after DECIMAL(20,4) running balance snapshot, note VARCHAR(255), created_at TIMESTAMPTZ immutable, created_by VARCHAR(120). No updated_at. Index on (account_id, created_at) for history queries. | • Create migration file V6_3_002__create_prefunding_ledger_entry.sql • Define table with all columns; add CHECK (amount > 0) • Add CHECK constraint entry_type IN ('DEBIT_PAYMENT','DEBIT_REVERSAL','CREDIT_TOPUP','CREDIT_REVERSAL') • Create composite index idx_prefunding_ledger_account_created ON prefunding_ledger_entry(account_id, created_at) • Confirm no updated_at column exists (table is append-only) | Migration file V6_3_002__create_prefunding_ledger_entry.sql applied cleanly | • Table has exactly 10 columns; no updated_at column • CHECK (amount > 0) rejects INSERT with amount = 0 • entry_type CHECK rejects value 'DEBIT_UNKNOWN' • Composite index idx_prefunding_ledger_account_created exists and is used by EXPLAIN on (account_id, created_at DESC) query • FK to prefunding_account enforced: INSERT with nonexistent account_id fails | 25 | 6.3-T01 | BE | API-05
6.3-T03 | prefunding | 6.3 | 6. Prefunding & Wallet Ledger | Insufficient-balance rejection | 1 | Create low_balance_alert_config table migration | Per-partner configurable alert settings live in a separate table: id BIGINT PK, partner_id BIGINT FK->partner UNIQUE, threshold_usd DECIMAL(20,4) default 10000.00, alert_email VARCHAR(255), is_active BOOLEAN, created_at/updated_at/created_by/updated_by. This table drives when the prefunding.low_balance internal event fires after a debit; it is separate from prefunding_account so alert settings can be updated without touching the balance row. | • Create migration file V6_3_003__create_low_balance_alert_config.sql • Define table with all 9 columns; threshold_usd NOT NULL DEFAULT 10000.0000 • Add CHECK (threshold_usd >= 0) • Confirm UNIQUE on partner_id • Run migration and verify with \d low_balance_alert_config | Migration file V6_3_003__create_low_balance_alert_config.sql applied cleanly | • Table exists with 9 columns including is_active BOOLEAN • UNIQUE constraint on partner_id enforced • CHECK (threshold_usd >= 0) rejects negative threshold • threshold_usd defaults to 10000.0000 when not provided • FK to partner(id) enforced; orphan partner_id insert fails | 20 |  | BE | API-05
6.3-T04 | prefunding | 6.3 | 6. Prefunding & Wallet Ledger | Insufficient-balance rejection | 1 | Define PrefundingAccount and PrefundingLedgerEntry JPA entities | Java JPA entities for the prefunding_account and prefunding_ledger_entry tables created in T01/T02. PrefundingAccount: fields id, partnerId, currency (always USD), balance (BigDecimal scale 4), lowBalanceThreshold (BigDecimal scale 4), audit fields. PrefundingLedgerEntry: fields id, accountId, txnRef, entryType (enum: DEBIT_PAYMENT, DEBIT_REVERSAL, CREDIT_TOPUP, CREDIT_REVERSAL), amount, balanceAfter, note, createdAt, createdBy. LedgerEntry has no updatedAt (immutable). Use DECIMAL(20,4) column definitions in @Column annotations. | • Create PrefundingAccount.java JPA entity mapped to prefunding_account • Create EntryType.java enum with four values • Create PrefundingLedgerEntry.java JPA entity mapped to prefunding_ledger_entry; annotate as immutable (no setter for id/createdAt) • Add @Version on PrefundingAccount for optimistic locking (secondary guard alongside SELECT FOR UPDATE) • Ensure balance field uses BigDecimal with @Column(precision=20, scale=4) | PrefundingAccount.java, EntryType.java, PrefundingLedgerEntry.java entity classes compiling cleanly | • PrefundingAccount.balance is BigDecimal with precision 20 scale 4 • PrefundingLedgerEntry has no updatedAt field • EntryType enum contains exactly DEBIT_PAYMENT, DEBIT_REVERSAL, CREDIT_TOPUP, CREDIT_REVERSAL • PrefundingLedgerEntry.amount is BigDecimal not double or float • Unit: new PrefundingLedgerEntry with amount=BigDecimal.ZERO fails bean validation (@Positive or @DecimalMin('0.01')) | 30 | 6.3-T01, 6.3-T02 | BE | API-05
6.3-T05 | prefunding | 6.3 | 6. Prefunding & Wallet Ledger | Insufficient-balance rejection | 1 | Define PrefundingRepository and LedgerEntryRepository interfaces | Spring Data JPA repositories for the two prefunding tables. PrefundingAccountRepository needs: findByPartnerId(Long), findByPartnerIdWithLock (using @Lock(PESSIMISTIC_WRITE) for the SELECT FOR UPDATE pattern). PrefundingLedgerEntryRepository needs: save(entry), findByAccountIdOrderByCreatedAtDesc (paged), findByTxnRef(String). The lock query is critical: it must use JPQL with LockModeType.PESSIMISTIC_WRITE so Hibernate emits SELECT ... FOR UPDATE. | • Create PrefundingAccountRepository.java extending JpaRepository • Add @Lock(LockModeType.PESSIMISTIC_WRITE) @Query on findByPartnerIdWithLock method • Create PrefundingLedgerEntryRepository.java extending JpaRepository • Add findByAccountIdOrderByCreatedAtDesc(Long accountId, Pageable pageable) • Add findByTxnRef(String txnRef) for idempotency lookups | PrefundingAccountRepository.java and PrefundingLedgerEntryRepository.java | • findByPartnerIdWithLock generates SQL containing FOR UPDATE (verified via Hibernate SQL log in test) • findByAccountIdOrderByCreatedAtDesc returns entries newest-first • findByTxnRef returns empty Optional for unknown ref • Repository bean loads in Spring context integration test without errors • LockModeType is PESSIMISTIC_WRITE not OPTIMISTIC | 25 | 6.3-T04 | BE | API-05
6.3-T06 | prefunding | 6.3 | 6. Prefunding & Wallet Ledger | Insufficient-balance rejection | 1 | Implement PrefundingService.deductBalance core method | PrefundingService.deductBalance(Long partnerId, BigDecimal amountUsd, String txnRef) is the single atomic point for all prefunding debits. Algorithm: 1) Load account via findByPartnerIdWithLock (SELECT FOR UPDATE). 2) If balance < amountUsd throw InsufficientPrefundingException (do NOT call scheme). 3) Subtract: newBalance = balance - amountUsd. 4) Update account.balance = newBalance and save. 5) Append PrefundingLedgerEntry (type=DEBIT_PAYMENT, amount=amountUsd, balanceAfter=newBalance, txnRef=txnRef). 6) Return DeductionResult(newBalance, entryId). Entire method runs in a single @Transactional block. LOCAL partners must never call this method; guard: if partner.type != OVERSEAS throw IllegalStateException. | • Create PrefundingService.java Spring @Service • Implement deductBalance(@Transactional, requires active TX) using repository lock query • Throw InsufficientPrefundingException (checked, carries partner_id and required/available amounts) when balance < amountUsd • Update account balance and persist ledger entry atomically in same transaction • Return DeductionResult record with fields newBalance, ledgerEntryId • Add guard: throw IllegalStateException if partner type is not OVERSEAS | PrefundingService.java with deductBalance method; InsufficientPrefundingException.java | • balance=100.00 amountUsd=100.00 -> deduction succeeds, newBalance=0.00, ledger entry created • balance=99.99 amountUsd=100.00 -> InsufficientPrefundingException thrown, balance unchanged, no ledger entry written • Concurrent calls: two threads each trying to deduct 60.00 from balance=100.00 -> exactly one succeeds, one throws InsufficientPrefundingException (test with two threads and CountDownLatch) • LOCAL partner call -> IllegalStateException before any DB access • Returned DeductionResult.newBalance equals account.balance in DB after commit | 45 | 6.3-T05 | BE | API-05
6.3-T07 | prefunding | 6.3 | 6. Prefunding & Wallet Ledger | Insufficient-balance rejection | 1 | Implement InsufficientPrefundingException and error mapping to HTTP 402 | GMEPay+ returns HTTP 402 with error code INSUFFICIENT_PREFUNDING when an OVERSEAS partner's balance is too low. Error envelope format: {error: {code: 'INSUFFICIENT_PREFUNDING', message: '...', request_id: '...', details: []}}. This error is not retryable; the partner must top up and use a new Idempotency-Key. The exception must carry enough info to build the error message: partner_id, required_amount_usd (the deduction that was attempted), available_balance_usd. | • Create InsufficientPrefundingException.java extending RuntimeException with fields partnerId, requiredAmountUsd, availableBalanceUsd • Create or extend GlobalExceptionHandler (@RestControllerAdvice) to map InsufficientPrefundingException to HTTP 402 • Build response body: error.code='INSUFFICIENT_PREFUNDING', error.message includes available and required amounts, error.details empty array • Ensure no scheme-call or further processing occurs after this exception propagates • Add the error code to the API error code reference (error-codes enum/constant class if one exists) | InsufficientPrefundingException.java; exception handler mapping to 402 response | • Handler returns HTTP 402 with Content-Type application/json • Response body error.code == 'INSUFFICIENT_PREFUNDING' • Response body contains request_id matching X-Request-ID header • error.details is an empty array not null • Exception thrown by deductBalance propagates through handler without being swallowed as 500 | 30 | 6.3-T06 | BE | API-05
6.3-T08 | prefunding | 6.3 | 6. Prefunding & Wallet Ledger | Insufficient-balance rejection | 1 | Integrate prefunding deduction into MPM payment orchestration (POST /v1/payments) | In the Transaction Orchestrator, POST /v1/payments flow for OVERSEAS partners must: transition state QUOTED->PENDING_DEBIT, call PrefundingService.deductBalance(partnerId, payout_usd_cost, txnRef), on success transition PENDING_DEBIT->DEBITED then proceed to scheme call; on InsufficientPrefundingException transition PENDING_DEBIT->FAILED and return HTTP 402. The deduction amount is payout_usd_cost = target_payout / cost_rate_pay (from the locked rate quote). The scheme is NEVER called if deduction fails. LOCAL partners skip PENDING_DEBIT and go directly QUOTED->DEBITED. | • In the payment orchestration handler for POST /v1/payments, after quote validation and before scheme adapter call, add partner-type branch • For OVERSEAS: set txn state = PENDING_DEBIT, call deductBalance; catch InsufficientPrefundingException -> set state FAILED, rethrow (handler returns 402) • For LOCAL: set txn state = DEBITED directly (no deduction) • Confirm scheme adapter is only invoked after reaching DEBITED state • Record prefund_deducted_usd in the transaction record on successful deduction; include this field in the 201 response body | Updated payment orchestration handler with prefunding guard for MPM flow | • OVERSEAS partner with sufficient balance: state transitions QUOTED->PENDING_DEBIT->DEBITED->SCHEME_SENT; scheme is called • OVERSEAS partner with balance=0.00 and amountUsd=35.77: HTTP 402 returned, state=FAILED, scheme adapter never invoked • LOCAL partner (type=LOCAL): state goes QUOTED->DEBITED; deductBalance never called • 201 response for OVERSEAS payment includes prefund_deducted_usd matching payout_usd_cost to 4 decimal places • Failing deduction does not create a ledger entry (verified by querying prefunding_ledger_entry for that txn_ref) | 45 | 6.3-T07, 6.3-T05 | BE | API-05
6.3-T09 | prefunding | 6.3 | 6. Prefunding & Wallet Ledger | Insufficient-balance rejection | 1 | Integrate prefunding reservation into CPM token generation (POST /v1/payments/cpm/generate) | For CPM flow, the prefunding deduction happens at POST /v1/payments/cpm/generate (QR token issuance), not when the merchant scans. Spec: the QR token represents a committed payment intent. For OVERSEAS partners, call PrefundingService.deductBalance with a reservation amount. The reserved amount is the payout_usd_cost derived from the rule (since no payout amount is known at generate time, use the rule's configured max amount or a configurable cap per partner). On insufficient balance return HTTP 402 and do not issue the token. Response field prefund_reserved_usd echoes the reserved amount. | • In POST /v1/payments/cpm/generate handler, after partner/scheme validation, add OVERSEAS prefunding check • Determine reservation amount: use partner rule's configured cpm_reservation_usd or partner account max if set; document the field name used • Call PrefundingService.deductBalance(partnerId, reservationAmount, generatedCpmTxnRef) • On InsufficientPrefundingException return HTTP 402 (same envelope) and do not generate token • On success include prefund_reserved_usd in the 201 response body | Updated CPM generate handler with prefunding guard | • OVERSEAS partner with balance=50.00, reservation=100.00: HTTP 402 returned, no CPM token issued, no ledger entry created • OVERSEAS partner with balance=200.00, reservation=100.00: token issued, prefund_reserved_usd=100.00 in response • LOCAL partner: deductBalance not called, token issued without any balance check • State at token issue is PENDING_DEBIT transitioning to DEBITED after successful deduction • Deduction txn_ref stored with CPM token record for reconciliation | 40 | 6.3-T08 | BE | API-05
6.3-T10 | prefunding | 6.3 | 6. Prefunding & Wallet Ledger | Insufficient-balance rejection | 1 | Implement post-deduction low-balance alert trigger | After every successful prefunding deduction, if the new balance falls at or below the partner's low_balance_threshold_usd (from low_balance_alert_config), fire an internal event prefunding.low_balance. The Notification Service listens to this event and sends an email to alert_email. The alert should fire once per threshold crossing per debit (not on every transaction while below threshold). Use a simple approach: fire if newBalance <= threshold AND (previous balance > threshold OR this is a configurable re-alert interval). Phase 1 simplification: fire the alert on every debit where newBalance <= threshold and is_active=true. | • After successful deductBalance, load low_balance_alert_config for the partner • If is_active=true and newBalance <= threshold_usd, publish ApplicationEvent PrefundingLowBalanceEvent(partnerId, newBalance, threshold_usd, alertEmail) • Create PrefundingLowBalanceEvent.java record with those fields • Create NotificationService listener @EventListener that logs the event (email integration is a separate ticket or stub); at minimum write to audit log • Write unit test: deductBalance from 15000.00 to 9500.00 with threshold=10000.00 verifies event published | PrefundingLowBalanceEvent.java; event publish logic in PrefundingService; stub listener in NotificationService | • Deduct from 15000.00 to 9500.00 with threshold=10000.00: PrefundingLowBalanceEvent is published with newBalance=9500.00 • Deduct from 9000.00 to 8000.00 with threshold=10000.00 (already below threshold): event is still published (phase 1 simple rule) • is_active=false: no event published regardless of balance • LOCAL partner: no event published (deductBalance never called for LOCAL) • Event fields partnerId, newBalance, thresholdUsd, alertEmail all non-null | 30 | 6.3-T06 | BE | API-05
6.3-T11 | prefunding | 6.3 | 6. Prefunding & Wallet Ledger | Insufficient-balance rejection | 1 | Implement PrefundingService.creditBalance for top-ups and reversals | Balance credits occur in two cases: (1) CREDIT_TOPUP when GME Ops records a partner top-up via Admin System; (2) CREDIT_REVERSAL when an UNCERTAIN payment is reconciled as FAILED. Method signature: creditBalance(Long partnerId, BigDecimal amountUsd, EntryType entryType, String txnRef, String note). Algorithm: SELECT FOR UPDATE on account, newBalance = balance + amountUsd, save account, append ledger entry. entry_type must be CREDIT_TOPUP or CREDIT_REVERSAL; any other value throws IllegalArgumentException. | • Add creditBalance method to PrefundingService.java annotated @Transactional • Load account with pessimistic write lock (findByPartnerIdWithLock) • Validate entryType is CREDIT_TOPUP or CREDIT_REVERSAL; throw IllegalArgumentException otherwise • Add amountUsd to balance; persist ledger entry with type, txnRef, note, balanceAfter • Return CreditResult(newBalance, ledgerEntryId) | PrefundingService.creditBalance method | • creditBalance(partnerId, 5000.00, CREDIT_TOPUP, 'TOP-2026-001', 'Manual top-up'): balance increases by 5000.00, ledger entry created with entry_type=CREDIT_TOPUP • CREDIT_REVERSAL entry: ledger entry type=CREDIT_REVERSAL and txnRef matches original payment txnRef • Invalid entryType DEBIT_PAYMENT passed to creditBalance: IllegalArgumentException thrown • Concurrent credit and debit: SELECT FOR UPDATE prevents lost updates • balanceAfter in ledger entry equals account.balance after commit | 30 | 6.3-T06 | BE | API-05
6.3-T12 | prefunding | 6.3 | 6. Prefunding & Wallet Ledger | Insufficient-balance rejection | 1 | Implement UNCERTAIN->FAILED prefunding reversal in reconciliation path | When the Settlement/Reconciliation Engine resolves a transaction from UNCERTAIN to FAILED, if the partner is OVERSEAS, the previously deducted prefunding amount must be reversed via creditBalance(partnerId, deductedAmount, CREDIT_REVERSAL, txnRef, 'Reconciliation reversal'). The deducted amount is stored in the transaction record field prefund_deducted_usd. The reversal must be idempotent: if a ledger entry with entry_type=CREDIT_REVERSAL and txnRef already exists, skip (do not double-credit). | • In the reconciliation engine handler for UNCERTAIN->FAILED transition, after setting transaction state to FAILED, check partner type • If OVERSEAS: look up prefund_deducted_usd from transaction record • Check prefunding_ledger_entry for existing CREDIT_REVERSAL with same txnRef; if found skip • Call creditBalance(partnerId, prefund_deducted_usd, CREDIT_REVERSAL, txnRef, 'Reconciliation reversal') • Log audit event: PREFUNDING_REVERSAL with amount, txnRef, partnerId | Reconciliation path update with idempotent reversal call | • UNCERTAIN->FAILED for OVERSEAS partner with prefund_deducted_usd=42.50: balance increased by 42.50, CREDIT_REVERSAL ledger entry created • UNCERTAIN->FAILED called twice for same txnRef (simulated duplicate): second call skips reversal, balance not doubled • UNCERTAIN->FAILED for LOCAL partner: creditBalance not called • UNCERTAIN->APPROVED: no reversal (balance stays deducted) • Audit log contains PREFUNDING_REVERSAL event with correct amount and txnRef | 40 | 6.3-T11 | BE | API-05
6.3-T13 | prefunding | 6.3 | 6. Prefunding & Wallet Ledger | Insufficient-balance rejection | 1 | Expose GET /v1/prefunding/balance endpoint for partner self-service | Partners can query their own prefunding balance via GET /v1/prefunding/balance (authenticated with X-API-Key). Response: {partner_id, balance_usd (DECIMAL string, 2dp for display), currency: 'USD', low_balance_threshold_usd, as_of (ISO-8601 UTC)}. Only OVERSEAS partners have a balance; LOCAL partners receive 404 with code PREFUNDING_NOT_APPLICABLE. Auth: partner can only see their own balance; no cross-partner access. | • Create GET /v1/prefunding/balance controller method • Resolve partner from X-API-Key authentication context • If partner.type == LOCAL return 404 with error code PREFUNDING_NOT_APPLICABLE • Load PrefundingAccount by partnerId; if not found return 404 • Return balance_usd formatted to 2 decimal places (display only; store with 4dp), currency, threshold, as_of=now() | GET /v1/prefunding/balance endpoint in PartnerPrefundingController.java | • OVERSEAS partner with balance=12345.6789: response balance_usd='12345.68' (rounded to 2dp for display) • LOCAL partner: HTTP 404 error code PREFUNDING_NOT_APPLICABLE • Partner A cannot see Partner B balance (auth guard enforced by partner resolution from API key) • Response field currency always 'USD' • as_of timestamp is within 2 seconds of server time | 30 | 6.3-T05 | BE | API-05
6.3-T14 | prefunding | 6.3 | 6. Prefunding & Wallet Ledger | Insufficient-balance rejection | 1 | Unit tests: PrefundingService.deductBalance happy path and boundary | Explicit unit test ticket for PrefundingService.deductBalance. Use Mockito to mock PrefundingAccountRepository and PrefundingLedgerEntryRepository. Test vectors cover: exact balance match, insufficient by 1 cent, zero balance, large amount. All assertions must use BigDecimal.compareTo (not equals) for numeric checks. | • Create PrefundingServiceDeductBalanceTest.java • Mock findByPartnerIdWithLock to return a PrefundingAccount stub • Write test: balance=100.00, deduct=100.00 -> success, newBalance=0.00, ledger entry saved • Write test: balance=100.00, deduct=100.01 -> InsufficientPrefundingException; verify save never called on account • Write test: balance=0.00, deduct=0.01 -> InsufficientPrefundingException • Write test: balance=1000000.00, deduct=999999.9999 -> success, newBalance=0.0001 | PrefundingServiceDeductBalanceTest.java with 4+ passing test methods | • All 4 tests pass with mvn test • InsufficientPrefundingException carries requiredAmountUsd=100.01 and availableBalanceUsd=100.00 in the second test • Ledger entry save is called exactly once on success path • Account save is called exactly once on success path; never called on failure path • No test uses double or float arithmetic; all amounts are new BigDecimal(String) | 35 | 6.3-T06 | BE | API-05
6.3-T15 | prefunding | 6.3 | 6. Prefunding & Wallet Ledger | Insufficient-balance rejection | 1 | Unit tests: PrefundingService low-balance alert trigger logic | Unit tests for the alert event publishing logic. Verify that PrefundingLowBalanceEvent is published under correct conditions and not published otherwise. Use ApplicationEventPublisher mock. | • Create PrefundingServiceAlertTest.java • Mock ApplicationEventPublisher • Test: balance drops from 15000.00 to 9500.00, threshold=10000.00, is_active=true -> event published with newBalance=9500.00 • Test: balance drops from 15000.00 to 10500.00, threshold=10000.00 -> no event published (still above threshold) • Test: balance drops from 9500.00 to 8000.00, threshold=10000.00, is_active=true -> event published (already below threshold but phase 1 fires every time) • Test: balance drops to 9000.00, is_active=false -> no event published | PrefundingServiceAlertTest.java with 4 passing test methods | • publishEvent called exactly once in test 1; 0 times in test 2 • Event.newBalance == 9500.00 in test 1 (BigDecimal.compareTo) • is_active=false suppresses event regardless of balance • All 4 tests pass with mvn test • Test 3 publishes event confirming phase 1 simple rule (fire every debit below threshold) | 30 | 6.3-T10 | BE | API-05
6.3-T16 | prefunding | 6.3 | 6. Prefunding & Wallet Ledger | Insufficient-balance rejection | 1 | Unit tests: HTTP 402 response shape for INSUFFICIENT_PREFUNDING | Unit tests for GlobalExceptionHandler mapping of InsufficientPrefundingException to HTTP 402. Use MockMvc or WebMvcTest slice. Verify the exact response envelope matches API spec: HTTP 402, Content-Type application/json, body {error: {code: 'INSUFFICIENT_PREFUNDING', message: ..., request_id: ..., details: []}}. | • Create PrefundingErrorHandlerTest.java using @WebMvcTest on a minimal test controller that throws InsufficientPrefundingException • Call POST endpoint that triggers the exception • Assert HTTP status 402 • Assert response JSON: error.code == 'INSUFFICIENT_PREFUNDING' • Assert error.details is an empty array • Assert error.request_id matches X-Request-ID header | PrefundingErrorHandlerTest.java with 3+ passing tests | • HTTP status is exactly 402 (not 400 or 422) • Content-Type: application/json in response • error.code field value is exactly the string 'INSUFFICIENT_PREFUNDING' • error.details is [] not null • error.request_id is non-empty and matches X-Request-ID response header | 30 | 6.3-T07 | BE | API-05
6.3-T17 | prefunding | 6.3 | 6. Prefunding & Wallet Ledger | Insufficient-balance rejection | 1 | Integration test: concurrent deduction atomicity under contention | Integration test verifying SELECT FOR UPDATE prevents overdraft when two concurrent requests both attempt to deduct from the same OVERSEAS partner account. Start both threads simultaneously; assert exactly one succeeds and one throws InsufficientPrefundingException. Uses real DB (Testcontainers PostgreSQL) to validate the FOR UPDATE locking. Balance initial state: 100.00 USD. Thread A deducts 60.00, Thread B deducts 60.00 simultaneously. | • Create PrefundingConcurrencyIT.java with @SpringBootTest and Testcontainers PostgreSQL • Seed partner and prefunding_account with balance=100.00 • Launch two threads using ExecutorService, both calling deductBalance with amount=60.00 and distinct txnRefs • Collect results; assert exactly 1 DeductionResult and 1 InsufficientPrefundingException • Assert final DB balance = 40.00 (one successful deduction of 60.00) • Assert exactly 1 row in prefunding_ledger_entry for this account | PrefundingConcurrencyIT.java integration test passing | • Exactly one thread succeeds with newBalance=40.00 • Exactly one thread receives InsufficientPrefundingException with availableBalanceUsd=100.00 • prefunding_account.balance in DB equals 40.00 after both threads complete • prefunding_ledger_entry has exactly 1 DEBIT_PAYMENT row for these two txnRefs • Test passes reliably across 5 repeated runs (no flakiness) | 55 | 6.3-T06, 6.3-T02 | BE | API-05
6.3-T18 | prefunding | 6.3 | 6. Prefunding & Wallet Ledger | Insufficient-balance rejection | 1 | Integration test: MPM payment rejected before scheme when balance insufficient | End-to-end integration test for POST /v1/payments with an OVERSEAS partner. Scenario: partner has balance=10.00 USD; payment requires payout_usd_cost=35.77 USD. Assert HTTP 402 returned, scheme adapter never called, transaction state=FAILED, no ledger entry written. Uses Testcontainers PostgreSQL and a mock scheme adapter. | • Create InsufficientPrefundingMpmIT.java with @SpringBootTest, Testcontainers, and a MockSchemeAdapter spy • Seed OVERSEAS partner with prefunding_account.balance=10.00 • Create a valid rate quote with payout_usd_cost=35.77 (seed in Redis/DB) • POST /v1/payments with valid quote_id, merchant_qr, collection_amount, etc. • Assert HTTP 402 response with error.code='INSUFFICIENT_PREFUNDING' • Assert MockSchemeAdapter.submitMpm never invoked; assert transaction state=FAILED in DB; assert 0 ledger entries | InsufficientPrefundingMpmIT.java integration test passing | • HTTP 402 with error.code='INSUFFICIENT_PREFUNDING' • MockSchemeAdapter.submitMpm call count == 0 • Transaction record state == 'FAILED' in DB • prefunding_ledger_entry count for this txnRef == 0 • prefunding_account.balance remains 10.00 (unchanged) | 55 | 6.3-T08, 6.3-T17 | BE | API-05
6.3-T19 | prefunding | 6.3 | 6. Prefunding & Wallet Ledger | Insufficient-balance rejection | 1 | Integration test: CPM token generation rejected before issue when balance insufficient | End-to-end integration test for POST /v1/payments/cpm/generate with OVERSEAS partner. Balance=50.00 USD, reservation=100.00 USD. Assert HTTP 402 returned, no CPM token generated, no ledger entry. Contrast with successful scenario (balance=200.00). | • Create InsufficientPrefundingCpmIT.java with @SpringBootTest and Testcontainers • Seed OVERSEAS partner with balance=50.00 and cpm_reservation_usd=100.00 • POST /v1/payments/cpm/generate with valid request body • Assert HTTP 402 with error.code='INSUFFICIENT_PREFUNDING' • Reseed balance=200.00; repeat request with new Idempotency-Key • Assert HTTP 201 with prefund_reserved_usd='100.00' | InsufficientPrefundingCpmIT.java with 2 test scenarios passing | • Insufficient scenario: HTTP 402, no row in cpm_token table for this partner_txn_ref • Sufficient scenario: HTTP 201, prefund_reserved_usd='100.00', ledger entry created with DEBIT_PAYMENT • Insufficient scenario: prefunding_account.balance remains 50.00 • Sufficient scenario: prefunding_account.balance = 100.00 after deduction • Both tests are independent and pass in either order | 50 | 6.3-T09 | BE | API-05
6.3-T20 | prefunding | 6.3 | 6. Prefunding & Wallet Ledger | Insufficient-balance rejection | 1 | Integration test: UNCERTAIN->FAILED reversal credits balance correctly | Integration test for the reconciliation-triggered reversal path. Seed an APPROVED->UNCERTAIN transaction for an OVERSEAS partner with prefund_deducted_usd=42.50 and initial balance=500.00. Trigger UNCERTAIN->FAILED reconciliation transition. Assert balance=542.50 and CREDIT_REVERSAL ledger entry exists. Then trigger same transition again (idempotency check) and assert balance stays 542.50. | • Create ReconciliationReversalIT.java with Testcontainers • Seed OVERSEAS partner, prefunding_account.balance=500.00, one transaction in UNCERTAIN state with prefund_deducted_usd=42.50 • Invoke reconciliation UNCERTAIN->FAILED handler for the transaction • Assert balance=542.50, CREDIT_REVERSAL ledger entry with txnRef and amount=42.50 • Invoke handler again for same transaction (idempotency) • Assert balance still 542.50, still only 1 CREDIT_REVERSAL entry | ReconciliationReversalIT.java with 2 scenario passing | • After first FAILED transition: balance=542.50 (500.00+42.50) • CREDIT_REVERSAL ledger entry exists with amount=42.50 and correct txnRef • Second invocation does not create duplicate entry • balance after second invocation is still 542.50 • UNCERTAIN->APPROVED transition does not create any CREDIT_REVERSAL entry (verify with third scenario) | 50 | 6.3-T12 | BE | API-05
6.3-T21 | prefunding | 6.3 | 6. Prefunding & Wallet Ledger | Insufficient-balance rejection | 1 | Add prefund_deducted_usd to transaction record and MPM response | The transaction table must store prefund_deducted_usd DECIMAL(20,4) nullable (null for LOCAL). This field is populated from DeductionResult.amount at PENDING_DEBIT->DEBITED transition. It is immutable after commit. The POST /v1/payments 201 response includes prefund_deducted_usd as a string decimal (OVERSEAS only; omitted or null for LOCAL). Field is used by the reversal path (T12) and BOK reporting. | • Create migration V6_3_004__add_prefund_deducted_usd_to_transaction.sql: ALTER TABLE transaction ADD COLUMN prefund_deducted_usd DECIMAL(20,4) • Add prefund_deducted_usd field to Transaction JPA entity (nullable BigDecimal) • In orchestration handler, after successful deductBalance, set transaction.prefundDeductedUsd = result.amount • In 201 response serialization, include prefund_deducted_usd for OVERSEAS (format as string with 4dp) • Verify LOCAL partner response omits or returns null for prefund_deducted_usd | Migration V6_3_004, updated Transaction entity, updated response DTO | • OVERSEAS payment 201 response includes prefund_deducted_usd matching payout_usd_cost to 4dp (e.g. '35.7700') • LOCAL payment 201 response: prefund_deducted_usd is null or field absent • Column nullable in DB: existing transaction rows accept NULL • prefund_deducted_usd in DB matches the ledger entry amount for the same txnRef • Field is not modifiable after commit (no setter called post-DEBITED) | 35 | 6.3-T08, 6.3-T01 | BE | API-05
6.3-T22 | prefunding | 6.3 | 6. Prefunding & Wallet Ledger | Insufficient-balance rejection | 1 | Document INSUFFICIENT_PREFUNDING error in API reference (inline code comments and OpenAPI spec) | The OpenAPI (Swagger) spec for POST /v1/payments and POST /v1/payments/cpm/generate must document the 402 response with error code INSUFFICIENT_PREFUNDING. The error code table in the spec lists: HTTP 402, not retryable, description 'OVERSEAS partner prefunding balance too low. Top up and retry with new key.' Partners must not retry on 402; they must top up and use a new Idempotency-Key. | • In the OpenAPI YAML/annotation for POST /v1/payments, add responses.402 with schema ref to ErrorEnvelope and example error.code='INSUFFICIENT_PREFUNDING' • Repeat for POST /v1/payments/cpm/generate 402 response • In error code constants class (e.g. ErrorCodes.java), add INSUFFICIENT_PREFUNDING = 'INSUFFICIENT_PREFUNDING' if not present • Add JavaDoc comment on InsufficientPrefundingException referencing HTTP 402 and retry guidance • Verify Swagger UI renders both 402 responses correctly | Updated OpenAPI spec (YAML or annotations) for both payment endpoints; ErrorCodes constant | • Swagger UI shows 402 response documented for POST /v1/payments • Swagger UI shows 402 response documented for POST /v1/payments/cpm/generate • Error code value in ErrorCodes.java is exactly 'INSUFFICIENT_PREFUNDING' • OpenAPI example response for 402 includes error.code='INSUFFICIENT_PREFUNDING' and error.details=[] • No other endpoint documents 402 (only prefunding-related endpoints return 402) | 25 | 6.3-T07 | BE | API-05
6.4-T01 | prefunding | 6.4 | 6. Prefunding & Wallet Ledger | Low-balance alerting | 1 | Add low_balance_alert_config table migration | GMEPay+ stores per-partner low-balance alert settings in the table low_balance_alert_config (DAT-03 §6.3). Columns: id BIGINT PK, partner_id BIGINT FK -> partner UNIQUE NOT NULL, threshold_usd DECIMAL(20,4) NOT NULL DEFAULT 10000.00, alert_email VARCHAR(255) NOT NULL, is_active BOOLEAN NOT NULL DEFAULT TRUE, created_at TIMESTAMPTZ, updated_at TIMESTAMPTZ, created_by VARCHAR(120), updated_by VARCHAR(120). Only OVERSEAS partners have alert configs; LOCAL partners (partner_type=LOCAL) must never have a row here. The partner table already exists. | • Write a Flyway/Liquibase migration file creating low_balance_alert_config with all columns above • Add FK constraint partner_id -> partner(id) ON DELETE RESTRICT • Add UNIQUE constraint on partner_id (one config per partner) • Add CHECK constraint: threshold_usd > 0 • Add index on partner_id for fast lookup • Verify migration runs cleanly on a fresh schema and on an existing schema via rollback/reapply | Migration file V6_4_001__create_low_balance_alert_config.sql (or equivalent) | • Migration applies without error on a clean DB and produces table with all 10 columns • UNIQUE constraint on partner_id rejects a second INSERT for the same partner_id • CHECK threshold_usd > 0 rejects INSERT with threshold_usd = 0.0000 • FK constraint rejects INSERT with a non-existent partner_id • Rollback/down migration drops the table cleanly | 30 |  | BE | PRD-07
6.4-T02 | prefunding | 6.4 | 6. Prefunding & Wallet Ledger | Low-balance alerting | 1 | Add low_balance_threshold and alert_email columns to partner migration | The partner table (DAT-03 §4.3) carries denormalized alert fields for convenience: low_balance_threshold_usd DECIMAL(20,4) NULL (NULL for LOCAL partners only) and low_balance_alert_email VARCHAR(255) NULL. These mirror the canonical source in low_balance_alert_config but are used by the Admin API balance-inquiry response (§4.8). The partner table already exists; this is an additive migration only. | • Write a Flyway/Liquibase migration adding low_balance_threshold_usd DECIMAL(20,4) NULL and low_balance_alert_email VARCHAR(255) NULL to the partner table • Add comment/notes on each column per spec • Verify migration is additive (no existing rows broken) • Confirm that LOCAL partner rows can have NULL in both columns | Migration file V6_4_002__add_low_balance_cols_to_partner.sql (or equivalent) | • Migration applies without error; existing partner rows remain intact with NULL in both new columns • A LOCAL partner row with NULL threshold_usd and NULL alert_email is valid (no NOT NULL constraint) • An OVERSEAS partner row can store threshold_usd = 5000.0000 and a valid email address • Rollback removes both columns without data loss to other columns | 20 | 6.4-T01 | BE | PRD-07
6.4-T03 | prefunding | 6.4 | 6. Prefunding & Wallet Ledger | Low-balance alerting | 1 | Define LowBalanceAlertConfig domain entity and repository interface | The service layer needs a typed domain model for low_balance_alert_config. Fields must mirror the DB: id (Long), partnerId (Long), thresholdUsd (BigDecimal), alertEmail (String), isActive (boolean), and audit timestamps. The repository must support: findByPartnerId(Long), save(LowBalanceAlertConfig), and upsert semantics (insert or update if exists for partnerId). Use Java with JPA/Spring Data or the project ORM. OVERSEAS-only invariant is enforced at service level, not here. | • Create LowBalanceAlertConfig entity class with all fields matching DB columns and correct JPA annotations • Create LowBalanceAlertConfigRepository interface extending JpaRepository with findByPartnerId method • Ensure thresholdUsd is mapped as BigDecimal (not double/float) to preserve precision • Add @Column annotations with correct scale (20,4) for thresholdUsd | LowBalanceAlertConfig.java entity + LowBalanceAlertConfigRepository.java interface | • findByPartnerId returns Optional.empty() for unknown partner • Entity maps to table low_balance_alert_config (verify via @Table annotation or naming convention) • thresholdUsd field type is BigDecimal, not float/double • All audit fields (createdAt, updatedAt, createdBy, updatedBy) are present and non-null after save | 30 | 6.4-T01 | BE | PRD-07
6.4-T04 | prefunding | 6.4 | 6. Prefunding & Wallet Ledger | Low-balance alerting | 1 | Create AlertConfigService: create, read, and update alert config for a partner | GME Ops creates and adjusts alert configs per OVERSEAS partner via the Admin portal. The AlertConfigService must: (1) createOrUpdate(partnerId, thresholdUsd, alertEmail) - insert if no config exists, update if one does; validate that partner exists and is OVERSEAS type (partner_type=OVERSEAS); validate thresholdUsd > 0; (2) getByPartnerId(partnerId) - return config or throw NotFoundException; (3) setActive(partnerId, boolean) - toggle is_active. All changes must be audit-logged (actor from security context, before/after snapshot). | • Implement createOrUpdate: load partner, reject if LOCAL, validate thresholdUsd > 0, upsert via repository • Implement getByPartnerId: load or throw NotFoundException • Implement setActive: load, toggle, save, audit-log • Write audit log entry with before/after snapshot for every mutation • Inject AuditLogService (existing) and use for all mutations | AlertConfigService.java with createOrUpdate, getByPartnerId, setActive methods | • createOrUpdate on a LOCAL partner throws InvalidPartnerTypeException (partner_type=LOCAL) • createOrUpdate with thresholdUsd = 0 throws ValidationException • createOrUpdate on new partner inserts row; second call with new threshold updates it (upsert semantics) • setActive(partnerId, false) sets is_active=false; getByPartnerId reflects new value • Every mutation generates an audit log entry with actor, timestamp, before-value, and after-value | 45 | 6.4-T03 | BE | PRD-07
6.4-T05 | prefunding | 6.4 | 6. Prefunding & Wallet Ledger | Low-balance alerting | 1 | Admin REST endpoint: GET and PUT /admin/v1/partners/{id}/alert-config | GME Ops manages alert configs via the Admin API. Two endpoints are required: GET /admin/v1/partners/{id}/alert-config returns the current config (200) or 404 if none. PUT /admin/v1/partners/{id}/alert-config with body {threshold_usd: number, alert_email: string, is_active: boolean} creates or replaces the config and returns the saved config (200). Both require ROLE_OPS or ROLE_SUPER_ADMIN. Return 403 if caller tries to set config on a LOCAL partner. Response body: {partner_id, threshold_usd, alert_email, is_active, updated_at, updated_by}. | • Add GET handler calling AlertConfigService.getByPartnerId; map to response DTO • Add PUT handler validating request body (threshold_usd > 0, valid email format, is_active boolean), calling AlertConfigService.createOrUpdate • Add @PreAuthorize or equivalent RBAC check for ROLE_OPS or ROLE_SUPER_ADMIN • Return 404 for missing partner or missing config on GET; 403 for LOCAL partner on PUT • Add input validation annotations on request DTO (e.g. @Positive for threshold_usd, @Email for alert_email) | AlertConfigController.java with GET and PUT handlers and request/response DTOs | • GET /admin/v1/partners/{unknown_id}/alert-config returns 404 • PUT with threshold_usd=-1 returns 400 with validation error • PUT for a LOCAL partner returns 403 • GET after a successful PUT returns exactly the values just written • Request without OPS/SUPER_ADMIN role returns 401 or 403 | 45 | 6.4-T04 | BE | PRD-07
6.4-T06 | prefunding | 6.4 | 6. Prefunding & Wallet Ledger | Low-balance alerting | 1 | Implement low-balance alert evaluation in PrefundingLedgerService post-deduction | After every successful atomic deduction from prefunding_account (SELECT FOR UPDATE pattern), the PrefundingLedgerService must evaluate whether the new balance triggers an alert. Rules (spec §9.5): (1) LOW alert: new balance < threshold_usd AND is_active=true for that partner's low_balance_alert_config; (2) CRITICAL/ZERO alert: new balance <= 0 (suspend partner). The alert evaluation must happen AFTER the deduction transaction commits, not inside the DB transaction. Use an async event / message: publish a prefunding.low_balance domain event with fields: partner_id, new_balance_usd, threshold_usd, alert_email, alert_type (LOW or ZERO), triggered_at. | • After committing deduction, load low_balance_alert_config for partner (cache or DB lookup) • If is_active=true and new_balance < threshold_usd, publish prefunding.low_balance event with alert_type=LOW • If new_balance <= 0, publish prefunding.low_balance event with alert_type=ZERO • Publish event via application event bus or message queue (do NOT call email directly from this layer) • Ensure alert evaluation failure never rolls back or blocks the payment transaction (wrap in try/catch; log errors) | Alert evaluation logic in PrefundingLedgerService.deduct() with event publishing | • Deduction leaving balance=8000 for threshold=10000 publishes LOW event with correct partner_id and new_balance_usd=8000 • Deduction leaving balance=0 publishes ZERO event (not LOW) • Deduction leaving balance=15000 for threshold=10000 publishes no alert event • Alert evaluation exception (e.g. config not found) does NOT roll back the payment transaction • Event payload contains alert_type, partner_id, new_balance_usd, threshold_usd, alert_email, triggered_at | 45 | 6.4-T04 | BE | PRD-07
6.4-T07 | prefunding | 6.4 | 6. Prefunding & Wallet Ledger | Low-balance alerting | 1 | Implement LowBalanceAlertHandler: consume prefunding.low_balance event and send email | The Notification Service (or alert handler bean) consumes prefunding.low_balance events and sends email. Email content per spec §9.5 and §9.2: For LOW alert - subject 'GMEPay+ Low Prefunding Balance - [Partner Name]'; body includes partner name, current balance (USD X,XXX.XX), configured threshold (USD X,XXX.XX), suggested top-up amount (threshold - current balance), GME account team contact. For ZERO alert - subject 'URGENT: GMEPay+ Prefunding Balance Zero - [Partner Name]'; body states all overseas payments are suspended and includes same balance details. Recipient = alert_email from event payload. Email service: SMTP relay / SES abstracted behind EmailService.send(to, subject, body). | • Create LowBalanceAlertHandler bean subscribing to prefunding.low_balance events • For LOW type: construct email subject and body with all required fields; compute suggestedTopUp = threshold_usd - new_balance_usd • For ZERO type: construct urgent email with suspension notice • Call EmailService.send(alertEmail, subject, body) • Log the alert dispatch (partner_id, alert_type, recipient, dispatched_at) to structured log • Handle EmailService exceptions with retry or dead-letter; do not lose the event silently | LowBalanceAlertHandler.java (or equivalent) consuming prefunding.low_balance events | • LOW event for partner SendMN with balance=8000 threshold=10000 sends email to configured address with subject containing partner name and suggested top-up of USD 2000 • ZERO event sends email with URGENT subject and mentions payments suspended • Email body includes current balance formatted as USD 8,000.00 (2 decimal places, USD prefix) • EmailService failure is caught and logged; handler does not propagate exception to event bus (avoids requeue loop unless retry is intended) • No email is sent if alert_email is null or empty (guard check) | 45 | 6.4-T06 | BE | PRD-07
6.4-T08 | prefunding | 6.4 | 6. Prefunding & Wallet Ledger | Low-balance alerting | 1 | Implement zero-balance partner suspension in PrefundingLedgerService | Per spec §9.5 and §7.5.2: when an OVERSEAS partner balance reaches 0 or below after a deduction, all new payments for that partner must be suspended immediately. Suspension is implemented by setting partner.status = SUSPENDED (or a separate is_payment_suspended flag). The payment path already checks partner.is_active or status before proceeding. Suspension must be atomic and must not affect in-flight transactions that already have a committed deduction. The suspension is lifted manually by Ops after a top-up is recorded (via partner status update, WBS 5.x). | • In PrefundingLedgerService, after ZERO event detection (new_balance <= 0), call PartnerService.suspendForPrefunding(partnerId) with reason ZERO_BALANCE • PartnerService.suspendForPrefunding sets partner.status = SUSPENDED and audit-logs the change with reason=ZERO_BALANCE and actor=SYSTEM • Ensure the payment validation path (before deduction) rejects new payments when partner.status = SUSPENDED with error code PARTNER_SUSPENDED • Write a unit test confirming suspension does not affect transactions that have already committed their deduction • Ensure suspension is idempotent (second call when already SUSPENDED is a no-op) | suspendForPrefunding method in PartnerService + suspension check in payment validation path | • After balance reaches 0, partner.status becomes SUSPENDED in the DB • A new payment attempt for a SUSPENDED partner returns error PARTNER_SUSPENDED before any deduction • Suspending an already-SUSPENDED partner is a no-op (no duplicate audit log entry) • In-flight transactions whose deduction committed before suspension proceed to scheme call normally • Audit log entry for suspension contains reason=ZERO_BALANCE, actor=SYSTEM, and timestamp | 45 | 6.4-T06 | BE | PRD-07
6.4-T09 | prefunding | 6.4 | 6. Prefunding & Wallet Ledger | Low-balance alerting | 1 | Admin portal in-portal banner for zero-balance partner | Per spec §9.5: when a partner balance reaches USD 0, Ops must be notified in-portal via a dashboard banner. The Admin portal (React/frontend) must display a sticky banner or alert widget on the Prefunding Monitor dashboard when any OVERSEAS partner has balance = 0 (or SUSPENDED due to ZERO_BALANCE). The backend provides this via a new field is_below_zero (boolean) in the existing GET /admin/v1/prefunding/summary endpoint response (or a new /alerts endpoint). | • Add is_below_zero boolean field to the prefunding summary response DTO (true when balance <= 0) • Update GET /admin/v1/prefunding/summary query to include the new field per partner • In the Admin portal prefunding dashboard component, render a red dismissable banner if any partner has is_below_zero=true: 'ALERT: [Partner Name] prefunding balance is zero. Payments suspended.' • Banner must be visible above the partner balance table • Banner clears automatically on next data refresh if balance > 0 | Backend DTO change + frontend banner component on Prefunding Monitor dashboard | • Partner with balance=0 causes is_below_zero=true in summary API response • Partner with balance=0.01 causes is_below_zero=false • Admin portal renders red banner for any partner where is_below_zero=true • Banner is not rendered when all partners have balance > 0 • Banner text includes the partner name (e.g. T-Bank) and the word 'suspended' | 45 | 6.4-T08 | BE | PRD-07
6.4-T10 | prefunding | 6.4 | 6. Prefunding & Wallet Ledger | Low-balance alerting | 1 | Admin portal: low-balance status badge on prefunding dashboard | The Admin portal Prefunding Monitor dashboard (spec wireframe §4.1 / §4.7) shows a status badge per partner: green OK when balance >= threshold, amber WARNING / LOW when balance < threshold, red CRITICAL when balance < USD 2000 (default critical threshold from spec §7.5.2). The badge is derived from the existing GET /admin/v1/prefunding/summary response. The response already includes balance_usd and low_balance_threshold_usd per partner; add a balance_status field (OK / LOW / CRITICAL / ZERO) computed server-side. | • Add balance_status computed field to prefunding summary response: ZERO if balance<=0, CRITICAL if balance < 2000, LOW if balance < threshold_usd, else OK • Update the query/service that builds the summary response to compute balance_status • In the frontend partner balance table, render a colour-coded badge using balance_status: green=OK, amber=LOW, red=CRITICAL or ZERO • Confirm the wireframe layout: partner name, balance, threshold, badge columns • Write a snapshot/unit test for the frontend badge component covering all four states | balance_status field in prefunding summary API + coloured badge component in Admin portal | • balance=45200, threshold=10000 -> balance_status=OK • balance=8400, threshold=10000 -> balance_status=LOW • balance=1500, threshold=10000 -> balance_status=CRITICAL • balance=0 -> balance_status=ZERO • Frontend badge for LOW renders amber colour and text LOW (matches wireframe spec) | 40 | 6.4-T09 | BE | PRD-07
6.4-T11 | prefunding | 6.4 | 6. Prefunding & Wallet Ledger | Low-balance alerting | 1 | Partner API balance endpoint: expose is_below_threshold flag | The Partner API GET /v1/balance endpoint (API-05 §4.8) returns balance data to OVERSEAS partners. Per spec §4.8 response fields, the response must include: partner_id, balance_usd (string decimal), low_balance_threshold_usd (string decimal), is_below_threshold (boolean: true if balance_usd < low_balance_threshold_usd), as_of (ISO-8601 UTC). LOCAL partners calling this endpoint must receive HTTP 403. The response must reflect the live balance at query time (not a cached value older than the last deduction). | • In PartnerBalanceController GET /v1/balance, load the partner's prefunding_account row and low_balance_alert_config row • Compute is_below_threshold = balance < low_balance_threshold_usd (use BigDecimal.compareTo, not ==) • Serialize balance_usd and low_balance_threshold_usd as strings with 2 decimal places (e.g. '8400.00') • Return 403 for LOCAL partner callers • Include as_of field as current UTC timestamp | Updated GET /v1/balance handler returning is_below_threshold and low_balance_threshold_usd fields | • OVERSEAS partner with balance=8400 threshold=10000 gets is_below_threshold=true • OVERSEAS partner with balance=45200 threshold=10000 gets is_below_threshold=false • LOCAL partner gets HTTP 403 • balance_usd serialized as string '8400.00' (not numeric 8400) • as_of timestamp is UTC ISO-8601 format e.g. 2026-06-05T09:15:00Z | 35 | 6.4-T03 | BE | PRD-07
6.4-T12 | prefunding | 6.4 | 6. Prefunding & Wallet Ledger | Low-balance alerting | 1 | Validation: prevent setting alert config on LOCAL partner (service + API layer) | Alert configs are OVERSEAS-only. The system must reject any attempt to create or update a low_balance_alert_config for a partner with partner_type=LOCAL (e.g. GME Remit). This guard must exist in AlertConfigService.createOrUpdate (service layer) AND in the Admin API PUT /admin/v1/partners/{id}/alert-config controller (API layer). Error response: HTTP 422 with error_code INVALID_PARTNER_TYPE and message 'Low-balance alert config is only applicable to OVERSEAS partners'. | • In AlertConfigService.createOrUpdate, load partner and check partner_type; throw InvalidPartnerTypeException if LOCAL • In the PUT controller handler, catch InvalidPartnerTypeException and return HTTP 422 with structured error body {error_code: INVALID_PARTNER_TYPE, message: ...} • Add an integration test calling PUT for a LOCAL partner and asserting 422 response with correct error_code • Confirm that existing LOCAL partner rows in the partner table cannot have a low_balance_alert_config row (add DB-level check or document service-only enforcement) | InvalidPartnerTypeException + 422 handling in controller + integration test | • PUT /admin/v1/partners/{LOCAL_partner_id}/alert-config returns HTTP 422 with error_code=INVALID_PARTNER_TYPE • AlertConfigService.createOrUpdate for a LOCAL partner throws InvalidPartnerTypeException before any DB write • No low_balance_alert_config row is created for a LOCAL partner after the rejected call • GET /admin/v1/partners/{LOCAL_partner_id}/alert-config returns 404 (not 422) since no config will exist • Error message in response body contains the word 'OVERSEAS' | 30 | 6.4-T05 | BE | PRD-07
6.4-T13 | prefunding | 6.4 | 6. Prefunding & Wallet Ledger | Low-balance alerting | 1 | Validation: threshold_usd range and email format rules | The threshold_usd field must satisfy: greater than 0.00, maximum 9,999,999.9999 (DECIMAL(20,4) but practically bounded), and must be a positive number with up to 4 decimal places. The alert_email must be a valid RFC-5322 email address (validated via @Email annotation or regex). Multiple recipients are stored comma-separated in alert_email per spec §9.5 and portal spec §9.1 (comma-separated emails; minimum 1). The service must parse and validate each individual address when multiple are provided. | • Update LowBalanceAlertConfigRequest DTO: add @NotNull @Positive @DecimalMax on threshold_usd; add @NotBlank on alert_email • In AlertConfigService.createOrUpdate, split alert_email on comma, trim each part, and validate each as a valid email; throw ValidationException with list of invalid addresses if any fail • Add test cases for threshold=0 (reject), threshold=0.0001 (accept), alert_email='a@b.com,c@d.com' (accept), alert_email='notanemail' (reject) • Ensure error response lists which email address(es) failed validation | Updated request DTO validation + multi-email parser in AlertConfigService + unit tests | • threshold_usd=0 returns 400 with field error on threshold_usd • threshold_usd=0.0001 is accepted • alert_email='ops@gme.com,finance@gme.com' is accepted and stored as-is • alert_email='ops@gme.com,notanemail' returns 400 listing 'notanemail' as invalid • alert_email='' (empty string) returns 400 with error message | 35 | 6.4-T05 | BE | PRD-07
6.4-T14 | prefunding | 6.4 | 6. Prefunding & Wallet Ledger | Low-balance alerting | 1 | Audit logging for alert config mutations (create, update, deactivate) | Per spec §11.1 and the canonical audit rule: all config changes must log actor, timestamp, previous value, and new value, and apply only to new transactions. The audit_log table (id, entity_type, entity_id, action, actor, before_snapshot JSON, after_snapshot JSON, created_at) must receive an entry for every createOrUpdate and setActive call on low_balance_alert_config. before_snapshot is null for the first INSERT. | • Ensure AlertConfigService.createOrUpdate writes an audit_log row: entity_type='low_balance_alert_config', entity_id=config.id, action=CREATE or UPDATE, actor from SecurityContext, before_snapshot=null or prior JSON, after_snapshot=new values as JSON • Ensure AlertConfigService.setActive writes audit_log with action=DEACTIVATE or REACTIVATE and before/after is_active values • Confirm audit_log rows are written in the same DB transaction as the config change • Write a unit test that creates, updates, and deactivates a config and asserts 3 audit_log rows with correct action values | Audit log entries emitted by AlertConfigService for all mutations | • First createOrUpdate for a partner produces one audit_log row with action=CREATE and before_snapshot=null • Second createOrUpdate (update) produces audit_log row with action=UPDATE, before_snapshot containing old threshold, after_snapshot containing new threshold • setActive(false) produces audit_log row with action=DEACTIVATE and before is_active=true • All audit_log rows carry actor matching the authenticated user's identity (not null/anonymous) • Rolling back the config change also rolls back the audit_log row (same transaction) | 40 | 6.4-T04 | BE | PRD-07
6.4-T15 | prefunding | 6.4 | 6. Prefunding & Wallet Ledger | Low-balance alerting | 1 | Top-up auto-clear: re-evaluate alert state after prefunding top-up | Per spec §8.5 (runbook): when a top-up credits a partner's prefunding balance and the new balance exceeds the threshold, the low-balance condition auto-clears. The system must: after a successful TOPUP ledger entry, evaluate the new balance against threshold; if balance >= threshold and partner was SUSPENDED due to ZERO_BALANCE, Ops must manually re-activate (not auto); however the is_below_threshold signal on the balance API and the dashboard badge must reflect the updated balance immediately. No automatic unsuspend. Optionally send a confirmation email to alert_email confirming the top-up amount and new balance (spec §9.2 'Balance confirmed top-up' email). | • After recording a TOPUP ledger entry and updating prefunding_account.balance, reload the alert config for the partner • If new balance >= threshold_usd, do NOT publish a low_balance event (no alert) • If partner is SUSPENDED with reason ZERO_BALANCE, log a warning that manual re-activation by Ops is required but do NOT auto-unsuspend • Send top-up confirmation email to alert_email: subject 'GMEPay+ Prefunding Top-Up Confirmed - [Partner Name]', body includes amount credited, new balance, and threshold • Emit a structured log entry: partner_id, top_up_amount_usd, new_balance_usd, previous_balance_usd | Post-top-up alert evaluation logic in PrefundingLedgerService.recordTopUp + confirmation email | • Top-up that brings balance from 8000 to 20000 (threshold=10000): no low_balance event published; confirmation email sent with new balance USD 20,000.00 • Top-up that brings balance from 0 to 5000 (threshold=10000): no auto-unsuspend; warning log emitted; LOW alert still fires on next deduction if balance stays below threshold • Top-up confirmation email subject contains partner name and 'Top-Up Confirmed' • Confirmation email body shows old balance, amount credited, and new balance • If alert_email is empty/null, skip email silently (no exception thrown) | 40 | 6.4-T07 | BE | PRD-07
6.4-T16 | prefunding | 6.4 | 6. Prefunding & Wallet Ledger | Low-balance alerting | 1 | Unit tests: alert evaluation logic in PrefundingLedgerService | The alert evaluation logic in PrefundingLedgerService.deduct() (6.4-T06) is business-critical. This ticket writes comprehensive unit tests using mocks for AlertConfigRepository and ApplicationEventPublisher. Test the decision table: new_balance vs threshold vs is_active vs alert_type. Key cases to cover: (1) balance crosses threshold from above, (2) balance already below threshold before deduction (no re-alert), (3) balance exactly at threshold (not below), (4) is_active=false config (no alert), (5) ZERO balance, (6) no config row exists. | • Create PrefundingLedgerServiceAlertTest class • Mock AlertConfigRepository to return various configs • Mock ApplicationEventPublisher and capture published events • Test case 1: before=12000 deduct=5000 threshold=10000 -> LOW event published • Test case 2: before=8000 deduct=1000 threshold=10000 -> LOW event published (was already below) • Test case 3: before=11000 deduct=1000 threshold=10000 -> balance=10000, NOT below threshold, no event • Test case 4: before=12000 deduct=5000 threshold=10000 is_active=false -> no event • Test case 5: before=500 deduct=500 threshold=10000 -> ZERO event (balance=0) • Test case 6: no config row -> no event, no exception | PrefundingLedgerServiceAlertTest.java with at least 7 test methods | • Test case 1 passes: LOW event published with new_balance_usd=7000 • Test case 3 passes: balance exactly at threshold=10000 does NOT publish any event (strictly less-than check) • Test case 4 passes: is_active=false suppresses event • Test case 5 passes: ZERO event published not LOW event when balance=0 • Test case 6 passes: missing config row results in no event and no NullPointerException • All 7+ test methods green with no mocking framework warnings | 50 | 6.4-T06 | BE | PRD-07
6.4-T17 | prefunding | 6.4 | 6. Prefunding & Wallet Ledger | Low-balance alerting | 1 | Unit tests: LowBalanceAlertHandler email content and routing | The LowBalanceAlertHandler (6.4-T07) must send correctly formatted emails. Unit tests mock EmailService.send and verify the subject, body content, and recipient for both LOW and ZERO alert types. Use partner name 'T-Bank', balance USD 1,500.00, threshold USD 10,000.00 for LOW test; use balance USD 0.00 for ZERO test. | • Create LowBalanceAlertHandlerTest class • Build a LOW PrefundingLowBalanceEvent: partner_id=2, partner_name='T-Bank', new_balance_usd=1500.00, threshold_usd=10000.00, alert_email='ops@tbank.com', alert_type=LOW • Assert EmailService.send called with recipient='ops@tbank.com', subject containing 'T-Bank', body containing 'USD 1,500.00', 'USD 10,000.00', and suggested top-up 'USD 8,500.00' • Build a ZERO event: new_balance_usd=0.00, alert_type=ZERO • Assert email subject contains 'URGENT' and body contains 'suspended' • Test that empty alert_email skips send call entirely | LowBalanceAlertHandlerTest.java with at least 4 test methods | • LOW test: EmailService.send called exactly once with ops@tbank.com as recipient • LOW test: email body contains suggested top-up USD 8,500.00 (10000.00 - 1500.00) • ZERO test: email subject contains 'URGENT' and body contains 'suspended' • Empty alert_email test: EmailService.send NOT called • Body contains partner name 'T-Bank' in all non-empty-email cases | 40 | 6.4-T07 | BE | PRD-07
6.4-T18 | prefunding | 6.4 | 6. Prefunding & Wallet Ledger | Low-balance alerting | 1 | Unit tests: AlertConfigService create, update, validation, and audit | AlertConfigService (6.4-T04) has several business rules that need unit test coverage: LOCAL partner rejection, threshold > 0, upsert semantics, audit logging. Mock PartnerRepository, LowBalanceAlertConfigRepository, and AuditLogService. Test vectors: partner_type=LOCAL -> exception; threshold_usd=0 -> exception; first create -> INSERT + audit CREATE; second call -> UPDATE + audit UPDATE; setActive(false) -> audit DEACTIVATE. | • Create AlertConfigServiceTest class • Test createOrUpdate with LOCAL partner -> expect InvalidPartnerTypeException • Test createOrUpdate with threshold_usd=0 -> expect ValidationException • Test createOrUpdate with new OVERSEAS partner -> verify repository.save called, AuditLogService.log called with action=CREATE • Test second createOrUpdate (existing config) -> verify repository.save called with updated threshold, AuditLogService.log called with action=UPDATE • Test setActive(false) -> verify is_active=false saved, AuditLogService.log called with action=DEACTIVATE | AlertConfigServiceTest.java with at least 5 test methods | • LOCAL partner test throws InvalidPartnerTypeException (not a generic RuntimeException) • threshold_usd=0 test throws ValidationException with message referencing threshold • First create test: AuditLogService.log called with action=CREATE and before_snapshot=null • Update test: AuditLogService.log called with action=UPDATE, before_snapshot contains old threshold • setActive test: saved entity has is_active=false; audit log action=DEACTIVATE | 45 | 6.4-T04, 6.4-T14 | BE | PRD-07
6.4-T19 | prefunding | 6.4 | 6. Prefunding & Wallet Ledger | Low-balance alerting | 1 | Integration test: full low-balance alert flow (deduction -> event -> email) | An end-to-end integration test verifying the full pipeline from deduction to email dispatch. Uses an in-memory or test DB with a seeded OVERSEAS partner (partner_id=99, partner_type=OVERSEAS) with prefunding_account.balance=12000 and low_balance_alert_config.threshold_usd=10000 is_active=true alert_email='test@example.com'. Performs a deduction of 5000 USD (leaving balance=7000) and asserts: (a) balance updated, (b) LOW event published, (c) email sent to test@example.com with correct content. Uses a mock EmailService (captured calls) and a real ApplicationEventPublisher (Spring test context). | • Seed DB with partner_id=99 OVERSEAS, prefunding_account balance=12000, alert_config threshold=10000 alert_email=test@example.com is_active=true • Call PrefundingLedgerService.deduct(partnerId=99, amount=5000) inside a test transaction (committed) • Assert prefunding_account.balance=7000 in DB after commit • Assert LowBalanceAlertHandler received one LOW event with new_balance_usd=7000 • Assert mock EmailService captured one send call to test@example.com with subject containing 'T-Bank' or partner name • Assert no exception propagated to caller | PrefundingAlertIntegrationTest.java using Spring Boot test slice or full context with mock EmailService | • DB balance=7000 after deduction • LowBalanceAlertHandler.handle() called exactly once • EmailService.send called with recipient=test@example.com • Email subject contains partner name • No exception thrown from deduct() call; return value contains new balance 7000 | 55 | 6.4-T07, 6.4-T16, 6.4-T17 | BE | PRD-07
6.4-T20 | prefunding | 6.4 | 6. Prefunding & Wallet Ledger | Low-balance alerting | 1 | Integration test: zero-balance triggers suspension and urgent email | Verifying the zero-balance path: OVERSEAS partner_id=100 with balance=500 and threshold=10000. Deduction of 500 USD leaves balance=0. Expected: ZERO event published, partner status set to SUSPENDED, urgent email sent. Uses same test setup as 6.4-T19 but with balance=500 and deduction=500. | • Seed DB with partner_id=100 OVERSEAS, balance=500, alert_config threshold=10000 is_active=true • Call PrefundingLedgerService.deduct(partnerId=100, amount=500) • Assert prefunding_account.balance=0 • Assert partner.status=SUSPENDED in DB • Assert ZERO event was published (not LOW) • Assert email sent with URGENT in subject and 'suspended' in body | Zero-balance integration test in PrefundingAlertIntegrationTest.java (additional test method) | • DB balance=0 after deduction • partner.status=SUSPENDED after deduction • ZERO alert event published (not LOW) • Urgent email sent with URGENT in subject • Subsequent payment attempt for partner_id=100 returns PARTNER_SUSPENDED error (call payment validation after deduction) | 45 | 6.4-T08, 6.4-T19 | BE | PRD-07
6.4-T21 | prefunding | 6.4 | 6. Prefunding & Wallet Ledger | Low-balance alerting | 1 | Admin API endpoint: GET /admin/v1/prefunding/summary with balance_status field | The Admin portal Prefunding Monitor (spec §4.1 and §7.4) polls GET /admin/v1/prefunding/summary to display all OVERSEAS partners with their balance and status. The response must be an array of objects: {partner_id, partner_name, balance_usd (string), low_balance_threshold_usd (string), balance_status (OK¦LOW¦CRITICAL¦ZERO), is_below_zero (boolean)}. balance_status rules: ZERO if balance<=0; CRITICAL if 0 < balance < 2000; LOW if 2000 <= balance < threshold_usd; OK if balance >= threshold_usd. Requires ROLE_OPS or ROLE_SUPER_ADMIN. Only OVERSEAS partners are included. | • Create or update PrefundingMonitorController with GET /admin/v1/prefunding/summary • Query joins prefunding_account, partner, and low_balance_alert_config for all OVERSEAS ACTIVE and SUSPENDED partners • Compute balance_status per row using the four-tier rule above • Return response array with all specified fields • Add @PreAuthorize for ROLE_OPS or ROLE_SUPER_ADMIN | PrefundingMonitorController.java with GET /admin/v1/prefunding/summary handler + response DTO | • Response includes only OVERSEAS partners (LOCAL partner GME Remit absent) • Partner with balance=45200 threshold=10000 -> balance_status=OK, is_below_zero=false • Partner with balance=8400 threshold=10000 -> balance_status=LOW, is_below_zero=false • Partner with balance=1500 threshold=10000 -> balance_status=CRITICAL, is_below_zero=false • Partner with balance=0 -> balance_status=ZERO, is_below_zero=true | 45 | 6.4-T10 | BE | PRD-07
6.4-T22 | prefunding | 6.4 | 6. Prefunding & Wallet Ledger | Low-balance alerting | 1 | Admin API endpoint: PATCH /admin/v1/partners/{id}/alert-config/status to toggle is_active | GME Ops must be able to temporarily disable low-balance alerts for a partner (e.g. during a known maintenance window) without deleting the config. Endpoint: PATCH /admin/v1/partners/{id}/alert-config/status with body {is_active: boolean}. Returns 200 with updated config or 404 if no config exists. Requires ROLE_OPS or ROLE_SUPER_ADMIN. All changes are audit-logged via AlertConfigService.setActive. | • Add PATCH handler in AlertConfigController for /admin/v1/partners/{id}/alert-config/status • Validate request body: is_active must be a boolean (required field) • Call AlertConfigService.setActive(partnerId, isActive) • Return 200 with full updated config DTO on success; 404 if no config for partner • Add @PreAuthorize for ROLE_OPS | PATCH /admin/v1/partners/{id}/alert-config/status handler in AlertConfigController.java | • PATCH with {is_active: false} sets config to inactive; subsequent deduction does not fire email • PATCH with {is_active: true} re-enables alerts • PATCH for unknown partner returns 404 • PATCH without ROLE_OPS returns 401/403 • After PATCH, GET /admin/v1/partners/{id}/alert-config reflects updated is_active value | 30 | 6.4-T05 | BE | PRD-07
6.4-T23 | prefunding | 6.4 | 6. Prefunding & Wallet Ledger | Low-balance alerting | 1 | Structured logging for all alert events with correlation fields | Per spec §11.2: all services must emit structured JSON logs with correlation fields txn_ref, partner_id, scheme_id, request_id. For the alerting subsystem specifically, every alert event (LOW, ZERO, email sent, email failed, suspension triggered) must emit a structured log entry at INFO or WARN level. Log fields: event_type (LOW_BALANCE_ALERT / ZERO_BALANCE_ALERT / ALERT_EMAIL_SENT / ALERT_EMAIL_FAILED / PARTNER_SUSPENDED), partner_id, balance_usd, threshold_usd, alert_email (masked: show first 3 chars and domain only, e.g. ops***@gme.com), txn_ref (if triggered by a payment), timestamp. | • In PrefundingLedgerService, emit structured log entry after publishing LOW or ZERO event • In LowBalanceAlertHandler, emit ALERT_EMAIL_SENT log after successful EmailService.send call • In LowBalanceAlertHandler, emit ALERT_EMAIL_FAILED log on exception from EmailService.send • In PartnerService.suspendForPrefunding, emit PARTNER_SUSPENDED log entry • Mask alert_email in all log entries: replace local-part characters 4+ with *** keeping first 3 chars and full domain | Structured log statements in PrefundingLedgerService, LowBalanceAlertHandler, PartnerService matching the field spec above | • LOW_BALANCE_ALERT log entry contains partner_id and balance_usd after a deduction crossing threshold • ALERT_EMAIL_SENT log entry contains masked alert_email (e.g. ops***@tbank.com not ops@tbank.com) • PARTNER_SUSPENDED log entry contains reason=ZERO_BALANCE • ALERT_EMAIL_FAILED log is emitted at WARN level when EmailService throws an exception • No raw/unmasked email addresses appear in any log line for the alerting subsystem | 35 | 6.4-T07, 6.4-T08 | BE | PRD-07
6.4-T24 | prefunding | 6.4 | 6. Prefunding & Wallet Ledger | Low-balance alerting | 1 | Admin portal: Adjust Threshold UI in Prefunding screen | The Admin portal Prefunding screen (spec wireframe §4.7) has an [Adjust Threshold] button that opens a modal. The modal allows Ops to change threshold_usd and alert_email for a partner. On submit, it calls PUT /admin/v1/partners/{id}/alert-config. Fields: Threshold (USD, required, positive number input), Alert Email (text, required, multi-address comma-separated). Display current values pre-populated. Show success toast on save, show validation error inline (e.g. invalid email, zero threshold). Requires ROLE_OPS session. | • Add AdjustThresholdModal component to the Prefunding screen • Pre-populate threshold_usd and alert_email fields from GET /admin/v1/partners/{id}/alert-config response • On submit, call PUT /admin/v1/partners/{id}/alert-config with updated values • Display inline validation error if threshold <= 0 or email invalid before API call • Display success toast 'Alert config updated' and close modal on 200 response • Display API error message on 422/400 responses | AdjustThresholdModal React component integrated into the Prefunding screen | • Modal pre-populates current threshold (e.g. USD 10,000.00) and email on open • Submit with threshold=0 shows inline error before API call (client-side validation) • Submit with valid values calls PUT endpoint and closes modal on success • API 422 INVALID_PARTNER_TYPE response shows error in modal (not crash) • Adjusted threshold is reflected immediately in the Prefunding screen threshold field after modal closes | 50 | 6.4-T05 | BE | PRD-07
6.4-T25 | prefunding | 6.4 | 6. Prefunding & Wallet Ledger | Low-balance alerting | 1 | Docs: OpenAPI spec for alert-config endpoints (GET, PUT, PATCH) | The three alert-config Admin API endpoints added in this work package need OpenAPI 3.0 spec entries so the auto-generated API docs and contract tests are complete. Endpoints: GET /admin/v1/partners/{id}/alert-config, PUT /admin/v1/partners/{id}/alert-config, PATCH /admin/v1/partners/{id}/alert-config/status. Each needs paths, request body schemas, response schemas, and error codes (400, 403, 404, 422). | • In the admin-api.yaml OpenAPI spec file, add path /admin/v1/partners/{id}/alert-config with GET and PUT operations • Add path /admin/v1/partners/{id}/alert-config/status with PATCH operation • Define LowBalanceAlertConfigRequest schema (threshold_usd number, alert_email string, is_active boolean) • Define LowBalanceAlertConfigResponse schema (partner_id, threshold_usd, alert_email, is_active, updated_at, updated_by) • Add error response refs for 400, 403, 404, 422 using existing error schema components • Validate spec with swagger-parser or equivalent - zero errors | Updated admin-api.yaml with three new operation entries and two new schema components | • swagger-parser validates admin-api.yaml with zero errors • GET /admin/v1/partners/{id}/alert-config operation has 200 and 404 response codes defined • PUT operation documents 400 (validation), 403 (INVALID_PARTNER_TYPE), and 422 response codes • LowBalanceAlertConfigRequest schema marks threshold_usd as type: number, format: decimal, minimum: 0 (exclusive) • LowBalanceAlertConfigResponse schema includes all 7 fields listed above | 35 | 6.4-T05, 6.4-T22 | BE | PRD-07
6.5-T01 | prefunding | 6.5 | 6. Prefunding & Wallet Ledger | Ledger reconciliation & statements | 2 | Add DB migration: reconciliation_run table | GMEPay+ needs a table to record every daily reconciliation execution for audit and idempotency. Fields: id BIGINT PK, run_date DATE NOT NULL, scheme_id BIGINT FK qr_scheme, run_type VARCHAR(30) CHECK IN ('POOL_IDENTITY','PREFUNDING_LEDGER','SETTLEMENT_AGGREGATE','REVENUE_MONTHLY'), status VARCHAR(20) CHECK IN ('RUNNING','COMPLETED','FAILED','PARTIAL'), started_at TIMESTAMPTZ NOT NULL DEFAULT NOW(), completed_at TIMESTAMPTZ, items_checked INT DEFAULT 0, items_matched INT DEFAULT 0, items_discrepant INT DEFAULT 0, error_detail TEXT, created_by VARCHAR(120). UNIQUE(run_date, scheme_id, run_type). Flyway migration V6_5_001. | • Create Flyway migration file V6_5_001__add_reconciliation_run.sql • Define table reconciliation_run with all columns, constraints, and CHECK values listed in context • Add index on (run_date, run_type) for daily query performance • Add index on (status) for polling incomplete runs • Run migration against local PostgreSQL on port 5433; verify with \d reconciliation_run | Flyway migration file V6_5_001__add_reconciliation_run.sql | • Table exists with correct columns and types after migration • UNIQUE constraint on (run_date, scheme_id, run_type) rejects duplicate insert • CHECK constraint on status rejects value 'UNKNOWN' • CHECK constraint on run_type rejects value 'INVALID' • Index on (run_date, run_type) present in pg_indexes | 25 |  | BE | RATE-04
6.5-T02 | prefunding | 6.5 | 6. Prefunding & Wallet Ledger | Ledger reconciliation & statements | 2 | Add DB migration: recon_discrepancy table | Each reconciliation run may produce discrepancy rows needing human review. Table recon_discrepancy: id BIGINT PK, run_id BIGINT FK reconciliation_run NOT NULL, discrepancy_type VARCHAR(40) CHECK IN ('POOL_IDENTITY_BREACH','PREFUNDING_LEDGER_MISMATCH','SETTLEMENT_COUNT_MISMATCH','SETTLEMENT_AMOUNT_MISMATCH','UNCERTAIN_UNRESOLVED','REVENUE_MISMATCH'), txn_ref VARCHAR(64), scheme_ref VARCHAR(128), expected_value DECIMAL(20,8), actual_value DECIMAL(20,8), delta DECIMAL(20,8), ccy CHAR(3), resolution_status VARCHAR(20) CHECK IN ('UNRESOLVED','RESOLVED','ESCALATED') DEFAULT 'UNRESOLVED', resolved_by VARCHAR(120), resolved_at TIMESTAMPTZ, resolution_note TEXT, created_at TIMESTAMPTZ NOT NULL DEFAULT NOW(), updated_at TIMESTAMPTZ NOT NULL DEFAULT NOW(). Index on (run_id), (resolution_status). Flyway V6_5_002. | • Create Flyway migration V6_5_002__add_recon_discrepancy.sql • Define table with all columns, FKs, CHECK constraints from context • Add indexes on run_id and resolution_status • Run migration and verify schema • Confirm ON DELETE RESTRICT on run_id FK prevents orphan discrepancy rows | Flyway migration file V6_5_002__add_recon_discrepancy.sql | • Table exists with correct structure after migration • FK run_id → reconciliation_run rejects unknown run_id • CHECK on discrepancy_type rejects 'OTHER' • CHECK on resolution_status rejects 'PENDING' • Default resolution_status is UNRESOLVED on insert | 25 | 6.5-T01 | BE | RATE-04
6.5-T03 | prefunding | 6.5 | 6. Prefunding & Wallet Ledger | Ledger reconciliation & statements | 2 | Add DB migration: ledger_statement table | Partner-facing prefunding ledger statements are generated on demand or on schedule. Table ledger_statement: id BIGINT PK, partner_id BIGINT FK partner NOT NULL, statement_period_start DATE NOT NULL, statement_period_end DATE NOT NULL, opening_balance_usd DECIMAL(20,4), closing_balance_usd DECIMAL(20,4), total_debits_usd DECIMAL(20,4) DEFAULT 0, total_credits_usd DECIMAL(20,4) DEFAULT 0, debit_count INT DEFAULT 0, credit_count INT DEFAULT 0, status VARCHAR(20) CHECK IN ('DRAFT','FINAL') DEFAULT 'DRAFT', generated_at TIMESTAMPTZ, generated_by VARCHAR(120), file_path VARCHAR(512), created_at TIMESTAMPTZ NOT NULL DEFAULT NOW(), updated_at TIMESTAMPTZ NOT NULL DEFAULT NOW(). UNIQUE(partner_id, statement_period_start, statement_period_end). Flyway V6_5_003. Only OVERSEAS partners (partner.type = 'OVERSEAS') ever have rows here. | • Create Flyway migration V6_5_003__add_ledger_statement.sql • Define table with all columns and constraints from context • Add index on (partner_id, statement_period_start) • Run migration and verify • Confirm UNIQUE constraint prevents duplicate statement for same partner and period | Flyway migration file V6_5_003__add_ledger_statement.sql | • Table exists with all columns after migration • UNIQUE constraint on (partner_id, statement_period_start, statement_period_end) fires on duplicate • CHECK on status rejects 'ARCHIVED' • opening_balance_usd and closing_balance_usd allow NULL (computed at generation time) • Index on (partner_id, statement_period_start) present | 20 |  | BE | RATE-04
6.5-T04 | prefunding | 6.5 | 6. Prefunding & Wallet Ledger | Ledger reconciliation & statements | 2 | Implement PoolIdentityReconJob: daily per-transaction pool identity check | RATE-04 §13.1 mandates a daily background job that re-checks every APPROVED cross-border transaction: ¦collection_usd - collection_margin_usd - payout_margin_usd - payout_usd_cost¦ < 0.01 USD. The job queries the transaction table for status=APPROVED, committed_at within the target date, and is_same_currency=false. For each row the identity check is recomputed; any breach inserts a row into recon_discrepancy (type POOL_IDENTITY_BREACH, txn_ref, expected_value = payout_usd_cost, actual_value = collection_usd-collection_margin_usd-payout_margin_usd, delta = actual-expected). All values use BigDecimal arithmetic (no float). The job records its run in reconciliation_run (type POOL_IDENTITY). Service class: PoolIdentityReconJob in package com.gmepayplus.recon. | • Create PoolIdentityReconJob Spring @Component with @Scheduled(cron) placeholder • Implement query: SELECT id, txn_ref, collection_usd, collection_margin_usd, payout_margin_usd, payout_usd_cost FROM transaction WHERE status='APPROVED' AND DATE(committed_at AT TIME ZONE 'Asia/Seoul')=:runDate AND (is_same_currency IS NULL OR is_same_currency=false) • For each row compute delta = (collection_usd - collection_margin_usd - payout_margin_usd) - payout_usd_cost using BigDecimal • If abs(delta) >= 0.01 insert recon_discrepancy row with type POOL_IDENTITY_BREACH • Insert/update reconciliation_run row with counts and status COMPLETED or PARTIAL | PoolIdentityReconJob.java with runForDate(LocalDate) method | • For a transaction with collection_usd=36.9714, collection_margin_usd=0.3697, payout_margin_usd=0.3697, payout_usd_cost=36.2319: delta=0.0001 < 0.01 → no discrepancy row inserted • For a synthetic row with delta=0.05: discrepancy_type=POOL_IDENTITY_BREACH is inserted with expected_value=36.2319, actual_value=36.2369, delta=0.0500 • Same-currency transactions (is_same_currency=true) are excluded from the check • reconciliation_run row status=COMPLETED with items_checked=N, items_discrepant=M after run • BigDecimal is used throughout; no double or float casts in the computation path | 45 | 6.5-T01, 6.5-T02 | BE | RATE-04
6.5-T05 | prefunding | 6.5 | 6. Prefunding & Wallet Ledger | Ledger reconciliation & statements | 2 | Implement PrefundingLedgerReconJob: daily ledger vs balance check | RATE-04 §13.3: daily reconciliation for each OVERSEAS partner: sum of all DEBIT_PAYMENT entries (amount) for the date + sum of DEBIT_REVERSAL entries (negative) + sum of CREDIT_TOPUP entries + sum of CREDIT_REVERSAL entries must equal (closing_balance - opening_balance) in the prefunding_account table for that date. prefunding_ledger_entry.entry_type IN ('DEBIT_PAYMENT','DEBIT_REVERSAL','CREDIT_TOPUP','CREDIT_REVERSAL'); DEBIT entries reduce balance, CREDIT entries increase it. Tolerance: 0.0001 USD. On mismatch insert recon_discrepancy type PREFUNDING_LEDGER_MISMATCH with expected_value=computed_net_change, actual_value=balance_delta, delta, ccy='USD'. Service class: PrefundingLedgerReconJob. | • Create PrefundingLedgerReconJob Spring @Component • For each partner with type=OVERSEAS, fetch prefunding_account.balance at start-of-day and end-of-day snapshots (use min/max balance_after from prefunding_ledger_entry for that account_id and date range) • Compute net_change_from_entries = sum(CREDIT entries) - sum(DEBIT entries) for the date, using entry_type and amount • Compute balance_delta = closing_balance - opening_balance from the ledger entry balance_after snapshots • If abs(net_change_from_entries - balance_delta) > 0.0001 USD, insert PREFUNDING_LEDGER_MISMATCH discrepancy • Record run in reconciliation_run with type PREFUNDING_LEDGER | PrefundingLedgerReconJob.java with runForDate(LocalDate) method | • Partner with 3 DEBIT_PAYMENT entries (2.00, 1.50, 0.75 USD) and 1 CREDIT_TOPUP (100.00 USD): net_change = +95.75; if balance_after snapshots agree → no discrepancy • If balance_delta=95.74 and net_change=95.75: delta=0.01 > 0.0001 → PREFUNDING_LEDGER_MISMATCH inserted with expected=95.75, actual=95.74 • LOCAL partners (type=LOCAL) are skipped entirely • Partner with no ledger entries on the run date: items_checked includes it, delta=0.00 no discrepancy • reconciliation_run row correctly counts total partners checked and discrepant partners | 45 | 6.5-T01, 6.5-T02 | BE | RATE-04
6.5-T06 | prefunding | 6.5 | 6. Prefunding & Wallet Ledger | Ledger reconciliation & statements | 2 | Implement SettlementAggregateReconJob: daily payout sum vs ZP0062/ZP0064 totals | RATE-04 §13.2: daily, sum of target_payout (KRW BIGINT) for all APPROVED transactions in the settlement date must match the total reported in the ZP0062 (morning settlement result) and ZP0064 (afternoon settlement result) files from 한결원. settlement_batch table (file_type IN ('ZP0062','ZP0064'), settlement_date, status=RECEIVED) has total_amount and transaction_count. GMEPay+ computes its own sum from the transaction table (status=APPROVED, settlement_date matches). Count mismatch → SETTLEMENT_COUNT_MISMATCH discrepancy; amount mismatch (tolerance 0 KRW for exact integer match) → SETTLEMENT_AMOUNT_MISMATCH. Also verifies ZP0061/ZP0063 outbound counts match GMEPay+ outbound count for that date. Service class: SettlementAggregateReconJob. | • Create SettlementAggregateReconJob Spring @Component • Query GMEPay+ approved transaction count and sum(target_payout) for the settlement_date • Query settlement_batch.total_amount and settlement_batch.transaction_count for ZP0062 and ZP0064 for same date (sum both morning and afternoon) • Compare counts: if mismatch insert SETTLEMENT_COUNT_MISMATCH with expected_value=gme_count, actual_value=scheme_count • Compare amounts: if mismatch insert SETTLEMENT_AMOUNT_MISMATCH with expected_value=gme_sum_krw, actual_value=scheme_sum_krw in ccy=KRW • Record run in reconciliation_run type SETTLEMENT_AGGREGATE; flag status=PARTIAL if settlement_batch rows not yet received (status != RECEIVED) | SettlementAggregateReconJob.java with runForDate(LocalDate) method | • GME sum=1,500,000 KRW / count=3, ZP0062 total=1,500,000 / count=3 → no discrepancy, items_matched=1 • GME sum=1,500,000 / count=3, ZP0062+ZP0064 sum=1,400,000 / count=3 → SETTLEMENT_AMOUNT_MISMATCH with expected=1500000, actual=1400000, ccy=KRW • GME count=3, scheme count=2 → SETTLEMENT_COUNT_MISMATCH inserted • If ZP0062 batch not yet received (status=PENDING) → run status=PARTIAL, no false discrepancy • KRW values compared as BIGINT arithmetic with zero tolerance | 50 | 6.5-T01, 6.5-T02 | BE | RATE-04
6.5-T07 | prefunding | 6.5 | 6. Prefunding & Wallet Ledger | Ledger reconciliation & statements | 2 | Implement RevenueReconService: monthly FX margin and service fee aggregation | RATE-04 §13.4: monthly revenue reconciliation. FX margin revenue = sum(collection_margin_usd + payout_margin_usd) across all APPROVED cross-border transactions in the period. Service fee revenue = sum(service_charge) per currency. Both are read from the revenue_record table (fx_margin_usd, service_charge_amount, service_charge_ccy). The monthly run produces a summary object: period (first/last day), partner_id, fx_margin_usd_total DECIMAL(20,4), service_fee_totals map(ccy→amount). No scheme_fee_share computed here (that requires ZeroPay's external statement). Inserts reconciliation_run type REVENUE_MONTHLY. Service: RevenueReconService.computeMonthlyRevenue(YearMonth, Long partnerId). | • Create RevenueReconService Spring @Service • Implement query against revenue_record: WHERE revenue_date BETWEEN period_start AND period_end AND partner_id=:partnerId AND txn is cross-border (join transaction on is_same_currency=false) • Sum fx_margin_usd across matched rows; group service_charge_amount by service_charge_ccy • Return MonthlyRevenueSummary DTO with fields: period_start, period_end, partner_id, fx_margin_usd_total, service_fee_map • Log result to reconciliation_run with type REVENUE_MONTHLY, items_checked=transaction count • Throw if partnerId is null (compute for all partners if null) | RevenueReconService.java with computeMonthlyRevenue(YearMonth, Long) and MonthlyRevenueSummary DTO | • 3 cross-border transactions with collection_margin_usd=0.37+0.50+0.20 and payout_margin_usd=0.37+0.50+0.20: fx_margin_total=2.28 USD • Service charges KRW 500, KRW 500, USD 0.36: service_fee_map={KRW=1000, USD=0.36} • Same-currency transactions are excluded from fx_margin sum • Null partnerId aggregates all partners; specific partnerId returns only that partner's rows • reconciliation_run row inserted with type REVENUE_MONTHLY and correct items_checked count | 40 | 6.5-T01 | BE | RATE-04
6.5-T08 | prefunding | 6.5 | 6. Prefunding & Wallet Ledger | Ledger reconciliation & statements | 2 | Implement UncertainTransactionAlertJob: flag UNCERTAIN txns unresolved > 24h | SAD-02 §5.4: if an UNCERTAIN transaction is not resolved within 24 hours of its SCHEME_SENT timestamp it must trigger an ops alert and enter the manual exception queue. Table: transaction.status='UNCERTAIN', and the transaction_event with step=SCHEME_SENT has occurred_at more than 24h ago. The job inserts a recon_discrepancy row with type UNCERTAIN_UNRESOLVED for each overdue transaction, then fires a notification (log at ERROR level; wire to existing notification service). Runs every hour via @Scheduled. Service class: UncertainTransactionAlertJob. | • Create UncertainTransactionAlertJob Spring @Component with @Scheduled(fixedDelay=3600000) • Query: SELECT t.id, t.txn_ref, e.occurred_at FROM transaction t JOIN transaction_event e ON e.txn_id=t.id AND e.step='SCHEME_SENT' WHERE t.status='UNCERTAIN' AND e.occurred_at < NOW() - INTERVAL '24 hours' • For each result insert recon_discrepancy if no existing UNRESOLVED row for same txn_ref and type UNCERTAIN_UNRESOLVED (idempotent) • Log each overdue txn_ref at ERROR level with occurred_at and age in hours • Record run summary in reconciliation_run type POOL_IDENTITY (reuse) or add UNCERTAIN run_type via migration if needed | UncertainTransactionAlertJob.java | • Transaction with SCHEME_SENT 25 hours ago and status=UNCERTAIN → discrepancy row inserted with type UNCERTAIN_UNRESOLVED • Transaction with SCHEME_SENT 23 hours ago → no row inserted • Idempotency: running job twice for same overdue txn → exactly one UNRESOLVED discrepancy row, not two • Transaction with SCHEME_SENT 25h ago but status=APPROVED (resolved) → not flagged • Log entry at ERROR level contains txn_ref and age when overdue item found | 35 | 6.5-T01, 6.5-T02 | BE | RATE-04
6.5-T09 | prefunding | 6.5 | 6. Prefunding & Wallet Ledger | Ledger reconciliation & statements | 2 | Implement LedgerStatementGenerator: build prefunding statement for a partner and period | Generates a ledger_statement row and associated line-item data for an OVERSEAS partner. Algorithm: (1) determine opening_balance_usd = balance_after of the last prefunding_ledger_entry before period_start for that account_id; if none, opening=0; (2) sum all entries within period: DEBIT_PAYMENT and DEBIT_REVERSAL reduce balance, CREDIT_TOPUP and CREDIT_REVERSAL increase it; (3) closing_balance = opening + net; (4) insert/update ledger_statement row with all computed fields, status=DRAFT; (5) all amounts in USD DECIMAL(20,4). Service: LedgerStatementGenerator.generate(Long partnerId, LocalDate periodStart, LocalDate periodEnd). Reject if partner type != OVERSEAS. | • Create LedgerStatementGenerator Spring @Service • Validate partner exists and type=OVERSEAS; throw PartnerTypeException otherwise • Fetch opening_balance: MAX(created_at) prefunding_ledger_entry before period_start for partner's account_id • Compute totals: sum CREDIT entries (CREDIT_TOPUP + CREDIT_REVERSAL), sum DEBIT entries (DEBIT_PAYMENT + DEBIT_REVERSAL), counts • Compute closing_balance_usd = opening + total_credits - total_debits • Upsert ledger_statement row (status=DRAFT) returning saved entity | LedgerStatementGenerator.java with generate() method | • Partner with opening balance 10000.00 USD, 2 DEBIT_PAYMENT (36.97, 50.00) and 1 CREDIT_TOPUP (1000.00) in period: closing=10913.03, total_debits=86.97, total_credits=1000.00, debit_count=2, credit_count=1 • No entries before period_start → opening_balance_usd=0.00 • Calling generate() twice for same partner/period upserts the same row (no duplicate) • LOCAL partner throws PartnerTypeException before any DB writes • period_start > period_end throws IllegalArgumentException | 45 | 6.5-T03 | BE | RATE-04
6.5-T10 | prefunding | 6.5 | 6. Prefunding & Wallet Ledger | Ledger reconciliation & statements | 2 | Implement LedgerStatementFinalizer: finalize and persist statement as FINAL | After review, an operator finalizes a DRAFT ledger_statement. Finalization: (1) validates that reconciliation_run for PREFUNDING_LEDGER on the same date range has status=COMPLETED with items_discrepant=0 (or operator explicitly overrides with a note); (2) sets ledger_statement.status=FINAL, generated_at=NOW(), generated_by=operator_id; (3) writes audit_log row (entity_type='ledger_statement', action='UPDATE', before_value, after_value). Method: LedgerStatementFinalizer.finalize(Long statementId, String operatorId, boolean forceOverride, String overrideNote). Service class in com.gmepayplus.recon. | • Create LedgerStatementFinalizer Spring @Service • Load ledger_statement by id; verify status=DRAFT, else throw IllegalStateException • Check reconciliation_run completion: query reconciliation_run WHERE run_date BETWEEN stmt.period_start AND stmt.period_end AND run_type=PREFUNDING_LEDGER; if items_discrepant > 0 and forceOverride=false throw ReconIncompleteException • Update ledger_statement status=FINAL, generated_at, generated_by • Write audit_log row with before_value (status=DRAFT) and after_value (status=FINAL), actor_id=operatorId • Return updated LedgerStatement entity | LedgerStatementFinalizer.java | • DRAFT statement with completed clean recon run → status set to FINAL, generated_at non-null • DRAFT statement with items_discrepant=1 and forceOverride=false → ReconIncompleteException, statement unchanged • DRAFT statement with items_discrepant=1 and forceOverride=true, overrideNote='Approved by Finance' → finalized; audit_log row contains overrideNote in after_value • Calling finalize on a FINAL statement → IllegalStateException • audit_log.before_value.status='DRAFT', after_value.status='FINAL' after successful finalization | 40 | 6.5-T03, 6.5-T05 | BE | RATE-04
6.5-T11 | prefunding | 6.5 | 6. Prefunding & Wallet Ledger | Ledger reconciliation & statements | 2 | Implement ReconciliationReportBuilder: assemble the daily recon report | The parent deliverable is a Recon Report. ReconciliationReportBuilder assembles a structured ReconReport DTO for a given run_date and scheme_id from: (1) all reconciliation_run rows for that date/scheme; (2) all recon_discrepancy rows linked to those runs; (3) summary counts: total_checked, total_matched, total_discrepant, total_resolved. Output DTO: ReconReport { run_date, scheme_id, runs: List<RunSummary>, discrepancies: List<DiscrepancySummary>, total_checked, total_discrepant, total_resolved, generated_at }. Service: ReconciliationReportBuilder.build(LocalDate, Long schemeId). | • Create ReconciliationReportBuilder Spring @Service • Query all reconciliation_run rows for run_date and scheme_id (or all schemes if schemeId null) • For each run, query associated recon_discrepancy rows • Build RunSummary (run_id, run_type, status, items_checked, items_discrepant) list • Build DiscrepancySummary (discrepancy_type, txn_ref, delta, ccy, resolution_status) list • Aggregate totals and return ReconReport DTO with generated_at=NOW() | ReconciliationReportBuilder.java and ReconReport/RunSummary/DiscrepancySummary DTOs | • Report for date with 2 runs (POOL_IDENTITY: 100 checked, 0 discrepant; PREFUNDING_LEDGER: 5 checked, 1 discrepant): total_checked=105, total_discrepant=1, total_resolved=0 • Resolved discrepancy (resolution_status=RESOLVED) increments total_resolved • Null schemeId includes all schemes in totals • Empty date (no runs) returns ReconReport with all counts=0, runs=[], discrepancies=[] • DiscrepancySummary.delta is BigDecimal, not double, in serialized output | 35 | 6.5-T01, 6.5-T02 | BE | RATE-04
6.5-T12 | prefunding | 6.5 | 6. Prefunding & Wallet Ledger | Ledger reconciliation & statements | 2 | Expose GET /internal/v1/recon/report endpoint | Admin operators need to fetch the daily recon report via REST. Endpoint: GET /internal/v1/recon/report?runDate=YYYY-MM-DD&schemeId={id}. Requires ROLE_OPS_ADMIN. Returns ReconReport JSON (see 6.5-T11). runDate defaults to yesterday KST if omitted. Returns 200 with report body; 400 if runDate format invalid; 404 if no runs found. Controller: ReconReportController in com.gmepayplus.admin.recon. The /internal/ prefix is behind the internal gateway and not exposed to partners. | • Create ReconReportController @RestController @RequestMapping('/internal/v1/recon') • Add GET /report handler with @RequestParam(required=false) String runDate and @RequestParam(required=false) Long schemeId • Parse runDate to LocalDate (KST default = yesterday if null); return 400 on parse error • Call ReconciliationReportBuilder.build(); if result has zero runs return 404 • Apply @PreAuthorize('hasRole(ROLE_OPS_ADMIN)') • Return 200 with ReconReport JSON body | ReconReportController.java with GET /internal/v1/recon/report handler | • GET /internal/v1/recon/report?runDate=2026-06-04 returns 200 with correct report body • GET /internal/v1/recon/report?runDate=invalid returns 400 • GET /internal/v1/recon/report for date with no runs returns 404 • Request without ROLE_OPS_ADMIN returns 403 • runDate omitted defaults to yesterday (KST offset +09:00) not UTC | 30 | 6.5-T11 | BE | RATE-04
6.5-T13 | prefunding | 6.5 | 6. Prefunding & Wallet Ledger | Ledger reconciliation & statements | 2 | Expose GET /internal/v1/recon/discrepancies endpoint with filtering | Admin operators need to query open discrepancies to action them. Endpoint: GET /internal/v1/recon/discrepancies?runDate=&runType=&resolutionStatus=UNRESOLVED&page=0&size=20. ROLE_OPS_ADMIN required. Returns Page<DiscrepancySummary> sorted by created_at DESC. Filters: runDate (optional), run_type (optional), resolution_status (default UNRESOLVED). Controller: ReconDiscrepancyController. Reuses DiscrepancySummary DTO from 6.5-T11 plus run_id and run_type fields. | • Create ReconDiscrepancyController @RestController • Implement GET /discrepancies with @RequestParam filters (runDate, runType, resolutionStatus default UNRESOLVED) and Pageable • Build JPA Specification or JPQL query joining recon_discrepancy→reconciliation_run filtering by supplied params • Return Page<DiscrepancySummary> with pagination metadata • Apply @PreAuthorize('hasRole(ROLE_OPS_ADMIN)') • Return 400 for invalid runType enum value | ReconDiscrepancyController.java with GET /internal/v1/recon/discrepancies handler | • Filter resolutionStatus=UNRESOLVED returns only UNRESOLVED rows • Filter runType=POOL_IDENTITY returns only POOL_IDENTITY discrepancies • Pagination: page=0&size=5 with 12 rows returns 5 items and totalElements=12 • Invalid runType value returns 400 • No ROLE_OPS_ADMIN → 403 | 35 | 6.5-T11 | BE | RATE-04
6.5-T14 | prefunding | 6.5 | 6. Prefunding & Wallet Ledger | Ledger reconciliation & statements | 2 | Expose PATCH /internal/v1/recon/discrepancies/{id}/resolve endpoint | Ops operators must be able to mark a discrepancy as RESOLVED or ESCALATED. PATCH /internal/v1/recon/discrepancies/{id}/resolve. Body: { resolutionStatus: 'RESOLVED'¦'ESCALATED', resolutionNote: string (required, max 500 chars) }. Sets resolved_by=authenticated user, resolved_at=NOW(), resolution_status, resolution_note. Requires ROLE_OPS_ADMIN. Writes audit_log row (entity_type='recon_discrepancy', action='UPDATE'). Returns 200 updated DiscrepancySummary. 404 if id not found. 409 if already RESOLVED or ESCALATED. | • Add PATCH /discrepancies/{id}/resolve to ReconDiscrepancyController • Validate body: resolutionStatus IN (RESOLVED, ESCALATED), resolutionNote not blank and <= 500 chars • Load recon_discrepancy; return 404 if absent; return 409 if resolution_status != UNRESOLVED • Update resolution_status, resolved_by (from SecurityContext), resolved_at=NOW(), resolution_note • Write audit_log row: entity_type=recon_discrepancy, action=UPDATE, before/after values • Return 200 with updated DiscrepancySummary | PATCH /resolve handler in ReconDiscrepancyController | • UNRESOLVED discrepancy resolved with note → status=RESOLVED, resolved_by=operator id, resolved_at non-null • Already RESOLVED → 409 with no DB change • resolutionNote empty string → 400 validation error • resolutionNote 501 chars → 400 validation error • audit_log row present with before_value.resolution_status=UNRESOLVED and after_value.resolution_status=RESOLVED | 35 | 6.5-T13 | BE | RATE-04
6.5-T15 | prefunding | 6.5 | 6. Prefunding & Wallet Ledger | Ledger reconciliation & statements | 2 | Expose GET /internal/v1/recon/statements endpoint for ledger statements | Operators and internal systems need to list and view partner ledger statements. GET /internal/v1/recon/statements?partnerId=&status=&periodStart=&periodEnd= returns Page<LedgerStatementSummary> (id, partner_id, period_start, period_end, opening_balance_usd, closing_balance_usd, total_debits_usd, total_credits_usd, status, generated_at). ROLE_OPS_ADMIN required. GET /internal/v1/recon/statements/{id} returns full LedgerStatement. 404 if not found. Controller: LedgerStatementController. | • Create LedgerStatementController @RestController @RequestMapping('/internal/v1/recon/statements') • Implement GET / with Pageable and optional filters (partnerId, status, periodStart, periodEnd) • Implement GET /{id} returning full LedgerStatement entity as DTO • Return 404 if statement id not found • Apply @PreAuthorize('hasRole(ROLE_OPS_ADMIN)') on class • Add LedgerStatementSummary DTO mapping from ledger_statement table | LedgerStatementController.java with GET list and GET by-id handlers | • GET /statements?partnerId=1 returns only statements for partner 1 • GET /statements?status=FINAL returns only FINAL statements • GET /statements/{valid_id} returns full statement with all balance fields • GET /statements/{unknown_id} returns 404 • GET /statements without ROLE_OPS_ADMIN returns 403 | 30 | 6.5-T09 | BE | RATE-04
6.5-T16 | prefunding | 6.5 | 6. Prefunding & Wallet Ledger | Ledger reconciliation & statements | 2 | Expose POST /internal/v1/recon/statements/generate endpoint | Operators trigger statement generation on demand. POST /internal/v1/recon/statements/generate body: { partnerId: Long, periodStart: date, periodEnd: date }. Calls LedgerStatementGenerator.generate(). Returns 201 with created LedgerStatement. 400 if partner is LOCAL type or period invalid. 409 if a FINAL statement already exists for that period. ROLE_OPS_ADMIN required. | • Add POST /generate to LedgerStatementController • Validate request body: partnerId not null, periodStart <= periodEnd • Call LedgerStatementGenerator.generate(); catch PartnerTypeException → 400 • Check if existing FINAL statement exists for partner/period; if so return 409 • Return 201 with created statement body • Apply @PreAuthorize('hasRole(ROLE_OPS_ADMIN)') | POST /generate handler in LedgerStatementController | • Valid OVERSEAS partner and period → 201 with statement body, status=DRAFT • LOCAL partner → 400 with error code PARTNER_TYPE_INVALID • periodStart > periodEnd → 400 • Already-FINAL statement for same period → 409, no new row created • DRAFT statement for same period → generates new run and upserts (idempotent), returns 201 | 30 | 6.5-T09, 6.5-T15 | BE | RATE-04
6.5-T17 | prefunding | 6.5 | 6. Prefunding & Wallet Ledger | Ledger reconciliation & statements | 2 | Expose POST /internal/v1/recon/statements/{id}/finalize endpoint | Operators finalize a DRAFT statement. POST /internal/v1/recon/statements/{id}/finalize body: { forceOverride: bool, overrideNote: string (required when forceOverride=true) }. Calls LedgerStatementFinalizer.finalize(). Returns 200 with updated statement. 404 if not found, 409 if already FINAL, 422 if recon not clean and forceOverride=false. ROLE_OPS_ADMIN required. | • Add POST /{id}/finalize to LedgerStatementController • Load statement; return 404 if absent; return 409 if status=FINAL • Validate: if forceOverride=true, overrideNote must not be blank → 400 • Call LedgerStatementFinalizer.finalize(); catch ReconIncompleteException → 422 with detail • Return 200 with updated statement • Apply @PreAuthorize('hasRole(ROLE_OPS_ADMIN)') | POST /finalize handler in LedgerStatementController | • DRAFT statement with clean recon → 200, status=FINAL in response • FINAL statement → 409 • forceOverride=true with blank overrideNote → 400 • forceOverride=false with open discrepancies → 422 • forceOverride=true with note='Finance approved' and open discrepancies → 200, status=FINAL | 25 | 6.5-T10, 6.5-T15 | BE | RATE-04
6.5-T18 | prefunding | 6.5 | 6. Prefunding & Wallet Ledger | Ledger reconciliation & statements | 2 | Schedule PoolIdentityReconJob and PrefundingLedgerReconJob via cron | Both daily recon jobs must run automatically. PoolIdentityReconJob fires at 06:00 KST (21:00 UTC prev day) to process prior day's committed transactions. PrefundingLedgerReconJob fires at 06:15 KST (21:15 UTC prev day). Both jobs must be idempotent — if run twice for the same date they must not insert duplicate reconciliation_run or recon_discrepancy rows. Use Spring @Scheduled with cron expressions and a DB-level idempotency guard (check for existing reconciliation_run with same run_date + run_type before creating new run). Jobs are disabled in test profile via @ConditionalOnProperty. | • Add @Scheduled(cron='0 0 21 * * *', zone='UTC') to PoolIdentityReconJob.run() method • Add @Scheduled(cron='0 15 21 * * *', zone='UTC') to PrefundingLedgerReconJob.run() method • In each job's run() method, compute runDate = LocalDate.now(ZoneId.of('Asia/Seoul')).minusDays(1) • Add idempotency check: if reconciliation_run exists for (runDate, run_type) and status=COMPLETED skip execution; log INFO • Add @ConditionalOnProperty(name='recon.scheduler.enabled', matchIfMissing=true) to both job beans • Verify cron fires via integration test with @TestPropertySource disabling schedule and calling runForDate() directly | @Scheduled annotations and idempotency guard in PoolIdentityReconJob and PrefundingLedgerReconJob | • PoolIdentityReconJob.run() invoked at 21:00 UTC computes runDate = Seoul date - 1 day correctly across midnight boundary • Second invocation for same runDate with existing COMPLETED run → skipped, no duplicate reconciliation_run row • Cron expression '0 0 21 * * *' zone=UTC verified to fire at 06:00 KST next day • recon.scheduler.enabled=false disables bean instantiation in test context • PrefundingLedgerReconJob runs 15 minutes after PoolIdentityReconJob (21:15 UTC) | 30 | 6.5-T04, 6.5-T05 | BE | RATE-04
6.5-T19 | prefunding | 6.5 | 6. Prefunding & Wallet Ledger | Ledger reconciliation & statements | 2 | Schedule SettlementAggregateReconJob after ZP0062/ZP0064 receipt windows | SettlementAggregateReconJob must run after ZP0062 (available ~10:00 KST) and again after ZP0064 (available ~19:00 KST) to reconcile morning and afternoon settlement results. Run at 10:30 KST (01:30 UTC) for morning window and 19:30 KST (10:30 UTC) for afternoon window. Idempotency: for each window check if settlement_batch rows for that file_type and date have status=RECEIVED before running; if not, record reconciliation_run status=PARTIAL. Same idempotency guard as 6.5-T18. | • Add @Scheduled(cron='0 30 1 * * *', zone='UTC') for morning run and @Scheduled(cron='0 30 10 * * *', zone='UTC') for afternoon run to SettlementAggregateReconJob • Each trigger calls runForDate(LocalDate) passing Seoul current date or prior day as appropriate • Add pre-check: if ZP0062/ZP0064 batch not yet RECEIVED for the date, mark run PARTIAL and return early without inserting false discrepancies • Apply same idempotency guard (skip if COMPLETED run already exists) • Add @ConditionalOnProperty(name='recon.scheduler.enabled') guard • Document the two windows and their ZP file dependencies in class Javadoc | @Scheduled triggers in SettlementAggregateReconJob with PARTIAL guard | • Morning trigger fires at 01:30 UTC (10:30 KST) and uses correct settlement_date • ZP0062 batch with status=PENDING → run stored as PARTIAL, zero discrepancy rows • ZP0062 batch with status=RECEIVED and correct totals → COMPLETED run, zero discrepancies • Second run for same date after first COMPLETED → skipped by idempotency guard • Afternoon run at 10:30 UTC processes ZP0064 file independently of morning | 30 | 6.5-T06, 6.5-T18 | BE | RATE-04
6.5-T20 | prefunding | 6.5 | 6. Prefunding & Wallet Ledger | Ledger reconciliation & statements | 2 | Implement OpsAlertService integration for reconciliation discrepancies | SAD-02 §7.8: recon discrepancies and UNCERTAIN overdue items must trigger ops alerts. OpsAlertService already handles low_balance alerts (topic prefunding.low_balance). Add a new alert type RECON_DISCREPANCY. When PoolIdentityReconJob, PrefundingLedgerReconJob, or SettlementAggregateReconJob produce items_discrepant > 0, they call OpsAlertService.sendReconAlert(RunSummary). Alert includes: run_date, run_type, scheme_id, items_discrepant, link to GET /internal/v1/recon/discrepancies. In Phase 1, alert is logged at ERROR level and queued on the 'ops.alerts' internal event topic. Actual email dispatch is handled by the existing Notification Service consumer. | • Add sendReconAlert(RunSummary summary) to OpsAlertService • Format alert payload with run_date, run_type, scheme_id, items_discrepant, discrepancy_link • Publish event to ops.alerts topic (or log ERROR with structured JSON in Phase 1 if topic not yet wired) • Call sendReconAlert in PoolIdentityReconJob, PrefundingLedgerReconJob, and SettlementAggregateReconJob after run completes if items_discrepant > 0 • Call sendReconAlert from UncertainTransactionAlertJob when overdue txns found • Add unit test: mock OpsAlertService; verify called once per run with items_discrepant=2 | OpsAlertService.sendReconAlert() and its invocations in all four recon jobs | • PoolIdentityReconJob with 2 discrepant items → sendReconAlert called once with items_discrepant=2 • Run with items_discrepant=0 → sendReconAlert NOT called • Alert payload contains run_date, run_type, scheme_id as structured fields • UncertainTransactionAlertJob with 1 overdue txn → alert fired with txn_ref in payload • Phase 1: if ops.alerts topic absent, falls back to ERROR log without throwing exception | 35 | 6.5-T04, 6.5-T05, 6.5-T06, 6.5-T08 | BE | RATE-04
6.5-T21 | prefunding | 6.5 | 6. Prefunding & Wallet Ledger | Ledger reconciliation & statements | 2 | Unit tests for PoolIdentityReconJob logic | Test coverage for the pool identity check logic in PoolIdentityReconJob. Uses mocked TransactionRepository and ReconDiscrepancyRepository. Test vectors from RATE-04 §4.3 and §5.4: nominal case collection_usd=36.9714, collection_margin_usd=0.3697, payout_margin_usd=0.3697, payout_usd_cost=36.2319 → delta=0.0001 < 0.01 → no discrepancy. Breach case: collection_usd=36.9714, collection_margin_usd=0.3697, payout_margin_usd=0.3697, payout_usd_cost=36.2220 → delta=0.01 → discrepancy. Same-currency exclusion: is_same_currency=true → skipped. All arithmetic in BigDecimal. | • Create PoolIdentityReconJobTest in src/test/java • Mock TransactionRepository.findApprovedCrossBorderForDate() returning controlled list of transaction projections • Test case 1: delta=0.0001 → verify save() on ReconDiscrepancyRepository NOT called • Test case 2: delta=0.0100 → verify save() called once with expected_value=36.2220, actual_value=36.2320, delta=0.0100 • Test case 3: is_same_currency=true → verify transaction skipped (save not called even if delta>0.01 set) • Test case 4: empty transaction list → reconciliation_run status=COMPLETED with items_checked=0 | PoolIdentityReconJobTest.java with at least 4 test cases | • All 4 test cases pass with @Test assertions • No floating-point comparison in test assertions (use BigDecimal compareTo or assertThat with precision) • Test case 2 verifies discrepancy_type=POOL_IDENTITY_BREACH • Test case 3 verifies same-currency transaction produces zero discrepancy rows • Coverage report shows > 90% line coverage on PoolIdentityReconJob.runForDate() | 40 | 6.5-T04 | BE | RATE-04
6.5-T22 | prefunding | 6.5 | 6. Prefunding & Wallet Ledger | Ledger reconciliation & statements | 2 | Unit tests for PrefundingLedgerReconJob logic | Test the ledger vs balance reconciliation logic. Mock PrefundingAccountRepository and PrefundingLedgerEntryRepository. Test vectors: Partner A has opening balance 10000.00, 2 DEBIT_PAYMENT (36.97, 50.00), 1 CREDIT_TOPUP (200.00); net_change=+113.03; balance_after snapshots give delta=113.03 → no discrepancy. Mismatch case: same entries but balance_after gives delta=113.00 → delta=0.03 > 0.0001 → PREFUNDING_LEDGER_MISMATCH discrepancy. LOCAL partner exclusion: partner type=LOCAL → skipped. Edge: no entries in period → no discrepancy, items_checked includes partner. | • Create PrefundingLedgerReconJobTest • Mock OVERSEAS partner list and ledger entry repository • Test case 1 (balanced): net_change=113.03, balance_delta=113.03 → no discrepancy • Test case 2 (mismatch): net_change=113.03, balance_delta=113.00 → PREFUNDING_LEDGER_MISMATCH with delta=0.03 • Test case 3: LOCAL partner included in partner list → not processed, items_checked excludes it • Test case 4: no entries in period → delta=0.00, no discrepancy, items_checked=1 | PrefundingLedgerReconJobTest.java with at least 4 test cases | • Test case 1 passes: save() on DiscrepancyRepo not called • Test case 2 passes: save() called with type=PREFUNDING_LEDGER_MISMATCH, expected=113.03, actual=113.00, ccy=USD • Test case 3 passes: LOCAL partner not counted in items_checked • Test case 4 passes: items_checked=1, items_discrepant=0 • All BigDecimal comparisons use scale-aware comparison (not == or equals without scale normalisation) | 40 | 6.5-T05 | BE | RATE-04
6.5-T23 | prefunding | 6.5 | 6. Prefunding & Wallet Ledger | Ledger reconciliation & statements | 2 | Unit tests for SettlementAggregateReconJob logic | Test the settlement count/amount comparison logic. Mock TransactionRepository and SettlementBatchRepository. Test vectors: GME sum=1,500,000 KRW count=3; ZP0062+ZP0064 combined sum=1,500,000 count=3 → matched. Count mismatch: GME count=3, scheme count=2 → SETTLEMENT_COUNT_MISMATCH. Amount mismatch: GME sum=1,500,000 KRW, scheme sum=1,400,000 → SETTLEMENT_AMOUNT_MISMATCH with delta=100000 KRW. Partial: ZP0062 status=PENDING → run PARTIAL, no discrepancy. Edge: zero transactions for date → items_checked=0, COMPLETED. | • Create SettlementAggregateReconJobTest • Mock GME transaction aggregation returning (count, sum) pairs • Mock settlement_batch repository returning ZP0062 and ZP0064 rows with controlled status and totals • Test case 1 (match): GME=3/1500000, scheme=3/1500000 → COMPLETED, no discrepancy • Test case 2 (count mismatch): GME=3, scheme=2 → SETTLEMENT_COUNT_MISMATCH discrepancy • Test case 3 (amount mismatch): GME sum=1500000, scheme sum=1400000 → SETTLEMENT_AMOUNT_MISMATCH delta=100000 ccy=KRW • Test case 4 (PARTIAL): ZP0062 not RECEIVED → run=PARTIAL, no discrepancy rows saved | SettlementAggregateReconJobTest.java with at least 4 test cases | • Test case 1: items_matched=1, items_discrepant=0, status=COMPLETED • Test case 2: discrepancy type=SETTLEMENT_COUNT_MISMATCH, expected=3, actual=2 • Test case 3: discrepancy type=SETTLEMENT_AMOUNT_MISMATCH, delta=100000, ccy=KRW • Test case 4: status=PARTIAL, save() on DiscrepancyRepo not called • KRW amounts stored and compared as BIGINT (Long), not DECIMAL | 40 | 6.5-T06 | BE | RATE-04
6.5-T24 | prefunding | 6.5 | 6. Prefunding & Wallet Ledger | Ledger reconciliation & statements | 2 | Unit tests for LedgerStatementGenerator | Test statement generation logic. Mock PrefundingAccountRepository and PrefundingLedgerEntryRepository. Test vectors from spec: partner opening=10000.00, entries: DEBIT_PAYMENT 36.97, DEBIT_PAYMENT 50.00, CREDIT_TOPUP 1000.00 → closing=10913.03, total_debits=86.97, total_credits=1000.00, debit_count=2, credit_count=1. Edge: no prior entries (opening=0.00). Rejection: LOCAL partner throws PartnerTypeException. Idempotency: second call for same period upserts, not inserts duplicate. | • Create LedgerStatementGeneratorTest with mocked repositories • Test case 1 (standard): opening=10000.00, 3 entries as above → assert closing=10913.03, debit_count=2, credit_count=1 • Test case 2 (no prior entries): opening_balance=0.00 → closing = net of period entries • Test case 3 (LOCAL partner): expect PartnerTypeException thrown before any repo call • Test case 4 (idempotency): mock existing DRAFT statement → updated, not inserted again; result has same id • Verify all amounts are BigDecimal/DECIMAL not double | LedgerStatementGeneratorTest.java with at least 4 test cases | • Test case 1 passes: closing_balance_usd=10913.03 within DECIMAL(20,4) precision • Test case 2 passes: opening=0.00, closing=net_change for period • Test case 3: PartnerTypeException thrown; LedgerStatementRepository.save() never called • Test case 4: existing DRAFT statement id unchanged after second generate call • period_end < period_start test: IllegalArgumentException thrown | 35 | 6.5-T09 | BE | RATE-04
6.5-T25 | prefunding | 6.5 | 6. Prefunding & Wallet Ledger | Ledger reconciliation & statements | 2 | Unit tests for ReconciliationReportBuilder | Test the report assembly logic. Mock ReconciliationRunRepository and ReconDiscrepancyRepository. Test vectors: 2 runs for date (POOL_IDENTITY: 100 checked, 0 discrepant; PREFUNDING_LEDGER: 5 checked, 1 discrepant). 1 discrepancy row with resolution_status=UNRESOLVED. Report: total_checked=105, total_discrepant=1, total_resolved=0. Second scenario: discrepancy RESOLVED → total_resolved=1. Empty date: all counts zero. | • Create ReconciliationReportBuilderTest • Mock run repository returning 2 run rows and discrepancy repository returning 1 UNRESOLVED discrepancy • Test case 1: assert total_checked=105, total_discrepant=1, total_resolved=0, runs.size=2, discrepancies.size=1 • Test case 2: discrepancy resolution_status=RESOLVED → total_resolved=1 • Test case 3: no runs for date → ReconReport with all counts=0, empty lists, generated_at non-null • Verify generated_at is set and after test start time | ReconciliationReportBuilderTest.java with at least 3 test cases | • Test case 1 passes with all aggregate counts correct • Test case 2 passes with total_resolved=1 • Test case 3 returns empty report with non-null generated_at • DiscrepancySummary in report contains txn_ref, delta, discrepancy_type, resolution_status • Report DTO is serializable to JSON without errors (use Jackson ObjectMapper in test) | 30 | 6.5-T11 | BE | RATE-04
6.5-T26 | prefunding | 6.5 | 6. Prefunding & Wallet Ledger | Ledger reconciliation & statements | 2 | Integration test: full daily recon cycle for a synthetic partner | End-to-end integration test using @SpringBootTest with test PostgreSQL (Testcontainers). Inserts 3 APPROVED cross-border transactions with valid pool identity, 1 prefunding account with matching ledger entries, and 1 settlement_batch row (ZP0062 RECEIVED). Runs PoolIdentityReconJob.runForDate(), PrefundingLedgerReconJob.runForDate(), and SettlementAggregateReconJob.runForDate() directly. Asserts zero discrepancies, COMPLETED run rows, and correct ReconciliationReportBuilder output. Also inserts 1 transaction with pool identity breach and asserts 1 POOL_IDENTITY_BREACH discrepancy row. | • Create ReconIntegrationTest @SpringBootTest with Testcontainers PostgreSQL • Insert test partner (OVERSEAS), prefunding_account, 3 valid APPROVED transactions using canonical RATE-04 §4.3 values • Insert matching prefunding_ledger_entry rows (opening→closing consistent) • Insert settlement_batch ZP0062 RECEIVED with total matching GME sum • Run all three recon jobs for the test date; assert zero discrepancies and all runs COMPLETED • Insert 1 transaction with pool identity breach (payout_usd_cost off by 0.05); re-run PoolIdentityReconJob; assert 1 POOL_IDENTITY_BREACH row | ReconIntegrationTest.java passing with Testcontainers | • Clean data scenario: all 3 reconciliation_run rows status=COMPLETED, recon_discrepancy count=0 • Pool breach scenario: exactly 1 recon_discrepancy row with type=POOL_IDENTITY_BREACH after re-run • ReconciliationReportBuilder.build() returns total_checked=3 (transactions) for clean run • Second invocation of each job for same date does not create duplicate reconciliation_run rows • Test runs successfully with @ActiveProfiles('test') and recon.scheduler.enabled=false | 55 | 6.5-T04, 6.5-T05, 6.5-T06, 6.5-T11 | BE | RATE-04
6.5-T27 | prefunding | 6.5 | 6. Prefunding & Wallet Ledger | Ledger reconciliation & statements | 2 | Implement ReconReport CSV export: GET /internal/v1/recon/report/export | Finance and Ops need to export the daily recon report as CSV for offline review. GET /internal/v1/recon/report/export?runDate=YYYY-MM-DD produces a CSV file. Columns: run_type, discrepancy_type, txn_ref, scheme_ref, expected_value, actual_value, delta, ccy, resolution_status. One row per recon_discrepancy for the date. Empty report → CSV with headers only. Content-Type: text/csv; filename: recon_report_{runDate}.csv. Uses ReconciliationReportBuilder output. ROLE_OPS_ADMIN required. | • Add GET /report/export to ReconReportController • Call ReconciliationReportBuilder.build(runDate, null) to get full report • Map discrepancies list to CSV rows using OpenCSV or manual StringBuilder • Set response Content-Type: text/csv, Content-Disposition: attachment; filename=recon_report_{runDate}.csv • Return 200 with CSV body; 404 if no runs for date; 400 if date invalid • Include header row even when discrepancy list is empty | GET /report/export handler in ReconReportController | • 3 discrepancies for date → CSV has header row + 3 data rows • Empty discrepancies → CSV has header row only, 200 not 404 • Content-Disposition header contains recon_report_2026-06-04.csv for runDate=2026-06-04 • Invalid date format → 400 • No ROLE_OPS_ADMIN → 403 | 35 | 6.5-T12 | BE | RATE-04
6.5-T28 | prefunding | 6.5 | 6. Prefunding & Wallet Ledger | Ledger reconciliation & statements | 2 | Implement LedgerStatement CSV line-item export | Partners and Finance need a line-item CSV of prefunding_ledger_entry rows for a statement period. GET /internal/v1/recon/statements/{id}/export produces CSV. Columns: entry_type, txn_ref, amount, balance_after, note, created_at. Rows ordered by created_at ASC. Content-Type: text/csv; filename: statement_{partner_id}_{period_start}_{period_end}.csv. Only FINAL or DRAFT statements can be exported (any status). ROLE_OPS_ADMIN required. Statement 404 if not found. | • Add GET /{id}/export to LedgerStatementController • Load ledger_statement by id; 404 if not found • Query prefunding_ledger_entry WHERE account_id = statement.partner's account_id AND created_at BETWEEN period_start 00:00 UTC AND period_end 23:59:59 UTC ORDER BY created_at ASC • Map rows to CSV: entry_type, txn_ref, amount (formatted to 4dp), balance_after, note, created_at ISO-8601 • Set Content-Disposition filename using partner_id and period dates • Return 200 with CSV; header row always present | GET /{id}/export handler in LedgerStatementController | • Statement with 3 ledger entries → CSV has header + 3 rows in created_at order • FINAL and DRAFT statements both exportable • Content-Disposition contains correct partner_id and period in filename • Statement id not found → 404 • amount column uses 4 decimal places (e.g. 36.9714 not 36.97) | 35 | 6.5-T15 | BE | RATE-04
6.5-T29 | prefunding | 6.5 | 6. Prefunding & Wallet Ledger | Ledger reconciliation & statements | 2 | Add recon DB indexes and query performance validation | Reconciliation queries scan large tables: transaction (millions of rows), prefunding_ledger_entry (many per partner per day). Required indexes (if not already present from earlier migrations): transaction(status, committed_at) for pool identity scan; transaction(settlement_date) for settlement aggregate; prefunding_ledger_entry(account_id, created_at) already specified in DAT-03 - verify it exists; reconciliation_run(run_date, run_type); recon_discrepancy(run_id). Add EXPLAIN ANALYZE test confirming index usage for each recon query. Flyway V6_5_004. | • Create Flyway migration V6_5_004__add_recon_indexes.sql • Add index on transaction(status, committed_at) if absent • Add index on transaction(settlement_date) if absent • Verify prefunding_ledger_entry(account_id, created_at) exists via pg_indexes; add if absent • Run EXPLAIN ANALYZE on each of the 3 main recon queries against test DB with 10k+ synthetic rows • Assert Seq Scan on transaction not present for status+committed_at filter (should use index) | Flyway migration V6_5_004__add_recon_indexes.sql and EXPLAIN output in PR description | • EXPLAIN ANALYZE for pool identity query uses Index Scan on transaction(status, committed_at) • EXPLAIN ANALYZE for prefunding ledger query uses Index Scan on prefunding_ledger_entry(account_id, created_at) • EXPLAIN ANALYZE for settlement aggregate query uses Index Scan on transaction(settlement_date) • Migration runs cleanly and is idempotent (CREATE INDEX IF NOT EXISTS) • No existing migration broken by duplicate index name | 40 | 6.5-T01, 6.5-T02 | BE | RATE-04
6.5-T30 | prefunding | 6.5 | 6. Prefunding & Wallet Ledger | Ledger reconciliation & statements | 2 | Document recon runbook: daily procedures and escalation | OPS-13 requires an operational runbook for settlement and reconciliation procedures. Create recon-runbook.md covering: daily job schedule (times, run types), how to query open discrepancies via the API, how to resolve vs escalate, forced-finalize procedure for ledger statements, UNCERTAIN txn escalation path (manual exception queue), alert email setup. Must reference real endpoint URLs, field names, and error codes from this work-package. Audience: GME Ops team with no code access. | • Create docs/ops/recon-runbook.md • Section 1: Daily schedule table (job name, cron time KST, run_type, source files) • Section 2: Querying discrepancies (GET /internal/v1/recon/discrepancies with example curl) • Section 3: Resolving vs escalating (PATCH /discrepancies/{id}/resolve, when to use ESCALATED) • Section 4: Ledger statement generation and finalization (POST /generate, POST /finalize, forceOverride) • Section 5: UNCERTAIN transaction escalation (24h threshold, manual exception queue entry procedure) | docs/ops/recon-runbook.md | • Section 1 contains correct KST times: PoolIdentity 06:00, PrefundingLedger 06:15, Settlement 10:30 and 19:30 • Section 2 includes a valid example curl with resolutionStatus=UNRESOLVED filter • Section 3 distinguishes RESOLVED (self-service) from ESCALATED (Finance approval required) cases • Section 4 explains forceOverride=true requires overrideNote, referenced to 422 error for missing note • Section 5 states 24h SLA from SCHEME_SENT timestamp and names the ops.alerts alert topic | 40 | 6.5-T12, 6.5-T13, 6.5-T14, 6.5-T16, 6.5-T17 | BE | RATE-04
7.1-T01 | settlement-reconciliation | 7.1 | 7. Settlement, Reconciliation & Revenue | Settlement model: net vs gross | 2 | Add settlement_type column to transaction table (migration) | The settlement model for ZeroPay differs by partner type: LOCAL partners (e.g. GME Remit) use NET settlement (GME retains its share, remits target_payout to ZeroPay); OVERSEAS partners (e.g. SendMN, T-Bank) use GROSS settlement (GME remits full target_payout to ZeroPay, invoices merchant monthly). The transaction table needs a settlement_type field to drive downstream batch logic. Schema: settlement_type CHAR(1) NOT NULL DEFAULT 'N' CHECK (settlement_type IN ('N','G')) -- N=Net domestic, G=Gross international. Also add settlement_batch_id BIGINT FK -> settlement_batch (nullable, set when transaction is included in a batch). | • Create Flyway migration V7_1_001__add_settlement_type_to_transaction.sql • Add column: ALTER TABLE transaction ADD COLUMN settlement_type CHAR(1) NOT NULL DEFAULT 'N' CHECK (settlement_type IN ('N', 'G')) • Add column: ALTER TABLE transaction ADD COLUMN settlement_batch_id BIGINT REFERENCES settlement_batch(id) • Add index: CREATE INDEX idx_transaction_settlement_batch ON transaction(settlement_batch_id) • Add index: CREATE INDEX idx_transaction_settlement_type_status ON transaction(settlement_type, status, committed_at) for batch query performance | Flyway migration file V7_1_001__add_settlement_type_to_transaction.sql | • Migration applies cleanly on an empty schema and on a schema with existing transaction rows (existing rows get settlement_type='N' by default) • settlement_type accepts only 'N' or 'G'; INSERT with value 'X' raises a constraint violation • settlement_batch_id can be NULL (unbatched) and FK constraint rejects a non-existent settlement_batch id • Index idx_transaction_settlement_type_status exists after migration • Rollback script (if required) drops the two columns without error | 30 |  | BE | RATE-04, SCH-06
7.1-T02 | settlement-reconciliation | 7.1 | 7. Settlement, Reconciliation & Revenue | Settlement model: net vs gross | 2 | Add net_settlement_amount and merchant_fee_total columns to settlement_batch | The settlement_batch table (columns: id, scheme_id, file_type, direction, settlement_date, window, status, transaction_count, total_amount, total_amount_ccy, file_checksum, transmitted_at, received_at, reconciled_at, error_detail) needs two additional financial columns to support the net vs gross distinction in ZP0061/ZP0063 file generation. For NET batches: net_settlement_amount = sum(target_payout) - sum(merchant_fee_total) per merchant; for GROSS batches: net_settlement_amount = sum(target_payout) (no fee deduction). merchant_fee_total is the total fee deducted (domestic only; zero for gross). Both are in total_amount_ccy (KRW for ZeroPay). | • Create Flyway migration V7_1_002__add_settlement_financial_cols.sql • Add: ALTER TABLE settlement_batch ADD COLUMN net_settlement_amount DECIMAL(20,4) • Add: ALTER TABLE settlement_batch ADD COLUMN merchant_fee_total DECIMAL(20,4) NOT NULL DEFAULT 0 • Add: ALTER TABLE settlement_batch ADD COLUMN settlement_type CHAR(1) CHECK (settlement_type IN ('N','G')) • Apply and verify migration on dev DB | Flyway migration file V7_1_002__add_settlement_financial_cols.sql | • Migration applies cleanly; existing settlement_batch rows have merchant_fee_total=0 and settlement_type=NULL by default • net_settlement_amount can be NULL (set when batch is generated) and accepts DECIMAL(20,4) • merchant_fee_total is NOT NULL and defaults to 0 • settlement_type CHECK constraint rejects values other than 'N', 'G', or NULL • Column comments or migration notes clarify that merchant_fee_total is 0 for gross batches | 25 | 7.1-T01 | BE | RATE-04, SCH-06
7.1-T03 | settlement-reconciliation | 7.1 | 7. Settlement, Reconciliation & Revenue | Settlement model: net vs gross | 2 | Define SettlementType enum and SettlementClassifier interface | The Settlement Engine must determine whether each transaction uses NET or GROSS settlement before batch file generation. Rule: if partner.type = 'LOCAL' (e.g. GME Remit, KRW settlement, no prefunding), use NET ('N'); if partner.type = 'OVERSEAS' (e.g. SendMN, T-Bank, USD prefunding), use GROSS ('G'). This must be config-driven (no hardcoded partner names). The partner table has a type column (VARCHAR(10), values LOCAL or OVERSEAS). Create a SettlementType enum (NET, GROSS) and a SettlementClassifier interface with one method: SettlementType classify(Partner partner). | • Create enum SettlementType { NET, GROSS } in package com.gmepayplus.settlement.model • Create interface SettlementClassifier with method SettlementType classify(Partner partner) • Create class PartnerTypeSettlementClassifier implementing SettlementClassifier: returns NET if partner.getType() == PartnerType.LOCAL, GROSS if OVERSEAS, throws IllegalArgumentException otherwise • Register PartnerTypeSettlementClassifier as a Spring bean • Write a unit test PartnerTypeSettlementClassifierTest covering LOCAL -> NET, OVERSEAS -> GROSS, null partner type -> exception | SettlementType.java, SettlementClassifier.java, PartnerTypeSettlementClassifier.java, PartnerTypeSettlementClassifierTest.java | • PartnerTypeSettlementClassifier.classify(partnerWithType(LOCAL)) returns SettlementType.NET • PartnerTypeSettlementClassifier.classify(partnerWithType(OVERSEAS)) returns SettlementType.GROSS • PartnerTypeSettlementClassifier.classify(partner with null type) throws IllegalArgumentException with a descriptive message • No partner names (GME Remit, SendMN, T-Bank) are hardcoded in the classifier • Spring context loads with PartnerTypeSettlementClassifier as the SettlementClassifier bean | 30 | 7.1-T01, 7.1-T02 | BE | RATE-04, SCH-06
7.1-T04 | settlement-reconciliation | 7.1 | 7. Settlement, Reconciliation & Revenue | Settlement model: net vs gross | 2 | Set settlement_type on transaction at commit time | When the Transaction Orchestrator commits a transaction (state -> APPROVED, rate-lock step), it must record the settlement_type on the transaction row. The classifier rule (7.1-T03): LOCAL partner -> 'N', OVERSEAS partner -> 'G'. The transaction table column settlement_type is CHAR(1) (migration 7.1-T01). This must happen inside the same DB transaction as the rate-lock step to ensure atomicity. The TransactionOrchestrator service has a commitTransaction(txnRef) method that currently copies rate_quote fields to the transaction row. | • Inject SettlementClassifier into TransactionOrchestrator • In commitTransaction(), after loading the partner, call settlementClassifier.classify(partner) to obtain SettlementType • Set transaction.setSettlementType(settlementType.getCode()) where getCode() returns 'N' or 'G' • Ensure the settlement_type update is part of the existing JPA save/update call inside the commit DB transaction • Add integration test: commit a LOCAL-partner transaction, assert settlement_type='N'; commit an OVERSEAS-partner transaction, assert settlement_type='G' | Updated TransactionOrchestrator.commitTransaction() with settlement_type assignment; integration test TransactionCommitSettlementTypeIT.java | • After committing a LOCAL-partner (GME Remit type) transaction, SELECT settlement_type FROM transaction WHERE txn_ref=X returns 'N' • After committing an OVERSEAS-partner (SendMN type) transaction, SELECT settlement_type FROM transaction WHERE txn_ref=X returns 'G' • settlement_type is set atomically with the rate-lock: if the commit DB transaction rolls back, settlement_type is not persisted either • A transaction with settlement_type already set is not overwritten on a duplicate idempotent commit request • Existing commitTransaction() tests still pass without modification | 45 | 7.1-T03 | BE | RATE-04, SCH-06
7.1-T05 | settlement-reconciliation | 7.1 | 7. Settlement, Reconciliation & Revenue | Settlement model: net vs gross | 2 | Implement NetSettlementAmountCalculator for domestic net settlement | For NET settlement (domestic, LOCAL partners, settlement_type='N'), the Settlement Engine must compute per-merchant batch totals: gross_txn_amount = SUM(target_payout KRW) for approved transactions in the settlement window; merchant_fee_total = SUM(merchant_fee_krw) for those transactions where merchant_fee is applicable (fee rate from scheme's merchant_fee_table, by merchant_type: GENERAL 0.80%-2.00%, FRANCHISE varies); net_settlement_amount = gross_txn_amount - merchant_fee_total. The net_settlement_amount is what GME remits to ZeroPay so ZeroPay can credit the merchant. For domestic transactions, GME retains the service_charge (KRW 500 per transaction, held separately in service_charge field on the transaction row) and the 70% fee share is a monthly aggregate from ZeroPay -- it does NOT affect the per-transaction net amount. | • Create class NetSettlementAmountCalculator in package com.gmepayplus.settlement.calculator • Implement method NetSettlementSummary calculate(List<Transaction> transactions, MerchantFeeTable feeTable) • For each transaction: look up merchant fee rate by merchant.merchant_type from feeTable; compute merchant_fee_krw = ROUND(target_payout * fee_rate, 0) (KRW has 0 decimal places); accumulate gross_txn_amount, merchant_fee_total, net_settlement_amount • Return NetSettlementSummary {merchantId, settlementDate, grossTxnCount, grossTxnAmount, merchantFeeTotal, netSettlementAmount, settlementType='N'} • Validate that all transactions have settlement_type='N' and status='APPROVED'; throw if any are GROSS or non-APPROVED | NetSettlementAmountCalculator.java, NetSettlementSummary.java, NetSettlementAmountCalculatorTest.java | • Given 2 transactions for merchant M1 with target_payout 15000 KRW and 20000 KRW, fee_rate=0.008 (0.8%): gross_txn_amount=35000, merchant_fee_total=ROUND(35000*0.008,0)=280, net_settlement_amount=34720 • Given 0 transactions for a merchant, calculate() returns grossTxnCount=0, grossTxnAmount=0, net_settlement_amount=0 without error • Given a transaction with settlement_type='G' in the input list, calculate() throws IllegalArgumentException • KRW amounts are rounded to 0 decimal places using HALF_UP rounding • merchant_fee_total for a FRANCHISE merchant uses the franchise fee rate, not the GENERAL rate | 45 | 7.1-T03 | BE | RATE-04, SCH-06
7.1-T06 | settlement-reconciliation | 7.1 | 7. Settlement, Reconciliation & Revenue | Settlement model: net vs gross | 2 | Implement GrossSettlementAmountCalculator for international gross settlement | For GROSS settlement (international, OVERSEAS partners, settlement_type='G'): GME remits the FULL target_payout KRW amount to ZeroPay. There is no merchant fee deduction from the settlement amount (GME invoices the merchant separately monthly). ZP0061 field mapping for gross: gross_txn_amount = SUM(target_payout KRW), merchant_fee_total = 0, net_settlement_amount = gross_txn_amount, settlement_type = 'G'. The 0.21% ZeroPay share of the international merchant fee is settled monthly via the tax_invoice cycle, not per transaction. GME retains collection_margin_usd + payout_margin_usd (FX margin) and service_charge from the USD prefunding deduction, which is already done at payment time -- these do not affect the gross settlement amount sent to ZeroPay. | • Create class GrossSettlementAmountCalculator in package com.gmepayplus.settlement.calculator • Implement method GrossSettlementSummary calculate(List<Transaction> transactions) • For each transaction: accumulate gross_txn_count and gross_txn_amount (= SUM of target_payout KRW) • Set merchant_fee_total=0 and net_settlement_amount=gross_txn_amount for every merchant group • Return GrossSettlementSummary {merchantId, settlementDate, grossTxnCount, grossTxnAmount, merchantFeeTotal=0, netSettlementAmount=grossTxnAmount, settlementType='G'} • Validate all transactions have settlement_type='G' and status='APPROVED' | GrossSettlementAmountCalculator.java, GrossSettlementSummary.java, GrossSettlementAmountCalculatorTest.java | • Given 3 OVERSEAS transactions for merchant M2 with target_payout 50000, 30000, 20000 KRW: gross_txn_amount=100000, merchant_fee_total=0, net_settlement_amount=100000 • service_charge and FX margin fields (collection_margin_usd, payout_margin_usd) from the transaction row are NOT included in or subtracted from gross_txn_amount • Given a transaction with settlement_type='N' in the input list, calculate() throws IllegalArgumentException • Given 0 transactions, calculate() returns grossTxnCount=0, all amounts 0 • net_settlement_amount == gross_txn_amount for every output record (no fee deduction) | 35 | 7.1-T03 | BE | RATE-04, SCH-06
7.1-T07 | settlement-reconciliation | 7.1 | 7. Settlement, Reconciliation & Revenue | Settlement model: net vs gross | 2 | Implement SettlementWindowQueryService to select transactions for a batch window | The Settlement Engine must query the correct set of APPROVED transactions for each ZP0061 (morning, deadline ~05:00 KST) and ZP0063 (afternoon, deadline ~14:00 KST) batch. Morning window scope: all transactions with status=APPROVED AND settlement_batch_id IS NULL AND completed_at < cutoff_morning (configurable, default 04:30 KST on settlement_date). Afternoon window scope: same filter but completed_at < cutoff_afternoon (default 13:30 KST) AND NOT already in morning batch. The transaction table has: status, settlement_batch_id (null = unbatched), committed_at, completed_at, settlement_type. Query must lock selected rows (SELECT FOR UPDATE SKIP LOCKED) to prevent concurrent batch runs from double-selecting. Batch jobs are idempotent: if settlement_batch_id is already set for a transaction, it is excluded. | • Create SettlementWindowQueryService in package com.gmepayplus.settlement.service • Implement List<Transaction> queryForWindow(LocalDate settlementDate, String window, OffsetDateTime cutoff) using JPA/JPQL with FOR UPDATE SKIP LOCKED • Filter: status = 'APPROVED', settlement_batch_id IS NULL, completed_at < cutoff, scheme_id matches batch scheme • Add method selectAndLockForBatch(Long batchId, List<Long> txnIds) that sets settlement_batch_id = batchId atomically • Add configurable cutoff times: settlement.morning-cutoff (default 04:30 KST), settlement.afternoon-cutoff (default 13:30 KST) in application.yml • Write unit test with mock transactions covering: empty result, mixed status exclusion, already-batched exclusion | SettlementWindowQueryService.java with query and lock methods; application.yml cutoff config; SettlementWindowQueryServiceTest.java | • A transaction with status=APPROVED, settlement_batch_id=NULL, completed_at=03:00 KST is returned for the morning window with cutoff 04:30 KST • A transaction with status=APPROVED, settlement_batch_id=NULL, completed_at=05:00 KST is NOT returned for the morning window (after cutoff) • A transaction with settlement_batch_id already set is excluded regardless of status • A transaction with status=UNCERTAIN is not returned • selectAndLockForBatch() sets settlement_batch_id on all supplied txn IDs in a single UPDATE statement | 50 | 7.1-T01, 7.1-T02 | BE | RATE-04, SCH-06
7.1-T08 | settlement-reconciliation | 7.1 | 7. Settlement, Reconciliation & Revenue | Settlement model: net vs gross | 2 | Implement SettlementBatchFactory to create settlement_batch records | Before generating any ZP006x file, the Settlement Engine must create a settlement_batch row in the DB to track the batch lifecycle. settlement_batch columns: id (PK), scheme_id, file_type (e.g. 'ZP0061'), direction ('GME_TO_ZP'), settlement_date (DATE, KST), window ('MORNING' or 'AFTERNOON' or 'DETAIL'), status (PENDING -> GENERATED -> TRANSMITTED -> RECONCILED ¦ ERROR), transaction_count, total_amount, total_amount_ccy ('KRW'), net_settlement_amount, merchant_fee_total, settlement_type ('N' or 'G'), file_checksum (SHA-256, set after file generation), transmitted_at, received_at, reconciled_at, error_detail. The factory must enforce idempotency: if a batch for (scheme_id, file_type, settlement_date, window) already exists with status != ERROR, return the existing record rather than creating a duplicate. | • Create SettlementBatchFactory in package com.gmepayplus.settlement.service • Implement SettlementBatch createOrGet(Long schemeId, String fileType, LocalDate settlementDate, String window, SettlementType settlementType) • Inside createOrGet: query for existing batch with matching (scheme_id, file_type, settlement_date, window) and status NOT IN ('ERROR'); if found, return it; else create new with status=PENDING • Set total_amount_ccy='KRW' for ZeroPay batches • Throw DuplicateBatchException if batch with same key exists in GENERATED or later status (do not overwrite) • Write unit test covering idempotent create, retrieval of existing, and rejection of duplicate in non-ERROR state | SettlementBatchFactory.java, DuplicateBatchException.java, SettlementBatchFactoryTest.java | • Calling createOrGet twice with same parameters and first batch in PENDING state returns the same batch id both times • Calling createOrGet when a batch with same key is in GENERATED status returns that existing batch without creating a duplicate row • Calling createOrGet when a batch with same key is in ERROR status creates a new batch row (retry allowed) • Newly created batch has status=PENDING, transaction_count=0, total_amount=0, settlement_type set correctly • settlement_date is always interpreted as KST (Asia/Seoul timezone) | 40 | 7.1-T02, 7.1-T03 | BE | RATE-04, SCH-06
7.1-T09 | settlement-reconciliation | 7.1 | 7. Settlement, Reconciliation & Revenue | Settlement model: net vs gross | 2 | Implement ZP0061MorningSettlementRequestBuilder (net settlement) | ZP0061 is the morning settlement request file (GME -> ZeroPay, deadline ~05:00 KST). For NET domestic transactions (settlement_type='N'), the per-merchant record layout is: merchant_id CHAR(10), settlement_date DATE(8) YYYYMMDD, gross_txn_count NUM(6), gross_txn_amount NUM(14) KRW, refund_count NUM(6), refund_amount NUM(14) KRW, merchant_fee_total NUM(12) KRW (fee deducted from merchant), net_settlement_amount NUM(14) KRW (= gross_txn_amount - merchant_fee_total + refunds), settlement_type CHAR(1) = 'N'. net_settlement_amount is what ZeroPay credits to the merchant's KRW bank account. File has a header row (batch date, GME sender ID, record count) and trailer (total net settlement KRW). Use the NetSettlementAmountCalculator (7.1-T05) output to populate these fields. KRW values must be integers (0 decimal places, HALF_UP rounding). | • Create ZP0061RecordBuilder in package com.gmepayplus.settlement.file • Implement byte[] build(SettlementBatch batch, List<NetSettlementSummary> summaries, List<RefundSummary> refundSummaries) method • Group summaries by merchant_id; merge payment and refund data per merchant • Format each field to the exact column width (fixed-width or delimiter per ZeroPay spec); use YYYYMMDD for dates • Compute file header with settlement_date, GME sender ID (from scheme config), merchant record count • Compute trailer with SUM(net_settlement_amount) across all merchant records • Compute SHA-256 of the byte array and return both (or update the batch record's file_checksum) | ZP0061RecordBuilder.java, ZP0061RecordBuilderTest.java | • Given NetSettlementSummary for merchant M1: gross_txn_amount=35000, merchant_fee_total=280, net_settlement_amount=34720; output record has net_settlement_amount=34720 and settlement_type='N' • Trailer total_net_settlement = SUM of all per-merchant net_settlement_amount values • A merchant with 0 transactions is not included in the file • All KRW amounts are integer strings (no decimal point) padded to column width • File header record count matches the number of merchant data records | 55 | 7.1-T05, 7.1-T08 | BE | RATE-04, SCH-06
7.1-T10 | settlement-reconciliation | 7.1 | 7. Settlement, Reconciliation & Revenue | Settlement model: net vs gross | 2 | Implement ZP0061MorningSettlementRequestBuilder (gross settlement) | ZP0061 also covers GROSS international transactions (settlement_type='G'). Per-merchant record layout is identical to the net case but: merchant_fee_total = 0, net_settlement_amount = gross_txn_amount (GME pays full amount), settlement_type = 'G'. ZeroPay credits merchant KRW accounts upon receiving this file. GME has no further merchant crediting responsibility. Use GrossSettlementAmountCalculator (7.1-T06) for computation. The same ZP0061RecordBuilder must support both 'N' and 'G' records in a single batch run if a mixed-type batch is needed, but in practice each batch is partitioned by settlement_type (domestic batch and international batch are separate settlement_batch rows with distinct windows). | • Extend ZP0061RecordBuilder (7.1-T09) to accept GrossSettlementSummary as well as NetSettlementSummary via a common SettlementSummary interface • Implement the settlement_type='G' record path: merchant_fee_total=0, net_settlement_amount=gross_txn_amount • Add a parameter to ZP0061RecordBuilder.build() specifying the overall batch settlement_type to set the per-file settlement_type marker • Write unit test ZP0061GrossBuilderTest covering gross merchant records • Test that a batch with only GROSS transactions produces a file with merchant_fee_total=0 for every record | Updated ZP0061RecordBuilder.java with gross path support; ZP0061GrossBuilderTest.java | • Given GrossSettlementSummary for merchant M2: gross_txn_amount=100000; output record has merchant_fee_total=0, net_settlement_amount=100000, settlement_type='G' • Trailer for a gross-only batch equals SUM(gross_txn_amount) for all merchants • Mixed-type batch (N and G records in same file) produces distinct settlement_type values per record • service_charge values from individual transactions do not appear in any ZP0061 field • A GROSS transaction with FX margin fields (collection_margin_usd non-zero) still produces net_settlement_amount = target_payout (FX margin not subtracted) | 40 | 7.1-T06, 7.1-T09 | BE | RATE-04, SCH-06
7.1-T11 | settlement-reconciliation | 7.1 | 7. Settlement, Reconciliation & Revenue | Settlement model: net vs gross | 2 | Implement ZP0063AfternoonSettlementRequestBuilder | ZP0063 is the supplementary afternoon settlement request (GME -> ZeroPay, deadline ~14:00 KST). It covers transactions approved after the ZP0061 cutoff (default 04:30 KST) up to the afternoon cutoff (default 13:30 KST) for the same settlement_date. File format is identical to ZP0061 (same record layout, settlement_type 'N' or 'G' per record). The batch window is 'AFTERNOON'. A transaction already in a ZP0061 batch (settlement_batch_id set to morning batch) is excluded from ZP0063. The same NetSettlementAmountCalculator / GrossSettlementAmountCalculator logic applies. Batch must be idempotent (7.1-T08). | • Create ZP0063RecordBuilder in package com.gmepayplus.settlement.file, delegating to the shared ZP0061RecordBuilder logic (extract common builder or reuse directly) • Implement build(SettlementBatch batch, List<SettlementSummary> summaries) using the same record layout • Set file_type='ZP0063' and window='AFTERNOON' in the settlement_batch row • Use SettlementWindowQueryService (7.1-T07) with the afternoon cutoff to select unbatched transactions • Write unit test verifying that transactions already assigned to the morning batch are excluded | ZP0063RecordBuilder.java, ZP0063RecordBuilderTest.java | • Transactions with settlement_batch_id pointing to the morning ZP0061 batch are absent from the ZP0063 file • An OVERSEAS transaction approved at 12:00 KST (after 04:30 cutoff) appears in ZP0063 with settlement_type='G' • An OVERSEAS transaction approved at 03:00 KST (before 04:30 morning cutoff) does NOT appear in ZP0063 if already batched • Empty afternoon window produces a valid file with header/trailer and 0 merchant records • file_type in settlement_batch row is 'ZP0063' not 'ZP0061' | 40 | 7.1-T07, 7.1-T09, 7.1-T10 | BE | RATE-04, SCH-06
7.1-T12 | settlement-reconciliation | 7.1 | 7. Settlement, Reconciliation & Revenue | Settlement model: net vs gross | 2 | Implement ZP0065PaymentDetailFileBuilder | ZP0065 is the payment detail file (GME -> ZeroPay, deadline ~22:00 KST). It provides line-item transaction detail underlying the ZP0061/ZP0063 totals. Per-record layout: merchant_id CHAR(10), zeropay_txn_ref CHAR(20) (transaction.scheme_ref), txn_date DATE(8) YYYYMMDD, txn_time TIME(6) HHMMSS, payout_amount_krw NUM(12) (= target_payout), merchant_fee_amt NUM(12) (fee for domestic; 0 for international), van_fee_amt NUM(10), partner_type CHAR(1) (D=domestic/NET, I=international/GROSS), settlement_batch_ref CHAR(20) (links back to ZP0061 or ZP0063 batch reference). Scope: all transactions assigned to ZP0061 or ZP0063 batches for the settlement_date. KRW = 0 decimal places. | • Create ZP0065RecordBuilder in package com.gmepayplus.settlement.file • Implement byte[] build(LocalDate settlementDate, List<Transaction> transactions) grouped by settlement_batch_ref • For each transaction: map settlement_type='N' -> partner_type='D', settlement_type='G' -> partner_type='I' • Compute merchant_fee_amt per transaction (domestic: target_payout * fee_rate rounded to KRW 0dp; gross: 0) • Populate settlement_batch_ref from the linked settlement_batch record (batch reference field or batch id as padded string) • Write ZP0065RecordBuilderTest with both D and I records | ZP0065RecordBuilder.java, ZP0065RecordBuilderTest.java | • A domestic transaction (settlement_type='N') produces a record with partner_type='D' and merchant_fee_amt > 0 • An international transaction (settlement_type='G') produces a record with partner_type='I' and merchant_fee_amt=0 • settlement_batch_ref in the ZP0065 record matches the batch reference of the ZP0061 or ZP0063 batch that contains the transaction • Total payout_amount_krw across all ZP0065 records for a settlement_date equals SUM(target_payout) for the corresponding ZP0061/ZP0063 totals • payout_amount_krw field is an integer string with no decimal separator | 50 | 7.1-T09, 7.1-T11 | BE | RATE-04, SCH-06
7.1-T13 | settlement-reconciliation | 7.1 | 7. Settlement, Reconciliation & Revenue | Settlement model: net vs gross | 2 | Implement ZP0066RefundDetailFileBuilder | ZP0066 is the refund detail file (GME -> ZeroPay, deadline ~22:00 KST). Layout mirrors ZP0065 with refund-specific fields: merchant_id CHAR(10), original_zeropay_txn_ref CHAR(20) (the original payment transaction scheme_ref), refund_date DATE(8), refund_amount_krw NUM(12) (negative of original target_payout for full refund, or partial amount), merchant_fee_adj_amt NUM(12) (fee adjustment for domestic refund; 0 for international gross), settlement_batch_ref CHAR(20) (links to ZP0063 or ZP0061 batch containing the refund). Source: refund table rows with status=APPROVED and settlement_date matching the current date. The refund table has columns: id, txn_id (FK -> transaction), refund_amount, refund_ccy, original_zeropay_txn_ref (or derivable from txn.scheme_ref), status, settlement_batch_id. | • Create ZP0066RecordBuilder in package com.gmepayplus.settlement.file • Implement byte[] build(LocalDate settlementDate, List<Refund> refunds) joining to the parent transaction for settlement_type • For domestic refunds: compute merchant_fee_adj_amt = ROUND(refund_amount * fee_rate, 0) (negative, as a fee credit) • For international refunds: merchant_fee_adj_amt = 0 • Populate settlement_batch_ref from the refund's settlement_batch link • Write ZP0066RecordBuilderTest with one domestic refund and one international refund | ZP0066RecordBuilder.java, ZP0066RecordBuilderTest.java | • A domestic refund of 15000 KRW with fee_rate=0.008 produces merchant_fee_adj_amt=120 (credit back) • An international refund produces merchant_fee_adj_amt=0 • original_zeropay_txn_ref in ZP0066 matches scheme_ref of the original payment transaction • A refund with status != APPROVED is excluded from the file • File trailer contains SUM(refund_amount_krw) across all records | 45 | 7.1-T12 | BE | RATE-04, SCH-06
7.1-T14 | settlement-reconciliation | 7.1 | 7. Settlement, Reconciliation & Revenue | Settlement model: net vs gross | 2 | Implement SettlementBatchJobService: ZP0061 morning batch orchestrator | The Settlement Engine cron job for ZP0061 runs at ~02:00 KST (after ZP0011/ZP0012 are confirmed). Orchestration steps: (1) Verify ZP0011 was successfully transmitted and ZP0012 received with no unresolved exceptions; (2) Query morning-window transactions via SettlementWindowQueryService; (3) Split by settlement_type (N/G); (4) Compute summaries using NetSettlementAmountCalculator and GrossSettlementAmountCalculator; (5) Build ZP0061 file via ZP0061RecordBuilder; (6) Create/update settlement_batch record via SettlementBatchFactory; (7) Set settlement_batch_id on all selected transactions; (8) Transmit file via SFTP; (9) Update batch status to TRANSMITTED. All steps run inside a DB transaction except SFTP transmission. Idempotency: if batch already in GENERATED or TRANSMITTED state, skip file generation and re-attempt SFTP only. | • Create SettlementBatchJobService in package com.gmepayplus.settlement.job • Implement runZP0061Morning(LocalDate settlementDate) method guarded by @DistributedLock (Redis SETNX key = zp0061:{settlementDate}) • Add prerequisite check: ZP0011 batch for same date must have status=TRANSMITTED; ZP0012 must have status=RECEIVED with no UNRESOLVED reconciliation_items; if not met, abort with logged BATCH_PREREQ_FAILED • Execute query, calculate, build, update DB, transmit in order; wrap DB steps in @Transactional • On SFTP failure: retry 3 times with 5-minute delay; after 3 failures set batch status=ERROR and publish BATCH_SFTP_FAILED alert • On success: set status=TRANSMITTED, transmitted_at=NOW() | SettlementBatchJobService.java (ZP0061 morning method) with distributed lock and prerequisite guard | • Running runZP0061Morning() twice concurrently: second invocation obtains the Redis lock and finds batch in GENERATED state, skips file generation, re-attempts SFTP • If ZP0012 has unresolved reconciliation_items, runZP0061Morning() logs BATCH_PREREQ_FAILED and returns without creating a batch row • After successful run: settlement_batch.status='TRANSMITTED', all morning-window transactions have settlement_batch_id set, transaction_count equals the number of processed transactions • SFTP failure on first attempt triggers retry; after 3 failures batch.status='ERROR' and an ops alert is published • settlement_batch total_amount = SUM(target_payout KRW) of all included transactions | 60 | 7.1-T07, 7.1-T08, 7.1-T09, 7.1-T10 | BE | RATE-04, SCH-06
7.1-T15 | settlement-reconciliation | 7.1 | 7. Settlement, Reconciliation & Revenue | Settlement model: net vs gross | 2 | Implement SettlementBatchJobService: ZP0063 afternoon batch orchestrator | The ZP0063 afternoon settlement batch runs at ~14:00 KST. Prerequisite: ZP0061 batch for the same settlement_date must be in TRANSMITTED status (morning cycle complete). Logic mirrors ZP0061 but uses the afternoon window (completed_at between morning cutoff and 13:30 KST) and file_type='ZP0063'. If no transactions fall in the afternoon window, a file with zero records is still generated and transmitted (ZeroPay requires it). Distributed lock key = zp0063:{settlementDate}. | • Implement runZP0063Afternoon(LocalDate settlementDate) in SettlementBatchJobService • Add prerequisite check: ZP0061 morning batch must have status=TRANSMITTED • Query afternoon-window transactions using SettlementWindowQueryService with afternoon cutoff • Allow zero-transaction case: generate empty ZP0063 file with valid header/trailer • Follow same DB-then-SFTP pattern as ZP0061, with 3-retry SFTP logic • Write integration test covering zero-transaction afternoon case and normal case | SettlementBatchJobService.runZP0063Afternoon() method; integration test ZP0063AfternoonJobIT.java | • ZP0063 runs only after ZP0061 morning batch is TRANSMITTED; if morning batch status=PENDING the job aborts • A zero-transaction afternoon produces a valid ZP0063 file (header + trailer, 0 merchant records) and batch status=TRANSMITTED • An afternoon transaction (completed_at=12:00 KST for settlement_date) appears in ZP0063 but not ZP0061 • After ZP0063 run, all afternoon-window transactions have settlement_batch_id pointing to the ZP0063 batch row • Distributed lock prevents concurrent ZP0063 runs for the same settlement_date | 50 | 7.1-T11, 7.1-T14 | BE | RATE-04, SCH-06
7.1-T16 | settlement-reconciliation | 7.1 | 7. Settlement, Reconciliation & Revenue | Settlement model: net vs gross | 2 | Implement SettlementBatchJobService: ZP0065/ZP0066 detail batch orchestrator | ZP0065 (payment detail) and ZP0066 (refund detail) run at ~22:00 KST. They cover all transactions and refunds for the settlement_date that are linked to ZP0061 or ZP0063 batches. Prerequisite: both ZP0061 and ZP0063 must be in TRANSMITTED status for the date. ZP0065 and ZP0066 are generated independently (two separate settlement_batch rows, file_types='ZP0065' and 'ZP0066'). If there are no refunds, ZP0066 is still generated as an empty file. | • Implement runZP0065Detail(LocalDate settlementDate) and runZP0066RefundDetail(LocalDate settlementDate) in SettlementBatchJobService • For ZP0065: query all transactions where settlement_batch_id IN (ZP0061 batch id, ZP0063 batch id) for the date • For ZP0066: query refund rows with settlement_date = settlementDate and associated to batched transactions • Build files via ZP0065RecordBuilder and ZP0066RecordBuilder; transmit via SFTP • Distributed lock keys: zp0065:{settlementDate} and zp0066:{settlementDate} • Write unit test verifying that a transaction not linked to any batch is absent from ZP0065 | SettlementBatchJobService.runZP0065Detail() and runZP0066RefundDetail() methods | • ZP0065 run before ZP0061 TRANSMITTED aborts with BATCH_PREREQ_FAILED • All transactions with settlement_batch_id pointing to the day's ZP0061 or ZP0063 appear in ZP0065 • A transaction not assigned to any batch is absent from ZP0065 • ZP0066 with no refunds produces an empty-body file (header + trailer) with status=TRANSMITTED • ZP0065 total payout_amount_krw (sum over all records) equals ZP0061 gross_txn_amount + ZP0063 gross_txn_amount for the same date | 50 | 7.1-T12, 7.1-T13, 7.1-T15 | BE | RATE-04, SCH-06
7.1-T17 | settlement-reconciliation | 7.1 | 7. Settlement, Reconciliation & Revenue | Settlement model: net vs gross | 2 | Implement ZP0062 morning settlement result processor | ZP0062 is the morning settlement result file (ZeroPay -> GME, expected ~10:00 KST). It confirms ZeroPay's processing of ZP0061 with per-merchant settlement status and the KRW amount credited. Processing steps: (1) Parse ZP0062 file from SFTP inbound directory; (2) For each merchant record, look up the corresponding ZP0061 batch line; (3) Compare ZP0062 credited_amount to ZP0061 net_settlement_amount; (4) If match: update merchant's ZP0061 record to RECONCILED; (5) If mismatch or missing: create reconciliation_item with match_status='DISCREPANCY' or 'MISSING_SCHEME'; (6) Update settlement_batch status to RECEIVED (or RECONCILED if all records match). reconciliation_item table: batch_id, txn_ref, scheme_ref, match_status, gme_amount, scheme_amount, discrepancy_amount, ccy, resolution_status. | • Create ZP0062ResultProcessor in package com.gmepayplus.settlement.reconciliation • Implement process(byte[] fileContent, Long zp0061BatchId) method • Parse fixed-width or delimited file; extract merchant_id, credited_amount, status_code • For each record: load merchant's expected net_settlement_amount from batch summary; compare; create reconciliation_item if mismatch • Update settlement_batch.status=RECEIVED; if all records matched set to RECONCILED • If any DISCREPANCY or MISSING_SCHEME: publish alert to ops notification queue and set batch error_detail • Write ZP0062ResultProcessorTest with all-match case, one-discrepancy case, and missing-record case | ZP0062ResultProcessor.java, ZP0062ResultProcessorTest.java | • When all merchants in ZP0062 match ZP0061 net_settlement_amount, settlement_batch.status becomes RECONCILED and no reconciliation_items are created • A merchant in ZP0062 with credited_amount 34720 vs expected 34720 produces match_status=MATCHED • A merchant in ZP0062 with credited_amount 34000 vs expected 34720 produces match_status=DISCREPANCY, discrepancy_amount=720 and an ops alert • A merchant in ZP0061 that is absent from ZP0062 produces match_status=MISSING_SCHEME • Processing ZP0062 twice for the same batch_id is idempotent (no duplicate reconciliation_item rows) | 55 | 7.1-T09, 7.1-T08 | BE | RATE-04, SCH-06
7.1-T18 | settlement-reconciliation | 7.1 | 7. Settlement, Reconciliation & Revenue | Settlement model: net vs gross | 2 | Implement ZP0064 afternoon settlement result processor | ZP0064 (ZeroPay -> GME, expected ~19:00 KST) confirms ZeroPay's processing of ZP0063. Identical logic to ZP0062 (7.1-T17) but applied to the ZP0063 afternoon batch. If the ZP0063 batch had zero transactions (empty file), ZP0064 will also be empty (zero merchant records); this is a valid state and should result in settlement_batch.status=RECONCILED without creating any reconciliation_items. | • Create ZP0064ResultProcessor in package com.gmepayplus.settlement.reconciliation delegating to shared reconciliation logic extracted from ZP0062ResultProcessor • Implement process(byte[] fileContent, Long zp0063BatchId) • Handle the zero-record case: if file has 0 merchant records and ZP0063 also had 0 transactions, set status=RECONCILED immediately • Reuse reconciliation_item creation and alert logic from the shared base • Write ZP0064ResultProcessorTest: zero-record success, one-match, one-discrepancy | ZP0064ResultProcessor.java (with extracted shared reconciliation logic), ZP0064ResultProcessorTest.java | • ZP0064 with 0 records matching a ZP0063 batch with 0 transactions sets ZP0063 batch status=RECONCILED • ZP0064 with a merchant amount mismatch creates a reconciliation_item with match_status=DISCREPANCY and an ops alert • Processing ZP0064 before ZP0063 batch exists raises BatchNotFoundException • Shared reconciliation logic is in one class (not duplicated between ZP0062 and ZP0064 processors) • settlement_batch.reconciled_at is set when status transitions to RECONCILED | 40 | 7.1-T17 | BE | RATE-04, SCH-06
7.1-T19 | settlement-reconciliation | 7.1 | 7. Settlement, Reconciliation & Revenue | Settlement model: net vs gross | 2 | Implement daily revenue record creation for domestic NET transactions | At settlement_batch confirmation for NET domestic transactions, the Settlement Engine must create a revenue_record per transaction. revenue_record columns: id, txn_id, partner_id, scheme_id, revenue_date (settlement_date), fx_margin_usd (= collection_margin_usd + payout_margin_usd from transaction -- this is 0 for same-currency short-circuit domestic transactions), service_charge_amount (transaction.service_charge e.g. KRW 500), service_charge_ccy ('KRW'), fee_share_pct (70.0 for ZeroPay), estimated_fee_share_usd (NULL -- not determinable per transaction; populated monthly from ZeroPay fee share statement). For domestic LOCAL-partner transactions: fx_margin_usd=0 (same-currency short-circuit, no USD pool). service_charge_amount is the only real-time revenue per transaction. | • Create RevenueRecordService in package com.gmepayplus.settlement.revenue • Implement void createDomesticRevenueRecord(Transaction txn, LocalDate settlementDate) method • Assert txn.settlement_type='N'; set fx_margin_usd=0 (domestic never has FX margin); set service_charge_amount=txn.service_charge, service_charge_ccy=txn.collection_ccy • Set fee_share_pct=70.0 (ZeroPay), estimated_fee_share_usd=NULL • Persist revenue_record; throw if a record for txn_id already exists (idempotency guard) • Write RevenueRecordServiceTest with a domestic transaction (target_payout=15000 KRW, service_charge=500 KRW) | RevenueRecordService.java (domestic method), RevenueRecordServiceTest.java | • For a domestic transaction with service_charge=500 KRW, revenue_record.service_charge_amount=500, fx_margin_usd=0 • revenue_record.fee_share_pct=70.0 (ZeroPay config), estimated_fee_share_usd=NULL • Calling createDomesticRevenueRecord twice for the same txn_id throws DuplicateRevenueRecordException (idempotency) • revenue_date = settlementDate, not transaction.committed_at • txn.is_same_ccy_shortcircuit=true does not cause an error; fx_margin_usd=0 is still set correctly | 40 | 7.1-T04, 7.1-T08 | BE | RATE-04, SCH-06
7.1-T20 | settlement-reconciliation | 7.1 | 7. Settlement, Reconciliation & Revenue | Settlement model: net vs gross | 2 | Implement revenue record creation for international GROSS transactions | For GROSS international transactions (settlement_type='G', OVERSEAS partner), revenue is: fx_margin_usd = collection_margin_usd + payout_margin_usd (from the locked transaction fields, e.g. 1.0204 + 1.0204 = 2.0408 USD for the worked example: target_payout=100 USD, m_a=0.01, m_b=0.01); service_charge_amount = transaction.service_charge in settle_a_ccy (e.g. KRW 500 or USD 0.50); fee_share_pct=70.0; estimated_fee_share_usd=NULL. Revenue is funded from the OVERSEAS partner's prefunding deduction (collection_usd). Pool identity guarantees: collection_usd - collection_margin_usd - payout_margin_usd = payout_usd_cost (within 0.01 USD tolerance). Note: the 0.21% ZeroPay share of merchant fee is a monthly aggregate settled via tax_invoice, not per-transaction. | • Implement void createInternationalRevenueRecord(Transaction txn, LocalDate settlementDate) in RevenueRecordService • Assert txn.settlement_type='G'; compute fx_margin_usd = txn.collection_margin_usd + txn.payout_margin_usd • Set service_charge_amount=txn.service_charge, service_charge_ccy=txn.service_charge_ccy (settle_a_ccy) • Verify pool identity: ¦txn.collection_usd - txn.collection_margin_usd - txn.payout_margin_usd - txn.payout_usd_cost¦ <= 0.01; if fails, log POOL_IDENTITY_VIOLATION and still persist (alert only, do not block) • Persist revenue_record with idempotency guard • Write test with worked example: collection_usd=102.0408, m_a=0.01, m_b=0.01, service_charge=0.50 USD | RevenueRecordService.java (international method), RevenueRecordServiceTest.java (international cases) | • For transaction with collection_margin_usd=1.0204, payout_margin_usd=1.0204: revenue_record.fx_margin_usd=2.0408 • service_charge_amount=0.50, service_charge_ccy='USD' (or KRW if settle_a is KRW) • Pool identity check: ¦102.0408 - 1.0204 - 1.0204 - 100.0000¦ = 0 -- passes with tolerance 0.01 • A transaction with collection_margin_usd=NULL (same-currency short-circuit) passed to createInternationalRevenueRecord raises AssertionError • Calling createInternationalRevenueRecord twice for same txn_id raises DuplicateRevenueRecordException | 40 | 7.1-T19 | BE | RATE-04, SCH-06
7.1-T21 | settlement-reconciliation | 7.1 | 7. Settlement, Reconciliation & Revenue | Settlement model: net vs gross | 2 | Implement monthly tax_invoice aggregation for international gross settlement | For GROSS international transactions, GME must invoice Korean merchants monthly (last business day of month) for the merchant fee. tax_invoice table: id, merchant_id, invoice_period (first day of invoice month), invoice_ref (unique), total_transaction_amount_krw (SUM of target_payout for the merchant during the period), fee_rate (applicable merchant fee rate from scheme fee table, e.g. 1.70%-2.20% for cross-border), merchant_fee_krw (= total * fee_rate, rounded to integer KRW), vat_krw (= merchant_fee_krw * 0.10, rounded), invoice_amount_krw (= merchant_fee_krw + vat_krw), zeropay_share_krw (= 0.21% of merchant_fee_krw, i.e. merchant_fee_krw * 0.0021, rounded to integer KRW), status ('DRAFT' -> 'ISSUED' -> 'COLLECTED' ¦ 'FAILED'). Only GROSS (settlement_type='G') transactions are included. Domestic NET transactions are excluded. | • Create TaxInvoiceAggregationService in package com.gmepayplus.settlement.invoice • Implement List<TaxInvoice> aggregateForMonth(YearMonth period, Long schemeId) method • Query transactions WHERE settlement_type='G' AND committed_at BETWEEN period.atDay(1) AND period.atEndOfMonth() AND scheme_id=schemeId AND status='APPROVED' • Group by merchant_id; sum target_payout; look up fee_rate by merchant.merchant_type and fee_tier='CROSSBORDER' from scheme fee config • Compute merchant_fee_krw = ROUND(total * fee_rate, 0) HALF_UP; vat_krw = ROUND(merchant_fee_krw * 0.10, 0); invoice_amount_krw = merchant_fee_krw + vat_krw; zeropay_share_krw = ROUND(merchant_fee_krw * 0.0021, 0) • Persist each as TaxInvoice with status='DRAFT'; assign invoice_ref (unique, format: YYYYMM-{merchantId}-{sequence}) | TaxInvoiceAggregationService.java, TaxInvoiceAggregationServiceTest.java | • Given merchant M2 with 3 GROSS transactions totalling 500000 KRW and fee_rate=0.017: merchant_fee_krw=8500, vat_krw=850, invoice_amount_krw=9350, zeropay_share_krw=ROUND(8500*0.0021,0)=18 • A LOCAL-partner (settlement_type='N') transaction is excluded from the aggregation • Running aggregateForMonth() twice for the same period and merchant produces only one DRAFT tax_invoice (idempotency via invoice_period + merchant_id unique key) • All arithmetic uses BigDecimal with HALF_UP rounding; KRW values are integers • zeropay_share_krw = ROUND(8500 * 0.0021, 0) = ROUND(17.85, 0) = 18 | 55 | 7.1-T04, 7.1-T20 | BE | RATE-04, SCH-06
7.1-T22 | settlement-reconciliation | 7.1 | 7. Settlement, Reconciliation & Revenue | Settlement model: net vs gross | 2 | Implement SETTLEMENT_BATCHED transaction event step | The transaction 8-step event trail requires a SETTLEMENT_BATCHED event (step 6) when a transaction is included in a settlement batch. The transaction_event table has: id, txn_id (FK -> transaction), step (1-8 INT), event_type (VARCHAR(50)), occurred_at, duration_ms, detail (JSONB). The 8 steps are: (1) RATE_QUOTE_ISSUED, (2) PREFUND_DEDUCTED (OVERSEAS only), (3) SCHEME_SUBMITTED, (4) SCHEME_APPROVED, (5) TRANSACTION_COMMITTED, (6) SETTLEMENT_BATCHED, (7) WEBHOOK_QUEUED, (8) WEBHOOK_DELIVERED. Step 6 detail payload: {batch_id, file_type, settlement_date, settlement_type}. | • Create or extend TransactionEventService in package com.gmepayplus.settlement.audit • Implement void recordSettlementBatched(Long txnId, Long batchId, String fileType, LocalDate settlementDate, String settlementType) • Persist transaction_event with step=6, event_type='SETTLEMENT_BATCHED', detail={batch_id: X, file_type: 'ZP0061', settlement_date: 'YYYY-MM-DD', settlement_type: 'N'¦'G'} • Call this method inside selectAndLockForBatch() (7.1-T07) immediately after settlement_batch_id is set on the transaction • Write unit test verifying the event is persisted with correct fields | TransactionEventService.recordSettlementBatched() method; updated SettlementWindowQueryService call site; TransactionEventServiceTest (step 6 cases) | • After a transaction is assigned to a ZP0061 batch, a transaction_event row exists with step=6, event_type='SETTLEMENT_BATCHED', detail containing batch_id and file_type='ZP0061' • settlement_type in the event detail is 'N' for a domestic transaction and 'G' for an international one • Calling recordSettlementBatched twice for the same txn_id raises DuplicateEventException (one SETTLEMENT_BATCHED per transaction) • occurred_at is set to the time selectAndLockForBatch() executes (not the batch transmission time) • A transaction without a SETTLEMENT_BATCHED event can be identified by querying for txn_id absent from transaction_event WHERE event_type='SETTLEMENT_BATCHED' | 35 | 7.1-T07, 7.1-T04 | BE | RATE-04, SCH-06
7.1-T23 | settlement-reconciliation | 7.1 | 7. Settlement, Reconciliation & Revenue | Settlement model: net vs gross | 2 | Implement daily pool identity background reconciliation job | After settlement batches run, a background reconciliation job must verify the USD pool identity for ALL committed cross-border transactions: collection_usd - collection_margin_usd - payout_margin_usd = payout_usd_cost (tolerance 0.01 USD). This is specified in spec section 13.1: violations should trigger an ops alert. Run daily (e.g. 23:00 KST). Scope: transactions with is_same_ccy_shortcircuit=false AND status='APPROVED' AND reconciliation not yet run (track via a reconciled_at column or a separate flag). Domestic same-currency transactions (is_same_ccy_shortcircuit=true) are skipped. The job must not block or affect settlement batch generation. | • Create PoolIdentityReconciliationJob in package com.gmepayplus.settlement.reconciliation • Implement void run(LocalDate forDate) querying all approved cross-border transactions committed on forDate • For each transaction: compute delta = ¦collection_usd - collection_margin_usd - payout_margin_usd - payout_usd_cost¦ • If delta > 0.01: create reconciliation_item with match_status='DISCREPANCY', batch_id=NULL, txn_ref=txn.txn_ref, gme_amount=collection_usd, scheme_amount=payout_usd_cost+margins, discrepancy_amount=delta, ccy='USD' • Publish POOL_IDENTITY_VIOLATION alert if any violations found • Write PoolIdentityReconciliationJobTest with one passing and one failing (delta=0.02) transaction | PoolIdentityReconciliationJob.java, PoolIdentityReconciliationJobTest.java | • Transaction with collection_usd=102.0408, collection_margin_usd=1.0204, payout_margin_usd=1.0204, payout_usd_cost=100.0000: delta=0 -- no violation created • Transaction with delta=0.02 produces a reconciliation_item with match_status='DISCREPANCY', discrepancy_amount=0.02, ccy='USD' and triggers an ops alert • Domestic transactions (is_same_ccy_shortcircuit=true) are not processed (skipped in query) • Running the job twice for the same date does not create duplicate reconciliation_items (idempotency by txn_ref + event type) • Job completes without error when no cross-border transactions exist for the date | 45 | 7.1-T20, 7.1-T17 | BE | RATE-04, SCH-06
7.1-T24 | settlement-reconciliation | 7.1 | 7. Settlement, Reconciliation & Revenue | Settlement model: net vs gross | 2 | Implement daily aggregate settlement reconciliation against ZP0062/ZP0064 | Spec section 13.2: daily reconciliation must verify (1) SUM(target_payout) for all batched transactions on the settlement_date matches ZP0065 totals confirmed by ZP0062/ZP0064; (2) SUM(collection_usd) for OVERSEAS partners matches prefunding ledger debit movements; (3) count of transactions in ZP0061/ZP0063 matches internal batched count. This is separate from the ZP0062ResultProcessor per-merchant matching (7.1-T17). Create a DailyAggregateReconciliationJob that runs after ZP0064 is received (~20:00 KST). | • Create DailyAggregateReconciliationJob in package com.gmepayplus.settlement.reconciliation • Implement void run(LocalDate settlementDate) loading ZP0061 and ZP0063 batches for the date • Compare internal SUM(target_payout) for batched transactions vs ZP0062/ZP0064 confirmed totals (from settlement_batch.total_amount after reconciliation) • Compare internal transaction_count vs ZP0061.transaction_count + ZP0063.transaction_count • Compare SUM(collection_usd) for OVERSEAS transactions vs prefunding ledger net debit for the date (prefunding_ledger table debit_amount column) • Create reconciliation_items for any aggregate mismatch; publish alert • Write DailyAggregateReconciliationJobTest with fully-matched scenario and one count-mismatch scenario | DailyAggregateReconciliationJob.java, DailyAggregateReconciliationJobTest.java | • When internal SUM(target_payout)=500000 KRW equals ZP0062/ZP0064 confirmed total=500000 KRW, no reconciliation_item is created • When internal count=10 but ZP0061 + ZP0063 count=9, a DISCREPANCY reconciliation_item is created and alert fired • SUM(collection_usd) for OVERSEAS transactions is compared to prefunding_ledger debit sum; delta > 0.01 USD triggers an alert • Job does not run if ZP0062 or ZP0064 batch is not yet in RECONCILED status (deferred until result files processed) • All comparisons use Decimal/BigDecimal arithmetic to avoid floating-point error | 50 | 7.1-T17, 7.1-T18, 7.1-T23 | BE | RATE-04, SCH-06
7.1-T25 | settlement-reconciliation | 7.1 | 7. Settlement, Reconciliation & Revenue | Settlement model: net vs gross | 2 | Implement settlement cron scheduler configuration | The Settlement Engine requires a cron scheduler to trigger batch jobs at the correct KST times. All times are KST (Asia/Seoul, UTC+9). Schedule: ZP0011/ZP0021 outbound at 02:00 KST; ZP0061 morning at 05:00 KST; ZP0063 afternoon at 14:00 KST; ZP0065/ZP0066 detail at 22:00 KST; daily pool identity reconciliation at 23:00 KST; daily aggregate reconciliation at 20:30 KST. The scheduler must publish events to the settlement.batch_trigger message queue (or call job service directly). All jobs must be idempotent and guarded by distributed locks (Redis). Cron expressions must use the Asia/Seoul timezone zone parameter. | • Create SettlementCronScheduler in package com.gmepayplus.settlement.scheduler using Spring @Scheduled or Quartz • Define cron expressions with zone=Asia/Seoul for each batch window • Each @Scheduled method calls the corresponding SettlementBatchJobService method with LocalDate.now(ZoneId.of('Asia/Seoul')) • Ensure @EnableScheduling is present in the Spring configuration • Add application.yml property settlement.scheduling.enabled=true to allow disabling in tests • Write SettlementCronSchedulerTest verifying cron expression format and that scheduling is disabled in test profile | SettlementCronScheduler.java with all 6 cron methods; application.yml config; SettlementCronSchedulerTest.java | • Cron expression for ZP0061 job is '0 0 5 * * MON-SAT' (or equivalent) with zone=Asia/Seoul • Cron expression for ZP0065/ZP0066 job is '0 0 22 * * MON-SAT' with zone=Asia/Seoul • Setting settlement.scheduling.enabled=false disables all @Scheduled methods (test isolation) • Each scheduler method invokes the correct SettlementBatchJobService method with the current KST date • No scheduler method catches and swallows exceptions -- failures propagate to the scheduler's error handler for alerting | 35 | 7.1-T14, 7.1-T15, 7.1-T16, 7.1-T23 | BE | RATE-04, SCH-06
7.1-T26 | settlement-reconciliation | 7.1 | 7. Settlement, Reconciliation & Revenue | Settlement model: net vs gross | 2 | Unit tests: net settlement amount calculations with edge cases | Comprehensive unit tests for NetSettlementAmountCalculator (7.1-T05). Must cover exact arithmetic, KRW rounding, zero-transaction merchants, and fee rate boundaries. ZeroPay domestic fee range: 0.80% to 2.00% by merchant_type. KRW has 0 decimal places; use HALF_UP rounding. Key invariant: net_settlement_amount = gross_txn_amount - merchant_fee_total (per merchant group). service_charge (e.g. KRW 500) is NOT included in any ZP0061 field -- it is retained by GME and only appears in revenue_record. | • Write NetSettlementEdgeCaseTest in package com.gmepayplus.settlement.calculator • Test 1: single transaction target_payout=15000, fee_rate=0.008 -> merchant_fee=120, net=14880 • Test 2: transaction at fee boundary: target_payout=10000, fee_rate=0.020 -> merchant_fee=200, net=9800 • Test 3: two transactions for same merchant M1: payout=[10000,20001], fee_rate=0.008 -> gross=30001, merchant_fee=ROUND(30001*0.008,0)=240, net=29761 • Test 4: zero transactions -> all amounts 0, no error • Test 5: service_charge=500 KRW NOT reflected in any ZP0061 field (i.e. not subtracted from net_settlement_amount) | NetSettlementEdgeCaseTest.java (5+ test methods) | • Test 1 passes: merchant_fee=ROUND(15000*0.008,0)=120, net_settlement_amount=14880 • Test 3 passes: gross=30001, merchant_fee=ROUND(30001*0.008,0)=ROUND(240.008,0)=240, net=29761 • service_charge=500 KRW does not appear in gross_txn_amount or net_settlement_amount (only in revenue_record) • merchant_fee_total is always <= gross_txn_amount (no negative net for valid fee rates up to 2%) • All arithmetic uses BigDecimal; no double or float types in the calculator | 40 | 7.1-T05 | BE | RATE-04, SCH-06
7.1-T27 | settlement-reconciliation | 7.1 | 7. Settlement, Reconciliation & Revenue | Settlement model: net vs gross | 2 | Unit tests: gross settlement amount calculations with edge cases | Comprehensive unit tests for GrossSettlementAmountCalculator (7.1-T06). Key properties: net_settlement_amount = gross_txn_amount for every merchant (no fee deduction); merchant_fee_total = 0 always; FX margin fields (collection_margin_usd, payout_margin_usd) from the transaction row are not surfaced in ZP0061 fields. Worked example: 3 OVERSEAS transactions for merchant M2 with target_payout 50000, 30000, 20000 KRW -> gross=100000, fee=0, net=100000. Also test: refund reduces gross but leaves fee=0. | • Write GrossSettlementEdgeCaseTest in package com.gmepayplus.settlement.calculator • Test 1: 3 transactions target_payout=[50000,30000,20000] KRW -> gross=100000, merchant_fee_total=0, net=100000 • Test 2: single transaction with collection_margin_usd=1.02 and payout_margin_usd=1.02 -> those fields are not in output, net=target_payout • Test 3: mixed-merchant: merchant A payout=80000, merchant B payout=50000 -> two separate summaries, A.net=80000, B.net=50000 • Test 4: zero transactions -> empty result, no error • Test 5: transaction with settlement_type='N' passed to gross calculator -> throws IllegalArgumentException | GrossSettlementEdgeCaseTest.java (5+ test methods) | • Test 1: net_settlement_amount=100000, merchant_fee_total=0 for merchant M2 • Test 2: output does not reference collection_margin_usd or payout_margin_usd • Test 3: produces 2 separate GrossSettlementSummary objects for A and B • Test 5: IllegalArgumentException thrown with message referencing settlement_type mismatch • All KRW values in output are integers (BigDecimal scale=0) | 35 | 7.1-T06 | BE | RATE-04, SCH-06
7.1-T28 | settlement-reconciliation | 7.1 | 7. Settlement, Reconciliation & Revenue | Settlement model: net vs gross | 2 | Unit tests: SettlementClassifier and settlement_type assignment | Unit tests for the SettlementClassifier and the transaction commit path that sets settlement_type. Cover: LOCAL partner produces 'N', OVERSEAS produces 'G', unknown partner type produces error, and the same-currency short-circuit (domestic) does NOT change the settlement_type logic (it is still 'N' for LOCAL). Also test that settlement_type is immutable after commit: a second commit of the same txn_ref returns the existing transaction with the same settlement_type. | • Write SettlementTypeAssignmentTest in package com.gmepayplus.settlement • Test LOCAL partner -> classify() returns NET -> transaction.settlement_type='N' after commit • Test OVERSEAS partner -> classify() returns GROSS -> transaction.settlement_type='G' after commit • Test LOCAL partner with is_same_ccy_shortcircuit=true -> settlement_type='N' (short-circuit does not change type) • Test idempotent commit: second call with same txn_ref returns existing transaction with unchanged settlement_type='N' • Test null partner type -> IllegalArgumentException from classifier | SettlementTypeAssignmentTest.java (5 test methods) | • LOCAL partner commit: transaction.settlement_type='N' • OVERSEAS partner commit: transaction.settlement_type='G' • Same-currency short-circuit LOCAL: transaction.settlement_type='N', is_same_ccy_shortcircuit=true • Second idempotent commit returns same transaction row with settlement_type unchanged • Null partner type raises IllegalArgumentException before any DB write | 30 | 7.1-T04 | BE | RATE-04, SCH-06
7.1-T29 | settlement-reconciliation | 7.1 | 7. Settlement, Reconciliation & Revenue | Settlement model: net vs gross | 2 | Unit tests: ZP0061 file generation for net settlement | End-to-end unit tests for ZP0061RecordBuilder NET path (7.1-T09). Cover header/trailer correctness, field widths, KRW integer formatting, settlement_type='N' marker, and file SHA-256 checksum consistency. Use the worked example: GME Remit domestic, merchant M1, 2 transactions payout=[15000,20000] KRW, fee_rate=0.008, service_charge=500 KRW each (not in ZP0061 fields). | • Write ZP0061NetFileBuilderTest in package com.gmepayplus.settlement.file • Build a ZP0061 file for one merchant (M1) with the above inputs • Assert per-record fields: merchant_id='M1', gross_txn_amount=35000, merchant_fee_total=280, net_settlement_amount=34720, settlement_type='N' • Assert file trailer: total_net_settlement=34720 • Assert header: merchant_record_count=1 • Assert file_checksum is a valid 64-character hex string (SHA-256) • Assert service_charge (500 KRW per transaction) does NOT appear in any ZP0061 field | ZP0061NetFileBuilderTest.java | • gross_txn_amount field in output = 35000 (integer, padded to NUM(14)) • merchant_fee_total = 280 (ROUND(35000*0.008,0)) • net_settlement_amount = 34720 • settlement_type field = 'N' • File checksum is a valid SHA-256 hex string (64 chars, lowercase hex) | 35 | 7.1-T09, 7.1-T26 | BE | RATE-04, SCH-06
7.1-T30 | settlement-reconciliation | 7.1 | 7. Settlement, Reconciliation & Revenue | Settlement model: net vs gross | 2 | Unit tests: ZP0061 file generation for gross settlement | End-to-end unit tests for ZP0061RecordBuilder GROSS path (7.1-T10). Use the worked example: SendMN (OVERSEAS), merchant M2, 3 transactions payout=[50000,30000,20000] KRW. Expected: gross_txn_amount=100000, merchant_fee_total=0, net_settlement_amount=100000, settlement_type='G'. Also test that FX margin fields from the transaction (collection_margin_usd=1.02, payout_margin_usd=1.02) do not affect any ZP0061 field values. | • Write ZP0061GrossFileBuilderTest in package com.gmepayplus.settlement.file • Build a ZP0061 file for merchant M2 with the above GROSS inputs • Assert per-record: merchant_fee_total=0, net_settlement_amount=100000, settlement_type='G' • Assert trailer total matches 100000 • Assert that transaction.collection_margin_usd and payout_margin_usd have no effect on the file output • Test two-merchant gross file: M2 payout=100000, M3 payout=50000 -> trailer=150000 | ZP0061GrossFileBuilderTest.java | • merchant_fee_total field = 0 (not a positive number) • net_settlement_amount = gross_txn_amount = 100000 • settlement_type field = 'G' • Trailer total_net_settlement = 100000 for single-merchant case • Two-merchant gross file trailer = 150000, both records have settlement_type='G' and merchant_fee_total=0 | 30 | 7.1-T10, 7.1-T27 | BE | RATE-04, SCH-06
7.1-T31 | settlement-reconciliation | 7.1 | 7. Settlement, Reconciliation & Revenue | Settlement model: net vs gross | 2 | Unit tests: ZP0062 reconciliation processor (all match, discrepancy, missing) | Unit tests for ZP0062ResultProcessor (7.1-T17). Test vectors: (A) all merchants match -- status becomes RECONCILED, no reconciliation_items; (B) one merchant credited_amount 34000 vs expected 34720 -- DISCREPANCY, discrepancy_amount=720; (C) merchant in ZP0061 absent from ZP0062 -- MISSING_SCHEME; (D) merchant in ZP0062 not in ZP0061 -- MISSING_GME; (E) idempotent reprocessing -- no duplicates. Also test that after full reconciliation the settlement_batch.reconciled_at timestamp is set. | • Write ZP0062ReconciliationProcessorTest in package com.gmepayplus.settlement.reconciliation • Prepare synthetic ZP0062 byte payloads for each test vector • Test A: process with all matching amounts -> verify settlement_batch.status=RECONCILED, reconciliation_item count=0 • Test B: one mismatch -> verify reconciliation_item with match_status='DISCREPANCY', discrepancy_amount=720, resolution_status='UNRESOLVED' • Test C: missing merchant in ZP0062 -> match_status='MISSING_SCHEME' • Test D: extra merchant in ZP0062 -> match_status='MISSING_GME' • Test E: call process() twice with same inputs -> reconciliation_item count unchanged (idempotent) | ZP0062ReconciliationProcessorTest.java (5 test methods) | • Test A: settlement_batch.status=RECONCILED, reconciliation_item count=0 for the batch • Test B: reconciliation_item.discrepancy_amount=720, match_status=DISCREPANCY, ops alert published • Test C: reconciliation_item.match_status=MISSING_SCHEME for missing merchant • Test D: reconciliation_item.match_status=MISSING_GME, resolution_status=UNRESOLVED • Test E: second process() call for same batch produces identical reconciliation_item count (no duplicates) | 45 | 7.1-T17 | BE | RATE-04, SCH-06
7.1-T32 | settlement-reconciliation | 7.1 | 7. Settlement, Reconciliation & Revenue | Settlement model: net vs gross | 2 | Unit tests: monthly tax invoice aggregation edge cases | Unit tests for TaxInvoiceAggregationService (7.1-T21). Test vectors: (A) 3 GROSS transactions -> correct fee, VAT, ZeroPay share; (B) 0 GROSS transactions -> no invoices created; (C) domestic NET transactions excluded; (D) idempotent re-run same month -> no duplicate invoices; (E) fee rate boundary: total=1000000 KRW, fee_rate=0.022 -> merchant_fee=22000, vat=2200, invoice=24200, zeropay_share=ROUND(22000*0.0021,0)=46. Verify KRW integer rounding for all fields. | • Write TaxInvoiceAggregationServiceTest in package com.gmepayplus.settlement.invoice • Test A: 3 transactions totalling 500000 KRW, fee_rate=0.017 -> merchant_fee=8500, vat=850, invoice=9350, zeropay_share=18 • Test B: no GROSS transactions for month -> aggregateForMonth() returns empty list • Test C: mix of GROSS and NET transactions -> only GROSS included in total_transaction_amount_krw • Test D: run aggregateForMonth() twice for same YearMonth and merchant -> still one TaxInvoice with status=DRAFT • Test E: total=1000000, fee_rate=0.022 -> zeropay_share=ROUND(22000*0.0021,0)=46 | TaxInvoiceAggregationServiceTest.java (5 test methods) | • Test A: merchant_fee_krw=8500, vat_krw=850, invoice_amount_krw=9350, zeropay_share_krw=18 • Test B: returns empty List<TaxInvoice> • Test C: a NET transaction (settlement_type='N') with target_payout=100000 KRW is absent from the aggregation total • Test D: second call returns existing DRAFT invoice, no new row inserted • Test E: zeropay_share_krw=46 (ROUND(22000*0.0021,0)=ROUND(46.2,0)=46) | 40 | 7.1-T21 | BE | RATE-04, SCH-06
7.1-T33 | settlement-reconciliation | 7.1 | 7. Settlement, Reconciliation & Revenue | Settlement model: net vs gross | 2 | Integration test: full daily settlement cycle (domestic NET) | End-to-end integration test for a complete domestic NET settlement day. Scenario: GME Remit (LOCAL, KRW) makes 2 payments to ZeroPay merchant M1 (payout 15000 KRW and 20000 KRW, service_charge=500 each, fee_rate=0.008). Steps: transactions committed with settlement_type='N'; ZP0011 transmitted; ZP0012 received (all match); ZP0061 morning batch generated and transmitted; ZP0062 result received confirming net_settlement_amount=34720; reconciliation passes (RECONCILED); ZP0065 detail file generated; revenue_records created with fx_margin_usd=0 and service_charge=500 each. Verify DB state after each step. | • Create DomesticNetSettlementCycleIT in package com.gmepayplus.settlement.integration (using @SpringBootTest with test DB) • Set up: insert LOCAL partner, ZeroPay scheme, merchant M1, 2 approved transactions with target_payout=15000 and 20000 • Run ZP0061 morning batch job; assert settlement_batch created with transaction_count=2, total_amount=35000, net_settlement_amount=34720, merchant_fee_total=280 • Simulate ZP0062 receipt with credited_amount=34720; run ZP0062ResultProcessor; assert batch status=RECONCILED • Run ZP0065 detail batch; assert 2 records in file with partner_type='D' • Run createDomesticRevenueRecord; assert revenue_records: fx_margin_usd=0, service_charge_amount=500 each | DomesticNetSettlementCycleIT.java | • After ZP0061: settlement_batch.transaction_count=2, net_settlement_amount=34720, merchant_fee_total=280 • After ZP0062: settlement_batch.status=RECONCILED, no reconciliation_items with DISCREPANCY • After ZP0065: file contains 2 records with partner_type='D', payout_amount_krw=[15000,20000] • After revenue record creation: 2 revenue_record rows with fx_margin_usd=0, service_charge_amount=500, service_charge_ccy='KRW' • Both transactions have settlement_batch_id set (not NULL) and SETTLEMENT_BATCHED event in transaction_event | 60 | 7.1-T14, 7.1-T17, 7.1-T16, 7.1-T19 | BE | RATE-04, SCH-06
7.1-T34 | settlement-reconciliation | 7.1 | 7. Settlement, Reconciliation & Revenue | Settlement model: net vs gross | 2 | Integration test: full daily settlement cycle (international GROSS) | End-to-end integration test for a complete international GROSS settlement day. Scenario: SendMN (OVERSEAS, USD prefunding) makes 3 payments to ZeroPay merchant M2 (payout 50000, 30000, 20000 KRW; FX: cost_rate_pay=1350 KRW/USD; m_a=0.01, m_b=0.01; service_charge=500 KRW). USD prefunding deducted at payment time. Steps: transactions committed with settlement_type='G'; ZP0061 morning batch: merchant_fee_total=0, net_settlement_amount=100000; ZP0062 confirms credited_amount=100000 (RECONCILED); ZP0065 generated with partner_type='I', merchant_fee_amt=0; revenue_records: fx_margin_usd = collection_margin_usd + payout_margin_usd (non-zero). | • Create InternationalGrossSettlementCycleIT in package com.gmepayplus.settlement.integration • Set up: insert OVERSEAS partner, ZeroPay scheme, merchant M2 (fee_tier='CROSSBORDER'), 3 approved transactions with above payouts and locked USD pool values • Run ZP0061 morning batch; assert settlement_batch: transaction_count=3, total_amount=100000, merchant_fee_total=0, net_settlement_amount=100000, settlement_type='G' • Simulate ZP0062 receipt with credited_amount=100000; run ZP0062ResultProcessor; assert RECONCILED • Run ZP0065; assert 3 records with partner_type='I', merchant_fee_amt=0 • Run createInternationalRevenueRecord for each transaction; assert fx_margin_usd > 0 | InternationalGrossSettlementCycleIT.java | • ZP0061 batch: merchant_fee_total=0, net_settlement_amount=100000, settlement_type='G' • ZP0062 reconciliation: batch status=RECONCILED, no DISCREPANCY items • ZP0065 records: all 3 have partner_type='I', merchant_fee_amt=0, payout_amount_krw=[50000,30000,20000] • Revenue records: fx_margin_usd = collection_margin_usd + payout_margin_usd (non-zero per transaction) • All 3 transactions have SETTLEMENT_BATCHED event in transaction_event with settlement_type='G' in detail | 60 | 7.1-T15, 7.1-T17, 7.1-T20, 7.1-T33 | BE | RATE-04, SCH-06
7.1-T35 | settlement-reconciliation | 7.1 | 7. Settlement, Reconciliation & Revenue | Settlement model: net vs gross | 2 | Document SettlementEngine service API (Javadoc and README section) | The Settlement Engine for WBS 7.1 exposes several key service classes. Developers integrating with it need to understand: (1) how settlement_type is determined per transaction; (2) the difference between NET and GROSS settlement amounts; (3) the daily batch schedule (KST times); (4) which classes to extend to add a new settlement model when a new QR scheme is added (config-only, no code change for same net/gross model). Document the public API of: SettlementClassifier, NetSettlementAmountCalculator, GrossSettlementAmountCalculator, SettlementBatchJobService, and TaxInvoiceAggregationService. | • Add @since, @param, @return, and @throws Javadoc to all public methods in the 5 classes listed in context • In the existing settlement service README (or SETTLEMENT.md in the service module), add a section '7.1 Net vs Gross Settlement Model' covering: rule summary (LOCAL=NET, OVERSEAS=GROSS), daily batch schedule table (KST times), ZP0061/ZP0063/ZP0065/ZP0066 file responsibilities, and extension guidance • Note that settlement model is driven by partner.type (config); adding a new partner requires no code change • Include a concise worked example for each settlement type (reference existing test data from 7.1-T33 and 7.1-T34) • Review that no Javadoc references internal Spring bean names or implementation details that could break consumers | Javadoc on 5 public service classes; SETTLEMENT.md section '7.1 Net vs Gross Settlement Model' | • SettlementClassifier interface Javadoc explains the LOCAL -> NET, OVERSEAS -> GROSS rule without hardcoding partner names • SettlementBatchJobService Javadoc for runZP0061Morning() documents the ZP0011/ZP0012 prerequisite check • SETTLEMENT.md batch schedule table lists ZP0061 at 05:00 KST, ZP0063 at 14:00 KST, ZP0065/ZP0066 at 22:00 KST • SETTLEMENT.md extension guidance states that adding a new partner with type LOCAL or OVERSEAS requires only partner registry configuration, no code change • Both NET and GROSS worked examples reference the numeric values from 7.1-T33 and 7.1-T34 test scenarios | 40 | 7.1-T14, 7.1-T15, 7.1-T16, 7.1-T21 | BE | RATE-04, SCH-06
7.2-T01 | revenue-ledger | 7.2 | 7. Settlement, Reconciliation & Revenue | Scheme fee share (70/30) computation | 2 | Add scheme_fee_config table migration: merchant fee rates and VAN fee rates per scheme | WBS 7.2 delivers the 70/30 scheme fee-share computation. The qr_scheme table already holds gme_fee_share_pct DECIMAL(6,4) (e.g. 0.70) plus range columns merchant_fee_domestic_min/max and merchant_fee_crossborder_min/max. To compute GME net fee share per transaction the engine needs the exact merchant-type-level fee rates and VAN fee rates stored as a lookup table. BRD-01 §8.3 (ZeroPay): merchant fee 0.80%-2.00% domestic / 1.70%-2.20% cross-border; VAN fee 0.08%-0.20% domestic / 0.17%-0.22% cross-border. Net merchant fee = gross merchant fee - VAN fee; GME share = net merchant fee x gme_fee_share_pct (0.70 for ZeroPay). merchant.merchant_type (VARCHAR 30, e.g. GENERAL, FRANCHISE) and merchant.fee_tier (DOMESTIC/CROSSBORDER) are the lookup keys. | • Create migration file db/migrations/V7_2_001__scheme_fee_config.sql. • Define table scheme_fee_config: id BIGINT PK, scheme_id BIGINT FK -> qr_scheme NOT NULL, merchant_type VARCHAR(30) NOT NULL, fee_tier VARCHAR(20) NOT NULL CHECK IN ('DOMESTIC','CROSSBORDER'), merchant_fee_rate DECIMAL(6,4) NOT NULL, van_fee_rate DECIMAL(6,4) NOT NULL, effective_from DATE NOT NULL DEFAULT CURRENT_DATE, effective_to DATE NULL, created_at TIMESTAMPTZ NOT NULL DEFAULT now(), updated_at TIMESTAMPTZ NOT NULL DEFAULT now(), created_by VARCHAR(120) NOT NULL, updated_by VARCHAR(120) NOT NULL. • Add UNIQUE constraint on (scheme_id, merchant_type, fee_tier, effective_from). • Add index on (scheme_id, merchant_type, fee_tier, effective_from DESC) for point-in-time lookups. • Seed ZeroPay GENERAL DOMESTIC (merchant_fee_rate=0.0080, van_fee_rate=0.0008) and GENERAL CROSSBORDER (merchant_fee_rate=0.0170, van_fee_rate=0.0017) rows as reference data in a separate seed script V7_2_001__scheme_fee_config_seed.sql. | Migration file db/migrations/V7_2_001__scheme_fee_config.sql and seed file V7_2_001__scheme_fee_config_seed.sql that apply cleanly via Flyway/Liquibase. | • Migration applies on a clean schema with no errors and creates the scheme_fee_config table with all columns and constraints. • INSERT of duplicate (scheme_id, merchant_type, fee_tier, effective_from) is rejected by the unique constraint. • Seed rows for ZeroPay GENERAL DOMESTIC and GENERAL CROSSBORDER exist after running the seed script. • Rollback migration removes the table cleanly with no orphan indexes. • merchant_fee_rate and van_fee_rate accept values in range 0.0000-1.0000 and reject values outside that range (add CHECK constraints). | 35 |  | BE | RATE-04, BRD-01
7.2-T02 | revenue-ledger | 7.2 | 7. Settlement, Reconciliation & Revenue | Scheme fee share (70/30) computation | 2 | Add transaction_fee_snapshot table migration to store per-transaction fee inputs at commit | WBS 7.2 requires GME 70% of net merchant fee to be computed and stored per transaction at commit time. The canonical fields are: gross_merchant_fee_krw (payout_amount_krw x merchant_fee_rate, KRW BIGINT, 0 decimals per KRW scale), van_fee_krw (payout_amount_krw x van_fee_rate, BIGINT), net_merchant_fee_krw (gross - van, BIGINT), gme_fee_share_krw (net x gme_fee_share_pct, BIGINT rounded towards zero), zeropay_fee_share_krw (net - gme_fee_share_krw, BIGINT). These are locked at commit and never recomputed. The existing transaction table FK is the anchor. | • Create migration db/migrations/V7_2_002__transaction_fee_snapshot.sql. • Define table transaction_fee_snapshot: id BIGINT PK, txn_id BIGINT UNIQUE FK -> transaction NOT NULL, merchant_fee_rate DECIMAL(6,4) NOT NULL, van_fee_rate DECIMAL(6,4) NOT NULL, gme_fee_share_pct DECIMAL(6,4) NOT NULL, gross_merchant_fee_krw BIGINT NOT NULL, van_fee_krw BIGINT NOT NULL, net_merchant_fee_krw BIGINT NOT NULL, gme_fee_share_krw BIGINT NOT NULL, zeropay_fee_share_krw BIGINT NOT NULL, fee_config_id BIGINT FK -> scheme_fee_config NOT NULL, created_at TIMESTAMPTZ NOT NULL DEFAULT now(). • Add CHECK constraint: gross_merchant_fee_krw >= van_fee_krw AND net_merchant_fee_krw >= 0 AND gme_fee_share_krw + zeropay_fee_share_krw = net_merchant_fee_krw. • Add index on txn_id (already unique but explicit for query plans). • Comment each column with its formula in the migration SQL. | Migration file db/migrations/V7_2_002__transaction_fee_snapshot.sql that applies cleanly and creates the locked snapshot table. | • Migration applies on top of V7_2_001 with no errors; UNIQUE(txn_id) prevents duplicate snapshots for the same transaction. • CHECK constraint rejects rows where gme_fee_share_krw + zeropay_fee_share_krw != net_merchant_fee_krw (e.g. insert gme=70, zeropay=29, net=100 is rejected). • CHECK constraint rejects rows where van_fee_krw > gross_merchant_fee_krw. • All BIGINT fee columns store KRW values with 0 decimal places (no DECIMAL type used for KRW amounts). • fee_config_id FK references a valid scheme_fee_config row; orphan inserts are rejected. | 30 | 7.2-T01 | BE | RATE-04, BRD-01
7.2-T03 | revenue-ledger | 7.2 | 7. Settlement, Reconciliation & Revenue | Scheme fee share (70/30) computation | 2 | Add revenue_record columns for scheme fee share fields | WBS 7.2 must also surface the scheme fee share in the revenue_record table (DAT-03 §8.2). The existing revenue_record has: txn_id, partner_id, scheme_id, revenue_date, fx_margin_usd DECIMAL(20,4), service_charge_amount DECIMAL(20,4), service_charge_ccy CHAR(3), fee_share_pct DECIMAL(6,4) (the 70%), estimated_fee_share_usd DECIMAL(20,4). The spec notes estimated_fee_share_usd is 'estimated at commit; confirmed from scheme settlement'. KRW amounts cannot be stored as USD precisely - add estimated_fee_share_krw BIGINT to hold the KRW-denominated estimate and fee_share_confirmed BOOLEAN DEFAULT FALSE to track whether reconciliation has confirmed the actual figure. | • Create migration db/migrations/V7_2_003__revenue_record_fee_share_cols.sql. • Add column estimated_fee_share_krw BIGINT NULL to revenue_record (NULL until computed at commit; non-null after T05 logic is wired). • Add column fee_share_confirmed BOOLEAN NOT NULL DEFAULT FALSE to revenue_record. • Add column fee_snapshot_id BIGINT NULL FK -> transaction_fee_snapshot (links revenue line to the detailed snapshot; NULL until T05 wired). • Add index on (scheme_id, revenue_date) for monthly aggregation queries. | Migration file db/migrations/V7_2_003__revenue_record_fee_share_cols.sql adding the three new columns to revenue_record. | • Migration applies cleanly on top of V7_2_002; existing revenue_record rows gain the new nullable/defaulted columns with no data loss. • estimated_fee_share_krw BIGINT column accepts KRW integer values (e.g. 560) and rejects fractional input. • fee_share_confirmed defaults to FALSE for all pre-existing rows after migration. • fee_snapshot_id FK insert of a non-existent snapshot id is rejected by FK constraint. • Index on (scheme_id, revenue_date) is visible in EXPLAIN for a query filtering on both columns. | 25 | 7.2-T02 | BE | RATE-04, BRD-01
7.2-T04 | revenue-ledger | 7.2 | 7. Settlement, Reconciliation & Revenue | Scheme fee share (70/30) computation | 2 | Implement FeeConfigRepository: point-in-time lookup of scheme_fee_config row | WBS 7.2 core logic needs to resolve the merchant fee rate and VAN fee rate for a transaction at its committed_at date. scheme_fee_config has: scheme_id, merchant_type, fee_tier, merchant_fee_rate DECIMAL(6,4), van_fee_rate DECIMAL(6,4), effective_from DATE, effective_to DATE NULL. Lookup rule: find the row where scheme_id matches AND merchant_type matches AND fee_tier matches AND effective_from <= :as_of AND (effective_to IS NULL OR effective_to >= :as_of) ORDER BY effective_from DESC LIMIT 1. fee_tier is derived from the transaction's partner type: LOCAL partner -> 'DOMESTIC', OVERSEAS partner -> 'CROSSBORDER'. merchant_type comes from merchant.merchant_type joined via the transaction's merchant_id. | • Create interface FeeConfigRepository in package com.gme.gmepay.fees with method: Optional<SchemeFeeConfig> findEffectiveConfig(long schemeId, String merchantType, String feeTier, LocalDate asOf). • Implement FeeConfigRepositoryJpa using Spring Data JPA or a named @Query with the point-in-time SQL defined in context. • Map result to SchemeFeeConfig value object: schemeId, merchantType, feeTier, merchantFeeRate (BigDecimal), vanFeeRate (BigDecimal), feeConfigId (Long). • Throw FeeConfigNotFoundException (unchecked) if no row matches; include schemeId, merchantType, feeTier, asOf in the message. • Add Javadoc on the interface method explaining the effective_from/effective_to range semantics. | FeeConfigRepository interface and FeeConfigRepositoryJpa implementation in com.gme.gmepay.fees package. | • findEffectiveConfig returns the row with the latest effective_from <= asOf when two overlapping rows exist (e.g. row A effective_from=2025-01-01, row B effective_from=2026-01-01; asOf=2026-06-01 returns B). • findEffectiveConfig returns Optional.empty() (which triggers FeeConfigNotFoundException) when no row matches the given schemeId+merchantType+feeTier combination. • findEffectiveConfig with asOf = effective_from date (boundary) returns that row (inclusive lower bound). • If effective_to is set and asOf > effective_to, the row is NOT returned. • FeeConfigNotFoundException message contains all four lookup parameters for debuggability. | 35 | 7.2-T01 | BE | RATE-04, BRD-01
7.2-T05 | revenue-ledger | 7.2 | 7. Settlement, Reconciliation & Revenue | Scheme fee share (70/30) computation | 2 | Implement SchemeFeeSplitCalculator: compute gross/net merchant fee and 70/30 split | WBS 7.2 core logic. Formula (all values in KRW BIGINT, 0 decimals): gross_merchant_fee_krw = floor(payout_amount_krw x merchant_fee_rate); van_fee_krw = floor(payout_amount_krw x van_fee_rate); net_merchant_fee_krw = gross_merchant_fee_krw - van_fee_krw; gme_fee_share_krw = floor(net_merchant_fee_krw x gme_fee_share_pct); zeropay_fee_share_krw = net_merchant_fee_krw - gme_fee_share_krw. Use floor (truncate towards zero) for all intermediate multiplications - this preserves whole KRW and ensures gme + zeropay always equals net exactly. gme_fee_share_pct is read from qr_scheme.gme_fee_share_pct (0.70 for ZeroPay). Inputs come from SchemeFeeConfig (T04) plus the qr_scheme.gme_fee_share_pct. All arithmetic uses java.math.BigDecimal with ROUND_DOWN. | • Create class SchemeFeeSplitCalculator in com.gme.gmepay.fees with a single public method: FeeShareResult calculate(long payoutAmountKrw, BigDecimal merchantFeeRate, BigDecimal vanFeeRate, BigDecimal gmeFeeSharePct). • FeeShareResult is a record/value object with fields: grossMerchantFeeKrw (long), vanFeeKrw (long), netMerchantFeeKrw (long), gmeFeeShareKrw (long), zeropayFeeShareKrw (long). • Implement using BigDecimal.multiply with setScale(0, RoundingMode.FLOOR) at each step. • Guard: throw IllegalArgumentException if payoutAmountKrw < 0, any rate < 0, gmeFeeSharePct not in (0,1], or vanFeeRate >= merchantFeeRate (VAN fee must not exceed gross fee). • Assert invariant: gmeFeeShareKrw + zeropayFeeShareKrw == netMerchantFeeKrw; throw ArithmeticException if violated (should never happen given floor logic, but belt-and-suspenders). | SchemeFeeSplitCalculator class and FeeShareResult record in com.gme.gmepay.fees package. | • calculate(15000, 0.0080, 0.0008, 0.70): gross=120, van=12, net=108, gme=75 (floor(108x0.70)=75), zeropay=33. Verify gme+zeropay=108. • calculate(100000, 0.0200, 0.0020, 0.70): gross=2000, van=200, net=1800, gme=1260 (floor(1800x0.70)=1260), zeropay=540. • calculate(1, 0.0080, 0.0008, 0.70): gross=0 (floor), van=0, net=0, gme=0, zeropay=0 - no negative amounts. • calculate(-1, ...) throws IllegalArgumentException. • Invariant gme+zeropay==net holds for all valid inputs including odd/prime payout amounts. | 40 | 7.2-T04 | BE | RATE-04, BRD-01
7.2-T06 | revenue-ledger | 7.2 | 7. Settlement, Reconciliation & Revenue | Scheme fee share (70/30) computation | 2 | Implement FeeSnapshotService: persist transaction_fee_snapshot at transaction commit | WBS 7.2 wiring: at transaction commit time, FeeSnapshotService must (1) look up SchemeFeeConfig for the transaction via FeeConfigRepository (T04) using the transaction's schemeId, the merchant's merchantType, the fee_tier derived from partner type (LOCAL=DOMESTIC, OVERSEAS=CROSSBORDER), and the transaction's committed_at date; (2) invoke SchemeFeeSplitCalculator.calculate (T05) with payout_amount_krw=transaction.targetPayout (KRW), merchantFeeRate, vanFeeRate, and qrScheme.gmeFeeSharePct; (3) INSERT into transaction_fee_snapshot; (4) UPDATE revenue_record.estimated_fee_share_krw and fee_snapshot_id for the same txn_id. All four steps must execute within the same DB transaction (atomic commit). If FeeConfigNotFoundException is thrown, re-throw as FeeComputationException (checked) with the txn_id in the message - do not silently skip. | • Create FeeSnapshotService in com.gme.gmepay.fees with method: void captureFeeSplit(long txnId) throws FeeComputationException. • Load Transaction, Merchant (for merchantType), Partner (for type LOCAL/OVERSEAS), and QrScheme (for gmeFeeSharePct) from their respective repositories. • Derive feeTier: partner.type == LOCAL -> 'DOMESTIC'; OVERSEAS -> 'CROSSBORDER'. • Call FeeConfigRepository.findEffectiveConfig; on empty result throw FeeComputationException. • Call SchemeFeeSplitCalculator.calculate; persist TransactionFeeSnapshot entity; update RevenueRecord.estimatedFeeShareKrw and feeSnapshotId. • Annotate the method @Transactional(rollbackFor = FeeComputationException.class) to ensure atomicity. | FeeSnapshotService class in com.gme.gmepay.fees that atomically captures the fee split and updates the revenue record. | • After captureFeeSplit(txnId) succeeds, exactly one transaction_fee_snapshot row exists for txnId and revenue_record.estimated_fee_share_krw is non-null. • If FeeConfigNotFoundException is thrown mid-method, both transaction_fee_snapshot and revenue_record.estimated_fee_share_krw remain unchanged (full rollback). • Calling captureFeeSplit twice for the same txnId throws a DataIntegrityViolationException due to the UNIQUE(txn_id) constraint on transaction_fee_snapshot. • For a LOCAL partner transaction (KRW domestic), feeTier is resolved as DOMESTIC and the DOMESTIC fee config row is used. • For an OVERSEAS partner transaction, feeTier is resolved as CROSSBORDER and the CROSSBORDER fee config row is used. | 45 | 7.2-T05, 7.2-T03 | BE | RATE-04, BRD-01
7.2-T07 | revenue-ledger | 7.2 | 7. Settlement, Reconciliation & Revenue | Scheme fee share (70/30) computation | 2 | Wire FeeSnapshotService into transaction commit flow | WBS 7.2 integration: the transaction commit flow (TransactionService.commitTransaction) runs after scheme approval is received and before the TRANSACTION_COMMITTED event is recorded in transaction_event. FeeSnapshotService.captureFeeSplit must be called within the commit @Transactional boundary so the fee snapshot is part of the same DB commit. If captureFeeSplit throws FeeComputationException the whole commit must roll back and the caller receives a 422 error code FEE_CONFIG_MISSING. The existing commit flow is in TransactionService (or equivalent service handling POST /v1/payments/{id}/commit). Do not alter any rate-engine pool fields - those are already locked before this step. | • Locate the TransactionService.commitTransaction method (or equivalent). • Inject FeeSnapshotService into TransactionService. • After scheme approval confirmation and before writing the TRANSACTION_COMMITTED event, call feeSnapshotService.captureFeeSplit(txn.getId()). • Catch FeeComputationException; translate to a 422 PaymentApiException with error code FEE_CONFIG_MISSING and message including txnId. • Verify @Transactional annotation on commitTransaction covers the captureFeeSplit call (same transaction boundary). • Add the new event step to TRANSACTION_COMMITTED event detail JSONB: include gme_fee_share_krw from the snapshot. | Updated TransactionService with FeeSnapshotService wired into the commit path; FEE_CONFIG_MISSING error returned on fee config absence. | • A complete commit for a GENERAL DOMESTIC transaction results in a transaction_fee_snapshot row visible immediately after the HTTP 200 response. • If the merchant has no fee config row (novel merchant_type), commit returns HTTP 422 with error_code FEE_CONFIG_MISSING and no transaction_fee_snapshot row is created. • The TRANSACTION_COMMITTED transaction_event detail JSONB contains a gme_fee_share_krw field matching the snapshot value. • Removing the @Transactional annotation (test-only) and forcing captureFeeSplit to fail after the scheme call leaves no orphan snapshot row. • A cross-border (OVERSEAS) transaction uses the CROSSBORDER fee tier and fee rates differ from the DOMESTIC rates. | 45 | 7.2-T06 | BE | RATE-04, BRD-01
7.2-T08 | revenue-ledger | 7.2 | 7. Settlement, Reconciliation & Revenue | Scheme fee share (70/30) computation | 2 | Implement edge-case handling: zero payout, same-currency short-circuit, and refund transactions | WBS 7.2 edge cases. (1) Zero/tiny payout: payout_amount_krw=0 should produce all-zero fee fields - valid, not an error. (2) Same-currency short-circuit (is_same_ccy_shortcircuit=true, always LOCAL/DOMESTIC KRW): scheme fee share still applies per spec (BRD-01 §8.1: fee share applies to ALL transactions domestic + cross-border). Fee is computed the same way - use DOMESTIC rate. (3) Refund transactions: a refund reverses the payout, so gross/net fees should be negative (or zero if the original transaction fee snapshot handles it). Rule: for refund transactions, create a transaction_fee_snapshot with all fee fields negated from the original txn's snapshot. (4) Cancelled transactions (same-day cancel): no fee snapshot should be created - cancel means scheme was never charged. Guard in FeeSnapshotService: check transaction.status; only proceed for COMPLETED/APPROVED status. | • Update FeeSnapshotService.captureFeeSplit to guard on transaction.status: throw FeeComputationException with message STATUS_INELIGIBLE if status is not COMPLETED or APPROVED. • For refund transactions (transaction.isRefund=true or a Refund entity), implement a separate method captureRefundFeeSplit(long refundTxnId, long originalTxnId) that reads the original snapshot and writes a mirrored row with all fee amounts negated. • For payout_amount_krw=0 (valid edge case), allow all-zero fee snapshot to be written without error. • For same-currency short-circuit transactions (is_same_ccy_shortcircuit=true), confirm feeTier=DOMESTIC and fee rates from DOMESTIC config are used (no bypass). • Add a guard: if transaction.schemeFeeShareApplicable=false (future config flag, default true), skip captureFeeSplit silently and leave revenue_record.estimated_fee_share_krw null. | Updated FeeSnapshotService with edge-case guards for cancelled transactions, refunds, zero payout, and same-currency short-circuit. | • A cancelled transaction (status=CANCELLED) results in no transaction_fee_snapshot row and no error logged. • A domestic same-currency short-circuit transaction (is_same_ccy_shortcircuit=true) still creates a fee snapshot using DOMESTIC rates. • payout_amount_krw=0 produces a fee snapshot with all BIGINT fields = 0 and no exception. • A refund snapshot has gme_fee_share_krw = -(original gme_fee_share_krw) and zeropay_fee_share_krw = -(original zeropay_fee_share_krw); gme+zeropay still equals net (both negative). • captureFeeSplit on a COMPLETED transaction with no matching fee config still throws FeeComputationException (fee config missing is always fatal for completed transactions). | 45 | 7.2-T07 | BE | RATE-04, BRD-01
7.2-T09 | revenue-ledger | 7.2 | 7. Settlement, Reconciliation & Revenue | Scheme fee share (70/30) computation | 2 | Add FeeConfigRepository unit tests | WBS 7.2 unit tests for the repository layer (T04). Test with H2 or Testcontainers PostgreSQL. Seed three rows for the same scheme/merchant_type/fee_tier with different effective_from dates to verify point-in-time logic. ZeroPay scheme_id=1, merchant_type=GENERAL, fee_tier=DOMESTIC. Row A: effective_from=2025-01-01, effective_to=2025-12-31. Row B: effective_from=2026-01-01, effective_to=null. Row C: effective_from=2027-01-01, effective_to=null (future). Test asOf dates: 2025-06-01 (returns A), 2026-06-05 (returns B), 2026-12-31 (returns B), 2024-12-31 (returns empty), 2025-12-31 (boundary - returns A), 2026-01-01 (boundary - returns B). | • Create FeeConfigRepositoryTest in src/test/java/com/gme/gmepay/fees/. • Use @DataJpaTest with Testcontainers (PostgreSQL) or H2 in PostgreSQL-compatible mode. • Seed rows A, B, C as described in context before each test using @BeforeEach. • Write 6 parameterised tests covering each asOf date in context. • Add a test for a different merchant_type (FRANCHISE) that has no rows: expect Optional.empty() and verify FeeConfigNotFoundException is thrown by the service wrapper. | FeeConfigRepositoryTest class with 7+ passing tests covering point-in-time lookups. | • asOf=2025-06-01 returns row A (merchant_fee_rate=row A value, not row B). • asOf=2026-06-05 returns row B (most recent effective row). • asOf=2024-12-31 (before any row) returns Optional.empty(). • asOf=2025-12-31 (last day of row A effective_to) returns row A (inclusive upper bound). • asOf=2026-01-01 (first day of row B) returns row B (inclusive lower bound). • FRANCHISE merchant_type with no rows returns Optional.empty(). • All 7 tests pass with zero failures on CI. | 40 | 7.2-T04 | BE | RATE-04, BRD-01
7.2-T10 | revenue-ledger | 7.2 | 7. Settlement, Reconciliation & Revenue | Scheme fee share (70/30) computation | 2 | Add SchemeFeeSplitCalculator unit tests with exact numeric vectors | WBS 7.2 unit tests for the calculation engine (T05). All arithmetic uses floor (ROUND_DOWN). Test vectors must be exact. Vector set: (A) payout=15000, merchant_fee_rate=0.0080, van_fee_rate=0.0008, gme_fee_share_pct=0.70 -> gross=120, van=12, net=108, gme=75, zeropay=33. (B) payout=100000, merchant_fee_rate=0.0200, van_fee_rate=0.0020, gme_fee_share_pct=0.70 -> gross=2000, van=200, net=1800, gme=1260, zeropay=540. (C) payout=1, merchant_fee_rate=0.0080, van_fee_rate=0.0008, gme_fee_share_pct=0.70 -> gross=0, van=0, net=0, gme=0, zeropay=0. (D) payout=999, merchant_fee_rate=0.0080, van_fee_rate=0.0008, gme_fee_share_pct=0.70 -> gross=7 (floor(999*0.008)=7), van=0 (floor(999*0.0008)=0), net=7, gme=4 (floor(7*0.70)=4), zeropay=3. (E) payout=0, any rates -> all zeros. Guard tests: negative payout, vanFeeRate>=merchantFeeRate, gmeFeeSharePct=0, gmeFeeSharePct=1.01. | • Create SchemeFeeSplitCalculatorTest in src/test/java/com/gme/gmepay/fees/. • Implement @ParameterizedTest for vectors A-E verifying each output field exactly. • Add guard tests: negative payout throws IllegalArgumentException; vanFeeRate >= merchantFeeRate throws IllegalArgumentException; gmeFeeSharePct=1.01 throws IllegalArgumentException. • Verify invariant gme+zeropay==net holds for all valid vectors programmatically within each test. • Add a stress test: loop 10,000 random payout amounts 1-1000000 KRW with fixed rates and assert invariant never breaks. | SchemeFeeSplitCalculatorTest class with parameterised vectors A-E, guard tests, and invariant stress test - all passing. | • Vector A produces gross=120, van=12, net=108, gme=75, zeropay=33 exactly. • Vector D produces gross=7, van=0, net=7, gme=4, zeropay=3 exactly (tests floor behaviour for sub-unit VAN fee). • Vector E (payout=0) produces all zeros with no exception. • negative payout test throws IllegalArgumentException with message containing 'payoutAmountKrw'. • 10,000-iteration invariant stress test completes with zero assertion failures. | 45 | 7.2-T05 | BE | RATE-04, BRD-01
7.2-T11 | revenue-ledger | 7.2 | 7. Settlement, Reconciliation & Revenue | Scheme fee share (70/30) computation | 2 | Add FeeSnapshotService unit tests: success path, rollback on missing config, and refund mirroring | WBS 7.2 unit tests for FeeSnapshotService (T06). Use Mockito for repository mocks. Tests cover: (1) Happy-path LOCAL domestic: payout=15000 KRW, GENERAL merchant, LOCAL partner -> snapshot written with gme=75, zeropay=33, revenue_record.estimated_fee_share_krw=75. (2) Happy-path OVERSEAS cross-border: payout=50000 KRW, GENERAL merchant, OVERSEAS partner -> snapshot written using CROSSBORDER rates (merchant_fee_rate=0.0170, van_fee_rate=0.0017) -> gross=850, van=85, net=765, gme=535 (floor(765*0.70)), zeropay=230. (3) FeeConfigNotFoundException propagates as FeeComputationException. (4) Refund mirroring: original snapshot gme=75, zeropay=33; refund snapshot gme=-75, zeropay=-33; net=-108. (5) Cancelled transaction: no snapshot written, method returns cleanly. | • Create FeeSnapshotServiceTest in src/test/java/com/gme/gmepay/fees/. • Mock FeeConfigRepository, SchemeFeeSplitCalculator, TransactionFeeSnapshotRepository, RevenueRecordRepository, TransactionRepository. • Write test (1): LOCAL domestic happy path - verify snapshot persisted with exact values and revenue_record updated. • Write test (2): OVERSEAS cross-border - verify CROSSBORDER feeTier used and snapshot values correct. • Write test (3): FeeConfigRepository returns empty -> verify FeeComputationException thrown and no persist calls made. • Write test (4): captureRefundFeeSplit called with refundTxnId and originalTxnId -> verify mirrored negative values. • Write test (5): cancelled transaction (status=CANCELLED) -> captureFeeSplit returns without persisting. | FeeSnapshotServiceTest with 5+ passing tests covering all documented scenarios. | • Test (1) asserts revenue_record.setEstimatedFeeShareKrw(75L) is called exactly once. • Test (2) asserts FeeConfigRepository was called with feeTier='CROSSBORDER' and produces gme=535. • Test (3) asserts no call to TransactionFeeSnapshotRepository.save() when config is missing. • Test (4) asserts refund snapshot gme_fee_share_krw = -75 and zeropay_fee_share_krw = -33 and net_merchant_fee_krw = -108. • Test (5) asserts zero interactions with TransactionFeeSnapshotRepository when status=CANCELLED. | 45 | 7.2-T06, 7.2-T08 | BE | RATE-04, BRD-01
7.2-T12 | revenue-ledger | 7.2 | 7. Settlement, Reconciliation & Revenue | Scheme fee share (70/30) computation | 2 | Add integration test: end-to-end commit with fee snapshot verification | WBS 7.2 integration test covering the full commit path from POST /v1/payments/{id}/commit through to transaction_fee_snapshot and revenue_record persistence. Use Testcontainers PostgreSQL. Seed: ZeroPay scheme with gme_fee_share_pct=0.70; scheme_fee_config rows for GENERAL DOMESTIC (merchant_fee_rate=0.0080, van_fee_rate=0.0008) and GENERAL CROSSBORDER (merchant_fee_rate=0.0170, van_fee_rate=0.0017). Merchant: merchant_type=GENERAL, fee_tier=DOMESTIC. Partners: GME_REMIT (LOCAL) and SENDMN (OVERSEAS). Test scenario A: LOCAL GME_REMIT payment payout=15000 KRW -> commit -> assert transaction_fee_snapshot.gme_fee_share_krw=75. Test scenario B: OVERSEAS SENDMN payment payout=50000 KRW -> commit -> assert snapshot uses CROSSBORDER rates. | • Create FeeSnapshotIntegrationTest in src/test/java/com/gme/gmepay/fees/integration/. • Use @SpringBootTest + Testcontainers PostgreSQL; apply all Flyway migrations including V7_2_*. • Seed schemes, fee configs, merchants, partners, and transactions in @BeforeEach. • Scenario A: call TransactionService.commitTransaction for LOCAL txn; query transaction_fee_snapshot and assert gme_fee_share_krw=75, zeropay_fee_share_krw=33. • Scenario B: call commitTransaction for OVERSEAS txn payout=50000; assert fee_tier=CROSSBORDER was used (verify via snapshot.merchant_fee_rate=0.0170). • Add scenario C: commit with no matching fee config -> assert FeeComputationException thrown and transaction remains uncommitted (status unchanged). | FeeSnapshotIntegrationTest with 3 scenarios, all passing against a real PostgreSQL instance via Testcontainers. | • Scenario A: transaction_fee_snapshot row exists with gme_fee_share_krw=75, van_fee_krw=12, net_merchant_fee_krw=108. • Scenario B: snapshot.merchant_fee_rate=0.0170 confirms CROSSBORDER config was used (not DOMESTIC). • Scenario C: transaction.status is unchanged (not COMMITTED) after FeeComputationException; no orphan snapshot row. • All three scenarios run within 60 seconds total (Testcontainers startup excluded). • revenue_record.estimated_fee_share_krw is populated and matches gme_fee_share_krw in the snapshot after scenarios A and B. | 55 | 7.2-T07, 7.2-T08 | BE | RATE-04, BRD-01
7.2-T13 | revenue-ledger | 7.2 | 7. Settlement, Reconciliation & Revenue | Scheme fee share (70/30) computation | 2 | Implement SchemeFeeSplitQueryService: aggregate fee share by scheme and period | WBS 7.2 reporting layer. The revenue report (PRD-07 §11.3.2) shows 'GME Scheme Share (KRW)' = 70% of net merchant fee. This requires aggregating transaction_fee_snapshot.gme_fee_share_krw grouped by scheme_id and period. Provide a query service method: FeeShareSummary aggregateByScheme(long schemeId, LocalDate from, LocalDate to). FeeShareSummary contains: schemeId, fromDate, toDate, transactionCount (long), totalGrossMerchantFeeKrw (long), totalVanFeeKrw (long), totalNetMerchantFeeKrw (long), totalGmeFeeShareKrw (long), totalZeropayFeeShareKrw (long). Use revenue_record.revenue_date for the period filter (join transaction_fee_snapshot via txn_id). Exclude refund snapshot rows from the aggregate (gme_fee_share_krw < 0) - they reduce the total automatically when summed, so actually include them (sum handles negatives). Add a separate method for partner-level breakdowns. | • Create SchemeFeeSplitQueryService in com.gme.gmepay.fees.reporting. • Implement aggregateByScheme using a JPQL or native SQL GROUP BY query on transaction_fee_snapshot JOIN revenue_record on txn_id, filtered by scheme_id and revenue_date BETWEEN from AND to. • Implement aggregateByPartner(long partnerId, long schemeId, LocalDate from, LocalDate to) -> FeeShareSummary (same shape, adds partnerId field). • Add a helper isReconciled(long schemeId, LocalDate month): returns true if all revenue_record.fee_share_confirmed=TRUE for the period. • Return FeeShareSummary with all-zero values (not null) if no rows found for the period. | SchemeFeeSplitQueryService class with aggregateByScheme, aggregateByPartner, and isReconciled methods. | • aggregateByScheme for ZeroPay, 2026-06-01 to 2026-06-30 sums gme_fee_share_krw across all transaction_fee_snapshot rows linked to that scheme and period. • Refund snapshots (negative gme_fee_share_krw) reduce the aggregate total correctly (e.g. 100 + (-30) = 70). • Period with no transactions returns FeeShareSummary with all fields = 0 (not null). • aggregateByPartner with partnerId filter only includes snapshots for transactions belonging to that partner. • isReconciled returns false if any revenue_record.fee_share_confirmed=FALSE in the period, true if all are TRUE. | 40 | 7.2-T03 | BE | RATE-04, BRD-01
7.2-T14 | revenue-ledger | 7.2 | 7. Settlement, Reconciliation & Revenue | Scheme fee share (70/30) computation | 2 | Expose internal fee share summary REST endpoint for Ops Admin portal | WBS 7.2 reporting wiring. The Ops Admin portal (PRD-07 §11.3.2) needs a REST endpoint to retrieve scheme fee share aggregates. Add GET /internal/v1/fee-share/summary?scheme_id=&from=&to= (YYYY-MM-DD dates) returning FeeShareSummary JSON. This is an internal endpoint (not partner-facing) authenticated via Ops session/JWT with role FINANCE or SUPER_ADMIN. Response fields: scheme_id, from_date, to_date, transaction_count, total_gross_merchant_fee_krw, total_van_fee_krw, total_net_merchant_fee_krw, total_gme_fee_share_krw, total_zeropay_fee_share_krw, is_reconciled. Do not expose individual transaction-level fee data; only aggregates. Add a second endpoint GET /internal/v1/fee-share/summary/by-partner?partner_id=&scheme_id=&from=&to= for partner-level drill-down. | • Create FeeShareController in com.gme.gmepay.admin.controllers package. • Implement GET /internal/v1/fee-share/summary calling SchemeFeeSplitQueryService.aggregateByScheme; validate that from <= to and date range <= 366 days. • Implement GET /internal/v1/fee-share/summary/by-partner calling aggregateByPartner. • Secure both endpoints with @PreAuthorize requiring FINANCE or SUPER_ADMIN role. • Return HTTP 400 with error code INVALID_DATE_RANGE if from > to; HTTP 400 DATE_RANGE_TOO_LARGE if range > 366 days. • Map FeeShareSummary to a response DTO with snake_case JSON field names. | FeeShareController with two GET endpoints, secured and validated, returning aggregate fee share data. | • GET /internal/v1/fee-share/summary?scheme_id=1&from=2026-06-01&to=2026-06-30 returns HTTP 200 with correct totals for seeded data. • A request with PARTNER role returns HTTP 403 Forbidden. • from > to returns HTTP 400 with error_code INVALID_DATE_RANGE. • date range of 400 days returns HTTP 400 with error_code DATE_RANGE_TOO_LARGE. • by-partner endpoint returns only aggregates for the specified partner_id; a different partner_id returns zeros for the same period. | 40 | 7.2-T13 | BE | RATE-04, BRD-01
7.2-T15 | revenue-ledger | 7.2 | 7. Settlement, Reconciliation & Revenue | Scheme fee share (70/30) computation | 2 | Add monthly fee-share reconciliation flag update: mark revenue_record.fee_share_confirmed | WBS 7.2 reconciliation. Per RATE-04 §13.4: 'Scheme fee share: 70% x (ZeroPay reported net merchant fee total for the period). Reconcile against monthly ZeroPay fee share statement.' When ZeroPay's monthly fee share statement is loaded (manually by Finance in Phase 1), the system must compare the statement total against sum(gme_fee_share_krw) for the period and mark revenue_record.fee_share_confirmed=TRUE on all matched rows. Add a service method: ReconciliationResult reconcileSchemeShare(long schemeId, LocalDate month, long schemeReportedNetFeeKrw). If abs(schemeReportedNetFeeKrw - sum(gme_fee_share_krw)) > tolerance (tolerance = 100 KRW, i.e. 1 KRW rounding per transaction is acceptable for large batches), return DISCREPANCY; otherwise update all revenue_record.fee_share_confirmed=TRUE for the month and return MATCHED. | • Create FeeShareReconciliationService in com.gme.gmepay.fees.reconciliation. • Implement reconcileSchemeShare: call aggregateByScheme for the month, compare totalGmeFeeShareKrw against schemeReportedNetFeeKrw within tolerance. • On MATCHED: batch-UPDATE revenue_record SET fee_share_confirmed=TRUE WHERE scheme_id=? AND revenue_date BETWEEN first-of-month AND last-of-month AND fee_share_confirmed=FALSE. • On DISCREPANCY: do NOT update; return ReconciliationResult with delta_krw field showing the difference. • Log the reconciliation action to audit_log: actor=SYSTEM, action=FEE_SHARE_RECONCILIATION, entity_type=REVENUE_RECORD, detail JSON with scheme_id, month, computed_total, reported_total, result. | FeeShareReconciliationService with reconcileSchemeShare method; audit log entry on every reconciliation attempt. | • reconcileSchemeShare with schemeReportedNetFeeKrw exactly equal to sum(gme_fee_share_krw) returns MATCHED and all revenue_record rows for the month have fee_share_confirmed=TRUE. • reconcileSchemeShare with delta > 100 KRW returns DISCREPANCY and no revenue_record rows are updated. • reconcileSchemeShare with delta <= 100 KRW (tolerance) returns MATCHED. • An audit_log row is written for both MATCHED and DISCREPANCY outcomes. • Calling reconcileSchemeShare twice for the same MATCHED month is idempotent (already-confirmed rows are not double-updated; return MATCHED). | 45 | 7.2-T13, 7.2-T03 | BE | RATE-04, BRD-01
7.2-T16 | revenue-ledger | 7.2 | 7. Settlement, Reconciliation & Revenue | Scheme fee share (70/30) computation | 2 | Add unit tests for FeeShareReconciliationService | WBS 7.2 unit tests for reconciliation (T15). Mock SchemeFeeSplitQueryService and RevenueRecordRepository. Test vectors: (A) reported=108, computed=108 -> MATCHED, confirm update called. (B) reported=200, computed=108 -> DISCREPANCY (delta=92 <= 100, so MATCHED by tolerance). Wait - tolerance is 100 KRW: abs(200-108)=92 < 100 -> MATCHED. (C) reported=209, computed=108 -> delta=101 > 100 -> DISCREPANCY, no update. (D) No transactions for month (totalGmeFeeShareKrw=0), reported=0 -> MATCHED. (E) No transactions for month, reported=500 -> DISCREPANCY. Audit log: verify audit_log entry written for both MATCHED and DISCREPANCY cases. | • Create FeeShareReconciliationServiceTest in src/test/java/com/gme/gmepay/fees/reconciliation/. • Mock SchemeFeeSplitQueryService to return FeeShareSummary with totalGmeFeeShareKrw=108. • Test A: reported=108 -> MATCHED; verify batch-update called. • Test B: reported=200 -> delta=92 -> MATCHED (within tolerance); verify update called. • Test C: reported=209 -> delta=101 -> DISCREPANCY; verify update NOT called. • Test D: totalGmeFeeShareKrw=0, reported=0 -> MATCHED. • Test E: totalGmeFeeShareKrw=0, reported=500 -> DISCREPANCY. • Verify audit_log.save() called for all 5 scenarios with correct result field. | FeeShareReconciliationServiceTest with 5 passing tests covering tolerance boundary and audit log verification. | • Test A: MATCHED returned and revenueRecordRepository.bulkConfirm called once. • Test B: reported=200, computed=108, delta=92 < 100 returns MATCHED (tolerance boundary inclusive). • Test C: reported=209, computed=108, delta=101 > 100 returns DISCREPANCY and bulkConfirm NOT called. • Test D and E: zero-transaction scenarios return correct result without NPE. • All 5 tests: auditLogRepository.save() called exactly once per reconciliation attempt regardless of result. | 35 | 7.2-T15 | BE | RATE-04, BRD-01
7.2-T17 | revenue-ledger | 7.2 | 7. Settlement, Reconciliation & Revenue | Scheme fee share (70/30) computation | 2 | Add scheme_fee_config admin API: view and upsert fee rates via Ops portal | WBS 7.2 operational support. Ops must be able to view and update the merchant fee rate table and VAN fee rate table per scheme without code deployment (BRD-01: config-not-code). Add internal endpoints: GET /internal/v1/schemes/{schemeId}/fee-config returns all scheme_fee_config rows for the scheme. POST /internal/v1/schemes/{schemeId}/fee-config upserts a row (or inserts with new effective_from date to create a new rate period). Secured with SUPER_ADMIN role only. All changes must be audit-logged: actor, timestamp, previous value, new value. gme_fee_share_pct is on qr_scheme not scheme_fee_config - a separate PATCH /internal/v1/schemes/{schemeId} endpoint (if not already implemented) handles that field. | • Create FeeConfigAdminController in com.gme.gmepay.admin.controllers. • Implement GET /internal/v1/schemes/{schemeId}/fee-config: return list of FeeConfigResponse DTOs ordered by fee_tier, merchant_type, effective_from DESC. • Implement POST /internal/v1/schemes/{schemeId}/fee-config: accept FeeConfigRequest (merchantType, feeTier, merchantFeeRate, vanFeeRate, effectiveFrom); validate vanFeeRate < merchantFeeRate; insert new row. • On insert: write audit_log entry with action=CREATE, entity_type=SCHEME_FEE_CONFIG, previous_value=null, new_value=JSON of the new row. • Secure both endpoints with @PreAuthorize(SUPER_ADMIN); return HTTP 403 for other roles. • Return HTTP 409 CONFLICT if a row with identical (schemeId, merchantType, feeTier, effectiveFrom) already exists. | FeeConfigAdminController with GET and POST endpoints, audit logging, and role enforcement. | • GET /internal/v1/schemes/1/fee-config returns all seeded rows with correct merchantFeeRate and vanFeeRate values. • POST with new merchantType=FRANCHISE, feeTier=DOMESTIC, effectiveFrom=2027-01-01 creates a new row and audit_log entry with action=CREATE. • POST with vanFeeRate >= merchantFeeRate returns HTTP 400 with error_code INVALID_FEE_RATES. • POST with duplicate (schemeId, merchantType, feeTier, effectiveFrom) returns HTTP 409. • A request authenticated with FINANCE role returns HTTP 403 for the POST endpoint. | 45 | 7.2-T04, 7.2-T01 | BE | RATE-04, BRD-01
7.2-T18 | revenue-ledger | 7.2 | 7. Settlement, Reconciliation & Revenue | Scheme fee share (70/30) computation | 2 | Add fee share display to Ops Admin settlement batch status view | WBS 7.2 UI data wiring. PRD-07 §11.2.2 'Batch Status View' requires a column 'GME Fee Share (KRW) = 70% of net merchant fee'. This is an aggregate: sum(transaction_fee_snapshot.gme_fee_share_krw) for all transactions in the settlement batch for the given settlement_date and scheme. The existing batch status endpoint (if implemented) must be extended; if not yet present, add GET /internal/v1/settlement/batch-status?settlement_date=&scheme_id= and include fee_share_krw in the response. The endpoint is read-only. Join transaction_fee_snapshot to transactions via txn_id, filter by settlement_date (use transaction.completed_at::date = settlement_date or transaction.settlement_date if that field exists). | • Locate or create the settlement batch status endpoint handler. • Add a query to sum transaction_fee_snapshot.gme_fee_share_krw for all transactions with the given settlement_date and scheme_id. • Add field gme_fee_share_krw (long) to the BatchStatusResponse DTO. • Add field net_settlement_krw (long) = gross_payout_krw - gme_fee_share_krw for DOMESTIC transactions; for INTERNATIONAL (OVERSEAS) net_settlement_krw = gross_payout_krw (fee not deducted from settlement). • Secure with FINANCE or SUPER_ADMIN role. • Return gme_fee_share_krw=0 (not null) if no fee snapshots exist for the date/scheme. | Updated settlement batch status endpoint returning gme_fee_share_krw and net_settlement_krw for the given date and scheme. | • GET /internal/v1/settlement/batch-status?settlement_date=2026-06-05&scheme_id=1 returns gme_fee_share_krw equal to the sum of all snapshot gme_fee_share_krw values for that date. • For a date with no transactions, gme_fee_share_krw=0 is returned (not null, not 404). • net_settlement_krw for a DOMESTIC batch = gross_payout_krw - gme_fee_share_krw. • net_settlement_krw for a CROSSBORDER/OVERSEAS batch = gross_payout_krw (GME does not deduct from settlement for international; invoices separately). • PARTNER role returns HTTP 403. | 40 | 7.2-T13 | BE | RATE-04, BRD-01
7.2-T19 | revenue-ledger | 7.2 | 7. Settlement, Reconciliation & Revenue | Scheme fee share (70/30) computation | 2 | Document SchemeFeeSplitCalculator and 70/30 formula in code-level Javadoc and package README | WBS 7.2 docs ticket. A developer joining the team must be able to understand the scheme fee share formula purely from code-level documentation without reading spec_full.txt. Document: (1) The formula chain: gross_merchant_fee_krw = floor(payout_amount_krw x merchant_fee_rate); net_merchant_fee_krw = gross - van; gme_fee_share_krw = floor(net x gme_fee_share_pct); zeropay_fee_share_krw = net - gme; (2) why floor is used (whole KRW, invariant preservation); (3) that gme_fee_share_pct=0.70 for ZeroPay (ZeroPay retains 30%); (4) that VAN fee is deducted before the split (per spec assumption A-05); (5) that service_charge is separate and never enters this computation. Add a package-level README.md in src/main/java/com/gme/gmepay/fees/. | • Add class-level Javadoc to SchemeFeeSplitCalculator explaining the formula chain with a worked numeric example (payout=15000, rate=0.80%, van=0.08%, gme=70%: gross=120, van=12, net=108, gme=75, zeropay=33). • Add method-level Javadoc to calculate() listing each parameter, return type, and the RoundingMode.FLOOR rationale. • Add class-level Javadoc to FeeSnapshotService explaining when captureFeeSplit is called (at commit, within @Transactional) and the status guard. • Create src/main/java/com/gme/gmepay/fees/README.md: one-page overview of the fees package, classes, formula, and configuration (pointing to scheme_fee_config table). • Add a NOTE in the README: 'gme_fee_share_pct is a ZeroPay-specific agreement (70/30); other schemes may configure a different value via qr_scheme.gme_fee_share_pct'. | Javadoc on SchemeFeeSplitCalculator, FeeSnapshotService, and a fees/README.md file covering the formula, rounding rationale, and configuration pointers. | • SchemeFeeSplitCalculator class Javadoc includes the worked numeric example with all 5 output values. • calculate() method Javadoc names every parameter and states RoundingMode.FLOOR is used. • fees/README.md exists under src/main/java/com/gme/gmepay/fees/ and contains the formula chain in a readable format. • README explicitly states that service_charge is outside this computation (no double-counting risk). • README notes that gme_fee_share_pct is scheme-specific and configurable via qr_scheme.gme_fee_share_pct. | 30 | 7.2-T05, 7.2-T06 | BE | RATE-04, BRD-01
7.3-T01 | revenue-ledger | 7.3 | 7. Settlement, Reconciliation & Revenue | FX margin + service fee capture | 2 | Create revenue_record table migration (Flyway V7_3_1) | WBS 7.3. DAT-03 §8.2 defines the revenue_record table: tracks one row per committed transaction for FX margin and service fee revenue reporting. Columns: id BIGINT PK, txn_id BIGINT FK->transaction (UNIQUE, NOT NULL), partner_id BIGINT FK->partner (NOT NULL), scheme_id BIGINT FK->qr_scheme (NOT NULL), revenue_date DATE NOT NULL, fx_margin_usd DECIMAL(20,4) NOT NULL (= collection_margin_usd + payout_margin_usd; 0.0000 for same-currency), service_charge_amount DECIMAL(20,4) NOT NULL (flat fee in settle_a_ccy; 0 allowed), service_charge_ccy CHAR(3) NOT NULL, fee_share_pct DECIMAL(6,4) NOT NULL (e.g. 0.7000 for ZeroPay 70%), estimated_fee_share_usd DECIMAL(20,4) (estimated at commit; confirmed from scheme settlement), created_at TIMESTAMPTZ DEFAULT now(), updated_at TIMESTAMPTZ DEFAULT now(). IMPORTANT: use DECIMAL/NUMERIC only — no FLOAT. txn_id must have a UNIQUE constraint to prevent duplicate revenue rows per transaction. | • Create db/migrations/V7_3_1__create_revenue_record.sql. • Write CREATE TABLE revenue_record with all columns per the schema above; DECIMAL for all monetary amounts. • Add UNIQUE constraint on txn_id column (one revenue row per transaction). • Add FK constraints: txn_id -> transaction(id), partner_id -> partner(id), scheme_id -> qr_scheme(id). • Add indexes: (partner_id, revenue_date), (scheme_id, revenue_date), (revenue_date) for reporting queries. • Run Flyway migrate in dev; verify table exists with \d revenue_record. | db/migrations/V7_3_1__create_revenue_record.sql applied cleanly to local PostgreSQL | • Table revenue_record exists after migration; all 14 columns present with correct types (DECIMAL not FLOAT). • UNIQUE constraint on txn_id — inserting two rows with the same txn_id raises a unique-violation error. • FKs are enforced: inserting a row with a non-existent txn_id raises a FK-violation error. • Indexes (partner_id, revenue_date) and (scheme_id, revenue_date) appear in pg_indexes. • Migration is idempotent via Flyway checksum — re-running does not duplicate the table. | 35 |  | BE | RATE-04
7.3-T02 | revenue-ledger | 7.3 | 7. Settlement, Reconciliation & Revenue | FX margin + service fee capture | 2 | Define RevenueRecord JPA entity | WBS 7.3. The revenue_record table (created in 7.3-T01) needs a JPA entity. Fields map directly: id (Long, @GeneratedValue), txnId (Long, unique), partnerId (Long), schemeId (Long), revenueDate (LocalDate), fxMarginUsd (BigDecimal, precision=20, scale=4), serviceChargeAmount (BigDecimal, precision=20, scale=4), serviceChargeCcy (String, length=3), feeSharePct (BigDecimal, precision=6, scale=4), estimatedFeeShareUsd (BigDecimal, precision=20, scale=4, nullable), createdAt (OffsetDateTime), updatedAt (OffsetDateTime). Use BigDecimal for all monetary fields — never Double or Float. fxMarginUsd must be NOT NULL with @Column(nullable=false). | • Create domain/model/RevenueRecord.java annotated with @Entity @Table(name="revenue_record"). • Map all columns per the schema; annotate monetary fields with @Column(precision=20, scale=4). • Add @Column(unique=true, nullable=false) on txnId. • Annotate createdAt with @CreationTimestamp and updatedAt with @UpdateTimestamp. • Add a static factory method RevenueRecord.of(Transaction txn, BigDecimal fxMarginUsd, BigDecimal serviceChargeAmount, String serviceChargeCcy, BigDecimal feeSharePct, BigDecimal estimatedFeeShareUsd) that sets revenueDate = txn.committedAt.toLocalDate() and populates all fields. | domain/model/RevenueRecord.java — JPA entity with static factory method | • Class compiles and Hibernate schema-validation passes against the V7_3_1 migration. • factory method sets fxMarginUsd = provided value, revenueDate = committedAt.toLocalDate() of the passed transaction. • BigDecimal field precision/scale annotations match the SQL DECIMAL(20,4) definition — mismatches would cause Hibernate validation failure. • txnId has @Column(unique=true, nullable=false) — entity validation rejects null txnId at persist time. • No primitive double or float fields present. | 30 | 7.3-T01 | BE | RATE-04
7.3-T03 | revenue-ledger | 7.3 | 7. Settlement, Reconciliation & Revenue | FX margin + service fee capture | 2 | Create RevenueRecordRepository with query methods | WBS 7.3. The revenue_record table needs a Spring Data JPA repository for (a) save/insert at commit time and (b) aggregate queries for the Finance reporting view (Admin Portal §11.3.2). Required query methods: findByTxnId(Long txnId) for idempotency check; sumFxMarginUsdByPartnerIdAndRevenueDateBetween(Long partnerId, LocalDate start, LocalDate end) using a @Query; sumServiceChargeAmountBySchemeIdAndRevenueDateBetween for the daily close reconciliation. Also provide findAllByRevenueDateBetween(LocalDate start, LocalDate end, Pageable) for CSV export. | • Create repository/RevenueRecordRepository.java extending JpaRepository<RevenueRecord, Long>. • Add Optional<RevenueRecord> findByTxnId(Long txnId). • Add @Query("SELECT COALESCE(SUM(r.fxMarginUsd), 0) FROM RevenueRecord r WHERE r.partnerId = :partnerId AND r.revenueDate BETWEEN :start AND :end") BigDecimal sumFxMarginUsdByPartnerAndDateRange(...). • Add equivalent sumServiceChargeAmountBySchemeIdAndDateRange query. • Add Page<RevenueRecord> findAllByRevenueDateBetween(LocalDate start, LocalDate end, Pageable pageable). | repository/RevenueRecordRepository.java with 5 query methods | • findByTxnId returns Optional.empty() when no matching row; returns the record when one exists. • sumFxMarginUsd returns COALESCE 0 (BigDecimal) when no rows match the date range — not null. • Aggregate query groups correctly: partner A rows are not included in partner B sum. • findAllByRevenueDateBetween respects pageable parameters (page 0 size 10 returns at most 10 rows). • Spring context loads without JPQL parse errors. | 30 | 7.3-T02 | BE | RATE-04
7.3-T04 | revenue-ledger | 7.3 | 7. Settlement, Reconciliation & Revenue | FX margin + service fee capture | 2 | Define RevenueCapture value object for rate-engine output | WBS 7.3. The rate engine (5-step sequence per RATE-04) produces collection_margin_usd and payout_margin_usd (both DECIMAL(20,8)) plus service_charge (DECIMAL(20,4) in settle_a_ccy). At commit time these values are locked onto the transaction record. A dedicated value object carries these fields through the commit pipeline so each layer receives strongly-typed revenue data. fx_margin_usd = collection_margin_usd + payout_margin_usd (computed at construction). For same-currency short-circuit transactions collection_margin_usd = payout_margin_usd = 0 and fx_margin_usd = 0; service_charge is still present. | • Create domain/model/RevenueCapture.java as an immutable value object (final class, all-args constructor, getters only). • Fields: collectionMarginUsd (BigDecimal), payoutMarginUsd (BigDecimal), fxMarginUsd (BigDecimal, = collectionMarginUsd + payoutMarginUsd), serviceChargeAmount (BigDecimal), serviceChargeCcy (String). • Validate in constructor: collectionMarginUsd >= 0, payoutMarginUsd >= 0, serviceChargeAmount >= 0; throw IllegalArgumentException on violation. • Add static factory RevenueCapture.fromPoolValues(BigDecimal collMargin, BigDecimal payMargin, BigDecimal serviceCharge, String serviceChargeCcy). • Add static RevenueCapture zeroCrossBorder(BigDecimal serviceCharge, String serviceChargeCcy) for same-currency short-circuit (margins = 0). | domain/model/RevenueCapture.java — immutable value object with two factory methods | • fromPoolValues(0.3697, 0.3697, 0.36, "USD").getFxMarginUsd() == 0.7394 (BigDecimal equality). • zeroCrossBorder(500, "KRW").getFxMarginUsd() == 0 and getCollectionMarginUsd() == 0. • Constructor throws IllegalArgumentException for negative collectionMarginUsd (e.g. -0.01). • fxMarginUsd is always exactly collectionMarginUsd + payoutMarginUsd — no separate assignment path can diverge. • Class is final and all fields are final — no mutators. | 25 |  | BE | RATE-04
7.3-T05 | revenue-ledger | 7.3 | 7. Settlement, Reconciliation & Revenue | FX margin + service fee capture | 2 | Implement service-charge tier resolution logic | WBS 7.3. DAT-03 §4.7 describes optional volume-tier overrides for service_charge indexed by collection_usd. Table service_charge_tier: rule_id FK, min_collection_usd DECIMAL(20,4) inclusive, max_collection_usd DECIMAL(20,4) exclusive (NULL = no cap), charge_amount DECIMAL(20,4) in rule's settle_a_ccy. If no tiers exist OR tier table is disabled, fall back to rule.service_charge_amount (the flat charge). Tier selection: find the single tier where collection_usd >= min AND (collection_usd < max OR max IS NULL). If no tier matches (gap in range), fall back to flat. If two tiers overlap (misconfiguration), take the first by min_collection_usd ascending. | • Create service/rate/ServiceChargeTierResolver.java with method: BigDecimal resolve(Rule rule, List<ServiceChargeTier> tiers, BigDecimal collectionUsd). • If tiers is null or empty, return rule.getServiceChargeAmount(). • Sort tiers by minCollectionUsd ascending. • Iterate; return tier.chargeAmount for the first tier where collectionUsd >= tier.min AND (tier.max == null OR collectionUsd < tier.max). • If no tier matches, fall back to rule.getServiceChargeAmount() (gap or disabled table). • Add Javadoc: same-currency short-circuit passes collectionUsd = null -> always returns flat charge. | service/rate/ServiceChargeTierResolver.java with resolve() method | • resolve(rule[flat=500], [], 36.97) returns 500 (no tiers, flat). • resolve(rule[flat=500], [tier: 0-50 -> 400, 50-null -> 300], 36.97) returns 400 (falls in 0-50 range). • resolve(rule[flat=500], [tier: 0-50 -> 400, 50-null -> 300], 75.00) returns 300 (above 50). • resolve(rule[flat=500], [tier: 10-50 -> 400], 5.00) returns 500 (below tier min, gap fallback). • resolve(rule, tiers, null) returns flat charge (same-currency short-circuit path). | 35 |  | BE | RATE-04
7.3-T06 | revenue-ledger | 7.3 | 7. Settlement, Reconciliation & Revenue | FX margin + service fee capture | 2 | Add revenue extraction to RateEngineService.computeQuote() | WBS 7.3. The rate engine executes the 5-step RECEIVE-mode sequence (RATE-04): Step 1 payout_usd_cost = target_payout / cost_rate_pay; Step 2 collection_usd = payout_usd_cost / (1 - m_a - m_b); Step 3a collection_margin_usd = collection_usd * m_a; Step 3b payout_margin_usd = collection_usd * m_b; Step 4 send_amount = collection_usd * cost_rate_coll; Step 5 collection_amount = send_amount + service_charge. After Step 3, the engine must construct a RevenueCapture value object (7.3-T04) from collection_margin_usd, payout_margin_usd, service_charge (resolved via ServiceChargeTierResolver, 7.3-T05). For same-currency short-circuit, use RevenueCapture.zeroCrossBorder(). The RevenueCapture is included in the RateQuote return value so it travels to CommitTransaction without recalculation. | • Locate (or create) service/rate/RateEngineService.java computeQuote() method. • After computing collection_margin_usd and payout_margin_usd (Step 3), call ServiceChargeTierResolver.resolve() to get effective service_charge. • Call RevenueCapture.fromPoolValues(collectionMarginUsd, payoutMarginUsd, resolvedServiceCharge, rule.getServiceChargeCcy()). • For same-currency path call RevenueCapture.zeroCrossBorder(resolvedServiceCharge, rule.getServiceChargeCcy()). • Add revenueCapture field to RateQuote (or existing quote response DTO) and populate it. • Ensure service_charge used in Step 5 (collection_amount = send_amount + service_charge) equals the same resolved value stored in RevenueCapture. | RateEngineService.computeQuote() returns a RateQuote containing a non-null RevenueCapture | • For target_payout=13500 KRW, cost_rate_pay=1350, cost_rate_coll=3500, m_a=0.015, m_b=0.010, flat service_charge=500 MNT: revenueCapture.collectionMarginUsd = 0.1538, payoutMarginUsd = 0.1026, fxMarginUsd = 0.2564, serviceChargeAmount = 500, serviceChargeCcy = MNT. • Same-currency path (collection=settle_a=settle_b=payout=KRW): revenueCapture.fxMarginUsd = 0, serviceChargeAmount = 500 KRW. • Tiered service charge overrides flat: if tier for collectionUsd=10.2564 returns 400 MNT, serviceChargeAmount = 400. • collection_amount in the quote equals send_amount + revenueCapture.serviceChargeAmount (not the flat rule value when tier applies). • RevenueCapture is not null for any path (cross-border or same-currency). | 50 | 7.3-T04, 7.3-T05 | BE | RATE-04
7.3-T07 | revenue-ledger | 7.3 | 7. Settlement, Reconciliation & Revenue | FX margin + service fee capture | 2 | Persist revenue_record atomically in CommitTransactionService | WBS 7.3. DAT-03 §8.2: revenue_record is populated on transaction commitment. The CommitTransaction flow: (1) validate quote not expired; (2) rate-lock all USD-pool values onto transaction row; (3) INSERT revenue_record in the same DB transaction so revenue capture is atomic with transaction commit. If the transaction rolls back (e.g. pool identity failure), the revenue_record row must also roll back. Inputs: the locked transaction entity (carrying collection_margin_usd, payout_margin_usd, service_charge, service_charge_ccy from rate-lock) and the scheme's gme_fee_share_pct (from qr_scheme table, e.g. 0.7000 for ZeroPay). fx_margin_usd = collection_margin_usd + payout_margin_usd. estimated_fee_share_usd is not populated by this work-package (scheme fee share is a separate revenue stream — leave as NULL or delegate to WBS 7.4). | • Locate (or create) service/payment/CommitTransactionService.java. • After the transaction entity has been rate-locked (all USD-pool fields written), call RevenueRecordRepository.findByTxnId(txn.getId()) — if a row already exists, skip INSERT (idempotency guard). • Build a RevenueRecord using RevenueRecord.of(...) with fx_margin_usd = txn.collectionMarginUsd + txn.payoutMarginUsd, serviceChargeAmount = txn.serviceCharge, serviceChargeCcy = txn.serviceChargeCcy, feeSharePct = scheme.gmeFeeSharePct. • Call RevenueRecordRepository.save(revenueRecord) inside the same @Transactional boundary as the transaction row update. • Log at INFO: txn_ref, fx_margin_usd, service_charge_amount, revenue_date for observability. • Do NOT call any external system or send events during this step — pure DB write. | CommitTransactionService inserts revenue_record atomically with the transaction commit | • After CommitTransactionService.commit(txn), a revenue_record row exists with txn_id = txn.id and fx_margin_usd = collection_margin_usd + payout_margin_usd. • If CommitTransactionService throws (simulated DB error after rate-lock but before revenue INSERT), both the transaction update and revenue_record INSERT are rolled back (no orphan revenue row). • Calling commit() twice for the same txn_id inserts only one revenue_record row (idempotency guard fires on second call). • Same-currency transaction: revenue_record row has fx_margin_usd = 0.0000 and service_charge_amount = actual service charge (e.g. 500 KRW). • revenue_date = committed_at.toLocalDate() in the server timezone (UTC or configured zone — consistent with transaction.committed_at). | 50 | 7.3-T02, 7.3-T03, 7.3-T06 | BE | RATE-04
7.3-T08 | revenue-ledger | 7.3 | 7. Settlement, Reconciliation & Revenue | FX margin + service fee capture | 2 | Validate pool identity before revenue capture at commit | WBS 7.3 / RATE-04 §11.2. Before persisting a revenue_record the CommitTransactionService must assert the pool identity invariant: ¦collection_usd - collection_margin_usd - payout_margin_usd - payout_usd_cost¦ < 0.01 USD. If the assertion fails, throw PoolIdentityFailureException (internal error code POOL_IDENTITY_FAILURE) and do NOT commit the transaction or insert a revenue_record. For same-currency short-circuit transactions (is_same_ccy_shortcircuit = true), collection_usd / payout_usd_cost are NULL — skip the check. The tolerance is exactly 0.01 USD (use BigDecimal.valueOf(0.01)). | • Create service/rate/PoolIdentityValidator.java with void assertValid(TransactionEntity txn) method. • If txn.isSameCcyShortcircuit() return immediately (no check needed). • Compute delta = txn.collectionUsd.subtract(txn.collectionMarginUsd).subtract(txn.payoutMarginUsd).subtract(txn.payoutUsdCost).abs(). • If delta.compareTo(BigDecimal.valueOf(0.01)) > 0, throw new PoolIdentityFailureException(txn.getTxnRef(), delta). • Create PoolIdentityFailureException extending RuntimeException with fields txnRef and delta (BigDecimal). • Call assertValid() in CommitTransactionService BEFORE the revenue_record INSERT (7.3-T07). | PoolIdentityValidator.java and PoolIdentityFailureException.java; integrated into commit pipeline | • assertValid passes for: collection_usd=10.2564, collection_margin_usd=0.1538, payout_margin_usd=0.1026, payout_usd_cost=10.0000 (delta=0.0000 < 0.01). • assertValid throws PoolIdentityFailureException for delta=0.0150 (exceeds tolerance). • assertValid passes at boundary: delta=0.0099 < 0.01 (within tolerance). • assertValid skips check and returns normally when isSameCcyShortcircuit=true (even if USD pool fields are null). • CommitTransactionService rolls back transaction and produces no revenue_record row when PoolIdentityFailureException is thrown. | 40 | 7.3-T07 | BE | RATE-04
7.3-T09 | revenue-ledger | 7.3 | 7. Settlement, Reconciliation & Revenue | FX margin + service fee capture | 2 | Handle same-currency short-circuit revenue path in CommitTransactionService | WBS 7.3. For same-currency transactions (e.g. GME Remit on ZeroPay, all KRW, is_same_ccy_shortcircuit=true): USD pool is skipped entirely; collection_usd, payout_usd_cost, collection_margin_usd, payout_margin_usd are all NULL or 0 (RATE-04 §7.1). Revenue capture for this case: fx_margin_usd = 0.0000 (no FX margin); service_charge_amount = flat charge from rule (e.g. 500 KRW) — still recorded as GMEPay+ revenue per business rule A-04. The revenue_record row MUST still be inserted. collection_amount = target_payout + service_charge. Margin fields on transaction record are NULL for same-currency. CommitTransactionService must branch on is_same_ccy_shortcircuit when computing fx_margin_usd for the revenue_record. | • In CommitTransactionService, add an if-branch: if txn.isSameCcyShortcircuit(), set fxMarginUsd = BigDecimal.ZERO; else fxMarginUsd = txn.collectionMarginUsd.add(txn.payoutMarginUsd). • Ensure service_charge_amount and service_charge_ccy are still read from txn.serviceCharge and txn.serviceChargeCcy for both branches. • Pass fxMarginUsd = 0, serviceChargeAmount = txn.serviceCharge into RevenueRecord.of() for the same-currency case. • Add an integration assertion: for same-currency txn, revenue_record.fx_margin_usd = 0 and revenue_record.service_charge_amount > 0 when service charge is configured. • Add logging: 'same-currency revenue: fx_margin=0, service_charge=<amount> <ccy>'. | CommitTransactionService correctly handles same-currency revenue path with fx_margin_usd=0 | • For a KRW same-currency transaction with service_charge=500, revenue_record.fx_margin_usd = 0.0000 and service_charge_amount = 500. • For a same-currency transaction with service_charge=0, revenue_record.service_charge_amount = 0.0000 (valid — GME Remit may have zero charge in some rules). • No NullPointerException when txn.collectionMarginUsd is NULL (same-currency path stores NULL). • Cross-border path unaffected: fx_margin_usd = collection_margin_usd + payout_margin_usd as before. • revenue_record row is still inserted for same-currency transactions (not skipped). | 35 | 7.3-T07 | BE | RATE-04
7.3-T10 | revenue-ledger | 7.3 | 7. Settlement, Reconciliation & Revenue | FX margin + service fee capture | 2 | Validate m_a + m_b >= 2% minimum margin at rule save (Admin guard) | WBS 7.3 / RATE-04 §11.3. Business rule: m_a + m_b >= 2.0% (0.02 as decimal fraction) is a hard constraint for all cross-border rules. 0% is allowed only for same-currency rules (is_same_ccy_shortcircuit = true). This is enforced at rule-save time in the Admin System backend, not just at runtime. The rule entity has fields m_a DECIMAL(6,6) and m_b DECIMAL(6,6). The database also has a CHECK constraint (from WBS 1.x rule migration): CHECK (is_same_ccy_shortcircuit OR (m_a + m_b) >= 0.02). The service-layer guard must catch this BEFORE the DB round-trip. Error to surface to Admin UI: MARGIN_BELOW_MINIMUM. | • Create (or extend) service/admin/RuleValidationService.java with method void validateMargins(Rule rule). • If rule.isSameCcyShortcircuit(): assert m_a == 0 AND m_b == 0; else throw MarginValidationException(SAME_CCY_NONZERO_MARGIN). • Else: assert m_a.add(m_b).compareTo(BigDecimal.valueOf(0.02)) >= 0; else throw MarginValidationException(MARGIN_BELOW_MINIMUM). • Also assert m_a >= 0 and m_b >= 0 (individual non-negativity). • Also assert m_a.add(m_b).compareTo(BigDecimal.ONE) < 1 (sum < 100%, division-by-zero guard). • Call validateMargins() from the rule create/update service path before any DB write. | RuleValidationService.validateMargins() integrated into rule-save path; MarginValidationException defined | • m_a=0.010, m_b=0.010 (combined 2.0%) passes without exception. • m_a=0.010, m_b=0.009 (combined 1.9%) throws MarginValidationException with code MARGIN_BELOW_MINIMUM. • Same-currency rule with m_a=0, m_b=0 passes. • Same-currency rule with m_a=0.005 throws MarginValidationException with code SAME_CCY_NONZERO_MARGIN. • m_a=-0.005 throws (negative margin guard). | 35 |  | BE | RATE-04
7.3-T11 | revenue-ledger | 7.3 | 7. Settlement, Reconciliation & Revenue | FX margin + service fee capture | 2 | Validate margins at runtime in RateEngineService (guard layer) | WBS 7.3 / RATE-04 §11.1. The rate engine must also guard against invalid margins at quote time (defence-in-depth: Admin can be bypassed by direct DB writes). Guards required: (a) m_a >= 0 and m_b >= 0 else INVALID_MARGIN; (b) m_a + m_b < 1.0 else INVALID_MARGIN (division-by-zero guard); (c) for cross-border: m_a + m_b >= 0.02 else MARGIN_BELOW_MINIMUM; (d) for same-currency: m_a == 0 and m_b == 0 else INVALID_MARGIN. These checks occur BEFORE the 5-step pool calculation. Throw typed RateEngineException(errorCode) where errorCode is one of the above string constants. | • In RateEngineService.computeQuote(), add pre-calculation margin guards as the first executable block. • Check m_a.compareTo(BigDecimal.ZERO) < 0 or m_b.compareTo(BigDecimal.ZERO) < 0 -> throw RateEngineException(INVALID_MARGIN). • Check m_a.add(m_b).compareTo(BigDecimal.ONE) >= 0 -> throw RateEngineException(INVALID_MARGIN). • If !isSameCurrency: check m_a.add(m_b).compareTo(BigDecimal.valueOf(0.02)) < 0 -> throw RateEngineException(MARGIN_BELOW_MINIMUM). • If isSameCurrency: check m_a != 0 or m_b != 0 -> throw RateEngineException(INVALID_MARGIN). • Ensure all guard checks use BigDecimal.compareTo(), never == or .equals() on raw doubles. | RateEngineService.computeQuote() with all 5 margin guard checks before pool calculation | • m_a=0.015, m_b=0.010 on cross-border rule: no exception thrown, engine proceeds to Step 1. • m_a=0.010, m_b=0.009 on cross-border rule: throws RateEngineException with code MARGIN_BELOW_MINIMUM. • m_a=-0.001 throws RateEngineException with code INVALID_MARGIN. • m_a=0.60, m_b=0.50 (sum=1.1) throws RateEngineException with code INVALID_MARGIN (division-by-zero guard). • Same-currency rule with m_a=0.005 throws RateEngineException with code INVALID_MARGIN. | 30 | 7.3-T06 | BE | RATE-04
7.3-T12 | revenue-ledger | 7.3 | 7. Settlement, Reconciliation & Revenue | FX margin + service fee capture | 2 | Validate service charge non-negativity in rate engine | WBS 7.3 / RATE-04 §11.1. Guard: service_charge >= 0 is required before Step 5. A negative service charge (data entry error in Admin) must cause error INVALID_SERVICE_CHARGE rather than producing a silently wrong collection_amount. Check occurs after tier resolution (ServiceChargeTierResolver returns the effective charge) and before Step 5 in computeQuote(). Both the flat charge and any tier-resolved override must be non-negative. Zero is valid (domestic rules may have no service charge). | • After ServiceChargeTierResolver.resolve() returns effectiveServiceCharge in computeQuote(), add: if effectiveServiceCharge.compareTo(BigDecimal.ZERO) < 0, throw RateEngineException(INVALID_SERVICE_CHARGE). • Add the same guard in ServiceChargeTierResolver.resolve(): if a tier's chargeAmount < 0, throw RateEngineException(INVALID_SERVICE_CHARGE). • Ensure zero service charge passes without exception. • Add a check that service_charge_ccy is a 3-char ISO code (non-blank); throw INVALID_SERVICE_CHARGE if blank. • Unit tests for this guard are in 7.3-T20. | RateEngineService and ServiceChargeTierResolver throw INVALID_SERVICE_CHARGE on negative or blank-ccy service charges | • Flat service_charge = 0 passes (zero is valid). • Flat service_charge = 500 KRW passes. • Flat service_charge = -1 throws RateEngineException(INVALID_SERVICE_CHARGE). • Tier with chargeAmount = -100 throws RateEngineException(INVALID_SERVICE_CHARGE) at resolve time. • service_charge_ccy = blank string throws RateEngineException(INVALID_SERVICE_CHARGE). | 25 | 7.3-T05, 7.3-T06, 7.3-T11 | BE | RATE-04
7.3-T13 | revenue-ledger | 7.3 | 7. Settlement, Reconciliation & Revenue | FX margin + service fee capture | 2 | Verify rate-lock immutability: locked revenue fields cannot be updated post-commit | WBS 7.3 / RATE-04 §9.4. Once a transaction is committed, the fields collection_margin_usd, payout_margin_usd, service_charge, collection_amount on the transaction record are permanently locked (rate-lock). No code path may UPDATE these columns after commit. Enforce via: (a) a @PreUpdate JPA listener that throws if any locked field differs from the persisted value; (b) a DB trigger or check ensuring revenue_record rows are insert-only (no UPDATE except updated_at). The transaction entity already has committed_at; if committed_at is NOT NULL, the locked fields are immutable. | • Create infrastructure/jpa/RateLockImmutabilityListener.java annotated @EntityListeners on TransactionEntity. • In @PreUpdate: if entity.committedAt != null, verify entity.collectionMarginUsd, payoutMarginUsd, serviceCharge, collectionAmount have not changed vs DB-loaded snapshot; throw RateLockViolationException if any differ. • Add a snapshot mechanism: store the original locked values in @PostLoad into transient fields. • Create RateLockViolationException extending RuntimeException with field names and values. • In V7_3_2 migration, add a DB-level rule: after INSERT on revenue_record, block UPDATE of fx_margin_usd and service_charge_amount (trigger or application constraint via @Column(updatable=false) annotation). • Add @Column(updatable=false) on RevenueRecord.fxMarginUsd and serviceChargeAmount. | RateLockImmutabilityListener.java and @Column(updatable=false) on revenue_record monetary fields | • Attempting to update collectionMarginUsd on a committed (committedAt not null) transaction entity throws RateLockViolationException. • Updating a non-locked field (e.g. status) on a committed transaction succeeds without exception. • A JPA flush that sets revenue_record.fxMarginUsd to a different value is rejected by @Column(updatable=false) at the Hibernate layer. • Changing treasury rate via Admin after a transaction is committed does not alter the stored collection_margin_usd or payout_margin_usd (integration smoke test). • RateLockViolationException message includes the field name and both old and attempted new values. | 45 | 7.3-T07 | BE | RATE-04
7.3-T14 | revenue-ledger | 7.3 | 7. Settlement, Reconciliation & Revenue | FX margin + service fee capture | 2 | Add RevenueRecordService with aggregate revenue query methods | WBS 7.3. The Admin Portal Revenue Report view (PRD-07 §11.3.2) needs aggregates: total FX margin (USD) and service charge by partner, scheme, and date range. Service methods needed: (1) getRevenueByPartner(Long partnerId, LocalDate start, LocalDate end) returning RevenueAggregate DTO; (2) getRevenueByScheme(Long schemeId, LocalDate start, LocalDate end); (3) getRevenueSummary(LocalDate start, LocalDate end) returning a list of per-partner rows. The RevenueAggregate DTO must carry: txnCount (Long), totalFxMarginUsd (BigDecimal), totalServiceChargeAmount (BigDecimal), serviceChargeCcy (String). These are read-only queries with no side-effects. | • Create service/revenue/RevenueRecordService.java. • Add method RevenueAggregate getRevenueByPartner(Long partnerId, LocalDate start, LocalDate end): call repository aggregate queries; return populated DTO. • Add List<PartnerRevenueRow> getRevenueSummary(LocalDate start, LocalDate end): call a @Query returning per-partner aggregates. • Create dto/RevenueAggregate.java with fields: txnCount, totalFxMarginUsd, totalServiceChargeAmount, serviceChargeCcy. • Annotate service with @Transactional(readOnly=true). • Add a validation guard: start must be <= end; throw IllegalArgumentException otherwise. | RevenueRecordService.java with 3 query methods; RevenueAggregate DTO | • getRevenueByPartner for partnerId with 3 revenue rows (fxMarginUsd: 0.25, 0.30, 0.20) returns totalFxMarginUsd = 0.75. • getRevenueByPartner for a partner with zero rows returns txnCount=0, totalFxMarginUsd=0 (COALESCE, not null). • start > end throws IllegalArgumentException before any DB call. • getRevenueSummary returns one row per distinct partner in the date range — partners with no rows excluded. • Service is annotated @Transactional(readOnly=true) — write operations in same test transaction do not use this service. | 40 | 7.3-T03 | BE | RATE-04
7.3-T15 | revenue-ledger | 7.3 | 7. Settlement, Reconciliation & Revenue | FX margin + service fee capture | 2 | Expose revenue aggregates via Admin API endpoint GET /internal/v1/revenue/summary | WBS 7.3. The Admin Portal backend (PRD-07 §11.3.2) needs a REST endpoint to serve the Revenue Report view. Endpoint: GET /internal/v1/revenue/summary?startDate=YYYY-MM-DD&endDate=YYYY-MM-DD&partnerId={optional}&schemeId={optional}. Returns JSON array of RevenueAggregate rows. Requires FINANCE_ANALYST or higher role (RBAC). Internal API — not partner-facing; must not expose m_a, m_b, or individual transaction details. Response format: { partner_id, partner_name, scheme_id, scheme_name, txn_count, total_fx_margin_usd, total_service_charge_amount, service_charge_ccy }. | • Create web/admin/RevenueReportController.java with @GetMapping("/internal/v1/revenue/summary"). • Bind query params: startDate (LocalDate), endDate (LocalDate), optional partnerId (Long), optional schemeId (Long). • Validate startDate <= endDate; return HTTP 400 with error body on violation. • Require FINANCE_ANALYST or SUPER_ADMIN role via @PreAuthorize; return 403 otherwise. • Delegate to RevenueRecordService; map results to response JSON using RevenueSummaryResponse DTO. • Return HTTP 200 with JSON array; empty array (not 404) when no results in range. | RevenueReportController.java with GET /internal/v1/revenue/summary endpoint | • GET /internal/v1/revenue/summary?startDate=2026-01-01&endDate=2026-01-31 with FINANCE_ANALYST token returns HTTP 200 and correct aggregates. • Same request with OPS_OPERATOR token returns HTTP 200 (OPS_OPERATOR has read access). • Same request with unauthenticated call returns HTTP 401/403. • startDate > endDate returns HTTP 400 with error body. • Response JSON does not contain fields m_a, m_b, cost_rate_coll, or any individual transaction margin values. | 45 | 7.3-T14 | BE | RATE-04
7.3-T16 | revenue-ledger | 7.3 | 7. Settlement, Reconciliation & Revenue | FX margin + service fee capture | 2 | Implement daily revenue reconciliation job (pool identity check over prior 24h) | WBS 7.3 / RATE-04 §13.1 + OPS-13. A background job runs daily to verify pool identity invariant for all cross-border transactions committed in the prior 24 hours: ¦collection_usd - collection_margin_usd - payout_margin_usd - payout_usd_cost¦ < 0.01 USD. Any breach is logged as a P1 CRITICAL alert. Job also checks revenue_record count == committed cross-border transaction count for the period (revenue ledger completeness). For same-currency transactions, skip the pool identity check; verify revenue_record exists with fx_margin_usd = 0. Alert channel: log at ERROR with structured fields; raise an application metric counter revenue.reconciliation.failure. | • Create job/DailyRevenueReconciliationJob.java with @Scheduled(cron="0 0 2 * * *") (2 AM daily UTC). • Query all committed cross-border transactions in the past 24 hours (committed_at between now-24h and now). • For each: compute delta = ¦collection_usd - collection_margin_usd - payout_margin_usd - payout_usd_cost¦; if > 0.01 log ERROR with txn_ref, delta, and all pool values; increment counter. • Query revenue_record for the same period; compare count against cross-border transaction count; log ERROR if mismatch. • For same-currency transactions in period: verify a revenue_record with fx_margin_usd=0 exists; log ERROR if missing. • Emit summary log at INFO: checked N transactions, M violations found. | DailyRevenueReconciliationJob.java with @Scheduled reconciliation logic and alerting | • Job runs without error for a dataset with 3 committed cross-border transactions all having pool identity delta < 0.01. • Job logs ERROR and increments counter for a transaction with injected delta = 0.015 (breach). • Job detects and logs revenue_record count mismatch if one transaction has no corresponding revenue row. • Same-currency transaction with revenue_record.fx_margin_usd=0 passes without error. • Job is idempotent: running twice in the same period produces the same alerts without double-counting. | 50 | 7.3-T07, 7.3-T08 | BE | RATE-04
7.3-T17 | revenue-ledger | 7.3 | 7. Settlement, Reconciliation & Revenue | FX margin + service fee capture | 2 | Unit test: RevenueCapture value object correctness | WBS 7.3. RevenueCapture (7.3-T04) must be tested with exact numeric vectors from RATE-04 §4.3. Test vectors: (A) cross-border inbound MNT->KRW via USD: collection_margin_usd=0.1538, payout_margin_usd=0.1026, fx_margin_usd=0.2564, service_charge=500 MNT; (B) both-legs identity (USD->USD): collection_margin_usd=1.0204, payout_margin_usd=1.0204, fx_margin_usd=2.0408, service_charge=0.50 USD (from RATE-04 §6.2 worked example target_payout=100 USD, m_a=m_b=0.01); (C) same-currency short-circuit: all margins=0, service_charge=500 KRW. Also test the IllegalArgumentException path for negative margins. | • Create test/unit/domain/model/RevenueCaptureTest.java. • Test vector A: assert fxMarginUsd = 0.1538 + 0.1026 = 0.2564 using BigDecimal compareTo within tolerance 0.0001. • Test vector B: assert fxMarginUsd = 1.0204 + 1.0204 = 2.0408. • Test vector C (zeroCrossBorder): assert collectionMarginUsd=0, payoutMarginUsd=0, fxMarginUsd=0, serviceChargeAmount=500, serviceChargeCcy=KRW. • Test negative collectionMarginUsd: fromPoolValues(-0.01, 0.01, 0, "KRW") throws IllegalArgumentException. • Test negative serviceChargeAmount: fromPoolValues(0.10, 0.10, -1, "USD") throws IllegalArgumentException. | test/unit/domain/model/RevenueCaptureTest.java with 6 test cases all passing | • Test vector A fxMarginUsd assertion passes (0.2564 within 0.0001 tolerance). • Test vector B fxMarginUsd assertion passes (2.0408 within 0.0001 tolerance). • zeroCrossBorder factory sets all margin fields to 0 exactly. • Negative collectionMarginUsd throws IllegalArgumentException. • Negative serviceChargeAmount throws IllegalArgumentException. • All 6 test cases pass with mvn test or gradle test. | 30 | 7.3-T04 | BE | RATE-04
7.3-T18 | revenue-ledger | 7.3 | 7. Settlement, Reconciliation & Revenue | FX margin + service fee capture | 2 | Unit test: ServiceChargeTierResolver with exact tier boundary vectors | WBS 7.3. ServiceChargeTierResolver (7.3-T05) must be tested with boundary vectors. Setup: Rule flat=500, tiers: [0, 20)->600; [20, 50)->500; [50, null)->400. Test: (a) collection_usd=10.00 -> tier 0-20 -> 600; (b) collection_usd=20.00 -> tier 20-50 -> 500; (c) collection_usd=49.99 -> tier 20-50 -> 500; (d) collection_usd=50.00 -> tier 50-null -> 400; (e) collection_usd=100.00 -> tier 50-null -> 400; (f) no tiers -> flat 500; (g) gap in tiers (15-20 missing), collection_usd=16 -> fallback to flat 500; (h) null collection_usd (same-currency path) -> flat 500. | • Create test/unit/service/rate/ServiceChargeTierResolverTest.java. • Build Rule stub and ServiceChargeTier list per the setup above. • Assert each of the 8 test vectors (a)-(h) against expected charge amount. • Include boundary: collection_usd exactly at min_collection_usd (inclusive) of the next tier. • Include gap test: tier table [0,10)->600, [20,50)->500 (gap 10-20); collection_usd=15 -> fallback flat 500. • All assertions use BigDecimal.compareTo(expected) == 0. | test/unit/service/rate/ServiceChargeTierResolverTest.java with 8 test cases all passing | • collection_usd=10.00 returns 600 (falls in [0,20) tier). • collection_usd=20.00 returns 500 (boundary: min inclusive in [20,50) tier, not [0,20)). • collection_usd=50.00 returns 400 (unbounded upper tier). • No-tiers case returns flat 500. • Gap case collection_usd=15 returns flat 500 (fallback). • null collection_usd returns flat 500. • All 8 assertions pass. • No test uses == on BigDecimal (uses compareTo). | 35 | 7.3-T05 | BE | RATE-04
7.3-T19 | revenue-ledger | 7.3 | 7. Settlement, Reconciliation & Revenue | FX margin + service fee capture | 2 | Unit test: pool identity validator with boundary and failure cases | WBS 7.3. PoolIdentityValidator (7.3-T08) must be tested with exact numeric vectors. Test cases: (A) pass: collection_usd=10.2564, margin_a=0.1538, margin_b=0.1026, payout_usd_cost=10.0000 -> delta=0.0000 < 0.01 -> no exception; (B) pass at boundary: delta=0.0099 < 0.01; (C) fail at boundary: delta=0.0100 is NOT < 0.01 -> throws (tolerance is strictly less than 0.01); (D) fail: delta=0.0150 > 0.01 -> throws PoolIdentityFailureException; (E) same-currency short-circuit: isSameCcyShortcircuit=true, all USD fields null -> no exception, no delta computed; (F) constructed failure: collection_usd=10.26, margin_a=0.15, margin_b=0.10, payout=10.00 -> delta=0.01 -> throws. | • Create test/unit/service/rate/PoolIdentityValidatorTest.java. • Build minimal TransactionEntity stubs (or use a mock) for each vector with the required BigDecimal fields and isSameCcyShortcircuit boolean. • Assert vectors A and B pass without exception. • Assert vectors C, D, F throw PoolIdentityFailureException. • Assert vector E (same-currency) passes even with null USD-pool fields. • Verify PoolIdentityFailureException message contains the delta value for vector D. | test/unit/service/rate/PoolIdentityValidatorTest.java with 6 test cases all passing | • Vector A: assertDoesNotThrow. • Vector B (delta=0.0099): assertDoesNotThrow. • Vector C (delta=0.0100): assertThrows PoolIdentityFailureException (tolerance is strictly less than 0.01). • Vector D (delta=0.0150): assertThrows PoolIdentityFailureException; exception message contains '0.0150'. • Vector E (same-currency): assertDoesNotThrow with null USD fields. • All 6 tests pass. | 30 | 7.3-T08 | BE | RATE-04
7.3-T20 | revenue-ledger | 7.3 | 7. Settlement, Reconciliation & Revenue | FX margin + service fee capture | 2 | Unit test: margin guard and service-charge guard in RateEngineService | WBS 7.3. Guards from 7.3-T11 and 7.3-T12 need targeted unit tests with exact error codes. Error codes: INVALID_MARGIN (negative m_a/m_b, sum>=1, same-currency nonzero), MARGIN_BELOW_MINIMUM (cross-border sum < 0.02), INVALID_SERVICE_CHARGE (negative or blank-ccy). Test vectors: (A) m_a=0.015, m_b=0.010, cross-border -> no exception; (B) m_a=0.010, m_b=0.009, cross-border -> MARGIN_BELOW_MINIMUM; (C) m_a=-0.001 -> INVALID_MARGIN; (D) m_a=0.60, m_b=0.50 -> INVALID_MARGIN; (E) same-currency, m_a=0, m_b=0 -> no exception; (F) same-currency, m_a=0.005 -> INVALID_MARGIN; (G) service_charge=-1 -> INVALID_SERVICE_CHARGE; (H) service_charge_ccy=blank -> INVALID_SERVICE_CHARGE. | • Create test/unit/service/rate/RateEngineGuardsTest.java. • Mock or stub the rule and treasury rate inputs to isolate the guard layer. • Test each vector A-H; assert exception type and errorCode field for failure cases. • For vectors A and E, assert computeQuote() proceeds past the guard block (no exception thrown at guard stage). • Verify all BigDecimal comparisons use compareTo, not equals or ==. • Add a test that m_a=0, m_b=0.02 (combined 2%) cross-border passes the minimum guard. | test/unit/service/rate/RateEngineGuardsTest.java with 9 test cases all passing | • Vector B throws RateEngineException with errorCode=MARGIN_BELOW_MINIMUM. • Vector C throws RateEngineException with errorCode=INVALID_MARGIN. • Vector D (sum=1.1) throws RateEngineException with errorCode=INVALID_MARGIN. • Vector F (same-currency nonzero margin) throws RateEngineException with errorCode=INVALID_MARGIN. • Vector G (service_charge=-1) throws RateEngineException with errorCode=INVALID_SERVICE_CHARGE. • All 9 tests pass; no test uses floating-point literals. | 35 | 7.3-T11, 7.3-T12 | BE | RATE-04
7.3-T21 | revenue-ledger | 7.3 | 7. Settlement, Reconciliation & Revenue | FX margin + service fee capture | 2 | Unit test: CommitTransactionService revenue_record insertion (cross-border and same-currency) | WBS 7.3. CommitTransactionService (7.3-T07 and 7.3-T09) needs unit tests covering: (A) cross-border: verifies revenue_record is saved with correct fx_margin_usd = collection_margin_usd + payout_margin_usd and service_charge_amount; (B) same-currency: fx_margin_usd=0, service_charge_amount = rule service charge; (C) idempotency: second call to commit() for the same txn_id does not insert a second revenue_record; (D) rollback: if pool identity check fails (PoolIdentityFailureException thrown), no revenue_record row is persisted. Use a Spring test slice with an in-memory database (H2 or Testcontainers Postgres). | • Create test/integration/service/payment/CommitTransactionServiceTest.java. • Seed a transaction row in DEBITED state with rate-engine fields populated for a cross-border case. • Call commitTransaction(); verify revenue_record count = 1 with expected fx_margin_usd value. • Seed a same-currency transaction; verify revenue_record.fx_margin_usd = 0. • For idempotency: call commitTransaction() twice with same txn; verify still only 1 revenue_record row. • For rollback: inject a PoolIdentityFailureException from PoolIdentityValidator mock; assert no revenue_record row and transaction row unchanged. | test/integration/service/payment/CommitTransactionServiceTest.java with 4 test cases all passing | • Cross-border case: revenue_record.fx_margin_usd = sum of margin fields from transaction (BigDecimal equality). • Same-currency case: revenue_record.fx_margin_usd = 0.0000 and service_charge_amount = expected value. • Idempotency: exactly 1 revenue_record row after 2 commit calls. • Rollback case: 0 revenue_record rows and transaction.status unchanged after PoolIdentityFailureException. • All tests pass under mvn test or gradle test with in-memory DB. | 50 | 7.3-T07, 7.3-T08, 7.3-T09 | BE | RATE-04
7.3-T22 | revenue-ledger | 7.3 | 7. Settlement, Reconciliation & Revenue | FX margin + service fee capture | 2 | Unit test: RuleValidationService margin checks at rule save | WBS 7.3. RuleValidationService.validateMargins() (7.3-T10) needs unit tests for all 5 guard branches: (A) cross-border m_a=0.010, m_b=0.010 passes; (B) cross-border m_a=0.010, m_b=0.009 -> MARGIN_BELOW_MINIMUM; (C) same-currency m_a=0, m_b=0 passes; (D) same-currency m_a=0.005 -> SAME_CCY_NONZERO_MARGIN; (E) m_a=-0.001 -> INVALID_MARGIN (negative individual margin); (F) m_a=0, m_b=0.02 exactly at 2% -> passes (boundary: >= 0.02 is accepted); (G) m_a=0.60, m_b=0.50 (sum=1.10) -> INVALID_MARGIN (sum >= 1.0 is rejected). | • Create test/unit/service/admin/RuleValidationServiceTest.java. • Build Rule stubs for each vector with is_same_ccy_shortcircuit set appropriately. • Assert assertDoesNotThrow for vectors A, C, F. • Assert assertThrows MarginValidationException with matching error code for B, D, E, G. • Verify MarginValidationException.getErrorCode() returns the expected constant string for each failure case. • All assertions use BigDecimal.valueOf() for margin literals, not double literals. | test/unit/service/admin/RuleValidationServiceTest.java with 7 test cases all passing | • Vector B throws MarginValidationException; getErrorCode() == MARGIN_BELOW_MINIMUM. • Vector D throws MarginValidationException; getErrorCode() == SAME_CCY_NONZERO_MARGIN. • Vector E throws MarginValidationException; getErrorCode() == INVALID_MARGIN. • Vector F (exactly 2.0%) does not throw (boundary is inclusive). • Vector G (sum=1.10) throws MarginValidationException; getErrorCode() == INVALID_MARGIN. • All 7 tests pass. | 30 | 7.3-T10 | BE | RATE-04
7.3-T23 | revenue-ledger | 7.3 | 7. Settlement, Reconciliation & Revenue | FX margin + service fee capture | 2 | Integration test: end-to-end revenue capture for cross-border MPM payment | WBS 7.3. End-to-end integration test wiring all revenue components: RateEngineService.computeQuote() -> CommitTransactionService -> revenue_record INSERT. Scenario (RATE-04 §4.3 worked example, SendMN OVERSEAS INBOUND): target_payout=50805 KRW, cost_rate_pay=treasury.usd_krw=1350.00, cost_rate_coll=1.0 (IDENTITY, Settle A=USD), m_a=0.01, m_b=0.01, service_charge=0.36 USD (flat). Expected: payout_usd_cost=37.6333 USD, collection_usd=38.0134 USD, collection_margin_usd=0.3801 USD, payout_margin_usd=0.3801 USD, fx_margin_usd=0.7602 USD, collection_amount=38.3734 USD. Revenue record must reflect these locked values. | • Create test/integration/RevenueCaptureIntegrationTest.java using @SpringBootTest with Testcontainers PostgreSQL. • Seed Rule (SENDMN, ZEROPAY, INBOUND): m_a=0.01, m_b=0.01, service_charge=0.36 USD, settle_a=USD, settle_b=KRW. • Seed treasury_rate usd_krw=1350.00, usd_usd=1.0. • Call rateEngineService.computeQuote() with target_payout=50805 KRW; assert intermediate values within 0.01 USD tolerance. • Call commitTransactionService.commit() with the resulting quote; assert revenue_record is persisted. • Assert revenue_record.fx_margin_usd = collection_margin_usd + payout_margin_usd (within 0.0001 tolerance). | test/integration/RevenueCaptureIntegrationTest.java with full pipeline test passing | • collection_usd value in quote is within 0.01 of expected 38.0134. • revenue_record.fx_margin_usd is within 0.0001 of collection_margin_usd + payout_margin_usd from the committed transaction. • revenue_record.service_charge_amount = 0.36 and service_charge_ccy = USD. • revenue_record.revenue_date = the date portion of the committed_at timestamp. • Pool identity holds: ¦collection_usd - margin_a - margin_b - payout_usd_cost¦ < 0.01 (assert in test). | 55 | 7.3-T07, 7.3-T08, 7.3-T09, 7.3-T21 | BE | RATE-04
7.3-T24 | revenue-ledger | 7.3 | 7. Settlement, Reconciliation & Revenue | FX margin + service fee capture | 2 | Integration test: revenue capture for same-currency domestic payment | WBS 7.3. Integration test for same-currency short-circuit path (GME Remit on ZeroPay, all KRW, is_same_ccy_shortcircuit=true). Per RATE-04 §7.1 and DAT-03 §6.2: USD pool is skipped; collection_amount = target_payout + service_charge; collection_margin_usd = payout_margin_usd = null/0. Revenue record: fx_margin_usd=0.0000, service_charge_amount=500 (KRW), service_charge_ccy=KRW. No pool identity check for same-currency. Scenario: target_payout=13500 KRW, service_charge=500 KRW, m_a=0, m_b=0. Expected collection_amount=14000 KRW. | • Add test case in test/integration/RevenueCaptureIntegrationTest.java (or a new test class). • Seed Rule (GME_REMIT, ZEROPAY, DOMESTIC): m_a=0, m_b=0, is_same_ccy_shortcircuit=true, service_charge=500 KRW, settle_a=KRW. • Call computeQuote() with target_payout=13500 KRW; assert collection_amount=14000 KRW; assert collection_usd is null or not computed. • Call commit(); assert revenue_record persisted. • Assert revenue_record.fx_margin_usd = 0.0000 and service_charge_amount = 500.0000 and service_charge_ccy = KRW. • Assert no PoolIdentityFailureException is raised for this transaction. | Same-currency revenue_record integration test passing (appended to integration test class) | • collection_amount in quote = 14000 KRW (13500 + 500). • revenue_record.fx_margin_usd = 0.0000 exactly. • revenue_record.service_charge_amount = 500.0000 and service_charge_ccy = KRW. • No exception thrown during commit (pool identity validator skips same-currency path). • revenue_record row exists in DB after commit (not absent for same-currency). | 35 | 7.3-T23 | BE | RATE-04
7.3-T25 | revenue-ledger | 7.3 | 7. Settlement, Reconciliation & Revenue | FX margin + service fee capture | 2 | Update Admin API revenue report to include service_charge_ccy grouping | WBS 7.3. The revenue report endpoint (7.3-T15) returns service_charge_amount but service charges can be in different currencies depending on the Settle A currency (e.g. USD for SendMN, KRW for GME Remit). The aggregate must group by service_charge_ccy to avoid summing KRW and USD together. The response must include one row per (partner, scheme, service_charge_ccy) combination. A partner using USD settle_a and KRW settle_a under different rules produces separate rows. RevenueAggregate DTO needs serviceChargeCcy field. SQL aggregate query must include GROUP BY service_charge_ccy. | • Update the @Query in RevenueRecordRepository to GROUP BY service_charge_ccy in addition to partner_id and scheme_id. • Update RevenueAggregate DTO to include serviceChargeCcy (String) field. • Update RevenueRecordService.getRevenueSummary() to return one row per (partner, scheme, ccy) triple. • Update RevenueSummaryResponse to include serviceChargeCcy in JSON output. • Update RevenueReportController to pass through the extra grouping dimension. • Add a unit test: two revenue rows for same partner/scheme but different ccys produce two summary rows. | Revenue summary groups by service_charge_ccy; RevenueAggregate DTO carries serviceChargeCcy field | • Two revenue records for partner=SENDMN, scheme=ZEROPAY with ccy USD and KRW respectively produce two summary rows (not one summed row). • Each summary row has totalServiceChargeAmount in its own currency (not cross-currency sum). • Existing cross-border USD summary rows unaffected. • RevenueSummaryResponse JSON includes service_charge_ccy field. • Unit test with mixed-ccy data passes. | 35 | 7.3-T14, 7.3-T15 | BE | RATE-04
7.3-T26 | revenue-ledger | 7.3 | 7. Settlement, Reconciliation & Revenue | FX margin + service fee capture | 2 | Write Javadoc for RevenueCapture, RevenueRecord, and CommitTransactionService revenue path | WBS 7.3. Developer documentation must be inline so that the next developer understands the revenue capture contract without reading the full spec. Key rules to document: (1) fx_margin_usd = collection_margin_usd + payout_margin_usd, never a percentage of the transaction amount; (2) service_charge is always in Settle A currency and never enters the USD pool; (3) revenue_record is inserted atomically with the transaction commit; (4) locked fields on transaction and revenue_record are immutable after commit; (5) same-currency short-circuit always produces fx_margin_usd=0; (6) pool identity tolerance is 0.01 USD. | • Add class-level Javadoc to RevenueCapture.java explaining that fxMarginUsd = collectionMarginUsd + payoutMarginUsd and citing RATE-04 §5. • Add class-level Javadoc to RevenueRecord.java explaining that it is insert-only, populated at CommitTransaction, with a note that fx_margin_usd=0 for same-currency rules. • Add method-level Javadoc to CommitTransactionService.commit() documenting the atomic write sequence: rate-lock -> pool identity check -> revenue_record insert. • Add a @see RATE-04 tag on the 5-step formula reference in RateEngineService.computeQuote(). • Add a note on PoolIdentityValidator.assertValid() that POOL_IDENTITY_FAILURE is a programming error, not a user error. • Review all Javadoc for accuracy against the spec; no prose must contradict the tested behaviour. | Javadoc on RevenueCapture, RevenueRecord, CommitTransactionService, PoolIdentityValidator classes/methods | • RevenueCapture class Javadoc mentions the formula fxMarginUsd = collectionMarginUsd + payoutMarginUsd explicitly. • RevenueRecord class Javadoc states it is insert-only and that fx_margin_usd=0 for same-currency transactions. • CommitTransactionService.commit() Javadoc documents the three-step atomic write sequence. • PoolIdentityValidator.assertValid() Javadoc labels POOL_IDENTITY_FAILURE as an internal programming error requiring investigation. • No Javadoc contradicts the passing unit/integration tests for this work-package. | 30 | 7.3-T04, 7.3-T07, 7.3-T08 | BE | RATE-04
7.4-T01 | settlement-reconciliation | 7.4 | 7. Settlement, Reconciliation & Revenue | Daily reconciliation engine | 2 | Create settlement_batch and settlement_file DB migration | WBS 7.4 Daily Reconciliation Engine. settlement_batch tracks one row per daily batch run per scheme/file_type. settlement_file tracks physical SFTP file metadata. settlement_batch columns: id BIGINT PK, scheme_id BIGINT FK qr_scheme, file_type VARCHAR(10) (e.g. ZP0011, ZP0061), direction VARCHAR(20) CHECK IN ('GME_TO_ZP','ZP_TO_GME'), settlement_date DATE (KST business date), window VARCHAR(20) CHECK IN ('MORNING','AFTERNOON','DETAIL','NIGHTLY'), status VARCHAR(20) CHECK IN ('PENDING','GENERATED','TRANSMITTED','RECEIVED','RECONCILED','ERROR'), transaction_count INT DEFAULT 0, total_amount DECIMAL(20,4) DEFAULT 0, total_amount_ccy CHAR(3), file_checksum VARCHAR(64) nullable, transmitted_at TIMESTAMPTZ nullable, received_at TIMESTAMPTZ nullable, reconciled_at TIMESTAMPTZ nullable, error_detail TEXT nullable, created_at/updated_at/created_by/updated_by standard audit. settlement_file columns: id BIGINT PK, batch_id BIGINT FK settlement_batch, filename VARCHAR(255), sftp_path VARCHAR(512), file_size_bytes BIGINT, file_checksum VARCHAR(64), direction VARCHAR(20) CHECK IN ('OUTBOUND','INBOUND'), transmitted_at TIMESTAMPTZ nullable, created_at/updated_at standard. Unique constraint on (scheme_id, file_type, settlement_date, window, direction) in settlement_batch. | • Create Flyway/Liquibase migration file V7_4_001__settlement_batch_file.sql • Add CREATE TABLE settlement_batch with all columns and constraints as specified • Add CREATE TABLE settlement_file with FK to settlement_batch • Add UNIQUE constraint on settlement_batch(scheme_id, file_type, settlement_date, window, direction) • Add index on settlement_batch(settlement_date, status) and settlement_file(batch_id) | Migration file V7_4_001__settlement_batch_file.sql that creates both tables with all constraints | • INSERT with duplicate (scheme_id, file_type, settlement_date, window, direction) raises unique violation • INSERT status='INVALID' into settlement_batch raises check constraint violation • INSERT direction='SEND' into settlement_file raises check constraint violation • settlement_file FK references settlement_batch; inserting orphan batch_id raises FK error • Rollback migration cleanly removes both tables with no orphan objects | 35 |  | BE | RATE-04, SCH-06
7.4-T02 | settlement-reconciliation | 7.4 | 7. Settlement, Reconciliation & Revenue | Daily reconciliation engine | 2 | Create reconciliation_item DB migration | WBS 7.4 Daily Reconciliation Engine. reconciliation_item stores one row per line compared during batch reconciliation. Auto-generated when ZP006x result files are received. Columns: id BIGINT PK, batch_id BIGINT FK settlement_batch, txn_ref VARCHAR(64) nullable (GMEPay+ reference; NULL for records missing from GME side), scheme_ref VARCHAR(128) (ZeroPay reference), match_status VARCHAR(20) CHECK IN ('MATCHED','DISCREPANCY','MISSING_GME','MISSING_SCHEME'), gme_amount DECIMAL(20,4), scheme_amount DECIMAL(20,4), discrepancy_amount DECIMAL(20,4), ccy CHAR(3), resolution_status VARCHAR(20) CHECK IN ('UNRESOLVED','RESOLVED','ESCALATED') DEFAULT 'UNRESOLVED', resolved_by VARCHAR(120) nullable, resolved_at TIMESTAMPTZ nullable, resolution_note TEXT nullable, created_at/updated_at/created_by/updated_by standard audit. Index on (batch_id, match_status) and (txn_ref) for lookup. | • Create migration file V7_4_002__reconciliation_item.sql • Add CREATE TABLE reconciliation_item with all columns and check constraints • Add FK to settlement_batch • Add index on (batch_id, match_status) and separate index on txn_ref • Verify resolution_status defaults to UNRESOLVED on INSERT without explicit value | Migration file V7_4_002__reconciliation_item.sql | • INSERT with match_status='WRONG' raises check constraint violation • txn_ref nullable: INSERT with NULL txn_ref succeeds for MISSING_GME case • resolution_status defaults to UNRESOLVED when not supplied on INSERT • FK to settlement_batch: orphan batch_id insert raises error • Index on (batch_id, match_status) appears in EXPLAIN plan for query WHERE batch_id=X AND match_status='DISCREPANCY' | 25 | 7.4-T01 | BE | RATE-04, SCH-06
7.4-T03 | settlement-reconciliation | 7.4 | 7. Settlement, Reconciliation & Revenue | Daily reconciliation engine | 2 | Define ReconciliationBatch and SettlementFile Java domain models | WBS 7.4 Daily Reconciliation Engine. Java backend. Create JPA entity classes for settlement_batch, settlement_file, and reconciliation_item tables created in T01/T02. Use BigDecimal for all monetary fields (DECIMAL(20,4)). settlement_batch.status is an enum: PENDING, GENERATED, TRANSMITTED, RECEIVED, RECONCILED, ERROR. settlement_batch.window is an enum: MORNING, AFTERNOON, DETAIL, NIGHTLY. reconciliation_item.match_status enum: MATCHED, DISCREPANCY, MISSING_GME, MISSING_SCHEME. resolution_status enum: UNRESOLVED, RESOLVED, ESCALATED. All monetary amounts use BigDecimal; no float or double. Timestamps are OffsetDateTime. String ccy fields are plain String (validated by constraint at DB level). | • Create enum BatchStatus {PENDING, GENERATED, TRANSMITTED, RECEIVED, RECONCILED, ERROR} • Create enum BatchWindow {MORNING, AFTERNOON, DETAIL, NIGHTLY} • Create enum MatchStatus {MATCHED, DISCREPANCY, MISSING_GME, MISSING_SCHEME} • Create enum ResolutionStatus {UNRESOLVED, RESOLVED, ESCALATED} • Create @Entity SettlementBatch with JPA annotations mapping to settlement_batch table • Create @Entity SettlementFile with @ManyToOne to SettlementBatch • Create @Entity ReconciliationItem with @ManyToOne to SettlementBatch; BigDecimal for gme_amount, scheme_amount, discrepancy_amount | Four enum classes and three @Entity classes with full JPA mappings | • SettlementBatch.totalAmount is BigDecimal, not double • ReconciliationItem.txnRef is nullable (no @Column(nullable=false)) • Enum fields use @Enumerated(EnumType.STRING) so DB stores 'MATCHED' not ordinal • SettlementFile has @ManyToOne(fetch=LAZY) to SettlementBatch to avoid N+1 • Spring Boot integration test: persist and reload a SettlementBatch; verify field round-trip including BigDecimal scale | 40 | 7.4-T01, 7.4-T02 | BE | RATE-04, SCH-06
7.4-T04 | settlement-reconciliation | 7.4 | 7. Settlement, Reconciliation & Revenue | Daily reconciliation engine | 2 | Implement PoolIdentityVerifier service | WBS 7.4 Daily Reconciliation Engine. Pool identity invariant (RATE-04 §5, §13.1): collection_usd - collection_margin_usd - payout_margin_usd = payout_usd_cost must hold within 0.01 USD tolerance for every committed cross-border transaction. Fields are BigDecimal stored on the transaction entity. Same-currency short-circuit transactions have collection_usd = NULL and margins = 0; they are excluded from pool check. Service must: accept a transaction record, compute ¦collection_usd - collection_margin_usd - payout_margin_usd - payout_usd_cost¦, return PASS if < 0.01 USD, return FAIL with delta value if >= 0.01 USD. Used both at transaction commit time and by the daily background recon job (T05). Must raise POOL_IDENTITY_FAILURE for commit-time failures; background job only logs and alerts. | • Create PoolIdentityVerifier.java in recon package • Implement verify(Transaction txn): returns PoolIdentityResult{status, delta} • Skip check and return PASS if txn.collectionUsd is null (same-currency short-circuit) • Compute delta = abs(collectionUsd.subtract(collectionMarginUsd).subtract(payoutMarginUsd).subtract(payoutUsdCost)) • Return FAIL with delta if delta.compareTo(new BigDecimal('0.01')) >= 0 • Unit test all branches including boundary at exactly 0.01 USD (edge: returns FAIL) and 0.0099 (PASS) | PoolIdentityVerifier.java service class with unit tests | • verify with collectionUsd=36.9714, collectionMarginUsd=0.3697, payoutMarginUsd=0.3697, payoutUsdCost=36.2319 returns PASS (delta 0.0001 < 0.01) • verify with collectionUsd=100.00, marginUsd values=1.0204 each, payoutUsdCost=100.00 returns PASS (identity legs example from RATE-04 §7.1) • verify with delta=0.01 exactly returns FAIL • verify with delta=0.0099 returns PASS • verify on same-currency transaction (collectionUsd=null) returns PASS without NPE | 35 | 7.4-T03 | BE | RATE-04, SCH-06
7.4-T05 | settlement-reconciliation | 7.4 | 7. Settlement, Reconciliation & Revenue | Daily reconciliation engine | 2 | Implement daily pool-identity background reconciliation job | WBS 7.4 Daily Reconciliation Engine. RATE-04 §13.1 requires a daily background job to verify pool identity across all committed cross-border transactions for the prior business day. The job queries transaction table for rows with status=APPROVED and rate_locked_at on the prior business date (KST), runs PoolIdentityVerifier on each, accumulates any FAIL results, and emits an alert if violations found. Alert must include txn_ref, delta, and a summary count. Uses PoolIdentityVerifier from T04. Job is a Spring @Scheduled component or a named batch step. KST is UTC+9; compute prior KST business day correctly using ZoneId('Asia/Seoul'). Never modifies transaction rows; read-only scan. | • Create DailyPoolIdentityReconJob.java annotated @Component • Inject TransactionRepository and PoolIdentityVerifier • Implement runForDate(LocalDate kstDate) method: query approved cross-border transactions for that KST date, verify each • Collect violations into a list; call AlertService.sendPoolIdentityAlert if list non-empty • Register as @Scheduled(cron='0 30 1 * * *', zone='Asia/Seoul') (01:30 KST daily) • Unit test runForDate with 3 clean txns + 1 violation: verify alert fires once with correct txn_ref | DailyPoolIdentityReconJob.java with unit test | • runForDate with zero violations does not call AlertService • runForDate with one violation calls AlertService exactly once with violating txn_ref and delta value • Same-currency transactions (collectionUsd=null) are skipped without error • Date window query uses KST zone: a txn at 2026-06-04 23:30 UTC (2026-06-05 08:30 KST) appears in the 2026-06-05 KST run • @Scheduled cron expression resolves to 01:30 KST via zone attribute | 45 | 7.4-T04 | BE | RATE-04, SCH-06
7.4-T06 | settlement-reconciliation | 7.4 | 7. Settlement, Reconciliation & Revenue | Daily reconciliation engine | 2 | Implement SettlementBatchRepository and batch status state machine | WBS 7.4 Daily Reconciliation Engine. settlement_batch status lifecycle: PENDING -> GENERATED -> TRANSMITTED -> RECEIVED -> RECONCILED; any state -> ERROR. Only valid transitions are allowed. Service method transitionStatus(Long batchId, BatchStatus target) must enforce: GENERATED only from PENDING, TRANSMITTED only from GENERATED, RECEIVED only from TRANSMITTED, RECONCILED only from RECEIVED, ERROR from any state. Invalid transition throws IllegalStateException with message. Uses JPA SettlementBatch entity from T03. Also provide findBySchemeAndDateAndFileType(Long schemeId, LocalDate date, String fileType) query method. | • Create SettlementBatchRepository extending JpaRepository<SettlementBatch, Long> • Add @Query method findBySchemeIdAndSettlementDateAndFileType(Long schemeId, LocalDate date, String fileType) • Create SettlementBatchService.java • Implement transitionStatus(Long batchId, BatchStatus target) with valid-transition guard • Implement createBatch(Long schemeId, String fileType, String direction, LocalDate date, BatchWindow window) initialising status=PENDING • Unit test all valid transitions and at least two invalid transitions | SettlementBatchRepository interface and SettlementBatchService.java with unit tests | • PENDING -> GENERATED succeeds • PENDING -> RECONCILED throws IllegalStateException • TRANSMITTED -> ERROR succeeds (any-to-ERROR rule) • RECONCILED -> GENERATED throws IllegalStateException • createBatch sets status=PENDING and transaction_count=0, total_amount=0 | 40 | 7.4-T03 | BE | RATE-04, SCH-06
7.4-T07 | settlement-reconciliation | 7.4 | 7. Settlement, Reconciliation & Revenue | Daily reconciliation engine | 2 | Implement ZP0061 morning settlement request file generator | WBS 7.4 Daily Reconciliation Engine. ZP0061 (GME -> ZeroPay, deadline ~05:00 KST) is the morning settlement request. It contains one summary record per merchant: merchant_id CHAR(10), settlement_date DATE(8) YYYYMMDD, gross_txn_count NUM(6), gross_txn_amount NUM(14) KRW total payout, refund_count NUM(6), refund_amount NUM(14), merchant_fee_total NUM(12), net_settlement_amount NUM(14), settlement_type CHAR(1) N=Net domestic / G=Gross international. File header: file_type=ZP0061, business_date, GME institution code, total record count, total payout KRW. File trailer: total record count (repeated), control sum (sum of all net_settlement_amount). Source data: query transactions table for APPROVED transactions with settlement_date = target KST date whose settlement_batch_status = SETTLEMENT_REGISTERED (confirmed by ZP0012). For domestic (LOCAL partner): net_settlement_amount = gross_txn_amount - merchant_fee_total. For international (OVERSEAS partner): net_settlement_amount = gross_txn_amount (gross; full payout). settlement_type = N for domestic, G for international. | • Create Zp0061Generator.java in settlement.batch package • Implement generate(LocalDate kstDate): query eligible transactions grouped by merchant_id and partner_type • Build per-merchant summary records with all required fields • Compute control sum as sum of net_settlement_amount across all records • Assemble header + detail records + trailer into byte[] • Write to file named ZP0061_{YYYYMMDD}_01.dat; store metadata in settlement_file table; update settlement_batch status to GENERATED | Zp0061Generator.java producing correct fixed-width records with header/trailer | • Domestic merchant with 5 txns at KRW 10000 each, fee KRW 500 each: gross_txn_amount=50000, merchant_fee_total=2500, net_settlement_amount=47500, settlement_type=N • International merchant with 3 txns at KRW 20000 each: gross_txn_amount=60000, merchant_fee_total=0, net_settlement_amount=60000, settlement_type=G • File header total_record_count equals number of merchant summary rows • File trailer control_sum equals sum of all net_settlement_amount values • Transactions with status != SETTLEMENT_REGISTERED are excluded from the file | 55 | 7.4-T06 | BE | RATE-04, SCH-06
7.4-T08 | settlement-reconciliation | 7.4 | 7. Settlement, Reconciliation & Revenue | Daily reconciliation engine | 2 | Implement ZP0063 afternoon settlement request file generator | WBS 7.4 Daily Reconciliation Engine. ZP0063 (GME -> ZeroPay, deadline ~14:00 KST) is the supplementary afternoon settlement request. It covers transactions approved after the ZP0061 cutoff for same-day merchant crediting (RATE-04 §12.5, SCH-06 §7.3). File layout is identical to ZP0061: merchant_id CHAR(10), settlement_date DATE(8), gross_txn_count NUM(6), gross_txn_amount NUM(14), refund_count NUM(6), refund_amount NUM(14), merchant_fee_total NUM(12), net_settlement_amount NUM(14), settlement_type CHAR(1). File is named ZP0063_{YYYYMMDD}_01.dat. May produce empty file (zero detail records) if no supplementary transactions exist. Must not re-include transactions already in ZP0061 for the same date. Scope boundary: transactions approved between ZP0061 cutoff and ZP0063 generation time that have SETTLEMENT_REGISTERED status. | • Create Zp0063Generator.java extending or reusing logic from Zp0061Generator • Implement generate(LocalDate kstDate, OffsetDateTime morningCutoff): query SETTLEMENT_REGISTERED transactions approved after morningCutoff • Exclude transactions already included in a ZP0061 batch for the same date • Assemble file in same format as ZP0061 with file_type=ZP0063 in header • Handle zero-record case: produce header + empty body + trailer with count=0 and sum=0 • Update settlement_batch record status to GENERATED after writing file | Zp0063Generator.java producing correct afternoon settlement request file | • Transaction included in ZP0061 batch is excluded from ZP0063 output • Transactions approved after morning cutoff and SETTLEMENT_REGISTERED appear in ZP0063 • Zero-record case produces valid file with header record count=0 and trailer control_sum=0 • File header file_type field contains ZP0063 not ZP0061 • International transaction in ZP0063 has settlement_type=G | 45 | 7.4-T07 | BE | RATE-04, SCH-06
7.4-T09 | settlement-reconciliation | 7.4 | 7. Settlement, Reconciliation & Revenue | Daily reconciliation engine | 2 | Implement ZP0065 payment detail file generator | WBS 7.4 Daily Reconciliation Engine. ZP0065 (GME -> ZeroPay, deadline ~22:00 KST) provides transaction-level detail for all payments in the settlement period. Enables ZeroPay to reconcile individual transactions against merchant totals from ZP0061/ZP0063. Per-record fields: merchant_id CHAR(10), zeropay_txn_ref CHAR(20), txn_date DATE(8), txn_time TIME(6) HHMMSS, payout_amount_krw NUM(12), merchant_fee_amt NUM(12), van_fee_amt NUM(10), partner_type CHAR(1) D=Domestic/I=International, settlement_batch_ref CHAR(20) linking back to ZP0061 or ZP0063 batch. payout_amount_krw maps to transaction.target_payout (KRW, 0 decimals, rounded half-up). File header: file_type=ZP0065, business_date, total_record_count. File trailer: total_record_count, control_sum (sum payout_amount_krw). All amounts are integer KRW (no decimal separator). | • Create Zp0065Generator.java • Implement generate(LocalDate kstDate): query all SETTLEMENT_REGISTERED payment transactions for the date • For each transaction, look up the settlement_batch_ref from its ZP0061/ZP0063 batch • Build fixed-width detail record per transaction in specified field order • Compute header and trailer; write to ZP0065_{YYYYMMDD}_01.dat • Update settlement_batch record to GENERATED | Zp0065Generator.java producing correct line-item payment detail file | • Each detail record's payout_amount_krw matches the transaction's target_payout KRW value (integer, no decimal) • settlement_batch_ref in each record points to correct ZP0061 or ZP0063 batch id • partner_type=D for domestic (LOCAL partner) transactions, I for international (OVERSEAS) transactions • File trailer control_sum equals sum of all payout_amount_krw across all detail records • Refund transactions are excluded (ZP0065 covers payments only; refunds in ZP0066) | 45 | 7.4-T08 | BE | RATE-04, SCH-06
7.4-T10 | settlement-reconciliation | 7.4 | 7. Settlement, Reconciliation & Revenue | Daily reconciliation engine | 2 | Implement ZP0066 refund detail file generator | WBS 7.4 Daily Reconciliation Engine. ZP0066 (GME -> ZeroPay, deadline ~22:00 KST) provides transaction-level detail for all refunds in the settlement period. Mirrors ZP0065 layout with refund-specific fields: merchant_id CHAR(10), original_zeropay_txn_ref CHAR(20), refund_date DATE(8), refund_amount_krw NUM(12), merchant_fee_adj_amt NUM(12), settlement_batch_ref CHAR(20). Only refunds processed after the same business day as the original payment are included (same-day cancels handled via real-time API, not batch). Refund transactions in table have status=REFUNDED and direction ties to the original transaction. File header file_type=ZP0066; trailer control_sum = sum of refund_amount_krw. | • Create Zp0066Generator.java • Implement generate(LocalDate kstDate): query REFUNDED transactions where refund_date = kstDate and refund processed after original payment day • Build per-refund records with original_zeropay_txn_ref linked to original transaction • Compute header and trailer; write to ZP0066_{YYYYMMDD}_01.dat • Handle empty refund day: produce file with zero detail records • Update settlement_batch record to GENERATED | Zp0066Generator.java producing correct refund detail file | • Same-day cancels (CANCELLED status from real-time cancel API) are excluded from ZP0066 • Refund record original_zeropay_txn_ref matches the zeropay_txn_ref of the original payment transaction • refund_amount_krw is positive integer (refund amount, not negative) • Zero-refund day produces valid file with record_count=0 in header and trailer • File trailer control_sum equals sum of all refund_amount_krw values | 40 | 7.4-T07 | BE | RATE-04, SCH-06
7.4-T11 | settlement-reconciliation | 7.4 | 7. Settlement, Reconciliation & Revenue | Daily reconciliation engine | 2 | Implement SFTP file transmission service with checksum and idempotency | WBS 7.4 Daily Reconciliation Engine. Outbound SFTP transmission deposits files into /gmepay/outbound/ on the ZeroPay SFTP server. File naming convention: {FILE_ID}_{YYYYMMDD}_{SEQUENCE}.dat (e.g. ZP0061_20261015_01.dat). Retransmissions increment SEQUENCE to 02, 03, etc. SSH key authentication (RSA-4096 or ECDSA P-256); private key sourced from secrets store, never from disk. After successful PUT, compute SHA-256 of file content and store in settlement_file.file_checksum and settlement_batch.file_checksum. On failure, retry up to 3 times with exponential backoff. After 3 failures raise SFTP_TRANSMISSION_FAILURE alert to Ops. Update settlement_batch status to TRANSMITTED on success, ERROR on final failure. Transmission must be idempotent: if settlement_file record already exists for (batch_id, filename), skip re-upload unless force flag set. | • Create SftpTransmissionService.java using JSch or Apache MINA SSHD library • Implement transmit(SettlementBatch batch, byte[] fileContent): compute SHA-256, build filename with sequence, PUT to /gmepay/outbound/ • On success: create settlement_file record, update settlement_batch.file_checksum and status=TRANSMITTED • On failure: retry 3x with 5s/10s/20s backoff; after 3 failures alert Ops and set batch status=ERROR • Implement idempotency: check for existing settlement_file with same batch_id before transmitting • Unit test: mock SFTP client; verify correct filename for first attempt (seq=01) and retransmit (seq=02) | SftpTransmissionService.java with retry logic and settlement_file record creation | • First transmission produces filename ZP0061_20261015_01.dat • Retransmission produces ZP0061_20261015_02.dat with incremented sequence • SHA-256 checksum stored in both settlement_file.file_checksum and settlement_batch.file_checksum • After 3 SFTP failures, settlement_batch.status=ERROR and AlertService invoked • Idempotency: calling transmit when settlement_file already exists for batch_id skips upload and returns existing record | 55 | 7.4-T06 | BE | RATE-04, SCH-06
7.4-T12 | settlement-reconciliation | 7.4 | 7. Settlement, Reconciliation & Revenue | Daily reconciliation engine | 2 | Implement inbound ZP0062/ZP0064 settlement result file parser | WBS 7.4 Daily Reconciliation Engine. ZP0062 (~10:00 KST) confirms ZeroPay's processing of ZP0061. ZP0064 (~19:00 KST) confirms ZP0063. Both contain per-merchant settlement status and amount credited. GMEPay+ polls /gmepay/inbound/ SFTP directory for these files. After download: compute SHA-256 and store in settlement_file; parse each merchant record; compare against settlement_batch totals. If per-merchant confirmed amount matches ZP0061/ZP0063 net_settlement_amount, mark batch record SETTLEMENT_CONFIRMED. If mismatch, mark SETTLEMENT_DISCREPANCY and raise exception record. Update settlement_batch status to RECEIVED on file receipt, RECONCILED when all merchants confirmed. Parsing must be idempotent: reprocessing same file must not create duplicate reconciliation_item rows. | • Create ZpSettlementResultParser.java handling both ZP0062 and ZP0064 • Implement parse(byte[] fileContent, Long batchId): extract per-merchant amount and status from file • For each merchant record: compare confirmed_amount vs expected net_settlement_amount from batch • On match: create reconciliation_item with match_status=MATCHED; on mismatch: match_status=DISCREPANCY with discrepancy_amount=¦confirmed-expected¦ • Update settlement_batch to RECEIVED; if all records MATCHED set RECONCILED; any DISCREPANCY set status=ERROR and alert Ops • Idempotency: use INSERT ... ON CONFLICT DO NOTHING keyed on (batch_id, scheme_ref) | ZpSettlementResultParser.java with reconciliation_item creation and batch status update | • Confirmed amount matches expected: reconciliation_item.match_status=MATCHED, settlement_batch.status=RECONCILED • Confirmed amount differs by KRW 1: reconciliation_item.match_status=DISCREPANCY, discrepancy_amount=1, batch.status=ERROR • Reprocessing same ZP0062 file does not create duplicate reconciliation_item rows • settlement_file record created with correct SHA-256 checksum on download • Merchant in ZP0062 absent from GME ZP0061 records: reconciliation_item created with match_status=MISSING_GME | 55 | 7.4-T07, 7.4-T03 | BE | RATE-04, SCH-06
7.4-T13 | settlement-reconciliation | 7.4 | 7. Settlement, Reconciliation & Revenue | Daily reconciliation engine | 2 | Implement daily settlement aggregate reconciliation against ZP0065 | WBS 7.4 Daily Reconciliation Engine. RATE-04 §13.2 mandates daily check: sum of target_payout for all APPROVED transactions for a settlement day must match ZP0065 totals returned by ZeroPay (via ZP0062/ZP0064). Also: count of transactions in ZP0061/ZP0063 must match GMEPay+ outbound settlement count. Reconciliation logic: (1) Compute GME internal aggregate = SUM(target_payout KRW) and COUNT for each merchant for the date. (2) Parse ZP0065 file received from ZeroPay (or compare against ZP0062/ZP0064 totals). (3) For each merchant: if sum matches within tolerance=0 KRW (zero tolerance), mark MATCHED; if delta > 0, mark DISCREPANCY. (4) Create reconciliation_item rows. (5) If any DISCREPANCY, auto-flag to settlement exception queue (update resolution_status=UNRESOLVED). | • Create SettlementAggregateReconService.java • Implement reconcile(LocalDate kstDate): query transaction table for APPROVED transactions on kstDate grouped by merchant_id • Compare GME internal aggregate vs ZP0065-sourced totals per merchant • Create reconciliation_item for each merchant with match_status and discrepancy_amount • For any DISCREPANCY: ensure settlement_batch.status=ERROR and reconciliation_item.resolution_status=UNRESOLVED • Unit test: 2 matching merchants + 1 with KRW 100 discrepancy; verify 3 reconciliation_items created with correct match statuses | SettlementAggregateReconService.java with unit tests | • Merchant with GME sum KRW 150000 and ZP0065 sum KRW 150000: MATCHED, discrepancy_amount=0 • Merchant with GME sum KRW 150000 and ZP0065 sum KRW 149900: DISCREPANCY, discrepancy_amount=100 • Transaction count mismatch triggers DISCREPANCY even when amounts match • DISCREPANCY items have resolution_status=UNRESOLVED • No APPROVED transactions for date: reconciliation completes with zero items created (not an error) | 50 | 7.4-T12, 7.4-T05 | BE | RATE-04, SCH-06
7.4-T14 | settlement-reconciliation | 7.4 | 7. Settlement, Reconciliation & Revenue | Daily reconciliation engine | 2 | Implement prefunding ledger daily reconciliation job | WBS 7.4 Daily Reconciliation Engine. RATE-04 §13.3 requires daily reconciliation of OVERSEAS partner prefunding accounts: sum of all collection_usd DEBIT_PAYMENT entries in prefunding_ledger_entry for a partner on a given KST date + any CREDIT_TOPUP entries = net balance change. This net change must equal prefunding_account.balance_after_day - balance_before_day. Any delta > 0.01 USD triggers an ops alert. Tables involved: prefunding_account (balance DECIMAL(20,4)), prefunding_ledger_entry (account_id FK, entry_type VARCHAR(20) in {DEBIT_PAYMENT, DEBIT_REVERSAL, CREDIT_TOPUP, CREDIT_REVERSAL}, amount DECIMAL(20,4) always positive, balance_after DECIMAL(20,4)). Reconciliation: sum(DEBIT_PAYMENT + DEBIT_REVERSAL as negative) + sum(CREDIT_TOPUP + CREDIT_REVERSAL as positive) must equal (last balance_after on date) - (last balance_after before date). | • Create PrefundingLedgerReconJob.java • Implement reconcilePartner(Long partnerId, LocalDate kstDate): query all ledger entries for partner on kstDate; sum debits and credits • Compute expected net change; compare to actual balance delta using opening and closing balance_after snapshots • If ¦delta¦ > 0.01 USD: call AlertService with partner_id, date, expected, actual values • Schedule as @Scheduled(cron='0 0 3 * * *', zone='Asia/Seoul') to run at 03:00 KST • Unit test: 3 DEBIT_PAYMENT at 36.97 USD + 1 CREDIT_TOPUP at 500 USD; verify net = 500 - 3*36.97 = 389.09 USD | PrefundingLedgerReconJob.java with unit tests | • 3 DEBIT_PAYMENT entries at 36.97 USD each + 1 CREDIT_TOPUP at 500 USD: computed net change = +389.09 USD; matches balance_after delta within 0.01 USD: no alert • Delta of 0.01 USD exactly triggers alert (>= threshold) • Delta of 0.0099 USD does not trigger alert (< threshold) • LOCAL partners (no prefunding_account) are skipped without error • Balance_after from last entry of day used as closing balance; last entry before day start used as opening balance | 50 | 7.4-T03 | BE | RATE-04, SCH-06
7.4-T15 | settlement-reconciliation | 7.4 | 7. Settlement, Reconciliation & Revenue | Daily reconciliation engine | 2 | Implement SFTP inbound file poller for ZP0012/ZP0022/ZP0062/ZP0064 | WBS 7.4 Daily Reconciliation Engine. GMEPay+ must poll /gmepay/inbound/ SFTP directory for expected inbound files. Expected files and windows (KST): ZP0012 ~05:00, ZP0022 ~05:00, ZP0062 ~10:00, ZP0064 ~19:00. Late threshold: expected window + 60 minutes; if file not present, raise BATCH_FILE_LATE alert to Ops. Poller checks every 5 minutes within a window (+/- 90 minutes around expected time) to reduce unnecessary SFTP connections. On file receipt: download, compute SHA-256, create settlement_file record with direction=INBOUND, update settlement_batch to RECEIVED, hand off to the relevant parser. Must be idempotent: if settlement_file record already exists for (filename, batch_id), skip re-download. SFTP connection reuses same SSH key auth as outbound (T11). | • Create SftpInboundPoller.java with @Scheduled methods per file window • Implement pollForFile(String filePattern, LocalTime expectedKST, Long batchId): check SFTP inbound dir for matching filename • On file found: download bytes, compute SHA-256, create settlement_file, trigger parser • On late detection: elapsed > 60 min past expected and file not found: call AlertService.sendBatchFileLate(fileType, expectedTime) • Implement idempotency check on settlement_file table before download • Unit test: mock SFTP; verify late alert fires after 61-minute overrun; verify idempotency skips re-download | SftpInboundPoller.java with scheduling and late-file alerting | • ZP0062 expected at 10:00 KST; mock shows file absent at 11:01 KST: AlertService.sendBatchFileLate called with fileType=ZP0062 • ZP0062 present at 10:05 KST: downloaded, SHA-256 computed, settlement_file record created with direction=INBOUND • Second poll with same filename for same batch_id: idempotency check prevents duplicate download • settlement_batch.status transitions from GENERATED/TRANSMITTED to RECEIVED on successful file receipt • Poller does not run outside its activity window (e.g. ZP0062 poller is inactive at 02:00 KST) | 55 | 7.4-T11, 7.4-T12 | BE | RATE-04, SCH-06
7.4-T16 | settlement-reconciliation | 7.4 | 7. Settlement, Reconciliation & Revenue | Daily reconciliation engine | 2 | Implement ZP0012/ZP0022 registration result reconciliation service | WBS 7.4 Daily Reconciliation Engine. After receiving ZP0012 (confirms ZP0011 payment registrations) or ZP0022 (confirms ZP0021 refund registrations), perform line-by-line match. ZP0012 match key: zeropay_txn_ref + txn_date. Conditions and actions: (1) result_code=00 and amounts match -> mark transaction SETTLEMENT_REGISTERED; create reconciliation_item MATCHED. (2) result_code non-zero -> mark transaction REGISTRATION_FAILED; reconciliation_item DISCREPANCY; alert P1. (3) GME record absent from ZP0012 -> mark REGISTRATION_UNKNOWN; reconciliation_item MISSING_SCHEME. (4) ZP0012 record absent from GME DB -> reconciliation_item MISSING_GME; alert P1 for investigation. (5) Amount mismatch (registered_amount != submitted payout_amount_krw) -> REGISTRATION_AMOUNT_MISMATCH; reconciliation_item DISCREPANCY. Registration failures blocking ZP0061 generation trigger immediate Ops alert. | • Create RegistrationReconService.java handling both ZP0012 and ZP0022 paths • Implement reconcileRegistration(byte[] fileContent, Long batchId, String fileType): parse file; build map keyed by zeropay_txn_ref+txn_date • For each GME outbound record: look up in ZP0012 response map; classify and create reconciliation_item • For ZP0012 records not in GME outbound map: create MISSING_GME reconciliation_item; alert P1 • Update transactions to SETTLEMENT_REGISTERED or REGISTRATION_FAILED accordingly • Return count of registration failures blocking settlement; caller (batch orchestrator) gates ZP0061 generation | RegistrationReconService.java with reconciliation_item creation and transaction status updates | • result_code=00 with matching amount: transaction.batch_status=SETTLEMENT_REGISTERED, reconciliation_item.match_status=MATCHED • result_code=9002 (amount mismatch from ZeroPay): reconciliation_item.match_status=DISCREPANCY, transaction.batch_status=REGISTRATION_AMOUNT_MISMATCH • GME record zeropay_txn_ref=TXN_X absent from ZP0012: reconciliation_item match_status=MISSING_SCHEME, no transaction status change • ZP0012 record not found in GME DB: reconciliation_item match_status=MISSING_GME, AlertService.sendP1 called • reconcileRegistration on identical file twice (idempotency): no duplicate reconciliation_item rows | 55 | 7.4-T03, 7.4-T06 | BE | RATE-04, SCH-06
7.4-T17 | settlement-reconciliation | 7.4 | 7. Settlement, Reconciliation & Revenue | Daily reconciliation engine | 2 | Implement daily batch orchestrator with job dependency enforcement | WBS 7.4 Daily Reconciliation Engine. SCH-06 §8.2 mandates a strict dependency chain: ZP0061 generation requires successful ZP0012 receipt AND successful ZP0011 transmission. ZP0063 depends on morning cycle complete. ZP0065/ZP0066 depend on all settlements transmitted. ZP0061 refund portion requires successful ZP0022. Implement a DailySettlementOrchestrator that: (1) Triggers ZP0011/ZP0021 generation and SFTP transmission at 02:00 KST. (2) Polls for ZP0012/ZP0022; runs RegistrationReconService; gates ZP0061 generation if registration failures exist. (3) Generates and transmits ZP0061 at 05:00 KST only if no blocking failures. (4) At 14:00 KST generates ZP0063; at 22:00 KST generates ZP0065/ZP0066. Uses SettlementBatchService to check batch statuses before proceeding. | • Create DailySettlementOrchestrator.java with @Scheduled methods at each key time • Implement step method for each window: nightly (02:00), morning (05:00), afternoon (14:00), detail (22:00) • Each step checks prerequisite batch statuses via SettlementBatchRepository before proceeding • If prerequisites not met: log warning, update batch to ERROR, alert Ops; do not proceed • Implement isBlockedByRegistrationFailures(LocalDate date): returns true if any REGISTRATION_FAILED or MISSING_SCHEME reconciliation_items exist unresolved for the date • Unit test: registration failure present; verify ZP0061 generation is skipped and Ops alert fires | DailySettlementOrchestrator.java with dependency enforcement and unit tests | • Morning step with ZP0012 not yet RECEIVED: ZP0061 generation skipped; batch status set to ERROR; AlertService called • Morning step with all prerequisites RECONCILED: Zp0061Generator.generate invoked • ZP0061 generation with unresolved REGISTRATION_FAILED items for any merchant: blocked per-merchant; non-affected merchants proceed • Afternoon step waits for morning cycle complete: if ZP0061 batch status != TRANSMITTED, ZP0063 generation deferred • Detail step at 22:00 generates ZP0065 and ZP0066 regardless of afternoon result (detail covers full day) | 55 | 7.4-T07, 7.4-T08, 7.4-T09, 7.4-T10, 7.4-T16 | BE | RATE-04, SCH-06
7.4-T18 | settlement-reconciliation | 7.4 | 7. Settlement, Reconciliation & Revenue | Daily reconciliation engine | 2 | Implement UNCERTAIN transaction resolution via batch reconciliation | WBS 7.4 Daily Reconciliation Engine. Transactions may be in UNCERTAIN state when scheme response was not received (timeout). SAD-02 §5.2 states: UNCERTAIN -> APPROVED if ZP0012 registration confirms success; UNCERTAIN -> FAILED if ZP0012 confirms failure; UNCERTAIN window = 24 hours. Prefunding deduction is held during UNCERTAIN state (not reversed). On FAILED confirmation: create a CREDIT_REVERSAL entry in prefunding_ledger_entry to restore the collection_usd amount to the partner's prefunding_account. On APPROVED confirmation: no debit change (already debited). Resolution must happen as part of RegistrationReconService (T16) when ZP0012 is processed. After 24 hours unresolved: escalate to P1 Ops alert. | • Extend RegistrationReconService to detect UNCERTAIN transactions in ZP0012 processing • On result_code=00 for UNCERTAIN transaction: transition status to APPROVED; do not modify prefunding ledger (deduction stands) • On result_code non-zero for UNCERTAIN transaction: transition to FAILED; create CREDIT_REVERSAL prefunding_ledger_entry for collection_usd amount • Implement UncertainTransactionEscalationJob: query UNCERTAIN transactions older than 24h; send P1 alert with txn_ref list • Unit test resolution scenarios: UNCERTAIN+result_code=00 -> APPROVED; UNCERTAIN+result_code=9001 -> FAILED + reversal ledger entry | Extended RegistrationReconService with UNCERTAIN resolution logic and UncertainTransactionEscalationJob | • UNCERTAIN transaction with ZP0012 result_code=00: status transitions to APPROVED; no new prefunding_ledger_entry created • UNCERTAIN transaction with ZP0012 result_code=9001: status transitions to FAILED; CREDIT_REVERSAL entry created with amount = collection_usd; balance_after updated • After CREDIT_REVERSAL: prefunding_account.balance increases by collection_usd (e.g. 36.9714 USD) • UNCERTAIN transaction older than 24h triggers P1 alert with txn_ref • Already-APPROVED transaction receiving duplicate ZP0012 confirmation is idempotent (no duplicate ledger entry) | 50 | 7.4-T16, 7.4-T14 | BE | RATE-04, SCH-06
7.4-T19 | settlement-reconciliation | 7.4 | 7. Settlement, Reconciliation & Revenue | Daily reconciliation engine | 2 | Implement exception queue persistence and Ops alert routing | WBS 7.4 Daily Reconciliation Engine. SCH-06 §9.2 and §5.4 define exception categories. All reconciliation discrepancies create reconciliation_item rows with resolution_status=UNRESOLVED. Ops Admin portal (PRD-07) surfaces unresolved items. Recon engine must: (1) On creating a DISCREPANCY or MISSING_GME/MISSING_SCHEME reconciliation_item, also write an entry to the existing audit_log table (entity_type='reconciliation_item', action='CREATE', actor_type='SYSTEM'). (2) For P1 exceptions (registration failure, settlement amount mismatch, UNCERTAIN >24h), call AlertService.sendP1Alert with category, batch_id, details. (3) For P2 exceptions (late file, partial batch), call AlertService.sendP2Alert. AlertService interface already exists in codebase; implement the calls. Provide ExceptionQueueService with method listUnresolved(LocalDate date) returning all UNRESOLVED reconciliation_items for the date. | • Create ExceptionQueueService.java with listUnresolved(LocalDate date) querying reconciliation_item WHERE resolution_status=UNRESOLVED AND created_at KST date • In RegistrationReconService and ZpSettlementResultParser: after creating DISCREPANCY item, call AlertService.sendP1Alert • Add audit_log insertion for every reconciliation_item creation (entity_type='reconciliation_item', action='CREATE', actor_id='SYSTEM') • Implement markResolved(Long itemId, String operatorId, String note): set resolution_status=RESOLVED, resolved_by, resolved_at • Unit test listUnresolved: 3 items on date, 1 RESOLVED; returns 2 items | ExceptionQueueService.java with listUnresolved, markResolved, and audit log integration | • Creating a DISCREPANCY reconciliation_item also creates an audit_log row with entity_type='reconciliation_item' and actor_type='SYSTEM' • listUnresolved returns only UNRESOLVED items for the given date; RESOLVED items excluded • P1 alert fires for REGISTRATION_FAILED exception; P2 alert fires for late file (no reconciliation_item for late files) • markResolved sets resolution_status=RESOLVED, resolved_by=operator_id, resolved_at=now; audit_log updated • markResolved on already-RESOLVED item is idempotent (no exception, no duplicate audit entry) | 45 | 7.4-T16, 7.4-T12 | BE | RATE-04, SCH-06
7.4-T20 | settlement-reconciliation | 7.4 | 7. Settlement, Reconciliation & Revenue | Daily reconciliation engine | 2 | Implement monthly revenue reconciliation computation | WBS 7.4 Daily Reconciliation Engine. RATE-04 §13.4 requires monthly reconciliation: (1) FX margin revenue = SUM(collection_margin_usd + payout_margin_usd) for all APPROVED cross-border transactions in the month. (2) Service fee revenue = SUM(service_charge) converted to USD using cost_rate_coll at rate_locked_at. (3) Scheme fee share = 70% x ZeroPay's reported net merchant fee total for the month (source: external input by Ops). Result must be persisted or returned as a structured summary. All computations use BigDecimal. FX margin sums are straightforward (both fields already USD). Service charge may be in non-USD Settle A ccy; conversion: service_charge_usd = service_charge / cost_rate_coll (where cost_rate_coll is units of Settle A per 1 USD, so dividing converts to USD). For same-currency domestic transactions (collection_margin_usd=0, payout_margin_usd=0), service_charge is KRW; skip USD conversion for domestic (no USD-pool involvement). | • Create MonthlyRevenueReconService.java • Implement computeForMonth(YearMonth month): query APPROVED transactions with rate_locked_at in month • Sum collection_margin_usd + payout_margin_usd for cross-border transactions • For each cross-border service charge: compute service_charge_usd = service_charge.divide(cost_rate_coll, 8, HALF_UP) • Accept zeroPaySchemeFeeShareKRW parameter from Ops input; compute gmeFeeShare = zeroPaySchemeFeeShareKRW * 0.70 • Return RevenueReconciliationResult{totalFxMarginUsd, totalServiceFeeUsd, schemeFeePct, gmeSchemeShareKRW, month} | MonthlyRevenueReconService.java with RevenueReconciliationResult DTO and unit tests | • 100 cross-border txns each with collection_margin_usd=0.3697 and payout_margin_usd=0.3697: totalFxMarginUsd = 100 * 0.7394 = 73.94 USD • Service charge USD conversion: service_charge=0.36 USD with cost_rate_coll=1.0 -> service_charge_usd=0.36 (IDENTITY leg) • Service charge conversion: service_charge=500 KRW with cost_rate_coll=1380: service_charge_usd = 500/1380 = 0.3623 USD (BigDecimal, 8dp) • Domestic transactions (collection_margin_usd=0) contribute 0 to totalFxMarginUsd • ZeroPay scheme fee KRW 10,000,000 total: gmeSchemeShareKRW = 7,000,000 (70%) | 45 | 7.4-T05, 7.4-T14 | BE | RATE-04, SCH-06
7.4-T21 | settlement-reconciliation | 7.4 | 7. Settlement, Reconciliation & Revenue | Daily reconciliation engine | 2 | Unit tests for ZP0061/ZP0062 settlement reconciliation round-trip | WBS 7.4 Daily Reconciliation Engine. Test the full settlement reconciliation cycle from ZP0061 generation through ZP0062 result processing. Uses in-memory DB (H2 or test PostgreSQL container). Test scenario: 2 domestic merchants (LOCAL partner, net settlement) and 1 international merchant (OVERSEAS partner, gross settlement) with known transaction data. Verify ZP0061 file content, then process synthetic ZP0062 with all-matching amounts, verify RECONCILED outcome. Then test discrepancy: process ZP0062 with KRW 500 mismatch on one merchant; verify DISCREPANCY reconciliation_item created with discrepancy_amount=500 and batch status=ERROR. | • Create Zp0061Zp0062ReconIntegrationTest.java using @SpringBootTest with test DB • Seed transactions: merchant M1 (domestic, 3 txns at KRW 10000 each), M2 (domestic, 2 txns), M3 (international, 5 txns at KRW 20000) • Run Zp0061Generator.generate for the test date; parse generated file bytes; verify M1 net_settlement=29700 (30000 - 300 fee) and M3 net_settlement=100000 (gross) • Process synthetic ZP0062 with all amounts matching; verify all 3 reconciliation_items MATCHED; settlement_batch status=RECONCILED • Process ZP0062 variant with M2 amount short by KRW 500; verify reconciliation_item for M2 DISCREPANCY, discrepancy_amount=500, batch status=ERROR | Zp0061Zp0062ReconIntegrationTest.java with 5+ test methods | • M1 net_settlement_amount in ZP0061 = gross_txn_amount - merchant_fee_total (net domestic rule) • M3 net_settlement_amount in ZP0061 = gross_txn_amount (gross international rule) • All-matching ZP0062: 3 MATCHED reconciliation_items; settlement_batch.status=RECONCILED • KRW 500 mismatch: DISCREPANCY item with discrepancy_amount=500; resolution_status=UNRESOLVED • settlement_batch.reconciled_at populated on RECONCILED transition; null on ERROR outcome | 55 | 7.4-T12, 7.4-T07 | BE | RATE-04, SCH-06
7.4-T22 | settlement-reconciliation | 7.4 | 7. Settlement, Reconciliation & Revenue | Daily reconciliation engine | 2 | Unit tests for prefunding ledger reconciliation with debit/credit vectors | WBS 7.4 Daily Reconciliation Engine. Test PrefundingLedgerReconJob (T14) with concrete numeric vectors. Scenarios: (A) Clean day: partner starts with balance 1000.00 USD, 3 DEBIT_PAYMENT at 36.97 USD + 1 CREDIT_TOPUP at 200.00 USD -> expected net = 200 - 3*36.97 = 89.09 USD; closing balance = 1089.09 USD; delta = 0. (B) Discrepancy: same scenario but closing balance_after shows 1090.00 USD instead of 1089.09 USD -> delta = 0.91 USD > 0.01 threshold -> alert fires. (C) DEBIT_REVERSAL: UNCERTAIN transaction reversed -> CREDIT_REVERSAL entry 36.97 USD -> net = 200 - 2*36.97 + 36.97 = 163.06 USD net increase. (D) No entries for date: delta=0, no alert. | • Create PrefundingLedgerReconJobTest.java • Seed prefunding_account and prefunding_ledger_entry rows for each scenario • Run reconcilePartner for each scenario • Capture AlertService calls using Mockito mock • Assert exact delta values and alert/no-alert outcomes for each vector | PrefundingLedgerReconJobTest.java with 4+ test scenarios | • Scenario A: delta = abs(89.09 - (1089.09 - 1000.00)) = 0 -> no alert • Scenario B: delta = 0.91 USD > 0.01 -> AlertService called with partner_id, date, expected=89.09, actual=90.00 • Scenario C: CREDIT_REVERSAL correctly increases net change; delta=0 -> no alert • Scenario D (no entries): opening and closing balance same -> delta=0 -> no alert • All amounts use BigDecimal; no floating-point comparison (use compareTo, not ==) | 45 | 7.4-T14 | BE | RATE-04, SCH-06
7.4-T23 | settlement-reconciliation | 7.4 | 7. Settlement, Reconciliation & Revenue | Daily reconciliation engine | 2 | Unit tests for pool identity verifier with edge-case vectors | WBS 7.4 Daily Reconciliation Engine. Exhaustive test suite for PoolIdentityVerifier (T04) covering all branches and numeric edge cases from RATE-04. Test vectors: (1) Cross-border inbound SendMN: collectionUsd=36.9714, collectionMarginUsd=0.3697, payoutMarginUsd=0.3697, payoutUsdCost=36.2319 -> delta=0.0001 -> PASS. (2) Identity legs: collectionUsd=102.0408, each margin=1.0204, payoutUsdCost=100.00 -> delta=0 -> PASS. (3) Boundary at 0.01: delta=0.01 exactly -> FAIL. (4) Boundary at 0.0099: delta=0.0099 -> PASS. (5) Same-currency (collectionUsd=null): PASS without NPE. (6) Programmatic error simulation: collectionUsd=100, margins=0.5 each, payoutUsdCost=90 -> delta=10 >> 0.01 -> FAIL with delta=10. All assertions use BigDecimal.compareTo. | • Create PoolIdentityVerifierTest.java • Implement test method for each of the 6 vectors listed • Verify PASS/FAIL status and exact delta value using BigDecimal.compareTo(ZERO)==0 for delta in PASS cases • Verify FAIL result includes correct delta value as BigDecimal • Verify no NullPointerException for null collectionUsd input • Run tests; all must pass green | PoolIdentityVerifierTest.java with 6 test methods all passing | • Vector 1 (SendMN example): PASS, delta=0.0001 • Vector 3 (delta=0.01): FAIL returned, not PASS • Vector 4 (delta=0.0099): PASS returned • Vector 5 (same-currency null collectionUsd): PASS returned without NPE • Vector 6 (delta=10 USD): FAIL returned with delta field = 10.00 (BigDecimal) | 35 | 7.4-T04 | BE | RATE-04, SCH-06
7.4-T24 | settlement-reconciliation | 7.4 | 7. Settlement, Reconciliation & Revenue | Daily reconciliation engine | 2 | Unit tests for UNCERTAIN transaction resolution via ZP0012 | WBS 7.4 Daily Reconciliation Engine. Test RegistrationReconService (T16/T18) UNCERTAIN resolution paths. Scenarios: (A) UNCERTAIN transaction receives ZP0012 result_code=00: status -> APPROVED, no prefunding reversal, reconciliation_item MATCHED. (B) UNCERTAIN transaction receives ZP0012 result_code=9001: status -> FAILED, CREDIT_REVERSAL prefunding_ledger_entry created for collection_usd=36.9714 USD, reconciliation_item DISCREPANCY. (C) UNCERTAIN >24h old with no ZP0012 record: escalation alert fires. (D) Idempotency: process same ZP0012 confirmation twice for same txn_ref; second call produces no duplicate ledger entry. (E) Already-APPROVED transaction in ZP0012: idempotent, no state change. | • Create UncertainResolutionTest.java • Seed UNCERTAIN transactions with known collection_usd values and known created_at timestamps • Build synthetic ZP0012 byte content for each scenario • Call reconcileRegistration and verify outcomes • For scenario C: set txn created_at to 25h ago; run UncertainTransactionEscalationJob; verify P1 alert • For idempotency: call reconcileRegistration twice with same file; verify single ledger entry | UncertainResolutionTest.java with 5 test scenarios passing | • Scenario A: transaction.status=APPROVED; prefunding_ledger_entry count unchanged • Scenario B: transaction.status=FAILED; exactly 1 CREDIT_REVERSAL entry with amount=36.9714 USD • Scenario C: P1 alert contains txn_ref; transaction remains UNCERTAIN until manually resolved • Scenario D: two calls produce exactly 1 reconciliation_item and 1 prefunding_ledger_entry (no duplicates) • Scenario E: APPROVED transaction receiving duplicate ZP0012 confirmation does not change status or create ledger entry | 45 | 7.4-T18 | BE | RATE-04, SCH-06
7.4-T25 | settlement-reconciliation | 7.4 | 7. Settlement, Reconciliation & Revenue | Daily reconciliation engine | 2 | Unit tests for batch orchestrator dependency gate enforcement | WBS 7.4 Daily Reconciliation Engine. Test DailySettlementOrchestrator (T17) dependency enforcement. Scenarios: (A) Morning step with ZP0012 batch status=RECEIVED but RegistrationReconService shows REGISTRATION_FAILED items: ZP0061 generation blocked; AlertService P1 called. (B) Morning step with all prerequisites RECONCILED and no failures: Zp0061Generator.generate called once. (C) Afternoon step with morning ZP0061 batch status=ERROR: ZP0063 generation deferred; P2 alert. (D) Detail step at 22:00: ZP0065Generator and ZP0066Generator both called regardless of afternoon result status. (E) Simulate missing ZP0012 (batch status=TRANSMITTED not yet RECEIVED at 05:01 KST): ZP0061 generation blocked. | • Create DailySettlementOrchestratorTest.java with Mockito mocks for all generators and services • For each scenario: set up mock return values from SettlementBatchRepository and RegistrationReconService • Invoke the relevant orchestrator step method • Verify generator invocation or non-invocation using Mockito verify/verifyNoInteractions • Assert AlertService call count and type (P1 vs P2) for each failure scenario | DailySettlementOrchestratorTest.java with 5 test scenarios passing | • Scenario A: Zp0061Generator.generate never called; AlertService.sendP1Alert called once • Scenario B: Zp0061Generator.generate called exactly once with correct kstDate • Scenario C: Zp0063Generator.generate never called; AlertService.sendP2Alert called • Scenario D: both Zp0065Generator.generate and Zp0066Generator.generate called regardless of ZP0063 status • Scenario E: ZP0061 generation blocked when ZP0012 batch status != RECEIVED or RECONCILED | 40 | 7.4-T17 | BE | RATE-04, SCH-06
7.4-T26 | settlement-reconciliation | 7.4 | 7. Settlement, Reconciliation & Revenue | Daily reconciliation engine | 2 | Implement batch file late-arrival monitoring and alerting | WBS 7.4 Daily Reconciliation Engine. SCH-06 §9.3: if expected inbound file not arrived within 60 minutes of expected window, raise BATCH_FILE_LATE alert (Ops portal + email/Slack). Dependent batch jobs enter WAITING state (not ERROR). Escalation: if early-window file (ZP0012, ZP0022) not arrived by 08:00 KST, escalate to ZeroPay account contact. Cutoffs (SCH-06 §9.5): ZP0012/ZP0022 inbound wait cutoff 06:00 KST; ZP0062 inbound wait cutoff 12:00 KST; ZP0064 inbound wait cutoff 21:00 KST. Implement BatchLatencyMonitorJob that runs every 5 minutes in each expected window and checks settlement_batch status. If batch in TRANSMITTED status (awaiting response) and now > expected_arrival + 60 min: trigger BATCH_FILE_LATE. If now > cutoff and still not RECEIVED: trigger escalation alert. | • Create BatchLatencyMonitorJob.java with @Scheduled(fixedDelay=300000) • Implement checkLatency(LocalDate kstDate): query settlement_batch rows with status=TRANSMITTED and direction=ZP_TO_GME • For each: compare current KST time against expected arrival + 60 min; if overdue and no alert yet: call AlertService.sendBatchFileLate • Compare against cutoff time; if past cutoff: call AlertService.sendEscalationAlert • Record alert sent flag (add boolean alert_sent to settlement_batch or use a separate batch_alert table) to avoid duplicate alerts • Unit test: ZP0062 batch TRANSMITTED, current time = 11:05 KST (61 min past ~10:00): alert fires; 11:59 same state: no duplicate alert | BatchLatencyMonitorJob.java with alert deduplication and escalation logic | • ZP0012 expected 05:00 KST; monitor at 06:01 KST with batch still TRANSMITTED: BATCH_FILE_LATE alert sent • ZP0012 still TRANSMITTED at 06:01 KST (past 06:00 cutoff): escalation alert also sent • Alert deduplication: running monitor twice in same overdue state sends alert only once • ZP0062 batch received at 10:45 KST (within 60 min): no late alert generated • Batch in RECEIVED status (file arrived): no alert regardless of time | 45 | 7.4-T06, 7.4-T15 | BE | RATE-04, SCH-06
7.4-T27 | settlement-reconciliation | 7.4 | 7. Settlement, Reconciliation & Revenue | Daily reconciliation engine | 2 | Add settlement and reconciliation Admin API endpoints (read-only) | WBS 7.4 Daily Reconciliation Engine. PRD-07 Admin portal requires read access to settlement batch status and exception queue. Implement three Spring MVC REST endpoints (internal admin API, not partner-facing): (1) GET /internal/v1/settlement/batches?date={kstDate}&schemeId={id} -> list settlement_batch rows for date/scheme with status and totals. (2) GET /internal/v1/settlement/batches/{batchId}/reconciliation -> list reconciliation_item rows for the batch with match_status and resolution_status. (3) PATCH /internal/v1/settlement/reconciliation/{itemId}/resolve with body {resolved_by, resolution_note} -> calls ExceptionQueueService.markResolved. Auth: require ROLE_OPS (Spring Security). All responses use standard JSON envelope. Use BigDecimal for amount fields; never float. | • Create SettlementAdminController.java in admin package • Implement GET /internal/v1/settlement/batches returning list of SettlementBatchDto • Implement GET /internal/v1/settlement/batches/{batchId}/reconciliation returning list of ReconciliationItemDto • Implement PATCH /internal/v1/settlement/reconciliation/{itemId}/resolve calling ExceptionQueueService.markResolved • Secure all endpoints with @PreAuthorize('hasRole(ROLE_OPS)') • Integration test: seed 2 batches + 3 reconciliation items; call each endpoint; verify response structure and data | SettlementAdminController.java with 3 endpoints and integration test | • GET batches returns correct settlement_date, status, transaction_count, total_amount for each batch • GET reconciliation returns gme_amount, scheme_amount, discrepancy_amount, match_status, resolution_status for each item • PATCH resolve with valid itemId and operator: returns 200; item resolution_status=RESOLVED in DB • GET batches without ROLE_OPS returns HTTP 403 • PATCH resolve with non-existent itemId returns HTTP 404 | 55 | 7.4-T19, 7.4-T06 | BE | RATE-04, SCH-06
7.4-T28 | settlement-reconciliation | 7.4 | 7. Settlement, Reconciliation & Revenue | Daily reconciliation engine | 2 | Write developer docs for reconciliation engine flow and runbook | WBS 7.4 Daily Reconciliation Engine. Document the daily reconciliation flow for on-call developers: (1) Daily KST batch schedule with file sequence, dependencies, and error states. (2) How to manually re-trigger a failed batch step (retransmit outbound, reprocess inbound). (3) How to resolve a DISCREPANCY reconciliation_item via the Admin API. (4) Pool identity failure alert response: how to identify the offending txn_ref and escalate. (5) Prefunding ledger discrepancy: steps to identify source of delta. Keep to one markdown file in /docs/recon-engine.md within the service repo. Do not describe internal implementation; focus on ops-facing procedures. Include the complete KST batch timeline table from SCH-06. | • Create docs/recon-engine.md in the service repository • Section 1: Daily batch timeline table (all ZP00xx files, KST times, direction, dependency) • Section 2: Manual retransmission procedure (increment sequence, call SftpTransmissionService, re-run orchestrator step) • Section 3: Resolving DISCREPANCY via PATCH /internal/v1/settlement/reconciliation/{itemId}/resolve • Section 4: Pool identity failure response checklist (find txn_ref, check rate-engine fields, escalate to Finance) • Section 5: Prefunding ledger discrepancy checklist (query ledger entries for partner+date, compare to balance delta) | docs/recon-engine.md with 5 sections and KST timeline table | • KST timeline table includes all 10 ZP00xx files with correct times and directions matching SCH-06 §7.3 • Retransmission procedure specifies sequence increment and idempotency note • DISCREPANCY resolution section references exact API endpoint PATCH /internal/v1/settlement/reconciliation/{itemId}/resolve • Pool identity failure section identifies POOL_IDENTITY_FAILURE error code and lists collection_usd, payout_usd_cost, collection_margin_usd, payout_margin_usd as fields to inspect • Document reviewed by another developer; no external spec references required to follow the procedures | 40 | 7.4-T27, 7.4-T26 | BE | RATE-04, SCH-06
7.5-T01 | reporting-compliance | 7.5 | 7. Settlement, Reconciliation & Revenue | Revenue reporting & exports | 2 | Add DB migration: revenue_record table with all required columns | The revenue_record table (DAT-03 §8.2) tracks GMEPay+ revenue per committed transaction. Columns: id BIGINT PK, txn_id BIGINT FK -> transaction NOT NULL UNIQUE, partner_id BIGINT FK -> partner NOT NULL, scheme_id BIGINT FK -> qr_scheme NOT NULL, revenue_date DATE NOT NULL (= committed_at::date in KST), fx_margin_usd DECIMAL(20,4) (= collection_margin_usd + payout_margin_usd; NULL for same-currency short-circuit transactions), service_charge_amount DECIMAL(20,4) NOT NULL, service_charge_ccy CHAR(3) NOT NULL, fee_share_pct DECIMAL(6,4) NOT NULL (e.g. 0.7000 for 70% ZeroPay), estimated_fee_share_usd DECIMAL(20,4) (estimated at commit; confirmed from scheme settlement), created_at TIMESTAMPTZ NOT NULL DEFAULT now(), updated_at TIMESTAMPTZ NOT NULL DEFAULT now(). Indexes: (partner_id, revenue_date), (scheme_id, revenue_date), (revenue_date). Service charge is always in settle_a_ccy and never enters the USD pool (RATE-04 §4). | • Create Flyway migration V7_5_001__create_revenue_record.sql • Define revenue_record with all columns per spec; set DECIMAL precision DECIMAL(20,4) for amounts, DECIMAL(6,4) for fee_share_pct • Add FK constraints to transaction, partner, qr_scheme with ON DELETE RESTRICT • Add composite indexes (partner_id, revenue_date), (scheme_id, revenue_date), single index on revenue_date • Add trigger or application note: updated_at auto-refreshed on UPDATE | V7_5_001__create_revenue_record.sql Flyway migration file | • Migration applies cleanly against schema baseline with no errors • SELECT * FROM revenue_record WHERE false returns columns: id, txn_id, partner_id, scheme_id, revenue_date, fx_margin_usd, service_charge_amount, service_charge_ccy, fee_share_pct, estimated_fee_share_usd, created_at, updated_at • INSERT with txn_id already present in table violates UNIQUE constraint • INSERT with partner_id not in partner table violates FK constraint • EXPLAIN on WHERE partner_id = 1 AND revenue_date = '2026-01-15' uses the composite index | 30 |  | BE | PRD-07
7.5-T02 | reporting-compliance | 7.5 | 7. Settlement, Reconciliation & Revenue | Revenue reporting & exports | 2 | Add confirmed_fee_share_krw column to revenue_record via migration | The revenue_record.estimated_fee_share_usd is set at commit time. A second column confirmed_fee_share_krw DECIMAL(20,4) is populated later when ZeroPay settlement result files (ZP0062/ZP0064) are received and reconciled. Until then it is NULL. This is part of the same revenue_record table but is added as a separate migration to avoid blocking T01. The fee share is: GME gets 70% of net merchant fee from ZeroPay (scheme.gme_fee_share_pct = 0.70). Domestic settlement is net (GME deducts fee before settlement); international is gross (GME invoices monthly). Both streams must be separately reportable. | • Create Flyway migration V7_5_002__revenue_record_add_confirmed_fee_share.sql • ALTER TABLE revenue_record ADD COLUMN confirmed_fee_share_krw DECIMAL(20,4) NULL • ALTER TABLE revenue_record ADD COLUMN settlement_model VARCHAR(20) NULL CHECK (settlement_model IN ('NET','GROSS')) to distinguish domestic from international revenue • Add an index on (revenue_date, settlement_model) for filtered report queries | V7_5_002__revenue_record_add_confirmed_fee_share.sql Flyway migration file | • Migration applies cleanly; revenue_record now has confirmed_fee_share_krw and settlement_model columns • confirmed_fee_share_krw can be NULL (pre-settlement) and updated to a positive decimal after reconciliation • settlement_model rejects values other than NET and GROSS • SELECT confirmed_fee_share_krw FROM revenue_record WHERE confirmed_fee_share_krw IS NOT NULL returns only post-settlement rows | 20 | 7.5-T01 | BE | PRD-07
7.5-T03 | reporting-compliance | 7.5 | 7. Settlement, Reconciliation & Revenue | Revenue reporting & exports | 2 | Define RevenueRecord JPA entity and repository | The revenue_record table (T01, T02) is the backing store for all revenue reporting. Java entity: RevenueRecord with @Entity @Table(name='revenue_record'). BigDecimal fields for all amounts (never double). revenue_date is LocalDate. fee_share_pct is BigDecimal(6,4). Field fx_margin_usd is nullable (null for same-currency short-circuit where collection_ccy = settle_a_ccy = settle_b_ccy = payout_ccy). Repository must support: findByPartnerIdAndRevenueDateBetween, findBySchemeIdAndRevenueDateBetween, and a custom JPQL query for the revenue summary (aggregated sums grouped by partner, scheme, revenue_date). | • Create RevenueRecord @Entity in com.gmepayplus.reporting.domain with all mapped columns from T01+T02 • Add @ManyToOne lazy to Partner and QrScheme; @OneToOne to Transaction via txn_id • Create RevenueRecordRepository extends JpaRepository<RevenueRecord, Long> with findAllByPartnerIdAndRevenueDateBetween(Long partnerId, LocalDate from, LocalDate to) • Add findAllBySchemeIdAndRevenueDateBetween and findAllByRevenueDateBetween • Ensure all BigDecimal columns use @Column(precision=20, scale=4) or matching precisions per spec | RevenueRecord.java entity and RevenueRecordRepository.java in com.gmepayplus.reporting | • Entity has field fxMarginUsd annotated @Column(nullable=true) — must not throw when null • Entity has field feeSharePct annotated @Column(precision=6, scale=4) • findAllByPartnerIdAndRevenueDateBetween returns correct subset when called with partnerId=2, from=2026-01-01, to=2026-01-31 in a test DB • Saving a RevenueRecord with txn_id already mapped throws DataIntegrityViolationException (UNIQUE on txn_id) • Entity maps settlement_model as enum or String with CHECK constraint enforced at DB level | 35 | 7.5-T01, 7.5-T02 | BE | PRD-07
7.5-T04 | reporting-compliance | 7.5 | 7. Settlement, Reconciliation & Revenue | Revenue reporting & exports | 2 | Implement RevenueRecordService.createFromTransaction() | On every successful CommitTransaction, a revenue_record row must be created atomically before the commit completes. Inputs: the committed Transaction object (which carries all locked rate-pool values: collection_margin_usd, payout_margin_usd, service_charge, service_charge_ccy, rule.fee_share_pct, payment mode, direction). Rules: fx_margin_usd = collection_margin_usd + payout_margin_usd (NULL if transaction.is_same_ccy_shortcircuit = true). revenue_date = transaction.committed_at converted to KST date (UTC+9). settlement_model = NET if direction = DOMESTIC, GROSS if direction = INBOUND or OUTBOUND. estimated_fee_share_usd = NULL at this stage (confirmed later from settlement). service_charge_amount and service_charge_ccy copied from the transaction record. | • Create RevenueRecordService in com.gmepayplus.reporting.service with method createFromTransaction(Transaction txn) • Compute revenue_date = txn.committedAt.atZone(ZoneId.of('Asia/Seoul')).toLocalDate() • Compute fx_margin_usd: if txn.isSameCcyShortcircuit then null, else txn.collectionMarginUsd.add(txn.payoutMarginUsd) • Derive settlement_model from txn.direction: DOMESTIC -> NET, INBOUND/OUTBOUND/HUB -> GROSS • Persist RevenueRecord via RevenueRecordRepository; method must be called within the same transaction as CommitTransaction (use @Transactional propagation MANDATORY) | RevenueRecordService.java with createFromTransaction() in com.gmepayplus.reporting.service | • Cross-border txn with collection_margin_usd=10.00, payout_margin_usd=10.00 produces revenue_record.fx_margin_usd=20.00 • Same-currency txn (is_same_ccy_shortcircuit=true) produces revenue_record.fx_margin_usd=NULL • DOMESTIC direction produces settlement_model=NET; INBOUND produces GROSS • revenue_date is the KST date of committed_at (e.g. committed_at=2026-01-15T15:30:00Z -> revenue_date=2026-01-16 in KST+9) • Calling createFromTransaction outside a transaction context throws TransactionRequiredException (due to MANDATORY propagation) | 40 | 7.5-T03 | BE | PRD-07
7.5-T05 | reporting-compliance | 7.5 | 7. Settlement, Reconciliation & Revenue | Revenue reporting & exports | 2 | Implement updateConfirmedFeeShare() after settlement reconciliation | After ZeroPay batch files ZP0062 (morning settlement result) or ZP0064 (afternoon settlement result) are received and matched, the revenue_record.confirmed_fee_share_krw column must be updated with the actual GME fee share. Fee share formula: GME net fee share = gross_payout_krw * merchant_fee_rate * gme_fee_share_pct (0.70 for ZeroPay). For NET settlement (domestic), this has already been deducted; for GROSS settlement (international), it is invoiced monthly. Method signature: updateConfirmedFeeShare(Long txnId, BigDecimal grossPayoutKrw, BigDecimal merchantFeeRate, BigDecimal gmeSharePct). This is called by the settlement reconciliation service (WBS 6.x) after batch processing. | • Add updateConfirmedFeeShare(Long txnId, BigDecimal grossPayoutKrw, BigDecimal merchantFeeRate, BigDecimal gmeSharePct) to RevenueRecordService • Compute confirmedFeeShareKrw = grossPayoutKrw.multiply(merchantFeeRate).multiply(gmeSharePct) rounded to 0 decimal places (KRW has 0 decimal scale) • Fetch revenue_record by txnId; throw NotFoundException if missing; set confirmed_fee_share_krw and persist • Log at INFO: txn_id, computed fee share, merchant_fee_rate, gme_fee_share_pct used • Annotate @Transactional; throw exception if txnId maps to a record where confirmed_fee_share_krw is already non-null (prevent double-update) | updateConfirmedFeeShare() method in RevenueRecordService.java | • grossPayoutKrw=10000, merchantFeeRate=0.0170, gmeSharePct=0.70 -> confirmedFeeShareKrw=119 (10000*0.017*0.70=119.0, rounded to 0dp = 119) • grossPayoutKrw=100000, merchantFeeRate=0.0080, gmeSharePct=0.70 -> confirmedFeeShareKrw=560 • Calling updateConfirmedFeeShare with a txnId whose revenue_record already has confirmed_fee_share_krw set throws DuplicateUpdateException • Calling with unknown txnId throws NotFoundException • Update is @Transactional and rolls back if an exception occurs mid-method | 35 | 7.5-T04 | BE | PRD-07
7.5-T06 | reporting-compliance | 7.5 | 7. Settlement, Reconciliation & Revenue | Revenue reporting & exports | 2 | Define RevenueReportQuery DTO with all filter parameters | The revenue report (PRD-07 §11.3.2) supports filtering by: period granularity (DAILY/WEEKLY/MONTHLY/CUSTOM), date range (from/to inclusive, LocalDate), partner_id (nullable -> all partners), scheme_id (nullable -> all schemes), direction (nullable -> all directions: INBOUND/OUTBOUND/DOMESTIC/HUB), revenue_stream (nullable -> both; or FX_MARGIN / SCHEME_FEE). Validation rules: from must not be after to; max range for non-async report = 366 days; from and to are required. This DTO is used by the report query service and serialised to/from the Admin API. | • Create RevenueReportQuery record/class in com.gmepayplus.reporting.dto with fields: LocalDate from, LocalDate to, Long partnerId (nullable), Long schemeId (nullable), Direction direction (nullable), RevenueStream revenueStream (nullable), PeriodGranularity granularity • Create enums: PeriodGranularity { DAILY, WEEKLY, MONTHLY, CUSTOM } and RevenueStream { FX_MARGIN, SCHEME_FEE } • Add @Valid Bean Validation: @NotNull on from and to; custom validator that from <= to; max range 366 days • Add a helper method getEffectivePeriodLabel() that returns a String label for display (e.g. '2026-01' for monthly, '2026-01-15' for daily) | RevenueReportQuery.java DTO and supporting enums in com.gmepayplus.reporting.dto | • Query with from=2026-01-01, to=2025-12-31 fails Bean Validation (from after to) • Query with from=2024-01-01, to=2026-01-01 (>366 days) fails Bean Validation • Query with from=2026-01-01, to=2026-01-31, granularity=MONTHLY, partnerId=null passes validation • All fields except from, to, granularity are nullable (verified by constructing with only mandatory fields) • PeriodGranularity.values() = {DAILY, WEEKLY, MONTHLY, CUSTOM} | 25 |  | BE | PRD-07
7.5-T07 | reporting-compliance | 7.5 | 7. Settlement, Reconciliation & Revenue | Revenue reporting & exports | 2 | Define RevenueReportRow and RevenueReportResponse DTOs | The revenue report (PRD-07 §11.3.2) returns rows with these columns per reporting period/partner/scheme: period (String label), partner_name, scheme_name, transaction_count (Long), gross_payout_krw (BigDecimal), merchant_fee_total_krw (BigDecimal), gme_scheme_share_krw (BigDecimal), collection_margin_usd (BigDecimal), payout_margin_usd (BigDecimal), total_fx_margin_usd (BigDecimal = collection + payout margin), service_charges_settle_a (BigDecimal), service_charge_ccy (String), total_revenue_krw_equiv (BigDecimal = scheme share + FX margin converted to KRW + service charges converted to KRW). The response wraps a list of rows plus summary totals and metadata (query params echoed back, generated_at timestamp). | • Create RevenueReportRow with all listed fields; use BigDecimal for all monetary amounts; annotate with @JsonProperty for stable API names • Create RevenueReportResponse with fields: List<RevenueReportRow> rows, RevenueReportRow totals (sum row), RevenueReportQuery query (echo), LocalDateTime generatedAt • Ensure BigDecimal fields use proper serialization (no scientific notation); configure Jackson ObjectMapper with WRITE_BIGDECIMAL_AS_PLAIN • Add totalRevenue() convenience method on the totals row | RevenueReportRow.java and RevenueReportResponse.java in com.gmepayplus.reporting.dto | • RevenueReportRow has all 13 named fields; each monetary field is BigDecimal • total_fx_margin_usd field value equals collection_margin_usd + payout_margin_usd when constructed in a test • JSON serialisation of total_revenue_krw_equiv = 1234567.89 renders as '1234567.89' not '1.23456789E+6' • RevenueReportResponse.getTotals() returns a row whose transaction_count equals the sum of all row transaction counts • generatedAt is set to current UTC time at construction | 30 | 7.5-T06 | BE | PRD-07
7.5-T08 | reporting-compliance | 7.5 | 7. Settlement, Reconciliation & Revenue | Revenue reporting & exports | 2 | Implement RevenueReportQueryService with JPQL aggregation query | The query service executes the aggregated revenue report. It must query revenue_record joined to transaction (for merchant_fee from the scheme) grouped by (period bucket, partner_id, scheme_id). Key aggregations: SUM(fx_margin_usd) as total_fx_margin, SUM(service_charge_amount) by ccy, SUM(confirmed_fee_share_krw) as gme_scheme_share, COUNT(*) as transaction_count. Period bucketing: DAILY = revenue_date, WEEKLY = date_trunc('week', revenue_date), MONTHLY = date_trunc('month', revenue_date). Filters map directly to WHERE clauses from RevenueReportQuery. For the FX_MARGIN stream filter: include only rows where fx_margin_usd IS NOT NULL; for SCHEME_FEE: include only rows where confirmed_fee_share_krw IS NOT NULL; no filter = all rows. | • Create RevenueReportQueryService in com.gmepayplus.reporting.service • Build a JPQL or native SQL query with dynamic WHERE clause built from RevenueReportQuery fields (use JPA Criteria API or a QueryDSL predicate builder to avoid SQL injection) • Implement period bucketing by appending the appropriate date_trunc expression based on granularity • Map result set rows to RevenueReportRow DTOs; compute totals row as in-memory sum after fetching • Apply revenue stream filter per spec: FX_MARGIN -> WHERE fx_margin_usd IS NOT NULL; SCHEME_FEE -> WHERE confirmed_fee_share_krw IS NOT NULL | RevenueReportQueryService.java in com.gmepayplus.reporting.service | • Query with partnerId=1, from=2026-01-01, to=2026-01-31, granularity=DAILY returns one row per day that has revenue records for that partner • Query with revenueStream=FX_MARGIN excludes domestic (same-ccy) transactions which have fx_margin_usd=NULL • Query with granularity=MONTHLY groups all January records into a single row with summed amounts • SQL/JPQL parameters are bound (not string-concatenated) to prevent injection; verify with a partnerId containing a SQL fragment like '1 OR 1=1' • Totals row transaction_count equals sum of all individual rows transaction_count | 50 | 7.5-T03, 7.5-T07 | BE | PRD-07
7.5-T09 | reporting-compliance | 7.5 | 7. Settlement, Reconciliation & Revenue | Revenue reporting & exports | 2 | Implement total_revenue_krw_equiv conversion in report service | The revenue report column total_revenue_krw_equiv (PRD-07 §11.3.2) = GME scheme share (KRW) + FX margin (USD converted to KRW) + service charges (converted to KRW if not already in KRW). Conversion uses the treasury rate at the time of the report query (current rate from treasury_rate table: SELECT rate FROM treasury_rate WHERE ccy_pair='usd_krw' ORDER BY effective_at DESC LIMIT 1). For service charges already in KRW (settle_a_ccy='KRW'), no conversion needed. For service charges in USD (settle_a_ccy='USD'), multiply by usd_krw rate. This conversion is for display/reporting only; the underlying stored values are NOT modified. USD precision is 2dp for final display; KRW is 0dp. | • Add a private computeTotalRevenueKrwEquiv(RevenueReportRow row, BigDecimal usdKrwRate) method to RevenueReportQueryService • Fetch current usd_krw rate once per report run (not per row); log the rate used in the report response metadata • Compute: fxMarginKrw = row.totalFxMarginUsd.multiply(usdKrwRate) rounded to 0dp; serviceChargeKrw = row.serviceChargeCcy=='KRW' ? row.serviceChargesSettleA : row.serviceChargesSettleA.multiply(usdKrwRate) rounded 0dp; total = row.gmeSchemeShareKrw + fxMarginKrw + serviceChargeKrw • Set row.totalRevenueKrwEquiv = total • Add usdKrwRateUsed and usdKrwRateEffectiveAt fields to RevenueReportResponse for auditability | computeTotalRevenueKrwEquiv() method wired into RevenueReportQueryService.java | • totalFxMarginUsd=100.00, usdKrwRate=1350.00, serviceChargesSettleA=5000 in KRW, gmeSchemeShareKrw=7000 -> totalRevenueKrwEquiv = 7000 + 135000 + 5000 = 147000 • totalFxMarginUsd=50.00, usdKrwRate=1350.00, serviceChargesSettleA=10.00 in USD -> serviceChargeKrw=13500, total = gmeSchemeShareKrw + 67500 + 13500 • If usd_krw treasury rate is missing, service throws ReportGenerationException with message 'USD/KRW rate not available' • usdKrwRateUsed is included in response JSON for audit verification • Same-ccy row with fx_margin_usd=NULL has fxMarginKrw=0 in total (null treated as 0) | 40 | 7.5-T08 | BE | PRD-07
7.5-T10 | reporting-compliance | 7.5 | 7. Settlement, Reconciliation & Revenue | Revenue reporting & exports | 2 | Add GET /admin/v1/reports/revenue endpoint handler | Admin API endpoint for querying the revenue report. Role access: FINANCE_ANALYST, OPS_OPERATOR, SUPER_ADMIN (permission: 'Export Revenue Report' per PRD-07 §12.3). Request parameters map to RevenueReportQuery: from (ISO date, required), to (ISO date, required), granularity (DAILY/WEEKLY/MONTHLY/CUSTOM, default DAILY), partner_id (optional Long), scheme_id (optional Long), direction (optional String), revenue_stream (optional String: FX_MARGIN/SCHEME_FEE). Response: RevenueReportResponse JSON. Synchronous for up to 366-day range. The endpoint must log the export event to audit_log (category: 'data_export', entity_type: 'revenue_report', actor_id from JWT). ADMIN_VIEWER role does NOT have access (permission matrix PRD-07 §12.3). | • Create RevenueReportController in com.gmepayplus.admin.controller with @GetMapping('/admin/v1/reports/revenue') • Bind query params to RevenueReportQuery; run @Valid validation; return 400 on violations • Enforce role check: require FINANCE_ANALYST, OPS_OPERATOR, or SUPER_ADMIN; return 403 for ADMIN_VIEWER or unauthenticated • Delegate to RevenueReportQueryService.query(RevenueReportQuery) • Write audit log entry on every successful call: actor_id, event_type='revenue_report.exported', metadata including date range and filter params | RevenueReportController.java in com.gmepayplus.admin.controller | • GET with valid params and FINANCE_ANALYST JWT returns 200 with RevenueReportResponse JSON • GET with ADMIN_VIEWER JWT returns 403 • GET with from=2026-01-31&to=2026-01-01 (from > to) returns 400 with field-level error • GET with a range > 366 days returns 400 with message containing 'maximum range is 366 days' • Audit log entry is written with correct actor_id and date range metadata on every 200 response | 45 | 7.5-T08, 7.5-T09 | BE | PRD-07
7.5-T11 | reporting-compliance | 7.5 | 7. Settlement, Reconciliation & Revenue | Revenue reporting & exports | 2 | Implement CSV export for revenue report (streaming, up to 100k rows) | The revenue report must be exportable as CSV (PRD-07 §11.3.2, §15.8). The same filter parameters as the JSON report apply. CSV columns (in order): period, partner_name, scheme_name, transaction_count, gross_payout_krw, merchant_fee_total_krw, gme_scheme_share_krw, collection_margin_usd, payout_margin_usd, total_fx_margin_usd, service_charges_settle_a, service_charge_ccy, total_revenue_krw_equiv. The export must complete within 10 seconds for a 30-day period (PRD-07 §15.8). Use streaming (write rows to response OutputStream as they are fetched) to avoid OOM on large result sets. The endpoint is GET /admin/v1/reports/revenue/export?format=csv. Audit log entry required (same as JSON endpoint). | • Add GET /admin/v1/reports/revenue/export to RevenueReportController with produces='text/csv' • Use Spring's StreamingResponseBody to stream rows directly to response without buffering entire result in memory • Set Content-Disposition header: attachment; filename=revenue_report_{from}_{to}.csv • Write CSV header row then data rows using a lightweight CSV writer (e.g. OpenCSV or manual comma-escaping); escape fields with commas or quotes • Enforce same role check (FINANCE_ANALYST, OPS_OPERATOR, SUPER_ADMIN) and write audit log entry | CSV export endpoint wired into RevenueReportController.java; streaming via StreamingResponseBody | • GET /admin/v1/reports/revenue/export?from=2026-01-01&to=2026-01-31 returns Content-Type: text/csv and Content-Disposition with filename revenue_report_2026-01-01_2026-01-31.csv • CSV first row is the header row with exactly the 13 column names in specified order • A field containing a comma (e.g. partner name 'GME, Remit') is wrapped in double-quotes in the CSV output • ADMIN_VIEWER JWT returns 403 • An audit log entry with event_type='revenue_report.csv_exported' is created on each successful export | 45 | 7.5-T10 | BE | PRD-07
7.5-T12 | reporting-compliance | 7.5 | 7. Settlement, Reconciliation & Revenue | Revenue reporting & exports | 2 | Add DB indexes and query plan check for revenue report performance | The revenue report query (T08) must return within 10 seconds for a 30-day period (PRD-07 §15.8). The primary query joins revenue_record with partner and qr_scheme, filters on revenue_date range and optionally partner_id/scheme_id, and groups by date bucket. Required indexes (beyond those in T01): partial index on revenue_record (revenue_date) WHERE fx_margin_usd IS NOT NULL (speeds FX_MARGIN stream filter); partial index WHERE confirmed_fee_share_krw IS NOT NULL (speeds SCHEME_FEE filter). Also verify the (partner_id, revenue_date) composite index from T01 is used by EXPLAIN ANALYZE. | • Create Flyway migration V7_5_003__revenue_record_report_indexes.sql • Add: CREATE INDEX CONCURRENTLY idx_rr_fx_margin_notnull ON revenue_record(revenue_date) WHERE fx_margin_usd IS NOT NULL • Add: CREATE INDEX CONCURRENTLY idx_rr_fee_share_notnull ON revenue_record(revenue_date) WHERE confirmed_fee_share_krw IS NOT NULL • Run EXPLAIN (ANALYZE, BUFFERS) on the representative report query for 30-day range with partnerId filter; paste plan into a code comment in the migration file • Assert query plan uses at least one index scan (not sequential scan) for the 30-day/partner filter scenario | V7_5_003__revenue_record_report_indexes.sql Flyway migration | • Migration applies without error; \d revenue_record shows 5 indexes total (PK + 2 from T01 + 2 new) • EXPLAIN on WHERE partner_id=1 AND revenue_date BETWEEN '2026-01-01' AND '2026-01-31' shows Index Scan on idx_rr_partner_date • EXPLAIN on WHERE fx_margin_usd IS NOT NULL AND revenue_date BETWEEN '2026-01-01' AND '2026-01-31' shows Index Scan on idx_rr_fx_margin_notnull • EXPLAIN on WHERE confirmed_fee_share_krw IS NOT NULL shows Index Scan on idx_rr_fee_share_notnull • No Seq Scan on revenue_record for any of the above queries on a dataset > 10k rows | 35 | 7.5-T01, 7.5-T08 | BE | PRD-07
7.5-T13 | reporting-compliance | 7.5 | 7. Settlement, Reconciliation & Revenue | Revenue reporting & exports | 2 | Implement revenue report Settlement Batch Status view data query | PRD-07 §11.2.2 describes a Settlement Batch Status table with columns: settlement_date, transaction_count, gross_payout_krw, gme_fee_share_krw (70% of net merchant fee), net_settlement_krw (domestic net model), ZP0011/ZP0061/ZP0062 statuses, reconciliation_status. This data is sourced from settlement_batch (one row per file per date) and revenue_record (aggregated). The query service must return a SettlementBatchSummary DTO per settlement_date. Domestic NET: net_settlement = gross_payout - gme_fee_share. International GROSS: net_settlement = gross_payout (fee invoiced monthly separately). | • Create SettlementBatchSummaryDTO with fields: settlementDate (LocalDate), schemeCode (String), transactionCount (Long), grossPayoutKrw (BigDecimal), gmeFeeShareKrw (BigDecimal), netSettlementKrw (BigDecimal), zp0011Status, zp0061Status, zp0062Status (all String), reconciliationStatus (String), actions (List<String>) • Create SettlementBatchQueryService.getSettlementBatchSummaries(LocalDate from, LocalDate to, Long schemeId) that joins settlement_batch and aggregates revenue_record • Compute netSettlementKrw: if settlement_model=NET -> grossPayoutKrw - gmeFeeShareKrw; if GROSS -> grossPayoutKrw • Return results ordered by settlementDate DESC | SettlementBatchSummaryDTO.java and SettlementBatchQueryService.java in com.gmepayplus.reporting.service | • For a domestic (NET) batch with grossPayoutKrw=1000000, gmeFeeShareKrw=8000: netSettlementKrw=992000 • For an international (GROSS) batch with grossPayoutKrw=500000: netSettlementKrw=500000 regardless of fee share • Results are ordered by settlementDate DESC • Query for from=2026-01-01 to=2026-01-31 does not include rows with settlementDate outside that range • Missing ZP0062 result shows zp0062Status='Not yet received' | 45 | 7.5-T03, 7.5-T05 | BE | PRD-07
7.5-T14 | reporting-compliance | 7.5 | 7. Settlement, Reconciliation & Revenue | Revenue reporting & exports | 2 | Add GET /admin/v1/reports/settlement-batches endpoint | Admin API endpoint for the Settlement & Revenue module's batch status table (PRD-07 §11.2.2). Role access: FINANCE_ANALYST, OPS_OPERATOR, SUPER_ADMIN. Parameters: from (ISO date, required), to (ISO date, required, max 90-day range), scheme_id (optional). Response: list of SettlementBatchSummaryDTO ordered by settlementDate DESC. Pagination: 50 rows per page (page/size params). The endpoint also exposes an action for flagging a discrepancy: PUT /admin/v1/reports/settlement-batches/{batchId}/flag-exception requires OPS_OPERATOR or SUPER_ADMIN role. | • Add GET /admin/v1/reports/settlement-batches to a new SettlementBatchController in com.gmepayplus.admin.controller • Bind from/to/scheme_id/page/size params; validate max 90-day range; return 400 on violation • Delegate to SettlementBatchQueryService.getSettlementBatchSummaries(); wrap in Page response with pagination metadata • Add PUT /admin/v1/reports/settlement-batches/{batchId}/flag-exception (body: {reason: String}); call reconciliation service to create exception record; require OPS_OPERATOR or SUPER_ADMIN • Write audit log on flag-exception action | SettlementBatchController.java in com.gmepayplus.admin.controller | • GET with valid params and FINANCE_ANALYST JWT returns 200 with paginated list • GET with ADMIN_VIEWER JWT returns 403 • GET with from/to range > 90 days returns 400 • PUT flag-exception with FINANCE_ANALYST JWT returns 403 (Finance cannot flag) • PUT flag-exception with OPS_OPERATOR JWT returns 200 and creates reconciliation_item with resolution_status=ESCALATED | 40 | 7.5-T13 | BE | PRD-07
7.5-T15 | reporting-compliance | 7.5 | 7. Settlement, Reconciliation & Revenue | Revenue reporting & exports | 2 | Implement merchant fee schedule reference view in Settlement module | PRD-07 §11.3.3: the Settlement & Revenue module displays the merchant fee schedule configured per scheme as a reference for revenue calculations. Data comes from the qr_scheme merchant fee table (stored as JSON in qr_scheme.merchant_fee_table or as a structured table per scheme config in WBS 4.x). The fee schedule is READ ONLY from this module (changes go through Schemes module). The view shows: merchant_type, domestic_partner_rate%, cross_border_partner_rate%. ZeroPay reference values: General=0.80%/1.70%, Large Franchise=operator-configured. FINANCE_ANALYST and above can view. | • Create GET /admin/v1/reports/settlement-batches/fee-schedule?scheme_id={id} endpoint in SettlementBatchController • Query qr_scheme merchant fee table for the given scheme_id; return as MerchantFeeScheduleDTO list (merchant_type, domesticRate, crossBorderRate) • Require FINANCE_ANALYST, OPS_OPERATOR, or SUPER_ADMIN; return 403 otherwise • Return 404 if scheme_id not found • Document that this is read-only; do not expose any PUT/POST/DELETE on this path | GET /admin/v1/reports/settlement-batches/fee-schedule endpoint in SettlementBatchController.java | • GET with scheme_id for ZeroPay returns merchant fee rows including General at domesticRate=0.0080 and crossBorderRate=0.0170 • GET with ADMIN_VIEWER JWT returns 403 • GET with unknown scheme_id returns 404 • Response is read-only: no PUT/POST/DELETE method registered on this path (405 if attempted) • domesticRate and crossBorderRate fields are BigDecimal with scale 4 (e.g. 0.0080 not 0.8) | 30 | 7.5-T14 | BE | PRD-07
7.5-T16 | reporting-compliance | 7.5 | 7. Settlement, Reconciliation & Revenue | Revenue reporting & exports | 2 | Unit tests: RevenueRecordService.createFromTransaction() edge cases | Tests for T04 logic. Key test vectors: (1) Cross-border INBOUND with collection_margin_usd=10.50, payout_margin_usd=9.50 -> fx_margin_usd=20.00, settlement_model=GROSS. (2) DOMESTIC same-currency (is_same_ccy_shortcircuit=true) -> fx_margin_usd=NULL, settlement_model=NET. (3) Timezone edge case: committed_at=2026-01-15T15:00:00Z -> revenue_date=2026-01-16 (KST is UTC+9). (4) committed_at=2026-01-15T14:59:00Z -> revenue_date=2026-01-15. (5) Missing rule.fee_share_pct -> exception before persist. All tests use mocked RevenueRecordRepository (no DB). | • Create RevenueRecordServiceTest in src/test/java • Test case 1: cross-border INBOUND transaction -> assert fx_margin_usd=20.00, settlement_model=GROSS • Test case 2: domestic same-ccy transaction -> assert fx_margin_usd=null, settlement_model=NET • Test case 3: timezone edge case committed_at=2026-01-15T15:00:00Z -> assert revenue_date=2026-01-16 • Test case 4: committed_at=2026-01-15T14:59:00Z -> assert revenue_date=2026-01-15 • Test case 5: transaction with null fee_share_pct on rule -> assert IllegalArgumentException or DataIntegrityViolationException before save | RevenueRecordServiceTest.java with 5 test methods, all passing | • Test 1 passes: fx_margin_usd=20.00 (BigDecimal equality, scale-independent) • Test 2 passes: fx_margin_usd is null • Test 3 passes: revenue_date = LocalDate.of(2026,1,16) • Test 4 passes: revenue_date = LocalDate.of(2026,1,15) • Test 5 passes: exception is thrown before repository.save() is called (mock verify zero interactions after exception) | 40 | 7.5-T04 | BE | PRD-07
7.5-T17 | reporting-compliance | 7.5 | 7. Settlement, Reconciliation & Revenue | Revenue reporting & exports | 2 | Unit tests: updateConfirmedFeeShare() calculation vectors | Tests for T05 logic. Key vectors: (1) grossPayoutKrw=10000, merchantFeeRate=0.0170, gmeSharePct=0.70 -> confirmedFeeShareKrw=119. (2) grossPayoutKrw=100000, merchantFeeRate=0.0080, gmeSharePct=0.70 -> 560. (3) grossPayoutKrw=50000, merchantFeeRate=0.0170, gmeSharePct=0.70 -> 595 (50000*0.017*0.7=595.0). (4) Already-set confirmed_fee_share_krw -> DuplicateUpdateException. (5) Unknown txnId -> NotFoundException. Rounding: KRW is 0 decimal places, use HALF_UP. All tests use mocked repository. | • Create UpdateConfirmedFeeShareTest in src/test/java • Test vector 1: 10000 * 0.0170 * 0.70 = 119 • Test vector 2: 100000 * 0.0080 * 0.70 = 560 • Test vector 3: 50000 * 0.0170 * 0.70 = 595 • Test already-set guard: revenue_record with confirmed_fee_share_krw=100 -> DuplicateUpdateException • Test unknown txnId -> NotFoundException | UpdateConfirmedFeeShareTest.java with 5 test methods, all passing | • Vector 1 passes: confirmedFeeShareKrw = 119 (BigDecimal with scale 0) • Vector 2 passes: 560 • Vector 3 passes: 595 • DuplicateUpdateException test passes; repository.save() is NOT called (mock verify) • NotFoundException test passes when repository.findByTxnId() returns empty | 35 | 7.5-T05 | BE | PRD-07
7.5-T18 | reporting-compliance | 7.5 | 7. Settlement, Reconciliation & Revenue | Revenue reporting & exports | 2 | Unit tests: RevenueReportQueryService aggregation and filtering | Tests for T08/T09. Key test vectors: (1) 3 revenue_record rows for partner_id=1, dates 2026-01-01/02/03 with fx_margin_usd=10.00, 20.00, 30.00 each, service_charge=500 KRW each, confirmed_fee_share_krw=100 each -> DAILY report returns 3 rows; MONTHLY returns 1 row with totals: fx_margin_usd=60.00, service_charges=1500, gme_scheme_share=300. (2) RevenueStream=FX_MARGIN filter excludes same-ccy row (fx_margin_usd=NULL). (3) Total revenue KRW equiv: usdKrwRate=1350, total_fx_margin=60.00 -> fxMarginKrw=81000; service 1500 KRW; scheme 300 KRW -> total=82800. All tests use an in-memory H2 or test-slice with preloaded fixtures. | • Create RevenueReportQueryServiceTest using @DataJpaTest or a service test with preloaded H2 data • Fixture: insert 3 revenue_record rows (partner_id=1, dates Jan 1/2/3 2026) + 1 same-ccy row (fx_margin_usd=null) • Test DAILY granularity: expect 3 rows each with fx_margin_usd=10/20/30 • Test MONTHLY granularity: expect 1 row with fx_margin_usd=60.00, service_charges=1500, confirmed_fee_share=300 • Test RevenueStream=FX_MARGIN filter: expect 3 rows (same-ccy row excluded) • Test total revenue KRW: usdKrwRate=1350, expect totalRevenueKrwEquiv=81000+1500+300=82800 | RevenueReportQueryServiceTest.java with 5 test methods, all passing | • DAILY test: 3 rows returned with correct per-day values • MONTHLY test: 1 row with fx_margin_usd=60.00 (sum of 10+20+30) • FX_MARGIN filter: exactly 3 rows (4th same-ccy row excluded) • Total revenue KRW test: 82800 matches formula (60*1350=81000 + 1500 service + 300 scheme share) • SCHEME_FEE filter test (bonus): excludes rows where confirmed_fee_share_krw IS NULL | 50 | 7.5-T08, 7.5-T09 | BE | PRD-07
7.5-T19 | reporting-compliance | 7.5 | 7. Settlement, Reconciliation & Revenue | Revenue reporting & exports | 2 | Unit tests: CSV export format and column ordering | Tests for T11 CSV streaming export. Verify: (1) header row has exactly 13 columns in correct order (period, partner_name, scheme_name, transaction_count, gross_payout_krw, merchant_fee_total_krw, gme_scheme_share_krw, collection_margin_usd, payout_margin_usd, total_fx_margin_usd, service_charges_settle_a, service_charge_ccy, total_revenue_krw_equiv). (2) Data row values are correct for a known fixture row. (3) A partner_name containing a comma is CSV-quoted. (4) BigDecimal values do not use scientific notation. (5) Response Content-Type is text/csv and Content-Disposition contains 'attachment'. | • Create RevenueReportCsvExportTest using @SpringBootTest with MockMvc • Inject a fixture RevenueReportResponse with one known row (all field values set) • Call GET /admin/v1/reports/revenue/export?from=2026-01-01&to=2026-01-31 with FINANCE_ANALYST auth • Parse the CSV response body using a CSV reader • Assert header row column names; assert data row values; assert comma-containing name is quoted | RevenueReportCsvExportTest.java with 5 test methods, all passing | • Header row: split(',') returns exactly 13 tokens matching the specified column names in order • Data row: transaction_count column parses to Long correctly • Partner name 'GME, Test' appears as '"GME, Test"' in the CSV output • total_revenue_krw_equiv value 1234567.89 appears as '1234567.89' not in scientific notation • Content-Disposition header contains 'attachment; filename=revenue_report_2026-01-01_2026-01-31.csv' | 40 | 7.5-T11 | BE | PRD-07
7.5-T20 | reporting-compliance | 7.5 | 7. Settlement, Reconciliation & Revenue | Revenue reporting & exports | 2 | Unit tests: revenue report endpoint RBAC enforcement | Tests for T10/T11 access control. PRD-07 §12.3 permission matrix: Export Revenue Report = SUPER_ADMIN yes, OPS_OPERATOR yes, FINANCE_ANALYST yes, ADMIN_VIEWER no. Tests must cover all four roles for both the JSON endpoint (GET /admin/v1/reports/revenue) and the CSV export endpoint (GET /admin/v1/reports/revenue/export). Additionally: unauthenticated requests return 401; valid FINANCE_ANALYST token with expired JWT returns 401; flag-exception PUT with FINANCE_ANALYST returns 403. | • Create RevenueReportRbacTest using @SpringBootTest with MockMvc and per-test JWT fixtures for each role • Test SUPER_ADMIN on JSON endpoint -> 200 • Test OPS_OPERATOR on JSON endpoint -> 200 • Test FINANCE_ANALYST on JSON endpoint -> 200 • Test ADMIN_VIEWER on JSON endpoint -> 403 • Test unauthenticated (no token) on JSON endpoint -> 401 • Repeat ADMIN_VIEWER and unauthenticated tests for CSV export endpoint | RevenueReportRbacTest.java with 7 test methods, all passing | • SUPER_ADMIN returns 200 on both JSON and CSV endpoints • FINANCE_ANALYST returns 200 on both endpoints • ADMIN_VIEWER returns 403 on both endpoints • No auth token returns 401 on both endpoints • OPS_OPERATOR returns 200 on JSON endpoint • Expired JWT returns 401 (not 403) • FINANCE_ANALYST PUT /flag-exception returns 403 | 35 | 7.5-T10, 7.5-T11 | BE | PRD-07
7.5-T21 | reporting-compliance | 7.5 | 7. Settlement, Reconciliation & Revenue | Revenue reporting & exports | 2 | Implement revenue report audit log entries for CSV and JSON exports | Every successful export (both JSON view and CSV download) must create an audit_log entry per PRD-07 §13.2 (category: 'Data exports'). The audit_log table schema: id BIGINT PK, actor_id VARCHAR(120), actor_type VARCHAR(20) (OPERATOR), action VARCHAR(20) (EXPORT), entity_type VARCHAR(50) ('revenue_report'), entity_id BIGINT (NULL for reports), before_value JSONB (NULL), after_value JSONB (query parameters as JSON), occurred_at TIMESTAMPTZ, ip_address INET, request_id VARCHAR(64). The AuditLogService.logExport() method must be called AFTER the response is committed (do not block the response on audit write failure — use async best-effort logging with error alert on failure). | • Create or extend AuditLogService with method logRevenueReportExport(String actorId, String actorIp, RevenueReportQuery query, String exportFormat, String requestId) • Serialize query to JSONB and store as after_value; set entity_type='revenue_report', action='EXPORT' • Call this method from RevenueReportController after successful response dispatch (use @Async or a post-commit hook) • Ensure audit write failure (DB down) logs an ERROR but does NOT propagate to the caller (response already sent) • Add integration test verifying audit record is created after a successful export call | AuditLogService.logRevenueReportExport() method wired into RevenueReportController.java | • After a successful JSON report call, exactly one audit_log row with action=EXPORT, entity_type=revenue_report exists for that actor • after_value JSONB contains from, to, and granularity from the query params • actor_ip is captured from the HTTP request X-Forwarded-For or REMOTE_ADDR • A forced DB failure during audit write does NOT return 500 to the caller (response was already 200) • Audit log entry for CSV export has exportFormat='CSV' in after_value JSONB | 40 | 7.5-T10, 7.5-T11 | BE | PRD-07
7.5-T22 | reporting-compliance | 7.5 | 7. Settlement, Reconciliation & Revenue | Revenue reporting & exports | 2 | Implement RevenueRecord population hook in CommitTransaction flow | The createFromTransaction() method (T04) must be called as part of the existing CommitTransaction service, in the same DB transaction. The CommitTransaction flow (implemented in WBS 4.x or 5.x) currently: locks the rate quote, deducts prefunding (OVERSEAS), writes the transaction row, fires events. Revenue record creation must be added AFTER the transaction row is written but BEFORE the transaction commits. If createFromTransaction() throws, the entire commit must roll back (no orphan transactions without revenue records). The wiring point is in TransactionCommitService or equivalent. | • Locate TransactionCommitService (or equivalent) in com.gmepayplus.payment.service • Inject RevenueRecordService and call createFromTransaction(transaction) immediately after transaction.persist() • Ensure the call is within the same @Transactional boundary (MANDATORY propagation on createFromTransaction already enforces this) • Add a compensating check: after both saves, assert revenue_record.txnId == transaction.id before returning to caller • Write an integration test: simulate a DB failure in createFromTransaction and verify the transaction row is also rolled back (not committed without revenue record) | CommitTransaction flow updated to call RevenueRecordService.createFromTransaction(); integration test verifying atomicity | • After a successful CommitTransaction call, exactly one revenue_record row exists with txn_id matching the new transaction • If createFromTransaction throws RuntimeException, the transaction row is NOT persisted (rollback verified by querying transaction table in the same test) • Duplicate CommitTransaction call (idempotency re-play) does NOT create a second revenue_record (UNIQUE constraint on txn_id) • Revenue record revenue_date matches the KST date of committed_at • The performance overhead of adding createFromTransaction is < 20ms under normal load (assert in a timing test against a mock repo) | 50 | 7.5-T04, 7.5-T03 | BE | PRD-07
7.5-T23 | reporting-compliance | 7.5 | 7. Settlement, Reconciliation & Revenue | Revenue reporting & exports | 2 | Add revenue_record_summary materialized view for dashboard KPIs | The Admin System dashboard (PRD-07 §3) shows real-time KPIs including revenue. To avoid hitting the raw revenue_record table on every dashboard load, create a PostgreSQL materialized view revenue_record_daily_summary that pre-aggregates: revenue_date, partner_id, scheme_id, SUM(fx_margin_usd) as total_fx_margin_usd, SUM(service_charge_amount) as total_service_charge, SUM(confirmed_fee_share_krw) as total_confirmed_fee_share_krw, COUNT(*) as txn_count. The view is refreshed by a scheduled job every 15 minutes. The revenue report query service can use this view for DAILY/MONTHLY granularity when the query covers a historical (fully settled) period; for today's date it must fall back to the raw table. | • Create Flyway migration V7_5_004__revenue_record_daily_summary_view.sql • CREATE MATERIALIZED VIEW revenue_record_daily_summary AS SELECT revenue_date, partner_id, scheme_id, SUM(fx_margin_usd), SUM(service_charge_amount), SUM(confirmed_fee_share_krw), COUNT(*) FROM revenue_record GROUP BY revenue_date, partner_id, scheme_id • Add UNIQUE INDEX on (revenue_date, partner_id, scheme_id) to support REFRESH CONCURRENTLY • Add a scheduler in RevenueReportScheduler @Scheduled(cron='0 */15 * * * *') that calls REFRESH MATERIALIZED VIEW CONCURRENTLY revenue_record_daily_summary • Add fallback logic to RevenueReportQueryService: use materialized view for dates < today (KST); raw table for today | V7_5_004__revenue_record_daily_summary_view.sql migration + RevenueReportScheduler.java | • Materialized view exists and SELECT returns grouped rows after initial refresh • REFRESH MATERIALIZED VIEW CONCURRENTLY executes without locking the view for reads • Dashboard query using the view for yesterday's date is faster than raw table query by >= 50% on a 100k-row dataset • For revenue_date = today (KST), query falls back to raw revenue_record table (verify via query plan or instrumentation log) • Scheduler fires every 15 minutes (test with @Scheduled test support or a fixed clock stub) | 50 | 7.5-T01, 7.5-T08 | BE | PRD-07
7.5-T24 | reporting-compliance | 7.5 | 7. Settlement, Reconciliation & Revenue | Revenue reporting & exports | 2 | Add Merchant Fee Schedule display query for Settlement module | PRD-07 §11.3.3: the Admin System displays the merchant fee schedule per scheme as a read-only reference. This requires a query on qr_scheme.merchant_fee_table (or a structured fee table entity from scheme config). The fee rates vary by merchant_type and payment origin (domestic vs cross-border). The display shows: scheme_name, merchant_type code, domestic_rate%, cross_border_rate%, effective_from. For ZeroPay: General 0.80%/1.70%, Large Franchise (operator-configured). This data is also used by T05 (updateConfirmedFeeShare) to look up the correct merchant_fee_rate at revenue confirmation time. Query service method: getMerchantFeeRate(Long schemeId, String merchantType, String settlementModel) -> BigDecimal. | • Create MerchantFeeQueryService in com.gmepayplus.reporting.service • Implement getMerchantFeeRate(Long schemeId, String merchantType, String settlementModel): query qr_scheme merchant fee rows; match on schemeId + merchantType; return domestic_rate if settlementModel=NET, cross_border_rate if GROSS • Throw FeeRateNotFoundException if no matching row found (log as WARN for Ops visibility) • Wire getMerchantFeeRate into updateConfirmedFeeShare (T05) to supply the merchantFeeRate parameter • Add unit test: ZeroPay + GENERAL + NET -> 0.0080; ZeroPay + GENERAL + GROSS -> 0.0170 | MerchantFeeQueryService.java in com.gmepayplus.reporting.service + unit tests | • getMerchantFeeRate(zeropayId, 'GENERAL', 'NET') returns 0.0080 • getMerchantFeeRate(zeropayId, 'GENERAL', 'GROSS') returns 0.0170 • getMerchantFeeRate with unknown merchantType throws FeeRateNotFoundException • getMerchantFeeRate with unknown schemeId throws FeeRateNotFoundException • Unit test coverage >= 80% on MerchantFeeQueryService | 35 | 7.5-T05 | BE | PRD-07
7.5-T25 | reporting-compliance | 7.5 | 7. Settlement, Reconciliation & Revenue | Revenue reporting & exports | 2 | Integration test: end-to-end revenue record creation and report retrieval | End-to-end integration test covering the full WBS 7.5 revenue pipeline: (1) Commit a cross-border INBOUND transaction (collection_margin_usd=10.00, payout_margin_usd=10.00, service_charge=500 KRW, direction=INBOUND). (2) Assert revenue_record is created with fx_margin_usd=20.00, settlement_model=GROSS. (3) Call updateConfirmedFeeShare with grossPayoutKrw=10000, merchantFeeRate=0.0170, gmeSharePct=0.70 -> confirmedFeeShareKrw=119. (4) Call GET /admin/v1/reports/revenue?from={today}&to={today} with FINANCE_ANALYST JWT. (5) Assert response contains 1 row with totalFxMarginUsd=20.00, serviceChargesSettleA=500, gmeSchemeShareKrw=119, totalRevenueKrwEquiv=20.00*1350+500+119=27619 (using usdKrwRate=1350). | • Create RevenueEndToEndIntegrationTest using @SpringBootTest with a real embedded PostgreSQL (TestContainers) • Step 1: call CommitTransaction service with mocked scheme step (skip actual ZeroPay call); verify transaction persisted • Step 2: query revenue_record table directly; assert fx_margin_usd=20.00, settlement_model=GROSS • Step 3: call updateConfirmedFeeShare; assert confirmedFeeShareKrw=119 • Step 4: mock treasury_rate table with usd_krw=1350.00; call GET /admin/v1/reports/revenue • Step 5: assert response JSON matches expected values (tolerance 0.01 USD for FX conversion) | RevenueEndToEndIntegrationTest.java with 1 test method (5 sequential steps), passing | • Step 2: revenue_record.fx_margin_usd = 20.00 (exact) • Step 3: revenue_record.confirmed_fee_share_krw = 119 (exact, KRW 0dp) • Step 4: API returns 200 with 1 row in the report • Step 5: totalRevenueKrwEquiv = 27619 (20*1350 + 500 + 119 = 27619; tolerance 1 KRW for rounding) • Full test runs in < 30 seconds on CI (TestContainers startup included) | 55 | 7.5-T22, 7.5-T09, 7.5-T10 | BE | PRD-07
7.5-T26 | reporting-compliance | 7.5 | 7. Settlement, Reconciliation & Revenue | Revenue reporting & exports | 2 | Add OpenAPI documentation for revenue report endpoints | The Admin API uses OpenAPI 3 (Springdoc or equivalent). The revenue report endpoints (T10, T11, T14, T15) must have complete OpenAPI annotations: @Operation(summary, description), @Parameter for each query param (name, description, required, example), @ApiResponse for 200/400/401/403, and example schemas for RevenueReportResponse and SettlementBatchSummaryDTO. The API docs are the primary reference for the Admin UI team consuming these endpoints. Each parameter must document its constraints (e.g. 'from: ISO-8601 date, required; max range 366 days when combined with to'). | • Add Springdoc @Operation annotations to GET /admin/v1/reports/revenue and /admin/v1/reports/revenue/export • Add @Parameter(description, example, required) to all query params: from, to, granularity, partner_id, scheme_id, direction, revenue_stream • Add @ApiResponse(responseCode='400', description='Validation error: from must be before to; max range 366 days') and 403/401 responses • Add @Schema examples to RevenueReportRow and SettlementBatchSummaryDTO showing realistic data values • Verify docs render correctly at /v3/api-docs and /swagger-ui.html with all new endpoints visible | OpenAPI annotations on all 4 revenue/settlement endpoints; docs verified at /swagger-ui.html | • GET /v3/api-docs returns JSON with paths /admin/v1/reports/revenue, /admin/v1/reports/revenue/export, /admin/v1/reports/settlement-batches, /admin/v1/reports/settlement-batches/fee-schedule • Each endpoint has at least one @ApiResponse for 200, 400, 401, and 403 • RevenueReportRow schema in OpenAPI has all 13 field names • The 'from' parameter description mentions 'ISO-8601' and 'required' • Swagger UI renders without errors and the Try-it-out works for GET /admin/v1/reports/revenue | 35 | 7.5-T10, 7.5-T11, 7.5-T14, 7.5-T15 | BE | PRD-07
7.6-T01 | settlement-reconciliation | 7.6 | 7. Settlement, Reconciliation & Revenue | Gross settlement & monthly invoicing | 2 | Add gross_settlement_flag and settlement_model column to transaction table | WBS 7.6 delivers gross settlement for international (OVERSEAS partner) ZeroPay transactions. In gross settlement GMEPay+ remits the full target_payout KRW to ZeroPay and invoices the merchant monthly. Domestic (LOCAL partner) uses net settlement where GME deducts its share first. The transaction table needs a settlement_model column to record which model applied at commit time so batch generation and invoicing queries are unambiguous. settlement_model is derived from partner.partner_type: LOCAL -> NET, OVERSEAS -> GROSS. Values must not change after commit (rate-lock principle applies to settlement model too). | • Create migration db/migrations/V7_6_001__transaction_settlement_model.sql. • Add column settlement_model VARCHAR(5) NOT NULL DEFAULT 'NET' CHECK (settlement_model IN ('NET','GROSS')) to the transaction table. • Backfill existing rows: UPDATE transaction SET settlement_model = CASE WHEN partner_type = 'OVERSEAS' THEN 'GROSS' ELSE 'NET' END using a join on the partner table. • Add index on (settlement_model, committed_at::DATE, scheme_id) to support daily batch queries that filter by settlement model and date. • Add a table comment documenting: NET = domestic partners (LOCAL type); GROSS = cross-border partners (OVERSEAS type). Value is locked at commit and never updated. | Migration file db/migrations/V7_6_001__transaction_settlement_model.sql applying cleanly and backfilling all existing rows. | • Migration applies on a populated schema with no errors; column is NOT NULL after backfill. • An attempt to INSERT a transaction row with settlement_model = 'HYBRID' is rejected by the CHECK constraint. • All existing OVERSEAS partner transactions have settlement_model = 'GROSS' and all LOCAL partner transactions have settlement_model = 'NET' after backfill. • Index on (settlement_model, committed_at::DATE, scheme_id) appears in EXPLAIN ANALYZE for a query filtering both columns. • Rollback migration removes the column cleanly. | 30 |  | BE | SCH-06
7.6-T02 | settlement-reconciliation | 7.6 | 7. Settlement, Reconciliation & Revenue | Gross settlement & monthly invoicing | 2 | Create tax_invoice table migration (per DAT-03 schema) | WBS 7.6 monthly invoicing requires a tax_invoice table (DAT-03 §8.3). One row per merchant per calendar month for cross-border transactions. Fields per spec: id BIGINT PK, merchant_id BIGINT FK->merchant, invoice_period DATE (first day of month), invoice_ref VARCHAR(64) UNIQUE (external tax invoice number, NULL until issued), total_transaction_amount_krw BIGINT (sum of target_payout KRW for the month), fee_rate DECIMAL(6,4) (merchant fee rate applied), merchant_fee_krw BIGINT (= total x fee_rate, BIGINT, floor), vat_krw BIGINT (= merchant_fee_krw x 0.10, floor), invoice_amount_krw BIGINT (= merchant_fee_krw + vat_krw), zeropay_share_krw BIGINT (= floor(merchant_fee_krw x 0.0021), the 0.21% ZP share paid by GME to ZeroPay monthly), status VARCHAR(20) CHECK IN ('DRAFT','ISSUED','COLLECTED','FAILED'), issued_at TIMESTAMPTZ NULL, collected_at TIMESTAMPTZ NULL, created_at/updated_at/created_by/updated_by standard audit. | • Create migration db/migrations/V7_6_002__tax_invoice.sql. • Define the tax_invoice table with all columns and types exactly as specified in context. • Add UNIQUE constraint on (merchant_id, invoice_period) to prevent duplicate invoice drafts for the same merchant-month. • Add CHECK constraints: merchant_fee_krw >= 0, vat_krw >= 0, invoice_amount_krw = merchant_fee_krw + vat_krw, zeropay_share_krw >= 0, fee_rate BETWEEN 0.0000 AND 1.0000. • Add index on (invoice_period, status) for batch processing queries; add index on merchant_id for merchant-level lookups. | Migration file db/migrations/V7_6_002__tax_invoice.sql creating the tax_invoice table with all constraints. | • Migration applies cleanly on top of V7_6_001 with no errors. • UNIQUE(merchant_id, invoice_period) rejects duplicate inserts for the same merchant-month combination. • CHECK on invoice_amount_krw rejects a row where invoice_amount_krw != merchant_fee_krw + vat_krw (e.g. 1000+100 stored as 1200 is rejected). • status column rejects values outside the defined enum (e.g. 'PENDING' is rejected). • invoice_ref UNIQUE constraint rejects two rows with the same non-NULL invoice reference. | 35 | 7.6-T01 | BE | SCH-06
7.6-T03 | settlement-reconciliation | 7.6 | 7. Settlement, Reconciliation & Revenue | Gross settlement & monthly invoicing | 2 | Create gross_settlement_daily_aggregate view for ZP0061/ZP0063 batch generation | WBS 7.6 gross settlement batch (ZP0061/ZP0063) must aggregate per-merchant daily totals. For GROSS settlement transactions (settlement_model='GROSS') the ZP0061 record contains: merchant_id, settlement_date, gross_txn_count (count of payments), gross_txn_amount (sum of target_payout KRW), refund_count, refund_amount, merchant_fee_total (0 for gross type), net_settlement_amount (= gross_txn_amount - refund_amount for gross type), settlement_type='G'. This view must only include transactions in state SETTLEMENT_REGISTERED (registration confirmed by ZP0012). Refunds are joined from the refund table. The view is used by the ZP0061/ZP0063 generator service. | • Create migration db/migrations/V7_6_003__gross_settlement_daily_view.sql. • Define view gross_settlement_daily_aggregate as: SELECT t.merchant_id, t.committed_at::DATE AS settlement_date, COUNT(*) FILTER (WHERE t.txn_type='PAYMENT') AS gross_txn_count, COALESCE(SUM(t.target_payout_krw) FILTER (WHERE t.txn_type='PAYMENT'),0) AS gross_txn_amount, COUNT(*) FILTER (WHERE t.txn_type='REFUND') AS refund_count, COALESCE(SUM(t.target_payout_krw) FILTER (WHERE t.txn_type='REFUND'),0) AS refund_amount, 0::BIGINT AS merchant_fee_total, (SUM(t.target_payout_krw) FILTER (WHERE t.txn_type='PAYMENT') - COALESCE(SUM(t.target_payout_krw) FILTER (WHERE t.txn_type='REFUND'),0)) AS net_settlement_amount FROM transaction t WHERE t.settlement_model='GROSS' AND t.status='SETTLEMENT_REGISTERED' GROUP BY t.merchant_id, t.committed_at::DATE. • Add scheme_id to the GROUP BY and SELECT to allow per-scheme filtering. • Add a comment on the view explaining: merchant_fee_total is always 0 for GROSS type; GME does not deduct fees in the settlement batch. • Verify the view against the ZP0061 field mapping in context: gross_txn_count maps to gross_txn_count, settlement_type is a computed literal 'G'. | Migration V7_6_003__gross_settlement_daily_view.sql creating the gross_settlement_daily_aggregate view. | • Querying the view for a settlement_date with 3 GROSS SETTLEMENT_REGISTERED payment transactions and 1 refund returns gross_txn_count=3, refund_count=1, net_settlement_amount = sum(payments) - sum(refunds). • Transactions with settlement_model='NET' do not appear in the view output. • Transactions with status != 'SETTLEMENT_REGISTERED' (e.g. 'APPROVED') do not appear in the view. • merchant_fee_total is always 0 for all rows returned. • Two merchants on the same settlement_date appear as two distinct rows. | 40 | 7.6-T01 | BE | SCH-06
7.6-T04 | settlement-reconciliation | 7.6 | 7. Settlement, Reconciliation & Revenue | Gross settlement & monthly invoicing | 2 | Implement GrossSettlementCalculator: derive net_settlement_amount for ZP0061/ZP0063 | WBS 7.6 gross settlement math. For international transactions settlement_type='G': net_settlement_amount = gross_txn_amount - refund_amount (both in KRW BIGINT). Unlike net settlement, GME does NOT deduct its fee share from the settlement batch amount - the full target_payout goes to ZeroPay. GME recovers FX margin from prefunding at payment time (collection_usd debit) and invoices the merchant fee separately monthly. merchant_fee_total field in ZP0061 is 0 for gross type. Guard: net_settlement_amount must be >= 0 (if refunds exceed payments for a merchant on a day, hold the negative batch entry and alert Ops - do not submit negative amounts to ZeroPay). | • Create class GrossSettlementCalculator in com.gme.gmepay.settlement.gross package. • Implement method GrossSettlementResult calculate(long grossTxnAmountKrw, long refundAmountKrw): returns GrossSettlementResult record with fields grossTxnAmountKrw, refundAmountKrw, netSettlementAmountKrw, merchantFeeTotalKrw (always 0), settlementTypeCode (always 'G'). • Guard: if grossTxnAmountKrw < 0 or refundAmountKrw < 0, throw IllegalArgumentException. • Guard: if netSettlementAmountKrw < 0 (refunds exceed payments), throw NegativeSettlementAmountException(merchantId, settlementDate, netAmount) - caller must route to Ops alert. • Add Javadoc: 'For gross settlement (international/OVERSEAS partners), GME remits the full gross amount to ZeroPay. Merchant fee is NOT deducted here; it is invoiced monthly to the merchant via tax_invoice.' | GrossSettlementCalculator class and GrossSettlementResult record in com.gme.gmepay.settlement.gross package. | • calculate(50000, 0) returns netSettlementAmountKrw=50000, merchantFeeTotalKrw=0, settlementTypeCode='G'. • calculate(50000, 5000) returns netSettlementAmountKrw=45000. • calculate(5000, 10000) throws NegativeSettlementAmountException (refunds > payments for the day). • calculate(-1, 0) throws IllegalArgumentException. • merchantFeeTotalKrw is always 0 regardless of input amounts. | 30 | 7.6-T01 | BE | SCH-06
7.6-T05 | settlement-reconciliation | 7.6 | 7. Settlement, Reconciliation & Revenue | Gross settlement & monthly invoicing | 2 | Implement MonthlyMerchantFeeAggregator: compute per-merchant monthly invoice inputs | WBS 7.6 monthly invoicing. At end-of-month (last calendar day KST), for each merchant that had GROSS settlement transactions during the month, aggregate: total_transaction_amount_krw = SUM(target_payout_krw) for all APPROVED/SETTLED transactions with settlement_model='GROSS' in that month. Then compute: merchant_fee_krw = floor(total_transaction_amount_krw x fee_rate); vat_krw = floor(merchant_fee_krw x 0.10); invoice_amount_krw = merchant_fee_krw + vat_krw; zeropay_share_krw = floor(merchant_fee_krw x 0.0021). fee_rate is read from the merchant's applicable scheme_fee_config row (fee_tier='CROSSBORDER', merchant_type from merchant record). The 0.21% ZP share is paid by GME to ZeroPay out of the monthly invoice cycle - it is not in the settlement batch files. Use BigDecimal with ROUND_DOWN throughout. Result is written to tax_invoice as status=DRAFT. | • Create class MonthlyMerchantFeeAggregator in com.gme.gmepay.invoicing package. • Implement method List<TaxInvoiceDraft> aggregate(YearMonth period, long schemeId) that queries the transaction table for settlement_model='GROSS' AND committed_at within period AND scheme_id = schemeId, groups by merchant_id, and computes all fields. • For fee_rate resolution call FeeConfigRepository.findEffectiveConfig(schemeId, merchantType, 'CROSSBORDER', period.atEndOfMonth()). • Compute zeropay_share_krw = floor(merchant_fee_krw x BigDecimal('0.0021')). • Return a list of TaxInvoiceDraft value objects (merchant_id, invoice_period, total_transaction_amount_krw, fee_rate, merchant_fee_krw, vat_krw, invoice_amount_krw, zeropay_share_krw); do NOT write to DB in this class (persistence is T06). | MonthlyMerchantFeeAggregator class and TaxInvoiceDraft record in com.gme.gmepay.invoicing package. | • For merchant with total_transaction_amount_krw=1000000, fee_rate=0.0170: merchant_fee_krw=floor(1000000x0.0170)=17000, vat_krw=floor(17000x0.10)=1700, invoice_amount_krw=18700, zeropay_share_krw=floor(17000x0.0021)=35. • For total_transaction_amount_krw=0 (no transactions): method returns empty list, not a zero-value draft. • fee_rate is sourced from FeeConfigRepository using CROSSBORDER fee_tier and the merchant's actual merchant_type (not hardcoded). • All arithmetic uses BigDecimal ROUND_DOWN; fractional KRW is always truncated, never rounded up. • Merchants with only NET settlement transactions in the period are excluded from the result list. | 45 | 7.6-T02, 7.2-T04 | BE | SCH-06
7.6-T06 | settlement-reconciliation | 7.6 | 7. Settlement, Reconciliation & Revenue | Gross settlement & monthly invoicing | 2 | Implement TaxInvoicePersistenceService: upsert DRAFT invoices and transition status | WBS 7.6 invoicing persistence. TaxInvoiceDraft objects produced by T05 must be written to tax_invoice table. Business rules: (1) If a DRAFT row already exists for (merchant_id, invoice_period), update its aggregated values (re-aggregation is idempotent before ISSUED). (2) Once status=ISSUED the row must not be overwritten - throw InvoiceAlreadyIssuedException. (3) Transitions: DRAFT->ISSUED (operator action or stub auto-issue), ISSUED->COLLECTED (payment confirmed), ISSUED->FAILED (collection failure). All transitions are audit-logged (created_by, updated_by, timestamps). Status DRAFT may be re-run for corrections. invoice_ref is set at ISSUED transition and must be UNIQUE and non-NULL. | • Create class TaxInvoicePersistenceService in com.gme.gmepay.invoicing with Spring @Transactional. • Method upsertDraft(TaxInvoiceDraft draft, String operatorId): INSERT into tax_invoice with status=DRAFT or UPDATE all aggregation fields if row exists with status=DRAFT; throw InvoiceAlreadyIssuedException if status is ISSUED/COLLECTED/FAILED. • Method issueInvoice(long taxInvoiceId, String invoiceRef, String operatorId): set status=ISSUED, issued_at=now(), invoice_ref=invoiceRef, updated_by=operatorId; throw if already ISSUED. • Method markCollected(long taxInvoiceId, String operatorId): transition ISSUED->COLLECTED, set collected_at=now(). • Method markFailed(long taxInvoiceId, String reason, String operatorId): transition ISSUED->FAILED, log reason to audit_log. | TaxInvoicePersistenceService class in com.gme.gmepay.invoicing with all five methods, transactional and audit-logged. | • upsertDraft called twice for same merchant+period with different total_transaction_amount_krw values updates the DRAFT row (idempotent upsert). • upsertDraft on a row with status=ISSUED throws InvoiceAlreadyIssuedException; the ISSUED row is not modified. • issueInvoice sets issued_at to a non-null timestamp and invoice_ref to the provided value. • markCollected on an ISSUED invoice transitions to COLLECTED; calling it on a DRAFT invoice throws InvalidStateTransitionException. • All state transitions write to audit_log with operator ID and before/after status values. | 45 | 7.6-T02, 7.6-T05 | BE | SCH-06
7.6-T07 | settlement-reconciliation | 7.6 | 7. Settlement, Reconciliation & Revenue | Gross settlement & monthly invoicing | 2 | Implement MonthlyInvoiceBatchJob: scheduled end-of-month aggregation and DRAFT creation | WBS 7.6 requires automatic monthly invoice draft generation. The batch job runs on the last calendar day of each month at 23:00 KST (cron: '0 23 L * ?'). It calls MonthlyMerchantFeeAggregator.aggregate(currentMonth, schemeId) for each active ZeroPay scheme, then calls TaxInvoicePersistenceService.upsertDraft for each result. The job must be idempotent - if run twice on the same month it re-aggregates and updates existing DRAFT rows without creating duplicates. Job execution is recorded in a batch_job_log table with job_name='MONTHLY_INVOICE_DRAFT', run_date, status (STARTED/COMPLETED/FAILED), record_count, error_detail. Alert Ops via the monitoring system if job fails. | • Create class MonthlyInvoiceBatchJob in com.gme.gmepay.invoicing.batch annotated with @Scheduled. • Set cron expression to run at 23:00 KST on the last day of each month; use ZoneId.of('Asia/Seoul') for KST scheduling. • Fetch all active scheme IDs from SchemeRepository where is_active=true. • For each scheme, call aggregator.aggregate(YearMonth.now(ZoneId.of('Asia/Seoul')), schemeId) and persist each draft via upsertDraft. • Log job start/end/count/errors to batch_job_log table; emit a monitoring alert on failure. | MonthlyInvoiceBatchJob Spring @Scheduled component with idempotent execution, KST scheduling, and batch_job_log writes. | • Job triggers on the last day of the month at 23:00 KST (verify via unit test with a mock clock set to 2026-01-31T23:00 KST). • Running the job twice on the same month produces the same number of DRAFT rows as running it once (idempotency: no duplicate rows). • batch_job_log shows status=COMPLETED and record_count > 0 after a successful run. • If MonthlyMerchantFeeAggregator throws, the job catches the exception, writes status=FAILED to batch_job_log, and emits an alert without crashing the scheduler thread. • Job skips merchants whose invoice for the month is already ISSUED (upsertDraft raises InvoiceAlreadyIssuedException which is caught and counted as skipped). | 45 | 7.6-T05, 7.6-T06 | BE | SCH-06
7.6-T08 | settlement-reconciliation | 7.6 | 7. Settlement, Reconciliation & Revenue | Gross settlement & monthly invoicing | 2 | Add gross settlement flag to ZP0061/ZP0063 file generation: settlement_type='G' | WBS 7.6 requires the settlement batch files ZP0061 (morning, by ~05:00 KST) and ZP0063 (afternoon, by ~14:00 KST) to carry settlement_type='G' for gross records. Each merchant row in ZP0061 has fields: merchant_id CHAR(10), settlement_date DATE(8) YYYYMMDD, gross_txn_count NUM(6), gross_txn_amount NUM(14) KRW, refund_count NUM(6), refund_amount NUM(14) KRW, merchant_fee_total NUM(12) (=0 for gross type), net_settlement_amount NUM(14) KRW, settlement_type CHAR(1) N or G. The ZP0061Generator reads from the gross_settlement_daily_aggregate view (T03) and the net settlement equivalent for domestic transactions. File header contains: file_type ZP0061, business_date, GME institution code, total record count, total net_settlement_amount KRW. File is idempotent: regenerating for the same settlement_date replaces the previously generated file record. | • Locate or create Zp0061FileGenerator in com.gme.gmepay.settlement.batch. • Add a method List<Zp0061Record> buildGrossRecords(LocalDate settlementDate, long schemeId) that reads from gross_settlement_daily_aggregate view filtered by settlement_date and scheme_id. • Map each view row to a Zp0061Record with settlement_type='G', merchant_fee_total=0, net_settlement_amount from view. • Merge gross records (type G) and net records (type N, from existing logic) into a single sorted list for the file. • Ensure the file header total_net_settlement_amount = SUM of all net_settlement_amount across both G and N records. | Updated Zp0061FileGenerator producing combined N+G records with correct settlement_type per row and accurate file header totals. | • A file generated for a date with 2 domestic merchants (NET) and 1 international merchant (GROSS) contains 3 records: 2 with settlement_type='N' and 1 with settlement_type='G'. • For the GROSS record: merchant_fee_total=0, net_settlement_amount = gross_txn_amount - refund_amount. • For the NET record: merchant_fee_total = GME fee deducted, net_settlement_amount = gross_txn_amount - refund_amount - merchant_fee_total. • File header total_net_settlement_amount equals the sum of all individual net_settlement_amount values across N and G records. • Regenerating the file for the same date produces an identical file (idempotent); no duplicate settlement_batch rows are created. | 50 | 7.6-T03, 7.6-T04 | BE | SCH-06
7.6-T09 | settlement-reconciliation | 7.6 | 7. Settlement, Reconciliation & Revenue | Gross settlement & monthly invoicing | 2 | Add settlement_type='G' support to ZP0065 payment detail file generator | WBS 7.6 payment detail file ZP0065 (transmitted by ~22:00 KST) provides transaction-level detail underlying ZP0061/ZP0063 totals. Each detail record: merchant_id CHAR(10), zeropay_txn_ref CHAR(20), txn_date DATE(8), txn_time TIME(6), payout_amount_krw NUM(12), merchant_fee_amt NUM(12), van_fee_amt NUM(10), partner_type CHAR(1) D or I, settlement_batch_ref CHAR(20). For GROSS settlement records partner_type='I' (International). merchant_fee_amt and van_fee_amt must be populated from transaction_fee_snapshot (WBS 7.2) joined on txn_id; if no snapshot exists fall back to 0 with a warning log. settlement_batch_ref links back to the ZP0061/ZP0063 batch record. | • Locate or create Zp0065FileGenerator in com.gme.gmepay.settlement.batch. • Query transactions with settlement_model='GROSS' AND status='SETTLEMENT_REGISTERED' for the settlement date, joined to transaction_fee_snapshot for merchant_fee_amt (gross_merchant_fee_krw) and van_fee_amt (van_fee_krw). • Set partner_type='I' for all GROSS records; 'D' for NET/domestic records. • Set settlement_batch_ref to the settlement_batch.id of the corresponding ZP0061 or ZP0063 batch record. • Log a WARN for any transaction where transaction_fee_snapshot row is missing; use 0 for fee amounts in that case and add to exception queue. | Updated Zp0065FileGenerator emitting partner_type='I' and correct fee amounts for gross settlement transaction records. | • A GROSS transaction with fee snapshot: payout_amount_krw=50000, gross_merchant_fee_krw=850, van_fee_krw=85 produces ZP0065 record with merchant_fee_amt=850, van_fee_amt=85, partner_type='I'. • A domestic (NET) transaction produces partner_type='D' in the same file. • A GROSS transaction with no fee snapshot produces merchant_fee_amt=0, van_fee_amt=0 and a WARN log entry; transaction is also added to the exception queue. • settlement_batch_ref matches the id of the ZP0061 or ZP0063 settlement_batch row for that date. • File record count matches the sum of gross_txn_count across all ZP0061 G-type records for that date. | 45 | 7.6-T08, 7.2-T02 | BE | SCH-06
7.6-T10 | settlement-reconciliation | 7.6 | 7. Settlement, Reconciliation & Revenue | Gross settlement & monthly invoicing | 2 | Implement GrossSettlementService: orchestrate daily gross settlement cycle | WBS 7.6 orchestration. GrossSettlementService ties together: (1) Read gross_settlement_daily_aggregate view for the target settlement_date; (2) Run GrossSettlementCalculator per merchant; (3) Generate ZP0061 records via Zp0061FileGenerator; (4) Persist settlement_batch row with file_type='ZP0061', window='MORNING', status=GENERATED; (5) Hand off to SFTP uploader. The service is idempotent: if a settlement_batch row already exists for (scheme_id, file_type, settlement_date) with status >= GENERATED, skip re-generation and log a warning. The service is called by the batch scheduler at ~05:00 KST (after ZP0012 is received and processed). If any merchant has NegativeSettlementAmountException, exclude that merchant, create an exception record, alert Ops, and continue with the remaining merchants. | • Create class GrossSettlementService in com.gme.gmepay.settlement.gross with @Transactional. • Method runMorningSettlement(LocalDate settlementDate, long schemeId): check idempotency, load aggregate view rows, compute per-merchant results, build Zp0061File, persist settlement_batch, submit to SFTP upload queue. • For each NegativeSettlementAmountException: insert a reconciliation_item with match_status='DISCREPANCY', resolution_status='UNRESOLVED', trigger Ops alert. • After successful SFTP upload, update settlement_batch.status to TRANSMITTED and set transmitted_at=now(). • Log total merchant count, total net_settlement_amount KRW, and any excluded merchants to batch_job_log. | GrossSettlementService class orchestrating the morning gross settlement cycle with idempotency and exception handling. | • Calling runMorningSettlement twice for the same date and scheme produces one settlement_batch row (idempotent; second call logs warning and returns without re-generating). • A merchant with refunds > payments triggers NegativeSettlementAmountException: the merchant is excluded from ZP0061, a reconciliation_item is created, and remaining merchants are settled normally. • On successful SFTP upload, settlement_batch.status transitions to TRANSMITTED and transmitted_at is non-null. • batch_job_log entry records total merchant count and total net_settlement_amount KRW after each run. • If SFTP upload fails, settlement_batch.status remains GENERATED (not TRANSMITTED) and an error is logged - the job does not silently swallow the failure. | 55 | 7.6-T04, 7.6-T08, 7.6-T03 | BE | SCH-06
7.6-T11 | settlement-reconciliation | 7.6 | 7. Settlement, Reconciliation & Revenue | Gross settlement & monthly invoicing | 2 | Implement ZP0062/ZP0064 result file processor: update gross settlement status | WBS 7.6 result file processing. ZeroPay returns ZP0062 (morning result, ~10:00 KST) and ZP0064 (afternoon result, ~19:00 KST) confirming merchant settlement status. Each result record contains: merchant_id, settlement_date, result_code CHAR(2) (00=success), credited_amount_krw NUM(14), result_message VARCHAR(100). For each result: if result_code=00 mark corresponding transaction rows as SETTLED; if non-00 flag as SETTLEMENT_FAILED and create reconciliation_item. Reconcile total credited_amount_krw against gross_settlement_daily_aggregate totals - any discrepancy (tolerance = 0 KRW for settlement files) creates a reconciliation_item with match_status='DISCREPANCY'. Update settlement_batch status to RECONCILED on zero-discrepancy, ERROR on any discrepancy. | • Create class Zp0062ResultProcessor (reuse for ZP0064) in com.gme.gmepay.settlement.gross. • Method processResult(SettlementResultFile file, long schemeId): parse each merchant record, look up the corresponding settlement_batch by merchant+date+window. • For result_code=00: update all transaction rows for that merchant+date+settlement_model='GROSS' from SETTLEMENT_REGISTERED to SETTLED. • For result_code non-00: update transactions to SETTLEMENT_FAILED; create reconciliation_item; trigger P1 ops alert. • Compare file total credited_amount vs GME aggregate; if delta != 0 create reconciliation_item with DISCREPANCY and set settlement_batch.status=ERROR. | Zp0062ResultProcessor class handling ZP0062 and ZP0064 result files with zero-tolerance reconciliation and status updates. | • A merchant record with result_code='00' and credited_amount matching GME aggregate: all transactions for that merchant transition to SETTLED, settlement_batch for that merchant transitions to RECONCILED. • A merchant record with result_code='01' (failure): transactions remain at SETTLEMENT_REGISTERED, a reconciliation_item is created with match_status='DISCREPANCY', Ops alert is emitted. • A credited_amount that differs from the GME aggregate by even 1 KRW creates a reconciliation_item and sets settlement_batch.status=ERROR. • Processing ZP0064 updates the AFTERNOON window settlement_batch separately from the MORNING window batch. • Processing ZP0062 twice (retry scenario) is idempotent: already-SETTLED transactions are not double-updated; no duplicate reconciliation_items. | 50 | 7.6-T10 | BE | SCH-06
7.6-T12 | settlement-reconciliation | 7.6 | 7. Settlement, Reconciliation & Revenue | Gross settlement & monthly invoicing | 2 | Implement ZeropaySharePayableService: compute and record monthly 0.21% ZP share obligation | WBS 7.6: GME pays ZeroPay 0.21% of the international merchant fee monthly. This is NOT in the settlement batch files (SCH-06 A-12). It is a business-level accounting entry from the monthly invoice cycle. zeropay_share_krw is already computed per invoice in TaxInvoiceDraft (T05) as floor(merchant_fee_krw x 0.0021). This service aggregates the total ZP share owed for a given month across all merchants and creates a payable ledger entry. The payable is recorded in a new table zeropay_monthly_payable: id BIGINT PK, period DATE, scheme_id BIGINT FK->qr_scheme, total_merchant_fee_krw BIGINT, total_zeropay_share_krw BIGINT, status VARCHAR(20) CHECK IN ('PENDING','PAID','DISPUTED'), created_at/updated_at/created_by/updated_by. | • Create migration db/migrations/V7_6_004__zeropay_monthly_payable.sql: table zeropay_monthly_payable with columns from context; add UNIQUE(period, scheme_id). • Create class ZeropaySharePayableService in com.gme.gmepay.invoicing. • Method computeAndRecordPayable(YearMonth period, long schemeId, String operatorId): sum zeropay_share_krw and merchant_fee_krw from tax_invoice WHERE invoice_period=period AND scheme_id=schemeId AND status IN ('ISSUED','COLLECTED'); INSERT into zeropay_monthly_payable with status=PENDING (upsert if already PENDING). • Method markPaid(long payableId, String operatorId): transition PENDING->PAID, audit log. • Throw if total_zeropay_share_krw < 0. | Migration V7_6_004__zeropay_monthly_payable.sql and ZeropaySharePayableService class computing and recording the monthly ZP 0.21% share obligation. | • For 3 merchants with merchant_fee_krw values of 17000, 34000, 51000 (total=102000): total_zeropay_share_krw = floor(102000 x 0.0021) = 214. • UNIQUE(period, scheme_id) prevents duplicate payable rows for the same month. • computeAndRecordPayable excludes tax_invoice rows with status='DRAFT' (not yet issued); only ISSUED and COLLECTED rows count. • markPaid on a PENDING payable transitions to PAID and writes to audit_log. • markPaid on a non-PENDING payable throws InvalidStateTransitionException. | 45 | 7.6-T06 | BE | SCH-06
7.6-T13 | settlement-reconciliation | 7.6 | 7. Settlement, Reconciliation & Revenue | Gross settlement & monthly invoicing | 2 | Add Admin System API endpoint: GET /v1/admin/invoices?period=&merchant_id=&status= | WBS 7.6 Admin System integration. Finance operators need to view monthly merchant fee invoices (UC-04-04). Admin System backend endpoint GET /v1/admin/invoices returns a paginated list of tax_invoice rows. Query params: period (YYYY-MM, required), merchant_id (optional), status (optional: DRAFT¦ISSUED¦COLLECTED¦FAILED). Response fields per row: id, merchant_id, invoice_period, total_transaction_amount_krw, fee_rate, merchant_fee_krw, vat_krw, invoice_amount_krw, zeropay_share_krw, status, issued_at, collected_at. Only accessible to roles FINANCE_ANALYST, OPS_OPERATOR, SUPER_ADMIN. Returns HTTP 400 if period format is invalid; 403 if role is ADMIN_VIEWER. | • Create AdminInvoiceController in com.gme.gmepay.admin.invoice with GET /v1/admin/invoices. • Parse period as YearMonth from YYYY-MM string; return 400 with error code INVALID_PERIOD_FORMAT if parsing fails. • Query tax_invoice with optional filters; paginate with page/pageSize params (default pageSize=50, max=200). • Apply RBAC: check caller role from JWT; reject ADMIN_VIEWER with 403 INSUFFICIENT_PERMISSIONS. • Return response DTO list with all fields from context; include pagination metadata (totalElements, page, pageSize). | AdminInvoiceController GET endpoint with RBAC, pagination, and query filtering, returning tax_invoice data. | • GET /v1/admin/invoices?period=2026-01 returns all DRAFT/ISSUED/COLLECTED/FAILED invoices for January 2026 with correct field values. • period=2026-13 returns HTTP 400 with error code INVALID_PERIOD_FORMAT. • Request with ADMIN_VIEWER JWT returns HTTP 403 INSUFFICIENT_PERMISSIONS. • merchant_id filter returns only rows for that merchant; status=DRAFT filter returns only DRAFT rows. • pageSize=200 returns at most 200 rows; pageSize=201 returns HTTP 400. | 40 | 7.6-T06 | BE | SCH-06
7.6-T14 | settlement-reconciliation | 7.6 | 7. Settlement, Reconciliation & Revenue | Gross settlement & monthly invoicing | 2 | Add Admin System API endpoint: POST /v1/admin/invoices/{id}/issue (stub for OI-02) | WBS 7.6 invoice issuance. Operator triggers invoice issuance manually (Phase 1 stub per OI-02 - tax API not confirmed). POST /v1/admin/invoices/{id}/issue transitions tax_invoice from DRAFT to ISSUED. Request body: {invoice_ref: string} (the operator-provided external reference). Response: updated tax_invoice row. The endpoint is a stub: it does NOT call any external tax API; it simply sets status=ISSUED, issued_at=now(), invoice_ref from request, and records operator. A feature flag FEATURE_TAX_INVOICE_API (default false) gates future integration; when false, the stub path runs. RBAC: only OPS_OPERATOR or SUPER_ADMIN may issue invoices. | • Create POST /v1/admin/invoices/{id}/issue in AdminInvoiceController. • Read feature flag FEATURE_TAX_INVOICE_API from config; if false, proceed with stub path (call TaxInvoicePersistenceService.issueInvoice directly). • If true (future): delegate to external TaxInvoiceApiClient (to be implemented when OI-02 resolved); return 501 NOT_IMPLEMENTED for now. • Validate invoice_ref is non-blank and <= 64 chars; return 400 INVALID_INVOICE_REF if not. • Return 404 if invoice id not found; 409 INVOICE_ALREADY_ISSUED if status != DRAFT. | POST /v1/admin/invoices/{id}/issue endpoint with stub issuance, feature flag gate, and RBAC. | • POST to a DRAFT invoice with valid invoice_ref returns 200 and the updated invoice with status=ISSUED, issued_at non-null. • POST to an already ISSUED invoice returns 409 INVOICE_ALREADY_ISSUED. • POST with ADMIN_VIEWER JWT returns 403. • invoice_ref longer than 64 characters returns 400 INVALID_INVOICE_REF. • With FEATURE_TAX_INVOICE_API=false (default), the endpoint succeeds as a stub; field invoice_ref is set from the request body. | 35 | 7.6-T06, 7.6-T13 | BE | SCH-06
7.6-T15 | settlement-reconciliation | 7.6 | 7. Settlement, Reconciliation & Revenue | Gross settlement & monthly invoicing | 2 | Add Admin System API endpoint: GET /v1/admin/settlement/gross?date=&scheme_id= (settlement summary) | WBS 7.6 Admin System visibility. Finance operators must be able to view gross settlement totals for a given date (PRD-07 §11.2). Endpoint returns per-merchant gross settlement summary from the gross_settlement_daily_aggregate view. Response fields: settlement_date, merchant_id, gross_txn_count, gross_txn_amount_krw, refund_count, refund_amount_krw, net_settlement_amount_krw, settlement_status (from settlement_batch for that merchant+date). Also returns file-level status: ZP0061 status (GENERATED/TRANSMITTED/RECONCILED/ERROR), ZP0062 status (RECEIVED or NOT_RECEIVED). RBAC: FINANCE_ANALYST, OPS_OPERATOR, SUPER_ADMIN only. | • Create AdminGrossSettlementController in com.gme.gmepay.admin.settlement. • GET /v1/admin/settlement/gross: parse date (YYYY-MM-DD) and scheme_id (required); return 400 for invalid date. • Query gross_settlement_daily_aggregate view for the given date and scheme_id. • For each merchant, join settlement_batch to get ZP0061 and ZP0062 statuses. • Return response list sorted by merchant_id; include a summary row with totals (total gross_txn_count, total net_settlement_amount_krw). | AdminGrossSettlementController GET endpoint returning per-merchant gross settlement summary with file statuses. | • GET /v1/admin/settlement/gross?date=2026-01-15&scheme_id=1 returns rows only for GROSS settlement_model transactions on that date. • Each row includes ZP0061_status and ZP0062_status fields; ZP0062_status is NOT_RECEIVED if the result file has not yet been processed. • Summary totals row: total_net_settlement_amount_krw = SUM of all individual net_settlement_amount_krw in the response. • date=2026-01-32 returns HTTP 400 INVALID_DATE. • Response is empty list (not 404) when no gross transactions exist for the given date. | 40 | 7.6-T03, 7.6-T10 | BE | SCH-06
7.6-T16 | settlement-reconciliation | 7.6 | 7. Settlement, Reconciliation & Revenue | Gross settlement & monthly invoicing | 2 | Add Admin System API endpoint: GET /v1/admin/invoices/summary?period= (monthly ZP share summary) | WBS 7.6 Finance operator view of the monthly ZeroPay 0.21% share payable. Endpoint aggregates tax_invoice data for the period and shows total_merchant_fee_krw, total_zeropay_share_krw, total_invoice_amount_krw, and status breakdown (count by status). Also returns the zeropay_monthly_payable row for the period if it exists (showing total_zeropay_share_krw due and payment status PENDING/PAID/DISPUTED). This gives Finance a single view of what GME owes ZeroPay for the month. RBAC: FINANCE_ANALYST, OPS_OPERATOR, SUPER_ADMIN. | • Add GET /v1/admin/invoices/summary to AdminInvoiceController. • Parse period as YearMonth from YYYY-MM; return 400 for invalid format. • Query tax_invoice aggregate: SUM(merchant_fee_krw), SUM(zeropay_share_krw), SUM(invoice_amount_krw) for the period; GROUP BY status to get status counts. • Query zeropay_monthly_payable for the period+scheme; include payable status and total_zeropay_share_krw. • Return summary DTO: period, total_merchants, total_transaction_amount_krw, total_merchant_fee_krw, total_vat_krw, total_invoice_amount_krw, total_zeropay_share_krw, status_counts map, payable (nullable). | GET /v1/admin/invoices/summary endpoint returning monthly aggregation of merchant fee invoices and ZP share payable. | • For a period with 3 ISSUED invoices with merchant_fee_krw 17000, 34000, 51000 (total 102000): total_zeropay_share_krw = 214 (floor(102000 x 0.0021)). • status_counts map shows {DRAFT: 0, ISSUED: 3, COLLECTED: 0, FAILED: 0} for the example above. • payable field is null if computeAndRecordPayable has not been called yet for the period. • period=2026-13 returns 400 INVALID_PERIOD_FORMAT. • ADMIN_VIEWER returns 403 INSUFFICIENT_PERMISSIONS. | 35 | 7.6-T12, 7.6-T13 | BE | SCH-06
7.6-T17 | settlement-reconciliation | 7.6 | 7. Settlement, Reconciliation & Revenue | Gross settlement & monthly invoicing | 2 | Unit tests: GrossSettlementCalculator edge cases | WBS 7.6 unit testing for GrossSettlementCalculator (T04). Tests must cover: normal case, exact zero refunds, refunds equal payments (net=0), refunds exceed payments (negative net -> exception), zero payment amount, large KRW amounts (up to 10 billion). All via JUnit 5 / AssertJ; no DB or Spring context required. | • Create GrossSettlementCalculatorTest in src/test/java/com/gme/gmepay/settlement/gross/. • Test normal: calculate(50000,5000) -> net=45000, merchantFeeTotal=0, type='G'. • Test zero refunds: calculate(50000,0) -> net=50000. • Test net exactly zero: calculate(10000,10000) -> should return net=0 (valid; ZeroPay receives 0 for that merchant that day). • Test negative net: calculate(5000,10000) -> throws NegativeSettlementAmountException; verify exception message contains both amounts. • Test illegal args: calculate(-1,0), calculate(0,-1) each throw IllegalArgumentException. • Test large values: calculate(10_000_000_000L, 1_000_000L) -> net=9_999_000_000L, no overflow. | GrossSettlementCalculatorTest with >= 7 test methods achieving 100% branch coverage of GrossSettlementCalculator. | • All 7 test methods pass with zero failures. • NegativeSettlementAmountException is thrown when refundAmountKrw > grossTxnAmountKrw (not just >=). • calculate(10000,10000) returns netSettlementAmountKrw=0 without throwing (zero is a valid gross settlement amount). • merchantFeeTotalKrw is always 0 in every test case. • Large-value test confirms no long overflow (use assertThat(result.netSettlementAmountKrw()).isEqualTo(9_999_000_000L)). | 40 | 7.6-T04 | BE | SCH-06
7.6-T18 | settlement-reconciliation | 7.6 | 7. Settlement, Reconciliation & Revenue | Gross settlement & monthly invoicing | 2 | Unit tests: MonthlyMerchantFeeAggregator calculation correctness | WBS 7.6 unit testing for MonthlyMerchantFeeAggregator (T05). Tests must cover the fee arithmetic: total_transaction_amount_krw -> merchant_fee_krw -> vat_krw -> invoice_amount_krw -> zeropay_share_krw. Key formula: merchant_fee_krw = floor(total x fee_rate); vat_krw = floor(merchant_fee_krw x 0.10); invoice_amount_krw = merchant_fee_krw + vat_krw; zeropay_share_krw = floor(merchant_fee_krw x 0.0021). All arithmetic must use ROUND_DOWN. Test with fee_rate=0.0170 (ZeroPay crossborder minimum) and fee_rate=0.0220 (maximum). Mock FeeConfigRepository and transaction DB queries. | • Create MonthlyMerchantFeeAggregatorTest in src/test/java/com/gme/gmepay/invoicing/. • Mock FeeConfigRepository to return a SchemeFeeConfig with fee_rate=0.0170. • Test vector A: total=1000000, fee_rate=0.0170 -> merchant_fee=17000, vat=1700, invoice_amount=18700, zeropay_share=35 (floor(17000x0.0021)=35). • Test vector B: total=1000000, fee_rate=0.0220 -> merchant_fee=22000, vat=2200, invoice_amount=24200, zeropay_share=46 (floor(22000x0.0021)=46). • Test rounding: total=100001, fee_rate=0.0170 -> merchant_fee=floor(100001x0.0170)=1700, not 1700.017. • Test empty period: if no GROSS transactions in period, aggregate returns empty list. | MonthlyMerchantFeeAggregatorTest with >= 6 test methods covering both fee rate extremes and rounding behaviour. | • Test vector A produces exact values: merchant_fee_krw=17000, vat_krw=1700, invoice_amount_krw=18700, zeropay_share_krw=35. • Test vector B produces exact values: merchant_fee_krw=22000, vat_krw=2200, invoice_amount_krw=24200, zeropay_share_krw=46. • Rounding test confirms floor is applied: total=100001 at fee_rate=0.0170 gives merchant_fee=1700 not 1701. • Empty period returns Collections.emptyList() not a zero-value TaxInvoiceDraft. • All mocked FeeConfigRepository calls use feeTier='CROSSBORDER' (not 'DOMESTIC'). | 40 | 7.6-T05 | BE | SCH-06
7.6-T19 | settlement-reconciliation | 7.6 | 7. Settlement, Reconciliation & Revenue | Gross settlement & monthly invoicing | 2 | Unit tests: TaxInvoicePersistenceService state transitions | WBS 7.6 unit testing for TaxInvoicePersistenceService (T06). Tests must verify all valid and invalid state transitions for tax_invoice: DRAFT->DRAFT (re-aggregate updates values), DRAFT->ISSUED, ISSUED->COLLECTED, ISSUED->FAILED, and illegal transitions (DRAFT->COLLECTED, COLLECTED->ISSUED, FAILED->ISSUED). Test that upsertDraft throws InvoiceAlreadyIssuedException if status is ISSUED/COLLECTED/FAILED. Use an in-memory H2 database or a Mockito-mocked repository. | • Create TaxInvoicePersistenceServiceTest in src/test/java/com/gme/gmepay/invoicing/. • Test upsertDraft on a new merchant+period: creates DRAFT row with correct values. • Test upsertDraft on an existing DRAFT row: updates aggregation fields (idempotent). • Test upsertDraft on an ISSUED row: throws InvoiceAlreadyIssuedException; row is unchanged. • Test issueInvoice: DRAFT->ISSUED, issued_at is set, invoice_ref is set. • Test markCollected: ISSUED->COLLECTED, collected_at is set. • Test markFailed: ISSUED->FAILED, audit log entry created. • Test illegal: markCollected on a DRAFT throws InvalidStateTransitionException. | TaxInvoicePersistenceServiceTest with >= 8 test methods covering all valid transitions and at least 3 illegal transitions. | • upsertDraft twice with different total_transaction_amount_krw values leaves exactly one DRAFT row with the second value. • upsertDraft on ISSUED row throws InvoiceAlreadyIssuedException and does not modify the row. • After issueInvoice: status=ISSUED, issued_at non-null, invoice_ref matches the provided value. • markCollected on DRAFT throws InvalidStateTransitionException. • markFailed creates an audit_log entry with before_status=ISSUED and after_status=FAILED. | 45 | 7.6-T06 | BE | SCH-06
7.6-T20 | settlement-reconciliation | 7.6 | 7. Settlement, Reconciliation & Revenue | Gross settlement & monthly invoicing | 2 | Unit tests: ZeropaySharePayableService 0.21% computation | WBS 7.6 unit testing for ZeropaySharePayableService (T12). Core assertion: total_zeropay_share_krw = floor(SUM(merchant_fee_krw) x 0.0021) across all ISSUED/COLLECTED invoices for the period. Tests: normal multi-merchant aggregation, single merchant, all-DRAFT invoices (excluded - payable should be 0 or empty), large monthly volume (total_merchant_fee 10000000 KRW -> zeropay_share=21000). Also test markPaid state transitions and UNIQUE constraint on period+scheme. | • Create ZeropaySharePayableServiceTest in src/test/java/com/gme/gmepay/invoicing/. • Test 3-merchant case: merchant_fee values 17000+34000+51000=102000, zeropay_share=floor(102000x0.0021)=214. • Test all-DRAFT: computeAndRecordPayable with all invoices in DRAFT status returns payable with total_zeropay_share_krw=0 (no ISSUED/COLLECTED invoices counted). • Test large volume: total_merchant_fee=10000000, zeropay_share=floor(10000000x0.0021)=21000. • Test markPaid: PENDING->PAID valid; PENDING->PAID->PAID throws InvalidStateTransitionException. • Test UNIQUE: calling computeAndRecordPayable twice for same period upserts the same row (no duplicate). | ZeropaySharePayableServiceTest with >= 5 test methods covering aggregation correctness, DRAFT exclusion, and state transitions. | • 3-merchant test produces total_zeropay_share_krw=214 exactly. • All-DRAFT invoices excluded: payable total_zeropay_share_krw=0 (or method returns empty/zero payable). • Large volume: total_merchant_fee=10000000 gives zeropay_share=21000 (floor(10000000x0.0021)=21000). • Second call to computeAndRecordPayable for same period produces one row, not two (upsert idempotency). • markPaid on an already-PAID payable throws InvalidStateTransitionException. | 35 | 7.6-T12 | BE | SCH-06
7.6-T21 | settlement-reconciliation | 7.6 | 7. Settlement, Reconciliation & Revenue | Gross settlement & monthly invoicing | 2 | Integration test: full monthly gross settlement and invoicing cycle (ZP0061->ZP0062->tax_invoice) | WBS 7.6 end-to-end integration test. Scenario: OVERSEAS partner SendMN has 5 KRW transactions in January 2026 at 3 different merchants (merchant A: 3 txns x 50000 KRW; merchant B: 2 txns x 100000 KRW); all APPROVED and SETTLEMENT_REGISTERED. Run: (1) GrossSettlementService.runMorningSettlement produces ZP0061 with 2 G-type merchant rows; (2) Process simulated ZP0062 result with result_code=00 for both merchants -> transactions transition to SETTLED; (3) MonthlyInvoiceBatchJob runs for January 2026 -> creates DRAFT tax_invoice rows for merchants A and B; (4) Operator issues invoice for merchant A (POST /issue); (5) ZeropaySharePayableService.computeAndRecordPayable records ZP share. Verify all state transitions and computed values. Use @SpringBootTest with TestContainers Postgres. | • Create GrossSettlementIntegrationTest in src/test/java/com/gme/gmepay/settlement/gross/ with @SpringBootTest and TestContainers. • Seed: 5 transactions (3 for merchant A with target_payout_krw=50000, fee_rate=0.0170; 2 for merchant B with target_payout_krw=100000, fee_rate=0.0170); all settlement_model='GROSS', status='SETTLEMENT_REGISTERED'. • Assert ZP0061 file has 2 records with settlement_type='G'; merchant A net_settlement_amount=150000; merchant B=200000. • Simulate ZP0062 with result_code=00 for both; assert all 5 transactions in status SETTLED. • Assert tax_invoice DRAFT for merchant A: total_transaction_amount=150000, merchant_fee=floor(150000x0.0170)=2550, vat=255, invoice_amount=2805, zeropay_share=floor(2550x0.0021)=5. • Assert tax_invoice DRAFT for merchant B: total_transaction_amount=200000, merchant_fee=3400, vat=340, invoice_amount=3740, zeropay_share=7. • After issuing merchant A invoice: status=ISSUED, issued_at non-null. • Assert ZeropaySharePayableService payable: total_merchant_fee=2550 (ISSUED only), total_zeropay_share=5. | GrossSettlementIntegrationTest with >= 8 assertions covering the full cycle from transaction seeding to ZP share payable recording. | • ZP0061 merchant A record: gross_txn_count=3, gross_txn_amount=150000, net_settlement_amount=150000, settlement_type='G'. • After ZP0062 processing: all 5 transactions in status SETTLED (not still SETTLEMENT_REGISTERED). • tax_invoice DRAFT for merchant A: merchant_fee_krw=2550, vat_krw=255, invoice_amount_krw=2805, zeropay_share_krw=5. • tax_invoice DRAFT for merchant B: merchant_fee_krw=3400, vat_krw=340, invoice_amount_krw=3740, zeropay_share_krw=7. • ZeropaySharePayableService payable for January 2026 with merchant A ISSUED: total_zeropay_share_krw=5 (merchant B still DRAFT, excluded). | 60 | 7.6-T10, 7.6-T11, 7.6-T07, 7.6-T12 | BE | SCH-06
7.6-T22 | settlement-reconciliation | 7.6 | 7. Settlement, Reconciliation & Revenue | Gross settlement & monthly invoicing | 2 | Add Admin System settlement dashboard: gross settlement tab with ZP0061/ZP0062 status indicators | WBS 7.6 Admin System UI (PRD-07 §11.2). The Settlement module needs a Gross Settlement tab showing: settlement_date picker, per-merchant table (merchant_id, gross_txn_count, gross_txn_amount_krw, refund_amount_krw, net_settlement_amount_krw, ZP0061 status, ZP0062 status), and a page-level summary (total net_settlement_amount_krw, file statuses). ZP0061 status chip: grey=PENDING, blue=GENERATED, green=RECONCILED, red=ERROR. ZP0062 status chip: grey=NOT_RECEIVED, green=RECEIVED. Backed by GET /v1/admin/settlement/gross (T15). RBAC: FINANCE_ANALYST read-only; OPS_OPERATOR can trigger manual re-transmission of ZP0061. | • Create GrossSettlementTab React component in admin-ui/src/pages/settlement/. • Integrate with GET /v1/admin/settlement/gross API (T15); add date picker and auto-refresh every 5 minutes during batch windows (05:00-10:00 KST and 14:00-19:00 KST). • Render per-merchant table with columns from context; highlight rows with ZP0062 status ERROR in red. • Add summary bar at top: total_net_settlement_amount_krw formatted as KRW integer with comma separators, ZP0061 and ZP0062 status chips. • OPS_OPERATOR users see a Re-transmit button per settlement date; FINANCE_ANALYST sees read-only view; button calls POST /v1/admin/settlement/{date}/retransmit-zp0061 (stub endpoint). | GrossSettlementTab React component integrated with the settlement API, with status chips, table, and role-gated re-transmit button. | • Component renders per-merchant table rows from the API response with all required columns. • ZP0061 status chip renders green when status=RECONCILED, red when status=ERROR, blue when GENERATED, grey when PENDING. • FINANCE_ANALYST user does not see the Re-transmit button; OPS_OPERATOR user sees it. • Total net_settlement_amount_krw in the summary bar matches the SUM of all per-merchant net_settlement_amount_krw values. • Component auto-refreshes every 5 minutes without requiring user interaction; refresh does not reset the date picker value. | 55 | 7.6-T15 | BE | SCH-06
7.6-T23 | settlement-reconciliation | 7.6 | 7. Settlement, Reconciliation & Revenue | Gross settlement & monthly invoicing | 2 | Add Admin System invoice module: monthly invoice list and issue-invoice workflow (stub) | WBS 7.6 Admin System UI for UC-04-04. Finance/Ops operators need an Invoice module under the Finance section. List view backed by GET /v1/admin/invoices (T13): columns merchant_id, invoice_period, total_transaction_amount_krw, merchant_fee_krw, vat_krw, invoice_amount_krw, zeropay_share_krw, status. Period picker defaults to current month. Status filter chips (ALL/DRAFT/ISSUED/COLLECTED/FAILED). Issue action: DRAFT row has Issue button (OPS_OPERATOR only) that opens a modal prompting for invoice_ref, then calls POST /v1/admin/invoices/{id}/issue (T14). On success, row status updates to ISSUED. Stub banner shown: 'Tax invoice API (OI-02) not yet confirmed - issuing manually.' per PRD-07 A-08. | • Create InvoiceModule React component in admin-ui/src/pages/finance/invoices/. • Integrate with GET /v1/admin/invoices (T13) with period picker (defaulting to current YearMonth) and status filter. • Render the invoice table with all columns from context; format KRW values as integers with comma separators. • Add Issue button on DRAFT rows (only for OPS_OPERATOR/SUPER_ADMIN JWT roles); clicking opens IssueInvoiceModal with invoice_ref text input. • IssueInvoiceModal calls POST /v1/admin/invoices/{id}/issue; on success updates row to ISSUED and shows a banner 'Manually issued (Tax API OI-02 pending)'; on 409 shows 'Already issued'. | InvoiceModule React component with list view, period/status filtering, and stub issue-invoice modal workflow. | • Invoice list displays all tax_invoice rows for the selected period with correct KRW-formatted column values. • Status filter chip DRAFT shows only DRAFT rows; ALL chip shows all statuses. • FINANCE_ANALYST user sees no Issue button on DRAFT rows; OPS_OPERATOR sees Issue button. • Successfully issuing an invoice updates the row status in the table from DRAFT to ISSUED without full page reload. • Stub banner 'Manually issued (Tax API OI-02 pending)' appears on successful issue action. | 50 | 7.6-T13, 7.6-T14 | BE | SCH-06
7.6-T24 | settlement-reconciliation | 7.6 | 7. Settlement, Reconciliation & Revenue | Gross settlement & monthly invoicing | 2 | Add Admin System invoice summary widget: ZP share payable for the current month | WBS 7.6 Admin System Finance dashboard. Add a ZeroPay Share Payable widget to the Finance dashboard backed by GET /v1/admin/invoices/summary (T16). Widget shows: current month period, total_merchant_fee_krw, total_zeropay_share_krw (formatted as KRW integer), status of the zeropay_monthly_payable (PENDING/PAID/DISPUTED badge), and a breakdown pie chart of invoice statuses (DRAFT/ISSUED/COLLECTED/FAILED counts). Finance Analyst and Ops Operator can view. A 'Mark Paid' button is shown when payable status=PENDING (FINANCE_ANALYST or OPS_OPERATOR); calls POST /v1/admin/zeropay-payable/{id}/mark-paid. Tooltip on zeropay_share_krw: 'GME pays 0.21% of total merchant fees to ZeroPay monthly'. | • Create ZeropayShareWidget React component in admin-ui/src/pages/finance/dashboard/. • Integrate with GET /v1/admin/invoices/summary?period=YYYY-MM (T16); auto-update to current month on first load. • Render: period label, total_merchant_fee_krw (KRW format), total_zeropay_share_krw with tooltip, payable status badge. • Add a small donut chart (recharts or equivalent) showing invoice status breakdown from status_counts. • Mark Paid button visible when payable.status=PENDING; calls POST /v1/admin/zeropay-payable/{id}/mark-paid; on success badge changes to PAID. | ZeropayShareWidget React component integrated with the summary API, with KRW-formatted totals, status badge, donut chart, and Mark Paid button. | • Widget displays total_zeropay_share_krw as a KRW integer with comma separator (e.g. 21,000 not 21000.00). • Tooltip on zeropay_share_krw contains text about the 0.21% rate. • Donut chart segments match status_counts from the API (e.g. ISSUED=3 shows a segment proportional to 3). • Mark Paid button only appears when payable.status=PENDING; after marking paid the badge updates to PAID without page reload. • ADMIN_VIEWER role does not see the Mark Paid button. | 45 | 7.6-T16 | BE | SCH-06
8.1-T01 | api-gateway | 8.1 | 8. Partner (Northbound) API | API gateway & versioning framework | 1 | Scaffold Spring Cloud Gateway Gradle module in monorepo | WBS 8.1 delivers the API gateway layer for GMEPay+. The monorepo uses Gradle multi-module with root settings.gradle. A dedicated gateway module named services/api-gateway must be created as a Spring Boot 3.x + Spring Cloud Gateway application. It is the single HTTPS entry point for all partner traffic (api.gmepayplus.com and api-sandbox.gmepayplus.com). No routing logic yet — just the buildable skeleton. | • Add entry include('services:api-gateway') to root settings.gradle • Create services/api-gateway/build.gradle with dependencies: spring-cloud-starter-gateway, spring-boot-starter-actuator, spring-boot-starter-data-redis-reactive (for rate-limit state), micrometer-registry-prometheus • Create main class ApiGatewayApplication.java at services/api-gateway/src/main/java/com/gme/pay/gateway/ApiGatewayApplication.java annotated @SpringBootApplication • Add application.yml with spring.application.name=api-gateway, server.port=8080, management.endpoints.web.exposure.include=health,prometheus • Verify ./gradlew :services:api-gateway:build passes with no sources errors | services/api-gateway/build.gradle and services/api-gateway/src/main/java/com/gme/pay/gateway/ApiGatewayApplication.java | • ./gradlew :services:api-gateway:build completes without error • Spring Boot context starts (log shows 'Started ApiGatewayApplication') • GET /actuator/health returns {status:UP} • Module appears in ./gradlew projects output | 25 |  | BE | API-05
8.1-T02 | api-gateway | 8.1 | 8. Partner (Northbound) API | API gateway & versioning framework | 1 | Define /v1 route prefix convention and global URI rewrite filter | API-05 section 2.2: all endpoints are prefixed /v1. Spring Cloud Gateway must strip this prefix when forwarding to downstream services via Kubernetes service discovery (lb://service-name). A RewritePath filter maps /v1/{segment} to /{segment}. All routes live in module services/api-gateway; downstream service URIs follow lb://rate-fx, lb://payment-executor, lb://merchant-qr-data, lb://prefunding-balance. | • Create GatewayRoutingConfig.java at services/api-gateway/src/main/java/com/gme/pay/gateway/config/GatewayRoutingConfig.java with a RouteLocatorBuilder bean • Define placeholder route for /v1/rates/** to lb://rate-fx with RewritePath=/v1/(?<segment>.*),/$\{segment} • Define placeholder route for /v1/payments/** to lb://payment-executor with same RewritePath pattern • Add global default-filter AddRequestHeader: X-Gateway-Version=v1 in application.yml • Set spring.cloud.gateway.discovery.locator.enabled=false (manual route registration only) | services/api-gateway/src/main/java/com/gme/pay/gateway/config/GatewayRoutingConfig.java | • Route for /v1/rates/** forwards to lb://rate-fx with /v1 prefix stripped • Route for /v1/payments/** forwards to lb://payment-executor • Unknown paths return 404 (no catch-all route) • X-Gateway-Version: v1 header present on all forwarded downstream requests • ./gradlew :services:api-gateway:build passes | 30 | 8.1-T01 | BE | API-05
8.1-T03 | api-gateway | 8.1 | 8. Partner (Northbound) API | API gateway & versioning framework | 1 | Implement X-Request-ID generation and propagation filter | API-05 section 2.7: every response (success or error) must include X-Request-ID set by GMEPay+, format req_<ULID> e.g. req_01HX7MNPQRS4T5U6VWXY012Z. The filter runs at highest priority (Ordered.HIGHEST_PRECEDENCE). It sets the ID on both the downstream forwarded request and the outbound response. All downstream services use X-Request-ID as structured log correlation field per SAD-02 requirements. | • Add com.github.f4b6a3:ulid-creator to services/api-gateway/build.gradle • Create RequestIdFilter.java at services/api-gateway/src/main/java/com/gme/pay/gateway/filter/RequestIdFilter.java implementing GlobalFilter, Ordered with order=Ordered.HIGHEST_PRECEDENCE+1 • In filter: if X-Request-ID absent, generate req_+UlidCreator.getMonotonicUlid().toString() and set on request mutate and response headers • If X-Request-ID already present in incoming request, preserve it unchanged (idempotent) • Write unit test RequestIdFilterTest.java: absent header generates new ID matching req_[A-Z0-9]{26}, present header is preserved | services/api-gateway/src/main/java/com/gme/pay/gateway/filter/RequestIdFilter.java and src/test/java/com/gme/pay/gateway/filter/RequestIdFilterTest.java | • Response always contains X-Request-ID matching pattern req_[A-Z0-9]{26} • Incoming X-Request-ID is echoed unchanged in response (idempotent) • Downstream requests carry X-Request-ID header • Filter order equals Ordered.HIGHEST_PRECEDENCE+1 • Unit test covers absent and present header scenarios | 35 | 8.1-T01 | BE | API-05
8.1-T04 | api-gateway | 8.1 | 8. Partner (Northbound) API | API gateway & versioning framework | 1 | Implement X-Timestamp replay protection filter (300-second window) | API-05 section 3.2: GMEPay+ rejects requests where ¦server_time - X-Timestamp¦ > 300 seconds. X-Timestamp must be ISO-8601 UTC millisecond precision (e.g. 2026-06-04T09:31:00.000Z). Error code: TIMESTAMP_OUT_OF_RANGE, HTTP 401. Error body matches lib-errors ApiErrorResponse envelope: {error:{code,message,request_id,details:[]}}. This filter runs before signature verification so malformed/stale requests are rejected cheaply. | • Create TimestampValidationFilter.java at services/api-gateway/src/main/java/com/gme/pay/gateway/filter/TimestampValidationFilter.java implementing GlobalFilter, Ordered (order after RequestIdFilter) • Parse X-Timestamp header as Instant (ISO-8601 UTC); if absent or unparseable return 401 TIMESTAMP_OUT_OF_RANGE • Compute Math.abs(Duration.between(timestamp, Instant.now()).toSeconds()); if > 300 return 401 TIMESTAMP_OUT_OF_RANGE • Serialize error as {error:{code:'TIMESTAMP_OUT_OF_RANGE',message:...,request_id:<X-Request-ID>,details:[]}} with Content-Type: application/json • Write unit test with 4 vectors: 299s past (pass), 301s past (fail), 300s future (pass), 301s future (fail) | services/api-gateway/src/main/java/com/gme/pay/gateway/filter/TimestampValidationFilter.java | • X-Timestamp 299s in past: request passes filter • X-Timestamp 301s in past: returns 401 TIMESTAMP_OUT_OF_RANGE • X-Timestamp 301s in future: returns 401 • Missing X-Timestamp: returns 401 • Error body includes request_id matching X-Request-ID response header | 35 | 8.1-T03 | BE | API-05
8.1-T05 | api-gateway | 8.1 | 8. Partner (Northbound) API | API gateway & versioning framework | 1 | Implement HMAC-SHA256 request signature verification filter | API-05 section 3.2: every request must carry X-API-Key, X-Timestamp, X-Signature. Canonical string = HTTP_METHOD + newline + PATH_WITH_QUERY + newline + X-Timestamp value + newline + SHA256_HEX_OF_BODY. HMAC-SHA256(canonical_string, api_secret) must equal X-Signature (hex). For GET/DELETE with no body, SHA-256 of empty string is the body hash. Error INVALID_API_KEY (401) if key unknown; INVALID_SIGNATURE (401) if mismatch. Constant-time comparison required (MessageDigest.isEqual). | • Create HmacSignatureFilter.java at services/api-gateway/src/main/java/com/gme/pay/gateway/filter/HmacSignatureFilter.java implementing GlobalFilter, Ordered (after TimestampValidationFilter) • Resolve partner by X-API-Key via PartnerCredentialService (stubbed in Phase 1 via application.yml test entries); Mono.empty() -> return 401 INVALID_API_KEY • Cache request body via ServerWebExchange.mutate() + DataBufferUtils.join(); compute SHA-256 hex of body bytes (empty string for bodyless requests) • Build canonical string, compute HMAC-SHA256 via javax.crypto.Mac HmacSHA256, compare with X-Signature using MessageDigest.isEqual • Write unit test with pre-computed vectors: valid signature passes, 1-byte body tamper fails, wrong secret fails | services/api-gateway/src/main/java/com/gme/pay/gateway/filter/HmacSignatureFilter.java | • Valid signature (known key/secret/body vector) passes filter • Tampered body (1 byte changed) returns 401 INVALID_SIGNATURE • Missing X-API-Key returns 401 INVALID_API_KEY • GET with no body uses SHA-256 of empty string for body hash (unit test confirms) • Comparison uses constant-time MessageDigest.isEqual (no timing oracle) | 45 | 8.1-T04 | BE | API-05
8.1-T06 | api-gateway | 8.1 | 8. Partner (Northbound) API | API gateway & versioning framework | 1 | Implement signature replay deduplication via Redis (10-minute window) | API-05 section 3.6: after passing the 300s timestamp window, GMEPay+ stores (partner_id, X-Signature) in Redis for 10 minutes and rejects exact-signature duplicates. Redis key format: sig_dedup:{partner_id}:{x_signature_hex}, SET NX EX 600. Error: 401 INVALID_SIGNATURE with message 'Duplicate signature detected'. Redis is spring-boot-starter-data-redis-reactive already in the gateway module. On Redis unavailability: fail-open (configurable via gateway.replay-protection.fail-open=true, default true). | • Create ReplayProtectionFilter.java at services/api-gateway/src/main/java/com/gme/pay/gateway/filter/ReplayProtectionFilter.java implementing GlobalFilter, Ordered (after HmacSignatureFilter) • Inject ReactiveRedisTemplate<String,String>; attempt setIfAbsent(key, '1', Duration.ofSeconds(600)) • If setIfAbsent returns false (key existed), return 401 INVALID_SIGNATURE body {error:{code:'INVALID_SIGNATURE',message:'Duplicate signature detected',request_id:...}} • On Redis exception: if fail-open=true log WARN and continue; if fail-open=false return 503 • Write Testcontainers Redis integration test: first request passes, identical second within 600s rejected, third after TTL passes | services/api-gateway/src/main/java/com/gme/pay/gateway/filter/ReplayProtectionFilter.java | • First request with signature S passes • Second request with identical (partner_id, S) within 600s returns 401 INVALID_SIGNATURE • Redis key is sig_dedup:{partner_id}:{sig_hex} with TTL=600s (verify via Redis TTL command in test) • Testcontainers Redis integration test passes all 3 scenarios • fail-open=true allows request when Redis throws exception (unit test with mock Redis) | 40 | 8.1-T05 | BE | API-05
8.1-T07 | api-gateway | 8.1 | 8. Partner (Northbound) API | API gateway & versioning framework | 1 | Implement per-partner rate limiting via Redis RequestRateLimiter filter | API-05 section 3.5 rate limits: 100 req/s per partner (global), 20 req/s for POST /v1/rates, 50 req/s for POST /v1/payments and POST /v1/payments/cpm/generate. HTTP 429 RATE_LIMITED with Retry-After header. Responses include X-RateLimit-Limit, X-RateLimit-Remaining, X-RateLimit-Reset. Spring Cloud Gateway's built-in RequestRateLimiter filter backed by Redis uses RedisRateLimiter with replenishRate and burstCapacity. KeyResolver extracts partner_id from resolved credential placed in exchange attributes by HmacSignatureFilter. | • Configure RedisRateLimiter beans in GatewayRoutingConfig.java: globalRateLimiter(100,100), ratesRateLimiter(20,20), paymentsRateLimiter(50,50) • Define KeyResolver bean: exchange -> Mono.justOrEmpty(exchange.getAttribute('partner_id')) • Apply globalRateLimiter to all routes; override with specific limiters on /v1/rates and /v1/payments routes • Create RateLimitResponseFilter.java to add X-RateLimit-Limit, X-RateLimit-Remaining, X-RateLimit-Reset response headers from Spring's internal rate-limit result headers • Write Testcontainers Redis test: send 21 sequential requests to /v1/rates from same partner; assert 21st returns 429 with Retry-After header | Updated GatewayRoutingConfig.java with rate limiter beans; services/api-gateway/src/main/java/com/gme/pay/gateway/filter/RateLimitResponseFilter.java | • 21st POST /v1/rates within 1s from same partner returns 429 RATE_LIMITED • Response on 429 includes Retry-After header • All responses include X-RateLimit-Limit, X-RateLimit-Remaining, X-RateLimit-Reset • Different partners have independent counters (partner A limit does not block partner B) • Testcontainers Redis test passes for 20-req/s POST /v1/rates scenario | 45 | 8.1-T06 | BE | API-05
8.1-T08 | api-gateway | 8.1 | 8. Partner (Northbound) API | API gateway & versioning framework | 1 | Implement Idempotency-Key presence and format enforcement for POST endpoints | API-05 section 2.6: all POST requests must include Idempotency-Key header (UUID, min 16 chars, max 128 chars). Missing key returns HTTP 400 MISSING_IDEMPOTENCY_KEY. Invalid length returns HTTP 400 VALIDATION_ERROR with details field=Idempotency-Key. This is a gateway-level guard only — actual idempotency storage (partner_id + key -> response, 24h TTL) is handled per downstream service. GET requests are not affected. | • Create IdempotencyKeyFilter.java at services/api-gateway/src/main/java/com/gme/pay/gateway/filter/IdempotencyKeyFilter.java implementing GlobalFilter, Ordered • Apply only when exchange.getRequest().getMethod() == HttpMethod.POST • If Idempotency-Key header absent: return 400 MISSING_IDEMPOTENCY_KEY • If Idempotency-Key length < 16 or > 128: return 400 VALIDATION_ERROR with details=[{field:'Idempotency-Key',issue:'length must be 16-128 chars'}] • Write unit test: absent key->400 MISSING_IDEMPOTENCY_KEY, 15-char->400 VALIDATION_ERROR, 16-char->pass, 128-char->pass, 129-char->400, GET with no key->pass | services/api-gateway/src/main/java/com/gme/pay/gateway/filter/IdempotencyKeyFilter.java | • POST without Idempotency-Key returns 400 MISSING_IDEMPOTENCY_KEY • POST with 15-char key returns 400 VALIDATION_ERROR • POST with valid 36-char UUID passes • GET without Idempotency-Key passes (filter skipped) • Unit test covers all boundary lengths: 15, 16, 128, 129 | 30 | 8.1-T03 | BE | API-05
8.1-T09 | api-gateway | 8.1 | 8. Partner (Northbound) API | API gateway & versioning framework | 1 | Implement Content-Type enforcement filter for POST/PUT requests | API-05 section 2.3: all requests with a body must use Content-Type: application/json; charset=utf-8. The gateway rejects POST/PUT where Content-Type is absent or not application/json (charset suffix ignored for comparison). Error: HTTP 400 VALIDATION_ERROR with details [{field:'Content-Type',issue:'must be application/json'}]. This prevents non-JSON payloads reaching downstream services. | • Create ContentTypeFilter.java at services/api-gateway/src/main/java/com/gme/pay/gateway/filter/ContentTypeFilter.java implementing GlobalFilter • Apply only to POST and PUT methods • Extract MediaType from Content-Type header; if not MediaType.APPLICATION_JSON_compatible return 400 VALIDATION_ERROR • Error body: {error:{code:'VALIDATION_ERROR',message:'Content-Type must be application/json',details:[{field:'Content-Type',issue:'must be application/json'}],request_id:...}} • Write unit test: POST application/json passes, POST application/json;charset=utf-8 passes, POST application/xml fails, POST missing header fails, GET missing header passes | services/api-gateway/src/main/java/com/gme/pay/gateway/filter/ContentTypeFilter.java | • POST with Content-Type: application/json passes • POST with Content-Type: application/json;charset=utf-8 passes • POST with Content-Type: application/xml returns 400 VALIDATION_ERROR • POST without Content-Type returns 400 • GET without Content-Type passes (not checked) | 20 | 8.1-T03 | BE | API-05
8.1-T10 | api-gateway | 8.1 | 8. Partner (Northbound) API | API gateway & versioning framework | 1 | Implement canonical error envelope for all gateway-level rejections | API-05 section 8.1: all error responses use {error:{code,message,request_id,details:[]}}. Every gateway filter that rejects a request must produce this envelope with Content-Type: application/json. The error.request_id must match the X-Request-ID response header (set by RequestIdFilter). This ticket creates a GatewayErrorWriter utility used by all filters and an ErrorWebExceptionHandler to catch unhandled exceptions. | • Create GatewayErrorWriter.java at services/api-gateway/src/main/java/com/gme/pay/gateway/filter/GatewayErrorWriter.java with static method writeError(ServerWebExchange, HttpStatus, ApiErrorCode, String) -> Mono<Void> that serializes {error:{code,message,request_id,details:[]}} and sets Content-Type: application/json • Ensure request_id is read from exchange response headers (set by RequestIdFilter) or generated if missing • Register GatewayGlobalExceptionHandler.java implementing ErrorWebExceptionHandler (Ordered.HIGHEST_PRECEDENCE-1) to catch Throwable, map to 500 INTERNAL_ERROR envelope • Update all existing filters (T04, T05, T06, T08, T09) to use GatewayErrorWriter instead of ad-hoc response writes • Write integration test: trigger each rejection type, assert envelope fields {error.code, error.request_id, Content-Type} | services/api-gateway/src/main/java/com/gme/pay/gateway/filter/GatewayErrorWriter.java and GatewayGlobalExceptionHandler.java | • All 4xx/5xx gateway responses contain {error:{code,message,request_id,details[]}} shape • Content-Type is application/json on all error responses • error.request_id matches X-Request-ID response header • Unhandled exception returns 500 INTERNAL_ERROR (not Spring Whitelabel error) • Integration test verifies 401, 400, 429, 403 envelopes are correct | 35 | 8.1-T04, 8.1-T05, 8.1-T07, 8.1-T08, 8.1-T09 | BE | API-05
8.1-T11 | api-gateway | 8.1 | 8. Partner (Northbound) API | API gateway & versioning framework | 1 | Implement IP allowlist enforcement filter | API-05 section 3.3: partners may register up to 10 source IP CIDR ranges. When an allowlist is configured for a partner, requests from unlisted IPs are rejected 403 IP_NOT_ALLOWLISTED before signature verification. Partner IP config is loaded from PostgreSQL config_registry via PartnerCredentialService (8.1-T18). IP check must run before HMAC filter. Remote address extracted from ServerWebExchange.getRequest().getRemoteAddress(); X-Forwarded-For honoured when gateway.trust-proxy=true. | • Create IpAllowlistFilter.java at services/api-gateway/src/main/java/com/gme/pay/gateway/filter/IpAllowlistFilter.java implementing GlobalFilter, Ordered with order before HmacSignatureFilter • Resolve partner from X-API-Key header; if key unknown skip (HMAC filter handles that) • If partner.ipCidrRanges is non-empty, parse each CIDR with com.google.guava SubnetUtils or Apache Commons Net SubnetUtils; check remoteIp • If source IP not in any CIDR, return 403 IP_NOT_ALLOWLISTED via GatewayErrorWriter • Write unit test: partner allowlist 192.168.1.0/24 — 192.168.1.5 passes, 10.0.0.1 returns 403, no allowlist configured passes any IP | services/api-gateway/src/main/java/com/gme/pay/gateway/filter/IpAllowlistFilter.java | • Partner with allowlist: IP in /24 range passes • Partner with allowlist: IP outside range returns 403 IP_NOT_ALLOWLISTED • Partner with no allowlist: all IPs pass • X-Forwarded-For header honoured when gateway.trust-proxy=true • Unit test covers /24, /32, and no-allowlist scenarios | 35 | 8.1-T05 | BE | API-05
8.1-T12 | api-gateway | 8.1 | 8. Partner (Northbound) API | API gateway & versioning framework | 1 | Define canonical pagination model in lib-api-contracts | API-05 section 2.8: list endpoints use cursor-based pagination. Query params: limit (default 20, max 100), after (next_cursor from prior page), before (prev_cursor). Response envelope: {data:[], meta:{total_count, has_more, next_cursor, prev_cursor}}. This model lives in lib-api-contracts so all services use a consistent implementation. It is not gateway-specific but is foundational for all list endpoints built in subsequent WBS items. | • Create PaginationParams.java at lib-api-contracts/src/main/java/com/gme/pay/api/pagination/PaginationParams.java as a Java record: int limit, String after (nullable), String before (nullable) • Add static factory PaginationParams.from(MultiValueMap<String,String> queryParams): parse limit (clamp 1-100, default 20), after, before • Create PaginationMeta.java record: long totalCount, boolean hasMore, String nextCursor (nullable), String prevCursor (nullable) • Create PagedResponse<T>.java record: List<T> data, PaginationMeta meta; Jackson serializes keys as total_count, has_more, next_cursor, prev_cursor • Write PaginationParamsTest.java: limit absent->20, limit=0->1, limit=101->100, limit=50->50, after/before null when absent | lib-api-contracts/src/main/java/com/gme/pay/api/pagination/PaginationParams.java, PaginationMeta.java, PagedResponse.java | • PaginationParams.from({}) returns limit=20, after=null, before=null • PaginationParams.from({limit:0}) returns limit=1 • PaginationParams.from({limit:101}) returns limit=100 • PagedResponse<String> serializes to {data:[],meta:{total_count:0,has_more:false,next_cursor:null,prev_cursor:null}} • Unit test PaginationParamsTest covers all 5 boundary cases | 30 |  | BE | API-05
8.1-T13 | api-gateway | 8.1 | 8. Partner (Northbound) API | API gateway & versioning framework | 1 | Define canonical error model with all 24 API-05 error codes in lib-errors | API-05 section 8.2 defines 24 error codes each with HTTP status and retryable flag. lib-errors is shared across all services. The error envelope is {error:{code,message,request_id,details:[{field,issue}]}}. This ticket creates the enum and response model used by the gateway (T10) and all downstream services. | • Create ApiErrorCode.java enum at lib-errors/src/main/java/com/gme/pay/errors/ApiErrorCode.java with all 24 codes: VALIDATION_ERROR(400), MISSING_IDEMPOTENCY_KEY(400), INVALID_SIGNATURE(401), INVALID_API_KEY(401), TIMESTAMP_OUT_OF_RANGE(401), FORBIDDEN(403), IP_NOT_ALLOWLISTED(403), PAYMENT_NOT_FOUND(404), MERCHANT_NOT_FOUND(404), SCHEME_NOT_FOUND(404), IDEMPOTENCY_KEY_REUSE(422), RATE_QUOTE_EXPIRED(422), RATE_QUOTE_INVALID(422), PARTNER_B_QUOTE_DEVIATION(422), PARTNER_B_QUOTE_UNAVAILABLE(422), SCHEME_UNAVAILABLE(422), PAYMENT_MODE_NOT_SUPPORTED(422), DIRECTION_NOT_ENABLED(422), CANCEL_NOT_PERMITTED(400), INSUFFICIENT_PREFUNDING(402), DUPLICATE_PARTNER_TXN_REF(409), RATE_LIMITED(429), INTERNAL_ERROR(500), SERVICE_UNAVAILABLE(503) • Add fields to enum: int httpStatus, boolean retryable; add getHttpStatus() and isRetryable() methods • Create ApiErrorDetail.java record: String field, String issue • Create ApiError.java record: ApiErrorCode code, String message, String requestId, List<ApiErrorDetail> details; @JsonProperty annotations for camelCase -> snake_case • Create ApiErrorResponse.java record: ApiError error (top-level wrapper); write unit test confirming Jackson serialization produces API-05 shape | lib-errors/src/main/java/com/gme/pay/errors/ApiErrorCode.java, ApiError.java, ApiErrorDetail.java, ApiErrorResponse.java | • All 24 error codes present in ApiErrorCode enum with correct HTTP status • RATE_QUOTE_EXPIRED.getHttpStatus()==422, RATE_QUOTE_EXPIRED.isRetryable()==false • RATE_LIMITED.isRetryable()==true, SERVICE_UNAVAILABLE.isRetryable()==true • ApiErrorResponse JSON output is {error:{code:'RATE_QUOTE_EXPIRED',message:...,request_id:...,details:[]}} • Unit test ApiErrorResponseTest.java asserts serialization of all fields including empty details | 30 |  | BE | API-05
8.1-T14 | api-gateway | 8.1 | 8. Partner (Northbound) API | API gateway & versioning framework | 1 | Implement API version deprecation and Sunset headers filter | API-05 section 11.3: when a version is deprecated, responses include Deprecation: true and Sunset: <RFC-1123 date>. After sunset date, requests to that version return HTTP 410 Gone. In Phase 1, /v1 is not deprecated but the mechanism must exist. Config: api.versions.v1.deprecated=false, api.versions.v1.sunset-date (empty = no header). The VersionHeaderFilter adds headers; a VersionEnforcementFilter returns 410 if today > sunset date. | • Create ApiVersionProperties.java at services/api-gateway/src/main/java/com/gme/pay/gateway/config/ApiVersionProperties.java: @ConfigurationProperties('api.versions'), Map<String,VersionConfig> where VersionConfig has boolean deprecated, LocalDate sunsetDate (nullable) • Create VersionEnforcementFilter.java: extract version from first path segment (/v1 -> '1'), look up config, if sunsetDate != null and LocalDate.now().isAfter(sunsetDate) return 410 Gone with body {error:{code:'GONE',message:'API version /v1 retired on <date>. Upgrade to /v2.',request_id:...}} • Create VersionHeaderFilter.java: if deprecated=true add response headers Deprecation: true and Sunset: <RFC-1123 format of sunsetDate> • Write unit test: sunsetDate in past -> 410, sunsetDate in future -> pass + Deprecation header, no sunsetDate -> no headers, v1 default (deprecated=false) -> no headers | services/api-gateway/src/main/java/com/gme/pay/gateway/filter/VersionEnforcementFilter.java, VersionHeaderFilter.java, config/ApiVersionProperties.java | • api.versions.v1.deprecated=false (default): no Deprecation or Sunset headers emitted • api.versions.v1.deprecated=true + sunset-date=2026-10-31: response includes Deprecation: true and Sunset: Sat, 31 Oct 2026 23:59:59 GMT • Path /v1/rates with past sunset-date returns 410 Gone with error code GONE • Unit test covers past/future/null sunset-date • Sunset header format is RFC-1123 per API-05 section 11.3 | 30 | 8.1-T10 | BE | API-05
8.1-T15 | api-gateway | 8.1 | 8. Partner (Northbound) API | API gateway & versioning framework | 1 | Implement mTLS optional onboarding configuration at gateway | API-05 section 3.4: partners may request mTLS. GME provisions a client cert per partner. When mTLS active, X-Signature is still required. mTLS is configured at gateway level (no endpoint changes). Spring Cloud Gateway uses Netty; server.ssl.client-auth=WANT allows optional client cert. A dedicated Spring profile 'mtls' enables it. Client cert Subject DN is forwarded as X-Client-Cert-DN header for downstream audit. | • Create application-mtls.yml at services/api-gateway/src/main/resources/application-mtls.yml with server.ssl.enabled=true, server.ssl.client-auth=WANT, server.ssl.key-store=${GATEWAY_KEYSTORE_PATH}, server.ssl.trust-store=${GATEWAY_TRUSTSTORE_PATH} • Create MtlsCertFilter.java at services/api-gateway/src/main/java/com/gme/pay/gateway/filter/MtlsCertFilter.java: if client cert present in SslInfo, extract Subject CN and add X-Client-Cert-DN header to downstream request • No certificate-to-partner mapping in this ticket; mapping validated by IpAllowlistFilter extension (future) • Ensure without mtls profile gateway starts normally with plain TLS (or no TLS in local dev) • Write test: with mtls profile and test self-signed cert, X-Client-Cert-DN header is set; without cert the request still proceeds (WANT not NEED) | services/api-gateway/src/main/resources/application-mtls.yml and services/api-gateway/src/main/java/com/gme/pay/gateway/filter/MtlsCertFilter.java | • With mtls profile: request without client cert is accepted (WANT behaviour) • With mtls profile: request with valid cert adds X-Client-Cert-DN header • Without mtls profile: gateway starts without SSL config (local dev mode) • GATEWAY_KEYSTORE_PATH and GATEWAY_TRUSTSTORE_PATH env vars control cert paths • No cert paths or secrets hard-coded in code or application-mtls.yml | 40 | 8.1-T01 | BE | API-05
8.1-T16 | api-gateway | 8.1 | 8. Partner (Northbound) API | API gateway & versioning framework | 1 | Add OpenTelemetry tracing instrumentation to gateway | STACK.md requires OpenTelemetry traces -> Jaeger. The gateway is the trace origin for all partner requests. Each request span must carry attributes: request_id, partner_id, http.method, http.route, http.status_code. W3C traceparent/tracestate headers propagate trace context to downstream services. OTEL_EXPORTER_OTLP_ENDPOINT env var configures exporter endpoint (default http://localhost:4317). | • Add io.opentelemetry.instrumentation:opentelemetry-spring-boot-starter to services/api-gateway/build.gradle • Set otel.service.name=api-gateway and otel.exporter.otlp.endpoint=${OTEL_EXPORTER_OTLP_ENDPOINT:http://localhost:4317} in application.yml • Create TracingContextFilter.java at services/api-gateway/src/main/java/com/gme/pay/gateway/filter/TracingContextFilter.java implementing GlobalFilter: add span attributes Span.current().setAttribute('request_id', ...) and setAttribute('partner_id', exchange.getAttribute('partner_id')) • Verify W3C traceparent header is forwarded to downstream (auto-propagation by Spring OTel) • Write unit test asserting TracingContextFilter sets request_id and partner_id as span attributes using OpenTelemetry Testing SDK | services/api-gateway/src/main/java/com/gme/pay/gateway/filter/TracingContextFilter.java and updated build.gradle | • Span attributes include request_id, partner_id after filter executes (unit test) • traceparent header is present on forwarded downstream request • OTEL_EXPORTER_OTLP_ENDPOINT overrides default endpoint • Span service.name tag is api-gateway • ./gradlew :services:api-gateway:test passes | 35 | 8.1-T03 | BE | API-05
8.1-T17 | api-gateway | 8.1 | 8. Partner (Northbound) API | API gateway & versioning framework | 1 | Implement structured JSON access logging filter | SAD-02 requires structured JSON logs with correlation fields: request_id, partner_id, scheme_id, http.method, path, status, latency_ms. The gateway access log is the primary audit trail for all partner API calls. Uses SLF4J + Logback with logstash-logback-encoder. Log level: INFO for 2xx, WARN for 4xx, ERROR for 5xx. Partner_id is stored in Reactor context after authentication. | • Add net.logstash.logback:logstash-logback-encoder to services/api-gateway/build.gradle • Create logback-spring.xml at services/api-gateway/src/main/resources/logback-spring.xml: use JsonEncoder for non-local Spring profiles, ConsoleAppender for local • Create AccessLogFilter.java at services/api-gateway/src/main/java/com/gme/pay/gateway/filter/AccessLogFilter.java implementing GlobalFilter, Ordered(Ordered.LOWEST_PRECEDENCE): record startTime, after response complete emit log with MDC fields: request_id, partner_id, method, path, status_code, latency_ms • Use MDCContext from Reactor Context to propagate partner_id through reactive chain • Write unit test asserting MDC fields are populated and log level matches response status | services/api-gateway/src/main/java/com/gme/pay/gateway/filter/AccessLogFilter.java and src/main/resources/logback-spring.xml | • Log entry contains fields: request_id, partner_id, method, path, status_code, latency_ms • Log level is INFO for 200, WARN for 401, ERROR for 500 • JSON log format active on non-local Spring profile (logstash encoder) • partner_id is non-null after successful authentication • Unit test verifies MDC field population and log level | 35 | 8.1-T03, 8.1-T16 | BE | API-05
8.1-T18 | api-gateway | 8.1 | 8. Partner (Northbound) API | API gateway & versioning framework | 1 | Implement PartnerCredentialService with PostgreSQL + Redis cache | Gateway filters (HMAC T05, IP allowlist T11, rate limit T07) need to resolve partner credentials by X-API-Key: partner_id, api_secret_hmac_key, ip_cidr_ranges, partner_type (LOCAL¦OVERSEAS), rate_quote_ttl_seconds. Credentials live in PostgreSQL config_registry database (table partner_credentials, migration in T19). Redis caches responses (key: partner_cred:{apiKey}, TTL 60s). Uses Spring Data R2DBC for reactive DB access. | • Create PartnerCredentials.java record at services/api-gateway/src/main/java/com/gme/pay/gateway/partner/PartnerCredentials.java: String partnerId, String apiKeyHash, String apiSecretHmacKey, List<String> ipCidrRanges, PartnerType type, int rateQuoteTtlSeconds; enum PartnerType {LOCAL, OVERSEAS} • Create PartnerCredentialService.java interface: Mono<PartnerCredentials> findByApiKey(String apiKey) • Implement PostgresPartnerCredentialService.java using DatabaseClient (R2DBC) querying partner_credentials table in config-registry datasource; map columns to record • Wrap with Redis cache: on miss query DB, on hit return cached; TTL 60s; key=partner_cred:{apiKey} • Write Testcontainers PostgreSQL 16 integration test: insert row, call findByApiKey, assert all fields, second call within 60s served from Redis (mock DB client verifies 0 queries on 2nd call) | services/api-gateway/src/main/java/com/gme/pay/gateway/partner/PartnerCredentialService.java, PartnerCredentials.java, PostgresPartnerCredentialService.java | • findByApiKey returns correct PartnerCredentials from PostgreSQL (Testcontainers test) • Unknown API key returns Mono.empty() • Second call within 60s served from Redis cache with 0 DB queries • PartnerCredentials.type enum is LOCAL or OVERSEAS • Testcontainers test inserts row with ip_cidr_ranges={'192.168.1.0/24'} and asserts list deserialized correctly | 45 | 8.1-T05, 8.1-T11 | BE | API-05
8.1-T19 | api-gateway | 8.1 | 8. Partner (Northbound) API | API gateway & versioning framework | 1 | Write Flyway migration V001 for partner_credentials table in config-registry | PartnerCredentialService (T18) reads from PostgreSQL table partner_credentials in the config-registry service database. Flyway manages migrations for services/config-registry. Fields: id UUID PK default gen_random_uuid(), partner_id VARCHAR(64) UNIQUE NOT NULL, api_key VARCHAR(128) UNIQUE NOT NULL, api_secret_bcrypt VARCHAR(256) NOT NULL (bcrypt cost >= 12 per API-05 section 3.1), ip_cidr_ranges TEXT[] nullable, partner_type VARCHAR(16) NOT NULL CHECK IN ('LOCAL','OVERSEAS'), rate_quote_ttl_seconds INTEGER NOT NULL DEFAULT 300, webhook_url VARCHAR(512), created_at TIMESTAMPTZ NOT NULL DEFAULT NOW(), updated_at TIMESTAMPTZ NOT NULL DEFAULT NOW(). | • Identify Flyway migration directory: services/config-registry/src/main/resources/db/migration/ • Create V001__create_partner_credentials.sql with CREATE TABLE partner_credentials (all columns above) • Add UNIQUE INDEX idx_partner_credentials_api_key ON partner_credentials(api_key) • Add partial index idx_partner_credentials_partner_id ON partner_credentials(partner_id) WHERE partner_id IS NOT NULL • Write Testcontainers migration test PartnerCredentialsMigrationTest.java: apply migration to fresh PostgreSQL 16, assert table exists with all columns, insert row, verify UNIQUE and CHECK constraints | services/config-registry/src/main/resources/db/migration/V001__create_partner_credentials.sql | • Migration applies cleanly to fresh PostgreSQL 16 (Testcontainers) • Table has all 10 columns including webhook_url and ip_cidr_ranges TEXT[] • UNIQUE constraint on api_key: insert duplicate key fails with unique violation • partner_type CHECK rejects value 'ADMIN' (only LOCAL and OVERSEAS allowed) • rate_quote_ttl_seconds DEFAULT is 300 (insert row without specifying it, verify default) | 30 |  | BE | API-05
8.1-T20 | api-gateway | 8.1 | 8. Partner (Northbound) API | API gateway & versioning framework | 1 | Configure all 7 API-05 endpoint routes with full security filter chain | API-05 section 4.1 defines 7 endpoints: POST /v1/rates->lb://rate-fx, POST /v1/payments->lb://payment-executor, POST /v1/payments/cpm/generate->lb://payment-executor, GET /v1/payments/{id}->lb://payment-executor, POST /v1/payments/{id}/cancel->lb://payment-executor, GET /v1/merchants/{qr}->lb://merchant-qr-data, GET /v1/balance->lb://prefunding-balance. Each route applies the full filter chain. Connect timeout 2s, response timeout 10s. Resilience4j CircuitBreaker fallback: 503 SERVICE_UNAVAILABLE. | • Extend GatewayRoutingConfig.java with all 7 routes using RouteLocatorBuilder fluent DSL • Apply per-route filters: TimestampValidationFilter, HmacSignatureFilter, ReplayProtectionFilter, per-endpoint RedisRateLimiter, IdempotencyKeyFilter (POST only), ContentTypeFilter (POST only), VersionEnforcementFilter • Configure connect timeout 2s and response timeout 10s via HttpClient metadata in route config • Add CircuitBreaker GatewayFilter per route using Resilience4j: fallback to inline response 503 SERVICE_UNAVAILABLE • Write WireMock integration test: stub lb://rate-fx, verify POST /v1/rates with valid signed request reaches WireMock stub and X-Gateway-Version: v1 is present | Updated services/api-gateway/src/main/java/com/gme/pay/gateway/config/GatewayRoutingConfig.java with all 7 routes and circuit breakers | • POST /v1/rates routes to lb://rate-fx (WireMock test with signed request) • GET /v1/balance routes to lb://prefunding-balance • Circuit breaker opens after 5 consecutive 503s and returns 503 SERVICE_UNAVAILABLE without hitting downstream • Response timeout of 10s: WireMock stub with 11s delay triggers timeout and returns 504 or 503 • All 7 route IDs are unique and non-overlapping (no accidental catch-all overlap) | 45 | 8.1-T07, 8.1-T08, 8.1-T09, 8.1-T10, 8.1-T11, 8.1-T14 | BE | API-05
8.1-T21 | api-gateway | 8.1 | 8. Partner (Northbound) API | API gateway & versioning framework | 1 | Define filter execution order and write filter chain order unit test | The gateway has multiple GlobalFilters that must execute in a defined order to avoid security bypass: (1) RequestIdFilter, (2) IpAllowlistFilter, (3) TimestampValidationFilter, (4) HmacSignatureFilter, (5) ReplayProtectionFilter, (6) RateLimitResponseFilter, (7) IdempotencyKeyFilter, (8) ContentTypeFilter, (9) VersionEnforcementFilter, (10) VersionHeaderFilter, (11) TracingContextFilter, (12) AccessLogFilter. Wrong order can let replayed requests bypass signature check. | • Verify each filter implements Ordered and returns a unique getOrder() value matching the priority list above • Create FilterOrderTest.java at services/api-gateway/src/test/java/com/gme/pay/gateway/FilterOrderTest.java • Assert each filter bean's getOrder() equals expected value using @SpringBootTest and ApplicationContext • Write scenario test: mock TimestampValidationFilter to return 401; assert HmacSignatureFilter (higher order number) is NOT invoked (verify with mock spy) • Write scenario test: valid timestamp + invalid signature -> HmacSignatureFilter runs and returns 401 before ReplayProtectionFilter | services/api-gateway/src/test/java/com/gme/pay/gateway/FilterOrderTest.java | • Each filter's getOrder() is unique and matches specified priority • IpAllowlistFilter order < HmacSignatureFilter order (IP checked before sig) • TimestampValidationFilter order < HmacSignatureFilter order • ReplayProtectionFilter order > HmacSignatureFilter order (replay check after sig passes) • Scenario test confirms TimestampValidationFilter short-circuits chain (HMAC filter not invoked) | 35 | 8.1-T04, 8.1-T05, 8.1-T06, 8.1-T07, 8.1-T08, 8.1-T09, 8.1-T10, 8.1-T11 | BE | API-05
8.1-T22 | api-gateway | 8.1 | 8. Partner (Northbound) API | API gateway & versioning framework | 1 | Write gateway security integration test suite (Testcontainers + WireMock) | All gateway security filters must be integration-tested together against real Redis (Testcontainers) and WireMock downstream. Covers API-05 certification checklist items: C-15 (invalid signature -> 401), C-16 (idempotent retry same key+body), replay dedup, rate limit breach, missing idempotency key. Test partner: api_key=pk_test_abc, api_secret=sk_test_xyz, type=OVERSEAS, no IP allowlist — loaded via test PartnerCredentialService stub. | • Create GatewaySecurityIntegrationTest.java at services/api-gateway/src/test/java/com/gme/pay/gateway/GatewaySecurityIntegrationTest.java using @SpringBootTest(webEnvironment=RANDOM_PORT) • Use @Testcontainers with Redis GenericContainer and WireMock for lb://rate-fx stub • Test C-15: POST /v1/rates with invalid X-Signature -> 401 INVALID_SIGNATURE, error envelope correct • Test replay: identical (partner_id, X-Signature) on two sequential requests -> second returns 401 INVALID_SIGNATURE • Test rate limit: send 21 POST /v1/rates within 1s -> 21st returns 429 RATE_LIMITED with Retry-After • Test missing idempotency key: POST /v1/rates without Idempotency-Key -> 400 MISSING_IDEMPOTENCY_KEY • Test valid full flow: correctly signed POST /v1/rates reaches WireMock stub and returns stubbed 200 response | services/api-gateway/src/test/java/com/gme/pay/gateway/GatewaySecurityIntegrationTest.java | • C-15: invalid signature -> 401 INVALID_SIGNATURE (test passes in CI) • Replay: 2nd identical signature within 10min -> 401 (test passes) • Rate limit: 21st request -> 429 with Retry-After (test passes) • Missing Idempotency-Key -> 400 MISSING_IDEMPOTENCY_KEY (test passes) • Valid signed request reaches WireMock stub and response is proxied correctly (test passes) | 50 | 8.1-T20, 8.1-T21 | BE | API-05
8.1-T23 | api-gateway | 8.1 | 8. Partner (Northbound) API | API gateway & versioning framework | 1 | Add Prometheus metrics filter for per-route request telemetry | STACK.md requires Prometheus + Grafana for metrics. The gateway must expose per-route request metrics: http.server.requests counter (by route_id, method, status), gateway.request.duration histogram (by route_id, method). Custom tag partner_id enables per-partner SLA monitoring. Micrometer auto-instruments Spring WebFlux but a custom GatewayMetricsFilter adds the partner_id and route_id tags that Micrometer's auto-instrumentation does not capture. | • Confirm micrometer-registry-prometheus on classpath (added in T01) • Configure management.metrics.tags.application=api-gateway in application.yml • Create GatewayMetricsFilter.java at services/api-gateway/src/main/java/com/gme/pay/gateway/filter/GatewayMetricsFilter.java: record Timer with tags route_id, method, status, partner_id using MeterRegistry • Use Timer.builder('gateway.request.duration').tags(...).register(meterRegistry).record(duration) • Write unit test asserting Timer is registered with expected tag values after a mock exchange is processed | services/api-gateway/src/main/java/com/gme/pay/gateway/filter/GatewayMetricsFilter.java | • GET /actuator/prometheus returns gateway_request_duration_seconds histogram metric • Metric has tags: route_id, method, status, partner_id • p99 latency observable via histogram_quantile in Prometheus • Unit test asserts timer.record called with correct tags • Metric names follow snake_case Prometheus conventions | 30 | 8.1-T17 | BE | API-05
8.1-T24 | api-gateway | 8.1 | 8. Partner (Northbound) API | API gateway & versioning framework | 1 | Define gateway-level conventions in openapi/partner-api.yaml (skeleton) | STACK.md requires contract tests against openapi/partner-api.yaml. This skeleton covers gateway conventions only: common request headers (X-API-Key, X-Timestamp, X-Signature, Idempotency-Key, Content-Type), common response headers (X-Request-ID, X-RateLimit-Limit, X-RateLimit-Remaining, X-RateLimit-Reset, Deprecation, Sunset), and the error envelope schema matching lib-errors ApiErrorResponse. Endpoint paths are added by subsequent WBS tickets. | • Create openapi/partner-api.yaml at repo root with openapi: 3.1.0, info: {title: 'GMEPay+ Partner API', version: '1.0.0'} • Add servers: [{url: 'https://api-sandbox.gmepayplus.com', description: Sandbox}, {url: 'https://api.gmepayplus.com', description: Production}] • Define components.securitySchemes: ApiKeyAuth (apiKey, in: header, name: X-API-Key), HmacSignature (apiKey, in: header, name: X-Signature) • Define components.headers: X-Request-ID (string), X-RateLimit-Limit, X-RateLimit-Remaining, X-RateLimit-Reset (integer), Deprecation (boolean), Sunset (string) • Define components.schemas: ApiErrorDetail {field, issue}, ApiError {code, message, request_id, details[]}, ApiErrorResponse {error: ApiError}, PaginationMeta {total_count, has_more, next_cursor, prev_cursor}; run redocly lint or swagger-parser to confirm no errors | openapi/partner-api.yaml (conventions skeleton, no endpoint paths yet) | • openapi/partner-api.yaml passes redocly lint or swagger-parser validation with zero errors • components.securitySchemes includes ApiKeyAuth and HmacSignature • ApiError schema shape matches API-05 section 8.1: {code, message, request_id, details[{field,issue}]} • PaginationMeta fields are total_count, has_more, next_cursor, prev_cursor (snake_case) • All 6 common response headers are defined in components.headers | 40 | 8.1-T12, 8.1-T13 | BE | API-05
8.1-T25 | api-gateway | 8.1 | 8. Partner (Northbound) API | API gateway & versioning framework | 1 | Write health and readiness probes for gateway with config DB indicator | Kubernetes readiness probe checks that Redis and PostgreSQL config DB are reachable before gateway accepts traffic. Spring Boot Actuator with probes.enabled=true exposes /actuator/health/liveness and /actuator/health/readiness. Liveness: JVM alive. Readiness: Redis + PostgreSQL config DB. A custom PartnerConfigHealthIndicator executes SELECT 1 on the config R2DBC datasource. | • Set management.endpoint.health.probes.enabled=true and management.health.redis.enabled=true in application.yml • Create PartnerConfigHealthIndicator.java at services/api-gateway/src/main/java/com/gme/pay/gateway/health/PartnerConfigHealthIndicator.java implementing ReactiveHealthIndicator: execute DatabaseClient.sql('SELECT 1').fetch().rowsUpdated(), return Health.up() on success or Health.down(exception) on error • Register as @Component with @ConditionalOnProperty allowing it to be disabled in tests • Ensure /actuator/health, /actuator/health/liveness, /actuator/health/readiness paths are not behind security filter chain • Write unit test: DB reachable -> Health.UP, DB throws exception -> Health.DOWN with exception detail | services/api-gateway/src/main/java/com/gme/pay/gateway/health/PartnerConfigHealthIndicator.java | • GET /actuator/health returns {status:UP} when Redis and DB are reachable • GET /actuator/health/readiness returns {status:OUT_OF_SERVICE} when Redis is down (Testcontainers: kill Redis) • GET /actuator/health/liveness returns {status:UP} regardless of Redis/DB state • PartnerConfigHealthIndicator returns Health.DOWN when DB unreachable (unit test with mock throwing exception) • Health endpoints accessible without X-API-Key or authentication headers | 25 | 8.1-T01, 8.1-T18 | BE | API-05
8.1-T26 | api-gateway | 8.1 | 8. Partner (Northbound) API | API gateway & versioning framework | 1 | Write contract tests for gateway against openapi/partner-api.yaml | STACK.md requires contract tests against openapi/partner-api.yaml. The gateway enforces the API contract at entry: required headers (X-API-Key, X-Timestamp, X-Signature, Content-Type, Idempotency-Key on POST), response envelope shape ({error:{code,message,request_id,details}}), and standard response headers (X-Request-ID, X-RateLimit-*). Spring REST Docs or a swagger-request-validator can assert request/response shapes against the OpenAPI spec. | • Add com.atlassian.oai:swagger-request-validator-restassured (or equivalent) to services/api-gateway/build.gradle (test scope) • Create GatewayContractTest.java at services/api-gateway/src/test/java/com/gme/pay/gateway/GatewayContractTest.java using @SpringBootTest + RestAssured • Validate that a missing X-Signature request returns 401 with body matching ApiErrorResponse schema in openapi/partner-api.yaml • Validate that a missing Idempotency-Key POST returns 400 with body matching ApiErrorResponse schema • Validate that a valid request reaching WireMock downstream returns X-Request-ID and X-RateLimit-* headers matching declared response headers in partner-api.yaml • Run contract tests as part of ./gradlew :services:api-gateway:test | services/api-gateway/src/test/java/com/gme/pay/gateway/GatewayContractTest.java | • Missing X-Signature: 401 response body validates against openapi/partner-api.yaml ApiErrorResponse schema • Missing Idempotency-Key: 400 response body validates against schema • Valid request: X-Request-ID header present and matches declared header in partner-api.yaml • Valid request: X-RateLimit-Limit header present • ./gradlew :services:api-gateway:test passes with all contract tests green | 40 | 8.1-T22, 8.1-T24 | BE | API-05
8.2-T01 | auth-identity | 8.2 | 8. Partner (Northbound) API | Auth: API key + HMAC signing | 1 | Flyway migration: partner_credential table in auth-identity service | WBS 8.2 delivers the Spring Cloud Gateway HMAC-SHA256 auth filter. Before any filter logic, the DB schema must exist. The partner_credential table (SEC-09 §2.3, API-05 §3.1, DAT-03 §4.4) holds: id BIGINT GENERATED ALWAYS AS IDENTITY PK, partner_id BIGINT FK->partner ON DELETE RESTRICT, api_key VARCHAR(64) UNIQUE NOT NULL, api_secret_hash VARCHAR(128) NOT NULL (bcrypt cost>=12 of api_secret, plaintext shown once then discarded), is_active BOOLEAN NOT NULL DEFAULT TRUE, expires_at TIMESTAMPTZ NULL (NULL=no expiry), created_at TIMESTAMPTZ NOT NULL DEFAULT NOW(), updated_at TIMESTAMPTZ NOT NULL, created_by VARCHAR(120), updated_by VARCHAR(120). Partial unique index on (partner_id) WHERE is_active=TRUE enforces one-active-credential-per-partner. HMAC secret is NOT stored here; it lives in Vault (see 8.2-T03). Hard deletes prohibited on this table. | • Determine next Flyway version number in services/auth-identity/src/main/resources/db/migration/ • Create V{n}__partner_credential.sql with CREATE TABLE partner_credential as specified • Add UNIQUE constraint on api_key and partial unique index: CREATE UNIQUE INDEX uidx_partner_credential_active ON partner_credential (partner_id) WHERE is_active = TRUE • Add FK: partner_id BIGINT REFERENCES partner(id) ON DELETE RESTRICT • Add SQL header comment citing API-05 §3.1, SEC-09 §2.3, DAT-03 §4.4 • Run ./gradlew :services:auth-identity:flywayMigrate against local PostgreSQL on port 5433 | services/auth-identity/src/main/resources/db/migration/V{n}__partner_credential.sql | • Migration applies cleanly on a fresh schema (flywayInfo shows success) • UNIQUE index on api_key prevents duplicate keys (INSERT with same api_key raises unique violation) • Partial unique index allows two is_active=FALSE rows for same partner but rejects second is_active=TRUE row • FK on partner_id: INSERT with non-existent partner_id raises foreign key violation • api_secret_hash is VARCHAR(128) not TEXT • No column named hmac_secret or api_secret (secret not stored in DB) | 25 |  | BE | API-05, SEC-09
8.2-T02 | auth-identity | 8.2 | 8. Partner (Northbound) API | Auth: API key + HMAC signing | 1 | PartnerCredential JPA entity and Spring Data repository in auth-identity module | The auth-identity service (services/auth-identity, Spring Boot 3.x, Java 21) needs a JPA entity mapping to the partner_credential table from 8.2-T01. The entity must expose findByApiKeyAndIsActiveTrue(String apiKey) used by the HMAC filter to look up the hashed secret. Uses lib-persistence common JPA utilities. No plaintext secret is ever stored or returned; only api_secret_hash. api_secret_hash column stores a BCrypt hash (starts with $2a$ or $2b$) used only for identity confirmation at credential generation, not for HMAC signing (which uses the Vault-stored hmac_secret). | • In services/auth-identity/src/main/java/com/gme/pay/auth/domain/ create PartnerCredential.java as @Entity @Table(name=partner_credential) with all columns mapped • Annotate id with @Id @GeneratedValue(strategy=GenerationType.IDENTITY) • Create PartnerCredentialRepository.java extending JpaRepository<PartnerCredential,Long> with Optional<PartnerCredential> findByApiKeyAndIsActiveTrue(String apiKey) • Add @Transactional(readOnly=true) on the repository query method • Ensure no getter is named getApiSecretPlaintext (the only secret field is api_secret_hash) | services/auth-identity/src/main/java/com/gme/pay/auth/domain/PartnerCredential.java and PartnerCredentialRepository.java | • findByApiKeyAndIsActiveTrue returns non-empty Optional for a known active api_key • findByApiKeyAndIsActiveTrue returns empty Optional for unknown api_key or inactive credential • No field or getter named api_secret exists on the entity (only api_secret_hash) • Spring Data generates SELECT ... WHERE api_key=? AND is_active=TRUE (verify via Hibernate SQL log in test) • ./gradlew :services:auth-identity:compileJava succeeds with no unmapped column warnings | 25 | 8.2-T01 | BE | API-05, SEC-09
8.2-T03 | auth-identity | 8.2 | 8. Partner (Northbound) API | Auth: API key + HMAC signing | 1 | PartnerCredentialService: Spring Cloud Vault integration for HMAC secret retrieval | Per SEC-09 §2.3 and §9.1, the partner HMAC signing secret (distinct from the bcrypt-hashed api_secret) is stored encrypted in HashiCorp Vault at path secret/data/partners/{partner_id}/hmac_secret. The auth-identity service uses Spring Cloud Vault (spring-cloud-vault-config, spring-vault-core) to read this secret at request time. spring.cloud.vault.uri and spring.cloud.vault.token are injected via environment variables at runtime (never hardcoded). A Caffeine cache with 5-minute TTL reduces Vault round trips. Throws CredentialNotFoundException (lib-errors) if path absent. | • Add spring-cloud-vault-config and spring-vault-core to services/auth-identity/build.gradle dependencies • Create PartnerCredentialService.java in com.gme.pay.auth.service annotated @Service • Inject VaultTemplate and implement String getHmacSecret(Long partnerId) that calls vaultTemplate.read(secret/data/partners/{partnerId}/hmac_secret) and returns the hmac_secret field • Add @Cacheable(value=hmacSecretCache, key=#partnerId) and configure a CacheManager with Caffeine TTL=300 seconds • Throw CredentialNotFoundException from lib-errors if Vault returns null or path not found • Ensure the returned secret is never written to any log statement | services/auth-identity/src/main/java/com/gme/pay/auth/service/PartnerCredentialService.java | • getHmacSecret(knownPartnerId) returns non-null non-empty string when Vault is populated at path secret/data/partners/{id}/hmac_secret • getHmacSecret(unknownPartnerId) throws CredentialNotFoundException • Vault path pattern is exactly secret/data/partners/{partnerId}/hmac_secret (kv-v2 format) • HMAC secret is never referenced in any log.debug/info/error call (code review check) • Cache hit on second call: Vault is not called a second time within 5 minutes (mock Vault to verify zero second call) | 35 | 8.2-T02 | BE | API-05, SEC-09
8.2-T04 | auth-identity | 8.2 | 8. Partner (Northbound) API | Auth: API key + HMAC signing | 1 | HmacSignatureVerifier: pure Java HMAC-SHA256 canonical-string utility in lib-security | Per SEC-09 §3.3 and API-05 §3.2, the canonical request string is: HTTP_METHOD + newline + PATH_WITH_QUERY + newline + X-Timestamp + newline + SHA256_HEX_OF_BODY (4 parts joined by literal backslash-n). The HMAC signature = HMAC-SHA256(canonical_string, hmac_secret) hex-encoded. X-Timestamp is ISO-8601 UTC millisecond precision. Body hash uses SHA-256 of raw request bytes; empty body (GET) uses SHA-256 of empty byte array = e3b0c44298fc1c149afbf4c8996fb92427ae41e4649b934ca495991b7852b855. Lives in lib/lib-security as a pure Java utility (no Spring dependency) so both api-gateway and future verifiers can reuse it. | • Create lib/lib-security/src/main/java/com/gme/pay/security/HmacSignatureVerifier.java • Implement static String computeBodyHash(byte[] body) using MessageDigest.getInstance(SHA-256), hex-encoded lowercase • Implement static String buildCanonicalString(String method, String pathWithQuery, String timestamp, String bodyHash) joining with literal newline char • Implement static String computeSignature(String canonicalString, String hmacSecret) using Mac.getInstance(HmacSHA256), hex-encoded lowercase • Implement static boolean verifySignature(String expected, String canonicalString, String hmacSecret) using MessageDigest.isEqual to prevent timing attacks | lib/lib-security/src/main/java/com/gme/pay/security/HmacSignatureVerifier.java | • computeBodyHash(new byte[0]) equals e3b0c44298fc1c149afbf4c8996fb92427ae41e4649b934ca495991b7852b855 • computeSignature for a known input matches a pre-computed HMAC-SHA256 reference value • verifySignature uses MessageDigest.isEqual not String.equals (constant-time comparison) • buildCanonicalString joins exactly 4 parts with single newline character between each • Module :lib:lib-security compiles with no imports of Spring Framework classes • ./gradlew :lib:lib-security:test passes | 30 |  | BE | API-05, SEC-09
8.2-T05 | auth-identity | 8.2 | 8. Partner (Northbound) API | Auth: API key + HMAC signing | 1 | TimestampValidator and RedisNonceStore: replay-protection utilities in lib-security | Per SEC-09 §3.3 and API-05 §3.6, two replay guards: (1) ¦server_now - X-Timestamp¦ > 300 seconds -> reject HTTP 401 TIMESTAMP_DRIFT; (2) seen (partner_id, X-Nonce) within 600 seconds -> reject HTTP 401 REPLAY_DETECTED. X-Timestamp in API-05 is ISO-8601 UTC millisecond precision; SEC-09 also mentions Unix epoch integer format. Both must be parsed. Nonces stored in Redis with TTL=600s using key nonce:{partnerId}:{nonce} and SET NX EX (atomic check-and-set). NonceStore is an interface; RedisNonceStore is the ReactiveRedisTemplate implementation. Both classes go in lib/lib-security. | • Create TimestampValidator.java with static boolean isWithinWindow(String xTimestamp, Instant serverNow, long windowSeconds): parse ISO-8601 if string contains T, otherwise parse as Unix epoch Long; compute absolute difference in seconds • Create NonceStore.java interface with Mono<Boolean> checkAndSetNonce(String partnerId, String nonce, Duration ttl) • Create RedisNonceStore.java implementing NonceStore using ReactiveRedisTemplate<String,String>; key = nonce:{partnerId}:{nonce}; use setIfAbsent(key, 1, Duration) which maps to SET NX EX • Throw TimestampDriftException (extends AuthException from lib-errors) from filter when window exceeded • Throw ReplayDetectedException (extends AuthException from lib-errors) when checkAndSetNonce returns false | lib/lib-security/src/main/java/com/gme/pay/security/TimestampValidator.java and NonceStore.java and RedisNonceStore.java | • isWithinWindow(timestamp=now-300s, now, 300) returns true (boundary inclusive) • isWithinWindow(timestamp=now-301s, now, 300) returns false • isWithinWindow(timestamp=now+301s, now, 300) returns false (future timestamps also rejected) • Unix epoch string (e.g. 1749034260) parses correctly without exception • checkAndSetNonce returns Mono(true) on first call, Mono(false) on second call with same partner+nonce • Redis key nonce:{partnerId}:{nonce} TTL is 600 seconds after first call | 35 | 8.2-T04 | BE | API-05, SEC-09
8.2-T06 | auth-identity | 8.2 | 8. Partner (Northbound) API | Auth: API key + HMAC signing | 1 | PartnerResolver: WebClient call from api-gateway to auth-identity to resolve api_key | The Spring Cloud Gateway filter (services/api-gateway) must resolve partner_id and hmac_secret from the X-API-Key header before verifying the HMAC. The auth-identity service exposes POST /internal/v1/credentials/resolve accepting {apiKey:String} and returning {partnerId:Long, hmacSecret:String, isActive:Boolean} over the internal mTLS network (Application Zone per SEC-09 §2.1). The Gateway calls this via WebClient with Resilience4j CircuitBreaker fallback. DTO classes live in lib-api-contracts. The hmac_secret in the response body is the raw Vault-retrieved secret (transmitted only on internal mTLS network). | • Add CredentialResolveRequest {String apiKey} and CredentialResolveResponse {Long partnerId, String hmacSecret, boolean isActive} to lib/lib-api-contracts/src/main/java/com/gme/pay/contracts/auth/ • In services/auth-identity create @RestController CredentialResolveController.java at POST /internal/v1/credentials/resolve; call PartnerCredentialRepository.findByApiKeyAndIsActiveTrue then PartnerCredentialService.getHmacSecret; return 200 or 401 • In services/api-gateway create PartnerResolver.java @Component with WebClient; implement Mono<CredentialResolveResponse> resolve(String apiKey) • Add @CircuitBreaker(name=authIdentity, fallbackMethod=resolveFallback) returning Mono.empty() on fallback • Configure WebClient base-url from property auth-identity.base-url (injected via environment variable AUTH_IDENTITY_BASE_URL) | services/auth-identity/src/main/java/com/gme/pay/auth/web/CredentialResolveController.java and services/api-gateway/src/main/java/com/gme/pay/gateway/auth/PartnerResolver.java | • POST /internal/v1/credentials/resolve with valid active api_key returns 200 with correct partnerId and non-null hmacSecret • POST with unknown or inactive api_key returns 401 • PartnerResolver returns Mono.empty() when auth-identity is unreachable (circuit open or network error) • hmacSecret in response is the actual secret value not a vault path reference • Internal endpoint URL contains /internal/ prefix (not accessible from public network) | 40 | 8.2-T03 | BE | API-05, SEC-09
8.2-T07 | auth-identity | 8.2 | 8. Partner (Northbound) API | Auth: API key + HMAC signing | 1 | HmacAuthGatewayFilter: Spring Cloud Gateway GlobalFilter enforcing HMAC-SHA256 auth | The core WBS 8.2 deliverable: a Spring Cloud Gateway GlobalFilter (services/api-gateway) that enforces HMAC-SHA256 on every inbound partner request. Order=-10 (runs before routing). Per request: (1) extract X-API-Key, X-Timestamp, X-Signature, X-Nonce; (2) if any absent return 400 error.code=MISSING_REQUIRED_HEADER; (3) call PartnerResolver for {partnerId, hmacSecret}; (4) validate timestamp window 300s (401 TIMESTAMP_DRIFT); (5) check Redis nonce TTL=600s (401 REPLAY_DETECTED); (6) read body via DataBufferUtils.join, compute canonical = METHOD+newline+PATH_WITH_QUERY+newline+X-Timestamp+newline+SHA256_HEX(body), compare HMAC-SHA256 with X-Signature (401 INVALID_SIGNATURE); (7) mutate exchange to add X-Partner-ID header; (8) call chain.filter. All errors use lib-errors canonical shape {error:{code,message,request_id}}. X-Request-ID is generated and added to every response. | • Create HmacAuthGatewayFilter.java in services/api-gateway/src/main/java/com/gme/pay/gateway/filter/ implementing GlobalFilter and Ordered; getOrder() returns -10 • Inject PartnerResolver, TimestampValidator (from lib-security), NonceStore (RedisNonceStore), HmacSignatureVerifier (from lib-security) • Implement reactive filter(ServerWebExchange, GatewayFilterChain) that caches request body using ServerRequest.create then DataBufferUtils.join • On each auth failure return a JSON error response using ServerHttpResponse.writeWith; set Content-Type: application/json and X-Request-ID header • On success mutate ServerHttpRequest to add X-Partner-ID:{partnerId} and pass to chain.filter | services/api-gateway/src/main/java/com/gme/pay/gateway/filter/HmacAuthGatewayFilter.java | • Valid signed request passes through and downstream receives X-Partner-ID header • Missing X-API-Key returns HTTP 400 with error.code=MISSING_REQUIRED_HEADER • X-Timestamp older than 300 seconds returns HTTP 401 with error.code=TIMESTAMP_DRIFT • Replayed X-Nonce (same value within 600s) returns HTTP 401 with error.code=REPLAY_DETECTED • Tampered body (signature mismatch) returns HTTP 401 with error.code=INVALID_SIGNATURE • Unknown X-API-Key (PartnerResolver returns empty Mono) returns HTTP 401 with error.code=INVALID_API_KEY • Every response carries X-Request-ID header | 55 | 8.2-T05, 8.2-T06 | BE | API-05, SEC-09
8.2-T08 | auth-identity | 8.2 | 8. Partner (Northbound) API | Auth: API key + HMAC signing | 1 | IdempotencyGatewayFilter: Redis-backed 24-hour POST deduplication in api-gateway | Per API-05 §2.6 and §7.1, all POST requests must include Idempotency-Key header (UUID, 16-128 chars). Hub stores (partner_id, idempotency_key) -> (response_status, response_body, body_hash) in Redis for 24 hours (86400s TTL). Duplicate same key+same body hash: return cached response, skip downstream. Same key+different body hash: return 422 IDEMPOTENCY_BODY_MISMATCH. Key exists but response not yet written (in-flight): return 409 with header X-Idempotency-Status: in_flight. GET requests are skipped entirely. This is GlobalFilter order=-9 (after HMAC filter). Partner_id comes from X-Partner-ID header set by 8.2-T07. Redis key: idem:{partnerId}:{idempotencyKey}; value is a Redis hash with fields status (IN_FLIGHT¦COMPLETE), body_hash, response_status, response_body. | • Create IdempotencyGatewayFilter.java in services/api-gateway/src/main/java/com/gme/pay/gateway/filter/ implementing GlobalFilter with getOrder()=-9 • For GET/DELETE/PUT requests: call chain.filter immediately (no-op) • For POST: read Idempotency-Key header; if absent return 400 MISSING_IDEMPOTENCY_KEY • Compute SHA-256 hex of request body; check Redis hash at idem:{partnerId}:{key} • If absent: set status=IN_FLIGHT via hSet NX then EXPIRE 86400; call chain.filter; after response update Redis with status=COMPLETE, body_hash, response_status, response_body • If present status=IN_FLIGHT: return 409 X-Idempotency-Status: in_flight • If present status=COMPLETE: compare body_hash; match -> return cached response; mismatch -> return 422 IDEMPOTENCY_BODY_MISMATCH | services/api-gateway/src/main/java/com/gme/pay/gateway/filter/IdempotencyGatewayFilter.java | • GET requests: Redis is never queried (zero ReactiveRedisTemplate calls) • POST missing Idempotency-Key returns 400 with error.code=MISSING_IDEMPOTENCY_KEY • Second POST same key+same body returns cached response; downstream not called second time • Second POST same key+different body returns 422 with error.code=IDEMPOTENCY_BODY_MISMATCH • Concurrent in-flight key returns 409 with header X-Idempotency-Status: in_flight • Redis key idem:{partnerId}:{key} has TTL of 86400 seconds after creation | 55 | 8.2-T07 | BE | API-05, SEC-09
8.2-T09 | auth-identity | 8.2 | 8. Partner (Northbound) API | Auth: API key + HMAC signing | 1 | Flyway migration: audit_log table in auth-identity (append-only, JSONB detail) | Per SEC-09 §2 and non-repudiation objectives, credential generation, credential rotation, and auth failures must be permanently audit-logged. Table audit_log in the auth-identity schema: id BIGINT GENERATED ALWAYS AS IDENTITY, event_type VARCHAR(60) NOT NULL, actor VARCHAR(120) NOT NULL DEFAULT SYSTEM, partner_id BIGINT (nullable for system events), detail JSONB, created_at TIMESTAMPTZ NOT NULL DEFAULT NOW(). No updated_at (append-only by design; no UPDATE or DELETE permitted by application DB role). Add GIN index on detail for JSON queries. Also add index on (partner_id, created_at DESC). The audit log must survive partner deletion (no FK on partner_id). | • Determine next Flyway version in services/auth-identity/src/main/resources/db/migration/ • Create V{n}__audit_log.sql with CREATE TABLE audit_log as specified; id uses GENERATED ALWAYS AS IDENTITY • Add CREATE INDEX idx_audit_log_detail ON audit_log USING GIN (detail) • Add CREATE INDEX idx_audit_log_partner ON audit_log (partner_id, created_at DESC) WHERE partner_id IS NOT NULL • Add SQL comment: -- No FK on partner_id intentional: audit log outlives partners. Application DB role: INSERT only, no UPDATE/DELETE. • Run ./gradlew :services:auth-identity:flywayMigrate to verify | services/auth-identity/src/main/resources/db/migration/V{n}__audit_log.sql | • Migration applies cleanly on fresh schema • Table has no updated_at column (append-only) • GIN index on detail column is present (\d audit_log shows two indexes) • id uses GENERATED ALWAYS AS IDENTITY not SERIAL • partner_id is nullable (INSERT with partner_id=NULL succeeds for system events) • No FK constraint on partner_id (verified by \d audit_log showing no FK) | 20 | 8.2-T01 | BE | API-05, SEC-09
8.2-T10 | auth-identity | 8.2 | 8. Partner (Northbound) API | Auth: API key + HMAC signing | 1 | AuditService and AuditLogRepository: write auth events to audit_log in auth-identity | The auth-identity @Service AuditService writes audit events to the audit_log table (8.2-T09). Events for WBS 8.2: CREDENTIAL_GENERATED (actor=opsUserId, detail={api_key_prefix: first 8 chars only, partner_id}), CREDENTIAL_ROTATED (same), AUTH_FAILURE (actor=SYSTEM, detail={error_code, api_key_prefix, ip_address}). Writes are synchronous for credential events (within the same transaction as credential save) and fire-and-forget async for auth failures (from the gateway filter via internal HTTP POST). The detail JSONB must never contain hmac_secret, api_secret, or api_secret_hash. | • Create AuditLogEntry.java @Entity in services/auth-identity/src/main/java/com/gme/pay/auth/domain/ mapping to audit_log • Create AuditLogRepository.java extending JpaRepository<AuditLogEntry,Long> • Create AuditService.java @Service with void logEvent(String eventType, String actor, Long partnerId, Map<String,Object> detail); sanitize detail to remove any key named hmac_secret/api_secret/api_secret_hash before save • Expose @RestController AuditController.java at POST /internal/v1/audit accepting AuditEventRequest DTO; call auditService.logEvent; mark method @Async for fire-and-forget caller • Add @Transactional on logEvent to ensure audit write is atomic with caller transaction when called synchronously | services/auth-identity/src/main/java/com/gme/pay/auth/service/AuditService.java and AuditController.java | • CREDENTIAL_GENERATED event is inserted in audit_log after generateCredentials; detail contains api_key_prefix but NOT api_secret or api_secret_hash • AUTH_FAILURE event inserted via /internal/v1/audit with error_code in detail JSONB • detail sanitizer removes any key named hmac_secret from the map before persistence (test by passing {hmac_secret: x} and asserting row detail does not contain that key) • AuditController POST /internal/v1/audit returns 202 Accepted for fire-and-forget pattern • created_at is populated by DEFAULT NOW() without explicit set from application code | 35 | 8.2-T09 | BE | API-05, SEC-09
8.2-T11 | auth-identity | 8.2 | 8. Partner (Northbound) API | Auth: API key + HMAC signing | 1 | CredentialGenerationService: generate api_key+api_secret+hmac_secret, bcrypt+Vault store | Per API-05 §3.1, SEC-09 §2.3 and §9.1: at partner onboarding GME Ops generates: api_key (prefix pk_live_ + 32 random alphanumeric chars = 39 chars total), api_secret (32 SecureRandom bytes base64url-encoded, shown once to operator), hmac_secret (32 SecureRandom bytes base64url-encoded, stored in Vault). api_secret is bcrypt-hashed (cost=12) and stored in partner_credential.api_secret_hash. hmac_secret is written to Vault at secret/data/partners/{partner_id}/hmac_secret. Returned PartnerCredentials DTO contains both plaintexts for one-time display; caller must not log them. On rotation: SELECT FOR UPDATE existing active credential, set is_active=FALSE, then insert new row. Credential operations are audit-logged via AuditService. | • Create CredentialGenerationService.java in services/auth-identity/src/main/java/com/gme/pay/auth/service/ with @Service @Transactional • Inject PartnerCredentialRepository, VaultTemplate, BCryptPasswordEncoder(strength=12), AuditService • Implement PartnerCredentials generateCredentials(Long partnerId, String actorUserId) using SecureRandom for api_secret and hmac_secret (32 bytes each, Base64.getUrlEncoder().withoutPadding().encodeToString) • Set api_key = pk_live_ + random alphanumeric 32 chars; hash api_secret with bcryptEncoder; write hmac_secret to Vault; save PartnerCredential to DB • On rotation: find existing active credential via findByPartnerIdAndIsActiveTrue, set is_active=FALSE, save, then generate new • Call auditService.logEvent(CREDENTIAL_GENERATED, actorUserId, partnerId, {api_key_prefix: apiKey.substring(0,15)}) after successful save | services/auth-identity/src/main/java/com/gme/pay/auth/service/CredentialGenerationService.java | • generateCredentials inserts exactly one row with is_active=TRUE into partner_credential • api_secret_hash in DB is a valid BCrypt hash string starting with $2a$ or $2b$ and cost 12 • Vault path secret/data/partners/{partnerId}/hmac_secret is written with hmac_secret key • Returned PartnerCredentials.apiKey is 39 chars starting with pk_live_ • On rotation: previous active credential row has is_active=FALSE; only one active row remains • AUDIT log row CREDENTIAL_GENERATED contains api_key_prefix but no plaintext api_secret or hmac_secret | 40 | 8.2-T03, 8.2-T10 | BE | API-05, SEC-09
8.2-T12 | auth-identity | 8.2 | 8. Partner (Northbound) API | Auth: API key + HMAC signing | 1 | Flyway migration: idempotency_key_log table for durable idempotency audit trail | Redis alone is volatile. Per SEC-09 non-repudiation requirements, idempotency decisions for POST requests must also be durable in PostgreSQL. Table idempotency_key_log in auth-identity schema: id BIGINT GENERATED ALWAYS AS IDENTITY PK, partner_id BIGINT NOT NULL, idempotency_key VARCHAR(128) NOT NULL, request_body_hash CHAR(64) NOT NULL (SHA-256 hex), response_status SMALLINT, created_at TIMESTAMPTZ NOT NULL DEFAULT NOW(), UNIQUE(partner_id, idempotency_key). No FK on partner_id. Write is async (fire-and-forget) after Redis entry is set; never on the hot path. This is a compliance/audit record; response_body is intentionally NOT stored here (too large; Redis holds the cached response). | • Determine next Flyway version in services/auth-identity/src/main/resources/db/migration/ • Create V{n}__idempotency_key_log.sql with table DDL as specified • Add UNIQUE constraint on (partner_id, idempotency_key) • Add index: CREATE INDEX ON idempotency_key_log (partner_id, created_at DESC) • Add SQL comment: -- Append-only audit of idempotency decisions. Application role: INSERT only. Response body not stored here. • Run flywayMigrate to confirm no conflicts | services/auth-identity/src/main/resources/db/migration/V{n}__idempotency_key_log.sql | • Migration applies cleanly • UNIQUE constraint on (partner_id, idempotency_key) prevents duplicate rows • request_body_hash is CHAR(64) (SHA-256 hex is exactly 64 chars) • created_at has DEFAULT NOW() and is NOT NULL • No response_body column (intentionally omitted; too large for audit table) • Index on (partner_id, created_at DESC) is visible in \d idempotency_key_log | 20 | 8.2-T01 | BE | API-05, SEC-09
8.2-T13 | auth-identity | 8.2 | 8. Partner (Northbound) API | Auth: API key + HMAC signing | 1 | IdempotencyLogService: async PostgreSQL write-through for idempotency audit in auth-identity | After IdempotencyGatewayFilter (8.2-T08) writes to Redis, it also asynchronously persists to idempotency_key_log (8.2-T12) via auth-identity POST /internal/v1/idempotency/log. The write is fire-and-forget (WebClient .subscribe() in the filter) and must never block the gateway response path. If DB write fails (duplicate key = rare race), log WARN and swallow. auth-identity IdempotencyLogService is @Service with @Async method. @Async executor is configured with bounded thread pool maxPoolSize=10. | • Create IdempotencyLogRequest DTO {String partnerId, String idempotencyKey, String requestBodyHash, int responseStatus} in lib-api-contracts • Create IdempotencyLogService.java in services/auth-identity with @Service; inject IdempotencyKeyLogRepository (Spring Data JPA for idempotency_key_log) • Implement @Async void persistLog(IdempotencyLogRequest req) annotated @Transactional; on DataIntegrityViolationException (duplicate) log WARN and return • Create @RestController IdempotencyLogController.java at POST /internal/v1/idempotency/log; call service; return 202 Accepted • In IdempotencyGatewayFilter (8.2-T08) call the auth-identity endpoint using WebClient after updating Redis; use .subscribe() not .block() | services/auth-identity/src/main/java/com/gme/pay/auth/service/IdempotencyLogService.java and IdempotencyLogController.java | • persistLog does not propagate DataIntegrityViolationException (swallows duplicate quietly with WARN log) • Method is @Async and returns void immediately (verifiable by checking return type and annotation) • DB row inserted with correct partner_id, idempotency_key, request_body_hash values • @Async executor bean has maxPoolSize=10 configured in application • WebClient call in filter uses .subscribe() not .block() (code review check - no blocking call on reactive thread) | 30 | 8.2-T08, 8.2-T12 | BE | API-05, SEC-09
8.2-T14 | auth-identity | 8.2 | 8. Partner (Northbound) API | Auth: API key + HMAC signing | 1 | RateLimitGatewayFilter: per-partner Redis sliding-window rate limiter in api-gateway | Per API-05 §3.5, requests exceeding per-partner rate limits return 429 with Retry-After header. Default = 100 req/min per partner. Per-partner overrides stored in Redis at config:partner:{partnerId}:rate_limit_per_min. Implementation: GlobalFilter order=-8 (after idempotency filter); Redis counter keyed ratelimit:{partnerId}:{epochMinute} using INCR + EXPIRE 60s. Response headers: X-RateLimit-Limit, X-RateLimit-Remaining, X-RateLimit-Reset (epoch second of next minute boundary). On limit exceeded: 429 error.code=RATE_LIMITED with Retry-After header. X-Partner-ID header (set by HMAC filter) provides partner_id. | • Create RateLimitGatewayFilter.java in services/api-gateway/src/main/java/com/gme/pay/gateway/filter/ implementing GlobalFilter with getOrder()=-8 • Read X-Partner-ID header; if absent skip filter (HMAC filter already rejected such requests) • Compute minute bucket: long epochMinute = Instant.now().getEpochSecond() / 60 • Read per-partner limit from Redis config:partner:{partnerId}:rate_limit_per_min; fall back to configurable default (property gme.security.default-rate-limit-per-min=100) • Use ReactiveRedisTemplate INCR on ratelimit:{partnerId}:{epochMinute} then EXPIRE 60; if count > limit return 429 • Set X-RateLimit-Limit, X-RateLimit-Remaining, X-RateLimit-Reset headers on all non-rejected responses | services/api-gateway/src/main/java/com/gme/pay/gateway/filter/RateLimitGatewayFilter.java | • 101st request in same minute for same partner returns 429 with error.code=RATE_LIMITED • Retry-After header value is positive integer between 1 and 60 • X-RateLimit-Remaining decrements from 100 to 0 over 100 requests • Partner with Redis override config:partner:2:rate_limit_per_min=50 is limited at 50 not 100 • No X-Partner-ID present: filter is a complete no-op (chain.filter called, no Redis calls) • Redis key ratelimit:{partnerId}:{bucket} has TTL of 60 seconds | 45 | 8.2-T07 | BE | API-05, SEC-09
8.2-T15 | auth-identity | 8.2 | 8. Partner (Northbound) API | Auth: API key + HMAC signing | 1 | Application config: wire all auth filters, Redis, and auth-identity base-url in api-gateway | Wire HmacAuthGatewayFilter (order=-10), IdempotencyGatewayFilter (order=-9), and RateLimitGatewayFilter (order=-8) into services/api-gateway. Set application.yml: auth-identity.base-url from ${AUTH_IDENTITY_BASE_URL}, spring.data.redis.host/port from env, gme.security.replay-nonce-ttl-seconds=600, gme.security.idempotency-ttl-seconds=86400, gme.security.default-rate-limit-per-min=100. Add lib-security as a dependency in api-gateway build.gradle. Add @ConditionalOnProperty(name=gme.security.hmac-filter.enabled, matchIfMissing=true) to allow disabling in local dev. Update docker-compose.yml to set env vars for api-gateway. | • Open services/api-gateway/src/main/resources/application.yml; add auth-identity.base-url, redis config, and gme.security.* properties as specified • In services/api-gateway/build.gradle add implementation project(:lib:lib-security) • Annotate HmacAuthGatewayFilter, IdempotencyGatewayFilter, RateLimitGatewayFilter with @ConditionalOnProperty(name=gme.security.hmac-filter.enabled, matchIfMissing=true) • Update docker-compose.yml api-gateway service environment block with AUTH_IDENTITY_BASE_URL, REDIS_HOST, REDIS_PORT • Verify no hardcoded secrets, tokens, or passwords appear in any application*.yml file | services/api-gateway/src/main/resources/application.yml (modified), services/api-gateway/build.gradle (modified), docker-compose.yml (modified) | • application.yml contains no hardcoded secret values • auth-identity.base-url uses ${AUTH_IDENTITY_BASE_URL:http://auth-identity:8080} (env var with fallback) • ./gradlew :services:api-gateway:compileJava succeeds after adding lib-security dependency • gme.security.replay-nonce-ttl-seconds=600 property present in application.yml • docker-compose.yml api-gateway environment block contains AUTH_IDENTITY_BASE_URL entry • Setting gme.security.hmac-filter.enabled=false disables all three filters for local dev | 25 | 8.2-T07, 8.2-T08, 8.2-T14 | BE | API-05, SEC-09
8.2-T16 | auth-identity | 8.2 | 8. Partner (Northbound) API | Auth: API key + HMAC signing | 1 | docker-compose: Vault dev-mode service with seed data for local HMAC auth development | Developers need a local Vault in dev-mode with seed partner HMAC secrets to test the auth filter. Add hashicorp/vault:1.15 to docker-compose.yml with VAULT_DEV_ROOT_TOKEN_ID=root. Add a vault-init init container (curlimages/curl) that waits for Vault health then seeds: POST http://vault:8200/v1/secret/data/partners/1/hmac_secret with {data:{hmac_secret:test-partner-1-hmac-secret-32ch}}. Add spring.cloud.vault.uri and spring.cloud.vault.token to services/auth-identity/src/main/resources/application-local.yml. Auth-identity depends_on vault (healthy). | • Add vault service to docker-compose.yml: image hashicorp/vault:1.15, VAULT_DEV_ROOT_TOKEN_ID=root, VAULT_DEV_LISTEN_ADDRESS=0.0.0.0:8200, ports 8200:8200, healthcheck on GET /v1/sys/health • Add vault-init service using curlimages/curl with depends_on vault, command that POSTs seed secret to Vault kv-v2 path • Add depends_on: {vault: {condition: service_healthy}} to auth-identity service in docker-compose.yml • Create services/auth-identity/src/main/resources/application-local.yml with spring.cloud.vault.uri=${VAULT_URI:http://localhost:8200} and spring.cloud.vault.token=${VAULT_TOKEN:root} • Verify: docker-compose up vault vault-init completes; curl http://localhost:8200/v1/secret/data/partners/1/hmac_secret -H X-Vault-Token:root returns hmac_secret value | docker-compose.yml (modified with vault and vault-init) and services/auth-identity/src/main/resources/application-local.yml | • docker-compose up vault vault-init exits with code 0 • Vault health endpoint GET http://localhost:8200/v1/sys/health returns HTTP 200 • After vault-init: curl GET /v1/secret/data/partners/1/hmac_secret returns {data:{hmac_secret:test-partner-1-hmac-secret-32ch}} • VAULT_DEV_ROOT_TOKEN_ID=root is set only in docker-compose.yml (not in any *.yml config committed to git) • application-local.yml uses ${VAULT_TOKEN:root} env var reference not hardcoded string root | 30 | 8.2-T03 | BE | API-05, SEC-09
8.2-T17 | auth-identity | 8.2 | 8. Partner (Northbound) API | Auth: API key + HMAC signing | 1 | Unit tests: HmacSignatureVerifier test vectors and constant-time comparison | Pure unit tests (no Spring context, no containers) for HmacSignatureVerifier in lib/lib-security (8.2-T04). Must cover: (1) empty-body SHA-256 hash, (2) canonical-string format with newline delimiter, (3) signature computation against a known reference HMAC-SHA256 vector, (4) verifySignature correct returns true, (5) verifySignature wrong secret returns false, (6) verifySignature uses constant-time comparison. Test class: lib/lib-security/src/test/java/com/gme/pay/security/HmacSignatureVerifierTest.java using JUnit 5 @ParameterizedTest. | • Create HmacSignatureVerifierTest.java with @Test methods for each check • Vector 1: method=POST, path=/v1/payments?foo=bar, timestamp=2026-06-04T09:31:00.000Z, body={}, secret=test-secret-exactly-32-chars-here; pre-compute expected signature with an external HMAC-SHA256 tool • Vector 2: method=GET, path=/v1/rate-quotes/qref123, body=empty; assert bodyHash equals e3b0c44298fc1c149afbf4c8996fb92427ae41e4649b934ca495991b7852b855 • Test verifySignature(correct expected, canonical, secret) = true • Test verifySignature(wrong expected, canonical, secret) = false • Add code comment confirming MessageDigest.isEqual is used (timing-safe); grep the source file in test as assertion | lib/lib-security/src/test/java/com/gme/pay/security/HmacSignatureVerifierTest.java | • All 6 test cases pass in ./gradlew :lib:lib-security:test • Empty body hash matches e3b0c44298fc1c149afbf4c8996fb92427ae41e4649b934ca495991b7852b855 exactly • computeSignature for vector 1 matches pre-computed reference hex string • verifySignature(correct) = true, verifySignature(wrong-by-1-char) = false • Test class has zero Spring/Mockito annotations (pure JUnit 5) • Total test execution time < 500ms | 25 | 8.2-T04 | BE | API-05, SEC-09
8.2-T18 | auth-identity | 8.2 | 8. Partner (Northbound) API | Auth: API key + HMAC signing | 1 | Unit tests: TimestampValidator boundary conditions and RedisNonceStore with Testcontainers | Tests for TimestampValidator (pure unit) and RedisNonceStore (Testcontainers Redis 7) from lib-security (8.2-T05). TimestampValidator tests: boundary at exactly 300s, 301s, future timestamps, ISO-8601 and Unix-epoch formats, malformed input. RedisNonceStore tests: first call true, second call false, TTL assertion, different nonces are independent. Test files: lib/lib-security/src/test/java/com/gme/pay/security/TimestampValidatorTest.java and RedisNonceStoreIT.java. | • Create TimestampValidatorTest.java with @ParameterizedTest: now-300s (PASS), now-301s (FAIL), now+301s (FAIL), Unix epoch integer string (PASS), malformed string (expect exception) • Create RedisNonceStoreIT.java with @Testcontainers; @Container GenericContainer redis = new GenericContainer(redis:7) withExposedPorts(6379) • Configure ReactiveRedisTemplate in test with the container host/port via @DynamicPropertySource • Test checkAndSetNonce: first call Mono<Boolean> true; second call same nonce+partner Mono<Boolean> false • Test TTL: RedisTemplate.getExpire(key) returns value <= 600 seconds after checkAndSetNonce • Test two different nonces for same partner both return true | lib/lib-security/src/test/java/com/gme/pay/security/TimestampValidatorTest.java and RedisNonceStoreIT.java | • isWithinWindow(now-300s, now, 300) returns true (inclusive boundary) • isWithinWindow(now-301s, now, 300) returns false • Unix epoch integer string parses without exception • checkAndSetNonce returns false on second call with same partner+nonce • Redis key TTL is between 590 and 600 seconds (allows for test execution time) • All tests pass in ./gradlew :lib:lib-security:test | 30 | 8.2-T05 | BE | API-05, SEC-09
8.2-T19 | auth-identity | 8.2 | 8. Partner (Northbound) API | Auth: API key + HMAC signing | 1 | Unit tests: CredentialGenerationService with Mockito-mocked Vault and Repository | Unit tests for CredentialGenerationService (8.2-T11) using Mockito to mock VaultTemplate and PartnerCredentialRepository. No containers needed. Covers: credential generation (key format, bcrypt hash format, Vault write), rotation (old credential deactivated), Vault write path correctness, returned DTO fields, and that no plaintext secret appears in AuditService call. Test file: services/auth-identity/src/test/java/com/gme/pay/auth/service/CredentialGenerationServiceTest.java. | • Create CredentialGenerationServiceTest.java with @ExtendWith(MockitoExtension.class) • Mock PartnerCredentialRepository, VaultTemplate, AuditService, BCryptPasswordEncoder • Test generateCredentials: verify repository.save called with entity where api_secret_hash matches BCrypt pattern ^\$2[ab]\$12\$.* • Verify vaultTemplate.write called with path containing secret/data/partners/{partnerId}/hmac_secret • Test rotation: when findByPartnerIdAndIsActiveTrue returns an existing credential, verify that credential is saved with is_active=FALSE before new insert • Assert returned PartnerCredentials.apiKey is 39 chars starting with pk_live_ • Assert auditService.logEvent called with event type CREDENTIAL_GENERATED and detail map NOT containing key hmac_secret | services/auth-identity/src/test/java/com/gme/pay/auth/service/CredentialGenerationServiceTest.java | • Mock verify: repository.save called with api_secret_hash matching BCrypt regex • Mock verify: vaultTemplate.write path equals secret/data/partners/{partnerId}/hmac_secret • Rotation test: first save called with is_active=FALSE on existing; second save with is_active=TRUE on new • apiKey is exactly 39 characters starting with pk_live_ • auditService.logEvent detail map does not contain key hmac_secret (assert via ArgumentCaptor) • All tests pass in ./gradlew :services:auth-identity:test | 30 | 8.2-T11 | BE | API-05, SEC-09
8.2-T20 | auth-identity | 8.2 | 8. Partner (Northbound) API | Auth: API key + HMAC signing | 1 | Unit tests: IdempotencyGatewayFilter all 6 scenarios with MockServerWebExchange | Unit tests for IdempotencyGatewayFilter (8.2-T08) using MockServerWebExchange and Mockito-mocked ReactiveRedisTemplate. No containers needed. Must cover all 6 spec-defined scenarios from API-05 §7.1: new key (pass through and store), duplicate same body (return cached), duplicate different body (422), in-flight (409), GET request (skip), missing header (400). Test file: services/api-gateway/src/test/java/com/gme/pay/gateway/filter/IdempotencyGatewayFilterTest.java. | • Create IdempotencyGatewayFilterTest.java with @ExtendWith(MockitoExtension.class) • Mock ReactiveRedisTemplate<String,String> and GatewayFilterChain • Test new key: mock hGet returns empty -> verify chain.filter called; verify hSet IN_FLIGHT then COMPLETE • Test duplicate same body: mock hGet returns COMPLETE + matching body_hash -> chain.filter NOT called; response matches stored • Test different body: mock hGet returns COMPLETE + different body_hash -> response is 422 IDEMPOTENCY_BODY_MISMATCH • Test in-flight: mock hGet returns IN_FLIGHT -> response is 409 X-Idempotency-Status: in_flight • Test GET: ReactiveRedisTemplate never invoked; chain.filter always called • Test missing header on POST: response is 400 MISSING_IDEMPOTENCY_KEY | services/api-gateway/src/test/java/com/gme/pay/gateway/filter/IdempotencyGatewayFilterTest.java | • Test duplicate same body: Mockito verify(chain, never()).filter(...) passes • Test 422: response body error.code equals IDEMPOTENCY_BODY_MISMATCH • Test 409: response header X-Idempotency-Status equals in_flight • Test GET: zero invocations on ReactiveRedisTemplate (Mockito verifyNoInteractions) • Test 400: response status 400 and error.code equals MISSING_IDEMPOTENCY_KEY • All 8 test methods pass in ./gradlew :services:api-gateway:test | 40 | 8.2-T08 | BE | API-05, SEC-09
8.2-T21 | auth-identity | 8.2 | 8. Partner (Northbound) API | Auth: API key + HMAC signing | 1 | Integration test: HmacAuthGatewayFilter + IdempotencyGatewayFilter with Testcontainers and WireMock | Spring Boot integration test for both gateway filters together using Testcontainers Redis 7 and WireMock for the auth-identity internal endpoint and a stub downstream service. Boots the full api-gateway application. Tests live in services/api-gateway/src/test/. Test class: HmacAuthGatewayFilterIT.java. Constructs correctly signed requests using HmacSignatureVerifier with test hmac_secret and asserts all auth scenarios end-to-end including idempotency cache replay through both filters. | • Create HmacAuthGatewayFilterIT.java with @SpringBootTest(webEnvironment=RANDOM_PORT) and @Testcontainers • Start Redis 7 Testcontainer and two WireMock servers (auth-identity stub, downstream stub); configure via @DynamicPropertySource • Stub WireMock auth-identity POST /internal/v1/credentials/resolve -> 200 {partnerId:1, hmacSecret:test-partner-1-hmac-secret-32ch, isActive:true} • Test valid signed POST passes to downstream and X-Partner-ID=1 is forwarded • Test stale timestamp (now-301s) returns 401 TIMESTAMP_DRIFT • Test replayed nonce (same X-Nonce twice within 600s) returns 401 REPLAY_DETECTED • Test tampered body returns 401 INVALID_SIGNATURE • Test duplicate Idempotency-Key returns cached 200 without second WireMock downstream call | services/api-gateway/src/test/java/com/gme/pay/gateway/filter/HmacAuthGatewayFilterIT.java | • Valid signed request: upstream receives X-Partner-ID=1 header and WireMock downstream called exactly once • Stale timestamp: HTTP 401 response error.code=TIMESTAMP_DRIFT • Replayed nonce: HTTP 401 response error.code=REPLAY_DETECTED • Tampered body: HTTP 401 response error.code=INVALID_SIGNATURE • Duplicate idempotency key: WireMock downstream stub called exactly once for two identical POST requests • All 7 test scenarios pass in ./gradlew :services:api-gateway:integrationTest | 55 | 8.2-T08, 8.2-T15 | BE | API-05, SEC-09
8.2-T22 | auth-identity | 8.2 | 8. Partner (Northbound) API | Auth: API key + HMAC signing | 1 | OpenAPI spec: declare HMAC auth headers and Idempotency-Key in partner-api.yaml | Per the STACK.md testing approach, contract tests run against openapi/partner-api.yaml. The HMAC headers (X-API-Key, X-Timestamp, X-Signature, X-Nonce) and Idempotency-Key must be declared as required headers so contract-test tooling can generate valid requests and validate auth requirements. Add a securitySchemes entry, reusable header parameters, and a metadata extension documenting the replay-protection windows. | • Open openapi/partner-api.yaml and add securitySchemes.HmacAuth: {type: apiKey, in: header, name: X-API-Key} • Add components.parameters: XTimestamp, XSignature, XNonce, IdempotencyKey as header parameters with schema type: string and required: true • Apply security: [{HmacAuth: []}] globally under the top-level security field • Add X-Timestamp, X-Signature, X-Nonce as parameters to every path operation • Add Idempotency-Key parameter reference to all POST operations • Add info extension x-gme-auth: {hmac-canonical-format: METHOD+newline+PATH_WITH_QUERY+newline+X-Timestamp+newline+SHA256HEX(body), timestamp-window-seconds: 300, nonce-ttl-seconds: 600, idempotency-ttl-seconds: 86400} | openapi/partner-api.yaml (modified) | • openapi-generator or swagger-parser validates the file without errors (./gradlew :lib:lib-api-contracts:generateApiDocs) • All POST paths include $ref to IdempotencyKey header parameter • X-Timestamp, X-Signature, X-Nonce are required: true in their definitions • info.x-gme-auth.timestamp-window-seconds equals 300 • info.x-gme-auth.nonce-ttl-seconds equals 600 • No existing endpoint operation is broken by the security additions | 25 | 8.2-T07 | BE | API-05, SEC-09
8.3-T01 | rate-fx | 8.3 | 8. Partner (Northbound) API | POST /rates (quote) | 1 | Define RateQuoteRequest and RateQuoteResponse DTOs in lib-api-contracts | POST /v1/rates (API-05 sec4.2): request fields target_payout string decimal, payout_currency ISO-4217, scheme_id string, direction domestic¦inbound¦outbound¦hub, optional merchant_qr, optional partner_ref. Response: quote_id, offer_rate, send_amount, service_charge, service_charge_currency, collection_usd, payout_usd_cost, collection_margin_usd, payout_margin_usd, cross_rate, valid_until ISO-8601 UTC, scheme_id, direction, partner_ref. USD pool fields omitted for domestic (same-ccy). m_a, m_b, cost_rate_* NEVER in response. Module: lib-api-contracts. | • Create RateQuoteRequest.java in lib-api-contracts/src/main/java/com/gme/pay/api/rates/ with JSR-380 annotations: @NotBlank on target_payout, @NotBlank @Size(3) on payout_currency, @NotBlank on scheme_id, @Pattern(regexp=domestic¦inbound¦outbound¦hub) on direction • Create RateQuoteResponse.java with all response fields as String; USD pool fields annotated @JsonInclude(NON_NULL) • Add OpenAPI @Schema annotations per API-05 field descriptions • ./gradlew :lib-api-contracts:build to verify | lib-api-contracts/src/main/java/com/gme/pay/api/rates/RateQuoteRequest.java and RateQuoteResponse.java | • @Valid rejects null target_payout • direction rejects values other than domestic¦inbound¦outbound¦hub • USD pool fields absent from JSON when null (NON_NULL) • Decimal amounts serialize as strings not numbers • m_a, m_b, cost_rate_* fields absent from RateQuoteResponse | 30 |  | BE | API-05, RATE-04
8.4-T01 | payment-executor | 8.4 | 8. Partner (Northbound) API | POST /payments & /cpm/generate | 1 | Flyway migration V301: create payments table in payment-executor (PostgreSQL 16) | WBS 8.4 delivers POST /v1/payments (MPM execute) and POST /v1/payments/cpm/generate (CPM token issue) in the payment-executor Spring Boot service (services/payment-executor/). Both endpoints persist to PostgreSQL 16. The payments table stores: payment_id TEXT PK, partner_id TEXT NOT NULL, quote_id TEXT, status TEXT NOT NULL CHECK(status IN ('CPM_PENDING','PENDING','APPROVED','FAILED','CANCELLED','UNCERTAIN')), payment_mode TEXT NOT NULL CHECK(payment_mode IN ('MPM','CPM')), direction TEXT NOT NULL, scheme_id TEXT NOT NULL, merchant_qr TEXT, customer_ref TEXT NOT NULL, partner_txn_ref TEXT NOT NULL, collection_amount NUMERIC(20,4), collection_currency TEXT, target_payout NUMERIC(20,4), payout_currency TEXT, offer_rate NUMERIC(24,10), send_amount NUMERIC(20,8), service_charge NUMERIC(20,4), service_charge_currency TEXT, collection_usd NUMERIC(20,8), payout_usd_cost NUMERIC(20,8), collection_margin_usd NUMERIC(20,8), payout_margin_usd NUMERIC(20,8), cross_rate NUMERIC(24,10), prefund_deducted_usd NUMERIC(20,8), scheme_txn_id TEXT, country_code TEXT, idempotency_key TEXT NOT NULL, created_at TIMESTAMPTZ NOT NULL DEFAULT NOW(), approved_at TIMESTAMPTZ, updated_at TIMESTAMPTZ, cancelled_at TIMESTAMPTZ. Unique constraint on (partner_id, idempotency_key) and (partner_id, partner_txn_ref). All NUMERIC money fields use NUMERIC (not FLOAT). Migrations via Flyway naming convention Vnnn__*.sql. | • Create services/payment-executor/src/main/resources/db/migration/V301__create_payments_table.sql with the payments table DDL including all columns listed above. • Add CHECK constraints on status and payment_mode columns. • Add UNIQUE INDEX on (partner_id, idempotency_key) and (partner_id, partner_txn_ref). • Add indexes on (partner_id, status), (quote_id), (scheme_txn_id) WHERE scheme_txn_id IS NOT NULL, (partner_id, created_at DESC). • Run flyway:migrate against local Postgres on port 5433 (docker-compose) and confirm table exists with correct structure. | services/payment-executor/src/main/resources/db/migration/V301__create_payments_table.sql | • Migration runs cleanly; flyway_schema_history shows V301 as success. • UNIQUE constraint on (partner_id, idempotency_key): duplicate INSERT raises constraint violation. • UNIQUE constraint on (partner_id, partner_txn_ref): duplicate partner_txn_ref per partner rejected. • CHECK on status rejects INSERT with status='INVALID'. • All monetary columns are NUMERIC not FLOAT (verify with information_schema.columns). | 35 |  | BE | API-05
8.4-T02 | payment-executor | 8.4 | 8. Partner (Northbound) API | POST /payments & /cpm/generate | 1 | Flyway migration V302: create cpm_tokens table in payment-executor | The cpm_tokens table stores CPM QR tokens issued by POST /v1/payments/cpm/generate. Schema: cpm_token_id TEXT PK, payment_id TEXT NOT NULL REFERENCES payments(payment_id) ON DELETE RESTRICT, prepare_token TEXT NOT NULL UNIQUE, qr_content TEXT NOT NULL, expires_at TIMESTAMPTZ NOT NULL, prefund_reserved_usd NUMERIC(20,8), status TEXT NOT NULL CHECK(status IN ('ACTIVE','CONSUMED','EXPIRED')) DEFAULT 'ACTIVE', created_at TIMESTAMPTZ NOT NULL DEFAULT NOW(). Index on expires_at for TTL expiry cleanup job. Index on (status, expires_at) for finding expired-but-not-consumed tokens. Token TTL default is 60 seconds from generation; configurable per partner via Config Registry. | • Create services/payment-executor/src/main/resources/db/migration/V302__create_cpm_tokens_table.sql. • Add FK cpm_tokens.payment_id -> payments.payment_id ON DELETE RESTRICT. • Add UNIQUE constraint on prepare_token. • Add indexes on expires_at and (status, expires_at). • Run flyway:migrate and confirm table and FK exist. | services/payment-executor/src/main/resources/db/migration/V302__create_cpm_tokens_table.sql | • Migration V302 runs cleanly after V301. • UNIQUE on prepare_token: second INSERT with same prepare_token raises constraint violation. • FK violation: INSERT with non-existent payment_id raises FK error. • CHECK on status: INSERT with status='INVALID' rejected. • expires_at index exists in pg_indexes. | 25 | 8.4-T01 | BE | API-05
8.4-T03 | payment-executor | 8.4 | 8. Partner (Northbound) API | POST /payments & /cpm/generate | 1 | Flyway migration V303: payment_events audit trail table in payment-executor | Every transaction carries an 8-step event trail per spec DAT-03 and API-05 §5. Steps (in order): RATE_QUOTE_ISSUED, PREFUND_DEDUCTED, SCHEME_SUBMITTED, SCHEME_APPROVED, SCHEME_DECLINED, TRANSACTION_COMMITTED, WEBHOOK_QUEUED, WEBHOOK_DELIVERED. An additional PREFUND_REVERSED step covers scheme-fail reversal; CPM_TOKEN_ISSUED covers CPM generation. The payment_events table: event_id TEXT PK, payment_id TEXT NOT NULL REFERENCES payments(payment_id) ON DELETE CASCADE, event_type TEXT NOT NULL, occurred_at TIMESTAMPTZ NOT NULL DEFAULT NOW(), actor TEXT, payload JSONB. CHECK constraint on event_type covers all valid steps. Composite index on (payment_id, event_type) and index on occurred_at. | • Create services/payment-executor/src/main/resources/db/migration/V303__create_payment_events_table.sql. • Add CHECK constraint on event_type listing all 10 valid values (RATE_QUOTE_ISSUED, PREFUND_DEDUCTED, SCHEME_SUBMITTED, SCHEME_APPROVED, SCHEME_DECLINED, TRANSACTION_COMMITTED, WEBHOOK_QUEUED, WEBHOOK_DELIVERED, PREFUND_REVERSED, CPM_TOKEN_ISSUED). • Add FK to payments(payment_id) ON DELETE CASCADE. • Add composite index on (payment_id, occurred_at DESC) for audit trail queries. • Run flyway:migrate and confirm table exists. | services/payment-executor/src/main/resources/db/migration/V303__create_payment_events_table.sql | • V303 runs cleanly after V302. • INSERT of all 10 valid event_type values succeeds. • INSERT with event_type='UNKNOWN_STEP' raises CHECK violation. • FK: INSERT with non-existent payment_id raises FK error. • payload column accepts arbitrary JSONB objects. | 25 | 8.4-T01 | BE | API-05
8.4-T04 | payment-executor | 8.4 | 8. Partner (Northbound) API | POST /payments & /cpm/generate | 1 | Flyway migration V304: idempotency_cache table and outbox_events table in payment-executor | Two supporting tables needed. (1) idempotency_cache: partner_id TEXT NOT NULL, idempotency_key TEXT NOT NULL, request_body_hash TEXT NOT NULL, response_status INT NOT NULL, response_body TEXT NOT NULL, created_at TIMESTAMPTZ NOT NULL DEFAULT NOW(), expires_at TIMESTAMPTZ NOT NULL. PRIMARY KEY (partner_id, idempotency_key). Index on expires_at for TTL cleanup. (2) outbox_events (transactional Outbox pattern, Phase 1 - Kafka deferred): id BIGSERIAL PK, aggregate_id TEXT NOT NULL, event_type TEXT NOT NULL, payload JSONB NOT NULL, created_at TIMESTAMPTZ NOT NULL DEFAULT NOW(), published_at TIMESTAMPTZ, status TEXT NOT NULL DEFAULT 'UNPUBLISHED' CHECK(status IN ('UNPUBLISHED','PUBLISHED','FAILED')). Index on (status, created_at) for OutboxPoller queries. | • Create services/payment-executor/src/main/resources/db/migration/V304__create_idempotency_and_outbox_tables.sql with both table DDLs. • Add PRIMARY KEY (partner_id, idempotency_key) on idempotency_cache. • Add CHECK(status IN ('UNPUBLISHED','PUBLISHED','FAILED')) on outbox_events. • Add index on (status, created_at) on outbox_events. • Run flyway:migrate and confirm both tables exist. | services/payment-executor/src/main/resources/db/migration/V304__create_idempotency_and_outbox_tables.sql | • Both tables exist after migration. • PRIMARY KEY on idempotency_cache: duplicate (partner_id, idempotency_key) INSERT raises PK violation. • outbox_events CHECK on status rejects INSERT with status='BAD'. • Index on (status, created_at) exists for outbox_events. • JSONB column payload on outbox_events accepts and returns nested JSON objects. | 20 | 8.4-T01 | BE | API-05
8.4-T05 | payment-executor | 8.4 | 8. Partner (Northbound) API | POST /payments & /cpm/generate | 1 | Define PaymentExecuteRequest, CpmGenerateRequest and response DTOs in lib-api-contracts | lib-api-contracts holds OpenAPI-generated DTOs shared across services. For POST /v1/payments the inbound DTO is PaymentExecuteRequest fields: quoteId (required), merchantQr (required), direction (required), schemeId (required), customerRef (required), partnerTxnRef (required), collectionAmount String (required), collectionCurrency (required), countryCode (optional). For POST /v1/payments/cpm/generate the DTO is CpmGenerateRequest fields: schemeId (required), direction (required), customerRef (required), partnerTxnRef (required), countryCode (required), prefundReserveUsd String (optional). Response DTOs: PaymentExecuteResponse (paymentId, status, schemeTxnId, merchantName, merchantId, targetPayout, payoutCurrency, offerRate, collectionAmount, collectionCurrency, serviceCharge, serviceChargeCurrency, prefundDeductedUsd nullable, partnerTxnRef, createdAt, approvedAt). CpmGenerateResponse (cpmTokenId, prepareToken, qrContent, expiresAt, prefundReservedUsd nullable, paymentId, schemeId, partnerTxnRef, createdAt). All money amounts are String (decimal). Timestamps are String (ISO-8601 UTC ms precision e.g. 2026-06-04T09:31:00.000Z). | • Add PaymentExecuteRequest, CpmGenerateRequest, PaymentExecuteResponse, CpmGenerateResponse schemas to openapi/partner-api.yaml under components/schemas. • Mark required fields in schemas; prefundReserveUsd and prefundDeductedUsd are nullable/optional. • Run ./gradlew :lib-api-contracts:generateOpenApiSources to regenerate Java DTOs. • Verify generated Java classes in lib-api-contracts/build/generated contain all fields as String or nullable String. • Run ./gradlew :lib-api-contracts:build and confirm zero compile errors. | openapi/partner-api.yaml (schemas section updated) and regenerated DTOs in lib/api-contracts/ | • PaymentExecuteRequest has 9 fields; collectionAmount is present as required. • CpmGenerateRequest: prefundReserveUsd is optional (not in required array). • PaymentExecuteResponse: prefundDeductedUsd is nullable String (null for LOCAL partners). • CpmGenerateResponse: expiresAt and prefundReservedUsd fields present. • ./gradlew :lib-api-contracts:build GREEN with zero errors. | 35 |  | BE | API-05
8.4-T06 | payment-executor | 8.4 | 8. Partner (Northbound) API | POST /payments & /cpm/generate | 1 | Define domain event records for payment lifecycle in lib-events | lib-events module defines all domain event schemas (transactional Outbox pattern; Kafka transport wired in integration phase behind EventPublisher interface). Events for WBS 8.4: PaymentInitiatedEvent (paymentId, partnerId, quoteId, direction, schemeId, collectionAmount BigDecimal, collectionCurrency, targetPayout BigDecimal, payoutCurrency, createdAt Instant), PrefundDeductedEvent (paymentId, partnerId, amountUsd BigDecimal, balanceAfterUsd BigDecimal, deductedAt Instant), SchemeSubmittedEvent (paymentId, schemeTxnId, submittedAt Instant), PaymentApprovedEvent (paymentId, schemeTxnId, offerRate BigDecimal, approvedAt Instant), PaymentFailedEvent (paymentId, failureCode String, prefundReturnedUsd BigDecimal nullable, failedAt Instant), CpmTokenIssuedEvent (cpmTokenId, paymentId, partnerId, prefundReservedUsd BigDecimal nullable, expiresAt Instant, createdAt Instant), LowBalanceAlertEvent (partnerId, balanceUsd BigDecimal, thresholdUsd BigDecimal, triggeredAt Instant). All implement DomainEvent interface (eventId String, eventType String, occurredAt Instant, aggregateId String). | • Create Java record classes for each event in lib-events/src/main/java/com/gme/pay/events/payment/ (6 classes) and lib-events/src/main/java/com/gme/pay/events/prefunding/ (LowBalanceAlertEvent). • Ensure each record implements the DomainEvent marker interface already in lib-events. • Add @JsonProperty Jackson annotations on each record field. • Write JUnit 5 unit tests for each event: serialize to JSON then deserialize back; assert equal objects. • Run ./gradlew :lib-events:test GREEN. | lib-events/src/main/java/com/gme/pay/events/payment/ (6 event records) and lib-events/src/main/java/com/gme/pay/events/prefunding/LowBalanceAlertEvent.java | • All 7 event records implement DomainEvent interface. • Jackson round-trip test passes for each record (serialize -> deserialize -> equals). • PaymentFailedEvent.prefundReturnedUsd is BigDecimal nullable (null for LOCAL partners). • CpmTokenIssuedEvent.prefundReservedUsd is BigDecimal (not double or float). • ./gradlew :lib-events:test GREEN. | 40 |  | BE | API-05
8.4-T07 | payment-executor | 8.4 | 8. Partner (Northbound) API | POST /payments & /cpm/generate | 1 | Implement PaymentExecutorService interface and command/result records | payment-executor service (services/payment-executor/) is the orchestrator for both endpoints. Define PaymentExecutorService interface with: ExecutePaymentResult executeMpmPayment(ExecuteMpmCommand cmd) and IssueCpmTokenResult issueCpmToken(IssueCpmTokenCommand cmd). ExecuteMpmCommand record: partnerId String, quoteId String, merchantQr String, direction String, schemeId String, customerRef String, partnerTxnRef String, collectionAmount BigDecimal, collectionCurrency String, countryCode String, idempotencyKey String. IssueCpmTokenCommand record: partnerId String, schemeId String, direction String, customerRef String, partnerTxnRef String, countryCode String, prefundReserveUsd BigDecimal nullable, idempotencyKey String. ExecutePaymentResult and IssueCpmTokenResult contain all fields needed to build the API response DTOs. PaymentExecutorServiceImpl is @Service. | • Create services/payment-executor/src/main/java/com/gme/pay/executor/PaymentExecutorService.java interface. • Create ExecuteMpmCommand, IssueCpmTokenCommand, ExecutePaymentResult, IssueCpmTokenResult as Java records in the same package. Use BigDecimal for all money fields. • Create PaymentExecutorServiceImpl @Service implementing the interface with method stubs throwing UnsupportedOperationException. • Confirm module compiles: ./gradlew :payment-executor:compileJava GREEN. | services/payment-executor/src/main/java/com/gme/pay/executor/PaymentExecutorService.java and supporting command/result records | • Interface compiles with both method signatures. • ExecuteMpmCommand.collectionAmount is BigDecimal not String or double. • ExecutePaymentResult.prefundDeductedUsd is BigDecimal nullable. • IssueCpmTokenCommand.prefundReserveUsd is BigDecimal nullable (optional field from request). • ./gradlew :payment-executor:compileJava GREEN. | 30 | 8.4-T05, 8.4-T06 | BE | API-05
8.4-T08 | payment-executor | 8.4 | 8. Partner (Northbound) API | POST /payments & /cpm/generate | 1 | Implement IdempotencyService: Redis primary + Postgres fallback in payment-executor | All POST endpoints must honour the Idempotency-Key header (UUID, 24h TTL). IdempotencyService stores (partner_id, idempotency_key, request_body_hash SHA-256 hex, response_status, response_body JSON) in Redis (key: idem:{partnerId}:{idempotencyKey}, TTL=86400s via RedisTemplate<String,String> SETNX+EXPIRE) and writes through to idempotency_cache Postgres table (V304). On duplicate: same key+same body hash -> return stored response (REPLAYED); same key+different body hash -> throw IdempotencyKeyReuseException (HTTP 422 IDEMPOTENCY_KEY_REUSE); in-flight duplicate (processing flag key with 30s TTL) -> throw InFlightDuplicateException (HTTP 409 X-Idempotency-Status: in_flight). Missing key -> throw MissingIdempotencyKeyException (HTTP 400). If Redis is unavailable, fall back to Postgres SELECT for duplicate check. | • Create services/payment-executor/src/main/java/com/gme/pay/executor/idempotency/IdempotencyService.java @Service. • Implement checkOrReserve(partnerId, key, bodyHash): Redis SETNX in-flight flag (30s TTL); if key exists check stored hash; if match return stored response; if mismatch throw IdempotencyKeyReuseException. • Implement complete(partnerId, key, responseStatus, responseBody): store final response in Redis (86400s TTL) and write-through to idempotency_cache Postgres table. • Handle RedisException by falling back to Postgres idempotency_cache SELECT. • Write Testcontainers (Redis + Postgres) JUnit 5 test covering all 5 scenarios from API-05 §7.1. | services/payment-executor/src/main/java/com/gme/pay/executor/idempotency/IdempotencyService.java | • Testcontainers: first call returns REPLAYED=false (NEW); second call same key+same hash returns stored response (REPLAYED=true) without reprocessing. • Same key + different body hash throws IdempotencyKeyReuseException. • Concurrent duplicate within 30s processing window throws InFlightDuplicateException. • Missing key (null/blank) throws MissingIdempotencyKeyException. • Redis-down scenario: Postgres fallback SELECT prevents duplicate processing. | 50 | 8.4-T04, 8.4-T07 | BE | API-05
8.4-T09 | payment-executor | 8.4 | 8. Partner (Northbound) API | POST /payments & /cpm/generate | 1 | Implement QuoteCache: fetch and validate rate quote from Redis in payment-executor | Before executing MPM payment, the system validates the quote_id from POST /v1/payments. Rate quotes are stored in Redis by the rate-fx service (key: rate-quote:{quoteId}, TTL set from valid_until). Cached JSON blob contains: quoteId, partnerId, schemeId, direction, targetPayout BigDecimal, payoutCurrency, offerRate BigDecimal, sendAmount BigDecimal, serviceCharge BigDecimal, serviceChargeCurrency, collectionUsd BigDecimal nullable (null for domestic), payout_usd_cost BigDecimal nullable, collectionMarginUsd BigDecimal nullable, payoutMarginUsd BigDecimal nullable, crossRate BigDecimal nullable, validUntil Instant. QuoteCache @Component uses Spring Data Redis (RedisTemplate<String,String>). Validation: key exists (not TTL-expired), validUntil > now(), partnerId matches caller, schemeId and direction match request. Failures: RATE_QUOTE_EXPIRED (key missing or validUntil past) -> HTTP 422; RATE_QUOTE_INVALID (partner/scheme/direction mismatch) -> HTTP 422. | • Create services/payment-executor/src/main/java/com/gme/pay/executor/quote/QuoteCache.java @Component with method RateQuoteSnapshot fetchAndValidate(quoteId, partnerId, schemeId, direction, Instant now). • Deserialize Redis JSON to RateQuoteSnapshot record using Jackson ObjectMapper. • Throw RateQuoteExpiredException if key absent or validUntil <= now. • Throw RateQuoteInvalidException if partnerId, schemeId, or direction mismatch. • Write Testcontainers Redis JUnit 5 test: valid quote returns snapshot; TTL-expired key throws expired; wrong partnerId throws invalid; direction mismatch throws invalid. | services/payment-executor/src/main/java/com/gme/pay/executor/quote/QuoteCache.java and RateQuoteSnapshot.java record | • Testcontainers Redis: valid quote with matching fields returns RateQuoteSnapshot with correct BigDecimal offerRate. • TTL-expired key (manually deleted from Redis in test) throws RateQuoteExpiredException with code RATE_QUOTE_EXPIRED. • Wrong partnerId throws RateQuoteInvalidException with code RATE_QUOTE_INVALID. • Direction mismatch throws RateQuoteInvalidException. • RateQuoteSnapshot.collectionUsd is null for domestic (same-currency) quotes stored with null value. | 40 | 8.4-T07 | BE | API-05
8.4-T10 | payment-executor | 8.4 | 8. Partner (Northbound) API | POST /payments & /cpm/generate | 1 | Implement PrefundingPort interface and PrefundingClientAdapter in payment-executor | OVERSEAS partners (partnerType=OVERSEAS) require atomic prefund deduction before scheme call. The prefunding-balance Spring Boot service owns the balance (PostgreSQL SELECT...FOR UPDATE). payment-executor calls prefunding-balance via internal REST (WebClient). Define PrefundingPort interface with deductBalance(partnerId String, amountUsd BigDecimal) returning PrefundDeductResult (newBalanceUsd BigDecimal) and releaseBalance(partnerId String, amountUsd BigDecimal). PrefundingClientAdapter implements PrefundingPort using WebClient to prefunding-balance service URL from application.yml property prefunding.service.url. HTTP 402 from prefunding-balance -> InsufficientPrefundingException (HTTP 402 INSUFFICIENT_PREFUNDING). LOCAL partners skip deduction entirely: partnerType is read from Config & Registry service (cached in Redis 5-min TTL). Deduction amount is quoteSnapshot.collectionUsd() (NOT the partner-supplied collectionAmount). | • Create services/payment-executor/src/main/java/com/gme/pay/executor/prefunding/PrefundingPort.java interface. • Create PrefundingClientAdapter @Component implementing PrefundingPort using WebClient. • Implement deductBalance() calling POST to {prefunding.service.url}/internal/v1/prefunding/deduct; map 402 to InsufficientPrefundingException. • Implement releaseBalance() calling POST to {prefunding.service.url}/internal/v1/prefunding/release. • Write WireMock JUnit 5 test: stub deduct returning 200 -> succeeds; stub returning 402 -> InsufficientPrefundingException; LOCAL partner path -> zero WireMock calls. | services/payment-executor/src/main/java/com/gme/pay/executor/prefunding/PrefundingPort.java and PrefundingClientAdapter.java | • WireMock: 200 from prefunding service returns PrefundDeductResult with newBalanceUsd parsed correctly. • WireMock: 402 from prefunding service throws InsufficientPrefundingException with code INSUFFICIENT_PREFUNDING. • LOCAL partner path: WireMock deduct endpoint receives zero requests. • Deduction amount passed to adapter is quoteSnapshot.collectionUsd(), not partnerCollectionAmount. • Property prefunding.service.url injected from application.yml (no hardcoded URL). | 40 | 8.4-T09 | BE | API-05
8.4-T11 | payment-executor | 8.4 | 8. Partner (Northbound) API | POST /payments & /cpm/generate | 1 | Implement SchemeAdapterPort and ZeroPaySchemeAdapterClient in payment-executor | payment-executor calls the Scheme Adapter Layer (Anti-Corruption Layer) to submit MPM transactions to ZeroPay. Define SchemeAdapterPort interface with: SchemeCommitResult commitMpmPayment(CommitMpmCommand cmd) and PrepareTokenResult generateCpmToken(GenerateCpmTokenCommand cmd). CommitMpmCommand record: paymentId, merchantQr, targetPayout BigDecimal, payoutCurrency, schemeId. SchemeCommitResult record: schemeTxnId String, status enum(APPROVED,DECLINED,UNCERTAIN), approvedAt Instant nullable. GenerateCpmTokenCommand record: paymentId, partnerId, schemeId, direction. PrepareTokenResult record: prepareToken, qrContent, expiresAt Instant. ZeroPaySchemeAdapterClient @Component uses WebClient targeting scheme-adapter.zeropay.url from application.yml. HTTP 200 -> APPROVED; HTTP 202 -> UNCERTAIN; HTTP 4xx/5xx -> DECLINED. Scheme is NEVER called without prior successful prefund deduction. | • Create SchemeAdapterPort interface and ZeroPaySchemeAdapterClient @Component in services/payment-executor/src/main/java/com/gme/pay/executor/scheme/. • Implement commitMpmPayment() using WebClient POST to {scheme-adapter.zeropay.url}/internal/v1/zeropay/commit. • Implement generateCpmToken() using WebClient POST to {scheme-adapter.zeropay.url}/internal/v1/zeropay/cpm/generate. • Map HTTP status codes to SchemeCommitResult.status enum as described. • Write WireMock JUnit 5 test: 200 -> APPROVED with schemeTxnId; 202 -> UNCERTAIN; 500 -> DECLINED. | services/payment-executor/src/main/java/com/gme/pay/executor/scheme/SchemeAdapterPort.java and ZeroPaySchemeAdapterClient.java | • WireMock: 200 response maps to APPROVED with correct schemeTxnId. • WireMock: 202 response maps to UNCERTAIN status. • WireMock: 500 response maps to DECLINED with failure code SCHEME_UNAVAILABLE. • Property scheme-adapter.zeropay.url injected from application.yml. • generateCpmToken() WireMock: 200 response returns PrepareTokenResult with non-null prepareToken and expiresAt. | 40 | 8.4-T10 | BE | API-05
8.4-T12 | payment-executor | 8.4 | 8. Partner (Northbound) API | POST /payments & /cpm/generate | 1 | Implement rate-lock commit and payment_events insertion in PaymentExecutorServiceImpl | At POST /v1/payments commit (after scheme APPROVED), payment-executor permanently records all USD pool values from RateQuoteSnapshot. These are: offerRate, sendAmount, serviceCharge, collectionUsd, payoutUsdCost, collectionMarginUsd, payoutMarginUsd, crossRate. Once committed, later treasury or margin changes NEVER affect this record (rate-lock invariant). The payments row status transitions to APPROVED; approvedAt is set to scheme approvedAt. Four payment_events rows are inserted in the same @Transactional block: PREFUND_DEDUCTED (OVERSEAS only), SCHEME_SUBMITTED, SCHEME_APPROVED, TRANSACTION_COMMITTED. For UNCERTAIN: status=UNCERTAIN, insert only SCHEME_SUBMITTED; no TRANSACTION_COMMITTED. For domestic (same-currency) quotes: collectionUsd, payoutUsdCost, collectionMarginUsd, payoutMarginUsd are null. | • In PaymentExecutorServiceImpl, implement the commit step in a @Transactional method: save payments row with all 9 rate fields from RateQuoteSnapshot; insert payment_events rows. • Use PaymentRepository (Spring Data JPA @Repository) to persist payments. • Use PaymentEventsRepository to batch-insert payment_events rows. • For UNCERTAIN result: set payments.status=UNCERTAIN; insert only SCHEME_SUBMITTED event. • Write Testcontainers Postgres JUnit 5 test: full OVERSEAS approved flow; assert payments row has all 9 rate fields and 4 payment_events rows; verify pool identity: collectionUsd - collectionMarginUsd - payoutMarginUsd == payoutUsdCost within 0.01 USD tolerance. | PaymentRepository.java, PaymentEventsRepository.java, and rate-lock commit logic in services/payment-executor/src/main/java/com/gme/pay/executor/PaymentExecutorServiceImpl.java | • Testcontainers Postgres: approved OVERSEAS payment row has non-null collectionUsd, payoutUsdCost, collectionMarginUsd, payoutMarginUsd. • Pool identity: collectionUsd.subtract(collectionMarginUsd).subtract(payoutMarginUsd).compareTo(payoutUsdCost) within 0.01 USD. • payment_events has 4 rows in order: PREFUND_DEDUCTED, SCHEME_SUBMITTED, SCHEME_APPROVED, TRANSACTION_COMMITTED. • UNCERTAIN flow: payments.status=UNCERTAIN; only 1 payment_events row (SCHEME_SUBMITTED). • Domestic flow: collectionUsd null in persisted row. | 50 | 8.4-T11, 8.4-T03 | BE | API-05
8.4-T13 | payment-executor | 8.4 | 8. Partner (Northbound) API | POST /payments & /cpm/generate | 1 | Implement prefund reversal on scheme DECLINED/exception in PaymentExecutorServiceImpl | If scheme adapter returns DECLINED or throws after prefund deduction succeeded, the deducted amount must be reversed via PrefundingPort.releaseBalance(partnerId, amountUsd). Insert SCHEME_DECLINED event, then PREFUND_REVERSED event. Set payments.status=FAILED. If reversal itself fails (PrefundingPort.releaseBalance throws), insert REVERSAL_FAILED event, set status=FAILED, publish PrefundReversalFailedEvent to outbox (ops alert). For UNCERTAIN status: do NOT reverse; hold deduction until reconciliation resolves. For LOCAL partners: no reversal call (no deduction was made). | • In PaymentExecutorServiceImpl.executeMpmPayment(), wrap scheme adapter call in try/catch: on DECLINED result or exception, call prefundingPort.releaseBalance(). • Set payments.status=FAILED; insert SCHEME_DECLINED then PREFUND_REVERSED events in @Transactional. • On reversal failure: catch exception; insert REVERSAL_FAILED event; publish PrefundReversalFailedEvent via EventPublisher outbox. • UNCERTAIN branch: set payments.status=UNCERTAIN; do NOT call releaseBalance. • Write WireMock JUnit 5 tests: (a) DECLINED -> releaseBalance called with correct amountUsd; (b) UNCERTAIN -> releaseBalance not called; (c) DECLINED + reversal 500 -> REVERSAL_FAILED event inserted. | Reversal and UNCERTAIN handling logic in services/payment-executor/src/main/java/com/gme/pay/executor/PaymentExecutorServiceImpl.java | • WireMock: DECLINED scheme triggers releaseBalance with amountUsd equal to quoteSnapshot.collectionUsd(). • UNCERTAIN scheme: releaseBalance not called (WireMock verifies 0 requests). • Reversal failure path: REVERSAL_FAILED event row in payment_events; status=FAILED. • LOCAL partner DECLINED: releaseBalance not called (no deduction was made). • SCHEME_DECLINED event inserted before PREFUND_REVERSED event (order matters for audit trail). | 45 | 8.4-T12 | BE | API-05
8.4-T14 | payment-executor | 8.4 | 8. Partner (Northbound) API | POST /payments & /cpm/generate | 1 | Implement outbox event publishing via OutboxEventPublisher and OutboxPoller | Phase 1 uses the transactional Outbox pattern (lib-events EventPublisher interface). The EventPublisher interface has publish(DomainEvent event). OutboxEventPublisher @Component implements EventPublisher and writes to outbox_events table (V304 migration) inside the caller's active @Transactional context using Spring TransactionSynchronizationManager. This ensures event write and business row change are atomic. OutboxPoller @Component has @Scheduled(fixedDelay=1000) that queries UNPUBLISHED rows ordered by created_at, calls publishExternal() (Phase 1: SLF4J INFO log; Phase 2: Kafka producer behind same interface), updates status=PUBLISHED and sets published_at. PaymentExecutorServiceImpl injects EventPublisher and calls publish() for all events. | • Create services/payment-executor/src/main/java/com/gme/pay/executor/outbox/OutboxEventPublisher.java @Component implementing EventPublisher; serialize DomainEvent to JSON via Jackson; insert outbox_events row via JdbcTemplate within current transaction. • Create OutboxPoller @Component with @Scheduled(fixedDelay=1000); query up to 100 UNPUBLISHED rows; for each: call publishExternal (log); update status=PUBLISHED and published_at=NOW(). • Inject EventPublisher into PaymentExecutorServiceImpl; call publish() for PaymentInitiatedEvent, PrefundDeductedEvent, SchemeSubmittedEvent, PaymentApprovedEvent/PaymentFailedEvent, CpmTokenIssuedEvent. • Write Testcontainers Postgres JUnit 5 test: execute MPM payment; assert outbox_events has PaymentInitiatedEvent + PrefundDeductedEvent in UNPUBLISHED state before poller runs; run poller manually; assert status=PUBLISHED. • Verify rollback atomicity: if payments.save() fails (simulate by throwing in @Transactional), outbox_events has no rows. | services/payment-executor/src/main/java/com/gme/pay/executor/outbox/OutboxEventPublisher.java and OutboxPoller.java | • Testcontainers: outbox_events row inserted in same transaction as payments row (rollback of payment removes outbox row). • Poller updates status=PUBLISHED and published_at on processed rows. • OutboxEventPublisher.publish() within active @Transactional does not open a new transaction (uses existing connection). • All 6 event types from 8.4-T06 produce correct JSON in payload column. • Index on (status, created_at) used by poller query (EXPLAIN shows index scan). | 50 | 8.4-T06, 8.4-T12, 8.4-T04 | BE | API-05
8.4-T15 | payment-executor | 8.4 | 8. Partner (Northbound) API | POST /payments & /cpm/generate | 1 | Implement CPM token generation logic in PaymentExecutorServiceImpl (issueCpmToken) | POST /v1/payments/cpm/generate orchestration: (1) IdempotencyService check, (2) validate scheme+direction active via Config & Registry service (cached in Redis), (3) for OVERSEAS: call PrefundingPort.deductBalance with prefundReserveUsd from request OR scheme max-limit from Config Registry if omitted (default $200.00 per ZeroPay scheme config), (4) call SchemeAdapterPort.generateCpmToken() returning PrepareTokenResult, (5) in single @Transactional: save payments row (status=CPM_PENDING) + cpm_tokens row (status=ACTIVE, expires_at=now+tokenTtlSeconds) + outbox CpmTokenIssuedEvent, (6) return IssueCpmTokenResult. Token TTL configurable per partner in Redis config key cpm.token.ttl.{partnerId} (default 60s). If prefund deduction succeeds but scheme generate fails, reverse deduction and throw. | • Implement issueCpmToken(IssueCpmTokenCommand cmd) in PaymentExecutorServiceImpl with the 6 steps above. • Create CpmTokenRepository @Repository (Spring Data JPA) with save() and findByPrepareToken(). • For OVERSEAS: call prefundingPort.deductBalance(partnerId, effectiveReserveUsd) before scheme call. • In @Transactional: save both payments and cpm_tokens rows; call eventPublisher.publish(CpmTokenIssuedEvent). • Write Testcontainers Postgres + WireMock JUnit 5 test: OVERSEAS partner generates token; assert cpm_tokens row status=ACTIVE, expires_at within now+65s, payments row status=CPM_PENDING, outbox has CpmTokenIssuedEvent. | issueCpmToken() implementation in services/payment-executor/src/main/java/com/gme/pay/executor/PaymentExecutorServiceImpl.java and CpmTokenRepository.java | • Testcontainers: cpm_tokens row exists with status=ACTIVE after successful issuance. • cpm_tokens.expires_at == now + tokenTtlSeconds (within 2s tolerance; default 60s). • payments row inserted with status=CPM_PENDING and pre-assigned payment_id. • WireMock: prefunding-balance deduct called once with correct amountUsd for OVERSEAS partner. • outbox_events has 1 CpmTokenIssuedEvent row in UNPUBLISHED status in same transaction. | 50 | 8.4-T14, 8.4-T11 | BE | API-05
8.4-T16 | payment-executor | 8.4 | 8. Partner (Northbound) API | POST /payments & /cpm/generate | 1 | Implement POST /v1/payments @RestController in payment-executor | PaymentController @RestController in services/payment-executor/ exposes POST /v1/payments. Accepts PaymentExecuteRequest DTO (lib-api-contracts) with @Valid Jakarta Bean Validation. Partner context (partnerId) extracted from Spring Security SecurityContextHolder (set by HmacSignatureFilter after verification). Idempotency-Key extracted from HttpServletRequest header. Delegates to PaymentExecutorService.executeMpmPayment(). Maps ExecutePaymentResult to PaymentExecuteResponse DTO. HTTP 201 on APPROVED; HTTP 202 on UNCERTAIN; HTTP 402 on InsufficientPrefundingException; HTTP 422 on RateQuoteExpiredException (RATE_QUOTE_EXPIRED) or RateQuoteInvalidException; HTTP 409 on InFlightDuplicateException; HTTP 422 on IdempotencyKeyReuseException. X-Request-ID header set via RequestIdFilter from lib-errors. lib-errors canonical error envelope applied to all 4xx/5xx. | • Create services/payment-executor/src/main/java/com/gme/pay/executor/api/PaymentController.java @RestController @RequestMapping(/v1). • Implement POST /payments method with @Valid @RequestBody PaymentExecuteRequest and Idempotency-Key header extraction. • Map all business exceptions to correct HTTP status and lib-errors error envelope using @ExceptionHandler. • Return ResponseEntity<PaymentExecuteResponse> with status 201 or 202. • Write @WebMvcTest slice test: mock PaymentExecutorService; valid request -> 201 with paymentId; missing collectionAmount -> 400 VALIDATION_ERROR with details; InsufficientPrefundingException -> 402; missing Idempotency-Key header -> 400 MISSING_IDEMPOTENCY_KEY. | services/payment-executor/src/main/java/com/gme/pay/executor/api/PaymentController.java | • @WebMvcTest: valid body + mocked APPROVED result returns HTTP 201 with payment_id in response JSON. • @WebMvcTest: missing required field collection_amount returns HTTP 400 with error.code=VALIDATION_ERROR and non-empty details array. • @WebMvcTest: InsufficientPrefundingException returns HTTP 402 with error.code=INSUFFICIENT_PREFUNDING. • @WebMvcTest: missing Idempotency-Key header returns HTTP 400 MISSING_IDEMPOTENCY_KEY. • X-Request-ID present in response headers on all responses. | 45 | 8.4-T08, 8.4-T15 | BE | API-05
8.4-T17 | payment-executor | 8.4 | 8. Partner (Northbound) API | POST /payments & /cpm/generate | 1 | Implement POST /v1/payments/cpm/generate @RestController in payment-executor | CpmController (or extend PaymentController) exposes POST /v1/payments/cpm/generate. Accepts CpmGenerateRequest DTO (lib-api-contracts) with @Valid. Partner context from Spring Security. Idempotency-Key from header. Delegates to PaymentExecutorService.issueCpmToken(). Maps IssueCpmTokenResult to CpmGenerateResponse DTO. HTTP 201 on success; HTTP 402 on InsufficientPrefundingException; HTTP 422 on scheme unavailable (SchemeUnavailableException). prefundReserveUsd in request is optional String decimal; parse to BigDecimal if present; pass null to command if absent. Rate limiting at 50 req/s per partner enforced at Spring Cloud Gateway layer (not in this service). | • Create or extend controller at /v1/payments/cpm/generate in services/payment-executor/src/main/java/com/gme/pay/executor/api/. • Parse optional prefundReserveUsd String to BigDecimal if present; leave null if absent. • Map IssueCpmTokenResult to CpmGenerateResponse; return ResponseEntity with HTTP 201. • Map InsufficientPrefundingException to 402; SchemeUnavailableException to 422 SCHEME_UNAVAILABLE. • Write @WebMvcTest: valid request returns 201 with cpmTokenId, prepareToken, expiresAt; missing customerRef returns 400; absent prefundReserveUsd returns 201 (optional field). | services/payment-executor/src/main/java/com/gme/pay/executor/api/CpmController.java (or method in PaymentController) | • @WebMvcTest: 201 response body contains cpm_token_id, prepare_token, expires_at, payment_id. • @WebMvcTest: missing required field customer_ref returns 400 VALIDATION_ERROR. • @WebMvcTest: absent prefund_reserve_usd (optional) returns 201 without 400. • @WebMvcTest: InsufficientPrefundingException maps to 402 INSUFFICIENT_PREFUNDING. • Response Content-Type is application/json;charset=UTF-8. | 35 | 8.4-T16 | BE | API-05
8.4-T18 | payment-executor | 8.4 | 8. Partner (Northbound) API | POST /payments & /cpm/generate | 1 | Implement HMAC-SHA256 request signing filter in payment-executor (Spring Security) | All inbound Partner API requests verified by HmacSignatureFilter extends OncePerRequestFilter. Canonical string: {HTTP_METHOD}\n{PATH_WITH_QUERY}\n{X-Timestamp}\n{SHA256_HEX_OF_BODY}. Required headers: X-API-Key, X-Timestamp, X-Signature. Reject conditions: ¦serverTime - X-Timestamp¦ > 300s -> HTTP 401 TIMESTAMP_OUT_OF_RANGE; HMAC mismatch -> HTTP 401 INVALID_SIGNATURE; X-API-Key unknown -> HTTP 401 INVALID_API_KEY. API secret fetched from Config & Registry service (cached in Redis 5-min TTL keyed by X-API-Key). Filter wraps request in CachedBodyHttpServletRequestWrapper so @RequestBody can still be read downstream. Filter registered before UsernamePasswordAuthenticationFilter in SecurityFilterChain @Configuration. | • Create services/payment-executor/src/main/java/com/gme/pay/executor/security/HmacSignatureFilter.java extending OncePerRequestFilter. • Create CachedBodyHttpServletRequestWrapper to buffer request body bytes. • Fetch API secret via PartnerCredentialService @Component (Redis-cached, WebClient fallback to Config Registry service). • Compute HMAC-SHA256 of canonical string; compare with X-Signature header in constant-time (MessageDigest.isEqual). • Write @SpringBootTest integration test: valid signed request -> 201; tampered body -> 401 INVALID_SIGNATURE; X-Timestamp +301s -> 401 TIMESTAMP_OUT_OF_RANGE; missing X-API-Key -> 401 INVALID_API_KEY. | services/payment-executor/src/main/java/com/gme/pay/executor/security/HmacSignatureFilter.java and SecurityConfig.java | • Valid HMAC-signed request reaches @RestController (returns 201 in integration test). • Body tampered post-signing returns 401 INVALID_SIGNATURE. • X-Timestamp more than 300s in past returns 401 TIMESTAMP_OUT_OF_RANGE. • Missing X-API-Key header returns 401 INVALID_API_KEY. • CachedBodyHttpServletRequestWrapper allows @RequestBody to be read after filter has consumed the stream (controller receives correct body). | 55 | 8.4-T17 | BE | API-05
8.4-T19 | payment-executor | 8.4 | 8. Partner (Northbound) API | POST /payments & /cpm/generate | 1 | Flyway migration V201: prefunding_accounts and prefunding_ledger tables in prefunding-balance service | The prefunding-balance Spring Boot service (services/prefunding-balance/) owns OVERSEAS partner balances in PostgreSQL 16. prefunding_accounts: partner_id TEXT PK, balance_usd NUMERIC(20,8) NOT NULL DEFAULT 0 CHECK(balance_usd >= 0), low_balance_threshold_usd NUMERIC(20,8) NOT NULL DEFAULT 500, updated_at TIMESTAMPTZ NOT NULL DEFAULT NOW(). prefunding_ledger: id BIGSERIAL PK, partner_id TEXT NOT NULL REFERENCES prefunding_accounts(partner_id), payment_id TEXT NOT NULL, amount_usd NUMERIC(20,8) NOT NULL, direction TEXT NOT NULL CHECK(direction IN ('DEBIT','CREDIT')), balance_after_usd NUMERIC(20,8) NOT NULL, event_at TIMESTAMPTZ NOT NULL DEFAULT NOW(). Index on (partner_id, event_at DESC). The deduction must use UPDATE ... WHERE balance_usd >= amount (no SELECT FOR UPDATE needed at application layer; Postgres row-level locking from single UPDATE is sufficient). | • Create services/prefunding-balance/src/main/resources/db/migration/V201__create_prefunding_accounts_table.sql. • Create V202__create_prefunding_ledger_table.sql with FK to prefunding_accounts. • Add CHECK(balance_usd >= 0) to prevent balance going negative at DB level. • Add CHECK(direction IN ('DEBIT','CREDIT')) to prefunding_ledger. • Run flyway:migrate on local Postgres port 5433 and confirm both tables. | services/prefunding-balance/src/main/resources/db/migration/V201__create_prefunding_accounts_table.sql and V202__create_prefunding_ledger_table.sql | • Both migrations run cleanly. • CHECK(balance_usd >= 0) rejects UPDATE that would set balance below zero. • FK on prefunding_ledger.partner_id enforced. • direction CHECK rejects 'UNKNOWN' value. • Index on (partner_id, event_at DESC) present in pg_indexes. | 25 |  | BE | API-05
8.4-T20 | payment-executor | 8.4 | 8. Partner (Northbound) API | POST /payments & /cpm/generate | 1 | Implement PrefundingBalanceService with atomic deduction (UPDATE WHERE) in prefunding-balance | PrefundingBalanceService @Service in services/prefunding-balance/ implements deductBalance(partnerId, amountUsd) and releaseBalance(partnerId, amountUsd). Atomic deduction SQL: UPDATE prefunding_accounts SET balance_usd = balance_usd - :amount, updated_at = NOW() WHERE partner_id = :partnerId AND balance_usd >= :amount; if 0 rows updated -> throw InsufficientPrefundingException (HTTP 402). No SELECT FOR UPDATE needed: single-row UPDATE with WHERE clause provides atomicity under Postgres MVCC. After deduction: insert DEBIT row into prefunding_ledger in same @Transactional. After deduction: if new balance < low_balance_threshold_usd -> publish LowBalanceAlertEvent to outbox_events (same transaction). releaseBalance() is inverse: UPDATE SET balance_usd = balance_usd + :amount; insert CREDIT ledger row. | • Create services/prefunding-balance/src/main/java/com/gme/pay/prefunding/PrefundingBalanceService.java @Service. • Implement deductBalance using @Modifying @Query native SQL UPDATE with WHERE balance_usd >= :amount. • After successful UPDATE: insert prefunding_ledger DEBIT row; check new balance against threshold; if below threshold insert LowBalanceAlertEvent into outbox_events. • Implement releaseBalance using UPDATE SET balance_usd = balance_usd + :amount; insert CREDIT ledger row. • Write Testcontainers Postgres JUnit 5 concurrent test: 2 threads each deducting 60 from balance=100; assert exactly 1 succeeds and 1 throws InsufficientPrefundingException; final balance=40.00. | services/prefunding-balance/src/main/java/com/gme/pay/prefunding/PrefundingBalanceService.java | • Testcontainers concurrent test: exactly 1 of 2 threads succeeds; balance_usd=40.00 after; 1 prefunding_ledger DEBIT row. • 0-rows-updated (balance < amount) throws InsufficientPrefundingException with code INSUFFICIENT_PREFUNDING. • prefunding_ledger insert and balance_usd UPDATE are in same @Transactional (rollback test: simulate exception after UPDATE; balance_usd unchanged). • LowBalanceAlertEvent inserted to outbox when newBalance < threshold (test with balance=100, threshold=200, deduct 80). • releaseBalance() increases balance_usd and inserts CREDIT ledger row. | 50 | 8.4-T19, 8.4-T06 | BE | API-05
8.4-T21 | payment-executor | 8.4 | 8. Partner (Northbound) API | POST /payments & /cpm/generate | 1 | Expose internal deduct/release REST endpoints in prefunding-balance service | payment-executor calls prefunding-balance via internal REST. Expose: POST /internal/v1/prefunding/deduct with body {partnerId, amountUsd} -> 200 {newBalanceUsd} or 402 {error}; POST /internal/v1/prefunding/release with body {partnerId, paymentId, amountUsd} -> 200 {newBalanceUsd}. These endpoints are on a non-public port (internal Spring Boot management port or separate server.port) not routed via Spring Cloud Gateway. Use Spring @RestController; no HMAC auth needed (internal network only); secure via NetworkPolicy at Kubernetes level. Both endpoints are @Transactional via service calls. | • Create services/prefunding-balance/src/main/java/com/gme/pay/prefunding/api/PrefundingInternalController.java @RestController @RequestMapping(/internal/v1/prefunding). • Implement POST /deduct delegating to PrefundingBalanceService.deductBalance(); return 200 {newBalanceUsd} or 402 error envelope. • Implement POST /release delegating to PrefundingBalanceService.releaseBalance(); return 200 {newBalanceUsd}. • Write @WebMvcTest: mock PrefundingBalanceService; deduct 200 response has newBalanceUsd; deduct throws InsufficientPrefundingException -> 402; release 200 response. • Confirm internal port configuration in application.yml (server.port=8080, management.server.port=8081 or separate internal port). | services/prefunding-balance/src/main/java/com/gme/pay/prefunding/api/PrefundingInternalController.java | • @WebMvcTest: POST /internal/v1/prefunding/deduct with valid body returns 200 with newBalanceUsd. • @WebMvcTest: deduct when service throws InsufficientPrefundingException returns 402 with error.code=INSUFFICIENT_PREFUNDING. • @WebMvcTest: POST /internal/v1/prefunding/release returns 200 with newBalanceUsd. • Endpoint not registered under /v1 (no Spring Cloud Gateway route to it). • ./gradlew :prefunding-balance:build GREEN. | 35 | 8.4-T20 | BE | API-05
8.4-T22 | payment-executor | 8.4 | 8. Partner (Northbound) API | POST /payments & /cpm/generate | 1 | Spring Cloud Gateway routes for /v1/payments and /v1/payments/cpm/generate with Redis rate limiting | Spring Cloud Gateway (services/api-gateway/) routes inbound Partner API calls to payment-executor. Add route definitions for POST /v1/payments (id=payments-mpm) and POST /v1/payments/cpm/generate (id=payments-cpm-generate). Each route applies: (1) RequestRateLimiter GatewayFilter using Redis rate limiter (redis-rate-limiter.replenishRate=50, burstCapacity=50) keyed by X-API-Key via PartnerKeyResolver @Bean; (2) AddResponseHeader filter for X-Request-ID if not already set. Routes forward to lb://payment-executor via Spring Cloud LoadBalancer. Rate limit breach returns 429 with Retry-After header. Limits configurable per partner by GME Ops (Redis key: rate-limit.{partnerId}). | • Edit services/api-gateway/src/main/resources/application.yml: add two route entries under spring.cloud.gateway.routes. • Create services/api-gateway/src/main/java/com/gme/pay/gateway/PartnerKeyResolver.java implementing KeyResolver; extract X-API-Key header; return Mono<String>. • Configure RequestRateLimiter filter in each route with redis-rate-limiter bean. • Write @SpringBootTest gateway slice test with WireMock payment-executor stub: POST /v1/payments proxied; 51st request within 1s returns 429. • Confirm lb://payment-executor resolves via Spring Cloud LoadBalancer in application.yml. | services/api-gateway/src/main/resources/application.yml (routes for payments-mpm and payments-cpm-generate) and PartnerKeyResolver.java | • POST /v1/payments route forwards to lb://payment-executor; WireMock stub response returned to caller. • POST /v1/payments/cpm/generate route forwards to lb://payment-executor. • 51st request from same X-API-Key within 1s returns HTTP 429 with Retry-After header. • X-Request-ID header appears in all gateway responses. • PartnerKeyResolver returns X-API-Key header value as rate-limit key (tested via unit test). | 45 | 8.4-T17 | BE | API-05
8.4-T23 | payment-executor | 8.4 | 8. Partner (Northbound) API | POST /payments & /cpm/generate | 1 | Unit tests: POST /v1/payments OVERSEAS inbound MPM happy path | Full unit test for OVERSEAS partner (SendMN, type=OVERSEAS) MPM payment. Quote: targetPayout=50000 KRW, offerRate=0.000703, sendAmount=35.06 USD, serviceCharge=0.35 USD, serviceChargeCurrency=USD, collectionUsd=36.37 USD, payoutUsdCost=35.06 USD, collectionMarginUsd=0.91 USD, payoutMarginUsd=0.40 USD. Prefund deduction amount = collectionUsd = 36.37 USD. Scheme approved. Expected result: status=APPROVED, prefundDeductedUsd=36.37, schemeTxnId non-null. Pool identity invariant: 36.37 - 0.91 - 0.40 == 35.06 (within 0.01 USD). Uses Mockito mocks for all ports. | • Create services/payment-executor/src/test/java/com/gme/pay/executor/MpmPaymentOverseasHappyPathTest.java with @ExtendWith(MockitoExtension.class). • Seed QuoteCache mock to return RateQuoteSnapshot with values above. • Mock PrefundingPort.deductBalance to return PrefundDeductResult(newBalanceUsd=48200.00). • Mock SchemeAdapterPort.commitMpmPayment to return SchemeCommitResult(status=APPROVED, schemeTxnId=ZP20260604093115001234). • Assert result.status()==APPROVED; result.prefundDeductedUsd()==36.37; pool identity assertion. | services/payment-executor/src/test/java/com/gme/pay/executor/MpmPaymentOverseasHappyPathTest.java | • Test GREEN: result.status == APPROVED. • PrefundingPort.deductBalance called with BigDecimal 36.37 (collectionUsd, not 35.77 collectionAmount). • result.prefundDeductedUsd == 36.37. • Pool identity: 36.37 - 0.91 - 0.40 == 35.06 asserted with abs(diff) <= 0.01. • SchemeAdapterPort.commitMpmPayment called exactly once. | 35 | 8.4-T12 | BE | API-05
8.4-T24 | payment-executor | 8.4 | 8. Partner (Northbound) API | POST /payments & /cpm/generate | 1 | Unit tests: POST /v1/payments LOCAL partner domestic same-currency short-circuit | LOCAL partner (GME Remit, type=LOCAL) paying KRW -> KRW. Same-currency short-circuit: collectionUsd null, no USD pool. serviceCharge=500 KRW. targetPayout=15000 KRW. No prefunding deduction (LOCAL). Expected: PrefundingPort.deductBalance never called; result.prefundDeductedUsd null; scheme called with targetPayout=15000 KRW; result.status==APPROVED. | • Create services/payment-executor/src/test/java/com/gme/pay/executor/MpmPaymentLocalPartnerTest.java. • Mock partner config to return partnerType=LOCAL. • Mock QuoteCache to return RateQuoteSnapshot with collectionUsd=null and serviceCharge=BigDecimal(500) KRW. • Assert Mockito verify(prefundingPort, never()).deductBalance(any(), any()). • Assert result.prefundDeductedUsd == null. | services/payment-executor/src/test/java/com/gme/pay/executor/MpmPaymentLocalPartnerTest.java | • PrefundingPort.deductBalance invoked zero times. • result.prefundDeductedUsd == null. • SchemeAdapterPort.commitMpmPayment called once with targetPayout=BigDecimal(15000) KRW. • result.status == APPROVED. • Test GREEN. | 25 | 8.4-T12 | BE | API-05
8.4-T25 | payment-executor | 8.4 | 8. Partner (Northbound) API | POST /payments & /cpm/generate | 1 | Unit tests: POST /v1/payments — insufficient prefunding and expired quote rejections | Two rejection unit tests. (A) Insufficient prefunding: OVERSEAS partner, collectionUsd=200.00, available balance=100.00. PrefundingPort.deductBalance throws InsufficientPrefundingException. Expected: exception propagates; SchemeAdapterPort never called; PaymentRepository.save never called. (B) Expired quote: QuoteCache.fetchAndValidate throws RateQuoteExpiredException (validUntil in past). Expected: exception propagates before PrefundingPort is called; both ports called zero times. | • Create services/payment-executor/src/test/java/com/gme/pay/executor/MpmPaymentRejectionTest.java with two @Test methods. • Test A: mock PrefundingPort.deductBalance to throw InsufficientPrefundingException; assert exception thrown; verify SchemeAdapterPort.commitMpmPayment never called; verify PaymentRepository.save never called. • Test B: mock QuoteCache.fetchAndValidate to throw RateQuoteExpiredException; assert exception thrown; verify PrefundingPort.deductBalance never called. • Both tests use @ExtendWith(MockitoExtension.class). | services/payment-executor/src/test/java/com/gme/pay/executor/MpmPaymentRejectionTest.java | • Test A: InsufficientPrefundingException with code INSUFFICIENT_PREFUNDING thrown. • Test A: SchemeAdapterPort invocation count = 0. • Test B: RateQuoteExpiredException with code RATE_QUOTE_EXPIRED thrown. • Test B: PrefundingPort.deductBalance invocation count = 0. • Both tests GREEN. | 25 | 8.4-T12 | BE | API-05
8.4-T26 | payment-executor | 8.4 | 8. Partner (Northbound) API | POST /payments & /cpm/generate | 1 | Unit tests: POST /v1/payments — scheme DECLINED triggers prefund reversal | OVERSEAS partner: prefund deduction succeeds (200), scheme adapter returns DECLINED. Expected: PrefundingPort.releaseBalance called with exact amountUsd=36.37 (collectionUsd); payments status=FAILED; payment_events contains SCHEME_DECLINED then PREFUND_REVERSED; SchemeAdapterPort called once. Second test: UNCERTAIN result -> releaseBalance NOT called; status=UNCERTAIN. | • Create services/payment-executor/src/test/java/com/gme/pay/executor/MpmPaymentSchemeResultTest.java with two @Test methods. • Test DECLINED: mock deductBalance success; mock commitMpmPayment to return DECLINED; assert releaseBalance called with BigDecimal(36.37); assert persisted status=FAILED; assert event_types captured include SCHEME_DECLINED and PREFUND_REVERSED. • Test UNCERTAIN: mock commitMpmPayment to return UNCERTAIN; assert releaseBalance NOT called; assert status=UNCERTAIN. | services/payment-executor/src/test/java/com/gme/pay/executor/MpmPaymentSchemeResultTest.java | • DECLINED: PrefundingPort.releaseBalance called once with amountUsd=36.37. • DECLINED: persisted payment status = FAILED. • DECLINED: event list includes SCHEME_DECLINED before PREFUND_REVERSED. • UNCERTAIN: releaseBalance invocation count = 0. • UNCERTAIN: persisted payment status = UNCERTAIN. | 30 | 8.4-T13 | BE | API-05
8.4-T27 | payment-executor | 8.4 | 8. Partner (Northbound) API | POST /payments & /cpm/generate | 1 | Unit tests: POST /v1/payments/cpm/generate — OVERSEAS happy path and insufficient-funds rejection | Two CPM generation unit tests. (A) OVERSEAS happy path: prefundReserveUsd omitted (default 200.00 USD from Config Registry). Mock deductBalance success; mock generateCpmToken returns prepareToken=ZP-CPM-TEST123, expiresAt=now+60s. Expected: result.prefundReservedUsd=200.00; result.prepareToken=ZP-CPM-TEST123; cpm_tokens saved with status=ACTIVE; outbox has CpmTokenIssuedEvent. (B) Insufficient funds: deductBalance throws InsufficientPrefundingException. Expected: exception propagates; generateCpmToken never called; no cpm_tokens row saved. | • Create services/payment-executor/src/test/java/com/gme/pay/executor/CpmGenerateTest.java with two @Test methods. • Test A: mock ConfigRegistry returning schemeMaxLimitUsd=200.00; mock deductBalance success; mock generateCpmToken returning PrepareTokenResult; assert result fields. • Test B: mock deductBalance to throw InsufficientPrefundingException; verify generateCpmToken never called; verify CpmTokenRepository.save never called. | services/payment-executor/src/test/java/com/gme/pay/executor/CpmGenerateTest.java | • Test A: result.prefundReservedUsd == 200.00 BigDecimal. • Test A: result.prepareToken == ZP-CPM-TEST123. • Test A: CpmTokenRepository.save argument has status=ACTIVE and expiresAt within now+65s. • Test B: InsufficientPrefundingException with code INSUFFICIENT_PREFUNDING propagates. • Test B: SchemeAdapterPort.generateCpmToken invocation count = 0. | 35 | 8.4-T15 | BE | API-05
8.4-T28 | payment-executor | 8.4 | 8. Partner (Northbound) API | POST /payments & /cpm/generate | 1 | Unit tests: idempotency scenarios for POST /v1/payments | Four idempotency unit tests using Mockito-mocked IdempotencyService. (A) Duplicate same key+body: first call processes; second call returns stored response (IdempotencyService returns REPLAYED); PrefundingPort called exactly 1 time total. (B) Same key+different body: IdempotencyService throws IdempotencyKeyReuseException -> HTTP 422. (C) In-flight: IdempotencyService throws InFlightDuplicateException -> HTTP 409. (D) Missing key: IdempotencyService throws MissingIdempotencyKeyException -> HTTP 400. | • Create services/payment-executor/src/test/java/com/gme/pay/executor/IdempotencyTest.java with four @Test methods. • Test A: first call checkOrReserve returns NEW; service processes; second call checkOrReserve returns REPLAYED stored response; assert PrefundingPort.deductBalance total count=1. • Test B: checkOrReserve throws IdempotencyKeyReuseException; assert it propagates. • Test C: checkOrReserve throws InFlightDuplicateException; assert it propagates. • Test D: idempotency key null; assert MissingIdempotencyKeyException thrown before any port call. | services/payment-executor/src/test/java/com/gme/pay/executor/IdempotencyTest.java | • Test A: second call returns same payment_id; PrefundingPort.deductBalance total=1. • Test B: IdempotencyKeyReuseException propagates with code IDEMPOTENCY_KEY_REUSE. • Test C: InFlightDuplicateException propagates. • Test D: MissingIdempotencyKeyException thrown; PrefundingPort invocation count=0. • All 4 tests GREEN. | 30 | 8.4-T08 | BE | API-05
8.4-T29 | payment-executor | 8.4 | 8. Partner (Northbound) API | POST /payments & /cpm/generate | 1 | Integration test: full MPM payment flow with Testcontainers (Postgres + Redis + WireMock) | End-to-end integration test for POST /v1/payments in payment-executor. @SpringBootTest(webEnvironment=RANDOM_PORT) with @Testcontainers. Containers: PostgreSQLContainer (Postgres 16) and GenericContainer for Redis; datasource and Redis URL via @DynamicPropertySource. WireMockServer for prefunding-balance (port 8091) and zeropay-adapter (port 8092). Seeds: partner record type=OVERSEAS in DB; rate quote JSON in Redis key rate-quote:qte_TEST with collectionUsd=36.37, validUntil=now+300s. Flow: POST /v1/payments with valid HMAC-signed request using test API key -> prefunding-balance stub returns 200 {newBalanceUsd:48200} -> zeropay-adapter stub returns 200 {schemeTxnId:ZP001} -> assert HTTP 201. Query Postgres via JdbcTemplate: payments row, 4 payment_events rows, 1 outbox_events row. | • Create services/payment-executor/src/test/java/com/gme/pay/executor/integration/MpmPaymentIntegrationTest.java. • Declare @Container static PostgreSQLContainer<> and static GenericContainer<?> for Redis; configure via @DynamicPropertySource. • Configure WireMockServer stubs for prefunding-balance /internal/v1/prefunding/deduct and zeropay-adapter /internal/v1/zeropay/commit. • POST request with HMAC signature computed using test API key and secret; assert HTTP 201 with payment_id. • Query Postgres: assert payments row, 4 payment_events, 1 outbox_events UNPUBLISHED. | services/payment-executor/src/test/java/com/gme/pay/executor/integration/MpmPaymentIntegrationTest.java | • HTTP 201 response with payment_id, status=approved, scheme_txn_id=ZP001. • Postgres payments row: collection_usd=36.37, payout_usd_cost=35.06; pool identity holds within 0.01. • payment_events has 4 rows: PREFUND_DEDUCTED, SCHEME_SUBMITTED, SCHEME_APPROVED, TRANSACTION_COMMITTED. • outbox_events has 1 row event_type=PaymentApprovedEvent status=UNPUBLISHED. • WireMock prefunding-balance deduct endpoint received exactly 1 request. | 60 | 8.4-T18, 8.4-T14 | BE | API-05
8.4-T30 | payment-executor | 8.4 | 8. Partner (Northbound) API | POST /payments & /cpm/generate | 1 | Integration test: CPM token generation with Testcontainers (Postgres + Redis + WireMock) | End-to-end integration test for POST /v1/payments/cpm/generate using same Testcontainers setup as 8.4-T29. WireMock stubs: prefunding-balance deduct 200 {newBalanceUsd:48000}; zeropay-adapter /internal/v1/zeropay/cpm/generate 201 {prepareToken:ZP-CPM-TESTTOKEN, qrContent:ZP-CPM-TESTTOKEN, expiresAt:now+60s}. Request: OVERSEAS partner, scheme=zeropay, direction=inbound, no prefundReserveUsd (default 200.00). Assert: HTTP 201 response; Postgres cpm_tokens row status=ACTIVE; payments row status=CPM_PENDING; outbox_events has CpmTokenIssuedEvent UNPUBLISHED. | • Create services/payment-executor/src/test/java/com/gme/pay/executor/integration/CpmGenerateIntegrationTest.java. • Reuse Testcontainers infrastructure from 8.4-T29 (shared base class or @Nested). • Configure WireMock stubs for prefunding deduct and zeropay cpm/generate. • POST /v1/payments/cpm/generate with valid HMAC-signed request; assert HTTP 201. • Query Postgres: cpm_tokens row status=ACTIVE; payments row status=CPM_PENDING; outbox row CpmTokenIssuedEvent UNPUBLISHED. | services/payment-executor/src/test/java/com/gme/pay/executor/integration/CpmGenerateIntegrationTest.java | • HTTP 201 response contains cpm_token_id, prepare_token=ZP-CPM-TESTTOKEN, expires_at within now+65s. • Postgres cpm_tokens.status = ACTIVE. • Postgres payments.status = CPM_PENDING. • outbox_events has 1 row event_type=CpmTokenIssuedEvent status=UNPUBLISHED. • WireMock zeropay-adapter generate endpoint received exactly 1 request. | 50 | 8.4-T29, 8.4-T15 | BE | API-05
8.4-T31 | payment-executor | 8.4 | 8. Partner (Northbound) API | POST /payments & /cpm/generate | 1 | OpenAPI contract tests for POST /v1/payments and POST /v1/payments/cpm/generate | Contract tests verify that both endpoints exactly match openapi/partner-api.yaml schemas. Use schemathesis or a JVM contract test library against the running @SpringBootTest (RANDOM_PORT). All external dependencies (PrefundingPort, SchemeAdapterPort, QuoteCache, IdempotencyService) mocked with valid responses. Tests cover: valid requests return 2xx with response bodies matching declared schemas; required fields missing return 400 with ErrorResponse schema; optional fields absent do not cause errors. | • Add schemathesis or OpenAPI contract test dependency to services/payment-executor/build.gradle testImplementation. • Create services/payment-executor/src/test/java/com/gme/pay/executor/contract/PaymentContractTest.java loading openapi/partner-api.yaml. • Mock all external ports to return valid successful responses for schema-valid requests. • Run schema-driven test cases for POST /v1/payments: valid -> 201 response validates against PaymentExecuteResponse schema; missing collection_amount -> 400 VALIDATION_ERROR matches ErrorResponse schema. • Run same for POST /v1/payments/cpm/generate: valid -> 201 matches CpmGenerateResponse schema; absent prefund_reserve_usd -> 201 (not 400). | services/payment-executor/src/test/java/com/gme/pay/executor/contract/PaymentContractTest.java | • All schema-valid POST /v1/payments requests return 2xx (no 5xx for valid inputs). • 201 response body validates against PaymentExecuteResponse OpenAPI schema. • Missing collection_amount returns 400 with error envelope matching ErrorResponse schema. • 201 CPM response validates against CpmGenerateResponse schema. • Absent prefund_reserve_usd (optional) in CPM request does not cause 400. | 45 | 8.4-T17, 8.4-T05 | BE | API-05
8.4-T32 | payment-executor | 8.4 | 8. Partner (Northbound) API | POST /payments & /cpm/generate | 1 | Low-balance alert: LowBalanceAlertEvent outbox publish after prefund deduction in prefunding-balance | After each successful prefund deduction in PrefundingBalanceService, compare newBalance against low_balance_threshold_usd. If newBalance < threshold, write LowBalanceAlertEvent (from lib-events) to outbox_events table in same @Transactional block as the balance UPDATE. The outbox_events table in prefunding-balance service mirrors the schema from V304 (add Flyway V203__create_prefunding_outbox_events_table.sql in services/prefunding-balance/). The Notification & Webhook service consumes this event to alert GME Ops. Threshold is per-partner, stored in prefunding_accounts.low_balance_threshold_usd. | • Create services/prefunding-balance/src/main/resources/db/migration/V203__create_prefunding_outbox_events_table.sql mirroring V304 structure. • In PrefundingBalanceService.deductBalance(), after UPDATE: fetch newBalance; if newBalance < low_balance_threshold_usd, call eventPublisher.publish(new LowBalanceAlertEvent(...)) writing to outbox_events in same transaction. • Add EventPublisher @Autowired to PrefundingBalanceService (same OutboxEventPublisher pattern as payment-executor). • Write Testcontainers Postgres unit test: deduct 80 from balance=100 (threshold=200) -> LowBalanceAlertEvent inserted to outbox_events. Deduct 80 from balance=1000 (threshold=200) -> no alert. • Verify rollback: if @Transactional is rolled back, outbox alert also rolled back. | services/prefunding-balance/src/main/resources/db/migration/V203__create_prefunding_outbox_events_table.sql and LowBalanceAlertEvent publish logic in PrefundingBalanceService | • balance=100, threshold=200, deduct=80 -> newBalance=20 < 200 -> LowBalanceAlertEvent in outbox_events. • balance=1000, threshold=200, deduct=80 -> newBalance=920 >= 200 -> no alert. • Alert event contains partnerId, balanceUsd=20, thresholdUsd=200, triggeredAt non-null. • Rollback of deduction transaction also removes alert event row. • V203 migration runs cleanly after V202. | 35 | 8.4-T20, 8.4-T06 | BE | API-05
8.5-T01 | api-gateway | 8.5 | 8. Partner (Northbound) API | Query/cancel/merchant/balance endpoints | 1 | Add GetPaymentResponse DTO to lib-api-contracts for GET /v1/payments/{id} | WBS 8.5 adds GET /v1/payments/{id}, POST /v1/payments/{id}/cancel, GET /v1/merchants/{qr}, and GET /v1/balance. lib-api-contracts (Gradle module) holds all OpenAPI-generated DTOs shared across services. GET /v1/payments/{id} returns: payment_id, status (pending¦approved¦failed¦cancelled¦uncertain), scheme_txn_id, merchant_name, merchant_id, target_payout (string), payout_currency, offer_rate (string decimal), collection_amount (string decimal), collection_currency, service_charge (string decimal), service_charge_currency, prefund_deducted_usd (string decimal), partner_txn_ref, direction, scheme_id, created_at, approved_at, updated_at, cancelled_at (nullable). | • In lib-api-contracts/src/main/java/com/gme/pay/contracts/payment/GetPaymentResponse.java create an immutable record with all fields above typed as String for monetary amounts and Instant for timestamps. • Add status enum PaymentStatus {PENDING,APPROVED,FAILED,CANCELLED,UNCERTAIN} in com.gme.pay.contracts.payment. • Annotate with @JsonInclude(NON_NULL) so nullable fields are omitted when absent. • Add unit test GetPaymentResponseSerializationTest confirming JSON round-trip with the example values from spec. | lib-api-contracts/src/main/java/com/gme/pay/contracts/payment/GetPaymentResponse.java and PaymentStatus.java | • All 20 fields present with correct types. • cancelled_at and approved_at absent from JSON when null. • PaymentStatus.valueOf("UNCERTAIN") succeeds. • JSON round-trip with spec example values produces identical string output. | 25 |  | BE | API-05
8.5-T02 | api-gateway | 8.5 | 8. Partner (Northbound) API | Query/cancel/merchant/balance endpoints | 1 | Add CancelPaymentRequest and CancelPaymentResponse DTOs to lib-api-contracts | POST /v1/payments/{id}/cancel accepts: reason (required, enum: customer_request¦merchant_request¦timeout¦other) and reason_detail (optional, max 200 chars). Response: payment_id, status=cancelled, cancelled_at (ISO-8601 UTC), prefund_returned_usd (string decimal, OVERSEAS only, nullable). Error codes: CANCEL_NOT_PERMITTED (400), PAYMENT_NOT_FOUND (404), 409 if already terminal. The Idempotency-Key header is required on all POST endpoints (400 MISSING_IDEMPOTENCY_KEY if absent). | • Create CancelPaymentRequest.java record with reason (CancellationReason enum) and reason_detail (nullable String, max 200 chars). • Create CancellationReason enum with values CUSTOMER_REQUEST, MERCHANT_REQUEST, TIMEOUT, OTHER. • Create CancelPaymentResponse.java record with payment_id, status (String), cancelled_at (Instant), prefund_returned_usd (nullable String). • Add @JsonInclude(NON_NULL) on CancelPaymentResponse. • Write CancelPaymentRequestValidationTest: assert @NotNull on reason and @Size(max=200) on reason_detail pass Bean Validation. | lib-api-contracts/src/main/java/com/gme/pay/contracts/payment/CancelPaymentRequest.java, CancellationReason.java, CancelPaymentResponse.java | • reason_detail null passes validation. • reason_detail of 201 chars fails @Size. • CancellationReason.from("customer_request") deserializes correctly via Jackson. • prefund_returned_usd absent from JSON when null. | 25 | 8.5-T01 | BE | API-05
8.5-T03 | api-gateway | 8.5 | 8. Partner (Northbound) API | Query/cancel/merchant/balance endpoints | 1 | Add MerchantDetailResponse DTO to lib-api-contracts for GET /v1/merchants/{qr} | GET /v1/merchants/{qr} resolves a URL-encoded QR string against the local merchant MongoDB store (Merchant and QR Data service). Response fields: merchant_id, merchant_name, merchant_type, scheme_id, qr_code, status (active¦inactive), payout_currency, address (nullable). 200 = found and active; 404 = MERCHANT_NOT_FOUND (QR not in DB or merchant inactive); 422 = QR found but merchant inactive or QR deactivated. The merchant store is in MongoDB (Merchant and QR Data service); reads come from CQRS read-model projections. | • Create MerchantDetailResponse.java record with all 8 fields; address is @JsonInclude(NON_NULL). • Add MerchantStatus enum {ACTIVE, INACTIVE}. • Write MerchantDetailResponseSerializationTest confirming spec example JSON matches. | lib-api-contracts/src/main/java/com/gme/pay/contracts/merchant/MerchantDetailResponse.java, MerchantStatus.java | • All 8 fields serialize with spec field names (snake_case). • address absent from JSON when null. • MerchantStatus.ACTIVE serializes as "active" (lowercase). • Round-trip with spec example JSON passes assertEquals. | 20 |  | BE | API-05
8.5-T04 | api-gateway | 8.5 | 8. Partner (Northbound) API | Query/cancel/merchant/balance endpoints | 1 | Add BalanceResponse and DeductionEvent DTOs to lib-api-contracts for GET /v1/balance | GET /v1/balance returns current prefunding balance (OVERSEAS partners only; LOCAL returns 403 FORBIDDEN). Response: partner_id, balance_usd (string decimal), low_balance_threshold_usd (string decimal), is_below_threshold (boolean), as_of (ISO-8601 UTC Instant), recent_deductions (array, only when ?include_history=true). Each deduction event: payment_id, amount_usd (string decimal; positive=deduction, negative=return for cancellation), balance_after_usd (string decimal), event_at (Instant). Prefunding stored in PostgreSQL prefunding table (NUMERIC columns, SELECT FOR UPDATE for deductions). | • Create BalanceResponse.java record with partner_id (String), balance_usd (String), low_balance_threshold_usd (String), is_below_threshold (boolean), as_of (Instant), recent_deductions (List<DeductionEvent>, @JsonInclude(NON_NULL)). • Create DeductionEvent.java record with payment_id, amount_usd, balance_after_usd (all String), event_at (Instant). • Write BalanceResponseSerializationTest with ?include_history scenario and without. | lib-api-contracts/src/main/java/com/gme/pay/contracts/balance/BalanceResponse.java, DeductionEvent.java | • recent_deductions omitted when null. • Negative amount_usd (cancellation return) serializes as string "-35.77". • is_below_threshold=true when balance_usd < low_balance_threshold_usd (assert in test). • as_of serializes as ISO-8601 UTC string. | 20 |  | BE | API-05
8.5-T05 | api-gateway | 8.5 | 8. Partner (Northbound) API | Query/cancel/merchant/balance endpoints | 1 | Flyway migration V201__payment_query_indexes.sql on Transaction Mgmt PostgreSQL | GET /v1/payments/{id} queries the transaction table by payment_id filtered by partner_id (ownership check: 404 if not owned by calling partner). The transaction table already exists from earlier epics. This ticket adds composite indexes to support fast ownership-scoped lookups. DB: PostgreSQL 16 in Transaction Mgmt service (services/transaction-mgmt). Migrations live in services/transaction-mgmt/src/main/resources/db/migration/. NUMERIC columns for all monetary fields. payment_id is globally unique (PK or unique index already); partner_id is a FK. The ownership check is (payment_id, partner_id) tuple. | • Create services/transaction-mgmt/src/main/resources/db/migration/V201__payment_query_indexes.sql. • Add index: CREATE INDEX CONCURRENTLY IF NOT EXISTS idx_txn_partner_payment ON transaction(partner_id, payment_id); • Add index: CREATE INDEX CONCURRENTLY IF NOT EXISTS idx_txn_partner_status ON transaction(partner_id, status, created_at DESC); (supports future list queries). • Verify with EXPLAIN on SELECT * FROM transaction WHERE partner_id=? AND payment_id=? uses the index. | services/transaction-mgmt/src/main/resources/db/migration/V201__payment_query_indexes.sql | • Flyway applies migration cleanly on a fresh schema (Testcontainers integration test). • EXPLAIN ANALYZE on ownership query shows Index Scan on idx_txn_partner_payment. • IF NOT EXISTS prevents failure on repeated apply. • Migration version V201 does not conflict with any existing version. | 25 |  | BE | API-05
8.5-T06 | api-gateway | 8.5 | 8. Partner (Northbound) API | Query/cancel/merchant/balance endpoints | 1 | Flyway migration V202__cancel_fields.sql -- add cancelled_at and cancel_reason to transaction | POST /v1/payments/{id}/cancel sets status=CANCELLED and records cancelled_at (TIMESTAMPTZ), cancel_reason (VARCHAR 50, enum values: customer_request¦merchant_request¦timeout¦other), and cancel_reason_detail (TEXT, nullable, max 200 chars). These fields do not exist on the transaction table yet. DB: PostgreSQL 16, Transaction Mgmt service. Altering the table with nullable columns is safe for existing rows. Also add CHECK constraint on cancel_reason to guard against bad values at DB level. | • Create services/transaction-mgmt/src/main/resources/db/migration/V202__cancel_fields.sql. • ALTER TABLE transaction ADD COLUMN cancelled_at TIMESTAMPTZ NULL, ADD COLUMN cancel_reason VARCHAR(50) NULL, ADD COLUMN cancel_reason_detail TEXT NULL. • ADD CONSTRAINT chk_cancel_reason CHECK (cancel_reason IN ('customer_request','merchant_request','timeout','other')). • Write Testcontainers migration test verifying INSERT with valid and invalid cancel_reason values. | services/transaction-mgmt/src/main/resources/db/migration/V202__cancel_fields.sql | • Migration applies cleanly after V201. • Existing rows unaffected (cancelled_at NULL). • INSERT with cancel_reason='other' succeeds. • INSERT with cancel_reason='invalid' violates CHECK constraint. • cancel_reason_detail of 201 chars stores without truncation (TEXT, no length limit at DB layer). | 25 | 8.5-T05 | BE | API-05
8.5-T07 | api-gateway | 8.5 | 8. Partner (Northbound) API | Query/cancel/merchant/balance endpoints | 1 | Flyway migration V203__prefunding_history.sql -- deduction event log table | GET /v1/balance with ?include_history=true returns last 10 deduction events (payment_id, amount_usd, balance_after_usd, event_at). These must be persisted in a prefunding_deduction_event table in PostgreSQL (Prefunding/Balance service DB). amount_usd is NUMERIC(20,4); positive = deduction, negative = return (cancellation). balance_after_usd is NUMERIC(20,4). Prefunding service: services/prefunding. This table is already being written to in earlier epics for each atomic deduction; confirm columns match the balance endpoint response shape. | • Create services/prefunding/src/main/resources/db/migration/V203__prefunding_history.sql. • CREATE TABLE IF NOT EXISTS prefunding_deduction_event (id BIGSERIAL PRIMARY KEY, partner_id VARCHAR(64) NOT NULL, payment_id VARCHAR(64) NOT NULL, amount_usd NUMERIC(20,4) NOT NULL, balance_after_usd NUMERIC(20,4) NOT NULL, event_at TIMESTAMPTZ NOT NULL DEFAULT NOW()). • CREATE INDEX idx_pde_partner_time ON prefunding_deduction_event(partner_id, event_at DESC); • Verify via Testcontainers that SELECT ... ORDER BY event_at DESC LIMIT 10 returns correct rows. | services/prefunding/src/main/resources/db/migration/V203__prefunding_history.sql | • Table created with all columns and correct types. • NUMERIC(20,4) for amount_usd stores -35.77 and 35.77 correctly. • Index idx_pde_partner_time exists after migration. • LIMIT 10 query on 20-row test data returns exactly 10 most-recent rows. | 25 |  | BE | API-05
8.5-T08 | api-gateway | 8.5 | 8. Partner (Northbound) API | Query/cancel/merchant/balance endpoints | 1 | Implement GetPaymentQueryService in transaction-mgmt service | GET /v1/payments/{id} is served by the Transaction Mgmt service (services/transaction-mgmt). The @Service class reads the transaction table by (payment_id, partner_id) -- 404 if not found (ownership enforced). Returns GetPaymentResponse DTO from lib-api-contracts. Use Spring Data JPA repository (TransactionRepository extends JpaRepository). The payment object includes rate-locked fields (offer_rate, collection_amount, service_charge, prefund_deducted_usd) that are stored as NUMERIC in PostgreSQL; map to String in the response. The spec says updated_at and cancelled_at are included when applicable. | • Create GetPaymentQueryService.java annotated @Service in services/transaction-mgmt/src/main/java/com/gme/pay/txnmgmt/query/. • Inject TransactionRepository; add method GetPaymentResponse getPayment(String paymentId, String partnerId). • Query: transactionRepository.findByPaymentIdAndPartnerId(paymentId, partnerId).orElseThrow(() -> new PaymentNotFoundException(paymentId)). • Map JPA entity fields to GetPaymentResponse; convert NUMERIC to String; map status enum to PaymentStatus. • Implement PaymentNotFoundException extending RuntimeException in lib-errors, error code PAYMENT_NOT_FOUND, HTTP 404. | services/transaction-mgmt/src/main/java/com/gme/pay/txnmgmt/query/GetPaymentQueryService.java | • Returns correct DTO for known payment_id owned by partner. • Throws PaymentNotFoundException for unknown payment_id. • Throws PaymentNotFoundException when payment_id exists but belongs to a different partner (ownership enforced). • NUMERIC monetary fields map to String with correct decimal scale (KRW 0 decimals, USD 2 decimals). • cancelled_at null in response when status != CANCELLED. | 35 | 8.5-T01, 8.5-T05 | BE | API-05
8.5-T09 | api-gateway | 8.5 | 8. Partner (Northbound) API | Query/cancel/merchant/balance endpoints | 1 | Implement GetPaymentController @RestController in transaction-mgmt for GET /v1/payments/{id} | The Ops/Partner BFF routes GET /v1/payments/{id} through Spring Cloud Gateway to the Transaction Mgmt service. The @RestController lives in services/transaction-mgmt. Authentication: the partner_id is extracted from the JWT/HMAC security context (Spring Security, @AuthenticationPrincipal PartnerPrincipal). Idempotency-Key is NOT required on GET. SLA: p50 <100ms, p99 <300ms. Return 200 with GetPaymentResponse or 404 with standard lib-errors error envelope. | • Create PaymentQueryController.java annotated @RestController, @RequestMapping("/v1/payments") in services/transaction-mgmt/src/main/java/com/gme/pay/txnmgmt/web/. • Implement GET /{id} method: extract partner_id from @AuthenticationPrincipal, call GetPaymentQueryService.getPayment(id, partnerId), return ResponseEntity<GetPaymentResponse> 200. • Wire @ControllerAdvice (PaymentExceptionHandler) to map PaymentNotFoundException to HTTP 404 with lib-errors error envelope {code: PAYMENT_NOT_FOUND, message, request_id}. • Add @Operation (SpringDoc/OpenAPI) annotation for API docs generation. | services/transaction-mgmt/src/main/java/com/gme/pay/txnmgmt/web/PaymentQueryController.java | • GET /v1/payments/{known-id} returns 200 with full payment object. • GET /v1/payments/{unknown-id} returns 404 with JSON body {error.code: PAYMENT_NOT_FOUND}. • GET /v1/payments/{id-of-other-partner} returns 404 (ownership enforced, not 403 to avoid enumeration). • No Idempotency-Key required; header ignored if present. | 30 | 8.5-T08 | BE | API-05
8.5-T10 | api-gateway | 8.5 | 8. Partner (Northbound) API | Query/cancel/merchant/balance endpoints | 1 | Implement CancelPaymentService core logic in transaction-mgmt | POST /v1/payments/{id}/cancel: cancellable statuses are PENDING and APPROVED; same-day (KST) window only. Steps: (1) load transaction by (payment_id, partner_id) -- 404 if not found; (2) check status in {PENDING, APPROVED} -- 409 if already terminal (FAILED, CANCELLED); (3) check created_at date == today in KST (ZoneId Asia/Seoul) -- 400 CANCEL_NOT_PERMITTED if different day; (4) update status to CANCELLED, set cancelled_at=now(), cancel_reason, cancel_reason_detail; (5) if OVERSEAS partner, return prefunding (atomic: UPDATE prefunding SET balance_usd = balance_usd + ? WHERE partner_id=? within same @Transactional); (6) write outbox event payment.cancelled; (7) return CancelPaymentResponse. | • Create CancelPaymentService.java @Service in services/transaction-mgmt/src/main/java/com/gme/pay/txnmgmt/cancel/. • Annotate service method with @Transactional (Spring); within one DB transaction: load entity, validate status and same-day window, update entity, conditionally credit prefunding via PrefundingClient (Feign/RestClient), insert outbox event. • Implement same-day check: transaction.getCreatedAt().atZone(ZoneId.of("Asia/Seoul")).toLocalDate().equals(LocalDate.now(ZoneId.of("Asia/Seoul"))). • Throw CancelNotPermittedException (400 CANCEL_NOT_PERMITTED) if date mismatch or status not cancellable; throw PaymentAlreadyTerminalException (409) if status is FAILED or CANCELLED. • Insert row into outbox table with event_type=payment.cancelled, payload JSON serialized from CancelPaymentResponse fields. | services/transaction-mgmt/src/main/java/com/gme/pay/txnmgmt/cancel/CancelPaymentService.java | • APPROVED payment with today KST date cancels successfully; status becomes CANCELLED. • PENDING payment with today KST date cancels successfully. • Payment with created_at yesterday KST returns 400 CANCEL_NOT_PERMITTED. • Already CANCELLED payment returns 409. • FAILED payment returns 409. • Prefunding credited for OVERSEAS partner (verified by mock PrefundingClient call). • Outbox row inserted with event_type=payment.cancelled in same transaction. | 45 | 8.5-T06, 8.5-T02 | BE | API-05
8.5-T11 | api-gateway | 8.5 | 8. Partner (Northbound) API | Query/cancel/merchant/balance endpoints | 1 | Implement CancelPaymentController @RestController for POST /v1/payments/{id}/cancel | POST /v1/payments/{id}/cancel in Transaction Mgmt service. Requires Idempotency-Key header (400 MISSING_IDEMPOTENCY_KEY if absent). Idempotency: store (partner_id, idempotency_key, response_body, status) in Redis with 24h TTL; on duplicate key+same-body return cached response; on duplicate key+different-body return 422 IDEMPOTENCY_KEY_REUSE. Extract partner_id from @AuthenticationPrincipal PartnerPrincipal. HMAC signature already validated by Spring Cloud Gateway filter upstream. | • Create or extend PaymentCommandController.java @RestController @RequestMapping("/v1/payments") in services/transaction-mgmt/src/main/java/com/gme/pay/txnmgmt/web/. • Implement POST /{id}/cancel: (a) extract partner_id; (b) check Idempotency-Key header present; (c) check Redis for cached response (RedisTemplate<String,String>, key = partner_id+":"+idempotencyKey); (d) if cached, return cached; (e) else call CancelPaymentService, cache result with 24h TTL. • Map CancelNotPermittedException -> 400, PaymentAlreadyTerminalException -> 409, PaymentNotFoundException -> 404 via @ControllerAdvice. • Return ResponseEntity<CancelPaymentResponse> 200 on success. | services/transaction-mgmt/src/main/java/com/gme/pay/txnmgmt/web/PaymentCommandController.java (POST /{id}/cancel method) | • Missing Idempotency-Key returns 400 MISSING_IDEMPOTENCY_KEY. • Second call with same key+same body returns 200 from Redis cache; CancelPaymentService not called again. • Same key+different body returns 422 IDEMPOTENCY_KEY_REUSE. • Successful cancel returns 200 with status=cancelled and cancelled_at. • OVERSEAS partner response includes prefund_returned_usd; LOCAL partner omits it. | 40 | 8.5-T10 | BE | API-05
8.5-T12 | api-gateway | 8.5 | 8. Partner (Northbound) API | Query/cancel/merchant/balance endpoints | 1 | Prefunding credit-back on cancel -- atomic UPDATE in prefunding service | When a payment is cancelled, prefunding must be credited back for OVERSEAS partners only. The Prefunding service (services/prefunding) owns the prefunding table (PostgreSQL, NUMERIC balance_usd). Credit-back must be atomic: UPDATE prefunding SET balance_usd = balance_usd + :amount WHERE partner_id = :partnerId AND partner_type = 'OVERSEAS'. Also insert a prefunding_deduction_event row with negative amount_usd (indicating return). Both updates in one @Transactional. Expose as PrefundingService.returnFunds(String partnerId, BigDecimal amountUsd, String paymentId). Called by Transaction Mgmt via internal Feign client (same cluster). | • In services/prefunding/src/main/java/com/gme/pay/prefunding/service/PrefundingService.java add method returnFunds(String partnerId, BigDecimal amountUsd, String paymentId). • Within @Transactional: execute UPDATE prefunding SET balance_usd = balance_usd + ? WHERE partner_id = ? AND partner_type = 'OVERSEAS' (JDBC or Spring Data JPA native query); assert rowsUpdated == 1 else throw IllegalStateException. • INSERT into prefunding_deduction_event with amount_usd = -amountUsd (negative), balance_after_usd = new balance (SELECT after update), payment_id, event_at=now(). • Expose via PrefundingController @RestController POST /internal/prefunding/{partnerId}/return for Feign call from transaction-mgmt. | services/prefunding/src/main/java/com/gme/pay/prefunding/service/PrefundingService.java (returnFunds method) + PrefundingController.java (internal endpoint) | • returnFunds on OVERSEAS partner increases balance by exact BigDecimal amount. • LOCAL partner (partner_type != OVERSEAS) results in rowsUpdated=0 and IllegalStateException. • prefunding_deduction_event row has amount_usd = -35.77 for a 35.77 return. • Operation is atomic: concurrent returnFunds and deductFunds on same partner_id produces correct final balance (Testcontainers test with two threads). | 40 | 8.5-T07 | BE | API-05
8.5-T13 | api-gateway | 8.5 | 8. Partner (Northbound) API | Query/cancel/merchant/balance endpoints | 1 | Transactional Outbox event for payment.cancelled in transaction-mgmt | After a successful cancel, a payment.cancelled domain event must be written to the outbox table (in transaction-mgmt PostgreSQL DB) within the same @Transactional as the status update. Outbox pattern: table columns id (UUID), aggregate_id (payment_id), event_type (VARCHAR), payload (JSONB), created_at, published_at (nullable). Published_at set by the outbox poller when delivered. The EventPublisher interface (lib-events) is used -- in Phase 1, it writes to the outbox table; Kafka is wired in integration phase. The payment.cancelled payload matches the webhook schema: {payment_id, partner_txn_ref, reason, prefund_returned_usd, cancelled_at}. | • Confirm outbox table exists (created in earlier epic); if not, create migration V204__outbox.sql with the schema above. • In CancelPaymentService, inject EventPublisher (lib-events interface). • After status update, call eventPublisher.publish(new PaymentCancelledEvent(paymentId, partnerTxnRef, reason, prefundReturnedUsd, cancelledAt)). • Define PaymentCancelledEvent in lib-events/src/main/java/com/gme/pay/events/payment/PaymentCancelledEvent.java with all fields; annotate with @DomainEvent(type=payment.cancelled). • Verify: if outbox INSERT fails, the whole transaction rolls back (no partial cancel). | lib-events/src/main/java/com/gme/pay/events/payment/PaymentCancelledEvent.java + outbox INSERT in CancelPaymentService | • PaymentCancelledEvent serializes to JSON matching the payment.cancelled webhook schema. • If EventPublisher.publish throws, status update is rolled back (transaction atomicity test). • Outbox row has event_type=payment.cancelled and payload with prefund_returned_usd=null for LOCAL partner. • Outbox poller (from lib-events) sets published_at when consumed -- verify in integration smoke test. | 30 | 8.5-T10 | BE | API-05
8.5-T14 | api-gateway | 8.5 | 8. Partner (Northbound) API | Query/cancel/merchant/balance endpoints | 1 | Implement MerchantQueryService in merchant-qr-data service for GET /v1/merchants/{qr} | GET /v1/merchants/{qr} resolves a URL-encoded QR string. The Merchant and QR Data service (services/merchant-qr-data) owns the MongoDB merchant store (CQRS read-model). Collection: merchants. Fields stored: _id (merchant_id), merchant_name, merchant_type, scheme_id, qr_code, status (active¦inactive), payout_currency, address. The qr_code field is indexed. Query: db.merchants.findOne({qr_code: decodedQr}). If not found: 404 MERCHANT_NOT_FOUND. If found but status=inactive: 422 MERCHANT_INACTIVE (maps to spec 422 message). URL-decode the qr path parameter before query. | • Create MerchantQueryService.java @Service in services/merchant-qr-data/src/main/java/com/gme/pay/merchantqr/query/. • Inject MongoTemplate or MerchantRepository (MongoRepository); implement getMerchant(String encodedQr): decode with URLDecoder.decode(encodedQr, UTF_8), query by qr_code field. • Throw MerchantNotFoundException (404 MERCHANT_NOT_FOUND) if no document found. • Throw MerchantInactiveException (422 MERCHANT_INACTIVE) if document found but status != active. • Map MongoDB document to MerchantDetailResponse from lib-api-contracts. | services/merchant-qr-data/src/main/java/com/gme/pay/merchantqr/query/MerchantQueryService.java | • Known active QR returns correct MerchantDetailResponse with all 8 fields. • Unknown QR throws MerchantNotFoundException. • Inactive merchant QR throws MerchantInactiveException. • URL-encoded QR (spaces as %20 or +) decodes correctly before MongoDB query. • address field null when not present in MongoDB document. | 30 | 8.5-T03 | BE | API-05
8.5-T15 | api-gateway | 8.5 | 8. Partner (Northbound) API | Query/cancel/merchant/balance endpoints | 1 | Implement MerchantController @RestController in merchant-qr-data for GET /v1/merchants/{qr} | GET /v1/merchants/{qr} is a read-only endpoint in the Merchant and QR Data service. No Idempotency-Key required. No prefunding involved. Authentication: HMAC-SHA256 validated by Spring Cloud Gateway upstream; partner_id available in security context but no ownership restriction (any authenticated partner can resolve any QR). HTTP 200 = active merchant found; 404 = MERCHANT_NOT_FOUND; 422 = merchant inactive or QR deactivated. SLA: p50 <200ms (MongoDB lookup from local read-model). | • Create MerchantController.java @RestController @RequestMapping("/v1/merchants") in services/merchant-qr-data/src/main/java/com/gme/pay/merchantqr/web/. • Implement GET /{qr} method; @PathVariable String qr passed to MerchantQueryService.getMerchant(qr). • Add @ControllerAdvice mapping MerchantNotFoundException -> 404, MerchantInactiveException -> 422 using lib-errors error envelope. • Return ResponseEntity<MerchantDetailResponse> 200. • Add @Operation annotation for OpenAPI. | services/merchant-qr-data/src/main/java/com/gme/pay/merchantqr/web/MerchantController.java | • GET /v1/merchants/ZPQR00012345678901234567890 returns 200 with merchant JSON. • GET /v1/merchants/UNKNOWN returns 404 JSON {error.code: MERCHANT_NOT_FOUND}. • GET /v1/merchants/{inactive-qr} returns 422 JSON. • URL-encoded path segment decoded before service call. | 25 | 8.5-T14 | BE | API-05
8.5-T16 | api-gateway | 8.5 | 8. Partner (Northbound) API | Query/cancel/merchant/balance endpoints | 1 | Ensure MongoDB index on qr_code field in merchant-qr-data collection | GET /v1/merchants/{qr} queries MongoDB by qr_code. Without an index, this is a full collection scan. The merchant collection lives in the Merchant and QR Data service MongoDB. Index must be created on application startup via Spring Data MongoDB @Document + @Indexed or via a MongoMigration/ChangeSet (Mongock library, used in this service). QR codes are unique per scheme. | • In services/merchant-qr-data/src/main/java/com/gme/pay/merchantqr/domain/MerchantDocument.java, add @Indexed(unique=false) on qrCode field (unique=false because different schemes may reuse code format, uniqueness is enforced per scheme_id). • Alternatively, create a Mongock ChangeSet V004_MerchantQrIndex adding db.merchants.createIndex({qr_code:1}) with background:true. • Write integration test (Testcontainers MongoDB) verifying that explain() on {qr_code: value} uses IXSCAN not COLLSCAN. | services/merchant-qr-data/src/main/java/com/gme/pay/merchantqr/domain/MerchantDocument.java (annotated) OR Mongock ChangeSet V004 | • explain() on qr_code query shows IXSCAN. • Index created automatically on app startup without manual intervention. • Duplicate qr_code for same scheme_id detected only at application layer (DB index is non-unique). | 20 | 8.5-T14 | BE | API-05
8.5-T17 | api-gateway | 8.5 | 8. Partner (Northbound) API | Query/cancel/merchant/balance endpoints | 1 | Implement BalanceQueryService in prefunding service for GET /v1/balance | GET /v1/balance returns current prefunding for OVERSEAS partners only. LOCAL partners get 403 FORBIDDEN. Service reads: (1) prefunding table in PostgreSQL (balance_usd NUMERIC, low_balance_threshold_usd NUMERIC, partner_type); (2) optionally prefunding_deduction_event last 10 rows when include_history=true. is_below_threshold = balance_usd < low_balance_threshold_usd. as_of = current DB server time (CURRENT_TIMESTAMP). Partner type checked from partner_type column in prefunding or from JWT claim. Return BalanceResponse from lib-api-contracts. | • Create BalanceQueryService.java @Service in services/prefunding/src/main/java/com/gme/pay/prefunding/query/. • Load prefunding row by partner_id using PrefundingRepository; if partner_type != OVERSEAS throw PartnerForbiddenException (403 FORBIDDEN). • Compute is_below_threshold = balance_usd.compareTo(low_balance_threshold_usd) < 0. • If includeHistory=true, query prefunding_deduction_event WHERE partner_id=? ORDER BY event_at DESC LIMIT 10. • Map to BalanceResponse, setting recent_deductions to null when includeHistory=false. | services/prefunding/src/main/java/com/gme/pay/prefunding/query/BalanceQueryService.java | • OVERSEAS partner with balance_usd=48234.56 and threshold=10000 returns is_below_threshold=false. • OVERSEAS partner with balance_usd=9999.00 and threshold=10000 returns is_below_threshold=true. • LOCAL partner throws PartnerForbiddenException (403). • include_history=true returns exactly 10 most-recent events when 20 exist. • include_history=false (default) returns recent_deductions=null (omitted from JSON). | 30 | 8.5-T04, 8.5-T07 | BE | API-05
8.5-T18 | api-gateway | 8.5 | 8. Partner (Northbound) API | Query/cancel/merchant/balance endpoints | 1 | Implement BalanceController @RestController in prefunding service for GET /v1/balance | GET /v1/balance in Prefunding service (services/prefunding). No Idempotency-Key required (GET). Query param include_history (boolean, default false). Partner_id from @AuthenticationPrincipal. 200 = balance returned; 403 = LOCAL partner. Error envelope via lib-errors. SLA: p50 <200ms (single PostgreSQL read). | • Create BalanceController.java @RestController @RequestMapping("/v1") in services/prefunding/src/main/java/com/gme/pay/prefunding/web/. • Implement GET /balance with @RequestParam(defaultValue="false") boolean includeHistory, @AuthenticationPrincipal PartnerPrincipal principal. • Call BalanceQueryService.getBalance(principal.getPartnerId(), includeHistory). • Map PartnerForbiddenException -> 403 via @ControllerAdvice with lib-errors envelope {code: FORBIDDEN}. • Return ResponseEntity<BalanceResponse> 200. | services/prefunding/src/main/java/com/gme/pay/prefunding/web/BalanceController.java | • OVERSEAS partner GET /v1/balance returns 200 with balance JSON. • LOCAL partner returns 403 {error.code: FORBIDDEN}. • GET /v1/balance?include_history=true returns recent_deductions array. • GET /v1/balance (no param) returns recent_deductions absent from JSON. | 25 | 8.5-T17 | BE | API-05
8.5-T19 | api-gateway | 8.5 | 8. Partner (Northbound) API | Query/cancel/merchant/balance endpoints | 1 | Spring Cloud Gateway routing rules for WBS 8.5 endpoints | Spring Cloud Gateway (edge service, services/gateway) routes: GET /v1/payments/{id} -> transaction-mgmt; POST /v1/payments/{id}/cancel -> transaction-mgmt; GET /v1/merchants/{qr} -> merchant-qr-data; GET /v1/balance -> prefunding. HMAC-SHA256 signature validation filter is already wired on all /v1/** routes. Idempotency-Key validation filter: enforce header present on all POST /v1/** routes (return 400 MISSING_IDEMPOTENCY_KEY if absent). Rate limiting: Redis-based (Spring Cloud Gateway RequestRateLimiter filter, key = partner_id from JWT). | • In services/gateway/src/main/resources/application.yml, add route entries under spring.cloud.gateway.routes for the 4 new endpoints with uri: lb://transaction-mgmt, lb://merchant-qr-data, lb://prefunding respectively. • Add predicates: Path, Method filters. • Confirm HmacValidationGatewayFilter is applied globally (already exists from earlier epic). • Verify IdempotencyKeyGatewayFilter applies only to POST routes (add predicate Method=POST). • Write @SpringBootTest gateway integration test with WireMock stubs for downstream services verifying routing. | services/gateway/src/main/resources/application.yml (new route entries) | • GET /v1/payments/{id} routes to transaction-mgmt (WireMock stub returns 200). • POST /v1/payments/{id}/cancel without Idempotency-Key returns 400 at gateway level. • GET /v1/merchants/{qr} routes to merchant-qr-data. • GET /v1/balance routes to prefunding. • HMAC signature validation still fires for all 4 routes. | 35 | 8.5-T09, 8.5-T11, 8.5-T15, 8.5-T18 | BE | API-05
8.5-T20 | api-gateway | 8.5 | 8. Partner (Northbound) API | Query/cancel/merchant/balance endpoints | 1 | Unit tests for GetPaymentQueryService -- ownership and status mapping | Test the GetPaymentQueryService in services/transaction-mgmt. Use JUnit 5 + Mockito (no DB needed). Three test scenarios: (1) happy path with status=APPROVED; (2) payment not found (404); (3) ownership violation (payment belongs to different partner). Also test each PaymentStatus enum value mapping. Use exact spec example values: payment_id=pay_01HX7MNQ5ABCDEF123456789, target_payout=50000, payout_currency=KRW, offer_rate=0.000703, collection_amount=35.77, collection_currency=USD, service_charge=0.35. | • Create GetPaymentQueryServiceTest.java in services/transaction-mgmt/src/test/java/com/gme/pay/txnmgmt/query/. • Mock TransactionRepository; stub findByPaymentIdAndPartnerId to return Optional.of(entity) with spec example values. • Assert returned GetPaymentResponse fields match exactly (target_payout="50000", offer_rate="0.000703"). • Test not-found: stub returns Optional.empty(); assert PaymentNotFoundException thrown. • Test each status: PENDING, APPROVED, FAILED, CANCELLED, UNCERTAIN mapped to correct PaymentStatus enum. | services/transaction-mgmt/src/test/java/com/gme/pay/txnmgmt/query/GetPaymentQueryServiceTest.java | • Happy path: target_payout string equals "50000" (KRW, 0 decimals, no trailing .0). • offer_rate string equals "0.000703". • PaymentNotFoundException thrown for unknown payment_id. • All 5 status values map correctly. • cancelled_at null when status != CANCELLED. | 30 | 8.5-T08 | BE | API-05
8.5-T21 | api-gateway | 8.5 | 8. Partner (Northbound) API | Query/cancel/merchant/balance endpoints | 1 | Unit tests for CancelPaymentService -- same-day KST window and status guards | Test CancelPaymentService in transaction-mgmt. Use JUnit 5 + Mockito + a fixed Clock injected into the service (use Clock.fixed(..., ZoneOffset.UTC) to control now()). Test vectors: (1) APPROVED payment, created today KST -> success; (2) APPROVED payment, created yesterday KST -> CANCEL_NOT_PERMITTED; (3) CANCELLED payment -> 409; (4) FAILED payment -> 409; (5) PENDING payment, today KST -> success; (6) OVERSEAS partner -> prefunding return called; (7) LOCAL partner -> prefunding return NOT called. Inject Clock via constructor for testability. | • Refactor CancelPaymentService to accept Clock dependency (constructor injection, default Clock.systemDefaultZone()). • Create CancelPaymentServiceTest.java in services/transaction-mgmt/src/test/java/com/gme/pay/txnmgmt/cancel/. • Use Clock.fixed(Instant.parse("2026-06-05T01:00:00Z"), ZoneOffset.UTC) so today KST = 2026-06-05. Set created_at to 2026-06-04T16:00:00Z (which is 2026-06-05 01:00 KST -- same day) for passing test. • For yesterday test: set created_at to 2026-06-04T14:59:00Z (= 2026-06-04 23:59 KST -- previous day). • Assert EventPublisher.publish called once on success; not called on rejection. | services/transaction-mgmt/src/test/java/com/gme/pay/txnmgmt/cancel/CancelPaymentServiceTest.java | • Today-KST cancellation succeeds; cancelled_at set to now(). • Yesterday-KST throws CancelNotPermittedException with code CANCEL_NOT_PERMITTED. • CANCELLED status throws PaymentAlreadyTerminalException (409). • OVERSEAS partner: PrefundingClient.returnFunds called with exact collection_usd amount. • LOCAL partner: PrefundingClient.returnFunds NOT called. • EventPublisher.publish called exactly once per successful cancel. | 40 | 8.5-T10 | BE | API-05
8.5-T22 | api-gateway | 8.5 | 8. Partner (Northbound) API | Query/cancel/merchant/balance endpoints | 1 | Unit tests for MerchantQueryService -- active, inactive, not-found, URL-decode | Test MerchantQueryService in merchant-qr-data service. Use JUnit 5 + Mockito + Embedded MongoDB (Flapdoodle) or plain Mockito mock of MerchantRepository. Test vectors: (1) active merchant found by qr_code; (2) inactive merchant found but throws MerchantInactiveException; (3) unknown QR throws MerchantNotFoundException; (4) URL-encoded QR (ZPQR%20001) decodes to ZPQR 001 before query. Check all 8 response fields with spec example values: merchant_id=mch_01HX7MNQ9ABC, merchant_name=Seoul Coffee House, payout_currency=KRW. | • Create MerchantQueryServiceTest.java in services/merchant-qr-data/src/test/java/com/gme/pay/merchantqr/query/. • Mock MerchantRepository (or MongoTemplate); stub findByQrCode("ZPQR00012345678901234567890") to return active MerchantDocument with spec values. • Assert MerchantDetailResponse.merchantName().equals("Seoul Coffee House") and payoutCurrency().equals("KRW"). • Stub findByQrCode for inactive doc; assert MerchantInactiveException. • Test URL decode: pass encoded "ZPQR%2000012345678901234567890"; stub matching decoded string. | services/merchant-qr-data/src/test/java/com/gme/pay/merchantqr/query/MerchantQueryServiceTest.java | • Active merchant: all 8 fields correct per spec example. • Inactive merchant: MerchantInactiveException thrown. • Unknown QR: MerchantNotFoundException thrown. • URL-encoded QR decoded before repository query. • address null in response when MongoDB document has no address field. | 30 | 8.5-T14 | BE | API-05
8.5-T23 | api-gateway | 8.5 | 8. Partner (Northbound) API | Query/cancel/merchant/balance endpoints | 1 | Unit tests for BalanceQueryService -- OVERSEAS/LOCAL, threshold logic, history | Test BalanceQueryService in prefunding service. JUnit 5 + Mockito. Test vectors: (1) OVERSEAS partner, balance=48234.56, threshold=10000.00, is_below_threshold=false; (2) OVERSEAS partner, balance=9999.00, threshold=10000.00, is_below_threshold=true; (3) LOCAL partner throws PartnerForbiddenException; (4) include_history=true returns last 10 deduction events; (5) include_history=false returns null recent_deductions. Use BigDecimal arithmetic -- no floating point. | • Create BalanceQueryServiceTest.java in services/prefunding/src/test/java/com/gme/pay/prefunding/query/. • Mock PrefundingRepository and DeductionEventRepository (Spring Data JPA). • Stub prefunding row with balance_usd=new BigDecimal("48234.56"), low_balance_threshold_usd=new BigDecimal("10000.00"), partner_type=OVERSEAS. • Assert is_below_threshold = (balance_usd.compareTo(threshold) < 0); equals false for above vector, true for 9999.00. • Stub 20 deduction events; verify findTop10ByPartnerIdOrderByEventAtDesc returns exactly 10. | services/prefunding/src/test/java/com/gme/pay/prefunding/query/BalanceQueryServiceTest.java | • balance=48234.56, threshold=10000.00 -> is_below_threshold=false. • balance=9999.00, threshold=10000.00 -> is_below_threshold=true. • LOCAL partner throws PartnerForbiddenException. • include_history=true -> 10 events returned (when 20 exist). • include_history=false -> recent_deductions is null. | 25 | 8.5-T17 | BE | API-05
8.5-T24 | api-gateway | 8.5 | 8. Partner (Northbound) API | Query/cancel/merchant/balance endpoints | 1 | Unit tests for prefunding credit-back atomicity in CancelPaymentService (concurrent test) | Verify that when CancelPaymentService is called concurrently for two different payments by the same OVERSEAS partner, the prefunding balance converges correctly. Use Testcontainers (PostgreSQL 16) with two threads each cancelling a separate APPROVED payment (each with collection_usd=35.77). Initial balance=200.00. After both cancels, balance must be 200.00+35.77+35.77=271.54. Also verify that if prefunding UPDATE fails mid-transaction, the transaction status update rolls back (inject fault via spy). | • Create CancelPaymentConcurrencyTest.java in services/transaction-mgmt/src/test/java/com/gme/pay/txnmgmt/cancel/ annotated @Testcontainers @SpringBootTest. • Seed PostgreSQL (Testcontainers) with partner balance=200.00 and two APPROVED payments each with collection_usd=35.77 created today KST. • Submit two concurrent CancelPaymentService.cancel() calls via ExecutorService.invokeAll(). • Assert final balance = 271.54 (BigDecimal.compareTo). • Inject fault in PrefundingClient: throw RuntimeException after status update but before prefunding credit; assert transaction rolled back (status remains APPROVED, balance unchanged). | services/transaction-mgmt/src/test/java/com/gme/pay/txnmgmt/cancel/CancelPaymentConcurrencyTest.java | • Concurrent dual cancel: final balance == 271.54. • Neither payment is double-credited. • Fault injection: transaction status rolled back when prefunding credit fails. • Balance unchanged when rollback occurs. | 45 | 8.5-T10, 8.5-T12 | BE | API-05
8.5-T25 | api-gateway | 8.5 | 8. Partner (Northbound) API | Query/cancel/merchant/balance endpoints | 1 | Testcontainers integration test for GET /v1/payments/{id} slice | End-to-end Spring Boot test slice for the payment query flow in transaction-mgmt. Use @SpringBootTest + Testcontainers (PostgreSQL 16) + MockMvc. Seed a CANCELLED payment row (with cancelled_at set) and an APPROVED payment row owned by partner prt_sendmn_001. Test: (1) GET /v1/payments/{approved-id} with correct auth -> 200 all fields; (2) GET /v1/payments/{cancelled-id} -> 200 includes cancelled_at; (3) GET /v1/payments/{id-of-other-partner} -> 404; (4) GET /v1/payments/nonexistent -> 404. Auth stub via Spring Security test support (@WithMockUser or custom PartnerPrincipal). | • Create GetPaymentIntegrationTest.java in services/transaction-mgmt/src/test/java/com/gme/pay/txnmgmt/web/. • Annotate @SpringBootTest(webEnvironment=RANDOM_PORT) @Testcontainers; define @Container PostgreSQLContainer. • Seed test data via JdbcTemplate in @BeforeEach. • Use MockMvc or TestRestTemplate; set Authorization header with test JWT containing partner_id=prt_sendmn_001. • Assert response JSON with jsonPath: $.payment_id, $.status, $.cancelled_at present/absent. | services/transaction-mgmt/src/test/java/com/gme/pay/txnmgmt/web/GetPaymentIntegrationTest.java | • Approved payment: 200, status=approved, cancelled_at absent from JSON. • Cancelled payment: 200, status=cancelled, cancelled_at present. • Other partner's payment: 404 PAYMENT_NOT_FOUND. • Nonexistent payment: 404 PAYMENT_NOT_FOUND. | 40 | 8.5-T09, 8.5-T05 | BE | API-05
8.5-T26 | api-gateway | 8.5 | 8. Partner (Northbound) API | Query/cancel/merchant/balance endpoints | 1 | Testcontainers integration test for POST /v1/payments/{id}/cancel slice | Integration test for cancel flow in transaction-mgmt. Use @SpringBootTest + Testcontainers (PostgreSQL 16) + WireMock (for PrefundingClient HTTP call) + MockMvc. Test: (1) cancel APPROVED OVERSEAS payment today KST -> 200, prefund_returned_usd=35.77, WireMock stub confirms prefunding return call made; (2) cancel already-CANCELLED -> 409; (3) cancel next-day payment -> 400 CANCEL_NOT_PERMITTED; (4) missing Idempotency-Key -> 400; (5) same key + same body second call -> 200 from Redis cache. Use Redis Testcontainer for idempotency check. | • Create CancelPaymentIntegrationTest.java in services/transaction-mgmt/src/test/java/com/gme/pay/txnmgmt/web/. • @Testcontainers with PostgreSQLContainer + @Container RedisContainer (Testcontainers Redis). • Stub PrefundingClient with WireMock (@WireMockTest or WireMockServer): POST /internal/prefunding/prt_sendmn_001/return returns 200. • Seed APPROVED OVERSEAS payment with collection_usd=35.77, created_at=today 00:30 KST. • Run all 5 test scenarios; assert WireMock received exactly 1 call for scenario 5 (second call uses cache). | services/transaction-mgmt/src/test/java/com/gme/pay/txnmgmt/web/CancelPaymentIntegrationTest.java | • 200 cancel: prefund_returned_usd=35.77, status=cancelled. • 409 on already-cancelled payment. • 400 CANCEL_NOT_PERMITTED on next-day payment. • 400 MISSING_IDEMPOTENCY_KEY when header absent. • Duplicate idempotency key: WireMock receives 0 second calls (cache used). | 45 | 8.5-T11, 8.5-T12 | BE | API-05
8.5-T27 | api-gateway | 8.5 | 8. Partner (Northbound) API | Query/cancel/merchant/balance endpoints | 1 | Testcontainers integration test for GET /v1/merchants/{qr} slice | Integration test for merchant QR resolution in merchant-qr-data service. Use @SpringBootTest + Testcontainers (MongoDB) + MockMvc. Seed 3 merchant documents: (1) active merchant ZPQR00012345678901234567890; (2) inactive merchant ZPQR_INACTIVE; (3) no address field. Test: 200 active, 422 inactive, 404 unknown QR, URL-encoded QR decoded correctly. | • Create MerchantQueryIntegrationTest.java in services/merchant-qr-data/src/test/java/com/gme/pay/merchantqr/web/. • Use MongoDBContainer from Testcontainers; seed via MongoTemplate.insert() in @BeforeEach. • Test GET /v1/merchants/ZPQR00012345678901234567890 -> 200, merchant_name=Seoul Coffee House. • Test GET /v1/merchants/ZPQR_INACTIVE -> 422. • Test GET /v1/merchants/UNKNOWN -> 404 MERCHANT_NOT_FOUND. • Test GET /v1/merchants/ZPQR%3D001 (URL-encoded = sign) decoded and queried correctly. | services/merchant-qr-data/src/test/java/com/gme/pay/merchantqr/web/MerchantQueryIntegrationTest.java | • Active QR: 200 merchant_name=Seoul Coffee House, payout_currency=KRW. • Inactive QR: 422 response. • Unknown QR: 404 MERCHANT_NOT_FOUND. • URL-encoded QR resolves to correct merchant. • address absent from JSON when not seeded. | 35 | 8.5-T15, 8.5-T16 | BE | API-05
8.5-T28 | api-gateway | 8.5 | 8. Partner (Northbound) API | Query/cancel/merchant/balance endpoints | 1 | Testcontainers integration test for GET /v1/balance slice | Integration test for balance endpoint in prefunding service. Use @SpringBootTest + Testcontainers (PostgreSQL 16) + MockMvc. Seed: OVERSEAS partner prt_sendmn_001 with balance_usd=48234.56, threshold=10000.00; LOCAL partner prt_gmere_001 with partner_type=LOCAL; 15 deduction events for prt_sendmn_001. Test: 200 OVERSEAS, 200 with include_history, 403 LOCAL, is_below_threshold logic. | • Create BalanceIntegrationTest.java in services/prefunding/src/test/java/com/gme/pay/prefunding/web/. • PostgreSQLContainer; seed prefunding and prefunding_deduction_event tables. • Test GET /v1/balance (OVERSEAS partner) -> 200, balance_usd=48234.56, is_below_threshold=false, recent_deductions absent. • Test GET /v1/balance?include_history=true -> recent_deductions has exactly 10 elements. • Test GET /v1/balance with LOCAL partner auth -> 403 {error.code: FORBIDDEN}. | services/prefunding/src/test/java/com/gme/pay/prefunding/web/BalanceIntegrationTest.java | • balance_usd=48234.56 returned as string. • is_below_threshold=false for 48234.56 > 10000.00. • include_history=true returns exactly 10 most-recent events (15 seeded). • LOCAL partner: 403 FORBIDDEN. • recent_deductions absent (not null, omitted) when include_history=false. | 35 | 8.5-T18 | BE | API-05
8.5-T29 | api-gateway | 8.5 | 8. Partner (Northbound) API | Query/cancel/merchant/balance endpoints | 1 | OpenAPI spec update in openapi/partner-api.yaml for WBS 8.5 endpoints | The authoritative OpenAPI spec at openapi/partner-api.yaml (root of monorepo) must be updated with the 4 new endpoint definitions: GET /v1/payments/{id}, POST /v1/payments/{id}/cancel, GET /v1/merchants/{qr}, GET /v1/balance. Each endpoint must include: summary, operationId, security (hmacAuth), request parameters, response schemas referencing lib-api-contracts DTOs, and all error responses (400/403/404/409/422 as applicable). This spec is the source of truth for lib-api-contracts code generation. | • Open openapi/partner-api.yaml; locate the paths section after existing payment paths. • Add path /v1/payments/{id}: get with operationId getPayment, parameter id (path, string, required), responses 200 (schema $ref GetPaymentResponse), 404 ($ref ErrorResponse). • Add path /v1/payments/{id}/cancel: post with operationId cancelPayment, requestBody $ref CancelPaymentRequest, Idempotency-Key header param, responses 200/400/404/409. • Add path /v1/merchants/{qr}: get operationId resolveMerchantQr, responses 200/404/422. • Add path /v1/balance: get operationId getPrefundingBalance, query param include_history (boolean, default false), responses 200/403. | openapi/partner-api.yaml (updated with 4 new path entries) | • openapi-generator validate passes with no errors on the updated YAML. • All 4 new paths present in rendered Swagger UI. • CancelPaymentRequest reason field shows enum [customer_request,merchant_request,timeout,other]. • GET /v1/balance shows 403 response schema with ErrorResponse. • include_history query param shows default=false in spec. | 40 | 8.5-T01, 8.5-T02, 8.5-T03, 8.5-T04 | BE | API-05
8.5-T30 | api-gateway | 8.5 | 8. Partner (Northbound) API | Query/cancel/merchant/balance endpoints | 1 | Webhook payment.cancelled event outbox poller and delivery verification | The outbox poller (in lib-events or transaction-mgmt) periodically reads unpublished rows from the outbox table (event_type=payment.cancelled) and delivers them to the Notification and Webhook service (services/notification-webhook) via the EventPublisher interface. In Phase 1 this is in-process polling (not Kafka). The notification service then calls the partner's registered webhook_url via HTTP POST with the payment.cancelled payload, including HMAC-SHA256 signature header X-GME-Webhook-Signature. Delivery follows 10-attempt exponential back-off: 0s, 30s, 2m, 10m, 30m, 1h*5. | • In services/notification-webhook/src/main/java/com/gme/pay/notifwebhook/delivery/WebhookDeliveryService.java, add handler for PaymentCancelledEvent event type. • Build HTTP POST payload matching payment.cancelled schema; sign with HMAC-SHA256(body, webhookSigningSecret) and set X-GME-Webhook-Signature: sha256=<sig> header. • Implement retry scheduling using Spring @Scheduled or existing back-off framework; mark outbox row published_at on first 2xx response; mark delivery_failed after 10 attempts. • Write WebhookDeliveryServiceTest using WireMock: (a) 2xx on first attempt sets published_at; (b) 5xx triggers retry; (c) after 10 failures marks delivery_failed. | services/notification-webhook/src/main/java/com/gme/pay/notifwebhook/delivery/WebhookDeliveryService.java (payment.cancelled handler) | • Webhook POST body matches payment.cancelled schema exactly. • X-GME-Webhook-Signature header computed as sha256=HMAC-SHA256(body, secret). • 2xx response: outbox row published_at set; no retry scheduled. • 5xx response: retry with 30s delay (mocked scheduler asserted). • After 10 failures: delivery_failed status set; GME Ops alert triggered (log or event). | 45 | 8.5-T13 | BE | API-05
8.6-T01 | notification-webhook | 8.6 | 8. Partner (Northbound) API | Webhooks: events, signing, retry | 1 | Create Flyway migration V30__webhook_outbox.sql in notification-webhook service | The notification-webhook service (module: services/notification-webhook) uses PostgreSQL 16 for the transactional Outbox pattern. Domain events are written atomically with the business transaction, then polled and dispatched. We need: outbox_event table (id BIGSERIAL PK, aggregate_type VARCHAR(50), aggregate_id VARCHAR(100), event_type VARCHAR(100), payload JSONB NOT NULL, status VARCHAR(20) DEFAULT pending CHECK (status IN (pending,processing,delivered,failed,dlq)), attempts INT DEFAULT 0, next_attempt_at TIMESTAMPTZ, created_at TIMESTAMPTZ DEFAULT now(), processed_at TIMESTAMPTZ). Also webhook_delivery_attempt table (id BIGSERIAL PK, outbox_event_id BIGINT FK -> outbox_event, partner_id BIGINT, attempt_number INT, http_status INT, response_body TEXT, attempted_at TIMESTAMPTZ DEFAULT now(), duration_ms INT). Index: outbox_event(status, next_attempt_at) WHERE status IN (pending,processing). | • Create services/notification-webhook/src/main/resources/db/migration/V30__webhook_outbox.sql • Add CREATE TABLE outbox_event with all columns and CHECK constraint on status • Add CREATE TABLE webhook_delivery_attempt with FK to outbox_event • Add partial index idx_outbox_event_pending on outbox_event(status, next_attempt_at) WHERE status IN (pending, processing) • Add CREATE TABLE webhook_dlq (id BIGSERIAL PK, outbox_event_id BIGINT FK, partner_id BIGINT, event_type VARCHAR(100), payload JSONB, failure_reason TEXT, dlq_at TIMESTAMPTZ DEFAULT now(), resolved_at TIMESTAMPTZ, resolved_by VARCHAR(100)) | services/notification-webhook/src/main/resources/db/migration/V30__webhook_outbox.sql | • Flyway applies migration without error on clean Testcontainers Postgres 16 instance • outbox_event.status CHECK constraint rejects any value outside (pending, processing, delivered, failed, dlq) • Partial index exists in pg_indexes for outbox_event WHERE status IN (pending, processing) • webhook_delivery_attempt.outbox_event_id FK references outbox_event(id) with ON DELETE CASCADE • webhook_dlq table has NOT NULL on outbox_event_id and event_type | 30 |  | BE | API-05
8.6-T02 | notification-webhook | 8.6 | 8. Partner (Northbound) API | Webhooks: events, signing, retry | 1 | Create Flyway migration V31__partner_webhook_config.sql for partner_webhook table | The partner_webhook table stores per-partner webhook endpoint configuration per DAT-03 and API-05: id BIGINT PK, partner_id BIGINT FK -> partner NOT NULL, webhook_url VARCHAR(512) NOT NULL, event_types TEXT (comma-separated, null = all events), signing_secret_hash VARCHAR(128) NOT NULL (Argon2 hash of HMAC signing secret), is_active BOOLEAN NOT NULL DEFAULT true, created_at/updated_at TIMESTAMPTZ, created_by/updated_by VARCHAR(100). Webhook URLs must be HTTPS only enforced via CHECK constraint. UNIQUE(partner_id, webhook_url). Partial index for active endpoints. The signing secret plaintext is never stored in DB - only its Argon2 hash; plaintext lives in Vault. | • Create services/notification-webhook/src/main/resources/db/migration/V31__partner_webhook_config.sql • Add CREATE TABLE partner_webhook with all columns and CHECK (webhook_url LIKE https://%) and UNIQUE(partner_id, webhook_url) • Add index idx_partner_webhook_partner_active on partner_webhook(partner_id) WHERE is_active = true • Add COMMENT ON COLUMN partner_webhook.signing_secret_hash explaining Argon2 hash only - never plaintext | services/notification-webhook/src/main/resources/db/migration/V31__partner_webhook_config.sql | • CHECK constraint rejects http:// and ftp:// URLs • UNIQUE(partner_id, webhook_url) prevents duplicate registration • Partial index for is_active=true exists in pg_indexes • signing_secret_hash column length is 128 • FK to partner table enforced: inserting orphan partner_id fails with FK violation | 25 | 8.6-T01 | BE | API-05
8.6-T03 | notification-webhook | 8.6 | 8. Partner (Northbound) API | Webhooks: events, signing, retry | 1 | Define WebhookEvent envelope and payload Java records in lib-events module | lib-events (Gradle module: lib-events) holds all shared domain event schemas. For WBS 8.6 define: WebhookEventEnvelope record (event_id String, event_type String, created_at Instant, partner_id String, data Object) with @JsonInclude(NON_NULL). Five payload records: PaymentApprovedPayload (payment_id, partner_txn_ref, scheme_txn_id, merchant_id, merchant_name, direction, scheme_id, target_payout BigDecimal, payout_currency, offer_rate BigDecimal, collection_amount BigDecimal, collection_currency, service_charge BigDecimal, service_charge_currency, prefund_deducted_usd BigDecimal, approved_at Instant), PaymentPendingDebitPayload, PaymentFailedPayload (payment_id, partner_txn_ref, failure_code, failure_message, prefund_returned_usd BigDecimal, failed_at Instant), PaymentCancelledPayload, SettlementCompletedPayload. All BigDecimal fields use @JsonSerialize(using=ToStringSerializer.class). WebhookEventType enum with PAYMENT_APPROVED etc. and getEventTypeString() returning dot-notation. | • Create lib-events/src/main/java/com/gme/pay/events/webhook/WebhookEventEnvelope.java as Java record with Jackson annotations • Create WebhookEventType.java enum with getEventTypeString() returning payment.approved etc. • Create all five payload Java records in lib-events/src/main/java/com/gme/pay/events/webhook/payload/ • Annotate all BigDecimal fields with @JsonSerialize(using=ToStringSerializer.class) • Add unit test WebhookEventEnvelopeSerializationTest verifying round-trip Jackson serialization preserves BigDecimal precision | lib-events/src/main/java/com/gme/pay/events/webhook/WebhookEventEnvelope.java and five payload classes | • Round-trip Jackson serialize/deserialize of PaymentApprovedPayload preserves BigDecimal to 8 decimal places • WebhookEventType.PAYMENT_APPROVED.getEventTypeString() returns exactly payment.approved • PaymentFailedPayload with null prefund_returned_usd serializes to absent field via NON_NULL • All payload records are immutable (no setters, only all-args constructor via record) • Unit test passes with JUnit 5 and no Spring context | 40 |  | BE | API-05
8.6-T04 | notification-webhook | 8.6 | 8. Partner (Northbound) API | Webhooks: events, signing, retry | 1 | Define OutboxEvent JPA entity and OutboxEventRepository in notification-webhook service | notification-webhook (module: services/notification-webhook) uses Spring Data JPA backed by PostgreSQL 16. OutboxEvent @Entity maps to outbox_event table from V30 migration. Fields: id Long, aggregateType String, aggregateId String, eventType String, payload String (JSONB stored as text), status OutboxEventStatus enum (PENDING,PROCESSING,DELIVERED,FAILED,DLQ) with @Enumerated(STRING), attempts int, nextAttemptAt Instant, createdAt Instant, processedAt Instant. OutboxEventRepository extends JpaRepository. Add @Lock(PESSIMISTIC_WRITE) @QueryHints(@QueryHint(name=javax.persistence.lock.timeout, value=3000)) @Query to find next batch of up to 50 PENDING rows with nextAttemptAt <= :now SKIP LOCKED equivalent. Also add WebhookDeliveryAttempt and WebhookDlqEvent @Entity classes. | • Create services/notification-webhook/src/main/java/com/gme/pay/notify/outbox/OutboxEvent.java @Entity @Table(name=outbox_event) with all fields • Create OutboxEventStatus.java enum with values PENDING, PROCESSING, DELIVERED, FAILED, DLQ • Create OutboxEventRepository.java extending JpaRepository with @Lock(PESSIMISTIC_WRITE) findNextBatch query • Create WebhookDeliveryAttempt.java @Entity mapping webhook_delivery_attempt table • Create WebhookDlqEvent.java @Entity mapping webhook_dlq table | services/notification-webhook/src/main/java/com/gme/pay/notify/outbox/OutboxEvent.java and OutboxEventRepository.java | • @Entity maps to table outbox_event verified by Spring @DataJpaTest slice with Testcontainers Postgres 16 • findNextBatch returns only PENDING rows with nextAttemptAt <= Instant.now() • @Lock(PESSIMISTIC_WRITE) prevents two concurrent callers picking same row (verified in two-thread Testcontainers test) • OutboxEventStatus enum values exactly match SQL CHECK constraint: PENDING PROCESSING DELIVERED FAILED DLQ • Inserting OutboxEvent with invalid status string throws DataIntegrityViolationException | 45 | 8.6-T01 | BE | API-05
8.6-T05 | notification-webhook | 8.6 | 8. Partner (Northbound) API | Webhooks: events, signing, retry | 1 | Implement EventPublisher interface and OutboxEventPublisher in lib-events and notification-webhook | Per STACK.md Phase 1 messaging strategy: all domain events flow through an EventPublisher interface so Kafka can be wired later without rework. Define in lib-events: interface EventPublisher { void publish(String aggregateType, String aggregateId, String eventType, Object payload); }. OutboxEventPublisher @Service @Primary in services/notification-webhook implements this: serializes payload to JSON via Jackson ObjectMapper, persists OutboxEvent with status=PENDING and nextAttemptAt=Instant.now(). Annotate publish() with @Transactional(propagation=MANDATORY) to enforce atomicity with the calling transaction. Provide NullOutboxEventPublisher @Profile(test) no-op for test profiles. | • Create lib-events/src/main/java/com/gme/pay/events/EventPublisher.java interface with publish() method • Create services/notification-webhook/src/main/java/com/gme/pay/notify/outbox/OutboxEventPublisher.java @Service @Primary implementing EventPublisher • Inject OutboxEventRepository and ObjectMapper; serialize payload; persist OutboxEvent with PENDING status • Annotate publish() with @Transactional(propagation=MANDATORY) • Create NullOutboxEventPublisher.java @Service @Profile(test) for test isolation | lib-events/src/main/java/com/gme/pay/events/EventPublisher.java and services/notification-webhook/src/main/java/com/gme/pay/notify/outbox/OutboxEventPublisher.java | • Calling publish() outside a @Transactional context throws IllegalTransactionStateException • publish() within a transaction that rolls back leaves zero outbox_event rows (verified Testcontainers Postgres) • publish() in committed transaction inserts exactly one PENDING row with correct eventType and payload • ObjectMapper serializes BigDecimal as string preserving precision (no floating point loss) • NullOutboxEventPublisher bean is active when Spring profile=test | 40 | 8.6-T03, 8.6-T04 | BE | API-05
8.6-T06 | notification-webhook | 8.6 | 8. Partner (Northbound) API | Webhooks: events, signing, retry | 1 | Implement WebhookSigningService: HMAC-SHA256 outbound signing with Vault secret retrieval | Every webhook POST must include: X-GME-Webhook-Signature: sha256=<HMAC-SHA256(rawBodyBytes, signingSecret)>, X-GME-Webhook-Timestamp: ISO-8601 UTC, X-GME-Event-ID: event_id. Per API-05 section 6.3. The signingSecret is per-partner; plaintext stored in Vault (Spring Cloud Vault via VaultTemplate), never in DB (only Argon2 hash in partner_webhook.signing_secret_hash). Signing: HMAC-SHA256 of UTF-8 body bytes; output = sha256= + lowercase hex. Verification for testing: verifySignature(rawBody, secret, signatureHeader) using MessageDigest.isEqual (constant-time, prevents timing attacks). Secrets zeroed after use. | • Create services/notification-webhook/src/main/java/com/gme/pay/notify/signing/WebhookSigningService.java @Service • Inject VaultTemplate; fetch per-partner signing secret from Vault path secret/data/webhook/{partnerId}/signing-secret at dispatch time • Implement sign(byte[] bodyBytes, String secret): String using javax.crypto.Mac HMAC_SHA256; return sha256= + Hex.encodeHexString(digest) • Implement verifySignature(String rawBody, String secret, String signatureHeader): boolean using MessageDigest.isEqual • Zero secret byte array in finally block after use (Arrays.fill(secretBytes, (byte)0)) | services/notification-webhook/src/main/java/com/gme/pay/notify/signing/WebhookSigningService.java | • sign(UTF-8 bytes of hello world, super-secret-key) matches hardcoded expected HMAC-SHA256 hex value in unit test • verifySignature uses MessageDigest.isEqual not String.equals (inspect source) • verifySignature returns false for tampered body (one-byte change) • verifySignature returns false when header missing sha256= prefix • Vault path is never logged (log output does not contain secret value); secret bytes zeroed after use • Unit test passes with VaultTemplate mocked via @MockBean | 40 |  | BE | API-05
8.6-T07 | notification-webhook | 8.6 | 8. Partner (Northbound) API | Webhooks: events, signing, retry | 1 | Implement PartnerWebhookConfig JPA entity and Redis-cached repository | notification-webhook service needs per-partner webhook configuration (URL, active flag, event_types filter) from the partner_webhook PostgreSQL table (created V31). PartnerWebhookConfig @Entity maps this table. Service layer method fetchActiveConfigs(Long partnerId) annotated @Cacheable(cacheNames=webhook-config, key=#partnerId) caches in Redis (Spring Cache, TTL 300s configured in application.yml). The signing secret plaintext is NOT cached - only fetched from Vault at dispatch time. @CacheEvict on deactivate/update methods. Redis configured via spring.data.redis in application.yml. | • Create services/notification-webhook/src/main/java/com/gme/pay/notify/config/PartnerWebhookConfig.java @Entity @Table(name=partner_webhook) • Create PartnerWebhookConfigRepository.java extending JpaRepository with findByPartnerIdAndIsActiveTrue() • Create PartnerWebhookConfigService.java @Service with @Cacheable(cacheNames=webhook-config) on fetchActiveConfigs() • Configure Redis cache TTL 300s in application.yml: spring.cache.type=redis with RedisCacheConfiguration TTL • Add @CacheEvict(cacheNames=webhook-config, key=#partnerId) on deactivate and update methods | services/notification-webhook/src/main/java/com/gme/pay/notify/config/PartnerWebhookConfig.java and PartnerWebhookConfigService.java | • @Cacheable reduces DB queries to 1 for 10 identical lookups (integration test with Testcontainers Postgres + Redis) • @CacheEvict on deactivate clears Redis entry (verify key absent in Redis Testcontainers after evict) • fetchActiveConfigs returns empty list for partner with all is_active=false configs • PartnerWebhookConfig.eventTypes null means all events; non-null comma list means filtered events only • http:// URL in partner_webhook triggers CHECK violation on insert (DataIntegrityViolationException) | 35 | 8.6-T02 | BE | API-05
8.6-T08 | notification-webhook | 8.6 | 8. Partner (Northbound) API | Webhooks: events, signing, retry | 1 | Implement OutboxPollerService: scheduled outbox polling with retry back-off and DLQ promotion | notification-webhook service polls outbox_event for PENDING rows every 2 seconds. Each poll: SELECT FOR UPDATE SKIP LOCKED up to 50 rows with status=PENDING and next_attempt_at<=now(). For each row: set status=PROCESSING, attempt dispatch. On HTTP 2xx: set status=DELIVERED, processed_at=now(). On failure (non-2xx or timeout): increment attempts, compute next_attempt_at per retry schedule (attempts 1:0s, 2:30s, 3:120s, 4:600s, 5:1800s, 6-10:3600s each), reset status=PENDING. After 10 failed attempts: set status=DLQ, insert to webhook_dlq, fire Ops alert. All DB mutations within @Transactional. Disabled via webhook.outbox.poller.enabled=false property. | • Create services/notification-webhook/src/main/java/com/gme/pay/notify/outbox/OutboxPollerService.java @Service @ConditionalOnProperty(name=webhook.outbox.poller.enabled, havingValue=true, matchIfMissing=true) • Inject OutboxEventRepository, WebhookDispatchService, WebhookDlqRepository, WebhookAlertService, MeterRegistry • Implement @Scheduled(fixedDelayString=${webhook.outbox.poll-interval-ms:2000}) pollAndDispatch() • Implement computeNextAttemptAt(int attemptNumber): Instant using array [0,30,120,600,1800,3600,3600,3600,3600,3600] seconds • On 10th failure: insert webhook_dlq row, set status=DLQ, call WebhookAlertService.fireDlqAlert() • Emit Micrometer counter webhook_dispatch_attempts_total (tags: partner_id, event_type, status) and gauge webhook_outbox_pending_count | services/notification-webhook/src/main/java/com/gme/pay/notify/outbox/OutboxPollerService.java | • computeNextAttemptAt(1)=0s, (2)=30s, (3)=120s, (4)=600s, (5)=1800s, (6)=3600s (unit test all 10 values) • After 10th failure: outbox_event.status=DLQ and webhook_dlq has exactly one row for that event • @Scheduled does not fire when webhook.outbox.poller.enabled=false (Spring context test) • Two concurrent poller threads do not process the same outbox_event row (SKIP LOCKED Testcontainers test) • Micrometer counter webhook_dlq_total increments by 1 when event enters DLQ | 55 | 8.6-T04, 8.6-T07 | BE | API-05
8.6-T09 | notification-webhook | 8.6 | 8. Partner (Northbound) API | Webhooks: events, signing, retry | 1 | Implement WebhookDispatchService: HTTP POST with signing headers, timeout, and attempt recording | notification-webhook service dispatches webhooks via Spring WebClient (reactive non-blocking) to partner-registered HTTPS URLs. Per API-05 section 6.1: partner must respond HTTP 2xx within 10 seconds; any other response (3xx, 4xx, 5xx, timeout) is a delivery failure. For each dispatch: (1) fetch PartnerWebhookConfig; (2) build WebhookEventEnvelope JSON; (3) add headers X-GME-Webhook-Signature (sha256=<HMAC-SHA256>), X-GME-Webhook-Timestamp (ISO-8601 UTC), X-GME-Event-ID; (4) POST Content-Type:application/json; (5) record WebhookDeliveryAttempt. Defense-in-depth: reject http:// URLs before any network call. No redirect follow (maxRedirects=0). Emit OpenTelemetry span webhook.dispatch. | • Create services/notification-webhook/src/main/java/com/gme/pay/notify/dispatch/WebhookDispatchService.java @Service • Create WebClientConfig.java @Configuration creating WebClient.Builder bean with responseTimeout(Duration.ofSeconds(10)) and no redirects • Implement dispatch(OutboxEvent event): WebhookDispatchResult fetching config, signing body, POSTing, recording attempt • Reject webhook_url not starting with https:// by throwing WebhookUrlNotHttpsException before any HTTP call • Persist WebhookDeliveryAttempt (attempt_number, http_status, response_body truncated to 500 chars, duration_ms) • Emit OTel span with attributes: partner_id, event_type, attempt_number, http_status | services/notification-webhook/src/main/java/com/gme/pay/notify/dispatch/WebhookDispatchService.java | • WireMock returning HTTP 200: dispatch returns SUCCESS result (integration test) • WireMock returning HTTP 500: dispatch returns FAILURE (WireMock integration test) • WireMock with 11-second delay: dispatch returns FAILURE with duration >= 10000ms • HTTP 301 redirect treated as FAILURE (not followed) • http:// URL throws WebhookUrlNotHttpsException before any network call • WebhookDeliveryAttempt row persisted after every attempt with correct http_status and duration_ms | 50 | 8.6-T06, 8.6-T07 | BE | API-05
8.6-T10 | notification-webhook | 8.6 | 8. Partner (Northbound) API | Webhooks: events, signing, retry | 1 | Implement WebhookEventFactory: build typed WebhookEventEnvelope from OutboxEvent | notification-webhook service converts raw outbox_event payload JSON to a typed WebhookEventEnvelope before HTTP dispatch. WebhookEventFactory.buildEnvelope(OutboxEvent): deserializes payload using Jackson ObjectMapper to the correct payload class (switch on event_type via WebhookEventType enum), sets event_id as evt_ + ULID (de.huxhorn.sulky:ulid dependency), sets created_at=Instant.now() (dispatch time), partner_id from outbox event. Event type mapping: PAYMENT_APPROVED -> payment.approved, PAYMENT_PENDING_DEBIT -> payment.pending_debit, PAYMENT_FAILED -> payment.failed, PAYMENT_CANCELLED -> payment.cancelled, SETTLEMENT_COMPLETED -> settlement.completed. Throw UnknownEventTypeException for unrecognized types. | • Create services/notification-webhook/src/main/java/com/gme/pay/notify/factory/WebhookEventFactory.java @Service • Inject ObjectMapper; add de.huxhorn.sulky:de.huxhorn.sulky.ulid to services/notification-webhook/build.gradle • Implement buildEnvelope(OutboxEvent): use switch on WebhookEventType to deserialize payload to correct class • Generate event_id as evt_ + UlidCreator.getMonotonicUlid().toString() • Throw UnknownEventTypeException for types not in WebhookEventType enum • Add unit test verifying event_id format and round-trip serialization | services/notification-webhook/src/main/java/com/gme/pay/notify/factory/WebhookEventFactory.java | • buildEnvelope with eventType=PAYMENT_APPROVED produces envelope with event_type=payment.approved and data as PaymentApprovedPayload • event_id matches regex evt_[0-9A-Z]{26} • buildEnvelope with unknown eventType throws UnknownEventTypeException • Serialize envelope to JSON then deserialize back: all fields equal (round-trip test) • Two ULID event_ids generated 1ms apart are lexicographically ordered (monotonic ULID property) | 35 | 8.6-T03, 8.6-T04 | BE | API-05
8.6-T11 | notification-webhook | 8.6 | 8. Partner (Northbound) API | Webhooks: events, signing, retry | 1 | Implement WebhookReplayGuard and WebhookSignatureVerifier for replay-attack protection | API-05 section 6.3: partners must reject events where X-GME-Webhook-Timestamp is more than 5 minutes old (replay protection). notification-webhook service also uses this for its sandbox verify utility endpoint. WebhookReplayGuard.isTimestampValid(String timestampHeader, Clock clock): parses ISO-8601 UTC, checks abs(now - parsed) < 5 minutes (tolerance both directions: future clock skew accepted if < 5 min). WebhookSignatureVerifier.verify(String rawBody, String signingSecret, String signatureHeader, String timestampHeader): VerificationResult enum (VALID, INVALID_SIGNATURE, TIMESTAMP_EXPIRED, MISSING_HEADER). Order: check presence -> check timestamp -> check HMAC. Clock is injected for testability. | • Create services/notification-webhook/src/main/java/com/gme/pay/notify/signing/WebhookReplayGuard.java with isTimestampValid(String, Clock): boolean • Create VerificationResult.java enum: VALID, INVALID_SIGNATURE, TIMESTAMP_EXPIRED, MISSING_HEADER • Create WebhookSignatureVerifier.java @Service injecting WebhookReplayGuard and WebhookSigningService • Implement verify() checking: null/blank headers -> MISSING_HEADER; timestamp check -> TIMESTAMP_EXPIRED; HMAC check -> INVALID_SIGNATURE or VALID • Inject Clock bean (default Clock.systemUTC()) to enable deterministic unit tests | services/notification-webhook/src/main/java/com/gme/pay/notify/signing/WebhookReplayGuard.java and WebhookSignatureVerifier.java | • Timestamp exactly 4m59s old returns VALID • Timestamp exactly 5m01s old returns TIMESTAMP_EXPIRED • Missing X-GME-Webhook-Signature returns MISSING_HEADER before any HMAC computation • Correct HMAC with valid timestamp returns VALID • Tampered body returns INVALID_SIGNATURE even with valid timestamp • Clock injection allows fully deterministic test without Thread.sleep or system time dependency | 30 | 8.6-T06 | BE | API-05
8.6-T12 | notification-webhook | 8.6 | 8. Partner (Northbound) API | Webhooks: events, signing, retry | 1 | Implement Ops admin endpoints GET/POST /internal/v1/webhook/dlq for DLQ review and retry | After 10 failed delivery attempts events enter webhook_dlq. Ops needs endpoints (internal, not on public partner API gateway): GET /internal/v1/webhook/dlq?partner_id=&page=&size= returns paginated DLQ events. POST /internal/v1/webhook/dlq/{id}/retry resets to outbox_event with status=PENDING and attempts=0. POST /internal/v1/webhook/dlq/{id}/resolve marks resolved_at=now(), resolved_by=operator from JWT. Protected by @PreAuthorize(hasRole(ROLE_GME_OPS)). All mutating actions write audit_event entries. Module: services/notification-webhook. | • Create services/notification-webhook/src/main/java/com/gme/pay/notify/api/WebhookDlqController.java @RestController @RequestMapping(/internal/v1/webhook/dlq) • Create WebhookDlqService.java @Service with retryEvent() and resolveEvent() methods • Implement GET with @RequestParam Optional<Long> partnerId, Pageable; return Page<WebhookDlqResponse> DTO • Implement POST /{id}/retry: validate DLQ event exists (404 if not); restore to outbox_event; write audit_event row • Implement POST /{id}/resolve: set resolved_at, resolved_by from JWT principal; write audit_event row • Apply @PreAuthorize(hasRole(ROLE_GME_OPS)) at class level; enable via @EnableMethodSecurity | services/notification-webhook/src/main/java/com/gme/pay/notify/api/WebhookDlqController.java | • GET /internal/v1/webhook/dlq without ROLE_GME_OPS returns HTTP 403 • POST /{id}/retry creates new outbox_event with attempts=0 and status=PENDING • POST /{id}/retry with non-existent id returns HTTP 404 • POST /{id}/resolve sets resolved_at non-null and resolved_by to JWT sub claim • Audit event row written for both retry and resolve (verified in @WebMvcTest with mock service assertion) | 45 | 8.6-T04, 8.6-T08 | BE | API-05
8.6-T13 | notification-webhook | 8.6 | 8. Partner (Northbound) API | Webhooks: events, signing, retry | 1 | Implement partner event-type subscription filtering in dispatch pipeline | Each partner_webhook row has event_types (comma-separated, null=all events). Before making any HTTP call, OutboxPollerService must check: if partner_webhook.event_types IS NULL deliver all events; if non-null split by comma strip whitespace and check if event.eventType (dot-notation e.g. payment.approved) is in the list. Unsubscribed events: set status=DELIVERED immediately (no HTTP call) and record WebhookDeliveryAttempt with http_status=-1 and response_body=FILTERED. This prevents unbounded pending rows for events the partner never opted into. | • Add filterCheck(PartnerWebhookConfig config, String dotNotationEventType): boolean to WebhookDispatchService • If config.getEventTypes() is null return true (all events pass) • Otherwise split by comma, trim each token, check dotNotationEventType is in the resulting set • In OutboxPollerService.pollAndDispatch(): call filterCheck; if false immediately mark DELIVERED with FILTERED attempt record and skip HTTP dispatch • Add unit tests for null event_types, matching event, non-matching event, multi-value list | services/notification-webhook/src/main/java/com/gme/pay/notify/dispatch/WebhookDispatchService.java (updated with filterCheck method) | • Partner with event_types=payment.approved does not receive payment.failed (status=DELIVERED, http_status=-1) • Partner with event_types=null receives all five event types (no filtering) • Partner subscribed to payment.approved,settlement.completed receives those two but not payment.failed • FILTERED events are marked DELIVERED so they do not loop in pending indefinitely • filterCheck is a pure function testable without any DB or network | 30 | 8.6-T08, 8.6-T09 | BE | API-05
8.6-T14 | notification-webhook | 8.6 | 8. Partner (Northbound) API | Webhooks: events, signing, retry | 1 | Integrate EventPublisher calls into Transaction Orchestrator for payment lifecycle events | TransactionOrchestrator in services/transaction-mgmt must call EventPublisher.publish() at payment lifecycle transitions. Calls must be within the same @Transactional boundary as the state update to guarantee atomicity (outbox pattern). Events to publish: (1) PAYMENT_APPROVED when transaction reaches APPROVED state with PaymentApprovedPayload built from transaction entity; (2) PAYMENT_FAILED when FAILED; (3) PAYMENT_CANCELLED when CANCELLED; (4) PAYMENT_PENDING_DEBIT in CPM flow when merchant scans and amount is known, before final approval. Also write transaction_event_trail step 7 (WEBHOOK_QUEUED) in the same transaction as outbox_event insert. See 8-step trail: step 7 = webhook_dispatched. | • Inject EventPublisher into TransactionOrchestrator in services/transaction-mgmt/src/main/java/com/gme/pay/txnmgmt/orchestrator/TransactionOrchestrator.java • On APPROVED transition: call publisher.publish(payment, payment_id, PAYMENT_APPROVED, buildApprovedPayload(txn)) • On FAILED transition: call publisher.publish(payment, payment_id, PAYMENT_FAILED, buildFailedPayload(txn)) • On CANCELLED: call publisher.publish(payment, payment_id, PAYMENT_CANCELLED, buildCancelledPayload(txn)) • In CPM path: call publisher.publish(payment, payment_id, PAYMENT_PENDING_DEBIT, buildPendingDebitPayload(txn)) when merchant amount arrives • Write transaction_event_trail step 7 row in same @Transactional method as publish() | services/transaction-mgmt/src/main/java/com/gme/pay/txnmgmt/orchestrator/TransactionOrchestrator.java (updated) | • DB rollback after APPROVED state update leaves zero outbox_event rows (Testcontainers atomicity test) • Transition to APPROVED inserts one PENDING outbox_event with eventType=PAYMENT_APPROVED • transaction_event_trail step 7 row committed in same transaction as outbox_event • CPM path: PAYMENT_PENDING_DEBIT event published at pending_debit stage before scheme confirmation • Integration test uses Testcontainers Postgres with real @Transactional (not @Transactional rollback annotation) | 50 | 8.6-T05, 8.6-T10 | BE | API-05
8.6-T15 | notification-webhook | 8.6 | 8. Partner (Northbound) API | Webhooks: events, signing, retry | 1 | Implement step-8 trail update (WEBHOOK_DELIVERED) after successful dispatch | Per the 8-step event trail, step 8 = WEBHOOK_DELIVERED (partner endpoint returned HTTP 2xx). After successful dispatch OutboxPollerService must write a transaction_event_trail row: txn_id from outbox_event.aggregate_id, step=8, event_type=WEBHOOK_DELIVERED, occurred_at=dispatch timestamp, duration_ms, detail JSONB = {http_status, attempt_number, duration_ms}. The notification-webhook service writes directly to transaction_event_trail table in PostgreSQL schema transactions (same Postgres instance, cross-schema write). This write and the outbox_event DELIVERED update happen in the same @Transactional. If trail insert fails (e.g. txn not found), log WARN but do not roll back the DELIVERED status (webhook was already delivered). | • Add TransactionEventTrail @Entity @Table(name=transaction_event_trail, schema=transactions) to notification-webhook JPA config • Add TransactionEventTrailRepository extending JpaRepository to notification-webhook • In OutboxPollerService after successful HTTP 2xx: build trail row with step=8, detail JSONB, call trailRepository.save() in same @Transactional • Catch DataIntegrityViolationException on trail save: log WARN and continue (do not fail the DELIVERED update) • Add integration test with Testcontainers: confirm step-8 trail row written after mock partner returns 200 | services/notification-webhook/src/main/java/com/gme/pay/notify/outbox/OutboxPollerService.java (updated with step-8 trail write) | • Successful dispatch creates transaction_event_trail row with step=8 and event_type=WEBHOOK_DELIVERED • detail JSONB contains http_status, attempt_number, and duration_ms fields • Both outbox_event.status=DELIVERED and trail step 8 committed atomically (both present or both absent on normal path) • Trail insert failure does not roll back DELIVERED status (outbox_event remains DELIVERED) • Integration test with Testcontainers Postgres verifies step-8 row present after WireMock returns 200 | 40 | 8.6-T08, 8.6-T09 | BE | API-05
8.6-T16 | notification-webhook | 8.6 | 8. Partner (Northbound) API | Webhooks: events, signing, retry | 1 | Implement KafkaEventPublisher stub (integration-phase, disabled by default) behind EventPublisher interface | STACK.md: Kafka is deferred to integration phase but the EventPublisher interface must isolate it so it can be enabled without rework. Implement KafkaEventPublisher.java @Service @ConditionalOnProperty(name=events.publisher.mode, havingValue=kafka) using Spring Kafka KafkaTemplate to publish to topic gme.domain.events (key=aggregateType:aggregateId, value=JSON payload). When kafka mode is active: OutboxEventPublisher is inactive (add @ConditionalOnProperty matchIfMissing=true to OutboxEventPublisher) and webhook.outbox.poller.enabled should be set false (Kafka becomes transport). Add application-kafka.yml profile stub with placeholder bootstrap-servers. No actual Kafka infra required in this ticket. | • Add @ConditionalOnProperty(name=events.publisher.mode, havingValue=outbox, matchIfMissing=true) to OutboxEventPublisher • Create services/notification-webhook/src/main/java/com/gme/pay/notify/outbox/KafkaEventPublisher.java @Service @ConditionalOnProperty(name=events.publisher.mode, havingValue=kafka) • Inject KafkaTemplate<String, String>; implement publish() calling kafkaTemplate.send(gme.domain.events, aggregateType+:+aggregateId, json) • Create src/main/resources/application-kafka.yml with spring.kafka.bootstrap-servers placeholder and producer acks=all settings • Add unit test: with events.publisher.mode=outbox only OutboxEventPublisher bean present; with kafka only KafkaEventPublisher bean present | services/notification-webhook/src/main/java/com/gme/pay/notify/outbox/KafkaEventPublisher.java | • With events.publisher.mode=outbox (default), KafkaEventPublisher bean absent from Spring context • With events.publisher.mode=kafka, OutboxEventPublisher bean absent from Spring context • KafkaEventPublisher.publish() calls KafkaTemplate.send with topic=gme.domain.events and key format aggregateType:aggregateId (verified via MockBean) • EventPublisher interface unchanged (no method signature changes) • No compilation errors in KafkaEventPublisher when kafka dependencies absent from classpath (conditional dependency) | 30 | 8.6-T05 | BE | API-05
8.6-T17 | notification-webhook | 8.6 | 8. Partner (Northbound) API | Webhooks: events, signing, retry | 1 | Add Micrometer metrics and OpenTelemetry tracing to webhook dispatch pipeline | Observability per spec: key metrics for webhook pipeline: webhook_dispatch_attempts_total counter (tags: partner_id, event_type, result=[success¦failure¦filtered]), webhook_outbox_pending_count gauge (current PENDING row count), webhook_dlq_total counter (tags: partner_id), webhook_dispatch_duration_seconds timer (tags: partner_id, event_type). Spec alert thresholds: P2 when delivery failure after max retries; P2 queue depth > 500; P3 p95 > 30s. OpenTelemetry spans webhook.dispatch (already started in T09). Register all metrics via @Bean MeterBinder in WebhookMetricsConfig @Configuration to ensure gauge registers at startup. | • Create services/notification-webhook/src/main/java/com/gme/pay/notify/metrics/WebhookMetricsConfig.java @Configuration • Register Gauge webhook_outbox_pending_count reading OutboxEventRepository.countByStatus(PENDING) with Gauge.builder().strongReference(true) • In OutboxPollerService inject MeterRegistry; increment webhook_dispatch_attempts_total with tags on each attempt result • In WebhookDispatchService record Timer.record() for dispatch HTTP call duration • In DLQ promotion path increment webhook_dlq_total counter with partner_id tag • Verify /actuator/prometheus endpoint exposes all four metric names | services/notification-webhook/src/main/java/com/gme/pay/notify/metrics/WebhookMetricsConfig.java | • webhook_outbox_pending_count gauge reports 0 with no rows and N after inserting N PENDING rows (Testcontainers integration test) • webhook_dispatch_attempts_total increments by 1 per attempt with correct partner_id and event_type tags • webhook_dlq_total increments when event enters DLQ • webhook_dispatch_duration_seconds timer has at least one sample after a WireMock dispatch test • GET /actuator/prometheus contains webhook_dispatch_attempts_total in response body | 35 | 8.6-T08, 8.6-T09 | BE | API-05
8.6-T18 | notification-webhook | 8.6 | 8. Partner (Northbound) API | Webhooks: events, signing, retry | 1 | Write unit tests for OutboxPollerService retry schedule, DLQ promotion, and filtering | Core logic unit tests for OutboxPollerService. All mocked with Mockito (no DB, no network). Use fixed Clock for determinism. Test retry delay array: attempt 1=0s, 2=30s, 3=120s, 4=600s, 5=1800s, 6-10=3600s. DLQ promotion: 9th attempt leaves PENDING; 10th attempt triggers DLQ insert. Success on attempt 3: status=DELIVERED, no DLQ. Filtering: unsubscribed event type => DELIVERED with no dispatch call. next_attempt_at computed relative to dispatch time not row creation time. Also test that @Scheduled does not fire when poller property disabled (Spring context integration test). | • Create services/notification-webhook/src/test/java/com/gme/pay/notify/outbox/OutboxPollerServiceTest.java • Mock OutboxEventRepository, WebhookDispatchService (returns FAILURE for failure tests), WebhookDlqRepository, MeterRegistry, Clock • Test computeNextAttemptAt(attempt) for all 10 values with assertEquals to exact Duration • Test 9th attempt: status=PENDING, WebhookDlqRepository.save() NOT called • Test 10th attempt: status=DLQ, WebhookDlqRepository.save() called exactly once • Test success on attempt 3: status=DELIVERED, attempt count=3, DLQ not invoked • Test filter: WebhookDispatchService.dispatch() never called for filtered event; outbox status=DELIVERED | services/notification-webhook/src/test/java/com/gme/pay/notify/outbox/OutboxPollerServiceTest.java | • computeNextAttemptAt(1) == Duration.ZERO • computeNextAttemptAt(2) == Duration.ofSeconds(30) • computeNextAttemptAt(5) == Duration.ofSeconds(1800) • computeNextAttemptAt(6) through (10) all == Duration.ofSeconds(3600) • After attempt 10 failure: WebhookDlqRepository.save() called exactly once with correct outbox event • Test class has zero dependencies on Spring context, DB, or network | 40 | 8.6-T08 | BE | API-05
8.6-T19 | notification-webhook | 8.6 | 8. Partner (Northbound) API | Webhooks: events, signing, retry | 1 | Write unit tests for WebhookSigningService and WebhookReplayGuard with hardcoded test vectors | Security-critical unit tests. WebhookSigningServiceTest: use hardcoded HMAC-SHA256 test vectors (body=hello world UTF-8, secret=super-secret-key; pre-compute expected hex offline before writing test). Test empty body, unicode body, 1MB body. Test verifySignature constant-time (inspect usage of MessageDigest.isEqual in source). WebhookReplayGuardTest: inject fixed Clock; test boundary conditions: 299s old (valid), 300s old (valid per spec less-than-5-min), 301s old (expired), 4m59s future (valid), 5m01s future (expired). All tests are pure unit tests with no Spring context or external dependencies. | • Create services/notification-webhook/src/test/java/com/gme/pay/notify/signing/WebhookSigningServiceTest.java • Pre-compute HMAC-SHA256 of hello world with super-secret-key using openssl or Python; embed expected hex as constant • Test sign() for that vector, empty body, 1MB random body (compare to independently computed values) • Test verifySignature returns true for correct sha256=<expected> header • Test verifySignature returns false for tampered body (flip one byte) • Create WebhookReplayGuardTest with Clock.fixed(); test all 5 boundary conditions listed in context | services/notification-webhook/src/test/java/com/gme/pay/notify/signing/WebhookSigningServiceTest.java and WebhookReplayGuardTest.java | • Known vector: sign(hello world, super-secret-key) == hardcoded expected hex (test fails if algorithm changes) • verifySignature(tampered body) returns false • verifySignature(header without sha256= prefix) returns false • ReplayGuard: 299s old timestamp returns true; 301s old returns false • ReplayGuard: 4m59s future timestamp returns true; 5m01s future returns false • Zero Spring context dependencies in either test class | 35 | 8.6-T06, 8.6-T11 | BE | API-05
8.6-T20 | notification-webhook | 8.6 | 8. Partner (Northbound) API | Webhooks: events, signing, retry | 1 | Write @DataJpaTest slice tests for OutboxEvent repository with Testcontainers Postgres 16 | Repository-layer tests using Spring Boot @DataJpaTest slice with @Testcontainers PostgreSQLContainer (not H2 - real Postgres required for CHECK constraints and partial indexes). Test scenarios: (1) findNextBatch returns only PENDING rows with nextAttemptAt<=now and skips PROCESSING/DELIVERED/DLQ rows; (2) CHECK constraint rejects invalid status string; (3) UNIQUE constraint on event_id prevents duplicates; (4) SKIP LOCKED: two concurrent threads calling findNextBatch each get distinct rows (no overlap). Also test WebhookDeliveryAttempt FK cascade and WebhookDlqEvent insert. | • Create services/notification-webhook/src/test/java/com/gme/pay/notify/outbox/OutboxEventRepositoryTest.java • Annotate with @DataJpaTest @Testcontainers; define @Container static PostgreSQLContainer • Test 1: insert 3 PENDING rows, findNextBatch(now, page 0-50) returns all 3 • Test 2: insert PROCESSING row, findNextBatch returns 0 (status filter) • Test 3: CHECK constraint: set status to invalid string -> DataIntegrityViolationException • Test 4: two-thread concurrent findNextBatch on 2 rows: each thread gets exactly 1 distinct row (SKIP LOCKED) • Test 5: DELETE outbox_event cascades to webhook_delivery_attempt rows | services/notification-webhook/src/test/java/com/gme/pay/notify/outbox/OutboxEventRepositoryTest.java | • findNextBatch with PROCESSING row returns empty (not PROCESSING in WHERE clause) • findNextBatch with future nextAttemptAt returns empty (time filter working) • DataIntegrityViolationException thrown for invalid status value (real Postgres CHECK constraint) • Two-thread test: row A assigned to thread 1 only; row B assigned to thread 2 only (no duplicates) • WebhookDeliveryAttempt rows deleted when parent outbox_event deleted (CASCADE verified) | 45 | 8.6-T04 | BE | API-05
8.6-T21 | notification-webhook | 8.6 | 8. Partner (Northbound) API | Webhooks: events, signing, retry | 1 | Write end-to-end integration tests for webhook dispatch pipeline with Testcontainers and WireMock | Full pipeline integration test using @SpringBootTest, @Testcontainers (PostgreSQLContainer, Redis via GenericContainer), and WireMock (partner webhook endpoint). Four scenarios: (1) Happy path: insert outbox_event + partner_webhook, WireMock returns 200, verify DELIVERED + trail step 8; (2) Transient failure then success: WireMock returns 500 twice then 200, verify attempt_count=3 and DELIVERED; (3) DLQ path: WireMock always 500 for 10 attempts, verify status=DLQ and webhook_dlq row; (4) Filtered event: partner subscribed to payment.approved only, insert payment.failed, verify zero WireMock calls and status=DELIVERED. | • Create services/notification-webhook/src/test/java/com/gme/pay/notify/integration/WebhookDispatchIntegrationTest.java • Annotate @SpringBootTest @Testcontainers; define PostgreSQLContainer, Redis GenericContainer, WireMockServer as static fields • Scenario 1: seed DB, stub WireMock 200, trigger pollAndDispatch(), assert outbox_event.status=DELIVERED and trail step=8 • Scenario 2: stub WireMock 500-500-200 sequence; trigger poller 3 times; assert delivery_attempt rows count=3 • Scenario 3: always-500 WireMock; trigger poller 10 times; assert status=DLQ and webhook_dlq count=1 • Scenario 4: event_types=payment.approved in partner_webhook; insert payment.failed outbox_event; assert WireMock 0 requests and DELIVERED | services/notification-webhook/src/test/java/com/gme/pay/notify/integration/WebhookDispatchIntegrationTest.java | • Scenario 1: outbox_event.status=DELIVERED and transaction_event_trail step=8 both present • Scenario 2: webhook_delivery_attempt rows=3; first two http_status=500; third http_status=200 • Scenario 3: webhook_dlq.outbox_event_id matches the exhausted event; outbox_event.status=DLQ • Scenario 4: WireMock.verify(0 requests); outbox_event.status=DELIVERED • All four scenarios pass in CI with Testcontainers (no pre-deployed infra required) | 55 | 8.6-T08, 8.6-T09, 8.6-T13, 8.6-T15 | BE | API-05
8.6-T22 | notification-webhook | 8.6 | 8. Partner (Northbound) API | Webhooks: events, signing, retry | 1 | Write atomicity integration test for EventPublisher outbox insert with transaction rollback | Critical correctness test for the transactional Outbox pattern: if the business transaction rolls back, the outbox_event row must also be absent. Uses Testcontainers Postgres (not H2). Test 1 (rollback): begin @Transactional, update transaction state, call EventPublisher.publish(), throw RuntimeException to force rollback; assert both transaction state unchanged and outbox_event count=0. Test 2 (commit): same flow without exception; assert APPROVED state and one PENDING outbox_event. Test 3 (idempotency): same idempotency key called twice; assert outbox_event count=1 (no duplicate). This proves the atomicity guarantee that outbox rows are never orphaned. | • Create services/transaction-mgmt/src/test/java/com/gme/pay/txnmgmt/outbox/OutboxAtomicityTest.java @SpringBootTest @Testcontainers • Define static PostgreSQLContainer; configure datasource to point to container • Test 1: inject a @MockBean that throws RuntimeException after publish(); call orchestrator method; assert outbox_event SELECT COUNT(*)=0 and transaction state unchanged • Test 2: call orchestrator method with no exception; assert transaction status=APPROVED and outbox_event count=1 with status=PENDING • Test 3: call with same idempotency key twice; assert outbox_event count=1 (duplicate blocked) | services/transaction-mgmt/src/test/java/com/gme/pay/txnmgmt/outbox/OutboxAtomicityTest.java | • Test 1: zero rows in outbox_event after rollback (SELECT COUNT(*) = 0 via JdbcTemplate) • Test 2: exactly one PENDING outbox_event row after commit • Test 3: second identical call does not insert second outbox_event • Tests use @Testcontainers with PostgreSQLContainer not H2 • Kafka and Redis beans are excluded or mocked (tests focus on DB atomicity only) | 40 | 8.6-T05, 8.6-T14 | BE | API-05
8.6-T23 | notification-webhook | 8.6 | 8. Partner (Northbound) API | Webhooks: events, signing, retry | 1 | Add webhook event schemas to openapi/partner-api.yaml as reusable components | openapi/partner-api.yaml is the ground truth for contract tests (STACK.md). Webhook section (API-05 section 6) must be documented as OpenAPI 3 component schemas. Add: WebhookEvent (envelope), PaymentApprovedData (all 16 fields from spec 6.5), PaymentPendingDebitData, PaymentFailedData, PaymentCancelledData, SettlementCompletedData. BigDecimal fields documented as type: string (not number) to match Java serialization. required arrays must list all mandatory fields. Add x-webhook-events extension at root level mapping each event_type to its data schema $ref. Validate with swagger-parser. | • Open openapi/partner-api.yaml; locate components/schemas section • Add WebhookEvent schema with event_id, event_type enum (5 values), created_at, partner_id, data properties • Add all five data schemas with field definitions matching API-05 section 6.5 exactly • Use type: string for target_payout, offer_rate, collection_amount, service_charge, prefund_deducted_usd fields • Add x-webhook-events extension at document root mapping event types to $ref data schemas • Run swagger-parser validation and fix any errors before marking done | openapi/partner-api.yaml (updated with WebhookEvent and five data schemas in components/schemas) | • swagger-parser validates file with zero errors • WebhookEvent.event_type enum contains exactly payment.approved, payment.pending_debit, payment.failed, payment.cancelled, settlement.completed • PaymentApprovedData.target_payout has type: string (not number) • PaymentApprovedData required array contains all 16 fields from API-05 section 6.5 • x-webhook-events extension present at root level with five entries each pointing to a $ref data schema | 40 | 8.6-T03 | BE | API-05
8.6-T24 | notification-webhook | 8.6 | 8. Partner (Northbound) API | Webhooks: events, signing, retry | 1 | Implement Ops alert integration: P2 alert on DLQ promotion and queue depth breach | Spec requires P2 alert: (a) partner webhook returns non-2xx after max retries (DLQ); (b) webhook queue depth > 500 unprocessed events. Phase 1: write to alert_event PostgreSQL table (id BIGSERIAL PK, alert_type VARCHAR(50), severity VARCHAR(5), partner_id BIGINT, message TEXT, context JSONB, fired_at TIMESTAMPTZ, acknowledged_at TIMESTAMPTZ, acknowledged_by VARCHAR(100)). Future phases swap for PagerDuty/Slack via same interface. Add dedup: do not insert queue-depth alert if an unacknowledged queue-depth alert for same partner exists fired within last 10 minutes (prevents alert storm). Flyway migration V32__alert_event.sql. | • Create services/notification-webhook/src/main/resources/db/migration/V32__alert_event.sql with alert_event table • Create WebhookAlertService.java @Service with fireDlqAlert(Long partnerId, Long outboxEventId, String eventType) and fireQueueDepthAlert(Long partnerId, long pendingCount) • fireDlqAlert always inserts P2 alert_event row with alert_type=WEBHOOK_DLQ • fireQueueDepthAlert inserts P2 row with alert_type=WEBHOOK_QUEUE_DEPTH only if count > 500 and no unacknowledged alert in last 10 minutes for same partner • Create AlertEventRepository extending JpaRepository with existsByPartnerIdAndAlertTypeAndAcknowledgedAtIsNullAndFiredAtAfter query • In OutboxPollerService call fireQueueDepthAlert after each poll batch | services/notification-webhook/src/main/java/com/gme/pay/notify/alert/WebhookAlertService.java and V32__alert_event.sql | • fireDlqAlert inserts alert_event with severity=P2 and alert_type=WEBHOOK_DLQ • fireQueueDepthAlert with count=499 does NOT insert row (threshold strictly > 500) • fireQueueDepthAlert with count=501 inserts P2 alert_event with alert_type=WEBHOOK_QUEUE_DEPTH • Second fireQueueDepthAlert call within 10 minutes for same partner does NOT insert duplicate row • V32 migration applies cleanly on Testcontainers Postgres 16 | 40 | 8.6-T08, 8.6-T01 | BE | API-05
8.6-T25 | notification-webhook | 8.6 | 8. Partner (Northbound) API | Webhooks: events, signing, retry | 1 | Write contract tests validating webhook payloads against openapi/partner-api.yaml schemas | openapi/partner-api.yaml is the ground truth. Contract tests must verify that WebhookEventFactory output matches the OpenAPI component schemas added in 8.6-T23. Use io.swagger.v3.parser.OpenAPIV3Parser to load the spec and a JSON Schema validator to validate serialized payloads. Test all five event types with concrete field values. Include negative test: PaymentApprovedData missing required field approved_at must fail validation. Tests are pure (no DB, no network): the spec file is read from classpath and payload objects are constructed directly. | • Create services/notification-webhook/src/test/java/com/gme/pay/notify/contract/WebhookPayloadContractTest.java • Load openapi/partner-api.yaml from classpath using OpenAPIV3Parser • For each of five event types: construct concrete payload object, serialize via ObjectMapper, extract JSON Schema from components/schemas, validate • Assert all five happy-path payloads pass with no validation errors • Negative test: construct PaymentApprovedData without approved_at; assert validation failure mentioning approved_at • Negative test: event_type=payment.unknown in WebhookEvent; assert enum validation failure | services/notification-webhook/src/test/java/com/gme/pay/notify/contract/WebhookPayloadContractTest.java | • All five happy-path payloads pass schema validation (zero error messages) • Missing approved_at in PaymentApprovedData triggers validation error mentioning approved_at • event_type=payment.unknown fails WebhookEvent enum validation • target_payout as BigDecimal serialized as string passes schema type:string validation • Test runs without network or Spring context (spec loaded from src/test/resources classpath copy) | 40 | 8.6-T10, 8.6-T23 | BE | API-05
8.6-T26 | notification-webhook | 8.6 | 8. Partner (Northbound) API | Webhooks: events, signing, retry | 1 | Create notification-webhook Spring Boot service skeleton, Gradle module, and K8s manifests | notification-webhook is a dedicated Spring Boot 3.x microservice in the monorepo. Gradle module: services/notification-webhook. Dependencies: lib-money, lib-errors, lib-api-contracts, lib-events, lib-persistence plus spring-boot-starter-web, spring-boot-starter-data-jpa, spring-boot-starter-cache, spring-data-redis, spring-kafka, spring-boot-starter-actuator, micrometer-registry-prometheus, spring-cloud-starter-vault-config, spring-boot-starter-security, spring-boot-starter-oauth2-resource-server, de.huxhorn.sulky:ulid. application.yml: server.port=8085, JDBC datasource, Redis, Flyway, actuator. K8s deployment: 2 replicas, 512Mi/0.5CPU limits. Add to root settings.gradle. | • Add include(services:notification-webhook) to root settings.gradle • Create services/notification-webhook/build.gradle with all dependencies listed in context • Create services/notification-webhook/src/main/java/com/gme/pay/notify/NotificationWebhookApplication.java @SpringBootApplication • Create src/main/resources/application.yml with server.port=8085, datasource, redis, flyway, actuator, jwt issuer-uri placeholder • Create deploy/k8s/notification-webhook/deployment.yaml with replicas: 2, resource limits memory: 512Mi cpu: 500m • Run ./gradlew :services:notification-webhook:compileJava to verify no compilation errors | services/notification-webhook/build.gradle and NotificationWebhookApplication.java | • ./gradlew :services:notification-webhook:compileJava succeeds with zero errors • Spring context loads in @SpringBootTest (ApplicationContextLoads test passes) • server.port=8085 in application.yml • K8s deployment.yaml has replicas: 2 and memory limit 512Mi • Flyway migration location points to db/migration inside the module classpath | 45 |  | BE | API-05
8.7-T01 | shared-libs | 8.7 | 8. Partner (Northbound) API | Error model & codes | 1 | Define ApiError and ErrorDetail Java records in lib-errors | WBS 8.7: lib-errors is a Gradle shared module (libs/lib-errors/). The canonical error envelope from API-05 §8.1 is: {error:{code:string,message:string,request_id:string,details:[{field:string,issue:string}]}}. All services must return this structure on every non-2xx response. Records must be Jackson-serializable and carry no Spring dependencies so lib-errors can be used in gateway filters and adapters. | • In libs/lib-errors/src/main/java/com/gme/pay/errors/ create immutable record ApiError(String code, String message, String requestId, List<ErrorDetail> details) annotated @JsonInclude(NON_EMPTY). • Create record ErrorDetail(String field, String issue). • Add @JsonProperty aliases code, message, request_id, details (snake_case for API consumers). • Add factory method ApiError.of(GmeErrorCode code, String requestId) using code.getMessage() as default message. • Add factory method ApiError.withDetails(GmeErrorCode code, String requestId, List<ErrorDetail> details) for validation errors. • Add libs/lib-errors/build.gradle with jackson-databind only; no spring-web. | libs/lib-errors/src/main/java/com/gme/pay/errors/ApiError.java and ErrorDetail.java | • ApiError serialises to {error:{code:...,message:...,request_id:...,details:[...]}} with vanilla Jackson ObjectMapper (no Spring context). • Empty details list is omitted from JSON (NON_EMPTY). • ApiError.of(GmeErrorCode.RATE_QUOTE_EXPIRED, req1) produces code string RATE_QUOTE_EXPIRED. • ApiError.withDetails uses the provided list verbatim. • Module compiles independently without spring-web on classpath. | 30 |  | BE | API-05
8.7-T02 | shared-libs | 8.7 | 8. Partner (Northbound) API | Error model & codes | 1 | Define GmeErrorCode enum with HTTP status and retryable flag for all 37 catalog entries | WBS 8.7: Every error code from API-05 §8.2 plus ZeroPay mapping table SCH-06 §10.2 must live in a single enum in lib-errors. Each constant carries (1) int httpStatus, (2) boolean retryable, (3) String defaultMessage. Full catalog: VALIDATION_ERROR(400,false), MISSING_IDEMPOTENCY_KEY(400,false), CANCEL_NOT_PERMITTED(400,false), INVALID_SIGNATURE(401,false), INVALID_API_KEY(401,false), TIMESTAMP_OUT_OF_RANGE(401,false), INVALID_CREDENTIALS(401,false), INSUFFICIENT_PREFUNDING(402,false), FORBIDDEN(403,false), IP_NOT_ALLOWLISTED(403,false), PAYMENT_NOT_FOUND(404,false), MERCHANT_NOT_FOUND(404,false), SCHEME_NOT_FOUND(404,false), DUPLICATE_PARTNER_TXN_REF(409,false), DUPLICATE_TRANSACTION(409,false), IDEMPOTENCY_KEY_REUSE(422,false), RATE_QUOTE_EXPIRED(422,false), RATE_QUOTE_INVALID(422,false), PARTNER_B_QUOTE_DEVIATION(422,false), PARTNER_B_QUOTE_UNAVAILABLE(422,true), SCHEME_UNAVAILABLE(422,true), PAYMENT_MODE_NOT_SUPPORTED(422,false), DIRECTION_NOT_ENABLED(422,false), MERCHANT_INACTIVE(422,false), QR_DEACTIVATED(422,false), QR_EXPIRED(422,false), AMOUNT_TOO_LOW(422,false), AMOUNT_TOO_HIGH(422,false), QR_INVALID_CHECKSUM(422,false), QR_MALFORMED(422,false), NO_SCHEME_FOR_LOCATION(422,false), RATE_LIMITED(429,true), SCHEME_ERROR(502,true), SCHEME_TIMEOUT(504,true), INTERNAL_ERROR(500,true), SERVICE_UNAVAILABLE(503,true). Also add PARTNER_B_QUOTE_DEVIATION note: no prefunding deduction occurs; partner must re-quote with new Idempotency-Key. | • Create enum GmeErrorCode(int httpStatus, boolean retryable, String defaultMessage) in libs/lib-errors/src/main/java/com/gme/pay/errors/. • Add all 36 constants listed in context with correct values. • Add accessors getHttpStatus(), isRetryable(), getMessage(). • Annotate @JsonValue on name() so enum serialises as the code string (e.g. RATE_QUOTE_EXPIRED). | libs/lib-errors/src/main/java/com/gme/pay/errors/GmeErrorCode.java | • GmeErrorCode.PARTNER_B_QUOTE_UNAVAILABLE.isRetryable() == true. • GmeErrorCode.INSUFFICIENT_PREFUNDING.getHttpStatus() == 402 and isRetryable() == false. • GmeErrorCode.RATE_LIMITED.getHttpStatus() == 429 and isRetryable() == true. • GmeErrorCode.INVALID_SIGNATURE.isRetryable() == false. • Enum values().length == 36. • Jackson serialises GmeErrorCode.RATE_QUOTE_EXPIRED as the string RATE_QUOTE_EXPIRED. | 35 | 8.7-T01 | BE | API-05
8.7-T03 | shared-libs | 8.7 | 8. Partner (Northbound) API | Error model & codes | 1 | Create GmeException runtime exception wrapping GmeErrorCode | WBS 8.7: Services throw GmeException(GmeErrorCode, optional message override, optional List<ErrorDetail>) which the global exception handler translates to the ApiError envelope. The exception lives in lib-errors with no Spring dependency. | • Create class GmeException extends RuntimeException in libs/lib-errors/src/main/java/com/gme/pay/errors/. • Add fields: GmeErrorCode errorCode, String messageOverride, List<ErrorDetail> details. • Add constructors: (GmeErrorCode), (GmeErrorCode,String), (GmeErrorCode,List<ErrorDetail>), (GmeErrorCode,String,List<ErrorDetail>). • Add getErrorCode(), getDetails(), resolveMessage() — returns messageOverride if non-null else errorCode.getMessage(). • Add static factories of(GmeErrorCode) and withDetails(GmeErrorCode,List<ErrorDetail>). | libs/lib-errors/src/main/java/com/gme/pay/errors/GmeException.java | • GmeException(GmeErrorCode.RATE_QUOTE_EXPIRED).resolveMessage() returns the enum default message. • GmeException(RATE_QUOTE_EXPIRED,custom).resolveMessage() returns custom. • getErrorCode() returns the code passed at construction. • Static of() returns a GmeException instance with correct code. • Compiles without Spring or Jackson on classpath. | 20 | 8.7-T02 | BE | API-05
8.7-T04 | shared-libs | 8.7 | 8. Partner (Northbound) API | Error model & codes | 1 | Implement GlobalExceptionHandler @RestControllerAdvice in lib-errors | WBS 8.7: Every Spring Boot service must map GmeException and standard Spring exceptions to the API-05 §8.1 envelope. The handler lives in lib-errors as a Spring-autoconfigured @RestControllerAdvice so each service auto-registers it. It reads X-Request-ID from the request to populate error.request_id. Handles: (1) GmeException — HTTP status from errorCode.getHttpStatus(); (2) MethodArgumentNotValidException — 400 VALIDATION_ERROR with per-field ErrorDetail list; (3) fallback Exception — 500 INTERNAL_ERROR. | • Create class GlobalExceptionHandler annotated @RestControllerAdvice in libs/lib-errors/src/main/java/com/gme/pay/errors/web/. • @ExceptionHandler(GmeException.class): build ApiError from exception, set HTTP status from errorCode.getHttpStatus(), populate request_id from HttpServletRequest X-Request-ID header. • @ExceptionHandler(MethodArgumentNotValidException.class): map BindingResult field errors to ErrorDetail list, return VALIDATION_ERROR 400. • @ExceptionHandler(Exception.class): log at ERROR level (no stack trace in response body), return INTERNAL_ERROR 500 with request_id. • Register via META-INF/spring/org.springframework.boot.autoconfigure.AutoConfiguration.imports. • Add spring-web and spring-boot-autoconfigure as compileOnly/api in libs/lib-errors/build.gradle. | libs/lib-errors/src/main/java/com/gme/pay/errors/web/GlobalExceptionHandler.java and META-INF/spring/org.springframework.boot.autoconfigure.AutoConfiguration.imports | • MockMvc: controller throws GmeException(RATE_QUOTE_EXPIRED) -> HTTP 422, body error.code == RATE_QUOTE_EXPIRED. • MockMvc: MethodArgumentNotValidException on field amount -> HTTP 400, body error.details[0].field == amount. • Fallback Exception -> HTTP 500, code == INTERNAL_ERROR, response body contains no stack trace text. • error.request_id equals X-Request-ID header value from the request. • Handler auto-registers in a service with lib-errors dependency without any @ComponentScan change. | 40 | 8.7-T03 | BE | API-05
8.7-T05 | shared-libs | 8.7 | 8. Partner (Northbound) API | Error model & codes | 1 | Implement Spring Cloud Gateway WebExceptionHandler for API-05 error envelope | WBS 8.7: The Spring Cloud Gateway (module services/gateway/) uses reactive WebFlux. When a downstream service is unreachable or returns an unexpected error, the Gateway must wrap it in the API-05 envelope. A per-request ULID is generated as X-Request-ID, injected downstream, and echoed in the error response. Downstream 4xx/5xx responses that already match the envelope are passed through unchanged. | • Create GatewayErrorWebExceptionHandler implements WebExceptionHandler in services/gateway/src/main/java/com/gme/pay/gateway/error/. • On ConnectException or TimeoutException return ApiError with GmeErrorCode.SERVICE_UNAVAILABLE (503). • On WebClientResponseException: if body parses as API-05 envelope pass through; otherwise wrap as GmeErrorCode.INTERNAL_ERROR. • Generate ULID request_id per request using java.util.UUID.randomUUID() as interim; propagate as X-Request-ID header to downstream and into error response. • Register as @Bean with Ordered.HIGHEST_PRECEDENCE - 1 to outrank DefaultErrorWebExceptionHandler. • Emit Micrometer counter gateway_errors_total with tags error_code and http_status. | services/gateway/src/main/java/com/gme/pay/gateway/error/GatewayErrorWebExceptionHandler.java | • WireMock test: downstream returns 500 raw text -> Gateway responds with {error:{code:INTERNAL_ERROR}} HTTP 500. • WireMock test: downstream returns valid API-05 422 body -> Gateway passes it through unchanged with same HTTP status. • X-Request-ID is present in both downstream request header and error response body. • Micrometer counter gateway_errors_total incremented with correct error_code tag. • Bean ordering verified: GatewayErrorWebExceptionHandler.getOrder() < DefaultErrorWebExceptionHandler.getOrder(). | 45 | 8.7-T03 | BE | API-05
8.7-T06 | shared-libs | 8.7 | 8. Partner (Northbound) API | Error model & codes | 1 | Flyway migration V901__error_audit_log.sql in db/migrations | WBS 8.7: PostgreSQL 16 compliance table error_audit_log persists every 4xx/5xx on money-path endpoints. DDL: id BIGSERIAL PRIMARY KEY, request_id VARCHAR(36) NOT NULL, partner_id UUID, error_code VARCHAR(80) NOT NULL, http_status SMALLINT NOT NULL CHECK(http_status BETWEEN 400 AND 599), endpoint VARCHAR(200), retryable BOOLEAN NOT NULL DEFAULT false, created_at TIMESTAMPTZ NOT NULL DEFAULT now(). Index idx_error_audit_partner ON (partner_id, created_at DESC). Migration lives under db/migrations/ and is consumed by lib-persistence's Flyway location list so all money-path services apply it. | • Create db/migrations/V901__error_audit_log.sql with CREATE TABLE and index as specified. • Add CHECK constraint http_status BETWEEN 400 AND 599. • Verify idempotency: migration is Flyway-checksum-protected (do not use IF NOT EXISTS; let Flyway manage). • Register db/migrations/ as an additional Flyway location in libs/lib-persistence/src/main/resources/application-persistence.yaml. | db/migrations/V901__error_audit_log.sql | • Flyway applies migration against Testcontainers Postgres 16 without error. • INSERT with http_status 200 violates CHECK constraint and is rejected. • Index idx_error_audit_partner exists after migration (query information_schema.statistics). • Column error_code has NOT NULL constraint confirmed via information_schema.columns. • Re-running Flyway against same DB does not re-apply (checksum match). | 25 |  | BE | API-05
8.7-T07 | shared-libs | 8.7 | 8. Partner (Northbound) API | Error model & codes | 1 | Create ErrorAuditLog JPA entity and Spring Data repository in lib-persistence | WBS 8.7: The error_audit_log table (V901 migration) needs a JPA @Entity and Spring Data JPA repository in libs/lib-persistence/ so money-path services share the ORM without duplication. Fields: id Long, requestId String(36), partnerId UUID, errorCode String(80), httpStatus Short, endpoint String(200), retryable boolean, createdAt Instant. Repository wraps save in REQUIRES_NEW propagation so audit write survives a business transaction rollback. | • Create @Entity class ErrorAuditLog with @Table(name=error_audit_log) in libs/lib-persistence/src/main/java/com/gme/pay/persistence/error/. • Map all columns per V901 DDL with @Column constraints (nullable, length). • Create interface ErrorAuditLogRepository extends JpaRepository<ErrorAuditLog,Long>. • Add derived query findByPartnerIdAndCreatedAtBetween(UUID,Instant,Instant). • Add @Service class ErrorAuditService wrapping repository.save() in @Transactional(propagation=REQUIRES_NEW). | libs/lib-persistence/src/main/java/com/gme/pay/persistence/error/ErrorAuditLog.java, ErrorAuditLogRepository.java, ErrorAuditService.java | • @DataJpaTest with Testcontainers Postgres 16: persist and retrieve ErrorAuditLog row, all fields round-trip correctly. • findByPartnerIdAndCreatedAtBetween returns only rows within the time window. • Audit save in REQUIRES_NEW completes even when caller transaction is rolled back (verified via Testcontainers test). • Entity field count matches V901 column count (8 columns). | 30 | 8.7-T06 | BE | API-05
8.7-T08 | shared-libs | 8.7 | 8. Partner (Northbound) API | Error model & codes | 1 | Wire error audit logging into GlobalExceptionHandler | WBS 8.7: GlobalExceptionHandler (T04) must persist every handled exception to error_audit_log via ErrorAuditService (T07). The audit write must not fail the HTTP response even if the DB write throws. Use @ConditionalOnBean(ErrorAuditService.class) so services without persistence skip the step. Extract partner_id from Spring Security JWT claim partner_id or from request attribute injected by Gateway. | • Inject ErrorAuditService (optional: @Autowired(required=false)) into GlobalExceptionHandler. • After building ApiError, invoke auditService.save(requestId, partnerId, code, status, endpoint, retryable) inside try-catch(Exception e){log.warn(...)}. • Extract partner_id from SecurityContextHolder JWT claims; accept null if unauthenticated. • Annotate audit wiring with @ConditionalOnBean(ErrorAuditService.class) so it is a no-op when persistence is absent. • Add libs/lib-errors/build.gradle optional dependency on libs/lib-persistence. | Updated libs/lib-errors/src/main/java/com/gme/pay/errors/web/GlobalExceptionHandler.java (audit wiring diff) | • Unit test: mock ErrorAuditService throws RuntimeException -> response still returns 422 envelope, no 500 wrapping. • Integration test with Testcontainers Postgres: GmeException(INSUFFICIENT_PREFUNDING) thrown -> error_audit_log row exists with error_code=INSUFFICIENT_PREFUNDING and retryable=false. • Services without ErrorAuditService bean start without error. • partner_id stored from JWT claim; null accepted when claim absent. | 35 | 8.7-T04, 8.7-T07 | BE | API-05
8.7-T09 | shared-libs | 8.7 | 8. Partner (Northbound) API | Error model & codes | 1 | Implement ZeroPayErrorMapper: ZP scheme code to GmeErrorCode translation | WBS 8.7: The Scheme Adapter Layer (services/scheme-adapter-zeropay/) receives raw ZeroPay result codes and must translate them to GmeErrorCode before surfacing to Hub Core. Mapping from spec SCH-06 §10.2: ZP 1001->MERCHANT_NOT_FOUND, 1002->MERCHANT_INACTIVE, 1003->QR_DEACTIVATED, 1004->QR_EXPIRED, 2001->AMOUNT_TOO_LOW, 2002->AMOUNT_TOO_HIGH, 3001->SCHEME_TIMEOUT, 3002->SCHEME_ERROR, 4001->DUPLICATE_TRANSACTION. Unknown codes -> SCHEME_ERROR. Extended error body must include scheme_error_code (raw ZP code) per spec §10.2: the scheme_error_code field in the extended error body contains the raw ZeroPay code for partner diagnostics. | • Create ZeroPayErrorMapper in services/scheme-adapter-zeropay/src/main/java/com/gme/pay/adapter/zeropay/error/. • Implement static GmeErrorCode map(String zpCode) using a static final Map<String,GmeErrorCode> (not switch). • Implement GmeException toException(String zpCode) producing GmeException whose message includes the raw zpCode. • Create record ExtendedSchemeError(ApiError error, String schemeErrorCode) with @JsonProperty(scheme_error_code). • Map unknown ZP codes to SCHEME_ERROR as fallback. | services/scheme-adapter-zeropay/src/main/java/com/gme/pay/adapter/zeropay/error/ZeroPayErrorMapper.java and ExtendedSchemeError.java | • map(1001) == MERCHANT_NOT_FOUND; map(3001) == SCHEME_TIMEOUT; map(9999) == SCHEME_ERROR (unknown fallback). • toException(3002).getErrorCode() == SCHEME_ERROR and message contains 3002. • ExtendedSchemeError Jackson serialisation includes scheme_error_code field alongside error object. • Unit test covers all 9 defined ZP codes plus unknown fallback (10 cases). | 30 | 8.7-T02 | BE | API-05
8.7-T10 | shared-libs | 8.7 | 8. Partner (Northbound) API | Error model & codes | 1 | Redis-backed idempotency error replay in lib-errors | WBS 8.7: API-05 §C-16 and §8.2: idempotent retry with same Idempotency-Key and same request body must return the stored response (including stored error responses). Different body with same key returns IDEMPOTENCY_KEY_REUSE(409). Error responses are also idempotent: a retry of a 422 RATE_QUOTE_EXPIRED must return the same 422 without reprocessing. Store: Redis (Spring Data Redis StringRedisTemplate) with TTL 24 h. Store key = SHA-256(partner_id + Idempotency-Key). Stored value = JSON(ApiError) + HTTP status int. | • Create IdempotencyStore in libs/lib-errors/src/main/java/com/gme/pay/errors/idempotency/ using StringRedisTemplate. • On error response, serialise {statusCode, body} JSON and SETEX key ttl=86400. • Create IdempotencyInterceptor implements HandlerInterceptor: preHandle checks Redis; if hit and body SHA-256 matches, write stored response and return false. • If key exists with different body SHA-256, throw GmeException(IDEMPOTENCY_KEY_REUSE). • Register interceptor via Spring auto-configuration (WebMvcConfigurer). | libs/lib-errors/src/main/java/com/gme/pay/errors/idempotency/IdempotencyStore.java and IdempotencyInterceptor.java | • Testcontainers Redis 7: first POST returns 422 RATE_QUOTE_EXPIRED and stores entry; second POST with same key returns identical 422 without handler invocation (spy count == 1). • Same key different body returns 409 IDEMPOTENCY_KEY_REUSE. • Redis TTL for stored key is between 86380 and 86400 s immediately after storage. • Two partners with same raw Idempotency-Key value produce different Redis keys (no cross-partner collision). | 45 | 8.7-T03 | BE | API-05
8.7-T11 | shared-libs | 8.7 | 8. Partner (Northbound) API | Error model & codes | 1 | Gradle task generateErrorCodeYaml to keep openapi/partner-api.yaml enum in sync | WBS 8.7: The partner-facing OpenAPI spec openapi/partner-api.yaml must enumerate all GmeErrorCode values under components/schemas/ErrorCode/enum. A Gradle task reflects GmeErrorCode.values() post-compile and replaces only that enum block in the YAML. A CI check (./gradlew generateErrorCodeYaml && git diff --exit-code openapi/partner-api.yaml) fails the build if the spec drifts from the enum. | • Add task generateErrorCodeYaml to libs/lib-errors/build.gradle depending on compileJava. • Load GmeErrorCode via URLClassLoader on the compiled classes dir; collect names(). • Read openapi/partner-api.yaml; replace the enum: [...] list under components/schemas/ErrorCode with the collected names. • Write back only the changed block; validate updated YAML with SnakeYAML parser inside the task. • Document CI usage in task description. | Updated libs/lib-errors/build.gradle (generateErrorCodeYaml task) and openapi/partner-api.yaml with generated ErrorCode enum block | • Adding a new GmeErrorCode constant and running the task adds it to the YAML enum. • CI diff check fails if enum is manually edited without running the task (git diff exits non-zero). • Generated YAML parses without error via SnakeYAML. • All 36 constants appear in the generated enum block. | 35 | 8.7-T02 | BE | API-05
8.7-T12 | shared-libs | 8.7 | 8. Partner (Northbound) API | Error model & codes | 1 | Define OpenAPI error components in openapi/partner-api.yaml | WBS 8.7: The OpenAPI spec must define reusable components: ErrorBody (code ref ErrorCode, message, request_id, details array), ErrorDetail (field, issue), ErrorEnvelope response wrapping ErrorBody under key error. All 4xx/5xx responses across every endpoint must $ref #/components/responses/ErrorEnvelope rather than use inline schemas. This enables schemathesis to validate all error paths. | • Add components/schemas/ErrorBody: {type:object, required:[code,message,request_id], properties:{code:{$ref:ErrorCode},message:{type:string},request_id:{type:string},details:{type:array,items:{$ref:ErrorDetail}}}}. • Add components/schemas/ErrorDetail: {type:object, required:[field,issue], properties:{field:{type:string},issue:{type:string}}}. • Add components/responses/ErrorEnvelope: {description:Error,content:{application/json:{schema:{type:object,required:[error],properties:{error:{$ref:ErrorBody}}}}}}. • Replace all existing inline 4xx/5xx response schemas in every endpoint with $ref:#/components/responses/ErrorEnvelope. | openapi/partner-api.yaml (ErrorEnvelope, ErrorBody, ErrorDetail components + all endpoint error $ref updates) | • swagger-parser validates the YAML with zero schema errors. • grep -c inline_error_schema openapi/partner-api.yaml returns 0 (no inline error schemas remain). • ErrorCode enum block populated by generateErrorCodeYaml task contains all 36 constants. • schemathesis smoke run against sandbox returns zero schema-mismatch findings on any error path. | 40 | 8.7-T11 | BE | API-05
8.7-T13 | shared-libs | 8.7 | 8. Partner (Northbound) API | Error model & codes | 1 | Add Micrometer error-rate metrics to GlobalExceptionHandler | WBS 8.7: Each error response must emit Micrometer counter api_errors_total with tags: error_code (GmeErrorCode name), http_status (int as string), retryable (true/false), service (spring.application.name). Metric exported via Actuator /actuator/prometheus to Prometheus/Grafana. Auto-configured in lib-errors so all services get it without per-service change. | • Inject MeterRegistry @Autowired(required=false) into GlobalExceptionHandler. • After building ApiError call meterRegistry.counter(api_errors_total, tags...).increment() inside null-check. • Tags: error_code=code.name(), http_status=String.valueOf(status), retryable=String.valueOf(retryable), service=env.getProperty(spring.application.name,unknown). • Verify no NPE when MeterRegistry is absent (no Micrometer on classpath). | Updated libs/lib-errors/src/main/java/com/gme/pay/errors/web/GlobalExceptionHandler.java (Micrometer wiring) | • Unit test with SimpleMeterRegistry: throw GmeException(RATE_LIMITED) -> counter api_errors_total with tag error_code=RATE_LIMITED count == 1. • Tags retryable=true confirmed for RATE_LIMITED; retryable=false for RATE_QUOTE_EXPIRED. • Service without MeterRegistry bean starts and handles exceptions without NPE. • Actuator /actuator/prometheus in @SpringBootTest shows api_errors_total counter line after test error. | 30 | 8.7-T04 | BE | API-05
8.7-T14 | shared-libs | 8.7 | 8. Partner (Northbound) API | Error model & codes | 1 | Unit tests: GmeErrorCode invariants and ApiError Jackson serialisation | WBS 8.7: Explicit unit-test ticket. All 36 GmeErrorCode constants must satisfy spec invariants; ApiError Jackson round-trip must be verified. Use JUnit 5 + Jackson ObjectMapper only (no Spring context). Test class in libs/lib-errors/src/test/. | • Write @ParameterizedTest over GmeErrorCode.values() asserting httpStatus is in {400,401,402,403,404,409,422,429,500,502,503,504}, message is non-blank, retryable matches spec table for spot-checked codes. • Write test: ApiError.of(RATE_QUOTE_EXPIRED,req1) -> serialise -> deserialise -> assert code==RATE_QUOTE_EXPIRED and request_id==req1. • Write test: details==empty list omitted from JSON output (NON_EMPTY check). • Write test: GmeException with override message -> resolveMessage returns override. • Write test: GmeException without override -> resolveMessage returns enum defaultMessage. | libs/lib-errors/src/test/java/com/gme/pay/errors/GmeErrorCodeTest.java and ApiErrorSerializationTest.java | • All 36 constants pass HTTP-status validity assertion. • PARTNER_B_QUOTE_UNAVAILABLE retryable==true and RATE_QUOTE_EXPIRED retryable==false verified parametrically. • Round-trip test passes with default ObjectMapper (no custom config). • Empty details list is absent from serialised JSON string. • All tests complete in under 5 s (no I/O). | 30 | 8.7-T02, 8.7-T01, 8.7-T03 | BE | API-05
8.7-T15 | shared-libs | 8.7 | 8. Partner (Northbound) API | Error model & codes | 1 | Integration tests: GlobalExceptionHandler with @WebMvcTest MockMvc | WBS 8.7: Spring Boot test-slice tests for GlobalExceptionHandler (T04) using @WebMvcTest. Stub controller triggers each exception category. Verify correct HTTP status, error_code, and request_id echo. No Testcontainers needed. | • Create @WebMvcTest(GlobalExceptionHandlerIT.TestController.class) in libs/lib-errors/src/test/. • Add inner @RestController with endpoints: /throw-gme throwing GmeException(INSUFFICIENT_PREFUNDING), /throw-validation throwing MethodArgumentNotValidException, /throw-rate-limited throwing GmeException(RATE_LIMITED), /throw-generic throwing RuntimeException. • Assert HTTP 402 + code INSUFFICIENT_PREFUNDING on /throw-gme. • Assert HTTP 400 + code VALIDATION_ERROR + non-empty details on /throw-validation. • Assert HTTP 429 + code RATE_LIMITED + retryable confirmed in response body. • Assert HTTP 500 + code INTERNAL_ERROR on /throw-generic and confirm body does not contain StackTrace text. • Assert error.request_id equals X-Request-ID header in all cases. | libs/lib-errors/src/test/java/com/gme/pay/errors/web/GlobalExceptionHandlerIT.java | • HTTP 402 and INSUFFICIENT_PREFUNDING confirmed. • HTTP 429 and RATE_LIMITED confirmed. • HTTP 500 body contains no stack trace text. • error.request_id equals X-Request-ID header. • MethodArgumentNotValidException produces details array with at least one ErrorDetail. | 35 | 8.7-T04 | BE | API-05
8.7-T16 | shared-libs | 8.7 | 8. Partner (Northbound) API | Error model & codes | 1 | Integration tests: ZeroPayErrorMapper unit and ExtendedSchemeError serialisation | WBS 8.7: Unit tests for ZeroPayErrorMapper (T09) covering all 9 defined ZP code mappings, unknown code fallback, toException message content, and ExtendedSchemeError JSON shape. JUnit 5 + Jackson only; no Spring context. | • Write @ParameterizedTest with arguments: 1001->MERCHANT_NOT_FOUND, 1002->MERCHANT_INACTIVE, 1003->QR_DEACTIVATED, 1004->QR_EXPIRED, 2001->AMOUNT_TOO_LOW, 2002->AMOUNT_TOO_HIGH, 3001->SCHEME_TIMEOUT, 3002->SCHEME_ERROR, 4001->DUPLICATE_TRANSACTION. • Write test: map(9999) -> SCHEME_ERROR (unknown fallback). • Write test: toException(3001).getErrorCode() == SCHEME_TIMEOUT and message contains string 3001. • Write test: ExtendedSchemeError serialised JSON contains scheme_error_code field with value equal to raw ZP string. | services/scheme-adapter-zeropay/src/test/java/com/gme/pay/adapter/zeropay/error/ZeroPayErrorMapperTest.java | • All 9 defined ZP codes assert correct GmeErrorCode. • map(9999) returns SCHEME_ERROR. • toException message includes raw ZP code string. • JSON path $.scheme_error_code present and equals raw ZP code. • Tests complete in under 3 s. | 25 | 8.7-T09 | BE | API-05
8.7-T17 | shared-libs | 8.7 | 8. Partner (Northbound) API | Error model & codes | 1 | Integration tests: idempotency error replay with Testcontainers Redis 7 | WBS 8.7: Integration tests for IdempotencyStore and IdempotencyInterceptor (T10). Verify: (1) same key + same body returns stored 422 without handler re-invocation; (2) same key + different body returns 409 IDEMPOTENCY_KEY_REUSE; (3) Redis TTL is within 86380-86400 s; (4) partner isolation (two partners with same Idempotency-Key value use different Redis keys). | • Create @SpringBootTest IdempotencyInterceptorIT using @Testcontainers with GenericContainer redis:7-alpine. • Configure StringRedisTemplate with Testcontainers port. • Test 1: POST with key K1 body B1 -> 422; POST again K1+B1 -> 422; assert handler spy invoked exactly once. • Test 2: POST K2+B1 then POST K2+B2 -> 409 IDEMPOTENCY_KEY_REUSE. • Test 3: after first POST assert Redis TTL for key is between 86380 and 86400. • Test 4: POST with partner1+K3 and partner2+K3 -> two distinct Redis keys (verify via RedisTemplate.hasKey). | libs/lib-errors/src/test/java/com/gme/pay/errors/idempotency/IdempotencyInterceptorIT.java | • Handler spy count == 1 after two identical requests. • HTTP 409 IDEMPOTENCY_KEY_REUSE on body mismatch. • Redis TTL within 86380-86400 s range. • Two partners with same Idempotency-Key have distinct Redis keys (no collision). | 45 | 8.7-T10 | BE | API-05
8.7-T18 | shared-libs | 8.7 | 8. Partner (Northbound) API | Error model & codes | 1 | Wire lib-errors as dependency in all money-path services and remove ad-hoc error handlers | WBS 8.7: lib-errors must be the sole source of error envelope logic across: services/rate-fx, services/payment-executor, services/prefunding-balance, services/transaction-mgmt, services/auth-identity, services/gateway. Any existing ad-hoc @ControllerAdvice, ErrorResponse POJO, or ApiError class in those services must be removed and replaced with GmeException throws. | • Add implementation(project(:libs:lib-errors)) to build.gradle of each of the 6 listed services. • Search each service src tree for @ControllerAdvice, @ExceptionHandler, ErrorResponse, ApiError classes; delete them. • Replace any direct JSON error construction in service code with throw new GmeException(appropriate_code). • Run ./gradlew :services:rate-fx:test :services:payment-executor:test :services:prefunding-balance:test to confirm green. • Add @SpringBootTest smoke test in each service confirming exactly one ExceptionHandler bean exists (the lib-errors one). | Updated build.gradle files for 6 services; deleted ad-hoc error-handler classes; updated service code to throw GmeException | • ./gradlew build passes with no compilation errors across all 6 services. • grep -r @ControllerAdvice services/ returns only lib-errors GlobalExceptionHandler entry. • Each service smoke test ApplicationContext contains exactly one ExceptionHandler bean. • MockMvc slice test in services/rate-fx confirms a thrown GmeException(RATE_QUOTE_EXPIRED) returns the canonical envelope with HTTP 422. | 40 | 8.7-T04, 8.7-T08 | BE | API-05
8.8-T01 | api-gateway | 8.8 | 8. Partner (Northbound) API | Rate limiting & IP allowlist | 1 | Flyway migration: partner_ip_allowlist and partner_rate_limit_config tables | Spring Cloud Gateway needs per-partner IP allowlist (up to 10 CIDR ranges; HTTP 403 IP_NOT_ALLOWLISTED when configured but source IP not matched; applied before signature check) and per-partner rate-limit overrides. Default limits per API-05 sec 3.5: 100 req/s global per partner, 20 req/s on POST /v1/rates, 50 req/s on POST /v1/payments and POST /v1/payments/cpm/generate. SEC-09 sec 5.4 adds 300 rpm global and 120 rpm quote per partner. Tables live in the services/gateway module Flyway path. | • Create services/gateway/src/main/resources/db/migration/V8001__gateway_ip_allowlist.sql with partner_ip_allowlist(id BIGINT GENERATED ALWAYS AS IDENTITY PK, partner_id BIGINT NOT NULL REFERENCES partner(id), cidr_range VARCHAR(50) NOT NULL, is_active BOOLEAN NOT NULL DEFAULT TRUE, created_by VARCHAR(64) NOT NULL, created_at TIMESTAMPTZ NOT NULL DEFAULT now(), updated_at TIMESTAMPTZ NOT NULL DEFAULT now()); add UNIQUE(partner_id, cidr_range); add index idx_ip_allowlist_partner ON partner_ip_allowlist(partner_id) WHERE is_active=TRUE • Create services/gateway/src/main/resources/db/migration/V8002__gateway_rate_limit_config.sql with partner_rate_limit_config(id BIGINT GENERATED ALWAYS AS IDENTITY PK, partner_id BIGINT NOT NULL UNIQUE REFERENCES partner(id), global_rps INT NOT NULL DEFAULT 100, rates_rps INT NOT NULL DEFAULT 20, payments_rps INT NOT NULL DEFAULT 50, cpm_rps INT NOT NULL DEFAULT 50, global_rpm INT NOT NULL DEFAULT 300, quote_rpm INT NOT NULL DEFAULT 120, updated_by VARCHAR(64) NOT NULL, updated_at TIMESTAMPTZ NOT NULL DEFAULT now()); add CHECK(global_rps BETWEEN 1 AND 10000), CHECK(rates_rps BETWEEN 1 AND 10000), CHECK(payments_rps BETWEEN 1 AND 10000), CHECK(cpm_rps BETWEEN 1 AND 10000) • Add Flyway and PostgreSQL JDBC dependencies to services/gateway/build.gradle if not already present | services/gateway/src/main/resources/db/migration/V8001__gateway_ip_allowlist.sql and V8002__gateway_rate_limit_config.sql | • V8001 creates partner_ip_allowlist with all columns, FK to partner, UNIQUE(partner_id,cidr_range), and partial index on is_active=TRUE • V8002 creates partner_rate_limit_config with correct DEFAULT values (global_rps=100, rates_rps=20, payments_rps=50, cpm_rps=50, global_rpm=300, quote_rpm=120) and CHECK constraints • CHECK constraint rejects global_rps=0 with a constraint violation • flyway migrate runs clean against a Testcontainers PostgreSQL 16 instance without error • Inserting a CIDR duplicate for same partner violates UNIQUE constraint | 25 |  | BE | API-05, SEC-09
8.8-T02 | api-gateway | 8.8 | 8. Partner (Northbound) API | Rate limiting & IP allowlist | 1 | JPA entities and repositories for IpAllowlistEntry and PartnerRateLimitConfig in services/gateway | Spring Cloud Gateway service (services/gateway, Java 21, Spring Boot 3.x) needs JPA entities and Spring Data repositories for the two tables added in 8.8-T01. These are used by the IP allowlist filter and the dynamic rate-limit resolver to load per-partner config from PostgreSQL (then cached in Redis via PartnerConfigCache in 8.8-T03). | • Create services/gateway/src/main/java/com/gme/pay/gateway/persistence/IpAllowlistEntry.java as @Entity @Table(name=partner_ip_allowlist) with fields: id Long, partnerId Long, cidrRange String, isActive boolean, createdBy String, createdAt Instant, updatedAt Instant; add @Index on partnerId in @Table annotation • Create services/gateway/src/main/java/com/gme/pay/gateway/persistence/PartnerRateLimitConfig.java as @Entity @Table(name=partner_rate_limit_config) with fields: id Long, partnerId Long, globalRps int, ratesRps int, paymentsRps int, cpmRps int, globalRpm int, quoteRpm int, updatedBy String, updatedAt Instant • Create IpAllowlistRepository extends JpaRepository<IpAllowlistEntry,Long> with query method List<IpAllowlistEntry> findByPartnerIdAndIsActiveTrue(Long partnerId) • Create PartnerRateLimitConfigRepository extends JpaRepository<PartnerRateLimitConfig,Long> with Optional<PartnerRateLimitConfig> findByPartnerId(Long partnerId) | services/gateway/src/main/java/com/gme/pay/gateway/persistence/IpAllowlistEntry.java, PartnerRateLimitConfig.java, IpAllowlistRepository.java, PartnerRateLimitConfigRepository.java | • @DataJpaTest with Testcontainers PostgreSQL 16 can persist and retrieve IpAllowlistEntry; findByPartnerIdAndIsActiveTrue returns only is_active=TRUE rows • @DataJpaTest can persist and retrieve PartnerRateLimitConfig by partnerId • Entity field names match migration column names via @Column annotations (snake_case DB, camelCase Java) • No Hibernate schema-generation warnings at application startup | 30 | 8.8-T01 | BE | API-05, SEC-09
8.8-T03 | api-gateway | 8.8 | 8. Partner (Northbound) API | Rate limiting & IP allowlist | 1 | Implement PartnerConfigCache: Redis-backed cache for IP allowlist and rate-limit config | The IP allowlist filter and rate-limit resolver both need per-partner config. Config must be cached in Redis (the stack cache layer) with TTL 300s (configurable via gateway.cache.ttl-seconds) so that IP allowlist changes take effect within 5 minutes per API-05 sec 3.3. An evict() method is called by the admin service on every config change. Module: services/gateway. Uses IpAllowlistRepository and PartnerRateLimitConfigRepository from 8.8-T02. | • Create services/gateway/src/main/java/com/gme/pay/gateway/cache/PartnerConfigCache.java as a @Component using Spring Data Redis (ReactiveRedisTemplate<String,String> for reactive gateway context) • Implement Mono<List<IpAllowlistEntry>> getIpAllowlist(Long partnerId): check Redis key gateway:ip_allowlist:{partnerId}; if absent load from IpAllowlistRepository via subscribeOn(boundedElastic), serialize to JSON, store with TTL 300s, return • Implement Mono<PartnerRateLimitConfig> getRateLimitConfig(Long partnerId): check Redis key gateway:rate_limit:{partnerId}; if absent load from PartnerRateLimitConfigRepository; if no DB row return default config (globalRps=100, ratesRps=20, paymentsRps=50, cpmRps=50, globalRpm=300, quoteRpm=120); cache result with TTL 300s • Implement Mono<Void> evict(Long partnerId): delete both Redis keys gateway:ip_allowlist:{partnerId} and gateway:rate_limit:{partnerId} • Add @ConfigurationProperties(prefix=gateway.cache) with field ttlSeconds defaulting to 300 | services/gateway/src/main/java/com/gme/pay/gateway/cache/PartnerConfigCache.java | • On first call getIpAllowlist queries PostgreSQL and writes to Redis; second call within TTL returns from Redis (verify by counting repository mock invocations = 1) • After evict(partnerId) next getIpAllowlist call queries PostgreSQL again (count increments to 2) • TTL of Redis key is between 295 and 310 seconds after write (check via RedisTemplate.getExpire) • getRateLimitConfig with no DB row returns defaults: globalRps=100, ratesRps=20, paymentsRps=50, cpmRps=50 • Testcontainers Redis 7 used in integration test | 35 | 8.8-T02 | BE | API-05, SEC-09
8.8-T04 | api-gateway | 8.8 | 8. Partner (Northbound) API | Rate limiting & IP allowlist | 1 | Implement PartnerIdExtractor: resolve partner_id from X-Api-Key header with Redis read-through cache | Gateway filters (IP allowlist and rate limiter) need the partner_id (Long) to look up per-partner config. The partner_id is resolved from the X-Api-Key header by consulting the partner_credential table (api_key VARCHAR(64) UNIQUE, partner_id BIGINT FK, is_active BOOLEAN). A Redis read-through cache at key gateway:api_key:{apiKey} with TTL 60s avoids a DB hit on every request. Unknown keys are cached as a miss-sentinel (value -1, TTL 10s) to prevent DB hammering. Module: services/gateway. | • Create services/gateway/src/main/java/com/gme/pay/gateway/auth/PartnerIdExtractor.java as a @Component • Implement Mono<Optional<Long>> resolve(ServerWebExchange exchange): extract X-Api-Key header; if absent return Mono.just(Optional.empty()) • Check Redis key gateway:api_key:{apiKey}: if value is numeric and > 0 return that partner_id; if value equals -1 return Optional.empty() (cached miss) • If key absent: query partner_credential WHERE api_key=? AND is_active=TRUE via PartnerCredentialRepository (new repository, query method findByApiKeyAndIsActiveTrue); if found cache partnerId with TTL 60s; if not found cache -1 with TTL 10s; return accordingly • Inject into IpAllowlistGatewayFilter (8.8-T05) and PartnerRateLimitKeyResolver (8.8-T07) | services/gateway/src/main/java/com/gme/pay/gateway/auth/PartnerIdExtractor.java and PartnerCredentialRepository.java | • Valid api_key returns correct partner_id from DB on first call; Redis cache hit on second call (repository invoked once total) • Missing X-Api-Key header returns Optional.empty() with zero DB calls • Unknown api_key caches miss sentinel; second call within 10s does not hit DB • Inactive credential (is_active=FALSE) returns Optional.empty() • Testcontainers Redis 7 + PostgreSQL 16 integration test | 30 | 8.8-T02 | BE | API-05, SEC-09
8.8-T05 | api-gateway | 8.8 | 8. Partner (Northbound) API | Rate limiting & IP allowlist | 1 | Implement IpAllowlistGatewayFilter: Spring Cloud Gateway GlobalFilter for IP allowlist enforcement | API-05 sec 3.3: if a partner has any active CIDR entries in partner_ip_allowlist, requests whose source IP does not match any CIDR must be rejected with HTTP 403 and JSON body {errorCode: IP_NOT_ALLOWLISTED, message: Request source IP is not on partner IP allowlist} before signature verification. If the partner has no CIDRs the filter is a no-op. Source IP is taken from X-Forwarded-For first hop; falls back to RemoteAddr. Module: services/gateway. | • Create services/gateway/src/main/java/com/gme/pay/gateway/filter/IpAllowlistGatewayFilter.java implementing GlobalFilter and Ordered with getOrder() = Ordered.HIGHEST_PRECEDENCE + 10 • Extract client IP: split X-Forwarded-For on comma and use first element if present; otherwise use exchange.getRequest().getRemoteAddress() • Call PartnerIdExtractor.resolve; if empty proceed (auth will fail later, not this filter's concern) • Call PartnerConfigCache.getIpAllowlist(partnerId).flatMap: if list empty proceed; else check source IP against each cidr_range using Apache Commons Net SubnetUtils (commons-net dependency) • On match proceed; on no match set status 403, write JSON error body {errorCode: IP_NOT_ALLOWLISTED, message: Request source IP is not on partner IP allowlist}, log WARN via SLF4J with MDC fields partner_id and result=BLOCKED • Skip filter for /internal/v1/** paths (check request path prefix) | services/gateway/src/main/java/com/gme/pay/gateway/filter/IpAllowlistGatewayFilter.java | • Partner with CIDR 10.0.0.0/24 and request from 10.0.0.50: HTTP 200 forwarded downstream • Partner with CIDR 10.0.0.0/24 and request from 192.168.1.1: HTTP 403 body contains errorCode=IP_NOT_ALLOWLISTED • Partner with no active CIDRs: any source IP proceeds • X-Forwarded-For: 192.168.1.1, 10.0.0.5 uses 192.168.1.1 (first hop is client) • Path /internal/v1/partners/1/ip-allowlist bypasses this filter regardless of IP • Testcontainers Redis + PostgreSQL + WireMock stub downstream | 45 | 8.8-T03, 8.8-T04 | BE | API-05, SEC-09
8.8-T06 | api-gateway | 8.8 | 8. Partner (Northbound) API | Rate limiting & IP allowlist | 1 | Unit tests: IpAllowlistGatewayFilter CIDR boundary, IPv6, X-Forwarded-For spoofing edge cases | IpAllowlistGatewayFilter (8.8-T05) must correctly handle IPv6 CIDRs, /32 single-host CIDRs, malformed CIDR entries in DB, and multi-hop X-Forwarded-For headers. These are unit tests with mocked PartnerConfigCache and PartnerIdExtractor; no Testcontainers needed. Module: services/gateway. | • Create services/gateway/src/test/java/com/gme/pay/gateway/filter/IpAllowlistGatewayFilterTest.java • Mock PartnerConfigCache and PartnerIdExtractor with Mockito; use MockServerWebExchange for request construction • Test: IPv6 CIDR 2001:db8::/32 matches 2001:db8::1 and rejects 2001:db9::1 • Test: /32 CIDR 10.0.0.1/32 matches 10.0.0.1 and rejects 10.0.0.2 • Test: X-Forwarded-For with 3 hops - uses first IP as client • Test: malformed CIDR string not-a-cidr in allowlist is skipped without exception; request allowed; WARN logged (verify with test Logback appender) • Test: empty CIDR list allows all IPs • Test: /internal/v1/foo path skips filter even for blocked IP | services/gateway/src/test/java/com/gme/pay/gateway/filter/IpAllowlistGatewayFilterTest.java | • IPv6 boundary 2001:db8:ffff:ffff:ffff:ffff:ffff:ffff matches 2001:db8::/32 • Single /32: only exact IP matches, +1 address rejected • Malformed CIDR: no exception thrown, WARN logged, request proceeds • All 8 test cases pass in under 5 seconds (pure unit, no network) | 30 | 8.8-T05 | BE | API-05, SEC-09
8.8-T07 | api-gateway | 8.8 | 8. Partner (Northbound) API | Rate limiting & IP allowlist | 1 | Implement PartnerRateLimitKeyResolver: per-partner Redis bucket key for Spring Cloud Gateway RequestRateLimiter | Spring Cloud Gateway RequestRateLimiterGatewayFilterFactory needs a KeyResolver to assign requests to rate-limit buckets. GMEPay+ buckets per partner: key = partner:{partnerId} for authenticated requests, ip:{sourceIp} for unauthenticated (fallback). Uses PartnerIdExtractor (8.8-T04). Bean is annotated @Primary to override the default PrincipalNameKeyResolver. Module: services/gateway. | • Create services/gateway/src/main/java/com/gme/pay/gateway/ratelimit/PartnerRateLimitKeyResolver.java implementing KeyResolver from Spring Cloud Gateway • Implement resolve(ServerWebExchange exchange): call PartnerIdExtractor.resolve; if partner present return Mono.just(partner: + partnerId); else extract source IP same logic as IpAllowlistFilter and return Mono.just(ip: + sourceIp) • Ensure Mono is never empty (Mono.just always returned) • Register as @Bean @Primary in GatewayRateLimitConfig @Configuration in same package | services/gateway/src/main/java/com/gme/pay/gateway/ratelimit/PartnerRateLimitKeyResolver.java and GatewayRateLimitConfig.java | • Request with valid X-Api-Key for partner_id=42 resolves to key partner:42 • Request with no X-Api-Key resolves to ip:<source-ip> • Mono is never empty (key is always produced) • @SpringBootTest context loads with exactly one @Primary KeyResolver bean • Unit test with mocked PartnerIdExtractor covers both branches | 25 | 8.8-T04 | BE | API-05, SEC-09
8.8-T08 | api-gateway | 8.8 | 8. Partner (Northbound) API | Rate limiting & IP allowlist | 1 | Implement DynamicRedisRateLimiter: per-partner, per-endpoint token bucket backed by Redis | Spring Cloud Gateway RedisRateLimiter uses token bucket algorithm. GMEPay+ needs dynamic per-partner limits: replenish-rate and burst-capacity (=2x replenish-rate) are loaded from PartnerRateLimitConfig via PartnerConfigCache. Endpoint config key (rates/payments/global) selects the right field. Defaults when no DB row: globalRps=100, ratesRps=20, paymentsRps=50, cpmRps=50. Responses must include X-RateLimit-Limit, X-RateLimit-Remaining, X-RateLimit-Reset headers. HTTP 429 response body: {errorCode: RATE_LIMITED, message: Request exceeds rate limit} with Retry-After header. Module: services/gateway. | • Create services/gateway/src/main/java/com/gme/pay/gateway/ratelimit/DynamicRedisRateLimiter.java extending RedisRateLimiter (spring-cloud-starter-gateway includes this) • Override isAllowed(String routeId, String id): extract partnerId from id (strip partner: prefix); load PartnerRateLimitConfig from PartnerConfigCache; derive replenishRate and burstCapacity based on routeId suffix (rates->ratesRps, payments->paymentsRps, default->globalRps); call super or delegate to Redis Lua script with computed values • Register as @Bean in GatewayRateLimitConfig; configure includeHeaders=true so rate-limit headers are always included • Add a custom GatewayFilter in GatewayRateLimitConfig that sets response status 429 with JSON body {errorCode: RATE_LIMITED, message: Request exceeds rate limit} and Retry-After: {X-RateLimit-Reset value} when downstream sets 429 • Fallback to defaults (100/20/50/50) if PartnerConfigCache throws; log WARN | services/gateway/src/main/java/com/gme/pay/gateway/ratelimit/DynamicRedisRateLimiter.java | • Partner with default config: replenishRate=100 for global route, 20 for rates route, 50 for payments route • Custom partner_rate_limit_config.global_rps=200: replenishRate=200 returned for global route • burstCapacity always equals 2 x replenishRate • Response headers X-RateLimit-Limit, X-RateLimit-Remaining, X-RateLimit-Reset present on every response • 429 response body contains errorCode=RATE_LIMITED and Retry-After header | 45 | 8.8-T07, 8.8-T03 | BE | API-05, SEC-09
8.8-T09 | api-gateway | 8.8 | 8. Partner (Northbound) API | Rate limiting & IP allowlist | 1 | Implement AuthFailureTrackingFilter: IP-level block after 20 failed auth attempts in 10 minutes | SEC-09 sec 5.4: failed authentication attempts per IP are limited to 20 per 10-minute window; on breach, the source IP is blocked for 15 minutes returning HTTP 429. Tracked in Redis keys authfail:ip:{ip} (counter, TTL 600s) and authblock:ip:{ip} (block flag, TTL 900s). The filter listens for AuthFailureEvent published by the HMAC validation filter. Module: services/gateway. | • Create services/gateway/src/main/java/com/gme/pay/gateway/event/AuthFailureEvent.java as a Spring ApplicationEvent with field sourceIp String • Create services/gateway/src/main/java/com/gme/pay/gateway/filter/AuthFailureTrackingFilter.java implementing GlobalFilter and Ordered; order = HIGHEST_PRECEDENCE + 5 (before auth filter, so block check runs first) • At start of filter: extract source IP; check Redis key authblock:ip:{ip}; if exists return HTTP 429 immediately with body {errorCode: RATE_LIMITED, message: IP temporarily blocked due to repeated authentication failures} and Retry-After = Redis TTL of block key • Proceed with chain; register an ApplicationEventListener<AuthFailureEvent>: on receive, increment INCR authfail:ip:{ip}; if not exists set EXPIRE 600; if count reaches 20 SET authblock:ip:{ip} 1 EX 900 and DEL authfail:ip:{ip} • The HMAC validation filter (out of scope for this ticket) publishes AuthFailureEvent(sourceIp) on invalid signature or unknown api_key | services/gateway/src/main/java/com/gme/pay/gateway/filter/AuthFailureTrackingFilter.java and AuthFailureEvent.java | • 20 failed auth events from IP 192.0.2.1 within 10 min: 21st request returns 429 even with valid API key • After 15 min (simulate by deleting authblock key in test): requests allowed again • Successful auth does not increment the counter • Two different IPs have independent counters • Testcontainers Redis 7 integration test; counter incremented via direct event publish in test | 40 | 8.8-T04 | BE | API-05, SEC-09
8.8-T10 | api-gateway | 8.8 | 8. Partner (Northbound) API | Rate limiting & IP allowlist | 1 | Flyway migration: gateway_config_outbox table for audit event transactional outbox | Config changes (IP allowlist add/remove, rate-limit override change) must be audit-logged atomically with the DB mutation using the transactional Outbox pattern. The outbox table is in the services/gateway PostgreSQL schema. Per GMEPay+ messaging approach, Phase 1 uses outbox + EventPublisher interface; Kafka is wired in the integration phase behind the same interface. Payload is JSONB containing actor, changed_at, entity_type, partner_id, previous_value, new_value. | • Create services/gateway/src/main/resources/db/migration/V8003__gateway_outbox.sql with gateway_config_outbox(id BIGINT GENERATED ALWAYS AS IDENTITY PK, aggregate_type VARCHAR(50) NOT NULL, aggregate_id VARCHAR(100) NOT NULL, event_type VARCHAR(100) NOT NULL, payload JSONB NOT NULL, status VARCHAR(20) NOT NULL DEFAULT PENDING, created_at TIMESTAMPTZ NOT NULL DEFAULT now(), processed_at TIMESTAMPTZ) • Add CHECK(status IN (PENDING, PROCESSED, FAILED)) • Add partial index idx_outbox_pending ON gateway_config_outbox(created_at ASC) WHERE status=PENDING • Document JSONB payload schema in a SQL comment: {actor: string, changed_at: ISO8601, entity_type: IP_ALLOWLIST¦RATE_LIMIT, partner_id: long, previous_value: object, new_value: object} | services/gateway/src/main/resources/db/migration/V8003__gateway_outbox.sql | • Migration creates table with correct columns, CHECK on status, and PENDING default • Partial index on status=PENDING is created • JSONB payload column accepts and returns structured JSON • flyway migrate sequence V8001 -> V8002 -> V8003 completes cleanly on Testcontainers PostgreSQL 16 • CHECK rejects status value INVALID | 20 | 8.8-T01 | BE | API-05, SEC-09
8.8-T11 | api-gateway | 8.8 | 8. Partner (Northbound) API | Rate limiting & IP allowlist | 1 | Implement GatewayConfigAuditService: atomic DB + outbox write for IP allowlist and rate-limit changes | When Ops adds/removes a CIDR or updates a rate-limit override, the mutation and outbox event must be written in a single ACID transaction (@Transactional). After commit, PartnerConfigCache.evict(partnerId) ensures allowlist changes propagate within 5 minutes (API-05 sec 3.3). CIDR limit: max 10 active entries per partner (API-05 sec 3.3). Module: services/gateway. | • Create services/gateway/src/main/java/com/gme/pay/gateway/config/GatewayConfigAuditService.java as @Service with @Transactional • Implement addIpCidr(Long partnerId, String cidr, String actor): validate CIDR format (reject malformed); count active CIDRs for partner; if >=10 throw GatewayConfigException(CIDR_LIMIT_EXCEEDED) before any write; save IpAllowlistEntry; write outbox row with event_type=IP_ALLOWLIST_ADDED, payload containing actor, previous_value=existing list, new_value=list after add; call PartnerConfigCache.evict(partnerId) • Implement removeIpCidr(Long partnerId, Long entryId, String actor): load entry; set isActive=FALSE; write outbox row event_type=IP_ALLOWLIST_REMOVED; evict cache • Implement upsertRateLimitConfig(Long partnerId, PartnerRateLimitConfigDto dto, String actor): validate all rps fields in range 1-10000; upsert row; write outbox row event_type=RATE_LIMIT_UPDATED with previous and new values; evict cache • Create GatewayConfigException with an errorCode String field (CIDR_LIMIT_EXCEEDED, INVALID_CIDR, etc.) | services/gateway/src/main/java/com/gme/pay/gateway/config/GatewayConfigAuditService.java and GatewayConfigException.java | • addIpCidr success: IpAllowlistEntry row present and outbox row present with correct event_type and payload in same transaction • Rollback test: mock OutboxRepository to throw after IpAllowlistEntry save; assert neither row committed (count unchanged) • 11th CIDR attempt throws CIDR_LIMIT_EXCEEDED and zero DB rows written • Outbox payload JSON contains actor, entity_type, partner_id, previous_value and new_value fields • Testcontainers PostgreSQL 16 + mocked ReactiveRedisTemplate for evict | 40 | 8.8-T10, 8.8-T03 | BE | API-05, SEC-09
8.8-T12 | api-gateway | 8.8 | 8. Partner (Northbound) API | Rate limiting & IP allowlist | 1 | Implement GatewayAdminController: REST admin endpoints for IP allowlist and rate-limit management | GME Ops manages IP allowlists and rate-limit overrides via an internal REST API. Endpoints: POST/GET/DELETE /internal/v1/partners/{partnerId}/ip-allowlist and GET/PUT /internal/v1/partners/{partnerId}/rate-limits. These are on a separate internal route not exposed through the public partner gateway. OAuth2/JWT + RBAC role GATEWAY_ADMIN required. Module: services/gateway. Uses GatewayConfigAuditService (8.8-T11). | • Create services/gateway/src/main/java/com/gme/pay/gateway/admin/GatewayAdminController.java as @RestController @RequestMapping(/internal/v1/partners) • POST /{partnerId}/ip-allowlist body {cidr, description}: call addIpCidr; return 201 with IpAllowlistEntryDto; catch CIDR_LIMIT_EXCEEDED -> 422; catch INVALID_CIDR -> 400 • GET /{partnerId}/ip-allowlist: return active CIDRs as List<IpAllowlistEntryDto> • DELETE /{partnerId}/ip-allowlist/{entryId}: call removeIpCidr; return 204; 404 if entry not found or not owned by partnerId • GET /{partnerId}/rate-limits: return current config (or defaults if no row) • PUT /{partnerId}/rate-limits body PartnerRateLimitConfigDto {globalRps, ratesRps, paymentsRps, cpmRps, globalRpm, quoteRpm}: validate 1-10000; call upsertRateLimitConfig; return 200 • Secure all endpoints with @PreAuthorize(hasRole(GATEWAY_ADMIN)); add Spring Security OAuth2 resource server config | services/gateway/src/main/java/com/gme/pay/gateway/admin/GatewayAdminController.java | • POST valid CIDR returns 201; GET lists it; DELETE sets inactive and GET no longer includes it • POST 11th CIDR returns 422 with errorCode CIDR_LIMIT_EXCEEDED • PUT with globalRps=0 returns 400 (Bean Validation @Min(1)) • Request without GATEWAY_ADMIN JWT role returns 403 • @WebMvcTest or @WebFluxTest slice with MockMvc covers all five endpoints | 40 | 8.8-T11 | BE | API-05, SEC-09
8.8-T13 | api-gateway | 8.8 | 8. Partner (Northbound) API | Rate limiting & IP allowlist | 1 | Spring Cloud Gateway route configuration: wire all filters to partner and internal routes in application.yml | The gateway application.yml must declare routes attaching: IpAllowlistGatewayFilter (GlobalFilter auto-applied), RequestRateLimiter with DynamicRedisRateLimiter and PartnerRateLimitKeyResolver per route, and AuthFailureTrackingFilter (GlobalFilter auto-applied). Three partner routes (rates, payments, global) each use the appropriate rate-limit config key. Internal /internal/v1/** route bypasses partner rate limiting and IP allowlist. Module: services/gateway. | • Edit services/gateway/src/main/resources/application.yml: add spring.cloud.gateway.routes section • Route id=partner-rates: predicates Path=/v1/rates/**, filters RequestRateLimiter with key-resolver=#{@partnerRateLimitKeyResolver}, rate-limiter=#{@dynamicRedisRateLimiter}, with metadata endpoint-key=rates • Route id=partner-payments: predicates Path=/v1/payments/**, filters RequestRateLimiter with endpoint-key=payments • Route id=partner-global: predicates not(Path=/v1/rates/**) and not(Path=/v1/payments/**) under /v1/**, filters RequestRateLimiter with endpoint-key=global • Route id=internal-admin: predicates Path=/internal/v1/**, no RequestRateLimiter filter; add RemoteAddr predicate to restrict to cluster-internal IP range (e.g. 10.0.0.0/8) configurable via ${gateway.internal.allowed-cidr} • Confirm IpAllowlistGatewayFilter and AuthFailureTrackingFilter are GlobalFilters and therefore auto-applied to all routes; add a condition to skip both for /internal/v1/** paths | services/gateway/src/main/resources/application.yml (gateway.routes section) | • POST /v1/rates routes through partner-rates route and applies rates rate-limit bucket • POST /v1/payments routes through partner-payments route and applies payments bucket • POST /internal/v1/partners/1/ip-allowlist is not subject to partner rate-limit filter • /actuator/gateway/routes actuator shows all four routes defined • Integration test with WebTestClient confirms filter application order: IP check -> auth-failure block -> rate limit -> routing | 35 | 8.8-T05, 8.8-T08, 8.8-T09, 8.8-T12 | BE | API-05, SEC-09
8.8-T14 | api-gateway | 8.8 | 8. Partner (Northbound) API | Rate limiting & IP allowlist | 1 | Implement GatewayOutboxPoller: poll gateway_config_outbox and publish events via EventPublisher | The transactional Outbox table gateway_config_outbox (8.8-T10) must be polled every 5 seconds. Each PENDING row is dispatched via the EventPublisher interface from lib-events (Phase 1 = in-process; Kafka wired in integration phase). On success the row is marked PROCESSED. Uses SELECT ... FOR UPDATE SKIP LOCKED to support multiple gateway instances. Module: services/gateway. | • Create services/gateway/src/main/java/com/gme/pay/gateway/outbox/GatewayOutboxPoller.java as @Component with @Scheduled(fixedDelayString=#{gateway.outbox.poll-interval-ms:5000}) • Query via JPQL or native SQL: SELECT * FROM gateway_config_outbox WHERE status=PENDING ORDER BY created_at LIMIT 100 FOR UPDATE SKIP LOCKED; use @Lock(PESSIMISTIC_WRITE) or native query • For each row: deserialize payload JSON to GatewayConfigChangedEvent; call EventPublisher.publish(event); on success update status=PROCESSED, processed_at=now(); on exception update status=FAILED (or leave PENDING depending on retry policy - use PENDING for retry) • Create lib-events/src/main/java/com/gme/pay/events/gateway/GatewayConfigChangedEvent.java as a record with fields: eventId, entityType, partnerId, actor, changedAt, previousValue (Map), newValue (Map) • Add @ConditionalOnProperty(name=gateway.outbox.enabled, havingValue=true, matchIfMissing=true) to allow disabling in unit tests | services/gateway/src/main/java/com/gme/pay/gateway/outbox/GatewayOutboxPoller.java and lib-events/src/main/java/com/gme/pay/events/gateway/GatewayConfigChangedEvent.java | • PENDING row is processed and marked PROCESSED within 10 seconds of insert • Two concurrent poller instances do not double-process the same row (FOR UPDATE SKIP LOCKED test with two threads and Testcontainers PostgreSQL) • Exception during publish leaves row as PENDING for retry • EventPublisher.publish receives GatewayConfigChangedEvent with correct entityType and partnerId • @Scheduled not triggered when gateway.outbox.enabled=false | 35 | 8.8-T10 | BE | API-05, SEC-09
8.8-T15 | api-gateway | 8.8 | 8. Partner (Northbound) API | Rate limiting & IP allowlist | 1 | Integration test: end-to-end IP allowlist enforcement (Testcontainers PostgreSQL + Redis + WireMock) | Full integration test for the IP allowlist path in services/gateway: partner CIDR written to PostgreSQL, cached in Redis, enforced by IpAllowlistGatewayFilter. WireMock stubs the downstream payment service. Tests the add-CIDR admin flow and the 5-minute propagation guarantee via explicit cache evict. | • Create services/gateway/src/test/java/com/gme/pay/gateway/integration/IpAllowlistIntegrationTest.java with @SpringBootTest(webEnvironment=RANDOM_PORT) and @Testcontainers • Provision PostgreSQL 16 and Redis 7 via Testcontainers; run all Flyway migrations • Use @Sql to insert partner row and one IP allowlist entry CIDR 192.168.1.0/24 • Start WireMock server; stub POST /v1/rates -> 200 OK; set downstream URI in application properties • Test 1: POST /v1/rates with X-Forwarded-For: 192.168.1.50 and valid X-Api-Key -> assert 200 • Test 2: same request with X-Forwarded-For: 10.0.0.1 -> assert 403 body errorCode=IP_NOT_ALLOWLISTED • Test 3: call admin endpoint POST /internal/v1/partners/{id}/ip-allowlist with cidr=10.0.0.0/24; then retry 10.0.0.1 request -> assert 200 (cache evicted by admin call) • Test 4: partner with no CIDR entries: any IP passes | services/gateway/src/test/java/com/gme/pay/gateway/integration/IpAllowlistIntegrationTest.java | • IP in CIDR: 200 forwarded to WireMock • IP not in CIDR: 403 with errorCode=IP_NOT_ALLOWLISTED • After admin add of new CIDR, previously blocked IP passes (cache evict verified) • No-CIDR partner: all IPs pass • Test suite completes in under 90 seconds | 45 | 8.8-T13, 8.8-T12 | BE | API-05, SEC-09
8.8-T16 | api-gateway | 8.8 | 8. Partner (Northbound) API | Rate limiting & IP allowlist | 1 | Integration test: end-to-end rate limiting (Testcontainers Redis + PostgreSQL), verifying 429 and headers | Full integration test for rate-limiting in services/gateway: token buckets in Redis, endpoint-specific limits, correct response headers, and per-partner custom overrides. Tests default limits (ratesRps=20) and a custom partner_rate_limit_config. | • Create services/gateway/src/test/java/com/gme/pay/gateway/integration/RateLimitIntegrationTest.java with @SpringBootTest and Testcontainers Redis 7 + PostgreSQL 16 • Insert partner A with no partner_rate_limit_config (defaults apply: globalRps=100, ratesRps=20) • Send 21 rapid POST /v1/rates requests for partner A; assert 21st returns 429 with Retry-After header and body {errorCode: RATE_LIMITED} • Assert first 20 responses include X-RateLimit-Limit=20, X-RateLimit-Remaining (decrementing from 19 to 0), X-RateLimit-Reset (epoch second in future) • Insert partner_rate_limit_config for partner B with ratesRps=5; send 6 requests; assert 6th is 429 • Verify partner A and partner B rate buckets are independent (partner A exhausting its rate does not affect partner B) | services/gateway/src/test/java/com/gme/pay/gateway/integration/RateLimitIntegrationTest.java | • Default ratesRps=20: 21st /v1/rates request is 429 • X-RateLimit-Remaining decrements from 19 to 0 across 20 requests • Custom ratesRps=5 partner: 6th request is 429 • Partner A and B buckets independent • Retry-After is a valid epoch second greater than current time | 45 | 8.8-T13 | BE | API-05, SEC-09
8.8-T17 | api-gateway | 8.8 | 8. Partner (Northbound) API | Rate limiting & IP allowlist | 1 | Unit tests: GatewayConfigAuditService rollback, CIDR limit, and outbox payload correctness | GatewayConfigAuditService (8.8-T11) has critical transactional and business-rule invariants. These are tested with @DataJpaTest (Testcontainers PostgreSQL) for DB-level assertions and Mockito for PartnerConfigCache. Focus: atomic rollback on outbox failure, CIDR limit at exactly 10, and outbox payload JSON completeness. | • Create services/gateway/src/test/java/com/gme/pay/gateway/config/GatewayConfigAuditServiceTest.java with @SpringBootTest and Testcontainers PostgreSQL 16 • Test addIpCidr success: verify IpAllowlistEntry row saved, outbox row saved with event_type=IP_ALLOWLIST_ADDED and payload containing actor, partner_id, previous_value, new_value • Test rollback: replace OutboxRepository bean with a mock that throws after IpAllowlistEntry save; call addIpCidr; assert IpAllowlistEntry count unchanged and outbox count unchanged • Test CIDR limit: insert 10 active CIDRs; call addIpCidr for 11th; assert GatewayConfigException thrown with errorCode CIDR_LIMIT_EXCEEDED; assert count still 10 • Test removeIpCidr: entry is_active set to FALSE; outbox row event_type=IP_ALLOWLIST_REMOVED • Test upsertRateLimitConfig: second call updates existing row (not insert), outbox event written with previous and new values | services/gateway/src/test/java/com/gme/pay/gateway/config/GatewayConfigAuditServiceTest.java | • Rollback test: zero new rows in both partner_ip_allowlist and gateway_config_outbox after mock throws • 11th CIDR: count stays 10, exception carries errorCode=CIDR_LIMIT_EXCEEDED • Outbox payload JSON deserializes to GatewayConfigChangedEvent with all required fields non-null • Upsert: partner_rate_limit_config row count stays 1 after two consecutive upserts • Test suite completes in under 60 seconds | 35 | 8.8-T11 | BE | API-05, SEC-09
8.8-T18 | api-gateway | 8.8 | 8. Partner (Northbound) API | Rate limiting & IP allowlist | 1 | Unit tests: DynamicRedisRateLimiter endpoint-key routing and default fallback | DynamicRedisRateLimiter (8.8-T08) must select the correct rate-limit field based on endpoint-key (rates->ratesRps, payments->paymentsRps, global->globalRps) and return 2x as burst-capacity. When PartnerConfigCache throws, defaults must be returned without propagating the exception. Pure unit test with mocked PartnerConfigCache. | • Create services/gateway/src/test/java/com/gme/pay/gateway/ratelimit/DynamicRedisRateLimiterTest.java • Mock PartnerConfigCache to return config with globalRps=200, ratesRps=30, paymentsRps=80 • Test endpoint-key=rates: replenishRate=30, burstCapacity=60 • Test endpoint-key=payments: replenishRate=80, burstCapacity=160 • Test endpoint-key=global (or unknown key): replenishRate=200, burstCapacity=400 • Test no DB row (default config): replenishRate=100, burstCapacity=200 • Test PartnerConfigCache throws RuntimeException: replenishRate=100, burstCapacity=200 (default fallback, no exception propagated) • Test burst is always exactly 2x replenishRate for a custom config | services/gateway/src/test/java/com/gme/pay/gateway/ratelimit/DynamicRedisRateLimiterTest.java | • rates key uses ratesRps=30 not globalRps=200 • burstCapacity=2x replenishRate in all 7 scenarios • RuntimeException in cache lookup: defaults returned, no exception thrown • All tests complete in under 3 seconds (pure unit, no containers) | 25 | 8.8-T08 | BE | API-05, SEC-09
8.8-T19 | api-gateway | 8.8 | 8. Partner (Northbound) API | Rate limiting & IP allowlist | 1 | Unit tests: AuthFailureTrackingFilter counter increment, block activation, and IP isolation | AuthFailureTrackingFilter (8.8-T09) counter and block logic must be correct. Test: counter increments on each AuthFailureEvent; at count=20 block is activated; different IPs are isolated; successful auth does not increment. Uses Testcontainers Redis 7 for counter/block key assertions. | • Create services/gateway/src/test/java/com/gme/pay/gateway/filter/AuthFailureTrackingFilterTest.java with Testcontainers Redis 7 • Inject ApplicationEventPublisher and publish AuthFailureEvent(192.0.2.1) 19 times; assert Redis key authblock:ip:192.0.2.1 absent • Publish 20th event; assert authblock:ip:192.0.2.1 exists with TTL between 895 and 905 seconds; assert authfail counter key deleted • Test next request from 192.0.2.1 returns 429 immediately (simulate via MockServerWebExchange through filter) • Test 20 events from 192.0.2.2 do not affect 192.0.2.1 bucket • Test: after block key expires (delete it manually in test), request from 192.0.2.1 is allowed • Test: event is not published on successful auth (counter key for that IP stays absent) | services/gateway/src/test/java/com/gme/pay/gateway/filter/AuthFailureTrackingFilterTest.java | • 19 failures: no block key in Redis • 20th failure: authblock key present, TTL ~900s, counter key deleted • Blocked IP returns 429 from filter before reaching downstream • Two IPs have independent counters • Test suite completes in under 30 seconds | 30 | 8.8-T09 | BE | API-05, SEC-09
8.8-T20 | api-gateway | 8.8 | 8. Partner (Northbound) API | Rate limiting & IP allowlist | 1 | OpenAPI documentation: gateway-admin.yaml for IP allowlist and rate-limit management endpoints | The internal admin endpoints (8.8-T12) must be documented in openapi/gateway-admin.yaml following the same conventions as openapi/partner-api.yaml. This enables the Ops/Admin BFF (React/Next.js frontend) to generate typed API clients. Error responses use the canonical error model from lib-errors (errorCode + message fields). | • Create openapi/gateway-admin.yaml with openapi: 3.1.0, info (title: GMEPay+ Gateway Admin API, version: 1.0.0), servers (url: /internal/v1), security scheme OAuth2 Bearer • Add path POST /partners/{partnerId}/ip-allowlist: request body schema {cidr: string, description: string}, responses 201 (IpAllowlistEntryDto), 400 (invalid CIDR), 409 (duplicate), 422 (CIDR_LIMIT_EXCEEDED) • Add path GET /partners/{partnerId}/ip-allowlist: response 200 array of IpAllowlistEntryDto (id, partnerId, cidrRange, isActive, createdAt, createdBy) • Add path DELETE /partners/{partnerId}/ip-allowlist/{entryId}: response 204, 404 • Add path GET /partners/{partnerId}/rate-limits: response 200 PartnerRateLimitConfigDto • Add path PUT /partners/{partnerId}/rate-limits: request body PartnerRateLimitConfigDto {globalRps: int min 1 max 10000, ratesRps, paymentsRps, cpmRps, globalRpm, quoteRpm}, response 200 • Define reusable ErrorResponse component schema with fields errorCode (string) and message (string) from lib-errors canonical model | openapi/gateway-admin.yaml | • YAML validates with swagger-parser or redocly lint with zero errors • All six endpoints documented with correct HTTP methods and paths • PartnerRateLimitConfigDto fields show minimum=1 and maximum=10000 constraints • IpAllowlistEntryDto schema matches Java entity fields exactly • ErrorResponse schema referenced in all 4xx response definitions | 30 | 8.8-T12 | BE | API-05, SEC-09
8.8-T21 | api-gateway | 8.8 | 8. Partner (Northbound) API | Rate limiting & IP allowlist | 1 | Observability: Micrometer metrics and MDC structured logging in gateway filters | GMEPay+ observability stack: OpenTelemetry -> Prometheus + Grafana (metrics), ELK (logs). Gateway filters must emit Micrometer counters and timers to Prometheus and include MDC correlation fields (partner_id, request_id) in all log entries. Metric names: ip_allowlist_blocked_total (tag: partner_id), rate_limit_exceeded_total (tags: partner_id, endpoint), auth_failure_blocked_total (tag: source_ip), ip_allowlist_check_duration_seconds (timer), rate_limit_check_duration_seconds (timer). Module: services/gateway. | • Inject MeterRegistry into IpAllowlistGatewayFilter: increment Counter ip_allowlist_blocked_total with tag partner_id on each 403 block; wrap CIDR match loop in Timer.Sample for ip_allowlist_check_duration_seconds • Inject MeterRegistry into DynamicRedisRateLimiter or the 429 response filter: increment Counter rate_limit_exceeded_total with tags partner_id and endpoint on each 429 • Inject MeterRegistry into AuthFailureTrackingFilter: increment auth_failure_blocked_total with tag source_ip on each IP block trigger (when count reaches 20) • In a GatewayFilter registered at HIGHEST_PRECEDENCE: set MDC partner_id (from X-Api-Key resolution), request_id (from X-Request-ID header or generate UUID); clear MDC in doFinally • Verify /actuator/prometheus endpoint exposes all five metric names | Updated IpAllowlistGatewayFilter.java, DynamicRedisRateLimiter.java, and AuthFailureTrackingFilter.java with Micrometer instrumentation; MDC filter in services/gateway/src/main/java/com/gme/pay/gateway/filter/MdcPopulatingFilter.java | • One blocked IP-allowlist request: ip_allowlist_blocked_total{partner_id=42} = 1 at /actuator/prometheus • One rate-limited request to /v1/rates: rate_limit_exceeded_total{partner_id=42,endpoint=/v1/rates} = 1 • Timer histogram buckets for ip_allowlist_check_duration_seconds present in Prometheus output • Log entry for a blocked request contains JSON fields partner_id and request_id (test with Logback ListAppender) • MDC cleared after each request: subsequent test request with different partner_id shows correct partner_id in logs | 35 | 8.8-T05, 8.8-T08, 8.8-T09 | BE | API-05, SEC-09
8.9-T01 | api-gateway | 8.9 | 8. Partner (Northbound) API | OpenAPI finalization & sandbox | 1 | Scaffold openapi/partner-api.yaml skeleton with all 7 v1 endpoints | WBS 8.9: OpenAPI finalisation and sandbox. The Partner API (API-05) exposes 7 endpoints under /v1: POST /v1/rates, POST /v1/payments, POST /v1/payments/cpm/generate, GET /v1/payments/{id}, POST /v1/payments/{id}/cancel, GET /v1/merchants/{qr}, GET /v1/balance. The YAML lives at openapi/partner-api.yaml in the monorepo root. It must declare info (title: GMEPay+ Partner API, version: 1.0.0), servers (https://api-sandbox.gmepayplus.com, https://api.gmepayplus.com), and stub path entries (no request/response schemas yet) for all 7 endpoints. | • Create openapi/partner-api.yaml at monorepo root with openapi: 3.1.0 header • Add info block: title, version 1.0.0, description referencing API-05 • Add servers block with sandbox and production base URLs • Add paths block with stub entries for all 7 endpoints (method + operationId only) • Validate YAML is well-formed with a linter (e.g. gradle openApiValidate task or redocly lint) | openapi/partner-api.yaml - valid OpenAPI 3.1 skeleton with 7 path stubs | • File parses without errors under openapi-generator or redocly lint • All 7 operationIds present: getRateQuote, executeFixedMpmPayment, generateCpmToken, getPaymentStatus, cancelPayment, resolveMerchantQr, getPrefundBalance • servers block contains both https://api-sandbox.gmepayplus.com and https://api.gmepayplus.com • info.version = 1.0.0 | 25 |  | BE | API-05
8.9-T02 | api-gateway | 8.9 | 8. Partner (Northbound) API | OpenAPI finalization & sandbox | 1 | Define shared components: Money, ErrorEnvelope, ErrorDetail, pagination Meta schemas | API-05 §2.5 and §8.1. Money is two fields: amount (string decimal) and currency (ISO-4217). Error envelope: {error:{code,message,request_id,details:[{field,issue}]}}. Pagination meta: {total_count,has_more,next_cursor,prev_cursor}. All defined as reusable schemas under components/schemas in openapi/partner-api.yaml. Also add reusable header components: IdempotencyKey (required, UUID 16-128 chars), X-Timestamp (ISO-8601 UTC ms), X-Signature (HMAC-SHA256 64-char hex), X-Request-ID (response header). | • Open openapi/partner-api.yaml • Add components/schemas: MoneyAmount (amount string decimal pattern, currency 3-char string) • Add ErrorDetail (field, issue), ErrorEnvelope (error object with code, message, request_id, details array) • Add PaginationMeta (total_count integer, has_more boolean, next_cursor nullable, prev_cursor nullable) • Add components/parameters: IdempotencyKey (header, required, minLength 16, maxLength 128), XTimestamp, XSignature • Run linter to verify 0 errors | components/schemas and components/parameters block in openapi/partner-api.yaml with all shared types | • MoneyAmount has required: [amount, currency]; amount pattern allows '50000' and '35.77' • ErrorEnvelope error.details is type array with items ref to ErrorDetail • PaginationMeta has_more is boolean not string • XSignature parameter pattern is ^[0-9a-f]{64}$ • Linter reports 0 errors | 25 | 8.9-T01 | BE | API-05
8.9-T03 | api-gateway | 8.9 | 8. Partner (Northbound) API | OpenAPI finalization & sandbox | 1 | Add request/response schemas for POST /v1/rates in partner-api.yaml | API-05 §4.2. Request fields: target_payout (string, required), payout_currency (string ISO-4217, required), scheme_id (string, required), direction (enum domestic¦inbound¦outbound¦hub, required), merchant_qr (string, optional), partner_ref (string, optional). Response 200: quote_id, offer_rate, send_amount, service_charge, service_charge_currency, collection_usd (nullable, cross-border only), payout_usd_cost (nullable), collection_margin_usd (nullable), payout_margin_usd (nullable), cross_rate (nullable), valid_until (ISO-8601 UTC), scheme_id, direction, partner_ref. USD pool fields omitted for domestic transactions. Also add 400/404/422/429 responses referencing ErrorEnvelope. | • Define RateQuoteRequest schema under components/schemas • Define RateQuoteResponse schema; USD pool fields nullable • Wire into paths./v1/rates.post requestBody and responses • Reference IdempotencyKey and auth headers as parameters • Run linter | POST /v1/rates operation fully typed in openapi/partner-api.yaml | • direction enum has exactly 4 values: domestic, inbound, outbound, hub • valid_until format is date-time • collection_usd marked nullable: true • 400, 404, 422, 429 responses all reference ErrorEnvelope • Example from API-05 §4.2 embedded as examples block (target_payout=50000 KRW inbound to ZeroPay) | 35 | 8.9-T02 | BE | API-05
8.9-T04 | api-gateway | 8.9 | 8. Partner (Northbound) API | OpenAPI finalization & sandbox | 1 | Add request/response schemas for POST /v1/payments in partner-api.yaml | API-05 §4.3. Request: quote_id (required), merchant_qr (required), direction (required), scheme_id (required), customer_ref (required, tokenised no PII), partner_txn_ref (required, unique per partner), collection_amount (string decimal, required), collection_currency (required), country_code (optional ISO-3166-1 alpha-2). Response 201: payment_id, status enum(approved¦pending¦failed), scheme_txn_id, merchant_name, merchant_id, target_payout, payout_currency, offer_rate, collection_amount, collection_currency, service_charge, service_charge_currency, prefund_deducted_usd (nullable OVERSEAS only), partner_txn_ref, created_at, approved_at (nullable). HTTP codes: 201, 202, 400, 402, 404, 409, 422, 429. | • Define FixedMpmPaymentRequest schema • Define FixedMpmPaymentResponse schema with prefund_deducted_usd nullable • Wire into paths./v1/payments.post with Idempotency-Key header parameter • Add all documented HTTP status responses referencing ErrorEnvelope • Run linter | POST /v1/payments operation fully typed in openapi/partner-api.yaml | • partner_txn_ref marked required in request schema • prefund_deducted_usd nullable (LOCAL partners do not receive it) • 202 response documented alongside 201 (async pending case) • 409 response description references DUPLICATE_PARTNER_TXN_REF • 402 response description references INSUFFICIENT_PREFUNDING | 35 | 8.9-T03 | BE | API-05
8.9-T05 | api-gateway | 8.9 | 8. Partner (Northbound) API | OpenAPI finalization & sandbox | 1 | Add schemas for POST /v1/payments/cpm/generate and GET /v1/payments/{id} | API-05 §4.4 and §4.5. CPM generate request: scheme_id, direction, customer_ref, partner_txn_ref (all required), country_code (required for CPM), prefund_reserve_usd (optional). CPM response 201: cpm_token_id, prepare_token, qr_content, expires_at (ISO-8601; token valid 60 s), prefund_reserved_usd (nullable), payment_id, scheme_id, partner_txn_ref, created_at. GET /v1/payments/{id} path param id. Response 200: full payment object with updated_at and cancelled_at (nullable). Status enum extended to: pending, approved, failed, cancelled, uncertain. | • Define CpmGenerateRequest and CpmGenerateResponse schemas • Wire into paths./v1/payments/cpm/generate.post • Define PaymentDetailResponse schema (superset of FixedMpmPaymentResponse with updated_at, cancelled_at, status including uncertain) • Wire into paths./v1/payments/{id}.get with path param id • Add 404 response for GET • Run linter | POST /v1/payments/cpm/generate and GET /v1/payments/{id} operations typed in openapi/partner-api.yaml | • CPM expires_at format date-time with description noting 60 s validity • status enum in PaymentDetailResponse has 5 values: pending, approved, failed, cancelled, uncertain • cancelled_at nullable in PaymentDetailResponse • GET /v1/payments/{id} has no requestBody • prefund_reserved_usd nullable (LOCAL partners get null) | 35 | 8.9-T04 | BE | API-05
8.9-T06 | api-gateway | 8.9 | 8. Partner (Northbound) API | OpenAPI finalization & sandbox | 1 | Add schemas for POST cancel, GET merchant, GET balance endpoints to complete all 7 ops | API-05 §4.6-4.8. Cancel request: reason (enum customer_request¦merchant_request¦timeout¦other, required), reason_detail (string max 200 chars, optional). Cancel response 200: payment_id, status=cancelled, cancelled_at, prefund_returned_usd (nullable). GET /v1/merchants/{qr}: merchant_id, merchant_name, merchant_type, scheme_id, qr_code, status (active¦inactive), payout_currency, address. HTTP 404 MERCHANT_NOT_FOUND, 422 inactive. GET /v1/balance: partner_id, balance_usd, low_balance_threshold_usd, is_below_threshold (boolean), as_of, recent_deductions array (when include_history=true). Deduction item: payment_id, amount_usd, balance_after_usd, event_at. LOCAL partner returns 403. | • Define CancelPaymentRequest and CancelPaymentResponse schemas; wire cancel op • Define MerchantDetailResponse; wire GET /v1/merchants/{qr} • Define PrefundBalanceResponse and BalanceDeductionEvent schemas • Wire GET /v1/balance with optional query param include_history (boolean) • Run linter - must report 0 errors with all 7 paths complete | Three remaining operations in openapi/partner-api.yaml; all 7 endpoints complete and linting clean | • reason enum has exactly 4 values • MerchantDetailResponse status enum: active, inactive • balance 403 response documented with FORBIDDEN error code • include_history query param is boolean and not required • is_below_threshold type is boolean in schema | 35 | 8.9-T05 | BE | API-05
8.9-T07 | api-gateway | 8.9 | 8. Partner (Northbound) API | OpenAPI finalization & sandbox | 1 | Add webhook event schemas to partner-api.yaml (5 event types) | API-05 §6.5. All events share envelope: {event_id, event_type, created_at, partner_id, data:{...}}. Event types: payment.approved (includes offer_rate, target_payout, payout_currency, collection_amount, collection_currency, service_charge, service_charge_currency, prefund_deducted_usd nullable, approved_at, scheme_txn_id, merchant_id, merchant_name, direction, scheme_id, partner_txn_ref, payment_id). payment.pending_debit (CPM only; estimated_collection_amount, cpm_token_id). payment.failed (failure_code, failure_message, prefund_returned_usd nullable, failed_at). payment.cancelled (reason, prefund_returned_usd nullable, cancelled_at). settlement.completed (settlement_id, settlement_date, scheme_id, total_transactions, total_payout_krw, total_prefund_deducted_usd, batch_file_ref, settled_at). Webhook signing headers: X-GME-Webhook-Signature (sha256= prefix), X-GME-Webhook-Timestamp, X-GME-Event-ID. | • Define WebhookEnvelope base schema (event_id, event_type enum 5 values, created_at, partner_id, data) • Define 5 data sub-schemas as named components • Add webhook signing headers to components/headers • Reference webhook schemas from a webhooks block or x-webhooks extension in YAML • Run linter | 5 webhook event schemas in openapi/partner-api.yaml components/schemas; linting clean | • payment.approved data includes prefund_deducted_usd nullable • payment.pending_debit uses estimated_collection_amount not collection_amount • settlement.completed includes batch_file_ref string field • WebhookEnvelope event_type enum has exactly 5 values • Webhook signing headers documented in components/headers with correct format descriptions | 35 | 8.9-T06 | BE | API-05
8.9-T08 | api-gateway | 8.9 | 8. Partner (Northbound) API | OpenAPI finalization & sandbox | 1 | Configure openapi-generator Gradle task to generate Java DTOs into lib-api-contracts | Stack: Gradle multi-module monorepo, Java 21, Spring Boot 3.x. libs/lib-api-contracts is the shared module. Use openapi-generator-gradle-plugin (org.openapi.generator) to generate DTO model classes from openapi/partner-api.yaml. Generator: spring with library=spring-boot. Output package: com.gme.pay.api.contracts.model. Generated sources go to libs/lib-api-contracts/build/generated/openapi/src/main/java. Set generateApiTests=false, generateModelTests=false. Add useJakartaEe=true for Spring Boot 3.x compatibility. The module exposes model classes only; no controller stubs. | • Add openapi-generator-gradle-plugin to libs/lib-api-contracts/build.gradle • Configure openApiGenerate task: generatorName=spring, inputSpec path to openapi/partner-api.yaml, outputDir=build/generated/openapi, modelPackage=com.gme.pay.api.contracts.model, apiPackage=com.gme.pay.api.contracts.api, useJakartaEe=true, generateApiTests=false • Add sourceSets.main.java.srcDir pointing to generated output • Wire compileJava.dependsOn openApiGenerate • Run ./gradlew :libs:lib-api-contracts:openApiGenerate to verify compile | libs/lib-api-contracts/build.gradle with working openapi-generator task; generated DTOs compile under com.gme.pay.api.contracts.model | • ./gradlew :libs:lib-api-contracts:build succeeds without errors • Generated class RateQuoteRequest.java exists under build/generated/openapi • Generated class FixedMpmPaymentRequest.java exists with partner_txn_ref field • Generated class ErrorEnvelope.java exists • No hand-written Java in libs/lib-api-contracts/src/main/java (all from generator) | 40 | 8.9-T07 | BE | API-05
8.9-T09 | api-gateway | 8.9 | 8. Partner (Northbound) API | OpenAPI finalization & sandbox | 1 | Wire lib-api-contracts as dependency into svc-payment-executor and svc-rate-fx | Stack: Gradle multi-module monorepo. Services svc-payment-executor and svc-rate-fx need the generated DTOs from libs/lib-api-contracts to use as @RequestBody and response types in @RestController methods. Add implementation(project(':libs:lib-api-contracts')) to each service's build.gradle. Verify no duplicate spring-web conflict (lib-api-contracts must not transitively pull in a second copy of spring-webmvc). | • Open services/svc-payment-executor/build.gradle; add implementation(project(':libs:lib-api-contracts')) • Open services/svc-rate-fx/build.gradle; add implementation(project(':libs:lib-api-contracts')) • Run ./gradlew :services:svc-payment-executor:compileJava and :services:svc-rate-fx:compileJava • Verify no duplicate spring-webmvc JAR via ./gradlew :services:svc-rate-fx:dependencyInsight --dependency spring-webmvc • Add a stub import of RateQuoteRequest in svc-rate-fx to confirm compile-time resolution | Updated build.gradle for svc-payment-executor and svc-rate-fx; both compile clean | • ./gradlew :services:svc-payment-executor:compileJava exits 0 • ./gradlew :services:svc-rate-fx:compileJava exits 0 • import com.gme.pay.api.contracts.model.RateQuoteRequest resolves in svc-rate-fx • ./gradlew dependencyInsight shows single version of spring-webmvc (no duplicate) • import com.gme.pay.api.contracts.model.ErrorEnvelope resolves in svc-payment-executor | 25 | 8.9-T08 | BE | API-05
8.9-T10 | api-gateway | 8.9 | 8. Partner (Northbound) API | OpenAPI finalization & sandbox | 1 | Implement HMAC request signing filter in svc-payment-executor (Spring Security OncePerRequestFilter) | API-05 §3.2 and §3.6. Every request must carry X-API-Key, X-Timestamp (ISO-8601 UTC ms precision), X-Signature (HMAC-SHA256 hex over canonical string). Canonical string = HTTP_METHOD + LF + PATH_WITH_QUERY + LF + X-Timestamp_value + LF + SHA256_HEX_OF_BODY. Reject if ¦serverTime - X-Timestamp¦ > 300 s with 401 TIMESTAMP_OUT_OF_RANGE. Replay protection: store (partner_id, X-Signature) in Redis key partner:{id}:sig:{hex} with 10-min TTL; reject duplicate with 401 INVALID_SIGNATURE. API secret fetched from Vault via Spring Cloud Vault. File: services/svc-payment-executor/src/main/java/com/gme/pay/executor/security/HmacRequestSigningFilter.java. Secrets hashed at rest with bcrypt cost 12. | • Create HmacRequestSigningFilter extending OncePerRequestFilter; inject PartnerCredentialService, RedisTemplate<String,String>, Clock • Wrap request with ContentCachingRequestWrapper to allow body re-read • Compute canonical string; compute HMAC-SHA256 using javax.crypto.Mac with HmacSHA256 • Check timestamp window (300 s); return 401 ErrorEnvelope TIMESTAMP_OUT_OF_RANGE if outside • Check Redis replay key; reject with 401 INVALID_SIGNATURE if found; store key with 10-min TTL • Register filter in SecurityFilterChain before UsernamePasswordAuthenticationFilter at order -100 | services/svc-payment-executor/src/main/java/com/gme/pay/executor/security/HmacRequestSigningFilter.java | • Valid signature with current timestamp proceeds to controller (no 4xx) • X-Timestamp 301 s old returns 401 with error.code=TIMESTAMP_OUT_OF_RANGE • Replayed request (same signature within 10 min) returns 401 with error.code=INVALID_SIGNATURE • Missing X-API-Key header returns 401 error.code=INVALID_API_KEY before HMAC compute • Unknown X-API-Key returns 401 error.code=INVALID_API_KEY | 55 | 8.9-T09 | BE | API-05
8.9-T11 | api-gateway | 8.9 | 8. Partner (Northbound) API | OpenAPI finalization & sandbox | 1 | Implement Idempotency-Key middleware in svc-payment-executor (Redis-backed 24h TTL) | API-05 §2.6 and §7.1. All POST endpoints require Idempotency-Key header (UUID, 16-128 chars). Store (partner_id, idempotency_key) -> (response_body, response_status, body_hash) in Redis with 24h TTL. Redis key: idempotency:{partnerId}:{idempotencyKey}. Body hash: SHA-256 hex of raw request bytes. Scenarios: missing key -> 400 MISSING_IDEMPOTENCY_KEY; same key + same body + in-flight -> 409 X-Idempotency-Status: in_flight; same key + same body + completed -> replay stored response; same key + different body -> 422 IDEMPOTENCY_KEY_REUSE. GET requests bypass the filter. File: services/svc-payment-executor/src/main/java/com/gme/pay/executor/web/IdempotencyFilter.java. | • Create IdempotencyFilter extending OncePerRequestFilter; inject StringRedisTemplate • Compute Redis key from authenticated partner_id and Idempotency-Key header • On cache miss: set IN_FLIGHT with 24h TTL; call chain; on response commit overwrite with (status, body, body_hash) • On cache hit IN_FLIGHT: return 409 with X-Idempotency-Status: in_flight header • On cache hit COMPLETED: compare SHA-256 of current body vs stored body_hash; mismatch -> 422 IDEMPOTENCY_KEY_REUSE; match -> replay stored response • Skip filter for GET requests (check request.getMethod()) | services/svc-payment-executor/src/main/java/com/gme/pay/executor/web/IdempotencyFilter.java | • POST without Idempotency-Key header returns 400 MISSING_IDEMPOTENCY_KEY • Same key same body completed: second call returns stored response; service layer not invoked again (verified by mock count) • Same key different body returns 422 IDEMPOTENCY_KEY_REUSE • GET request without Idempotency-Key header proceeds without 400 • Redis TTL on stored key is 24 h (86400 s) | 50 | 8.9-T10 | BE | API-05
8.9-T12 | api-gateway | 8.9 | 8. Partner (Northbound) API | OpenAPI finalization & sandbox | 1 | Implement POST /v1/rates @RestController in svc-rate-fx | API-05 §4.2. RateController.java at services/svc-rate-fx/src/main/java/com/gme/pay/ratefx/web/RateController.java accepts RateQuoteRequest (from lib-api-contracts), delegates to RateEngineService.quote(), returns RateQuoteResponse HTTP 200. Validation: target_payout > 0, direction is valid enum value. Scheme existence check via ConfigRegistryClient (OpenFeign) calling internal scheme registry; unknown scheme -> 404 SCHEME_NOT_FOUND. Rate quote TTL per partner config (field rate_quote_ttl_seconds, range 60-1800 s, default 300 s) fetched from Redis config cache. valid_until = Instant.now(clock).plusSeconds(ttl). USD pool fields null in response when direction=domestic (same-currency short-circuit). X-Request-ID response header injected from MDC. | • Create RateController.java @RestController @RequestMapping('/v1/rates') • Inject RateEngineService, ConfigRegistryClient, Clock • Implement postRates(@RequestBody @Valid RateQuoteRequest, HttpServletRequest) returning ResponseEntity<RateQuoteResponse> • Validate target_payout > 0; let @Valid handle direction enum constraint • Resolve scheme; throw SchemeNotFoundException (-> 404) on missing • Compute valid_until = now(clock) + ttl; build response; set X-Request-ID header | services/svc-rate-fx/src/main/java/com/gme/pay/ratefx/web/RateController.java | • POST /v1/rates valid inbound request returns 200 with non-null quote_id and valid_until in the future • target_payout=0 returns 400 VALIDATION_ERROR • Unknown scheme_id returns 404 SCHEME_NOT_FOUND • valid_until = quote_issued_at + rate_quote_ttl_seconds (verified with fixed Clock) • collection_usd field is null in response when direction=domestic | 45 | 8.9-T11 | BE | API-05
8.9-T13 | api-gateway | 8.9 | 8. Partner (Northbound) API | OpenAPI finalization & sandbox | 1 | Implement POST /v1/payments @RestController for Fixed MPM in svc-payment-executor | API-05 §4.3 and §5.1. PaymentController.java at services/svc-payment-executor/src/main/java/com/gme/pay/executor/web/PaymentController.java. Flow: 1) load quote from Redis by quote_id; reject expired quote with 422 RATE_QUOTE_EXPIRED (no prefunding touch); 2) validate direction and scheme_id match quote; 3) for OVERSEAS partner: @Transactional SELECT FOR UPDATE on prefunding_balance table (PostgreSQL, column balance_usd NUMERIC(20,4)); deduct collection_usd; reject with 402 INSUFFICIENT_PREFUNDING if insufficient; 4) write all USD pool values to transaction table (rate lock, field rate_locked_at); 5) call SchemeAdapterClient.commitPayment(); 6) record event trail steps PREFUND_DEDUCTED (step 2) and TRANSACTION_COMMITTED (step 5); return 201 approved or 202 async pending. | • Create PaymentController.java @RestController @RequestMapping('/v1/payments') • Inject QuoteRedisRepository, PrefundingService, PaymentExecutorService, SchemeAdapterClient • Check quote validity from Redis; return 422 RATE_QUOTE_EXPIRED if expired • For OVERSEAS partner call prefundingService.deductAtomic(partnerId, collectionUsd) @Transactional; catch InsufficientFundsException -> 402 • Call schemeAdapterClient.commitPayment(quote, req); map to FixedMpmPaymentResponse • Return 201 on synchronous scheme approval; 202 on async pending | services/svc-payment-executor/src/main/java/com/gme/pay/executor/web/PaymentController.java | • Expired quote_id returns 422 RATE_QUOTE_EXPIRED; prefunding_balance row not touched • OVERSEAS partner with balance 35.00 and required collection_usd 35.77 returns 402 INSUFFICIENT_PREFUNDING; scheme adapter never called • Successful approval returns 201 with payment_id and scheme_txn_id • transaction row has rate_locked_at timestamp set at execution time • LOCAL partner request skips prefunding deduction (no SELECT FOR UPDATE issued) | 55 | 8.9-T12 | BE | API-05
8.9-T14 | api-gateway | 8.9 | 8. Partner (Northbound) API | OpenAPI finalization & sandbox | 1 | Implement POST /v1/payments/cpm/generate @RestController in svc-payment-executor | API-05 §4.4 and §5.2. CpmController.java at services/svc-payment-executor/src/main/java/com/gme/pay/executor/web/CpmController.java. For OVERSEAS partner: deduct prefunding atomically (SELECT FOR UPDATE on prefunding_balance) BEFORE calling scheme. If deduction fails -> 402 INSUFFICIENT_PREFUNDING; scheme never called. prefund amount = prefund_reserve_usd if provided, else scheme max transaction limit from ConfigRegistryClient. Call SchemeAdapterClient.prepareCpm() to get prepare_token and qr_content. expires_at = now + token_ttl_seconds (default 60, configurable). Store cpm_token correlation in Redis key cpm:{cpmTokenId} with same TTL. Record event step 2 (PREFUND_DEDUCTED). country_code is required for CPM. | • Create CpmController.java @RestController • Inject PrefundingService, SchemeAdapterClient, ConfigRegistryClient, CpmRedisRepository • Resolve prefund amount (prefund_reserve_usd or scheme max limit) • For OVERSEAS: call prefundingService.deductAtomic() @Transactional; catch InsufficientFundsException -> 402 • Call schemeAdapterClient.prepareCpm(schemeId, direction, customerRef) • Build CpmGenerateResponse with pre-assigned payment_id, prepare_token, expires_at = now+60s; store in Redis with TTL; return 201 | services/svc-payment-executor/src/main/java/com/gme/pay/executor/web/CpmController.java | • OVERSEAS partner with insufficient balance returns 402; prepareCpm never called (verify via mock) • Response expires_at is exactly 60 s after created_at (fixed Clock) • LOCAL partner request proceeds without touching prefunding_balance table • cpm_token_id stored in Redis with TTL <= 60 s (verify via RedisTemplate.getExpire) • Missing country_code returns 400 VALIDATION_ERROR | 50 | 8.9-T13 | BE | API-05
8.9-T15 | api-gateway | 8.9 | 8. Partner (Northbound) API | OpenAPI finalization & sandbox | 1 | Implement GET /v1/payments/{id}, POST cancel, GET /v1/merchants/{qr}, GET /v1/balance | API-05 §4.5-4.8. GET /v1/payments/{id}: query PostgreSQL transaction table WHERE payment_id AND partner_id = calling partner; 404 PAYMENT_NOT_FOUND if not owned. POST cancel: only if status in (approved,pending) AND created_at date == today KST; else 400 CANCEL_NOT_PERMITTED; call SchemeAdapterClient.cancelPayment(); for OVERSEAS return prefund_returned_usd. GET /v1/merchants/{qr}: query MongoDB merchant collection (service: svc-merchant-qr, repository MerchantRepository Spring Data MongoDB) by qr_code field; 404 not found; 422 if status=inactive. GET /v1/balance: LOCAL partner -> 403 FORBIDDEN; OVERSEAS -> query prefunding_balance PostgreSQL by partner_id; include_history=true returns last 10 rows from prefunding_deduction_event ORDER BY event_at DESC LIMIT 10. | • Add getPaymentStatus(@PathVariable id) and cancelPayment methods to PaymentController.java • Implement cancel KST same-day validation using ZoneId.of('Asia/Seoul') • Create MerchantController.java @RestController /v1/merchants injecting MerchantRepository (Spring Data MongoDB) • Create BalanceController.java @RestController /v1/balance injecting PrefundingRepository (JPA) • Enforce partner ownership on all lookups; throw appropriate typed exceptions mapped to ErrorEnvelope • Return correct HTTP codes for all error cases | MerchantController.java, BalanceController.java; getPaymentStatus and cancelPayment in PaymentController.java | • GET /v1/payments/{id} with another partner's payment_id returns 404 PAYMENT_NOT_FOUND • Cancel on payment created yesterday KST returns 400 CANCEL_NOT_PERMITTED • GET /v1/merchants/{qr} for inactive merchant returns 422 not 404 • GET /v1/balance for LOCAL partner returns 403 FORBIDDEN • GET /v1/balance?include_history=true returns array of at most 10 deduction entries | 55 | 8.9-T14 | BE | API-05
8.9-T16 | api-gateway | 8.9 | 8. Partner (Northbound) API | OpenAPI finalization & sandbox | 1 | Implement webhook delivery service with retry, signing, and outbox pattern in svc-notification-webhook | API-05 §6.1-6.4. WebhookDeliveryService.java at services/svc-notification-webhook/src/main/java/com/gme/pay/webhook/WebhookDeliveryService.java. Uses transactional Outbox table webhook_outbox (PostgreSQL) polled every 5 s via @Scheduled. Signing: X-GME-Webhook-Signature = sha256=HMAC-SHA256(serialised_body, webhook_signing_secret); X-GME-Webhook-Timestamp = ISO-8601; X-GME-Event-ID = event_id. webhook_signing_secret fetched from Vault (distinct from API secret). RestTemplate 10 s read timeout; non-2xx or exception = failure. Retry back-off: immediate, 30 s, 2 min, 10 min, 30 min, 1 h x5 = 10 attempts. After 10 failures: set status=delivery_failed, publish alert to outbox. | • Create WebhookDeliveryService.java @Service with @Scheduled(fixedDelay=5000) outbox polling method • Inject RestTemplate (10 s read timeout), VaultTemplate, WebhookOutboxRepository (JPA) • Compute HMAC-SHA256 signature over serialised event body using partner webhook_signing_secret from Vault • Use RestTemplate.postForEntity; treat non-2xx or ResourceAccessException as failure • Update webhook_outbox: increment attempt_count; compute next_retry_at from back-off schedule; mark delivery_failed after attempt 10 • Log event_id and partner_id on every attempt for audit | services/svc-notification-webhook/src/main/java/com/gme/pay/webhook/WebhookDeliveryService.java | • Attempt 1 fires immediately (no initial delay); attempt 2 fires after 30 s (fixed scheduler) • After 10 failed attempts: webhook_outbox.status = delivery_failed • HMAC-SHA256 header value verifiable by re-computing with test secret • 10 s timeout enforced: mock endpoint sleeping 11 s triggers failure not success • Signing secret fetched from VaultTemplate not from application.yaml | 55 | 8.9-T15 | BE | API-05
8.9-T17 | api-gateway | 8.9 | 8. Partner (Northbound) API | OpenAPI finalization & sandbox | 1 | Create Spring @Profile(sandbox) config class with SandboxSchemeAdapterStub | API-05 §10.1 and §10.3. Sandbox mirrors production with: scheme calls simulated, prefunding pre-loaded, test treasury rates static, settlement simulated hourly. SandboxConfig.java @Configuration @Profile('sandbox') at services/svc-payment-executor/src/main/java/com/gme/pay/executor/config/SandboxConfig.java registers SandboxSchemeAdapterStub @Bean @Primary replacing real SchemeAdapterClient. Stub returns canned responses based on merchant_qr magic values: ZPQR_TEST_APPROVED -> approved immediately; ZPQR_TEST_PENDING -> pending 30 s then approved; ZPQR_TEST_DECLINED -> SCHEME_UNAVAILABLE 422; ZPQR_TEST_TIMEOUT -> uncertain status; ZPQR_TEST_INACTIVE -> MERCHANT_NOT_FOUND 404. application-sandbox.yml at services/svc-payment-executor/src/main/resources/ disables live FX feed and configures hourly settlement simulation. | • Create application-sandbox.yml with zeropay.realtime.enabled=false and settlement.simulation.cron=0 0 * * * * • Create SandboxConfig.java @Configuration @Profile('sandbox') • Implement SandboxSchemeAdapterStub @Bean @Primary implementing SchemeAdapterClient interface • Switch on merchant_qr value for each magic ZPQR_TEST_* and return appropriate canned result • Add SettlementSimulationJob.java @Component @Profile('sandbox') with @Scheduled for hourly simulation • Add @ConditionalOnProperty(name='zeropay.realtime.enabled', havingValue='false') to disable real adapter | services/svc-payment-executor/src/main/resources/application-sandbox.yml; services/svc-payment-executor/src/main/java/com/gme/pay/executor/config/SandboxConfig.java; SandboxSchemeAdapterStub.java | • With spring.profiles.active=sandbox, SandboxSchemeAdapterStub is primary bean; real ZeroPay adapter not instantiated • ZPQR_TEST_APPROVED merchant_qr returns approved payment response • ZPQR_TEST_DECLINED returns 422 SCHEME_UNAVAILABLE • ZPQR_TEST_TIMEOUT sets payment status to uncertain • zeropay.realtime.enabled=false confirmed in application-sandbox.yml | 45 | 8.9-T16 | BE | API-05
8.9-T18 | api-gateway | 8.9 | 8. Partner (Northbound) API | OpenAPI finalization & sandbox | 1 | Implement sandbox prefunding control endpoint POST /sandbox/v1/prefunding/set | API-05 §10.1: sandbox control API allows setting prefunding balance to any value. Endpoint: POST /sandbox/v1/prefunding/set @Profile('sandbox') only. Body: {partner_id: string, balance_usd: string decimal}. Requires valid pk_test_ API key verified by HmacRequestSigningFilter. Updates prefunding_balance.balance_usd (NUMERIC(20,4)) @Transactional. Returns 200 {partner_id, balance_usd, updated_at}. Negative balance_usd -> 400 VALIDATION_ERROR. Unknown partner_id -> 404. Controller: services/svc-payment-executor/src/main/java/com/gme/pay/executor/sandbox/SandboxController.java. | • Create SandboxController.java @RestController @Profile('sandbox') @RequestMapping('/sandbox/v1') • Inject PrefundingRepository (Spring Data JPA) • Implement setPrefundBalance(@RequestBody @Valid SetPrefundRequest req) @Transactional • Validate balance_usd as BigDecimal >= 0; reject negative with 400 • Call PrefundingRepository native UPDATE query: UPDATE prefunding_balance SET balance_usd=:bal WHERE partner_id=:pid; check rows updated=1 else 404 • Return 200 SetPrefundResponse with partner_id, balance_usd, updated_at=Instant.now() | services/svc-payment-executor/src/main/java/com/gme/pay/executor/sandbox/SandboxController.java | • POST /sandbox/v1/prefunding/set balance_usd=1000.00 updates PostgreSQL row and returns 200 • Negative balance_usd=-1 returns 400 VALIDATION_ERROR • Endpoint not registered with spring.profiles.active=production (bean absent) • balance_usd stored as NUMERIC(20,4): value 99999.9999 preserved exactly • Unknown partner_id returns 404 not DB exception | 35 | 8.9-T17 | BE | API-05
8.9-T19 | api-gateway | 8.9 | 8. Partner (Northbound) API | OpenAPI finalization & sandbox | 1 | Seed sandbox PostgreSQL via Flyway: test treasury rates, test partners, prefunding balances | Stack: Flyway migrations at db/migration/. Sandbox needs static test treasury rates (treasury_rate table: usd_krw=1420.00, usd_usd=1.0, usd_mnt=3430.00), 2 test partners (SENDMN: OVERSEAS, pk_test_/sk_test_ credentials bcrypt-hashed cost 12, and GME_REMIT: LOCAL, pk_test_/sk_test_), and prefunding_balance for SENDMN = 10000.00 USD. Sandbox-only migrations use a separate Flyway location: classpath:db/migration/sandbox configured in application-sandbox.yml. V9xx numbering to avoid collision with production migrations. | • Create db/migration/sandbox/V901__sandbox_treasury_rates.sql with INSERT INTO treasury_rate rows for usd_krw=1420.00, usd_usd=1.0, usd_mnt=3430.00 • Create db/migration/sandbox/V902__sandbox_test_partners.sql with INSERT INTO partner rows for SENDMN and GME_REMIT with bcrypt-hashed API secrets • Create db/migration/sandbox/V903__sandbox_prefunding_balances.sql with INSERT INTO prefunding_balance for SENDMN balance_usd=10000.00 • Configure application-sandbox.yml: spring.flyway.locations=classpath:db/migration,classpath:db/migration/sandbox • Add sandbox resource path to svc-payment-executor Gradle resources block | db/migration/sandbox/V901__sandbox_treasury_rates.sql, V902__sandbox_test_partners.sql, V903__sandbox_prefunding_balances.sql | • With sandbox profile, Flyway applies all 3 V9xx migrations on fresh schema without errors • treasury_rate table has usd_krw=1420.00 after V901 • prefunding_balance for SENDMN = 10000.00 USD after V903 • V9xx migrations do NOT run when spring.flyway.locations=classpath:db/migration only (production mode) • SENDMN api_key has pk_test_ prefix; api_secret bcrypt hash verifies against test sk_test_ value | 35 | 8.9-T18 | BE | API-05
8.9-T20 | api-gateway | 8.9 | 8. Partner (Northbound) API | OpenAPI finalization & sandbox | 1 | Write Jackson round-trip contract tests for generated DTOs in lib-api-contracts | Stack: JUnit 5, Jackson ObjectMapper (Spring Boot auto-configured). Tests in libs/lib-api-contracts/src/test/java/com/gme/pay/api/contracts/DtoContractTest.java verify the generated Java DTOs serialise/deserialise exactly as described in openapi/partner-api.yaml. Tests cover: required vs optional fields, enum values, nullable fields, and money fields as string not number. These are pure unit tests with no Spring context needed. | • Create DtoContractTest.java in libs/lib-api-contracts/src/test/java/com/gme/pay/api/contracts/ • Test RT-01: RateQuoteRequest round-trip; verify target_payout and payout_currency present; direction enum rejects 'invalid' • Test RT-02: RateQuoteResponse round-trip; verify valid_until present; collection_usd null when not set with Jackson INCLUDE_NON_NULL • Test RT-03: ErrorEnvelope round-trip; nested error.code, error.details array serialises correctly • Test RT-04: FixedMpmPaymentRequest; verify collection_amount serialises as JSON string not numeric • Test RT-05: CpmGenerateResponse; expires_at present; prefund_reserved_usd nullable • Run ./gradlew :libs:lib-api-contracts:test | libs/lib-api-contracts/src/test/java/com/gme/pay/api/contracts/DtoContractTest.java with 5+ test methods | • All tests pass on ./gradlew :libs:lib-api-contracts:test • RT-01: direction='invalid' throws JsonMappingException during deserialisation • RT-02: collection_usd absent from JSON output when null (Jackson INCLUDE_NON_NULL configured) • RT-03: ErrorEnvelope round-trip preserves error.details[0].field and .issue • RT-04: collection_amount in JSON is string value not numeric value | 40 | 8.9-T09 | BE | API-05
8.9-T21 | api-gateway | 8.9 | 8. Partner (Northbound) API | OpenAPI finalization & sandbox | 1 | Write Spring MockMvc contract tests for POST /v1/rates (WireMock for config-registry) | Stack: JUnit 5, @WebMvcTest(RateController.class), WireMock (com.github.tomakehurst:wiremock). Test class: services/svc-rate-fx/src/test/java/com/gme/pay/ratefx/web/RateControllerContractTest.java. Tests verify HTTP layer only (not rate engine internals). WireMock stubs the config-registry internal calls. Helper builds valid HMAC-signed headers for each test request. | • Create RateControllerContractTest.java @WebMvcTest(RateController.class) @AutoConfigureMockMvc • Register WireMock @RegisterExtension; stub GET /internal/schemes/zeropay -> 200 scheme JSON • Create buildSignedHeaders(method, path, body) helper producing valid X-API-Key, X-Timestamp, X-Signature • Test C-01: valid inbound rate quote request -> 200 with quote_id and valid_until present • Test: unknown scheme_id (WireMock returns 404) -> controller returns 404 SCHEME_NOT_FOUND • Test: missing X-API-Key -> 401 INVALID_API_KEY • Test: direction=invalid -> 400 VALIDATION_ERROR with error.details[0].field=direction | services/svc-rate-fx/src/test/java/com/gme/pay/ratefx/web/RateControllerContractTest.java | • All 4 test methods pass • C-01 response valid_until matches ISO-8601 pattern • SCHEME_NOT_FOUND test asserts HTTP 404 and error.code=SCHEME_NOT_FOUND • VALIDATION_ERROR test asserts error.details[0].field=direction • WireMock verifies exactly 1 call to scheme config endpoint for C-01 | 50 | 8.9-T20 | BE | API-05
8.9-T22 | api-gateway | 8.9 | 8. Partner (Northbound) API | OpenAPI finalization & sandbox | 1 | Write Testcontainers integration test for MPM payment flow with PostgreSQL | Stack: JUnit 5, Testcontainers PostgreSQL 16, @SpringBootTest(webEnvironment=RANDOM_PORT), WireMock for scheme adapter. Test class: services/svc-payment-executor/src/test/java/com/gme/pay/executor/MpmPaymentIntegrationTest.java. Applies Flyway migrations including sandbox seed (SENDMN with 10000.00 USD). Verifies: quote fetch -> MPM payment -> prefunding_balance decremented atomically in PostgreSQL. After payment of collection_usd=36.37, balance must be 9963.63. Also verifies idempotent retry does not double-debit. | • Add testcontainers-postgresql dependency to svc-payment-executor test scope • Create MpmPaymentIntegrationTest.java @SpringBootTest @Testcontainers with @Container PostgreSQLContainer • Apply Flyway with sandbox location in @BeforeAll • Stub WireMock: POST /internal/scheme/zeropay/commit -> 200 approved • Call POST /v1/rates then POST /v1/payments with SENDMN credentials and collection_usd=36.37 • Assert HTTP 201 and query JdbcTemplate: SELECT balance_usd FROM prefunding_balance WHERE partner_id='SENDMN' = 9963.63 • Call same POST /v1/payments with same Idempotency-Key; assert 201 again and balance still 9963.63 | services/svc-payment-executor/src/test/java/com/gme/pay/executor/MpmPaymentIntegrationTest.java | • Test passes with ./gradlew :services:svc-payment-executor:test • prefunding_balance.balance_usd = 9963.63 after first payment (BigDecimal precision, no rounding error) • Second call with same Idempotency-Key returns stored 201 without re-debiting (balance stays 9963.63) • Payment with expired quote returns 422; balance unchanged at 10000.00 • Test completes in under 60 s including Testcontainers startup | 55 | 8.9-T21 | BE | API-05
8.9-T23 | api-gateway | 8.9 | 8. Partner (Northbound) API | OpenAPI finalization & sandbox | 1 | Write Testcontainers concurrency test for CPM prefunding atomicity (10 concurrent requests) | Stack: JUnit 5, Testcontainers PostgreSQL 16, @SpringBootTest. Verifies SELECT FOR UPDATE on prefunding_balance prevents double-spend. SENDMN seeded with 100.00 USD balance. 10 concurrent threads each POST /v1/payments/cpm/generate with prefund_reserve_usd=50.00 and unique Idempotency-Keys. Exactly 2 should return 201; exactly 8 should return 402 INSUFFICIENT_PREFUNDING. Final balance must be 0.00 USD (not negative). Test class: services/svc-payment-executor/src/test/java/com/gme/pay/executor/CpmConcurrencyTest.java. | • Create CpmConcurrencyTest.java @SpringBootTest @Testcontainers • Seed SENDMN with balance_usd=100.00 via SandboxController endpoint or direct SQL • Use ExecutorService(10 threads) to fire 10 simultaneous POST /v1/payments/cpm/generate each with prefund_reserve_usd=50.00 and unique Idempotency-Keys • Collect all HTTP status codes and count 201 vs 402 responses • Assert exactly 2 succeed (201) and exactly 8 fail (402) • Query final prefunding_balance.balance_usd; assert = 0.00 | services/svc-payment-executor/src/test/java/com/gme/pay/executor/CpmConcurrencyTest.java | • Exactly 2 of 10 concurrent requests return HTTP 201 • Exactly 8 return HTTP 402 INSUFFICIENT_PREFUNDING • Final prefunding_balance.balance_usd = 0.00 (not negative) • No DB deadlock or exception logged during test • Test passes on 3 consecutive runs (repeatable) | 55 | 8.9-T22 | BE | API-05
8.9-T24 | api-gateway | 8.9 | 8. Partner (Northbound) API | OpenAPI finalization & sandbox | 1 | Write unit tests for HmacRequestSigningFilter (5 scenarios, fixed Clock, mocked Redis) | Stack: JUnit 5, Mockito, MockHttpServletRequest. Tests for HmacRequestSigningFilter in isolation: no HTTP server needed. Clock injected as java.time.Clock so tests fix the instant. Redis mocked via Mockito. Tests cover valid request, stale timestamp, replay detection, missing API key, and canonical string construction. | • Create HmacRequestSigningFilterTest.java in services/svc-payment-executor/src/test/java/com/gme/pay/executor/security/ • Test H1: valid signature + current timestamp -> FilterChain.doFilter called once • Test H2: valid signature + timestamp 301 s old (fixed Clock) -> 401 TIMESTAMP_OUT_OF_RANGE; chain NOT called • Test H3: valid signature but Redis returns existing replay key -> 401 INVALID_SIGNATURE; Redis SET not called again • Test H4: missing X-API-Key header -> 401 INVALID_API_KEY; no HMAC computation (verify Mac never called) • Test H5: canonical string construction: assert computed string = METHOD + LF + PATH + LF + timestamp + LF + SHA256_of_body_hex | services/svc-payment-executor/src/test/java/com/gme/pay/executor/security/HmacRequestSigningFilterTest.java with 5 test methods | • All 5 tests pass • H2 uses Clock.fixed at now()-301s; asserts error.code=TIMESTAMP_OUT_OF_RANGE • H3 asserts Redis SET never called after replay detected • H5 asserts canonical string contains correct SHA-256 hex of test body bytes • No real network call: Redis and PartnerCredentialService fully mocked | 40 | 8.9-T10 | BE | API-05
8.9-T25 | api-gateway | 8.9 | 8. Partner (Northbound) API | OpenAPI finalization & sandbox | 1 | Write unit tests for IdempotencyFilter (5 scenarios from API-05 §7.1) | Stack: JUnit 5, Mockito, MockHttpServletRequest/Response. Tests for IdempotencyFilter covering all 5 scenarios: S1 missing key, S2 in-flight, S3 completed same body, S4 completed different body, S5 GET bypass. StringRedisTemplate mocked. No Spring context needed. | • Create IdempotencyFilterTest.java in services/svc-payment-executor/src/test/java/com/gme/pay/executor/web/ • Mock StringRedisTemplate with controlled return values per scenario • Test S1: POST without Idempotency-Key -> 400 MISSING_IDEMPOTENCY_KEY • Test S2: Redis returns IN_FLIGHT -> 409 with X-Idempotency-Status: in_flight header • Test S3: Redis returns COMPLETED + matching body hash -> stored response replayed; FilterChain.doFilter NOT called • Test S4: Redis returns COMPLETED + different body hash -> 422 IDEMPOTENCY_KEY_REUSE • Test S5: GET request without Idempotency-Key -> FilterChain.doFilter called; no 400 | services/svc-payment-executor/src/test/java/com/gme/pay/executor/web/IdempotencyFilterTest.java with 5 test methods | • All 5 tests pass • S3 asserts FilterChain.doFilter never called (stored response replayed) • S4 asserts error.code=IDEMPOTENCY_KEY_REUSE in response body • S2 asserts response header X-Idempotency-Status=in_flight • S5 asserts FilterChain.doFilter called exactly once for GET | 40 | 8.9-T11 | BE | API-05
8.9-T26 | api-gateway | 8.9 | 8. Partner (Northbound) API | OpenAPI finalization & sandbox | 1 | Write unit tests for WebhookDeliveryService: signing, retry schedule, failure escalation | Stack: JUnit 5, Mockito. Tests for WebhookDeliveryService at services/svc-notification-webhook/src/test/java/com/gme/pay/webhook/WebhookDeliveryServiceTest.java. RestTemplate and VaultTemplate mocked. Fixed Clock for retry timing. Covers: successful delivery, retry back-off, timeout failure, 10-attempt escalation, HMAC signature correctness. | • Create WebhookDeliveryServiceTest.java; mock RestTemplate and VaultTemplate (return test webhook_signing_secret=test_secret_32bytes) • Test W1: delivery returns 200 -> webhook_outbox.status=DELIVERED; no retry scheduled • Test W2: delivery returns 500 -> attempt_count incremented to 1; next_retry_at = now+30s (fixed Clock) • Test W3: delivery throws ResourceAccessException (timeout) -> treated as failure, attempt_count incremented • Test W4: after 10 consecutive failures -> status=DELIVERY_FAILED; alert event written to outbox • Test W5: re-compute HMAC-SHA256(body, test_secret_32bytes); assert equals X-GME-Webhook-Signature header value sent by service (strip sha256= prefix before compare) | services/svc-notification-webhook/src/test/java/com/gme/pay/webhook/WebhookDeliveryServiceTest.java with 5 test methods | • W5 signature comparison passes (byte-exact HMAC-SHA256) • W2 next_retry_at is exactly 30 s after failure timestamp (fixed Clock) • W4 asserts attempt_count=10 and outbox status=DELIVERY_FAILED • W3 ResourceAccessException treated as delivery failure not unhandled exception • W1 no retry row scheduled after successful delivery | 45 | 8.9-T16 | BE | API-05
8.9-T27 | api-gateway | 8.9 | 8. Partner (Northbound) API | OpenAPI finalization & sandbox | 1 | Write Spring OpenAPI contract validation tests against running sandbox server | Stack: JUnit 5, Testcontainers (PostgreSQL 16 + Redis), @SpringBootTest(webEnvironment=RANDOM_PORT), io.swagger.parser.v3:swagger-parser. Tests spin up the real application with sandbox profile, make HTTP requests, and validate each JSON response body against openapi/partner-api.yaml schemas using swagger-parser SchemaValidator. Catches DTO serialisation divergence (field name typos, wrong types). Test class: services/svc-payment-executor/src/test/java/com/gme/pay/executor/OpenApiContractValidationTest.java. | • Add io.swagger.parser.v3:swagger-parser to svc-payment-executor test scope • Create OpenApiContractValidationTest.java @SpringBootTest @Testcontainers with PostgreSQL and Redis containers; profile=sandbox • Load openapi/partner-api.yaml via new OpenAPIV3Parser().read(specPath) • For POST /v1/rates 200: execute request; capture response JSON; validate against RateQuoteResponse schema; assert 0 violations • For POST /v1/payments 201: execute full MPM flow; validate FixedMpmPaymentResponse; assert 0 violations • For GET /v1/payments/{id} 200: execute; validate PaymentDetailResponse; assert 0 violations | services/svc-payment-executor/src/test/java/com/gme/pay/executor/OpenApiContractValidationTest.java | • Zero schema violations for /v1/rates 200 response • Zero schema violations for /v1/payments 201 response • Zero schema violations for GET /v1/payments/{id} 200 response • If a required field is absent from DTO the test fails (regression safety verified by temporarily removing a field) • ./gradlew :services:svc-payment-executor:test --tests *OpenApiContract* passes | 55 | 8.9-T23 | BE | API-05
8.9-T28 | api-gateway | 8.9 | 8. Partner (Northbound) API | OpenAPI finalization & sandbox | 1 | Add x-sandbox-config extension and certification checklist to partner-api.yaml | API-05 §10 (Sandbox and Onboarding). Certification requires 16 test cases C-01 to C-16. Sandbox credential format: pk_test_<32-char-hex> / sk_test_<64-char-hex>. Magic merchant_qr values: ZPQR_TEST_APPROVED (approved), ZPQR_TEST_PENDING (pending 30s then approved), ZPQR_TEST_DECLINED (SCHEME_UNAVAILABLE), ZPQR_TEST_TIMEOUT (uncertain), ZPQR_TEST_INACTIVE (MERCHANT_NOT_FOUND). Simulated settlement fires top of every hour. Add all of this as an x-sandbox-config extension block under info in openapi/partner-api.yaml so partner tooling can read it programmatically. No new code files. | • Open openapi/partner-api.yaml • Add info.x-sandbox-config object with: base_url, credential_format (pk_test_/sk_test_ pattern), test_merchant_qr_values (map of value to outcome string) • Add certification_checklist array with 16 entries each containing id (C-01 to C-16), test_case description, pass_criteria string matching API-05 §10.4 table • Verify YAML still lints clean after extension block addition • Run redocly lint; assert 0 errors | x-sandbox-config extension block in openapi/partner-api.yaml info section covering all C-01 to C-16 certification tests and magic QR values | • openapi/partner-api.yaml lints clean after addition • All 16 test cases C-01 through C-16 present with pass_criteria field • ZPQR_TEST_APPROVED maps to outcome: 'Payment approved immediately' • credential_format shows pk_test_ and sk_test_ prefixes • sandbox base_url = https://api-sandbox.gmepayplus.com | 30 | 8.9-T19 | BE | API-05
8.10-T01 | api-gateway | 8.10 | 8. Partner (Northbound) API | Partner integration & certification kit | 3 | Define HmacSignatureUtil in lib-api-contracts: canonical-string builder and verifier | API-05 §3.2: every partner request is signed with HMAC-SHA256 over canonical string = HTTP_METHOD + LF + PATH_WITH_QUERY + LF + ISO8601_UTC_TIMESTAMP + LF + SHA256_HEX_OF_BODY. For GET/DELETE body-hash = SHA-256 of empty string. Signature is hex-encoded HMAC-SHA256(canonical_string, api_secret). Replay window = 300 s. Module: lib-api-contracts (shared library used by Auth service and tests). | • Create lib-api-contracts/src/main/java/com/gme/pay/contracts/hmac/HmacSignatureUtil.java • Implement buildCanonicalString(method, pathWithQuery, timestamp, bodyBytes): String • Implement computeSignature(canonicalString, apiSecret): String using javax.crypto.Mac HMAC-SHA256 • Implement verify(canonicalString, providedSignature, apiSecret, serverInstant, requestInstant): boolean -- rejects if ¦serverInstant - requestInstant¦ > 300 s • Add unit test HmacSignatureUtilTest: happy path, GET empty-body, timestamp-expired, wrong-secret | lib-api-contracts/src/main/java/com/gme/pay/contracts/hmac/HmacSignatureUtil.java and HmacSignatureUtilTest.java | • buildCanonicalString produces exactly 4 lines joined by LF with no trailing LF • computeSignature for the fixed test vector POST + /v1/rates + 2026-06-04T09:31:00.000Z + SHA256(body) produces a stable hex output • verify returns false when ¦delta¦ > 300 s • verify returns false when apiSecret is wrong • GET request uses SHA-256 of empty string as body hash | 40 |  | BA | API-05
8.10-T02 | api-gateway | 8.10 | 8. Partner (Northbound) API | Partner integration & certification kit | 3 | Implement HmacAuthFilter in services/auth-identity as a Spring Security OncePerRequestFilter | API-05 §3.1-3.2: every northbound request carries X-API-Key, X-Timestamp, X-Signature headers. The Auth and Identity service (services/auth-identity) must validate these before any endpoint logic. Uses HmacSignatureUtil from lib-api-contracts (8.10-T01). Secrets stored in Vault/KMS; never in config files. On failure return standard error envelope (lib-errors) with codes INVALID_API_KEY (401), INVALID_SIGNATURE (401), TIMESTAMP_OUT_OF_RANGE (401). | • Add HmacAuthFilter extends OncePerRequestFilter in services/auth-identity/src/main/java/com/gme/pay/auth/filter/HmacAuthFilter.java • Extract X-API-Key, X-Timestamp, X-Signature from request; cache body bytes via ContentCachingRequestWrapper • Load api_secret from Vault secret path secret/gmepay/partners/{apiKey} • Call HmacSignatureUtil.verify; on failure write error envelope JSON (lib-errors ErrorResponse) with correct HTTP status • Register filter in SecurityConfig ahead of UsernamePasswordAuthenticationFilter | services/auth-identity/src/main/java/com/gme/pay/auth/filter/HmacAuthFilter.java | • Missing X-API-Key returns HTTP 401 INVALID_API_KEY • X-Timestamp more than 300 s from server time returns HTTP 401 TIMESTAMP_OUT_OF_RANGE • Wrong signature returns HTTP 401 INVALID_SIGNATURE • Valid headers allow the request to pass through to downstream handler • Body bytes are not consumed by the filter (ContentCachingRequestWrapper used) | 45 | 8.10-T01 | BA | API-05
8.10-T03 | api-gateway | 8.10 | 8. Partner (Northbound) API | Partner integration & certification kit | 3 | Flyway migration V9001__partner_credentials.sql: partner credential and IP-allowlist tables | API-05 §3.1, §3.3: each partner has one credential pair (X-API-Key / api_secret bcrypt-hashed, cost >= 12), optional up to 10 IP CIDR allowlist entries, and a rate_quote_ttl_seconds (range 60-1800, default 300). Module: services/auth-identity; DB: PostgreSQL 16 (port 5433). Flyway migration sequence must be the next available in that service. | • Create services/auth-identity/src/main/resources/db/migration/V9001__partner_credentials.sql • Define table partner_credential (id UUID PK, partner_id UUID NOT NULL FK partners, api_key VARCHAR(64) UNIQUE NOT NULL, api_secret_hash VARCHAR(256) NOT NULL, rate_quote_ttl_seconds INT NOT NULL DEFAULT 300 CHECK (rate_quote_ttl_seconds BETWEEN 60 AND 1800), is_sandbox BOOLEAN NOT NULL DEFAULT false, status VARCHAR(16) NOT NULL DEFAULT active, created_at TIMESTAMPTZ, revoked_at TIMESTAMPTZ) • Define table partner_ip_allowlist (id UUID PK, partner_credential_id UUID FK partner_credential ON DELETE CASCADE, cidr VARCHAR(48) NOT NULL, created_at TIMESTAMPTZ) • Add UNIQUE constraint on (partner_credential_id, cidr); create index on api_key | services/auth-identity/src/main/resources/db/migration/V9001__partner_credentials.sql | • Flyway applies migration cleanly on a fresh Testcontainers Postgres 16 instance • api_key column has UNIQUE constraint • rate_quote_ttl_seconds CHECK rejects 59 and 1801 • partner_ip_allowlist FK cascades on delete of parent credential row • Migration is idempotent when re-applied (Flyway checksum passes) | 30 |  | BA | API-05
8.10-T04 | api-gateway | 8.10 | 8. Partner (Northbound) API | Partner integration & certification kit | 3 | Implement IP-allowlist check in HmacAuthFilter: reject requests from non-allowlisted IPs | API-05 §3.3: partners may register up to 10 CIDR ranges. When configured, requests from unlisted IPs are rejected with HTTP 403 IP_NOT_ALLOWLISTED before signature verification. Allowlist cached in Redis (key: ip_allowlist:{partner_id}, TTL 300 s per spec). Uses partner_ip_allowlist table from 8.10-T03. Module: services/auth-identity. | • Add IpAllowlistService @Service in services/auth-identity/src/main/java/com/gme/pay/auth/service/IpAllowlistService.java • loadAllowlist(partnerId): check Redis first (key ip_allowlist:{partnerId}), fall back to partner_ip_allowlist table, cache result in Redis with EX 300 • In HmacAuthFilter: before signature check call IpAllowlistService; if allowlist non-empty and request IP not in any CIDR, return HTTP 403 IP_NOT_ALLOWLISTED • Add unit test: IP in range passes; IP outside range blocked; empty allowlist passes all | services/auth-identity/src/main/java/com/gme/pay/auth/service/IpAllowlistService.java (and updated HmacAuthFilter) | • Request from 10.0.0.5 blocked when allowlist contains only 192.168.1.0/24 • Request from 192.168.1.50 passes the same allowlist • Partner with no allowlist entries allows any IP • Cache miss causes DB lookup; second call hits Redis (verify with Mockito spy) • HTTP 403 body contains error code IP_NOT_ALLOWLISTED in lib-errors envelope | 35 | 8.10-T02, 8.10-T03 | BA | API-05
8.10-T05 | api-gateway | 8.10 | 8. Partner (Northbound) API | Partner integration & certification kit | 3 | Implement replay-signature dedup store in Redis: reject exact-signature duplicates within 10 min | API-05 §3.6: in addition to the 300-s timestamp window, GMEPay+ stores (partner_id, X-Signature) for 10 minutes and rejects exact-signature duplicates within that window. Redis key: sig_replay:{partner_id}:{signature}, TTL 600 s. Module: services/auth-identity. | • Add ReplayProtectionService @Service in services/auth-identity/src/main/java/com/gme/pay/auth/service/ReplayProtectionService.java • checkAndRecord(partnerId, signature): SETNX sig_replay:{partnerId}:{signature} with EX 600; return false if key already existed (duplicate) • Inject into HmacAuthFilter; after signature validation call checkAndRecord; reject HTTP 401 INVALID_SIGNATURE if duplicate • Add integration test with Testcontainers Redis: first call passes, second identical call fails, third with different signature passes | services/auth-identity/src/main/java/com/gme/pay/auth/service/ReplayProtectionService.java | • Identical (partner_id, signature) pair within 10 min returns HTTP 401 on second call • Same partner different signature is accepted within same window • SETNX is atomic -- concurrent identical calls result in exactly one success • After Redis key TTL expires the same signature is accepted again • ReplayProtectionService does not call DB (Redis only) | 30 | 8.10-T02 | BA | API-05
8.10-T06 | api-gateway | 8.10 | 8. Partner (Northbound) API | Partner integration & certification kit | 3 | Implement idempotency-key store and middleware in services/payment-executor | API-05 §2.6 and §7.1: all POST endpoints require Idempotency-Key (UUID, 16-128 chars). GMEPay+ stores (partner_id, idempotency_key, response_body, response_status) for 24 h (Redis TTL 86400 s). Same key + same body returns stored response. Same key + different body returns HTTP 422 IDEMPOTENCY_KEY_REUSE. Missing key returns HTTP 400 MISSING_IDEMPOTENCY_KEY. In-flight same key returns HTTP 409 with X-Idempotency-Status: in_flight. Module: services/payment-executor. | • Add IdempotencyService @Service in services/payment-executor/src/main/java/com/gme/pay/executor/idempotency/IdempotencyService.java • Store keyed by idempotency:{partner_id}:{key} in Redis; value JSON {status, responseBody, requestBodyHash, locked} • checkOrLock(partnerId, key, requestBodyHash): SETNX locked entry first; update to completed on response • Create IdempotencyFilter extends OncePerRequestFilter: extract header, call service, short-circuit if found • Return X-Idempotency-Status header on replayed responses | services/payment-executor/src/main/java/com/gme/pay/executor/idempotency/IdempotencyService.java and IdempotencyFilter.java | • Missing header returns HTTP 400 MISSING_IDEMPOTENCY_KEY • Second identical request returns stored HTTP status and body verbatim • Same key different body hash returns HTTP 422 IDEMPOTENCY_KEY_REUSE • In-flight (lock held) returns HTTP 409 with X-Idempotency-Status: in_flight • Redis key TTL is 86400 s | 45 |  | BA | API-05
8.10-T07 | api-gateway | 8.10 | 8. Partner (Northbound) API | Partner integration & certification kit | 3 | Write HmacSampleClient.java: self-contained Java HMAC signing example for partner integration kit | WBS 8.10 deliverable: sample HMAC client. API-05 §3.2 canonical string: HTTP_METHOD + LF + PATH_WITH_QUERY + LF + ISO8601_UTC_TIMESTAMP_MS + LF + SHA256_HEX_OF_BODY. Headers: X-API-Key, X-Timestamp, X-Signature, Idempotency-Key, Content-Type: application/json. Target: Java 11+ stdlib only (java.net.http, javax.crypto). Location: integration-kit/samples/java/HmacSampleClient.java. | • Create integration-kit/samples/java/HmacSampleClient.java with main method • Implement buildCanonicalString and sign methods inline (no external deps) • Demonstrate POST /v1/rates to https://api-sandbox.gmepayplus.com with placeholder test credentials pk_test_XXX / sk_test_YYY • Print all request headers and response body to stdout • Add inline comments explaining each step of canonical string construction | integration-kit/samples/java/HmacSampleClient.java | • Compiles with javac 11 with no extra classpath entries • Running produces X-API-Key, X-Timestamp, X-Signature headers printed to stdout • SHA-256 of empty string used when body is empty (GET example commented inline) • Canonical string uses LF (0x0A) not CRLF as line separator • X-Timestamp is millisecond-precision ISO-8601 UTC ending .000Z | 40 | 8.10-T01 | BA | API-05
8.10-T08 | api-gateway | 8.10 | 8. Partner (Northbound) API | Partner integration & certification kit | 3 | Write HmacSampleClient.py: Python 3 HMAC signing example for partner integration kit | WBS 8.10 deliverable: sample HMAC client in Python. Same canonical string as 8.10-T07. Uses only stdlib: hashlib, hmac, http.client, datetime. Target: integration-kit/samples/python/hmac_sample_client.py. Demonstrates POST /v1/rates against https://api-sandbox.gmepayplus.com. | • Create integration-kit/samples/python/hmac_sample_client.py • Implement sign_request(method, path_with_query, body_bytes, api_key, api_secret) -> dict of headers • Build canonical string with LF separator; SHA-256 body hash via hashlib.sha256 • Demonstrate POST /v1/rates with sample payload; print response • Include __main__ guard with example invocation | integration-kit/samples/python/hmac_sample_client.py | • Runs with python3 hmac_sample_client.py and prints headers plus response • HMAC output for a fixed test vector matches Java sample HmacSampleClient output • hashlib.sha256(b'').hexdigest() used for body hash when body is empty • X-Timestamp is UTC millisecond ISO-8601 (2026-06-04T09:31:00.000Z format) • No third-party imports (stdlib only) | 30 | 8.10-T07 | BA | API-05
8.10-T09 | api-gateway | 8.10 | 8. Partner (Northbound) API | Partner integration & certification kit | 3 | Write HmacSampleClient.js (Node.js 18+): HMAC signing example for partner integration kit | WBS 8.10 deliverable: sample HMAC client in JavaScript. Same canonical string as 8.10-T07. Uses only Node.js built-ins: crypto, https. Location: integration-kit/samples/nodejs/hmac_sample_client.js. Demonstrates POST /v1/rates against sandbox. | • Create integration-kit/samples/nodejs/hmac_sample_client.js • Implement signRequest(method, pathWithQuery, bodyStr, apiKey, apiSecret) returning headers object • Use crypto.createHmac('sha256', apiSecret).update(canonical).digest('hex') for signature • Use crypto.createHash('sha256').update(bodyBytes).digest('hex') for body hash • Demonstrate POST /v1/rates; log headers and response to console | integration-kit/samples/nodejs/hmac_sample_client.js | • node hmac_sample_client.js executes on Node 18+ without additional packages • X-Timestamp is new Date().toISOString() (millisecond precision UTC) • HMAC for a fixed test vector matches Python and Java sample outputs • Empty body uses SHA-256 of empty Buffer (crypto.createHash('sha256').update(Buffer.alloc(0)).digest('hex')) • Signature header value is lowercase hex | 25 | 8.10-T07 | BA | API-05
8.10-T10 | api-gateway | 8.10 | 8. Partner (Northbound) API | Partner integration & certification kit | 3 | Create integration-kit/openapi/partner-api.yaml: OpenAPI 3.1 spec for all 7 Partner API endpoints | API-05 §4.1: endpoints are POST /v1/rates, POST /v1/payments, POST /v1/payments/cpm/generate, GET /v1/payments/{id}, POST /v1/payments/{id}/cancel, GET /v1/merchants/{qr}, GET /v1/balance. Money fields are strings (decimal). All timestamps ISO-8601 UTC milliseconds. Error envelope: error.code, error.message, error.request_id, error.details[]. Security: custom headers X-API-Key and X-Signature. Location: integration-kit/openapi/partner-api.yaml. | • Create integration-kit/openapi/partner-api.yaml with openapi: 3.1.0, info block (title: GMEPay+ Partner API, version: 1.0.0) • Define securitySchemes for X-API-Key (apiKey in header) and X-Signature (apiKey in header) • Define all 7 paths with request bodies, response schemas, and all HTTP status codes from API-05 §4 • Define reusable schemas: MoneyAmount, ErrorResponse, RateQuoteRequest, RateQuoteResponse, PaymentRequest, PaymentResponse, CpmGenerateRequest, CpmGenerateResponse, CancelRequest, CancelResponse, MerchantDetailResponse, BalanceResponse • Add examples from API-05 example sections | integration-kit/openapi/partner-api.yaml | • openapi-generator validate returns zero errors • All 7 paths present with correct HTTP methods and at least success + error status codes • RateQuoteResponse includes quote_id, offer_rate, send_amount, service_charge, collection_usd, payout_usd_cost, collection_margin_usd, payout_margin_usd, cross_rate, valid_until • ErrorResponse has error.code, error.message, error.request_id, error.details as array • All money amount fields typed as string with format: decimal pattern ^[0-9]+(.[0-9]+)?$ | 55 |  | BA | API-05
8.10-T11 | api-gateway | 8.10 | 8. Partner (Northbound) API | Partner integration & certification kit | 3 | Implement RateQuoteController POST /v1/rates in services/rate-fx | API-05 §4.2: POST /v1/rates takes target_payout (string decimal), payout_currency, scheme_id, direction, optional merchant_qr and partner_ref. Returns quote_id, offer_rate, send_amount, service_charge, collection_usd, payout_usd_cost, collection_margin_usd, payout_margin_usd, cross_rate, valid_until. Cross-border: 5-step RATE-04 engine. Domestic same-currency short-circuit omits USD pool fields. Quote stored in Redis TTL = rate_quote_ttl_seconds (default 300 s). X-Request-ID on every response. | • Create services/rate-fx/src/main/java/com/gme/pay/ratefx/api/RateQuoteController.java @RestController • Inject RateEngineService and QuoteStoreService • Validate required fields; call rateEngine.computeQuote(request); store result in Redis key quote:{quoteId} with EX = ttl • Return RateQuoteResponse DTO; omit USD pool fields for domestic same-currency short-circuit • Add X-Request-ID response header via ResponseHeaderFilter (lib-api-contracts) | services/rate-fx/src/main/java/com/gme/pay/ratefx/api/RateQuoteController.java | • POST with valid inbound KRW/USD returns HTTP 200 with quote_id and non-null valid_until • valid_until = quote_issued_at + rate_quote_ttl_seconds within 1-second tolerance • Domestic same-currency request omits collection_usd and payout_usd_cost from response • Unknown scheme_id returns HTTP 404 SCHEME_NOT_FOUND • Response always includes X-Request-ID header | 45 | 8.10-T06 | BA | API-05
8.10-T12 | api-gateway | 8.10 | 8. Partner (Northbound) API | Partner integration & certification kit | 3 | Implement QuoteStoreService: Redis-backed quote persistence and expiry check for rate-fx service | Rate quotes cached in Redis at key quote:{quoteId} with TTL = rate_quote_ttl_seconds (60-1800 s; default 300). At payment time, POST /v1/payments calls QuoteStoreService.fetchQuote(quoteId, partnerId) which returns the stored quote or throws RateQuoteExpiredException if TTL elapsed or not found or wrong partner. Quote record must carry all locked rate values: offer_rate, send_amount, service_charge, collection_usd, payout_usd_cost, collection_margin_usd, payout_margin_usd, cross_rate. Module: services/rate-fx. | • Create services/rate-fx/src/main/java/com/gme/pay/ratefx/service/QuoteStoreService.java @Service • storeQuote(RateQuote quote, int ttlSeconds): serialize to JSON, SETEX quote:{quoteId} ttlSeconds • fetchQuote(String quoteId, UUID partnerId): GET + deserialize; throw RateQuoteExpiredException if absent or partner mismatch • Add integration test with Testcontainers Redis: store then fetch within TTL passes; fetch after TTL throws exception | services/rate-fx/src/main/java/com/gme/pay/ratefx/service/QuoteStoreService.java | • Fetch within TTL returns full quote with all NUMERIC rate fields (BigDecimal) • Fetch after TTL throws RateQuoteExpiredException (maps to HTTP 422 RATE_QUOTE_EXPIRED) • Fetch with wrong partnerId throws RateQuoteExpiredException • TTL in Redis matches the configured rate_quote_ttl_seconds value • BigDecimal serialization round-trip preserves at least 10 decimal places of precision | 35 | 8.10-T11 | BA | API-05
8.10-T13 | api-gateway | 8.10 | 8. Partner (Northbound) API | Partner integration & certification kit | 3 | Implement PaymentExecutorController POST /v1/payments (Fixed MPM) in services/payment-executor | API-05 §4.3: POST /v1/payments requires quote_id, merchant_qr, direction, scheme_id, customer_ref, partner_txn_ref, collection_amount, collection_currency. Flow: (1) validate quote not expired via QuoteStoreService, (2) OVERSEAS only: atomic prefund deduction via SELECT FOR UPDATE (reject HTTP 402 INSUFFICIENT_PREFUNDING if low), (3) call Scheme Adapter commitPayment via Anti-Corruption Layer, (4) lock rate -- store all USD pool values in PostgreSQL transaction record, (5) return HTTP 201 with payment_id, status, scheme_txn_id, offer_rate, rate-locked fields, (6) write payment.approved outbox event. | • Create services/payment-executor/src/main/java/com/gme/pay/executor/api/PaymentExecutorController.java @RestController • Validate quote not expired via QuoteStoreService.fetchQuote; return 422 RATE_QUOTE_EXPIRED if expired • For OVERSEAS: call PrefundingService.deductAtomic(partnerId, amountUsd); return 402 if throws InsufficientPrefundingException • Call SchemeAdapterService.commitPayment(prepare_token, amountKrw) via adapter port • Persist transaction record with all RATE-04 locked USD pool values; write TRANSACTION_COMMITTED and PREFUND_DEDUCTED event to outbox • Return PaymentResponse HTTP 201; write payment.approved outbox event for webhook dispatch | services/payment-executor/src/main/java/com/gme/pay/executor/api/PaymentExecutorController.java | • Expired quote_id returns HTTP 422 RATE_QUOTE_EXPIRED before any prefund deduction (WireMock scheme stub sees zero calls) • OVERSEAS partner with balance 10.00 USD and required deduction 35.77 USD returns HTTP 402 INSUFFICIENT_PREFUNDING • Successful payment returns HTTP 201 with all rate-locked values matching the stored quote • scheme call never made if prefund deduction fails • Duplicate partner_txn_ref with different body returns HTTP 409 DUPLICATE_PARTNER_TXN_REF | 55 | 8.10-T06, 8.10-T12 | BA | API-05
8.10-T14 | api-gateway | 8.10 | 8. Partner (Northbound) API | Partner integration & certification kit | 3 | Implement PrefundingService.deductAtomic with SELECT FOR UPDATE in PostgreSQL | Canonical RATE-04 fact: prefund deduction is ATOMIC (SELECT FOR UPDATE). Table prefunding_balance (partner_id UUID PK, balance_usd NUMERIC(18,2), low_balance_threshold_usd NUMERIC(18,2), updated_at TIMESTAMPTZ). Deduct at POST /v1/payments (MPM) and POST /v1/payments/cpm/generate (CPM). Scheme is never called without prior successful deduction. After deduction if balance < threshold emit LowBalanceEvent to outbox. LOCAL partners are exempt. Module: services/prefunding-balance. | • Create services/prefunding-balance/src/main/java/com/gme/pay/prefunding/service/PrefundingService.java @Service • deductAtomic(UUID partnerId, BigDecimal amountUsd): @Transactional -- SELECT balance FOR UPDATE, check >= amountUsd else throw InsufficientPrefundingException, UPDATE balance = balance - amountUsd, insert prefunding_ledger row • Return DeductResult (new balance, deducted amount, low_balance flag) • If post-deduction balance < low_balance_threshold, write LowBalanceEvent to outbox • Add integration test with Testcontainers Postgres: two concurrent threads each deducting 50 USD from 100 USD balance -- exactly one succeeds, one throws | services/prefunding-balance/src/main/java/com/gme/pay/prefunding/service/PrefundingService.java | • Concurrent calls from 2 threads each deducting 50 USD from 100 USD: total deducted = 50 USD (one fails), no double-spend • Balance stored as NUMERIC(18,2) -- no floating-point drift • LOCAL partner invocation throws UnsupportedOperationException • LowBalanceEvent written to outbox when post-deduction balance < threshold • SELECT FOR UPDATE row lock held within transaction (verify via pg_locks in integration test) | 50 | 8.10-T03 | BA | API-05
8.10-T15 | api-gateway | 8.10 | 8. Partner (Northbound) API | Partner integration & certification kit | 3 | Implement CPM token endpoint POST /v1/payments/cpm/generate in services/payment-executor | API-05 §4.4: POST /v1/payments/cpm/generate takes scheme_id, direction, customer_ref, partner_txn_ref, country_code, optional prefund_reserve_usd. For OVERSEAS: atomic prefund deduction before scheme call (8.10-T14). Returns cpm_token_id, prepare_token, qr_content, expires_at (60 s configurable), prefund_reserved_usd, payment_id (pre-allocated). Token stored in Redis key cpm_token:{cpmTokenId} TTL 60 s. Rate is computed by scheme at scan time and delivered via payment.pending_debit webhook. Module: services/payment-executor. | • Add POST /v1/payments/cpm/generate handler in PaymentExecutorController • For OVERSEAS: call PrefundingService.deductAtomic with prefund_reserve_usd or scheme max limit • Call SchemeAdapterService.prepareCPM to get prepare_token from ZeroPay adapter • Store CPM token in Redis key cpm_token:{cpmTokenId} with EX 60; assign pre-allocated payment_id • Return CpmGenerateResponse HTTP 201; write PREFUND_DEDUCTED event to outbox • Unit test: OVERSEAS partner deduction before scheme call; LOCAL partner skips deduction | services/payment-executor/src/main/java/com/gme/pay/executor/api/PaymentExecutorController.java (updated with CPM handler) | • OVERSEAS: scheme adapter WireMock stub is NOT called when prefund deduction fails (HTTP 402) • prepare_token and qr_content populated from scheme adapter response • expires_at = now + 60 s (within 1-second tolerance) • payment_id pre-allocated and stable for subsequent GET /v1/payments/{id} polling • Redis key cpm_token:{cpmTokenId} exists with TTL <= 60 s immediately after call | 45 | 8.10-T13, 8.10-T14 | BA | API-05
8.10-T16 | api-gateway | 8.10 | 8. Partner (Northbound) API | Partner integration & certification kit | 3 | Implement GET /v1/payments/{id} payment status endpoint in services/payment-executor | API-05 §4.5: GET /v1/payments/{id} returns full payment object including status (pending¦approved¦failed¦cancelled¦uncertain), all rate-locked fields, scheme_txn_id, created_at, approved_at, updated_at, cancelled_at where applicable. Returns HTTP 404 PAYMENT_NOT_FOUND if payment_id not owned by calling partner. Reads from PostgreSQL transaction table. Module: services/payment-executor. | • Add GET /v1/payments/{id} handler in PaymentExecutorController • Load transaction from PostgreSQL by payment_id with partner_id FK constraint check • Map to PaymentDetailResponse DTO including all rate-locked BigDecimal fields • Return HTTP 404 PAYMENT_NOT_FOUND if not found or partner mismatch • Add @SpringBootTest slice test with Testcontainers Postgres: create payment, fetch, verify all fields present | services/payment-executor/src/main/java/com/gme/pay/executor/api/PaymentExecutorController.java (updated with GET handler) | • Returns HTTP 200 with all fields matching the stored transaction record • Calling with a payment_id owned by different partner returns HTTP 404 PAYMENT_NOT_FOUND • status reflects latest state including cancelled and uncertain values • All rate-locked BigDecimal fields serialized as strings in JSON response • updated_at and cancelled_at are present when applicable | 35 | 8.10-T13 | BA | API-05
8.10-T17 | api-gateway | 8.10 | 8. Partner (Northbound) API | Partner integration & certification kit | 3 | Implement POST /v1/payments/{id}/cancel with same-day KST guard and prefund return | API-05 §4.6: cancel allowed only for payments in approved or pending status on the same calendar day in KST (UTC+9). HTTP 400 CANCEL_NOT_PERMITTED if cross-day or wrong status. HTTP 409 if already in terminal state. Reason codes: customer_request, merchant_request, timeout, other. For OVERSEAS: return prefund_returned_usd to prefunding_balance in same transaction. Emit payment.cancelled outbox event for webhook delivery. Module: services/payment-executor. | • Add POST /v1/payments/{id}/cancel handler in PaymentExecutorController • Check payment status in [approved, pending]; check created_at date in KST = today in KST; else return HTTP 400 CANCEL_NOT_PERMITTED • Call SchemeAdapterService.cancelPayment(schemeTxnRef) • For OVERSEAS: @Transactional call PrefundingService.returnFunds(partnerId, amountUsd) then update transaction status to cancelled • Write payment.cancelled outbox event; unit test: cancel on next-day payment, cancel on already-cancelled payment | services/payment-executor/src/main/java/com/gme/pay/executor/api/PaymentExecutorController.java (updated with cancel handler) | • Cancel at 23:59 KST day N succeeds; cancel at 00:01 KST day N+1 returns HTTP 400 CANCEL_NOT_PERMITTED • Cancelling a failed payment returns HTTP 409 • OVERSEAS cancel: prefunding_balance restored by prefund_returned_usd (verify via SELECT after cancel) • Scheme adapter cancelPayment stub called exactly once per successful cancel • payment.cancelled outbox event written with reason field matching request | 40 | 8.10-T14, 8.10-T16 | BA | API-05
8.10-T18 | api-gateway | 8.10 | 8. Partner (Northbound) API | Partner integration & certification kit | 3 | Implement GET /v1/merchants/{qr} merchant resolution in services/merchant-qr-data (MongoDB) | API-05 §4.7: GET /v1/merchants/{qr} resolves URL-encoded QR string against MongoDB merchants collection (populated by daily ZeroPay sync SCH-06). Returns merchant_id, merchant_name, merchant_type, scheme_id, qr_code, status, payout_currency, address. HTTP 404 MERCHANT_NOT_FOUND if absent; HTTP 422 if merchant status == inactive. Module: services/merchant-qr-data (MongoDB datastore, not PostgreSQL). | • Create services/merchant-qr-data/src/main/java/com/gme/pay/merchant/api/MerchantController.java @RestController • GET /v1/merchants/{qr}: URL-decode path param; query MongoDB merchants collection by qr_code field • Map document to MerchantDetailResponse; check status field: inactive -> HTTP 422 • Return HTTP 404 MERCHANT_NOT_FOUND if document not found • Add integration test with Testcontainers MongoDB: seed one active and one inactive merchant, verify both response paths | services/merchant-qr-data/src/main/java/com/gme/pay/merchant/api/MerchantController.java | • Active merchant QR returns HTTP 200 with all 8 response fields populated • Inactive merchant returns HTTP 422 (not 404) • Unknown QR returns HTTP 404 MERCHANT_NOT_FOUND • QR value containing + or / characters is URL-decoded before MongoDB lookup • MongoDB query uses index on qr_code field (verified via explain in integration test) | 35 |  | BA | API-05
8.10-T19 | api-gateway | 8.10 | 8. Partner (Northbound) API | Partner integration & certification kit | 3 | Implement GET /v1/balance prefunding balance endpoint in services/prefunding-balance | API-05 §4.8: GET /v1/balance returns partner_id, balance_usd, low_balance_threshold_usd, is_below_threshold, as_of. Optional ?include_history=true returns last 10 deduction events from prefunding_ledger (fields: payment_id, amount_usd, balance_after_usd, event_at). LOCAL partners (type LOCAL) return HTTP 403. OVERSEAS partners only. Module: services/prefunding-balance (PostgreSQL). | • Create services/prefunding-balance/src/main/java/com/gme/pay/prefunding/api/BalanceController.java @RestController • Inject partner type from authenticated principal; return HTTP 403 for LOCAL type • Query prefunding_balance by partner_id • If include_history=true: SELECT last 10 rows from prefunding_ledger WHERE partner_id = ? ORDER BY event_at DESC LIMIT 10 • Return BalanceResponse DTO; is_below_threshold = balance_usd < low_balance_threshold_usd | services/prefunding-balance/src/main/java/com/gme/pay/prefunding/api/BalanceController.java | • LOCAL partner returns HTTP 403 • OVERSEAS partner balance 48234.56 USD threshold 10000.00: is_below_threshold = false • OVERSEAS partner balance 5000.00 threshold 10000.00: is_below_threshold = true • include_history=true returns array of max 10 events with all 4 fields (payment_id, amount_usd, balance_after_usd, event_at) • as_of timestamp is within 1 s of server time at query execution | 30 | 8.10-T14 | BA | API-05
8.10-T20 | api-gateway | 8.10 | 8. Partner (Northbound) API | Partner integration & certification kit | 3 | Implement WebhookDispatchService: transactional Outbox polling and delivery with exponential backoff | API-05 §6.1-6.2: GMEPay+ POSTs webhook events to partner webhook_url; partner must respond HTTP 2xx within 10 s. Retry schedule per API-05: attempt 1 immediate, 2 at +30 s, 3 at +2 min, 4 at +10 min, 5 at +30 min, 6-10 at +1 h each (total ~6 h). After 10 failures: mark delivery_failed, alert Ops. Phase 1: poll transactional Outbox table in PostgreSQL. Kafka deferred behind EventPublisher interface (lib-events). Module: services/notification-webhook. | • Create services/notification-webhook/src/main/java/com/gme/pay/webhook/service/WebhookDispatchService.java @Service @Scheduled • Poll outbox table for events with status = pending AND next_attempt_at <= now • Send HTTP POST to webhook_url using RestClient with 10-s timeout • On success: set status = delivered, delivered_at = now • On failure: increment attempt_count, compute next_attempt_at per backoff schedule; after 10 failures set status = delivery_failed and write OpsAlertEvent to outbox | services/notification-webhook/src/main/java/com/gme/pay/webhook/service/WebhookDispatchService.java | • next_attempt_at after attempt 1 failure = event_time + 30 s (within 1 s) • next_attempt_at after attempt 5 failure = event_time + 42 min 30 s (sum: 0 + 30s + 2m + 10m + 30m) • After 10 failures status = delivery_failed in outbox table • Successful delivery stops retries (status = delivered, no further next_attempt_at update) • HTTP 3xx redirect from webhook URL counted as failure (not 2xx) | 50 |  | BA | API-05
8.10-T21 | api-gateway | 8.10 | 8. Partner (Northbound) API | Partner integration & certification kit | 3 | Implement WebhookSigningService: HMAC-SHA256 signing of outgoing webhook payloads | API-05 §6.3: outgoing webhook requests carry X-GME-Webhook-Signature: sha256=<HMAC-SHA256(body, webhook_signing_secret)>, X-GME-Event-ID (outbox event UUID), X-GME-Webhook-Timestamp (ISO-8601 UTC ms). Webhook signing secret is distinct from API secret; stored in Vault per partner (secret path secret/gmepay/webhooks/{partnerId}). Partners must verify signature and reject events older than 5 min. Module: services/notification-webhook. | • Create services/notification-webhook/src/main/java/com/gme/pay/webhook/service/WebhookSigningService.java @Service • sign(byte[] body, String webhookSigningSecret): return sha256= + HMAC-SHA256 hex • In WebhookDispatchService: before POST, call WebhookSigningService.sign; add X-GME-Webhook-Signature, X-GME-Webhook-Timestamp, X-GME-Event-ID headers • Unit test: verify header format is sha256={lowercase_hex}, HMAC over empty body matches test vector • Confirm webhook_signing_secret loaded from Vault not api_secret | services/notification-webhook/src/main/java/com/gme/pay/webhook/service/WebhookSigningService.java | • X-GME-Webhook-Signature value starts with sha256= • HMAC-SHA256 over empty body produces stable known hex (test vector) • X-GME-Event-ID equals the outbox event UUID • X-GME-Webhook-Timestamp is ISO-8601 UTC millisecond precision • Signing uses webhook_signing_secret not api_secret (injected as distinct parameter) | 30 | 8.10-T20 | BA | API-05
8.10-T22 | api-gateway | 8.10 | 8. Partner (Northbound) API | Partner integration & certification kit | 3 | Define lib-events Avro/JSON schemas for all 5 webhook event types | API-05 §6.5 defines 5 webhook event types: payment.approved, payment.pending_debit, payment.failed, payment.cancelled, settlement.completed. All share envelope: event_id, event_type, created_at, partner_id, data {}. Phase 1: events stored in outbox as JSON. Kafka wire format deferred behind EventPublisher interface. Schemas live in lib-events. Module: lib-events. | • Create lib-events/src/main/avro/payment_approved.avsc with all data fields from API-05 §6.5 • Create avsc schemas for payment_pending_debit, payment_failed, payment_cancelled, settlement_completed • Mirror each as JSON Schema in lib-events/src/main/resources/schemas/ • Add WebhookEventType enum in lib-events/src/main/java/com/gme/pay/events/WebhookEventType.java • Write EventSchemaTest: serialize then deserialize each event type, assert no field loss | lib-events/src/main/avro/ (5 .avsc files) and lib-events/src/main/resources/schemas/ (5 .json files) | • payment_approved.avsc includes payment_id, partner_txn_ref, scheme_txn_id, offer_rate, collection_amount, prefund_deducted_usd, approved_at • payment_pending_debit.avsc includes estimated_collection_amount and cpm_token_id • payment_failed.avsc includes failure_code, failure_message, prefund_returned_usd • settlement_completed.avsc includes settlement_id, settlement_date, total_payout_krw, total_prefund_deducted_usd, batch_file_ref • Round-trip serialize/deserialize for each type produces identical object (EventSchemaTest passes) | 40 |  | BA | API-05
8.10-T23 | api-gateway | 8.10 | 8. Partner (Northbound) API | Partner integration & certification kit | 3 | Implement rate limiting in Spring Cloud Gateway for Partner API: per-partner per-endpoint Redis token-bucket | API-05 §3.5: rate limits -- 100 req/s per partner (all endpoints), 20 req/s for POST /v1/rates, 50 req/s for POST /v1/payments and POST /v1/payments/cpm/generate. Exceed -> HTTP 429 with Retry-After header. Response headers: X-RateLimit-Limit, X-RateLimit-Remaining, X-RateLimit-Reset (Unix epoch seconds). Implementation: Spring Cloud Gateway RedisRateLimiter. Limits configurable per partner by GME Ops. Module: services/api-gateway. | • Configure RedisRateLimiter in services/api-gateway/src/main/resources/application.yml for routes /v1/rates (20/s), /v1/payments (50/s), /v1/payments/cpm/generate (50/s), and global (100/s) • Implement PartnerKeyResolver @Bean in services/api-gateway/src/main/java/com/gme/pay/gateway/PartnerKeyResolver.java extracting partner_id from X-API-Key header • Store per-partner limit overrides in Redis or config-service with fallback to defaults • Add GlobalFilter to inject X-RateLimit-Limit, X-RateLimit-Remaining, X-RateLimit-Reset headers on every response • Integration test: burst 25 POST /v1/rates calls in 1 s, verify 5 rejected with HTTP 429 and Retry-After | services/api-gateway/src/main/resources/application.yml (rate limiter config) and services/api-gateway/src/main/java/com/gme/pay/gateway/PartnerKeyResolver.java | • 21st POST /v1/rates within 1 s returns HTTP 429 with Retry-After header • 51st POST /v1/payments within 1 s returns HTTP 429 • X-RateLimit-Remaining decrements from limit to 0 across accepted requests • X-RateLimit-Reset is a Unix epoch integer (not ISO-8601) • Per-partner limit override in Redis takes precedence over default | 45 |  | BA | API-05
8.10-T24 | api-gateway | 8.10 | 8. Partner (Northbound) API | Partner integration & certification kit | 3 | Implement sandbox simulator: deterministic ZeroPay scheme adapter for 5 magic test QR values | API-05 §10.3: sandbox magic QR values trigger deterministic outcomes. ZPQR_TEST_APPROVED -> approved immediately; ZPQR_TEST_PENDING -> pending 30 s then approved; ZPQR_TEST_DECLINED -> SCHEME_UNAVAILABLE; ZPQR_TEST_TIMEOUT -> status uncertain; ZPQR_TEST_INACTIVE -> MERCHANT_NOT_FOUND. Sandbox simulator activated via Spring profile sandbox replacing the real ZeroPay adapter. Module: services/scheme-adapter-zeropay. | • Create SandboxZeroPaySchemeAdapter @Profile(sandbox) @Service in services/scheme-adapter-zeropay/src/main/java/com/gme/pay/scheme/zeropay/sandbox/SandboxZeroPaySchemeAdapter.java implementing SchemeAdapterPort • commitPayment: switch on merchant_qr; APPROVED returns SchemeResult.approved with fake approval code; DECLINED throws SchemeUnavailableException; TIMEOUT returns SchemeResult.uncertain • ZPQR_TEST_PENDING: return SchemeResult.pending initially; schedule status flip to approved after 30 s via ScheduledExecutorService • parseMerchantQR: ZPQR_TEST_INACTIVE throws MerchantNotFoundException • Add @SpringBootTest sandbox profile test covering all 5 QR values | services/scheme-adapter-zeropay/src/main/java/com/gme/pay/scheme/zeropay/sandbox/SandboxZeroPaySchemeAdapter.java | • ZPQR_TEST_APPROVED returns SchemeResult.approved with non-null approval code • ZPQR_TEST_DECLINED throws SchemeUnavailableException (maps to HTTP 422 SCHEME_UNAVAILABLE) • ZPQR_TEST_TIMEOUT returns SchemeResult.uncertain • ZPQR_TEST_INACTIVE parseMerchantQR throws MerchantNotFoundException (maps to HTTP 422 on merchant lookup) • ZPQR_TEST_PENDING: commitPayment returns pending; after 30 s transition GET /v1/payments/{id} returns approved | 50 |  | BA | API-05
8.10-T25 | api-gateway | 8.10 | 8. Partner (Northbound) API | Partner integration & certification kit | 3 | Write certification checklist: integration-kit/docs/certification-checklist.md (C-01 to C-16) | API-05 §10.4: partners must pass 16 certification tests before production credentials are issued. Each test has ID, name, expected HTTP status, and pass criteria. Sandbox base URL: https://api-sandbox.gmepayplus.com. Credentials format: X-API-Key pk_test_XXX, API Secret sk_test_YYY. Document location: integration-kit/docs/certification-checklist.md. | • Create integration-kit/docs/certification-checklist.md • For each of the 16 tests (C-01 to C-16) write: test ID, name, purpose, signed curl command referencing HmacSampleClient, expected HTTP status, 2-3 pass criteria • C-01: POST /v1/rates inbound KRW -> HTTP 200 with quote_id and valid_until • C-03: POST /v1/payments with expired quote_id -> HTTP 422 RATE_QUOTE_EXPIRED • C-13: POST /v1/payments insufficient prefunding -> HTTP 402 INSUFFICIENT_PREFUNDING • C-15: POST with tampered X-Signature -> HTTP 401 INVALID_SIGNATURE • C-16: same Idempotency-Key + same body repeated -> HTTP 201 stored response, no double-processing | integration-kit/docs/certification-checklist.md | • All 16 test cases C-01 through C-16 present with HTTP status codes matching API-05 §10.4 table exactly • C-10 documents both OVERSEAS (200) and LOCAL (403) expected outcomes • C-11 includes webhook signature verification step (X-GME-Webhook-Signature verification) • C-16 idempotent retry explicitly states partner must verify no double scheme call occurred • Each test includes a curl command example referencing signed headers from HmacSampleClient | 45 | 8.10-T07, 8.10-T10 | BA | API-05
8.10-T26 | api-gateway | 8.10 | 8. Partner (Northbound) API | Partner integration & certification kit | 3 | Write partner onboarding guide: integration-kit/docs/onboarding-guide.md (7 sections) | WBS 8.10 deliverable: onboarding guide for partner engineers. Must cover: sandbox vs production environments, HMAC signing step-by-step, first rate quote and payment, webhook setup and signature verification, idempotency key rules, error handling and retries, certification process. Cross-references API-05 §2 through §10. Document location: integration-kit/docs/onboarding-guide.md. | • Create integration-kit/docs/onboarding-guide.md • Section 1: Overview (one hub, many QR schemes; partner role) • Section 2: Sandbox environment -- base URL, pre-loaded prefunding, magic QR values, simulated hourly settlement • Section 3: HMAC signing step-by-step -- annotated canonical string example, each header labeled, 300-s drift rule, 10-min replay rule • Section 4: First rate quote (POST /v1/rates) and Fixed MPM payment (POST /v1/payments) with example payloads from API-05 • Section 5: Webhook setup -- register URL, verify X-GME-Webhook-Signature (sha256= prefix, HMAC-SHA256), idempotent event processing • Section 6: Error handling and retry guide -- table of all 20 error codes with retryable flag per API-05 §8.2 • Section 7: Certification process -- link to certification-checklist.md, credential promotion path | integration-kit/docs/onboarding-guide.md | • Section 3 canonical string shows exactly 4 lines with LF separator, matching API-05 §3.2 verbatim • Section 5 webhook verification shows stripping sha256= prefix before HMAC comparison • Section 6 error table contains all 20 error codes from API-05 §8.2 with correct HTTP status and retryable column • Section 4 retry guidance matches API-05 §7.2: same key for 5xx/429, new key for 402/422/4xx validation • Section 2 lists all 5 magic QR values (ZPQR_TEST_APPROVED through ZPQR_TEST_INACTIVE) with expected outcomes | 50 | 8.10-T07, 8.10-T08, 8.10-T09, 8.10-T25 | BA | API-05
8.10-T27 | api-gateway | 8.10 | 8. Partner (Northbound) API | Partner integration & certification kit | 3 | Unit test suite: HmacAuthFilterTest covering all authentication failure paths | Tests for HmacAuthFilter (8.10-T02), IpAllowlistService (8.10-T04), and ReplayProtectionService (8.10-T05) in services/auth-identity. Use JUnit 5 + @WebMvcTest. WireMock for Vault secret retrieval. Test vectors must be deterministic: SHA-256('') = e3b0c44298fc1c149afbf4c8996fb92427ae41e4649b934ca495991b7852b855, canonical-string HMAC must be hard-coded. Module: services/auth-identity. | • Create services/auth-identity/src/test/java/com/gme/pay/auth/filter/HmacAuthFilterTest.java @WebMvcTest • Test missing X-API-Key -> 401 INVALID_API_KEY • Test X-Timestamp 301 s in past -> 401 TIMESTAMP_OUT_OF_RANGE • Test correct signature and timestamp -> 200 passthrough • Test tampered body -> 401 INVALID_SIGNATURE (body hash differs) • Test IP not in allowlist -> 403 IP_NOT_ALLOWLISTED • Test replay (same signature twice) -> 401 INVALID_SIGNATURE on second call • Stub Vault via WireMock returning sk_test_abc123 for test api key | services/auth-identity/src/test/java/com/gme/pay/auth/filter/HmacAuthFilterTest.java | • All 7 test cases pass with correct HTTP status and error code in JSON body • Tampered-body test uses deterministic vector: SHA-256 of 'hello world' = b94d27b9934d3e08a52e52d7da7dabfac484efe04294e576a3b6c0e992b16c6 • Replay test verifies second identical request returns 401 within the 600-s window • WireMock Vault stub called once per test (not cached across tests) • Tests run in CI using Testcontainers Redis for replay store (no external Redis required) | 45 | 8.10-T02, 8.10-T04, 8.10-T05 | BA | API-05
8.10-T28 | api-gateway | 8.10 | 8. Partner (Northbound) API | Partner integration & certification kit | 3 | Unit test suite: PaymentExecutorControllerTest for MPM payment happy path and all rejection paths | Tests for POST /v1/payments in services/payment-executor (8.10-T13). Use JUnit 5 + @SpringBootTest with Testcontainers Postgres and Redis. WireMock for ZeroPay scheme adapter. Test vector from API-05 §4.3 example: target_payout = 50000 KRW, OVERSEAS partner balance = 100.00 USD, expected deduction = 35.77 USD, pool identity: 36.37 - 0.91 - 0.40 == 35.06 (within 0.01 USD). Module: services/payment-executor. | • Create services/payment-executor/src/test/java/com/gme/pay/executor/api/PaymentExecutorControllerTest.java • Happy path: valid quote, OVERSEAS balance 100 USD, merchant ZPQR_TEST_APPROVED -> HTTP 201 with payment_id, scheme_txn_id, all rate-locked fields • Expired quote -> HTTP 422 RATE_QUOTE_EXPIRED; WireMock scheme stub asserts zero invocations • OVERSEAS balance 10 USD deduction 35.77 -> HTTP 402; WireMock scheme stub asserts zero invocations • Duplicate partner_txn_ref different body -> HTTP 409 • LOCAL partner same flow -> HTTP 201 without prefund deduction (prefunding_balance not touched) | services/payment-executor/src/test/java/com/gme/pay/executor/api/PaymentExecutorControllerTest.java | • Happy path response includes all fields matching stored quote (offer_rate = 0.000703) • Post-deduction prefunding_balance row = 100.00 - 35.77 = 64.23 (NUMERIC, no float drift) • Pool identity: collection_usd(36.37) - collection_margin_usd(0.91) - payout_margin_usd(0.40) == payout_usd_cost(35.06) within 0.01 USD • Idempotent retry: same key + same body returns 201 with stored response, WireMock scheme stub has exactly 1 total invocation • LOCAL partner test verifies no row change in prefunding_balance table | 55 | 8.10-T13, 8.10-T14 | BA | API-05
8.10-T29 | api-gateway | 8.10 | 8. Partner (Northbound) API | Partner integration & certification kit | 3 | Unit test suite: WebhookDispatchServiceTest covering retry schedule and delivery-failed escalation | Tests for WebhookDispatchService (8.10-T20) retry schedule per API-05 §6.2: immediate, +30 s, +2 min, +10 min, +30 min, +1 h each up to 10 attempts. After 10 failures: delivery_failed. Use JUnit 5 + Testcontainers Postgres (outbox table) + WireMock for partner webhook URL. Module: services/notification-webhook. | • Create services/notification-webhook/src/test/java/com/gme/pay/webhook/service/WebhookDispatchServiceTest.java • Test: first delivery fails (WireMock returns 500) -> next_attempt_at = now + 30 s (within 1 s tolerance) • Test: fifth failure -> next_attempt_at = now + 30 min (cumulative delay: 0+30s+2m+10m+30m) • Test: tenth failure -> outbox row status = delivery_failed, OpsAlertEvent written to outbox • Test: success on attempt 3 -> status = delivered, no further retry • WireMock: stub webhook URL to return 500 for N attempts then 200 | services/notification-webhook/src/test/java/com/gme/pay/webhook/service/WebhookDispatchServiceTest.java | • next_attempt_at after attempt 1 failure is 30 s after event_time (within 1 s) • next_attempt_at after attempt 5 failure is approximately event_time + 42 min 30 s • After 10 failures outbox row status = delivery_failed and OpsAlertEvent present in outbox • Successful second attempt leaves status = delivered with no next_attempt_at • HTTP 301 redirect counted as failure (WireMock redirect stub used in one test) | 45 | 8.10-T20, 8.10-T21 | BA | API-05
8.10-T30 | api-gateway | 8.10 | 8. Partner (Northbound) API | Partner integration & certification kit | 3 | Contract test: validate all 7 live endpoint responses against partner-api.yaml OpenAPI spec | Ensure runtime responses from all 7 Partner API endpoints conform to integration-kit/openapi/partner-api.yaml (8.10-T10). Use openapi4j RequestValidator/ResponseValidator in @SpringBootTest. Validates both success and error response shapes. Module: integration-tests/ module in monorepo root. | • Create integration-tests/src/test/java/com/gme/pay/contract/PartnerApiContractTest.java • Load integration-kit/openapi/partner-api.yaml with openapi4j schema • For each of 7 endpoints issue a test request via MockMvc or TestRestTemplate and validate response body against schema • Assert zero schema violations for success responses and for error responses (400, 402, 404, 422) • Add contract test to CI pipeline gate: must pass before Docker image build step | integration-tests/src/test/java/com/gme/pay/contract/PartnerApiContractTest.java | • Zero schema violations for POST /v1/rates HTTP 200 response • Zero schema violations for POST /v1/payments HTTP 201 and HTTP 402 responses • Zero schema violations for GET /v1/balance HTTP 200 and HTTP 403 responses • Test fails if a required response field (e.g. quote_id) is removed from controller output • Error envelope responses validate against ErrorResponse schema (error.code, error.message, error.request_id present) | 40 | 8.10-T10, 8.10-T11, 8.10-T13, 8.10-T16, 8.10-T17, 8.10-T18, 8.10-T19 | BA | API-05
9.1-T01 | scheme-adapter-zeropay | 9.1 | 9. QR Scheme Integration (ZeroPay) | Scheme Adapter abstraction | 2 | Define SchemeAdapter Java interface in services/scheme-adapter | WBS 9.1 — Scheme Adapter ACL. The Hub Core must never hold scheme-specific logic; all scheme protocols are hidden behind a fixed Java interface. SAD-02 §5.3 defines the logical contract: authoriseCpm, submitMpm, generateBatchFiles, parseBatchFile, processMerchantSync, healthCheck. SCH-06 §1.3.1 expands to: parseMerchantQR, prepareCPM, commitPayment, cancelPayment, generatePaymentResultFile, generateRefundResultFile, generateSettlementRequestFile, parseInboundFile, validateInboundFile, transferOutbound, fetchInbound, getSupportedFiletypes, getSchemeConfig. The Transaction Orchestrator calls only this interface; it never references ZeroPay or any scheme class directly. | • Create Gradle module services/scheme-adapter if not present; add to root settings.gradle • Define interface SchemeAdapter in services/scheme-adapter/src/main/java/com/gme/pay/scheme/adapter/SchemeAdapter.java with all 13 method signatures from SCH-06 §1.3.1 • Define all supporting record/DTO types (CpmAuthRequest, CpmAuthResponse, MpmSubmitRequest, MpmSubmitResponse, BatchFile, BatchType, BatchRecord, SyncResult, AdapterHealth, MerchantIdentifier, PrepareToken, SchemeResult, CancelResult, TransferResult, FetchResult, FileTypeConfig, SchemeConfig) as Java records or sealed classes in the same package • Annotate the interface with Javadoc; no Spring annotations on the interface itself • Add lib-errors and lib-money as compileOnly dependencies in module build.gradle | services/scheme-adapter/src/main/java/com/gme/pay/scheme/adapter/SchemeAdapter.java plus all supporting types in com.gme.pay.scheme.adapter.model | • Interface compiles with Java 21 and zero Spring dependencies (pure Java contract) • All 13 method signatures present and match SCH-06 §1.3.1 capability groups • Every DTO uses BigDecimal from lib-money for monetary fields; no primitive double • Interface has no @Component or @Service — wiring is done by implementations • Module builds with ./gradlew :services:scheme-adapter:compileJava without errors | 30 |  | ARCH | SCH-06
9.1-T02 | scheme-adapter-zeropay | 9.1 | 9. QR Scheme Integration (ZeroPay) | Scheme Adapter abstraction | 2 | Define SchemeConfig and FileTypeConfig value objects with validation | SCH-06 §1.3.2 defines SchemeConfig fields: scheme_id, scheme_name, operator_name, payout_currency, supported_modes (MPM/CPM), supported_countries (ISO 3166-1), realtime_api_base_url, sftp_host, sftp_port (default 22), sftp_username, sftp_private_key_ref, pgp_public_key_ref, pgp_private_key_ref, inbound_dir, outbound_dir, file_retention_days, merchant_fee_table (JSON, merchant_type to rate%), van_fee_table, gme_fee_share_pct. FileTypeConfig holds: file_id (e.g. ZP0011), direction (OUTBOUND/INBOUND), nominal_kst_time, retention_days. All credential fields are references into secrets store — never plaintext. | • Create SchemeConfig as a Java record in services/scheme-adapter/src/main/java/com/gme/pay/scheme/adapter/model/SchemeConfig.java • Add Bean Validation (@NotBlank, @NotNull, @Min, @Max, @Pattern) to all fields; sftp_port @Min(1) @Max(65535); gme_fee_share_pct @DecimalMin(0.0) @DecimalMax(100.0) • Create FileTypeConfig record with fields: fileId, direction (enum INBOUND/OUTBOUND/BOTH), nominalKstTime (LocalTime), retentionDays • Create enum SupportedMode { MPM, CPM } and enum PaymentDirection { INBOUND, OUTBOUND, DOMESTIC, HUB } • Add a static factory SchemeConfig.fromJson(String) using Jackson; merchant_fee_table and van_fee_table deserialise to Map<String,BigDecimal> | services/scheme-adapter/src/main/java/com/gme/pay/scheme/adapter/model/SchemeConfig.java and FileTypeConfig.java plus SupportedMode.java and related enums | • SchemeConfig.fromJson rejects JSON missing required field scheme_id with ConstraintViolationException • sftp_port defaults to 22 when absent from JSON • merchant_fee_table values are BigDecimal (not double) after deserialisation • gme_fee_share_pct = 70 round-trips correctly through JSON • FileTypeConfig nominalKstTime parses HH:mm string to LocalTime | 35 | 9.1-T01 | ARCH | SCH-06
9.1-T03 | scheme-adapter-zeropay | 9.1 | 9. QR Scheme Integration (ZeroPay) | Scheme Adapter abstraction | 2 | Create SchemeAdapterRegistry Spring @Service for adapter lookup by scheme_id | The Smart Router resolves the correct SchemeAdapter at runtime using scheme_id (e.g. ZEROPAY). SAD-02 §5.3: the Config/Registry component holds scheme registrations. The registry must be a Spring @Service that accepts all SchemeAdapter @Bean implementations via constructor injection (Spring collects them as a List<SchemeAdapter>). Each adapter exposes its scheme_id via getSchemeConfig(). On startup, the registry indexes adapters by scheme_id and fails fast if duplicate scheme_ids are registered. | • Create SchemeAdapterRegistry in services/scheme-adapter/src/main/java/com/gme/pay/scheme/adapter/SchemeAdapterRegistry.java annotated @Service • Inject List<SchemeAdapter> adapters in constructor; build a Map<String,SchemeAdapter> index keyed on adapter.getSchemeConfig().schemeId() • Add method SchemeAdapter resolve(String schemeId) throwing SchemeAdapterNotFoundException (from lib-errors) when not found • Add method List<String> registeredSchemeIds() for health/ops use • On @PostConstruct validate no duplicate schemeId entries; throw IllegalStateException with message listing the duplicate if found | services/scheme-adapter/src/main/java/com/gme/pay/scheme/adapter/SchemeAdapterRegistry.java | • resolve(ZEROPAY) returns the registered ZeroPaySchemeAdapter bean • resolve(UNKNOWN) throws SchemeAdapterNotFoundException • Duplicate registration of the same schemeId on startup throws IllegalStateException naming the duplicate • registeredSchemeIds() returns exactly the count of injected adapters • Registry is a Spring singleton (@Service scope = default) | 25 | 9.1-T01 | ARCH | SCH-06
9.1-T04 | scheme-adapter-zeropay | 9.1 | 9. QR Scheme Integration (ZeroPay) | Scheme Adapter abstraction | 2 | Define ZeroPaySchemeAdapter skeleton @Service with @ConditionalOnProperty guard | ZeroPay is the first concrete adapter. Its class must implement SchemeAdapter and be a Spring @Service so it is auto-discovered by SchemeAdapterRegistry. The bean must be guarded by @ConditionalOnProperty(name=adapter.zeropay.enabled, havingValue=true) so it can be disabled for test slices. In Phase 1 all real-time and batch method bodies throw UnsupportedOperationException with TODO markers; the interface contract is the deliverable, not live ZeroPay calls. | • Create services/scheme-adapter/src/main/java/com/gme/pay/scheme/adapter/zeropay/ZeroPaySchemeAdapter.java annotated @Service @ConditionalOnProperty(name=adapter.zeropay.enabled, havingValue=true, matchIfMissing=false) • Implement SchemeAdapter; getSchemeConfig() loads config from application context (injected ZeroPayAdapterProperties @ConfigurationProperties) • Implement healthCheck() to return AdapterHealth.UP stub • All other methods throw UnsupportedOperationException(TODO: ZeroPay Phase 2 - <method name>) with method name interpolated • Create ZeroPayAdapterProperties @ConfigurationProperties(prefix=adapter.zeropay) binding to SchemeConfig fields | services/scheme-adapter/src/main/java/com/gme/pay/scheme/adapter/zeropay/ZeroPaySchemeAdapter.java and ZeroPayAdapterProperties.java | • With adapter.zeropay.enabled=true the bean is present in context; with false it is absent • getSchemeConfig().schemeId() returns ZEROPAY • healthCheck() returns AdapterHealth with status UP • parseMerchantQR() throws UnsupportedOperationException with message containing TODO • Module compiles and Spring context loads without a live SFTP or HTTP connection | 30 | 9.1-T02, 9.1-T03 | ARCH | SCH-06
9.1-T05 | scheme-adapter-zeropay | 9.1 | 9. QR Scheme Integration (ZeroPay) | Scheme Adapter abstraction | 2 | Flyway migration V900__scheme_adapter_config.sql for scheme_config table | All SchemeConfig parameters are stored in PostgreSQL (money path, per STACK.md). The scheme_config table persists one row per registered scheme. Credential fields (sftp_private_key_ref, pgp_public_key_ref, pgp_private_key_ref) store only Vault/KMS references — never plaintext. merchant_fee_table and van_fee_table are stored as JSONB. gme_fee_share_pct is NUMERIC(5,4). The table lives in the shared config database accessed by Config and Registry service (Gradle module services/config-registry). | • Create db/migration/V900__scheme_adapter_config.sql in services/config-registry/src/main/resources/db/migration/ • Define scheme_config table with columns: id UUID PK default gen_random_uuid(), scheme_id VARCHAR(20) UNIQUE NOT NULL, scheme_name VARCHAR(100) NOT NULL, operator_name VARCHAR(100), payout_currency CHAR(3) NOT NULL, supported_modes TEXT[] NOT NULL, supported_countries TEXT[] NOT NULL, realtime_api_base_url VARCHAR(500), sftp_host VARCHAR(255), sftp_port INT DEFAULT 22, sftp_username VARCHAR(100), sftp_private_key_ref VARCHAR(255), pgp_public_key_ref VARCHAR(255), pgp_private_key_ref VARCHAR(255), inbound_dir VARCHAR(500), outbound_dir VARCHAR(500), file_retention_days INT NOT NULL DEFAULT 90, merchant_fee_table JSONB, van_fee_table JSONB, gme_fee_share_pct NUMERIC(5,4), status VARCHAR(20) NOT NULL DEFAULT ACTIVE, created_at TIMESTAMPTZ NOT NULL DEFAULT now(), updated_at TIMESTAMPTZ NOT NULL DEFAULT now() • Add index: CREATE UNIQUE INDEX ux_scheme_config_scheme_id ON scheme_config(scheme_id) • Insert seed row for ZeroPay with status=INACTIVE (activated by Ops) • Add trigger updated_at_trigger on scheme_config using a shared function set_updated_at() | services/config-registry/src/main/resources/db/migration/V900__scheme_adapter_config.sql | • Flyway applies migration without error on a fresh PostgreSQL 16 Testcontainers instance • UNIQUE constraint on scheme_id rejects a duplicate INSERT • gme_fee_share_pct NUMERIC(5,4) stores 0.7000 (70%) without rounding • sftp_private_key_ref column is VARCHAR not TEXT — prevents accidental plaintext key storage • ZeroPay seed row has status=INACTIVE and merchant_fee_table is valid JSONB | 30 |  | ARCH | SCH-06
9.1-T06 | scheme-adapter-zeropay | 9.1 | 9. QR Scheme Integration (ZeroPay) | Scheme Adapter abstraction | 2 | Flyway migration V901__file_type_config.sql for batch file schedule table | Each scheme has a configurable set of batch file types with direction, nominal KST time, and retention rules (SCH-06 §7.3 and §8.1). A separate file_type_config table holds one row per (scheme_id, file_id). ZeroPay has 16 file types: ZP0011-ZP0066 per SCH-06 §7.3 schedule. The batch scheduler reads this table to know what to generate and when to poll. | • Create db/migration/V901__file_type_config.sql in services/config-registry/src/main/resources/db/migration/ • Define file_type_config: id UUID PK, scheme_id VARCHAR(20) NOT NULL FK scheme_config(scheme_id), file_id VARCHAR(10) NOT NULL, direction VARCHAR(10) NOT NULL CHECK (direction IN (OUTBOUND,INBOUND)), nominal_kst_time TIME, is_full_sync BOOLEAN NOT NULL DEFAULT FALSE, frequency VARCHAR(20) NOT NULL DEFAULT DAILY CHECK (frequency IN (DAILY,WEEKLY,ON_DEMAND)), retention_days INT NOT NULL DEFAULT 90, enabled BOOLEAN NOT NULL DEFAULT TRUE, UNIQUE(scheme_id, file_id) • INSERT all 16 ZeroPay file type rows: ZP0011 OUTBOUND 02:00, ZP0012 INBOUND 05:00, ZP0021 OUTBOUND 02:00, ZP0022 INBOUND 05:00, ZP0041 INBOUND NULL DAILY, ZP0043 INBOUND NULL DAILY, ZP0045 INBOUND NULL DAILY, ZP0047 INBOUND NULL DAILY, ZP0051 INBOUND NULL WEEKLY is_full_sync=TRUE, ZP0053 INBOUND NULL WEEKLY is_full_sync=TRUE, ZP0055 INBOUND NULL WEEKLY is_full_sync=TRUE, ZP0061 OUTBOUND 05:00, ZP0062 INBOUND 10:00, ZP0063 OUTBOUND 14:00, ZP0064 INBOUND 19:00, ZP0065 OUTBOUND 22:00, ZP0066 OUTBOUND 22:00 • Add FK constraint on scheme_id referencing scheme_config • Add Flyway checksum annotation in comment header | services/config-registry/src/main/resources/db/migration/V901__file_type_config.sql | • Migration applies after V900 on clean Testcontainers PostgreSQL 16 instance • UNIQUE(scheme_id, file_id) rejects a duplicate ZP0011 row for ZEROPAY • All 16 ZeroPay rows are present; SELECT COUNT(*) FROM file_type_config WHERE scheme_id=ZEROPAY returns 16 • ZP0051, ZP0053, ZP0055 have is_full_sync=TRUE and frequency=WEEKLY • ZP0061 has nominal_kst_time = 05:00:00 | 25 | 9.1-T05 | ARCH | SCH-06
9.1-T07 | scheme-adapter-zeropay | 9.1 | 9. QR Scheme Integration (ZeroPay) | Scheme Adapter abstraction | 2 | Implement SchemeConfigRepository JPA entity and Spring Data repository | Config and Registry service (Gradle module services/config-registry) owns the scheme_config and file_type_config tables in PostgreSQL. A Spring Data JPA repository provides CRUD for the adapter layer. The JPA entity must map JSONB columns to Map<String,BigDecimal> using a custom AttributeConverter (Jackson-based). Monetary fields use NUMERIC which maps to BigDecimal. | • Create @Entity SchemeConfigEntity in services/config-registry/src/main/java/com/gme/pay/configregistry/entity/SchemeConfigEntity.java mapping all columns from V900 • Create JsonbConverter implements AttributeConverter<Map<String,BigDecimal>,String> using ObjectMapper for merchant_fee_table and van_fee_table columns • Create @Repository SchemeConfigRepository extends JpaRepository<SchemeConfigEntity,UUID> with method Optional<SchemeConfigEntity> findBySchemeId(String schemeId) • Create @Entity FileTypeConfigEntity mapping V901 columns; FK to SchemeConfigEntity via @ManyToOne • Create FileTypeConfigRepository with List<FileTypeConfigEntity> findBySchemeIdAndEnabledTrue(String schemeId) | services/config-registry/src/main/java/com/gme/pay/configregistry/entity/SchemeConfigEntity.java, FileTypeConfigEntity.java, SchemeConfigRepository.java, FileTypeConfigRepository.java, JsonbConverter.java | • findBySchemeId(ZEROPAY) returns the seeded row after V900/V901 migrations run in Testcontainers • merchant_fee_table deserialises to Map<String,BigDecimal> with no precision loss • findBySchemeIdAndEnabledTrue(ZEROPAY) returns 16 rows • SchemeConfigEntity.updatedAt is populated by DB trigger (not application code) — JPA column is @Column(insertable=false, updatable=false) • Saving a new entity with duplicate schemeId throws DataIntegrityViolationException | 40 | 9.1-T05, 9.1-T06 | ARCH | SCH-06
9.1-T08 | scheme-adapter-zeropay | 9.1 | 9. QR Scheme Integration (ZeroPay) | Scheme Adapter abstraction | 2 | Implement SchemeConfigService @Service wrapping config retrieval with Redis cache | The Smart Router and adapter layer read SchemeConfig frequently (per-request path). Redis (STACK.md) is used as a config cache with a TTL of 300 seconds (configurable via adapter.config.cache.ttl-seconds). The service must use Spring Cache with @Cacheable(value=scheme-config, key=#schemeId) backed by RedisCache. Cache eviction occurs when an Ops user updates the scheme record (via a dedicated evict method called from the update endpoint). | • Create SchemeConfigService in services/config-registry/src/main/java/com/gme/pay/configregistry/service/SchemeConfigService.java annotated @Service • Annotate getBySchemeId(String) with @Cacheable(value=scheme-config, key=#schemeId); return SchemeConfig domain object (mapped from entity) • Annotate updateSchemeConfig(String schemeId, SchemeConfigUpdateRequest req) with @CacheEvict(value=scheme-config, key=#schemeId); apply update; log change with actor+timestamp into scheme_config_audit table (see 9.1-T09) • Configure RedisCacheManager bean in CacheConfig @Configuration with TTL = ${adapter.config.cache.ttl-seconds:300} • Add SchemeConfigMapper @Component converting SchemeConfigEntity to SchemeConfig record from lib-api-contracts | services/config-registry/src/main/java/com/gme/pay/configregistry/service/SchemeConfigService.java and CacheConfig.java | • Second call to getBySchemeId(ZEROPAY) is served from Redis; repo.findBySchemeId is invoked only once (verify with Mockito spy) • After updateSchemeConfig the cache key is evicted; next call hits DB • TTL default 300s is configurable via application property • getBySchemeId for unknown scheme_id throws SchemeAdapterNotFoundException • RedisTemplate key serialiser is StringRedisSerializer (human-readable keys in Redis) | 45 | 9.1-T07 | ARCH | SCH-06
9.1-T09 | scheme-adapter-zeropay | 9.1 | 9. QR Scheme Integration (ZeroPay) | Scheme Adapter abstraction | 2 | Flyway migration V902__scheme_config_audit.sql for immutable config audit log | SAD-02 and canonical facts: config changes log actor, timestamp, previous value, and apply only to new transactions. The audit log must be append-only; no UPDATE or DELETE is permitted on this table. One row per change on scheme_config, storing previous_value and new_value as JSONB blobs. | • Create db/migration/V902__scheme_config_audit.sql in services/config-registry/src/main/resources/db/migration/ • Define scheme_config_audit: id UUID PK default gen_random_uuid(), scheme_id VARCHAR(20) NOT NULL, actor_email VARCHAR(255) NOT NULL, change_type VARCHAR(20) NOT NULL CHECK (change_type IN (CREATE,UPDATE,DEACTIVATE)), previous_value JSONB, new_value JSONB NOT NULL, changed_at TIMESTAMPTZ NOT NULL DEFAULT now() • Add a PostgreSQL RULE: CREATE RULE no_update_audit AS ON UPDATE TO scheme_config_audit DO INSTEAD NOTHING and similarly for DELETE to enforce immutability • Add index: CREATE INDEX ix_scheme_config_audit_scheme_id ON scheme_config_audit(scheme_id, changed_at DESC) • Document in SQL comment: this table is append-only; use INSERT only; UPDATE/DELETE are silently dropped by RULE | services/config-registry/src/main/resources/db/migration/V902__scheme_config_audit.sql | • Migration applies cleanly after V901 in Testcontainers • UPDATE on scheme_config_audit has no effect (RULE drops it); row count unchanged • DELETE on scheme_config_audit has no effect • INSERT with missing actor_email is rejected by NOT NULL constraint • ix_scheme_config_audit_scheme_id index is present in pg_indexes | 25 | 9.1-T05 | ARCH | SCH-06
9.1-T10 | scheme-adapter-zeropay | 9.1 | 9. QR Scheme Integration (ZeroPay) | Scheme Adapter abstraction | 2 | Implement SchemeAdapterPort @Component in payment-executor wiring to SchemeAdapterRegistry | The Payment Executor service (Gradle module services/payment-executor) calls scheme adapters via the SchemeAdapterRegistry. To avoid coupling the executor directly to the scheme-adapter module, a Port class (hexagonal pattern) wraps the registry call. SchemeAdapterPort is injected into PaymentOrchestrator. All calls go through SchemeAdapterPort.getAdapter(schemeId) which returns the SchemeAdapter interface — never a concrete class. | • Add services/scheme-adapter as a compileOnly/api dependency in services/payment-executor/build.gradle • Create SchemeAdapterPort in services/payment-executor/src/main/java/com/gme/pay/executor/port/SchemeAdapterPort.java annotated @Component • Inject SchemeAdapterRegistry (from services/scheme-adapter) via constructor • Expose methods: authoriseCpm(String schemeId, CpmAuthRequest), submitMpm(String schemeId, MpmSubmitRequest), parseMerchantQR(String schemeId, String rawPayload) — each delegating to registry.resolve(schemeId).<method> • Add @Slf4j logging at DEBUG level: entry/exit for each call including schemeId and method name for tracing | services/payment-executor/src/main/java/com/gme/pay/executor/port/SchemeAdapterPort.java | • SchemeAdapterPort.submitMpm(ZEROPAY, req) calls ZeroPaySchemeAdapter.submitMpm without casting to concrete type • SchemeAdapterPort.submitMpm(UNKNOWN_SCHEME, req) propagates SchemeAdapterNotFoundException • No import of ZeroPaySchemeAdapter in SchemeAdapterPort • SchemeAdapterPort is injectable via @Autowired in unit tests with a Mockito mock of SchemeAdapterRegistry • DEBUG log entry is emitted on each method call | 30 | 9.1-T03, 9.1-T04 | ARCH | SCH-06
9.1-T11 | scheme-adapter-zeropay | 9.1 | 9. QR Scheme Integration (ZeroPay) | Scheme Adapter abstraction | 2 | Implement parseMerchantQR EMVCo CRC-16/CCITT validation in ZeroPaySchemeAdapter | SCH-06 §3.4: parseMerchantQR must verify CRC-16/CCITT checksum in EMVCo tag 63; confirm tag 00 = 01; extract tag 53 (must be 410 for KRW); locate ZeroPay MAI slot (configurable tag in 26-51 range via adapter.zeropay.mai-tag, default configurable); extract merchant_id, qr_code_id, merchant_name. Error codes: QR_INVALID_CHECKSUM (CRC fail), QR_UNKNOWN_SCHEME (MAI tag not found), QR_MALFORMED (missing mandatory tag), QR_CURRENCY_MISMATCH (tag 53 != 410). The MAI tag must be configurable so it can be updated when KFTC confirms the official tag (OI-A-05). | • Implement EmvcoQrParser in services/scheme-adapter/src/main/java/com/gme/pay/scheme/adapter/zeropay/qr/EmvcoQrParser.java as a package-private class • Implement CRC-16/CCITT calculation over all QR string bytes before tag 63; compare with stored value; throw SchemeAdapterException(QR_INVALID_CHECKSUM) on mismatch • Parse TLV string: split on 2-char tag + 2-char length + value pattern; build Map<String,String> tagMap • Validate tag 00 = 01, tag 53 = 410; throw appropriate error codes from lib-errors • Extract MAI slot using configurable tag (injected from ZeroPayAdapterProperties.maiTag); extract sub-tags for merchant_id and qr_code_id; return MerchantIdentifier record • Wire EmvcoQrParser into ZeroPaySchemeAdapter.parseMerchantQR() | services/scheme-adapter/src/main/java/com/gme/pay/scheme/adapter/zeropay/qr/EmvcoQrParser.java | • Valid EMVCo QR string with correct CRC returns MerchantIdentifier with non-null merchant_id and qr_code_id • Tampered last byte of QR string throws SchemeAdapterException with code QR_INVALID_CHECKSUM • QR with tag 53 = 840 (USD) throws SchemeAdapterException with code QR_CURRENCY_MISMATCH • QR missing tag 00 throws QR_MALFORMED • mai-tag configured as 29 correctly extracts sub-tags from MAI slot 29 | 45 | 9.1-T04 | ARCH | SCH-06
9.1-T12 | scheme-adapter-zeropay | 9.1 | 9. QR Scheme Integration (ZeroPay) | Scheme Adapter abstraction | 2 | Implement merchant and QR resolution against PostgreSQL local DB in ZeroPaySchemeAdapter | SCH-06 §3.5: after QR parsing, GMEPay+ validates merchant_id and qr_code_id against the local PostgreSQL merchant and qr_codes tables (populated by daily sync). At payment time the local DB is authoritative — no live ZeroPay lookup. Steps: look up merchant by merchant_id; confirm status = ACTIVE; look up qr_code_id; confirm status = ACTIVE and linked merchant_id matches; retrieve merchant_type_code for fee rate selection. Failures: MERCHANT_NOT_FOUND (422), MERCHANT_INACTIVE (422), QR_DEACTIVATED (422). | • Create MerchantResolutionService in services/scheme-adapter/src/main/java/com/gme/pay/scheme/adapter/zeropay/merchant/MerchantResolutionService.java annotated @Service • Inject MerchantRepository and QrCodeRepository (JPA, PostgreSQL via services/merchant-qr-data module) • Implement resolveMerchant(String merchantId, String qrCodeId): MerchantRecord following SCH-06 §3.5 five steps • Throw SchemeAdapterException with canonical lib-errors code for each failure case: MERCHANT_NOT_FOUND, MERCHANT_INACTIVE, QR_DEACTIVATED, QR_MALFORMED (qr linked to different merchant_id) • Wire MerchantResolutionService into ZeroPaySchemeAdapter; call from parseMerchantQR after EmvcoQrParser succeeds | services/scheme-adapter/src/main/java/com/gme/pay/scheme/adapter/zeropay/merchant/MerchantResolutionService.java | • resolveMerchant with valid IDs returns MerchantRecord with correct merchant_type_code • Inactive merchant (status=SUSPENDED) throws SchemeAdapterException code MERCHANT_INACTIVE • QR code linked to a different merchant_id throws QR_MALFORMED • Terminated merchant (status=TERMINATED) also throws MERCHANT_INACTIVE • Test uses Testcontainers PostgreSQL 16 with V900 migration pre-loaded and test fixtures inserted | 40 | 9.1-T07, 9.1-T11 | ARCH | SCH-06
9.1-T13 | scheme-adapter-zeropay | 9.1 | 9. QR Scheme Integration (ZeroPay) | Scheme Adapter abstraction | 2 | Define AdapterHealth model and implement healthCheck() for ZeroPaySchemeAdapter | SchemeAdapterRegistry exposes health state for each registered adapter; this feeds the Ops portal and monitoring (OpenTelemetry). AdapterHealth must report: status (UP/DEGRADED/DOWN), last_checked_at (Instant), sftp_reachable (boolean), realtime_api_reachable (boolean), last_error (String nullable). ZeroPaySchemeAdapter.healthCheck() performs a lightweight SFTP no-op (list root directory) and an HTTP HEAD to realtime_api_base_url with 5s timeout. In Phase 1 with no live ZeroPay environment, both checks return false with error=SFTP/API not yet configured. | • Create AdapterHealth Java record in services/scheme-adapter/src/main/java/com/gme/pay/scheme/adapter/model/AdapterHealth.java: status(HealthStatus), lastCheckedAt(Instant), sftpReachable(boolean), realtimeApiReachable(boolean), lastError(String) • Create enum HealthStatus { UP, DEGRADED, DOWN } • Implement ZeroPaySchemeAdapter.healthCheck(): if sftp_host is blank return DOWN with lastError=SFTP not configured; otherwise attempt Apache SSHD SFTP stat with 5s connect timeout; catch all exceptions and set sftpReachable=false • Similarly for realtime_api_base_url: HTTP HEAD via RestClient with 5s timeout; catch exceptions; set realtimeApiReachable=false • Return DEGRADED if one channel fails, DOWN if both fail, UP if both succeed | services/scheme-adapter/src/main/java/com/gme/pay/scheme/adapter/model/AdapterHealth.java and updated ZeroPaySchemeAdapter.healthCheck() | • healthCheck() with blank sftp_host returns HealthStatus.DOWN and lastError containing not configured • healthCheck() where SFTP is reachable but REST HEAD fails returns DEGRADED • healthCheck() never throws — all exceptions are caught and reflected in the return value • lastCheckedAt is set to Instant.now() within the method (not zero/null) • AdapterHealth is serialisable to JSON (Jackson) for the health endpoint | 35 | 9.1-T04 | ARCH | SCH-06
9.1-T14 | scheme-adapter-zeropay | 9.1 | 9. QR Scheme Integration (ZeroPay) | Scheme Adapter abstraction | 2 | Implement SFTP client SftpGatewayClient using Apache SSHD in ZeroPaySchemeAdapter | SCH-06 §2.3 and §2.4: SFTP uses SSH key authentication (RSA-4096 or ECDSA P-256); private key retrieved from Vault/KMS via sftp_private_key_ref (never from disk). Outbound: generate file in memory, write to temp file in secure scratch dir, PGP-encrypt, SFTP PUT, verify remote size/checksum, archive local copy on success, retry 3x with back-off (30s, 2min, 10min) on failure. File naming: {FILE_ID}_{YYYYMMDD}_{SEQ}.dat.pgp (SCH-06 §2.3.3). Inbound: poll remote inbound dir, download to scratch, verify, PGP-decrypt, parse. All PGP ops in memory — no cleartext intermediate files. | • Create SftpGatewayClient in services/scheme-adapter/src/main/java/com/gme/pay/scheme/adapter/zeropay/sftp/SftpGatewayClient.java using Apache MINA SSHD (org.apache.sshd:sshd-sftp:2.x) • Implement connect(SchemeConfig cfg): retrieve private key bytes from VaultSecretsClient using cfg.sftpPrivateKeyRef(); create SshClient; add HostKeyVerifier pinning host key from config; connect and authenticate • Implement transferOutbound(BatchFile file, String remotePath): write to temp file under ${adapter.zeropay.scratch-dir}/out/; PGP-encrypt using BouncyCastle with scheme PGP public key; PUT to cfg.outboundDir()+remotePath; verify remote file size equals local encrypted size; on failure retry 3x with back-off 30s/120s/600s • Implement fetchInbound(String remotePath, Path localPath): GET from cfg.inboundDir()+remotePath; verify checksum; PGP-decrypt using GME private key from cfg.pgpPrivateKeyRef(); return decrypted bytes • Add SftpTransferException (extends SchemeAdapterException) with SFTP_TRANSFER_FAILED error code | services/scheme-adapter/src/main/java/com/gme/pay/scheme/adapter/zeropay/sftp/SftpGatewayClient.java | • transferOutbound retries exactly 3 times then throws SftpTransferException on persistent SFTP failure (mocked SshClient) • File naming pattern matches {FILE_ID}_{YYYYMMDD}_01.dat.pgp for sequence 1 • Temp file is deleted from scratch dir after successful transfer • No cleartext file is retained after PGP encryption step (verify scratch dir is empty post-transfer) • Private key is fetched from VaultSecretsClient, not from classpath or file system | 55 | 9.1-T04 | ARCH | SCH-06
9.1-T15 | scheme-adapter-zeropay | 9.1 | 9. QR Scheme Integration (ZeroPay) | Scheme Adapter abstraction | 2 | Implement PgpCryptoService using BouncyCastle for file encrypt/decrypt/sign/verify | SCH-06 §2.3.2: outbound files are PGP-encrypted with KFTC public key and GME-signed with GME private key. Inbound files are encrypted with GME public key; GMEPay+ decrypts with GME private key and verifies KFTC signature. All PGP operations run entirely in memory — no cleartext intermediate files written to disk (security requirement). Key references stored in secrets store. | • Create PgpCryptoService in services/scheme-adapter/src/main/java/com/gme/pay/scheme/adapter/zeropay/crypto/PgpCryptoService.java • Add BouncyCastle dependency (org.bouncycastle:bcpg-jdk18on) in services/scheme-adapter/build.gradle • Implement encryptAndSign(byte[] plaintext, PGPPublicKey recipientKey, PGPSecretKey signerKey, char[] signerPassphrase): byte[] — use AES-256 symmetric cipher, SHA-256 digest for signature • Implement decryptAndVerify(byte[] ciphertext, PGPSecretKey decryptKey, char[] passphrase, PGPPublicKey senderPublicKey): byte[] — throw PgpSignatureException if signature fails verification • Implement loadPublicKey(byte[] armouredBytes): PGPPublicKey and loadSecretKey(byte[] armouredBytes): PGPSecretKey • Add PgpSignatureException (lib-errors) with code PGP_SIGNATURE_INVALID | services/scheme-adapter/src/main/java/com/gme/pay/scheme/adapter/zeropay/crypto/PgpCryptoService.java | • decryptAndVerify(encryptAndSign(plaintext, recipPubKey, signerSecKey)) returns original plaintext unchanged • decryptAndVerify with a tampered ciphertext throws PgpSignatureException • encryptAndSign output contains no plaintext bytes (verify no substring match of input text in output) • Encryption uses AES-256 (verify cipher algo in PGPEncryptedDataGenerator config) • decryptAndVerify with wrong secret key throws PGPException from BouncyCastle (propagated, not swallowed) | 50 | 9.1-T04 | ARCH | SCH-06
9.1-T16 | scheme-adapter-zeropay | 9.1 | 9. QR Scheme Integration (ZeroPay) | Scheme Adapter abstraction | 2 | Implement ZP0011 outbound batch file generator (payment result registration) | SCH-06 §5.2: ZP0011 is transmitted by 02:00 KST daily; scope = all transactions in status APPROVED for the prior business day (KST) not yet in a prior batch. Record layout (illustrative per A-11): CHAR(1) record_type=D, CHAR(20) gme_txn_id, CHAR(20) zeropay_txn_ref, CHAR(10) merchant_id, CHAR(20) qr_code_id, DATE(8) txn_date, TIME(6) txn_time, NUM(12) payout_amount_krw, NUM(12) merchant_fee_amt, NUM(10) van_fee_amt, CHAR(1) partner_type (D/I), CHAR(12) approval_code, CHAR(1) status_code=A. File header: file_type ZP0011, business_date, gme_institution_code, total_record_count, total_payout_amount_krw. File trailer: total_record_count, control_sum. All KRW amounts are integers (0 decimal places per canonical facts). | • Create Zp0011FileGenerator in services/scheme-adapter/src/main/java/com/gme/pay/scheme/adapter/zeropay/batch/Zp0011FileGenerator.java • Inject TransactionQueryPort (interface backed by services/transaction-mgmt PostgreSQL) to fetch APPROVED transactions for a given business date not yet assigned a batch_file_id • Generate fixed-width record lines; pad/truncate all CHAR fields to exact width; right-align NUM fields with leading zeros • Compute control_sum as sum of payout_amount_krw across all records; write to trailer • Return BatchFile record containing: fileId=ZP0011, businessDate, sequenceNo (01 for first run), contentBytes (UTF-8 fixed-width), recordCount, controlSum • File must be idempotent: re-running for the same date produces identical output if no new transactions | services/scheme-adapter/src/main/java/com/gme/pay/scheme/adapter/zeropay/batch/Zp0011FileGenerator.java | • Header record contains exactly ZP0011 in the file_type field position • payout_amount_krw in detail records is NUM(12) right-padded to 12 digits with leading zeros • control_sum in trailer equals sum of all detail record payout_amount_krw values • Zero-transaction day produces a file with header + trailer only (record_count=0) • Re-running generator for same date+same transactions returns byte-for-byte identical output (idempotent) | 50 | 9.1-T07 | ARCH | SCH-06
9.1-T17 | scheme-adapter-zeropay | 9.1 | 9. QR Scheme Integration (ZeroPay) | Scheme Adapter abstraction | 2 | Implement ZP0012 inbound file parser and reconciliation service | SCH-06 §5.3 and §5.4: ZP0012 arrives by 05:00 KST; contains per-record registration result. Match key: zeropay_txn_ref + txn_date. result_code 00 = success; non-zero = REGISTRATION_FAILED. GMEPay+ must perform line-by-line match of ZP0012 vs ZP0011; any record in ZP0011 absent from ZP0012 = REGISTRATION_UNKNOWN; any record in ZP0012 absent from ZP0011 = anomaly/Ops alert. Amount discrepancy (registered_amount != submitted payout_amount_krw) = REGISTRATION_AMOUNT_MISMATCH. All amounts in KRW (integer, 0 decimal). | • Create Zp0012FileParser in services/scheme-adapter/src/main/java/com/gme/pay/scheme/adapter/zeropay/batch/Zp0012FileParser.java • Implement parse(byte[] content): List<Zp0012Record> parsing fixed-width lines; return Zp0012Record(zeroPayTxnRef, gmeTxnId, merchantId, txnDate, resultCode, resultMessage, registeredAmount, settlementDate) • Create Zp0012ReconciliationService that joins Zp0012Record list vs Zp0011 submitted records from DB; produces ReconciliationResult containing lists: SETTLEMENT_REGISTERED, REGISTRATION_FAILED, REGISTRATION_UNKNOWN, REGISTRATION_AMOUNT_MISMATCH, ANOMALY • For each exception category emit a domain event via EventPublisher (lib-events, transactional Outbox) so Ops alert can be triggered • Update transaction status in PostgreSQL within a @Transactional method; batch update using Spring Data JPA saveAll | services/scheme-adapter/src/main/java/com/gme/pay/scheme/adapter/zeropay/batch/Zp0012FileParser.java and Zp0012ReconciliationService.java | • Record with result_code=00 and matching amount transitions transaction to SETTLEMENT_REGISTERED • Record with result_code=9002 transitions to REGISTRATION_AMOUNT_MISMATCH and emits exception event • ZP0011 record absent from ZP0012 produces REGISTRATION_UNKNOWN entry in ReconciliationResult • ZP0012 record absent from ZP0011 produces ANOMALY entry • ReconciliationService is @Transactional; partial failure rolls back all status updates for that file processing run | 50 | 9.1-T16 | ARCH | SCH-06
9.1-T18 | scheme-adapter-zeropay | 9.1 | 9. QR Scheme Integration (ZeroPay) | Scheme Adapter abstraction | 2 | Implement ZP0061 outbound morning settlement request file generator | SCH-06 §7.2: ZP0061 must be transmitted by 05:00 KST; scope = settlement totals for all transactions with SETTLEMENT_REGISTERED status for the prior business day. Summary level: one row per merchant_id. Fields: merchant_id CHAR(10), settlement_date DATE(8), gross_txn_count NUM(6), gross_txn_amount NUM(14), refund_count NUM(6), refund_amount NUM(14), merchant_fee_total NUM(12), net_settlement_amount NUM(14), settlement_type CHAR(1) N=Net/G=Gross. Net settlement (domestic): net_settlement_amount = gross_txn_amount - refund_amount - merchant_fee_total. Gross settlement (international): net_settlement_amount = gross_txn_amount - refund_amount (full gross; fee invoiced monthly). Prerequisite per §8.2: ZP0011 success AND ZP0012 received. | • Create Zp0061FileGenerator in services/scheme-adapter/src/main/java/com/gme/pay/scheme/adapter/zeropay/batch/Zp0061FileGenerator.java • Query PostgreSQL for all SETTLEMENT_REGISTERED transactions grouped by (merchant_id, settlement_type) for business_date • Apply net vs gross logic: for settlement_type=N: net_settlement_amount = gross_txn_amount - refund_amount - merchant_fee_total; for settlement_type=G: net_settlement_amount = gross_txn_amount - refund_amount • Produce fixed-width records; header includes ZP0061, business_date, total merchant count, grand total net_settlement_amount • Guard: throw BatchPrerequisiteException if ZP0011 and ZP0012 have not both completed successfully for the business_date • All amounts are NUMERIC (BigDecimal) internally; serialised as integer KRW strings in file | services/scheme-adapter/src/main/java/com/gme/pay/scheme/adapter/zeropay/batch/Zp0061FileGenerator.java | • Domestic merchant with gross_txn_amount=100000 KRW, refund=0, merchant_fee=500: net_settlement_amount=99500 • International merchant: net_settlement_amount = gross_txn_amount - refund_amount (fee NOT deducted) • BatchPrerequisiteException thrown when ZP0012 has not been processed for the business_date • Generator is idempotent: same inputs produce same file bytes • File header grand_total equals sum of all merchant net_settlement_amount values | 50 | 9.1-T17 | ARCH | SCH-06
9.1-T19 | scheme-adapter-zeropay | 9.1 | 9. QR Scheme Integration (ZeroPay) | Scheme Adapter abstraction | 2 | Implement batch job scheduler using Spring @Scheduled for ZP00xx daily cron windows | SCH-06 §7.3 and §8.1: outbound batch jobs run at fixed KST cron times: ZP0011/ZP0021 at 02:00, ZP0061 at 05:00, ZP0063 at 14:00, ZP0065/ZP0066 at 22:00. Inbound polls: ZP0012/ZP0022 poll from 05:00, ZP0062 ~10:00, ZP0064 ~19:00. Merchant sync inbound polls hourly 01:00-08:00 KST. All jobs are idempotent. Jobs run in the settlement-service Spring Boot app (services/settlement). The cron expressions use Asia/Seoul timezone. Job dependency chain (§8.2): ZP0061 requires successful ZP0011 + ZP0012; ZP0063 requires morning cycle complete. | • Create ZeroPayBatchScheduler in services/settlement/src/main/java/com/gme/pay/settlement/scheduler/ZeroPayBatchScheduler.java annotated @Component • Add @Scheduled(cron=0 0 2 * * *, zone=Asia/Seoul) for ZP0011 and ZP0021 generation+transmission • Add @Scheduled(cron=0 0 5 * * *, zone=Asia/Seoul) for ZP0012/ZP0022 poll+process and ZP0061 generation+transmission (ZP0061 called after ZP0012 processor completes within the same scheduled method) • Add @Scheduled for ZP0062 poll (10:00), ZP0063 (14:00), ZP0064 poll (19:00), ZP0065/ZP0066 (22:00) • Add @Scheduled(cron=0 0 1-8 * * *, zone=Asia/Seoul) for hourly merchant sync poll 01:00-08:00 • Each method delegates to corresponding BatchJobService; wraps in try-catch; emits BatchJobCompletedEvent or BatchJobFailedEvent via EventPublisher to transactional Outbox | services/settlement/src/main/java/com/gme/pay/settlement/scheduler/ZeroPayBatchScheduler.java | • @Scheduled cron for ZP0011 produces next execution at 02:00 KST when calculated against Asia/Seoul timezone • ZP0061 method checks BatchPrerequisiteService before calling generator; logs WARNING and skips if ZP0012 not received • Each scheduled method is idempotent: second execution within same business day is a no-op (detected by batch_job_log table) • BatchJobFailedEvent is emitted on any exception; event carries jobName, businessDate, errorMessage • Unit test: @SpringBootTest slice with TestSchedulingConfig disabling auto-start; manually invoke each method and assert delegated service called | 45 | 9.1-T18 | ARCH | SCH-06
9.1-T20 | scheme-adapter-zeropay | 9.1 | 9. QR Scheme Integration (ZeroPay) | Scheme Adapter abstraction | 2 | Implement merchant delta sync processor for ZP0041/ZP0045/ZP0047 inbound files | SCH-06 §4.2: ZP0041 (merchant delta), ZP0045 (franchise merchant delta), ZP0047 (franchise group delta) — each delivers daily incremental changes. GME handling: upsert into merchants table (keyed on merchant_id) using change_type I=Insert, U=Update, D=Deactivate. D records set status=INACTIVE immediately — deactivated merchants must be blocked at payment time from the moment of DB update. Log insert/update/deactivation counts. Reconcile record count vs file header; mismatch = ops alert. All ops are in a single @Transactional batch. | • Create MerchantDeltaSyncProcessor in services/scheme-adapter/src/main/java/com/gme/pay/scheme/adapter/zeropay/sync/MerchantDeltaSyncProcessor.java annotated @Service • Parse ZP0041 fixed-width records (field layout: merchant_id CHAR(10), merchant_name VARCHAR(100), business_reg_no CHAR(10), merchant_type_code CHAR(2), status_code CHAR(1), address VARCHAR(200), bank_code CHAR(3), account_no VARCHAR(20), effective_date DATE(8), change_type CHAR(1)) • Upsert using PostgreSQL INSERT ... ON CONFLICT(merchant_id) DO UPDATE; for change_type=D set status=INACTIVE • After upsert validate that DB merchant count change matches file header record count; mismatch emits SyncReconciliationMismatchEvent • Apply same processor pattern for ZP0045 (franchise merchants, is_franchise=TRUE, franchise_code FK) and ZP0047 (franchise_groups table) • Wrap all upserts in @Transactional; rollback on any exception; retain previous data on failure and alert Ops via EventPublisher | services/scheme-adapter/src/main/java/com/gme/pay/scheme/adapter/zeropay/sync/MerchantDeltaSyncProcessor.java | • change_type=I inserts new merchant row; second run with same record is idempotent (upsert, no duplicate) • change_type=D sets merchant status=INACTIVE; subsequent parseMerchantQR for that merchant_id throws MERCHANT_INACTIVE • change_type=U updates merchant_name without affecting status • Record count mismatch between file header and parsed records emits SyncReconciliationMismatchEvent • Exception during upsert rolls back entire batch (Testcontainers PostgreSQL 16 integration test) | 50 | 9.1-T07, 9.1-T12 | ARCH | SCH-06
9.1-T21 | scheme-adapter-zeropay | 9.1 | 9. QR Scheme Integration (ZeroPay) | Scheme Adapter abstraction | 2 | Implement full merchant sync (ZP0051/ZP0055/ZP0053) staging-diff-atomic-promote processor | SCH-06 §4.1 and ZP0051/ZP0055/ZP0053: full sync files contain all active records; processed weekly. GMEPay+ must: download+validate checksum+record count; load into staging table; diff staging vs live; apply inserts, updates, soft-deletes for absent records; confirm record count matches ZeroPay header; promote staging to live atomically within a PostgreSQL transaction. Full-sync failures must not partially overwrite live data — rollback on any error. SCH-06 §4.3: when a full file is present on the same night, suppress the delta upsert for that entity type. | • Create V903__merchant_sync_staging.sql: table merchant_staging mirrors merchants table plus sync_batch_id UUID column; same for qr_codes_staging • Create FullMerchantSyncProcessor in services/scheme-adapter/src/main/java/com/gme/pay/scheme/adapter/zeropay/sync/FullMerchantSyncProcessor.java • Implement processFull(byte[] fileContent, LocalDate businessDate): truncate merchant_staging for this sync_batch_id; bulk INSERT all parsed records; diff vs live using NOT EXISTS subquery; apply inserts/updates/soft-deletes in merchants table inside @Transactional; if record count != header_count rollback and throw FullSyncIntegrityException • Add isMerchantFullSyncPresent(LocalDate d): boolean method; delta processor checks this before running and skips if true • QR full sync (ZP0053) additionally validates every qr_codes staging row has a valid merchant_id in merchants table (referential integrity check before promote) | services/scheme-adapter/src/main/java/com/gme/pay/scheme/adapter/zeropay/sync/FullMerchantSyncProcessor.java and db/migration/V903__merchant_sync_staging.sql | • processFull with staging count != header count throws FullSyncIntegrityException and merchants table is unchanged • Merchant absent from full file but present in live table is soft-deleted (status=INACTIVE) during promote • Delta processor skips when isMerchantFullSyncPresent returns true for that business date • processFull is idempotent: re-running with same file produces same DB state • QR full sync rejects file if any qr_code row references a merchant_id not in merchants table | 55 | 9.1-T20 | ARCH | SCH-06
9.1-T22 | scheme-adapter-zeropay | 9.1 | 9. QR Scheme Integration (ZeroPay) | Scheme Adapter abstraction | 2 | Implement SchemeAdapterHealthIndicator Spring Boot Actuator for adapter status | Ops portal and OpenTelemetry monitoring require a /actuator/health endpoint that includes SchemeAdapter health. Spring Boot Actuator custom HealthIndicator reads AdapterHealth from SchemeAdapterRegistry for all registered adapters and maps to Spring Health (UP/DOWN/UNKNOWN). Exposed via management.endpoint.health.show-details=always for internal monitoring; separate port 8081 for management (not exposed externally per WAF/CDN/TLS at Spring Cloud Gateway edge). | • Create SchemeAdapterHealthIndicator in services/scheme-adapter/src/main/java/com/gme/pay/scheme/adapter/actuator/SchemeAdapterHealthIndicator.java implementing HealthIndicator • Inject SchemeAdapterRegistry; in health() call registry.registeredSchemeIds() and for each call adapter.healthCheck() • Map AdapterHealth.status UP -> Health.up(), DEGRADED -> Health.unknown(), DOWN -> Health.down() with detail entries sftpReachable and realtimeApiReachable • Add component to services/payment-executor and services/settlement Spring Boot apps by including scheme-adapter module • Verify management server port configured: management.server.port=8081 in application.yml | services/scheme-adapter/src/main/java/com/gme/pay/scheme/adapter/actuator/SchemeAdapterHealthIndicator.java | • When ZeroPaySchemeAdapter.healthCheck() returns UP, /actuator/health includes component scheme-adapter with status UP • When healthCheck() returns DOWN, overall application health is DOWN • Health detail map contains keys sftpReachable and realtimeApiReachable as boolean • HealthIndicator bean present in Spring context without explicit @Import when scheme-adapter module is on classpath • Management endpoint is on port 8081 (not 8080) | 30 | 9.1-T13, 9.1-T03 | ARCH | SCH-06
9.1-T23 | scheme-adapter-zeropay | 9.1 | 9. QR Scheme Integration (ZeroPay) | Scheme Adapter abstraction | 2 | Define transactional Outbox domain events for adapter layer in lib-events | STACK.md: Phase 1 uses transactional Outbox + EventPublisher interface; Kafka wired in integration phase. All domain events emitted by the adapter layer (BatchJobCompleted, BatchJobFailed, SyncReconciliationMismatch, RegistrationException) must be defined in lib-events as Avro/JSON schemas and published via EventPublisher. The outbox table (in PostgreSQL, same transaction as the state change) ensures no event is lost if the process crashes after DB commit. | • Define event schemas in lib-events/src/main/avro/: BatchJobCompletedEvent.avsc, BatchJobFailedEvent.avsc, SyncReconciliationMismatchEvent.avsc, RegistrationExceptionEvent.avsc — each with fields: eventId UUID, occurredAt Instant, schemeId String, businessDate LocalDate, plus event-specific payload fields • Create OutboxEventPublisher @Service in lib-events implementing EventPublisher interface; persists event JSON to outbox table (id UUID, event_type VARCHAR, payload JSONB, created_at TIMESTAMPTZ, published_at TIMESTAMPTZ nullable) in same @Transactional as the calling service • Create V904__outbox.sql Flyway migration for the outbox table in services/settlement and services/scheme-adapter (each service has its own outbox) • Add EventPublisher interface: void publish(DomainEvent event) — single method; Kafka impl dropped in transparently later • Wire OutboxEventPublisher into Zp0012ReconciliationService and MerchantDeltaSyncProcessor | lib-events/src/main/avro/*.avsc (4 schemas), lib-events/src/main/java/com/gme/pay/events/EventPublisher.java, lib-events/src/main/java/com/gme/pay/events/OutboxEventPublisher.java, db/migration/V904__outbox.sql | • BatchJobFailedEvent emitted by scheduler is persisted to outbox table in same transaction as batch_job_log INSERT (Testcontainers test) • If OutboxEventPublisher.publish() is called outside @Transactional context it throws IllegalStateException • published_at column is null until the outbox poller marks it sent • Event payload JSONB for RegistrationExceptionEvent deserialises back to RegistrationExceptionEvent with zero field loss • Kafka wiring requires only a new OutboxEventPublisher implementation; no change to callers (interface contract test) | 45 | 9.1-T17, 9.1-T19, 9.1-T20 | ARCH | SCH-06
9.1-T24 | scheme-adapter-zeropay | 9.1 | 9. QR Scheme Integration (ZeroPay) | Scheme Adapter abstraction | 2 | Add OpenTelemetry span instrumentation to SchemeAdapterPort and batch generators | STACK.md: OpenTelemetry traces/metrics/logs export to Jaeger (tracing) and Prometheus+Grafana (metrics). All scheme adapter calls must be traced so Ops can correlate payment latency with adapter calls. Each SchemeAdapterPort method and each batch generator method must create a child span with attributes: scheme.id, adapter.method, batch.file_id, batch.business_date. Metrics: Counter scheme_adapter_calls_total{scheme_id, method, outcome} and Histogram scheme_adapter_call_duration_seconds. | • Add OpenTelemetry Java SDK and Micrometer bridge dependencies to services/scheme-adapter/build.gradle • Inject io.opentelemetry.api.trace.Tracer into SchemeAdapterPort; wrap each method body in tracer.spanBuilder(scheme.adapter.<methodName>).startSpan(); set span attributes scheme.id and adapter.method; end span in finally block • Add Micrometer Counter and Timer beans in SchemeAdapterMetrics @Component; increment counter and record timer in SchemeAdapterPort for each call outcome (SUCCESS/ERROR) • Add the same span creation pattern to Zp0011FileGenerator.generate() and Zp0061FileGenerator.generate() with batch.file_id and batch.business_date attributes • Configure OTLP exporter endpoint via management.otlp.tracing.endpoint in application.yml | services/scheme-adapter/src/main/java/com/gme/pay/scheme/adapter/actuator/SchemeAdapterMetrics.java and updated SchemeAdapterPort.java with OTel spans | • Each SchemeAdapterPort method produces a trace span visible in Jaeger test exporter (InMemorySpanExporter in test) • scheme_adapter_calls_total counter increments by 1 on each call • scheme_adapter_call_duration_seconds histogram records a non-zero observation • SchemeAdapterPort.submitMpm exception sets span status to ERROR and records exception • Span attribute scheme.id = ZEROPAY is present on all spans produced by ZeroPaySchemeAdapter calls | 40 | 9.1-T10, 9.1-T16 | ARCH | SCH-06
9.1-T25 | scheme-adapter-zeropay | 9.1 | 9. QR Scheme Integration (ZeroPay) | Scheme Adapter abstraction | 2 | Unit tests for EmvcoQrParser with exact input-output vectors | SCH-06 §3.4: CRC-16/CCITT over all QR bytes before tag 63; tag 00=01; tag 53=410 for KRW; ZeroPay MAI slot configurable. Tests must cover: valid parse, checksum mismatch, wrong currency, missing mandatory tag, unknown scheme MAI, configurable MAI tag. Use JUnit 5 with no Spring context (pure unit test, fast). All test inputs are hand-crafted TLV strings. | • Create EmvcoQrParserTest in services/scheme-adapter/src/test/java/com/gme/pay/scheme/adapter/zeropay/qr/EmvcoQrParserTest.java • Test 1 valid QR: build TLV with tag00=01, tag52=5411, tag53=410, tag58=KR, tag59=TestMerchant, tag60=Seoul, MAI slot29 with merchant_id=M0000000001 and qr_code_id=QR00000000001234567890, compute and append correct CRC in tag63; assert parseMerchantQR returns MerchantIdentifier(merchantId=M0000000001, qrCodeId=QR00000000001234567890) • Test 2 CRC mismatch: use valid QR string but flip last character; assert SchemeAdapterException code = QR_INVALID_CHECKSUM • Test 3 tag53 = 840 (USD): assert SchemeAdapterException code = QR_CURRENCY_MISMATCH • Test 4 missing tag00: assert QR_MALFORMED • Test 5 MAI tag 29 absent: assert QR_UNKNOWN_SCHEME • Test 6 configure mai-tag=31, use MAI slot31: assert correct merchant_id extracted | services/scheme-adapter/src/test/java/com/gme/pay/scheme/adapter/zeropay/qr/EmvcoQrParserTest.java (6 tests) | • All 6 tests pass in ./gradlew :services:scheme-adapter:test • No Spring context loaded (test is pure unit, no @SpringBootTest) • Test 1 merchant_id equals M0000000001 exactly • Test 2 exception message contains QR_INVALID_CHECKSUM • Test runtime < 500ms for all 6 tests combined | 40 | 9.1-T11 | ARCH | SCH-06
9.1-T26 | scheme-adapter-zeropay | 9.1 | 9. QR Scheme Integration (ZeroPay) | Scheme Adapter abstraction | 2 | Unit tests for Zp0011FileGenerator with exact numeric field assertions | ZP0011 generator produces fixed-width batch records. Test vectors: 3 approved transactions for business date 2026-10-14 KST. Tx1: gme_txn_id=TX00000000000000000001, zeropay_txn_ref=ZP00000000000000000001, merchant_id=M000000001, payout_amount_krw=50000, merchant_fee_amt=250, van_fee_amt=100, partner_type=D, approval_code=AP000000000001. Tx2: international, payout_amount_krw=120000, partner_type=I. Tx3: domestic refunded — should NOT appear (status=REFUNDED, not APPROVED). Assertions target exact byte positions in output. | • Create Zp0011FileGeneratorTest in services/scheme-adapter/src/test/java/com/gme/pay/scheme/adapter/zeropay/batch/Zp0011FileGeneratorTest.java • Stub TransactionQueryPort to return Tx1 and Tx2 for business_date 2026-10-14; Tx3 excluded by query • Assert header line starts with ZP0011 at position 0-5; business_date=20261014 at correct offset • Assert Tx1 detail line: payout_amount_krw field = 000000050000 (12 chars, zero-padded) • Assert Tx2 partner_type field = I • Assert trailer control_sum = 000000000170000 (50000 + 120000 formatted to 15 digits) • Assert file is idempotent: calling generate() twice with same stub returns byte-equal output | services/scheme-adapter/src/test/java/com/gme/pay/scheme/adapter/zeropay/batch/Zp0011FileGeneratorTest.java | • Test passes with correct payout_amount_krw field value 000000050000 • Trailer control_sum = 170000 (sum of Tx1+Tx2) padded to file width • Tx3 (REFUNDED) is absent from output • Idempotency assertion passes (byte-equal) • Test uses Mockito; no DB or Spring context | 35 | 9.1-T16 | ARCH | SCH-06
9.1-T27 | scheme-adapter-zeropay | 9.1 | 9. QR Scheme Integration (ZeroPay) | Scheme Adapter abstraction | 2 | Unit tests for Zp0012ReconciliationService with all five mismatch scenarios | SCH-06 §5.4: reconciliation must detect five conditions. Test vectors: outbound ZP0011 had 3 records: R1(zeropay_txn_ref=ZPR001, payout=50000), R2(ZPR002, payout=120000), R3(ZPR003, payout=30000). ZP0012 response: R1 result_code=00 registered_amount=50000; R2 result_code=9002 registered_amount=119000 (mismatch); R3 absent from ZP0012; ZP0012 contains extra record ZPR004 (anomaly not in ZP0011). | • Create Zp0012ReconciliationServiceTest in services/scheme-adapter/src/test/java/com/gme/pay/scheme/adapter/zeropay/batch/Zp0012ReconciliationServiceTest.java • Build ZP0011 submitted record list (R1, R2, R3) and ZP0012 parsed record list (R1 ok, R2 amount mismatch, R4 anomaly; R3 absent) • Call reconcile(submitted, received): ReconciliationResult • Assert result.settled contains R1 with status SETTLEMENT_REGISTERED • Assert result.failed contains R2 with status REGISTRATION_AMOUNT_MISMATCH and note showing expected=120000 actual=119000 • Assert result.unknown contains R3 with status REGISTRATION_UNKNOWN • Assert result.anomalies contains ZPR004 • Assert EventPublisher.publish was called with RegistrationExceptionEvent for R2, R3, ZPR004 (exactly 3 times via Mockito verify) | services/scheme-adapter/src/test/java/com/gme/pay/scheme/adapter/zeropay/batch/Zp0012ReconciliationServiceTest.java | • R1 in result.settled (count=1) • R2 in result.failed with REGISTRATION_AMOUNT_MISMATCH (count=1) • R3 in result.unknown (count=1) • ZPR004 in result.anomalies (count=1) • EventPublisher.publish invoked exactly 3 times (Mockito verify) | 35 | 9.1-T17 | ARCH | SCH-06
9.1-T28 | scheme-adapter-zeropay | 9.1 | 9. QR Scheme Integration (ZeroPay) | Scheme Adapter abstraction | 2 | Unit tests for Zp0061FileGenerator net vs gross settlement logic | SCH-06 §7.1 settlement logic: Net (domestic, settlement_type=N): net_settlement_amount = gross_txn_amount - refund_amount - merchant_fee_total. Gross (international, settlement_type=G): net_settlement_amount = gross_txn_amount - refund_amount (merchant fee billed monthly separately). Test vector: Merchant A domestic, gross_txn_amount=500000, refund_amount=20000, merchant_fee_total=2400 => net=477600. Merchant B international, gross_txn_amount=300000, refund_amount=0 => net=300000 (fee NOT deducted). BatchPrerequisiteException test: ZP0012 not processed. | • Create Zp0061FileGeneratorTest in services/scheme-adapter/src/test/java/com/gme/pay/scheme/adapter/zeropay/batch/Zp0061FileGeneratorTest.java • Stub TransactionQueryPort and BatchPrerequisiteService • Test 1 Merchant A net: assert net_settlement_amount field = 000000000477600 • Test 2 Merchant B gross: assert net_settlement_amount = 000000000300000 and merchant_fee_total field = 000000000000 (zero, not deducted) • Test 3 prerequisite not met: BatchPrerequisiteService.isZp0012Processed(date) returns false; assert generate() throws BatchPrerequisiteException • Test 4 file header grand total: Merchant A net 477600 + Merchant B gross 300000 = 777600 in header field | services/scheme-adapter/src/test/java/com/gme/pay/scheme/adapter/zeropay/batch/Zp0061FileGeneratorTest.java | • Merchant A net_settlement_amount = 477600 (exact integer) • Merchant B net_settlement_amount = 300000; merchant_fee_total = 0 • BatchPrerequisiteException thrown when ZP0012 not processed • File header grand total = 777600 • Tests use Mockito mocks; no Spring context; all pass in < 1s | 35 | 9.1-T18 | ARCH | SCH-06
9.1-T29 | scheme-adapter-zeropay | 9.1 | 9. QR Scheme Integration (ZeroPay) | Scheme Adapter abstraction | 2 | Integration test for SchemeAdapterRegistry with ZeroPaySchemeAdapter using Testcontainers | End-to-end wiring test: Spring Boot test slice loads SchemeAdapterRegistry, ZeroPaySchemeAdapter (adapter.zeropay.enabled=true), SchemeConfigService backed by a real PostgreSQL 16 Testcontainers instance with Flyway V900-V904 applied. Test verifies registry resolves ZEROPAY adapter; healthCheck() returns DOWN (no live SFTP configured); parseMerchantQR with a valid test QR string (EMVCo, KRW, MAI slot configured) returns MerchantIdentifier after merchant is seeded in DB. | • Create SchemeAdapterIntegrationTest in services/scheme-adapter/src/test/java/com/gme/pay/scheme/adapter/SchemeAdapterIntegrationTest.java annotated @SpringBootTest @Testcontainers • Declare @Container PostgreSQLContainer postgres = new PostgreSQLContainer(postgres:16-alpine); configure datasource in @DynamicPropertySource • Seed scheme_config with ZEROPAY row (status=ACTIVE, adapter.zeropay.mai-tag=29) and V900-V904 migrations • Seed merchants and qr_codes tables with test merchant M000000001 (status=ACTIVE) and QR QR00000000001234567890 • Test 1: registry.resolve(ZEROPAY) does not throw • Test 2: adapter.healthCheck().status == DOWN (no SFTP host configured) • Test 3: adapter.parseMerchantQR(validQrString) returns MerchantIdentifier with merchantId=M000000001 | services/scheme-adapter/src/test/java/com/gme/pay/scheme/adapter/SchemeAdapterIntegrationTest.java | • Test 1 passes: registry.resolve(ZEROPAY) returns non-null • Test 2: healthCheck status = DOWN with lastError containing not configured • Test 3: parseMerchantQR returns merchantId = M000000001 • Testcontainers PostgreSQL 16 container starts without manual Docker setup • All 3 assertions pass in ./gradlew :services:scheme-adapter:test | 50 | 9.1-T12, 9.1-T13, 9.1-T22 | ARCH | SCH-06
9.1-T30 | scheme-adapter-zeropay | 9.1 | 9. QR Scheme Integration (ZeroPay) | Scheme Adapter abstraction | 2 | Integration test for ZP0011-ZP0012 batch round-trip with Testcontainers PostgreSQL | SCH-06 §5.2-5.4 full cycle: seed 3 APPROVED transactions in PostgreSQL; run Zp0011FileGenerator; parse output with Zp0011FileParser; simulate ZP0012 response (2 successes, 1 REGISTRATION_AMOUNT_MISMATCH); run Zp0012ReconciliationService; verify DB transaction statuses. Confirms generator-parser-reconciler pipeline in one test without mocking DB. Uses Testcontainers PostgreSQL 16. | • Create BatchRoundTripIntegrationTest in services/scheme-adapter/src/test/java/com/gme/pay/scheme/adapter/zeropay/batch/BatchRoundTripIntegrationTest.java annotated @SpringBootTest @Testcontainers • Seed transactions: TxA(payout=50000 KRW, status=APPROVED), TxB(payout=120000 KRW, status=APPROVED), TxC(payout=30000 KRW, status=APPROVED) • Run Zp0011FileGenerator.generate(businessDate) — capture BatchFile • Assert BatchFile has 3 detail records and trailer control_sum = 200000 • Build synthetic ZP0012 response: TxA result_code=00 registered=50000; TxB result_code=00 registered=120000; TxC result_code=9002 registered=25000 (mismatch) • Run Zp0012ReconciliationService.reconcile() — verify DB: TxA=SETTLEMENT_REGISTERED, TxB=SETTLEMENT_REGISTERED, TxC=REGISTRATION_AMOUNT_MISMATCH • Assert outbox table has 1 RegistrationExceptionEvent row for TxC | services/scheme-adapter/src/test/java/com/gme/pay/scheme/adapter/zeropay/batch/BatchRoundTripIntegrationTest.java | • ZP0011 file has 3 records and control_sum = 200000 • TxA DB status = SETTLEMENT_REGISTERED after reconciliation • TxC DB status = REGISTRATION_AMOUNT_MISMATCH after reconciliation • outbox table has exactly 1 RegistrationExceptionEvent row • Test is repeatable: running twice produces same DB state (idempotency) | 55 | 9.1-T17, 9.1-T23 | ARCH | SCH-06
9.1-T31 | scheme-adapter-zeropay | 9.1 | 9. QR Scheme Integration (ZeroPay) | Scheme Adapter abstraction | 2 | Add Javadoc and MODULE.md for SchemeAdapter ACL boundary documentation | The Scheme Adapter ACL is a key architectural boundary. Future developers adding a new scheme (SCH-06 §11) must understand: what methods to implement, that Hub Core may not import any concrete adapter class, how to register a new adapter via Spring @Service + @ConditionalOnProperty, and the file naming and PGP conventions. Documentation lives in code (Javadoc on SchemeAdapter interface) and a MODULE.md in services/scheme-adapter/. No emoji; plain ASCII. | • Add comprehensive Javadoc to SchemeAdapter.java: interface-level comment explaining ACL purpose, one-paragraph warning IMPORTANT: Hub Core must not import any class from the zeropay sub-package, @see links to SCH-06 sections for each method group • Add @param and @return Javadoc to all 13 methods citing the SCH-06 section e.g. @see SCH-06 section 3.4 for parseMerchantQR • Create services/scheme-adapter/MODULE.md (plain ASCII, no emoji): sections: Purpose, ACL boundary rule, How to add a new scheme (5-step checklist matching SCH-06 §11.2 Steps 3-5), Spring wiring pattern (@ConditionalOnProperty), file naming convention, PGP key config • Add @apiNote Javadoc on ZeroPaySchemeAdapter: This adapter is Phase 2 pending KFTC spec (OI-SCH-01, OI-SCH-02); methods throw UnsupportedOperationException until then • Verify MODULE.md contains all five checklist steps | Updated SchemeAdapter.java Javadoc and services/scheme-adapter/MODULE.md | • SchemeAdapter.java Javadoc contains the ACL boundary warning on the interface declaration • Each of the 13 methods has @param and @return Javadoc • MODULE.md file exists at services/scheme-adapter/MODULE.md and is non-empty • MODULE.md checklist Step 3 references @ConditionalOnProperty naming pattern • ZeroPaySchemeAdapter class Javadoc references OI-SCH-01 | 30 | 9.1-T04, 9.1-T14, 9.1-T15 | ARCH | SCH-06
9.2-T01 | scheme-adapter-zeropay | 9.2 | 9. QR Scheme Integration (ZeroPay) | SFTP connectivity, keys, PGP | 2 | Gradle module setup: services/sftp-gateway build.gradle and application bootstrap | STACK.md: Gradle multi-module monorepo. The sftp-gateway service handles ZeroPay PPF egress via SFTP. Module must be declared in root settings.gradle with build.gradle specifying: spring-boot-starter-web, spring-boot-starter-security, spring-boot-starter-data-jpa, spring-cloud-vault-config, software.amazon.awssdk:s3, org.bouncycastle:bcpg-jdk18on, org.apache.sshd:sshd-sftp (Apache SSHD 2.x for Java 21 compatibility), spring-retry, micrometer-registry-prometheus, opentelemetry-api, lib-money, lib-errors, lib-events, lib-persistence. Test: spring-boot-testcontainers, testcontainers:postgresql, testcontainers:localstack, wiremock-standalone, junit-jupiter. Java 21 toolchain. | • Add include('services/sftp-gateway') to root settings.gradle if not present. • Create services/sftp-gateway/build.gradle with all dependencies; apply plugins: java, org.springframework.boot, io.spring.dependency-management; set java.toolchain.languageVersion = JavaLanguageVersion.of(21). • Create services/sftp-gateway/src/main/java/com/gme/pay/sftp/SftpGatewayApplication.java with @SpringBootApplication. • Create services/sftp-gateway/src/main/resources/application.yml with placeholder zeropay.sftp.* and zeropay.pgp.* config namespaces. • Run ./gradlew :services:sftp-gateway:compileJava and confirm zero errors; run ./gradlew :services:sftp-gateway:test with placeholder test. | services/sftp-gateway/build.gradle and services/sftp-gateway/src/main/java/com/gme/pay/sftp/SftpGatewayApplication.java | • ./gradlew :services:sftp-gateway:compileJava exits 0 with zero errors. • All declared dependencies resolve (no 'Could not resolve' in build output). • Java toolchain = 21 confirmed in build output. • SftpGatewayApplication annotated @SpringBootApplication in package com.gme.pay.sftp. • ./gradlew :services:sftp-gateway:test exits 0. | 25 |  | DevOps | SCH-06, SEC-09
9.2-T02 | scheme-adapter-zeropay | 9.2 | 9. QR Scheme Integration (ZeroPay) | SFTP connectivity, keys, PGP | 2 | Define SftpGatewayProperties @ConfigurationProperties with Vault-backed secret refs | SCH-06 §2.3 and SEC-09: all SFTP and PGP credentials are Vault references, never plaintext. Config namespace zeropay.sftp.*: host (String), port (int default 22), username (String), private_key_ref (Vault path), known_hosts_ref (Vault path for host-key pin), inbound_dir (default /gmepay/inbound/), outbound_dir (default /gmepay/outbound/), file_retention_days (int default 90), connect_timeout_ms (int default 30000), pool_max_connections (int default 3). Config namespace zeropay.pgp.*: scheme_public_key_ref (Vault path for hangulwon PGP public key), gme_private_key_ref (Vault path for GME PGP private key), gme_public_key_ref, use_armor (boolean default false), compression (ZLIB/ZIP/UNCOMPRESSED default ZLIB). All *_ref fields @NotBlank. No plaintext credential ever in application.yml or env vars. | • Create SftpGatewayProperties.java (@ConfigurationProperties(prefix=zeropay.sftp)) with all 10 fields and @Validated. • Create PgpProperties.java (@ConfigurationProperties(prefix=zeropay.pgp)) with all 5 fields and @Validated. • Add @Configuration SftpGatewayPropertiesConfig that @EnableConfigurationProperties for both classes. • Write SftpGatewayPropertiesTest: bind a properties file with valid values, assert all fields populated; bind with blank host, assert ConstraintViolationException. • Verify sftp_port defaults to 22 and file_retention_days defaults to 90 when not set. | services/sftp-gateway/src/main/java/com/gme/pay/sftp/config/SftpGatewayProperties.java and PgpProperties.java | • @NotBlank on host/username/private_key_ref/known_hosts_ref/pgp *_ref fields prevents startup with blank values. • sftp_port defaults to 22; file_retention_days defaults to 90. • ConstraintViolationException thrown when sftp_host is empty string. • PgpProperties.useArmor defaults to false and compression defaults to ZLIB. • Test passes with ./gradlew :services:sftp-gateway:test -Dtest=SftpGatewayPropertiesTest. | 30 | 9.2-T01 | DevOps | SCH-06, SEC-09
9.2-T03 | scheme-adapter-zeropay | 9.2 | 9. QR Scheme Integration (ZeroPay) | SFTP connectivity, keys, PGP | 2 | Flyway migrations V201-V203: sftp_transfer_log, sftp_file_archive, outbox_events tables | PostgreSQL 16 schema for SFTP Gateway. sftp_transfer_log: id BIGSERIAL PK, file_name VARCHAR(60) NOT NULL, direction VARCHAR(10) CHECK(IN('OUTBOUND','INBOUND')), file_type VARCHAR(10) NOT NULL, business_date DATE NOT NULL, sequence_no SMALLINT NOT NULL DEFAULT 1, transferred_at TIMESTAMPTZ, bytes_transferred BIGINT, checksum_sha256 CHAR(64), status VARCHAR(20) NOT NULL DEFAULT 'PENDING', retry_count SMALLINT NOT NULL DEFAULT 0, object_storage_key VARCHAR(512), error_message TEXT, created_at TIMESTAMPTZ NOT NULL DEFAULT now(). UNIQUE(file_type, business_date, sequence_no, direction). sftp_file_archive: id BIGSERIAL PK, transfer_log_id BIGINT NOT NULL REFERENCES sftp_transfer_log(id), bucket VARCHAR(100), object_key VARCHAR(512) NOT NULL, archived_at TIMESTAMPTZ NOT NULL DEFAULT now(), expires_at TIMESTAMPTZ, compliance_hold BOOLEAN NOT NULL DEFAULT FALSE, pgp_encrypted BOOLEAN NOT NULL DEFAULT TRUE. outbox_events: id UUID PK DEFAULT gen_random_uuid(), event_type VARCHAR(100) NOT NULL, aggregate_id VARCHAR(100), payload JSONB, status VARCHAR(20) NOT NULL DEFAULT 'PENDING', created_at TIMESTAMPTZ NOT NULL DEFAULT now(), published_at TIMESTAMPTZ. | • Create db/migration/V201__sftp_transfer_log.sql with sftp_transfer_log DDL including UNIQUE constraint and idx_stl_file_type_date index on (file_type, business_date). • Create db/migration/V202__sftp_file_archive.sql with sftp_file_archive DDL including FK to sftp_transfer_log. • Create db/migration/V203__sftp_outbox_events.sql with outbox_events DDL. • Run all three migrations via Flyway in order; verify clean apply on fresh Postgres 16 container. • Write Testcontainers migration test verifying V201-V203 apply in sequence with zero checksum errors. | db/migration/V201__sftp_transfer_log.sql, V202__sftp_file_archive.sql, V203__sftp_outbox_events.sql | • UNIQUE(file_type, business_date, sequence_no, direction) prevents duplicate transfer log entries. • FK sftp_file_archive.transfer_log_id -> sftp_transfer_log(id) enforced by DB. • Testcontainers migration test green (./gradlew :services:sftp-gateway:test -Dtest=SftpMigrationTest). • CHECK constraint on direction accepts only OUTBOUND or INBOUND. • outbox_events.payload column is JSONB type (not TEXT). | 30 | 9.2-T01 | DevOps | SCH-06, SEC-09
9.2-T04 | scheme-adapter-zeropay | 9.2 | 9. QR Scheme Integration (ZeroPay) | SFTP connectivity, keys, PGP | 2 | Implement Ed25519 SSH key-pair generation and Vault storage via SshKeyService | SEC-09 §2.5 and SCH-06 §2.3.1: GMEPay+ generates an Ed25519 key pair per environment (sandbox, production). Public key registered with hangulwon/KFTC for SFTP authentication. Private key stored in Vault at path zeropay/sftp/private_key - NEVER written to disk in plaintext. Key generation triggered by Admin API. Rotation: new pair written to zeropay/sftp/private_key_pending; old key at zeropay/sftp/private_key stays active until KFTC confirms new key. Rotation requires minimum 5 business-days lead time with KFTC (SEC-09 §9.3). Bouncy Castle used for key generation. RSA-4096 fallback if config use_rsa=true. | • Add SshKeyService.java (@Service) with generateKeyPair(KeyAlgorithm algo): KeyPairResult - stores private key PEM to Vault via VaultTemplate at zeropay/sftp/private_key_pending, returns public key PEM string. • Add KeyAlgorithm enum: ED25519 (default), RSA_4096. • Add getCurrentPublicKey(): String - reads from active Vault path zeropay/sftp/private_key, returns public key PEM. • Expose GET /internal/sftp/ssh-public-key (ADMIN role) returning current public key PEM for Ops to send to KFTC. • Write SshKeyServiceTest: generate Ed25519 pair, sign test data with private key, verify with public key; assert private key PEM never appears in log output. | services/sftp-gateway/src/main/java/com/gme/pay/sftp/security/SshKeyService.java | • Ed25519 key pair: private key is 32-byte scalar; public key is 32 bytes (verified via BouncyCastle API). • Private key PEM never written to logs (log capture assertion in test). • GET /internal/sftp/ssh-public-key returns 403 without ADMIN role (Spring Security mock). • generateKeyPair writes to _pending path; active path zeropay/sftp/private_key unchanged. • Sign-verify round-trip test passes with generated key pair. | 40 | 9.2-T02 | DevOps | SCH-06, SEC-09
9.2-T05 | scheme-adapter-zeropay | 9.2 | 9. QR Scheme Integration (ZeroPay) | SFTP connectivity, keys, PGP | 2 | Implement PGP key management service: import, Vault storage, and cache | SCH-06 §2.3.2: outbound files PGP-encrypted with hangulwon public key + signed with GME private key. Inbound files encrypted with GME public key + signed by hangulwon. GME PGP key pair: RSA-4096 preferred, RSA-2048 minimum. Key material stored in Vault (paths: zeropay/pgp/scheme_public_key, zeropay/pgp/gme_private_key, zeropay/pgp/gme_public_key). PgpKeyService loads keys from Vault on first call and caches in memory (refreshable). Ops uploads keys via Admin API. Library: org.bouncycastle:bcpg-jdk18on. No key material written to disk. | • Add PgpKeyService.java (@Service) with: importSchemePublicKey(byte[] armoredKey): void - stores to Vault zeropay/pgp/scheme_public_key; importGmeKeyPair(byte[] armoredPrivate, byte[] armoredPublic): void - stores to respective Vault paths; getSchemePublicKey(): PGPPublicKey; getGmeSecretKey(): PGPSecretKey. • Cache resolved keys in ConcurrentHashMap; expose reloadKeys(): void (flushes cache, forces next call to re-read Vault). • Expose POST /internal/sftp/pgp-keys/scheme-public (multipart, ADMIN role) and POST /internal/sftp/pgp-keys/gme-keypair (multipart, ADMIN role) endpoints. • Write PgpKeyServiceTest: import test RSA-4096 key pair, call getSchemePublicKey(), call getGmeSecretKey(), verify both non-null; test getSchemePublicKey() throws PgpKeyNotConfiguredException when Vault path empty. • Verify no key material bytes appear in application logs. | services/sftp-gateway/src/main/java/com/gme/pay/sftp/security/PgpKeyService.java | • getSchemePublicKey() throws PgpKeyNotConfiguredException when Vault path is empty. • After importSchemePublicKey, getSchemePublicKey() returns parsed PGPPublicKey with correct key ID. • POST endpoints return 403 without ADMIN role. • reloadKeys() flushes cache; subsequent getSchemePublicKey() re-reads Vault. • No armored key bytes appear in log output (log capture test). | 40 | 9.2-T02 | DevOps | SCH-06, SEC-09
9.2-T06 | scheme-adapter-zeropay | 9.2 | 9. QR Scheme Integration (ZeroPay) | SFTP connectivity, keys, PGP | 2 | Implement PGP encrypt+sign and decrypt+verify operations in PgpCryptoService | SCH-06 §2.3.2 and §2.4: outbound: PGP-encrypt with hangulwon public key AND sign with GME private key; inbound: decrypt with GME private key AND verify hangulwon signature. All operations in memory only - no cleartext intermediate files on disk. Bouncy Castle. Output: binary PGP packet (ASCII armor optional via PgpProperties.useArmor). Compression: ZLIB by default (PgpProperties.compression). The encrypted+signed output gets file extension .pgp appended (handled by naming tier T07). | • Add PgpCryptoService.java (@Service) with encryptAndSign(byte[] plaintext, String filename, PGPPublicKey recipientKey, PGPSecretKey signerKey, char[] passphrase): byte[] using BouncyCastle PGPEncryptedDataGenerator + PGPSignatureGenerator. • Add decryptAndVerify(byte[] pgpData, PGPSecretKey recipientKey, char[] passphrase, PGPPublicKey expectedSigner): byte[] - throws PgpVerificationException on signer mismatch or invalid signature. • Apply compression (PgpProperties.compression) and armor (PgpProperties.useArmor) based on injected PgpProperties. • Write PgpCryptoServiceTest: round-trip 50KB random bytes (encrypt+sign then decrypt+verify, assert input equals output); tamper 1 byte in ciphertext and assert PgpVerificationException. • Write negative tests: wrong recipient private key throws PgpDecryptionException; wrong expected signer public key throws PgpVerificationException. | services/sftp-gateway/src/main/java/com/gme/pay/sftp/security/PgpCryptoService.java | • 50KB round-trip test passes with RSA-4096 key pair. • Tampering 1 byte at offset 100 in ciphertext throws PgpVerificationException. • decryptAndVerify with wrong signer public key throws PgpVerificationException. • pgp_use_armor=true produces output starting with -----BEGIN PGP MESSAGE-----. • Empty payload (byte[0]) round-trips to byte[0] without exception. | 40 | 9.2-T05 | DevOps | SCH-06, SEC-09
9.2-T07 | scheme-adapter-zeropay | 9.2 | 9. QR Scheme Integration (ZeroPay) | SFTP connectivity, keys, PGP | 2 | Implement ZpFileName builder and parser for SCH-06 naming convention | SCH-06 §2.3.3: file naming pattern {FILE_ID}_{YYYYMMDD}_{SEQ}.dat.pgp where FILE_ID = ZeroPay file type code (e.g. ZP0011), YYYYMMDD = business date KST (UTC+9), SEQ = 2-digit zero-padded sequence starting at 01 (retransmission increments). Full example: ZP0011_20261015_01.dat.pgp. Parser must extract all three parts. ZpFileType enum: ZP0011, ZP0012, ZP0021, ZP0022, ZP0041, ZP0043, ZP0045, ZP0047, ZP0051, ZP0053, ZP0055, ZP0061, ZP0062, ZP0063, ZP0064, ZP0065, ZP0066 (17 codes total). Business date always in KST (ZoneId Asia/Seoul) regardless of server timezone. | • Create ZpFileType.java enum with all 17 codes and direction field (OUTBOUND/INBOUND per SCH-06 §8.1 table). • Create ZpFileName.java (immutable record): ZpFileType fileType, LocalDate businessDate, int sequenceNo; static of(ZpFileType, LocalDate, int), static parse(String filename), String toFileName(). • Builder validates: sequenceNo 1..99; throws ZpFileNameException for sequenceNo=0 or >99. • Parser validates regex ^(ZP[0-9]{4})_(\d{8})_(\d{2})\.dat\.pgp$ throws ZpFileNameException for non-match. • Write ZpFileNameTest: build ZP0011/2026-10-15/seq=1 -> ZP0011_20261015_01.dat.pgp; parse it back; verify retransmit(name) increments seq to 02; parse malformed name throws exception. | services/sftp-gateway/src/main/java/com/gme/pay/sftp/naming/ZpFileName.java and ZpFileType.java | • ZP0011_20261015_01.dat.pgp built correctly for fileType=ZP0011, date=2026-10-15, seq=1. • parse(ZP0011_20261015_01.dat.pgp).sequenceNo = 1, fileType = ZP0011, businessDate = 2026-10-15. • sequenceNo=0 throws ZpFileNameException; sequenceNo=100 throws ZpFileNameException. • ZpFileType enum has exactly 17 entries. • parse(ZP0011_2026101_01.dat.pgp) throws ZpFileNameException (wrong date length). | 25 |  | DevOps | SCH-06, SEC-09
9.2-T08 | scheme-adapter-zeropay | 9.2 | 9. QR Scheme Integration (ZeroPay) | SFTP connectivity, keys, PGP | 2 | Implement SFTP client with Apache SSHD, host-key pinning, and KnownHostsService | SEC-09 §2.5 and SCH-06 §2.3.1 and §2.4: GMEPay+ initiates all SFTP connections outbound-only to hangulwon SFTP server. Host key must be pinned (Vault path zeropay/sftp/known_hosts, OpenSSH known_hosts format). Mismatch throws SftpConnectionException(HOST_KEY_MISMATCH). Library: org.apache.sshd:sshd-sftp (Java 21 compatible). Connection pool: max 3 connections (zeropay.sftp.pool_max_connections). Connect timeout 30 000 ms (zeropay.sftp.connect_timeout_ms). Private key loaded from Vault (zeropay/sftp/private_key) via SshKeyService at session open time. | • Add KnownHostsService.java (@Service) with loadPinnedHostKey(): HostKeyEntry; isValid(String hostname, PublicKey serverKey): boolean; expose POST /internal/sftp/known-hosts (ADMIN) to update pin in Vault. • Add SftpClientFactory.java (@Component) building Apache SSHD SftpClient authenticated with Ed25519 key from SshKeyService; on connect verify host key via KnownHostsService.isValid; throw SftpConnectionException(HOST_KEY_MISMATCH) on mismatch. • SftpSession.java (AutoCloseable) wraps SftpClient; exposes put(InputStream, String remotePath): void; get(String remotePath): InputStream; exists(String remotePath): boolean; size(String remotePath): long. • Write SftpClientFactoryTest using Testcontainers (openssh container or WireMock SFTP stub): connect, put 1KB, get back, assert bytes equal; present wrong host key, assert HOST_KEY_MISMATCH exception. • Write KnownHostsServiceTest: valid known_hosts line -> isValid=true; modified key -> isValid=false. | services/sftp-gateway/src/main/java/com/gme/pay/sftp/client/SftpClientFactory.java and KnownHostsService.java | • Wrong host key throws SftpConnectionException with code HOST_KEY_MISMATCH (not a generic IOException). • put then size returns same byte count as uploaded stream. • Session is closed after try-with-resources (AutoCloseable). • POST /internal/sftp/known-hosts without ADMIN role returns 403. • loadPinnedHostKey() throws SftpGatewayException(KNOWN_HOSTS_NOT_CONFIGURED) when Vault path empty. | 50 | 9.2-T04, 9.2-T02 | DevOps | SCH-06, SEC-09
9.2-T09 | scheme-adapter-zeropay | 9.2 | 9. QR Scheme Integration (ZeroPay) | SFTP connectivity, keys, PGP | 2 | Implement ObjectStorageService: S3-compatible client, bucket lifecycle, and archival | STACK.md: Object Storage (S3-compatible) for ZeroPay SFTP files. Local dev: MinIO (docker-compose, endpoint http://minio:9000, bucket gme-zeropay). Prod: AWS S3 gme-zeropay-prod in ap-northeast-2 (Seoul, Korea data-residency per SAD-02 §10.4). AWS SDK v2 (software.amazon.awssdk:s3). Retention: 90 days configurable (file_retention_days), 7-year minimum for settlement evidence (SEC-09). Lifecycle: transition to STANDARD_IA after 90 days, GLACIER after 365, expire after 7*365=2555 days. Files stored PGP-encrypted (pgp_encrypted=true in sftp_file_archive). Archive key pattern: zeropay/batch/{direction}/{yyyy}/{MM}/{dd}/{filename}. | • Add ObjectStorageConfig.java (@Configuration) creating S3Client @Bean from zeropay.object-storage.* config (endpoint-override for MinIO, region, bucket). • Add ObjectStorageService.java (@Service) with: put(String key, byte[] data, Map<String,String> metadata): void; get(String key): byte[]; exists(String key): boolean. • On @PostConstruct: if bucket lifecycle not yet set, apply lifecycle rule via S3Client.putBucketLifecycleConfiguration (STANDARD_IA at 90d, GLACIER at 365d, expire at 2555d). • Add to docker-compose.yml: MinIO service with bucket creation init script for gme-zeropay if not present. • Write ObjectStorageServiceTest (Testcontainers MinIO): put then get round-trip for 1MB payload; exists returns false for absent key; bucket lifecycle rule set on startup. | services/sftp-gateway/src/main/java/com/gme/pay/sftp/storage/ObjectStorageService.java | • put then get returns byte-identical payload for 1MB test data. • exists returns false for non-existent key. • Bucket lifecycle rule: expire after 2555 days verified via S3Client.getBucketLifecycleConfiguration. • S3Client uses endpoint-override when zeropay.object-storage.endpoint-override is configured. • No AWS credentials appear in ObjectStorageConfig or application context log. | 35 | 9.2-T01 | DevOps | SCH-06, SEC-09
9.2-T10 | scheme-adapter-zeropay | 9.2 | 9. QR Scheme Integration (ZeroPay) | SFTP connectivity, keys, PGP | 2 | Implement outbound SFTP transfer pipeline: encrypt, upload, verify, archive to Object Storage | SCH-06 §2.4: outbound process: (1) content generated in memory, (2) PGP-encrypt with hangulwon public key + sign with GME private key, (3) SFTP put to /gmepay/outbound/{filename}, (4) verify by comparing remote file size with local encrypted size, (5) archive encrypted bytes to Object Storage at zeropay/batch/outbound/{yyyy}/{MM}/{dd}/{filename}, (6) persist sftp_transfer_log row (PostgreSQL) with status SUCCESS. Retry policy: up to 3 attempts with 5-minute intervals (Spring Retry); after 3 failures emit SftpTransferFailed Outbox event to outbox_events table in same @Transactional as sftp_transfer_log update. Sequence_no incremented on retransmission per SCH-06 §9.4. | • Add OutboundTransferService.java (@Service) with transferOutbound(ZpFileType, LocalDate businessDate, byte[] plaintext): TransferResult; builds ZpFileName, calls PgpCryptoService.encryptAndSign, calls SftpClientFactory. • On SFTP success: verify remote size == local encrypted size; archive to ObjectStorageService; persist sftp_transfer_log status=SUCCESS in @Transactional. • On failure: persist sftp_transfer_log status=FAILED, increment retry_count; RetryTemplate (Spring Retry, maxAttempts=3, fixedBackoff=300_000ms) wraps SFTP put+verify; after 3 failures publish SftpTransferFailed event to outbox_events in same @Transactional. • Write OutboundTransferServiceTest (Testcontainers Postgres + MinIO + WireMock SFTP): success path creates sftp_transfer_log SUCCESS row and Object Storage object; failure after 3 retries emits SftpTransferFailed event. • Verify @Transactional: mock exception after sftp_transfer_log insert, assert no Outbox row created (atomicity). | services/sftp-gateway/src/main/java/com/gme/pay/sftp/transfer/OutboundTransferService.java | • sftp_transfer_log row: direction=OUTBOUND, status=SUCCESS, object_storage_key set on happy path. • Remote size mismatch throws SftpTransferVerificationException and marks status=FAILED. • After 3 retries (retry_count=3) SftpTransferFailed event in outbox_events; no 4th SFTP attempt. • Object Storage key matches zeropay/batch/outbound/{yyyy}/{MM}/{dd}/{ZpFileName}. • Outbox write and sftp_transfer_log update are in one DB transaction (rollback test passes). | 55 | 9.2-T06, 9.2-T07, 9.2-T08, 9.2-T09, 9.2-T03 | DevOps | SCH-06, SEC-09
9.2-T11 | scheme-adapter-zeropay | 9.2 | 9. QR Scheme Integration (ZeroPay) | SFTP connectivity, keys, PGP | 2 | Implement inbound SFTP polling, download, decrypt+verify, archive | SCH-06 §2.4: inbound process: poll /gmepay/inbound/ for expected file, (1) download to in-memory buffer (no cleartext disk write), (2) verify size > 0, (3) PGP-decrypt with GME private key + verify hangulwon signature, (4) archive encrypted original to Object Storage at zeropay/batch/inbound/{yyyy}/{MM}/{dd}/{filename}, (5) persist sftp_transfer_log direction=INBOUND, (6) return plaintext bytes. If file not yet present: return Optional.empty() (no error; caller handles timing). On PgpVerificationException: persist status=FAILED, emit SftpInboundVerificationFailed Outbox event, return Optional.empty(). Poll schedule per SCH-06 §8.1: ZP0012 start 04:50 KST every 5 min until 06:00; ZP0062 from 09:00 every 10 min until 12:00; ZP0064 from 18:00 every 10 min until 21:00; merchant/QR sync hourly 01:00-08:00 KST. | • Add InboundTransferService.java (@Service) with fetchInbound(ZpFileType, LocalDate, int seqNo): Optional<byte[]>; uses SftpClientFactory.exists then get if present. • Archive encrypted bytes to ObjectStorageService; persist sftp_transfer_log direction=INBOUND in @Transactional. • PGP decrypt+verify via PgpCryptoService; on PgpVerificationException: persist FAILED, publish SftpInboundVerificationFailed to outbox_events. • Write InboundTransferServiceTest: mock SFTP returning encrypted test file (built with PgpCryptoService); assert decrypted plaintext correct; assert sftp_transfer_log INBOUND SUCCESS; assert tampered file emits verification failed event. • Verify Optional.empty() returned when SFTP exists() returns false. | services/sftp-gateway/src/main/java/com/gme/pay/sftp/transfer/InboundTransferService.java | • Returns Optional.empty() when file absent on remote (no exception thrown). • sftp_transfer_log: direction=INBOUND, status=SUCCESS, object_storage_key set on success. • Tampered ciphertext -> SftpInboundVerificationFailed in outbox_events and status=FAILED. • Decrypted plaintext equals original test payload. • Archive Object Storage key matches zeropay/batch/inbound/{yyyy}/{MM}/{dd}/{filename}. | 45 | 9.2-T06, 9.2-T08, 9.2-T10 | DevOps | SCH-06, SEC-09
9.2-T12 | scheme-adapter-zeropay | 9.2 | 9. QR Scheme Integration (ZeroPay) | SFTP connectivity, keys, PGP | 2 | Implement domain events in lib-events for SFTP Gateway | STACK.md messaging: transactional Outbox in PostgreSQL; Kafka deferred. All domain event schemas defined in lib-events (shared Gradle module). Events needed for WBS 9.2: SftpTransferFailedEvent (outbound after 3 retries), SftpInboundVerificationFailedEvent (PGP verify failure), BatchDeadlineMissedEvent (batch not completed by KST window), RegistrationExceptionEvent (ZP0012/ZP0022 result failure), AnomalousZp0012RecordEvent (ZP0012 record absent from GME DB), SettlementDiscrepancyEvent (ZP0062/ZP0064 amount mismatch), SettlementCompletedEvent (settlement cycle done, feeds partner webhook per API-05 settlement.completed), PrefundingReversalRequestedEvent (OVERSEAS refund confirmed). Each event implements DomainEvent interface (lib-events): String eventId (UUID), String eventType (constant), Instant occurredAt, String aggregateId, Map<String,Object> payload. | • Create lib-events/src/main/java/com/gme/pay/events/sftp/ package with one Java record per event (8 total), each implementing DomainEvent. • Each record: String eventId (auto UUID via static factory), String eventType (static final constant e.g. SFTP_TRANSFER_FAILED), Instant occurredAt, String aggregateId, Map<String,Object> payload. • Write JSON serialisation test for each event verifying ObjectMapper round-trip. • Register all 8 event type constants in EventTypeRegistry if it exists in lib-events. • Run ./gradlew :lib-events:test to confirm all tests green. | lib-events/src/main/java/com/gme/pay/events/sftp/ (8 event records) | • All 8 event records compile and serialise to valid JSON (ObjectMapper round-trip test). • Each has a distinct static eventType constant string (no collision; verify with set-deduplication test). • DomainEvent interface implemented by all 8 records. • ./gradlew :lib-events:test exits 0. • No two eventType constants are equal (uniqueness test on all 8 values). | 30 |  | DevOps | SCH-06, SEC-09
9.2-T13 | scheme-adapter-zeropay | 9.2 | 9. QR Scheme Integration (ZeroPay) | SFTP connectivity, keys, PGP | 2 | Implement OutboxEventPublisher writing to outbox_events table | STACK.md: Phase 1 uses transactional Outbox in PostgreSQL. EventPublisher interface (lib-events) abstracts the transport. sftp-gateway publishes via OutboxEventPublisher which inserts rows into outbox_events (V203 migration) in the same @Transactional as the primary DB operation. outbox_events columns: id UUID, event_type, aggregate_id, payload JSONB, status=PENDING, created_at. Kafka wiring is deferred; this ticket adds only the outbox-insertion publisher. An outbox-polling relay (separate concern) will later promote rows to Kafka. | • Add OutboxEventPublisher.java (@Service implementing EventPublisher from lib-events) that inserts into outbox_events via JdbcTemplate or Spring Data JPA repository in caller's existing @Transactional. • Serialize DomainEvent.payload Map to JSONB string via ObjectMapper. • Write OutboxEventPublisherTest (Testcontainers Postgres): publish SftpTransferFailedEvent; assert outbox_events row with status=PENDING and correct event_type. • Atomicity test: call publisher inside @Transactional, then throw RuntimeException; assert zero outbox_events rows (rollback confirmed). • Verify EventPublisher interface is the only import in callers (no direct Kafka or outbox_events table reference in OutboundTransferService). | services/sftp-gateway/src/main/java/com/gme/pay/sftp/events/OutboxEventPublisher.java | • outbox_events row created with status=PENDING, event_type correct, payload valid JSONB. • Rollback test: exception after publish -> zero outbox rows (atomic with primary operation). • EventPublisher interface (not OutboxEventPublisher directly) is what callers inject. • No Kafka dependency imported in sftp-gateway build.gradle. • Testcontainers test green. | 30 | 9.2-T12, 9.2-T03 | DevOps | SCH-06, SEC-09
9.2-T14 | scheme-adapter-zeropay | 9.2 | 9. QR Scheme Integration (ZeroPay) | SFTP connectivity, keys, PGP | 2 | Implement BatchJobService: aggregate transactions and generate ZP0011 payment result file | SCH-06 §5.2: ZP0011 (GME->ZP ~02:00 KST) fixed-width file. Header: file_type=ZP0011, business_date, GME institution_code, total_record_count, total_payout_amount_krw (KRW integer, 0 decimals). Detail per transaction (layout per SCH-06 §5.2 field list; exact widths TBD per OI-SCH-01 - implement via configurable FixedWidthFileBuilder): zeropay_txn_ref CHAR(20), gme_txn_id CHAR(20), merchant_id CHAR(10), txn_date DATE (YYYYMMDD), amount_krw NUMERIC(15,0), approval_code CHAR(10). Trailer: record_count repeated, control_sum = sum(amount_krw). Source: transactions table (PostgreSQL) WHERE status='APPROVED' AND settlement_date=:businessDate AND settlement_batch_id IS NULL. Exactly-once: set settlement_batch_id atomically in same @Transactional using SELECT...FOR UPDATE before SFTP upload. | • Add BatchJobService.java (@Service) with generateZp0011(LocalDate businessDate): byte[]; query transactions via TransactionRepository using SELECT t.* FROM transactions t WHERE t.settlement_date=:date AND t.status='APPROVED' AND t.settlement_batch_id IS NULL FOR UPDATE. • Claim rows: set settlement_batch_id (UUID for this batch run) on all included transactions in @Transactional; commit before SFTP upload. • Build header/detail/trailer via FixedWidthFileBuilder (new utility class same module); control_sum = sum(payout_amount_krw). • Call OutboundTransferService.transferOutbound(ZP0011, businessDate, bytes); persist settlement_batch row. • Write BatchJobServiceTest (Testcontainers Postgres): seed 5 transactions, call generateZp0011, assert header.record_count=5, trailer.control_sum=sum; re-run asserts 0 records (idempotent). | services/sftp-gateway/src/main/java/com/gme/pay/sftp/batch/BatchJobService.java (generateZp0011 method) | • header.total_payout_amount_krw = sum of all 5 detail record amounts. • trailer.control_sum = same sum value as header total. • Idempotency: second generateZp0011 call for same businessDate includes 0 transactions. • SELECT...FOR UPDATE prevents concurrent double-inclusion (Testcontainers concurrency test with 2 threads). • settlement_batch_id set on transaction rows in same @Transactional as file generation (mock SFTP failure - verify DB settlement_batch_id still set). | 55 | 9.2-T10, 9.2-T03 | DevOps | SCH-06, SEC-09
9.2-T15 | scheme-adapter-zeropay | 9.2 | 9. QR Scheme Integration (ZeroPay) | SFTP connectivity, keys, PGP | 2 | Implement BatchJobService: generate ZP0021 refund result file | SCH-06 §6.2: ZP0021 (GME->ZP ~02:00 KST) mirrors ZP0011 structure for refunds. Header: file_type=ZP0021, business_date, institution_code, record_count, total_refund_amount_krw. Detail: original_zeropay_txn_ref CHAR(20), gme_refund_id CHAR(20), merchant_id CHAR(10), refund_date DATE, refund_amount_krw NUMERIC(15,0) (stored as positive value in DB, written as negative in file per convention), refund_reason_code CHAR(4). Trailer: control_sum = sum(abs(refund_amount_krw)). Source: refunds table WHERE status='REFUND_PENDING' AND refund_date=:businessDate AND refund_batch_id IS NULL. State transition: REFUND_PENDING -> REFUND_SUBMITTED atomically with batch claim. Empty file (0 refunds) still transmitted with valid header+trailer (record_count=0, control_sum=0). | • Add generateZp0021(LocalDate businessDate): byte[] in BatchJobService; SELECT r.* FROM refunds r WHERE r.status='REFUND_PENDING' AND r.refund_date=:date AND r.refund_batch_id IS NULL FOR UPDATE. • Set refund_batch_id and status=REFUND_SUBMITTED in same @Transactional; build file via FixedWidthFileBuilder. • control_sum = sum(abs(refund_amount_krw)) for all detail records. • Call OutboundTransferService.transferOutbound(ZP0021, businessDate, bytes). • Write test: 3 REFUND_PENDING refunds; call generateZp0021; assert status=REFUND_SUBMITTED; control_sum correct; re-run asserts 0; assert empty file path (0 refunds) produces valid header record_count=0. | services/sftp-gateway/src/main/java/com/gme/pay/sftp/batch/BatchJobService.java (generateZp0021 method) | • REFUND_PENDING -> REFUND_SUBMITTED transition in same @Transactional. • Empty day (0 refunds): valid file with header file_type=ZP0021, record_count=0, trailer control_sum=0. • control_sum = sum(abs(refund_amount_krw)) for all detail records. • Idempotency: second call for same businessDate includes 0 records. • detail record refund_amount_krw values written as negative numbers in file bytes. | 40 | 9.2-T14 | DevOps | SCH-06, SEC-09
9.2-T16 | scheme-adapter-zeropay | 9.2 | 9. QR Scheme Integration (ZeroPay) | SFTP connectivity, keys, PGP | 2 | Implement ZP0012 parser and payment registration reconciliation | SCH-06 §5.3-§5.4: ZP0012 (ZP->GME ~05:00 KST) contains registration status per ZP0011 record. Match key: zeropay_txn_ref + txn_date. Outcomes: result_code=00 and amounts match -> SETTLEMENT_REGISTERED; non-zero result_code -> REGISTRATION_FAILED + RegistrationExceptionEvent; absent in ZP0012 (in ZP0011 but missing from ZP0012) -> REGISTRATION_UNKNOWN + RegistrationExceptionEvent; in ZP0012 but absent from GME DB -> AnomalousZp0012RecordEvent. Tolerance: zero (every record must match). After reconciliation: if any REGISTRATION_FAILED or REGISTRATION_UNKNOWN exist for businessDate, ZP0061 generation for that date is blocked. All transitions @Transactional. | • Add Zp0012Parser.java (@Component) parsing fixed-width ZP0012 bytes into List<Zp0012Record>; validate header file_type=ZP0012 and trailer record_count == parsed count (throws Zp0012ParseException on mismatch). • Add Zp0012ReconciliationService.java (@Service) with reconcile(LocalDate, byte[] zp0012Bytes): ReconciliationResult; line-by-line match against transactions with settlement_batch_id for businessDate. • Apply status transitions in batch UPDATE within single @Transactional; publish RegistrationExceptionEvent per FAILED and UNKNOWN record; publish AnomalousZp0012RecordEvent for ZP0012-extra records. • ReconciliationResult.blockedForSettlement = true if any REGISTRATION_FAILED count > 0. • Write Zp0012ReconciliationServiceTest (Testcontainers Postgres): 5 txns in ZP0011, ZP0012 has 4 (code=00) + 1 (code=01) + 1 extra; assert 4 SETTLEMENT_REGISTERED, 1 REGISTRATION_FAILED, 1 REGISTRATION_UNKNOWN (record 5 absent from ZP0012), 1 AnomalousZp0012RecordEvent, blockedForSettlement=true. | services/sftp-gateway/src/main/java/com/gme/pay/sftp/batch/reconcile/Zp0012ReconciliationService.java | • 5-txn test: 4 SETTLEMENT_REGISTERED, 1 REGISTRATION_FAILED, 1 REGISTRATION_UNKNOWN, 1 AnomalousZp0012RecordEvent in outbox. • Trailer record_count mismatch throws Zp0012ParseException. • ReconciliationResult.blockedForSettlement=true when REGISTRATION_FAILED count > 0. • All status transitions in one @Transactional (partial failure rollback test). • Amount mismatch in matching record -> REGISTRATION_AMOUNT_MISMATCH status + RegistrationExceptionEvent. | 50 | 9.2-T14, 9.2-T11, 9.2-T13 | DevOps | SCH-06, SEC-09
9.2-T17 | scheme-adapter-zeropay | 9.2 | 9. QR Scheme Integration (ZeroPay) | SFTP connectivity, keys, PGP | 2 | Implement ZP0022 parser and refund registration reconciliation | SCH-06 §6.3-§6.4: ZP0022 (ZP->GME ~05:00 KST) mirrors ZP0012 for refunds. Match key: original_zeropay_txn_ref + refund_date. Outcomes: result_code=00 -> REFUND_CONFIRMED; non-zero -> REFUND_FAILED + RefundRegistrationFailedEvent; absent -> REFUND_UNKNOWN. For OVERSEAS partners (partner.type=OVERSEAS): on REFUND_CONFIRMED, publish PrefundingReversalRequestedEvent (NOT direct DB update to prefunding - that is in Prefunding/Balance service). Unresolved refund failure blocking settlement is P1 incident. | • Add Zp0022Parser.java (@Component) parsing ZP0022 bytes; validate header file_type=ZP0022 and trailer count (throws Zp0022ParseException). • Add Zp0022ReconciliationService.java (@Service) with reconcile(LocalDate, byte[] zp0022Bytes): void; match refunds with refund_batch_id for date. • Transitions: REFUND_SUBMITTED -> REFUND_CONFIRMED or REFUND_FAILED; publish events via OutboxEventPublisher in same @Transactional. • PrefundingReversalRequestedEvent only when partner.type=OVERSEAS and result=CONFIRMED; LOCAL partners do not get this event. • Write Zp0022ReconciliationServiceTest: 3 REFUND_SUBMITTED (2 OVERSEAS + 1 LOCAL), ZP0022 has 2 success + 1 failure; assert 2 REFUND_CONFIRMED + 1 REFUND_FAILED + 1 RefundRegistrationFailedEvent + 2 PrefundingReversalRequestedEvents (both successful OVERSEAS refunds) + 0 for LOCAL. | services/sftp-gateway/src/main/java/com/gme/pay/sftp/batch/reconcile/Zp0022ReconciliationService.java | • OVERSEAS REFUND_CONFIRMED -> PrefundingReversalRequestedEvent in outbox (not direct DB update to prefunding table). • LOCAL REFUND_CONFIRMED -> NO PrefundingReversalRequestedEvent. • REFUND_FAILED + RefundRegistrationFailedEvent per failed record. • Zp0022ParseException on trailer count mismatch. • All transitions @Transactional (rollback test). | 40 | 9.2-T15, 9.2-T11, 9.2-T13 | DevOps | SCH-06, SEC-09
9.2-T18 | scheme-adapter-zeropay | 9.2 | 9. QR Scheme Integration (ZeroPay) | SFTP connectivity, keys, PGP | 2 | Implement ZP0061 morning settlement request file generation | SCH-06 §7.2 ZP0061 and NFR §5.3: ZP0061 (GME->ZP ~05:00 KST) after ZP0012 confirmed. Settlement totals for SETTLEMENT_REGISTERED transactions for prior business day. Header: file_type=ZP0061, business_date, institution_code, record_count, total_payout_krw. Detail per merchant: merchant_id CHAR(10), transaction_count INT, total_payout_amount NUMERIC(15,0), net_or_gross_flag CHAR(1) (N=net/domestic LOCAL partner, G=gross/international OVERSEAS partner). Trailer: control_sum. Prerequisite: ZP0011 status=SUCCESS AND ZP0012 received AND ReconciliationResult.blockedForSettlement=false. Exactly-once: set morning_batch_id on transaction rows in same @Transactional. Each payment transaction in exactly one settlement file (ZP0061 or ZP0063) - NFR §5.3. | • Add generateZp0061(LocalDate businessDate): byte[] in BatchJobService; SELECT transactions WHERE status='SETTLEMENT_REGISTERED' AND settlement_date=:date AND morning_batch_id IS NULL FOR UPDATE. • Validate prerequisite: sftp_transfer_log ZP0012 status=SUCCESS for businessDate AND Zp0012ReconciliationService.blockedForSettlement=false; else throw BatchPrerequisiteException. • Group by merchant_id; apply net/gross flag per partner.type; compute merchant totals. • Set morning_batch_id in same @Transactional; insert settlement_batch row; call OutboundTransferService.transferOutbound(ZP0061, ...). • Write test: 3 LOCAL + 2 OVERSEAS transactions across 2 merchants; assert net_or_gross_flag correct per merchant; assert prerequisite throws when ZP0012 absent. | services/sftp-gateway/src/main/java/com/gme/pay/sftp/batch/BatchJobService.java (generateZp0061 method) | • net_or_gross_flag=N for LOCAL partner merchant rows; G for OVERSEAS. • BatchPrerequisiteException when ZP0012 not status=SUCCESS in sftp_transfer_log. • total_payout_krw in header = sum of all merchant total_payout_amount values. • morning_batch_id set on all included transactions in same @Transactional. • Idempotency: second generateZp0061 call returns 0 records for same businessDate. | 50 | 9.2-T16, 9.2-T14 | DevOps | SCH-06, SEC-09
9.2-T19 | scheme-adapter-zeropay | 9.2 | 9. QR Scheme Integration (ZeroPay) | SFTP connectivity, keys, PGP | 2 | Implement ZP0062/ZP0064 parsers and settlement result reconciliation | SCH-06 §7.2 ZP0062 (ZP->GME ~10:00 KST) and ZP0064 (~19:00 KST): settlement result files confirming per-merchant settlement amounts. Reconciliation rule: for each merchant, sum(target_payout_krw) of SETTLEMENT_REGISTERED transactions in GME DB must equal merchant total in ZP0062/ZP0064. Tolerance: ZERO (1 KRW mismatch = SETTLEMENT_DISCREPANCY). On full match: SETTLEMENT_CONFIRMED + SettlementCompletedEvent (feeds partner settlement.completed webhook; payload must include batch_file_ref e.g. ZP0062-{businessDate}). On mismatch: SETTLEMENT_DISCREPANCY + SettlementDiscrepancyEvent per merchant. ZP0064 uses identical logic for afternoon batch (ZP0063 subset). | • Add Zp0062Parser.java and Zp0064Parser.java (@Component) parsing per-merchant result records; validate header file_type and trailer count (throw ZpSettlementResultParseException on mismatch). • Add SettlementResultReconciliationService.java (@Service) with reconcile(ZpFileType resultFileType, LocalDate, byte[] bytes): ReconciliationSummary. • Compute GME per-merchant totals from DB; compare to file totals; apply transitions in batch UPDATE + publish events in single @Transactional. • SettlementCompletedEvent.payload must include batch_file_ref, total_payout_krw, business_date (required by API-05 settlement.completed webhook). • Write test: Merchant A GME 500 000 KRW / ZP0062 500 000 (match) + Merchant B GME 200 000 / ZP0062 199 999 (1 KRW mismatch); assert 1 SettlementDiscrepancyEvent (B) + SettlementCompletedEvent present. | services/sftp-gateway/src/main/java/com/gme/pay/sftp/batch/reconcile/SettlementResultReconciliationService.java | • 1 KRW discrepancy triggers SETTLEMENT_DISCREPANCY + SettlementDiscrepancyEvent for that merchant. • Full match -> SETTLEMENT_CONFIRMED transitions and SettlementCompletedEvent published. • SettlementCompletedEvent.payload contains batch_file_ref=ZP0062-{businessDate}. • ZpSettlementResultParseException on file_type mismatch. • Idempotent: processing ZP0062 twice for same businessDate does not emit duplicate events. | 50 | 9.2-T18, 9.2-T11, 9.2-T13 | DevOps | SCH-06, SEC-09
9.2-T20 | scheme-adapter-zeropay | 9.2 | 9. QR Scheme Integration (ZeroPay) | SFTP connectivity, keys, PGP | 2 | Implement ZP0063 afternoon settlement request and ZP0065/ZP0066 detail files | SCH-06 §7.2: ZP0063 (14:00 KST) covers transactions approved after ZP0061 cutoff (04:30 KST) for same business day; same structure as ZP0061. ZP0065 (22:00 KST): transaction-level detail for ZP0061+ZP0063; one row per transaction: txn_id, merchant_id, txn_date, payout_amount_krw, zeropay_txn_ref, approval_code, settlement_batch_ref (link back to ZP0061 or ZP0063 file name). ZP0066 (22:00 KST): mirrors ZP0065 for refunds. Prerequisite ZP0063: morning cycle complete (ZP0062 received per sftp_transfer_log). Prerequisite ZP0065/ZP0066: both ZP0062 and ZP0064 received. Exactly-once for ZP0063: afternoon_batch_id on transactions. Each transaction in exactly one ZP006x detail file. | • Add generateZp0063(LocalDate): byte[] in BatchJobService; SELECT SETTLEMENT_REGISTERED WHERE morning_batch_id IS NULL AND afternoon_batch_id IS NULL FOR UPDATE; set afternoon_batch_id; guard on ZP0062 received. • Add generateZp0065(LocalDate): byte[] expanding all ZP0061+ZP0063 transactions to line-item detail; settlement_batch_ref = ZP0061 or ZP0063 file name per transaction.morning_batch_id/afternoon_batch_id. • Add generateZp0066(LocalDate): byte[] same structure for refunds in settlement batches. • Guard ZP0065/ZP0066: both ZP0062 and ZP0064 in sftp_transfer_log with status=SUCCESS; else BatchPrerequisiteException. • Write test: 5 morning + 2 afternoon transactions; assert ZP0065 has 7 detail rows; settlement_batch_ref correct per row; idempotency check. | services/sftp-gateway/src/main/java/com/gme/pay/sftp/batch/BatchJobService.java (generateZp0063, generateZp0065, generateZp0066 methods) | • ZP0063 includes only transactions with morning_batch_id IS NULL (no ZP0061 overlap). • ZP0065 detail record count = ZP0061 + ZP0063 transaction count for businessDate. • settlement_batch_ref in ZP0065 correctly references ZP0061 or ZP0063 file name per transaction. • ZP0063 throws BatchPrerequisiteException when ZP0062 not received. • Re-run of ZP0065 produces byte-identical output (regenerable from committed records). | 50 | 9.2-T19 | DevOps | SCH-06, SEC-09
9.2-T21 | scheme-adapter-zeropay | 9.2 | 9. QR Scheme Integration (ZeroPay) | SFTP connectivity, keys, PGP | 2 | Implement batch scheduler cron jobs for all ZP00xx outbound and inbound poll windows | SCH-06 §7.3 and §8.1: Spring @Scheduled cron jobs in zone Asia/Seoul (KST = UTC+9). Outbound triggers: ZP0011+ZP0021 at 01:30 KST, ZP0061 at 04:30 KST, ZP0063 at 13:30 KST, ZP0065+ZP0066 at 21:30 KST. Inbound pollers: ZP0012+ZP0022 start 04:50 KST every 5 min until 06:00 KST; ZP0062 start 09:00 KST every 10 min until 12:00 KST; ZP0064 start 18:00 KST every 10 min until 21:00 KST; merchant/QR sync ZP0041-ZP0055 hourly 01:00-08:00 KST. BatchWindowMonitor checks SLA deadlines and emits BatchDeadlineMissedEvent if job not completed in time. ZP0061 guarded: only runs if ZP0011 SUCCESS AND ZP0012 received AND not blocked. | • Add BatchScheduler.java (@Component) with @Scheduled(cron=..., zone=Asia/Seoul) methods for each outbound file; each delegates to BatchJobService and logs start/end/error. • Add inbound pollers as @Scheduled(fixedDelay) methods calling InboundTransferService.fetchInbound; each polls within its KST window, stops when file received or window expires. • ZP0061 scheduler: check sftp_transfer_log for ZP0011 SUCCESS + ZP0012 received + Zp0012ReconciliationService.blockedForSettlement=false before calling generateZp0061; if guard fails publish BatchDeadlineMissedEvent. • Add BatchWindowMonitor.java (@Component) with deadline check scheduled 5 min after each window close; emits BatchDeadlineMissedEvent if sftp_transfer_log status!=SUCCESS. • Write BatchSchedulerTest (unit, mock BatchJobService): verify ZP0011 cron = 01:30 Asia/Seoul; verify ZP0061 blocked when ZP0012 absent; verify BatchDeadlineMissedEvent published when ZP0011 not SUCCESS by 02:05 KST. | services/sftp-gateway/src/main/java/com/gme/pay/sftp/batch/BatchScheduler.java and BatchWindowMonitor.java | • ZP0011 cron expression evaluates to 01:30 Asia/Seoul (CronExpression.parse test). • ZP0061 NOT triggered when ZP0012 not received (mock sftp_transfer_log lookup returns null). • BatchDeadlineMissedEvent in outbox when ZP0011 not SUCCESS by 02:05 KST (mock clock). • Idempotent trigger: if sftp_transfer_log ZP0011 already SUCCESS for businessDate, scheduleZp0011Zp0021 logs WARN and skips. • Inbound poller stops polling once InboundTransferService returns non-empty Optional. | 45 | 9.2-T14, 9.2-T15, 9.2-T18, 9.2-T20, 9.2-T13 | DevOps | SCH-06, SEC-09
9.2-T22 | scheme-adapter-zeropay | 9.2 | 9. QR Scheme Integration (ZeroPay) | SFTP connectivity, keys, PGP | 2 | Implement file retention cleanup and compliance_hold guard | SCH-06 §2.3.5: files retained 90 days (configurable file_retention_days). SEC-09: SFTP batch file logs retained 7 years (settlement evidence). sftp_file_archive.expires_at is set at archive write time as archived_at + file_retention_days days. Compliance hold (compliance_hold=true) prevents expiry marking regardless of age. A scheduled cleanup job daily at 03:00 KST marks expired rows status=EXPIRED in sftp_file_archive where expires_at <= now() AND compliance_hold=false. Object Storage lifecycle rule (set in T09) handles physical deletion. RetentionCleanupService does NOT delete from Object Storage directly. | • Add RetentionCleanupService.java (@Service) with markExpiredArchives(): int - UPDATE sftp_file_archive SET status='EXPIRED' WHERE expires_at <= now() AND compliance_hold = FALSE; return rows affected. • Add status VARCHAR(20) NOT NULL DEFAULT 'ACTIVE' column to sftp_file_archive via db/migration/V204__sftp_file_archive_status.sql. • Schedule markExpiredArchives() daily at 03:00 KST via @Scheduled(cron=0 0 3 * * *, zone=Asia/Seoul). • In OutboundTransferService and InboundTransferService: at archive write time, set sftp_file_archive.expires_at = archived_at + SftpGatewayProperties.fileRetentionDays. • Write RetentionCleanupServiceTest (Testcontainers Postgres): 3 past-expires_at rows + 1 compliance_hold + 1 future; run markExpiredArchives(); assert 3 EXPIRED, compliance_hold untouched, future untouched. | db/migration/V204__sftp_file_archive_status.sql and services/sftp-gateway/src/main/java/com/gme/pay/sftp/storage/RetentionCleanupService.java | • compliance_hold=true rows never marked EXPIRED. • expires_at = archived_at + file_retention_days set correctly at archive time. • @Scheduled cron Asia/Seoul 03:00 KST (cron expression test). • Testcontainers test: 3 expired rows -> 3 EXPIRED; compliance_hold row status unchanged. • V204 migration applies cleanly on top of V203. | 35 | 9.2-T09, 9.2-T10, 9.2-T11 | DevOps | SCH-06, SEC-09
9.2-T23 | scheme-adapter-zeropay | 9.2 | 9. QR Scheme Integration (ZeroPay) | SFTP connectivity, keys, PGP | 2 | Implement SSH key rotation service: initiate, promote, retire procedure | SEC-09 §9.3: SFTP key rotation requires 5 business-day lead time with KFTC. Steps: (1) generate new Ed25519 pair stored at Vault zeropay/sftp/private_key_pending, (2) Ops extracts public key and registers with KFTC (manual), (3) on KFTC confirmation Ops promotes: _pending moves to active zeropay/sftp/private_key; old active archived to zeropay/sftp/private_key_previous for overlap window, (4) Ops retires: _previous deleted. Old key NOT revoked until KFTC confirms. Each step audit-logged: event_type=SSH_KEY_ROTATION_INITIATED/PROMOTED/RETIRED, actor, key_fingerprint, timestamp in audit_log table. | • Add SshKeyRotationService.java (@Service) with initiateRotation(): String publicKeyPem (generates new Ed25519 to _pending, returns public key); promoteRotation(String actorId): void (moves _pending to active, archives active to _previous); retirePreviousKey(String actorId): void (deletes _previous). • Guard: promoteRotation throws SshKeyRotationException(NO_PENDING_KEY) if _pending path empty; retirePreviousKey throws SshKeyRotationException(PENDING_KEY_EXISTS) if _pending still exists. • Persist audit_log row for each step with event_type, actor, key_fingerprint (SHA256 of public key bytes), timestamp. • Expose POST /internal/sftp/ssh-keys/rotate (initiateRotation), POST /internal/sftp/ssh-keys/promote, POST /internal/sftp/ssh-keys/retire-previous - all require ADMIN role. • Write SshKeyRotationServiceTest: full 3-step sequence; verify audit_log rows; verify promoting without initiating throws; verify retiring before promoting throws. | services/sftp-gateway/src/main/java/com/gme/pay/sftp/security/SshKeyRotationService.java | • initiateRotation: active Vault path unchanged; _pending path written. • promoteRotation: active path = new key; _previous path = old key; _pending deleted. • retirePreviousKey: throws SshKeyRotationException(PENDING_KEY_EXISTS) if _pending not empty. • 3 audit_log rows created with correct event_types and non-null key_fingerprints. • promoteRotation without prior initiate throws SshKeyRotationException(NO_PENDING_KEY). | 45 | 9.2-T04, 9.2-T08 | DevOps | SCH-06, SEC-09
9.2-T24 | scheme-adapter-zeropay | 9.2 | 9. QR Scheme Integration (ZeroPay) | SFTP connectivity, keys, PGP | 2 | Expose /internal/sftp/transfer-log and /internal/sftp/batch-status REST endpoints | Ops needs visibility into SFTP transfer state. GET /internal/sftp/transfer-log?businessDate=YYYY-MM-DD&fileType=ZP0011 returns List<SftpTransferLogDto> with all transfer attempts for that file on that date. GET /internal/sftp/batch-status?businessDate=YYYY-MM-DD returns BatchStatusSummary: one row per ZP file type showing expected direction, scheduled KST time, current status (PENDING/SUCCESS/FAILED/NOT_APPLICABLE), and lateness flag. Both endpoints secured by ADMIN or OPS role (Spring Security @PreAuthorize). Used by Admin portal Settlement batch view (PRD-07 §11.2.2). | • Add SftpTransferLogController.java (@RestController, @RequestMapping(/internal/sftp)) with getTransferLog(@RequestParam ZpFileType, @RequestParam LocalDate): List<SftpTransferLogDto>. • Add getBatchStatus(@RequestParam LocalDate): BatchStatusSummaryDto - queries sftp_transfer_log for the date and builds a summary row per all 17 ZpFileType entries (PENDING for those not yet created). • Add SftpTransferLogRepository (Spring Data JPA) with findByFileTypeAndBusinessDate. • Secure both methods with @PreAuthorize(hasAnyRole('ADMIN','OPS')). • Write SftpTransferLogControllerTest (@WebMvcTest): ADMIN role returns 200 with correct JSON; no auth returns 401; malformed businessDate returns 400; PARTNER role returns 403. | services/sftp-gateway/src/main/java/com/gme/pay/sftp/api/SftpTransferLogController.java | • GET with ADMIN JWT returns 200 and correct List<SftpTransferLogDto>. • GET without JWT returns 401. • Malformed businessDate (e.g. 20261015) returns 400 with error body. • getBatchStatus returns exactly 17 entries (one per ZpFileType) for the date. • PARTNER role JWT returns 403. | 35 | 9.2-T03, 9.2-T07 | DevOps | SCH-06, SEC-09
9.2-T25 | scheme-adapter-zeropay | 9.2 | 9. QR Scheme Integration (ZeroPay) | SFTP connectivity, keys, PGP | 2 | Implement SFTP connectivity test endpoint for Ops scheme configuration | PRD-07 §4.3.2 Connectivity Configuration: when Ops saves ZeroPay SFTP config, a Connectivity Test button verifies the connection. POST /internal/sftp/connectivity-test (ADMIN role) loads current SftpGatewayProperties, attempts SFTP connect with current Vault-stored credentials and known_hosts pin, attempts to list /gmepay/outbound/, returns ConnectivityTestResult {success: boolean, errorCode: String, errorMessage: String, latencyMs: long}. Timeout: 10 seconds. Any exception mapped to errorCode field (HOST_KEY_MISMATCH, CONNECTION_TIMEOUT, AUTH_FAILED, DIRECTORY_NOT_FOUND). | • Add ConnectivityTestService.java (@Service) with testConnectivity(): ConnectivityTestResult; opens SftpSession via SftpClientFactory, lists outbound directory, closes session; measures latencyMs; catches all exceptions and maps to ConnectivityTestResult.errorCode. • Apply 10-second timeout via CompletableFuture.get(10, TimeUnit.SECONDS) wrapping the SFTP operation. • Add ConnectivityTestController.java (@RestController) with POST /internal/sftp/connectivity-test; @PreAuthorize(hasRole('ADMIN')). • Write ConnectivityTestControllerTest (@WebMvcTest + WireMock SFTP): success returns {success:true, latencyMs>0}; wrong host key returns {success:false, errorCode:HOST_KEY_MISMATCH}; timeout returns {success:false, errorCode:CONNECTION_TIMEOUT}. • Verify ConnectivityTestService never throws unchecked exception to caller. | services/sftp-gateway/src/main/java/com/gme/pay/sftp/api/ConnectivityTestController.java | • Success: {success:true, latencyMs > 0} returned within 10 s. • HOST_KEY_MISMATCH error surfaced in ConnectivityTestResult.errorCode. • Timeout after 10 s: {success:false, errorCode:CONNECTION_TIMEOUT}. • OPS role (not ADMIN) returns 403 for POST /internal/sftp/connectivity-test. • No exception propagates out of ConnectivityTestService.testConnectivity(); all errors mapped to result. | 30 | 9.2-T08, 9.2-T23 | DevOps | SCH-06, SEC-09
9.2-T26 | scheme-adapter-zeropay | 9.2 | 9. QR Scheme Integration (ZeroPay) | SFTP connectivity, keys, PGP | 2 | Add OpenTelemetry and Prometheus metrics instrumentation for SFTP batch operations | STACK.md observability: OpenTelemetry traces/metrics/logs -> Prometheus + Grafana + Jaeger. Key SFTP metrics per SAD-02: SFTP batch delivery success rate, batch job duration, transfer byte count. Prometheus counters: sftp_transfers_total{fileType, direction, status} (incremented per transfer); sftp_transfer_bytes_total{fileType, direction} (total bytes). Gauge: sftp_batch_pending_count (count of PENDING rows in sftp_transfer_log for today). OTel span on each batch job: span name = batch.{fileType}.{direction}, attributes: fileType, businessDate, direction, bytes_transferred. Alert threshold per NFR: ZeroPay SFTP delivery failure triggers BatchDeadlineMissedEvent (already T21); Prometheus rule: sftp_transfers_total{status=FAILED} > 0 triggers alert. | • Add SftpMetrics.java (@Component) using Micrometer MeterRegistry: register Counter sftp_transfers_total with tags fileType, direction, status; register Counter sftp_transfer_bytes_total; register Gauge sftp_batch_pending_count. • Instrument OutboundTransferService.transferOutbound and InboundTransferService.fetchInbound with @WithSpan (opentelemetry-instrumentation-annotations) setting span attributes. • Increment counters in OutboundTransferService (SUCCESS/FAILED) and InboundTransferService; increment byte counter with bytes_transferred. • Register Prometheus scrape endpoint via spring-boot-actuator (management.endpoints.web.exposure.include=health,prometheus). • Write SftpMetricsTest: run OutboundTransferService mock success; assert sftp_transfers_total{fileType=ZP0011,direction=OUTBOUND,status=SUCCESS}.count() = 1; assert byte counter > 0. | services/sftp-gateway/src/main/java/com/gme/pay/sftp/observability/SftpMetrics.java | • sftp_transfers_total incremented with correct fileType, direction, status tags on each transfer. • sftp_transfer_bytes_total incremented with correct bytes_transferred value. • @WithSpan produces span with fileType and businessDate attributes (in-memory OTel SDK assertion). • sftp_batch_pending_count gauge reflects current count from sftp_transfer_log for today. • No PII or credential values in span attributes or metric tag values. | 35 | 9.2-T10, 9.2-T11 | DevOps | SCH-06, SEC-09
9.2-T27 | scheme-adapter-zeropay | 9.2 | 9. QR Scheme Integration (ZeroPay) | SFTP connectivity, keys, PGP | 2 | Unit tests: PGP edge cases - wrong key, empty payload, large payload, armored mode | Full edge-case coverage for PgpCryptoService beyond the basic round-trip in T06. Test cases: (1) decrypt with wrong private key -> PgpDecryptionException; (2) verify with wrong expected signer public key -> PgpVerificationException; (3) empty payload (byte[0]) round-trips to byte[0]; (4) 10 MB random payload round-trip completes under 5 seconds (no disk I/O); (5) corrupted PGP packet (random 100 bytes input to decryptAndVerify) -> PgpDecryptionException; (6) pgp_use_armor=true produces ASCII-armored output; (7) passphrase-protected GME private key (char[] passphrase supplied): decrypt succeeds with correct passphrase, PgpDecryptionException with wrong passphrase. | • Write PgpCryptoServiceEdgeCaseTest class in services/sftp-gateway test source. • Add testWrongPrivateKey, testSignerMismatch, testEmptyPayload, testLargePayload, testCorruptedInput, testArmoredOutput, testPassphraseProtection test methods. • Each test is fully independent (generates its own key pair; no static shared state). • Assert no temp files created during 10 MB test (File.listFiles on temp dir before vs after). • Run with ./gradlew :services:sftp-gateway:test -Dtest=PgpCryptoServiceEdgeCaseTest. | services/sftp-gateway/src/test/java/com/gme/pay/sftp/security/PgpCryptoServiceEdgeCaseTest.java | • Wrong private key -> PgpDecryptionException. • Wrong signer key -> PgpVerificationException. • Empty payload round-trips to byte[0] without exception. • 10 MB round-trip under 5 seconds with zero temp files created. • Armored output starts with -----BEGIN PGP MESSAGE-----. • Correct passphrase succeeds; wrong passphrase throws PgpDecryptionException. | 35 | 9.2-T06 | DevOps | SCH-06, SEC-09
9.2-T28 | scheme-adapter-zeropay | 9.2 | 9. QR Scheme Integration (ZeroPay) | SFTP connectivity, keys, PGP | 2 | Unit tests: ZP0011/ZP0021 file generation vectors with concrete KRW amounts | Concrete acceptance vectors for FixedWidthFileBuilder output. ZP0011 vector: 3 transactions with payout_amount_krw of 150000, 75000, 200000; business_date 2026-10-15; institution_code GME01. Expected: header record_count=3, total_payout_amount_krw=425000; 3 detail records with correct field values in correct byte positions; trailer control_sum=425000. File must be deterministic: same inputs always produce byte-identical output. ZP0021 vector: 2 refunds with refund_amount_krw 50000 and 30000; expected control_sum=80000 (sum of abs); detail values written as negative (-50000, -30000). | • Write Zp0011FileGenerationTest (Testcontainers Postgres): seed 3 transactions with amounts 150000/75000/200000, business_date=2026-10-15. • Call BatchJobService.generateZp0011(2026-10-15); capture returned byte[]. • Parse bytes via Zp0011Parser; assert header record_count=3, total_payout_amount_krw=425000; assert detail[0].amount=150000; assert trailer control_sum=425000. • Assert determinism: reset settlement_batch_id on all 3 rows (test utility), call generateZp0011 again; assert output byte-identical to first call. • Write Zp0021FileGenerationTest: 2 refunds 50000/30000; assert control_sum=80000; assert detail amounts are -50000 and -30000. | services/sftp-gateway/src/test/java/com/gme/pay/sftp/batch/Zp0011FileGenerationTest.java and Zp0021FileGenerationTest.java | • ZP0011 header.total_payout_amount_krw = 425000. • ZP0011 trailer.control_sum = 425000. • ZP0011 3 detail records with amounts 150000, 75000, 200000 at correct field positions. • Byte-identical output on repeat generation from same DB state. • ZP0021 control_sum = 80000; detail amounts written as -50000 and -30000. | 35 | 9.2-T14, 9.2-T15 | DevOps | SCH-06, SEC-09
9.2-T29 | scheme-adapter-zeropay | 9.2 | 9. QR Scheme Integration (ZeroPay) | SFTP connectivity, keys, PGP | 2 | Unit tests: ZP0012 reconciliation vectors covering all 4 outcome codes | Concrete test vectors for Zp0012ReconciliationService covering all 4 outcomes per SCH-06 §5.4: (A) result_code=00 amounts match -> SETTLEMENT_REGISTERED; (B) result_code=01 non-zero -> REGISTRATION_FAILED + RegistrationExceptionEvent; (C) record in ZP0011 absent from ZP0012 -> REGISTRATION_UNKNOWN + RegistrationExceptionEvent; (D) extra record in ZP0012 absent from GME DB -> AnomalousZp0012RecordEvent. Test vector: ZP0011 has 4 transactions (T1/T2/T3/T4); ZP0012 response has T1(code=00 match), T2(code=01 fail), T4_extra(no GME txn); T3 absent from ZP0012. Expected: 1 SETTLEMENT_REGISTERED (T1), 1 REGISTRATION_FAILED (T2), 1 REGISTRATION_UNKNOWN (T3), 1 AnomalousZp0012RecordEvent (T4_extra); blockedForSettlement=true. | • Seed DB with 4 APPROVED transactions in settlement_batch_id=batch1 for businessDate 2026-10-15 (Testcontainers Postgres). • Build synthetic ZP0012 bytes using Zp0012Builder (test utility): T1(code=00), T2(code=01), T4_extra(zeropay_txn_ref=UNKNOWN999, code=00). • Call Zp0012ReconciliationService.reconcile(2026-10-15, zp0012Bytes). • Assert T1.status=SETTLEMENT_REGISTERED; T2.status=REGISTRATION_FAILED; T3.status=REGISTRATION_UNKNOWN; T4_extra generates AnomalousZp0012RecordEvent in outbox_events. • Assert ReconciliationResult.blockedForSettlement=true (REGISTRATION_FAILED count>0). | services/sftp-gateway/src/test/java/com/gme/pay/sftp/batch/reconcile/Zp0012ReconciliationTest.java | • T1 -> SETTLEMENT_REGISTERED. • T2 -> REGISTRATION_FAILED + RegistrationExceptionEvent in outbox_events. • T3 -> REGISTRATION_UNKNOWN + RegistrationExceptionEvent in outbox_events. • T4_extra -> AnomalousZp0012RecordEvent in outbox_events; T4 GME row status unchanged. • blockedForSettlement=true when REGISTRATION_FAILED count > 0. | 35 | 9.2-T16 | DevOps | SCH-06, SEC-09
9.2-T30 | scheme-adapter-zeropay | 9.2 | 9. QR Scheme Integration (ZeroPay) | SFTP connectivity, keys, PGP | 2 | Unit tests: SettlementDiscrepancy zero-tolerance and SettlementCompleted event vector | Concrete test vectors for SettlementResultReconciliationService. Two merchants: Merchant A GME total 500000 KRW / ZP0062 total 500000 KRW (exact match -> SETTLEMENT_CONFIRMED); Merchant B GME total 200000 KRW / ZP0062 total 199999 KRW (1 KRW mismatch -> SETTLEMENT_DISCREPANCY). Expected: SettlementCompletedEvent published with batch_file_ref=ZP0062-2026-10-15 and total_payout_krw=500000 (confirmed merchant only); SettlementDiscrepancyEvent for Merchant B with difference_krw=1. Verify idempotency: processing same ZP0062 bytes twice does not create duplicate events. | • Seed DB with morning batch transactions for Merchant A (total 500000 KRW) and Merchant B (total 200000 KRW) in status=SETTLEMENT_REGISTERED (Testcontainers Postgres). • Build synthetic ZP0062 bytes: Merchant A total=500000, Merchant B total=199999. • Call SettlementResultReconciliationService.reconcile(ZP0062, 2026-10-15, bytes). • Assert Merchant A -> SETTLEMENT_CONFIRMED; Merchant B -> SETTLEMENT_DISCREPANCY. • Assert exactly 1 SettlementDiscrepancyEvent in outbox_events with payload.difference_krw=1; assert SettlementCompletedEvent present with correct batch_file_ref; call reconcile again and assert no additional events (idempotency). | services/sftp-gateway/src/test/java/com/gme/pay/sftp/batch/reconcile/SettlementDiscrepancyTest.java | • 1 KRW discrepancy -> SETTLEMENT_DISCREPANCY for Merchant B; SettlementDiscrepancyEvent.payload.difference_krw=1. • Merchant A -> SETTLEMENT_CONFIRMED. • SettlementCompletedEvent.payload.batch_file_ref=ZP0062-2026-10-15. • SettlementCompletedEvent.payload.total_payout_krw=500000 (Merchant A only). • Second reconcile call produces 0 new outbox events (idempotent). | 35 | 9.2-T19 | DevOps | SCH-06, SEC-09
9.2-T31 | scheme-adapter-zeropay | 9.2 | 9. QR Scheme Integration (ZeroPay) | SFTP connectivity, keys, PGP | 2 | Integration test: full ZP0011->ZP0012->ZP0061 batch pipeline round-trip | End-to-end integration test for the core payment batch pipeline using Testcontainers (Postgres 16, MinIO) and WireMock SFTP server. Test scenario: (1) seed 5 APPROVED transactions; (2) trigger generateZp0011 (WireMock SFTP accepts put); (3) inject synthetic ZP0012 all success (result_code=00); (4) call Zp0012ReconciliationService.reconcile; (5) trigger generateZp0061; (6) assert full DB state chain. Verifies the primary settlement pipeline works end-to-end in isolation from the scheduler. | • Set up @SpringBootTest with @Container Testcontainers Postgres 16 and MinIO; configure WireMock SFTP stub to accept put and return success. • Seed 5 APPROVED transactions via TransactionRepository.saveAll; call batchJobService.generateZp0011(today). • Build ZP0012 bytes (all 5 result_code=00); call inboundTransferService.fetchInbound mock; call reconciliationService.reconcile. • Call batchJobService.generateZp0061(today). • Assert: all 5 transactions SETTLEMENT_REGISTERED; sftp_transfer_log has ZP0011 and ZP0061 rows both status=SUCCESS; Object Storage (MinIO) contains both files; settlement_batch row created; 0 events in outbox_events. | services/sftp-gateway/src/test/java/com/gme/pay/sftp/integration/SftpBatchPipelineIntegrationTest.java | • All 5 transactions have settlement_batch_id set after generateZp0011. • All 5 transactions SETTLEMENT_REGISTERED after reconcile. • sftp_transfer_log ZP0011 and ZP0061 both status=SUCCESS. • Object Storage (MinIO) contains 2 objects at expected keys. • outbox_events table has 0 rows (no failures). | 55 | 9.2-T18, 9.2-T22, 9.2-T10, 9.2-T11 | DevOps | SCH-06, SEC-09
9.2-T32 | scheme-adapter-zeropay | 9.2 | 9. QR Scheme Integration (ZeroPay) | SFTP connectivity, keys, PGP | 2 | Integration test: retry exhaustion and SftpTransferFailed Outbox event | Test that OutboundTransferService emits SftpTransferFailed after 3 failed SFTP attempts and that transactions still have settlement_batch_id set (file can be regenerated from committed records per NFR §6.5). WireMock SFTP configured to reject all put() calls. After failure, simulate SFTP recovery and re-run generateZp0011: verify same settlement_batch_id used (no double-inclusion since transactions already claimed). | • Configure WireMock SFTP to return IOException on all put() calls. • Seed 3 APPROVED transactions; call batchJobService.generateZp0011(today); assert 3 SFTP attempts made (WireMock verify 3 invocations). • Assert sftp_transfer_log: status=FAILED, retry_count=3. • Assert SftpTransferFailed event in outbox_events with payload.fileType=ZP0011. • Configure WireMock to accept put; clear failed transfer log row; call generateZp0011 again; verify file generated with same 3 transactions (idempotent re-inclusion allowed since settlement_batch_id was not preserved on FAILED path - re-query finds IS NULL still); assert sftp_transfer_log new SUCCESS row. | services/sftp-gateway/src/test/java/com/gme/pay/sftp/integration/SftpTransferFailureTest.java | • Exactly 3 SFTP put() attempts (WireMock verify(exactly(3), putRequest)). • sftp_transfer_log retry_count=3, status=FAILED. • SftpTransferFailed Outbox event in outbox_events with payload.fileType=ZP0011. • After SFTP recovery + re-run: new sftp_transfer_log row status=SUCCESS. • Testcontainers Postgres and WireMock SFTP used (no mocks via Mockito for infrastructure). | 45 | 9.2-T10, 9.2-T13, 9.2-T31 | DevOps | SCH-06, SEC-09
9.2-T33 | scheme-adapter-zeropay | 9.2 | 9. QR Scheme Integration (ZeroPay) | SFTP connectivity, keys, PGP | 2 | Security tests: PGP signature rejection and SFTP path traversal guard | SEC-09 §3 threat model T-06: settlement file tampering. OWASP API10: defensive validation on all inbound batch files. Two security tests: (1) inbound file with tampered ciphertext (1 byte mutated) must trigger PgpVerificationException -> SftpInboundVerificationFailed Outbox event -> NO DB status updates (transaction status unchanged); (2) SFTP path traversal: for all 17 ZpFileType values, constructed remote paths must start with /gmepay/ and contain no ../ sequence; InboundTransferService must reject any injected path with ../ characters. | • Write PgpSignatureRejectionTest: build valid ZP0012 file encrypted+signed with test keys; mutate byte at offset 100 in ciphertext; call InboundTransferService.fetchInbound with tampered bytes; assert Optional.empty() returned; assert SftpInboundVerificationFailed in outbox_events; assert zero transaction status changes. • Write SftpPathTraversalTest: for each ZpFileType, call the remote path construction logic and assert result starts with /gmepay/inbound/ or /gmepay/outbound/ and contains no ../. • Write SftpPathInjectionTest: directly call InboundTransferService with a crafted remotePath containing ../ and assert SftpPathTraversalException thrown. • Assert SftpInboundVerificationFailed event payload.verificationError is non-empty. • Run tests with ./gradlew :services:sftp-gateway:test. | services/sftp-gateway/src/test/java/com/gme/pay/sftp/security/PgpSignatureRejectionTest.java and SftpPathTraversalTest.java | • Tampered ciphertext -> SftpInboundVerificationFailed event in outbox; no DB transaction status changes. • All 17 ZpFileType remote paths start with /gmepay/ (path traversal impossible via file type enum). • ../ in injected remotePath throws SftpPathTraversalException. • SftpInboundVerificationFailed payload.verificationError is non-empty string. • No SFTP credentials or key material in exception messages. | 40 | 9.2-T11, 9.2-T06, 9.2-T12 | DevOps | SCH-06, SEC-09
9.2-T34 | scheme-adapter-zeropay | 9.2 | 9. QR Scheme Integration (ZeroPay) | SFTP connectivity, keys, PGP | 2 | Document SFTP Gateway ops runbook: key rotation, batch SLAs, escalation, retention | SEC-09 §9.3, SCH-06 §9.4, and NFR §2.3: Ops requires a runbook covering: (1) SSH key rotation (Ed25519 generation, 5 business-day KFTC lead time, promote/retire steps via Admin portal /internal/sftp/ssh-keys/* endpoints); (2) PGP key refresh (upload new hangulwon public key and GME key pair via /internal/sftp/pgp-keys/* endpoints; all operations in-memory only); (3) batch window SLA table (all 10 outbound file types with KST times and P1/P2 incident priorities per SCH-06 §9.4); (4) SFTP failure escalation (retry logic: 3x at 5-min intervals, then P1 alert + manual re-transmit steps); (5) file retention policy (90-day default configurable via file_retention_days, 7-year settlement archive, compliance_hold flag prevents deletion). This is an explicitly requested ops documentation artifact. | • Create docs/ops/sftp-gateway-runbook.md with sections: 1. SSH Key Rotation, 2. PGP Key Refresh, 3. Batch Window SLA Table, 4. SFTP Failure Escalation, 5. File Retention Policy. • Section 1: 3-step procedure (initiate, promote, retire); note 5-business-day KFTC lead time; warn do not revoke old key until KFTC confirms. • Section 3: table of all outbound file types with KST scheduled time, P1/P2 priority, and internal deadline (ZP0011 internal complete by 01:30 KST, due 02:00 KST). • Section 4: retry policy (3x, 5-min interval); manual re-transmit using POST /internal/sftp/transfer-log/{id}/retransmit (stub described, to be wired later). • Section 5: compliance_hold=true use case; note 7-year minimum for settlement evidence files. | docs/ops/sftp-gateway-runbook.md | • File exists at docs/ops/sftp-gateway-runbook.md. • Section 1 includes the 5-business-day KFTC lead time warning explicitly. • Section 3 table covers all 10 outbound ZP file types with correct KST times and priorities. • Section 2 states all PGP operations in-memory only (no cleartext temp files on disk). • Section 5 states 7-year minimum retention for settlement evidence files. | 25 | 9.2-T23, 9.2-T24, 9.2-T25 | DevOps | SCH-06, SEC-09
9.3-T01 | merchant-qr-data | 9.3 | 9. QR Scheme Integration (ZeroPay) | Merchant & QR synchronization | 2 | Flyway migration V1: merchant, qr_code, franchise_groups, merchant_sync_log tables | WBS 9.3 Merchant and QR Synchronisation. The merchant-qr-data service (Gradle module services/merchant-qr-data) owns a PostgreSQL 16 canonical store. Tables: merchant (id BIGSERIAL PK, merchant_id VARCHAR(50) UNIQUE NOT NULL, merchant_type VARCHAR(30), name VARCHAR(200), business_registration_no VARCHAR(30), franchise_code VARCHAR(30), category_code VARCHAR(20), bank_code VARCHAR(10), account_no VARCHAR(30) [AES-256 encrypted at rest via app layer], fee_tier VARCHAR(20), status VARCHAR(20) CHECK IN (ACTIVE,SUSPENDED,DEACTIVATED), is_active BOOLEAN NOT NULL DEFAULT TRUE, is_franchise BOOLEAN NOT NULL DEFAULT FALSE, synced_at TIMESTAMPTZ, created_at TIMESTAMPTZ NOT NULL DEFAULT now(), updated_at TIMESTAMPTZ NOT NULL DEFAULT now()); qr_code (id BIGSERIAL PK, qr_code_id VARCHAR(20) UNIQUE NOT NULL, merchant_id BIGINT FK->merchant(id), qr_type CHAR(1) CHECK IN (M,C), status VARCHAR(20) CHECK IN (ACTIVE,DEACTIVATED), is_active BOOLEAN NOT NULL DEFAULT TRUE, issue_date DATE, deactivation_date DATE, synced_at TIMESTAMPTZ, created_at TIMESTAMPTZ NOT NULL DEFAULT now(), updated_at TIMESTAMPTZ NOT NULL DEFAULT now()); franchise_groups (id BIGSERIAL PK, franchise_code CHAR(6) UNIQUE NOT NULL, franchise_name VARCHAR(100), franchise_type CHAR(2), head_merchant_id VARCHAR(50), status CHAR(1), created_at TIMESTAMPTZ NOT NULL DEFAULT now(), updated_at TIMESTAMPTZ NOT NULL DEFAULT now()); merchant_sync_log (id BIGSERIAL PK, file_type VARCHAR(10), sync_date DATE, records_received INT, records_inserted INT, records_updated INT, records_deactivated INT, error_count INT, status VARCHAR(20) CHECK IN (SUCCESS,PARTIAL,FAILED), detail TEXT, created_at TIMESTAMPTZ NOT NULL DEFAULT now()). account_no encryption is at the application layer; column type is VARCHAR(30). | • Create services/merchant-qr-data/src/main/resources/db/migration/V1__merchant_qr_schema.sql • Add merchant table DDL with all columns and CHECK constraints as described • Add qr_code table DDL with FK to merchant(id), UNIQUE on qr_code_id • Add franchise_groups table DDL with UNIQUE on franchise_code • Add merchant_sync_log table DDL with CHECK on status • Add indexes: merchant(status), merchant(franchise_code), qr_code(merchant_id), qr_code(status) • Validate with Flyway in Testcontainers PostgreSQL 16 via ./gradlew :merchant-qr-data:flywayValidate | services/merchant-qr-data/src/main/resources/db/migration/V1__merchant_qr_schema.sql | • Flyway applies V1 on a fresh PostgreSQL 16 Testcontainers instance with zero errors • merchant table has UNIQUE constraint on merchant_id and CHECK constraint on status • qr_code.merchant_id FK references merchant(id) and is NOT NULL • merchant_sync_log.status column rejects values outside SUCCESS/PARTIAL/FAILED • account_no is VARCHAR(30) - no plain-text storage constraint; encryption enforced at service layer | 35 |  | BE | SCH-06
9.3-T02 | merchant-qr-data | 9.3 | 9. QR Scheme Integration (ZeroPay) | Merchant & QR synchronization | 2 | Flyway migration V2: merchant_staging, qr_code_staging, franchise_groups_staging, staging_run tables | WBS 9.3. ZP0051 (full merchant), ZP0055 (franchise full), ZP0053 (full QR) use staging+diff+atomic-promote to prevent partial overwrites of live data. Staging tables mirror their live counterparts plus a staging_run_id BIGINT NOT NULL column. staging_run table: (id BIGSERIAL PK, file_type VARCHAR(10) NOT NULL, business_date DATE NOT NULL, record_count INT, status VARCHAR(20) DEFAULT PENDING, created_at TIMESTAMPTZ NOT NULL DEFAULT now()). Full-sync failure must rollback entirely leaving live tables intact; staging tables are cleared on rollback. All in services/merchant-qr-data. | • Create services/merchant-qr-data/src/main/resources/db/migration/V2__merchant_qr_staging.sql • Add merchant_staging with same non-PK columns as merchant plus staging_run_id BIGINT NOT NULL • Add qr_code_staging with same non-PK columns as qr_code plus staging_run_id BIGINT NOT NULL • Add franchise_groups_staging mirroring franchise_groups plus staging_run_id BIGINT NOT NULL • Add staging_run table as specified • Confirm V2 applies after V1 in Testcontainers Flyway sequence | services/merchant-qr-data/src/main/resources/db/migration/V2__merchant_qr_staging.sql | • V2 applies cleanly after V1 with no errors on PostgreSQL 16 Testcontainers • merchant_staging has staging_run_id NOT NULL and same non-PK columns as merchant • staging_run table exists with status DEFAULT PENDING • Rolling back a transaction that inserted into merchant_staging leaves staging table empty (JUnit 5 @Transactional rollback test) • merchant table unaffected by merchant_staging inserts that are rolled back | 25 | 9.3-T01 | BE | SCH-06
9.3-T03 | merchant-qr-data | 9.3 | 9. QR Scheme Integration (ZeroPay) | Merchant & QR synchronization | 2 | Flyway migration V3: merchant_sync_log index, V4: outbox_events table | WBS 9.3. V3 adds a composite index on merchant_sync_log(file_type, sync_date) to support the idempotency guard query. V4 adds the transactional outbox table for domain events (per STACK.md Phase 1 outbox pattern, Kafka behind interface). outbox_events: (id UUID PK DEFAULT gen_random_uuid(), event_type VARCHAR(100) NOT NULL, aggregate_id VARCHAR(100), payload JSONB NOT NULL, status VARCHAR(20) NOT NULL DEFAULT PENDING, created_at TIMESTAMPTZ NOT NULL DEFAULT now(), processed_at TIMESTAMPTZ). Index on outbox_events(status, created_at) for polling. All in services/merchant-qr-data. | • Create V3__merchant_sync_log_index.sql: CREATE INDEX CONCURRENTLY idx_merchant_sync_log_file_date ON merchant_sync_log(file_type, sync_date) • Create V4__outbox_events.sql: CREATE TABLE outbox_events with id UUID PK, event_type, aggregate_id, payload JSONB, status VARCHAR(20) DEFAULT PENDING, created_at, processed_at • Add index idx_outbox_events_status_created on outbox_events(status, created_at) • Confirm V3 then V4 apply in sequence on Testcontainers | services/merchant-qr-data/src/main/resources/db/migration/V3__merchant_sync_log_index.sql and V4__outbox_events.sql | • V3 creates idx_merchant_sync_log_file_date visible in pg_indexes • V4 creates outbox_events with payload JSONB type (not TEXT) • outbox_events.id column type is UUID with DEFAULT gen_random_uuid() • Both migrations apply in sequence without error on Testcontainers PostgreSQL 16 • outbox_events status column has DEFAULT PENDING | 25 | 9.3-T01 | BE | SCH-06
9.3-T04 | merchant-qr-data | 9.3 | 9. QR Scheme Integration (ZeroPay) | Merchant & QR synchronization | 2 | Flyway migration V5: ShedLock table for distributed sync-job locking | WBS 9.3. The daily merchant sync Spring @Scheduled job in services/zeropay-adapter must not run concurrently across multiple pod replicas (Kubernetes). ShedLock with PostgreSQL JdbcTemplateLockProvider prevents this. ShedLock requires table: shedlock (name VARCHAR(64) NOT NULL, lock_until TIMESTAMP(3) NOT NULL, locked_at TIMESTAMP(3) NOT NULL, locked_by VARCHAR(255) NOT NULL, CONSTRAINT PK_shedlock PRIMARY KEY (name)). Migration lives in services/zeropay-adapter or services/merchant-qr-data (whichever DB the adapter uses); use merchant-qr-data DB for consolidation. | • Create services/merchant-qr-data/src/main/resources/db/migration/V5__shedlock.sql • Add shedlock table DDL exactly as ShedLock library requires • Add ShedLock dependency to services/zeropay-adapter/build.gradle: net.javacrumbs.shedlock:shedlock-spring and shedlock-provider-jdbc-template • Add LockProvider @Bean in ZeroPayAdapterConfig.java using JdbcTemplateLockProvider pointing to DataSource • Confirm V5 applies after V4 | services/merchant-qr-data/src/main/resources/db/migration/V5__shedlock.sql and services/zeropay-adapter/src/main/java/com/gme/pay/zeropay/config/ZeroPayAdapterConfig.java (LockProvider bean) | • V5 applies cleanly after V4 on Testcontainers • shedlock table has PRIMARY KEY on name column • LockProvider bean is of type JdbcTemplateLockProvider • Two concurrent Spring context test instances cannot both acquire lock zeropay-merchant-sync simultaneously (ShedLock integration test) • ShedLock dependency appears in services/zeropay-adapter/build.gradle | 25 | 9.3-T03 | BE | SCH-06
9.3-T05 | merchant-qr-data | 9.3 | 9. QR Scheme Integration (ZeroPay) | Merchant & QR synchronization | 2 | Define SyncRecord POJOs and ZpFileType enum for ZP0041/43/45/47/51/53/55 in zeropay-adapter | WBS 9.3. Parsed file records are typed Java records. Place in services/zeropay-adapter/src/main/java/com/gme/pay/zeropay/batch/model/. MerchantSyncRecord fields: merchantId (String 10), merchantName (String 100), businessRegNo (String 10), merchantTypeCode (String 2), statusCode (char: A/S/T), address (String 200), bankCode (String 3), accountNo (String 20), effectiveDate (LocalDate), changeType (char: I/U/D). FranchiseMerchantSyncRecord: same plus franchiseCode (String 6). FranchiseGroupSyncRecord: franchiseCode (String 6), franchiseName (String 100), franchiseType (String 2), headMerchantId (String 10), statusCode (char: A/S/T), changeType (char: I/U/D). QrSyncRecord: qrCodeId (String 20), merchantId (String 10), qrType (char: M/C), statusCode (char: A/D), issueDate (LocalDate), deactivationDate (LocalDate nullable), changeType (char: I/D). All implement marker interface SyncRecord. ZpFileType enum: ZP0041, ZP0043, ZP0045, ZP0047, ZP0051, ZP0053, ZP0055 with boolean isFullSync(). | • Create SyncRecord.java marker interface in the batch/model package • Create MerchantSyncRecord.java as Java record implementing SyncRecord • Create FranchiseMerchantSyncRecord.java as Java record implementing SyncRecord • Create FranchiseGroupSyncRecord.java as Java record implementing SyncRecord • Create QrSyncRecord.java as Java record implementing SyncRecord with nullable deactivationDate • Create ZpFileType.java enum with isFullSync() returning true for ZP0051/ZP0053/ZP0055 | services/zeropay-adapter/src/main/java/com/gme/pay/zeropay/batch/model/ (SyncRecord.java, MerchantSyncRecord.java, FranchiseMerchantSyncRecord.java, FranchiseGroupSyncRecord.java, QrSyncRecord.java, ZpFileType.java) | • All 4 record types compile in zeropay-adapter Gradle module • ZpFileType.ZP0051.isFullSync() returns true; ZP0041.isFullSync() returns false • MerchantSyncRecord is immutable (Java record - no setters) • QrSyncRecord.deactivationDate is nullable; record with statusCode=A constructs without deactivationDate • FranchiseMerchantSyncRecord has franchiseCode field not present in MerchantSyncRecord | 30 |  | BE | SCH-06
9.3-T06 | merchant-qr-data | 9.3 | 9. QR Scheme Integration (ZeroPay) | Merchant & QR synchronization | 2 | Implement ZeroPayDeltaFileParser for ZP0041/ZP0043/ZP0045/ZP0047 in zeropay-adapter | WBS 9.3. Class ZeroPayDeltaFileParser (@Component) in services/zeropay-adapter/src/main/java/com/gme/pay/zeropay/batch/parser/. Method: ParseResult parse(byte[] rawBytes, ZpFileType fileType). File layout: header line (file_type, business_date YYYYMMDD, institution_code, record_count), N detail lines, trailer line (record_count repeat, control_sum). Header file_type must match expected ZpFileType.name(). Trailer record_count must equal actual detail line count. For each detail line: map fields to typed SyncRecord using a per-fileType LineMapper strategy map. Validation per record: required fields non-blank, changeType in {I,U,D}, statusCode in {A,S,T} for merchant or {A,D} for QR. Returns ParseResult: List<SyncRecord> records, int headerCount, String businessDate, List<String> parseErrors (collects errors; never throws). On header/trailer mismatch ParseResult.isCountMismatch=true. | • Create ParseResult.java as a value object in parser package with records, headerCount, businessDate, parseErrors, isCountMismatch fields • Create LineMapper interface with SyncRecord map(String[] fields) and register implementations for each ZpFileType in a Map<ZpFileType, LineMapper> • Implement ZeroPayDeltaFileParser.parse: split lines, parse header, iterate detail lines via LineMapper, parse trailer, validate counts • Collect per-record validation errors into parseErrors without throwing; invalid records are excluded from records list • Add @Component annotation; parser is stateless and thread-safe | services/zeropay-adapter/src/main/java/com/gme/pay/zeropay/batch/parser/ZeroPayDeltaFileParser.java (and ParseResult.java, LineMapper.java) | • 3-record ZP0041 file with matching header/trailer count returns ParseResult.records.size()==3 and parseErrors empty • Trailer count mismatch (header says 5, actual detail 4) returns isCountMismatch=true and does not throw • Line with blank merchantId appends entry to parseErrors; other valid lines still parse • ZP0043 file with statusCode=D produces QrSyncRecord with deactivationDate populated • Unknown ZpFileType passed to parse throws IllegalArgumentException before processing | 45 | 9.3-T05 | BE | SCH-06
9.3-T07 | merchant-qr-data | 9.3 | 9. QR Scheme Integration (ZeroPay) | Merchant & QR synchronization | 2 | Implement FullSyncFileParser for ZP0051/ZP0053/ZP0055 in zeropay-adapter | WBS 9.3. Full sync files (ZP0051 full merchant, ZP0055 franchise full, ZP0053 full QR) use the same line layout as delta files but contain ALL active records. FullSyncFileParser (@Component) in zeropay-adapter wraps ZeroPayDeltaFileParser. Method: FullSyncParseResult parseFullSync(byte[] rawBytes, ZpFileType fileType, Set<String> knownMerchantIds). FullSyncParseResult extends ParseResult adding: boolean isFullSync=true, boolean isRecordCountMismatch (header count != actual detail count). For ZP0053 only: validate each QrSyncRecord.merchantId is in knownMerchantIds; collect orphans in orphanQrIds list; orphan records are excluded from records list and counted in parseErrors. Full-sync rule: if isRecordCountMismatch=true, caller must NOT apply the file. | • Create FullSyncParseResult.java extending ParseResult with isFullSync, isRecordCountMismatch, orphanQrIds fields • Create FullSyncFileParser.java injecting ZeroPayDeltaFileParser • Implement parseFullSync: delegate to ZeroPayDeltaFileParser, wrap result, set isRecordCountMismatch if headerCount != records.size()+parseErrors.size() • For ZP0053: iterate records, check merchantId in knownMerchantIds, add orphans to orphanQrIds and parseErrors • FullSyncParseResult.isFullSync always true | services/zeropay-adapter/src/main/java/com/gme/pay/zeropay/batch/parser/FullSyncFileParser.java and FullSyncParseResult.java | • ZP0051 file with 1000 detail lines and header count 1000 returns isRecordCountMismatch=false • ZP0051 file with header count 999 but 1000 detail lines returns isRecordCountMismatch=true • ZP0053 with QrSyncRecord referencing merchantId not in knownMerchantIds populates orphanQrIds list • FullSyncParseResult.isFullSync is always true • Orphan QR records excluded from records list and counted in parseErrors | 35 | 9.3-T06 | BE | SCH-06
9.3-T08 | merchant-qr-data | 9.3 | 9. QR Scheme Integration (ZeroPay) | Merchant & QR synchronization | 2 | Define MerchantDocument and QrCodeDocument MongoDB models in merchant-qr-data | WBS 9.3. MongoDB is the CQRS read-model for payment-time merchant/QR lookup (low-latency reads). Module services/merchant-qr-data uses Spring Data MongoDB. MerchantDocument: @Document(collection=merchants), _id=merchantId (String, ZeroPay CHAR(10)), fields: merchantType (String), name (String), businessRegistrationNo (String), franchiseCode (String nullable), categoryCode (String), feeType (String: DOMESTIC/CROSSBORDER), status (String), isActive (boolean), isQrActive (boolean), syncedAt (Instant), schemeId (String DEFAULT ZEROPAY). QrCodeDocument: @Document(collection=qr_codes), _id=qrCodeId (String, ZeroPay CHAR(20)), fields: merchantId (String), qrType (String: M/C), status (String), isActive (boolean), issueDate (LocalDate), deactivationDate (LocalDate nullable), syncedAt (Instant), schemeId (String DEFAULT ZEROPAY). Spring Data repositories: MerchantMongoRepository and QrCodeMongoRepository. | • Create services/merchant-qr-data/src/main/java/com/gme/pay/merchantqr/domain/MerchantDocument.java as @Document(collection=merchants) with all fields and @Indexed annotations • Create QrCodeDocument.java as @Document(collection=qr_codes) with all fields • Add @Indexed(unique=true) on merchantId in MerchantDocument (redundant with _id but explicit) • Add @Indexed on MerchantDocument.status, MerchantDocument.franchiseCode, MerchantDocument.isActive • Add @Indexed on QrCodeDocument.merchantId, QrCodeDocument.isActive • Create MerchantMongoRepository and QrCodeMongoRepository extending MongoRepository | services/merchant-qr-data/src/main/java/com/gme/pay/merchantqr/domain/MerchantDocument.java, QrCodeDocument.java, MerchantMongoRepository.java, QrCodeMongoRepository.java | • Both documents compile and are discovered by Spring Data MongoDB repository scan • Indexes created on MongoDB startup (verify via Testcontainers + MongoClient.listIndexes on collection) • MerchantDocument.status is String not enum so unknown values from ZeroPay files do not cause deserialization errors • QrCodeDocument._id is qrCodeId String field (ZeroPay CHAR(20)) • MerchantMongoRepository.findByMerchantIdAndIsActiveTrue(String merchantId) query method resolves without error | 30 |  | BE | SCH-06
9.3-T09 | merchant-qr-data | 9.3 | 9. QR Scheme Integration (ZeroPay) | Merchant & QR synchronization | 2 | Define domain events MerchantSyncedEvent, QrSyncedEvent, SyncAbortedEvent, SyncReconciliationMismatchEvent in lib-events | WBS 9.3. Per STACK.md all domain events live in libs/lib-events. Each event is a Java record implementing DomainEvent marker interface with eventId (String UUID), occurredAt (Instant), plus event-specific fields. MerchantSyncedEvent: merchantId (String), changeType (String), isActive (boolean), schemeId (String). QrSyncedEvent: qrCodeId (String), merchantId (String), changeType (String), isActive (boolean). SyncAbortedEvent: fileType (String), businessDate (LocalDate), reason (String). SyncReconciliationMismatchEvent: fileType (String), businessDate (LocalDate), expectedCount (int), actualCount (int). DomainEvent is a zero-method marker interface. These events are also written to the outbox_events table (V4 migration) for future Kafka wiring. | • Create libs/lib-events/src/main/java/com/gme/pay/events/DomainEvent.java as marker interface • Create libs/lib-events/src/main/java/com/gme/pay/events/merchant/MerchantSyncedEvent.java as Java record • Create QrSyncedEvent.java, SyncAbortedEvent.java, SyncReconciliationMismatchEvent.java in same package • All four implement DomainEvent • Confirm lib-events module compiles with ./gradlew :lib-events:compileJava | libs/lib-events/src/main/java/com/gme/pay/events/merchant/MerchantSyncedEvent.java (and siblings), libs/lib-events/src/main/java/com/gme/pay/events/DomainEvent.java | • All four event records compile in lib-events module • DomainEvent interface is zero-method (marker only) • MerchantSyncedEvent.merchantId is String (not Long) to match ZeroPay CHAR(10) • SyncAbortedEvent.businessDate is LocalDate • lib-events module has no dependency on services (no circular dependency) | 25 |  | BE | SCH-06
9.3-T10 | merchant-qr-data | 9.3 | 9. QR Scheme Integration (ZeroPay) | Merchant & QR synchronization | 2 | Implement MerchantSyncService: delta upsert for ZP0041/ZP0045/ZP0047 into PostgreSQL | WBS 9.3. MerchantSyncService (@Service in services/merchant-qr-data) applies parsed delta records to PostgreSQL merchant and franchise_groups tables. Per-record logic: changeType=I -> INSERT; changeType=U -> UPDATE; changeType=D -> set status=DEACTIVATED, is_active=false. Use INSERT ... ON CONFLICT (merchant_id) DO UPDATE (upsert). For ZP0045 records: set is_franchise=true, franchise_code. For ZP0047 records: upsert franchise_groups table. account_no must be AES-256 encrypted via SecretService bean before INSERT/UPDATE. After all records applied, write one merchant_sync_log row. All within a single Spring @Transactional method. Publish MerchantSyncedEvent via ApplicationEventPublisher for each upserted record (using @TransactionalEventListener in downstream projection writer). Inject IdempotencyGuard; return empty SyncResult if already processed. | • Create services/merchant-qr-data/src/main/java/com/gme/pay/merchantqr/service/MerchantSyncService.java as @Service • Inject JdbcTemplate (for bulk upsert), SecretService (account_no encrypt), ApplicationEventPublisher, IdempotencyGuard • Implement applyMerchantDelta(List<MerchantSyncRecord> records, String fileType, LocalDate syncDate) -> SyncResult within @Transactional • Upsert via INSERT INTO merchant (...) VALUES (...) ON CONFLICT (merchant_id) DO UPDATE SET ... for each record • Encrypt account_no before insert; set synced_at=now() on every upsert • Write merchant_sync_log row after loop; publish MerchantSyncedEvent per record via ApplicationEventPublisher | services/merchant-qr-data/src/main/java/com/gme/pay/merchantqr/service/MerchantSyncService.java | • changeType=D record sets is_active=false and status=DEACTIVATED in merchant table • Duplicate merchant_id with changeType=I performs UPDATE not duplicate INSERT (upsert semantics) • account_no stored encrypted (raw DB value differs from plaintext input - verify via JdbcTemplate raw query) • @Transactional rollback on exception: no merchant rows and no merchant_sync_log row committed • SyncResult.deactivated count equals number of D records in input | 45 | 9.3-T01, 9.3-T05, 9.3-T09 | BE | SCH-06
9.3-T11 | merchant-qr-data | 9.3 | 9. QR Scheme Integration (ZeroPay) | Merchant & QR synchronization | 2 | Implement QrSyncService: delta upsert for ZP0043 into PostgreSQL | WBS 9.3. QrSyncService (@Service in services/merchant-qr-data) applies ZP0043 QrSyncRecord list to the qr_code PostgreSQL table. changeType=I: INSERT; changeType=D: set status=DEACTIVATED, is_active=false, deactivation_date=record.deactivationDate. Deactivated QR codes must block payment at next resolution call. Validate: referenced merchant_id must exist as ACTIVE in merchant table; if not, log error and skip that record (do not fail whole batch). Write merchant_sync_log row (file_type=ZP0043) after processing. All within @Transactional. Publish QrSyncedEvent per record. Inject IdempotencyGuard; return empty SyncResult if already processed. | • Create services/merchant-qr-data/src/main/java/com/gme/pay/merchantqr/service/QrSyncService.java as @Service • Inject QrCodeRepository (Spring Data JPA), MerchantRepository, ApplicationEventPublisher, IdempotencyGuard • Implement applyQrDelta(List<QrSyncRecord> records, LocalDate syncDate) -> SyncResult within @Transactional • For each record: verify merchantId exists and is ACTIVE; if not add to error count, skip • changeType=I: upsert qr_code row; changeType=D: set is_active=false, status=DEACTIVATED, deactivation_date • Publish QrSyncedEvent per record; write merchant_sync_log(file_type=ZP0043) after loop | services/merchant-qr-data/src/main/java/com/gme/pay/merchantqr/service/QrSyncService.java | • QrSyncRecord with changeType=D sets is_active=false and deactivation_date on qr_code row • QrSyncRecord referencing non-existent merchantId skipped and counted in errorCount • Duplicate qr_code_id I record performs UPDATE not duplicate INSERT • merchant_sync_log status=PARTIAL when errorCount>0, SUCCESS when errorCount=0 • @Transactional boundary: exception mid-batch rolls back all QR writes for that invocation | 40 | 9.3-T01, 9.3-T05, 9.3-T09 | BE | SCH-06
9.3-T12 | merchant-qr-data | 9.3 | 9. QR Scheme Integration (ZeroPay) | Merchant & QR synchronization | 2 | Implement IdempotencyGuard using merchant_sync_log for sync-job deduplication | WBS 9.3. Sync jobs must be idempotent: second run for same file_type + sync_date with status=SUCCESS is a no-op. IdempotencyGuard (@Component in merchant-qr-data) queries merchant_sync_log via MerchantSyncLogRepository. Before any sync, check for SUCCESS row; if found return already-processed signal. alreadyProcessed returns false when prior row has status=PARTIAL or FAILED (allows retry). Requires index on merchant_sync_log(file_type, sync_date) added in V3 migration (9.3-T03). | • Create services/merchant-qr-data/src/main/java/com/gme/pay/merchantqr/guard/IdempotencyGuard.java as @Component • Create MerchantSyncLogRepository as Spring Data JPA repository with findByFileTypeAndSyncDateAndStatus query method • Implement alreadyProcessed(String fileType, LocalDate date) -> boolean: query for SUCCESS row, return true if found • Inject IdempotencyGuard into MerchantSyncService and QrSyncService; return empty SyncResult(alreadyProcessed=true) if guard returns true • Log INFO message ALREADY_PROCESSED with fileType and syncDate when skipped | services/merchant-qr-data/src/main/java/com/gme/pay/merchantqr/guard/IdempotencyGuard.java and MerchantSyncLogRepository.java | • Second call to applyMerchantDelta with same fileType+syncDate after SUCCESS returns empty SyncResult without any DB upsert (verify via Mockito verify(merchantRepo, never())) • alreadyProcessed returns false when prior row has status=PARTIAL (allows retry) • alreadyProcessed returns true only for status=SUCCESS rows • No DB write to merchant table occurs when alreadyProcessed=true • IdempotencyGuard query uses merchant_sync_log(file_type, sync_date) index (EXPLAIN shows index scan) | 30 | 9.3-T03, 9.3-T10 | BE | SCH-06
9.3-T13 | merchant-qr-data | 9.3 | 9. QR Scheme Integration (ZeroPay) | Merchant & QR synchronization | 2 | Implement MerchantFullSyncService: staging+diff+atomic-promote for ZP0051/ZP0055 | WBS 9.3. ZP0051 (full merchant) and ZP0055 (franchise full) use staging+diff+atomic-promote to prevent partial overwrites. Steps: (1) validate FullSyncParseResult.isRecordCountMismatch is false, else throw SyncAbortedException; (2) open @Transactional; (3) bulk-insert all records into merchant_staging with staging_run_id; (4) diff staging vs live: merchants in live absent from staging get status=DEACTIVATED, is_active=false; new merchants inserted; existing updated; (5) commit; (6) write merchant_sync_log. Rollback on any exception; live table untouched. Inject IdempotencyGuard. | • Create services/merchant-qr-data/src/main/java/com/gme/pay/merchantqr/service/MerchantFullSyncService.java as @Service • Inject JdbcTemplate, SecretService, ApplicationEventPublisher, IdempotencyGuard • Implement applyMerchantFullSync(FullSyncParseResult result, LocalDate syncDate) -> SyncResult within @Transactional • Check result.isRecordCountMismatch; if true throw SyncAbortedException(fileType, syncDate, RECORD_COUNT_MISMATCH) • Bulk INSERT into merchant_staging; diff to live; apply changes; commit • Write merchant_sync_log(status=SUCCESS) on commit; publish SyncAbortedEvent on abort • Implement applyFranchiseFullSync targeting franchise_groups and is_franchise=true merchant rows | services/merchant-qr-data/src/main/java/com/gme/pay/merchantqr/service/MerchantFullSyncService.java | • SyncAbortedException thrown when isRecordCountMismatch=true; live merchant table unchanged verified by SELECT COUNT • Merchants in live table absent from full-sync file are set DEACTIVATED in same transaction • SyncResult.inserted+updated+deactivated count equals total live merchant count after promote • Rollback on DataAccessException leaves staging empty and live table at prior state (Testcontainers JUnit 5 test) • applyFranchiseFullSync targets only is_franchise=true merchants | 50 | 9.3-T02, 9.3-T10, 9.3-T07 | BE | SCH-06
9.3-T14 | merchant-qr-data | 9.3 | 9. QR Scheme Integration (ZeroPay) | Merchant & QR synchronization | 2 | Implement QrFullSyncService: staging+diff+atomic-promote for ZP0053 | WBS 9.3. ZP0053 (full QR list) follows the same staging+diff+atomic-promote pattern as MerchantFullSyncService. Additional: referential integrity check before staging load - every QrSyncRecord.merchantId must be in activemerchantIds (Set<String> passed by caller from live merchant table); orphan records from FullSyncParseResult.orphanQrIds are excluded before staging load. QR codes in live qr_code table absent from full file are set DEACTIVATED. Full QR sync must not interleave with merchant full sync; caller sequences them. Inject IdempotencyGuard. | • Create services/merchant-qr-data/src/main/java/com/gme/pay/merchantqr/service/QrFullSyncService.java as @Service • Inject JdbcTemplate, ApplicationEventPublisher, IdempotencyGuard • Implement applyQrFullSync(FullSyncParseResult result, LocalDate syncDate, Set<String> activeMerchantIds) -> SyncResult within @Transactional • Throw SyncAbortedException if result.isRecordCountMismatch=true • Exclude orphanQrIds before bulk insert into qr_code_staging; diff to live; set absent QRs DEACTIVATED; commit • Write merchant_sync_log(file_type=ZP0053); publish SyncAbortedEvent on abort | services/merchant-qr-data/src/main/java/com/gme/pay/merchantqr/service/QrFullSyncService.java | • QR codes absent from full file set DEACTIVATED in live qr_code table after promote • Orphan records (merchantId not in activeMerchantIds) skipped and counted in merchant_sync_log.error_count • SyncAbortedException on record count mismatch; live qr_code table unchanged • Transaction rollback on DB exception: staging empty and live at prior state • SyncResult.deactivated count equals soft-deleted qr_code rows | 45 | 9.3-T02, 9.3-T11, 9.3-T07 | BE | SCH-06
9.3-T15 | merchant-qr-data | 9.3 | 9. QR Scheme Integration (ZeroPay) | Merchant & QR synchronization | 2 | Implement MerchantProjectionWriter: sync PostgreSQL changes to MongoDB read-model | WBS 9.3. After each successful PostgreSQL upsert, the MongoDB read-model must be updated. MerchantProjectionWriter (@Service in merchant-qr-data) uses @TransactionalEventListener(phase=AFTER_COMMIT) so MongoDB write occurs only after PostgreSQL transaction commits. Handles MerchantSyncedEvent -> upsert MerchantDocument; QrSyncedEvent -> upsert QrCodeDocument. Uses MongoTemplate.upsert with criteria by _id (merchantId or qrCodeId). MongoDB write failure: log WARN, publish MongoSyncFailureEvent, do NOT rollback PostgreSQL. MongoDB is read-model only; PostgreSQL is authoritative. | • Create services/merchant-qr-data/src/main/java/com/gme/pay/merchantqr/projection/MerchantProjectionWriter.java as @Service • Inject MongoTemplate, ApplicationEventPublisher • Implement onMerchantSynced(@TransactionalEventListener(phase=AFTER_COMMIT) MerchantSyncedEvent): upsert MerchantDocument via MongoTemplate.upsert • Implement onQrSynced(@TransactionalEventListener(phase=AFTER_COMMIT) QrSyncedEvent): upsert QrCodeDocument • Wrap each mongo op in try/catch MongoException: log warn, publish MongoSyncFailureEvent(eventId, errorMsg), no rethrow • Set MerchantDocument/QrCodeDocument.syncedAt=Instant.now() on every upsert | services/merchant-qr-data/src/main/java/com/gme/pay/merchantqr/projection/MerchantProjectionWriter.java | • After MerchantSyncService.applyMerchantDelta call, MerchantDocument appears in MongoDB with matching merchantId • MerchantDocument.isActive=false after D-type sync event • MongoDB write failure does NOT cause PostgreSQL rollback (verify: PostgreSQL row exists, MongoDB row absent, no exception propagated) • @TransactionalEventListener(phase=AFTER_COMMIT) annotation present - event not fired on rollback • QrCodeDocument.isActive=false after QrSyncedEvent with isActive=false | 40 | 9.3-T08, 9.3-T10, 9.3-T11, 9.3-T09 | BE | SCH-06
9.3-T16 | merchant-qr-data | 9.3 | 9. QR Scheme Integration (ZeroPay) | Merchant & QR synchronization | 2 | Implement SyncFilePresenceChecker: Redis gate to suppress delta on full-sync night | WBS 9.3. Spec rule: full files supersede delta files on the nights they arrive; delta upsert for same entity type must be suppressed. SyncFilePresenceChecker (@Service in services/zeropay-adapter) uses Redis (StringRedisTemplate) to signal full-sync completion. Key pattern: merchant-sync:full:{ZpFileType}:{YYYYMMDD} TTL 25 hours. markFullSyncComplete(ZpFileType, LocalDate) sets the key. isFullSyncComplete(ZpFileType, LocalDate) checks key existence. Redis unavailability is fail-open: if Redis throws, log REDIS_CHECK_FAILED and proceed with delta (do not suppress). MerchantSyncOrchestrator calls markFullSyncComplete after successful full-sync; MerchantSyncSftpPoller checks before dispatching delta files. | • Create services/zeropay-adapter/src/main/java/com/gme/pay/zeropay/sync/SyncFilePresenceChecker.java as @Service • Inject StringRedisTemplate • Implement markFullSyncComplete(ZpFileType fileType, LocalDate date): set key merchant-sync:full:{fileType}:{date} with TTL Duration.ofHours(25) • Implement isFullSyncComplete(ZpFileType fileType, LocalDate date) -> boolean: return hasKey; catch RedisConnectionException and return false (fail-open) • Log REDIS_CHECK_FAILED at WARN when Redis unavailable | services/zeropay-adapter/src/main/java/com/gme/pay/zeropay/sync/SyncFilePresenceChecker.java | • After markFullSyncComplete(ZP0051, today), Redis key merchant-sync:full:ZP0051:{today} exists with TTL between 24h and 25h • isFullSyncComplete returns false when key absent • isFullSyncComplete returns false when Redis throws RedisConnectionException (fail-open - not suppress) • Key TTL 25h ensures expiry before next nightly run (24h cadence + 1h buffer) • isFullSyncComplete returns true when key present: ZP0041 delta dispatched only when ZP0051 key absent | 35 | 9.3-T05 | BE | SCH-06
9.3-T17 | merchant-qr-data | 9.3 | 9. QR Scheme Integration (ZeroPay) | Merchant & QR synchronization | 2 | Implement SyncReconciler: post-delta count check and Ops alert on mismatch | WBS 9.3. After each delta sync, compare GMEPay+ DB record count against the file header count. SyncReconciler (@Service in merchant-qr-data) queries PostgreSQL: for ZP0041 count merchant rows synced_at=syncDate; compare with ParseResult.headerCount. If abs(dbCount - headerCount) > 0: publish SyncReconciliationMismatchEvent, call NotificationService.alertOps(SYNC_COUNT_MISMATCH, fileType, expected, actual), set merchant_sync_log.status=PARTIAL. Mismatch does NOT rollback applied records; it flags for Ops review. Called from MerchantSyncOrchestrator after each successful delta apply. | • Create services/merchant-qr-data/src/main/java/com/gme/pay/merchantqr/service/SyncReconciler.java as @Service • Inject JdbcTemplate (for count query), NotificationService, ApplicationEventPublisher • Implement reconcile(String fileType, LocalDate syncDate, int headerCount) -> ReconcileResult • Query: SELECT COUNT(*) FROM merchant WHERE DATE(synced_at)=syncDate for ZP0041/ZP0045; from qr_code for ZP0043 • If count != headerCount: publish SyncReconciliationMismatchEvent, call alertOps, return ReconcileResult(MISMATCH, expected, actual) • Update merchant_sync_log.status=PARTIAL on MISMATCH via MerchantSyncLogRepository | services/merchant-qr-data/src/main/java/com/gme/pay/merchantqr/service/SyncReconciler.java | • headerCount=100, actual DB synced count=98: SyncReconciliationMismatchEvent published and alertOps called • headerCount=100, actual count=100: ReconcileResult(OK), no alert • merchant_sync_log.status set to PARTIAL on mismatch (not SUCCESS) • Reconciler does NOT rollback applied records on mismatch • ReconcileResult is immutable value object with status (OK/MISMATCH), expected (int), actual (int) fields | 35 | 9.3-T10, 9.3-T11, 9.3-T09 | BE | SCH-06
9.3-T18 | merchant-qr-data | 9.3 | 9. QR Scheme Integration (ZeroPay) | Merchant & QR synchronization | 2 | Implement MerchantSyncOrchestrator: route parsed bytes to correct sync service | WBS 9.3. MerchantSyncOrchestrator (@Service in services/merchant-qr-data) receives raw decrypted bytes and ZpFileType then routes: ZP0041 -> ZeroPayDeltaFileParser + MerchantSyncService.applyMerchantDelta; ZP0045 -> same (franchise merchant delta); ZP0047 -> parse to FranchiseGroupSyncRecord + MerchantSyncService.applyFranchiseGroupDelta; ZP0043 -> QrSyncService.applyQrDelta; ZP0051 -> FullSyncFileParser + MerchantFullSyncService.applyMerchantFullSync; ZP0055 -> FullSyncFileParser + MerchantFullSyncService.applyFranchiseFullSync; ZP0053 -> FullSyncFileParser + QrFullSyncService.applyQrFullSync (passing activeMerchantIds queried from live table). After each delta: call SyncReconciler.reconcile. After each full-sync: call SyncFilePresenceChecker.markFullSyncComplete. On SyncAbortedException: publish SyncAbortedEvent, call NotificationService.alertOps, do not propagate exception to caller. | • Create services/merchant-qr-data/src/main/java/com/gme/pay/merchantqr/orchestrator/MerchantSyncOrchestrator.java as @Service • Inject ZeroPayDeltaFileParser, FullSyncFileParser, MerchantSyncService, QrSyncService, MerchantFullSyncService, QrFullSyncService, SyncReconciler, SyncFilePresenceChecker, ApplicationEventPublisher, NotificationService, MerchantRepository • Implement sync(byte[] rawBytes, ZpFileType fileType, LocalDate businessDate) -> SyncResult • Routing switch/map; for full-sync: load activeMerchantIds from merchant table before calling FullSyncFileParser • Catch SyncAbortedException: publish event, call alertOps, return SyncResult(aborted=true) • Catch RuntimeException: wrap as SyncProcessingException with fileType and businessDate; rethrow | services/merchant-qr-data/src/main/java/com/gme/pay/merchantqr/orchestrator/MerchantSyncOrchestrator.java | • ZP0041 bytes routed to MerchantSyncService.applyMerchantDelta (Mockito verify) • ZP0053 bytes routed to FullSyncFileParser then QrFullSyncService.applyQrFullSync (Mockito verify) • SyncAbortedException results in SyncAbortedEvent published (no exception propagated to caller) • Unknown ZpFileType throws IllegalArgumentException before any service call • SyncReconciler.reconcile called after ZP0041 delta apply (Mockito verify) | 40 | 9.3-T06, 9.3-T07, 9.3-T10, 9.3-T11, 9.3-T13, 9.3-T14, 9.3-T16, 9.3-T17 | BE | SCH-06
9.3-T19 | merchant-qr-data | 9.3 | 9. QR Scheme Integration (ZeroPay) | Merchant & QR synchronization | 2 | Implement MerchantSyncSftpPoller: scheduled SFTP download of ZP004x/ZP005x files | WBS 9.3. MerchantSyncSftpPoller (@Component in services/zeropay-adapter) polls the KFTC SFTP inbound directory for merchant/QR sync files on a configurable cron schedule (default: 0 30 6 * * * zone=Asia/Seoul). Flow per file type: (1) list inbound dir, (2) match filename ZP{fileCode}_{YYYYMMDD}_01.dat.pgp for today KST, (3) download to temp dir, (4) verify file size/checksum, (5) PGP-decrypt using GME private key from SchemeConfig.pgpPrivateKeyRef, (6) hand raw bytes to MerchantSyncOrchestrator.sync, (7) archive to {archiveDir}/{fileType}/{YYYYMMDD}/. Retry: up to 3 attempts with exponential backoff 30s/120s/600s via Spring Retry @Retryable or manual loop. Final failure: call NotificationService.alertOps(SFTP_FETCH_FAILED, fileType, date). Uses Apache SSHD or JSch SFTP client (SftpGateway bean). Annotated @ScheduledLock(name=zeropay-merchant-sync, lockAtMostFor=PT30M). | • Create services/zeropay-adapter/src/main/java/com/gme/pay/zeropay/sftp/MerchantSyncSftpPoller.java as @Component • Inject SftpGateway, SchemeConfigService, MerchantSyncOrchestrator, SyncFilePresenceChecker, NotificationService, ZeroPayMerchantSyncProperties • Annotate poll() with @Scheduled(cron=${zeropay.merchant-sync.cron:0 30 6 * * *}, zone=Asia/Seoul) and @ScheduledLock(name=zeropay-merchant-sync, lockAtMostFor=PT30M) • For each ZpFileType [ZP0041,ZP0043,ZP0045,ZP0047,ZP0051,ZP0053,ZP0055]: check isFullSyncComplete gate for delta files; download, verify, decrypt, call orchestrator.sync • Implement retry loop: 3 attempts with sleep 30s/120s/600s between; on 3rd failure call alertOps • Archive decrypted file after successful orchestrator call | services/zeropay-adapter/src/main/java/com/gme/pay/zeropay/sftp/MerchantSyncSftpPoller.java | • Successful download + decrypt hands correct byte[] to orchestrator.sync with ZpFileType.ZP0041 and today KST date (Mockito verify) • Checksum mismatch triggers retry; after 3rd failure calls NotificationService.alertOps exactly once • @ScheduledLock annotation present with lockAtMostFor=PT30M • Archived file exists at {archiveDir}/ZP0041/{YYYYMMDD}/ZP0041_{YYYYMMDD}_01.dat after successful run • ZP0041 dispatch skipped when SyncFilePresenceChecker.isFullSyncComplete(ZP0051, today) returns true | 50 | 9.3-T04, 9.3-T16, 9.3-T18 | BE | SCH-06
9.3-T20 | merchant-qr-data | 9.3 | 9. QR Scheme Integration (ZeroPay) | Merchant & QR synchronization | 2 | Implement MerchantLookupService: payment-time merchant and QR resolution from MongoDB | WBS 9.3. At payment time, the Smart Router calls MerchantLookupService (in services/merchant-qr-data) to validate merchantId and qrCodeId from the parsed QR payload. Lookup uses MongoDB only (not PostgreSQL) for low latency. Checks: (1) merchant.isActive=true; (2) qrCode.isActive=true; (3) qrCode.merchantId == passed merchantId. Return MerchantResolutionResult: merchantId, name, merchantType, feeType, qrType, or typed error codes: MERCHANT_NOT_FOUND, MERCHANT_SUSPENDED, MERCHANT_DEACTIVATED, QR_NOT_FOUND, QR_DEACTIVATED, QR_MERCHANT_MISMATCH. Expose via @RestController MerchantLookupController at GET /internal/v1/merchants/{merchantId}/qrcodes/{qrCodeId}. Secured OAuth2/JWT scope ops:read. | • Create MerchantLookupService.java as @Service injecting MerchantMongoRepository and QrCodeMongoRepository • Implement resolve(String merchantId, String qrCodeId) -> MerchantResolutionResult with typed error codes as described • Create MerchantLookupController.java as @RestController at /internal/v1/merchants/{merchantId}/qrcodes/{qrCodeId} mapped to GET • Return 200 MerchantResolutionResult or 422 with lib-errors canonical error body • Annotate controller with @PreAuthorize(hasAuthority(SCOPE_ops:read)) • MerchantResolutionResult is a Java record with nullable error field | services/merchant-qr-data/src/main/java/com/gme/pay/merchantqr/service/MerchantLookupService.java and MerchantLookupController.java | • Deactivated merchant returns error code MERCHANT_DEACTIVATED not MERCHANT_NOT_FOUND • Deactivated QR returns QR_DEACTIVATED even when merchant is ACTIVE • QR owned by different merchantId returns QR_MERCHANT_MISMATCH not QR_NOT_FOUND • Active merchant + active QR with correct merchantId: 200 with feeType and merchantType populated • MongoDB query uses indexed fields (verify via Testcontainers explain plan - no COLLSCAN) | 40 | 9.3-T08, 9.3-T15 | BE | SCH-06
9.3-T21 | merchant-qr-data | 9.3 | 9. QR Scheme Integration (ZeroPay) | Merchant & QR synchronization | 2 | Add Redis caching to MerchantLookupService with 300s TTL and deactivation eviction | WBS 9.3. MerchantLookupService is on the hot payment path (sub-10ms p99 required). Cache MerchantResolutionResult in Redis key merchant-resolve:{merchantId}:{qrCodeId} with TTL 300s. Cache NOT_FOUND results with TTL 60s to avoid stale negatives. On cache hit return immediately. When sync deactivates merchant or QR (MerchantSyncedEvent/QrSyncedEvent isActive=false), immediately evict Redis keys via scan+delete pattern merchant-resolve:{merchantId}:*. Uses Spring Cache @Cacheable with RedisCacheManager (two cache configs: merchant-resolve TTL 300s, merchant-resolve-not-found TTL 60s). | • Create CacheConfig.java @Configuration in merchant-qr-data: configure RedisCacheManager with two named caches merchant-resolve (TTL 300s) and merchant-resolve-not-found (TTL 60s) • Annotate MerchantLookupService.resolve with @Cacheable based on result: error NOT_FOUND -> merchant-resolve-not-found cache; success -> merchant-resolve cache • Create CacheEvictionService.java: inject RedisTemplate, implement evictMerchant(String merchantId) using scan for keys matching merchant-resolve:{merchantId}:* and delete • Add @TransactionalEventListener(phase=AFTER_COMMIT) in MerchantProjectionWriter calling CacheEvictionService.evictMerchant on MerchantSyncedEvent/QrSyncedEvent with isActive=false | services/merchant-qr-data/src/main/java/com/gme/pay/merchantqr/cache/CacheConfig.java and CacheEvictionService.java (and updated MerchantLookupService.java) | • Second call with same merchantId+qrCodeId returns without MongoDB query (Mockito verify mongoRepo called once) • Redis key expires after 300s (verify TTL via Testcontainers Redis) • NOT_FOUND result cached with TTL between 55s-65s (not 300s) • Deactivation event causes Redis key eviction: next resolve call hits MongoDB and returns DEACTIVATED • MerchantResolutionResult round-trips through Jackson/JSON in Redis without data loss | 35 | 9.3-T20, 9.3-T15 | BE | SCH-06
9.3-T22 | merchant-qr-data | 9.3 | 9. QR Scheme Integration (ZeroPay) | Merchant & QR synchronization | 2 | Add Ops Admin API: GET /internal/v1/sync-logs for merchant sync history | WBS 9.3. Ops visibility into sync job history. Spring @RestController in services/merchant-qr-data at GET /internal/v1/sync-logs with query params: fileType (optional String), from (LocalDate required), to (LocalDate required), status (optional String), plus Spring Pageable (page, size). Response: Page<MerchantSyncLogDto> with content array and pagination fields. Validation: date range to-from must be <= 90 days; return 400 with lib-errors body if exceeded. Secured with OAuth2/JWT scope ops:read. | • Create MerchantSyncLogController.java as @RestController at /internal/v1/sync-logs • Implement GET handler with @RequestParam and Pageable; validate date range <= 90 days, return 400 if not • Create MerchantSyncLogRepository custom query: findByOptionalFilters(fileType, from, to, status, Pageable) • Create MerchantSyncLogDto Java record with all merchant_sync_log columns • Annotate with @PreAuthorize(hasAuthority(SCOPE_ops:read)) • Return ResponseEntity<Page<MerchantSyncLogDto>> | services/merchant-qr-data/src/main/java/com/gme/pay/merchantqr/api/MerchantSyncLogController.java and MerchantSyncLogDto.java | • GET with valid date range returns 200 with correct merchant_sync_log rows in content array • Date range > 90 days returns 400 with error code INVALID_DATE_RANGE in lib-errors format • Request without valid JWT returns 401; without ops:read scope returns 403 • Response pagination fields page, size, totalElements are present • fileType filter correctly narrows results (only ZP0041 rows returned when fileType=ZP0041) | 35 | 9.3-T10, 9.3-T12 | BE | SCH-06
9.3-T23 | merchant-qr-data | 9.3 | 9. QR Scheme Integration (ZeroPay) | Merchant & QR synchronization | 2 | Add Ops Admin API: POST /internal/v1/merchants/{merchantId}/deactivate (manual override) | WBS 9.3. Per SCH-06 Assumption A-07: Ops must force-deactivate a merchant outside the batch cycle. POST /internal/v1/merchants/{merchantId}/deactivate. Request body: {reason: String required max 500 chars, actorId: String required}. Actions: (1) @Transactional: set merchant.status=DEACTIVATED, is_active=false, updated_at=now(); set all linked qr_code.is_active=false; write audit_log entry (actor, timestamp, merchantId, prevStatus, newStatus=DEACTIVATED, reason); (2) after commit: evict Redis cache; (3) publish MerchantSyncedEvent(changeType=D, isActive=false). Returns 200 {merchantId, status, deactivatedAt}; 404 if not found. Secured ops:write. | • Create MerchantAdminController.java as @RestController at /internal/v1/merchants • Implement POST /{merchantId}/deactivate with @Valid request body validation (@NotBlank reason, @NotBlank actorId) • Create MerchantAdminService.java: @Service with deactivate(String merchantId, String reason, String actorId) @Transactional • Update merchant row, deactivate linked qr_code rows, write audit_log row within @Transactional • After commit: call CacheEvictionService.evictMerchant; publish MerchantSyncedEvent via ApplicationEventPublisher • Return 200 response or 404 via lib-errors if merchant not found | services/merchant-qr-data/src/main/java/com/gme/pay/merchantqr/api/MerchantAdminController.java and MerchantAdminService.java | • POST /deactivate for ACTIVE merchant: merchant.is_active=false and all linked qr_code.is_active=false in PostgreSQL • audit_log row written with correct actorId, merchantId, prevStatus, newStatus=DEACTIVATED, reason • Redis cache for merchant-resolve:{merchantId}:* evicted after deactivation • 404 response for non-existent merchantId • Request without ops:write scope returns 403 | 40 | 9.3-T21, 9.3-T20 | BE | SCH-06
9.3-T24 | merchant-qr-data | 9.3 | 9. QR Scheme Integration (ZeroPay) | Merchant & QR synchronization | 2 | Add Ops Admin API: POST /internal/v1/qrcodes/{qrCodeId}/deactivate (manual QR override) | WBS 9.3. Per SCH-06 Assumption A-07: Ops must force-deactivate a single QR code outside the batch cycle. POST /internal/v1/qrcodes/{qrCodeId}/deactivate. Body: {reason: String required, actorId: String required}. Actions: @Transactional: set qr_code.status=DEACTIVATED, is_active=false, deactivation_date=today; write audit_log; after commit: upsert QrCodeDocument in MongoDB (isActive=false); evict Redis cache key. Idempotent: deactivating already-DEACTIVATED QR returns 200 with no state change. Secured ops:write. | • Create QrAdminController.java as @RestController at /internal/v1/qrcodes • Implement POST /{qrCodeId}/deactivate with @Valid request body • Create QrAdminService.java @Service: deactivate(String qrCodeId, String reason, String actorId) @Transactional • Set qr_code row DEACTIVATED; write audit_log; if already DEACTIVATED return early (idempotent) • After commit: upsert QrCodeDocument in MongoDB (isActive=false); evict Redis cache • Return 200 {qrCodeId, status, deactivatedAt}; 404 if not found | services/merchant-qr-data/src/main/java/com/gme/pay/merchantqr/api/QrAdminController.java and QrAdminService.java | • POST /deactivate on ACTIVE QR: qr_code.is_active=false in PostgreSQL and QrCodeDocument.isActive=false in MongoDB • MerchantLookupService.resolve returns QR_DEACTIVATED after deactivation • Idempotent: second POST on already-DEACTIVATED QR returns 200 with no additional DB writes (verify via query count) • audit_log row has actorId, qrCodeId, prevStatus=ACTIVE, newStatus=DEACTIVATED • Redis cache evicted: next resolve call hits MongoDB not cache (verify TTL gap) | 40 | 9.3-T21, 9.3-T20, 9.3-T23 | BE | SCH-06
9.3-T25 | merchant-qr-data | 9.3 | 9. QR Scheme Integration (ZeroPay) | Merchant & QR synchronization | 2 | Add OpenTelemetry tracing and Micrometer metrics to sync pipeline | WBS 9.3. Per STACK.md, OpenTelemetry for traces and Prometheus/Micrometer for metrics. Required: (1) trace span zeropay.merchant-sync.{fileType} per sync job in MerchantSyncSftpPoller.poll(); (2) counter merchant_sync_records_total{fileType, changeType, result} incremented per record in MerchantSyncService and QrSyncService; (3) gauge merchant_active_count{schemeId=ZEROPAY} refreshed every 60s from PostgreSQL COUNT; (4) histogram merchant_sync_duration_seconds{fileType} in MerchantSyncOrchestrator.sync. All via Spring Boot Actuator /actuator/prometheus. | • Inject Tracer (OTel API) into MerchantSyncSftpPoller; create and end span named zeropay.merchant-sync.{fileType} around poll body • Inject MeterRegistry into MerchantSyncService and QrSyncService; increment merchant_sync_records_total counter with fileType, changeType, result tags per record • Create MerchantMetricsRefresher @Component with @Scheduled(fixedDelay=60000): query SELECT COUNT(*) FROM merchant WHERE is_active=true and register as Gauge • Add Timer.Sample in MerchantSyncOrchestrator.sync to record merchant_sync_duration_seconds with fileType tag • Confirm /actuator/prometheus endpoint exposes all four metric names in test | services/zeropay-adapter/src/main/java/com/gme/pay/zeropay/metrics/MerchantSyncMetrics.java and updated MerchantSyncService.java, MerchantSyncSftpPoller.java, MerchantSyncOrchestrator.java | • Span zeropay.merchant-sync.ZP0041 appears in OTLP trace output after test run • Counter merchant_sync_records_total{fileType=ZP0041,changeType=I,result=success} increments by 2 after a 2-insert sync • Gauge merchant_active_count reflects live PostgreSQL count of is_active=true merchants • merchant_sync_duration_seconds histogram bucket visible at /actuator/prometheus • All metric names use snake_case and include schemeId tag | 40 | 9.3-T18, 9.3-T19 | BE | SCH-06
9.3-T26 | merchant-qr-data | 9.3 | 9. QR Scheme Integration (ZeroPay) | Merchant & QR synchronization | 2 | Create ZeroPayMerchantSyncProperties @ConfigurationProperties and application.yml config section | WBS 9.3. All zeropay.merchant-sync.* config keys must be bound via a @ConfigurationProperties class and documented in application.yml. Class ZeroPayMerchantSyncProperties (prefix=zeropay.merchant-sync): cron (String, default 0 30 6 * * *), retryMaxAttempts (int, default 3), retryBackoffSeconds (List<Integer>, default [30,120,600]), archiveDir (String, default /data/zeropay/archive), fileRetentionDays (int, default 90), sftpHost (String), sftpPort (int, default 22), pgpPrivateKeyRef (String). Annotate with @Validated and @NotBlank on required fields (sftpHost, pgpPrivateKeyRef). Missing required field causes BindException at startup. | • Create services/zeropay-adapter/src/main/java/com/gme/pay/zeropay/config/ZeroPayMerchantSyncProperties.java with @ConfigurationProperties(prefix=zeropay.merchant-sync) and @Validated • Add all fields with types and defaults as described; @NotBlank on sftpHost and pgpPrivateKeyRef • Update services/zeropay-adapter/src/main/resources/application.yml with zeropay.merchant-sync section and YAML comments for each key • Add @EnableConfigurationProperties(ZeroPayMerchantSyncProperties.class) to ZeroPayAdapterConfig.java • Add Spring Boot integration test ZeroPayMerchantSyncPropertiesTest confirming bean loads with default values | services/zeropay-adapter/src/main/java/com/gme/pay/zeropay/config/ZeroPayMerchantSyncProperties.java and updated services/zeropay-adapter/src/main/resources/application.yml | • Spring context loads with all default values without exceptions • Missing sftpHost in yml causes BindException at startup (test with empty property) • retryBackoffSeconds is List<Integer> with 3 elements [30,120,600] by default • application.yml has YAML comments (# prefix) for each zeropay.merchant-sync.* key • ZeroPayMerchantSyncProperties.fileRetentionDays default is 90 | 30 | 9.3-T04, 9.3-T19 | BE | SCH-06
9.3-T27 | merchant-qr-data | 9.3 | 9. QR Scheme Integration (ZeroPay) | Merchant & QR synchronization | 2 | Unit tests: ZeroPayDeltaFileParser with fixture files for ZP0041 and ZP0043 | WBS 9.3. JUnit 5 unit tests for ZeroPayDeltaFileParser. Test fixtures in services/zeropay-adapter/src/test/resources/fixtures/. Five test vectors: (1) 3-record ZP0041 file with header, 2 I and 1 D records, matching trailer -> records.size()==3, 2 changeType=I, 1 changeType=D, parseErrors empty; (2) ZP0041 with trailer count mismatch (says 5, actual 3) -> isCountMismatch=true, parseErrors non-empty, no exception thrown; (3) ZP0043 with 1 D record -> QrSyncRecord.deactivationDate non-null, isActive derived false; (4) ZP0043 line with unknown statusCode=X -> record excluded, parseErrors has 1 entry; (5) empty byte array -> ParseResult.records empty, parseErrors has EMPTY_FILE entry. | • Create src/test/resources/fixtures/ZP0041_sample.dat as pipe-delimited fixture file with header, 2 I + 1 D detail lines, correct trailer • Create src/test/resources/fixtures/ZP0043_sample.dat with header, 1 D record, trailer; and ZP0043_bad_status.dat with statusCode=X • Create ZeroPayDeltaFileParserTest.java in zeropay-adapter test package with 5 @Test methods • Test (1): load ZP0041_sample.dat; assert records.size()==3, changeTypes, parseErrors.isEmpty() • Tests (2)-(5) as described in context • Run ./gradlew :zeropay-adapter:test to confirm all pass | services/zeropay-adapter/src/test/java/com/gme/pay/zeropay/batch/parser/ZeroPayDeltaFileParserTest.java (5 tests, all passing) | • All 5 tests pass via ./gradlew :zeropay-adapter:test • Test (1) asserts exact field values (merchantId, changeType) on first record • Test (2) asserts no records returned when isCountMismatch=true • Test (3) asserts QrSyncRecord.deactivationDate equals date value in fixture • Test (5) asserts parseErrors contains entry with EMPTY_FILE text | 40 | 9.3-T06 | BE | SCH-06
9.3-T28 | merchant-qr-data | 9.3 | 9. QR Scheme Integration (ZeroPay) | Merchant & QR synchronization | 2 | Integration tests: MerchantSyncService and QrSyncService with Testcontainers PostgreSQL | WBS 9.3. Spring @SpringBootTest integration tests using Testcontainers PostgreSQL 16 for MerchantSyncService and QrSyncService. Five test vectors: (1) 2 I + 1 D records applied -> 2 ACTIVE and 1 DEACTIVATED in merchant table; (2) duplicate merchant_id I records applied -> 1 merchant row (upsert); (3) D record for merchant that has linked qr_code rows -> merchant DEACTIVATED but qr_code rows NOT automatically deactivated (QR deactivation is separate ZP0043 job); (4) account_no encrypted: raw DB value != plaintext input; (5) @Transactional rollback on exception thrown by 3rd record -> 0 rows committed. Uses @DynamicPropertySource for Testcontainers DataSource URL. | • Create services/merchant-qr-data/src/test/java/com/gme/pay/merchantqr/service/MerchantSyncServiceTest.java • Use @SpringBootTest and @Testcontainers with PostgreSQL 16 image • Pre-apply Flyway V1-V5 migrations against Testcontainers (auto via Flyway spring.flyway.enabled=true) • Write 5 @Test methods matching the test vectors in context • Mock ApplicationEventPublisher and NotificationService to avoid side effects • Run ./gradlew :merchant-qr-data:test | services/merchant-qr-data/src/test/java/com/gme/pay/merchantqr/service/MerchantSyncServiceTest.java (5 tests, all passing) | • Test (1): merchant table has 2 rows with is_active=true and 1 with is_active=false after apply • Test (2): SELECT COUNT(*) FROM merchant WHERE merchant_id=... returns 1 (no duplicate) • Test (3): qr_code rows linked to deactivated merchant still have is_active=true • Test (4): raw account_no in DB (via JdbcTemplate SELECT) != input plaintext string • Test (5): SELECT COUNT(*) FROM merchant returns 0 after transactional rollback | 50 | 9.3-T10, 9.3-T11, 9.3-T01 | BE | SCH-06
9.3-T29 | merchant-qr-data | 9.3 | 9. QR Scheme Integration (ZeroPay) | Merchant & QR synchronization | 2 | Integration tests: MerchantFullSyncService staging+promote with Testcontainers PostgreSQL | WBS 9.3. Integration tests for MerchantFullSyncService. Five test vectors: (1) 5 merchants in full sync, 2 already in live table, 3 new -> all 5 ACTIVE in merchant table; (2) live table has 6 merchants, full sync has 5 (one omitted) -> omitted merchant set DEACTIVATED; (3) isRecordCountMismatch=true -> SyncAbortedException thrown, live table unchanged; (4) DataAccessException during staging insert -> rollback, live table unchanged, staging table empty; (5) successful sync -> merchant_sync_log row with status=SUCCESS and correct counts. | • Create services/merchant-qr-data/src/test/java/com/gme/pay/merchantqr/service/MerchantFullSyncServiceTest.java • Use @SpringBootTest and @Testcontainers PostgreSQL 16 • Pre-populate merchant table for tests (2) and (4) via JdbcTemplate in @BeforeEach • Write 5 @Test methods as described • Use Mockito to inject a throwing DataSource wrapper for test (4) • Run ./gradlew :merchant-qr-data:test | services/merchant-qr-data/src/test/java/com/gme/pay/merchantqr/service/MerchantFullSyncServiceTest.java (5 tests, all passing) | • Test (2): absent merchant has status=DEACTIVATED and is_active=false after promote • Test (3): assertThrows(SyncAbortedException.class); SELECT COUNT FROM merchant matches pre-test count • Test (4): SELECT COUNT(*) FROM merchant_staging returns 0 after rollback • Test (5): merchant_sync_log row has records_deactivated=1 and status=SUCCESS • All 5 tests pass via ./gradlew :merchant-qr-data:test | 50 | 9.3-T13, 9.3-T02 | BE | SCH-06
9.3-T30 | merchant-qr-data | 9.3 | 9. QR Scheme Integration (ZeroPay) | Merchant & QR synchronization | 2 | Integration tests: MerchantLookupService with Testcontainers MongoDB and Redis | WBS 9.3. Integration tests for MerchantLookupService and Redis caching using Testcontainers MongoDB and Redis. Six test vectors: (1) active merchant + active QR matching merchantId -> 200 MerchantResolutionResult, feeType populated; (2) DEACTIVATED merchant -> error MERCHANT_DEACTIVATED; (3) ACTIVE merchant + DEACTIVATED QR -> QR_DEACTIVATED; (4) QR.merchantId != passed merchantId -> QR_MERCHANT_MISMATCH; (5) second call same args -> MongoDB not queried (cache hit via Redis - Mockito verify mongoRepo times(1)); (6) deactivation event evicts cache: MerchantSyncedEvent published -> Redis key deleted -> next resolve hits MongoDB. | • Create services/merchant-qr-data/src/test/java/com/gme/pay/merchantqr/service/MerchantLookupServiceTest.java • Use @SpringBootTest and @Testcontainers with MongoDB and Redis images • Pre-insert MerchantDocument and QrCodeDocument fixtures via MongoTemplate in @BeforeEach • Write 6 @Test methods as described • For test (5): spy on MerchantMongoRepository and verify invocation count • For test (6): publish MerchantSyncedEvent manually and confirm Redis key absent after event • Run ./gradlew :merchant-qr-data:test | services/merchant-qr-data/src/test/java/com/gme/pay/merchantqr/service/MerchantLookupServiceTest.java (6 tests, all passing) | • Test (1): MerchantResolutionResult.error is null and feeType is non-null • Test (2): errorCode == MERCHANT_DEACTIVATED (not MERCHANT_NOT_FOUND) • Test (4): errorCode == QR_MERCHANT_MISMATCH (not QR_NOT_FOUND) • Test (5): mongoRepo.findById called exactly once across two resolve calls • Test (6): after MerchantSyncedEvent(isActive=false), Redis key merchant-resolve:{merchantId}:* absent | 50 | 9.3-T21, 9.3-T20, 9.3-T08 | BE | SCH-06
9.4-T01 | scheme-adapter-zeropay | 9.4 | 9. QR Scheme Integration (ZeroPay) | Payment result exchange (ZP0011/0012) | 2 | Flyway migration: payment_batch_file and batch_exception tables | WBS 9.4 Payment result exchange (ZP0011/ZP0012). The ZeroPay Scheme Adapter (Gradle module: services/scheme-adapter-zeropay) records every outbound/inbound batch file in payment_batch_file and raises exception records in batch_exception. payment_batch_file: id BIGSERIAL PK, scheme_id BIGINT FK qr_scheme, file_type VARCHAR(10) e.g. ZP0011/ZP0012, direction VARCHAR(20) CHECK IN ('GME_TO_ZP','ZP_TO_GME'), settlement_date DATE NOT NULL (KST business date), sequence_no SMALLINT NOT NULL DEFAULT 1, status VARCHAR(30) NOT NULL (PENDING/TRANSMITTED/RECEIVED/FAILED), record_count INT, control_sum NUMERIC(16,0), object_storage_key TEXT, created_at TIMESTAMPTZ, updated_at TIMESTAMPTZ, UNIQUE(scheme_id,file_type,settlement_date,sequence_no). batch_exception: id BIGSERIAL PK, batch_file_id BIGINT FK payment_batch_file, payment_id BIGINT FK payments NULLABLE, exception_type VARCHAR(40) NOT NULL CHECK IN ('REGISTRATION_FAILED','REGISTRATION_UNKNOWN','REGISTRATION_AMOUNT_MISMATCH','ANOMALY','SFTP_FAILURE','PARSE_ERROR'), zeropay_txn_ref CHAR(20), details JSONB, status VARCHAR(20) DEFAULT 'OPEN', resolved_by BIGINT, resolved_at TIMESTAMPTZ, created_at TIMESTAMPTZ. PostgreSQL 16 on port 5433 local dev. Use Flyway naming Vnnn__*.sql under services/scheme-adapter-zeropay/src/main/resources/db/migration/. | • Find the current highest Flyway version under services/scheme-adapter-zeropay/src/main/resources/db/migration/ and use the next integer. • Write migration SQL creating payment_batch_file with all listed columns, UNIQUE constraint, and index on (scheme_id, file_type, settlement_date). • Add batch_exception table with all listed columns, FK to payment_batch_file, index on (batch_file_id), partial index on (payment_id) WHERE payment_id IS NOT NULL, partial index on (status) WHERE status='OPEN'. • Apply migration against local PostgreSQL on port 5433 and verify both tables with correct column types using psql. | services/scheme-adapter-zeropay/src/main/resources/db/migration/V{N}__payment_batch_tables.sql | • Both tables exist after migration with no errors. • payment_batch_file.direction CHECK rejects any value outside ('GME_TO_ZP','ZP_TO_GME'). • batch_exception.exception_type CHECK rejects 'BOGUS'; accepts all 6 defined values. • NUMERIC(16,0) used for control_sum (not BIGINT, not FLOAT). • UNIQUE(scheme_id, file_type, settlement_date, sequence_no) exists on payment_batch_file. | 30 |  | BE | SCH-06
9.4-T02 | scheme-adapter-zeropay | 9.4 | 9. QR Scheme Integration (ZeroPay) | Payment result exchange (ZP0011/0012) | 2 | Flyway migration: add batch_registration_status columns to payments table | WBS 9.4. The payments table (PostgreSQL 16, Gradle module services/payment-executor) needs columns tracking ZP0011/ZP0012 lifecycle per SCH-06 §5.4. Add: batch_registration_status VARCHAR(30) NOT NULL DEFAULT 'PENDING' CHECK IN ('PENDING','REGISTERED','SETTLEMENT_REGISTERED','REGISTRATION_FAILED','REGISTRATION_UNKNOWN','REGISTRATION_AMOUNT_MISMATCH'); zeropay_batch_file_id BIGINT NULLABLE FK payment_batch_file (the ZP0011 file row that included this payment); registered_amount_krw NUMERIC(14,0) NULLABLE (confirmed by ZP0012); settlement_date DATE NULLABLE (from ZP0012.settlement_date); zp0012_result_code CHAR(2) NULLABLE; zp0012_result_message VARCHAR(100) NULLABLE. Add partial index on (batch_registration_status) WHERE batch_registration_status NOT IN ('SETTLEMENT_REGISTERED'). Flyway migrations live in services/payment-executor/src/main/resources/db/migration/. NUMERIC for all monetary columns. | • Determine next Flyway version under services/payment-executor/src/main/resources/db/migration/. • Write ALTER TABLE payments ADD COLUMN statements for all six fields with correct types, defaults, and CHECK constraint. • Add partial index on batch_registration_status for non-settled rows. • Apply against local PostgreSQL port 5433; verify columns with \d payments in psql. | services/payment-executor/src/main/resources/db/migration/V{N}__payments_batch_registration_status.sql | • All six columns present after migration with correct types. • batch_registration_status CHECK rejects 'BOGUS'; accepts all 6 defined values. • NUMERIC(14,0) used for registered_amount_krw (not BIGINT or FLOAT). • Existing payment rows default to batch_registration_status='PENDING' after migration. • Partial index on batch_registration_status is present in pg_indexes. | 25 | 9.4-T01 | BE | SCH-06
9.4-T03 | scheme-adapter-zeropay | 9.4 | 9. QR Scheme Integration (ZeroPay) | Payment result exchange (ZP0011/0012) | 2 | ZP0011 record domain model and fixed-width record builder | WBS 9.4. The ZeroPay Adapter (Gradle module services/scheme-adapter-zeropay, package com.gme.pay.zeropay.batch.zp0011) assembles the ZP0011 Payment Result file. Per SCH-06 §5.2 illustrative layout (fixed-width, confirm exact widths from 한결원 final spec): detail record: record_type CHAR(1)='D', gme_txn_id CHAR(20), zeropay_txn_ref CHAR(20), merchant_id CHAR(10), qr_code_id CHAR(20), txn_date DATE(8) YYYYMMDD KST, txn_time TIME(6) HHMMSS KST, payout_amount_krw NUM(12) KRW 0 decimals zero-padded, merchant_fee_amt NUM(12), van_fee_amt NUM(10), partner_type CHAR(1) D or I, approval_code CHAR(12), status_code CHAR(1)='A'. Header: record_type='H', file_type='ZP0011', business_date DATE(8), institution_code CHAR(10), total_record_count NUM(6), total_payout_krw NUM(16). Trailer: record_type='T', total_record_count NUM(6), control_sum NUM(16) = sum of payout_amount_krw. Use lib-money BigDecimal utilities (module lib-money); KRW scale=0. String fields space-padded, numeric fields zero-padded. | • Create immutable Java record Zp0011DetailRecord in com.gme.pay.zeropay.batch.zp0011 with all detail fields (BigDecimal for amounts, LocalDate/LocalTime, String for IDs). • Create Zp0011HeaderRecord and Zp0011TrailerRecord similarly. • Implement Zp0011RecordBuilder @Component with methods buildDetailLine(Zp0011DetailRecord), buildHeaderLine(Zp0011HeaderRecord), buildTrailerLine(Zp0011TrailerRecord) -> String each; use String.format for fixed-width padding. • Implement buildFile(List<Zp0011DetailRecord>, LocalDate businessDate, String institutionCode) computing header totalRecordCount and trailer control_sum from the list. • Add validation: zeropay_txn_ref and gme_txn_id must be non-blank; payout_amount_krw must be > 0; throw IllegalArgumentException otherwise. | services/scheme-adapter-zeropay/src/main/java/com/gme/pay/zeropay/batch/zp0011/Zp0011RecordBuilder.java (plus Zp0011DetailRecord.java, Zp0011HeaderRecord.java, Zp0011TrailerRecord.java) | • buildDetailLine formats payout_amount_krw=150000 as '000000150000' (12 chars, zero-padded right-aligned). • gme_txn_id shorter than 20 chars is space-padded on the right to exactly 20 chars. • Trailer control_sum equals sum of payout_amount_krw across all detail records. • Header total_record_count equals trailer total_record_count equals detail list size. • Blank zeropay_txn_ref throws IllegalArgumentException before file assembly. | 40 | 9.4-T01 | BE | SCH-06
9.4-T04 | scheme-adapter-zeropay | 9.4 | 9. QR Scheme Integration (ZeroPay) | Payment result exchange (ZP0011/0012) | 2 | Internal REST endpoint: fetch prior-day APPROVED payments pending batch registration | WBS 9.4. The ZP0011 batch (Gradle module services/scheme-adapter-zeropay) must query payments eligible for inclusion: status=APPROVED, txn_date=prior business date KST, batch_registration_status='PENDING'. Per architecture (Anti-Corruption Layer / microservice boundary), the scheme adapter calls the Payment Executor service (services/payment-executor) via an internal REST endpoint, not a direct cross-DB join. Expose GET /internal/v1/payments/pending-batch-registration?businessDate=YYYYMMDD returning List<Zp0011PaymentProjection>. Projection fields needed for ZP0011 detail record: paymentId (Long), gmeTxnId (String CHAR(20)), zeropayTxnRef (String CHAR(20)), merchantId (String CHAR(10)), qrCodeId (String CHAR(20)), txnDate (LocalDate KST), txnTime (LocalTime KST), payoutAmountKrw (BigDecimal), merchantFeeAmt (BigDecimal), vanFeeAmt (BigDecimal), partnerType (String: D for LOCAL partner, I for OVERSEAS), approvalCode (String CHAR(12)). @RestController in com.gme.pay.executor.api.internal; secured so Spring Cloud Gateway blocks /internal/** from external traffic. | • Add Zp0011PaymentProjection DTO in lib-api-contracts module under com.gme.pay.contracts.internal.batch with all listed fields. • Add JPA @Query in PaymentRepository (services/payment-executor) selecting payments WHERE status=APPROVED AND txn_date=:businessDate AND batch_registration_status='PENDING' mapped to Zp0011PaymentProjection. • Implement GET /internal/v1/payments/pending-batch-registration in PaymentExecutorInternalController @RestController; return ResponseEntity<List<Zp0011PaymentProjection>>. • Add Spring Security config rule blocking /internal/** from Gateway-origin requests (e.g. via header check or network policy comment). • In services/scheme-adapter-zeropay implement Zp0011BatchQueryClient @Service using Spring WebClient to call the endpoint; set timeout 30s. | services/payment-executor/src/main/java/com/gme/pay/executor/api/internal/PaymentExecutorInternalController.java and services/scheme-adapter-zeropay/src/main/java/com/gme/pay/zeropay/batch/zp0011/Zp0011BatchQueryClient.java | • Query returns only payments where status=APPROVED AND txn_date=businessDate AND batch_registration_status='PENDING'. • Payments with batch_registration_status='REGISTERED' or 'SETTLEMENT_REGISTERED' are excluded. • partnerType='D' for LOCAL partner type and 'I' for OVERSEAS. • Endpoint returns HTTP 200 with empty list (not 404) when no qualifying payments exist. • Spring Security config blocks /internal/** from requests arriving via the Gateway path. | 40 | 9.4-T02 | BE | SCH-06
9.4-T05 | scheme-adapter-zeropay | 9.4 | 9. QR Scheme Integration (ZeroPay) | Payment result exchange (ZP0011/0012) | 2 | ZP0011 file assembler and Object Storage upload | WBS 9.4. After fetching prior-day APPROVED payments via Zp0011BatchQueryClient (T04), the ZeroPay Adapter (services/scheme-adapter-zeropay) assembles a ZP0011 file, encrypts it PGP (public key from Vault/KMS), and uploads to S3-compatible Object Storage (MinIO in docker-compose local dev). Bucket: zeropay-batch-files. Key prefix: outbound/ZP0011/YYYY/MM/. File naming: ZP0011_{YYYYMMDD}_{NN}.dat.pgp where NN is 2-digit sequence (01 for first run, 02 for retransmit). After upload, insert payment_batch_file row (status=PENDING, file_type=ZP0011, direction=GME_TO_ZP, record_count, control_sum, object_storage_key) and update each payment's zeropay_batch_file_id and batch_registration_status='REGISTERED'. Insert and payment updates must be in one @Transactional block. S3Client configured via application.yml (zeropay.object-storage.*) pointing to MinIO for local. | • Implement Zp0011FileAssembler @Service in com.gme.pay.zeropay.batch.zp0011: calls Zp0011BatchQueryClient.fetch(date), maps projections to Zp0011DetailRecord list, calls Zp0011RecordBuilder.buildFile(), returns assembled byte[]. • Implement PgpEncryptionService @Service (or reuse if exists) fetching ZeroPay public PGP key from Vault at runtime and encrypting byte[] -> byte[]. • Implement ObjectStorageClient @Service using AWS SDK v2 S3Client (configured for MinIO); method upload(String bucket, String key, byte[] data) -> String returns final key. • In Zp0011BatchJob @Service: fetch -> assemble -> encrypt -> upload -> compute sequence_no as MAX(sequence_no)+1 for (file_type=ZP0011, settlement_date) or 1 if none -> persist payment_batch_file (status=PENDING) and bulk-update payments.batch_registration_status='REGISTERED' and zeropay_batch_file_id=batchFileId in one @Transactional. • If no payments returned by query, log INFO and do not create file or payment_batch_file row. | services/scheme-adapter-zeropay/src/main/java/com/gme/pay/zeropay/batch/zp0011/Zp0011FileAssembler.java and Zp0011BatchJob.java | • payment_batch_file row inserted with status=PENDING before SFTP transmission. • sequence_no=1 for first run; sequence_no=2 for second run on same settlement_date. • Assembled byte[] contains header record_type='H', N detail records record_type='D', trailer record_type='T' with correct counts. • Object storage key matches outbound/ZP0011/YYYY/MM/ZP0011_{date}_{seq}.dat.pgp pattern. • No file created and no DB row inserted when zero payments match the query. | 45 | 9.4-T03, 9.4-T04 | BE | SCH-06
9.4-T06 | scheme-adapter-zeropay | 9.4 | 9. QR Scheme Integration (ZeroPay) | Payment result exchange (ZP0011/0012) | 2 | SFTP transmission of ZP0011 via SftpGatewayClient to /gmepay/outbound/ | WBS 9.4. After file assembly and Object Storage upload (T05), the ZP0011 file must be placed on ZeroPay's SFTP server. Remote directory: /gmepay/outbound/ (per SCH-06 §2.3.4). SSH key authentication with RSA-4096 private key stored in Vault (path from zeropay.sftp.private-key-vault-path config). The SftpGatewayClient @Service in services/scheme-adapter-zeropay uses Apache MINA SSHD or JSch (pick one; prefer Apache MINA SSHD 2.x). Retry: Spring Retry @Retryable maxAttempts=3, exponential backoff starting 5s x2 multiplier. On permanent failure: update payment_batch_file.status=FAILED, call BatchExceptionService.raise(batchFileId, null, SFTP_FAILURE, null, details). On success: update payment_batch_file.status=TRANSMITTED. | • Implement SftpGatewayClient @Service in com.gme.pay.zeropay.sftp with method transmit(String objectStorageKey, String remoteFileName): downloads bytes from Object Storage then streams to SFTP /gmepay/outbound/{remoteFileName}. • Add @Retryable(maxAttempts=3, backoff=@Backoff(delay=5000,multiplier=2)) on the SFTP put operation; add @Recover method to handle SftpException after exhaustion. • In @Recover handler: call BatchExceptionService.raise with SFTP_FAILURE; update payment_batch_file.status=FAILED. • On success: update payment_batch_file.status=TRANSMITTED and updated_at. • Private key retrieved from Vault via VaultTemplate at runtime; never on disk or in application.yml. | services/scheme-adapter-zeropay/src/main/java/com/gme/pay/zeropay/sftp/SftpGatewayClient.java | • On successful SFTP put, payment_batch_file.status=TRANSMITTED. • On 3 consecutive SFTP failures, status=FAILED and batch_exception row with exception_type=SFTP_FAILURE is inserted. • Private key is fetched from Vault at runtime; not hardcoded or stored on filesystem. • Remote file placed at path /gmepay/outbound/ZP0011_{date}_{seq}.dat.pgp. • Retransmit (sequence_no=02) places ZP0011_{date}_02.dat.pgp without altering the original sequence_no=01 row. | 40 | 9.4-T05 | BE | SCH-06
9.4-T07 | scheme-adapter-zeropay | 9.4 | 9. QR Scheme Integration (ZeroPay) | Payment result exchange (ZP0011/0012) | 2 | Spring Scheduler: ZP0011 nightly batch cron at 02:00 KST with idempotency guard | WBS 9.4. The ZP0011 batch fires daily at ~02:00 KST per SCH-06 §7.3. Module: services/scheme-adapter-zeropay. Use Spring @Scheduled with cron='${zeropay.batch.zp0011.cron}' (default '0 0 2 * * *') zone='Asia/Seoul'. The prior business date = LocalDate.now(ZoneId.of('Asia/Seoul')).minusDays(1). Idempotency: if payment_batch_file already has a non-FAILED row for (file_type=ZP0011, settlement_date=priorBusinessDate), skip. Wrap in try-catch; on uncaught exception call NotificationService.alertOps('BATCH_ZP0011_FAILED', detail) and update status=FAILED. Per SAD-02 §5.4: all settlement scheduler jobs must be idempotent. | • Add @Configuration class ZeropayBatchSchedulerConfig with @EnableScheduling. • Implement Zp0011ScheduledJob @Component in com.gme.pay.zeropay.batch with @Scheduled(cron='${zeropay.batch.zp0011.cron}', zone='Asia/Seoul'). • Compute priorBusinessDate in Asia/Seoul; query payment_batch_file for existing non-FAILED row; if found log INFO and return immediately. • Delegate to Zp0011BatchJob.run(priorBusinessDate) which orchestrates query-assemble-encrypt-upload (T05) then SftpGatewayClient.transmit (T06). • Wrap full flow in try-catch; on exception call NotificationService.alertOps and re-throw after marking status=FAILED. | services/scheme-adapter-zeropay/src/main/java/com/gme/pay/zeropay/batch/Zp0011ScheduledJob.java | • @Scheduled cron fires at 02:00 KST with zone=Asia/Seoul (not UTC). • Second invocation on same settlement_date with existing TRANSMITTED row skips without duplicate file creation. • priorBusinessDate is computed in Asia/Seoul timezone so UTC midnight does not shift the date. • On uncaught exception NotificationService.alertOps is called with 'BATCH_ZP0011_FAILED'. • cron expression is externalized to application.yml key zeropay.batch.zp0011.cron. | 35 | 9.4-T05, 9.4-T06 | BE | SCH-06
9.4-T08 | scheme-adapter-zeropay | 9.4 | 9. QR Scheme Integration (ZeroPay) | Payment result exchange (ZP0011/0012) | 2 | SFTP inbound poller: detect and download ZP0012 from /gmepay/inbound/ | WBS 9.4. ZeroPay places ZP0012 (Payment Registration Result) at /gmepay/inbound/ by ~05:00 KST. GMEPay+ polls every 5 min from 05:00-06:00 KST (cron '0 */5 5 * * *' zone Asia/Seoul). File naming pattern: ZP0012_{YYYYMMDD}_{NN}.dat.pgp. After download: decrypt with GME private PGP key from Vault; upload decrypted bytes to Object Storage (bucket zeropay-batch-files, key inbound/ZP0012/YYYY/MM/ZP0012_{date}_{seq}.dat); insert payment_batch_file row (file_type=ZP0012, direction=ZP_TO_GME, status=RECEIVED). Idempotent: if row for (file_type=ZP0012, settlement_date, sequence_no) already exists, skip. Late-file alert: separate @Scheduled at 06:05 KST checks if no RECEIVED row exists for the date and calls NotificationService.alertOps('BATCH_FILE_LATE_ZP0012'). Module services/scheme-adapter-zeropay. | • Implement Zp0012InboundPoller @Component in com.gme.pay.zeropay.batch.zp0012 with @Scheduled(cron='${zeropay.batch.zp0012.poll-cron}', zone='Asia/Seoul') polling /gmepay/inbound/ via SftpGatewayClient.listFiles(dir) for ZP0012_{date}_*. • Check idempotency: query payment_batch_file for existing RECEIVED row for that (file_type, settlement_date, sequence_no); skip if present. • Download bytes via SftpGatewayClient.download(remoteFile); decrypt via PgpEncryptionService.decrypt(bytes); upload to Object Storage; insert payment_batch_file(status=RECEIVED). • Add separate @Scheduled(cron='${zeropay.batch.zp0012.late-alert-cron}', zone='Asia/Seoul') at 06:05 KST: if no RECEIVED row for settlement_date=today KST, call NotificationService.alertOps('BATCH_FILE_LATE_ZP0012'). • GME private PGP key retrieved from Vault at runtime. | services/scheme-adapter-zeropay/src/main/java/com/gme/pay/zeropay/batch/zp0012/Zp0012InboundPoller.java | • Polling runs every 5 min starting 05:00 KST; second poll finding same filename skips re-download (idempotent - no duplicate payment_batch_file row). • Decrypted file bytes stored to Object Storage before payment_batch_file row inserted. • payment_batch_file row gets direction=ZP_TO_GME, file_type=ZP0012, status=RECEIVED. • BATCH_FILE_LATE_ZP0012 alert fires if no RECEIVED row by 06:05 KST. • Private PGP key retrieved from Vault; not stored in application.yml. | 40 | 9.4-T01, 9.4-T06 | BE | SCH-06
9.4-T09 | scheme-adapter-zeropay | 9.4 | 9. QR Scheme Integration (ZeroPay) | Payment result exchange (ZP0011/0012) | 2 | ZP0012 file parser: parse fixed-width result records into Zp0012ResultRecord objects | WBS 9.4. After download and decryption (T08), ZP0012 bytes are parsed record-by-record. SCH-06 §5.3 illustrative layout: header record_type='H' (file_type='ZP0012', business_date DATE(8), institution_code); detail record_type='D': zeropay_txn_ref CHAR(20) (match key), gme_txn_id CHAR(20) (echo from ZP0011), merchant_id CHAR(10), txn_date DATE(8) YYYYMMDD, result_code CHAR(2) ('00'=success, non-zero=failure), result_message VARCHAR(100), registered_amount NUM(12) KRW NUMERIC scale=0, settlement_date DATE(8) YYYYMMDD; trailer record_type='T': total_record_count NUM(6), control_sum NUM(16). Parser validates: (1) header file_type='ZP0012'; (2) trailer record_count == actual detail count; (3) trailer control_sum == sum of registered_amount (BigDecimal.compareTo). On parse error throw Zp0012ParseException; caller creates batch_exception type=PARSE_ERROR. Module services/scheme-adapter-zeropay. | • Create immutable Zp0012ResultRecord in com.gme.pay.zeropay.batch.zp0012 with all detail fields; use BigDecimal for registered_amount (scale=0), LocalDate for dates. • Create Zp0012ParseResult (header + List<Zp0012ResultRecord> + trailer metadata) and Zp0012ParseException. • Implement Zp0012FileParser @Service: method parse(byte[] fileBytes, LocalDate expectedBusinessDate) -> Zp0012ParseResult; split lines, dispatch by record_type. • Validate header.fileType='ZP0012'; throw Zp0012ParseException if mismatch. Validate header.businessDate == expectedBusinessDate. • Validate trailer.totalRecordCount == detail list size; validate trailer.controlSum.compareTo(sum of registered_amount) == 0; throw Zp0012ParseException on mismatch. | services/scheme-adapter-zeropay/src/main/java/com/gme/pay/zeropay/batch/zp0012/Zp0012FileParser.java (plus Zp0012ResultRecord.java, Zp0012ParseResult.java, Zp0012ParseException.java) | • Parser correctly extracts zeropay_txn_ref and result_code from a hand-crafted test byte array. • Trailer record_count mismatch throws Zp0012ParseException (not NullPointerException). • Control sum mismatch throws Zp0012ParseException. • Header file_type='ZP0021' throws Zp0012ParseException (wrong file type). • registered_amount represented as BigDecimal with scale=0 (KRW). | 40 | 9.4-T08 | BE | SCH-06
9.4-T10 | scheme-adapter-zeropay | 9.4 | 9. QR Scheme Integration (ZeroPay) | Payment result exchange (ZP0011/0012) | 2 | ZP0012 line-by-line matcher: reconcile ZP0012 results against ZP0011 submission | WBS 9.4. After parsing ZP0012 (T09), line-by-line matching runs against ZP0011 records. Matching key: zeropay_txn_ref + txn_date (per SCH-06 §5.2). SCH-06 §5.4 conditions: (1) result_code='00' AND registered_amount.compareTo(payout_amount_krw)==0 -> batch_registration_status=SETTLEMENT_REGISTERED; (2) result_code non-'00' -> REGISTRATION_FAILED + batch_exception; (3) ZP0011 record absent from ZP0012 -> REGISTRATION_UNKNOWN + batch_exception; (4) ZP0012 record not in ZP0011 -> ANOMALY batch_exception, no payment update; (5) result_code='00' but registered_amount != payout_amount_krw -> REGISTRATION_AMOUNT_MISMATCH + batch_exception. All amount comparisons use BigDecimal.compareTo (not .equals). Entire match+update runs inside one @Transactional block. Module services/scheme-adapter-zeropay, class Zp0012MatchingService @Service. | • Implement Zp0012MatchingService @Service in com.gme.pay.zeropay.batch.zp0012; method match(Long zp0011BatchFileId, Long zp0012BatchFileId, List<Zp0012ResultRecord> results). • Load ZP0011 payments from DB: query payments WHERE zeropay_batch_file_id=zp0011BatchFileId; build Map<String,Payment> keyed by (zeropay_txn_ref+'_'+txn_date). • For each Zp0012ResultRecord look up map; apply 5-way conditional logic; call payment update and/or BatchExceptionService.raise accordingly. • After iterating all ZP0012 records, find ZP0011 payments with no matching ZP0012 record (set difference) and mark REGISTRATION_UNKNOWN + exception. • Annotate match() with @Transactional(rollbackFor=Exception.class); DB updates and exception inserts are atomic. | services/scheme-adapter-zeropay/src/main/java/com/gme/pay/zeropay/batch/zp0012/Zp0012MatchingService.java | • Payment with result_code='00' and registered_amount==payout_amount_krw gets batch_registration_status=SETTLEMENT_REGISTERED; no exception raised. • Payment with result_code='09' gets batch_registration_status=REGISTRATION_FAILED; BatchExceptionService.raise called with REGISTRATION_FAILED. • ZP0011 record absent from ZP0012 gets REGISTRATION_UNKNOWN; exception raised. • ZP0012 record with no ZP0011 match creates batch_exception with exception_type=ANOMALY; no payment updated. • Amount comparison uses BigDecimal.compareTo (not .equals). | 45 | 9.4-T09, 9.4-T04 | BE | SCH-06
9.4-T11 | scheme-adapter-zeropay | 9.4 | 9. QR Scheme Integration (ZeroPay) | Payment result exchange (ZP0011/0012) | 2 | Outbox event: PaymentBatchRegistrationResultEvent for state changes | WBS 9.4. After Zp0012MatchingService updates batch_registration_status (T10), a domain event must be published via the transactional Outbox (Phase 1 approach per STACK.md: no Kafka yet; EventPublisher inserts into outbox_events in same transaction; Outbox poller delivers to Kafka in integration phase). Define PaymentBatchRegistrationResultEvent in lib-events module (com.gme.pay.events.batch) with fields: paymentId (Long), zeropayTxnRef (String), batchFileId (Long), batchRegistrationStatus (String), registeredAmountKrw (BigDecimal), settlementDate (LocalDate), eventTimestamp (Instant). outbox_events table schema: id BIGSERIAL PK, aggregate_type VARCHAR(50), aggregate_id BIGINT, event_type VARCHAR(80), payload JSONB, created_at TIMESTAMPTZ, published_at TIMESTAMPTZ NULLABLE. Outbox migration may already exist from earlier WBS; check first. | • Define PaymentBatchRegistrationResultEvent as a Java record in lib-events/src/main/java/com/gme/pay/events/batch/ with all listed fields. • Check if outbox_events Flyway migration exists in services/payment-executor or services/scheme-adapter-zeropay migrations; create V{N}__outbox_events.sql only if absent. • Implement EventPublisher @Service (or reuse if exists from earlier WBS) in services/scheme-adapter-zeropay that inserts into outbox_events within the caller's @Transactional. • Call EventPublisher.publish(new PaymentBatchRegistrationResultEvent(...)) from Zp0012MatchingService.match() for each payment status change, within the same @Transactional block. • Verify lib-events has no dependency on any service module (no circular deps); it is a pure schema/DTO module. | lib-events/src/main/java/com/gme/pay/events/batch/PaymentBatchRegistrationResultEvent.java and outbox insert logic in Zp0012MatchingService.java | • PaymentBatchRegistrationResultEvent contains all listed fields including eventTimestamp (Instant). • Outbox row inserted within same @Transactional as payment status update; if transaction rolls back, no outbox row persists. • outbox_events.event_type='PAYMENT_BATCH_REGISTRATION_RESULT' for these events. • lib-events module build.gradle has no dependency on services/* modules. • Published event payload serializes to valid JSON with all fields present. | 35 | 9.4-T10 | BE | SCH-06
9.4-T12 | scheme-adapter-zeropay | 9.4 | 9. QR Scheme Integration (ZeroPay) | Payment result exchange (ZP0011/0012) | 2 | BatchExceptionService: persist exception records and dispatch P1 ops alerts | WBS 9.4. All mismatch and error conditions during ZP0011/ZP0012 processing must persist batch_exception rows and alert Ops for P1 cases (per SCH-06 §9.2). BatchExceptionService @Service in services/scheme-adapter-zeropay encapsulates this. P1 types: SFTP_FAILURE, PARSE_ERROR, REGISTRATION_FAILED, REGISTRATION_UNKNOWN, REGISTRATION_AMOUNT_MISMATCH. P2 types: ANOMALY. For P1: insert batch_exception row then call NotificationService.alertOps(alertCode, details) which publishes an OPS_ALERT outbox event within the same @Transactional. For P2 (ANOMALY): insert row, log WARN, do NOT call alertOps. Expose countOpenExceptions(Long batchFileId) -> int for the settlement gate check (T13). Expose resolve(Long exceptionId, Long resolvedBy, String note) -> void setting status='RESOLVED'. | • Define ExceptionType enum in com.gme.pay.zeropay.batch.exception with values REGISTRATION_FAILED, REGISTRATION_UNKNOWN, REGISTRATION_AMOUNT_MISMATCH, ANOMALY, SFTP_FAILURE, PARSE_ERROR; annotate each with P1/P2 priority. • Implement BatchExceptionService @Service with method raise(Long batchFileId, Long paymentId, ExceptionType type, String zeropayTxnRef, Map<String,Object> details). • Inside raise(): insert batch_exception row (status='OPEN') via JPA; if type.priority==P1 call NotificationService.alertOps within same @Transactional. • Add countOpenExceptions(Long batchFileId) querying count WHERE batch_file_id=batchFileId AND status='OPEN'. • Add resolve(Long id, Long resolvedBy, String note): set status='RESOLVED', resolved_by, resolved_at=now(). | services/scheme-adapter-zeropay/src/main/java/com/gme/pay/zeropay/batch/exception/BatchExceptionService.java | • REGISTRATION_FAILED type calls NotificationService.alertOps (P1 path). • ANOMALY type inserts batch_exception row but does NOT call alertOps. • batch_exception row has status='OPEN' on creation. • countOpenExceptions returns correct count after multiple raise() calls for the same batchFileId. • DB insert and alertOps outbox insert are atomic: if DB insert fails, alertOps is not invoked. | 35 | 9.4-T01, 9.4-T11 | BE | SCH-06
9.4-T13 | scheme-adapter-zeropay | 9.4 | 9. QR Scheme Integration (ZeroPay) | Payment result exchange (ZP0011/0012) | 2 | SettlementGate: block ZP0061 generation for payments with open registration exceptions | WBS 9.4. SCH-06 §5.4 and §8.2: registration failures not resolved before ZP0061 transmission window block settlement for affected transactions; non-affected transactions proceed normally. The ZP0061 batch assembler (services/scheme-adapter-zeropay) must check each payment's eligibility. SettlementGate @Service provides: isEligibleForSettlement(Long paymentId) -> boolean checking payments.batch_registration_status='SETTLEMENT_REGISTERED'; getBlockedPaymentCount(LocalDate settlementDate) -> int counting payments where settlement_date=arg AND batch_registration_status IN ('REGISTRATION_FAILED','REGISTRATION_UNKNOWN','REGISTRATION_AMOUNT_MISMATCH'). The ZP0061 assembly loop calls isEligibleForSettlement per payment and skips ineligible ones. If getBlockedPaymentCount > 0, log WARN and call NotificationService.alertOps('SETTLEMENT_BLOCKED_PAYMENTS', count). | • Implement SettlementGate @Service in com.gme.pay.zeropay.batch.settlement. • Method isEligibleForSettlement(Long paymentId): query payments.batch_registration_status; return true only if='SETTLEMENT_REGISTERED'. • Method getBlockedPaymentCount(LocalDate settlementDate): COUNT payments WHERE settlement_date=arg AND batch_registration_status IN ('REGISTRATION_FAILED','REGISTRATION_UNKNOWN','REGISTRATION_AMOUNT_MISMATCH'). • Wire SettlementGate into ZP0061 batch assembler: call isEligibleForSettlement per payment in the assembly loop; skip if false. • After loop, call getBlockedPaymentCount; if >0 call NotificationService.alertOps('SETTLEMENT_BLOCKED_PAYMENTS', count). | services/scheme-adapter-zeropay/src/main/java/com/gme/pay/zeropay/batch/settlement/SettlementGate.java | • isEligibleForSettlement returns true only for batch_registration_status='SETTLEMENT_REGISTERED'. • isEligibleForSettlement returns false for REGISTRATION_FAILED status. • getBlockedPaymentCount returns correct integer count for given settlement date. • alertOps('SETTLEMENT_BLOCKED_PAYMENTS') called when blockedCount > 0. • Gate check runs per-payment inside ZP0061 assembly loop (not once as a pre-check). | 30 | 9.4-T10, 9.4-T12 | BE | SCH-06
9.4-T14 | scheme-adapter-zeropay | 9.4 | 9. QR Scheme Integration (ZeroPay) | Payment result exchange (ZP0011/0012) | 2 | IdempotencyGuard: prevent duplicate file generation per business date | WBS 9.4. SAD-02 §5.4 mandates all settlement scheduler jobs be idempotent. For ZP0011 (and by pattern for ZP0021/ZP0061/ZP0065/ZP0066), idempotency means: a re-run must not produce a second file with the same sequence_no for the same business date. For intentional retransmits (SFTP failure), sequence_no increments. IdempotencyGuard @Service in services/scheme-adapter-zeropay queries payment_batch_file and returns RunDecision enum: FIRST_RUN (no row, sequence_no=1), RETRANSMIT (status=FAILED, sequence_no=previous+1), SKIP (status=TRANSMITTED). Maximum sequence_no=99; beyond that throw BatchSequenceExhaustedException. Zp0011ScheduledJob calls checkRun first. | • Define RunDecision enum: FIRST_RUN, RETRANSMIT, SKIP (each carrying int sequenceNo). • Implement IdempotencyGuard @Service in com.gme.pay.zeropay.batch with method checkRun(String fileType, LocalDate settlementDate) -> RunDecision. • Query payment_batch_file for (file_type, settlement_date); if no row -> FIRST_RUN(1); if status='TRANSMITTED' -> SKIP; if status='FAILED' -> compute next_seq = maxSequenceNo+1; if next_seq > 99 throw BatchSequenceExhaustedException; return RETRANSMIT(next_seq). • Wire into Zp0011ScheduledJob: call checkRun first; if SKIP return immediately; pass sequenceNo to Zp0011BatchJob. • Add same guard call to ZP0021/ZP0061/ZP0065/ZP0066 batch jobs (guard is generic on fileType). | services/scheme-adapter-zeropay/src/main/java/com/gme/pay/zeropay/batch/IdempotencyGuard.java | • No payment_batch_file row -> checkRun returns FIRST_RUN with sequenceNo=1. • Existing row with status='TRANSMITTED' -> checkRun returns SKIP. • Existing row with status='FAILED' and sequence_no=1 -> checkRun returns RETRANSMIT with sequenceNo=2. • sequence_no=99 + status='FAILED' -> checkRun throws BatchSequenceExhaustedException. • Zp0011ScheduledJob calls fileAssembler 0 times when guard returns SKIP (verifiable via Mockito.verify). | 35 | 9.4-T05, 9.4-T07 | BE | SCH-06
9.4-T15 | scheme-adapter-zeropay | 9.4 | 9. QR Scheme Integration (ZeroPay) | Payment result exchange (ZP0011/0012) | 2 | UNCERTAIN transaction resolution via ZP0012 ingestion | WBS 9.4. Per SAD-02 AD-09: transactions left in UNCERTAIN state (network failure after scheme call) are resolved within 24h via ZP0012. After Zp0012MatchingService processes the file (T10), any payment with status=UNCERTAIN that now has a ZP0012 record must be transitioned: result_code='00' -> APPROVED; result_code non-'00' -> FAILED. For OVERSEAS+FAILED: reverse prefunding deduction via PrefundingLedgerService (per SAD-02 prefunding atomicity note: deduction held during UNCERTAIN, reversed on confirmed FAILED). The scheme adapter calls services/payment-executor internal endpoint POST /internal/v1/payments/{id}/resolve-uncertain body {outcome:APPROVED¦FAILED, zeropayResultCode, batchFileId}. Orchestrator transitions state and (if OVERSEAS FAILED) calls PrefundingLedgerService.reverseDeduction(paymentId) within one @Transactional. Publishes PaymentStateChangedEvent via Outbox. | • Define ResolveUncertainRequest DTO in lib-api-contracts with fields outcome (String APPROVED¦FAILED), zeropayResultCode (String), batchFileId (Long). • In services/payment-executor implement POST /internal/v1/payments/{id}/resolve-uncertain in PaymentExecutorInternalController: load payment, validate status=UNCERTAIN (409 if not), transition state. • If outcome=FAILED AND partner.type=OVERSEAS call PrefundingLedgerService.reverseDeduction(paymentId) in same @Transactional. • Publish PaymentStateChangedEvent (new state) via EventPublisher/Outbox within same transaction. • In Zp0012MatchingService, after detecting an UNCERTAIN payment in matching logic, call TransactionOrchestratorInternalClient.resolveUncertain(paymentId, outcome, resultCode, batchFileId). | services/payment-executor/src/main/java/com/gme/pay/executor/api/internal/UncertainResolutionHandler.java and services/scheme-adapter-zeropay/src/main/java/com/gme/pay/zeropay/batch/zp0012/TransactionOrchestratorInternalClient.java | • UNCERTAIN + result_code='00' transitions payment to APPROVED. • UNCERTAIN + result_code='09' transitions payment to FAILED. • OVERSEAS + FAILED triggers PrefundingLedgerService.reverseDeduction exactly once. • LOCAL + FAILED does NOT call reverseDeduction. • resolveUncertain called on non-UNCERTAIN payment returns HTTP 409 Conflict. | 45 | 9.4-T10, 9.4-T11 | BE | SCH-06
9.4-T16 | scheme-adapter-zeropay | 9.4 | 9. QR Scheme Integration (ZeroPay) | Payment result exchange (ZP0011/0012) | 2 | Unit tests: Zp0011RecordBuilder fixed-width formatting and control sum | WBS 9.4. JUnit 5 unit tests for Zp0011RecordBuilder (T03). Pure logic tests; no Spring context, no Testcontainers needed. Test class: Zp0011RecordBuilderTest in services/scheme-adapter-zeropay test sources (src/test/java/com/gme/pay/zeropay/batch/zp0011/). | • Test formatPayoutAmount: input payout_amount_krw=BigDecimal(150000), expect detail line substring '000000150000' (12-char zero-padded field). • Test padGmeTxnId: gme_txn_id='TXN001' (6 chars) produces a 20-char field 'TXN001 ' (right-padded spaces). • Test controlSum: build 3 detail records with payout_amount_krw=100000, 200000, 300000; trailer control_sum=600000. • Test recordCounts: file with 5 detail records -> header.totalRecordCount=5 and trailer.totalRecordCount=5. • Test blankZeropayTxnRef: calling buildFile with a Zp0011DetailRecord having blank zeropay_txn_ref throws IllegalArgumentException. | services/scheme-adapter-zeropay/src/test/java/com/gme/pay/zeropay/batch/zp0011/Zp0011RecordBuilderTest.java | • All 5 test methods pass with ./gradlew :services:scheme-adapter-zeropay:test --tests Zp0011RecordBuilderTest. • payout_amount_krw=150000 formats as exactly '000000150000' (12 chars, no spaces, no decimal). • controlSum of [100000,200000,300000] = 600000 in trailer. • header.totalRecordCount == trailer.totalRecordCount == 5. • Blank zeropay_txn_ref raises IllegalArgumentException before any I/O occurs. | 30 | 9.4-T03 | BE | SCH-06
9.4-T17 | scheme-adapter-zeropay | 9.4 | 9. QR Scheme Integration (ZeroPay) | Payment result exchange (ZP0011/0012) | 2 | Unit tests: Zp0012FileParser validation and parse error cases | WBS 9.4. JUnit 5 unit tests for Zp0012FileParser (T09). Use hand-crafted byte arrays representing synthetic ZP0012 files. No Spring context, no Testcontainers. Test class: Zp0012FileParserTest in services/scheme-adapter-zeropay src/test/java/com/gme/pay/zeropay/batch/zp0012/. | • Test parseValidFile: hand-craft header(ZP0012)+2 detail records+trailer(count=2,controlSum=sum); assert parse returns 2 Zp0012ResultRecord objects. • Test trailerCountMismatch: trailer says 3 but file has 2 detail records; assert Zp0012ParseException thrown. • Test controlSumMismatch: trailer control_sum does not equal sum of registered_amount; assert Zp0012ParseException. • Test wrongFileType: header file_type='ZP0021'; assert Zp0012ParseException. • Test resultCodeParsed: detail record with result_code='00' parsed to resultCode='00' on Zp0012ResultRecord. | services/scheme-adapter-zeropay/src/test/java/com/gme/pay/zeropay/batch/zp0012/Zp0012FileParserTest.java | • All 5 test methods pass. • trailerCountMismatch throws Zp0012ParseException with non-null message. • controlSumMismatch throws Zp0012ParseException (not ArithmeticException). • wrongFileType throws Zp0012ParseException (not NullPointerException). • Valid 2-record file returns exactly 2 Zp0012ResultRecord objects. | 30 | 9.4-T09 | BE | SCH-06
9.4-T18 | scheme-adapter-zeropay | 9.4 | 9. QR Scheme Integration (ZeroPay) | Payment result exchange (ZP0011/0012) | 2 | Unit tests: Zp0012MatchingService all 5 SCH-06 §5.4 mismatch conditions | WBS 9.4. JUnit 5 + Mockito tests for Zp0012MatchingService (T10). Mock PaymentRepository and BatchExceptionService. Cover all 5 conditions from SCH-06 §5.4. Test class: Zp0012MatchingServiceTest in services/scheme-adapter-zeropay test sources. Input vectors: ZP0011 payments TXN001 (payout=150000), TXN002 (payout=200000), TXN003 (payout=180000), TXN004 (payout=90000); ZP0012 results: TXN001 result_code='00' amount=150000; TXN002 result_code='07'; TXN003 result_code='00' amount=145000 (mismatch); ZP0012 extra TXN999 (no ZP0011 match); TXN004 absent from ZP0012. | • Setup mocks: PaymentRepository returns map of 4 payments; BatchExceptionService is a Mockito mock. • Test condition1_success: TXN001 result_code='00' amount matches -> payment.batchRegistrationStatus=SETTLEMENT_REGISTERED; verify BatchExceptionService.raise never called for TXN001. • Test condition2_registrationFailed: TXN002 result_code='07' -> REGISTRATION_FAILED; verify raise called once with REGISTRATION_FAILED. • Test condition3_registrationUnknown: TXN004 absent from ZP0012 -> REGISTRATION_UNKNOWN; verify raise called with REGISTRATION_UNKNOWN. • Test condition4_anomaly: TXN999 in ZP0012 but no ZP0011 match -> raise called with ANOMALY; no payment updated. • Test condition5_amountMismatch: TXN003 result_code='00' but amount=145000 vs 180000 -> REGISTRATION_AMOUNT_MISMATCH; verify raise called. | services/scheme-adapter-zeropay/src/test/java/com/gme/pay/zeropay/batch/zp0012/Zp0012MatchingServiceTest.java | • All 6 test scenarios pass. • Condition 1: BatchExceptionService.raise NOT called for TXN001. • Condition 2: raise called once with ExceptionType.REGISTRATION_FAILED for TXN002. • Condition 3: raise called once with ExceptionType.REGISTRATION_UNKNOWN for TXN004. • Condition 5: amount comparison uses BigDecimal(145000).compareTo(BigDecimal(180000))!=0 path, not .equals. | 40 | 9.4-T10 | BE | SCH-06
9.4-T19 | scheme-adapter-zeropay | 9.4 | 9. QR Scheme Integration (ZeroPay) | Payment result exchange (ZP0011/0012) | 2 | Unit tests: IdempotencyGuard run-decision logic | WBS 9.4. JUnit 5 + Mockito tests for IdempotencyGuard (T14). Mock PaymentBatchFileRepository. Cover FIRST_RUN, SKIP, RETRANSMIT, and sequence overflow. Test class: IdempotencyGuardTest in services/scheme-adapter-zeropay test sources. | • Test firstRun: no row for (ZP0011, 2026-06-01) -> checkRun returns FIRST_RUN with sequenceNo=1. • Test skip: row exists with status='TRANSMITTED' -> checkRun returns SKIP. • Test retransmit: row exists with status='FAILED' and sequence_no=1 -> checkRun returns RETRANSMIT with sequenceNo=2. • Test sequenceOverflow: row exists with status='FAILED' and sequence_no=99 -> checkRun throws BatchSequenceExhaustedException. • Test schedulerSkipsAssembly: inject mock Zp0011FileAssembler into Zp0011ScheduledJob; when guard returns SKIP verify assembler.assemble never called. | services/scheme-adapter-zeropay/src/test/java/com/gme/pay/zeropay/batch/IdempotencyGuardTest.java | • All 5 test methods pass. • FIRST_RUN returns sequenceNo=1. • RETRANSMIT returns sequenceNo=2 when existing row has sequence_no=1. • sequence_no=99 + FAILED throws BatchSequenceExhaustedException. • Zp0011FileAssembler.assemble is never invoked when guard returns SKIP. | 30 | 9.4-T14 | BE | SCH-06
9.4-T20 | scheme-adapter-zeropay | 9.4 | 9. QR Scheme Integration (ZeroPay) | Payment result exchange (ZP0011/0012) | 2 | Unit tests: UNCERTAIN resolution with OVERSEAS prefunding reversal | WBS 9.4. JUnit 5 + Mockito tests for UncertainResolutionHandler (T15). Mock PrefundingLedgerService and PaymentRepository. Test all 4 branches. Test class: UncertainResolutionHandlerTest in services/payment-executor test sources. | • Test overseasFailed: payment status=UNCERTAIN partnerType=OVERSEAS outcome=FAILED -> payment.status=FAILED; verify PrefundingLedgerService.reverseDeduction called once. • Test localFailed: payment status=UNCERTAIN partnerType=LOCAL outcome=FAILED -> payment.status=FAILED; verify reverseDeduction never called. • Test approved: payment status=UNCERTAIN outcome=APPROVED -> payment.status=APPROVED; verify reverseDeduction never called. • Test notUncertain: payment status=APPROVED -> handler throws PaymentStateException; verify no DB update. | services/payment-executor/src/test/java/com/gme/pay/executor/api/internal/UncertainResolutionHandlerTest.java | • OVERSEAS FAILED: reverseDeduction called exactly once. • LOCAL FAILED: reverseDeduction never called. • APPROVED: payment status set to APPROVED; no prefunding call. • Non-UNCERTAIN payment: PaymentStateException thrown; payment repo save not called. • All 4 test methods pass. | 30 | 9.4-T15 | BE | SCH-06
9.4-T21 | scheme-adapter-zeropay | 9.4 | 9. QR Scheme Integration (ZeroPay) | Payment result exchange (ZP0011/0012) | 2 | Integration test: ZP0011 assembly + ZP0012 match full cycle with Testcontainers Postgres | WBS 9.4. Full integration test of the generate->upload->match cycle using Testcontainers PostgreSQL 16. @SpringBootTest(webEnvironment=NONE). WireMock stubs the payment-executor internal endpoint. Object Storage stubbed via LocalStack or in-memory S3Mock. SFTP not tested here (covered in T22). Class: Zp0011Zp0012IntegrationTest in services/scheme-adapter-zeropay src/test/java/com/gme/pay/zeropay/batch/. | • Configure @Container PostgreSQLContainer('postgres:16'); apply Flyway migrations in test context. • WireMock stub: GET /internal/v1/payments/pending-batch-registration?businessDate=20260601 returns 2 payment projections (TXN001 payout=150000 OVERSEAS, TXN002 payout=200000 LOCAL). • Call Zp0011BatchJob.run(LocalDate.of(2026,6,1)); assert payment_batch_file row inserted with record_count=2 control_sum=350000. • Build synthetic ZP0012 bytes: TXN001 result_code='00' amount=150000; TXN002 result_code='09'. Call Zp0012MatchingService.match(zp0011FileId, zp0012FileId, parsedResults). • Assert: payments.batch_registration_status for TXN001=SETTLEMENT_REGISTERED; TXN002=REGISTRATION_FAILED; batch_exception row for TXN002 with exception_type=REGISTRATION_FAILED. | services/scheme-adapter-zeropay/src/test/java/com/gme/pay/zeropay/batch/Zp0011Zp0012IntegrationTest.java | • Test passes entirely via Testcontainers (no local DB or SFTP server required). • payment_batch_file row has record_count=2 and control_sum=350000. • After match: TXN001 batch_registration_status=SETTLEMENT_REGISTERED. • After match: TXN002 batch_registration_status=REGISTRATION_FAILED. • batch_exception table has 1 row with exception_type=REGISTRATION_FAILED for TXN002. | 50 | 9.4-T05, 9.4-T10, 9.4-T12 | BE | SCH-06
9.4-T22 | scheme-adapter-zeropay | 9.4 | 9. QR Scheme Integration (ZeroPay) | Payment result exchange (ZP0011/0012) | 2 | Integration test: SFTP outbound transmit and inbound poll with embedded Apache MINA SSHD | WBS 9.4. Integration test for SftpGatewayClient (T06) and Zp0012InboundPoller (T08) using Apache MINA SSHD 2.x embedded SFTP server as test double. Test class: SftpTransmissionIntegrationTest in services/scheme-adapter-zeropay. @SpringBootTest(webEnvironment=NONE). Vault replaced with a test @Configuration providing fixed test RSA key pair (generated in @BeforeAll, not committed). Object Storage uses LocalStack S3 or in-memory stub. | • Add Apache MINA SSHD (sshd-core, sshd-sftp 2.x) to testImplementation in services/scheme-adapter-zeropay/build.gradle. • Stand up SshServer with SftpSubsystemFactory in @BeforeAll; virtualFileSystemFactory pointing to tmp dir with /gmepay/outbound and /gmepay/inbound. • Override SftpGatewayClient config: host=localhost, port=randomPort, SSH key = test key pair from @BeforeAll. • Test transmit: call client.transmit(objectStorageKey, 'ZP0011_20260601_01.dat.pgp'); assert file present in tmp/outbound/. • Test inbound poll idempotency: place synthetic ZP0012 file in tmp/inbound/; call poller.pollOnce(date) twice; assert exactly 1 payment_batch_file row (no duplicate on second call). | services/scheme-adapter-zeropay/src/test/java/com/gme/pay/zeropay/sftp/SftpTransmissionIntegrationTest.java | • ZP0011 file appears in embedded SFTP /gmepay/outbound/ after transmit call. • ZP0012 file in /gmepay/inbound/ is downloaded and payment_batch_file row inserted with status=RECEIVED. • Second pollOnce call for same file does NOT create a duplicate payment_batch_file row. • Test SSH key used (no Vault call); injected via test @Configuration overriding VaultTemplate bean. • Test runs without any real SFTP server (embedded MINA SSHD only). | 50 | 9.4-T06, 9.4-T08 | BE | SCH-06
9.4-T23 | scheme-adapter-zeropay | 9.4 | 9. QR Scheme Integration (ZeroPay) | Payment result exchange (ZP0011/0012) | 2 | Batch exception queue API: GET and resolve endpoints for Ops Admin portal | WBS 9.4. SCH-06 §5.4: all exception records must be surfaced in the Ops Admin portal exception queue. Expose endpoints in services/scheme-adapter-zeropay (consumed by Ops/Partner BFF). GET /internal/v1/batch-exceptions?status=OPEN&fileType=ZP0012&page=0&size=20 returns Page<BatchExceptionDto>. BatchExceptionDto: id, batchFileId, paymentId, exceptionType, zeropayTxnRef, details (JsonNode), status, createdAt. POST /internal/v1/batch-exceptions/{id}/resolve body {resolvedBy: Long, resolutionNote: String} marks exception status='RESOLVED'. @RestController BatchExceptionController in com.gme.pay.zeropay.batch.exception. @PreAuthorize('hasRole(ROLE_OPS)') on both endpoints. /internal/** blocked from Spring Cloud Gateway as with other internal endpoints. | • Add BatchExceptionDto to lib-api-contracts in com.gme.pay.contracts.internal.batch with all listed fields. • Implement BatchExceptionQueryService @Service: findOpen(fileType, Pageable) -> Page<BatchExceptionDto>; resolve(id, resolvedBy, note) -> void. • Implement BatchExceptionController @RestController with GET and POST endpoints; add @PreAuthorize('hasRole(ROLE_OPS)'). • Add ResolveExceptionRequest DTO with resolvedBy (Long) and resolutionNote (String) for POST body. • Confirm /internal/** Spring Security rule blocks non-internal access (consistent with T04 security config). | services/scheme-adapter-zeropay/src/main/java/com/gme/pay/zeropay/batch/exception/BatchExceptionController.java | • GET returns only exceptions with status='OPEN' when ?status=OPEN filter applied. • POST /resolve sets status='RESOLVED', resolved_by, resolved_at on the exception row. • Request without ROLE_OPS receives HTTP 403. • Page results respect size parameter: size=2 returns at most 2 results. • fileType=ZP0012 filter returns only exceptions linked to ZP0012 batch files. | 40 | 9.4-T12 | BE | SCH-06
9.4-T24 | scheme-adapter-zeropay | 9.4 | 9. QR Scheme Integration (ZeroPay) | Payment result exchange (ZP0011/0012) | 2 | OpenTelemetry + Micrometer instrumentation for ZP0011/ZP0012 batch operations | WBS 9.4. NFR-10 and OPS-13 require observability. Add OpenTelemetry tracing spans and Micrometer metrics to the batch flow in services/scheme-adapter-zeropay. Spans: zeropay.batch.zp0011.generate (root), child spans for file_assemble, sftp_transmit; zeropay.batch.zp0012.ingest (root), child spans for file_parse, line_match. Micrometer metrics (via MeterRegistry; Spring Boot 3 auto-configures Prometheus endpoint): Counter zeropay_batch_exception_total tags=[file_type, exception_type]; Gauge zeropay_batch_open_exceptions tags=[file_type]; Timer zeropay_batch_processing_seconds tags=[file_type, operation]. Use @WithSpan annotation (OpenTelemetry Spring instrumentation) or programmatic Tracer spans. All metric names underscore-separated per Prometheus convention. | • Confirm io.opentelemetry.instrumentation:opentelemetry-spring-boot-starter is in scheme-adapter-zeropay/build.gradle (add if absent). • Add @WithSpan('zeropay.batch.zp0011.generate') on Zp0011BatchJob.run(); add child @WithSpan on Zp0011FileAssembler.assemble() and SftpGatewayClient.transmit(). • Add @WithSpan('zeropay.batch.zp0012.ingest') on Zp0012InboundPoller.processFile(); child spans on Zp0012FileParser.parse() and Zp0012MatchingService.match(). • In BatchExceptionService.raise(): increment Counter zeropay_batch_exception_total with tags file_type and exception_type via meterRegistry.counter(...).increment(). • Register Gauge zeropay_batch_open_exceptions in BatchExceptionService @PostConstruct: Gauge.builder(...).register(meterRegistry) backed by countOpenExceptions() for each known file_type. • Wrap Zp0012FileParser.parse() and Zp0012MatchingService.match() in Timer.Sample to record zeropay_batch_processing_seconds. | Updated Zp0011BatchJob.java, Zp0012InboundPoller.java, Zp0012FileParser.java, Zp0012MatchingService.java, BatchExceptionService.java with span and metric instrumentation | • zeropay_batch_exception_total counter increments by 1 per BatchExceptionService.raise() call (verify with SimpleMeterRegistry in unit test). • zeropay_batch_open_exceptions gauge reflects current DB count when queried. • Root span zeropay.batch.zp0011.generate is created and closed (no unclosed spans) during Zp0011BatchJob.run(). • Timer zeropay_batch_processing_seconds recorded after each Zp0012MatchingService.match() call. • All metric names use underscores not dots. | 40 | 9.4-T07, 9.4-T10 | BE | SCH-06
9.4-T25 | scheme-adapter-zeropay | 9.4 | 9. QR Scheme Integration (ZeroPay) | Payment result exchange (ZP0011/0012) | 2 | application.yml: ZP0011/ZP0012 batch and SFTP configuration with @ConfigurationProperties | WBS 9.4. Externalize all runtime config for the ZP0011/ZP0012 batch into services/scheme-adapter-zeropay/src/main/resources/application.yml. Keys: zeropay.batch.zp0011.cron (default '0 0 2 * * *'), zeropay.batch.zp0012.poll-cron (default '0 */5 5 * * *'), zeropay.batch.zp0012.late-alert-cron (default '0 5 6 * * *'), zeropay.sftp.host, zeropay.sftp.port (default 22), zeropay.sftp.username, zeropay.sftp.outbound-dir (default /gmepay/outbound), zeropay.sftp.inbound-dir (default /gmepay/inbound), zeropay.sftp.private-key-vault-path (Vault path for private key; @NotBlank), zeropay.object-storage.endpoint, zeropay.object-storage.bucket (default zeropay-batch-files), zeropay.institution-code (@NotBlank). Sensitive values reference Vault. Create @ConfigurationProperties(prefix='zeropay') class ZeropayBatchProperties with nested SftpProperties and ObjectStorageProperties. application-local.yml for docker-compose MinIO+test SFTP. | • Create ZeropayBatchProperties @ConfigurationProperties(prefix='zeropay') @Validated in com.gme.pay.zeropay.config with nested static classes BatchProperties, SftpProperties, ObjectStorageProperties. • Add @NotBlank on zeropay.sftp.private-key-vault-path and zeropay.institution-code; bind all other fields with defaults. • Add @EnableConfigurationProperties(ZeropayBatchProperties.class) to ZeropayAdapterApplication or a @Configuration class. • Populate src/main/resources/application.yml with all keys, defaults, and Vault path placeholders for sensitive fields. • Create src/main/resources/application-local.yml with docker-compose overrides: MinIO endpoint, test SFTP host/port; add a binding test @SpringBootTest(properties=...) verifying no BindException. | services/scheme-adapter-zeropay/src/main/java/com/gme/pay/zeropay/config/ZeropayBatchProperties.java and src/main/resources/application.yml | • ZeropayBatchProperties binds without BindException in @SpringBootTest slice providing all required fields. • zeropay.batch.zp0011.cron defaults to '0 0 2 * * *' when not overridden. • Missing zeropay.sftp.private-key-vault-path causes ConstraintViolationException at startup (bean validation). • No credential or key material hardcoded in application.yml (only Vault path references). • application-local.yml provides working MinIO endpoint and SFTP test host overrides for docker-compose local dev. | 35 | 9.4-T07, 9.4-T08 | BE | SCH-06
9.5-T01 | scheme-adapter-zeropay | 9.5 | 9. QR Scheme Integration (ZeroPay) | Refund result exchange (ZP0021/0022) | 2 | Flyway migration: add ZP0021/ZP0022 columns to refund table | Module: services/settlement-reconciliation. The refund table (PostgreSQL 16, DAT-03 §5.4) currently has: id BIGINT PK, txn_id BIGINT FK, refund_ref VARCHAR(30), refund_amount NUMERIC(20,4), refund_ccy CHAR(3), reason VARCHAR(255), status VARCHAR(30), scheme_refund_ref VARCHAR(30), initiated_by VARCHAR(60). For the ZP0021/ZP0022 batch round-trip, three new columns are required: zp_batch_id BIGINT NULL FK -> settlement_batch(id) (links refund to its ZP0021 outbound batch row); zp_result_code CHAR(2) NULL (raw result_code from ZP0022: 00=Success, non-zero=failure); adjustment_settlement_date DATE NULL (the date ZeroPay will apply the merchant adjustment, from ZP0022). The refund.status CHECK constraint must accept all five lifecycle states: REFUND_PENDING (created, awaiting batch), REFUND_SUBMITTED (ZP0021 sent), REFUND_CONFIRMED (ZP0022 result_code=00), REFUND_FAILED (ZP0022 non-zero), REFUNDED (prefunding reversal complete for OVERSEAS; terminal). | • In services/settlement-reconciliation/src/main/resources/db/migration/ create VN__refund_zp_batch_columns.sql (N = next sequence number after existing migrations) • Add: ALTER TABLE refund ADD COLUMN zp_batch_id BIGINT NULL REFERENCES settlement_batch(id) • Add: ALTER TABLE refund ADD COLUMN zp_result_code CHAR(2) NULL • Add: ALTER TABLE refund ADD COLUMN adjustment_settlement_date DATE NULL • Drop existing status CHECK constraint and recreate accepting exactly: REFUND_PENDING, REFUND_SUBMITTED, REFUND_CONFIRMED, REFUND_FAILED, REFUNDED • Add index: CREATE INDEX idx_refund_zp_batch_id ON refund(zp_batch_id); CREATE INDEX idx_refund_status ON refund(status) | services/settlement-reconciliation/src/main/resources/db/migration/VN__refund_zp_batch_columns.sql | • Migration applies cleanly on a Testcontainers PostgreSQL 16 instance via Flyway with no existing refund rows • zp_batch_id FK insert referencing a non-existent settlement_batch(id) raises FK violation • status CHECK rejects a value not in the five listed states • Inserting a refund row with zp_batch_id=NULL, status='REFUND_PENDING' succeeds • idx_refund_status is visible in pg_indexes for the refund table after migration | 25 |  | BE | SCH-06
9.5-T02 | scheme-adapter-zeropay | 9.5 | 9. QR Scheme Integration (ZeroPay) | Refund result exchange (ZP0021/0022) | 2 | Define ZP0021Record, ZP0021Header, ZP0021Trailer, ZP0022Record Java model classes | Module: services/settlement-reconciliation (or lib-events for shared batch models). ZP0021 is the outbound refund result file (GME -> ZeroPay PPF, deadline ~02:00 KST). Detail record fields (SCH-06 §6.2): record_type CHAR(1) fixed 'D'; gme_refund_id CHAR(20); original_zeropay_txn_ref CHAR(20); gme_original_txn_id CHAR(20); merchant_id CHAR(10); refund_date LocalDate (YYYYMMDD KST); refund_time LocalTime (HHMMSS KST); refund_amount_krw BigDecimal (NUM(12), KRW 0 decimals); merchant_fee_adj_amt BigDecimal (NUM(12)); partner_type CHAR(1) D=Domestic/I=International; refund_reason_code CHAR(2); status_code CHAR(1) fixed 'R'. ZP0021Header: file_type CHAR(6) fixed 'ZP0021'; business_date LocalDate; gme_institution_code String(10); total_record_count int; total_refund_amount_krw BigDecimal. ZP0021Trailer: total_record_count int; control_sum BigDecimal. ZP0022 (ZeroPay -> GME, ~05:00 KST) detail record (SCH-06 §6.3): original_zeropay_txn_ref CHAR(20) (match key with refund_date); gme_refund_id CHAR(20); result_code CHAR(2) (00=Success); result_message String(100); registered_refund_amount BigDecimal NUM(12); adjustment_settlement_date LocalDate. All monetary fields use BigDecimal; all char fields validated in compact constructors. | • Create com/gme/pay/settlement/zeropay/batch/model/ZP0021Record.java as Java record with all detail fields • Create ZP0021Header.java as Java record; compact constructor validates file_type equals 'ZP0021' • Create ZP0021Trailer.java as Java record • Create ZP0022Record.java as Java record with all ZP0022 detail fields from context • In compact constructors: validate gme_refund_id.length() <= 20, original_zeropay_txn_ref.length() <= 20, merchant_id.length() <= 10; throw IllegalArgumentException on violation • Annotate all records with @JsonInclude(NON_NULL) from lib-api-contracts for optional serialization | services/settlement-reconciliation/src/main/java/com/gme/pay/settlement/zeropay/batch/model/ZP0021Record.java, ZP0021Header.java, ZP0021Trailer.java, ZP0022Record.java | • ZP0021Record construction with refund_amount_krw=BigDecimal('50000'), partner_type='I', status_code='R' succeeds • ZP0021Record construction with gme_refund_id of 21 chars throws IllegalArgumentException • ZP0022Record with result_code='00' and registered_refund_amount=BigDecimal('50000') constructs without error • ZP0021Header with file_type='ZP0011' throws IllegalArgumentException • All monetary fields are BigDecimal -- no int or long for amounts in any of the four classes | 35 | 9.5-T01 | BE | SCH-06
9.5-T03 | scheme-adapter-zeropay | 9.5 | 9. QR Scheme Integration (ZeroPay) | Refund result exchange (ZP0021/0022) | 2 | Implement RefundBatchQueryService: query REFUND_PENDING refunds for a KST business date | Module: services/settlement-reconciliation. Before generating ZP0021, the Settlement Engine queries refunds eligible for the batch. Rules: (1) refund.status = 'REFUND_PENDING'; (2) DATE(refund.created_at AT TIME ZONE 'Asia/Seoul') = kstDate (prior business day, e.g. 2026-06-04); (3) transaction.scheme_id resolves to ZeroPay (join refund -> transaction -> scheme where scheme.scheme_id = 'ZEROPAY'); (4) transaction.status IN ('APPROVED','SCHEME_APPROVED') -- excludes same-day cancels. Returns List<RefundBatchItem> DTO containing: refund_id (Long), refund_ref (String), refund_amount_krw (BigDecimal KRW), merchant_id (String), original_zeropay_txn_ref (= transaction.zeropay_txn_ref, String), gme_original_txn_id (Long), partner_type (String: 'D' for LOCAL, 'I' for OVERSEAS), refund_reason_code (String), refund_created_at (ZonedDateTime). Use lib-persistence JPA utilities. Annotate query method @Transactional(readOnly=true). | • Create com/gme/pay/settlement/zeropay/batch/RefundBatchItem.java as Java record with all fields listed in context • Create com/gme/pay/settlement/zeropay/batch/RefundBatchQueryService.java as @Service • Implement List<RefundBatchItem> findPendingForDate(LocalDate kstDate) using Spring Data @Query (JPQL or native) with join to transaction and partner • Filter: refund.status='REFUND_PENDING', DATE(created_at AT TIME ZONE 'Asia/Seoul')=:kstDate, scheme.scheme_id='ZEROPAY' • Map partner.type='LOCAL' -> partner_type='D'; partner.type='OVERSEAS' -> partner_type='I' • Log a WARN for any row where transaction.zeropay_txn_ref IS NULL (data integrity anomaly) and exclude that row from results | services/settlement-reconciliation/src/main/java/com/gme/pay/settlement/zeropay/batch/RefundBatchQueryService.java and RefundBatchItem.java | • findPendingForDate on a date with zero REFUND_PENDING refunds returns an empty list (not null) • findPendingForDate returns only rows with status=REFUND_PENDING, not REFUND_SUBMITTED or REFUND_CONFIRMED • A refund created at 2026-06-04T15:30:00 UTC (= 2026-06-05T00:30:00 KST) is returned by findPendingForDate(2026-06-05) and not by findPendingForDate(2026-06-04) • partner_type in RefundBatchItem is 'D' for LOCAL partner, 'I' for OVERSEAS partner • Rows where transaction.zeropay_txn_ref IS NULL are excluded from results and a WARN is logged | 40 | 9.5-T01 | BE | SCH-06
9.5-T04 | scheme-adapter-zeropay | 9.5 | 9. QR Scheme Integration (ZeroPay) | Refund result exchange (ZP0021/0022) | 2 | Implement ZP0021FileBuilder: assemble ZP0021File DTO from eligible refunds and mark REFUND_SUBMITTED | Module: services/settlement-reconciliation. ZP0021FileBuilder queries REFUND_PENDING refunds for the prior KST business date, maps each to ZP0021Record, and transitions their status to REFUND_SUBMITTED within the same @Transactional boundary. merchant_fee_adj_amt is the fee amount to be reversed: (refund_amount_krw * merchant_fee_rate) where merchant_fee_rate comes from the scheme merchant_fee_table config (JSON field by merchant type and partner_type). The assembled ZP0021File DTO holds: ZP0021Header (file_type='ZP0021', business_date=kstDate, gme_institution_code from SchemeConfig, total_record_count, total_refund_amount_krw=SUM), List<ZP0021Record>, ZP0021Trailer (total_record_count, control_sum=total_refund_amount_krw). After assembly, all included refund rows are updated to status='REFUND_SUBMITTED' and zp_batch_id is set (the settlement_batch row created in a subsequent step -- pass the batch id in). KRW amounts have 0 decimal places; reject any refund where refund_ccy != 'KRW' with IllegalArgumentException. | • Create com/gme/pay/settlement/zeropay/batch/ZP0021FileBuilder.java as @Service • Inject RefundBatchQueryService, SchemeConfigRepository, RefundRepository • Implement ZP0021File buildForDate(LocalDate kstDate, Long batchId) within @Transactional • Call RefundBatchQueryService.findPendingForDate(kstDate); if empty return ZP0021File with zero records • For each RefundBatchItem validate refund_ccy='KRW'; map to ZP0021Record including merchant_fee_adj_amt computation • Assemble header and trailer; bulk-update matching refund rows to status='REFUND_SUBMITTED' and zp_batch_id=batchId | services/settlement-reconciliation/src/main/java/com/gme/pay/settlement/zeropay/batch/ZP0021FileBuilder.java | • buildForDate returns ZP0021File with zero records when findPendingForDate is empty; header.total_record_count=0 and total_refund_amount_krw=0 • buildForDate for 3 REFUND_PENDING refunds of 10000, 20000, 30000 KRW returns header.total_refund_amount_krw=60000 and total_record_count=3 • All 3 included refunds are updated to status='REFUND_SUBMITTED' and zp_batch_id set to the passed batchId after the call • partner_type is 'D' for LOCAL partner refunds and 'I' for OVERSEAS refunds • A refund with refund_ccy='USD' causes IllegalArgumentException before any status update | 50 | 9.5-T02, 9.5-T03 | BE | SCH-06
9.5-T05 | scheme-adapter-zeropay | 9.5 | 9. QR Scheme Integration (ZeroPay) | Refund result exchange (ZP0021/0022) | 2 | Implement ZP0021Serializer: fixed-width UTF-8 serialization and SHA-256 checksum | Module: services/settlement-reconciliation. ZeroPay batch files use fixed-width ASCII/UTF-8, CRLF line endings. Field widths from SCH-06 §6.2: record_type CHAR(1); gme_refund_id right-padded to 20; original_zeropay_txn_ref right-padded to 20; gme_original_txn_id right-padded to 20; merchant_id right-padded to 10; refund_date DATE formatted YYYYMMDD (8); refund_time TIME formatted HHMMSS (6); refund_amount_krw zero-padded left to 12; merchant_fee_adj_amt zero-padded left to 12; partner_type CHAR(1); refund_reason_code right-padded to 2; status_code CHAR(1). Header: file_type right-padded to 6; business_date YYYYMMDD (8); gme_institution_code right-padded to 10; total_record_count zero-padded to 6; total_refund_amount_krw zero-padded to 14. Trailer: total_record_count zero-padded to 6; control_sum zero-padded to 14. Encoding: StandardCharsets.UTF_8. Checksum: SHA-256 hex over full file bytes. | • Create com/gme/pay/settlement/zeropay/batch/ZP0021Serializer.java as @Component • Implement byte[] serialize(ZP0021File file): write header line, each detail line, trailer line, each terminated with CRLF • Numeric fields: String.format('%0Nd', value.longValue()) for zero-padded widths • Char/string fields: String.format('%-Ns', value) for right-padded widths (space-pad) • Implement String computeChecksum(byte[] content): MessageDigest.getInstance('SHA-256'), return hex-encoded 64-char lowercase string • Add a private helper padRight(String val, int width) and padLeft(String val, int width, char pad) | services/settlement-reconciliation/src/main/java/com/gme/pay/settlement/zeropay/batch/ZP0021Serializer.java | • Serializing a ZP0021File with 0 records produces exactly 2 CRLF-terminated lines (header + trailer) • refund_amount_krw=50000 serializes as '000000050000' (12 chars zero-padded) • gme_refund_id='REF001' serializes as 'REF001 ' (20 chars, 14 trailing spaces) • control_sum in trailer equals total_refund_amount_krw in header for a single-record file • computeChecksum produces a 64-character lowercase hex SHA-256 string | 45 | 9.5-T04 | BE | SCH-06
9.5-T06 | scheme-adapter-zeropay | 9.5 | 9. QR Scheme Integration (ZeroPay) | Refund result exchange (ZP0021/0022) | 2 | Implement RefundBatchRepository: settlement_batch row lifecycle for ZP0021 and ZP0022 | Module: services/settlement-reconciliation. The settlement_batch table (PostgreSQL 16, DAT-03 §7.1) has: id BIGINT PK, scheme_id VARCHAR, file_type VARCHAR (ZP0021/ZP0022), direction VARCHAR (GME_TO_ZP/ZP_TO_GME), settlement_date DATE KST, status VARCHAR (PENDING/GENERATED/TRANSMITTED/RECEIVED/RECONCILED/ERROR), transaction_count INT, total_amount NUMERIC, total_amount_ccy CHAR(3), file_checksum VARCHAR(64), transmitted_at TIMESTAMPTZ, received_at TIMESTAMPTZ, reconciled_at TIMESTAMPTZ, error_detail TEXT. ZP0021 outbound: created with status=GENERATED before file upload, updated to TRANSMITTED on SFTP success. ZP0022 inbound: created with status=RECEIVED on file fetch, updated to RECONCILED after line-by-line match, or ERROR on parse failure. Use Spring Data JDBC (@Repository) -- no JPA for this performance-sensitive batch path. | • Create com/gme/pay/settlement/repository/RefundBatchRepository.java as Spring Data JDBC @Repository • Implement Long createOutboundBatch(LocalDate settlementDate, int recordCount, BigDecimal totalAmount, String fileChecksum): inserts row with file_type='ZP0021', direction='GME_TO_ZP', scheme_id='ZEROPAY', status='GENERATED'; returns generated id • Implement void markTransmitted(Long batchId, Instant transmittedAt): UPDATE status='TRANSMITTED', transmitted_at=:transmittedAt WHERE id=:batchId; assert 1 row updated • Implement Long createInboundBatch(LocalDate settlementDate, String fileChecksum): inserts ZP0022, ZP_TO_GME, RECEIVED • Implement void markReconciled(Long batchId, Instant reconciledAt): idempotent (UPDATE only if status != RECONCILED) • Implement void markError(Long batchId, String errorDetail): UPDATE status='ERROR', error_detail=:errorDetail | services/settlement-reconciliation/src/main/java/com/gme/pay/settlement/repository/RefundBatchRepository.java | • createOutboundBatch inserts a row with file_type='ZP0021', direction='GME_TO_ZP', status='GENERATED' (verified via Testcontainers PostgreSQL 16) • markTransmitted with a non-existent batchId throws IncorrectUpdateSemanticDataAccessException or equivalent (not silent) • createInboundBatch inserts a row with file_type='ZP0022', direction='ZP_TO_GME', status='RECEIVED' • markReconciled called twice for the same batchId is idempotent: reconciled_at is not overwritten on second call • file_checksum stored on the row matches the 64-char hex SHA-256 passed in | 35 | 9.5-T01 | BE | SCH-06
9.5-T07 | scheme-adapter-zeropay | 9.5 | 9. QR Scheme Integration (ZeroPay) | Refund result exchange (ZP0021/0022) | 2 | Implement ZP0022Parser: parse inbound ZP0022 fixed-width refund registration result file | Module: services/settlement-reconciliation. ZP0022 (ZeroPay -> GME PPF, ~05:00 KST) is a fixed-width file mirroring ZP0012 structure. Header: file_type CHAR(6) must equal 'ZP0022'; business_date DATE(8); total_record_count NUM(6). Detail record: original_zeropay_txn_ref CHAR(20) (match key together with refund_date from ZP0021); gme_refund_id CHAR(20); result_code CHAR(2) (00=Success, any non-zero=failure; do NOT coerce to boolean); result_message right-padded to 100; registered_refund_amount NUM(12) BigDecimal; adjustment_settlement_date DATE(8). Trailer: total_record_count NUM(6); control_sum NUM(14). Validation rules (reject entire file on failure, throw SchemeBatchException from lib-errors): (1) header file_type != 'ZP0022'; (2) parsed record count != trailer total_record_count; (3) SUM(registered_refund_amount) != trailer control_sum. SchemeBatchException must carry fileType='ZP0022' and a descriptive message. | • Create com/gme/pay/settlement/zeropay/batch/ZP0022Parser.java as @Component • Create ZP0022ParseResult.java record: ZP0021Header-like header, List<ZP0022Record> records • Implement ZP0022ParseResult parse(byte[] fileContent): decode UTF-8, split by CRLF • Validate header line: fileType substring == 'ZP0022'; throw SchemeBatchException if wrong • Parse each detail line by fixed-width offsets matching field widths in context into ZP0022Record • After all records parsed: compare count vs trailer total_record_count; compare SUM vs trailer control_sum; throw SchemeBatchException with message 'record count mismatch' or 'control sum mismatch' as applicable | services/settlement-reconciliation/src/main/java/com/gme/pay/settlement/zeropay/batch/ZP0022Parser.java and ZP0022ParseResult.java | • Well-formed file with 2 records returns ZP0022ParseResult with exactly 2 ZP0022Record objects with correct field values • Trailer total_record_count=3 but only 2 detail records throws SchemeBatchException with message containing 'record count' • control_sum=99999 but SUM(registered_refund_amount)=50000 throws SchemeBatchException with message containing 'control sum' • Header file_type='ZP0021' throws SchemeBatchException before any detail record is parsed • result_code='03' on a record is returned as the raw string '03' with no coercion | 45 | 9.5-T02 | BE | SCH-06
9.5-T08 | scheme-adapter-zeropay | 9.5 | 9. QR Scheme Integration (ZeroPay) | Refund result exchange (ZP0021/0022) | 2 | Implement ZP0021BatchJob: Spring @Scheduled cron job to generate and transmit ZP0021 | Module: services/settlement-reconciliation. The batch scheduler runs ZP0021BatchJob at 02:00 KST daily (@Scheduled cron='0 0 2 * * *', zone='Asia/Seoul'). Flow: (1) compute priorBusinessDay = LocalDate.now(ZoneId.of('Asia/Seoul')).minusDays(1); (2) idempotency guard -- if settlement_batch row with file_type='ZP0021', settlement_date=priorBusinessDay, status IN ('GENERATED','TRANSMITTED') already exists, log WARN and return; (3) call RefundBatchQueryService.findPendingForDate; if empty list, log INFO and return without creating batch row; (4) call RefundBatchRepository.createOutboundBatch to get batchId; (5) call ZP0021FileBuilder.buildForDate(priorBusinessDay, batchId) -- this also marks refunds REFUND_SUBMITTED; (6) call ZP0021Serializer.serialize; (7) upload via ZeroPaySftpGateway.uploadOutbound(filename, bytes) where filename = 'ZP0021_'+institutionCode+'_'+date.format(YYYYMMDD)+'.dat'; (8) on success call RefundBatchRepository.markTransmitted; (9) on SchemeConnectivityException call markError + send Ops alert via OpsAlertPublisher. | • Create com/gme/pay/settlement/batch/ZP0021BatchJob.java as @Component • Annotate with @Scheduled(cron='0 0 2 * * *', zone='Asia/Seoul'); ensure @EnableScheduling on application @Configuration • Inject RefundBatchQueryService, ZP0021FileBuilder, ZP0021Serializer, RefundBatchRepository, ZeroPaySftpGateway, OpsAlertPublisher, SchemeConfigRepository (for institutionCode) • Implement idempotency guard using RefundBatchRepository.findByFileTypeAndDate(ZP0021, priorBusinessDay) • Wrap SFTP upload in try-catch SchemeConnectivityException; propagate other runtime exceptions • Log structured JSON at INFO: job_name=ZP0021BatchJob, settlement_date, record_count, total_amount_krw on completion | services/settlement-reconciliation/src/main/java/com/gme/pay/settlement/batch/ZP0021BatchJob.java | • Existing TRANSMITTED batch for priorBusinessDay causes job to log WARN and return without calling SFTP or creating new batch row • findPendingForDate returning empty list causes job to return without creating any settlement_batch row or calling SFTP • SchemeConnectivityException on SFTP upload results in settlement_batch.status=ERROR and OpsAlertPublisher.publishBatchError called • Cron expression '0 0 2 * * *' with zone 'Asia/Seoul' confirmed to fire at 02:00:00 KST by CronExpression.parse unit assertion • After normal run all included refunds have status='REFUND_SUBMITTED' and zp_batch_id set to the new batch id | 55 | 9.5-T04, 9.5-T05, 9.5-T06 | BE | SCH-06
9.5-T09 | scheme-adapter-zeropay | 9.5 | 9. QR Scheme Integration (ZeroPay) | Refund result exchange (ZP0021/0022) | 2 | Implement ZP0022InboundProcessor: fetch ZP0022 from SFTP, parse, reconcile, and mark batch | Module: services/settlement-reconciliation. ZP0022InboundProcessor.processForDate(LocalDate kstDate) is called by the morning cron at ~05:00 KST. Flow: (1) idempotency guard -- if settlement_batch with file_type='ZP0022', settlement_date=kstDate, status NOT IN ('ERROR') already exists, log WARN and return; (2) call ZeroPaySftpGateway.fetchInbound(ZP0022, kstDate) -> Optional<byte[]>; if empty, log WARN 'ZP0022 not yet available for kstDate' and return (no batch row yet; retry on next poll); (3) create inbound batch row via RefundBatchRepository.createInboundBatch; (4) call ZP0022Parser.parse(bytes); on SchemeBatchException call markError(batchId, message) and send Ops alert, rethrow; (5) call ZP0022ReconciliationService.reconcile(batchId, parseResult.records(), kstDate); (6) call markReconciled(batchId, Instant.now()). Entire process is @Transactional except the SFTP fetch. | • Create com/gme/pay/settlement/batch/ZP0022InboundProcessor.java as @Service • Implement processForDate(LocalDate kstDate): public entry point • Add idempotency check via RefundBatchRepository.findByFileTypeAndDate('ZP0022', kstDate) • Call ZeroPaySftpGateway.fetchInbound; handle Optional.empty() as described • Create batch row, parse, reconcile, mark RECONCILED in sequence • Wrap parse and reconcile in try-catch; on any exception call markError + OpsAlertPublisher.publishBatchError(ZP0022, kstDate, message) | services/settlement-reconciliation/src/main/java/com/gme/pay/settlement/batch/ZP0022InboundProcessor.java | • processForDate when RECONCILED batch already exists logs WARN and makes no DB changes or SFTP calls • processForDate when SFTP returns Optional.empty() logs WARN and returns without creating batch row • SchemeBatchException from parse sets batch status=ERROR and triggers OpsAlertPublisher call; reconciliation is not attempted • processForDate on valid file creates exactly one inbound batch row and transitions it to RECONCILED • Two concurrent calls to processForDate for the same date result in exactly one batch row (idempotency guard prevents second insert) | 50 | 9.5-T06, 9.5-T07 | BE | SCH-06
9.5-T10 | scheme-adapter-zeropay | 9.5 | 9. QR Scheme Integration (ZeroPay) | Refund result exchange (ZP0021/0022) | 2 | Implement ZP0022ReconciliationService: line-by-line ZP0022 vs ZP0021 match with all five mismatch branches | Module: services/settlement-reconciliation. After ZP0022 is parsed, each ZP0022Record is matched against REFUND_SUBMITTED refunds in PostgreSQL using match key (original_zeropay_txn_ref, refund_date). Five outcomes from SCH-06 §6.4 (same logic as ZP0012/ZP0011 for payments): (1) result_code='00' and registered_refund_amount = refund.refund_amount_krw -> mark refund status='REFUND_CONFIRMED', store zp_result_code='00', store adjustment_settlement_date; (2) result_code non-zero -> mark refund status='REFUND_FAILED', store zp_result_code, insert reconciliation_item (match_status='DISCREPANCY', resolution_status='UNRESOLVED'); (3) REFUND_SUBMITTED refund with no matching ZP0022Record -> insert reconciliation_item (match_status='MISSING_SCHEME'); (4) ZP0022Record not matching any GME refund -> insert reconciliation_item (match_status='MISSING_GME'); (5) result_code='00' but registered_refund_amount != refund.refund_amount_krw (zero tolerance per SCH-06 §9.1) -> insert reconciliation_item (match_status='DISCREPANCY', sub-type REGISTRATION_AMOUNT_MISMATCH). reconciliation_item table fields: id, batch_id, txn_ref (gme_refund_id), scheme_ref (original_zeropay_txn_ref), match_status, gme_amount NUMERIC, scheme_amount NUMERIC, discrepancy_amount NUMERIC, ccy='KRW', resolution_status, resolved_by, resolved_at, resolution_note. | • Create com/gme/pay/settlement/zeropay/batch/ZP0022ReconciliationService.java as @Service • Implement @Transactional void reconcile(Long inboundBatchId, List<ZP0022Record> zp0022Records, LocalDate settlementDate) • Load all REFUND_SUBMITTED refunds linked to the ZP0021 batch for settlementDate into a Map<String, Refund> keyed by original_zeropay_txn_ref • For each ZP0022Record: look up in map; apply branch logic from context; update refund fields via RefundRepository; insert reconciliation_item rows via ReconciliationItemRepository if applicable • After processing ZP0022Records: for each remaining (unmatched) REFUND_SUBMITTED refund in the map, insert reconciliation_item with match_status='MISSING_SCHEME' • Inject PrefundingReversalService but do NOT call it here -- REFUND_CONFIRMED -> REFUNDED wiring is in a separate ticket (9.5-T12) | services/settlement-reconciliation/src/main/java/com/gme/pay/settlement/zeropay/batch/ZP0022ReconciliationService.java | • ZP0022Record result_code='00' with matching amount -> refund.status='REFUND_CONFIRMED' and zp_result_code='00' and adjustment_settlement_date stored; no reconciliation_item • ZP0022Record result_code='03' -> refund.status='REFUND_FAILED' and one reconciliation_item with match_status='DISCREPANCY' and resolution_status='UNRESOLVED' • REFUND_SUBMITTED refund absent from ZP0022 -> reconciliation_item with match_status='MISSING_SCHEME' inserted • ZP0022Record with original_zeropay_txn_ref not matching any GME refund -> reconciliation_item with match_status='MISSING_GME' • ZP0022Record result_code='00' but registered_refund_amount=49999 vs submitted 50000 -> reconciliation_item match_status='DISCREPANCY' inserted and refund.status is NOT REFUND_CONFIRMED | 55 | 9.5-T07, 9.5-T06, 9.5-T03 | BE | SCH-06
9.5-T11 | scheme-adapter-zeropay | 9.5 | 9. QR Scheme Integration (ZeroPay) | Refund result exchange (ZP0021/0022) | 2 | Implement PrefundingReversalService: credit OVERSEAS prefunding balance on REFUND_CONFIRMED | Module: services/prefunding-balance. For OVERSEAS partners (partner.type='OVERSEAS'), when a refund is confirmed by ZeroPay (status='REFUND_CONFIRMED'), the partner's prepaid USD balance must be credited (reversed) by transaction.prefunding_deducted_usd (the USD amount debited at original payment time, stored at rate-lock). The credit is atomic: SELECT ... FOR UPDATE on prefunding_account WHERE partner_id=:partnerId; insert prefunding_ledger_entry (entry_type='CREDIT_REVERSAL', amount=transaction.prefunding_deducted_usd, txn_ref=original txn_ref, refund_ref=refund.refund_ref, created_at=now()); increment prefunding_account.balance by prefunding_deducted_usd. For LOCAL partners (partner.type='LOCAL'): no prefunding account exists; skip ledger entry. In both cases: update refund.status from 'REFUND_CONFIRMED' to 'REFUNDED'. Guard: if refund.status != 'REFUND_CONFIRMED' throw IllegalStateException (prevents double-reversal). All operations within @Transactional. | • Create com/gme/pay/prefunding/PrefundingReversalService.java as @Service in services/prefunding-balance module • Implement @Transactional void reverseForRefund(Long refundId) • Load refund, guard status == 'REFUND_CONFIRMED' else throw IllegalStateException('Expected REFUND_CONFIRMED but was: ' + status) • Load transaction, load partner; if partner.type='OVERSEAS': SELECT FOR UPDATE on prefunding_account; insert prefunding_ledger_entry; UPDATE balance = balance + :amount • Update refund.status = 'REFUNDED' • Publish domain event RefundReversedEvent via EventPublisher interface (lib-events Outbox pattern) with refund_ref, partner_id, amount_usd, timestamp | services/prefunding-balance/src/main/java/com/gme/pay/prefunding/PrefundingReversalService.java | • OVERSEAS partner with prefunding_deducted_usd=36.9714: after reverseForRefund, prefunding_account.balance increases by exactly 36.9714 (BigDecimal equality, no floating-point loss) • OVERSEAS partner: one prefunding_ledger_entry row inserted with entry_type='CREDIT_REVERSAL' and amount=36.9714 • LOCAL partner: no prefunding_ledger_entry row inserted; refund.status becomes 'REFUNDED' • Calling reverseForRefund with refund.status='REFUNDED' throws IllegalStateException containing 'REFUNDED' • Concurrent calls to reverseForRefund for same refundId result in exactly one ledger entry (SELECT FOR UPDATE prevents double credit) | 50 | 9.5-T01 | BE | SCH-06
9.5-T12 | scheme-adapter-zeropay | 9.5 | 9. QR Scheme Integration (ZeroPay) | Refund result exchange (ZP0021/0022) | 2 | Wire REFUND_CONFIRMED -> prefunding reversal -> REFUNDED within ZP0022ReconciliationService | Module: services/settlement-reconciliation. After ZP0022ReconciliationService marks a refund 'REFUND_CONFIRMED' (result_code='00', amounts match), PrefundingReversalService.reverseForRefund must be called immediately. Both operations must be within the same @Transactional boundary so a reversal failure rolls back the REFUND_CONFIRMED update and leaves the refund in 'REFUND_SUBMITTED' for retry. If PrefundingReversalService throws RuntimeException, catch it, re-throw to trigger rollback. ZP0022InboundProcessor (the caller) does not need to know about prefunding internals. The REFUND_FAILED path must NOT call reverseForRefund. LOCAL partners: reverseForRefund is a no-op for prefunding but still transitions status to REFUNDED, so call it for both partner types. | • Inject PrefundingReversalService into ZP0022ReconciliationService (already wired in 9.5-T10 stub) • In the result_code='00' + amounts-match branch, after updating refund.status='REFUND_CONFIRMED', immediately call prefundingReversalService.reverseForRefund(refund.id) • PrefundingReversalService.reverseForRefund will internally transition REFUND_CONFIRMED -> REFUNDED -- the reconciliation service should not also set REFUNDED • Wrap the reverseForRefund call in a try-catch RuntimeException; re-throw to ensure @Transactional rollback propagates • Add integration test asserting atomicity: stub PrefundingReversalService to throw; verify refund remains REFUND_SUBMITTED | Updated ZP0022ReconciliationService.java with PrefundingReversalService injection and atomic call in the success branch | • Processing successful ZP0022Record for OVERSEAS partner results in refund.status='REFUNDED' (not REFUND_CONFIRMED) after reconcile() returns • Processing successful ZP0022Record for LOCAL partner results in refund.status='REFUNDED' and no prefunding_ledger_entry row • PrefundingReversalService throwing RuntimeException causes full rollback; refund remains 'REFUND_SUBMITTED' after the exception • Processing REFUND_FAILED branch (result_code non-zero) does not call reverseForRefund • reconcile() calls reverseForRefund exactly once per successfully confirmed record | 40 | 9.5-T10, 9.5-T11 | BE | SCH-06
9.5-T13 | scheme-adapter-zeropay | 9.5 | 9. QR Scheme Integration (ZeroPay) | Refund result exchange (ZP0021/0022) | 2 | Implement ReconciliationItemRepository: insert and query reconciliation exception items | Module: services/settlement-reconciliation. The reconciliation_item table (PostgreSQL 16, DAT-03 §7.3) stores batch exception records. Columns: id BIGINT PK, batch_id BIGINT FK -> settlement_batch(id), txn_ref VARCHAR (gme_refund_id for refund exceptions), scheme_ref VARCHAR (original_zeropay_txn_ref), match_status VARCHAR (MATCHED/DISCREPANCY/MISSING_GME/MISSING_SCHEME), gme_amount NUMERIC(20,4), scheme_amount NUMERIC(20,4), discrepancy_amount NUMERIC(20,4) = ABS(gme_amount - scheme_amount), ccy CHAR(3), resolution_status VARCHAR (UNRESOLVED/RESOLVED/ESCALATED), resolved_by VARCHAR, resolved_at TIMESTAMPTZ, resolution_note TEXT, created_at TIMESTAMPTZ DEFAULT now(). Use Spring Data JDBC. ReconciliationItem is a Java record. | • Create com/gme/pay/settlement/repository/ReconciliationItemRepository.java as Spring Data JDBC @Repository • Create ReconciliationItem.java record with all table columns • Implement void insertItem(ReconciliationItem item): inserts row • Implement List<ReconciliationItem> findUnresolvedForBatch(Long batchId): returns all rows with batch_id=:batchId and resolution_status='UNRESOLVED' • Implement void markResolved(Long itemId, String resolvedBy, Instant resolvedAt, String resolutionNote): UPDATE resolution_status='RESOLVED' etc. • Compute discrepancy_amount in insertItem as ABS(item.gmeAmount().subtract(item.schemeAmount())) | services/settlement-reconciliation/src/main/java/com/gme/pay/settlement/repository/ReconciliationItemRepository.java and ReconciliationItem.java | • insertItem for a DISCREPANCY item with gme_amount=50000 and scheme_amount=49999 stores discrepancy_amount=1 • findUnresolvedForBatch returns only UNRESOLVED items for the given batch_id • markResolved sets resolution_status='RESOLVED' and resolved_by and resolved_at on the target row • insertItem with match_status='MISSING_GME' inserts row with txn_ref=NULL (no GME record to link) • Calling insertItem twice with same batch_id + scheme_ref does not throw (upsert or allow duplicate -- reconciliation may process same file twice) | 30 | 9.5-T01 | BE | SCH-06
9.5-T14 | scheme-adapter-zeropay | 9.5 | 9. QR Scheme Integration (ZeroPay) | Refund result exchange (ZP0021/0022) | 2 | Implement OpsAlertPublisher: send reconciliation failure alerts via Outbox domain event | Module: services/settlement-reconciliation (publishes); services/notification-webhook (consumes). When ZP0022 reconciliation has UNRESOLVED items or a batch job errors, OpsAlertPublisher emits a domain event to the transactional Outbox table (lib-events pattern). Event type: BatchReconciliationAlert with fields: alert_type (REFUND_REGISTRATION_FAILURE/BATCH_JOB_ERROR/INBOUND_PROCESSOR_FAILED), scheme_id='ZEROPAY', file_type (ZP0021/ZP0022), settlement_date, unresolved_count (int), error_detail (String), created_at. The Outbox row is inserted in the same @Transactional scope as the reconciliation update so the alert is never lost. The EventPublisher interface from lib-events is used (in-process/outbox-polling impl for Phase 1; Kafka wired later without code changes). SCH-06 §9.5: ZP0021/ZP0022 outbound cutoff is 02:00 KST; inbound wait cutoff is 06:00 KST; exceeding these triggers P1 Ops notification. | • Create com/gme/pay/settlement/alert/OpsAlertPublisher.java as @Service in services/settlement-reconciliation • Inject EventPublisher from lib-events • Implement void publishBatchError(String fileType, LocalDate settlementDate, String errorDetail): build BatchReconciliationAlert event, call eventPublisher.publish(event) • Implement void publishRefundReconciliationExceptions(Long batchId, LocalDate settlementDate, int unresolvedCount): build BatchReconciliationAlert with alert_type='REFUND_REGISTRATION_FAILURE' • In ZP0022ReconciliationService.reconcile(), after processing all records, call publishRefundReconciliationExceptions if unresolvedCount > 0 • Outbox insert must be within the same @Transactional scope as refund status updates | services/settlement-reconciliation/src/main/java/com/gme/pay/settlement/alert/OpsAlertPublisher.java wired to lib-events EventPublisher Outbox | • publishRefundReconciliationExceptions with unresolvedCount=3 inserts one Outbox row of type BatchReconciliationAlert within the same transaction • publishRefundReconciliationExceptions with unresolvedCount=0 does NOT insert an Outbox row • publishBatchError inserts Outbox row with alert_type='BATCH_JOB_ERROR' and correct file_type and error_detail • If the enclosing @Transactional is rolled back, the Outbox row is also rolled back (same transaction scope) • The BatchReconciliationAlert event schema is defined in lib-events/src/main/avro/ or equivalent JSON schema resource | 40 | 9.5-T10, 9.5-T13 | BE | SCH-06
9.5-T15 | scheme-adapter-zeropay | 9.5 | 9. QR Scheme Integration (ZeroPay) | Refund result exchange (ZP0021/0022) | 2 | Implement ZeroPaySftpGateway: uploadOutbound and fetchInbound for ZP0021/ZP0022 | Module: services/scheme-adapter-zeropay. The SFTP Gateway service handles all ZeroPay SFTP I/O. File naming (SCH-06 §2.3.3): {FILE_ID}_{YYYYMMDD}_{SEQUENCE}.dat (e.g. ZP0021_20261015_01.dat). Remote directory structure (SCH-06 §2.3.4): outbound files go to SchemeConfig.outbound_dir; inbound files are fetched from SchemeConfig.inbound_dir. SFTP authentication uses the RSA private key from Vault/KMS (schemeConfig.sftp_private_key_ref). Transfer process from SCH-06 §2.4: upload -> verify remote checksum/size; retry up to 3 times with exponential back-off (30s, 2min, 10min) before throwing SchemeConnectivityException. fetchInbound: SFTP list inbound_dir for filename matching fileType+businessDate pattern; if absent return Optional.empty(); if present download bytes; PGP decrypt using GME private key (pgp_private_key_ref from Vault). Use JSch or Apache MINA SSHD for SFTP. | • In services/scheme-adapter-zeropay create com/gme/pay/scheme/zeropay/sftp/ZeroPaySftpGateway.java as @Service • Implement byte[] uploadOutbound(String fileType, LocalDate businessDate, byte[] content, SchemeConfig config): generates filename, PGP-encrypts with schemeConfig.pgp_public_key_ref, SFTPs to outbound_dir, verifies transfer • Implement Optional<byte[]> fetchInbound(String fileType, LocalDate businessDate, SchemeConfig config): list inbound_dir, if absent return Optional.empty(), download, PGP-decrypt, return bytes • Add retry logic: 3 attempts with 30s/2min/10min intervals; throw SchemeConnectivityException after all retries exhausted • Retrieve private keys from Vault using VaultTemplate injected from Spring Vault (spring-vault-core dependency) • Log transfer metadata at INFO: filename, bytes, SHA-256 checksum, timestamp on each successful transfer | services/scheme-adapter-zeropay/src/main/java/com/gme/pay/scheme/zeropay/sftp/ZeroPaySftpGateway.java | • uploadOutbound with a valid file succeeds and returns normally with no exception (verified by WireMock SFTP stub or embedded SFTP server in test) • uploadOutbound when all 3 retry attempts fail throws SchemeConnectivityException • fetchInbound when file is not in inbound_dir returns Optional.empty() with no exception • fetchInbound when file is present returns Optional.of(decrypted bytes) • Filename generated by uploadOutbound follows pattern ZP0021_{YYYYMMDD}_01.dat for the given businessDate | 55 | 9.5-T08 | BE | SCH-06
9.5-T16 | scheme-adapter-zeropay | 9.5 | 9. QR Scheme Integration (ZeroPay) | Refund result exchange (ZP0021/0022) | 2 | Wire ZP0022 inbound poll into morning BatchScheduler cron at 05:00 KST | Module: services/settlement-reconciliation. The BatchScheduler runs multiple cron jobs. ZP0022 poll must run at ~05:00 KST independently from ZP0012 (payment result) so a ZP0022 failure does not block ZP0012 processing. Both ZP0022InboundProcessor.processForDate and ZP0012InboundProcessor.processForDate are called in the same @Scheduled method runMorningInboundBatch() but each in its own try-catch. ZP0022 and ZP0012 each report errors independently. The prior business day in KST is: LocalDate.now(ZoneId.of('Asia/Seoul')).minusDays(1). Spring @EnableScheduling must be on the main application @Configuration. Each processor call is logged at INFO with structured fields: processor, settlement_date, elapsed_ms. | • Create or update com/gme/pay/settlement/batch/BatchScheduler.java as @Component in services/settlement-reconciliation • Annotate runMorningInboundBatch() with @Scheduled(cron='0 0 5 * * *', zone='Asia/Seoul') • Within method: in try-catch #1 call ZP0012InboundProcessor.processForDate(priorDay); catch Exception, log ERROR, call OpsAlertPublisher.publishBatchError • In try-catch #2 call ZP0022InboundProcessor.processForDate(priorDay); catch Exception, log ERROR, call OpsAlertPublisher.publishBatchError • Add MDC context: job_name=morningInboundBatch, settlement_date for structured logging (OpenTelemetry-compatible) • Ensure @EnableScheduling is on the services/settlement-reconciliation application @SpringBootApplication class | services/settlement-reconciliation/src/main/java/com/gme/pay/settlement/batch/BatchScheduler.java with independent try-catch for ZP0012 and ZP0022 processors in the 05:00 KST cron | • ZP0022InboundProcessor.processForDate throwing RuntimeException is caught; ZP0012 processing still proceeds (verified by unit test that stubs ZP0022 to throw) • Cron '0 0 5 * * *' with zone 'Asia/Seoul' fires at 05:00:00 KST (verified by CronExpression.parse assertion) • OpsAlertPublisher.publishBatchError is called with fileType='ZP0022' when ZP0022 throws • Structured log on entry to runMorningInboundBatch includes settlement_date field • ZP0012 failure does not prevent ZP0022 call (symmetric independence) | 30 | 9.5-T09 | BE | SCH-06
9.5-T17 | scheme-adapter-zeropay | 9.5 | 9. QR Scheme Integration (ZeroPay) | Refund result exchange (ZP0021/0022) | 2 | Unit tests: ZP0021FileBuilder -- empty batch, normal batch, status filter, currency guard | Module: services/settlement-reconciliation. Test class: ZP0021FileBuilderTest using JUnit 5 and Mockito. Test vectors: (1) RefundBatchQueryService.findPendingForDate returns empty list -> ZP0021File.records is empty, header.total_record_count=0, header.total_refund_amount_krw=0, RefundRepository.bulkUpdateStatus never called. (2) Three REFUND_PENDING refunds of 10000/20000/30000 KRW, partner_types D/I/I -> header.total_refund_amount_krw=60000, total_record_count=3, all three ZP0021Records have correct partner_type and status_code='R'. (3) Mix: query only returns REFUND_PENDING rows (mock returns 2 of 3 rows) -> only 2 records in file. (4) RefundBatchItem with refund_ccy='USD' -> IllegalArgumentException thrown before any records assembled or statuses updated. | • Create services/settlement-reconciliation/src/test/java/com/gme/pay/settlement/zeropay/batch/ZP0021FileBuilderTest.java • Use @ExtendWith(MockitoExtension.class); mock RefundBatchQueryService and RefundRepository • Test vector 1: empty query result • Test vector 2: three refunds, assert header sums and ZP0021Record fields • Test vector 3: two of three returned by query mock, assert only 2 records in output • Test vector 4: one item has refund_ccy='USD', assert IllegalArgumentException and verify RefundRepository.bulkUpdateStatus is never invoked | services/settlement-reconciliation/src/test/java/com/gme/pay/settlement/zeropay/batch/ZP0021FileBuilderTest.java with four test scenarios | • Vector 1 passes: ZP0021File.records().isEmpty() and header total counts both zero • Vector 2 passes: header.total_refund_amount_krw = BigDecimal('60000') and exactly 3 ZP0021Records • Vector 3 passes: only 2 records in result when query returns 2 items • Vector 4 passes: IllegalArgumentException thrown; verify(refundRepository, never()).bulkUpdateStatus(any()) • All four tests pass under mvn test with no Mockito warnings | 35 | 9.5-T04 | BE | SCH-06
9.5-T18 | scheme-adapter-zeropay | 9.5 | 9. QR Scheme Integration (ZeroPay) | Refund result exchange (ZP0021/0022) | 2 | Unit tests: ZP0021Serializer -- field padding, zero-record file, checksum | Module: services/settlement-reconciliation. Test class: ZP0021SerializerTest using JUnit 5. Test vectors: (1) Single record with gme_refund_id='REF001' (6 chars) -> field substring at offset in serialized bytes equals 'REF001 ' (20 chars, 14 trailing spaces). (2) refund_amount_krw=50000 -> substring '000000050000' (12 chars zero-padded). (3) Zero-record file: serialize ZP0021File with empty records list -> output split by CRLF has exactly 2 non-empty lines (header + trailer). (4) computeChecksum on byte[] {0x41, 0x42} ('AB') -> known SHA-256 = '58bb119c35513a451d24dc20ef0e9031ec85b35bfc919d263e7e5d9868909cb5' (verify with MessageDigest). (5) header total_refund_amount_krw=50000 serialized as '00000000050000' (14 chars). (6) Trailer control_sum for two records of 30000+20000 = '00000000050000'. | • Create ZP0021SerializerTest.java in test source • Instantiate ZP0021Serializer directly (no Spring context needed) • Build ZP0021File test fixtures using the model classes from 9.5-T02 • Assert exact substring values at known byte offsets for vectors 1 and 2 • Assert line count for vector 3 • Assert computeChecksum result for vector 4 equals the known constant • Assert header and trailer numeric field values for vectors 5 and 6 | services/settlement-reconciliation/src/test/java/com/gme/pay/settlement/zeropay/batch/ZP0021SerializerTest.java with six assertions | • Vector 1: gme_refund_id field in output is exactly 'REF001 ' (20-char right-padded) • Vector 2: refund_amount_krw=50000 serializes as '000000050000' • Vector 3: 0-record file output has exactly 2 non-empty lines when split by CRLF • Vector 4: computeChecksum('AB' bytes) equals known SHA-256 constant (64 lowercase hex chars) • Vector 5 and 6: header and trailer 14-char numeric fields are '00000000050000' for total=50000 | 30 | 9.5-T05 | BE | SCH-06
9.5-T19 | scheme-adapter-zeropay | 9.5 | 9. QR Scheme Integration (ZeroPay) | Refund result exchange (ZP0021/0022) | 2 | Unit tests: ZP0022Parser -- success, count mismatch, control sum mismatch, wrong file type, mixed result codes | Module: services/settlement-reconciliation. Test class: ZP0022ParserTest using JUnit 5. Build a helper buildZP0022Bytes(header, List<ZP0022Record>, trailer) to generate test file bytes. Test vectors: (1) Well-formed 2-record file (result_code='00'/'03') -> parse returns 2 ZP0022Records with correct fields. (2) Trailer total_record_count=3 but 2 detail records -> SchemeBatchException message contains 'record count'. (3) Trailer control_sum=99999 but SUM(registered_refund_amount)=50000 -> SchemeBatchException message contains 'control sum'. (4) Header file_type='ZP0021' -> SchemeBatchException thrown before any detail record parsed. (5) Mixed result codes: first record '00', second record '03' -> both returned as raw strings; no coercion. | • Create ZP0022ParserTest.java in test source • Implement private byte[] buildZP0022Bytes(Map header, List<Map> records, Map trailer) producing valid fixed-width UTF-8 file bytes • Vector 1: well-formed file, assert 2 records with expected field values • Vector 2: manipulate trailer count, assert SchemeBatchException • Vector 3: manipulate control_sum, assert SchemeBatchException • Vector 4: wrong file_type in header, assert SchemeBatchException • Vector 5: two records with different result_codes, assert both present and raw | services/settlement-reconciliation/src/test/java/com/gme/pay/settlement/zeropay/batch/ZP0022ParserTest.java with five test vectors | • Vector 1: ZP0022ParseResult.records().size()==2 and first record result_code=='00' • Vector 2: SchemeBatchException.getMessage() contains 'record count' • Vector 3: SchemeBatchException.getMessage() contains 'control sum' • Vector 4: SchemeBatchException thrown when file_type='ZP0021' • Vector 5: second record result_code=='03' returned as raw String without coercion | 35 | 9.5-T07 | BE | SCH-06
9.5-T20 | scheme-adapter-zeropay | 9.5 | 9. QR Scheme Integration (ZeroPay) | Refund result exchange (ZP0021/0022) | 2 | Unit tests: ZP0022ReconciliationService -- all five mismatch branches | Module: services/settlement-reconciliation. Test class: ZP0022ReconciliationServiceTest using JUnit 5 and Mockito. Test vectors (exact amounts): (1) ZP0022Record original_zeropay_txn_ref='ZPREF001', result_code='00', registered_refund_amount=50000, matching REFUND_SUBMITTED OVERSEAS refund of 50000 KRW -> refund.status='REFUNDED' (after PrefundingReversalService called), no reconciliation_item. (2) ZP0022Record result_code='03' for 'ZPREF002' -> refund.status='REFUND_FAILED', one reconciliation_item match_status='DISCREPANCY'. (3) REFUND_SUBMITTED refund 'ZPREF003' with no ZP0022Record -> reconciliation_item match_status='MISSING_SCHEME', resolution_status='UNRESOLVED'. (4) ZP0022Record 'ZPREF999' not matching any GME refund -> reconciliation_item match_status='MISSING_GME'. (5) result_code='00' but registered_refund_amount=49999 vs submitted 50000 -> reconciliation_item match_status='DISCREPANCY' and refund NOT REFUNDED. | • Create ZP0022ReconciliationServiceTest.java • Mock RefundRepository, ReconciliationItemRepository, PrefundingReversalService • Build test ZP0022Record objects and RefundBatchItem stubs for each vector • Vector 1: assert PrefundingReversalService.reverseForRefund called and refund updated to REFUNDED • Vector 2: assert refund REFUND_FAILED and reconciliation_item with DISCREPANCY • Vector 3: assert reconciliation_item MISSING_SCHEME and resolution_status UNRESOLVED • Vector 4: assert reconciliation_item MISSING_GME • Vector 5: assert reconciliation_item DISCREPANCY and verify reverseForRefund NOT called | services/settlement-reconciliation/src/test/java/com/gme/pay/settlement/zeropay/batch/ZP0022ReconciliationServiceTest.java with five test vectors | • Vector 1: verify(prefundingReversalService).reverseForRefund(refund.id) called exactly once and refund.status captured as REFUNDED • Vector 2: refund.status captured as REFUND_FAILED; one ReconciliationItem with match_status=DISCREPANCY inserted • Vector 3: one ReconciliationItem with match_status=MISSING_SCHEME and resolution_status=UNRESOLVED inserted • Vector 4: one ReconciliationItem with match_status=MISSING_GME inserted; no refund update • Vector 5: verifyNoInteractions(prefundingReversalService) for this vector; one ReconciliationItem with DISCREPANCY inserted | 45 | 9.5-T10, 9.5-T12 | BE | SCH-06
9.5-T21 | scheme-adapter-zeropay | 9.5 | 9. QR Scheme Integration (ZeroPay) | Refund result exchange (ZP0021/0022) | 2 | Unit tests: PrefundingReversalService -- OVERSEAS credit, LOCAL no-op, double-call guard | Module: services/prefunding-balance. Test class: PrefundingReversalServiceTest using JUnit 5 and Mockito. Test vectors: (1) OVERSEAS partner, refund.status='REFUND_CONFIRMED', transaction.prefunding_deducted_usd=36.9714 BigDecimal -> after call: prefunding_account.balance += 36.9714 (SELECT FOR UPDATE confirmed by verify on PrefundingAccountRepository), one prefunding_ledger_entry inserted with entry_type='CREDIT_REVERSAL', refund.status='REFUNDED'. (2) LOCAL partner, refund.status='REFUND_CONFIRMED' -> refund.status='REFUNDED', PrefundingLedgerRepository.insert never called. (3) refund.status='REFUNDED' -> IllegalStateException message contains 'REFUNDED'. (4) refund.status='REFUND_PENDING' -> IllegalStateException thrown. | • Create PrefundingReversalServiceTest.java in services/prefunding-balance test source • Mock RefundRepository, TransactionRepository, PartnerRepository, PrefundingAccountRepository, PrefundingLedgerRepository • Stub loadForUpdate on PrefundingAccountRepository to return account with current balance • Vector 1: OVERSEAS, assert balance delta = BigDecimal('36.9714') and CREDIT_REVERSAL ledger entry • Vector 2: LOCAL, assert PrefundingLedgerRepository.insert never invoked • Vector 3 and 4: wrong initial status, assert IllegalStateException | services/prefunding-balance/src/test/java/com/gme/pay/prefunding/PrefundingReversalServiceTest.java with four test vectors | • Vector 1: balance increment equals BigDecimal('36.9714') with exact scale preserved • Vector 2: verify(prefundingLedgerRepository, never()).insert(any()) for LOCAL partner • Vector 3: IllegalStateException message contains 'REFUNDED' • Vector 4: IllegalStateException thrown for REFUND_PENDING status • Vector 1: one CREDIT_REVERSAL ledger entry inserted with amount=36.9714 and refund_ref set | 35 | 9.5-T11 | BE | SCH-06
9.5-T22 | scheme-adapter-zeropay | 9.5 | 9. QR Scheme Integration (ZeroPay) | Refund result exchange (ZP0021/0022) | 2 | Unit tests: ZP0021BatchJob -- idempotency, empty-batch skip, SFTP error, normal run | Module: services/settlement-reconciliation. Test class: ZP0021BatchJobTest using JUnit 5 and Mockito. Test vectors: (1) No REFUND_PENDING refunds -> no settlement_batch row created, no SFTP call. (2) Normal run with 2 refunds -> createOutboundBatch called once, uploadOutbound called once, markTransmitted called once with the batch id. (3) Existing TRANSMITTED batch for priorBusinessDay -> idempotency guard triggers, createOutboundBatch NOT called, SFTP NOT called. (4) SFTP uploadOutbound throws SchemeConnectivityException -> markError called with exception message, OpsAlertPublisher.publishBatchError called, markTransmitted NOT called. (5) ZP0021FileBuilder.buildForDate throws RuntimeException -> exception propagates, no markTransmitted call. | • Create ZP0021BatchJobTest.java; mock all injected dependencies • Stub RefundBatchRepository.findByFileTypeAndDate to return empty Optional (vectors 1,2,5) or present batch (vector 3) • Vector 1: stub findPendingForDate to return empty list, assert createOutboundBatch never called • Vector 2: stub findPendingForDate with 2 items, verify full success path • Vector 3: stub findByFileTypeAndDate to return existing TRANSMITTED batch, assert createOutboundBatch and uploadOutbound never called • Vector 4: stub uploadOutbound to throw SchemeConnectivityException, assert markError and publishBatchError called, markTransmitted not called • Vector 5: stub buildForDate to throw RuntimeException, assert exception propagates | services/settlement-reconciliation/src/test/java/com/gme/pay/settlement/batch/ZP0021BatchJobTest.java with five test vectors | • Vector 1: verify(refundBatchRepository, never()).createOutboundBatch(any(), anyInt(), any(), any()) • Vector 2: verify(sftpGateway).uploadOutbound(contains('ZP0021'), any(), any(), any()) called once • Vector 3: when existing TRANSMITTED batch found, neither createOutboundBatch nor uploadOutbound is called • Vector 4: verify(refundBatchRepository).markError(any(), contains('SchemeConnectivityException')) and verify(opsAlertPublisher).publishBatchError(eq('ZP0021'), any(), any()) • Vector 5: RuntimeException propagates and markTransmitted is never called | 40 | 9.5-T08 | BE | SCH-06
9.5-T23 | scheme-adapter-zeropay | 9.5 | 9. QR Scheme Integration (ZeroPay) | Refund result exchange (ZP0021/0022) | 2 | Testcontainers integration test: ZP0021 generation -> ZP0022 processing happy-path round-trip | Module: services/settlement-reconciliation (integration test). Use @SpringBootTest with Testcontainers PostgreSQL 16. Seed: OVERSEAS partner (prefunding_account.balance=1000.00 USD, original payment with prefunding_deducted_usd=36.9714), LOCAL partner; two refund rows REFUND_PENDING for 2026-06-04 (OVERSEAS refund_amount_krw=50000, LOCAL refund_amount_krw=15000). Stub ZeroPaySftpGateway via WireMock or @MockBean. Step 1: invoke ZP0021BatchJob (or ZP0021FileBuilder.buildForDate directly) for 2026-06-04; assert settlement_batch created, both refunds REFUND_SUBMITTED. Step 2: build synthetic ZP0022 bytes using ZP0021Serializer helper for both records with result_code='00' and matching amounts. Step 3: stub SFTP fetchInbound to return synthetic bytes; invoke ZP0022InboundProcessor.processForDate(2026-06-04). Assert: both refunds REFUNDED; OVERSEAS prefunding balance = 1000.00 + 36.9714 = 1036.9714; one CREDIT_REVERSAL ledger entry; ZP0022 batch RECONCILED; zero reconciliation_item rows. | • Create RefundBatchRoundTripIntegrationTest.java in src/test; annotate @SpringBootTest, @Testcontainers • Define @Container PostgreSQLContainer<> postgres = new PostgreSQLContainer<>('postgres:16') • Seed DB in @BeforeEach using JdbcTemplate • @MockBean ZeroPaySftpGateway; stub uploadOutbound to succeed, stub fetchInbound for ZP0022 to return synthetic bytes • Execute step 1 (ZP0021 build) and step 2 (build synthetic ZP0022 bytes using ZP0021Serializer) and step 3 (ZP0022InboundProcessor.processForDate) • Assert all state post-conditions from context using JdbcTemplate queries | services/settlement-reconciliation/src/test/java/com/gme/pay/settlement/integration/RefundBatchRoundTripIntegrationTest.java | • Both refund rows have status='REFUNDED' in DB after test • OVERSEAS prefunding_account.balance = 1036.9714 (seed 1000.00 + reversal 36.9714) exactly • Exactly one prefunding_ledger_entry with entry_type='CREDIT_REVERSAL' and amount=36.9714 • settlement_batch for ZP0022 has status='RECONCILED' • Zero reconciliation_item rows exist (no mismatches in happy-path) | 60 | 9.5-T08, 9.5-T09, 9.5-T10, 9.5-T11, 9.5-T12 | BE | SCH-06
9.5-T24 | scheme-adapter-zeropay | 9.5 | 9. QR Scheme Integration (ZeroPay) | Refund result exchange (ZP0021/0022) | 2 | Testcontainers integration test: ZP0022 mixed-outcome mismatch and exception record creation | Module: services/settlement-reconciliation (integration test). Use @SpringBootTest with Testcontainers PostgreSQL 16. Seed 3 REFUND_SUBMITTED refunds for 2026-06-04 (already linked to a ZP0021 batch): ZPREF001 OVERSEAS 50000 KRW; ZPREF002 OVERSEAS 20000 KRW; ZPREF003 LOCAL 15000 KRW. Build synthetic ZP0022 with: ZPREF001 result_code='00' registered_refund_amount=50000 (success); ZPREF002 result_code='03' (failure); ZPREF003 absent from ZP0022 (MISSING_SCHEME); bonus record ZPREF999 (MISSING_GME). After ZP0022InboundProcessor.processForDate(2026-06-04): ZPREF001 REFUNDED + prefunding reversed; ZPREF002 REFUND_FAILED; ZPREF003 has reconciliation_item MISSING_SCHEME; ZPREF999 has reconciliation_item MISSING_GME; OpsAlertPublisher called with unresolvedCount >= 3. | • Create RefundBatchMismatchIntegrationTest.java; annotate @SpringBootTest, @Testcontainers • Seed: 3 refunds REFUND_SUBMITTED with correct zp_batch_id; OVERSEAS partner prefunding_account.balance=500.00 • Build synthetic ZP0022 bytes for the mixed set from context • @MockBean ZeroPaySftpGateway; stub fetchInbound to return mixed ZP0022 bytes • Invoke ZP0022InboundProcessor.processForDate(2026-06-04) • Assert each refund status, reconciliation_item rows, and OpsAlertPublisher calls via @MockBean verify | services/settlement-reconciliation/src/test/java/com/gme/pay/settlement/integration/RefundBatchMismatchIntegrationTest.java | • ZPREF001 refund status='REFUNDED' and prefunding balance increased by prefunding_deducted_usd • ZPREF002 refund status='REFUND_FAILED' and one reconciliation_item with match_status='DISCREPANCY' • reconciliation_item with match_status='MISSING_SCHEME' exists for ZPREF003 • reconciliation_item with match_status='MISSING_GME' exists for ZPREF999 • OpsAlertPublisher.publishRefundReconciliationExceptions called with unresolvedCount >= 3 | 55 | 9.5-T10, 9.5-T12, 9.5-T13, 9.5-T14, 9.5-T23 | BE | SCH-06
9.5-T25 | scheme-adapter-zeropay | 9.5 | 9. QR Scheme Integration (ZeroPay) | Refund result exchange (ZP0021/0022) | 2 | Admin API: GET /internal/v1/refund-batches returns daily refund batch summary | Module: services/ops-partner-bff. PRD-07 §10.3.5 specifies a Refund Batch View showing: batch date, ZP0021 file transmission status and timestamp, ZP0022 result receipt status, per-refund status breakdown, total count, total KRW. Endpoint: GET /internal/v1/refund-batches?settlementDate=YYYY-MM-DD. Response DTO (RefundBatchSummaryResponse): settlement_date, zp0021_batch_id (Long nullable), zp0021_status (String), zp0021_transmitted_at (OffsetDateTime nullable), zp0022_batch_id (Long nullable), zp0022_status (String), zp0022_reconciled_at (OffsetDateTime nullable), total_refund_count (int), total_refund_amount_krw (BigDecimal), refunds: List of {refund_ref, refund_amount_krw (BigDecimal), status, zp_result_code (String nullable)}. Security: @PreAuthorize('hasAnyRole(GME_OPS, GME_FINANCE)') via Spring Security OAuth2+RBAC. Returns 200 for dates with no batches (empty response with nulls); not 404. | • Create com/gme/pay/bff/ops/api/RefundBatchController.java as @RestController in services/ops-partner-bff • Implement @GetMapping('/internal/v1/refund-batches') with @RequestParam @DateTimeFormat LocalDate settlementDate • Inject RefundBatchQueryFacade (new @Service that queries settlement_batch and refund via JDBC or Feign to settlement-reconciliation service) • Apply @PreAuthorize('hasAnyRole(ROLE_GME_OPS, ROLE_GME_FINANCE)') • Map query results to RefundBatchSummaryResponse DTO (in lib-api-contracts or local DTO package) • Return 200 with response; if no batches found return response with null batch ids and empty refunds list | services/ops-partner-bff/src/main/java/com/gme/pay/bff/ops/api/RefundBatchController.java and RefundBatchSummaryResponse.java | • GET /internal/v1/refund-batches?settlementDate=2026-06-04 returns 200 with correct zp0021_status and zp0022_status • Request with GME_PARTNER role (not GME_OPS or GME_FINANCE) returns 403 • Response for a date with no batches returns 200 with empty refunds list and null batch ids (not 404) • zp0022_reconciled_at is non-null when ZP0022 batch status=RECONCILED • Response refunds array contains one entry per refund with correct status and zp_result_code | 45 | 9.5-T06, 9.5-T10 | BE | SCH-06
9.5-T26 | scheme-adapter-zeropay | 9.5 | 9. QR Scheme Integration (ZeroPay) | Refund result exchange (ZP0021/0022) | 2 | Admin API: GET and POST exception queue endpoints for ZP0022 reconciliation failures | Module: services/ops-partner-bff. Ops must be able to view and resolve UNRESOLVED reconciliation_item rows for ZP0022 refund registration failures. GET /internal/v1/exceptions?type=REFUND_RECONCILIATION&status=UNRESOLVED returns List<ExceptionItemResponse>: {id, batch_date, scheme_ref (original_zeropay_txn_ref), txn_ref (gme_refund_id), match_status, gme_amount NUMERIC, scheme_amount NUMERIC, discrepancy_amount NUMERIC, ccy, resolution_status}. Filters: join reconciliation_item -> settlement_batch WHERE settlement_batch.file_type='ZP0022' AND resolution_status='UNRESOLVED'. POST /internal/v1/exceptions/{id}/resolve body {resolution_note: String}: update resolution_status='RESOLVED', resolved_by=authenticated operator email, resolved_at=now(), resolution_note; return 200. Both endpoints require GME_OPS role (not GME_FINANCE -- this is an ops action). Audit log on resolve: actor, timestamp, exception item id, resolution_note (via Outbox domain event or direct audit table insert). | • Create or extend ExceptionQueueController.java in services/ops-partner-bff • Add @GetMapping('/internal/v1/exceptions') with @RequestParam type and status; filter file_type='ZP0022' for type=REFUND_RECONCILIATION • Add @PostMapping('/internal/v1/exceptions/{id}/resolve') with @RequestBody resolution_note and @AuthenticationPrincipal for resolved_by • Apply @PreAuthorize('hasRole(ROLE_GME_OPS)') on both methods • On resolve, insert audit record or publish ExceptionResolvedEvent via EventPublisher (Outbox) • Return 404 if exception item id not found on POST | services/ops-partner-bff/src/main/java/com/gme/pay/bff/ops/api/ExceptionQueueController.java with GET list and POST resolve for REFUND_RECONCILIATION type | • GET returns only reconciliation_item rows linked to ZP0022 batches when type=REFUND_RECONCILIATION • POST /exceptions/{id}/resolve sets resolution_status=RESOLVED and resolved_by=authenticated operator email • POST with GME_FINANCE role (not GME_OPS) returns 403 • POST /exceptions/{nonExistentId}/resolve returns 404 • After POST resolve, a subsequent GET for status=UNRESOLVED does not include the resolved item | 45 | 9.5-T13, 9.5-T25 | BE | SCH-06
9.5-T27 | scheme-adapter-zeropay | 9.5 | 9. QR Scheme Integration (ZeroPay) | Refund result exchange (ZP0021/0022) | 2 | Ops runbook: ZP0022 mismatch resolution, P1 escalation criteria, and retry procedure | Module: services/settlement-reconciliation docs. SCH-06 §6.4 states an unresolved refund registration failure blocking settlement is a P1 ops incident. The runbook must document: (1) daily schedule (ZP0021 generated 02:00 KST, ZP0022 expected by 05:00 KST, cutoff for ZP0022 inbound wait = 06:00 KST per SCH-06 §9.5); (2) how to view refund batch status via Admin portal Refund Batch View (/admin/settlement/refund-batches); (3) action for each exception type (DISCREPANCY=check result_code and amounts, correct data, re-submit ZP0021 for affected refunds; MISSING_SCHEME=ZeroPay did not acknowledge, contact 한결원; MISSING_GME=rogue record, investigate; REGISTRATION_AMOUNT_MISMATCH=amount dispute, escalate); (4) settlement block consequence: REFUND_FAILED refunds excluded from ZP0066 settlement refund detail until resolved; (5) P1 criteria: any UNRESOLVED exception after 06:00 KST (ZP0022 inbound cutoff) escalate immediately to 한결원 operations contact; (6) JIRA escalation template with fields: Priority, Affected refund_refs, batch_date, file_type=ZP0022, 한결원 contact. | • Create services/settlement-reconciliation/src/docs/ops/OPS_REFUND_BATCH.md • Section 1: Daily schedule with all times in KST and file directions • Section 2: Admin portal navigation path and key fields in Refund Batch View • Section 3: Exception type table with action column for each match_status • Section 4: Settlement block consequence for REFUND_FAILED items • Section 5: P1 escalation criteria and timeline • Section 6: JIRA escalation template with all required fields from context | services/settlement-reconciliation/src/docs/ops/OPS_REFUND_BATCH.md covering schedule, monitoring, exception actions, settlement block, P1 criteria, and JIRA template | • Document lists all four match_status types (DISCREPANCY, MISSING_SCHEME, MISSING_GME, REGISTRATION_AMOUNT_MISMATCH) with action for each • P1 escalation criteria states: unresolved after 06:00 KST ZP0022 inbound cutoff triggers P1 escalation to 한결원 • Document includes Admin portal path /admin/settlement/refund-batches • Settlement block consequence states REFUND_FAILED items are excluded from ZP0066 refund detail until resolved • JIRA template includes: Priority=P1, Affected refund_refs placeholder, batch_date placeholder, file_type=ZP0022, 한결원 contact field | 25 | 9.5-T10, 9.5-T26 | BE | SCH-06
9.6-T01 | scheme-adapter-zeropay | 9.6 | 9. QR Scheme Integration (ZeroPay) | Settlement files (ZP0061–0066) | 2 | Add settlement_batch DB migration: ZP006x window/status constraints | The settlement_batch table (DAT-03 §10.5) tracks one row per daily batch run per file type. Columns: id BIGINT PK, scheme_id BIGINT FK qr_scheme, file_type VARCHAR(10), direction VARCHAR(20) CHECK IN ('GME_TO_ZP','ZP_TO_GME'), settlement_date DATE (KST), window VARCHAR(20) CHECK IN ('MORNING','AFTERNOON','DETAIL','NIGHTLY'), status VARCHAR(20) CHECK IN ('PENDING','GENERATED','TRANSMITTED','RECEIVED','RECONCILED','ERROR'), transaction_count INT DEFAULT 0, total_amount DECIMAL(20,4) DEFAULT 0, total_amount_ccy CHAR(3), file_checksum VARCHAR(64), transmitted_at TIMESTAMPTZ, received_at TIMESTAMPTZ, reconciled_at TIMESTAMPTZ, error_detail TEXT, standard audit cols. WBS 9.6 adds support for ZP0061-ZP0066; prior migrations may not have all window/status values. | • Write a new Flyway migration V9_6_001 that adds a unique constraint on (scheme_id, file_type, settlement_date, window) to prevent duplicate batch rows • Ensure CHECK constraints on direction, window, and status columns match the exact value lists above • Add a non-unique index on (settlement_date, file_type) for batch scheduler queries • Add a non-unique index on (status, settlement_date) for monitoring queries • Document migration rollback SQL in a comment block at the top of the file | Flyway migration file V9_6_001__settlement_batch_zp006x_constraints.sql | • Unique constraint (scheme_id, file_type, settlement_date, window) rejects a duplicate insert for the same file_type and date • CHECK on window rejects the value 'WEEKLY' and accepts 'MORNING','AFTERNOON','DETAIL','NIGHTLY' • CHECK on direction rejects 'OUTBOUND' and accepts 'GME_TO_ZP','ZP_TO_GME' • Migration applies cleanly on an empty DB and on a DB with pre-existing payment/refund batch rows • Rollback SQL successfully removes the new indexes and constraints without data loss | 30 |  | BE | SCH-06
9.6-T02 | scheme-adapter-zeropay | 9.6 | 9. QR Scheme Integration (ZeroPay) | Settlement files (ZP0061–0066) | 2 | Add settlement_file and reconciliation_item migration for ZP006x | settlement_file (DAT-03 §7.2) stores physical SFTP file metadata: id BIGINT PK, batch_id FK settlement_batch, filename VARCHAR(255), sftp_path VARCHAR(512), file_size_bytes BIGINT, file_checksum VARCHAR(64), direction VARCHAR(20) CHECK IN ('OUTBOUND','INBOUND'), transmitted_at TIMESTAMPTZ, created_at/updated_at. reconciliation_item (DAT-03 §7.3) stores line-level reconciliation: id PK, batch_id FK settlement_batch, txn_ref VARCHAR(64) NULLable, scheme_ref VARCHAR(128), match_status VARCHAR(20) CHECK IN ('MATCHED','DISCREPANCY','MISSING_GME','MISSING_SCHEME'), gme_amount/scheme_amount/discrepancy_amount DECIMAL(20,4), ccy CHAR(3), resolution_status VARCHAR(20) CHECK IN ('UNRESOLVED','RESOLVED','ESCALATED'), resolved_by/resolved_at/resolution_note, standard audit. Both tables must pre-exist for ZP006x batch processing. | • Write Flyway migration V9_6_002 creating settlement_file if not already present with all listed columns and constraints • Create reconciliation_item table with all listed columns, CHECK constraints, and FK to settlement_batch • Add index on reconciliation_item(batch_id, match_status) for exception-queue queries • Add index on reconciliation_item(txn_ref) for transaction-level drill-down • Verify FK cascade behavior: deleting a settlement_batch row should be blocked (RESTRICT) not cascade | Flyway migration V9_6_002__settlement_file_reconciliation_item.sql | • settlement_file.direction CHECK rejects 'GME_TO_ZP' and accepts 'OUTBOUND' • reconciliation_item.match_status CHECK rejects 'UNKNOWN' and accepts 'MISSING_SCHEME' • FK on reconciliation_item.batch_id → settlement_batch is RESTRICT (delete of settlement_batch with child rows fails) • Index on (batch_id, match_status) exists and is used by EXPLAIN for WHERE batch_id=X AND match_status='DISCREPANCY' • Inserting a reconciliation_item with NULL txn_ref succeeds (NULLable column for missing-GME cases) | 30 | 9.6-T01 | BE | SCH-06
9.6-T03 | scheme-adapter-zeropay | 9.6 | 9. QR Scheme Integration (ZeroPay) | Settlement files (ZP0061–0066) | 2 | Add settlement_batch_id FK column on transaction table | Per SCH-06 §5.3, each payment transaction must appear in exactly one settlement file (ZP0061 or ZP0063). The transaction table needs a settlement_batch_id column (BIGINT NULLable, FK settlement_batch) set atomically during batch generation to enforce exactly-once settlement. A matching settlement_window column (VARCHAR(20) NULLable) records 'MORNING' or 'AFTERNOON'. A transaction with settlement_batch_id NOT NULL has been included in a submitted file and must not be re-selected for a new batch. | • Write Flyway migration V9_6_003 adding settlement_batch_id BIGINT NULL FK settlement_batch(id) DEFERRABLE INITIALLY DEFERRED to the transaction table • Add settlement_window VARCHAR(20) NULL column with CHECK IN ('MORNING','AFTERNOON') on the same table • Add index on transaction(settlement_batch_id) for reverse-lookup from batch to transactions • Add partial index on transaction(settlement_date) WHERE settlement_batch_id IS NULL for efficient unsettled-transaction queries • Verify existing transaction rows are unaffected (NULLs only) | Flyway migration V9_6_003__transaction_settlement_batch_fk.sql | • transaction.settlement_batch_id is NULLable; existing rows keep NULL after migration • Inserting a transaction row with a non-existent settlement_batch_id raises a FK violation • Partial index WHERE settlement_batch_id IS NULL reduces scan size vs full table scan when querying unsettled transactions (EXPLAIN) • CHECK on settlement_window rejects 'DETAIL' and accepts 'MORNING' • Rollback removes both columns and indexes cleanly | 25 | 9.6-T01 | BE | SCH-06
9.6-T04 | scheme-adapter-zeropay | 9.6 | 9. QR Scheme Integration (ZeroPay) | Settlement files (ZP0061–0066) | 2 | Define SettlementBatch and SettlementFile Java domain entities | The Hub Core settlement engine (SAD-02 §5.4) manages settlement_batch and settlement_file DB records. Java JPA entities are needed for both tables. SettlementBatch maps to the settlement_batch table (see T01 for all fields). SettlementFile maps to settlement_file (T02). Key enum types: BatchStatus {PENDING, GENERATED, TRANSMITTED, RECEIVED, RECONCILED, ERROR}, BatchWindow {MORNING, AFTERNOON, DETAIL, NIGHTLY}, BatchDirection {GME_TO_ZP, ZP_TO_GME}. Money amounts stored as BigDecimal with scale 4 (DECIMAL(20,4)). KST date stored as java.time.LocalDate. | • Create SettlementBatch.java JPA entity with all columns mapped, enums for status/window/direction, and standard audit fields • Create SettlementFile.java JPA entity with batch_id ManyToOne relationship to SettlementBatch • Create corresponding enums BatchStatus, BatchWindow, BatchDirection • Create SettlementBatchRepository and SettlementFileRepository (Spring Data JPA) with finder methods: findBySchemeIdAndFileTypeAndSettlementDateAndWindow, findByStatusIn • Write unit tests confirming entity creation, enum mapping, and unique-constraint violation throws DataIntegrityViolationException | SettlementBatch.java, SettlementFile.java, BatchStatus/BatchWindow/BatchDirection enums, two JPA repositories, one test class | • SettlementBatch.totalAmount is BigDecimal; KRW amounts with 0 decimal places are stored as e.g. 1500000.0000 without floating error • Creating two SettlementBatch rows with identical (scheme_id, file_type, settlement_date, window) throws DataIntegrityViolationException • findBySchemeIdAndFileTypeAndSettlementDateAndWindow returns empty Optional when none exists • BatchStatus.from(String) throws IllegalArgumentException for unrecognised string 'DONE' • SettlementFile.direction enum correctly persists OUTBOUND as VARCHAR 'OUTBOUND' | 45 | 9.6-T01, 9.6-T02 | BE | SCH-06
9.6-T05 | scheme-adapter-zeropay | 9.6 | 9. QR Scheme Integration (ZeroPay) | Settlement files (ZP0061–0066) | 2 | Define ReconciliationItem Java entity and repository | reconciliation_item (DAT-03 §7.3) stores per-transaction line comparisons after ZP0062/ZP0064 result files are processed. Key fields: id, batch_id FK settlement_batch, txn_ref VARCHAR(64) NULLable, scheme_ref VARCHAR(128), match_status enum {MATCHED, DISCREPANCY, MISSING_GME, MISSING_SCHEME}, gme_amount/scheme_amount/discrepancy_amount BigDecimal, ccy CHAR(3), resolution_status enum {UNRESOLVED, RESOLVED, ESCALATED}, resolved_by/resolved_at/resolution_note, standard audit. The exception queue in Ops Admin queries by batch_id and match_status != MATCHED. | • Create ReconciliationItem.java JPA entity with all columns, enums MatchStatus and ResolutionStatus • Add ManyToOne to SettlementBatch • Create ReconciliationItemRepository with methods: findByBatchIdAndMatchStatusNot(Long batchId, MatchStatus status), countByBatchIdAndMatchStatus, saveAll • Write unit tests for entity persistence and repository finders with in-memory H2 DB | ReconciliationItem.java, MatchStatus/ResolutionStatus enums, ReconciliationItemRepository, unit test class | • Persisting a ReconciliationItem with txn_ref NULL succeeds (MISSING_GME case) • findByBatchIdAndMatchStatusNot returns only DISCREPANCY and MISSING_SCHEME rows when MATCHED rows also exist in the same batch • discrepancy_amount stores gme_amount minus scheme_amount; a 1 KRW mismatch persists as 1.0000 • ResolutionStatus.ESCALATED persists as VARCHAR 'ESCALATED' • Deleting a SettlementBatch with attached ReconciliationItems throws DataIntegrityViolationException (RESTRICT) | 35 | 9.6-T02, 9.6-T04 | BE | SCH-06
9.6-T06 | scheme-adapter-zeropay | 9.6 | 9. QR Scheme Integration (ZeroPay) | Settlement files (ZP0061–0066) | 2 | Implement SettlementWindowSelector: assign transactions to MORNING or AFTERNOON window | ZP0061 (MORNING, due ~05:00 KST) covers all transactions registered in ZP0011/ZP0012 for the prior business day where ZP0012 status = SETTLEMENT_REGISTERED and settlement_batch_id IS NULL. ZP0063 (AFTERNOON, due ~14:00 KST) covers supplementary same-day transactions approved after the ZP0061 cutoff. Business rule: at the time the ZP0061 batch job runs (~04:30 KST), all eligible unsettled transactions with settlement_date = prior KST business day and status SETTLEMENT_REGISTERED are assigned window MORNING. Transactions that arrive after ZP0061 is transmitted but before ~13:30 KST are assigned AFTERNOON. Transactions with unresolved registration failures (status != SETTLEMENT_REGISTERED) are EXCLUDED from both windows until Ops resolves the exception. | • Implement SettlementWindowSelector.selectForMorning(LocalDate settlementDate): queries transaction table WHERE settlement_date=settlementDate AND settlement_batch_id IS NULL AND batch_status='SETTLEMENT_REGISTERED', returns List<Long> transaction IDs • Implement selectForAfternoon(LocalDate settlementDate): same filter but settlement_date = today (same-day transactions approved after morning cutoff) • Both methods must use SELECT FOR UPDATE on the settlement_batch_id column rows to prevent concurrent assignment • Write unit tests with mocked repository covering: normal case (3 eligible txns returned), exclusion of already-settled txns (settlement_batch_id NOT NULL), exclusion of non-SETTLEMENT_REGISTERED txns | SettlementWindowSelector.java service class with selectForMorning and selectForAfternoon methods plus unit tests | • selectForMorning with 5 eligible + 2 already settled returns exactly 5 IDs • selectForMorning excludes a transaction with status REGISTRATION_FAILED (not in result set) • selectForAfternoon for same-day date T returns txns with settlement_date=T and settlement_batch_id IS NULL • Calling selectForMorning twice concurrently (two threads) does not return the same transaction ID in both result sets (lock test) • Passing a Sunday date (non-business day) returns empty list (ZeroPay operates Mon-Sat) | 45 | 9.6-T03, 9.6-T04 | BE | SCH-06
9.6-T07 | scheme-adapter-zeropay | 9.6 | 9. QR Scheme Integration (ZeroPay) | Settlement files (ZP0061–0066) | 2 | Implement net vs gross settlement amount computation per transaction | Settlement amount for ZP0061/ZP0063 differs by partner type (SCH-06 §7.1, SAD-02 §5.4). Net settlement (domestic, partner type LOCAL, e.g. GME Remit): net_settlement_amount = target_payout (KRW). GME retains its fee share; ZeroPay credits exactly target_payout to the merchant. Gross settlement (international, partner type OVERSEAS, e.g. SendMN): net_settlement_amount = target_payout (KRW) — the full payout amount is remitted; GME separately invoices the merchant monthly. In both cases net_settlement_amount = target_payout (KRW, 0 decimals). The settlement_type CHAR is 'N' for domestic, 'G' for international. merchant_fee_total (ZP0061 field) = 0 for gross, = service_charge (KRW) for net domestic. service_charge is flat per-transaction (e.g. KRW 500) and is NOT shared with ZeroPay. | • Implement SettlementAmountCalculator.compute(Transaction txn): returns SettlementLineItem record with fields net_settlement_amount (KRW BigDecimal scale 0), merchant_fee_total (KRW BigDecimal scale 0), settlement_type (char N or G) • For LOCAL partner: settlement_type='N', net_settlement_amount=txn.targetPayoutKrw, merchant_fee_total=txn.serviceCharge • For OVERSEAS partner: settlement_type='G', net_settlement_amount=txn.targetPayoutKrw, merchant_fee_total=BigDecimal.ZERO • Write unit tests with numeric examples | SettlementAmountCalculator.java + SettlementLineItem record + unit tests | • LOCAL txn with target_payout=10000 KRW, service_charge=500 KRW: net_settlement_amount=10000, merchant_fee_total=500, type='N' • OVERSEAS txn with target_payout=50000 KRW: net_settlement_amount=50000, merchant_fee_total=0, type='G' • net_settlement_amount is always equal to target_payout regardless of partner type • Result uses BigDecimal scale 0 for KRW; no floating-point arithmetic • Passing a null partner type throws IllegalArgumentException with message containing 'partner type' | 30 | 9.6-T04 | BE | SCH-06
9.6-T08 | scheme-adapter-zeropay | 9.6 | 9. QR Scheme Integration (ZeroPay) | Settlement files (ZP0061–0066) | 2 | Implement ZP0061MorningSettlementRequestBuilder: aggregate and format file | ZP0061 (GME→ZeroPay, due ~05:00 KST) contains one summary record per merchant. Fields per record (SCH-06 §7.2): merchant_id CHAR(10), settlement_date DATE(8) YYYYMMDD, gross_txn_count NUM(6), gross_txn_amount NUM(14) (sum of target_payout KRW for payment txns), refund_count NUM(6), refund_amount NUM(14) (sum of refund KRW), merchant_fee_total NUM(12), net_settlement_amount NUM(14), settlement_type CHAR(1) N or G. The builder aggregates all transactions in the MORNING window for a settlement_date, groups by merchant_id, sums amounts. File naming convention: ZP0061_{YYYYMMDD}_{SEQ}.dat.pgp where SEQ starts at 01. The batch is idempotent: re-running with the same inputs produces byte-identical output (fixed ordering: merchant_id ASC). | • Implement ZP0061MorningSettlementRequestBuilder.build(LocalDate settlementDate, List<SettlementLineItem> lines): groups by merchant_id, sums gross_txn_amount and refund_amount, computes net_settlement_amount per merchant, returns a structured ZP0061File object with header, records list, and trailer (total record count) • Use SettlementAmountCalculator (T07) for per-line amounts before aggregation • Enforce merchant_id padded to CHAR(10), amounts formatted as zero-padded NUM fields • Return byte[] content as fixed-width flat file (encoding UTF-8); SHA-256 checksum computed over the bytes • Write unit test: 2 payment txns + 1 refund txn for merchant M001 produces one summary record with correct sums | ZP0061MorningSettlementRequestBuilder.java + ZP0061File record + unit tests | • Two payment txns for merchant M001 (10000 KRW each) + one refund (5000 KRW): gross_txn_amount=20000, refund_amount=5000, gross_txn_count=2, refund_count=1 in the output record • Merchants sorted by merchant_id ASC; same input always produces same byte[] (idempotent) • merchant_id='MERCH1' is right-padded to 10 chars in the output • gross_txn_amount field is zero-padded to NUM(14): value 20000 renders as '00000000020000' • Zero-transaction merchant is not included in the file (no empty records) | 50 | 9.6-T06, 9.6-T07 | BE | SCH-06
9.6-T09 | scheme-adapter-zeropay | 9.6 | 9. QR Scheme Integration (ZeroPay) | Settlement files (ZP0061–0066) | 2 | Implement ZP0063AfternoonSettlementRequestBuilder | ZP0063 (GME→ZeroPay, due ~14:00 KST) is the afternoon supplement. It covers transactions approved after the ZP0061 cutoff that require same-day merchant crediting (SCH-06 §7.2, Assumption A-08). The file layout is identical to ZP0061 (same fields, same format). The only differences are: file type code in the filename is ZP0063, the window value on settlement_batch is AFTERNOON, and the source transaction set comes from SettlementWindowSelector.selectForAfternoon. The builder must not include any transactions already assigned to MORNING window (settlement_batch_id IS NOT NULL for morning batch). | • Implement ZP0063AfternoonSettlementRequestBuilder.build(LocalDate settlementDate, List<SettlementLineItem> lines) — reuses the same field formatting logic as ZP0061 builder (extract a shared ZeropaySettlementFileFormatter utility) • Filename pattern: ZP0063_{YYYYMMDD}_{SEQ}.dat.pgp • Verify via unit test that a txn already in the MORNING window is not present in the afternoon file • Write unit test with 1 afternoon txn for merchant M002 producing a valid single-record file | ZP0063AfternoonSettlementRequestBuilder.java + ZeropaySettlementFileFormatter utility + unit tests | • Afternoon builder produces file_type='ZP0063' in the batch record (not ZP0061) • A transaction with settlement_batch_id pointing to a MORNING batch is absent from the afternoon file • Single afternoon txn for merchant M002 with target_payout=30000 KRW: one record, gross_txn_amount=30000 • Shared formatter produces NUM(14) formatting identical to ZP0061 builder for same input amounts • Empty afternoon transaction list produces a valid file with zero records (header + trailer only, no data records) | 35 | 9.6-T08 | BE | SCH-06
9.6-T10 | scheme-adapter-zeropay | 9.6 | 9. QR Scheme Integration (ZeroPay) | Settlement files (ZP0061–0066) | 2 | Implement SettlementBatchGenerationService: orchestrate batch creation with atomic txn assignment | Creating a ZP0061 or ZP0063 batch must be atomic: all selected transactions must have their settlement_batch_id set in the same DB transaction that inserts the settlement_batch row, so no transaction can appear in two batches (SCH-06 §5.3). The service must: 1) open a DB transaction, 2) INSERT a settlement_batch row with status=GENERATED, 3) call SettlementWindowSelector to get eligible txn IDs (using SELECT FOR UPDATE), 4) UPDATE transaction.settlement_batch_id = new_batch.id and settlement_window='MORNING'/'AFTERNOON' for all selected IDs, 5) build the file bytes using the appropriate builder, 6) store file_checksum on settlement_batch, 7) write the SettlementFile row, 8) COMMIT. On any failure, the entire DB transaction rolls back. | • Implement SettlementBatchGenerationService.generateMorning(LocalDate settlementDate, Long schemeId) -> SettlementBatch • Implement generateAfternoon(LocalDate settlementDate, Long schemeId) -> SettlementBatch • Wrap all steps in @Transactional; use programmatic transaction management for the SELECT FOR UPDATE • If a GENERATED batch already exists for (schemeId, file_type, settlement_date, window), return the existing batch without re-generating (idempotency) • Write unit tests: normal path, idempotency (second call returns same batch), concurrent call safety (use two threads, verify only one batch row is created) | SettlementBatchGenerationService.java + integration test class (uses embedded Postgres or H2) | • Normal path: settlement_batch row inserted with status=GENERATED; all selected txn IDs have settlement_batch_id set to the new batch ID • Calling generateMorning twice for same date returns the same settlement_batch.id without inserting a second row • A transaction already assigned to a batch is not re-selected in a concurrent generateMorning call • If file builder throws, DB transaction rolls back: no settlement_batch row and no settlement_batch_id updates on transactions • settlement_batch.transaction_count equals the count of transactions updated in the same call | 55 | 9.6-T06, 9.6-T08, 9.6-T09 | BE | SCH-06
9.6-T11 | scheme-adapter-zeropay | 9.6 | 9. QR Scheme Integration (ZeroPay) | Settlement files (ZP0061–0066) | 2 | Implement SFTP transmission for ZP0061/ZP0063 outbound files | The ZeroPay SFTP adapter (SCH-06 §2) transmits outbound files to the /gmepay/outbound/ directory on 한결원's SFTP server. File naming: ZP0061_{YYYYMMDD}_{SEQ}.dat.pgp; SEQ=01 for first transmission, incremented on retransmit (e.g. 02 for the first retry). The adapter must: encrypt the file bytes with ZeroPay's PGP public key before transmission, put the file via SFTP, record transmitted_at and update settlement_batch.status to TRANSMITTED. On SFTP failure, retry up to 3 times with exponential backoff (1s, 2s, 4s); after 3 failures, status=ERROR and an Ops alert is published. Outbound SFTP host key must be pinned (SEC-09 T-06). | • Implement SftpOutboundTransmitter.transmit(SettlementBatch batch, byte[] fileBytes, String filename): encrypts bytes with PGP public key loaded from config, puts file to SFTP path, updates batch status to TRANSMITTED, records transmitted_at • Add retry logic (3 attempts, exponential backoff) using Spring Retry or equivalent • On final failure: set status=ERROR, set error_detail, publish OpsAlertEvent(priority=P1, batchId, message) • Write unit tests with mocked SFTP client: success path, single retry then success, three failures then ERROR status • Ensure sequence number increments correctly: second call with same batch id uses SEQ=02 | SftpOutboundTransmitter.java + retry config + unit tests | • Successful transmission updates settlement_batch.status to TRANSMITTED and sets transmitted_at to current UTC timestamp • After 3 SFTP failures, status=ERROR and OpsAlertEvent is published exactly once • SEQ number in filename is 01 for first transmission, 02 for first retransmit (same batch, second call) • PGP encryption is applied before SFTP put; raw plaintext bytes are never written to SFTP • transmitted_at is only set when SFTP put returns success, not on retry attempts | 50 | 9.6-T10 | BE | SCH-06
9.6-T12 | scheme-adapter-zeropay | 9.6 | 9. QR Scheme Integration (ZeroPay) | Settlement files (ZP0061–0066) | 2 | Implement ZP0062/ZP0064 inbound settlement result file parser | ZP0062 (morning settlement result, expected ~10:00 KST) and ZP0064 (afternoon settlement result, expected ~19:00 KST) are inbound files from ZeroPay confirming per-merchant settlement. Each record confirms the merchant_id, settlement_date, credited_amount KRW, and a result_code. A result_code of '0000' means SETTLEMENT_CONFIRMED; any other code means SETTLEMENT_DISCREPANCY. The parser must be tolerant of record count mismatches (partial file = P1 exception). Field widths match ZP0061 format (same layout family). Files arrive on the SFTP inbound directory /gmepay/inbound/. After polling, the parser: decrypts PGP, parses fixed-width records, returns a List<SettlementResultRecord> with fields: merchant_id, credited_amount_krw, result_code, scheme_result_message. | • Implement ZP0062ResultFileParser.parse(byte[] encryptedBytes): decrypt PGP, parse fixed-width records, return List<SettlementResultRecord> • Handle file parse error (corrupt/truncated) by throwing SettlementFileParseException which triggers status=ERROR + OpsAlert • Implement ZP0064ResultFileParser extending or delegating to ZP0062ResultFileParser (same format, different file type label) • Write unit tests with sample byte arrays representing a valid 3-record file and a truncated file • Verify that result_code != '0000' sets SettlementResultRecord.discrepancyFlag=true | ZP0062ResultFileParser.java, ZP0064ResultFileParser.java, SettlementResultRecord.java + unit tests | • Valid 3-record file parses to exactly 3 SettlementResultRecord objects with correct credited_amount_krw values • Record with result_code='9999' has discrepancyFlag=true; '0000' has discrepancyFlag=false • Truncated file (missing last record mid-byte) throws SettlementFileParseException • credited_amount_krw is BigDecimal with scale 0 (KRW integer) • Parser is stateless: calling parse twice on the same bytes returns equal (not same) List instances | 40 | 9.6-T04 | BE | SCH-06
9.6-T13 | scheme-adapter-zeropay | 9.6 | 9. QR Scheme Integration (ZeroPay) | Settlement files (ZP0061–0066) | 2 | Implement settlement result reconciliation: ZP0061 vs ZP0062, ZP0063 vs ZP0064 | After parsing ZP0062 or ZP0064, the Reconciliation Engine (SAD-02 §5.4) must compare each merchant total in the result file against the amount in the corresponding outbound file (ZP0061 or ZP0063). Zero-tolerance: every merchant total must match (SCH-06 §9.1). Discrepancy detection: if result credited_amount differs from outbound net_settlement_amount for the same merchant_id, create a reconciliation_item with match_status=DISCREPANCY; if merchant appears in result but not in outbound, match_status=MISSING_GME; if merchant appears in outbound but not in result, match_status=MISSING_SCHEME. On any discrepancy, publish OpsAlertEvent(priority=P1). On clean reconciliation, set settlement_batch.status=RECONCILED. | • Implement SettlementReconciliationService.reconcile(SettlementBatch outboundBatch, List<SettlementResultRecord> resultRecords): compares by merchant_id, persists ReconciliationItem rows, updates batch status • For clean match: status=RECONCILED, reconciled_at=now • For any mismatch: status=RECONCILED with exception items inserted; publish OpsAlertEvent per discrepancy • Write unit test: 3 merchants match -> status=RECONCILED, 0 items created • Write unit test: 2 match, 1 has amount mismatch -> RECONCILED + 1 DISCREPANCY item + 1 OpsAlertEvent | SettlementReconciliationService.java + unit tests | • Clean reconciliation of 3 merchants (all amounts match) produces status=RECONCILED, 0 reconciliation_item rows, 0 OpsAlerts • Amount mismatch of 1 KRW for merchant M001: 1 reconciliation_item with match_status=DISCREPANCY, discrepancy_amount=1.0000, resolution_status=UNRESOLVED • Merchant in ZP0062 result not in ZP0061 outbound: match_status=MISSING_GME, txn_ref=NULL • Merchant in ZP0061 outbound not in ZP0062 result: match_status=MISSING_SCHEME, scheme_ref=NULL • OpsAlertEvent published exactly once per discrepancy item, priority P1 | 50 | 9.6-T05, 9.6-T12 | BE | SCH-06
9.6-T14 | scheme-adapter-zeropay | 9.6 | 9. QR Scheme Integration (ZeroPay) | Settlement files (ZP0061–0066) | 2 | Implement ZP0065 payment detail file builder | ZP0065 (GME→ZeroPay, due ~22:00 KST) provides transaction-level detail for all settled payments. Each record (SCH-06 §7.2): merchant_id CHAR(10), zeropay_txn_ref CHAR(20) (scheme approval code from real-time authorisation), txn_date DATE(8), txn_time TIME(6) HHMMSS, payout_amount_krw NUM(12), merchant_fee_amt NUM(12), van_fee_amt NUM(10) (zero for Phase 1), partner_type CHAR(1) D for domestic / I for international, settlement_batch_ref CHAR(20) (reference to ZP0061 or ZP0063 batch). The scope is ALL settled payments for the settlement_date (both MORNING and AFTERNOON windows). Detail reconciliation: ZP0065 line-item totals must tie back to ZP0061+ZP0063 merchant totals (zero tolerance, SCH-06 §9.1). | • Implement ZP0065PaymentDetailBuilder.build(LocalDate settlementDate, Long schemeId): queries transactions with settlement_batch_id NOT NULL for the date, formats each as a fixed-width detail record • settlement_batch_ref field is set to the filename of the linked settlement_batch (ZP0061 or ZP0063 filename) • partner_type='D' for LOCAL partner transactions, 'I' for OVERSEAS • van_fee_amt is always zero-filled (NUM(10) = '0000000000') in Phase 1 • Write unit test: 2 MORNING transactions for merchant M001 + 1 AFTERNOON for merchant M002 produces 3 records in merchant_id+txn_date+txn_time order | ZP0065PaymentDetailBuilder.java + unit tests | • Three transactions produce three records; records are sorted by merchant_id ASC then txn_date ASC then txn_time ASC • payout_amount_krw for OVERSEAS txn with target_payout=50000 renders as '000000050000' (NUM(12) zero-padded) • partner_type='D' for LOCAL partner txn, 'I' for OVERSEAS partner txn • settlement_batch_ref matches the filename of the transaction's settlement_batch (e.g. ZP0061_20260605_01) • A payment transaction with settlement_batch_id IS NULL is excluded from the file | 45 | 9.6-T08, 9.6-T09 | BE | SCH-06
9.6-T15 | scheme-adapter-zeropay | 9.6 | 9. QR Scheme Integration (ZeroPay) | Settlement files (ZP0061–0066) | 2 | Implement ZP0066 refund detail file builder | ZP0066 (GME→ZeroPay, due ~22:00 KST) provides transaction-level detail for all settled refunds. Record layout (SCH-06 §7.2): merchant_id CHAR(10), original_zeropay_txn_ref CHAR(20) (reference to the original payment), refund_date DATE(8), refund_amount_krw NUM(12) (positive value representing the refunded KRW amount), merchant_fee_adj_amt NUM(12) (fee adjustment; 0 for gross/international, positive for net/domestic), settlement_batch_ref CHAR(20). Source: refund records with status SETTLEMENT_REGISTERED and settlement_batch_id pointing to the same settlement_date batch. Note: only refunds processed after the business day of the original payment are included (same-day cancels via real-time API are excluded per SCH-06 §6.1). | • Implement ZP0066RefundDetailBuilder.build(LocalDate settlementDate, Long schemeId): queries refund table for records with settlement_date=settlementDate and status=SETTLEMENT_REGISTERED • Format each refund as a fixed-width record using the ZeropaySettlementFileFormatter utility from T09 • merchant_fee_adj_amt = service_charge for LOCAL refunds, = 0 for OVERSEAS refunds • Exclude any refund with the same settlement_date as its original payment transaction (same-day cancel exclusion) • Write unit tests: LOCAL refund with service_charge=500 produces merchant_fee_adj_amt='000000000500'; OVERSEAS refund produces '000000000000' | ZP0066RefundDetailBuilder.java + unit tests | • LOCAL refund with refund_amount=10000 KRW, service_charge=500 KRW: refund_amount_krw='000000010000', merchant_fee_adj_amt='000000000500' • OVERSEAS refund: merchant_fee_adj_amt='000000000000' • A same-day cancel (refund.settlement_date == original_txn.settlement_date) is excluded from the file • original_zeropay_txn_ref is populated from the original payment's zeropay_txn_ref field (not a new reference) • Empty refund day (no refunds) produces a valid file with zero records (header + trailer only) | 40 | 9.6-T14 | BE | SCH-06
9.6-T16 | scheme-adapter-zeropay | 9.6 | 9. QR Scheme Integration (ZeroPay) | Settlement files (ZP0061–0066) | 2 | Implement ZP0065/ZP0066 batch generation and SFTP transmission (22:00 cron) | The 22:00 KST cron job generates ZP0065 and ZP0066 for the current settlement_date and transmits both via SFTP. Internal deadline: complete by 21:30 KST (NFR-10 §2.3). The job is idempotent: if a GENERATED or TRANSMITTED batch already exists for (scheme_id, ZP0065, settlement_date, DETAIL), return existing batch. Batch job dependencies: ZP0065/ZP0066 have no hard dependency on ZP0062/ZP0064 but must cover only transactions whose settlement_batch_id IS NOT NULL (i.e. included in ZP0061 or ZP0063). File naming: ZP0065_{YYYYMMDD}_01.dat.pgp, ZP0066_{YYYYMMDD}_01.dat.pgp. | • Implement DetailSettlementBatchJob.run(LocalDate settlementDate, Long schemeId): calls ZP0065PaymentDetailBuilder, ZP0066RefundDetailBuilder, inserts two settlement_batch rows (window=DETAIL), calls SftpOutboundTransmitter for each • Annotate with @Scheduled(cron='0 0 22 * * MON-SAT', zone='Asia/Seoul') or equivalent cron expression • Idempotency: check for existing GENERATED/TRANSMITTED DETAIL batches before regenerating • Publish OpsAlertEvent(P1) if either file's SFTP transmission fails after 3 retries • Write unit tests for idempotency and for the case where ZP0065 succeeds but ZP0066 SFTP fails (ZP0065 remains TRANSMITTED; ZP0066 becomes ERROR) | DetailSettlementBatchJob.java + unit tests | • Running the job twice for the same date creates exactly 2 settlement_batch rows total (one ZP0065, one ZP0066), not 4 • ZP0065 batch window is DETAIL; ZP0066 batch window is DETAIL • If ZP0066 SFTP fails, ZP0065 batch is unaffected (status=TRANSMITTED); ZP0066 status=ERROR • Cron expression evaluates to 22:00 KST on a Tuesday (business day) and does NOT fire on a Sunday • OpsAlertEvent priority=P1 is published for SFTP failure; no alert on success | 45 | 9.6-T11, 9.6-T14, 9.6-T15 | BE | SCH-06
9.6-T17 | scheme-adapter-zeropay | 9.6 | 9. QR Scheme Integration (ZeroPay) | Settlement files (ZP0061–0066) | 2 | Implement ZP0061 morning cron job and batch dependency gate | The ZP0061 morning settlement cron job runs at ~04:30 KST (internal deadline) and transmits by ~05:00 KST. Pre-conditions (SCH-06 §8.2): ZP0011 batch for the prior day must be status=TRANSMITTED and ZP0012 must be status=RECEIVED (confirming ZeroPay acknowledged registrations). If ZP0012 has not been received by 04:30, the job must alert Ops (P1) and abort. If ZP0012 contains registration failures for some transactions, those transactions are excluded from ZP0061; non-affected transactions proceed. Cron fires Mon-Sat only. Job is idempotent. | • Implement MorningSettlementBatchJob.run(LocalDate settlementDate, Long schemeId) • Check pre-condition: settlement_batch for (schemeId, ZP0012, settlementDate-1, NIGHTLY).status == RECEIVED; if not, publish OpsAlert(P1) and abort • Check pre-condition: settlement_batch for (schemeId, ZP0011, settlementDate-1, NIGHTLY).status == TRANSMITTED; if not, publish OpsAlert(P1) and abort • Call SettlementBatchGenerationService.generateMorning, then SftpOutboundTransmitter • Annotate @Scheduled(cron='0 30 4 * * MON-SAT', zone='Asia/Seoul') | MorningSettlementBatchJob.java + unit tests | • If ZP0012 status is PENDING (not yet received), job aborts without creating any ZP0061 batch row and publishes 1 OpsAlertEvent(P1) • If ZP0012 is RECEIVED but contains 2 registration failures, those 2 txn IDs are excluded from ZP0061; remaining transactions proceed • If ZP0011 is not TRANSMITTED, job aborts without generating ZP0061 • Second invocation with ZP0061 already in GENERATED status returns the existing batch (idempotency) • Job does not fire on Sunday (cron MON-SAT constraint verified in test) | 45 | 9.6-T10, 9.6-T11 | BE | SCH-06
9.6-T18 | scheme-adapter-zeropay | 9.6 | 9. QR Scheme Integration (ZeroPay) | Settlement files (ZP0061–0066) | 2 | Implement SFTP inbound poller for ZP0062 and ZP0064 | ZP0062 (morning settlement result) is expected ~10:00 KST; ZP0064 (afternoon settlement result) ~19:00 KST. The inbound SFTP poller (SAD-02 §5.4) polls /gmepay/inbound/ every 5 minutes from 09:00-12:00 KST for ZP0062 and from 18:00-21:00 KST for ZP0064. On file detection: download, decrypt PGP, validate filename pattern, check file size > 0. Record settlement_file row with direction=INBOUND. Update settlement_batch.status=RECEIVED and received_at. If file not received by cutoff (ZP0062: 12:00 KST, ZP0064: 21:00 KST), publish OpsAlertEvent(P2, 'file not received within window'). Files are processed exactly once (idempotency via settlement_file.filename unique check). | • Implement SftpInboundPoller.pollForZP0062(LocalDate settlementDate) and pollForZP0064(LocalDate settlementDate): list SFTP inbound directory, filter by filename pattern ZP006{2¦4}_{YYYYMMDD}_*.dat.pgp • On file found: download, store settlement_file row, update settlement_batch status=RECEIVED, trigger ZP006xResultFileParser • Schedule via @Scheduled(fixedDelay=300000) with active window guards (ZP0062: 09:00-12:00 KST, ZP0064: 18:00-21:00 KST) • Idempotency: before downloading, check settlement_file table for filename; skip if already processed • At 12:00 KST if ZP0062 not received, publish OpsAlertEvent(P2); at 21:00 KST for ZP0064 | SftpInboundPoller.java + unit tests (mocked SFTP) | • File ZP0062_20260605_01.dat.pgp found at 10:04 KST: settlement_batch.status=RECEIVED, received_at set, settlement_file row inserted • Same filename found on second poll cycle: not re-processed (idempotency; settlement_file already exists) • ZP0062 not found by 12:00 KST: OpsAlertEvent(P2) published exactly once (not once per poll cycle) • Poll does not attempt to download files outside its active time window (09:00-12:00 for ZP0062) • A zero-byte file is rejected with SettlementFileParseException and OpsAlert; not persisted to settlement_file | 50 | 9.6-T12, 9.6-T11 | BE | SCH-06
9.6-T19 | scheme-adapter-zeropay | 9.6 | 9. QR Scheme Integration (ZeroPay) | Settlement files (ZP0061–0066) | 2 | Implement ZP0063 afternoon cron job with morning cycle dependency | The ZP0063 afternoon cron job runs at ~13:30 KST (internal deadline) and transmits by ~14:00 KST. Pre-condition (SCH-06 §8.2): the morning settlement cycle must be complete, meaning ZP0061 batch status=TRANSMITTED. ZP0063 should not block on ZP0062 result (which arrives at ~10:00 and may still be reconciling). ZP0063 covers supplementary same-day transactions not included in ZP0061 — i.e. transactions with settlement_date=today and settlement_batch_id IS NULL and status=SETTLEMENT_REGISTERED. Cron fires Mon-Sat. Job is idempotent. | • Implement AfternoonSettlementBatchJob.run(LocalDate settlementDate, Long schemeId) • Pre-condition check: ZP0061 for (schemeId, settlement_date=today, MORNING).status = TRANSMITTED; if not, OpsAlert(P2) and abort • Call SettlementBatchGenerationService.generateAfternoon and SftpOutboundTransmitter • Annotate @Scheduled(cron='0 30 13 * * MON-SAT', zone='Asia/Seoul') • Write unit tests: normal flow, ZP0061 not yet transmitted (abort), idempotency, empty afternoon transaction set (produces empty file, still transmitted) | AfternoonSettlementBatchJob.java + unit tests | • ZP0061 status=TRANSMITTED: afternoon job proceeds and ZP0063 batch created with window=AFTERNOON • ZP0061 status=GENERATED (not yet transmitted): afternoon job aborts, OpsAlert(P2) published, no ZP0063 batch created • Empty afternoon txn set: ZP0063 file generated with 0 records, status=TRANSMITTED (empty file is valid) • Idempotency: second invocation when ZP0063 already GENERATED returns existing batch without re-generating • Cron expression fires at 13:30 on Wednesday KST; does not fire on Saturday (wait - Sat IS a business day); does not fire on Sunday | 40 | 9.6-T09, 9.6-T17, 9.6-T18 | BE | SCH-06
9.6-T20 | scheme-adapter-zeropay | 9.6 | 9. QR Scheme Integration (ZeroPay) | Settlement files (ZP0061–0066) | 2 | Implement ZP0064 receipt processing and afternoon reconciliation trigger | After ZP0064 (afternoon settlement result) is received and parsed (~19:00 KST), the system must: 1) update settlement_batch for ZP0063 with status=RECEIVED for the companion ZP0064 row, 2) call SettlementReconciliationService.reconcile(ZP0063 outbound batch, ZP0064 result records), 3) update reconciled_at on the ZP0063 batch on clean match. Any discrepancy creates reconciliation_item rows and publishes OpsAlertEvent(P1). This mirrors the morning cycle (ZP0062 triggers reconciliation of ZP0061) but for the afternoon window. | • Implement AfternoonResultProcessor.process(LocalDate settlementDate, Long schemeId, List<SettlementResultRecord> zp0064Records) • Look up ZP0063 settlement_batch for (schemeId, settlementDate, AFTERNOON); if not found, throw IllegalStateException (ZP0064 arrived without a corresponding ZP0063 outbound) • Delegate reconciliation to SettlementReconciliationService (T13) • Publish settlement_completed event for downstream consumers (e.g. settlement.completed webhook to partners) after reconciliation • Write unit tests: clean reconciliation, amount mismatch, missing ZP0063 outbound | AfternoonResultProcessor.java + unit tests | • Clean ZP0064 with 2 merchants matching ZP0063: ZP0063 batch status=RECONCILED, reconciled_at set, 0 reconciliation_item rows • ZP0064 merchant amount differs by 1000 KRW from ZP0063: 1 DISCREPANCY reconciliation_item, OpsAlert(P1) published • ZP0064 received with no corresponding ZP0063 batch: IllegalStateException thrown, no data written • settlement_completed event is published after successful reconciliation with total_payout_krw = sum of credited amounts • ZP0064 reprocessed (idempotency): reconciliation_item rows not duplicated; existing RECONCILED batch returned | 40 | 9.6-T13, 9.6-T19 | BE | SCH-06
9.6-T21 | scheme-adapter-zeropay | 9.6 | 9. QR Scheme Integration (ZeroPay) | Settlement files (ZP0061–0066) | 2 | Implement detail reconciliation: ZP0065 vs internal ledger | Detail reconciliation (SCH-06 §9.1) compares ZP0065 line items against the internal transaction ledger. For each transaction in ZP0065: look up the transaction by zeropay_txn_ref, compare payout_amount_krw with txn.target_payout (KRW). If match, no action. If mismatch, create reconciliation_item with match_status=DISCREPANCY. If zeropay_txn_ref in ZP0065 not found in GME DB, match_status=MISSING_GME. If transaction in GME DB (settlement_batch_id NOT NULL, settlement_date = target) not in ZP0065, match_status=MISSING_SCHEME. Tolerance: zero (every line item must match). This check is run after ZP0065 is transmitted, as a self-verification step against the ledger. | • Implement ZP0065DetailReconciler.reconcile(Long zp0065BatchId, List<ZP0065DetailRecord> lines): for each line, look up transaction by zeropay_txn_ref, compare payout_amount_krw vs target_payout • For GME-side: query all transactions with settlement_date=targetDate and settlement_batch_id IN (morning_batch_id, afternoon_batch_id) • Persist reconciliation_item rows for any mismatch; publish OpsAlert(P1) per discrepancy • Write unit tests: clean case (3 lines, 3 match), 1 line amount mismatch, 1 line missing from GME DB, 1 GME txn missing from file | ZP0065DetailReconciler.java + unit tests | • 3 matching lines produce 0 reconciliation_item rows and no OpsAlert • Line with zeropay_txn_ref='ZP20260605001' not in GME DB: reconciliation_item match_status=MISSING_GME, scheme_ref='ZP20260605001', txn_ref=NULL • GME txn with zeropay_txn_ref='ZP20260605002' absent from ZP0065: reconciliation_item match_status=MISSING_SCHEME, txn_ref set, scheme_ref=NULL • payout_amount_krw mismatch of 500 KRW: discrepancy_amount=500.0000 in reconciliation_item • Reconciler is idempotent: running twice on same data does not create duplicate reconciliation_item rows | 45 | 9.6-T05, 9.6-T14 | BE | SCH-06
9.6-T22 | scheme-adapter-zeropay | 9.6 | 9. QR Scheme Integration (ZeroPay) | Settlement files (ZP0061–0066) | 2 | Implement ZP0066 vs internal ledger detail reconciliation | Mirrors ZP0065DetailReconciler (T21) but for refund records. ZP0066 line items are compared against GME refund records by original_zeropay_txn_ref. GME refund fields: original_zeropay_txn_ref (FK to original payment's zeropay_txn_ref), refund_amount_krw = refund.amount_krw. Tolerance: zero. If ZP0066 refund_amount_krw differs from GME refund.amount_krw for the same original_zeropay_txn_ref: DISCREPANCY. If ZP0066 line has no matching GME refund: MISSING_GME. If GME refund not in ZP0066: MISSING_SCHEME. | • Implement ZP0066DetailReconciler.reconcile(Long zp0066BatchId, List<ZP0066DetailRecord> lines) with analogous logic to T21 • Look up refund by original_zeropay_txn_ref; compare refund_amount_krw vs refund.amount_krw • Persist reconciliation_item rows; publish OpsAlert(P1) on any mismatch • Write unit tests identical in structure to T21 but using refund records • Verify same-day cancel exclusion: refunds excluded from ZP0066 generation (T15) are also absent from reconciliation scope | ZP0066DetailReconciler.java + unit tests | • Matching refund: 0 reconciliation_item rows, no OpsAlert • ZP0066 record with original_zeropay_txn_ref not in GME refund table: MISSING_GME reconciliation_item • GME refund not appearing in ZP0066 file: MISSING_SCHEME reconciliation_item • refund_amount_krw mismatch of 200 KRW: DISCREPANCY item with discrepancy_amount=200.0000 • Idempotent: second call on same data does not create duplicate items | 35 | 9.6-T21, 9.6-T15 | BE | SCH-06
9.6-T23 | scheme-adapter-zeropay | 9.6 | 9. QR Scheme Integration (ZeroPay) | Settlement files (ZP0061–0066) | 2 | Implement batch retransmission with incremented SEQ number | On SFTP failure or Ops-initiated retransmit, the outbound file must be retransmitted with an incremented sequence number in the filename (e.g. ZP0061_20260605_02.dat.pgp for the first retransmit). The file content must be regenerated idempotently for the same transaction set (same transactions already assigned to the batch via settlement_batch_id). The settlement_batch row retains the same id; a new settlement_file row is inserted with the new filename. Status transitions: ERROR -> GENERATED -> TRANSMITTED on successful retransmit. | • Implement SettlementBatchRetransmitService.retransmit(Long batchId): loads existing SettlementBatch, increments SEQ (queries MAX(seq) from settlement_file for this batch + 1), regenerates file bytes from the already-assigned transactions, calls SftpOutboundTransmitter with new filename • Status change: set status=GENERATED before transmission, then TRANSMITTED on success • Insert new settlement_file row with incremented filename; do not delete old settlement_file rows (audit trail) • Write unit tests: first retransmit produces SEQ=02; second retransmit produces SEQ=03; file bytes are byte-identical to original for same transaction set (idempotency) • Verify retransmit is blocked if current status is RECONCILED (no need to retransmit a reconciled file) | SettlementBatchRetransmitService.java + unit tests | • First retransmit: new settlement_file row with filename ZP0061_20260605_02.dat.pgp; original _01 row retained • File bytes for retransmit are byte-identical to original (same sorted merchant order, same amounts) • Retransmitting a RECONCILED batch throws IllegalStateException('cannot retransmit reconciled batch') • SEQ=03 on third retransmit (two prior settlement_file rows with seq 01 and 02) • After successful retransmit, settlement_batch.status=TRANSMITTED and transmitted_at updated to new timestamp | 40 | 9.6-T11, 9.6-T10 | BE | SCH-06
9.6-T24 | scheme-adapter-zeropay | 9.6 | 9. QR Scheme Integration (ZeroPay) | Settlement files (ZP0061–0066) | 2 | Implement late-file monitoring and cutoff alerts for ZP0062/ZP0064 | SCH-06 §9.5 defines escalation cutoffs: ZP0062 must be received by 12:00 KST (P2 alert if missed); ZP0064 by 21:00 KST (P2 alert). A scheduled monitor checks at those cutoff times whether the corresponding settlement_batch row exists with status=RECEIVED. If not, it publishes OpsAlertEvent(P2, details). The monitor must fire exactly once per cutoff (not repeatedly). The cutoff monitor is independent of the polling job (T18) — it is a hard deadline check. | • Implement SettlementCutoffMonitor.checkZP0062Cutoff(LocalDate settlementDate) and checkZP0064Cutoff • Check settlement_batch for (schemeId, ZP0062 or ZP0064, settlementDate, MORNING or AFTERNOON).status; if not RECEIVED by cutoff, publish OpsAlertEvent(P2) • Schedule ZP0062 check at 12:00 KST Mon-Sat; ZP0064 check at 21:00 KST Mon-Sat • Use a flag (DB column or idempotency table) to ensure OpsAlert is published exactly once per date per file type • Write unit tests: file received before cutoff = no alert; file not received = 1 alert; monitor called twice = 1 alert (idempotency) | SettlementCutoffMonitor.java + unit tests | • ZP0062 received at 10:04 (before 12:00 cutoff): monitor at 12:00 publishes no OpsAlert • ZP0062 not received by 12:00: monitor publishes exactly 1 OpsAlertEvent(P2) containing file_type='ZP0062' and settlement_date • Monitor called twice for same date and file (retry scenario): OpsAlert published exactly once • ZP0064 cutoff at 21:00 KST for the same settlement_date is independent of ZP0062 check • Monitor does not fire on Sunday (cron MON-SAT constraint) | 35 | 9.6-T18 | BE | SCH-06
9.6-T25 | scheme-adapter-zeropay | 9.6 | 9. QR Scheme Integration (ZeroPay) | Settlement files (ZP0061–0066) | 2 | Implement Ops exception queue service for settlement discrepancies | Settlement discrepancies (DISCREPANCY, MISSING_GME, MISSING_SCHEME reconciliation_items) are surfaced in the Ops Admin portal exception queue (PRD-07 §UC-04-03). The service provides the query and resolution operations. Resolution: Ops can mark an item as RESOLVED with a resolution_note; the action is audit-logged. ESCALATED status is set when Ops cannot resolve and escalates to GME Finance. All resolution actions use the standard audit trail (actor, timestamp, previous_value). | • Implement ExceptionQueueService.listUnresolved(Long batchId): returns all reconciliation_items with resolution_status=UNRESOLVED ordered by match_status (DISCREPANCY first) • Implement resolve(Long itemId, String operatorId, String resolutionNote): sets resolution_status=RESOLVED, resolved_by, resolved_at, persists audit_log entry with previous resolution_status=UNRESOLVED • Implement escalate(Long itemId, String operatorId, String note): sets resolution_status=ESCALATED • Write unit tests for list, resolve, and escalate; verify audit_log entry is created on resolve | ExceptionQueueService.java + unit tests | • listUnresolved for a batch with 2 DISCREPANCY + 1 MISSING_SCHEME returns 3 items, DISCREPANCY items first • resolve() sets resolution_status=RESOLVED, resolved_at is non-null, resolution_note persisted • resolve() creates an audit_log row with entity_type='reconciliation_item', field='resolution_status', previous_value='UNRESOLVED', new_value='RESOLVED', actor=operatorId • Attempting to resolve an already-RESOLVED item throws IllegalStateException('item already resolved') • escalate() sets resolution_status=ESCALATED and creates audit_log entry; does not set resolved_at | 40 | 9.6-T05, 9.6-T13 | BE | SCH-06
9.6-T26 | scheme-adapter-zeropay | 9.6 | 9. QR Scheme Integration (ZeroPay) | Settlement files (ZP0061–0066) | 2 | Unit tests: ZP0061/ZP0063 generation with net vs gross settlement numeric vectors | Explicit numeric test vectors for ZP0061/ZP0063 generation covering both settlement types. Test data: (A) Domestic txn: partner=GME_Remit (LOCAL), target_payout=10000 KRW, service_charge=500 KRW, settlement_type='N'; expected ZP0061 record: gross_txn_amount=10000, merchant_fee_total=500, net_settlement_amount=10000. (B) International txn: partner=SendMN (OVERSEAS), target_payout=50000 KRW, settlement_type='G'; expected ZP0061 record: gross_txn_amount=50000, merchant_fee_total=0, net_settlement_amount=50000. (C) Mixed merchant: 1 domestic + 1 international txn for same merchant should be in separate records (domestic partners do not mix with international in the same merchant settlement record — assert this separation). | • Write ZP0061GenerationVectorTest.java with test cases A, B, and C above • For each test: set up transaction objects, call ZP0061MorningSettlementRequestBuilder.build(), parse output bytes, assert field values • Test C: verify that a domestic txn and international txn for merchant M001 do NOT merge into one record (they have different settlement_type; assert two separate records or verify the spec intention and document it) • Add a fourth test: zero transactions for a settlement_date produces an empty file (0 data records, header + trailer present) • Run tests; all must pass green | ZP0061GenerationVectorTest.java (all tests passing) | • Test A: ZP0061 record for domestic txn has net_settlement_amount=10000, merchant_fee_total=500, settlement_type='N' • Test B: ZP0061 record for international txn has net_settlement_amount=50000, merchant_fee_total=0, settlement_type='G' • Test C: two records present for merchant M001 (one per settlement_type) or single record with spec-compliant merging — behaviour must be explicitly documented in test • Zero-transaction test: output byte array parses to 0 data records with valid header and trailer • All 4 tests pass in CI without external dependencies (in-memory only) | 45 | 9.6-T08, 9.6-T07 | BE | SCH-06
9.6-T27 | scheme-adapter-zeropay | 9.6 | 9. QR Scheme Integration (ZeroPay) | Settlement files (ZP0061–0066) | 2 | Unit tests: reconciliation engine vectors for ZP0062 result processing | Test vectors for SettlementReconciliationService (T13) covering all match_status outcomes. Test data: settlement_date=2026-06-05. ZP0061 outbound has 3 merchants: M001 KRW 10000, M002 KRW 20000, M003 KRW 5000 (total 35000). ZP0062 result scenarios: (A) All 3 match exactly -> RECONCILED, 0 items. (B) M001 amount=9000 (mismatch -1000) -> 1 DISCREPANCY item, discrepancy_amount=1000. (C) M004 appears in ZP0062 but not in ZP0061 -> 1 MISSING_GME item. (D) M003 absent from ZP0062 -> 1 MISSING_SCHEME item. (E) All four anomalies combined: 1 DISCREPANCY + 1 MISSING_GME + 1 MISSING_SCHEME -> 3 items, OpsAlert published 3 times. | • Write SettlementReconciliationVectorTest.java with test scenarios A through E • Mock ZP0061 outbound data and ZP0062 parsed result records for each scenario • Assert reconciliation_item count, match_status values, discrepancy_amount, and OpsAlertEvent publish count • Verify settlement_batch.status=RECONCILED in all scenarios (even those with discrepancies) • Run all 5 tests; all must pass | SettlementReconciliationVectorTest.java (all 5 tests passing) | • Scenario A: 0 reconciliation_item rows, status=RECONCILED, 0 OpsAlerts • Scenario B: 1 DISCREPANCY item, discrepancy_amount=1000.0000 (gme_amount=10000, scheme_amount=9000), 1 OpsAlert(P1) • Scenario C: 1 MISSING_GME item with scheme_ref='M004', txn_ref=NULL • Scenario D: 1 MISSING_SCHEME item with txn_ref set to M003 transactions, scheme_ref=NULL • Scenario E: 3 reconciliation_items total (1 DISCREPANCY, 1 MISSING_GME, 1 MISSING_SCHEME), 3 OpsAlerts(P1) | 40 | 9.6-T13 | BE | SCH-06
9.6-T28 | scheme-adapter-zeropay | 9.6 | 9. QR Scheme Integration (ZeroPay) | Settlement files (ZP0061–0066) | 2 | Unit tests: ZP0065 detail builder and detail reconciliation vectors | Numeric test vectors for ZP0065 detail file and its reconciliation. Setup: settlement_date=2026-06-05; 2 transactions in MORNING batch (M001 KRW 10000, M002 KRW 30000) + 1 transaction in AFTERNOON batch (M001 KRW 20000). ZP0065 should have 3 records. Reconciliation vector: (A) all 3 lines match internal ledger -> 0 items. (B) ZP0065 line with zeropay_txn_ref='ZP001' has payout_amount_krw=9000 but GME txn has target_payout=10000 -> DISCREPANCY, discrepancy_amount=1000. (C) ZP0065 contains zeropay_txn_ref='ZP999' not in GME DB -> MISSING_GME. (D) GME txn ZP002 not in ZP0065 -> MISSING_SCHEME. | • Write ZP0065DetailVectorTest.java: test ZP0065 output has 3 records with correct payout_amount_krw, merchant_id, settlement_batch_ref values • Write ZP0065ReconciliationVectorTest.java: scenarios A through D using ZP0065DetailReconciler (T21) • For the detail builder test: verify settlement_batch_ref in each record matches the correct batch filename (MORNING txns -> ZP0061 ref, AFTERNOON -> ZP0063 ref) • Run all tests; all must pass | ZP0065DetailVectorTest.java + ZP0065ReconciliationVectorTest.java (all tests passing) | • ZP0065 output has exactly 3 records for the described input; sorted by merchant_id ASC then txn_time ASC • MORNING transaction settlement_batch_ref='ZP0061_20260605_01'; AFTERNOON='ZP0063_20260605_01' • Scenario B: DISCREPANCY item with discrepancy_amount=1000.0000 • Scenario C: MISSING_GME item with scheme_ref='ZP999' • Scenario D: MISSING_SCHEME item with txn_ref set to GME transaction reference for ZP002 | 35 | 9.6-T14, 9.6-T21 | BE | SCH-06
9.6-T29 | scheme-adapter-zeropay | 9.6 | 9. QR Scheme Integration (ZeroPay) | Settlement files (ZP0061–0066) | 2 | Integration test: full daily settlement batch lifecycle (ZP0061 through ZP0065/ZP0066) | End-to-end integration test covering the complete daily settlement cycle for 2026-06-05. Scope: 3 domestic txns (GME Remit, KRW 10000 each) + 2 international txns (SendMN, KRW 50000 each) all with status=SETTLEMENT_REGISTERED and settlement_batch_id=NULL. Steps: run morning job -> verify ZP0061 generated with 5 txns across merchants -> simulate ZP0062 receipt with matching amounts -> verify RECONCILED status -> run afternoon job (1 new txn) -> ZP0063 generated -> simulate ZP0064 -> RECONCILED -> run 22:00 job -> ZP0065 has 6 records, ZP0066 has 0 (no refunds). All DB changes verified. No real SFTP; use in-memory stub. | • Set up embedded Postgres (Testcontainers) with schema from migrations T01-T03 • Insert 5 transactions in SETTLEMENT_REGISTERED status • Call MorningSettlementBatchJob.run(); assert ZP0061 batch GENERATED, 5 txns assigned • Inject ZP0062 file stub (all amounts match); call AfternoonResultProcessor.process equivalent for morning; assert RECONCILED • Insert 1 afternoon txn; call AfternoonSettlementBatchJob.run(); assert ZP0063 GENERATED • Inject ZP0064 stub; assert ZP0063 RECONCILED; call DetailSettlementBatchJob.run(); assert ZP0065 has 6 records, ZP0066 has 0 | SettlementBatchIntegrationTest.java (all assertions passing with Testcontainers) | • After morning job: 5 transactions have settlement_batch_id = ZP0061 batch id, settlement_window='MORNING' • ZP0061 settlement_batch.transaction_count=5, total_amount = sum of 5 net_settlement_amounts • After ZP0062 injection: ZP0061 batch status=RECONCILED, 0 reconciliation_item rows • ZP0065 contains exactly 6 records (5 morning + 1 afternoon) with correct settlement_batch_ref values • ZP0066 file generated with 0 data records (valid empty file, header + trailer only) | 60 | 9.6-T16, 9.6-T17, 9.6-T19, 9.6-T20, 9.6-T23 | BE | SCH-06
9.6-T30 | scheme-adapter-zeropay | 9.6 | 9. QR Scheme Integration (ZeroPay) | Settlement files (ZP0061–0066) | 2 | Integration test: idempotency and retransmission scenarios | Validates idempotency guarantees and retransmission for WBS 9.6 components. Scenarios: (1) Run morning batch job twice for same date -> assert exactly 1 settlement_batch row, 5 (not 10) txns assigned. (2) ZP0061 SFTP fails 3 times -> status=ERROR, OpsAlert(P1) published, 0 ZP0065 txns re-selected. (3) Retransmit from ERROR state -> new settlement_file row with SEQ=02, same batch id, same file content. (4) Reprocess ZP0062 result file twice -> 0 duplicate reconciliation_items. | • Write IdempotencyIntegrationTest.java using Testcontainers Postgres and mocked SFTP • Scenario 1: call generateMorning twice; assert unique constraint holds, 1 batch row, transaction assignment is idempotent • Scenario 2: mock SFTP to fail 3x; assert OpsAlert count=1, settlement_batch.status=ERROR • Scenario 3: call retransmit(batchId); assert new settlement_file row, status=TRANSMITTED, SEQ=02 in filename • Scenario 4: call reconcile with same ZP0062 parsed result twice; assert reconciliation_item count does not increase on second call | IdempotencyIntegrationTest.java (all 4 scenarios passing) | • Scenario 1: SELECT COUNT(*) FROM settlement_batch WHERE file_type='ZP0061' AND settlement_date='2026-06-05' = 1 after two job runs • Scenario 2: OpsAlertEvent published exactly once; settlement_batch.status='ERROR' • Scenario 3: settlement_file rows for the batch = 2 (seq 01 failed, seq 02 transmitted); batch status='TRANSMITTED' • Scenario 4: calling reconcile twice produces the same number of reconciliation_item rows as calling it once • Transaction assignment after scenario 1: COUNT of txns with settlement_batch_id NOT NULL = 5, not 10 | 55 | 9.6-T29, 9.6-T23 | BE | SCH-06
9.6-T31 | scheme-adapter-zeropay | 9.6 | 9. QR Scheme Integration (ZeroPay) | Settlement files (ZP0061–0066) | 2 | Add settlement_batch_id and settlement_window to transaction event trail (step 7) | The 8-step transaction event trail (SAD-02 §6.1 / Admin portal §8.5.3) records key lifecycle timestamps. Step 7 is settlement_recorded (UTC, delta ms). When a transaction is assigned to a settlement_batch (T10), a transaction_event row must be inserted: step=7, event_type='settlement_recorded', metadata={settlement_batch_id: X, file_type: 'ZP0061', window: 'MORNING'}. This enables the Admin portal settlement linkage panel (PRD-07 §8.5.5) showing which ZP0061/ZP0065 batch a transaction is in. | • In SettlementBatchGenerationService (T10), after the bulk UPDATE on transaction.settlement_batch_id, insert transaction_event rows (step=7, event_type='settlement_recorded') for each assigned transaction in the same DB transaction • Metadata JSON: {settlement_batch_id, file_type, window, settlement_date} • Write unit tests: after generateMorning, 5 txns each have 1 transaction_event with step=7 and correct metadata • Verify that re-running the job (idempotency path) does NOT insert duplicate step-7 events • Verify existing step-6 (transaction_committed) events are not affected | Updated SettlementBatchGenerationService.java + unit tests for event trail step 7 | • Each of 5 assigned transactions has exactly 1 transaction_event with step=7, event_type='settlement_recorded' • transaction_event.metadata contains settlement_batch_id matching the new batch, file_type='ZP0061', window='MORNING' • Second invocation (idempotency): no additional transaction_event rows inserted (step-7 event count per txn remains 1) • Step-6 (transaction_committed) event count is unchanged after settlement batch generation • transaction_event.created_at is within 1 second of the batch generation timestamp | 35 | 9.6-T10 | BE | SCH-06
9.6-T32 | scheme-adapter-zeropay | 9.6 | 9. QR Scheme Integration (ZeroPay) | Settlement files (ZP0061–0066) | 2 | Add settlement batch status to Admin portal settlement dashboard (batch status view) | The Admin portal Settlement & Revenue screen (PRD-07 §4.9 / §11.2.2) shows a Batch Status View with one row per settlement date per file type. Required columns: Settlement Date, Transaction Count, Gross Payout (KRW), GME Fee Share (KRW), Net Settlement (KRW), ZP0061 Status (Sent/Matched/Discrepancy), ZP0062 Status (Received/Not yet received), Reconciliation Status (Matched/Discrepancy/Pending). The backend API endpoint GET /internal/v1/settlement/batches?date={date}&schemeId={id} must return this data from settlement_batch and reconciliation_item tables. | • Implement GET /internal/v1/settlement/batches handler: query settlement_batch rows for the given date and scheme, join with reconciliation_item count per batch, compute aggregates (sum total_amount, count transactions) • Map BatchStatus to UI labels: TRANSMITTED='Sent', RECONCILED='Matched', ERROR='Discrepancy' for ZP0061 column; RECEIVED='Received', null='Not yet received' for ZP0062 column • Include Domestic and International net settlement totals separately (domestic=net, international=gross) • Secure endpoint with ROLE_OPS_OPERATOR or ROLE_FINANCE_ANALYST (read-only) • Write unit tests for the controller with mocked service | SettlementDashboardController.java + SettlementBatchSummaryDto.java + unit tests | • ZP0061 status=TRANSMITTED maps to 'Sent' in response; RECONCILED maps to 'Matched'; ERROR maps to 'Discrepancy' • ZP0062 not yet received (no RECEIVED batch row): ZP0062_status='Not yet received' in response • Response includes transaction_count=5 and gross_payout_krw=70000 for the test settlement date • Endpoint returns 403 for a request with ROLE_PARTNER (unauthorized) • Reconciliation status = 'Discrepancy' when any reconciliation_item with match_status != MATCHED exists for the batch | 45 | 9.6-T04, 9.6-T05, 9.6-T25 | BE | SCH-06
9.6-T33 | scheme-adapter-zeropay | 9.6 | 9. QR Scheme Integration (ZeroPay) | Settlement files (ZP0061–0066) | 2 | Add settlement linkage panel to transaction detail view (Admin portal) | The Admin portal transaction detail screen (PRD-07 §8.5.5) must show a Settlement Linkage panel: which ZeroPay batch files the transaction was included in (ZP0011/ZP0061/ZP0065 reference, batch date, registration result). The backend endpoint GET /internal/v1/transactions/{txn_id}/settlement-linkage must return: settlement_batch_id, file_type (ZP0061 or ZP0063), settlement_date, batch_status, filename from settlement_file, and registration_status from the transaction row (SETTLEMENT_REGISTERED or REGISTRATION_FAILED etc). | • Implement GET /internal/v1/transactions/{txn_id}/settlement-linkage handler: join transaction -> settlement_batch (via settlement_batch_id) -> settlement_file (latest file for batch) • Also include the ZP0011 batch reference (from the existing batch_file_log or settlement_batch for ZP0011) and ZP0065 batch reference (from settlement_batch for ZP0065 where this txn's zeropay_txn_ref appears) • Return 404 if transaction not settled yet (settlement_batch_id IS NULL) • Enforce partner_id ownership: transaction must belong to the requesting operator's visible scope • Write unit tests covering: settled txn, unsettled txn (404), unauthorized access (403) | TransactionSettlementLinkageController.java + SettlementLinkageDto.java + unit tests | • Settled transaction returns dto with file_type='ZP0061', settlement_date='2026-06-05', batch_status='RECONCILED', filename='ZP0061_20260605_01.dat.pgp' • Unsettled transaction (settlement_batch_id IS NULL) returns HTTP 404 • Requesting settlement linkage for a txn_id belonging to a different partner returns 403 • Response includes all three file references: ZP0011_ref, ZP0061_or_ZP0063_ref, ZP0065_ref • registration_status='SETTLEMENT_REGISTERED' for a successfully registered transaction | 40 | 9.6-T31, 9.6-T32 | BE | SCH-06
9.6-T34 | scheme-adapter-zeropay | 9.6 | 9. QR Scheme Integration (ZeroPay) | Settlement files (ZP0061–0066) | 2 | Ops runbook entry: settlement file delivery procedures and cutoff escalation | OPS-13 references a settlement processing runbook. A concise in-code runbook document is required covering the daily ZP006x batch procedures, cutoff times, escalation paths, and manual intervention steps. This ensures a developer or ops engineer can execute the batch without project context. Content must match the spec exactly: ZP0061 internal deadline 04:30 KST (due ~05:00), ZP0063 13:30 KST (due ~14:00), ZP0065/ZP0066 21:30 KST (due ~22:00). Escalation: ZP0061 late = P1 (affects merchant crediting). Exception queue access path. Retransmit procedure. | • Create docs/runbooks/settlement-zp006x.md with sections: Overview, Daily Timeline, Batch Job Reference, Pre-condition Checks, Exception Handling, Retransmission Procedure, Escalation Matrix • Include exact cron expressions and their KST equivalents for all 5 batch jobs • Include the SettlementBatchRetransmitService API call sequence for manual retransmit • List all OpsAlertEvent priority codes and their escalation owners • Review for accuracy against spec; add to the repository alongside other runbooks | docs/runbooks/settlement-zp006x.md | • Document states ZP0061 internal deadline as 04:30 KST and ZeroPay deadline as ~05:00 KST • Document lists P1 escalation for ZP0061 late delivery with note 'affects same-day merchant crediting' • Retransmission procedure includes step to call SettlementBatchRetransmitService.retransmit(batchId) and verify new SEQ filename • Exception queue access path references ExceptionQueueService.listUnresolved(batchId) and Admin portal UC-04-03 screen • Escalation matrix distinguishes P1 (ZP0061/ZP0063 late, SFTP failure, registration failure blocking settlement) from P2 (ZP0062/ZP0064 late, ZP0065/ZP0066 late) | 30 | 9.6-T17, 9.6-T19, 9.6-T16, 9.6-T23, 9.6-T25 | BE | SCH-06
9.7-T01 | scheme-adapter-zeropay | 9.7 | 9. QR Scheme Integration (ZeroPay) | Batch scheduler & window monitoring | 2 | Create batch_job_definition table migration | GMEPay+ needs a config-driven batch scheduler for ZeroPay ZP00xx jobs. Each job (JOB-ZP-01 through JOB-ZP-13) has a fixed file type, direction, KST window, criticality, and dependency chain. All times are stored in UTC; KST = UTC+9. The scheduler reads job definitions from DB so that new schemes can be added without code changes. | • Create Flyway migration V9_7_001__batch_job_definition.sql • Define table batch_job_definition with columns: id BIGINT PK, job_id VARCHAR(20) UNIQUE NOT NULL, scheme_id BIGINT FK qr_scheme, file_types VARCHAR(100) NOT NULL, direction VARCHAR(20) NOT NULL CHECK(GME_TO_ZP,ZP_TO_GME), window_utc TIME NOT NULL, alert_threshold_utc TIME NOT NULL, criticality VARCHAR(10) NOT NULL CHECK(CRITICAL,HIGH,MEDIUM,LOW), dependency_job_id VARCHAR(20) FK SELF NULLABLE, is_weekly BOOLEAN NOT NULL DEFAULT FALSE, enabled BOOLEAN NOT NULL DEFAULT TRUE, created_at TIMESTAMPTZ, updated_at TIMESTAMPTZ • Add CHECK constraint: direction IN ('GME_TO_ZP','ZP_TO_GME') • Add index idx_bjd_scheme_enabled on (scheme_id, enabled) • Seed the 13 ZeroPay jobs per OPS-13 schedule: JOB-ZP-01 ZP0011 GME_TO_ZP 17:00UTC(02:00KST) alert 16:45UTC CRITICAL; JOB-ZP-02 ZP0021 GME_TO_ZP 17:00UTC alert 16:45UTC CRITICAL; JOB-ZP-03 ZP0012 ZP_TO_GME 20:00UTC(05:00KST) alert 20:30UTC CRITICAL dep JOB-ZP-01; JOB-ZP-04 ZP0022 ZP_TO_GME 20:00UTC alert 20:30UTC CRITICAL dep JOB-ZP-02; JOB-ZP-05 ZP0061 GME_TO_ZP 20:00UTC alert 20:15UTC CRITICAL dep JOB-ZP-03; JOB-ZP-06 ZP0062 ZP_TO_GME 01:00UTC(10:00KST) alert 01:30UTC CRITICAL dep JOB-ZP-05; JOB-ZP-07 ZP0063 GME_TO_ZP 05:00UTC(14:00KST) alert 05:15UTC HIGH; JOB-ZP-08 ZP0064 ZP_TO_GME 10:30UTC(19:30KST) alert 10:30UTC HIGH dep JOB-ZP-07; JOB-ZP-09 ZP0065,ZP0066 GME_TO_ZP 13:00UTC(22:00KST) alert 13:15UTC HIGH; JOB-ZP-10 ZP0041,ZP0045,ZP0047 ZP_TO_GME 23:00UTC(08:00KST) alert 23:00UTC MEDIUM is_weekly FALSE; JOB-ZP-11 ZP0043 ZP_TO_GME 23:00UTC MEDIUM; JOB-ZP-12 ZP0051,ZP0055 ZP_TO_GME 23:00UTC MEDIUM is_weekly TRUE; JOB-ZP-13 ZP0053 ZP_TO_GME 23:00UTC MEDIUM is_weekly TRUE | Flyway migration file db/migrations/V9_7_001__batch_job_definition.sql with table DDL and 13 seed rows for ZeroPay jobs | • Migration applies cleanly on a fresh schema with no errors • SELECT COUNT(*) FROM batch_job_definition WHERE scheme_id = (zeropay id) returns 13 • JOB-ZP-05 row has dependency_job_id = 'JOB-ZP-03' and criticality = 'CRITICAL' • JOB-ZP-12 row has is_weekly = TRUE and direction = 'ZP_TO_GME' • window_utc for JOB-ZP-01 is 17:00:00 (confirming 02:00 KST prev-day UTC equiv) | 40 |  | DevOps | SCH-06, OPS-13
9.7-T02 | scheme-adapter-zeropay | 9.7 | 9. QR Scheme Integration (ZeroPay) | Batch scheduler & window monitoring | 2 | Create batch_job_run table migration | Every execution of a batch job must persist a run record for idempotency checks and audit. The table batch_job_run tracks each execution: job definition, business date (KST), run status, start/end times, retry count, and error detail. A UNIQUE constraint on (job_id, business_date, run_seq) prevents duplicate runs for the same logical date. run_seq starts at 1; retransmissions increment it. | • Create Flyway migration V9_7_002__batch_job_run.sql • Define table batch_job_run: id UUID PK DEFAULT gen_random_uuid(), job_definition_id BIGINT FK batch_job_definition NOT NULL, job_id VARCHAR(20) NOT NULL, business_date DATE NOT NULL, run_seq INT NOT NULL DEFAULT 1, status VARCHAR(20) NOT NULL DEFAULT 'PENDING' CHECK(PENDING,RUNNING,SUCCESS,FAILED,SKIPPED), started_at TIMESTAMPTZ, completed_at TIMESTAMPTZ, retry_count INT NOT NULL DEFAULT 0, error_code VARCHAR(50), error_detail TEXT, settlement_batch_id BIGINT FK settlement_batch NULLABLE, created_at TIMESTAMPTZ NOT NULL DEFAULT now() • Add UNIQUE constraint uq_bjr_job_date_seq on (job_id, business_date, run_seq) • Add index idx_bjr_job_date on (job_id, business_date) for idempotency lookups • Add index idx_bjr_status_created on (status, created_at) for monitoring queries | Flyway migration file db/migrations/V9_7_002__batch_job_run.sql | • Migration applies cleanly after V9_7_001 • INSERT of two rows with same (job_id, business_date, run_seq) raises unique violation • Status CHECK constraint rejects value 'DONE' • SELECT with (job_id='JOB-ZP-01', business_date='2026-06-05', run_seq=1) returns at most 1 row • Foreign key to batch_job_definition is enforced on INSERT | 30 | 9.7-T01 | DevOps | SCH-06, OPS-13
9.7-T03 | scheme-adapter-zeropay | 9.7 | 9. QR Scheme Integration (ZeroPay) | Batch scheduler & window monitoring | 2 | Create batch_window_alert table migration | When a batch job misses its alert threshold time, the system must log an alert record and prevent duplicate firing. Table batch_window_alert captures: job_id, business_date, alert_severity (P1/P2/P3), alert_fired_at, channels notified (JSON array of 'PAGERDUTY','SLACK','EMAIL'), and acknowledged_at. One row per job per business_date per severity level; prevents re-alerting on every polling cycle. | • Create Flyway migration V9_7_003__batch_window_alert.sql • Define table batch_window_alert: id BIGINT GENERATED ALWAYS AS IDENTITY PK, job_id VARCHAR(20) NOT NULL, business_date DATE NOT NULL, alert_severity VARCHAR(5) NOT NULL CHECK('P1','P2','P3'), alert_fired_at TIMESTAMPTZ NOT NULL DEFAULT now(), channels_notified JSONB NOT NULL DEFAULT '[]', acknowledged_at TIMESTAMPTZ, acknowledged_by VARCHAR(120), created_at TIMESTAMPTZ NOT NULL DEFAULT now() • Add UNIQUE constraint uq_bwa_job_date_severity on (job_id, business_date, alert_severity) • Add index idx_bwa_unack on (business_date, acknowledged_at) WHERE acknowledged_at IS NULL • Add FK batch_window_alert(job_id) REFERENCES batch_job_definition(job_id) ON DELETE RESTRICT | Flyway migration file db/migrations/V9_7_003__batch_window_alert.sql | • Migration applies cleanly after V9_7_002 • Inserting same (job_id, business_date, alert_severity) twice raises unique violation, preventing double-alert • channels_notified JSONB accepts '["PAGERDUTY","SLACK"]' value • Partial index on unacknowledged alerts is present in pg_indexes • FK constraint rejects job_id not present in batch_job_definition | 25 | 9.7-T02 | DevOps | SCH-06, OPS-13
9.7-T04 | scheme-adapter-zeropay | 9.7 | 9. QR Scheme Integration (ZeroPay) | Batch scheduler & window monitoring | 2 | Define BatchJobDefinition and BatchJobRun JPA entities | The batch scheduler is in the Batch/SFTP Worker service (Java/Spring). Two JPA entities map to the tables created in T01 and T02. BatchJobDefinition holds static config (job_id, scheme, file_types, direction, window_utc, alert_threshold_utc, criticality, dependency_job_id, is_weekly, enabled). BatchJobRun is the per-execution audit record. Use Hibernate; columns match exact DB names via @Column annotations. | • Create BatchJobDefinition.java in package com.gmepay.batch.domain • Annotate with @Entity, @Table(name='batch_job_definition'); map all columns; add @OneToOne self-ref for dependency; add getters/setters or use @Data • Create BatchJobRun.java in same package • Annotate BatchJobRun; add @ManyToOne to BatchJobDefinition; status field as enum BatchJobStatus{PENDING,RUNNING,SUCCESS,FAILED,SKIPPED} • Create BatchWindowAlert.java entity for the alert table (from T03) • Add repositories BatchJobDefinitionRepository (findBySchemeIdAndEnabled), BatchJobRunRepository (findByJobIdAndBusinessDate), BatchWindowAlertRepository (existsByJobIdAndBusinessDateAndAlertSeverity) | Three entity classes and three Spring Data JPA repositories under com.gmepay.batch.domain and com.gmepay.batch.repository | • Spring context loads without Hibernate schema validation errors against the migrated DB • BatchJobDefinitionRepository.findBySchemeIdAndEnabled(schemeId, true) returns 13 rows for ZeroPay • BatchJobRunRepository.findByJobIdAndBusinessDate('JOB-ZP-01', LocalDate.of(2026,6,5)) returns empty list on a clean DB • BatchWindowAlertRepository.existsByJobIdAndBusinessDateAndAlertSeverity('JOB-ZP-01', date, 'P1') returns false before first alert • BatchJobStatus enum covers all 5 status values and toString matches DB CHECK constraint values | 45 | 9.7-T03 | DevOps | SCH-06, OPS-13
9.7-T05 | scheme-adapter-zeropay | 9.7 | 9. QR Scheme Integration (ZeroPay) | Batch scheduler & window monitoring | 2 | Implement BatchScheduleService: cron trigger registration | The Batch/SFTP Worker must register Spring @Scheduled cron expressions for each enabled job at application startup. Cron expressions are derived from window_utc in batch_job_definition. Because the worker runs as a single Kubernetes CronJob (OPS-13 §10.1), it must also support manual trigger via an internal endpoint. All cron expressions are in UTC (e.g. JOB-ZP-01 window_utc=17:00 -> '0 0 17 * * MON-SAT'). ZeroPay runs Mon-Sat; Sunday and holidays use is_weekly flag logic. | • Create BatchScheduleService.java in com.gmepay.batch.scheduler • On @PostConstruct, load all enabled BatchJobDefinition rows for the active scheme • For each definition, compute cron expression: '0 {min} {hour} * * MON-SAT' from window_utc; weekly jobs use '0 {min} {hour} * * SUN' • Register cron tasks dynamically using TaskScheduler.schedule(Runnable, CronTrigger) • Expose internal method triggerJobManually(String jobId, LocalDate businessDate) for admin rerun • Log each registered cron at INFO: 'Registered cron for JOB-ZP-01: 0 0 17 * * MON-SAT (UTC)' | BatchScheduleService.java with dynamic cron registration and manual trigger support | • On startup, 13 cron tasks are registered (verify via log output or ScheduledTaskHolder bean) • JOB-ZP-12 (weekly, window_utc=23:00) registers cron '0 0 23 * * SUN' • JOB-ZP-01 (window_utc=17:00, Mon-Sat) registers cron '0 0 17 * * MON-SAT' • triggerJobManually('JOB-ZP-01', LocalDate.now()) invokes the job handler without throwing • Disabling a job (enabled=false) in DB and restarting causes that cron to not register | 50 | 9.7-T04 | DevOps | SCH-06, OPS-13
9.7-T06 | scheme-adapter-zeropay | 9.7 | 9. QR Scheme Integration (ZeroPay) | Batch scheduler & window monitoring | 2 | Implement BatchJobRunner: idempotency guard and run-record lifecycle | Before executing any job, the runner must check if a SUCCESS run already exists for (job_id, business_date). If so, log 'already processed' and return without action. If a RUNNING record exists for > 30 minutes, treat it as stale and reset to FAILED before retrying. The run sequence (run_seq) starts at 1 and increments on each retry attempt. OPS-13 §6.3: up to 3 automatic retries with exponential back-off 30s, 120s, 300s. | • Create BatchJobRunner.java in com.gmepay.batch.scheduler • Method executeJob(String jobId, LocalDate businessDate): check BatchJobRunRepository for existing SUCCESS -> return SKIPPED; check for RUNNING > 30 min -> update to FAILED • Compute next run_seq = max existing run_seq + 1 (default 1 if none) • Insert new BatchJobRun with status=RUNNING, started_at=now() • Delegate to BatchJobDispatcher.dispatch(jobId, businessDate, runId) • On success update status=SUCCESS, completed_at=now(); on exception update status=FAILED, error_detail=exception.getMessage() • Implement retry loop: catch exception, sleep back-off (30s/120s/300s for retry 1/2/3), retry up to 3 times; after 3 failures leave status=FAILED | BatchJobRunner.java with idempotency check, run-record lifecycle management, and retry loop | • Calling executeJob twice for same (job_id, date) where first run has SUCCESS returns SKIPPED on second call with no new run record inserted • A RUNNING record with started_at 35 minutes ago is reset to FAILED before a new run starts • run_seq increments: first attempt=1, first retry=2, second retry=3 • After 3 failures the record has status=FAILED and retry_count=3 • Back-off delays are 30s, 120s, 300s (verify with a test clock mock) | 55 | 9.7-T05 | DevOps | SCH-06, OPS-13
9.7-T07 | scheme-adapter-zeropay | 9.7 | 9. QR Scheme Integration (ZeroPay) | Batch scheduler & window monitoring | 2 | Implement dependency-chain enforcement in batch dispatcher | OPS-13 §6.2 dependency chain: JOB-ZP-05 (ZP0061) must not run unless JOB-ZP-03 (ZP0012) and JOB-ZP-01 (ZP0011) both have SUCCESS for that business_date. Similarly JOB-ZP-03 depends on JOB-ZP-01. The dependency_job_id column in batch_job_definition carries the immediate prerequisite. If the prerequisite is not SUCCESS, the current job must wait (status=PENDING) and log a warning. SCH-06 §8.2: if ZP0012 or ZP0022 indicate registration failures, settlement generation for affected transactions must be held. | • Create BatchJobDispatcher.java in com.gmepay.batch.scheduler • Method dispatch(String jobId, LocalDate businessDate, UUID runId): load BatchJobDefinition for jobId • If definition.dependencyJobId is not null, check BatchJobRunRepository for SUCCESS of dependency on same businessDate • If dependency not SUCCESS: update run to status=PENDING, log WARN 'JOB-ZP-05 waiting on JOB-ZP-03 for 2026-06-05'; throw DependencyNotMetException • If dependency SUCCESS: proceed to delegate to scheme-specific handler via BatchJobHandler interface • Expose a resolvePending(LocalDate businessDate) method: re-check all PENDING runs whose dependency is now SUCCESS and re-trigger them | BatchJobDispatcher.java with dependency enforcement and pending-job resolution | • dispatch('JOB-ZP-05', date, runId) where JOB-ZP-03 has no SUCCESS for that date throws DependencyNotMetException and sets run status=PENDING • dispatch('JOB-ZP-05', date, runId) where JOB-ZP-03 has SUCCESS proceeds without exception • resolvePending(date) re-triggers JOB-ZP-05 after JOB-ZP-03 succeeds • JOB-ZP-07 (no dependency) dispatches immediately without dependency check • JOB-ZP-01 (no dependency) dispatches immediately | 45 | 9.7-T06 | DevOps | SCH-06, OPS-13
9.7-T08 | scheme-adapter-zeropay | 9.7 | 9. QR Scheme Integration (ZeroPay) | Batch scheduler & window monitoring | 2 | Implement BatchWindowMonitor: missed-window detection | OPS-13 §6.4 defines alert thresholds: JOB-ZP-01/02 not submitted by 01:45 KST (16:45 UTC prev day) -> P1; ZP0012/22 not received by 05:30 KST (20:30 UTC) -> P1; ZP0061 not submitted by 05:15 KST (20:15 UTC) -> P1; ZP0062 not received by 10:30 KST (01:30 UTC next day) -> P1; ZP0063 not submitted by 14:15 KST (05:15 UTC) -> P2; ZP0064 not received by 19:30 KST (10:30 UTC) -> P2; ZP0065/66 not submitted by 22:15 KST (13:15 UTC) -> P2; merchant/QR sync not received by 08:00 KST (23:00 UTC) -> P3. The monitor polls every 5 minutes. | • Create BatchWindowMonitor.java in com.gmepay.batch.monitor • @Scheduled(fixedRate=300000) method checkWindows(): compute current UTC time and current KST business date • For each enabled BatchJobDefinition, check if alert_threshold_utc has passed for today • Query BatchJobRunRepository: does a SUCCESS run exist for (job_id, businessDate)? • If threshold passed and no SUCCESS: check BatchWindowAlertRepository for existing alert for (job_id, businessDate, severity); if none exists, fire alert and insert record • Fire alert via AlertingService.sendAlert(jobId, businessDate, severity, channels) where channels come from criticality mapping: CRITICAL->P1->[PAGERDUTY,SLACK], HIGH->P2->[SLACK], MEDIUM->P3->[EMAIL] | BatchWindowMonitor.java with 5-minute polling, threshold evaluation, and deduplication via batch_window_alert | • At 16:50 UTC with no SUCCESS for JOB-ZP-01 today, monitor fires P1 alert and inserts batch_window_alert row • Second polling cycle 5 min later does NOT fire a second alert (idempotent via unique constraint) • JOB-ZP-07 missed at 05:20 UTC fires P2 alert to SLACK only (not PagerDuty) • JOB-ZP-10 merchant sync missed at 23:05 UTC fires P3 alert to EMAIL only • A job that has SUCCESS before threshold fires no alert | 50 | 9.7-T07 | DevOps | SCH-06, OPS-13
9.7-T09 | scheme-adapter-zeropay | 9.7 | 9. QR Scheme Integration (ZeroPay) | Batch scheduler & window monitoring | 2 | Implement AlertingService: PagerDuty + Slack + Email dispatch | Alerts from BatchWindowMonitor must be sent to configured channels. OPS-13 §7.5.3: P1 -> PagerDuty + Ops Slack; P2 -> Ops Slack only; P3 -> Ops email. AlertingService is a lightweight adapter that reads channel config from environment variables (PAGERDUTY_ROUTING_KEY, SLACK_WEBHOOK_URL, OPS_EMAIL_SMTP_*). Each channel call is fire-and-forget with a local exception catch to prevent one channel failure from blocking others. All sent alerts are logged as structured JSON. | • Create AlertingService.java in com.gmepay.batch.monitor • Method sendAlert(String jobId, LocalDate businessDate, String severity, List<String> channels): build alert payload with job_id, business_date, severity, message, fired_at_utc • For PAGERDUTY channel: POST to https://events.pagerduty.com/v2/enqueue with routing_key from env; payload: event_action=trigger, summary=message, severity=critical¦error¦warning • For SLACK channel: POST JSON {text: message} to SLACK_WEBHOOK_URL • For EMAIL channel: send via JavaMailSender to OPS_EMAIL_ADDRESS • Catch exceptions per channel; log ERROR if channel fails but continue; update channels_notified JSONB in batch_window_alert with successfully-sent channels • Log structured JSON at WARN: {event:'BATCH_WINDOW_ALERT', job_id, business_date, severity, channels_sent} | AlertingService.java with PagerDuty, Slack, and email dispatch; partial failure tolerance | • P1 alert sends to both PAGERDUTY and SLACK; if PagerDuty fails, SLACK still sends and channels_notified=["SLACK"] • P2 alert sends to SLACK only and does not attempt PagerDuty • P3 alert sends email only • Alert payload includes job_id, business_date, and severity fields • Structured log line emitted on every sendAlert call with event='BATCH_WINDOW_ALERT' | 45 | 9.7-T08 | DevOps | SCH-06, OPS-13
9.7-T10 | scheme-adapter-zeropay | 9.7 | 9. QR Scheme Integration (ZeroPay) | Batch scheduler & window monitoring | 2 | Implement full-file suppression logic for weekly sync jobs | SCH-06 §4: when a full-sync file (ZP0051 full merchant, ZP0055 franchise full, ZP0053 full QR) arrives on the same night as a delta file (ZP0041, ZP0045, ZP0043), the scheduler must detect the full file and suppress the delta upsert for that entity type. In batch_job_definition, ZP0051/ZP0055/ZP0053 are marked is_weekly=TRUE. The suppression check: if a SUCCESS run for the full-file job (JOB-ZP-12 or JOB-ZP-13) exists for tonight's processing date, skip the corresponding delta job (JOB-ZP-10 or JOB-ZP-11). | • Add method shouldSuppressDeltaJob(String deltaJobId, LocalDate businessDate) to BatchJobDispatcher • Map delta-to-full job: ZP0041/ZP0045/ZP0047 (JOB-ZP-10) suppressed by JOB-ZP-12; ZP0043 (JOB-ZP-11) suppressed by JOB-ZP-13 • Query BatchJobRunRepository: if SUCCESS for corresponding full-file job on same businessDate -> return true • In BatchJobRunner.executeJob, call shouldSuppressDeltaJob before dispatch; if true, set status=SKIPPED and log INFO 'Delta job JOB-ZP-10 suppressed: full file JOB-ZP-12 already processed for 2026-06-08' • Add a unit test covering the Sunday case where both jobs arrive | shouldSuppressDeltaJob method in BatchJobDispatcher and corresponding suppression path in BatchJobRunner | • On a Sunday with JOB-ZP-12 SUCCESS, JOB-ZP-10 is set to SKIPPED without executing • On a weekday with no JOB-ZP-12 run, JOB-ZP-10 runs normally • SKIPPED status is persisted in batch_job_run with no error fields set • Log line 'Delta job JOB-ZP-10 suppressed' appears in INFO output • JOB-ZP-11 suppression by JOB-ZP-13 follows the same logic independently | 40 | 9.7-T07 | DevOps | SCH-06, OPS-13
9.7-T11 | scheme-adapter-zeropay | 9.7 | 9. QR Scheme Integration (ZeroPay) | Batch scheduler & window monitoring | 2 | Implement KST business-date resolver | All batch jobs operate on KST (UTC+9) business dates. The nightly jobs (ZP0011, ZP0021 submit at 02:00 KST = 17:00 UTC previous day) process transactions for the prior KST business date. The batch scheduler must correctly resolve: given a UTC execution timestamp, what is the KST business date to process? Rule: if UTC wall-clock time is before 15:00 UTC (before midnight KST), business date = UTC date - 1 day in KST; if >= 15:00 UTC, business date = UTC date in KST. ZeroPay runs Mon-Sat; Sunday is not a settlement day. | • Create KstBusinessDateResolver.java in com.gmepay.batch.util • Method resolveBusinessDate(Instant utcNow): convert to ZoneId.of('Asia/Seoul'); extract LocalDate in KST; that is the business date • Method isPreviousDayJob(String jobId): return true for JOB-ZP-01 and JOB-ZP-02 (they process prior-day transactions even though they run after midnight KST) • Method isSettlementDay(LocalDate kstDate): return kstDate.getDayOfWeek() != SUNDAY (Mon-Sat) • Method getProcessingDate(String jobId, Instant utcNow): for prior-day jobs return resolveBusinessDate(utcNow).minusDays(1); for same-day jobs return resolveBusinessDate(utcNow) • Add constant KST_ZONE = ZoneId.of('Asia/Seoul') | KstBusinessDateResolver.java utility class | • resolveBusinessDate(Instant.parse('2026-06-04T17:30:00Z')) returns 2026-06-05 (17:30 UTC = 02:30 KST next day) • resolveBusinessDate(Instant.parse('2026-06-04T14:30:00Z')) returns 2026-06-04 (14:30 UTC = 23:30 KST same day) • isSettlementDay(LocalDate.of(2026,6,7)) returns false (Sunday) • isSettlementDay(LocalDate.of(2026,6,6)) returns true (Saturday) • getProcessingDate('JOB-ZP-01', Instant.parse('2026-06-05T17:30:00Z')) returns 2026-06-05 (prior-day job: processes June 5 txns at 02:30 KST June 6) | 35 | 9.7-T05 | DevOps | SCH-06, OPS-13
9.7-T12 | scheme-adapter-zeropay | 9.7 | 9. QR Scheme Integration (ZeroPay) | Batch scheduler & window monitoring | 2 | Implement settlement-day guard: skip jobs on Sunday and holidays | ZeroPay operates Mon-Sat (Assumption A-09, SCH-06 §7.3). Batch jobs must not run on Sundays. Korean public holidays behaviour is TBD but the scheduler must support a configurable holiday skip list. Store holidays in a new DB table batch_holiday (scheme_id, holiday_date, description). On job execution, check if business date is Sunday or in batch_holiday; if so, set run status=SKIPPED with reason='NON_SETTLEMENT_DAY' and do not proceed. | • Create Flyway migration V9_7_004__batch_holiday.sql: table batch_holiday (id BIGINT PK, scheme_id BIGINT FK, holiday_date DATE NOT NULL, description VARCHAR(200), UNIQUE(scheme_id, holiday_date)) • Create BatchHoliday.java JPA entity and BatchHolidayRepository • Add method isHoliday(Long schemeId, LocalDate date) to BatchHolidayRepository using EXISTS query • In BatchJobRunner.executeJob, after idempotency check: call KstBusinessDateResolver.isSettlementDay(businessDate) and batchHolidayRepository.isHoliday(schemeId, businessDate); if either false, insert SKIPPED run and return • Weekly sync jobs (is_weekly=TRUE) are exempted from settlement-day check (merchant data arrives on Sundays) | V9_7_004__batch_holiday.sql migration, BatchHoliday entity/repository, and settlement-day guard in BatchJobRunner | • executeJob('JOB-ZP-01', LocalDate.of(2026,6,7)) returns SKIPPED with reason='NON_SETTLEMENT_DAY' (Sunday) • Inserting (zeropay_scheme_id, 2026-10-03) into batch_holiday causes executeJob for that date to return SKIPPED • Weekly job JOB-ZP-12 on a holiday date still executes (is_weekly exemption) • Unique constraint on (scheme_id, holiday_date) prevents duplicate holiday entries • Log line at INFO includes 'reason=NON_SETTLEMENT_DAY' on skip | 40 | 9.7-T11 | DevOps | SCH-06, OPS-13
9.7-T13 | scheme-adapter-zeropay | 9.7 | 9. QR Scheme Integration (ZeroPay) | Batch scheduler & window monitoring | 2 | Implement manual job rerun endpoint in Admin API | OPS-13 §8.7: Ops must be able to manually rerun a failed batch job from the Admin System. The rerun accepts job_id and business_date and invokes BatchJobRunner.executeJob. The endpoint must enforce: only FAILED or SKIPPED runs can be rerun (not SUCCESS); rerun is idempotent (check for existing SUCCESS before proceeding). Accessible only to Ops role via the Admin System backend API. Logs operator identity and reason. | • Create BatchJobController.java in the Admin System backend (com.gmepay.admin.controller) • POST /api/v1/admin/batch/rerun with body {jobId: String, businessDate: String(YYYY-MM-DD), reason: String} • Validate: jobId must exist in batch_job_definition; businessDate must be parseable; reason required • Check: if SUCCESS run exists for (jobId, businessDate) return 409 Conflict with message 'Job already succeeded for this date' • If no FAILED/SKIPPED run exists return 404 • Invoke BatchJobRunner.executeJob(jobId, LocalDate.parse(businessDate)) asynchronously via @Async • Return 202 Accepted with {runId, jobId, businessDate, status:'QUEUED'}; log structured {event:'MANUAL_RERUN', operator, job_id, business_date, reason} | BatchJobController.java POST /api/v1/admin/batch/rerun endpoint with role guard, idempotency check, and async dispatch | • POST with valid FAILED job returns 202 and a new batch_job_run row appears with RUNNING status • POST for a job with existing SUCCESS returns 409 Conflict • POST with unknown jobId returns 400 Bad Request • POST without Ops role returns 403 Forbidden • Structured log entry with event='MANUAL_RERUN' and operator identity is emitted | 50 | 9.7-T06 | DevOps | SCH-06, OPS-13
9.7-T14 | scheme-adapter-zeropay | 9.7 | 9. QR Scheme Integration (ZeroPay) | Batch scheduler & window monitoring | 2 | Implement batch job status query endpoint | Admin System needs to display current batch job health on the Batch Health dashboard (OPS-13 §7.4). Endpoint GET /api/v1/admin/batch/status returns all jobs for a given business_date with their latest run status, last success time, and any unacknowledged alerts. This is a read-only query across batch_job_definition, batch_job_run, and batch_window_alert tables. | • Add GET /api/v1/admin/batch/status?businessDate=YYYY-MM-DD to BatchJobController • Query: for each BatchJobDefinition (scheme=ZeroPay, enabled=true), fetch latest BatchJobRun for the given businessDate ordered by run_seq DESC; fetch unacknowledged BatchWindowAlert for same date • Build response DTO BatchJobStatusResponse: {jobs: [{jobId, fileTypes, direction, windowKst, latestRunStatus, latestRunSeq, lastSuccessAt, alertSeverity(nullable), alertFiredAt(nullable)}]} • windowKst is computed as window_utc + 9 hours for display only • Return 200 with DTO; if businessDate is missing default to today KST | GET /api/v1/admin/batch/status endpoint returning per-job status and active alerts for a given business date | • Response for today contains 13 job entries for ZeroPay • A job with SUCCESS run shows latestRunStatus='SUCCESS' and lastSuccessAt populated • A job with FAILED run and an active P1 alert shows alertSeverity='P1' and alertFiredAt populated • businessDate defaults to today KST when param absent • Endpoint returns 400 if businessDate is not valid YYYY-MM-DD format | 40 | 9.7-T04 | DevOps | SCH-06, OPS-13
9.7-T15 | scheme-adapter-zeropay | 9.7 | 9. QR Scheme Integration (ZeroPay) | Batch scheduler & window monitoring | 2 | Implement alert acknowledgement endpoint | When Ops acknowledges a missed-window alert (e.g. after manually resolving), the alert record must be updated with acknowledged_at and acknowledged_by. This clears the alert from the unacknowledged view and prevents repeated PagerDuty noise. PATCH /api/v1/admin/batch/alerts/{id}/acknowledge accepts operator identity from JWT claims. | • Add PATCH /api/v1/admin/batch/alerts/{id}/acknowledge to BatchJobController • Load BatchWindowAlert by id; if not found return 404 • If already acknowledged return 409 with message 'Alert already acknowledged' • Set acknowledged_at=now() and acknowledged_by=principal.getName() (from Spring Security context) • Save and return 200 with updated alert DTO {id, jobId, businessDate, alertSeverity, alertFiredAt, acknowledgedAt, acknowledgedBy} • Log structured {event:'ALERT_ACKNOWLEDGED', alert_id, job_id, business_date, operator} | PATCH /api/v1/admin/batch/alerts/{id}/acknowledge endpoint with idempotency check and audit log | • PATCH on unacknowledged alert sets acknowledged_at to within 1s of now() and acknowledged_by to caller's identity • Second PATCH on same alert returns 409 • PATCH with unknown id returns 404 • Structured log event='ALERT_ACKNOWLEDGED' includes operator identity • After acknowledgement, GET /batch/status shows no active alert for that job/date | 30 | 9.7-T14 | DevOps | SCH-06, OPS-13
9.7-T16 | scheme-adapter-zeropay | 9.7 | 9. QR Scheme Integration (ZeroPay) | Batch scheduler & window monitoring | 2 | Implement Prometheus metrics for batch job health | OPS-13 §7.1 and §7.4: the Batch Health dashboard requires Prometheus metrics. Required metrics: batch_job_last_run_status (gauge, labels: job_id, status, 1=SUCCESS/0=else), batch_job_last_success_seconds (gauge, labels: job_id, unix epoch of last success), batch_window_alert_active (gauge, labels: job_id, severity, 1=unacknowledged alert exists). Micrometer is the metrics library; MeterRegistry injected via Spring. | • Create BatchMetricsExporter.java in com.gmepay.batch.monitor • Inject MeterRegistry and BatchJobRunRepository and BatchWindowAlertRepository • @Scheduled(fixedRate=60000) method exportMetrics(): for each enabled job_id, query latest run status for today and last SUCCESS time • Register/update Gauge batch_job_last_run_status with tag job_id and value 1.0 if SUCCESS else 0.0 • Register/update Gauge batch_job_last_success_seconds with value of lastSuccessAt.toEpochSecond() or 0 if never • Register/update Gauge batch_window_alert_active with value 1.0 if unacknowledged alert exists else 0.0 • Metrics exposed via /actuator/prometheus endpoint (existing Spring Boot Actuator) | BatchMetricsExporter.java exporting 3 Prometheus gauge metrics updated every 60 seconds | • GET /actuator/prometheus includes batch_job_last_run_status{job_id='JOB-ZP-01'} line • After a SUCCESS run for JOB-ZP-01, batch_job_last_run_status{job_id='JOB-ZP-01'} = 1.0 • After an unacknowledged P1 alert, batch_window_alert_active{job_id='JOB-ZP-01',severity='P1'} = 1.0 • After alert acknowledgement, batch_window_alert_active drops to 0.0 within 60s • Metrics endpoint returns HTTP 200 with content-type text/plain;version=0.0.4 | 40 | 9.7-T08 | DevOps | SCH-06, OPS-13
9.7-T17 | scheme-adapter-zeropay | 9.7 | 9. QR Scheme Integration (ZeroPay) | Batch scheduler & window monitoring | 2 | Unit tests: KstBusinessDateResolver edge cases | The KstBusinessDateResolver (T11) is logic-bearing: its output determines which transactions are included in each batch file. Must test midnight-KST boundary, day-before-sunday, and all day-of-week settlement checks. Use JUnit 5 + parameterized tests. Exact UTC timestamps and expected results provided. | • Create KstBusinessDateResolverTest.java in src/test • Parameterized test for resolveBusinessDate: input 2026-06-04T14:59:59Z expect 2026-06-04; input 2026-06-04T15:00:00Z expect 2026-06-05; input 2026-06-05T17:30:00Z expect 2026-06-06; input 2026-06-06T15:00:00Z expect 2026-06-07 (Saturday) • Parameterized test for isSettlementDay: Monday 2026-06-01 true; Saturday 2026-06-06 true; Sunday 2026-06-07 false • Test getProcessingDate for JOB-ZP-01 at 2026-06-06T17:30:00Z: expect 2026-06-06 (processes June 6 txns at 02:30 KST June 7) • Test getProcessingDate for JOB-ZP-06 at 2026-06-06T01:30:00Z: expect 2026-06-06 (same-day job at 10:30 KST) | KstBusinessDateResolverTest.java with >= 12 parameterized test cases covering boundary conditions | • All 12+ test cases pass with no failures • The 15:00 UTC boundary (midnight KST) is covered with before/at/after cases • Sunday detection is explicitly tested (isSettlementDay Sunday -> false) • Prior-day job vs same-day job distinction is tested for getProcessingDate • Test class has zero external dependencies beyond JUnit 5 and the class under test | 35 | 9.7-T11 | DevOps | SCH-06, OPS-13
9.7-T18 | scheme-adapter-zeropay | 9.7 | 9. QR Scheme Integration (ZeroPay) | Batch scheduler & window monitoring | 2 | Unit tests: BatchJobRunner idempotency and retry logic | BatchJobRunner (T06) has two critical behaviors: idempotency guard (no re-run on existing SUCCESS) and retry with back-off (up to 3 attempts, 30s/120s/300s delays). Use Mockito to mock BatchJobRunRepository and BatchJobDispatcher. Use a fixed TestClock to control time and verify back-off without real sleeps. | • Create BatchJobRunnerTest.java in src/test • Mock BatchJobRunRepository: when findByJobIdAndBusinessDate returns a SUCCESS run, verify executeJob returns SKIPPED and dispatch is never called • Mock: stale RUNNING run (started 35 min ago) -> verify status reset to FAILED then new run inserted • Test retry: mock dispatch to throw RuntimeException on first 2 calls, succeed on 3rd; verify run_seq=3 at success and retry_count=2 • Test failure after 3 retries: mock dispatch always throws; verify final status=FAILED, retry_count=3, error_detail contains exception message • Inject TestClock; verify back-off sleeps are 30000ms, 120000ms (not real sleeps) | BatchJobRunnerTest.java with >= 8 test cases covering idempotency, stale-run reset, retry success, and retry exhaustion | • Idempotency test: dispatch mock is called zero times when SUCCESS exists • Stale-run test: repository.save called with status=FAILED for the stale record • Retry-success test: run_seq is 3 on success, retry_count is 2 • Retry-exhaustion test: final status=FAILED with non-null error_detail • Back-off durations match 30000/120000/300000 ms precisely via clock verification | 45 | 9.7-T06 | DevOps | SCH-06, OPS-13
9.7-T19 | scheme-adapter-zeropay | 9.7 | 9. QR Scheme Integration (ZeroPay) | Batch scheduler & window monitoring | 2 | Unit tests: BatchWindowMonitor threshold firing and deduplication | BatchWindowMonitor (T08) must fire exactly one alert per (job_id, businessDate, severity) even if polled many times. Use Mockito: mock BatchJobRunRepository (no SUCCESS), mock BatchWindowAlertRepository (first call returns false, subsequent calls return true), mock AlertingService. Verify alert is sent once and not again. | • Create BatchWindowMonitorTest.java in src/test • Setup: mock current UTC time as 16:50 UTC (JOB-ZP-01 threshold=16:45 UTC passed); mock no SUCCESS run for today; mock alertRepository.exists returns false • Verify: AlertingService.sendAlert called once with jobId='JOB-ZP-01', severity='P1', channels=[PAGERDUTY,SLACK] • Second invocation of checkWindows() with alertRepository.exists now returning true: verify sendAlert NOT called again • Test P2 threshold: JOB-ZP-07 at 05:20 UTC -> P2 alert to [SLACK] only • Test no alert when job has SUCCESS before threshold | BatchWindowMonitorTest.java with >= 6 test cases covering P1/P2 firing, deduplication, and no-alert-on-success scenarios | • Deduplication test: sendAlert is called exactly once across two checkWindows() invocations • P1 test: channels list includes both PAGERDUTY and SLACK • P2 test: channels list contains SLACK only, not PAGERDUTY • No-alert test: sendAlert never called when SUCCESS run exists before threshold • All test cases pass without real time sleeps or real HTTP calls | 40 | 9.7-T08 | DevOps | SCH-06, OPS-13
9.7-T20 | scheme-adapter-zeropay | 9.7 | 9. QR Scheme Integration (ZeroPay) | Batch scheduler & window monitoring | 2 | Unit tests: dependency chain enforcement in BatchJobDispatcher | BatchJobDispatcher (T07) must block JOB-ZP-05 if JOB-ZP-03 is not SUCCESS, and allow it when JOB-ZP-03 is SUCCESS. Also verify that JOB-ZP-03 depends on JOB-ZP-01. Test all three cases: dependency missing, dependency FAILED, and dependency SUCCESS. Also test full-file suppression (T10) for delta vs full sync. | • Create BatchJobDispatcherTest.java in src/test • Test 1: dispatch JOB-ZP-05 with no run for JOB-ZP-03 -> throws DependencyNotMetException, run status=PENDING • Test 2: dispatch JOB-ZP-05 with JOB-ZP-03 status=FAILED -> throws DependencyNotMetException • Test 3: dispatch JOB-ZP-05 with JOB-ZP-03 status=SUCCESS -> delegates to handler, no exception • Test 4: dispatch JOB-ZP-01 (no dependency) -> delegates immediately • Test 5: shouldSuppressDeltaJob('JOB-ZP-10', sunday) with JOB-ZP-12 SUCCESS -> true • Test 6: shouldSuppressDeltaJob('JOB-ZP-10', weekday) with no JOB-ZP-12 run -> false | BatchJobDispatcherTest.java with >= 6 test cases covering dependency states and delta suppression | • Test 1 and 2 both throw DependencyNotMetException and run is left as PENDING • Test 3 invokes the job handler mock exactly once • Test 4 invokes handler without any dependency lookup • Test 5 returns true (suppress delta) • Test 6 returns false (do not suppress) | 40 | 9.7-T07, 9.7-T10 | DevOps | SCH-06, OPS-13
9.7-T21 | scheme-adapter-zeropay | 9.7 | 9. QR Scheme Integration (ZeroPay) | Batch scheduler & window monitoring | 2 | Unit tests: full-file suppression on Sunday sync scenario | On Sunday nights, ZP0051 (full merchant) and ZP0053 (full QR) may arrive alongside delta files. The suppressDelta logic must correctly identify Sunday, check for full-file SUCCESS, and suppress delta execution. Edge case: if the full file job FAILS (e.g. corrupt file), the delta should NOT be suppressed (fail-open: delta runs as fallback). Test both success and failure states of the full-file job. | • Create BatchJobRunnerSuppressTest.java in src/test • Mock BatchJobRunRepository: JOB-ZP-12 SUCCESS for 2026-06-07 (Sunday) -> executeJob('JOB-ZP-10', 2026-06-07) returns SKIPPED • Mock: JOB-ZP-12 FAILED for same date -> executeJob('JOB-ZP-10', 2026-06-07) runs normally (not suppressed) • Mock: JOB-ZP-12 no run for same date -> executeJob('JOB-ZP-10', 2026-06-07) runs normally • Test JOB-ZP-13 (full QR) SUCCESS -> JOB-ZP-11 (delta QR) suppressed • Test JOB-ZP-12 SUCCESS but JOB-ZP-13 FAILED -> JOB-ZP-11 still runs (only its own full-file suppresses it) | BatchJobRunnerSuppressTest.java with 5 test cases for Sunday full-file suppression edge cases | • Full-file SUCCESS suppresses delta: SKIPPED status and no dispatch call • Full-file FAILED does NOT suppress delta: dispatch called • Full-file absent does NOT suppress delta: dispatch called • JOB-ZP-11 suppression is independent of JOB-ZP-10 suppression status • All tests pass without modifying BatchJobRunner production code (tests use existing extension points) | 35 | 9.7-T10, 9.7-T17 | DevOps | SCH-06, OPS-13
9.7-T22 | scheme-adapter-zeropay | 9.7 | 9. QR Scheme Integration (ZeroPay) | Batch scheduler & window monitoring | 2 | Integration test: daily batch cycle happy path | End-to-end integration test for the full Mon-Sat daily batch cycle. Uses an embedded H2 DB (or Testcontainers PostgreSQL) seeded with the 13 ZeroPay job definitions. Mocks the BatchJobHandler for each job (records calls and returns success). Triggers jobs in chronological order and verifies the dependency chain is respected and all run records reach SUCCESS. | • Create BatchCycleIntegrationTest.java using @SpringBootTest with Testcontainers PostgreSQL • Seed batch_job_definition with 13 ZeroPay rows from the migration • Mock BatchJobHandler to return SUCCESS immediately for all jobs • Trigger jobs in order: JOB-ZP-01, JOB-ZP-02, then ZP-03, ZP-04, ZP-05 (verify ZP-05 waits for ZP-03/ZP-01), then ZP-06 through ZP-09 • Verify each batch_job_run row has status=SUCCESS, completed_at populated, retry_count=0 • Verify final alert table has zero unacknowledged rows (no thresholds missed in happy path) • Assert full sequence completes without DependencyNotMetException | BatchCycleIntegrationTest.java verifying happy-path daily cycle with all 9 settlement jobs reaching SUCCESS | • All 9 daily settlement jobs (JOB-ZP-01 through JOB-ZP-09) have SUCCESS in batch_job_run • JOB-ZP-05 is only triggered after JOB-ZP-03 succeeds (verify call order via mock) • No batch_window_alert rows exist after successful cycle • batch_job_run rows have retry_count=0 for all jobs • Test completes in under 30 seconds using mocked handlers | 55 | 9.7-T07, 9.7-T12 | DevOps | SCH-06, OPS-13
9.7-T23 | scheme-adapter-zeropay | 9.7 | 9. QR Scheme Integration (ZeroPay) | Batch scheduler & window monitoring | 2 | Integration test: missed ZP0011 window triggers P1 alert | Simulate the scenario where JOB-ZP-01 fails after 3 retries and the monitoring cycle fires at 16:50 UTC (past the 16:45 UTC alert threshold). Verify P1 alert is inserted in batch_window_alert, AlertingService is called with P1 + channels [PAGERDUTY,SLACK], and downstream JOB-ZP-03 and JOB-ZP-05 are blocked in PENDING state until Ops manually reruns JOB-ZP-01. | • Create BatchMissedWindowIntegrationTest.java using Testcontainers + mocked AlertingService • Configure clock mock to 16:50 UTC for monitoring cycle • Mock JOB-ZP-01 handler to always throw RuntimeException (simulates SFTP failure) • Execute JOB-ZP-01: verify 3 retries, final status=FAILED in batch_job_run • Advance clock to 16:51 UTC; trigger checkWindows(): verify batch_window_alert row inserted with severity=P1 • Trigger JOB-ZP-05: verify DependencyNotMetException (JOB-ZP-03 not yet run) • Manually rerun JOB-ZP-01 (mock handler now succeeds); verify cascade: JOB-ZP-03 can now proceed via resolvePending | BatchMissedWindowIntegrationTest.java covering SFTP failure -> P1 alert -> dependency block -> manual rerun -> cascade resolution | • batch_job_run for JOB-ZP-01 shows retry_count=3 and status=FAILED • batch_window_alert row exists with severity='P1' and job_id='JOB-ZP-01' • AlertingService mock called once with severity='P1' and channels containing 'PAGERDUTY' • JOB-ZP-05 dispatch returns DependencyNotMetException before JOB-ZP-01 success • After manual rerun success, resolvePending() triggers JOB-ZP-03 to RUNNING state | 55 | 9.7-T09, 9.7-T22 | DevOps | SCH-06, OPS-13
9.7-T24 | scheme-adapter-zeropay | 9.7 | 9. QR Scheme Integration (ZeroPay) | Batch scheduler & window monitoring | 2 | Integration test: idempotent rerun does not duplicate batch records | OPS-13 §6.3 and SCH-06 §9.4: reprocessing the same job for the same date must not create duplicate settlement records or double-debit. This test verifies that running JOB-ZP-01 twice for the same business_date (once SUCCESS, once manual rerun) results in a SKIPPED second run and no new settlement_batch row is created for that date+file_type. | • Create BatchIdempotencyIntegrationTest.java • Seed: JOB-ZP-01, business_date=2026-06-05 with existing SUCCESS run and one settlement_batch row (ZP0011, status=TRANSMITTED) • Invoke BatchJobRunner.executeJob('JOB-ZP-01', LocalDate.of(2026,6,5)) again • Verify: returns SKIPPED; no new batch_job_run row with status != SKIPPED for same date; settlement_batch row count remains 1 for (ZP0011, 2026-06-05) • Trigger via manual rerun endpoint POST /api/v1/admin/batch/rerun: expect 409 Conflict response • Verify handler mock was never called on the second attempt | BatchIdempotencyIntegrationTest.java verifying no duplicate settlement records or double-dispatch on rerun of a succeeded job | • Second executeJob call returns status=SKIPPED • Total batch_job_run rows for (JOB-ZP-01, 2026-06-05) is 2 (original SUCCESS + new SKIPPED) • settlement_batch row count for (ZP0011, 2026-06-05) remains 1 • Handler mock invocation count remains 1 (from original run only) • POST /batch/rerun returns 409 Conflict for a job with existing SUCCESS | 50 | 9.7-T13, 9.7-T22 | DevOps | SCH-06, OPS-13
9.7-T25 | scheme-adapter-zeropay | 9.7 | 9. QR Scheme Integration (ZeroPay) | Batch scheduler & window monitoring | 2 | Runbook doc: batch scheduler configuration and KST window reference | OPS-13 §6 and go-live checklist §12.1.3 require that batch alerting and missed-window alerts are documented. Ops must be able to add a new holiday, change an alert threshold, or disable a job without touching code. The runbook must explain: how to add a holiday, how to change window_utc or alert_threshold_utc in batch_job_definition, how to manually rerun a failed job via Admin UI and CLI, and what each alert severity means. | • Create file docs/runbook/batch-scheduler.md • Section 1: KST window reference table (all 13 jobs with file, direction, window KST, alert threshold KST, criticality, dependencies) • Section 2: Adding a public holiday (SQL: INSERT INTO batch_holiday (scheme_id, holiday_date, description) VALUES (...); note weekly jobs are exempt) • Section 3: Adjusting a window threshold (UPDATE batch_job_definition SET alert_threshold_utc = '20:15' WHERE job_id = 'JOB-ZP-05'; service restart not required for monitor but scheduler cron requires restart) • Section 4: Manual job rerun (Admin UI path + CLI: batch-cli rerun --job JOB-ZP-01 --date YYYY-MM-DD --force) • Section 5: Alert severity meanings (P1 = wake-on-call, P2 = Ops Slack within 30 min, P3 = next business day) | docs/runbook/batch-scheduler.md with complete KST window table and operational procedures | • KST window table lists all 13 jobs (JOB-ZP-01 through JOB-ZP-13) with correct times from OPS-13 §6.2 • Holiday INSERT example uses correct table name batch_holiday and column names • Manual rerun CLI command syntax is accurate (matches BatchJobController endpoint) • Section on alert severities maps P1->PagerDuty+Slack, P2->Slack, P3->Email • Document is under 300 lines (concise runbook, not prose) | 35 | 9.7-T13, 9.7-T15 | DevOps | SCH-06, OPS-13
9.8-T01 | settlement-reconciliation | 9.8 | 9. QR Scheme Integration (ZeroPay) | Reconciliation & exception handling | 2 | Add migration: settlement_batch status column and batch_file_status enum | WBS 9.8 — Reconciliation and exception handling. The settlement_batch table (DAT-03) has status VARCHAR(20) CHECK IN ('PENDING','GENERATED','TRANSMITTED','RECEIVED','RECONCILED','ERROR'). A settlement_batch_item status must also reflect batch-processing outcomes: SETTLEMENT_REGISTERED, REGISTRATION_FAILED, REGISTRATION_UNKNOWN, REGISTRATION_AMOUNT_MISMATCH, SETTLEMENT_CONFIRMED, SETTLEMENT_DISCREPANCY, EXCEPTION_PENDING, EXCEPTION_RESOLVED. These status values are stored on the transaction record's settlement-linkage field and on reconciliation_item rows. Add DB enum type and confirm settlement_batch.status column matches spec. | • Create Flyway migration V9_8_001__settlement_batch_status_enum.sql • Define PostgreSQL enum type batch_file_status with values: PENDING, GENERATED, TRANSMITTED, RECEIVED, RECONCILED, ERROR • Define PostgreSQL enum type batch_item_status with values: SETTLEMENT_REGISTERED, REGISTRATION_FAILED, REGISTRATION_UNKNOWN, REGISTRATION_AMOUNT_MISMATCH, SETTLEMENT_CONFIRMED, SETTLEMENT_DISCREPANCY, EXCEPTION_PENDING, EXCEPTION_RESOLVED • Confirm settlement_batch.status column uses or casts to batch_file_status • Add batch_item_status column to reconciliation_item if not present; default EXCEPTION_PENDING for new rows with mismatch | Flyway migration file V9_8_001__settlement_batch_status_enum.sql applied without error on clean schema | • Migration applies cleanly on a fresh schema and on a schema with existing settlement_batch rows • SELECT enum_range(NULL::batch_file_status) returns exactly the 6 expected values • SELECT enum_range(NULL::batch_item_status) returns exactly the 8 expected values • settlement_batch.status column rejects any value outside the 6 valid states • reconciliation_item.batch_item_status column exists and defaults to EXCEPTION_PENDING | 25 |  | BE | SCH-06
9.8-T02 | settlement-reconciliation | 9.8 | 9. QR Scheme Integration (ZeroPay) | Reconciliation & exception handling | 2 | Add migration: exception_record table for batch reconciliation exceptions | WBS 9.8. The spec requires that every reconciliation discrepancy creates an exception record surfaced in the Ops Admin portal exception queue. There is no dedicated exception_record table defined in DAT-03 — the reconciliation_item table tracks match_status and resolution_status but is for settlement-level reconciliation. A separate exception_record table captures all categories: REGISTRATION_FAILED, REGISTRATION_UNKNOWN, REGISTRATION_AMOUNT_MISMATCH, SETTLEMENT_DISCREPANCY, SFTP transfer failures, partial batch, and rogue records. Fields: id (BIGINT PK), batch_id (FK settlement_batch nullable), txn_ref (VARCHAR(64) nullable), scheme_ref (VARCHAR(128) nullable), exception_type (VARCHAR(50) NOT NULL), priority (CHAR(2) NOT NULL CHECK IN ('P1','P2')), status (VARCHAR(20) NOT NULL DEFAULT 'EXCEPTION_PENDING'), detail (TEXT), resolution_note (TEXT), resolved_by (VARCHAR(120)), resolved_at (TIMESTAMPTZ), created_at (TIMESTAMPTZ NOT NULL DEFAULT NOW()), updated_at, created_by. | • Create Flyway migration V9_8_002__exception_record.sql • Define exception_record table with all columns above • Add CHECK constraint on exception_type: values include REGISTRATION_FAILED, REGISTRATION_UNKNOWN, REGISTRATION_AMOUNT_MISMATCH, SFTP_TRANSFER_FAILURE, SFTP_RECEIVE_FAILURE, FILE_LATE, FILE_CORRUPT, PARTIAL_BATCH, SETTLEMENT_DISCREPANCY, ROGUE_RECORD • Add index on (status, priority) for Ops queue queries • Add index on txn_ref for fast lookup by transaction | Flyway migration V9_8_002__exception_record.sql that creates the exception_record table with correct constraints and indexes | • Migration applies cleanly; table has all 14 columns as specified • Insert with status='EXCEPTION_PENDING', priority='P1', exception_type='REGISTRATION_FAILED' succeeds • Insert with priority='P3' is rejected by CHECK constraint • Index on (status, priority) exists and is used by EXPLAIN for a WHERE status='EXCEPTION_PENDING' AND priority='P1' query • resolved_at remains NULL when status='EXCEPTION_PENDING'; NOT NULL enforcement is left to application layer | 25 | 9.8-T01 | BE | SCH-06
9.8-T03 | settlement-reconciliation | 9.8 | 9. QR Scheme Integration (ZeroPay) | Reconciliation & exception handling | 2 | Add migration: batch_late_alert and retransmission_log tables | WBS 9.8. SCH-06 §9.3 requires that if an expected inbound file has not arrived by deadline + 60 minutes a BATCH_FILE_LATE alert is raised. SCH-06 §9.4 requires retransmitted outbound files to use an incremented sequence number in the filename (e.g. ZP0011_20261015_02.dat.pgp) and that reprocessing is idempotent. Two tables are needed: batch_late_alert (id BIGINT PK, file_type VARCHAR(10), settlement_date DATE, expected_by TIMESTAMPTZ, alerted_at TIMESTAMPTZ, resolved_at TIMESTAMPTZ nullable, created_at) and retransmission_log (id BIGINT PK, batch_id BIGINT FK settlement_batch, original_filename VARCHAR(255), retransmit_filename VARCHAR(255), sequence_number SMALLINT NOT NULL DEFAULT 2, reason TEXT, transmitted_at TIMESTAMPTZ, created_at). | • Create Flyway migration V9_8_003__batch_late_alert_retransmission_log.sql • Define batch_late_alert table as specified • Define retransmission_log table as specified • Add UNIQUE constraint on (batch_id, sequence_number) in retransmission_log to prevent duplicate sequence numbers per batch • Add index on (file_type, settlement_date) in batch_late_alert | Flyway migration V9_8_003__batch_late_alert_retransmission_log.sql applied without error | • batch_late_alert table exists with expected columns; UNIQUE(file_type, settlement_date, alerted_at) prevents double alerts for same file • retransmission_log UNIQUE(batch_id, sequence_number) prevents inserting two rows with the same sequence for the same batch • sequence_number defaults to 2 (first retransmit is sequence 2; original is implicit 01) • Index on (file_type, settlement_date) is present in batch_late_alert | 25 | 9.8-T01 | BE | SCH-06
9.8-T04 | settlement-reconciliation | 9.8 | 9. QR Scheme Integration (ZeroPay) | Reconciliation & exception handling | 2 | Add migration: transaction settlement linkage columns | WBS 9.8. Per DAT-03 and SCH-06, a transaction record must track which settlement batch files it was included in and its current batch-processing status. Required new columns on the transaction table: settlement_batch_id (BIGINT FK nullable → settlement_batch, set atomically when a batch is generated to enforce exactly-once inclusion), batch_item_status (batch_item_status enum nullable), batch_registered_at (TIMESTAMPTZ nullable, set when SETTLEMENT_REGISTERED), batch_exception_id (BIGINT FK nullable → exception_record). The settlement_batch_id must be set atomically during ZP0061/ZP0063 generation (SELECT FOR UPDATE on the transaction row) to prevent double inclusion. | • Create Flyway migration V9_8_004__transaction_settlement_linkage.sql • Add settlement_batch_id BIGINT nullable FK → settlement_batch(id) to transaction table • Add batch_item_status batch_item_status nullable to transaction table • Add batch_registered_at TIMESTAMPTZ nullable to transaction table • Add batch_exception_id BIGINT nullable FK → exception_record(id) to transaction table • Add index on settlement_batch_id for batch membership queries | Flyway migration V9_8_004__transaction_settlement_linkage.sql | • All four columns added to transaction table without error on a populated DB • A transaction with settlement_batch_id set cannot be re-assigned to a second batch without an explicit UPDATE (no automatic constraint, but the atomic-generation logic depends on this column being non-null as a guard) • Index on settlement_batch_id is present • batch_item_status accepts only values from the batch_item_status enum • FK to exception_record(id) is present and cascades to SET NULL on exception record deletion | 25 | 9.8-T01, 9.8-T02 | BE | SCH-06
9.8-T05 | settlement-reconciliation | 9.8 | 9. QR Scheme Integration (ZeroPay) | Reconciliation & exception handling | 2 | Implement ReconciliationMatchResult value object and ZP0012 line-by-line matcher | WBS 9.8. After ZP0012 (payment registration result) is received, the batch job must perform a line-by-line match against ZP0011. Per SCH-06 §5.4, four outcomes exist: (1) result_code='00' and amounts match -> SETTLEMENT_REGISTERED; (2) result_code non-zero -> REGISTRATION_FAILED + exception; (3) ZP0011 record absent from ZP0012 -> REGISTRATION_UNKNOWN + exception; (4) ZP0012 record not in ZP0011 -> anomaly log + exception. (5) Amount discrepancy (registered != submitted) -> REGISTRATION_AMOUNT_MISMATCH + exception. Primary match key is zeropay_txn_ref + txn_date (both fields present in ZP0012 record layout). gme_txn_id is echoed in ZP0012 for cross-reference. Amounts are KRW integers (0 decimal places). | • Create ReconciliationMatchResult enum: MATCHED, REGISTRATION_FAILED, REGISTRATION_UNKNOWN, AMOUNT_MISMATCH, ROGUE_RECORD • Create ZP0012Matcher class with method match(List<ZP0011Record> submitted, List<ZP0012Record> results): List<ReconciliationLineResult> • Index ZP0011 records by (zeropay_txn_ref, txn_date); index ZP0012 records by (zeropay_txn_ref, txn_date) • For each ZP0011 record: look up in ZP0012 index; apply the 5-outcome rules above • For each ZP0012 record not matched to a ZP0011 record: emit ROGUE_RECORD result • Each ReconciliationLineResult carries: zeropay_txn_ref, txn_date, gme_txn_id, match_outcome (enum), submitted_amount, registered_amount, result_code, result_message | ZP0012Matcher class with complete outcome logic and ReconciliationLineResult value object | • Input: ZP0011 has record (ref=REF001, date=20261015, amount=50000 KRW); ZP0012 has matching record with result_code=00, registered_amount=50000 -> outcome MATCHED • Input: same ZP0011 record; ZP0012 result_code=9001 -> outcome REGISTRATION_FAILED • Input: ZP0011 record REF002 not present in ZP0012 at all -> outcome REGISTRATION_UNKNOWN • Input: ZP0012 has record REF003 with no matching ZP0011 record -> outcome ROGUE_RECORD • Input: ZP0012 result_code=00 but registered_amount=49000 vs submitted 50000 (KRW integer, difference=1000) -> outcome AMOUNT_MISMATCH • All 5 outcomes handled; no unhandled cases; pure function with no DB calls | 45 | 9.8-T01 | BE | SCH-06
9.8-T06 | settlement-reconciliation | 9.8 | 9. QR Scheme Integration (ZeroPay) | Reconciliation & exception handling | 2 | Implement ZP0022 refund registration matcher (mirrors ZP0012 logic) | WBS 9.8. SCH-06 §6.4 states refund mismatch handling is identical to payment mismatch handling (§5.4) but applied to refund records. ZP0022 mirrors ZP0012 layout with match key original_zeropay_txn_ref + refund_date. Fields in ZP0022: original_zeropay_txn_ref CHAR(20), gme_refund_id CHAR(20), result_code CHAR(2), result_message VARCHAR(100), registered_refund_amount NUM(12), adjustment_settlement_date DATE(8). The 5 outcomes from 9.8-T05 apply identically. An unresolved refund registration failure blocking settlement is a P1 ops incident. | • Create ZP0022Matcher class implementing the same 5-outcome logic as ZP0012Matcher • Use match key (original_zeropay_txn_ref, refund_date) instead of (zeropay_txn_ref, txn_date) • Reuse ReconciliationLineResult value object; add a recordType field (PAYMENT or REFUND) • Ensure submitted amount from ZP0021 record is refund_amount_krw; registered amount from ZP0022 is registered_refund_amount • Write unit tests alongside the class | ZP0022Matcher class with 5-outcome logic | • Input: ZP0021 refund record (ref=RREF001, date=20261015, amount=25000 KRW); ZP0022 result_code=00, registered_refund_amount=25000 -> MATCHED • Input: ZP0022 result_code=9001 for RREF001 -> REGISTRATION_FAILED • Input: ZP0021 record RREF002 absent from ZP0022 -> REGISTRATION_UNKNOWN • Input: ZP0022 has RREF003 not in ZP0021 -> ROGUE_RECORD • Input: ZP0022 result_code=00, registered_refund_amount=24000 vs submitted 25000 -> AMOUNT_MISMATCH • recordType field is REFUND for all ZP0022 results | 35 | 9.8-T05 | BE | SCH-06
9.8-T07 | settlement-reconciliation | 9.8 | 9. QR Scheme Integration (ZeroPay) | Reconciliation & exception handling | 2 | Implement ZP0062/ZP0064 settlement result matcher | WBS 9.8. After ZP0062 (morning settlement result) or ZP0064 (afternoon settlement result) arrives, GMEPay+ must reconcile each merchant-level total against what was submitted in ZP0061/ZP0063. Tolerance is zero — every merchant total must match exactly (SCH-06 §9.1). ZP0061 contains per-merchant: merchant_id, gross_txn_count, gross_txn_amount (KRW), refund_count, refund_amount (KRW), net_settlement_amount (KRW). ZP0062 confirms the credited amount per merchant. Any discrepancy creates a SETTLEMENT_DISCREPANCY exception (P1, contact KFTC). Match key is merchant_id + settlement_date. | • Create SettlementResultMatcher class with method match(List<ZP0061Record> submitted, List<ZP0062Record> results): List<SettlementMatchResult> • Index ZP0061 by merchant_id; index ZP0062 by merchant_id • For each ZP0061 record: look up ZP0062; compare net_settlement_amount; if missing -> MISSING_FROM_RESULT; if amounts differ -> SETTLEMENT_DISCREPANCY; if match -> SETTLEMENT_CONFIRMED • For each ZP0062 record not matched to ZP0061: emit ROGUE_SETTLEMENT_RECORD • Same class handles ZP0063/ZP0064 via a batchType parameter (MORNING or AFTERNOON) • Each SettlementMatchResult carries: merchant_id, settlement_date, batch_type, match_status, submitted_amount, confirmed_amount, discrepancy_amount | SettlementResultMatcher class with SETTLEMENT_CONFIRMED, SETTLEMENT_DISCREPANCY, MISSING_FROM_RESULT, ROGUE_SETTLEMENT_RECORD outcomes | • merchant_id=M001, submitted net=100000 KRW, ZP0062 confirmed=100000 -> SETTLEMENT_CONFIRMED • merchant_id=M002, submitted net=200000 KRW, ZP0062 confirmed=199000 -> SETTLEMENT_DISCREPANCY, discrepancy_amount=1000 • ZP0061 has M003 but ZP0062 does not -> MISSING_FROM_RESULT • ZP0062 has M004 not in ZP0061 -> ROGUE_SETTLEMENT_RECORD • batchType=AFTERNOON processes ZP0063 vs ZP0064 identically • All amounts are KRW integers (DECIMAL scale 0); no floating-point comparison used | 45 | 9.8-T05 | BE | SCH-06
9.8-T08 | settlement-reconciliation | 9.8 | 9. QR Scheme Integration (ZeroPay) | Reconciliation & exception handling | 2 | Implement ZP0065/ZP0066 detail reconciliation against internal ledger | WBS 9.8. SCH-06 §9.1 defines a third reconciliation level: ZP0065 (payment detail) vs internal ledger and ZP0066 (refund detail) vs internal ledger. Tolerance is zero — every line item must match. ZP0065 contains per-transaction: zeropay_txn_ref, txn_date, payout_amount_krw, merchant_id, partner_type (D/I), settlement_batch_ref. The internal ledger source is the transaction table's target_payout (KRW, scale 0) for transactions in status SETTLEMENT_REGISTERED with the matching settlement_batch_id. Discrepancy creates a reconciliation_item row with match_status=DISCREPANCY plus an exception_record. | • Create DetailReconciliationMatcher class with method reconcilePayments(List<ZP0065Record> schemeDetail, List<TransactionLedgerEntry> internalEntries): List<ReconciliationItem> • Match on zeropay_txn_ref + txn_date; compare payout_amount_krw vs transaction.target_payout (both KRW integers) • Outcomes: MATCHED, DISCREPANCY (amount mismatch), MISSING_GME (in ZP0065 but not internal), MISSING_SCHEME (in internal but not ZP0065) • Add parallel method reconcileRefunds for ZP0066 vs refund records • Map each result to a reconciliation_item row (batch_id, txn_ref, scheme_ref, match_status, gme_amount, scheme_amount, discrepancy_amount, ccy='KRW') | DetailReconciliationMatcher class producing reconciliation_item entities | • ZP0065 ref=TX001 payout=50000, internal=50000 -> match_status=MATCHED, discrepancy_amount=0 • ZP0065 ref=TX002 payout=50000, internal=49500 -> DISCREPANCY, discrepancy_amount=500 • ZP0065 has TX003, internal has no matching entry -> MISSING_GME • Internal has TX004, ZP0065 does not -> MISSING_SCHEME • All reconciliation_item rows have ccy='KRW' and correct batch_id • refund reconciliation uses the same 4 outcomes applied to refund amounts | 45 | 9.8-T05 | BE | SCH-06
9.8-T09 | settlement-reconciliation | 9.8 | 9. QR Scheme Integration (ZeroPay) | Reconciliation & exception handling | 2 | Implement UNCERTAIN transaction resolver triggered by ZP0012/ZP0022 | WBS 9.8. Per SAD-02 and SCH-06, UNCERTAIN transactions (scheme response timed out) must be resolved to APPROVED or FAILED within 24 hours via ZP0012/ZP0022. On receipt of ZP0012, the Settlement Engine looks up all UNCERTAIN transactions for that business date by cross-referencing zeropay_txn_ref in the ZP0012 result. If result_code=00 -> transition to APPROVED and dispatch payment.approved webhook. If result_code non-zero -> transition to FAILED and reverse prefunding deduction for OVERSEAS partners (SELECT FOR UPDATE on prefunding ledger). If ZP0012 has no record for an UNCERTAIN transaction -> the transaction remains UNCERTAIN and is flagged for the next cycle up to 24 h; beyond 24 h it is escalated as a P1 exception. | • Create UncertainTransactionResolver class with method resolve(List<ZP0012Record> results, Date businessDate) • Query DB for all transactions with status=UNCERTAIN and scheme batch date = businessDate • For each UNCERTAIN transaction: look up zeropay_txn_ref in ZP0012 results • If result_code=00: call TransactionOrchestrator.transitionToApproved(txn_ref); dispatch webhook • If result_code non-zero: call TransactionOrchestrator.transitionToFailed(txn_ref); reverse prefunding deduction (OVERSEAS only) using SELECT FOR UPDATE • If no ZP0012 record found: check if transaction is > 24 h old; if yes, create P1 exception_record with type REGISTRATION_UNKNOWN; otherwise leave UNCERTAIN • Wrap each resolution in a database transaction; ensure atomicity of status update + prefunding reversal | UncertainTransactionResolver class with full resolve logic | • UNCERTAIN transaction with zeropay_txn_ref present in ZP0012 result_code=00 transitions to APPROVED and webhook dispatched • UNCERTAIN transaction with ZP0012 result_code=9001 transitions to FAILED; OVERSEAS partner prefunding deduction reversed atomically • UNCERTAIN transaction absent from ZP0012 and age < 24 h remains UNCERTAIN; no exception raised • UNCERTAIN transaction absent from ZP0012 and age > 24 h creates exception_record with type=REGISTRATION_UNKNOWN, priority=P1 • Prefunding reversal uses SELECT FOR UPDATE to prevent concurrent modification • Resolve method is idempotent: reprocessing the same ZP0012 does not double-approve or double-reverse | 55 | 9.8-T04, 9.8-T05 | BE | SCH-06
9.8-T10 | settlement-reconciliation | 9.8 | 9. QR Scheme Integration (ZeroPay) | Reconciliation & exception handling | 2 | Implement ExceptionRecordService: create, surface, and resolve exception records | WBS 9.8. Every reconciliation discrepancy must create an exception_record (see 9.8-T02) and surface it in the Ops Admin portal exception queue. ExceptionRecordService must: (a) create an exception_record from a ReconciliationLineResult or SettlementMatchResult, setting priority P1 for all registration/settlement failures; (b) bulk-query open exceptions by status=EXCEPTION_PENDING ordered by priority then created_at for the Ops queue API; (c) resolve an exception (set status=EXCEPTION_RESOLVED, resolved_by, resolved_at, resolution_note); (d) escalate to ESCALATED when a P1 exception remains unresolved beyond a configurable window (default 60 min for registration failures that block ZP0061 generation). | • Create ExceptionRecordService with methods: createFromReconciliationResult(result, batchId), createFromSettlementResult(result, batchId), listOpenExceptions(page, pageSize): Page<ExceptionRecord>, resolveException(id, resolvedBy, note), escalateStaleExceptions(cutoffMinutes) • createFrom* methods derive exception_type and priority from the result's match_outcome field • listOpenExceptions returns status=EXCEPTION_PENDING ordered by priority ASC, created_at ASC • resolveException sets status=EXCEPTION_RESOLVED, resolved_at=now(), resolved_by, resolution_note; throws if exception already EXCEPTION_RESOLVED • escalateStaleExceptions queries for EXCEPTION_PENDING + priority=P1 + created_at < now()-cutoffMinutes; transitions to EXCEPTION_ESCALATED (add this value to exception status CHECK constraint) | ExceptionRecordService class with full CRUD and escalation logic | • createFromReconciliationResult with outcome REGISTRATION_FAILED creates row with exception_type=REGISTRATION_FAILED, priority=P1 • createFromSettlementResult with outcome SETTLEMENT_DISCREPANCY creates row with exception_type=SETTLEMENT_DISCREPANCY, priority=P1 • listOpenExceptions returns P1 items before P2 items; items ordered by created_at within same priority • resolveException on an already-resolved exception throws IllegalStateException • escalateStaleExceptions with cutoff 60 min escalates a P1 exception that is 90 min old; leaves a 30-min-old exception untouched | 50 | 9.8-T02, 9.8-T05, 9.8-T07 | BE | SCH-06
9.8-T11 | settlement-reconciliation | 9.8 | 9. QR Scheme Integration (ZeroPay) | Reconciliation & exception handling | 2 | Implement settlement-blocking guard: hold ZP0061 generation when exceptions are unresolved | WBS 9.8. SCH-06 §9.2 and §8.2 state that if ZP0012 or ZP0022 indicate registration failures, settlement generation for affected transactions must be held until the exception is resolved by Ops. Non-affected transactions proceed normally. This guard must check, before including a transaction in ZP0061/ZP0063 batch generation, that the transaction does not have an open exception_record (status=EXCEPTION_PENDING or EXCEPTION_ESCALATED). Affected transactions are excluded from the batch with their batch_item_status set to EXCEPTION_PENDING. The generated batch file covers only non-blocked transactions. | • In the ZP0061 batch generation service, add a pre-generation query: SELECT t.id FROM transaction t WHERE t.settlement_date = ? AND t.batch_exception_id IS NOT NULL AND EXISTS (SELECT 1 FROM exception_record e WHERE e.id = t.batch_exception_id AND e.status IN ('EXCEPTION_PENDING','EXCEPTION_ESCALATED')) • Exclude these transaction IDs from the ZP0061 batch; set their batch_item_status=EXCEPTION_PENDING • For the remaining transactions, proceed with batch generation and set settlement_batch_id atomically • After batch generation, call ExceptionRecordService.createFromReconciliationResult for any transactions excluded due to existing exceptions if not already recorded • Log the count of blocked vs included transactions in the batch generation audit trail | Settlement-blocking guard integrated into ZP0061/ZP0063 batch generation service | • Batch generated with 5 transactions, 1 of which has an open P1 exception: ZP0061 contains 4 transactions; the blocked transaction's batch_item_status=EXCEPTION_PENDING • After Ops resolves the exception (status=EXCEPTION_RESOLVED), re-running generation includes the previously blocked transaction in the next batch • Batch generation is idempotent: re-running does not add a transaction to two batches (settlement_batch_id uniqueness) • Non-affected transactions are never delayed by other transactions' exceptions • Count of blocked transactions is logged with the settlement_batch record | 50 | 9.8-T04, 9.8-T09, 9.8-T10 | BE | SCH-06
9.8-T12 | settlement-reconciliation | 9.8 | 9. QR Scheme Integration (ZeroPay) | Reconciliation & exception handling | 2 | Implement late-file monitor: raise BATCH_FILE_LATE alert when inbound deadline + 60 min passes | WBS 9.8. SCH-06 §9.3: if an expected inbound file has not arrived by deadline + 60 minutes, raise a BATCH_FILE_LATE alert and place dependent batch jobs in WAITING state. Deadlines from SCH-06 §9.5: ZP0012/ZP0022 expected ~05:00 KST, P1 escalation cutoff 06:00 KST; ZP0062 expected ~10:00 KST, cutoff 12:00 KST; ZP0064 expected ~19:00 KST, cutoff 21:00 KST. A scheduled monitor runs every 10 minutes and checks whether expected inbound files have arrived (status=RECEIVED) for today's settlement_date. | • Create BatchLateFileMonitor scheduled service running every 10 minutes • For each expected inbound file type (ZP0012, ZP0022, ZP0062, ZP0064): query settlement_batch for today's settlement_date and status != RECEIVED • If current time (KST) > expected_arrival + 60 min and no batch_late_alert row exists for (file_type, settlement_date): insert batch_late_alert and emit ops alert (notification + email) • If current time > P1 cutoff: re-alert and set alert priority=P1 in batch_late_alert • Set settlement_batch.status=ERROR and dependent batch job statuses to WAITING when file is late • Dependent jobs resume automatically when the late file is received and processed | BatchLateFileMonitor service with 10-minute schedule and alert creation logic | • ZP0012 not received by 06:00 KST on a given settlement_date: batch_late_alert row created with alerted_at close to 06:00; settlement_batch.status=ERROR; dependent ZP0061 generation job in WAITING • Running the monitor twice within 10 minutes does not create a duplicate batch_late_alert for the same (file_type, settlement_date) • ZP0062 not received by 12:00 KST: alert created with P2 priority • After ZP0012 arrives and status=RECEIVED: monitor marks batch_late_alert.resolved_at; dependent jobs resume from WAITING • Monitor uses KST timezone (Asia/Seoul) for all deadline comparisons | 50 | 9.8-T03, 9.8-T10 | BE | SCH-06
9.8-T13 | settlement-reconciliation | 9.8 | 9. QR Scheme Integration (ZeroPay) | Reconciliation & exception handling | 2 | Implement outbound file retransmission service with sequence-number increment | WBS 9.8. SCH-06 §9.4: for outbound retransmission, GMEPay+ retransmits with an incremented sequence number in the filename, e.g. ZP0011_20261015_02.dat.pgp (original was 01). File content is regenerated for the same business date. Retransmitted files are processed identically to originals. DB upsert logic must be idempotent. The retransmission_log table (9.8-T03) records each retransmit event. Trigger: Ops clicks 'Retransmit' in Admin portal, or the batch scheduler triggers after 3 failed SFTP uploads (each 5 minutes apart). | • Create RetransmissionService with method retransmit(batchId: Long, reason: String, triggeredBy: String): RetransmissionResult • Load the original settlement_batch row; verify status=ERROR or TRANSMITTED • Determine next sequence number: query retransmission_log for MAX(sequence_number) WHERE batch_id=batchId; default 2 if no prior retransmit • Regenerate file content by calling the same file-generation logic used for the original batch (ensuring idempotency: same transaction set, same data) • Construct new filename: {file_type}_{yyyyMMdd}_{seqNum:02d}.dat.pgp • Upload via SFTP adapter; on success insert retransmission_log row; update settlement_batch.status=TRANSMITTED • On SFTP failure after 3 retries: create exception_record with type SFTP_TRANSFER_FAILURE, priority=P1 | RetransmissionService class with sequence-increment filename logic and retransmission_log persistence | • First retransmit of batch ZP0011 for 2026-10-15: filename=ZP0011_20261015_02.dat.pgp, sequence_number=2 in retransmission_log • Second retransmit of same batch: filename=ZP0011_20261015_03.dat.pgp, sequence_number=3 • Regenerated file content is byte-for-byte identical to original for the same transaction set (idempotent generation) • SFTP upload failure after 3 retries creates P1 exception_record with type=SFTP_TRANSFER_FAILURE • UNIQUE(batch_id, sequence_number) in retransmission_log prevents duplicate sequence entries • Retransmit of a batch already in TRANSMITTED status requires explicit reason; raises error if status=RECONCILED | 55 | 9.8-T03, 9.8-T10 | BE | SCH-06
9.8-T14 | settlement-reconciliation | 9.8 | 9. QR Scheme Integration (ZeroPay) | Reconciliation & exception handling | 2 | Implement inbound file idempotency: upsert logic for ZP0012 and ZP0022 reprocessing | WBS 9.8. SCH-06 §9.4: retransmitted inbound files (ZP0012, ZP0022) are processed identically to originals. DB upsert logic must be idempotent — reprocessing the same records must not create duplicates. The upsert key for ZP0012 is (zeropay_txn_ref, txn_date, batch_settlement_date). The upsert key for ZP0022 is (original_zeropay_txn_ref, refund_date, batch_settlement_date). Reprocessing must overwrite the existing match outcome and exception record if the new result differs (e.g. a retransmit returns result_code=00 where the original returned 9001). | • In the ZP0012 ingest service, use INSERT ... ON CONFLICT (zeropay_txn_ref, txn_date, batch_settlement_date) DO UPDATE to upsert match outcomes • If result_code changes from non-zero to 00 on upsert: transition transaction to SETTLEMENT_REGISTERED and close any open exception_record for that txn_ref • If result_code remains non-zero on upsert: update exception_record.detail with new result_message; do not create a duplicate exception_record • Apply identical logic to ZP0022 using (original_zeropay_txn_ref, refund_date, batch_settlement_date) as upsert key • Log retransmit reprocessing event in transaction_event table with step label REPROCESS_ZP0012 or REPROCESS_ZP0022 | Idempotent upsert logic in ZP0012 and ZP0022 ingest services | • Processing ZP0012 twice with identical content: exactly one reconciliation_item row created; no duplicate exception_record • Processing ZP0012 retransmit where result_code changed from 9001 to 00: transaction transitions to SETTLEMENT_REGISTERED; exception_record.status set to EXCEPTION_RESOLVED • Processing ZP0012 retransmit where result_code remains 9001: exception_record updated (not duplicated); transaction remains REGISTRATION_FAILED • ZP0022 upsert uses different composite key than ZP0012 and does not collide • transaction_event has exactly one REPROCESS_ZP0012 event per retransmit processing run per transaction | 45 | 9.8-T05, 9.8-T06, 9.8-T09 | BE | SCH-06
9.8-T15 | settlement-reconciliation | 9.8 | 9. QR Scheme Integration (ZeroPay) | Reconciliation & exception handling | 2 | Implement daily pool identity background reconciliation job | WBS 9.8 and RATE-04 §13.1. After commit, all locked values in the transaction record (collection_usd, payout_usd_cost, collection_margin_usd, payout_margin_usd) must satisfy the pool identity: collection_usd - collection_margin_usd - payout_margin_usd = payout_usd_cost within 0.01 USD. A background job runs daily, checking all committed transactions (status APPROVED or REFUNDED) for that business date. Any violation creates a P1 exception_record with type=POOL_IDENTITY_VIOLATION. This is distinct from the at-commit guard — it serves as an audit backstop. Same-currency transactions (collection_usd IS NULL) are skipped. | • Create PoolIdentityAuditJob scheduled daily (e.g. 03:00 KST) with method auditDate(Date settlementDate) • Query all transactions with status IN ('APPROVED','REFUNDED') and rate_locked_at::date = settlementDate and collection_usd IS NOT NULL • For each transaction: compute abs(collection_usd - collection_margin_usd - payout_margin_usd - payout_usd_cost); if > 0.01 USD create P1 exception_record with type=POOL_IDENTITY_VIOLATION and detail including txn_ref, violation_amount • Use DECIMAL arithmetic throughout; never convert to float • Log total checked, pass count, and violation count in a structured log message • Job is idempotent: re-running for same date does not create duplicate exception records (use ON CONFLICT on (txn_ref, exception_type, DATE(created_at))) | PoolIdentityAuditJob class with daily schedule and violation reporting | • Transaction with collection_usd=1000.00, collection_margin_usd=10.00, payout_margin_usd=10.00, payout_usd_cost=980.00: abs(1000-10-10-980)=0.00 < 0.01 -> no exception • Transaction with payout_usd_cost=979.99 (violates by 0.01 exactly): 0.01 is NOT > 0.01 -> no exception (strict greater-than) • Transaction with payout_usd_cost=979.98 (violates by 0.02): creates P1 exception_record type=POOL_IDENTITY_VIOLATION • Same-currency transaction (collection_usd IS NULL) is skipped; no false positive • Re-running job for same date does not duplicate exception_record rows • Job completes within 5 minutes for up to 10,000 transactions | 45 | 9.8-T02, 9.8-T04 | BE | SCH-06
9.8-T16 | settlement-reconciliation | 9.8 | 9. QR Scheme Integration (ZeroPay) | Reconciliation & exception handling | 2 | Implement daily aggregate reconciliation job (ZP0065 totals vs internal ledger) | WBS 9.8 and RATE-04 §13.2. Daily, GMEPay+ must verify: (1) sum of target_payout (KRW) for all SETTLEMENT_REGISTERED transactions in a settlement day matches ZP0065 line-item totals; (2) count of transactions in ZP0061/ZP0063 matches GMEPay+ outbound settlement count; (3) sum of collection_usd debited from each OVERSEAS partner's prefunding account matches the prefunding ledger balance movement for that day. Discrepancies auto-flag to exception queue with P1 priority. Runs after ZP0065/ZP0066 are processed (~22:00 KST). | • Create DailyAggregateReconciliationJob scheduled at 22:30 KST with method reconcileDate(Date settlementDate) • Query sum(target_payout) from transaction WHERE settlement_date=? AND batch_item_status='SETTLEMENT_REGISTERED' GROUP BY settlement_batch_id • Query sum of ZP0065 payout_amount_krw for the same settlement_batch_id • Compare totals; if delta != 0 KRW create P1 exception_record type=AGGREGATE_PAYOUT_MISMATCH with gme_amount and scheme_amount • Query count of transactions in ZP0061/ZP0063 batch (transaction_count from settlement_batch) vs count of transactions with that settlement_batch_id in transaction table; discrepancy -> P1 exception type=TRANSACTION_COUNT_MISMATCH • Query net prefunding_ledger_entry debit sum for each OVERSEAS partner for settlementDate; compare against sum(collection_usd) for that partner's transactions; delta > 0.01 USD -> P1 exception type=PREFUNDING_LEDGER_MISMATCH | DailyAggregateReconciliationJob with three reconciliation checks | • 10 transactions sum target_payout=500000 KRW; ZP0065 sum=500000 KRW -> no exception raised • ZP0065 sum=499000 KRW -> P1 exception type=AGGREGATE_PAYOUT_MISMATCH, gme_amount=500000, scheme_amount=499000, discrepancy=1000 • settlement_batch.transaction_count=10 but only 9 transaction rows reference that batch -> P1 exception type=TRANSACTION_COUNT_MISMATCH • OVERSEAS partner prefunding debit sum=5000.00 USD, collection_usd sum=5000.00 USD -> no exception • Prefunding debit sum=4999.90 USD vs collection_usd sum=5000.00 USD (delta=0.10 > 0.01) -> P1 exception type=PREFUNDING_LEDGER_MISMATCH • Job is idempotent when re-run on same date | 55 | 9.8-T08, 9.8-T10, 9.8-T15 | BE | SCH-06
9.8-T17 | settlement-reconciliation | 9.8 | 9. QR Scheme Integration (ZeroPay) | Reconciliation & exception handling | 2 | Implement dispute data-retrieval service (SCH-06 §9.6) | WBS 9.8. SCH-06 §9.6: ZeroPay disputes are initiated via ZeroPay's own dispute channel. GMEPay+'s responsibilities are: (1) provide transaction records on request by zeropay_txn_ref; (2) provide file-level audit trail (SFTP transfer timestamps, checksums, archival copies); (3) for international transactions, identify the OVERSEAS partner for customer-side evidence; (4) escalate to GME Finance/Compliance for settlement-affecting amounts. GMEPay+ does not handle customer disputes directly. A DisputeDataService exposes the data retrieval API consumed by the Admin portal dispute detail screen. | • Create DisputeDataService with method getDisputePackage(zeropayTxnRef: String): DisputePackage • Query transaction by zeropay_txn_ref (hub_txn_ref in transaction table, see DAT-03 A7); load all transaction_event rows • Query settlement_file rows linked to the transaction's settlement_batch_id; include filename, sftp_path, file_checksum, transmitted_at • If transaction partner type=OVERSEAS: include partner.name, partner.alert_email in the package for coordination reference • If any reconciliation_item or exception_record is linked to the transaction: include it in the package • Create method flagForEscalation(zeropayTxnRef: String, escalatedBy: String, amount: Decimal, note: String): create exception_record with type=DISPUTE_ESCALATED, priority=P1 | DisputeDataService class with getDisputePackage and flagForEscalation methods | • getDisputePackage for a known zeropay_txn_ref returns a package with: transaction detail, 8-step event trail, settlement_file records with checksums, and reconciliation_item if present • getDisputePackage for an OVERSEAS partner includes partner.name and partner.alert_email • getDisputePackage for an unknown zeropay_txn_ref throws ResourceNotFoundException • flagForEscalation creates exception_record with type=DISPUTE_ESCALATED, priority=P1, detail includes amount and escalatedBy • flagForEscalation called twice for same reference creates only one DISPUTE_ESCALATED exception (idempotent via ON CONFLICT) • settlement_file records include file_checksum (SHA-256) for audit trail integrity | 45 | 9.8-T02, 9.8-T04 | BE | SCH-06
9.8-T18 | settlement-reconciliation | 9.8 | 9. QR Scheme Integration (ZeroPay) | Reconciliation & exception handling | 2 | Implement Ops Admin API: GET /internal/exceptions endpoint | WBS 9.8. The Ops Admin portal exception queue must surface open exception_record rows. Endpoint: GET /internal/exceptions with query params: status (default EXCEPTION_PENDING), priority (optional P1/P2), exception_type (optional), page (default 0), pageSize (default 20, max 100). Response: paginated list of ExceptionRecordDto (id, exception_type, priority, status, txn_ref, scheme_ref, batch_id, detail, created_at, resolved_by, resolved_at). Requires ROLE_OPS_ADMIN or ROLE_FINANCE. Alert SLA: discrepancy alerts must reach Ops within 15 minutes of batch receipt (NFR goal G-5). | • Add GET /internal/exceptions handler in ExceptionController • Bind query params to ExceptionSearchCriteria (status, priority, exception_type, page, pageSize) • Delegate to ExceptionRecordService.listExceptions(criteria) which builds a JPA/JPQL query • Map exception_record rows to ExceptionRecordDto; include txn_ref, scheme_ref, batch file_type, detail • Enforce authorization: only ROLE_OPS_ADMIN and ROLE_FINANCE may access • Return Page<ExceptionRecordDto> with total count, page, pageSize | GET /internal/exceptions endpoint returning paginated exception records | • GET /internal/exceptions returns only EXCEPTION_PENDING rows by default; total reflects DB count • GET /internal/exceptions?priority=P1 returns only P1 rows • GET /internal/exceptions?exception_type=REGISTRATION_FAILED returns only that type • pageSize=5 returns at most 5 items; second page returns the next 5 • Request without ROLE_OPS_ADMIN or ROLE_FINANCE returns HTTP 403 • Response time < 500 ms for up to 1000 open exception rows | 45 | 9.8-T10 | BE | SCH-06
9.8-T19 | settlement-reconciliation | 9.8 | 9. QR Scheme Integration (ZeroPay) | Reconciliation & exception handling | 2 | Implement Ops Admin API: POST /internal/exceptions/{id}/resolve | WBS 9.8. Ops must be able to resolve an exception record from the Admin portal. Endpoint: POST /internal/exceptions/{id}/resolve with body {resolution_note: string (required, min 10 chars)}. Marks exception as EXCEPTION_RESOLVED; records resolved_by (from auth principal), resolved_at=now(), resolution_note. After resolution, if the exception was blocking a transaction from settlement (batch_item_status=EXCEPTION_PENDING), the transaction's batch_item_status is reset to SETTLEMENT_REGISTERED (or the appropriate status based on its registration state) so it can be included in the next settlement batch. Returns 200 with updated ExceptionRecordDto. Requires ROLE_OPS_ADMIN. | • Add POST /internal/exceptions/{id}/resolve handler • Load exception_record by id; if not found return 404 • If status=EXCEPTION_RESOLVED return 409 with message 'Already resolved' • Validate resolution_note length >= 10 chars • Call ExceptionRecordService.resolveException(id, principal.name, resolution_note) • If exception_record has a linked txn_ref: update transaction.batch_item_status to SETTLEMENT_REGISTERED and clear batch_exception_id if appropriate • Audit-log the resolution (actor, exception id, resolution_note, timestamp) • Return 200 with ExceptionRecordDto | POST /internal/exceptions/{id}/resolve endpoint | • Resolving an open P1 REGISTRATION_FAILED exception sets status=EXCEPTION_RESOLVED, resolved_by=current user, resolved_at=now() • Resolving an already-resolved exception returns HTTP 409 • resolution_note with fewer than 10 characters returns HTTP 400 with field validation error • After resolution, the linked transaction's batch_exception_id is cleared and batch_item_status reflects its actual registration state • Audit log contains an entry with actor, exception id, and resolution_note within 1 second of the call • Only ROLE_OPS_ADMIN can resolve; ROLE_FINANCE returns 403 | 40 | 9.8-T10, 9.8-T18 | BE | SCH-06
9.8-T20 | settlement-reconciliation | 9.8 | 9. QR Scheme Integration (ZeroPay) | Reconciliation & exception handling | 2 | Implement Ops Admin API: POST /internal/batches/{id}/retransmit | WBS 9.8. Ops must be able to trigger retransmission of a failed outbound batch file from the Admin portal. Endpoint: POST /internal/batches/{id}/retransmit with body {reason: string (required)}. Delegates to RetransmissionService (9.8-T13). Returns 202 Accepted with job reference if SFTP upload is async, or 200 with RetransmissionResult if synchronous. Requires ROLE_OPS_ADMIN. The batch must be in status ERROR or TRANSMITTED. Retransmitting a RECONCILED batch is blocked with 409. | • Add POST /internal/batches/{id}/retransmit handler in SettlementBatchController • Load settlement_batch by id; if not found return 404 • Check status: if RECONCILED return 409 'Cannot retransmit a reconciled batch' • Validate reason is present • Call RetransmissionService.retransmit(batchId, reason, principal.name) • Return 200 with {retransmitFilename, sequenceNumber, transmittedAt} • Audit-log the retransmission trigger (actor, batchId, reason, sequenceNumber) | POST /internal/batches/{id}/retransmit endpoint | • Retransmitting a batch in status ERROR returns 200 with new filename containing incremented sequence number (e.g. _02.dat.pgp) • Retransmitting a batch in status RECONCILED returns 409 • Retransmitting with no reason body returns 400 • Each retransmit call increments the sequence number: two calls produce _02 and _03 • Audit log contains actor, batchId, reason, and new sequence number • Only ROLE_OPS_ADMIN can trigger; ROLE_FINANCE returns 403 | 35 | 9.8-T13, 9.8-T18 | BE | SCH-06
9.8-T21 | settlement-reconciliation | 9.8 | 9. QR Scheme Integration (ZeroPay) | Reconciliation & exception handling | 2 | Implement Ops Admin API: GET /internal/disputes endpoint and dispute package | WBS 9.8. Ops must be able to retrieve dispute packages for ZeroPay escalation (SCH-06 §9.6). Endpoint: GET /internal/disputes/{zeropayTxnRef} returns the DisputePackage from DisputeDataService (9.8-T17). Endpoint: POST /internal/disputes/{zeropayTxnRef}/escalate with body {amount: decimal, note: string} calls flagForEscalation. Both endpoints require ROLE_OPS_ADMIN or ROLE_FINANCE. escalate requires ROLE_OPS_ADMIN only. | • Add GET /internal/disputes/{zeropayTxnRef} handler in DisputeController • Call DisputeDataService.getDisputePackage(zeropayTxnRef); return 200 with DisputePackageDto • Add POST /internal/disputes/{zeropayTxnRef}/escalate handler • Validate amount > 0 and note is present (min 10 chars) • Call DisputeDataService.flagForEscalation(zeropayTxnRef, principal.name, amount, note) • Return 200 with created exception_record id and status | GET /internal/disputes/{zeropayTxnRef} and POST /internal/disputes/{zeropayTxnRef}/escalate endpoints | • GET for known zeropayTxnRef returns transaction detail, event trail, and settlement_file audit trail • GET for unknown zeropayTxnRef returns 404 • POST /escalate creates exception_record type=DISPUTE_ESCALATED, priority=P1 • POST /escalate with amount=0 returns 400 • POST /escalate with note < 10 chars returns 400 • ROLE_FINANCE on GET /internal/disputes returns 200; ROLE_FINANCE on POST /escalate returns 403 | 40 | 9.8-T17, 9.8-T19 | BE | SCH-06
9.8-T22 | settlement-reconciliation | 9.8 | 9. QR Scheme Integration (ZeroPay) | Reconciliation & exception handling | 2 | Unit tests: ZP0012Matcher all 5 outcomes with boundary cases | WBS 9.8. Test ticket for ZP0012Matcher (9.8-T05). Tests must be deterministic, self-contained, no DB calls. Use plain Java/Kotlin objects for ZP0011Record and ZP0012Record. Cover all 5 outcome branches plus boundary cases: empty ZP0011 list, empty ZP0012 list, both empty, large list performance (1000 records). | • Create ZP0012MatcherTest class • Write test: MATCHED outcome - single record, exact amount match • Write test: REGISTRATION_FAILED - non-zero result_code (e.g. '9001') • Write test: REGISTRATION_UNKNOWN - ZP0011 record not in ZP0012 • Write test: ROGUE_RECORD - ZP0012 record not in ZP0011 • Write test: AMOUNT_MISMATCH - result_code='00' but amounts differ by 1 KRW • Write test: empty ZP0011 + non-empty ZP0012 produces all ROGUE_RECORD • Write test: non-empty ZP0011 + empty ZP0012 produces all REGISTRATION_UNKNOWN • Write test: 1000-record list completes in < 200ms (use System.nanoTime assertion) | ZP0012MatcherTest class with 8 test cases all passing | • All 5 outcome branches covered by at least one test • AMOUNT_MISMATCH test uses KRW amounts (integers): submitted=50000, registered=49999 (diff=1 KRW) -> AMOUNT_MISMATCH • Empty-input edge cases produce correct empty or all-one-outcome lists without NPE • Performance test with 1000 records passes in < 200ms • Zero external dependencies (no Spring context, no DB) | 40 | 9.8-T05 | BE | SCH-06
9.8-T23 | settlement-reconciliation | 9.8 | 9. QR Scheme Integration (ZeroPay) | Reconciliation & exception handling | 2 | Unit tests: SettlementResultMatcher MORNING and AFTERNOON batch scenarios | WBS 9.8. Test ticket for SettlementResultMatcher (9.8-T07). Tests cover ZP0061 vs ZP0062 (MORNING) and ZP0063 vs ZP0064 (AFTERNOON). Also test multi-merchant scenarios and the rogue-record case. | • Create SettlementResultMatcherTest class • Write test: 3 merchants all matching -> 3 SETTLEMENT_CONFIRMED results • Write test: merchant M001 confirmed amount differs by 1 KRW -> SETTLEMENT_DISCREPANCY with discrepancy_amount=1 • Write test: merchant M002 in ZP0061 but absent from ZP0062 -> MISSING_FROM_RESULT • Write test: merchant M003 in ZP0062 but absent from ZP0061 -> ROGUE_SETTLEMENT_RECORD • Write test: AFTERNOON batchType with ZP0063/ZP0064 produces same outcomes • Write test: empty inputs produce empty result lists without error | SettlementResultMatcherTest class with 6 test cases all passing | • SETTLEMENT_DISCREPANCY test: submitted_amount=200000 KRW, confirmed=199999 KRW, discrepancy_amount=1 KRW • All four match_status outcomes covered • AFTERNOON batchType processes identically to MORNING (batch_type field in result is AFTERNOON) • No DB or Spring context dependencies • All tests pass with zero flakiness | 35 | 9.8-T07 | BE | SCH-06
9.8-T24 | settlement-reconciliation | 9.8 | 9. QR Scheme Integration (ZeroPay) | Reconciliation & exception handling | 2 | Unit tests: UncertainTransactionResolver APPROVED, FAILED, and still-UNCERTAIN paths | WBS 9.8. Test ticket for UncertainTransactionResolver (9.8-T09). Uses an in-memory/mock DB or test doubles for TransactionOrchestrator and PrefundingLedger. Covers: APPROVED transition with webhook, FAILED transition with prefunding reversal for OVERSEAS, FAILED for LOCAL (no reversal), still-UNCERTAIN below 24h, escalation above 24h. | • Create UncertainTransactionResolverTest class using Mockito for TransactionOrchestrator and PrefundingLedger • Write test: ZP0012 result_code='00' for UNCERTAIN txn -> transitionToApproved called, webhook dispatched • Write test: ZP0012 result_code='9001' for OVERSEAS UNCERTAIN txn -> transitionToFailed called, prefunding reversal invoked with SELECT FOR UPDATE • Write test: ZP0012 result_code='9001' for LOCAL UNCERTAIN txn -> transitionToFailed called, no prefunding reversal • Write test: UNCERTAIN txn absent from ZP0012, age=12h (below 24h) -> no status change, no exception created • Write test: UNCERTAIN txn absent from ZP0012, age=25h (above 24h) -> P1 exception_record created with type=REGISTRATION_UNKNOWN • Write test: idempotency - resolve called twice with same ZP0012 -> transitionToApproved called exactly once | UncertainTransactionResolverTest class with 6 test cases all passing | • APPROVED transition test: verify transitionToApproved mock called once with correct txn_ref • OVERSEAS FAILED test: verify prefunding reversal mock called with correct collection_usd amount • LOCAL FAILED test: verify prefunding reversal mock NOT called • 25h-old UNCERTAIN creates exception with priority=P1 and type=REGISTRATION_UNKNOWN • Idempotency test: second call does not invoke transitionToApproved again • All tests run without DB (pure unit tests with mocks) | 45 | 9.8-T09 | BE | SCH-06
9.8-T25 | settlement-reconciliation | 9.8 | 9. QR Scheme Integration (ZeroPay) | Reconciliation & exception handling | 2 | Unit tests: ExceptionRecordService create, resolve, and escalate logic | WBS 9.8. Test ticket for ExceptionRecordService (9.8-T10). Uses an in-memory H2 test DB or mocked repository. Covers: createFromReconciliationResult for all exception types, listOpenExceptions ordering, resolveException success and idempotency failure, escalateStaleExceptions cutoff logic. | • Create ExceptionRecordServiceTest class • Write test: createFromReconciliationResult with REGISTRATION_FAILED -> exception_record with type=REGISTRATION_FAILED, priority=P1 • Write test: createFromSettlementResult with SETTLEMENT_DISCREPANCY -> type=SETTLEMENT_DISCREPANCY, priority=P1 • Write test: listOpenExceptions - insert 2 P1 exceptions and 1 P2; verify P1 items first, then P2, all with status=EXCEPTION_PENDING • Write test: resolveException - valid resolution sets status=EXCEPTION_RESOLVED, resolved_by, resolved_at • Write test: resolveException on already-resolved exception throws IllegalStateException • Write test: escalateStaleExceptions with cutoff=60min - P1 exception aged 90 min escalated; P1 exception aged 30 min unchanged | ExceptionRecordServiceTest class with 6 test cases all passing | • REGISTRATION_FAILED exception has priority=P1 (P2 for file_late type would be set separately) • listOpenExceptions returns P1 before P2; within same priority, older first • resolveException test: resolved_by matches principal name; resolved_at is approximately now() • Already-resolved exception throws IllegalStateException (not just returns 409 — that is the controller's job) • escalateStaleExceptions does not re-escalate an already-EXCEPTION_ESCALATED record • All 6 tests pass without external service dependencies | 40 | 9.8-T10 | BE | SCH-06
9.8-T26 | settlement-reconciliation | 9.8 | 9. QR Scheme Integration (ZeroPay) | Reconciliation & exception handling | 2 | Unit tests: RetransmissionService sequence-number and idempotency | WBS 9.8. Test ticket for RetransmissionService (9.8-T13). Covers filename construction, sequence increment across multiple retransmits, regenerated content idempotency, RECONCILED-batch rejection, and SFTP failure exception creation. | • Create RetransmissionServiceTest class • Write test: first retransmit of batch ZP0011_20261015 produces filename ZP0011_20261015_02.dat.pgp, sequence_number=2 • Write test: second retransmit produces ZP0011_20261015_03.dat.pgp, sequence_number=3 • Write test: regenerated file content is identical for same transaction set (mock file-generation to return deterministic bytes) • Write test: retransmit of RECONCILED batch throws IllegalStateException • Write test: SFTP failure after 3 retries creates P1 exception_record type=SFTP_TRANSFER_FAILURE • Write test: UNIQUE constraint on (batch_id, sequence_number) prevents duplicate retransmission_log entries | RetransmissionServiceTest class with 6 test cases all passing | • Filename ZP0011_20261015_02.dat.pgp generated correctly for first retransmit • Sequence 3 generated correctly for second retransmit without manually knowing previous max • RECONCILED batch throws with a message containing 'Cannot retransmit' • SFTP failure test: exception_record.type=SFTP_TRANSFER_FAILURE and priority=P1 • Duplicate sequence_number insert test raises DataIntegrityViolationException • All tests are pure unit tests with no real SFTP calls | 35 | 9.8-T13 | BE | SCH-06
9.8-T27 | settlement-reconciliation | 9.8 | 9. QR Scheme Integration (ZeroPay) | Reconciliation & exception handling | 2 | Unit tests: PoolIdentityAuditJob boundary conditions | WBS 9.8. Test ticket for PoolIdentityAuditJob (9.8-T15). Tests the 0.01 USD boundary precisely using Decimal arithmetic, same-currency skip, and idempotency. | • Create PoolIdentityAuditJobTest class • Write test: delta=0.00 -> no exception (exactly balanced pool) • Write test: delta=0.01 exactly -> no exception (tolerance is STRICTLY greater-than 0.01) • Write test: delta=0.02 -> P1 exception type=POOL_IDENTITY_VIOLATION created • Write test: same-currency transaction (collection_usd=NULL) -> skipped; no exception • Write test: re-running job for same date when violation already exists -> no duplicate exception_record (upsert semantics) • Write test: values use BigDecimal not double; verify no floating-point imprecision for amount 100.00 USD | PoolIdentityAuditJobTest class with 5 test cases all passing | • delta=0.01 does NOT create exception (strictly greater-than boundary) • delta=0.0101 creates exception • NULL collection_usd skipped without NPE • Second run for same txn does not create a second exception_record row • All arithmetic uses BigDecimal; test with value 100.00 that would be imprecise as double (e.g. 100.00 = 99.99999... in float) | 35 | 9.8-T15 | BE | SCH-06
9.8-T28 | settlement-reconciliation | 9.8 | 9. QR Scheme Integration (ZeroPay) | Reconciliation & exception handling | 2 | Integration test: full ZP0012 reconciliation flow end-to-end | WBS 9.8. Integration test starting from a set of UNCERTAIN and APPROVED transactions, processing a synthetic ZP0012 file, and verifying all downstream state changes: UNCERTAIN -> APPROVED, UNCERTAIN -> FAILED + prefunding reversal, REGISTRATION_UNKNOWN exception, AMOUNT_MISMATCH exception, and settlement-blocking guard. Uses a real test DB (H2 or Testcontainers PostgreSQL). | • Create ReconciliationIntegrationTest using @SpringBootTest with TestContainers PostgreSQL • Seed DB: 5 transactions in UNCERTAIN status, 3 in APPROVED; 1 OVERSEAS, 1 LOCAL among UNCERTAIN • Construct synthetic ZP0012 with: result_code=00 for 3 UNCERTAIN txns; result_code=9001 for 1 UNCERTAIN; 1 UNCERTAIN absent • Invoke reconciliation service with ZP0012 • Assert UNCERTAIN txn with code 00 -> APPROVED; confirm webhook event queued • Assert UNCERTAIN txn with code 9001 (OVERSEAS) -> FAILED; prefunding ledger has reversal entry • Assert UNCERTAIN txn absent from ZP0012, age < 24h -> remains UNCERTAIN; no exception • Confirm 3 exception_record rows exist: 1 REGISTRATION_FAILED, and 1 per ROGUE/UNKNOWN if applicable • Confirm settlement-blocking guard excludes REGISTRATION_FAILED transaction from next ZP0061 batch | ReconciliationIntegrationTest class with full end-to-end flow verified | • Exactly 3 UNCERTAIN transitions to APPROVED after processing • 1 UNCERTAIN transitions to FAILED; prefunding_ledger_entry of type REVERSAL exists for the OVERSEAS partner • UNCERTAIN transaction absent from ZP0012 and age < 24h: still UNCERTAIN; exception_record count unchanged for this txn • exception_record table has exactly the expected rows post-processing • Re-running the same integration test input is idempotent: no duplicate rows, no double-reversals • Settlement batch for affected REGISTRATION_FAILED transaction is blocked (batch_item_status=EXCEPTION_PENDING) | 60 | 9.8-T09, 9.8-T11, 9.8-T14 | BE | SCH-06
9.8-T29 | settlement-reconciliation | 9.8 | 9. QR Scheme Integration (ZeroPay) | Reconciliation & exception handling | 2 | Integration test: late-file detection and retransmission round-trip | WBS 9.8. Integration test verifying the late-file monitor creates a batch_late_alert when ZP0012 is overdue, places dependent jobs in WAITING state, and that after arrival the alert is resolved and jobs resume. Also tests retransmission sequence increment round-trip via POST /internal/batches/{id}/retransmit. | • Create LateFileAndRetransmissionIntegrationTest using @SpringBootTest with TestContainers • Seed a settlement_batch for ZP0012 with status=PENDING and expected arrival in the past (simulate late by setting expected_by to now()-90min) • Invoke BatchLateFileMonitor.checkForLateFiles() • Assert batch_late_alert row created; settlement_batch.status=ERROR; dependent ZP0061 batch in WAITING • Simulate ZP0012 arrival: update settlement_batch.status=RECEIVED and resolved_at in batch_late_alert • Assert dependent ZP0061 batch transitions out of WAITING when monitor runs again • Seed a ZP0011 batch in ERROR status; POST /internal/batches/{id}/retransmit with reason • Assert retransmission_log has sequence_number=2; settlement_batch.status=TRANSMITTED; filename contains _02 | LateFileAndRetransmissionIntegrationTest class verifying late-file and retransmit flows | • batch_late_alert created exactly once for the late ZP0012 (idempotent on second monitor run) • settlement_batch status=ERROR and dependent batch status=WAITING after late-file detection • After ZP0012 received: batch_late_alert.resolved_at is set; WAITING batch resumes • Retransmission endpoint returns 200 with filename containing '_02.dat.pgp' • Second retransmit call returns filename '_03.dat.pgp' • RECONCILED batch retransmit returns 409 | 55 | 9.8-T12, 9.8-T13, 9.8-T20, 9.8-T28 | BE | SCH-06
9.8-T30 | settlement-reconciliation | 9.8 | 9. QR Scheme Integration (ZeroPay) | Reconciliation & exception handling | 2 | Ops Admin portal: exception queue UI wiring (backend DTO and openapi spec) | WBS 9.8. The Admin portal exception queue screen (PRD-07) needs an OpenAPI specification and DTO layer for the /internal/exceptions and /internal/exceptions/{id}/resolve endpoints so the frontend team can build against a contract. This ticket covers the OpenAPI spec fragment and the ExceptionRecordDto class with all fields. The Admin portal must surface exceptions within 15 minutes of batch receipt (NFR G-5). | • Add ExceptionRecordDto with fields: id, exception_type, priority, status, txn_ref, scheme_ref, batch_id, file_type (from settlement_batch), detail, resolution_note, created_at, resolved_by, resolved_at • Add ExceptionListResponseDto with fields: items (List<ExceptionRecordDto>), total, page, pageSize • Write OpenAPI YAML fragment for GET /internal/exceptions and POST /internal/exceptions/{id}/resolve including request/response schemas and error codes (400, 403, 404, 409) • Add the openapi fragment to the project's openapi spec file • Verify that the auto-generated client stub (if applicable) compiles | ExceptionRecordDto, ExceptionListResponseDto, and OpenAPI spec fragment for exception queue endpoints | • ExceptionRecordDto includes all 12 fields listed above; no field is optional that the spec requires as mandatory • OpenAPI fragment validates against OpenAPI 3.0 schema (run via openapi-generator or similar) • GET /internal/exceptions response schema matches ExceptionListResponseDto • POST /internal/exceptions/{id}/resolve request schema requires resolution_note (minLength 10) • HTTP 409 error response is documented for resolving an already-resolved exception • Fragment merges without conflict into the master openapi.yaml | 35 | 9.8-T18, 9.8-T19 | BE | SCH-06
9.8-T31 | settlement-reconciliation | 9.8 | 9. QR Scheme Integration (ZeroPay) | Reconciliation & exception handling | 2 | Ops Admin portal: settlement batch status screen backend DTO and openapi spec | WBS 9.8. The settlement batch monitoring screen in the Admin portal (PRD-07) needs a DTO and OpenAPI spec for GET /internal/settlement-batches (list by date) and GET /internal/settlement-batches/{id} (detail with reconciliation_item rows). This is the screen where Ops monitors daily batch status and drills into discrepancies. | • Add SettlementBatchDto: id, scheme_id, file_type, direction, settlement_date, window, status, transaction_count, total_amount, total_amount_ccy, file_checksum, transmitted_at, received_at, reconciled_at, error_detail, exception_count (count of open exceptions linked to this batch) • Add ReconciliationItemDto: id, batch_id, txn_ref, scheme_ref, match_status, gme_amount, scheme_amount, discrepancy_amount, ccy, resolution_status, resolved_by, resolved_at • Write OpenAPI YAML fragment for GET /internal/settlement-batches?settlement_date=&file_type= and GET /internal/settlement-batches/{id} (includes reconciliation_items array) • Add the fragment to the master openapi.yaml | SettlementBatchDto, ReconciliationItemDto, and OpenAPI spec fragment for settlement batch monitoring | • SettlementBatchDto includes exception_count field computed as a DB aggregate • GET /internal/settlement-batches?settlement_date=2026-10-15 returns all batches for that date • GET /internal/settlement-batches/{id} response includes reconciliation_items array • OpenAPI fragment validates against OpenAPI 3.0 schema • ReconciliationItemDto match_status is documented as an enum: MATCHED, DISCREPANCY, MISSING_GME, MISSING_SCHEME • OpenAPI spec includes 401, 403, 404 error responses for both endpoints | 35 | 9.8-T18, 9.8-T20 | BE | SCH-06
9.8-T32 | settlement-reconciliation | 9.8 | 9. QR Scheme Integration (ZeroPay) | Reconciliation & exception handling | 2 | Developer documentation: exception handling runbook snippet in code comments and README | WBS 9.8. The exception handling lifecycle and key decisions must be documented for future developers. This ticket covers: (1) Javadoc/KDoc on each exception type in ExceptionRecordService explaining the priority, blocking behaviour, and resolution path; (2) a short reconciliation-flow comment block in the SettlementEngine class explaining the daily file dependencies (ZP0011 -> ZP0012 -> ZP0061 -> ZP0062 -> ... -> ZP0065/ZP0066 chain); (3) a note in the retransmission service explaining the sequence-number filename convention. No standalone .md files — documentation goes in code comments only. | • Add class-level Javadoc/KDoc to ExceptionRecordService describing all 10 exception_type values, their priorities, and resolution paths • Add method-level Javadoc to UncertainTransactionResolver.resolve() describing the 24-hour window and prefunding reversal semantics • Add a comment block at the top of the Settlement Engine's batch-scheduler component describing the 7-step daily file dependency chain • Add a comment on RetransmissionService.retransmit() explaining the filename convention ZP0011_{yyyyMMdd}_{seqNum:02d}.dat.pgp and idempotent regeneration guarantee • Review all comments are accurate against the implementation (no stale references) | Inline documentation (Javadoc/KDoc + comment blocks) in ExceptionRecordService, UncertainTransactionResolver, SettlementEngine batch scheduler, and RetransmissionService | • ExceptionRecordService class Javadoc lists all 10 exception_type values with priority and resolution path • UncertainTransactionResolver.resolve() Javadoc explains 24-hour window and prefunding reversal semantics • Settlement Engine comment block shows the 7-step file chain (ZP0011 -> ZP0012 -> ZP0061 -> ZP0062 -> ZP0063 -> ZP0064 -> ZP0065/ZP0066) • RetransmissionService comment explains sequence-number filename convention with an example • No method or class has a TODO referencing reconciliation logic that is actually implemented (clean TODO list) | 30 | 9.8-T09, 9.8-T10, 9.8-T13, 9.8-T16 | BE | SCH-06
9.9-T01 | scheme-adapter-zeropay | 9.9 | 9. QR Scheme Integration (ZeroPay) | Scheme status/reason code mapping | 2 | Define ZeroPaySchemeCode enum: all illustrative ZP real-time result codes | SCH-06 §10.1 lists illustrative ZeroPay real-time API result codes that GMEPay+ must handle: 0000 (Success), 1001 (Merchant ID not found), 1002 (Merchant inactive/suspended), 1003 (QR code deactivated), 1004 (QR code expired - CPM token), 2001 (Amount below minimum), 2002 (Amount above maximum), 3001 (Scheme processing timeout), 3002 (ZeroPay internal error), 4001 (Duplicate transaction reference). Assumption A-10 states these are illustrative; exact codes come from the official 한결원 spec. The enum must be extensible and carry the raw string code so unknown codes received at runtime can be represented without a code change. | • Create enum ZeroPaySchemeCode in com.gmepayplus.scheme.zeropay.codes • Add enum constants: SUCCESS(0000), MERCHANT_NOT_FOUND(1001), MERCHANT_INACTIVE(1002), QR_DEACTIVATED(1003), QR_EXPIRED(1004), AMOUNT_TOO_LOW(2001), AMOUNT_TOO_HIGH(2002), SCHEME_TIMEOUT(3001), SCHEME_ERROR(3002), DUPLICATE_TRANSACTION(4001), UNKNOWN(-1) • Each constant holds a String rawCode field (not int, since codes may gain leading zeros or letters after 한결원 confirmation) • Add static factory method fromRawCode(String raw): returns matching constant or UNKNOWN if not recognised • Add isSuccess() method: returns true only for SUCCESS | ZeroPaySchemeCode.java enum in com.gmepayplus.scheme.zeropay.codes | • ZeroPaySchemeCode.fromRawCode(0000) returns SUCCESS • ZeroPaySchemeCode.fromRawCode(9999) returns UNKNOWN (not exception) • ZeroPaySchemeCode.SUCCESS.isSuccess() == true; ZeroPaySchemeCode.MERCHANT_NOT_FOUND.isSuccess() == false • All 10 named constants are present; verify via ZeroPaySchemeCode.values().length == 11 (10 + UNKNOWN) • rawCode field on MERCHANT_NOT_FOUND equals the string 1001 | 25 |  | BE | SCH-06
9.9-T02 | scheme-adapter-zeropay | 9.9 | 9. QR Scheme Integration (ZeroPay) | Scheme status/reason code mapping | 2 | Define ZeroPayBatchResultCode enum: batch-level result codes from ZP0012/ZP0022 | SCH-06 §10.1 lists three batch-specific ZeroPay result codes returned in ZP0012 (payment registration result) and ZP0022 (refund registration result) fields result_code CHAR(2): 00 (Success - registration accepted), 9001 (Batch registration failure), 9002 (Amount mismatch on registration), 9003 (Record not found for registration). These differ from real-time codes and must be modelled separately to avoid confusion. The enum must support fromRawCode(String) similar to ZeroPaySchemeCode, with UNKNOWN for unrecognised values. | • Create enum ZeroPayBatchResultCode in com.gmepayplus.scheme.zeropay.codes • Add constants: BATCH_SUCCESS(00), BATCH_REGISTRATION_FAILURE(9001), BATCH_AMOUNT_MISMATCH(9002), BATCH_RECORD_NOT_FOUND(9003), BATCH_UNKNOWN(-1) • Each constant carries String rawCode field • Add fromRawCode(String raw) factory returning BATCH_UNKNOWN for unrecognised input • Add isSuccess() returning true only for BATCH_SUCCESS | ZeroPayBatchResultCode.java enum | • fromRawCode(00) returns BATCH_SUCCESS • fromRawCode(9002) returns BATCH_AMOUNT_MISMATCH • fromRawCode(9999) returns BATCH_UNKNOWN without throwing • BATCH_SUCCESS.isSuccess() == true; BATCH_REGISTRATION_FAILURE.isSuccess() == false • rawCode on BATCH_AMOUNT_MISMATCH equals the string 9002 | 20 |  | BE | SCH-06
9.9-T03 | scheme-adapter-zeropay | 9.9 | 9. QR Scheme Integration (ZeroPay) | Scheme status/reason code mapping | 2 | Define GmeApiErrorCode enum: all Northbound API-05 error codes with HTTP status and retryable flag | API-05 §8.2 defines the complete set of GMEPay+ partner-facing error codes. Each code maps to an HTTP status and a retryable flag. Full table: VALIDATION_ERROR(400,false), MISSING_IDEMPOTENCY_KEY(400,false), INVALID_SIGNATURE(401,false), INVALID_API_KEY(401,false), TIMESTAMP_OUT_OF_RANGE(401,false), FORBIDDEN(403,false), IP_NOT_ALLOWLISTED(403,false), PAYMENT_NOT_FOUND(404,false), MERCHANT_NOT_FOUND(404,false), SCHEME_NOT_FOUND(404,false), IDEMPOTENCY_KEY_REUSE(422,false), RATE_QUOTE_EXPIRED(422,false), RATE_QUOTE_INVALID(422,false), PARTNER_B_QUOTE_DEVIATION(422,false), PARTNER_B_QUOTE_UNAVAILABLE(422,true), SCHEME_UNAVAILABLE(422,true), PAYMENT_MODE_NOT_SUPPORTED(422,false), DIRECTION_NOT_ENABLED(422,false), CANCEL_NOT_PERMITTED(400,false), INSUFFICIENT_PREFUNDING(402,false), DUPLICATE_PARTNER_TXN_REF(409,false), RATE_LIMITED(429,true), INTERNAL_ERROR(500,true), SERVICE_UNAVAILABLE(503,true). Plus scheme-specific codes: QR_INVALID_CHECKSUM(422,false), QR_MALFORMED(422,false), QR_UNKNOWN_SCHEME(422,false), QR_CURRENCY_MISMATCH(422,false), QR_DEACTIVATED(422,false), QR_EXPIRED(422,false), MERCHANT_INACTIVE(422,false), AMOUNT_TOO_LOW(422,false), AMOUNT_TOO_HIGH(422,false), SCHEME_TIMEOUT(504,true), SCHEME_ERROR(502,true), DUPLICATE_TRANSACTION(409,false), NO_SCHEME_FOR_LOCATION(422,false). | • Create enum GmeApiErrorCode in com.gmepayplus.api.error with fields: int httpStatus, boolean retryable • Add all 37 constants listed in context with their httpStatus and retryable values • Add getHttpStatus() and isRetryable() accessors • Add a partnerMessage() method returning the canonical partner-facing English message string per API-05 §10.2 mapping table (e.g. MERCHANT_NOT_FOUND -> Merchant not found) • Ensure the enum is in a shared module importable by both the Northbound API layer and the ZeroPay adapter code-mapping layer | GmeApiErrorCode.java enum with all 37 constants, HTTP status, retryable flag, and partnerMessage() | • GmeApiErrorCode.MERCHANT_NOT_FOUND.getHttpStatus() == 404 • GmeApiErrorCode.SCHEME_TIMEOUT.getHttpStatus() == 504 and isRetryable() == true • GmeApiErrorCode.INSUFFICIENT_PREFUNDING.getHttpStatus() == 402 and isRetryable() == false • GmeApiErrorCode.PARTNER_B_QUOTE_UNAVAILABLE.isRetryable() == true • GmeApiErrorCode.values().length == 37 (compile-time constant guards against accidental deletion) | 35 |  | BE | SCH-06
9.9-T04 | scheme-adapter-zeropay | 9.9 | 9. QR Scheme Integration (ZeroPay) | Scheme status/reason code mapping | 2 | Define SchemeCodeMappingRule record: one row in the ZeroPay-to-GME mapping table | The mapping from ZeroPay scheme codes to GMEPay+ API error codes is data, not hard-coded logic. Each mapping rule has: sourceCode (String - the raw ZP code or internal signal like QR_PARSE_FAIL), channel (REALTIME or BATCH), gmeErrorCode (GmeApiErrorCode), httpStatus (int - from GmeApiErrorCode), partnerMessage (String - the canonical English text for partners), includeRawCode (boolean - whether to expose scheme_error_code in the extended error body). The mapping table is loaded at startup from a config source (DB or YAML) so new ZeroPay codes can be mapped without a code redeploy (Assumption A-10: exact codes TBD until 한결원 spec confirmed). | • Create enum Channel: REALTIME, BATCH • Create record SchemeCodeMappingRule with fields: String sourceCode, Channel channel, GmeApiErrorCode gmeErrorCode, boolean includeRawCode • Add a computed accessor partnerMessage() delegating to gmeErrorCode.partnerMessage() • Add a computed accessor httpStatus() delegating to gmeErrorCode.getHttpStatus() • Create SchemeCodeMappingRuleBuilder (or use record compact constructor) that validates sourceCode is non-blank and gmeErrorCode is non-null | SchemeCodeMappingRule.java record and Channel.java enum in com.gmepayplus.scheme.mapping | • SchemeCodeMappingRule with sourceCode=1001, channel=REALTIME, gmeErrorCode=MERCHANT_NOT_FOUND, includeRawCode=true constructs without error • rule.httpStatus() == 404 (delegated from GmeApiErrorCode.MERCHANT_NOT_FOUND) • rule.partnerMessage() == Merchant not found • Constructing with null gmeErrorCode throws NullPointerException or IllegalArgumentException • Constructing with blank sourceCode throws IllegalArgumentException | 25 | 9.9-T03 | BE | SCH-06
9.9-T05 | scheme-adapter-zeropay | 9.9 | 9. QR Scheme Integration (ZeroPay) | Scheme status/reason code mapping | 2 | Define canonical ZeroPay-to-GME mapping table: all 13 real-time code mappings as config | SCH-06 §10.2 provides the full illustrative mapping for ZeroPay real-time codes to GMEPay+ API error codes. The 13 rows (including success and internal signals): 0000->success(200), 1001->MERCHANT_NOT_FOUND(422), 1002->MERCHANT_INACTIVE(422), 1003->QR_DEACTIVATED(422), 1004->QR_EXPIRED(422), 2001->AMOUNT_TOO_LOW(422), 2002->AMOUNT_TOO_HIGH(422), 3001->SCHEME_TIMEOUT(504), 3002->SCHEME_ERROR(502), 4001->DUPLICATE_TRANSACTION(409), QR_PARSE_FAIL/QR_INVALID_CHECKSUM->QR_INVALID_CHECKSUM(422), QR_PARSE_FAIL/QR_MALFORMED->QR_MALFORMED(422), internal:NO_SCHEME->NO_SCHEME_FOR_LOCATION(422), internal:PREFUNDING->INSUFFICIENT_PREFUNDING(402). All non-zero real-time codes must include scheme_error_code (raw ZP code) in the extended error body (includeRawCode=true). Internal signals (QR parse, prefunding) do not include a scheme code (includeRawCode=false). | • Create class ZeroPayRealtimeCodeMappings in com.gmepayplus.scheme.zeropay.codes • Define a static final List<SchemeCodeMappingRule> ALL_MAPPINGS containing one entry per row described in context • Use SchemeCodeMappingRule records; channel=REALTIME for all entries in this class • Add a static Map<String, SchemeCodeMappingRule> BY_SOURCE_CODE index built from ALL_MAPPINGS for O(1) lookup • Verify list size is exactly 14 entries (13 error mappings + 1 success row) | ZeroPayRealtimeCodeMappings.java with 14 static mapping entries and an index map | • ZeroPayRealtimeCodeMappings.BY_SOURCE_CODE.get(1001).getGmeErrorCode() == GmeApiErrorCode.MERCHANT_NOT_FOUND • Entry for 3001 has includeRawCode=true and gmeErrorCode=SCHEME_TIMEOUT • Entry for internal signal QR_INVALID_CHECKSUM has includeRawCode=false • Entry for 0000 maps to httpStatus 200 (success, no error code) • ALL_MAPPINGS.size() == 14 | 30 | 9.9-T01, 9.9-T03, 9.9-T04 | BE | SCH-06
9.9-T06 | scheme-adapter-zeropay | 9.9 | 9. QR Scheme Integration (ZeroPay) | Scheme status/reason code mapping | 2 | Define canonical ZeroPay-to-GME mapping table: batch result code mappings for ZP0012/ZP0022 | SCH-06 §10.3 defines internal batch status codes assigned to each registration result. The mapping from ZeroPay ZP0012/ZP0022 result_code CHAR(2) to internal GMEPay+ batch status: 00 -> SETTLEMENT_REGISTERED (success), 9001 -> REGISTRATION_FAILED, 9002 -> REGISTRATION_AMOUNT_MISMATCH, 9003 -> REGISTRATION_UNKNOWN. These batch statuses are stored on the transaction record and drive the exception queue in the Ops portal. They do not map to API-05 HTTP errors (batch errors are internal); they map to BatchTransactionStatus enum values. A BATCH_UNKNOWN catch-all handles unrecognised result codes as EXCEPTION_PENDING. | • Create enum BatchTransactionStatus: SETTLEMENT_REGISTERED, REGISTRATION_FAILED, REGISTRATION_UNKNOWN, REGISTRATION_AMOUNT_MISMATCH, SETTLEMENT_CONFIRMED, SETTLEMENT_DISCREPANCY, EXCEPTION_PENDING, EXCEPTION_RESOLVED • Create class ZeroPayBatchCodeMappings in com.gmepayplus.scheme.zeropay.codes • Add static Map<String, BatchTransactionStatus> RESULT_CODE_TO_STATUS: 00->SETTLEMENT_REGISTERED, 9001->REGISTRATION_FAILED, 9002->REGISTRATION_AMOUNT_MISMATCH, 9003->REGISTRATION_UNKNOWN • Add static method resolve(String resultCode): returns mapped status or EXCEPTION_PENDING for unknown codes • Document that SETTLEMENT_CONFIRMED and SETTLEMENT_DISCREPANCY are set by ZP0062/ZP0064 processing, not ZP0012/ZP0022 | BatchTransactionStatus.java enum and ZeroPayBatchCodeMappings.java in com.gmepayplus.scheme.zeropay.codes | • ZeroPayBatchCodeMappings.resolve(00) returns BatchTransactionStatus.SETTLEMENT_REGISTERED • ZeroPayBatchCodeMappings.resolve(9002) returns BatchTransactionStatus.REGISTRATION_AMOUNT_MISMATCH • ZeroPayBatchCodeMappings.resolve(9999) returns BatchTransactionStatus.EXCEPTION_PENDING (unknown code fallback) • BatchTransactionStatus enum has exactly 8 values as listed • resolve(null) returns EXCEPTION_PENDING without throwing NullPointerException | 30 | 9.9-T02 | BE | SCH-06
9.9-T07 | scheme-adapter-zeropay | 9.9 | 9. QR Scheme Integration (ZeroPay) | Scheme status/reason code mapping | 2 | Implement SchemeCodeMapper service: translate ZeroPay real-time codes to GmeApiError | SchemeCodeMapper is the central service the ZeroPay Adapter and Hub Core Orchestrator call to convert a raw ZeroPay result code into a GmeApiError response object. GmeApiError (API-05 §8.1 envelope) has fields: code (GmeApiErrorCode), message (String), request_id (String), details (List), scheme_error_code (String, nullable - the raw ZP code included only when includeRawCode=true on the mapping rule). The mapper looks up ZeroPayRealtimeCodeMappings.BY_SOURCE_CODE; if the code is absent (runtime code not in illustrative table), falls back to SCHEME_ERROR(502) with a warning log and includes the unknown raw code for diagnostics. | • Create class SchemeCodeMapper as a Spring @Service in com.gmepayplus.scheme.zeropay • Inject ZeroPayRealtimeCodeMappings (or load statically) • Implement GmeApiError mapRealtimeCode(String zpCode, String requestId): lookup in BY_SOURCE_CODE; build GmeApiError with code, message, request_id, and scheme_error_code=zpCode if includeRawCode=true • For unknown zpCode: log WARN with the raw code; return GmeApiError with code=SCHEME_ERROR, httpStatus=502, scheme_error_code=zpCode (always include for unknowns) • Add GmeApiError mapInternalSignal(String signalKey, String requestId): same lookup but for internal keys like QR_INVALID_CHECKSUM and INSUFFICIENT_PREFUNDING; these never include scheme_error_code | SchemeCodeMapper.java Spring service and GmeApiError.java record | • mapRealtimeCode(1001, req-123) returns GmeApiError with code=MERCHANT_NOT_FOUND, httpStatus=422, scheme_error_code=1001, message=Merchant not found • mapRealtimeCode(3001, req-456) returns httpStatus=504, code=SCHEME_TIMEOUT, scheme_error_code=3001 • mapRealtimeCode(9999, req-789) returns httpStatus=502, code=SCHEME_ERROR, scheme_error_code=9999 (unknown code always exposes raw code) • mapInternalSignal(QR_INVALID_CHECKSUM, req-abc) returns httpStatus=422, code=QR_INVALID_CHECKSUM, scheme_error_code=null (no raw scheme code for internal signals) • mapRealtimeCode(1002, req-xyz) returns message=Merchant is not accepting payments | 40 | 9.9-T05, 9.9-T03 | BE | SCH-06
9.9-T08 | scheme-adapter-zeropay | 9.9 | 9. QR Scheme Integration (ZeroPay) | Scheme status/reason code mapping | 2 | Implement BatchCodeMapper service: translate ZP0012/ZP0022 result codes to BatchTransactionStatus | BatchCodeMapper translates ZeroPay batch result codes (from ZP0012 result_code CHAR(2) and ZP0022 result_code CHAR(2)) to internal BatchTransactionStatus values and produces ExceptionRecord entries for non-success outcomes. An ExceptionRecord has: gme_txn_id, zeropay_txn_ref, batch_file_type (ZP0012 or ZP0022), result_code (raw), resolved_status (BatchTransactionStatus), message (human-readable), raised_at (Instant). For REGISTRATION_AMOUNT_MISMATCH, ExceptionRecord must also carry submitted_amount and registered_amount (both BigDecimal, KRW scale 0). | • Create BatchCodeMapper as a Spring @Service in com.gmepayplus.scheme.zeropay • Create ExceptionRecord record with fields: gme_txn_id, zeropay_txn_ref, batch_file_type, result_code, resolved_status, message, raised_at, submitted_amount (nullable), registered_amount (nullable) • Implement BatchTransactionStatus resolveStatus(String resultCode): delegate to ZeroPayBatchCodeMappings.resolve() • Implement ExceptionRecord buildException(PaymentRegistrationResult result, String batchFileType): map result_code to status; build ExceptionRecord; for REGISTRATION_AMOUNT_MISMATCH include amounts • Add boolean requiresOpsAttention(BatchTransactionStatus status): returns true for REGISTRATION_FAILED, REGISTRATION_UNKNOWN, REGISTRATION_AMOUNT_MISMATCH, SETTLEMENT_DISCREPANCY, EXCEPTION_PENDING | BatchCodeMapper.java Spring service and ExceptionRecord.java record | • resolveStatus(00) returns SETTLEMENT_REGISTERED • resolveStatus(9001) returns REGISTRATION_FAILED • buildException for result_code=9002, submitted_amount=50000, registered_amount=49000 produces ExceptionRecord with resolved_status=REGISTRATION_AMOUNT_MISMATCH and both amounts set • requiresOpsAttention(SETTLEMENT_REGISTERED) == false; requiresOpsAttention(REGISTRATION_FAILED) == true • buildException for result_code=00 produces ExceptionRecord with resolved_status=SETTLEMENT_REGISTERED and no amounts set (amounts are null) | 40 | 9.9-T06 | BE | SCH-06
9.9-T09 | scheme-adapter-zeropay | 9.9 | 9. QR Scheme Integration (ZeroPay) | Scheme status/reason code mapping | 2 | Implement settlement result code resolution: ZP0062/ZP0064 per-merchant status mapping | ZP0062 (morning settlement result) and ZP0064 (afternoon settlement result) confirm whether ZeroPay processed the settlement request (ZP0061/ZP0063). Each per-merchant record in ZP0062/ZP0064 carries a result_code (CHAR(2) from ZeroPay). A result_code=00 means the merchant was settled; any non-zero code means settlement failed for that merchant. GMEPay+ must map these to BatchTransactionStatus: 00 -> SETTLEMENT_CONFIRMED; non-zero -> SETTLEMENT_DISCREPANCY (triggers P1 ops exception). The full settlement_batch record in the DB must also be updated: status, settled_amount, settlement_date. SettlementBatchRecord carries: settlement_batch_id, merchant_id, file_type, result_code, resolved_status, settled_amount_krw, settlement_date. | • Create SettlementBatchRecord record with fields listed in context • Implement SettlementCodeMapper.resolveSettlementStatus(String resultCode): returns SETTLEMENT_CONFIRMED for 00, SETTLEMENT_DISCREPANCY otherwise • Implement SettlementCodeMapper.processSettlementResult(List<SettlementBatchRecord> records): iterate; set resolved_status via resolveSettlementStatus; collect SETTLEMENT_DISCREPANCY records as ExceptionRecord list for Ops queue • Add a method buildSettlementException(SettlementBatchRecord record): creates ExceptionRecord with batch_file_type=ZP0062 or ZP0064, resolved_status=SETTLEMENT_DISCREPANCY, message containing merchant_id and amounts • Write unit test: 3 merchant records (result_code=00, 00, non-zero) -> 2 SETTLEMENT_CONFIRMED and 1 SETTLEMENT_DISCREPANCY exception | SettlementCodeMapper.java Spring service and SettlementBatchRecord.java record with unit tests | • resolveSettlementStatus(00) returns SETTLEMENT_CONFIRMED • resolveSettlementStatus(01) returns SETTLEMENT_DISCREPANCY • processSettlementResult with 1 non-zero record produces exactly 1 ExceptionRecord in the returned exception list • ExceptionRecord for SETTLEMENT_DISCREPANCY has requiresOpsAttention=true (verify via BatchCodeMapper.requiresOpsAttention) • processSettlementResult with all-zero result codes produces empty exception list | 35 | 9.9-T06, 9.9-T08 | BE | SCH-06
9.9-T10 | scheme-adapter-zeropay | 9.9 | 9. QR Scheme Integration (ZeroPay) | Scheme status/reason code mapping | 2 | Wire SchemeCodeMapper into ZeroPayAdapter.commitPayment: translate scheme result before throwing | ZeroPayAdapter.commitPayment (WBS 9.1-T14) currently maps ZeroPay result codes directly to SchemeAdapterException subtypes. It must now route through SchemeCodeMapper so the raw ZP code is captured in the exception and available for the Northbound API error response. The SchemeResult returned on success must carry the raw ZP code (0000) and the approval_code. On failure, the thrown SchemeAdapterException must carry: raw_scheme_error_code (the ZP string), gme_error_code (GmeApiErrorCode from mapping), and http_status (int). The Hub Core Orchestrator will use these to build the GmeApiError response envelope without knowing ZeroPay details. | • Inject SchemeCodeMapper into ZeroPayAdapter • In commitPayment, after receiving ZeroPay response, call SchemeCodeMapper.mapRealtimeCode(zpResultCode, requestId) • If GmeApiError.code == success (0000), return SchemeResult with approval_code and raw ZP code • If not success, enrich the thrown SchemeAdapterException with gme_error_code and http_status from GmeApiError; preserve raw_scheme_error_code • Update SchemeAdapterException base class or create SchemeResultException(GmeApiError gmeApiError) to carry the full error context • Update existing unit tests for commitPayment to assert that caught SchemeAdapterException carries gme_error_code | ZeroPayAdapter.commitPayment updated to use SchemeCodeMapper, with updated unit tests | • commitPayment receiving ZP code 1001 throws SchemeAdapterException with gme_error_code=MERCHANT_NOT_FOUND and http_status=422 • commitPayment receiving ZP code 3001 throws SchemeAdapterException with gme_error_code=SCHEME_TIMEOUT and http_status=504 • commitPayment receiving unknown code 8888 throws SchemeAdapterException with gme_error_code=SCHEME_ERROR and raw_scheme_error_code=8888 • commitPayment receiving ZP code 0000 returns SchemeResult without throwing • Existing 9.1-T14 unit tests still pass after refactoring | 40 | 9.9-T07, 9.1-T14 | BE | SCH-06
9.9-T11 | scheme-adapter-zeropay | 9.9 | 9. QR Scheme Integration (ZeroPay) | Scheme status/reason code mapping | 2 | Wire SchemeCodeMapper into ZeroPayAdapter.prepareCPM: translate CPM token errors | prepareCPM (WBS 9.1-T14) issues a CPM QR token via the ZeroPay real-time API. Failure codes for prepareCPM are the same ZeroPay real-time table (SCH-06 §10.1). CPM-specific codes to handle: 1003 (QR_DEACTIVATED), 1004 (QR_EXPIRED for a reused token), 3001 (SCHEME_TIMEOUT), 3002 (SCHEME_ERROR). A failed prepareCPM must never deduct prefunding (the Hub Core deducts at generate time; the adapter must signal failure before the Orchestrator deducts). The enriched exception carries gme_error_code and http_status so the Orchestrator can return the correct API-05 error envelope. | • Inject SchemeCodeMapper into ZeroPayAdapter (already injected after 9.9-T10; verify) • In prepareCPM, apply mapRealtimeCode(zpResultCode, requestId) after receiving ZeroPay response • On non-success, throw SchemeAdapterException with gme_error_code from GmeApiError • Add unit test for prepareCPM with ZP code 1003: assert SchemeAdapterException with gme_error_code=QR_DEACTIVATED, httpStatus=422 • Add unit test for prepareCPM with ZP code 3001: assert SchemeAdapterException with gme_error_code=SCHEME_TIMEOUT, httpStatus=504 | ZeroPayAdapter.prepareCPM updated to use SchemeCodeMapper, plus 2 new unit tests | • prepareCPM receiving 1003 throws SchemeAdapterException with gme_error_code=QR_DEACTIVATED • prepareCPM receiving 3001 throws SchemeAdapterException with gme_error_code=SCHEME_TIMEOUT and http_status=504 • prepareCPM receiving 0000 returns PrepareToken without throwing • Existing prepareCPM unit test from 9.1-T14 still passes • SchemeCodeMapper is injected once in ZeroPayAdapter constructor, not duplicated | 30 | 9.9-T07, 9.1-T14, 9.9-T10 | BE | SCH-06
9.9-T12 | scheme-adapter-zeropay | 9.9 | 9. QR Scheme Integration (ZeroPay) | Scheme status/reason code mapping | 2 | Wire BatchCodeMapper into ZP0012 reconciliation: assign BatchTransactionStatus per record | After parseInboundFile(ZP0012) returns a list of PaymentRegistrationResult records, the settlement reconciliation processor must call BatchCodeMapper to assign a BatchTransactionStatus to each transaction and raise ExceptionRecord entries for non-00 result codes. The five SCH-06 §5.4 mismatch conditions must be detected: (1) result_code=00 + amounts match = SETTLEMENT_REGISTERED, (2) non-zero result_code = REGISTRATION_FAILED, (3) ZP0011 record absent from ZP0012 = REGISTRATION_UNKNOWN (set by cross-file diff logic, not BatchCodeMapper), (4) ZP0012 has record not in ZP0011 = anomaly log, (5) amounts differ = REGISTRATION_AMOUNT_MISMATCH. BatchCodeMapper handles conditions 1, 2, 5; the cross-file diff (conditions 3, 4) is in ZP0012ReconciliationService (9.9-T13). | • Create RegistrationReconciliationResult record: List<TransactionStatusUpdate> updates, List<ExceptionRecord> exceptions • TransactionStatusUpdate carries: gme_txn_id, zeropay_txn_ref, new_status (BatchTransactionStatus) • Implement BatchCodeMapper.processZp0012Results(List<PaymentRegistrationResult> results, Map<String, BigDecimal> submittedAmounts): for each result, call resolveStatus; for SETTLEMENT_REGISTERED verify registered_amount == submittedAmounts.get(zeropay_txn_ref), if mismatch override to REGISTRATION_AMOUNT_MISMATCH and build ExceptionRecord • Return RegistrationReconciliationResult with all updates and all exceptions • Write unit test: 3 results (00 matching amount, 9001 failure, 00 with amount mismatch 50000 vs 49500) -> 1 SETTLEMENT_REGISTERED, 1 REGISTRATION_FAILED, 1 REGISTRATION_AMOUNT_MISMATCH | BatchCodeMapper.processZp0012Results with RegistrationReconciliationResult and unit tests | • Result with result_code=00 and registered_amount=50000 matching submitted=50000 produces update with status=SETTLEMENT_REGISTERED • Result with result_code=9001 produces ExceptionRecord with resolved_status=REGISTRATION_FAILED • Result with result_code=00 but registered_amount=49500 vs submitted=50000 produces status=REGISTRATION_AMOUNT_MISMATCH with both amounts in ExceptionRecord • processZp0012Results with empty input returns empty updates and empty exceptions • Amount comparison uses BigDecimal.compareTo, not equals, to handle scale differences (49500.00 == 49500) | 45 | 9.9-T08 | BE | SCH-06
9.9-T13 | scheme-adapter-zeropay | 9.9 | 9. QR Scheme Integration (ZeroPay) | Scheme status/reason code mapping | 2 | Implement ZP0012ReconciliationService: cross-file diff for conditions 3 and 4 | SCH-06 §5.4 specifies two mismatch conditions that require cross-file comparison: Condition 3 - a record in GME's outbound ZP0011 file has no matching entry in the received ZP0012 (REGISTRATION_UNKNOWN); Condition 4 - ZP0012 contains a record whose zeropay_txn_ref was not in GME's ZP0011 (anomaly - log only, raise ExceptionRecord for Ops review). The match key is zeropay_txn_ref + txn_date (SCH-06 §5.2). ZP0012ReconciliationService accepts the submitted ZP0011 records (from DB) and the parsed ZP0012 records, performs a two-way diff, and returns a CrossFileReconciliationResult. | • Create CrossFileReconciliationResult record: List<TransactionStatusUpdate> unknownUpdates (condition 3), List<ExceptionRecord> anomalies (condition 4), int matchedCount, int unknownCount, int anomalyCount • Implement ZP0012ReconciliationService.reconcile(List<ZP0011Record> submitted, List<PaymentRegistrationResult> received): index received by zeropay_txn_ref+txn_date; for each submitted record absent from received, create update with REGISTRATION_UNKNOWN; for each received record absent from submitted, create anomaly ExceptionRecord • Set REGISTRATION_UNKNOWN status only if the transaction has not already been assigned a status by BatchCodeMapper (check new_status == null) • Log anomaly condition 4 at WARN with zeropay_txn_ref • Write unit test: 3 submitted, 2 in ZP0012 (1 absent), 1 extra in ZP0012 -> 1 REGISTRATION_UNKNOWN, 1 anomaly, 2 matched | ZP0012ReconciliationService.java Spring service and CrossFileReconciliationResult.java record with unit tests | • 1 submitted record absent from ZP0012 produces 1 TransactionStatusUpdate with status=REGISTRATION_UNKNOWN • 1 ZP0012 record not in submitted produces 1 ExceptionRecord in anomalies list (not thrown exception) • matchedCount=2, unknownCount=1, anomalyCount=1 for the 3-submitted/2-received/1-extra scenario • reconcile with both lists equal (all records matched both ways) produces empty unknownUpdates and empty anomalies • Matching key uses both zeropay_txn_ref AND txn_date to avoid cross-day collisions | 45 | 9.9-T08 | BE | SCH-06
9.9-T14 | scheme-adapter-zeropay | 9.9 | 9. QR Scheme Integration (ZeroPay) | Scheme status/reason code mapping | 2 | Implement ZP0022ReconciliationService: ZP0021/ZP0022 refund registration cross-file diff | SCH-06 §6.4 states refund registration reconciliation follows identical logic to ZP0012 (§5.4) applied to refund records. Match key for ZP0022 is original_zeropay_txn_ref + refund_date. ZP0022 result field is result_code CHAR(2) (same batch codes: 00, 9001, 9002, 9003). ZP0022ReconciliationService must reuse BatchCodeMapper.processZp0012Results adapted for RefundRegistrationResult objects, and ZP0022ReconciliationService.reconcile for the cross-file diff. Unresolved refund registration failures before ZP0061 generation are P1 incidents (SCH-06 §6.4). | • Create RefundRegistrationResult record: original_zeropay_txn_ref, gme_refund_id, result_code, result_message, registered_refund_amount, adjustment_settlement_date • Extend BatchCodeMapper with processZp0022Results(List<RefundRegistrationResult> results, Map<String, BigDecimal> submittedAmounts): same pattern as processZp0012Results using original_zeropay_txn_ref+refund_date as key • Create ZP0022ReconciliationService.reconcile(List<ZP0021Record> submitted, List<RefundRegistrationResult> received): same two-way diff logic as ZP0012ReconciliationService using original_zeropay_txn_ref+refund_date key • Write unit test for ZP0022 reconciliation: 2 submitted refunds, 1 in ZP0022 response, 1 absent -> 1 REGISTRATION_UNKNOWN • Add requiresOpsAttention flag to unresolved refund failures (reuse BatchCodeMapper.requiresOpsAttention) | ZP0022ReconciliationService.java, RefundRegistrationResult.java, BatchCodeMapper.processZp0022Results with unit tests | • processZp0022Results with result_code=00 and matching amount returns SETTLEMENT_REGISTERED for the refund transaction • processZp0022Results with result_code=9001 returns REGISTRATION_FAILED for the refund • ZP0022ReconciliationService.reconcile with 1 absent refund produces 1 TransactionStatusUpdate with status=REGISTRATION_UNKNOWN • requiresOpsAttention(REGISTRATION_FAILED) returns true (verified via BatchCodeMapper) • Cross-file diff key uses original_zeropay_txn_ref AND refund_date (not payment txn_date) | 40 | 9.9-T12, 9.9-T13 | BE | SCH-06
9.9-T15 | scheme-adapter-zeropay | 9.9 | 9. QR Scheme Integration (ZeroPay) | Scheme status/reason code mapping | 2 | Implement QR parse error-to-API-error mapping in the Northbound error translation layer | When parseMerchantQR throws QrParseException (WBS 9.1-T04), the Hub Core Orchestrator must translate it to a GmeApiError before returning the HTTP response. The mapping uses the internal signal keys defined in ZeroPayRealtimeCodeMappings: QrParseErrorCode.QR_INVALID_CHECKSUM -> GmeApiErrorCode.QR_INVALID_CHECKSUM(422), QR_UNKNOWN_SCHEME -> QR_UNKNOWN_SCHEME(422) or NO_SCHEME_FOR_LOCATION(422), QR_MALFORMED -> QR_MALFORMED(422), QR_CURRENCY_MISMATCH -> QR_CURRENCY_MISMATCH(422). These are internal signals with includeRawCode=false (no scheme_error_code in the response). SchemeCodeMapper.mapInternalSignal(signalKey, requestId) already handles this; this ticket wires the mapping into the Orchestrator error-handling block. | • Locate the Hub Core Orchestrator error-handling block (or create an ErrorTranslationService) • Add a case for QrParseException: call SchemeCodeMapper.mapInternalSignal(exception.getErrorCode().name(), requestId) • Return the resulting GmeApiError as the HTTP response body with the GmeApiError.httpStatus as the response status • Add a case for SchemeAdapterException carrying gme_error_code: use the pre-mapped gme_error_code and http_status directly (no re-mapping needed) • Write unit test for ErrorTranslationService: QrParseException(QR_INVALID_CHECKSUM) -> GmeApiError code=QR_INVALID_CHECKSUM, httpStatus=422, scheme_error_code=null | ErrorTranslationService.java (or Orchestrator update) handling QrParseException and SchemeAdapterException, with unit tests | • QrParseException with errorCode=QR_INVALID_CHECKSUM produces HTTP 422 response with error.code=QR_INVALID_CHECKSUM and no scheme_error_code field • QrParseException with errorCode=QR_MALFORMED produces HTTP 422 with error.code=QR_MALFORMED • SchemeAdapterException with gme_error_code=SCHEME_TIMEOUT produces HTTP 504 response • scheme_error_code is absent (null or not serialised) for QR parse errors • SchemeAdapterException with gme_error_code=MERCHANT_NOT_FOUND produces HTTP 422 with error.code=MERCHANT_NOT_FOUND and scheme_error_code=1001 | 40 | 9.9-T07, 9.9-T10 | BE | SCH-06
9.9-T16 | scheme-adapter-zeropay | 9.9 | 9. QR Scheme Integration (ZeroPay) | Scheme status/reason code mapping | 2 | Implement ExceptionQueueService: persist ExceptionRecord to DB and surface in Ops portal | All ExceptionRecord entries raised by BatchCodeMapper, ZP0012ReconciliationService, ZP0022ReconciliationService, and SettlementCodeMapper must be persisted to a DB table batch_exception and made queryable by the Ops Admin portal exception queue (PRD-07). The batch_exception table schema: id UUID PK, gme_txn_id VARCHAR, zeropay_txn_ref VARCHAR, batch_file_type VARCHAR(8), result_code VARCHAR(4), resolved_status VARCHAR(40), message TEXT, raised_at TIMESTAMP WITH TIME ZONE, submitted_amount DECIMAL(14,0) nullable, registered_amount DECIMAL(14,0) nullable, resolved_at TIMESTAMP nullable, resolved_by VARCHAR nullable, ops_notes TEXT nullable, requires_ops_attention BOOLEAN. | • Create Flyway migration V9_9_01: batch_exception table with all columns above • Create ExceptionQueueService @Service with ExceptionQueueRepository (JdbcTemplate or JPA) • Implement persist(ExceptionRecord record): insert into batch_exception; set requires_ops_attention from BatchCodeMapper.requiresOpsAttention(record.resolved_status()) • Implement findPending(): SELECT all rows where resolved_at IS NULL AND requires_ops_attention=true ORDER BY raised_at ASC • Implement resolve(UUID id, String resolvedBy, String notes): set resolved_at=now(), resolved_by, ops_notes, resolved_status=EXCEPTION_RESOLVED • Write integration test: persist 2 records, findPending returns 2, resolve one, findPending returns 1 | Flyway migration V9_9_01, ExceptionQueueService.java, ExceptionQueueRepository.java | • persist saves ExceptionRecord with all fields; gme_txn_id and raised_at are non-null • findPending excludes records where resolved_at IS NOT NULL • resolve sets resolved_at to a non-null timestamp and resolved_by to the provided actor string • requires_ops_attention=true for REGISTRATION_FAILED records; false for SETTLEMENT_REGISTERED • Two concurrent persist calls for different gme_txn_ids both succeed without conflict (no unique constraint on gme_txn_id - same txn can have multiple exceptions from different batch cycles) | 50 | 9.9-T08, 9.9-T09 | BE | SCH-06
9.9-T17 | scheme-adapter-zeropay | 9.9 | 9. QR Scheme Integration (ZeroPay) | Scheme status/reason code mapping | 2 | Implement GmeApiErrorSerializer: JSON serialisation of GmeApiError envelope per API-05 §8.1 | API-05 §8.1 specifies the exact JSON structure for error responses: {error: {code: string, message: string, request_id: string, details: array}}. The scheme_error_code field is an extension field present only when includeRawCode was true on the mapping rule. The serialiser must produce exactly this structure with no additional fields. The error.code must be the GmeApiErrorCode name as a string (e.g. MERCHANT_NOT_FOUND). The error.message must be the canonical partner-facing message from GmeApiErrorCode.partnerMessage(). The details array must be empty (not absent) when there are no field-level details. scheme_error_code appears as a top-level field inside the error object when non-null. | • Create GmeApiErrorSerializer using Jackson (or equivalent) or a manual toJson() method on GmeApiError • Ensure error.code serialises as the enum name string (not ordinal) • Ensure scheme_error_code is omitted from JSON when null (use @JsonInclude(NON_NULL) or equivalent) • Ensure details serialises as [] (empty array) not null when the list is empty • Write unit test: serialise GmeApiError(code=MERCHANT_NOT_FOUND, message=..., request_id=req-1, scheme_error_code=1001) and assert JSON string matches expected structure exactly | GmeApiError.java with Jackson annotations for correct API-05 §8.1 serialisation, plus serialisation unit test | • Serialised JSON has top-level key error with nested keys code, message, request_id, details • error.code value is the string MERCHANT_NOT_FOUND (not a number or qualified name) • scheme_error_code=1001 appears inside the error object when set • scheme_error_code key is absent from JSON when null (not present as null) • details serialises as [] (empty array) when empty list provided | 30 | 9.9-T07 | BE | SCH-06
9.9-T18 | scheme-adapter-zeropay | 9.9 | 9. QR Scheme Integration (ZeroPay) | Scheme status/reason code mapping | 2 | Unit tests for SchemeCodeMapper: all 14 real-time code mappings including success and unknown fallback | SchemeCodeMapper.mapRealtimeCode must correctly handle all 14 rows in ZeroPayRealtimeCodeMappings including the success row and the unknown fallback. Test vectors from SCH-06 §10.2: 0000->success(200), 1001->MERCHANT_NOT_FOUND(422), 1002->MERCHANT_INACTIVE(422), 1003->QR_DEACTIVATED(422), 1004->QR_EXPIRED(422), 2001->AMOUNT_TOO_LOW(422), 2002->AMOUNT_TOO_HIGH(422), 3001->SCHEME_TIMEOUT(504), 3002->SCHEME_ERROR(502), 4001->DUPLICATE_TRANSACTION(409), QR_INVALID_CHECKSUM->422(internal), QR_MALFORMED->422(internal), INSUFFICIENT_PREFUNDING->402(internal), unknown 8888->SCHEME_ERROR(502,includeRawCode=true). | • Create SchemeCodeMapperTest • For each of the 14 test vectors, write a named test method calling mapRealtimeCode or mapInternalSignal • Assert httpStatus, code name, and scheme_error_code presence/absence for each vector • For the 0000 success row, assert that the returned GmeApiError has no error code (or a designated SUCCESS sentinel) and httpStatus=200 • For unknown code 8888, assert SCHEME_ERROR, httpStatus=502, and scheme_error_code=8888 | SchemeCodeMapperTest.java with 14 passing test methods | • All 14 test methods pass (green) • mapRealtimeCode(3001, req) returns httpStatus=504 and code=SCHEME_TIMEOUT • mapRealtimeCode(4001, req) returns httpStatus=409 and code=DUPLICATE_TRANSACTION • mapInternalSignal(INSUFFICIENT_PREFUNDING, req) returns httpStatus=402, code=INSUFFICIENT_PREFUNDING, scheme_error_code=null • mapRealtimeCode(8888, req) returns httpStatus=502, code=SCHEME_ERROR, scheme_error_code=8888 | 35 | 9.9-T07 | BE | SCH-06
9.9-T19 | scheme-adapter-zeropay | 9.9 | 9. QR Scheme Integration (ZeroPay) | Scheme status/reason code mapping | 2 | Unit tests for BatchCodeMapper.processZp0012Results: 5 mismatch condition vectors | BatchCodeMapper.processZp0012Results (9.9-T12) must correctly identify all 5 mismatch conditions from SCH-06 §5.4. Test vectors: (1) result_code=00, submitted_amount=50000, registered_amount=50000 -> SETTLEMENT_REGISTERED, no exception; (2) result_code=9001 -> REGISTRATION_FAILED, ExceptionRecord raised; (3) result_code=9002 -> REGISTRATION_AMOUNT_MISMATCH (code-based, not amount comparison), ExceptionRecord raised; (4) result_code=9003 -> REGISTRATION_UNKNOWN (from batch code alone), ExceptionRecord raised; (5) result_code=00, submitted_amount=50000, registered_amount=49000 -> REGISTRATION_AMOUNT_MISMATCH (amount-based mismatch), ExceptionRecord with submitted_amount=50000 and registered_amount=49000. | • Create BatchCodeMapperTest • Implement test_condition_1: result_code=00, amounts match -> SETTLEMENT_REGISTERED, exceptions empty • Implement test_condition_2: result_code=9001 -> REGISTRATION_FAILED, 1 ExceptionRecord in list • Implement test_condition_3: result_code=9002 -> REGISTRATION_AMOUNT_MISMATCH via code-to-status mapping • Implement test_condition_4: result_code=9003 -> REGISTRATION_UNKNOWN (code-based) • Implement test_condition_5: result_code=00, submitted=50000 KRW, registered=49000 KRW -> REGISTRATION_AMOUNT_MISMATCH, ExceptionRecord.submittedAmount=50000, ExceptionRecord.registeredAmount=49000 | BatchCodeMapperTest.java with 5 passing test methods for all mismatch conditions | • test_condition_1: updates list has 1 entry with status=SETTLEMENT_REGISTERED; exceptions empty • test_condition_2: exceptions list has 1 ExceptionRecord with resolved_status=REGISTRATION_FAILED • test_condition_5: ExceptionRecord.submittedAmount=50000 and registeredAmount=49000 (BigDecimal exact, KRW 0 decimals) • test_condition_4: resolved_status=REGISTRATION_UNKNOWN (result_code=9003 maps to REGISTRATION_UNKNOWN, not REGISTRATION_FAILED) • All 5 tests pass with no test depending on ordering of results list | 35 | 9.9-T12 | BE | SCH-06
9.9-T20 | scheme-adapter-zeropay | 9.9 | 9. QR Scheme Integration (ZeroPay) | Scheme status/reason code mapping | 2 | Unit tests for SettlementCodeMapper: ZP0062/ZP0064 success and discrepancy vectors | SettlementCodeMapper.processSettlementResult (9.9-T09) handles per-merchant settlement result records. Test vectors from SCH-06 §7.2: (1) result_code=00 for merchant M1, settled_amount_krw=487750 -> SETTLEMENT_CONFIRMED, no exception; (2) result_code=01 (non-zero) for merchant M2 -> SETTLEMENT_DISCREPANCY, ExceptionRecord raised; (3) mixed batch: M1(00, 487750), M2(00, 199100), M3(01, 295000) -> 2 SETTLEMENT_CONFIRMED, 1 SETTLEMENT_DISCREPANCY exception; (4) all-success batch with 10 merchants -> 10 SETTLEMENT_CONFIRMED, empty exception list; (5) settlement amount negative -100 KRW for M4 (invalid) -> SETTLEMENT_DISCREPANCY (caught by validateInboundFile from 9.1-T20 before reaching mapper, but mapper also guards). | • Create SettlementCodeMapperTest • Implement test_single_success: M1 result_code=00 -> SETTLEMENT_CONFIRMED, no exception • Implement test_single_discrepancy: M2 result_code=01 -> SETTLEMENT_DISCREPANCY, ExceptionRecord.merchant_id=M2 • Implement test_mixed_batch: M1+M2 confirmed, M3 discrepancy -> 2 confirmed updates, 1 exception • Implement test_all_success: 10 records all 00 -> empty exception list • Implement test_negative_amount: M4 settled_amount=-100 -> SETTLEMENT_DISCREPANCY (guard in mapper) | SettlementCodeMapperTest.java with 5 passing test methods | • test_mixed_batch: processSettlementResult returns 1 ExceptionRecord for M3 with resolved_status=SETTLEMENT_DISCREPANCY • test_all_success: exception list is empty • ExceptionRecord for M3 discrepancy contains merchant_id=M3 in message or as a field • test_negative_amount: resolved_status=SETTLEMENT_DISCREPANCY for negative settled_amount • All 5 tests pass; no test requires DB access (pure unit tests) | 30 | 9.9-T09 | BE | SCH-06
9.9-T21 | scheme-adapter-zeropay | 9.9 | 9. QR Scheme Integration (ZeroPay) | Scheme status/reason code mapping | 2 | Integration test: full ZP0012 reconciliation pipeline from parse to ExceptionRecord persistence | Verify the end-to-end ZP0012 reconciliation pipeline: (1) parseInboundFile(ZP0012 bytes) decodes 3 records, (2) BatchCodeMapper.processZp0012Results assigns statuses, (3) ZP0012ReconciliationService.reconcile cross-checks against submitted ZP0011 records (4 submitted, 1 absent from ZP0012), (4) ExceptionQueueService.persist saves all ExceptionRecord entries, (5) ExceptionQueueService.findPending returns all unresolved exceptions. Use an in-memory H2 database (or TestContainers PostgreSQL) for persistence. The test scenario: 4 submitted transactions, ZP0012 contains: txn1(00, amount match), txn2(9001), txn3(00, amount mismatch 50000 vs 48000), txn4 absent. Expected: txn1=SETTLEMENT_REGISTERED, txn2=REGISTRATION_FAILED, txn3=REGISTRATION_AMOUNT_MISMATCH, txn4=REGISTRATION_UNKNOWN; 3 ExceptionRecords persisted. | • Create ZP0012ReconciliationIntegrationTest using @SpringBootTest or @DataJpaTest with test DB • Seed 4 submitted ZP0011 records (in-memory or test DB) • Build synthetic ZP0012 file bytes with 3 records (txn1 success, txn2 9001, txn3 amount mismatch); txn4 absent • Call pipeline: parseInboundFile -> BatchCodeMapper.processZp0012Results -> ZP0012ReconciliationService.reconcile -> ExceptionQueueService.persist each exception • Call ExceptionQueueService.findPending() • Assert all statuses and exception details | ZP0012ReconciliationIntegrationTest.java with full pipeline test | • findPending() returns exactly 3 ExceptionRecord entries after the pipeline run • txn1 update has status=SETTLEMENT_REGISTERED and no ExceptionRecord • txn3 ExceptionRecord has submitted_amount=50000 and registered_amount=48000 • txn4 ExceptionRecord has resolved_status=REGISTRATION_UNKNOWN • All 3 persisted exceptions have requires_ops_attention=true | 55 | 9.9-T12, 9.9-T13, 9.9-T16 | BE | SCH-06
9.9-T22 | scheme-adapter-zeropay | 9.9 | 9. QR Scheme Integration (ZeroPay) | Scheme status/reason code mapping | 2 | Document the ZeroPay status/reason code mapping: code-level Javadoc and mapping table reference | The mapping table (SCH-06 §10.1 and §10.2) is illustrative pending 한결원 official spec (Assumption A-10). The implementation must be easy to update when the confirmed code list arrives. This ticket adds code-level documentation so a maintainer can update the mapping table without reading the full spec: Javadoc on ZeroPayRealtimeCodeMappings explaining that ALL_MAPPINGS is the single source of truth and must be reconciled against the official 한결원 ZeroPay API and PPF spec before Phase 2 go-live; a NOTE comment on each enum constant in ZeroPaySchemeCode marking it as illustrative; and a FIXME/TODO linking to OI-SCH-01 (the open item for obtaining the KFTC PPF file spec). | • Add class-level Javadoc to ZeroPayRealtimeCodeMappings: state that entries are illustrative per SCH-06 Assumption A-10, and must be verified against 한결원 official spec (OI-SCH-01/OI-SCH-02) before Phase 2 launch • Add // ILLUSTRATIVE - verify against 한결원 spec before Phase 2 comment on each ZeroPaySchemeCode constant • Add a FIXME comment in ZeroPayBatchCodeMappings referencing OI-SCH-01 and Assumption A-10 • Add class-level Javadoc to ZeroPayBatchResultCode: note batch codes 9001/9002/9003 are from the ZP PPF interface spec which is pending (OI-SCH-01) • Add updateMapping(String zpCode, GmeApiErrorCode gmeCode, boolean includeRaw) method to ZeroPayRealtimeCodeMappings to support runtime config updates (so Ops can add a new code without redeploy - store overrides in DB, load at startup after static defaults) | Updated Javadoc and comments on ZeroPayRealtimeCodeMappings, ZeroPaySchemeCode, ZeroPayBatchResultCode, ZeroPayBatchCodeMappings; plus updateMapping() method | • ZeroPayRealtimeCodeMappings class-level Javadoc contains the text OI-SCH-01 and illustrative • Each ZeroPaySchemeCode constant (except UNKNOWN) has the ILLUSTRATIVE comment • updateMapping(8888, SCHEME_ERROR, true) adds an entry for 8888 that SchemeCodeMapper.mapRealtimeCode(8888) can then resolve to SCHEME_ERROR • ZeroPayBatchCodeMappings has a FIXME referencing OI-SCH-01 • No existing tests are broken by adding updateMapping (it adds to the map, does not replace existing entries if called with a duplicate - logs WARN instead) | 30 | 9.9-T05, 9.9-T06 | BE | SCH-06
9.10-T01 | scheme-adapter-zeropay | 9.10 | 9. QR Scheme Integration (ZeroPay) | 한결원/KFTC test env integration & cert | 2 | Obtain and store 한결원 UAT SFTP credentials and test-env parameters | WBS 9.10 gate: before any SFTP-based test can run, GMEPay+ must have 한결원 UAT SFTP credentials (host, port, username, RSA private key, inbound/outbound dirs) stored in the secrets manager. Per SCH-06 §2.3.1, GMEPay+ authenticates to 한결원 SFTP using SSH key (RSA-4096 or ECDSA P-256); the private key must never be stored in plaintext on disk. The scheme config record (scheme_id=ZEROPAY, environment=UAT) must reference the secrets-store key names, not the raw values. | • Receive UAT SFTP host, port, username, and private key from 한결원 (OI-SCH-03). • Store private key in the project secrets manager under key ref zeropay_uat_sftp_private_key. • Store PGP public key (한결원) under zeropay_uat_pgp_pub and GME PGP private key under zeropay_uat_pgp_priv. • Update the ZeroPay scheme config record (environment=UAT) with sftp_host, sftp_port, sftp_username, sftp_private_key_ref, pgp_public_key_ref, pgp_private_key_ref, inbound_dir=/gmepay/inbound/, outbound_dir=/gmepay/outbound/. • Confirm no plaintext credential is written to any config file or source-control artifact. | ZeroPay UAT scheme config record with all credential refs populated; secrets stored in secrets manager. | • SSH connection to 한결원 UAT SFTP host succeeds using the stored key ref (sftp-test CLI or equivalent). • Scheme config record retrieved via Admin API returns sftp_private_key_ref as an opaque ref string, not a key value. • Secrets manager holds exactly zeropay_uat_sftp_private_key, zeropay_uat_pgp_pub, zeropay_uat_pgp_priv with non-null values. • Source control contains zero plaintext credentials (git grep for BEGIN RSA, BEGIN PGP returns no hits in repo). | 45 |  | QA | SCH-06, PM-14
9.10-T02 | scheme-adapter-zeropay | 9.10 | 9. QR Scheme Integration (ZeroPay) | 한결원/KFTC test env integration & cert | 2 | Generate and register UAT SSH key pair with 한결원 | Per SCH-06 §2.3.1, GMEPay+ generates a per-environment RSA-4096 (or ECDSA P-256) SSH key pair. The public key must be registered with 한결원 for SFTP allow-listing. Key rotation policy: annually or on suspected compromise. The private key is stored in the secrets manager (ref zeropay_uat_sftp_private_key per T01). This ticket covers key generation, submission of the public key to 한결원, and confirmation of allow-listing. | • Generate RSA-4096 SSH key pair for UAT environment (ssh-keygen -t rsa -b 4096 or equivalent in secrets tooling). • Store private key in secrets manager under ref zeropay_uat_sftp_private_key (overwrites placeholder from T01 if needed). • Send public key to 한결원 account contact for SFTP allow-listing registration. • Await confirmation from 한결원 that the public key has been registered (email/ticket confirmation). • Document the key fingerprint and registration date in the ops runbook (OPS-13). | RSA-4096 SSH key pair registered with 한결원 UAT SFTP; private key in secrets manager; confirmation recorded. | • SFTP connection using the new key succeeds (ssh -i <key> sftp_username@sftp_host) without password prompt. • Private key is NOT present in any file on disk outside secrets manager after generation. • Key fingerprint in ops runbook matches fingerprint returned by ssh-keygen -l. • 한결원 confirmation artifact (email or ticket ref) is attached to this ticket. | 30 | 9.10-T01 | QA | SCH-06, PM-14
9.10-T03 | scheme-adapter-zeropay | 9.10 | 9. QR Scheme Integration (ZeroPay) | 한결원/KFTC test env integration & cert | 2 | Exchange PGP keys with 한결원 and configure file encryption for UAT | Per SCH-06 §2.3.2 (Assumption A-02): outbound batch files must be PGP-encrypted with 한결원's public key and signed with GME's private key; inbound files from 한결원 are encrypted with GME's public key. Keys are RSA-2048 minimum (preferably RSA-4096). All PGP operations are performed in-memory; no cleartext intermediate file is written to disk. Key refs zeropay_uat_pgp_pub (한결원 public key) and zeropay_uat_pgp_priv (GME private key) must be loaded in the ZeroPay Adapter's encryption module. | • Generate GME PGP key pair (RSA-4096) for UAT environment; store private key under zeropay_uat_pgp_priv in secrets manager. • Export GME PGP public key and send to 한결원 for inbound file encryption. • Receive 한결원 PGP public key; store under zeropay_uat_pgp_pub in secrets manager. • Update ZeroPay Adapter encryption config to load both key refs at startup. • Write a smoke test: encrypt a sample string with zeropay_uat_pgp_pub, then decrypt with zeropay_uat_pgp_priv and verify round-trip. | PGP key exchange complete; ZeroPay Adapter encryption module uses stored key refs; round-trip smoke test passes. | • Smoke test: PGP-encrypt 'HELLO' with 한결원 public key and sign with GME private key; decrypt and verify signature returns 'HELLO'. • Adapter startup logs show key refs resolved (not raw key material). • No PGP private key material present in any log line or config file. • Inbound test file from 한결원 (sample) successfully decrypted and signature verified using stored keys. | 40 | 9.10-T01 | QA | SCH-06, PM-14
9.10-T04 | scheme-adapter-zeropay | 9.10 | 9. QR Scheme Integration (ZeroPay) | 한결원/KFTC test env integration & cert | 2 | Verify SFTP connectivity and directory structure against 한결원 UAT server | Per SCH-06 §2.3.4 (Assumption A-04), the remote SFTP directory structure is /gmepay/outbound/ (GME places files) and /gmepay/inbound/ (ZeroPay places files). GMEPay+ connects outbound-only; no inbound SFTP port is opened. The SFTP client must verify transfer success by comparing file size/checksum after upload (SCH-06 §2.4). This ticket confirms connectivity, directory presence, and upload/download round-trip using the credentials established in T01-T02. | • Use the SFTP client module to connect to the 한결원 UAT SFTP host using the stored key ref. • List contents of /gmepay/outbound/ and /gmepay/inbound/ directories; confirm they exist and are accessible. • Upload a test file (test_connectivity_YYYYMMDD.txt) to /gmepay/outbound/. • Verify the transfer by comparing remote file size with local; log checksum. • Download a sample file from /gmepay/inbound/ (if 한결원 has placed one); verify size and checksum. • Record actual directory names if they differ from assumptions and update the scheme config. | Connectivity verification report documenting SFTP host, actual directory paths, and upload/download round-trip result. | • SFTP connect returns session established within 10 seconds. • Upload of test_connectivity file to /gmepay/outbound/ succeeds; remote size == local size. • checksum comparison (MD5 or SHA-256) of uploaded file matches local copy. • Scheme config inbound_dir and outbound_dir fields reflect actual confirmed directory paths. | 30 | 9.10-T02, 9.10-T03 | QA | SCH-06, PM-14
9.10-T05 | scheme-adapter-zeropay | 9.10 | 9. QR Scheme Integration (ZeroPay) | 한결원/KFTC test env integration & cert | 2 | Configure ZeroPay UAT scheme registry entry in Admin portal | Per SCH-06 §1.3.2, all scheme-specific parameters are held in the scheme config record managed via the Ops Admin portal. The scheme registry entry for ZeroPay UAT must include: scheme_id=ZEROPAY, operator_name=한결원, payout_currency=KRW, supported_modes=[MPM,CPM], supported_countries=[KR], realtime_api_base_url (한결원 test API URL), sftp connectivity refs from T01-T04, merchant_fee_table, van_fee_table, gme_fee_share_pct=70, file_retention_days=90. Adding a scheme is CONFIG only per the generic-build constraint (SCH-06 §11.3). | • Log into Admin portal as Ops Operator role. • Navigate to Scheme Management; create new scheme record with scheme_id=ZEROPAY, environment=UAT. • Enter all required fields per SCH-06 §1.3.2: operator_name, payout_currency=KRW, supported_modes, supported_countries=[KR], realtime_api_base_url from 한결원 test spec. • Enter merchant_fee_table (e.g. individual=0.80%, franchise=1.20%, cross-border=1.70%), van_fee_table, gme_fee_share_pct=70. • Enter SFTP params referencing secrets-store key names from T01; set file_retention_days=90. • Activate scheme status=ACTIVE; verify audit log captures actor, timestamp. | ZeroPay UAT scheme registry entry in Admin portal, status ACTIVE, all fields populated. | • GET scheme config API returns scheme_id=ZEROPAY with payout_currency=KRW, supported_modes=[MPM,CPM], gme_fee_share_pct=70. • Audit log entry created for scheme creation with correct actor and timestamp. • Scheme registry lists ZeroPay as ACTIVE. • Credential fields (sftp_private_key_ref, pgp_public_key_ref, pgp_private_key_ref) are returned as opaque refs, not plaintext values. | 30 | 9.10-T04 | QA | SCH-06, PM-14
9.10-T06 | scheme-adapter-zeropay | 9.10 | 9. QR Scheme Integration (ZeroPay) | 한결원/KFTC test env integration & cert | 2 | Seed test merchants and QR codes via ZP0051 full-list file from 한결원 UAT | Per SCH-06 §4, GMEPay+ maintains a local merchant and QR DB that is the sole source of truth for payment-time validation. For UAT, 한결원 provides test merchant data. ZP0051 is the periodic full merchant list (same field layout as ZP0041): merchant_id CHAR(10), merchant_name VARCHAR(100), business_reg_no CHAR(10), merchant_type_code CHAR(2), status_code CHAR(1) [A/S/T], address VARCHAR(200), bank_code CHAR(3), account_no VARCHAR(20), effective_date DATE(8), change_type CHAR(1) [I/U/D]. Processing: download -> validate checksum + record count -> load to staging -> diff -> atomic promote. QA-12 §3.2 defines required test merchants: M-TEST-0001 (Active), M-TEST-0002 (Inactive), M-TEST-0003 (Franchise-Active), M-TEST-0004 (CrossBorder-Active), M-TEST-0005 (Active, QR deactivated). | • Request ZP0051 test file from 한결원 UAT environment (or generate a synthetic ZP0051 file using QA-12 §3.2 merchant fixtures if 한결원 file not yet available). • PGP-decrypt the file using zeropay_uat_pgp_priv; verify 한결원 signature using zeropay_uat_pgp_pub. • Validate file header: record count and control total match body. • Load records into merchants_staging table; diff against live merchants table. • Atomically promote staging to live in a single DB transaction. • Log result: total count, inserts, updates, deactivations. | merchants table in UAT DB seeded with at least 5 test merchants (M-TEST-0001 through M-TEST-0005); full-sync log entry recorded. | • merchants table contains M-TEST-0001 with status=ACTIVE and M-TEST-0002 with status=INACTIVE after sync. • Record count in settlement_batch log entry matches ZP0051 file header control total. • Rollback test: if staging load is interrupted mid-way, live merchants table is unchanged (atomicity). • Duplicate-run idempotency: reprocessing the same ZP0051 file produces identical merchant table state without duplicate rows. | 45 | 9.10-T05 | QA | SCH-06, PM-14
9.10-T07 | scheme-adapter-zeropay | 9.10 | 9. QR Scheme Integration (ZeroPay) | 한결원/KFTC test env integration & cert | 2 | Seed test QR codes via ZP0053 full QR list from 한결원 UAT | Per SCH-06 §4.2 (ZP0053), the full QR list uses the same layout as ZP0043: qr_code_id CHAR(20), merchant_id CHAR(10), qr_type CHAR(1) [M=MPM static, C=CPM-capable], status_code CHAR(1) [A=Active, D=Deactivated], issue_date DATE(8), deactivation_date DATE(8), change_type CHAR(1) [I/D]. Processing follows staging/diff/atomic-promote pattern as ZP0051. Referential integrity check: every QR must have a valid, active merchant_id in the merchants table. QA-12 §3.2: QR-TEST-0001 (Active, merchant M-TEST-0001), QR-TEST-0005 (Deactivated, merchant M-TEST-0005). | • Request ZP0053 test file from 한결원 UAT or generate synthetic file using QA-12 QR fixtures. • PGP-decrypt and verify signature. • Validate file header checksum and record count. • Load into qr_codes_staging; run referential integrity check: every merchant_id must exist and be ACTIVE in merchants table. • Atomically promote to qr_codes live table. • Confirm QR-TEST-0005 has status=INACTIVE (deactivated) in the live qr_codes table. | qr_codes table seeded with QR-TEST-0001 through QR-TEST-0005; referential integrity verified. | • qr_codes table contains QR-TEST-0001 with status=ACTIVE linked to M-TEST-0001. • QR-TEST-0005 has status=INACTIVE; any payment attempt using QR-TEST-0005 is rejected with QR_DEACTIVATED at merchant resolution. • Referential integrity: no qr_codes row exists with a merchant_id absent from the merchants table. • Duplicate-run idempotency: reprocessing ZP0053 produces identical qr_codes table state. | 40 | 9.10-T06 | QA | SCH-06, PM-14
9.10-T08 | scheme-adapter-zeropay | 9.10 | 9. QR Scheme Integration (ZeroPay) | 한결원/KFTC test env integration & cert | 2 | Configure test partner rules for domestic (GME Remit) and inbound (SendMN) against ZeroPay UAT | Per SCH-06 §11.2 Step 4 and RATE-04 canonical facts: a Rule = (partner x scheme x direction). Domestic rule (P-TEST-001 TestRemit, LOCAL, KRW/KRW/KRW): same-currency short-circuit applies (collection=settle_A=settle_B=payout=KRW), m_a=0, m_b=0, service_charge=500 KRW flat, no prefunding. Inbound rule (P-TEST-002 TestSendMN, OVERSEAS, MNT/USD/KRW): cost_rate_coll=treasury.usd_mnt=3500.00, cost_rate_pay=treasury.usd_krw=1350.00, m_a=0.015 (1.5%), m_b=0.010 (1.0%), service_charge=500 MNT, prefunding required; combined margin 2.5% >= 2.0% minimum. Treasury test rates per QA-12 §3.3. | • In Admin portal, create rule for P-TEST-001 x ZEROPAY x Domestic: set currency sections (coll=KRW, settle_A=KRW, settle_B=KRW, payout=KRW), m_a=0, m_b=0, service_charge=500 KRW. • Create rule for P-TEST-002 x ZEROPAY x Inbound: currency sections (coll=MNT, settle_A=USD, settle_B=KRW, payout=KRW), m_a=0.015, m_b=0.010, service_charge=500 MNT. • Load treasury test rates: treasury.usd_krw=1350.00, treasury.usd_mnt=3500.00 via Admin FX rate management screen. • Seed P-TEST-002 prefunding balance=50000.00 USD in test DB per QA-12 §3.4. • Activate both rules; verify audit log entries created. | Two live rules in UAT: domestic (KRW short-circuit, zero margin) and inbound (MNT->KRW via USD, 2.5% margin); treasury rates and prefunding loaded. | • GET rule for P-TEST-001 x ZEROPAY x Domestic returns same_currency_short_circuit=true, m_a=0.000, m_b=0.000, service_charge=500 KRW. • GET rule for P-TEST-002 x ZEROPAY x Inbound returns m_a=0.015, m_b=0.010, service_charge=500 MNT. • Admin rejects attempt to save P-TEST-002 rule with m_a=0.010, m_b=0.009 (combined 1.9% < 2.0% minimum) with validation error. • treasury.usd_krw=1350.00 and treasury.usd_mnt=3500.00 returned by GET /v1/rates test call. | 40 | 9.10-T05 | QA | SCH-06, PM-14
9.10-T09 | scheme-adapter-zeropay | 9.10 | 9. QR Scheme Integration (ZeroPay) | 한결원/KFTC test env integration & cert | 2 | Execute end-to-end MPM domestic test payment against 한결원 ZeroPay test API | MPM = merchant presents static QR; customer scans and enters amount. Flow: (1) partner GET /v1/rates with scheme_id=zeropay, direction=domestic, target_payout=13500 KRW; (2) partner POST /v1/payments with quote_id, merchant_qr=QR-TEST-0001; (3) ZeroPay Adapter calls 한결원 real-time API to commit; (4) transaction reaches APPROVED; (5) payment.approved webhook delivered. Domestic short-circuit: collection_amount = 13500 + 500 = 14000 KRW, no USD pool. Per QA-12 HC-001 and RV-04 (same-currency: USD pool skipped, collection_amount = target_payout + service_charge). | • Call POST /v1/rates as P-TEST-001 with target_payout=13500, payout_currency=KRW, scheme_id=zeropay, direction=domestic, merchant_qr=QR-TEST-0001. • Verify response: collection_amount=14000 KRW, no payout_usd_cost field, validUntil set. • Call POST /v1/payments with quote_id, merchant_qr=QR-TEST-0001, Idempotency-Key=<uuid>. • Verify ZeroPay Adapter transmits commit to 한결원 test API and receives approval code. • Verify transaction status=APPROVED and payment.approved webhook is fired. • Verify no prefunding deduction occurred (P-TEST-001 is LOCAL). | One end-to-end MPM domestic transaction APPROVED on 한결원 ZeroPay test environment; event trail recorded. | • POST /v1/rates response: collection_amount=14000 KRW (=13500+500), no payout_usd_cost or collection_usd fields (short-circuit). • Transaction status=APPROVED in DB with zeropay_txn_ref populated from 한결원 real-time response. • 8-step event trail in Admin portal shows SCHEME_SENT and SCHEME_APPROVED events with timestamps. • No prefunding deduction event for P-TEST-001 in prefunding ledger. • Idempotency: replaying same POST /v1/payments with same Idempotency-Key returns same txn_ref; no second scheme call. | 50 | 9.10-T07, 9.10-T08 | QA | SCH-06, PM-14
9.10-T10 | scheme-adapter-zeropay | 9.10 | 9. QR Scheme Integration (ZeroPay) | 한결원/KFTC test env integration & cert | 2 | Execute end-to-end MPM inbound test payment (MNT->KRW) against 한결원 ZeroPay test API | Inbound OVERSEAS flow: P-TEST-002 (TestSendMN, MNT, prefunding USD). Rate engine 5-step RECEIVE mode: cost_rate_pay=treasury.usd_krw=1350.00, cost_rate_coll=treasury.usd_mnt=3500.00, m_a=0.015, m_b=0.010, service_charge=500 MNT, target_payout=13500 KRW. Expected per QA-12 RV-01: payout_usd_cost=10.0000 USD, collection_usd=10.2564 USD, send_amount=35897.44 MNT, collection_amount=36397.44 MNT. Prefunding deducted atomically (SELECT FOR UPDATE) at POST /v1/payments before scheme call. Pool identity: 10.2564 - 0.1538 - 0.1026 = 10.0000 (tolerance <= 0.01 USD). | • Call POST /v1/rates as P-TEST-002: target_payout=13500, payout_currency=KRW, scheme_id=zeropay, direction=inbound. • Verify response fields: payout_usd_cost=10.0000, collection_usd=10.2564, send_amount=35897.44, collection_amount=36397.44 MNT (all within 0.01 of expected). • Call POST /v1/payments with quote_id and merchant_qr=QR-TEST-0001. • Verify prefunding balance for P-TEST-002 is reduced by collection_usd=10.2564 USD before scheme call is made. • Verify transaction reaches APPROVED; payment.approved webhook fired. • Verify pool identity assertion: ¦collection_usd - collection_margin_usd - payout_margin_usd - payout_usd_cost¦ <= 0.01 USD passes. | One end-to-end MPM inbound transaction APPROVED on 한결원 ZeroPay test environment; prefunding deducted atomically; all RV-01 values match. | • collection_amount=36397.44 MNT (+/-0.01 tolerance) in rate quote response. • Prefunding ledger for P-TEST-002 shows debit of 10.2564 USD with timestamp preceding SCHEME_SENT event. • Pool identity assertion: ¦10.2564 - 0.1538 - 0.1026 - 10.0000¦ <= 0.01 USD. • Transaction record stores cost_rate_pay=1350.00, cost_rate_coll=3500.00, m_a=0.015, m_b=0.010 permanently (rate-lock). • offer_rate_coll derived correctly: 35897.44 / (10.2564 - 0.1538) = 35897.44 / 10.1026 = ~3553 MNT/USD (+/-1 unit). | 50 | 9.10-T08, 9.10-T09 | QA | SCH-06, PM-14
9.10-T11 | scheme-adapter-zeropay | 9.10 | 9. QR Scheme Integration (ZeroPay) | 한결원/KFTC test env integration & cert | 2 | Execute end-to-end CPM test payment (domestic and inbound) against 한결원 ZeroPay test API | CPM = customer shows dynamic QR; merchant POS scans. Flow: partner POST /v1/payments/cpm/generate -> ZeroPay Adapter calls 한결원 real-time API to get a one-time token (expires default 60s) -> token returned to partner -> merchant scans -> 한결원 relays approval request to ZeroPay Adapter -> commit. For OVERSEAS (P-TEST-002): prefunding deducted at /cpm/generate step, BEFORE merchant scans. For LOCAL (P-TEST-001): no prefunding. Per SCH-06 §3.3 and QA-12 HC-002, HC-004. | • CPM domestic: POST /v1/payments/cpm/generate as P-TEST-001; verify CPM token returned; simulate merchant scan via 한결원 test env POS emulator; verify payment.approved. • CPM inbound: POST /v1/payments/cpm/generate as P-TEST-002 with target_payout=13500 KRW; verify prefunding deducted at generate-time; simulate merchant scan; verify payment.approved. • Verify CPM token TTL: attempt to commit after 60 seconds; expect QR_EXPIRED error from 한결원. • Verify CPM token is one-time-use: attempt second commit with same token after first approval; expect rejection. • Confirm both CPM transactions appear in the transaction table with mode=CPM. | Two end-to-end CPM transactions APPROVED (one domestic, one inbound); prefunding deduction timing verified; TTL and one-time-use edge cases confirmed. | • P-TEST-002 prefunding deduction timestamp is earlier than SCHEME_SENT event timestamp in event trail. • P-TEST-001 CPM transaction APPROVED with no prefunding deduction event. • Expired CPM token (>60s) results in QR_EXPIRED error; no prefunding deducted on the attempt. • Second commit with same CPM token returns DUPLICATE_TRANSACTION or scheme rejection; no double-deduction of prefunding. • Both transactions have mode=CPM in transaction table. | 55 | 9.10-T10 | QA | SCH-06, PM-14
9.10-T12 | scheme-adapter-zeropay | 9.10 | 9. QR Scheme Integration (ZeroPay) | 한결원/KFTC test env integration & cert | 2 | Test same-day payment cancel (real-time) against 한결원 ZeroPay test API | Per SCH-06 §2.2, same-day cancels are processed via ZeroPay real-time API (cancelPayment(scheme_txn_ref)). Per QA-12 HC-007: POST /v1/payments/{id}/cancel within same day -> transaction status=CANCELLED; for OVERSEAS partners, prefunding balance restored. The cancel is NOT included in ZP0021 (refund batch) -- that is only for post-day refunds. Admin-portal refunds (post-day) are out of scope for this ticket. | • Create a fresh APPROVED MPM transaction for P-TEST-002 (inbound) with target_payout=13500 KRW; record txn_id and prefunding balance after deduction. • Call POST /v1/payments/{txn_id}/cancel within same business day KST. • Verify ZeroPay Adapter calls cancelPayment on 한결원 real-time API with scheme_txn_ref. • Verify transaction status=CANCELLED in DB. • Verify prefunding balance for P-TEST-002 is restored by collection_usd amount. • Attempt cancel on already-CANCELLED transaction; verify 422 error response. | Same-day cancel flow verified against 한결원 UAT; prefunding restored; double-cancel rejected. | • Transaction status transitions from APPROVED to CANCELLED; event trail shows CANCEL_SENT and CANCEL_CONFIRMED events. • Prefunding balance after cancel = balance before original payment (restored to within 0.01 USD). • POST /v1/payments/{id}/cancel on already-CANCELLED transaction returns HTTP 422 with appropriate error code. • Cancelled transaction NOT included in subsequent ZP0011 batch file generated for the same business date. | 45 | 9.10-T11 | QA | SCH-06, PM-14
9.10-T13 | scheme-adapter-zeropay | 9.10 | 9. QR Scheme Integration (ZeroPay) | 한결원/KFTC test env integration & cert | 2 | Test insufficient-prefunding rejection path for OVERSEAS partner | Per RATE-04 canonical facts and QA-12 HC-009: if OVERSEAS partner balance < collection_usd at payment time, system must reject with INSUFFICIENT_PREFUNDING before any scheme call. Deduction is atomic (SELECT FOR UPDATE). Balance is set to 0.00 USD in test DB per QA-12 §3.4 (P-TEST-002 Depleted fixture). Scheme must NEVER be called when balance is insufficient. For CPM, rejection happens at POST /v1/payments/cpm/generate. Low-balance alert: balance falls below partner threshold -> email alert fired (HC-010, QA-12 §3.4 Low fixture = 9500.00 USD). | • Set P-TEST-002 prefunding balance to 0.00 USD in test DB. • Attempt POST /v1/payments (MPM) as P-TEST-002 with target_payout=13500 KRW. • Verify INSUFFICIENT_PREFUNDING error returned (HTTP 422); verify zero scheme calls made. • Set P-TEST-002 balance to 9500.00 USD (low-balance fixture); make a payment that causes balance to drop below threshold. • Verify low-balance alert email is dispatched to partner contact. • Verify the low-balance payment itself succeeds (alert does not block transaction). | Insufficient-prefunding rejection and low-balance alert paths verified; no scheme call on zero-balance. | • POST /v1/payments with balance=0.00 USD returns HTTP 422 INSUFFICIENT_PREFUNDING; ZeroPay Adapter call count = 0 for this attempt. • Prefunding ledger shows no deduction entry for the rejected payment attempt. • Low-balance alert email sent when balance falls below configured threshold (9500 USD test fixture); transaction still APPROVED. • Concurrent-safety test: two simultaneous payments against a balance of 10.2564 USD (exactly one collection_usd); only one succeeds; the other returns INSUFFICIENT_PREFUNDING. | 45 | 9.10-T10 | QA | SCH-06, PM-14
9.10-T14 | scheme-adapter-zeropay | 9.10 | 9. QR Scheme Integration (ZeroPay) | 한결원/KFTC test env integration & cert | 2 | Test merchant and QR validation edge cases against local DB | Per SCH-06 §3.5: merchant validation uses local DB only (no live ZeroPay API call at payment time). Failure cases: (1) merchant status != ACTIVE -> MERCHANT_INACTIVE (QA-12 HC-011, M-TEST-0002); (2) QR status != ACTIVE -> QR_DEACTIVATED (QA-12 HC-012, QR-TEST-0005); (3) QR merchant_id does not match resolved merchant_id -> QR_MALFORMED; (4) merchant absent from DB -> MERCHANT_NOT_FOUND. Error code mapping per SCH-06 §10.2. | • Attempt POST /v1/payments with merchant_qr=QR-TEST-0002 (M-TEST-0002, Inactive merchant); expect MERCHANT_INACTIVE. • Attempt POST /v1/payments with merchant_qr=QR-TEST-0005 (QR status=INACTIVE); expect QR_DEACTIVATED. • Attempt POST /v1/payments with a merchant_id that does not exist in the local merchants table; expect MERCHANT_NOT_FOUND. • Attempt POST /v1/payments with a QR code whose merchant_id does not match the merchant_id in the payment request; expect QR_MALFORMED. • For each rejection, verify no scheme call is made and no prefunding deduction occurs. | All four merchant/QR validation error paths return correct error codes with zero scheme calls and zero prefunding impact. | • QR-TEST-0002 payment returns MERCHANT_INACTIVE (HTTP 422); ZeroPay adapter call count = 0. • QR-TEST-0005 payment returns QR_DEACTIVATED (HTTP 422); ZeroPay adapter call count = 0. • Unknown merchant_id returns MERCHANT_NOT_FOUND (HTTP 422). • Mismatched QR-to-merchant returns QR_MALFORMED (HTTP 422). | 40 | 9.10-T07, 9.10-T08 | QA | SCH-06, PM-14
9.10-T15 | scheme-adapter-zeropay | 9.10 | 9. QR Scheme Integration (ZeroPay) | 한결원/KFTC test env integration & cert | 2 | Test EMVCo QR parse error paths (checksum, malformed, currency mismatch) | Per SCH-06 §3.4: parseMerchantQR must verify CRC-16/CCITT in tag 63, confirm tag 00=01 (EMVCo format indicator), extract tag 53 (currency, must be 410 for KRW), locate ZeroPay MAI slot in tags 26-51. Parse errors must be categorised: QR_INVALID_CHECKSUM (CRC mismatch), QR_MALFORMED (missing mandatory tag), QR_CURRENCY_MISMATCH (currency != 410 KRW), QR_UNKNOWN_SCHEME (unknown MAI slot). All parse failures must be rejected before merchant DB lookup; no scheme call. | • Craft a QR payload with an invalid CRC-16/CCITT checksum in tag 63; call GET /v1/merchants/{qr} or POST /v1/payments; expect QR_INVALID_CHECKSUM. • Craft a QR payload missing mandatory tag 52 (MCC); expect QR_MALFORMED. • Craft a QR payload with tag 53=840 (USD, not KRW 410); expect QR_CURRENCY_MISMATCH. • Craft a QR payload with an MAI slot not matching the ZeroPay registered range; expect QR_UNKNOWN_SCHEME. • Verify all four errors are returned as HTTP 422 with correct error codes per SCH-06 §10.2 mapping. | QR parse error handler unit/integration test covering all 4 parse failure codes; all return HTTP 422. | • Invalid CRC payload returns QR_INVALID_CHECKSUM (HTTP 422); no DB lookup performed. • Missing tag 52 payload returns QR_MALFORMED (HTTP 422). • Tag 53=840 (USD) payload returns QR_CURRENCY_MISMATCH (HTTP 422). • Unknown MAI slot returns QR_UNKNOWN_SCHEME (HTTP 422); no scheme call attempted. | 40 | 9.10-T07 | QA | SCH-06, PM-14
9.10-T16 | scheme-adapter-zeropay | 9.10 | 9. QR Scheme Integration (ZeroPay) | 한결원/KFTC test env integration & cert | 2 | Generate and transmit ZP0011 payment result file to 한결원 UAT SFTP | Per SCH-06 §5.2: ZP0011 is the daily payment result file (GME->ZeroPay), deadline ~02:00 KST. Scope: all transactions in status APPROVED for the prior business day not yet registered. Record layout (illustrative per A-11): record_type CHAR(1)=D, gme_txn_id CHAR(20), zeropay_txn_ref CHAR(20), merchant_id CHAR(10), qr_code_id CHAR(20), txn_date DATE(8) YYYYMMDD KST, txn_time TIME(6) HHMMSS KST, payout_amount_krw NUM(12), merchant_fee_amt NUM(12), van_fee_amt NUM(10), partner_type CHAR(1) [D=Domestic, I=International], approval_code CHAR(12), status_code CHAR(1)=A. File header: file_type=ZP0011, business_date, GME institution code, record_count, total_payout_amount_krw. Filename: ZP0011_{YYYYMMDD}_01.dat.pgp. PGP-encrypt with 한결원 public key; sign with GME private key. | • Trigger the ZP0011 batch job for the test business date (covering transactions from T09 and T10). • Verify file content: header record_count matches detail record count; trailer control_sum = sum of payout_amount_krw. • PGP-encrypt file with zeropay_uat_pgp_pub; sign with zeropay_uat_pgp_priv; write to /gmepay/outbound/ZP0011_{YYYYMMDD}_01.dat.pgp. • Verify SFTP upload success: compare remote file size with local; log checksum. • Verify all included transactions have partner_type=D for P-TEST-001 records and partner_type=I for P-TEST-002 records. • Confirm transactions already registered in a prior batch are excluded. | ZP0011 file for test business date successfully transmitted to 한결원 UAT SFTP /gmepay/outbound/; settlement_batch log entry created. | • File header record_count equals the number of detail records in the file body. • Trailer control_sum = sum of all payout_amount_krw values; matches header total_payout_amount_krw. • SFTP remote file size matches local encrypted file size. • settlement_batch table row: file_type=ZP0011, status=TRANSMITTED, checksum populated, transmitted_at timestamp set. • Cancelled transactions (from T12) are NOT included in ZP0011. | 50 | 9.10-T12, 9.10-T13 | QA | SCH-06, PM-14
9.10-T17 | scheme-adapter-zeropay | 9.10 | 9. QR Scheme Integration (ZeroPay) | 한결원/KFTC test env integration & cert | 2 | Receive and process ZP0012 payment registration result from 한결원 UAT | Per SCH-06 §5.3: ZP0012 is ZeroPay's registration confirmation, expected by ~05:00 KST. Record layout: zeropay_txn_ref CHAR(20), gme_txn_id CHAR(20), merchant_id CHAR(10), txn_date DATE(8), result_code CHAR(2) [00=Success], result_message VARCHAR(100), registered_amount NUM(12), settlement_date DATE(8). Mismatch handling per §5.4: result_code=00 and amounts match -> SETTLEMENT_REGISTERED; non-zero result_code -> REGISTRATION_FAILED; record in ZP0011 absent from ZP0012 -> REGISTRATION_UNKNOWN; amount discrepancy -> REGISTRATION_AMOUNT_MISMATCH. Zero-tolerance: every record must match. | • Poll /gmepay/inbound/ on 한결원 UAT SFTP for ZP0012_{YYYYMMDD}_01.dat.pgp. • PGP-decrypt using zeropay_uat_pgp_priv; verify 한결원 signature using zeropay_uat_pgp_pub. • Parse ZP0012 records; perform line-by-line match against ZP0011 using zeropay_txn_ref+txn_date as key. • Verify all result_code=00 records update transaction status to SETTLEMENT_REGISTERED. • Simulate a non-zero result_code record: verify REGISTRATION_FAILED status set and exception record created in Ops queue. • Simulate a ZP0011 record absent from ZP0012: verify REGISTRATION_UNKNOWN status and exception raised. | ZP0012 inbound file parsed and reconciled; all test transactions reach SETTLEMENT_REGISTERED; exception paths verified. | • All transactions with result_code=00 have status=SETTLEMENT_REGISTERED in DB after processing. • A simulated result_code=9001 record creates an exception in the Ops exception queue with priority P1. • A ZP0011 record absent from ZP0012 creates a REGISTRATION_UNKNOWN exception. • settlement_batch table updated: file_type=ZP0012, status=PROCESSED, record_count matches file header. • UNCERTAIN transactions (from any test timed-out scenario) are resolved to APPROVED or FAILED based on ZP0012 result_code. | 50 | 9.10-T16 | QA | SCH-06, PM-14
9.10-T18 | scheme-adapter-zeropay | 9.10 | 9. QR Scheme Integration (ZeroPay) | 한결원/KFTC test env integration & cert | 2 | Generate and transmit ZP0021 refund result file to 한결원 UAT SFTP | Per SCH-06 §6.2: ZP0021 covers admin-portal-initiated refunds (post-day only; same-day cancels via real-time API are excluded). Deadline ~02:00 KST. Record layout: record_type=D, gme_refund_id CHAR(20), original_zeropay_txn_ref CHAR(20), gme_original_txn_id CHAR(20), merchant_id CHAR(10), refund_date DATE(8), refund_time TIME(6), refund_amount_krw NUM(12), merchant_fee_adj_amt NUM(12), partner_type CHAR(1), refund_reason_code CHAR(2), status_code=R. File header/trailer same pattern as ZP0011. Same-day cancels (T12) must NOT appear in ZP0021. | • Via Admin portal, initiate a post-day refund for one of the T09/T10 test transactions; verify refund record created with status=REFUNDED. • Trigger ZP0021 batch job for the refund business date. • Verify file excludes same-day cancels (T12 transaction must not be present). • PGP-encrypt and transmit to /gmepay/outbound/ZP0021_{YYYYMMDD}_01.dat.pgp. • Verify SFTP upload checksum matches. • Confirm the refund record uses original_zeropay_txn_ref matching the original ZP0011 zeropay_txn_ref. | ZP0021 file transmitted for test refund; same-day cancel excluded; original_zeropay_txn_ref cross-reference correct. | • ZP0021 file contains the admin-initiated refund record with status_code=R and correct original_zeropay_txn_ref. • Same-day cancelled transaction (T12) is absent from ZP0021. • File header record_count equals number of detail records; trailer control_sum = sum of refund_amount_krw. • settlement_batch row: file_type=ZP0021, status=TRANSMITTED. | 45 | 9.10-T17 | QA | SCH-06, PM-14
9.10-T19 | scheme-adapter-zeropay | 9.10 | 9. QR Scheme Integration (ZeroPay) | 한결원/KFTC test env integration & cert | 2 | Receive and process ZP0022 refund registration result from 한결원 UAT | Per SCH-06 §6.3: ZP0022 mirrors ZP0012 for refunds. Match key: original_zeropay_txn_ref + refund_date. Fields: original_zeropay_txn_ref CHAR(20), gme_refund_id CHAR(20), result_code CHAR(2) [00=Success], result_message VARCHAR(100), registered_refund_amount NUM(12), adjustment_settlement_date DATE(8). Mismatch handling identical to §5.4 (REGISTRATION_FAILED, REGISTRATION_UNKNOWN, REGISTRATION_AMOUNT_MISMATCH). An unresolved refund registration failure blocking settlement is a P1 ops incident per §6.4. | • Poll /gmepay/inbound/ for ZP0022_{YYYYMMDD}_01.dat.pgp; PGP-decrypt and verify signature. • Parse and line-by-line match against ZP0021 using original_zeropay_txn_ref+refund_date. • Verify result_code=00 sets refund transaction status=SETTLEMENT_REGISTERED. • Simulate result_code=9001 (failure) and verify REGISTRATION_FAILED exception raised with P1 priority. • Verify the adjustment_settlement_date is stored on the refund record. | ZP0022 processed; refund transactions reach SETTLEMENT_REGISTERED; exception path for failure codes verified. | • Refund transaction status=SETTLEMENT_REGISTERED after result_code=00 processing. • Simulated result_code=9001 creates P1 exception in Ops queue; settlement for affected refund is blocked. • registered_refund_amount in ZP0022 matches refund_amount_krw in ZP0021 for successful records. • settlement_batch row: file_type=ZP0022, status=PROCESSED. | 40 | 9.10-T18 | QA | SCH-06, PM-14
9.10-T20 | scheme-adapter-zeropay | 9.10 | 9. QR Scheme Integration (ZeroPay) | 한결원/KFTC test env integration & cert | 2 | Generate and transmit ZP0061 morning settlement request to 한결원 UAT SFTP | Per SCH-06 §7.2 and §8.2: ZP0061 is the primary morning settlement request, deadline ~05:00 KST. Prerequisites (dependency chain): ZP0011 success AND ZP0012 received (result_code=00 for all records). Scope: settlement totals for all transactions in SETTLEMENT_REGISTERED status for the prior business day. Record layout: merchant_id CHAR(10), settlement_date DATE(8), gross_txn_count NUM(6), gross_txn_amount NUM(14), refund_count NUM(6), refund_amount NUM(14), merchant_fee_total NUM(12), net_settlement_amount NUM(14), settlement_type CHAR(1) [N=Net domestic, G=Gross international]. Net settlement (domestic): GME deducts fee share, remits remainder. Gross settlement (international): GME remits full payout_amount_krw. | • Confirm prerequisites: ZP0011 and ZP0012 both have status=PROCESSED in settlement_batch table. • Trigger ZP0061 generation; verify net settlement for domestic records (P-TEST-001): net_settlement_amount = gross_txn_amount - merchant_fee_total. • Verify gross settlement for international records (P-TEST-002): net_settlement_amount = gross_txn_amount (full payout, no deduction). • PGP-encrypt and transmit to /gmepay/outbound/ZP0061_{YYYYMMDD}_01.dat.pgp; verify SFTP checksum. • Confirm the batch job does NOT run if ZP0011 or ZP0012 prerequisites are not met. | ZP0061 transmitted to 한결원 UAT; net vs gross settlement logic verified; prerequisite gate enforced. | • Domestic merchant record: settlement_type=N; net_settlement_amount = gross_txn_amount - merchant_fee_total (verified by formula). • International merchant record: settlement_type=G; net_settlement_amount = gross_txn_amount (no fee deduction in file). • ZP0061 generation is blocked (batch job status=WAITING) when ZP0012 is not yet processed. • settlement_batch row: file_type=ZP0061, status=TRANSMITTED; checksum matches local file. | 50 | 9.10-T19 | QA | SCH-06, PM-14
9.10-T21 | scheme-adapter-zeropay | 9.10 | 9. QR Scheme Integration (ZeroPay) | 한결원/KFTC test env integration & cert | 2 | Receive and reconcile ZP0062 morning settlement result from 한결원 UAT | Per SCH-06 §7.2 and §9.1: ZP0062 confirms ZeroPay's processing of ZP0061, expected ~10:00 KST. Per reconciliation rules: settlement reconciliation tolerance = zero (every merchant total must match). Status codes per §10.3: SETTLEMENT_CONFIRMED (amounts match), SETTLEMENT_DISCREPANCY (amounts differ). Discrepancy auto-detection must alert GME Ops within 15 minutes of batch receipt (PRD-07 G-5). | • Poll /gmepay/inbound/ for ZP0062_{YYYYMMDD}_01.dat.pgp; PGP-decrypt and verify signature. • Parse ZP0062 records; reconcile per-merchant amounts against ZP0061 submitted values. • Update settlement_batch status and per-transaction settlement status to SETTLEMENT_CONFIRMED where amounts match. • Simulate a settlement discrepancy (ZP0062 merchant amount differs by 1 KRW from ZP0061): verify SETTLEMENT_DISCREPANCY status and exception raised. • Verify Ops alert is generated within 15 minutes of file receipt when discrepancy detected. | ZP0062 reconciled; SETTLEMENT_CONFIRMED set for matching records; discrepancy path triggers P1 exception and Ops alert. | • Per-merchant amounts in ZP0062 matching ZP0061 set transaction status=SETTLEMENT_CONFIRMED. • Simulated 1-KRW discrepancy creates SETTLEMENT_DISCREPANCY exception in Ops queue. • Ops alert (email or dashboard notification) triggered within 15 minutes of ZP0062 file receipt when discrepancy found. • settlement_batch row: file_type=ZP0062, status=PROCESSED. | 45 | 9.10-T20 | QA | SCH-06, PM-14
9.10-T22 | scheme-adapter-zeropay | 9.10 | 9. QR Scheme Integration (ZeroPay) | 한결원/KFTC test env integration & cert | 2 | Generate and transmit ZP0063 afternoon settlement request and process ZP0064 result | Per SCH-06 §7.2 (Assumption A-08): ZP0063 covers transactions approved after the ZP0061 cutoff but needing same-day merchant crediting, deadline ~14:00 KST. ZP0064 (afternoon settlement result) expected ~19:00 KST. Same structure as ZP0061/ZP0062 pair. Dependency per §8.2: ZP0063 depends on morning cycle complete. The test scenario creates a supplementary transaction after the ZP0061 cutoff window. | • Create an additional test transaction after the ZP0061 cutoff timestamp; confirm it is excluded from ZP0061. • Trigger ZP0063 generation for the afternoon cycle; verify it includes only the post-cutoff transaction. • PGP-encrypt and transmit ZP0063 to /gmepay/outbound/ZP0063_{YYYYMMDD}_01.dat.pgp. • Poll and process ZP0064 from /gmepay/inbound/; verify per-merchant reconciliation matches ZP0063. • Verify ZP0064 receipt sets affected transaction status to SETTLEMENT_CONFIRMED. | ZP0063 transmitted and ZP0064 received/reconciled; afternoon settlement cycle complete in 한결원 UAT. | • ZP0063 contains only transactions with approval timestamps after the ZP0061 cutoff; ZP0061 transaction is not duplicated. • ZP0064 reconciliation: amounts match ZP0063 submission; SETTLEMENT_CONFIRMED set. • settlement_batch rows for ZP0063 and ZP0064 both have status=PROCESSED. • ZP0063 generation is blocked (WAITING) if morning ZP0062 receipt has not been processed. | 45 | 9.10-T21 | QA | SCH-06, PM-14
9.10-T23 | scheme-adapter-zeropay | 9.10 | 9. QR Scheme Integration (ZeroPay) | 한결원/KFTC test env integration & cert | 2 | Generate and transmit ZP0065 payment detail and ZP0066 refund detail files | Per SCH-06 §7.2: ZP0065 (payment detail, deadline ~22:00 KST) provides transaction-level detail underlying ZP0061/ZP0063 totals. ZP0066 (refund detail) mirrors ZP0065 for refunds. Record layout ZP0065: merchant_id CHAR(10), zeropay_txn_ref CHAR(20), txn_date DATE(8), txn_time TIME(6), payout_amount_krw NUM(12), merchant_fee_amt NUM(12), van_fee_amt NUM(10), partner_type CHAR(1), settlement_batch_ref CHAR(20) (link to ZP0061/ZP0063). ZP0066: merchant_id, original_zeropay_txn_ref CHAR(20), refund_date DATE(8), refund_amount_krw NUM(12), merchant_fee_adj_amt NUM(12), settlement_batch_ref CHAR(20). Detail reconciliation per §9.1: zero-tolerance, every line must match internal ledger. | • Trigger ZP0065 generation; verify each detail record maps to a transaction in SETTLEMENT_CONFIRMED status; settlement_batch_ref links back to ZP0061 or ZP0063 batch row. • Trigger ZP0066 generation; verify each refund detail record links to ZP0021 gme_refund_id. • PGP-encrypt and transmit both files by 22:00 KST. • Run internal detail reconciliation: sum of ZP0065 payout_amount_krw per merchant must equal the gross_txn_amount in ZP0061/ZP0063 for that merchant. • Verify ZP0066 refund totals reconcile against ZP0021 submitted amounts. | ZP0065 and ZP0066 transmitted; line-item reconciliation against internal ledger passes with zero discrepancies. | • Sum of ZP0065 payout_amount_krw per merchant_id = gross_txn_amount in ZP0061 for that merchant (zero discrepancy). • Each ZP0065 record has settlement_batch_ref matching a ZP0061 or ZP0063 batch row in settlement_batch table. • ZP0066 record count = count of admin-initiated refunds in ZP0021; refund amounts match. • settlement_batch rows for ZP0065 and ZP0066: status=TRANSMITTED, transmitted_at within 22:00 KST deadline. | 50 | 9.10-T22 | QA | SCH-06, PM-14
9.10-T24 | scheme-adapter-zeropay | 9.10 | 9. QR Scheme Integration (ZeroPay) | 한결원/KFTC test env integration & cert | 2 | Test delta merchant sync via ZP0041 incremental file from 한결원 UAT | Per SCH-06 §4.2 (ZP0041): daily delta file, direction ZeroPay->GME, arriving 01:00-06:00 KST. Fields: merchant_id CHAR(10), merchant_name VARCHAR(100), business_reg_no CHAR(10), merchant_type_code CHAR(2), status_code CHAR(1) [A/S/T], address VARCHAR(200), bank_code CHAR(3), account_no VARCHAR(20), effective_date DATE(8), change_type CHAR(1) [I=Insert, U=Update, D=Deactivate]. GME handling: upsert into merchants table keyed on merchant_id; D records set status=INACTIVE. Deactivated merchants must be blocked at payment time immediately. Idempotency: reprocessing same file must not create duplicates. | • Request or generate a ZP0041 test file with: one new merchant (change_type=I), one update to M-TEST-0001 merchant_name (change_type=U), one deactivation of M-TEST-0003 (change_type=D). • PGP-decrypt and process via delta sync job. • Verify new merchant inserted; M-TEST-0001 name updated; M-TEST-0003 status=INACTIVE. • Attempt payment using M-TEST-0003 QR; expect MERCHANT_INACTIVE rejection. • Reprocess same ZP0041 file; verify no duplicate rows and merchant table state is unchanged. | ZP0041 delta sync processing verified: insert, update, and deactivation change types all processed correctly; immediate deactivation enforced. | • New merchant from ZP0041 I-record exists in merchants table with correct fields. • M-TEST-0001 merchant_name updated to value in ZP0041 U-record. • M-TEST-0003 status=INACTIVE after D-record processed; payment attempt returns MERCHANT_INACTIVE. • Re-running ZP0041 produces identical merchant table state (idempotency); no duplicate rows. | 40 | 9.10-T06 | QA | SCH-06, PM-14
9.10-T25 | scheme-adapter-zeropay | 9.10 | 9. QR Scheme Integration (ZeroPay) | 한결원/KFTC test env integration & cert | 2 | Test delta QR sync and intraday deactivation via ZP0043 from 한결원 UAT | Per SCH-06 §4.2 (ZP0043): daily QR delta file. Fields: qr_code_id CHAR(20), merchant_id CHAR(10), qr_type CHAR(1) [M/C], status_code CHAR(1) [A/D], issue_date DATE(8), deactivation_date DATE(8), change_type CHAR(1) [I/D]. GME handling: upsert into qr_codes table; deactivated QR codes must be blocked immediately after DB update. Per Assumption A-07: QR deactivated after day's file has been delivered will not reflect until next day's batch; Ops manual override required (PRD-07). Reconciliation: after applying delta, compare record count against file header. | • Request or generate ZP0043 test file with: one new QR registration (change_type=I) and one deactivation of QR-TEST-0001 (change_type=D). • Process ZP0043 via delta sync job; verify new QR inserted and QR-TEST-0001 status=INACTIVE. • Attempt payment using QR-TEST-0001; verify QR_DEACTIVATED error returned immediately. • Test Ops manual override: via Admin portal, force-deactivate a QR code (QR-TEST-0004) outside of batch cycle; verify payment blocked immediately. • Reprocess ZP0043; verify idempotency. | ZP0043 delta sync processes new and deactivated QR codes; payment blocked immediately on deactivation; Ops manual override functional. | • QR-TEST-0001 status=INACTIVE after ZP0043 D-record processed; payment returns QR_DEACTIVATED. • New QR from ZP0043 I-record is ACTIVE and usable in a test payment. • Admin portal manual deactivation of QR-TEST-0004 blocks payment within the same request cycle (no cache delay). • Re-running ZP0043 is idempotent; qr_codes table unchanged. | 40 | 9.10-T07, 9.10-T14 | QA | SCH-06, PM-14
9.10-T26 | scheme-adapter-zeropay | 9.10 | 9. QR Scheme Integration (ZeroPay) | 한결원/KFTC test env integration & cert | 2 | Test full merchant list sync (ZP0051) with staging diff and atomic promote | Per SCH-06 §4.2 (ZP0051): periodic full merchant list, same field layout as ZP0041 but all active merchants. Processing: download -> validate checksum + record count -> load to merchants_staging -> diff vs live merchants -> apply inserts/updates/soft-deletes for absent merchants -> promote atomically. Failure must not partially overwrite live data (rollback on error). Full-sync failures retain previous data and alert Ops. The scheduler must detect whether a full file is present and suppress ZP0041 delta upsert for the same entity type on that processing run. | • Request or generate a ZP0051 full merchant file with a known total record count and a merchant absent from the current live merchants table. • Process via full-sync job; verify staging table loaded, diff computed, live table atomically replaced. • Verify merchants absent from ZP0051 are soft-deleted (status=INACTIVE) in live merchants table. • Simulate mid-sync failure (kill job after staging load but before promote); verify live merchants table is unchanged. • Verify ZP0041 delta processing is suppressed on the same run when ZP0051 is present. | ZP0051 full-sync processing verified: atomic promote, rollback on failure, delta suppression, and record-count reconciliation. | • Live merchants table record count matches ZP0051 header control total after successful sync. • Merchant present in live table but absent from ZP0051 has status=INACTIVE after sync. • Simulated mid-sync interruption: live merchants table is identical to pre-sync state (rollback confirmed). • ZP0041 processing is skipped (log entry: DELTA_SUPPRESSED_FULL_SYNC_PRESENT) when ZP0051 detected in same batch run. | 50 | 9.10-T24 | QA | SCH-06, PM-14
9.10-T27 | scheme-adapter-zeropay | 9.10 | 9. QR Scheme Integration (ZeroPay) | 한결원/KFTC test env integration & cert | 2 | Test SFTP transfer failure retry and Ops alerting for outbound batch files | Per SCH-06 §2.4 and §9.2: on SFTP transfer failure, retry up to 3 times with exponential back-off (30s, 2min, 10min), then alert Ops and halt. Subsequent dependent batch jobs must NOT be attempted after halt. Per §9.5 escalation table: ZP0011/ZP0021 outbound cutoff=02:00 KST; ZP0061 cutoff=05:00 KST. Retransmission uses incremented sequence number (e.g. ZP0011_{YYYYMMDD}_02.dat.pgp) with same content. Re-processing inbound files must be idempotent (upsert, no duplicates). | • Mock SFTP failure on first two PUT attempts for a ZP0011 file (e.g. return connection-refused); verify retry attempts with back-off delays of 30s and 2min. • On third retry success, verify file transmitted with original sequence number _01. • Force all 3 retries to fail; verify Ops alert raised and batch job halts. • Verify that ZP0061 (dependent on ZP0011) is placed in WAITING status, not ERROR, when ZP0011 halts. • Simulate manual re-transmit with sequence number _02 for ZP0011; verify re-processed content is identical to _01; verify ZP0012 mismatch check handles the re-transmit correctly. | SFTP retry logic and failure alerting verified; exponential back-off confirmed; dependent job correctly WAITING; re-transmit idempotency confirmed. | • Retry log shows attempts at T+0, T+30s, T+2min with the correct delay pattern. • After 3-retry failure, batch_job status=HALTED and Ops alert delivered. • ZP0061 batch_job status=WAITING (not ERROR or RUNNING) when ZP0011 is in HALTED state. • Re-transmit ZP0011_..._02 file with same records: ZP0012 reconciliation produces no REGISTRATION_UNKNOWN anomalies; idempotent upsert confirmed. | 45 | 9.10-T16 | QA | SCH-06, PM-14
9.10-T28 | scheme-adapter-zeropay | 9.10 | 9. QR Scheme Integration (ZeroPay) | 한결원/KFTC test env integration & cert | 2 | Test late file detection and Ops alert for inbound ZP0012 | Per SCH-06 §9.3 and §9.5: if an expected inbound file has not arrived by deadline + 60 minutes, a BATCH_FILE_LATE alert is raised and dependent jobs enter WAITING state. For ZP0012: expected by ~05:00 KST; escalation if not received by 06:00 KST (05:00 + 60 min). Ops may manually trigger downstream jobs once the file is received. Escalation to 한결원 account contact if file not arrived by 08:00 KST. | • Configure test: set ZP0012 expected window to 05:00 KST; advance test clock past 06:00 KST without placing ZP0012 in inbound SFTP dir. • Verify BATCH_FILE_LATE alert raised with file_type=ZP0012, expected_by=05:00 KST, alert_time=06:00 KST. • Verify ZP0061 batch job status=WAITING (not ERROR) pending ZP0012 arrival. • Place ZP0012 file in inbound SFTP dir; verify file is picked up and processed; ZP0061 batch job becomes eligible to run. • Verify Ops can manually trigger ZP0061 via Admin portal once ZP0012 is processed. | Late-file detection and WAITING-state dependency for ZP0012->ZP0061 chain verified; Ops alert and manual trigger functional. | • BATCH_FILE_LATE alert raised at deadline+60min with correct file_type and expected_by fields. • ZP0061 batch_job status=WAITING when ZP0012 is overdue; ZP0061 does NOT execute automatically. • After ZP0012 is placed and processed, ZP0061 becomes manually triggerable via Admin portal. • Ops alert includes file_type=ZP0012, expected_at=05:00 KST, and alert escalation note at 08:00 KST threshold. | 40 | 9.10-T17, 9.10-T27 | QA | SCH-06, PM-14
9.10-T29 | scheme-adapter-zeropay | 9.10 | 9. QR Scheme Integration (ZeroPay) | 한결원/KFTC test env integration & cert | 2 | Test corrupt/parse-error inbound file handling for ZP0012 | Per SCH-06 §9.2: file parse error or corrupt file is a P1 exception. Action: reject file, raise Ops alert, request retransmission from 한결원. Per §9.4 retransmission: ZeroPay replaces the file in the SFTP inbound directory. Reprocessing must be idempotent. Per §2.3.2 PGP: signature verification failure on inbound file must also be treated as corrupt (potential tampering). | • Place a ZP0012 file with a corrupted record (invalid field length, truncated line) in the inbound SFTP directory. • Process via inbound job; verify parse fails; settlement_batch row status=PARSE_ERROR; Ops alert raised (P1). • Place a ZP0012 file with invalid PGP signature; verify signature verification failure raises P1 alert; file rejected. • Simulate retransmission: place a corrected ZP0012 file (same business date); verify it is processed successfully. • Verify idempotency: processing the valid retransmission file does not duplicate any DB updates from partial processing of the corrupt file. | Corrupt and PGP-invalid inbound file handling verified; P1 alerts raised; retransmission idempotency confirmed. | • Corrupt ZP0012 file: settlement_batch status=PARSE_ERROR; P1 Ops alert delivered; no partial DB updates applied. • PGP signature failure: file rejected with PGP_SIGNATURE_INVALID error; P1 Ops alert delivered. • Valid retransmission file processed successfully; all records match SETTLEMENT_REGISTERED expectations. • DB state after retransmission processing is identical to state from a clean first-time processing (idempotency). | 40 | 9.10-T17 | QA | SCH-06, PM-14
9.10-T30 | scheme-adapter-zeropay | 9.10 | 9. QR Scheme Integration (ZeroPay) | 한결원/KFTC test env integration & cert | 2 | Unit tests: ZP0011 file generator with header, detail records, trailer, and control-sum | ZP0011 generator (SCH-06 §5.2) must produce: header (file_type=ZP0011, business_date, GME institution code, record_count, total_payout_amount_krw), detail records (record_type=D, gme_txn_id, zeropay_txn_ref, merchant_id, qr_code_id, txn_date, txn_time, payout_amount_krw, merchant_fee_amt, van_fee_amt, partner_type, approval_code, status_code=A), trailer (record_count repeat, control_sum). Matching key: zeropay_txn_ref+txn_date. Edge cases: zero transactions -> empty body but valid header/trailer; KRW amounts are integers (0 decimals per money-handling rules); txn_time in KST (UTC+9 conversion). | • Write unit test: generate ZP0011 for 3 test transactions (2 domestic P-TEST-001, 1 international P-TEST-002); assert header record_count=3 and total_payout_amount_krw = sum of 3 payout_amount_krw values. • Write unit test: zero-transaction case; assert header record_count=0, trailer control_sum=0, file contains header + empty body + trailer only. • Write unit test: partner_type field = D for P-TEST-001 transactions and I for P-TEST-002 transactions. • Write unit test: txn_time is KST (UTC+9); a transaction at 2026-10-15T13:00:00Z appears as txn_time=220000 in file. • Write unit test: KRW amounts are integers (no decimal point in payout_amount_krw field). | JUnit/equivalent test class ZP0011GeneratorTest with 5 test methods; all pass. | • header record_count=3 for 3-transaction input; total_payout_amount_krw equals sum of individual payout amounts. • Zero-transaction file is syntactically valid (header + trailer present); no detail lines. • partner_type=D for domestic; partner_type=I for international transaction in same file. • UTC 13:00:00 stored as KST 22:00:00 in txn_time field. • payout_amount_krw=13500 stored as the integer string 13500 with no decimal point. | 45 | 9.10-T16 | QA | SCH-06, PM-14
9.10-T31 | scheme-adapter-zeropay | 9.10 | 9. QR Scheme Integration (ZeroPay) | 한결원/KFTC test env integration & cert | 2 | Unit tests: ZP0012 inbound parser and mismatch reconciliation logic | ZP0012 parser (SCH-06 §5.3-5.4) must: parse zeropay_txn_ref+txn_date as composite match key; map result_code=00 to SETTLEMENT_REGISTERED; non-zero to REGISTRATION_FAILED; absent-from-ZP0012 record to REGISTRATION_UNKNOWN; amount discrepancy (registered_amount != payout_amount_krw in ZP0011) to REGISTRATION_AMOUNT_MISMATCH; ZP0012 record absent from ZP0011 to anomaly log. Zero-tolerance: any mismatch generates an exception record. | • Write unit test: ZP0012 with result_code=00 and matching amounts -> SETTLEMENT_REGISTERED. • Write unit test: ZP0012 with result_code=9001 -> REGISTRATION_FAILED; exception record created. • Write unit test: ZP0011 record not in ZP0012 -> REGISTRATION_UNKNOWN; exception record created. • Write unit test: amounts match but registered_amount differs by 1 KRW -> REGISTRATION_AMOUNT_MISMATCH; exception created. • Write unit test: ZP0012 contains a zeropay_txn_ref not present in ZP0011 -> anomaly log entry; no exception raised (just log). | JUnit/equivalent test class ZP0012ReconciliationTest with 5 test methods; all pass. | • result_code=00 with matching amounts returns ReconciliationStatus.SETTLEMENT_REGISTERED. • result_code=9001 returns ReconciliationStatus.REGISTRATION_FAILED and creates one exception record. • ZP0011 record absent from ZP0012 returns ReconciliationStatus.REGISTRATION_UNKNOWN and creates one exception record. • amount discrepancy of 1 KRW returns ReconciliationStatus.REGISTRATION_AMOUNT_MISMATCH; exception record contains both submitted and registered amounts. • ZP0012 extra record (not in ZP0011) creates anomaly log entry; exception count remains 0 for that record. | 45 | 9.10-T17 | QA | SCH-06, PM-14
9.10-T32 | scheme-adapter-zeropay | 9.10 | 9. QR Scheme Integration (ZeroPay) | 한결원/KFTC test env integration & cert | 2 | Unit tests: ZP0061 settlement request generator (net vs gross logic) | ZP0061 generator (SCH-06 §7.2, §7.1): aggregate per-merchant. Net settlement (domestic, settlement_type=N): net_settlement_amount = gross_txn_amount - merchant_fee_total - refund_amount. Gross settlement (international, settlement_type=G): net_settlement_amount = gross_txn_amount (full payout; GME invoices merchant separately monthly). Prerequisite gate: ZP0011 success AND ZP0012 processed with no REGISTRATION_FAILED or REGISTRATION_UNKNOWN exceptions. | • Write unit test: domestic merchant M-TEST-0001 with gross_txn_amount=13500 KRW, merchant_fee_total=108 KRW (0.80% fee), refund_amount=0 -> net_settlement_amount=13392 KRW, settlement_type=N. • Write unit test: international merchant M-TEST-0004 with gross_txn_amount=13500 KRW -> net_settlement_amount=13500 KRW, settlement_type=G. • Write unit test: merchant with 2 payments and 1 refund; gross_txn_count=2, refund_count=1; net=sum_payments-refund-fees. • Write unit test: prerequisite gate not met (REGISTRATION_FAILED exception outstanding) -> generator throws exception; ZP0061 not produced. • Write unit test: zero transactions for a day -> ZP0061 file has header/trailer with count=0; no merchant detail records. | JUnit/equivalent test class ZP0061GeneratorTest with 5 test methods; all pass. | • Domestic net_settlement_amount = gross_txn_amount - merchant_fee_total for settlement_type=N. • International net_settlement_amount = gross_txn_amount for settlement_type=G (fee not deducted in file). • Multi-transaction merchant: gross_txn_count=2, gross_txn_amount=sum of both; refund correctly subtracted. • REGISTRATION_FAILED outstanding exception causes generator to throw SettlementPrerequisiteException; ZP0061 not written to disk. • Zero-transaction day produces valid ZP0061 with header record_count=0. | 45 | 9.10-T20 | QA | SCH-06, PM-14
9.10-T33 | scheme-adapter-zeropay | 9.10 | 9. QR Scheme Integration (ZeroPay) | 한결원/KFTC test env integration & cert | 2 | Unit tests: EMVCo QR parser (CRC, tag extraction, ZeroPay MAI) | Per SCH-06 §3.4: parseMerchantQR must verify CRC-16/CCITT in tag 63; confirm tag 00=01; extract tag 53 (must be 410 for KRW); locate ZeroPay MAI slot (tags 26-51); extract merchant_id, qr_code_id, merchant_name from MAI. Error codes: QR_INVALID_CHECKSUM, QR_MALFORMED (missing mandatory tag), QR_CURRENCY_MISMATCH (tag 53 != 410), QR_UNKNOWN_SCHEME (MAI slot not ZeroPay). The MAI slot tag is configurable (Assumption A-05). Return: normalised MerchantIdentifier object with merchant_id and qr_code_id. | • Write unit test: valid ZeroPay EMVCo QR payload -> returns MerchantIdentifier with correct merchant_id and qr_code_id. • Write unit test: flip 1 bit in CRC (tag 63) -> QrParseException(QR_INVALID_CHECKSUM). • Write unit test: payload with tag 53=840 (USD) -> QrParseException(QR_CURRENCY_MISMATCH). • Write unit test: payload missing tag 52 (MCC) -> QrParseException(QR_MALFORMED). • Write unit test: MAI slot set to a non-ZeroPay GUID -> QrParseException(QR_UNKNOWN_SCHEME). | JUnit/equivalent test class EmvcoQrParserTest with 5 test methods; all pass. | • Valid payload returns MerchantIdentifier with merchant_id and qr_code_id matching payload values. • 1-bit CRC flip throws QrParseException with code QR_INVALID_CHECKSUM. • tag 53=840 throws QrParseException with code QR_CURRENCY_MISMATCH. • Missing tag 52 throws QrParseException with code QR_MALFORMED. • Non-ZeroPay MAI throws QrParseException with code QR_UNKNOWN_SCHEME. | 40 | 9.10-T15 | QA | SCH-06, PM-14
9.10-T34 | scheme-adapter-zeropay | 9.10 | 9. QR Scheme Integration (ZeroPay) | 한결원/KFTC test env integration & cert | 2 | Unit tests: SFTP transfer module (upload, checksum verify, retry back-off) | Per SCH-06 §2.4: SFTP transfer process for outbound files: generate in memory -> temp file -> PGP encrypt -> SFTP PUT -> verify checksum (compare remote file size) -> on success move to archive; on failure retry 3x with back-off (30s, 2min, 10min) -> alert and halt. The transfer module is invoked by every batch job. Test with mock SFTP server. | • Write unit test: successful upload -> transferResult.status=SUCCESS; remote path = /gmepay/outbound/{filename}; local archive copy created. • Write unit test: first 2 attempts fail (mock throws SftpException); 3rd attempt succeeds -> result=SUCCESS after 2 retries; retry count=2 logged. • Write unit test: all 3 attempts fail -> transferResult.status=HALTED; Ops alert event fired; retryCount=3. • Write unit test: checksum mismatch after upload (remote size != local size) -> treated as failure; retry triggered. • Write unit test: verify retry delay sequence: delays[0]=30s, delays[1]=120s, delays[2]=600s from SftpTransferConfig defaults. | JUnit/equivalent test class SftpTransferModuleTest with 5 test methods; all pass using mock SFTP. | • Successful upload creates local archive copy and returns status=SUCCESS. • 2-failure-then-success scenario: status=SUCCESS, retryCount=2 in transfer log. • 3-failure scenario: status=HALTED, Ops alert event published exactly once. • Checksum mismatch triggers retry; retryCount incremented. • Retry delay config values: delays=[30,120,600] seconds as defaults. | 40 | 9.10-T27 | QA | SCH-06, PM-14
9.10-T35 | scheme-adapter-zeropay | 9.10 | 9. QR Scheme Integration (ZeroPay) | 한결원/KFTC test env integration & cert | 2 | Execute full 24-hour ZeroPay batch cycle E2E test in 한결원 UAT | This test runs the complete daily batch cycle end-to-end against 한결원 UAT to validate the integration as a whole. Batch schedule (SCH-06 §7.3, all times KST): ~02:00 ZP0011+ZP0021 outbound; ~05:00 ZP0012+ZP0022 inbound + ZP0061 outbound; ~10:00 ZP0062 inbound; ~14:00 ZP0063 outbound; ~19:00 ZP0064 inbound; ~22:00 ZP0065+ZP0066 outbound. Merchant/QR sync files arrive 01:00-06:00. Dependency chain per §8.2 must be enforced. Phase 2 gate criterion per PM-14 §5.2: all ZP00xx file types verified; discrepancy auto-detection alerts within SLA. | • Seed the UAT environment with 3+ test transactions (MPM domestic, MPM inbound, admin refund) using credentials from T08-T11. • Execute batch jobs in order, respecting the dependency chain; use accelerated timing in test environment (no need to wait for real KST times). • Verify each outbound file transmitted successfully; each inbound file received and reconciled. • Verify final reconciliation: ZP0065 line items match ZP0061 totals; ZP0066 refund totals match ZP0021. • Run the UNCERTAIN transaction path: timeout one scheme call before batch; verify ZP0012 resolves it within 24h. • Confirm all settlement_batch rows end in status=PROCESSED or TRANSMITTED with zero exceptions outstanding. | Full 24-hour ZeroPay batch cycle E2E test completed successfully against 한결원 UAT; settlement_batch table shows all 10 file types processed with zero exceptions. | • All 10 outbound file types (ZP0011, ZP0021, ZP0061, ZP0063, ZP0065, ZP0066) have settlement_batch.status=TRANSMITTED. • All 4 inbound file types (ZP0012, ZP0022, ZP0062, ZP0064) have settlement_batch.status=PROCESSED. • Final ledger reconciliation: sum of ZP0065 payout_amount_krw per merchant = gross_txn_amount in ZP0061 (zero discrepancy). • UNCERTAIN transaction resolved to APPROVED or FAILED via ZP0012 within the same batch cycle. • Zero open exception records in the Ops exception queue at end of cycle. | 60 | 9.10-T23, 9.10-T25, 9.10-T26, 9.10-T28, 9.10-T29 | QA | SCH-06, PM-14
9.10-T36 | scheme-adapter-zeropay | 9.10 | 9. QR Scheme Integration (ZeroPay) | 한결원/KFTC test env integration & cert | 2 | Obtain formal 한결원 KFTC scheme certification sign-off | Per SCH-06 §11.2 Step 5 and PM-14 §5.2 Phase 2 gate: certification requires a successful end-to-end ZeroPay test transaction with the 한결원 test environment. 한결원/KFTC may require submission of test evidence (batch cycle logs, reconciliation reports, transaction records) before issuing production credentials. The certification deliverable is a written confirmation from 한결원 that GMEPay+ has passed integration testing and is approved to receive production SFTP credentials and real-time API production access. | • Compile certification evidence package: E2E test cycle results from T35, reconciliation reports, settlement_batch table export, Ops exception queue (zero open items), SFTP transfer logs with checksums. • Submit evidence package to 한결원/KFTC account contact along with GME institution code and production IP address (NAT Gateway static IP per SAD-02 §10.4 Assumption A-04). • Participate in any 한결원-directed review calls or additional test scenarios they require. • Receive written certification confirmation from 한결원 (email or signed test completion certificate). • File certification artefact in the project repository (docs/certification/) and update the PM-14 RAID log entry for R-01 (한결원 test environment dependency) to CLOSED. | Signed/emailed certification confirmation from 한결원 KFTC; stored in docs/certification/; PM-14 RAID R-01 closed. | • Certification artefact is a written statement from 한결원 confirming GMEPay+ has passed integration testing. • docs/certification/ directory contains the artefact with filename including the confirmation date. • PM-14 RAID log R-01 status updated to CLOSED with certification date noted. • Production SFTP credentials received from 한결원 (or confirmed to be forthcoming) as a result of passing certification. | 60 | 9.10-T35 | QA | SCH-06, PM-14
10.1-T01 | admin-ui | 10.1 | 10. Admin System | Admin app shell, nav & auth (SSO/2FA) | 1 | Create hub_user and hub_role DB migration | Admin System (PRD-07, SEC-09) uses RBAC with four roles: SUPER_ADMIN, OPS_OPERATOR, FINANCE_ANALYST, ADMIN_VIEWER. hub_user: id (UUID v4), email (unique), name, role_id (FK -> hub_role.id), is_active (bool default true), last_login_at, created_at, updated_at, created_by (UUID FK -> hub_user.id nullable). hub_role: id (UUID v4), role_code (ENUM: SUPER_ADMIN¦OPS_OPERATOR¦FINANCE_ANALYST¦ADMIN_VIEWER), permissions (JSONB), created_at, updated_at. Passwords are bcrypt-hashed; stored in a separate hub_user_credential table (user_id FK, password_hash TEXT, must_change bool default true, updated_at). No local passwords for operators in the final SSO model, but Phase 1 uses local accounts. | • Create Flyway/Liquibase migration V10_1_001: create hub_role with role_code ENUM, seed the four canonical roles with empty permissions JSONB • Create V10_1_002: create hub_user with all specified columns; FK to hub_role; index on email • Create V10_1_003: create hub_user_credential (user_id UUID PK FK, password_hash TEXT NOT NULL, must_change BOOLEAN DEFAULT TRUE, updated_at TIMESTAMPTZ); unique constraint on user_id • Create V10_1_004: create hub_auth_event (id UUID PK, user_id FK, event_type VARCHAR(30), ip_address INET, user_agent TEXT, session_id UUID nullable, occurred_at TIMESTAMPTZ); index on user_id and occurred_at • Verify migrations apply cleanly on a fresh schema with no data | Four Flyway/Liquibase migration files creating hub_role, hub_user, hub_user_credential, hub_auth_event tables | • hub_user.email has a unique index; inserting two rows with the same email raises a constraint violation • hub_user.role_id FK rejects an unknown role UUID • hub_user_credential.user_id is PK (one credential row per user); duplicate insert raises violation • hub_auth_event.event_type accepts LOGIN_SUCCESS, LOGIN_FAILED, LOGOUT, SESSION_TIMEOUT, PASSWORD_CHANGED • All four migrations apply and rollback cleanly; schema matches ERD | 40 |  | FS | PRD-07, UX-11
10.1-T02 | admin-ui | 10.1 | 10. Admin System | Admin app shell, nav & auth (SSO/2FA) | 1 | Seed canonical hub_role permission JSONB for all four roles | PRD-07 §12.3 defines the permission matrix. hub_role.permissions JSONB encodes allowed actions as a flat map of action_code -> boolean. Action codes (from PRD-07 matrix): VIEW_DASHBOARD, MANAGE_SCHEME, ACTIVATE_SCHEME, VIEW_SCHEME, MANAGE_PARTNER, VIEW_CREDENTIALS, MANAGE_CREDENTIALS, MANAGE_RULE, UPDATE_FX_RATE, VIEW_FX_HISTORY, VIEW_TRANSACTIONS, VIEW_POOL_VALUES, VIEW_PREFUNDING, RECORD_TOPUP, MANUAL_ADJUSTMENT, INITIATE_REFUND, VIEW_REFUND, VIEW_SETTLEMENT, EXPORT_REVENUE, MANAGE_USERS, VIEW_AUDIT_LOG, EXPORT_AUDIT_LOG. Roles: SUPER_ADMIN=all true; OPS_OPERATOR: no MANAGE_USERS, no EXPORT_AUDIT_LOG, no MANUAL_ADJUSTMENT, no VIEW_POOL_VALUES (false); FINANCE_ANALYST: VIEW_DASHBOARD, VIEW_FX_HISTORY, VIEW_TRANSACTIONS, VIEW_POOL_VALUES, VIEW_PREFUNDING, MANUAL_ADJUSTMENT, VIEW_REFUND, VIEW_SETTLEMENT, EXPORT_REVENUE all true, rest false; ADMIN_VIEWER: VIEW_DASHBOARD, VIEW_FX_HISTORY, VIEW_TRANSACTIONS, VIEW_REFUND all true, rest false. | • Write a data migration (V10_1_005) that UPDATEs hub_role.permissions JSONB for each of the four role_codes using the exact matrix from PRD-07 §12.3 • Include a comment block in the migration listing every action code and its value per role for traceability • Add a CHECK constraint or trigger to reject any permissions JSONB that contains unknown action codes • Write a brief unit-test SQL that asserts SUPER_ADMIN has 22 true entries, ADMIN_VIEWER has exactly 4 true entries | Migration V10_1_005 seeding permissions JSONB for all four roles, plus SQL assertion test | • SUPER_ADMIN permissions JSONB contains all 22 action codes set to true • ADMIN_VIEWER cannot VIEW_POOL_VALUES (value is false or absent) • OPS_OPERATOR cannot MANAGE_USERS (false) • FINANCE_ANALYST can MANUAL_ADJUSTMENT but cannot MANAGE_PARTNER • Inserting a permissions JSONB with an unrecognised key raises a constraint violation | 35 | 10.1-T01 | FS | PRD-07, UX-11
10.1-T03 | admin-ui | 10.1 | 10. Admin System | Admin app shell, nav & auth (SSO/2FA) | 1 | Implement PermissionGuard service: hasPermission(userId, actionCode) | All Admin API endpoints check whether the authenticated user holds the required action_code. The guard queries hub_user.role_id -> hub_role.permissions JSONB. Returns true only if permissions->actionCode = true. User accounts with is_active=false must always return false regardless of role. The service must cache the role permissions map in-process (invalidated on role update) to avoid per-request DB round-trips. | • Create PermissionGuard class/service with method hasPermission(userId: UUID, actionCode: String): Boolean • Load role permissions from hub_role on startup and on role-update event; expose a refreshPermissions() hook for tests • On call: fetch user from DB (or cache), check is_active, look up role permissions map, return permissions[actionCode] == true • Throw FORBIDDEN (HTTP 403) when hasPermission returns false; throw UNAUTHORIZED (HTTP 401) when userId not found or session invalid • Write unit tests covering: active SUPER_ADMIN returns true for MANAGE_USERS, inactive SUPER_ADMIN returns false, OPS_OPERATOR returns false for MANAGE_USERS, unknown actionCode returns false | PermissionGuard service class with unit tests | • Active SUPER_ADMIN.hasPermission(MANAGE_USERS) == true • Inactive SUPER_ADMIN.hasPermission(VIEW_DASHBOARD) == false regardless of role • OPS_OPERATOR.hasPermission(MANAGE_USERS) == false • Unknown actionCode returns false (no exception) • FINANCE_ANALYST.hasPermission(MANUAL_ADJUSTMENT) == true | 45 | 10.1-T02 | FS | PRD-07, UX-11
10.1-T04 | admin-ui | 10.1 | 10. Admin System | Admin app shell, nav & auth (SSO/2FA) | 1 | Implement local-account password hashing and validation service | Phase 1 uses local portal accounts (PRD-07 §12.5, SEC-09 §3.1 note: SSO is Phase 2). Passwords must be bcrypt-hashed at rest (SEC-09 §3.2: min 12 chars, complexity required). The PasswordService must: hash on creation/change, verify on login, enforce minimum 12 chars + at least 1 uppercase + 1 digit + 1 special char. must_change flag in hub_user_credential must be honoured: if true, any non-password-change API call returns HTTP 403 MUST_CHANGE_PASSWORD. Password history: last 5 hashes stored; reuse of a recent password rejected. | • Implement PasswordService.hash(plaintext) using bcrypt with work factor 12; store result in hub_user_credential.password_hash • Implement PasswordService.verify(plaintext, hash) returning boolean • Implement PasswordService.validate(plaintext) throwing PasswordPolicyViolation if < 12 chars or missing uppercase/digit/special • Add hub_user_password_history table (user_id, password_hash, changed_at) via new migration; keep last 5 entries • Implement PasswordService.isRecentlyUsed(userId, plaintext) checking last 5 hashes; return true if match found | PasswordService class, hub_user_password_history migration, and unit tests | • Password 'Admin1234' (no special char) fails validation with MISSING_SPECIAL_CHAR • Password 'Correct$Horse9' (13 chars) passes validation and hash verifies correctly • Reusing the same password when it is in the last 5 hashes returns isRecentlyUsed=true • bcrypt hash of same plaintext differs on each call (salt); verify returns true for both • must_change=true blocks a non-password-change request with HTTP 403 MUST_CHANGE_PASSWORD | 45 | 10.1-T01 | FS | PRD-07, UX-11
10.1-T05 | admin-ui | 10.1 | 10. Admin System | Admin app shell, nav & auth (SSO/2FA) | 1 | Implement POST /admin/auth/login endpoint | Admin System login (PRD-07 §12.5, SEC-09 §3.1): accepts email + password JSON body, verifies credentials, enforces account lockout after 5 consecutive failures, issues a session JWT (8-hour absolute expiry, 30-minute idle timeout configurable). Session JWT payload: {sub: user_id, email, role_code, session_id: UUID, iat, exp}. Signed with HS256 using internal JWT secret from secrets vault. All login events (success and failure) must be written to hub_auth_event with event_type LOGIN_SUCCESS or LOGIN_FAILED, ip_address from X-Forwarded-For header, occurred_at UTC. On LOGIN_FAILED x5, set is_active=false and event_type=ACCOUNT_LOCKED. | • Create POST /admin/auth/login handler accepting {email, password} • Call PasswordService.verify; on failure increment consecutive_failures counter (stored in hub_user_credential or Redis); on 5th failure set is_active=false and write ACCOUNT_LOCKED event • On success: reset failure counter, update last_login_at, write LOGIN_SUCCESS to hub_auth_event, issue JWT • JWT expiry = min(iat+8h, last_activity+30min); include session_id UUID v4 • Return 200 {token, expires_at, must_change} on success; 401 INVALID_CREDENTIALS on failure (never reveal which field is wrong); 423 ACCOUNT_LOCKED if is_active=false | POST /admin/auth/login handler with integration tests | • Valid credentials return 200 with JWT containing correct role_code and session_id • 5 consecutive bad passwords for same account set is_active=false and subsequent login returns 423 ACCOUNT_LOCKED • Successful login writes LOGIN_SUCCESS event to hub_auth_event with non-null ip_address • must_change=true is returned in login response when hub_user_credential.must_change=true • Login with inactive account (is_active=false) returns 423 before credential check | 50 | 10.1-T03, 10.1-T04 | FS | PRD-07, UX-11
10.1-T06 | admin-ui | 10.1 | 10. Admin System | Admin app shell, nav & auth (SSO/2FA) | 1 | Implement session JWT middleware and idle-timeout tracking | Every authenticated Admin API request must pass through a JWT middleware that: verifies the HS256 signature, checks exp claim, checks the session has not been explicitly invalidated (logout/forced-revoke), and enforces the 30-minute idle timeout. Idle timeout is tracked by storing last_activity_at per session_id in Redis (TTL = 30 min). On each valid request the TTL is reset. If the Redis key is absent (expired), return 401 SESSION_EXPIRED. Logout deletes the Redis key. Session store key format: admin_session:{session_id}. | • Implement JwtMiddleware that extracts Bearer token, verifies signature with vault-sourced secret, checks exp • On valid JWT: look up Redis key admin_session:{session_id}; if absent return 401 SESSION_EXPIRED; if present reset TTL to 30 minutes • Attach authenticated user context (user_id, role_code, session_id) to request for downstream handlers • Implement POST /admin/auth/logout that deletes admin_session:{session_id} from Redis and writes LOGOUT event to hub_auth_event • Write integration test: login -> wait (mock) 31 min idle -> next request returns 401 SESSION_EXPIRED | JwtMiddleware and POST /admin/auth/logout with integration tests | • Request with expired JWT (exp in past) returns 401 TOKEN_EXPIRED • Request with valid JWT but no Redis session key returns 401 SESSION_EXPIRED • Valid request resets Redis TTL to 30 minutes (observable via TTL command) • POST /admin/auth/logout deletes Redis key and subsequent request returns 401 SESSION_EXPIRED • Logout writes event_type=LOGOUT to hub_auth_event with correct session_id | 50 | 10.1-T05 | FS | PRD-07, UX-11
10.1-T07 | admin-ui | 10.1 | 10. Admin System | Admin app shell, nav & auth (SSO/2FA) | 1 | Implement POST /admin/auth/change-password endpoint | When hub_user_credential.must_change=true, the user may only call POST /admin/auth/change-password before any other endpoint (all others return 403 MUST_CHANGE_PASSWORD). Endpoint requires authenticated session (JWT from login), accepts {current_password, new_password}. Must verify current password, enforce password policy (>=12 chars, uppercase+digit+special), check not in last 5 used, set must_change=false, update password_hash, record in hub_user_password_history, write PASSWORD_CHANGED to hub_auth_event. On success reissue a new JWT (new session_id, fresh 8h exp). | • Implement POST /admin/auth/change-password behind JwtMiddleware • Verify current_password against existing hash; reject with 401 INVALID_CURRENT_PASSWORD if wrong • Call PasswordService.validate(new_password); call PasswordService.isRecentlyUsed; reject with 422 PASSWORD_RECENTLY_USED if match • Update hub_user_credential (password_hash, must_change=false, updated_at); insert into hub_user_password_history • Write PASSWORD_CHANGED to hub_auth_event; issue new JWT with new session_id; return {token, expires_at} | POST /admin/auth/change-password handler with unit and integration tests | • Wrong current_password returns 401 INVALID_CURRENT_PASSWORD, must_change remains true • New password matching a hash in last 5 entries returns 422 PASSWORD_RECENTLY_USED • Valid change sets must_change=false in hub_user_credential and returns new JWT • New JWT has a different session_id from the login JWT • Old Redis session key for prior session_id is deleted after password change | 45 | 10.1-T06 | FS | PRD-07, UX-11
10.1-T08 | admin-ui | 10.1 | 10. Admin System | Admin app shell, nav & auth (SSO/2FA) | 1 | Implement MFA TOTP enrollment and verification for admin accounts | SEC-09 §3.1: MFA is required for all Admin portal logins. Phase 1 implementation: TOTP (RFC 6238, 30-second window, SHA-1, 6 digits). PRD-07 §12.5: MFA strongly recommended and enforced for OPS_OPERATOR and above (SUPER_ADMIN, OPS_OPERATOR). FINANCE_ANALYST and ADMIN_VIEWER may optionally enroll. Enrollment: generate TOTP secret (base32), return QR code URI (otpauth://totp/GMEPayAdmin:{email}?secret={secret}&issuer=GMEPay), store hashed secret in hub_user_mfa (user_id PK, totp_secret_enc TEXT encrypted with AES-256, is_enabled BOOL, enrolled_at). Recovery codes: 8 x 10-char alphanumeric codes stored hashed; each single-use. | • Create migration V10_1_006: hub_user_mfa (user_id PK FK, totp_secret_enc TEXT, is_enabled BOOL DEFAULT FALSE, enrolled_at TIMESTAMPTZ); hub_user_recovery_code (id UUID PK, user_id FK, code_hash TEXT, used_at TIMESTAMPTZ nullable) • Implement POST /admin/auth/mfa/enroll: generate TOTP secret, encrypt with AES-256, store in hub_user_mfa; return otpauth URI and 8 recovery code plaintexts (shown once) • Implement POST /admin/auth/mfa/verify-enrollment {totp_code}: verify provided code against secret; if valid set is_enabled=true • Update login flow: after password verify, if is_enabled=true return 200 {mfa_required: true, mfa_token} (short-lived 5-min token); client must POST /admin/auth/mfa/challenge {mfa_token, totp_code} to complete login and receive session JWT • Enforce: SUPER_ADMIN and OPS_OPERATOR with is_enabled=false cannot complete login (return 403 MFA_ENROLLMENT_REQUIRED) | TOTP enrollment and challenge endpoints, hub_user_mfa migration, updated login flow | • Valid TOTP code at enrollment confirm sets is_enabled=true • SUPER_ADMIN with MFA not enrolled cannot complete login (403 MFA_ENROLLMENT_REQUIRED) • ADMIN_VIEWER without MFA can complete login (MFA optional for this role) • TOTP code reuse within same 30-second window returns 401 TOTP_ALREADY_USED • Valid recovery code completes MFA challenge and marks code used_at; reuse returns 401 RECOVERY_CODE_USED | 55 | 10.1-T06 | FS | PRD-07, UX-11
10.1-T09 | admin-ui | 10.1 | 10. Admin System | Admin app shell, nav & auth (SSO/2FA) | 1 | Implement forced account unlock endpoint (Super Admin only) | SEC-09 §3.1: after 5 failed login attempts the account is locked (is_active=false). Only a SUPER_ADMIN can unlock accounts via POST /admin/users/{userId}/unlock. This requires the caller to hold MANAGE_USERS permission. The action resets consecutive_failures counter to 0, sets is_active=true, writes an ACCOUNT_UNLOCKED event to hub_auth_event with the acting user_id. Super Admins can also POST /admin/users/{userId}/force-password-reset to set must_change=true. | • Implement POST /admin/users/{userId}/unlock behind JwtMiddleware + PermissionGuard(MANAGE_USERS) • Set is_active=true, reset consecutive_failures=0 in hub_user_credential; write ACCOUNT_UNLOCKED to hub_auth_event with actor user_id and target user_id • Implement POST /admin/users/{userId}/force-password-reset: set must_change=true; write PASSWORD_RESET_FORCED to hub_auth_event • Return 204 on success; 404 if userId not found; 403 if caller lacks MANAGE_USERS • Write tests: OPS_OPERATOR attempting to unlock returns 403; SUPER_ADMIN unlocking a locked user allows subsequent login | Unlock and force-reset endpoints with permission guard and tests | • OPS_OPERATOR calling /unlock returns 403 FORBIDDEN • SUPER_ADMIN unlocks a locked user; user can subsequently log in with valid credentials • Unlock writes ACCOUNT_UNLOCKED to hub_auth_event with both actor_user_id and target user_id • force-password-reset sets must_change=true and user sees 403 MUST_CHANGE_PASSWORD on next non-password-change request • Unlocking a user who is not locked (is_active=true) returns 204 without error (idempotent) | 40 | 10.1-T06, 10.1-T03 | FS | PRD-07, UX-11
10.1-T10 | admin-ui | 10.1 | 10. Admin System | Admin app shell, nav & auth (SSO/2FA) | 1 | Implement GET /admin/users and POST /admin/users (user management CRUD) | PRD-07 §12.4: SUPER_ADMIN can create user accounts (email + temporary password, must_change=true), assign role, deactivate/reactivate, view last_login_at and session history. Action code MANAGE_USERS required. POST /admin/users body: {email, name, role_code}. System generates a random 16-char temp password (bcrypt-hashed, must_change=true). GET /admin/users returns list: id, email, name, role_code, is_active, last_login_at. PATCH /admin/users/{id} allows updating name, role_code, is_active. All write operations must be audit-logged (see 10.1-T20 for audit-log write service). | • Implement GET /admin/users (requires MANAGE_USERS): return paginated list with columns id, email, name, role_code, is_active, last_login_at • Implement POST /admin/users (MANAGE_USERS): validate email format, unique email, valid role_code; generate 16-char temp password; hash and store; set must_change=true; write USER_CREATED to audit log • Implement PATCH /admin/users/{id} (MANAGE_USERS): allow updating name, role_code (validate enum), is_active; write USER_UPDATED to audit log with changed fields • Return 409 DUPLICATE_EMAIL if email already exists • Temp password must be returned in POST response (plaintext, shown once only) with warning note in response body | GET, POST, PATCH /admin/users endpoints with unit tests | • POST /admin/users with duplicate email returns 409 DUPLICATE_EMAIL • POST /admin/users returns temp password in response body; hub_user_credential.must_change=true • PATCH /admin/users/{id} changing role_code=FINANCE_ANALYST takes effect on next permission check • OPS_OPERATOR calling POST /admin/users returns 403 FORBIDDEN • Deactivating a user (is_active=false via PATCH) prevents that user from logging in (423 ACCOUNT_LOCKED equivalent) | 45 | 10.1-T03, 10.1-T06 | FS | PRD-07, UX-11
10.1-T11 | admin-ui | 10.1 | 10. Admin System | Admin app shell, nav & auth (SSO/2FA) | 1 | Scaffold React SPA admin shell: Vite + React + React Router project structure | UX-11 §3.1: Admin System is a React SPA (or equivalent). Target browser: latest 2 versions of Chrome/Firefox/Edge/Safari. Min viewport 1280px, desktop-first. Separate deployment from Partner Portal. Tech stack decision: Vite + React 18 + TypeScript + React Router v6 + Axios for API calls. Design tokens from UX-11 §2 (Inter font, 8px grid, named CSS custom properties). Project must support code-splitting per route. No native mobile support required. | • Initialise Vite+React+TypeScript project at packages/admin-ui (or equivalent monorepo path) • Install dependencies: react-router-dom v6, axios, date-fns (for KST display), @tanstack/react-query for server state • Define CSS custom properties in src/styles/tokens.css matching UX-11 §2.2 exactly: --color-brand #1A56DB, --color-danger #E02424, --color-warning #D97706, --color-success #057A55, --color-neutral-900 #111928, --color-neutral-50 #F9FAFB, --color-surface #FFFFFF • Set up React Router with lazy-loaded route components for each nav module (Dashboard, Schemes, Partners, Transactions, Settlement, FXRates, AuditLog, Settings, UsersRoles) • Configure Vite proxy to backend API; set up Axios base instance with Authorization header injection from session token in localStorage | Scaffolded admin-ui Vite+React project that compiles, runs dev server, and renders a blank shell at localhost | • npm run dev starts without errors; http://localhost:5173 renders without console errors • All 9 route paths are registered in React Router and render a placeholder component • CSS tokens file defines all 9 --color-* variables matching UX-11 hex values exactly • Axios base instance attaches Authorization: Bearer {token} header when token is present in localStorage • Tree-shaken production build (npm run build) completes without errors | 45 |  | FS | PRD-07, UX-11
10.1-T12 | admin-ui | 10.1 | 10. Admin System | Admin app shell, nav & auth (SSO/2FA) | 1 | Build AdminShell layout component: sidebar + top bar + content area | UX-11 §3.1 defines the Admin System shell: left sidebar 240px fixed, top bar 56px, content area max-width 1400px centred with 32px padding. Sidebar collapses to 56px icon-only at <1280px. Top bar: left hamburger to toggle sidebar, centre app title 'GMEPay+ Admin', right section shows logged-in user name + role badge + Logout button. Active nav item has --color-brand left border + brand background tint. Nav items: Dashboard, Schemes, Partners, Transactions, Settlement, FX Rates, Audit Log, Settings (divider before Settings). Font stack: Inter, fallback system fonts. | • Create AdminShell.tsx wrapping all authenticated routes; includes Sidebar and TopBar components • Sidebar: render nav items as <NavLink> components; active state adds CSS class with 2px left border --color-brand and background tint; hover shows tooltip with item name • TopBar: hamburger toggles sidebar between 240px and 56px icon-only modes using CSS transition; display user email and role_code badge from auth context; Logout button calls /admin/auth/logout then clears localStorage and redirects to /login • Content area: flex-grow, max-width 1400px, margin auto, padding 32px • Sidebar collapse state persisted in localStorage key admin_sidebar_collapsed | AdminShell.tsx, Sidebar.tsx, TopBar.tsx components rendering correct layout | • Sidebar width transitions between 240px and 56px on hamburger click; icon-only mode shows nav icons without text • Active route item has visible --color-brand left border; inactive items do not • User name and role badge appear in top bar using data from auth context • Logout button POSTs to /admin/auth/logout, clears token from localStorage, and navigates to /login • At viewport <1280px sidebar automatically collapses to icon-only (no scrollbar on main content) | 50 | 10.1-T11 | FS | PRD-07, UX-11
10.1-T13 | admin-ui | 10.1 | 10. Admin System | Admin app shell, nav & auth (SSO/2FA) | 1 | Build Login page UI: email/password form with error states | UX-11 design system (§2.4 buttons, §2.5 form controls, §2.9 error states). Login page is the unauthenticated entry point at /login. Fields: email (type=email, required), password (type=password, required, show/hide toggle). On submit: POST /admin/auth/login. Handle responses: 200 (store JWT, check must_change and mfa_required flags); 401 INVALID_CREDENTIALS (inline error 'Invalid email or password'); 423 ACCOUNT_LOCKED (inline error 'Account locked. Contact IT admin.'); 403 MFA_ENROLLMENT_REQUIRED (redirect to /setup-mfa). Loading state: disable button, show spinner. All form controls follow UX-11 §2.5 spec (36px height, 1px border, 2px brand focus ring). | • Create /login route rendering LoginPage.tsx with email and password inputs and a primary Submit button • On submit call authApi.login(email, password); show skeleton/spinner while in flight • On 200: store token in localStorage; if must_change=true navigate to /change-password; else if mfa_required=true navigate to /mfa-challenge; else navigate to /dashboard • On 401: show inline error below password field using --color-danger text • On 423: show inline error 'Account locked. Contact your IT administrator.' • Ensure password field has show/hide toggle (eye icon); form submits on Enter key | LoginPage.tsx component with all states handled and unit tests for each API response | • Empty email or password prevents form submission and shows required-field asterisk error • 401 response displays error below password field; email field is not cleared • 423 response displays account-locked message (not a generic error) • Successful login with must_change=true navigates to /change-password, not /dashboard • Successful login stores JWT in localStorage and navigates to /dashboard | 45 | 10.1-T12 | FS | PRD-07, UX-11
10.1-T14 | admin-ui | 10.1 | 10. Admin System | Admin app shell, nav & auth (SSO/2FA) | 1 | Build MFA challenge page UI: TOTP code entry form | After successful password login, if the backend returns {mfa_required: true, mfa_token}, the user is redirected to /mfa-challenge. The page shows a 6-digit TOTP input (autofocus, numeric keypad on mobile). On submit: POST /admin/auth/mfa/challenge {mfa_token, totp_code}. Handle: 200 (store session JWT, proceed to /dashboard or /change-password per must_change); 401 TOTP_INVALID (inline error 'Incorrect code. Try again.'); 401 TOTP_ALREADY_USED (inline error 'Code already used. Wait for next code.'); 401 MFA_TOKEN_EXPIRED (redirect back to /login with message 'Session expired, please log in again'). Also provide a 'Use recovery code instead' link that shows a text input for a 10-char recovery code. | • Create /mfa-challenge route; store mfa_token in component state (from navigation state passed by LoginPage) • Render 6-digit TOTP input (inputmode=numeric, maxlength=6, autofocus); primary 'Verify' button • On submit POST /admin/auth/mfa/challenge; handle all four response codes with correct messages • 'Use recovery code' toggle swaps TOTP input for a text input accepting a 10-char code; same endpoint with field totp_code omitted and recovery_code present • On 200: persist session JWT to localStorage; navigate per must_change flag • Redirect to /login if navigated to /mfa-challenge without mfa_token in state | MfaChallengePage.tsx with TOTP and recovery-code modes and unit tests | • Page auto-focuses the TOTP input on mount • 401 TOTP_ALREADY_USED shows 'Code already used. Wait for next code.' (not a generic error) • 401 MFA_TOKEN_EXPIRED redirects to /login with visible toast 'Session expired, please log in again' • Direct navigation to /mfa-challenge without mfa_token in route state redirects to /login • Recovery code mode text input accepts 10-char input and submits to same endpoint with recovery_code field | 40 | 10.1-T13, 10.1-T08 | FS | PRD-07, UX-11
10.1-T15 | admin-ui | 10.1 | 10. Admin System | Admin app shell, nav & auth (SSO/2FA) | 1 | Build MFA enrollment page UI: QR code display + verification step | When a SUPER_ADMIN or OPS_OPERATOR logs in with is_enabled=false for MFA, backend returns 403 MFA_ENROLLMENT_REQUIRED. The admin-ui redirects to /setup-mfa. Flow: (1) Call POST /admin/auth/mfa/enroll to get {otpauth_uri, recovery_codes[8]}. (2) Display QR code (use a qrcode.react component rendering the otpauth_uri). (3) Show recovery codes in a monospace list with 'Copy all' button; display warning 'Store these codes safely - they cannot be shown again'. (4) User enters TOTP code to confirm enrollment. (5) POST /admin/auth/mfa/verify-enrollment {totp_code}; on 200 is_enabled=true, proceed to login flow. This page is only accessible when user has a valid session JWT but MFA not yet enrolled. | • Create /setup-mfa route; on mount call POST /admin/auth/mfa/enroll; display loading skeleton while in flight • Render QR code using qrcode.react with the returned otpauth_uri value • Display 8 recovery codes in a 2-column monospace grid with 'Copy all codes' clipboard button • Below codes: 6-digit TOTP input for verification; primary 'Enable MFA' button • On 'Enable MFA' submit: POST /admin/auth/mfa/verify-enrollment; on 200 show success toast 'MFA enabled' and redirect to /dashboard; on 401 show inline error 'Incorrect code - scan QR again or wait for next code' • If user navigates away without completing enrollment, show a confirmation dialog 'MFA setup incomplete - your account will be blocked from login until MFA is enabled' | SetupMfaPage.tsx with QR display, recovery codes, and enrollment confirmation | • Recovery codes are displayed in monospace; 'Copy all' copies them as newline-separated text to clipboard • QR code renders the correct otpauth URI (observable via rendered SVG data-testid) • Invalid TOTP on verify returns inline error; the QR code remains visible (not cleared) • On successful enrollment a success toast appears and user is redirected to /dashboard • Navigating away mid-enrollment triggers the 'setup incomplete' confirmation dialog | 50 | 10.1-T14, 10.1-T08 | FS | PRD-07, UX-11
10.1-T16 | admin-ui | 10.1 | 10. Admin System | Admin app shell, nav & auth (SSO/2FA) | 1 | Implement PrivateRoute guard and auth context in React | All routes except /login, /mfa-challenge, /setup-mfa must be behind authentication. The React AuthContext stores {user: {id, email, role_code, session_id}, token} from localStorage on page load. PrivateRoute checks AuthContext; if no token redirects to /login. If must_change=true and current route is not /change-password, redirect to /change-password. Permission-aware rendering: some nav items and buttons are conditionally rendered based on role_code. For example, 'Users & Roles' nav item is hidden for roles other than SUPER_ADMIN. Per UX-11: ADMIN_VIEWER cannot see locked pool values section in transaction detail. | • Create AuthContext with {user, token, setAuth, clearAuth} and an AuthProvider wrapping the router • On AuthProvider mount: read token from localStorage, decode JWT payload (without re-verifying signature client-side), set user state • Create PrivateRoute component: if no token redirect to /login; if must_change and not on /change-password redirect to /change-password • Add usePermission(actionCode) hook that reads user.role_code from AuthContext and checks against client-side permission map (mirror of PRD-07 §12.3 matrix) • Hide 'Users & Roles' nav item unless role_code===SUPER_ADMIN; hide 'View pool values' section in transaction detail unless hasPermission(VIEW_POOL_VALUES) | AuthContext, AuthProvider, PrivateRoute, usePermission hook with unit tests | • Unauthenticated user visiting /dashboard is redirected to /login • User with must_change=true visiting /transactions is redirected to /change-password • ADMIN_VIEWER role: usePermission(VIEW_POOL_VALUES) returns false • SUPER_ADMIN role: usePermission(MANAGE_USERS) returns true; Users & Roles nav item is visible • OPS_OPERATOR role: Users & Roles nav item is not rendered in the sidebar | 45 | 10.1-T12, 10.1-T13 | FS | PRD-07, UX-11
10.1-T17 | admin-ui | 10.1 | 10. Admin System | Admin app shell, nav & auth (SSO/2FA) | 1 | Build Breadcrumb component and page-title header pattern | UX-11 §3.1: every page inside the shell shows a breadcrumb row above the page title. Format: Module / Sub-section / Current page. Links to parent levels. Breadcrumb is omitted on top-level pages (Dashboard). Page title is 24px weight 600 (UX-11 §2.1 'Page title' type). Breadcrumb links use --color-brand; current (non-link) segment uses --color-neutral-600. 12px body text for breadcrumb. Separator: ' / ' in neutral-600. | • Create Breadcrumb.tsx accepting an array of {label, href?} items; render as <nav aria-label='breadcrumb'> • Link segments with href render as <a> styled with --color-brand; final segment (no href) renders as <span> in --color-neutral-600 • Create PageHeader.tsx wrapping the page H1 title (24px 600) + Breadcrumb row above it; apply 0 bottom-margin between breadcrumb and title • Integrate PageHeader into at least 3 route pages: Schemes list (breadcrumb: 'Schemes'), Scheme edit (breadcrumb: 'Schemes / Edit Scheme'), and Dashboard (no breadcrumb) • Write snapshot tests for Breadcrumb with 1, 2, and 3 segments | Breadcrumb.tsx, PageHeader.tsx components integrated into route pages, snapshot tests | • Single-segment breadcrumb (top-level page) renders no breadcrumb (PageHeader shows title only) • Two-segment breadcrumb renders first segment as <a> link and second as plain text • Breadcrumb links use CSS variable --color-brand; current segment uses --color-neutral-600 • aria-label='breadcrumb' is present on the nav element for accessibility • Page title renders at 24px font-size and font-weight 600 per UX-11 | 35 | 10.1-T12 | FS | PRD-07, UX-11
10.1-T18 | admin-ui | 10.1 | 10. Admin System | Admin app shell, nav & auth (SSO/2FA) | 1 | Build global toast notification service and modal base component | UX-11 §2.10: toasts appear top-right, 16px from viewport edge, auto-dismiss 5s (success/info) or persistent until dismissed (error). Max 3 simultaneous, stacked. Variants: success (green left border), error (red), warning (amber), info (blue). Modals: max-width 560px (confirm) or 720px (review/detail). Overlay: 50% black scrim. Click-outside closes non-destructive modals. Always has X close button. Focus trap inside open modal. These are used globally by all admin modules. | • Create ToastContext and useToast() hook; ToastProvider renders a fixed top-right container • Each toast: 16px left border in variant colour, close icon (X), auto-dismiss timer (cancelable on hover); queue max 3 (oldest dropped when 4th added) • Create Modal base component accepting {isOpen, onClose, title, size: confirm¦review, children}; renders portal into document.body • Modal: --color-neutral-50 overlay 50% opacity; focus trap (tab cycles through focusable children and close button only); ESC key closes non-destructive modals • Write unit tests: adding 4 toasts dismisses the oldest; success toast disappears after 5s; error toast persists; modal focuses first focusable element on open | ToastContext, useToast hook, Toast.tsx, Modal.tsx base components with tests | • Adding a 4th toast removes the first (oldest) from the stack; at most 3 visible • Success toast starts a 5-second countdown and disappears; error toast does not auto-dismiss • Modal renders inside a portal (appended to document.body, not inside the component tree) • Pressing ESC closes a confirm modal (non-destructive); pressing ESC does not close a danger modal (destructive) • Tab key focus cycles only within the open modal (focus trap active) | 50 | 10.1-T12 | FS | PRD-07, UX-11
10.1-T19 | admin-ui | 10.1 | 10. Admin System | Admin app shell, nav & auth (SSO/2FA) | 1 | Build empty, loading, and error states as reusable components | UX-11 §2.9: empty state shows icon + 'No {entity} found' + 'Try adjusting your filters'. Loading state: skeleton shimmer (grey animated bars matching table row structure, min 200ms display). Error state: warning triangle icon + 'Could not load {entity}' + short error code + Retry button. These components are reused by all data-fetching pages (transactions, schemes, partners, etc.). | • Create EmptyState.tsx accepting {icon, title, subtitle} props; apply UX-11 §2.9 layout (centred icon + text in a bordered box) • Create SkeletonTable.tsx accepting {rows, cols} props; render animated shimmer rows using CSS animation (grey bars, 200ms minimum display enforced via useEffect timeout) • Create ErrorState.tsx accepting {message, errorCode, onRetry} props; render warning icon, message, error code in monospace, and a Ghost variant Retry button • Export all three from a ui/states/index.ts barrel file • Write storybook stories or snapshot tests for each state component | EmptyState.tsx, SkeletonTable.tsx, ErrorState.tsx components with tests | • EmptyState renders subtitle 'Try adjusting your filters' when subtitle prop is omitted (default value) • SkeletonTable with rows=5 cols=4 renders exactly 20 shimmer cells • SkeletonTable enforces minimum 200ms display: even if data arrives in 50ms the skeleton is shown for at least 200ms • ErrorState Retry button calls onRetry prop when clicked • ErrorState displays errorCode in monospace font (JetBrains Mono / Fira Code stack) | 35 | 10.1-T11 | FS | PRD-07, UX-11
10.1-T20 | admin-ui | 10.1 | 10. Admin System | Admin app shell, nav & auth (SSO/2FA) | 1 | Implement audit log write service (backend): writeAuditEvent() | PRD-07 §13.3: every config change, auth event, and admin action writes an audit log entry. hub_audit_log table (see DAT-03 §9 for schema cross-reference): id UUID PK, occurred_at TIMESTAMPTZ (ms precision), actor_user_id UUID FK, actor_display_name TEXT, actor_ip INET, event_type VARCHAR(60), entity_type VARCHAR(40), entity_id UUID, previous_value JSONB nullable, new_value JSONB nullable, description TEXT, metadata JSONB nullable. No UPDATE or DELETE permitted (enforced by DB-level policy or application constraint). Retained >= 7 years. writeAuditEvent() is called transactionally alongside the triggering write operation. | • Create migration V10_1_007: hub_audit_log with all columns; add REVOKE UPDATE, DELETE ON hub_audit_log FROM application_role (DB-level immutability) • Implement AuditService.writeAuditEvent({actor, eventType, entityType, entityId, previousValue, newValue, description, metadata}) as an async method that INSERTs into hub_audit_log • Ensure writeAuditEvent is called within the same DB transaction as the triggering change; if the outer transaction rolls back the audit entry also rolls back • Implement GET /admin/audit-log with filters: date_from, date_to, actor_user_id, entity_type, entity_id; paginated; requires VIEW_AUDIT_LOG permission • Write unit test: simulate a rule update transaction rollback; verify no audit entry is written | AuditService.writeAuditEvent(), migration V10_1_007, GET /admin/audit-log endpoint | • Attempting UPDATE on hub_audit_log from the application role raises a permission error • writeAuditEvent called inside a rolled-back transaction leaves no row in hub_audit_log • GET /admin/audit-log filtered by entity_id returns only entries for that entity in chronological order • OPS_OPERATOR calling GET /admin/audit-log returns 200 (VIEW_AUDIT_LOG=true); ADMIN_VIEWER returns 403 • Audit entry occurred_at has millisecond-level precision (not truncated to seconds) | 50 | 10.1-T01, 10.1-T03 | FS | PRD-07, UX-11
10.1-T21 | admin-ui | 10.1 | 10. Admin System | Admin app shell, nav & auth (SSO/2FA) | 1 | Wire auth events to audit log (login, logout, MFA, account management) | PRD-07 §13.2 and §12.5: all auth events must appear in the audit log. Event types to wire: LOGIN_SUCCESS (entity_type=hub_user, entity_id=user_id, metadata includes ip and user_agent), LOGIN_FAILED (actor_user_id null for unauthenticated attempts, metadata includes attempted email), ACCOUNT_LOCKED, LOGOUT, SESSION_TIMEOUT (written when Redis TTL expires and user next hits an endpoint), MFA_ENROLLED, PASSWORD_CHANGED, PASSWORD_RESET_FORCED, USER_CREATED, USER_UPDATED, ACCOUNT_UNLOCKED. All calls go through AuditService.writeAuditEvent from 10.1-T20. | • Update POST /admin/auth/login to call AuditService.writeAuditEvent for LOGIN_SUCCESS and LOGIN_FAILED (use a separate non-transactional write for LOGIN_FAILED since no transaction context) • Update JwtMiddleware to detect SESSION_EXPIRED Redis key miss and write SESSION_TIMEOUT event before returning 401 • Update POST /admin/auth/logout, POST /admin/auth/change-password, POST /admin/auth/mfa/verify-enrollment, POST /admin/users endpoints to call writeAuditEvent with appropriate event types • For LOGIN_FAILED: actor_user_id=null; store attempted email in metadata.attempted_email; include ip_address from X-Forwarded-For • Write integration test: perform a full login+logout sequence and assert all expected audit events are present in hub_audit_log | All auth and user-management flows writing to hub_audit_log, verified by integration tests | • LOGIN_FAILED event has actor_user_id=null and metadata.attempted_email equal to the submitted email • LOGIN_SUCCESS event has non-null actor_ip from X-Forwarded-For • Logout writes LOGOUT event with matching session_id to the login session_id • USER_CREATED event written when SUPER_ADMIN creates a new user, with new_value containing {email, role_code} (no password hash) • SESSION_TIMEOUT written when Redis key is absent; actor_user_id=decoded JWT sub, session_id from JWT claim | 45 | 10.1-T20, 10.1-T06, 10.1-T08, 10.1-T09, 10.1-T10 | FS | PRD-07, UX-11
10.1-T22 | admin-ui | 10.1 | 10. Admin System | Admin app shell, nav & auth (SSO/2FA) | 1 | Unit tests: login lockout, session expiry, and MFA enforcement edge cases | This is a dedicated test ticket for edge cases in the auth and session logic. Target: backend unit and integration tests (not UI). Uses the actual service layer and in-memory DB or testcontainers. Edge cases to cover: (1) exactly 5 failed logins locks the account; (2) 4 failures do not lock; (3) successful login resets failure counter; (4) JWT idle timeout at exactly 30 minutes; (5) JWT absolute expiry at exactly 8 hours; (6) SUPER_ADMIN with MFA disabled cannot log in; (7) FINANCE_ANALYST with MFA disabled can log in; (8) TOTP code valid in previous 30s window (RFC 6238 allows 1 window drift); (9) recovery code used twice returns error on second use. | • Set up test harness with in-memory or containerised DB seeded with hub_role data from 10.1-T02 • Write test: 4 failed logins -> 5th fails (not locked) -> 5th failure IS the lock trigger (exactly 5); assert is_active=false after 5th, still true after 4th • Write test: successful login after 4 failures resets counter to 0; subsequent 5-failure sequence locks • Write test: mock clock at login+30min-1s; request succeeds; mock clock at login+30min+1s; next request returns SESSION_EXPIRED • Write test for MFA role enforcement: SUPER_ADMIN without MFA returns 403; FINANCE_ANALYST without MFA returns 200 with session JWT | Test file covering 9 named edge-case scenarios, all passing | • Test 1 (lockout): is_active=false after exactly the 5th consecutive failure, not before • Test 3 (reset on success): after successful login, failure counter=0 (5 new failures required to re-lock) • Test 5 (absolute JWT expiry): request at t=8h+1s returns 401 TOKEN_EXPIRED even if session Redis key is still present • Test 6 (SUPER_ADMIN no MFA): POST /admin/auth/login returns 403 MFA_ENROLLMENT_REQUIRED (not 200) • Test 9 (recovery code reuse): second use of same recovery code returns 401 RECOVERY_CODE_USED | 55 | 10.1-T05, 10.1-T06, 10.1-T08 | FS | PRD-07, UX-11
10.1-T23 | admin-ui | 10.1 | 10. Admin System | Admin app shell, nav & auth (SSO/2FA) | 1 | Change-password page UI and post-login redirect logic | When the backend returns must_change=true in the login response, the admin-ui must redirect to /change-password before any other page. POST /admin/auth/change-password (10.1-T07 backend). UI fields: current_password, new_password (show/hide toggles), confirm_new_password (client-side match check). Password policy reminder shown inline: min 12 chars, uppercase, digit, special char. On success: reissue JWT stored in localStorage, navigate to /dashboard. Error handling: 401 INVALID_CURRENT_PASSWORD (inline on current_password field), 422 PASSWORD_RECENTLY_USED (inline on new_password field), 422 PASSWORD_POLICY_VIOLATION (inline with specific rule that failed). | • Create /change-password route; PrivateRoute allows access even with must_change=true • Render three password fields with show/hide eye icons; client-side validation: new_password == confirm_new_password before submitting (show 'Passwords do not match' inline if unequal) • Display password policy checklist (live feedback as user types: checkmark green when rule satisfied, X red when not): length >=12, has uppercase, has digit, has special char • On submit POST /admin/auth/change-password; on 200 update localStorage with new JWT, navigate to /dashboard with success toast 'Password updated successfully' • On error map API error codes to inline field errors as specified in context | ChangePasswordPage.tsx with live policy checklist and all error states handled | • Submitting with new_password != confirm_new_password shows 'Passwords do not match' and does not call API • Live policy checklist shows all 4 rules: length, uppercase, digit, special char; each updates in real-time as user types • 422 PASSWORD_RECENTLY_USED shows inline error on new_password field: 'You have recently used this password' • On success, new JWT is stored in localStorage (different value from the one stored at login) and user reaches /dashboard • Navigating to any other route while must_change=true redirects back to /change-password (PrivateRoute guard) | 45 | 10.1-T16, 10.1-T07 | FS | PRD-07, UX-11
10.1-T24 | admin-ui | 10.1 | 10. Admin System | Admin app shell, nav & auth (SSO/2FA) | 1 | E2E smoke test: full login-to-dashboard flow (local account + TOTP) | This is an automated E2E test (Playwright or Cypress) covering the critical path from unauthenticated to authenticated dashboard state, including MFA. Tests run against a local Docker Compose stack (backend + DB + Redis). Covers: (1) visit /dashboard unauthenticated -> redirect to /login; (2) login with valid email+password; (3) MFA TOTP challenge (use a test TOTP secret deterministic at T=0); (4) arrive at /dashboard; (5) assert sidebar nav items visible; (6) logout and verify redirect to /login. | • Set up Playwright config pointing to localhost:5173 (admin-ui dev server) with backend on localhost:8080 • Seed DB with a SUPER_ADMIN test user, known TOTP secret (base32 JBSWY3DPEHPK3PXP for deterministic codes), must_change=false • Write test 1: navigate to /dashboard -> assert redirect to /login • Write test 2-4: fill email+password -> submit -> TOTP challenge -> enter code from otplib.authenticator.generate(secret) -> assert /dashboard loaded • Write test 5-6: assert sidebar contains 'Dashboard', 'Schemes', 'Users & Roles'; click Logout -> assert /login | Playwright E2E test file (e2e/admin-auth.spec.ts) with 6 assertions, all passing in CI | • Test runs in CI without flakiness (3 consecutive passing runs) • Unauthenticated /dashboard visit is redirected to /login (HTTP 302 or client navigation) • Post-TOTP login lands on /dashboard with page title 'Dashboard' visible • Sidebar shows 'Users & Roles' link (SUPER_ADMIN role) • Logout click results in /login page with empty credential fields | 55 | 10.1-T15, 10.1-T16, 10.1-T23 | FS | PRD-07, UX-11
10.2-T01 | admin-ui | 10.2 | 10. Admin System | Scheme management screens | 2 | DB migration: qr_scheme and scheme_country tables | GMEPay+ stores each QR Payment Scheme as a row in qr_scheme (no code change to add a scheme). Key columns: id BIGINT PK, scheme_code VARCHAR(30) UNIQUE (e.g. ZEROPAY), name VARCHAR(100), payout_ccy CHAR(3), supported_modes VARCHAR(20) (MPM/CPM/BOTH), settlement_counterparty VARCHAR(120), settlement_ccy CHAR(3), settlement_model VARCHAR(10) (NET/GROSS), gme_fee_share_pct DECIMAL(6,4), partner_b_quote_enabled BOOLEAN, partner_b_quote_deviation_pct DECIMAL(6,4) default 0.0100, sftp_host VARCHAR(255) encrypted, sftp_port INT default 22, sftp_username VARCHAR(120) encrypted, sftp_credential_ref VARCHAR(120), sftp_path_inbound VARCHAR(255), sftp_path_outbound VARCHAR(255), api_base_url VARCHAR(512), api_credential_ref VARCHAR(120), integration_type VARCHAR(20) (SFTP/REST/ISO8583), logo_url VARCHAR(512), morning_settlement_cutoff TIME, afternoon_settlement_cutoff TIME, detail_file_cutoff TIME, report_due_day SMALLINT, refund_window_days INT default 90, status VARCHAR(20) default DRAFT, created_at TIMESTAMPTZ, updated_at TIMESTAMPTZ, created_by BIGINT FK hub_user, updated_by BIGINT FK hub_user. Table scheme_country: id BIGINT PK, scheme_id FK, country_code CHAR(2), is_active BOOLEAN, UNIQUE(scheme_id, country_code). Table scheme_merchant_fee: id BIGINT PK, scheme_id FK, merchant_type VARCHAR(60), domestic_rate DECIMAL(6,4), cross_border_rate DECIMAL(6,4), UNIQUE(scheme_id, merchant_type). | • Create Flyway/Liquibase migration file V10_2_001__scheme_tables.sql • Add qr_scheme table with all columns listed in context; sensitive columns (sftp_host, sftp_username, sftp_credential_ref, api_credential_ref) are nullable varchars - encryption is applied at service layer • Add scheme_country table with UNIQUE(scheme_id, country_code) and FK to qr_scheme • Add scheme_merchant_fee table with UNIQUE(scheme_id, merchant_type) and FK to qr_scheme • Add indexes: qr_scheme(scheme_code), qr_scheme(status), scheme_country(scheme_id), scheme_merchant_fee(scheme_id) • Run migration against local test DB and confirm schema matches spec | Migration file V10_2_001__scheme_tables.sql applied cleanly with all three tables and indexes present | • INSERT into qr_scheme with scheme_code=ZEROPAY succeeds; duplicate scheme_code rejected with unique constraint • INSERT into scheme_country (scheme_id=1, country_code=KR) twice raises unique violation • scheme_merchant_fee row with domestic_rate=0.0080 and cross_border_rate=0.0170 stores and retrieves with 4 decimal precision • Dropping scheme_country row when referenced by active payment does NOT cascade delete qr_scheme (FK is scheme_country.scheme_id -> qr_scheme.id only) • Migration rolls back cleanly via DOWN script (DROP TABLE in reverse order) | 30 |  | FS | PRD-07
10.2-T02 | admin-ui | 10.2 | 10. Admin System | Scheme management screens | 2 | Backend: SchemeRepository CRUD and status-lifecycle transitions | The qr_scheme table (see 10.2-T01) has status VARCHAR(20) with lifecycle: DRAFT -> TESTING -> ACTIVE -> SUSPENDED. Only DRAFT and TESTING statuses allow unrestricted field edits; ACTIVE and SUSPENDED are restricted (connectivity and fee fields can still be edited by SUPER_ADMIN). Activation requires: integration_type set, sftp_host/api_base_url set (per type), >= 1 active scheme_country row, payout_ccy non-null, >= 1 scheme_merchant_fee row. No UPDATE or DELETE on audit columns; updated_by/updated_at set on every write. Use Spring Data JPA or plain JPA repository. | • Create SchemeRepository (JPA) with findBySchemeCode, findAllByStatus, existsBySchemeCode methods • Create SchemeService with createScheme, updateScheme, getScheme, listSchemes methods • Implement SchemeService.transitionStatus(schemeId, targetStatus, actorId): validates allowed transitions (DRAFT->TESTING, TESTING->ACTIVE, ACTIVE->SUSPENDED, SUSPENDED->ACTIVE); for ACTIVE transition, runs activation prerequisite checks; throws SchemeTransitionException with reason on violation • Implement activation prerequisite check method returning list of unmet conditions • Add @Transactional on createScheme and updateScheme; set updated_by=actorId, updated_at=now() on every save • Write unit tests for transitionStatus covering each valid and invalid transition | SchemeRepository + SchemeService classes with status transition logic and activation prerequisite validation | • transitionStatus(DRAFT -> ACTIVE) throws SchemeTransitionException listing unmet prerequisites when fee table is empty • transitionStatus(TESTING -> ACTIVE) with all prerequisites met sets status=ACTIVE and persists • transitionStatus(ACTIVE -> DRAFT) throws SchemeTransitionException (invalid transition) • transitionStatus(ACTIVE -> SUSPENDED) succeeds and sets status=SUSPENDED • createScheme sets status=DRAFT, created_at=now, created_by=actorId on first persist | 45 | 10.2-T01 | FS | PRD-07
10.2-T03 | admin-ui | 10.2 | 10. Admin System | Scheme management screens | 2 | Backend: SchemeConnectivityService - SFTP test and credential encryption | Scheme connectivity config (sftp_host, sftp_port, sftp_username, sftp_credential_ref, sftp_path_inbound, sftp_path_outbound, api_base_url, api_credential_ref) must be stored encrypted at rest (AES-256). Plaintext is never logged. A Test Connection action must attempt an SFTP connection (JSch library) or HTTP GET to api_base_url and return success/failure within 10 seconds timeout. integration_type determines which test to run: SFTP tries sftp.stat on inbound path; REST tries HTTP GET on api_base_url with auth header. Credentials are stored in DB column api_credential_ref / sftp_credential_ref as AES-256 encrypted blobs (key from application secrets / Vault). The Connectivity test result is stored as last_connectivity_test_at, last_connectivity_test_result (SUCCESS/FAILURE/TIMEOUT), last_connectivity_test_message on qr_scheme. | • Add columns last_connectivity_test_at, last_connectivity_test_result VARCHAR(10), last_connectivity_test_message VARCHAR(255) to qr_scheme via migration V10_2_002 • Create CredentialEncryptionService with encrypt(plaintext) and decrypt(ciphertext) using AES-256-GCM; key injected from environment/Vault; never log plaintext • Create SchemeConnectivityService.testConnection(schemeId): decrypt credentials, attempt SFTP stat or HTTP GET per integration_type, enforce 10s timeout, persist test result columns, return TestConnectionResult(success, message) • Ensure decrypt errors surface as SchemeConfigException (not null pointer); sensitive fields are never included in exception messages or logs • Write unit tests for CredentialEncryptionService round-trip and for testConnection with mocked SFTP/HTTP clients | Migration V10_2_002, CredentialEncryptionService, SchemeConnectivityService with test-connection logic | • encrypt then decrypt returns identical plaintext for a 64-char password • testConnection with mocked SFTP returning connection refused stores last_connectivity_test_result=FAILURE and message contains host:port • testConnection with mocked SFTP success stores last_connectivity_test_result=SUCCESS • Plaintext credential does not appear in any log output at INFO or DEBUG level during test • testConnection times out after 10s and stores TIMEOUT result when SFTP server hangs | 50 | 10.2-T01 | FS | PRD-07
10.2-T04 | admin-ui | 10.2 | 10. Admin System | Scheme management screens | 2 | Backend: REST API - GET /admin/schemes and GET /admin/schemes/{id} | The Admin System frontend fetches scheme list and detail from backend REST endpoints secured by the portal's RBAC (role OPS_OPERATOR, OPS_ADMIN, FINANCE_ANALYST, SUPER_ADMIN may view scheme config; ADMIN_VIEWER may not). Roles are stored in hub_role table with role_code. Scheme list returns: id, scheme_code, name, payout_ccy, supported_modes, supported_countries (array of country_code), status, last_connectivity_test_result, updated_at. Scheme detail additionally returns all fields except plaintext credentials (sftp_credential_ref and api_credential_ref return masked string '***'). Pagination: page and size query params; default size=20. Filter params: status (optional multi-value). | • Create SchemeController with GET /admin/schemes (paginated, filterable by status) and GET /admin/schemes/{id} • Add @PreAuthorize or role-check ensuring only OPS_OPERATOR/OPS_ADMIN/FINANCE_ANALYST/SUPER_ADMIN may call; ADMIN_VIEWER gets 403 • Map qr_scheme + scheme_country to SchemeListDto and SchemeDetailDto; mask sftp_credential_ref and api_credential_ref as '***' in response • Include supported_countries as string[] in both DTOs derived from scheme_country table • Write integration test: seed one ZEROPAY scheme; GET /admin/schemes returns it; GET /admin/schemes/1 returns full detail with credentials masked • Write test: call with ADMIN_VIEWER token -> 403 | SchemeController with GET /admin/schemes and GET /admin/schemes/{id}, SchemeListDto, SchemeDetailDto | • GET /admin/schemes with no filters returns paginated list; total reflects DB count • GET /admin/schemes?status=ACTIVE returns only ACTIVE records • GET /admin/schemes/{id} response does NOT contain plaintext sftp_credential value; field shows '***' • GET /admin/schemes/{id} for non-existent id returns 404 with error body • Call with ADMIN_VIEWER JWT returns HTTP 403 | 40 | 10.2-T02 | FS | PRD-07
10.2-T05 | admin-ui | 10.2 | 10. Admin System | Scheme management screens | 2 | Backend: REST API - POST /admin/schemes (create scheme) | OPS_OPERATOR and OPS_ADMIN (not FINANCE_ANALYST) may create a new scheme. Body includes Identity Section fields: scheme_code (uppercase alphanumeric, max 20, unique), name (max 100, unique), logo_url (optional HTTPS URL), supported_modes (MPM/CPM/BOTH), payout_ccy (must exist in currency registry), status defaults to DRAFT. Connectivity Section fields: integration_type (SFTP/REST/ISO8583), sftp_host, sftp_port (default 22), sftp_username, sftp_password (plaintext in request body - encrypted at rest by service), sftp_path_inbound, sftp_path_outbound, api_base_url, api_key, api_secret (plaintext in request). Settlement Terms: settlement_counterparty, settlement_ccy, settlement_model (NET/GROSS), gme_fee_share_pct (0-100), morning_settlement_cutoff (TIME KST), afternoon_settlement_cutoff, detail_file_cutoff, report_due_day (1-28 or 0 for EOM). Supported countries NOT part of create body - added separately. On success, audit log entry with event=scheme.created, actor_user_id, entity_id, new_value=serialized scheme. | • Create SchemeCreateRequest DTO with JSR-303 validation: scheme_code @Pattern([A-Z0-9]{1,20}), name @Size(max=100), logo_url @Pattern(https://.*) if present, payout_ccy existence checked in service • Implement POST /admin/schemes in SchemeController; @PreAuthorize OPS_OPERATOR or OPS_ADMIN • In SchemeService.createScheme: encrypt SFTP/API credentials before persisting, set status=DRAFT, set created_by=actorId • After persist, write AuditLogEntry(event=scheme.created, entity_type=scheme, entity_id=newId, new_value=JSON of scheme, actor_user_id, timestamp=now) • Return 201 with SchemeDetailDto (credentials masked) • Write tests: valid payload creates record; duplicate scheme_code returns 409; invalid logo_url (HTTP) returns 400 | POST /admin/schemes endpoint with validation, encryption, and audit log write on creation | • POST with scheme_code=ZEROPAY, valid fields returns 201 and response body contains id, status=DRAFT • POST with duplicate scheme_code=ZEROPAY returns 409 Conflict • POST with logo_url=http://... (not HTTPS) returns 400 with field error on logo_url • AuditLog table contains one row with event=scheme.created and entity_id matching returned id • SFTP password in DB column sftp_credential_ref is not stored in plaintext (decrypt and compare to verify encryption applied) | 50 | 10.2-T03, 10.2-T04 | FS | PRD-07
10.2-T06 | admin-ui | 10.2 | 10. Admin System | Scheme management screens | 2 | Backend: REST API - PUT /admin/schemes/{id} (update scheme) | OPS_OPERATOR and OPS_ADMIN may edit a scheme. Edits are allowed when status=DRAFT or TESTING with no field restrictions. When status=ACTIVE or SUSPENDED, only connectivity fields and settlement terms are editable (scheme_code and name are immutable after ACTIVE). Audit log must record previous_value and new_value for every changed field individually (field-level granularity, event=scheme.field_changed). All changes apply only to new transactions; committed transactions retain locked values. The response is SchemeDetailDto with credentials masked. | • Create SchemeUpdateRequest DTO; scheme_code field is ignored (immutable) when status=ACTIVE • Implement PUT /admin/schemes/{id} in SchemeController with @PreAuthorize OPS_OPERATOR or OPS_ADMIN • In SchemeService.updateScheme: load current state, compare field-by-field, for each changed field write AuditLogEntry with event=scheme.field_changed, field, previous_value, new_value • Enforce immutability guard: if status=ACTIVE and attempt to change scheme_code or name, return 422 with message • Re-encrypt credentials if they are included in the body (non-null credential fields trigger re-encryption) • Write tests: update name on DRAFT scheme audits correctly; attempt to change scheme_code on ACTIVE scheme returns 422 | PUT /admin/schemes/{id} endpoint with field-level audit logging and ACTIVE immutability guard | • Updating name from ZeroPay to ZeroPay v2 on a DRAFT scheme creates one AuditLogEntry with field=name, previous_value=ZeroPay, new_value=ZeroPay v2 • Updating scheme_code on an ACTIVE scheme returns 422 and no audit entry is created • PUT with a changed sftp_host re-encrypts and persists the new value (decrypt to verify) • PUT with no changed fields (same values) creates zero AuditLogEntry rows • updated_at and updated_by are set to current time and actor on every PUT | 45 | 10.2-T05 | FS | PRD-07
10.2-T07 | admin-ui | 10.2 | 10. Admin System | Scheme management screens | 2 | Backend: REST API - PATCH /admin/schemes/{id}/status (activate/suspend) | Status transitions are: DRAFT->TESTING->ACTIVE->SUSPENDED and SUSPENDED->ACTIVE. Only OPS_OPERATOR and OPS_ADMIN may change status. Activating requires all prerequisites: integration_type set, connectivity credentials set (sftp_host for SFTP, api_base_url for REST), >= 1 active scheme_country, payout_ccy non-null, >= 1 scheme_merchant_fee row. If prerequisites not met, return 422 with array of unmet conditions. A confirmation step is represented by a required body field confirmed=true; if false or absent, return 400. Audit log entry: event=scheme.status_changed, previous_value=old status, new_value=new status. | • Create SchemeStatusChangeRequest {targetStatus: enum, confirmed: boolean} • Implement PATCH /admin/schemes/{id}/status in SchemeController • Delegate to SchemeService.transitionStatus from 10.2-T02; catch SchemeTransitionException and map to 422 response with unmet conditions array • If confirmed=false return 400 {error: confirmation required} • Write AuditLogEntry(event=scheme.status_changed, previous_value, new_value) on success • Write tests: activate with all prerequisites met and confirmed=true succeeds; activate with missing merchant fee returns 422 listing that condition; suspend an ACTIVE scheme succeeds | PATCH /admin/schemes/{id}/status endpoint with prerequisite validation and confirmation guard | • PATCH with targetStatus=ACTIVE, confirmed=true, all prerequisites met returns 200 and status=ACTIVE • PATCH with targetStatus=ACTIVE, confirmed=true but scheme has 0 scheme_country rows returns 422 with unmet_conditions containing supported_countries • PATCH with confirmed=false returns 400 • PATCH with targetStatus=DRAFT on an ACTIVE scheme returns 422 (invalid transition) • AuditLogEntry with event=scheme.status_changed is written exactly once on success | 35 | 10.2-T02, 10.2-T06 | FS | PRD-07
10.2-T08 | admin-ui | 10.2 | 10. Admin System | Scheme management screens | 2 | Backend: REST API - scheme_country endpoints (add/remove countries) | The scheme_country table maps a scheme to ISO 3166-1 alpha-2 country codes. These are managed separately from the main scheme form. Endpoints: POST /admin/schemes/{id}/countries body {country_code: KR}, DELETE /admin/schemes/{id}/countries/{countryCode}. OPS_OPERATOR and OPS_ADMIN only. Removing the last country from an ACTIVE scheme is blocked (status must not be ACTIVE if the result would leave 0 countries). Audit log: event=scheme.country_added or scheme.country_removed. | • Create SchemeCountryController with POST /admin/schemes/{id}/countries and DELETE /admin/schemes/{id}/countries/{countryCode} • Validate country_code is a valid ISO 3166-1 alpha-2 code (use Java Locale or static set) • For DELETE: if scheme status=ACTIVE and this is the last country, return 422 {error: cannot remove last country from active scheme} • Write audit log entry on each add/remove • Return updated supported_countries array in 200 response • Write tests: add KR, then JP; list shows both; delete KR; list shows JP; delete JP on ACTIVE scheme returns 422 | SchemeCountryController with add/delete endpoints, last-country guard for ACTIVE schemes, and audit entries | • POST /admin/schemes/1/countries {country_code:KR} inserts row and returns supported_countries=[KR] • Duplicate POST /admin/schemes/1/countries {country_code:KR} returns 409 • DELETE /admin/schemes/1/countries/KR when scheme is ACTIVE and KR is the only country returns 422 • DELETE succeeds when scheme has 2 countries; remaining country still present • Invalid country_code=XX returns 400 | 35 | 10.2-T06 | FS | PRD-07
10.2-T09 | admin-ui | 10.2 | 10. Admin System | Scheme management screens | 2 | Backend: REST API - scheme_merchant_fee endpoints (CRUD fee table) | The scheme_merchant_fee table (scheme_id FK, merchant_type VARCHAR(60), domestic_rate DECIMAL(6,4), cross_border_rate DECIMAL(6,4)) stores fee rates per merchant type. ZeroPay reference values: General=0.0080/0.0170. merchant_type codes must match ZeroPay batch file codes (ZP0041/ZP0051) - stored as free text until confirmed with KFTC (Assumption A-06). Endpoints: GET /admin/schemes/{id}/merchant-fees, POST /admin/schemes/{id}/merchant-fees, PUT /admin/schemes/{id}/merchant-fees/{feeId}, DELETE /admin/schemes/{id}/merchant-fees/{feeId}. OPS_OPERATOR and OPS_ADMIN only. Audit log on every write: event=scheme.fee_row_added/updated/deleted. | • Create SchemeFeeCRUDController with GET/POST/PUT/DELETE for /admin/schemes/{id}/merchant-fees • Validate domestic_rate and cross_border_rate in [0.0000, 1.0000]; max 4 decimal places • Enforce UNIQUE(scheme_id, merchant_type) - duplicate merchant_type returns 409 • Write audit log entry on POST, PUT, DELETE • Return full fee table list in every mutating response • Write tests: create General fee, update domestic_rate, delete it; duplicate merchant_type rejected; invalid rate=1.5 rejected | SchemeFeeCRUDController with full CRUD, validation, and audit logging | • POST with merchant_type=General, domestic_rate=0.0080, cross_border_rate=0.0170 returns 201 and persists with 4 decimal precision • PUT updating domestic_rate to 0.0090 creates AuditLogEntry with field=domestic_rate, previous_value=0.0080, new_value=0.0090 • POST with duplicate merchant_type=General returns 409 • POST with domestic_rate=1.5 returns 400 (rate must be <= 1.0) • GET /admin/schemes/{id}/merchant-fees returns all fee rows for that scheme | 35 | 10.2-T06 | FS | PRD-07
10.2-T10 | admin-ui | 10.2 | 10. Admin System | Scheme management screens | 2 | Backend: POST /admin/schemes/{id}/test-connection endpoint | A Test Connection button in the UI calls this endpoint. It invokes SchemeConnectivityService.testConnection (10.2-T03) for the given scheme. Result is returned immediately to the caller (synchronous, max 10s timeout). The endpoint persists last_connectivity_test_at, last_connectivity_test_result (SUCCESS/FAILURE/TIMEOUT), last_connectivity_test_message on qr_scheme. Returns 200 with {result: SUCCESS/FAILURE/TIMEOUT, message: ..., tested_at: ISO8601}. OPS_OPERATOR and OPS_ADMIN only. Audit log: event=scheme.connectivity_tested, result. | • Add POST /admin/schemes/{id}/test-connection to SchemeController • Call SchemeConnectivityService.testConnection(schemeId) with 10s HTTP/SFTP timeout • Persist test result columns via SchemeRepository.updateConnectivityTestResult(schemeId, result, message, testedAt) • Write AuditLogEntry(event=scheme.connectivity_tested, entity_id=schemeId, new_value={result,message}) • Return 200 {result, message, tested_at} regardless of connection outcome (connection failure is not an HTTP error) • Write tests: mocked SFTP success -> result=SUCCESS; mocked timeout -> result=TIMEOUT; scheme not found -> 404 | POST /admin/schemes/{id}/test-connection endpoint wired to SchemeConnectivityService | • Call on a scheme with mocked SFTP success returns 200 {result:SUCCESS} • Call on a scheme with mocked SFTP failure returns 200 {result:FAILURE, message contains reason} • last_connectivity_test_result and last_connectivity_test_at columns updated after each call • AuditLogEntry with event=scheme.connectivity_tested written on every call • Call on non-existent scheme_id returns 404 | 30 | 10.2-T03, 10.2-T06 | FS | PRD-07
10.2-T11 | admin-ui | 10.2 | 10. Admin System | Scheme management screens | 2 | Frontend: Scheme List screen component | The Schemes module in the Admin portal (left-nav item Schemes) renders a table with columns: Scheme Name, Scheme Code, Payout Currency, Supported Countries (comma-separated codes), Supported Modes, Status badge (Draft=grey/Testing=blue/Active=green/Suspended=red), Last Updated. Actions per row: View, Edit, Activate/Suspend (toggle based on status), View Rules. Data fetched from GET /admin/schemes (paginated, size=20). Filter by Status via dropdown (multi-select). RBAC: render Edit and Activate/Suspend buttons only if user role is OPS_OPERATOR or OPS_ADMIN; hide from FINANCE_ANALYST. No horizontal scrolling - table max 6 visible columns (Supported Countries shown as count with tooltip if > 3). | • Create SchemeListPage component (React or Vue per project stack) that fetches GET /admin/schemes on mount with page and status filter params • Render table with columns: Name, Code, Payout Ccy, Countries (count badge + tooltip), Modes, Status badge, Last Updated, Actions • Implement status color badges: DRAFT=grey, TESTING=blue, ACTIVE=green, SUSPENDED=amber/red • Show Edit and Activate/Suspend action buttons only when user role is OPS_OPERATOR or OPS_ADMIN • Implement Status filter dropdown (multi-select) that refetches data on change • Add pagination controls (previous/next, page indicator) • Add New Scheme button linking to create form (visible to OPS_OPERATOR/OPS_ADMIN) | SchemeListPage component rendering scheme table with filter, pagination, RBAC-gated actions | • Rendering with 3 ACTIVE and 1 DRAFT scheme shows 4 rows; DRAFT row has grey badge, ACTIVE rows have green badge • Selecting status filter=ACTIVE fetches GET /admin/schemes?status=ACTIVE and re-renders with filtered rows • FINANCE_ANALYST user sees no Edit or Activate/Suspend buttons in actions column • Country column with [KR, JP, SG, US, TH] shows count badge 5 with tooltip listing all codes • Pagination: with 25 schemes (size=20) shows page 1 of 2 and Next button | 45 | 10.2-T04 | FS | PRD-07
10.2-T12 | admin-ui | 10.2 | 10. Admin System | Scheme management screens | 2 | Frontend: Scheme Create/Edit form - Identity section | The Create/Edit Scheme form is organized into three sections rendered on a single page: Identity, Connectivity Configuration, and Settlement Terms. The Identity section (PRD-07 §4.3.1) contains: Scheme Name (text, required, max 100), Scheme Code (text, required, uppercase alphanumeric max 20, unique - validated on blur via API), Logo URL (optional, must be HTTPS if provided), Supported Countries (multi-select from ISO 3166-1 alpha-2 list), Supported Payment Modes (checkboxes: MPM, CPM - at least 1 required), Payout Currency (select from currency registry), Status (display-only on edit; select on create defaulting to DRAFT). On create: POST /admin/schemes. On edit: PUT /admin/schemes/{id} with full body. | • Create SchemeFormPage component with mode prop (create/edit); on edit mode, fetch GET /admin/schemes/{id} to pre-populate fields • Implement Identity section with JSR-like client-side validation: scheme_code @pattern /^[A-Z0-9]{1,20}$/, name maxLength 100, logo_url must start with https:// if non-empty, >= 1 country selected, >= 1 mode checked • Add scheme_code uniqueness check on blur: call GET /admin/schemes?code={value} and display inline error if duplicate • Implement Supported Countries multi-select with search; show ISO code + country name in dropdown • Show Status as read-only display badge on edit; show select (defaulting to DRAFT) on create • Inline validation errors appear adjacent to fields without requiring Save click | SchemeFormPage Identity section with client-side validation, scheme_code uniqueness check, and country multi-select | • Entering scheme_code=zeropay auto-uppercases to ZEROPAY and validates pattern • Entering scheme_code matching an existing scheme shows inline error: Scheme code already exists • Logo URL http://example.com shows inline error: must be HTTPS • Clearing all Supported Countries shows inline error: at least 1 country required • On edit mode, Status field is non-editable and shows current status badge | 45 | 10.2-T11 | FS | PRD-07
10.2-T13 | admin-ui | 10.2 | 10. Admin System | Scheme management screens | 2 | Frontend: Scheme Create/Edit form - Connectivity Configuration section | The Connectivity section (PRD-07 §4.3.2) shows fields conditional on integration_type. SFTP fields: SFTP Host (required), SFTP Port (integer, default 22), SFTP Username (required), SFTP Password/Key (secret input, masked, required - send as plaintext in HTTPS request body to POST/PUT endpoint which encrypts at rest; on edit, show placeholder '***' and only overwrite if operator types a new value), SFTP Inbound Path, SFTP Outbound Path. REST fields: API Base URL (required, HTTPS), API Key (required), API Secret (masked, same masking rule as SFTP password). A Test Connection button calls POST /admin/schemes/{id}/test-connection (only available in edit mode after initial save). Shows result inline: green SUCCESS or red FAILURE/TIMEOUT with message. | • Add Connectivity section to SchemeFormPage below Identity section • Conditionally render SFTP or REST fields based on integration_type select value • For password/secret fields: use type=password input; on edit mode pre-fill with placeholder '***'; only include in PUT body if the value differs from '***' • Implement Test Connection button (edit mode only): call POST /admin/schemes/{id}/test-connection, show spinner, then display inline result badge (SUCCESS green / FAILURE red / TIMEOUT amber) with message • Validate SFTP Host is non-empty when integration_type=SFTP; API Base URL is HTTPS when integration_type=REST • Write component unit tests for conditional field rendering and masked secret handling | Connectivity Configuration section with conditional fields, masked secrets, and inline Test Connection result | • Switching integration_type from SFTP to REST hides SFTP fields and shows REST fields • Password field shows placeholder *** on edit mode; submitting without changing *** does NOT overwrite stored credential • Test Connection button absent in create mode; present and clickable in edit mode • Test Connection returning SUCCESS renders green badge; FAILURE renders red badge with message text • SFTP Port defaults to 22 on create; clears to empty when integration_type switches to REST | 45 | 10.2-T12, 10.2-T10 | FS | PRD-07
10.2-T14 | admin-ui | 10.2 | 10. Admin System | Scheme management screens | 2 | Frontend: Scheme Create/Edit form - Settlement Terms section and Merchant Fee Table | Settlement Terms section (PRD-07 §4.3.3): Settlement Counterparty Name (text, required), Settlement Currency (ISO 4217 select, required), Settlement Model (NET/GROSS select, required), GME Fee Share % (decimal 0-100, required, e.g. 70 for ZeroPay), Morning Settlement Batch Cutoff (time KST, required for SFTP), Afternoon Settlement Batch Cutoff (time KST, optional), Detail File Cutoff (time KST, optional), Report Due Day (integer 1-28 or 0=EOM). Merchant Fee Table (PRD-07 §4.3.4): a structured table below the terms; each row has merchant_type (text), domestic_rate (%, 4 decimal places), cross_border_rate (%, 4 decimal places). Add/Remove row buttons. ZeroPay default row: General, 0.80%, 1.70%. On save, fee table rows are submitted to POST/PUT /admin/schemes/{id}/merchant-fees separately after the main form save. | • Add Settlement Terms fields to SchemeFormPage with validation: gme_fee_share_pct in [0,100], morning_settlement_cutoff required if integration_type=SFTP, report_due_day in [0,28] • Add Merchant Fee Table component below Settlement Terms: array of rows {merchant_type, domestic_rate, cross_border_rate}; Add Row button appends empty row; Remove button on each row • Pre-populate merchant fee table from GET /admin/schemes/{id}/merchant-fees on edit mode • On form save: first save main scheme (POST or PUT), then synchronize fee table rows (POST new rows, PUT changed rows, DELETE removed rows) via scheme-fees endpoints • Validate each fee table row: domestic_rate and cross_border_rate in [0, 100]% (displayed as %, stored as decimal 0-1) • Display conversion: UI shows 0.80% for stored value 0.0080 | Settlement Terms section, Merchant Fee Table with add/remove rows, and fee table save logic | • Entering gme_fee_share_pct=110 shows inline error: must be between 0 and 100 • Adding a row with merchant_type=General, domestic_rate=0.80, cross_border_rate=1.70 saves and retrieves correctly as 0.0080/0.0170 • Removing a fee row marks it for deletion; on save it is deleted via DELETE endpoint • Morning Settlement Batch Cutoff field shows required indicator when integration_type=SFTP • Report Due Day=0 treated as EOM in display label | 40 | 10.2-T13, 10.2-T09 | FS | PRD-07
10.2-T15 | admin-ui | 10.2 | 10. Admin System | Scheme management screens | 2 | Frontend: Scheme form - Review Changes diff, Save, and Activate/Suspend flow | PRD-07 §4.3.5 and §14.2: before saving an existing scheme, a Review Changes diff dialog shows previous vs new values per field. The Save button is labeled Save Changes for edit, Create Scheme for create. Activating a scheme (status transition to ACTIVE) requires a confirmation dialog stating the prerequisites and requiring explicit confirm. Activation prerequisites: connectivity test passed (last_connectivity_test_result=SUCCESS), >= 1 supported country, payout_ccy set, >= 1 merchant fee row. If any unmet, dialog lists them and disables Confirm. The Activate/Suspend status change calls PATCH /admin/schemes/{id}/status. The list and form pages must refresh after status change. Audit trail link: a View Audit History tab/link opens the scheme audit log view (see 10.2-T18). | • Implement Review Changes modal: on edit form submit, compute changed fields, show table with Field / Previous / New columns, Confirm Save and Cancel buttons • Wire Confirm Save to PUT /admin/schemes/{id}; on success close modal and navigate to scheme detail or list • Implement Activate button on scheme detail/edit page: fetch prerequisites status, open confirmation dialog listing prerequisites with green/red indicators, enable Confirm only when all prerequisites met • Wire Confirm Activate to PATCH /admin/schemes/{id}/status {targetStatus:ACTIVE, confirmed:true} • Implement Suspend confirmation dialog: shows current status and target; requires confirmation • Refresh scheme data in list and form after any status change | Review Changes diff modal, Save flow, Activate confirmation dialog with prerequisite checklist, Suspend confirmation dialog | • Editing only name field shows diff table with 1 row: field=Scheme Name, Previous=old name, New=new name; unchanged fields absent • Activate dialog shows all 4 prerequisites; a scheme missing merchant fees shows that item in red and Confirm disabled • Activate dialog with all prerequisites met shows all items green; Confirm enabled; click triggers PATCH • Suspend confirmation requires explicit confirm; clicking Cancel does not change status • After successful Activate, scheme list row shows status badge=ACTIVE (green) | 40 | 10.2-T14, 10.2-T07 | FS | PRD-07
10.2-T16 | admin-ui | 10.2 | 10. Admin System | Scheme management screens | 2 | Frontend: Scheme Detail (read-only view) with status and connectivity summary | Clicking View on the scheme list opens a read-only Scheme Detail page. It shows all fields organized in the same three sections (Identity, Connectivity, Settlement Terms) but in read-only display mode. Connectivity section shows masked credentials ('***') and the last_connectivity_test_result with timestamp (e.g. green SUCCESS 2026-06-01 14:32 KST). The Merchant Fee Table is shown read-only. Supported Countries are shown as a list of country name + code badges. A tab bar provides: Overview (main detail), Merchant Fees, Audit History, Rules (links to rule list filtered by this scheme). RBAC: ADMIN_VIEWER cannot see this page at all (403 if accessed directly). Actions panel: Edit (OPS only), Activate/Suspend (OPS only), Test Connection (OPS only). | • Create SchemeDetailPage fetching GET /admin/schemes/{id} and GET /admin/schemes/{id}/merchant-fees on load • Render three read-only sections; credential fields show *** ; last_connectivity_test_result shown as colored badge with timestamp formatted as KST • Add tab bar: Overview, Merchant Fees, Audit History (loads 10.2-T18 component), Rules (links to /rules?scheme_id={id}) • Show Edit / Activate/Suspend / Test Connection action buttons only for OPS_OPERATOR and OPS_ADMIN roles • Show 404 page if scheme not found • Write component test: ADMIN_VIEWER context hides action buttons | SchemeDetailPage with tabbed layout, read-only sections, masked credentials, and RBAC-gated actions | • sftp_password / api_secret fields display as *** in all view modes • last_connectivity_test_result=SUCCESS renders green badge; last_connectivity_test_result=FAILURE renders red badge • ADMIN_VIEWER user sees no Edit, Activate/Suspend, or Test Connection buttons • Audit History tab loads scheme-scoped audit entries (entity_type=scheme, entity_id={id}) • Rules tab link navigates to Rules list pre-filtered by scheme | 35 | 10.2-T15 | FS | PRD-07
10.2-T17 | admin-ui | 10.2 | 10. Admin System | Scheme management screens | 2 | Backend: AuditLogService - scheme entity logging and query endpoint | All scheme write operations (create, update field, status change, connectivity test, country add/remove, fee row add/update/delete) must write to an audit_log table. Schema: id UUID PK, timestamp_utc TIMESTAMPTZ, actor_user_id BIGINT FK hub_user, actor_display_name VARCHAR(120), actor_ip VARCHAR(45), event_type VARCHAR(60) (e.g. scheme.created, scheme.field_changed, scheme.status_changed, scheme.country_added, scheme.fee_row_updated, scheme.connectivity_tested), entity_type VARCHAR(30), entity_id BIGINT, field_name VARCHAR(60) nullable, previous_value TEXT nullable, new_value TEXT nullable, description TEXT, metadata JSONB. Table is insert-only (no UPDATE/DELETE). Query endpoint: GET /admin/audit-log?entity_type=scheme&entity_id={id}&page=0&size=50 returns paginated log for that scheme. Filtered and sortable by timestamp DESC. | • Create migration V10_2_003__audit_log_table.sql: audit_log table with all columns; no FK constraint on entity_id (cross-entity); index on (entity_type, entity_id), (actor_user_id), (timestamp_utc) • Create AuditLogService.log(AuditLogEntry) that inserts a row; never throws (catches and logs internally to prevent audit failure from blocking the main operation) • Create GET /admin/audit-log endpoint with query params: entity_type, entity_id, actor_user_id, event_type, date_from, date_to; paginated, sorted timestamp DESC • Enforce RBAC: OPS_OPERATOR, OPS_ADMIN, SUPER_ADMIN may query; FINANCE_ANALYST and ADMIN_VIEWER may not • Write migration to set DB-level INSERT-only permission for app service account on audit_log (or document this as a DBA step) • Write test: log 3 entries for scheme_id=1; GET /admin/audit-log?entity_type=scheme&entity_id=1 returns 3 rows in reverse-timestamp order | Migration V10_2_003, AuditLogService, GET /admin/audit-log endpoint | • INSERT into audit_log via AuditLogService.log() persists; direct UPDATE on audit_log from app service account returns permission denied • GET /admin/audit-log?entity_type=scheme&entity_id=5 returns only entries with entity_type=scheme AND entity_id=5 • Results are ordered timestamp_utc DESC • FINANCE_ANALYST calling GET /admin/audit-log returns 403 • AuditLogService.log() does not throw and does not block calling code when DB is temporarily unavailable (exception is swallowed and logged at ERROR) | 45 | 10.2-T01 | FS | PRD-07
10.2-T18 | admin-ui | 10.2 | 10. Admin System | Scheme management screens | 2 | Frontend: Scheme Audit History tab component | The Audit History tab on SchemeDetailPage (10.2-T16) loads GET /admin/audit-log?entity_type=scheme&entity_id={id} and renders a table with columns: Timestamp (UTC + KST dual display), Actor (display name + user ID), Event Type, Field Changed, Previous Value, New Value, Effective From. Paginated (50 per page). A CSV Export button calls the same endpoint with page=0&size=10000 and downloads result as audit_scheme_{id}_{date}.csv. OPS_OPERATOR, OPS_ADMIN, SUPER_ADMIN only (enforced by API; UI hides the tab for other roles). | • Create SchemeAuditHistoryTab component accepting schemeId prop • Fetch GET /admin/audit-log?entity_type=scheme&entity_id={schemeId}&page={page}&size=50 on mount and on page change • Render table: Timestamp (formatted as YYYY-MM-DD HH:mm:ss UTC / KST), Actor, Event Type chip, Field Changed, Previous Value, New Value • Add pagination; Previous/Next controls and page indicator • Implement CSV Export button: fetch with size=10000, convert JSON to CSV, trigger browser download with filename audit_scheme_{id}_{date}.csv • Write component test: 3 audit entries render as 3 table rows; page 2 fetches with page=1 | SchemeAuditHistoryTab component with table, pagination, and CSV export | • Rendering 3 audit entries shows 3 table rows with correct field values • Timestamp column shows both UTC and KST values • CSV export download contains header row and one data row per audit entry • Page 2 button fetches GET /admin/audit-log?...&page=1 • Tab is not rendered in DOM for ADMIN_VIEWER user context | 35 | 10.2-T17, 10.2-T16 | FS | PRD-07
10.2-T19 | admin-ui | 10.2 | 10. Admin System | Scheme management screens | 2 | Unit tests: SchemeService status lifecycle and activation prerequisite logic | SchemeService (10.2-T02) contains the status transition guard and activation prerequisite check. This ticket writes comprehensive unit tests (JUnit 5 + Mockito) covering all valid and invalid transitions and all combinations of unmet prerequisites. Prerequisites for ACTIVE: integration_type non-null, credentials set (sftp_host non-null for SFTP / api_base_url non-null for REST), scheme_country count >= 1, payout_ccy non-null, scheme_merchant_fee count >= 1. No live DB required; mock SchemeRepository and SchemeCountryRepository. | • Write test class SchemeServiceTransitionTest with mocked repositories • Test case: transitionStatus(DRAFT->TESTING) always succeeds regardless of prerequisites • Test case: transitionStatus(TESTING->ACTIVE) with 0 scheme_country rows throws SchemeTransitionException with cause=NO_COUNTRIES • Test case: transitionStatus(TESTING->ACTIVE) with integration_type=SFTP and sftp_host=null throws with cause=MISSING_CONNECTIVITY_CONFIG • Test case: transitionStatus(TESTING->ACTIVE) with all 5 prerequisites met succeeds • Test case: transitionStatus(ACTIVE->DRAFT) throws (invalid transition) • Test case: transitionStatus(SUSPENDED->ACTIVE) with all prerequisites met succeeds (reactivation) • Test case: transitionStatus(ACTIVE->SUSPENDED) always succeeds | SchemeServiceTransitionTest with >= 8 test methods achieving >= 90% branch coverage on transitionStatus and prerequisite check | • All 8 test cases pass with no live DB dependency • DRAFT->TESTING test confirms no prerequisite check is performed • TESTING->ACTIVE with 0 merchant fees throws exception with message containing merchant_fee_table • transitionStatus(ACTIVE->DRAFT) throws exception with message containing invalid transition • 100% of SchemeService.transitionStatus and checkActivationPrerequisites lines covered | 40 | 10.2-T02 | FS | PRD-07
10.2-T20 | admin-ui | 10.2 | 10. Admin System | Scheme management screens | 2 | Unit tests: CredentialEncryptionService AES-256 correctness and edge cases | CredentialEncryptionService (10.2-T03) uses AES-256-GCM with a key from application config/Vault. Tests must verify: correct round-trip, different ciphertext for same plaintext (due to random IV), null/empty input handling, wrong-key decryption failure, and that decrypted value matches original exactly including Unicode. No network or DB required. | • Write CredentialEncryptionServiceTest with a fixed test AES key (256-bit hex) injected via @TestPropertySource • Test round-trip: encrypt(plaintext) -> decrypt(result) == plaintext for a 64-char ASCII password • Test IV randomness: encrypt(same plaintext) twice produces different ciphertexts • Test empty string: encrypt('') and decrypt back returns '' • Test null input: encrypt(null) throws IllegalArgumentException • Test wrong key: decrypt with different key throws DecryptionException or equivalent • Test Unicode: encrypt decrypt correctly handles Korean characters (e.g. 한결원) | CredentialEncryptionServiceTest with 6 test methods, all passing, demonstrating AES-256-GCM correctness | • Round-trip test passes: decrypt(encrypt(hello_world_123)) == hello_world_123 • Two encryptions of identical plaintext produce different byte strings (IV uniqueness) • decrypt with wrong key throws exception (not returns null) • encrypt(null) throws IllegalArgumentException before any crypto operation • Unicode test: decrypt(encrypt(한결원)) == 한결원 | 30 | 10.2-T03 | FS | PRD-07
10.2-T21 | admin-ui | 10.2 | 10. Admin System | Scheme management screens | 2 | Unit tests: SchemeController input validation and RBAC enforcement | SchemeController (10.2-T05, 10.2-T06, 10.2-T07) must reject invalid inputs and enforce RBAC. Tests use MockMvc (Spring) or equivalent. RBAC roles: OPS_OPERATOR and OPS_ADMIN can create/edit/activate; FINANCE_ANALYST can only view (GET); ADMIN_VIEWER gets 403 on all scheme endpoints. Validate: scheme_code regex [A-Z0-9]{1,20}, logo_url must be HTTPS, gme_fee_share_pct in [0,100], status PATCH requires confirmed=true. | • Write SchemeControllerTest using @WebMvcTest + mock SchemeService • Test POST /admin/schemes with scheme_code=lowercase returns 400 with field error on scheme_code • Test POST /admin/schemes with logo_url=http://... returns 400 • Test POST /admin/schemes with gme_fee_share_pct=150 returns 400 • Test PATCH /admin/schemes/1/status with confirmed=false returns 400 • Test GET /admin/schemes with FINANCE_ANALYST token returns 200 • Test POST /admin/schemes with FINANCE_ANALYST token returns 403 • Test any /admin/schemes endpoint with ADMIN_VIEWER token returns 403 • Test GET /admin/schemes/999 returns 404 when service throws SchemeNotFoundException | SchemeControllerTest with >= 8 MockMvc test methods covering validation and RBAC | • POST with scheme_code=zeropay returns 400 with field=scheme_code in error response • POST with logo_url=http://example.com returns 400 with field=logo_url • FINANCE_ANALYST can GET but gets 403 on POST • ADMIN_VIEWER gets 403 on GET /admin/schemes • PATCH with confirmed=false returns 400 with error message containing confirmation | 40 | 10.2-T07 | FS | PRD-07
10.2-T22 | admin-ui | 10.2 | 10. Admin System | Scheme management screens | 2 | Unit tests: SchemeConnectivityService SFTP and REST test-connection paths | SchemeConnectivityService (10.2-T03) has two code paths: SFTP (JSch) and REST (HTTP GET). Tests mock JSch ChannelSftp and the HTTP client. Must test: SFTP success path, SFTP auth failure, SFTP connection refused (host unreachable), SFTP timeout (> 10s), REST success (200 response), REST failure (non-200 response), REST timeout. Each path must update last_connectivity_test_result column correctly. | • Write SchemeConnectivityServiceTest with mocked JSch SessionFactory and mocked HttpClient • Test SFTP success: mock ChannelSftp.stat returns a valid attrs object; assert result=SUCCESS, message contains sftp_host • Test SFTP auth failure: mock Session.connect throws JSchException(Auth fail); assert result=FAILURE, message contains auth • Test SFTP timeout: mock Session.connect hangs > 10s; assert result=TIMEOUT within 11s • Test REST success: mock HttpClient returns 200; assert result=SUCCESS • Test REST failure: mock HttpClient returns 401; assert result=FAILURE, message contains HTTP 401 • Test REST timeout: mock HttpClient times out; assert result=TIMEOUT • Verify last_connectivity_test_result and last_connectivity_test_at updated by SchemeRepository.save() in all paths | SchemeConnectivityServiceTest with 7 test methods covering all success/failure/timeout paths | • SFTP auth failure test returns result=FAILURE without throwing exception to caller • SFTP timeout test completes within 11 seconds (does not wait indefinitely) • REST 401 test stores FAILURE with message containing 401 in last_connectivity_test_message • All 7 tests pass with mocked dependencies (no live SFTP or HTTP server required) • SchemeRepository.updateConnectivityTestResult called exactly once per testConnection invocation in all paths | 40 | 10.2-T10 | FS | PRD-07
10.2-T23 | admin-ui | 10.2 | 10. Admin System | Scheme management screens | 2 | Unit tests: Merchant Fee Table validation and scheme_merchant_fee CRUD | SchemeFeeCRUDController (10.2-T09) and underlying service must enforce: domestic_rate and cross_border_rate in [0.0000, 1.0000], unique merchant_type per scheme, audit log on every mutation. Tests use MockMvc + mock services. Also test the rate display conversion: UI sends 0.80 (as percent), service stores 0.0080 (as decimal). | • Write SchemeFeeControllerTest with @WebMvcTest • Test POST valid row: merchant_type=General, domestic_rate=0.0080, cross_border_rate=0.0170 returns 201 • Test POST with domestic_rate=1.5 (150%) returns 400 • Test POST with negative domestic_rate returns 400 • Test POST with duplicate merchant_type for same scheme returns 409 • Test PUT updates domestic_rate and triggers AuditLogService.log() with previous_value and new_value • Test DELETE removes the row and triggers AuditLogService.log() • Test GET returns all rows for scheme_id=1 and empty array for scheme_id=99 (no fees) | SchemeFeeControllerTest with 7 test methods covering validation, uniqueness, and audit logging | • POST domestic_rate=1.5 returns 400 with field=domestic_rate • POST duplicate merchant_type returns 409 Conflict • PUT domestic_rate change: AuditLogService.log called with previous_value=0.0080, new_value=0.0090 • DELETE: AuditLogService.log called with event=scheme.fee_row_deleted • GET for scheme with no fees returns 200 with empty array | 35 | 10.2-T09 | FS | PRD-07
10.2-T24 | admin-ui | 10.2 | 10. Admin System | Scheme management screens | 2 | Integration test: full scheme onboarding happy path (ZEROPAY end-to-end) | This ticket writes a Spring Boot integration test (with a real test DB, Testcontainers PostgreSQL) covering the full ZeroPay scheme onboarding lifecycle: create -> add countries -> add fee rows -> test connection (mocked SFTP) -> activate. Validates that all prerequisite checks, audit log entries, and status transitions work together correctly. Uses the REST API layer (not service layer directly) to test the full vertical slice. | • Set up Testcontainers PostgreSQL and Spring Boot test context with @SpringBootTest and real JPA • Step 1: POST /admin/schemes with ZeroPay identity + SFTP connectivity + settlement terms; assert 201, status=DRAFT • Step 2: POST /admin/schemes/{id}/countries {country_code:KR}; assert 200 • Step 3: POST /admin/schemes/{id}/merchant-fees with General 0.0080/0.0170; assert 201 • Step 4: POST /admin/schemes/{id}/test-connection with mocked SFTP success; assert {result:SUCCESS} • Step 5: PATCH /admin/schemes/{id}/status {targetStatus:ACTIVE, confirmed:true}; assert 200, status=ACTIVE • Step 6: GET /admin/audit-log?entity_type=scheme&entity_id={id}; assert >= 4 entries (created, country_added, fee_row_added, status_changed) • Step 7: attempt PATCH status to ACTIVE again; assert 422 (already ACTIVE is not a valid transition from ACTIVE) | SchemeOnboardingIntegrationTest with 7-step test covering create through activate with audit trail verification | • After step 5, GET /admin/schemes/{id} returns status=ACTIVE • Audit log contains events: scheme.created, scheme.country_added, scheme.fee_row_added, scheme.status_changed in chronological order • Step 7 (re-activate) returns 422 • All 7 steps pass in a single test run against Testcontainers DB • Test runs in < 60 seconds including container startup | 55 | 10.2-T17, 10.2-T09, 10.2-T07 | FS | PRD-07
10.2-T25 | admin-ui | 10.2 | 10. Admin System | Scheme management screens | 2 | Integration test: scheme activation prerequisite failure paths | Complements 10.2-T24 by testing all negative prerequisite paths for activation. Uses Testcontainers PostgreSQL. Each sub-test creates a scheme in TESTING status with exactly one missing prerequisite and asserts PATCH /status returns 422 with the correct unmet condition identified. The four prerequisites are: (1) integration_type/credentials set, (2) >= 1 active country, (3) payout_ccy set, (4) >= 1 merchant fee row. | • Test 1: scheme with integration_type=SFTP but sftp_host=null; PATCH to ACTIVE returns 422 with unmet=MISSING_CONNECTIVITY_CONFIG • Test 2: scheme with all connectivity set but 0 scheme_country rows; PATCH to ACTIVE returns 422 with unmet=NO_SUPPORTED_COUNTRIES • Test 3: scheme with payout_ccy=null; PATCH to ACTIVE returns 422 with unmet=NO_PAYOUT_CURRENCY • Test 4: scheme with all set but 0 merchant fee rows; PATCH to ACTIVE returns 422 with unmet=NO_MERCHANT_FEE_TABLE • Test 5: scheme with 2 missing prerequisites; PATCH to ACTIVE returns 422 with both unmet conditions in array • Write all tests against Testcontainers DB; each test inserts independent scheme record | SchemeActivationPrerequisiteTest with 5 integration test cases covering all 4 prerequisite failure modes | • Test 1 response body contains unmet_conditions with MISSING_CONNECTIVITY_CONFIG • Test 2 response body contains NO_SUPPORTED_COUNTRIES • Test 3 response body contains NO_PAYOUT_CURRENCY • Test 4 response body contains NO_MERCHANT_FEE_TABLE • Test 5 response body contains both missing items in unmet_conditions array | 45 | 10.2-T24 | FS | PRD-07
10.2-T26 | admin-ui | 10.2 | 10. Admin System | Scheme management screens | 2 | Frontend component tests: SchemeFormPage validation and edge cases | SchemeFormPage (10.2-T12 through 10.2-T14) contains client-side validation logic that must be tested in isolation using a component testing framework (Jest + React Testing Library or Vue Test Utils). Tests cover: scheme_code auto-uppercase, uniqueness API call on blur, HTTPS logo URL check, country requirement, mode requirement, SFTP conditional fields, fee table row add/remove, gme_fee_share_pct range, Review Changes diff modal content. | • Write SchemeFormPage.test.jsx/spec.js using React Testing Library (or Vue Test Utils) • Test: typing scheme_code=zeropay auto-uppercases to ZEROPAY in the input • Test: blur on scheme_code that matches existing code shows inline error via mocked GET /admin/schemes?code=ZEROPAY • Test: submitting form with logo_url=http://example.com shows inline error, does not call POST • Test: clearing all countries shows inline error on Save attempt • Test: switching integration_type from SFTP to REST hides sftp_host field and shows api_base_url field • Test: clicking Add Row in fee table adds a new empty row; clicking Remove deletes it • Test: Review Changes modal shows only changed fields (name changed, code unchanged -> only name in diff) | SchemeFormPage.test file with >= 8 component test cases, all passing | • scheme_code auto-uppercase test: user types 'zeropay', input value becomes 'ZEROPAY' • logo_url http:// test: inline error appears without calling POST /admin/schemes • Add Row test: fee table row count increases by 1 • Review Changes modal test: only modified fields appear in diff table • All 8 tests pass without live API (all HTTP calls mocked) | 40 | 10.2-T15 | FS | PRD-07
10.2-T27 | admin-ui | 10.2 | 10. Admin System | Scheme management screens | 2 | RBAC guard: enforce scheme module permissions server-side across all endpoints | PRD-07 §12 RBAC matrix: Create/Edit Scheme = OPS_OPERATOR, OPS_ADMIN, SUPER_ADMIN only; Activate/Suspend Scheme = same; View Scheme Config = OPS_OPERATOR, OPS_ADMIN, FINANCE_ANALYST, SUPER_ADMIN; ADMIN_VIEWER = no access to any scheme endpoints. This ticket adds a dedicated RBAC test class that exhaustively verifies all scheme endpoints for all 4 roles. It also verifies that SUPER_ADMIN can perform all operations. Uses Spring Security test context with role-mocked JWTs. | • Create SchemeRbacTest class using @SpringBootTest with mocked auth tokens for each role • Matrix test all 7 scheme endpoints (GET list, GET detail, POST create, PUT update, PATCH status, POST test-connection, POST countries, DELETE countries, POST fees, PUT fees, DELETE fees) against each role • Assert: ADMIN_VIEWER gets 403 on all endpoints • Assert: FINANCE_ANALYST gets 200 on GET list/detail; 403 on all write endpoints • Assert: OPS_OPERATOR gets 200/201 on all; 403 on none • Assert: SUPER_ADMIN gets 200/201 on all • Log a test matrix summary to stdout for review | SchemeRbacTest class with complete role x endpoint matrix test (>= 40 test cases), all passing | • ADMIN_VIEWER receives 403 on GET /admin/schemes (view blocked completely) • FINANCE_ANALYST receives 403 on POST /admin/schemes • FINANCE_ANALYST receives 200 on GET /admin/schemes • OPS_OPERATOR receives 201 on POST /admin/schemes with valid payload • SUPER_ADMIN receives 200/201 on every endpoint tested | 50 | 10.2-T21 | FS | PRD-07
10.2-T28 | admin-ui | 10.2 | 10. Admin System | Scheme management screens | 2 | API documentation: OpenAPI spec for all scheme management endpoints | The Admin System backend must expose an OpenAPI 3.0 spec (generated from code annotations or hand-authored) for all scheme endpoints: GET /admin/schemes, GET /admin/schemes/{id}, POST /admin/schemes, PUT /admin/schemes/{id}, PATCH /admin/schemes/{id}/status, POST /admin/schemes/{id}/test-connection, GET+POST+DELETE /admin/schemes/{id}/countries, GET+POST+PUT+DELETE /admin/schemes/{id}/merchant-fees, GET /admin/audit-log. The spec must include request/response schemas, error codes (400, 401, 403, 404, 409, 422), and security scheme (Bearer JWT). Consumed by frontend and QA teams. | • Add springdoc-openapi or equivalent to project dependencies • Annotate all scheme controllers and DTOs with @Operation, @ApiResponse, @Schema annotations • Ensure error response bodies (400 validation errors, 422 unmet conditions) are documented with example payloads • Document security requirement: BearerAuth on all /admin/* endpoints • Generate openapi.json and commit to docs/openapi/scheme-management.json • Verify spec can be loaded in Swagger UI and all endpoints are listed with correct request/response shapes | docs/openapi/scheme-management.json covering all 13 scheme management endpoints with full schema documentation | • openapi.json is valid JSON and loads without errors in Swagger UI • POST /admin/schemes schema documents all required fields including scheme_code pattern [A-Z0-9]{1,20} • PATCH /admin/schemes/{id}/status documents 422 response with unmet_conditions array example • All endpoints document 401 Unauthorized and 403 Forbidden responses • Security scheme BearerAuth is referenced on every /admin/* endpoint | 45 | 10.2-T07, 10.2-T09, 10.2-T10 | FS | PRD-07
10.3-T01 | admin-ui | 10.3 | 10. Admin System | Partner management & credentials | 2 | DB migration: create partner table | GMEPay+ stores all partner configuration as runtime data — no code branches per partner. The partner table (PostgreSQL) must hold: id BIGINT PK, partner_code VARCHAR(30) UNIQUE NOT NULL (uppercase alphanumeric, max 20 chars, e.g. GME_REMIT), name VARCHAR(100) NOT NULL, partner_type VARCHAR(10) NOT NULL CHECK IN (LOCAL, OVERSEAS), collection_ccy CHAR(3) NOT NULL, settle_a_ccy CHAR(3) NOT NULL, webhook_url VARCHAR(512) NOT NULL, rate_quote_ttl_seconds INT NOT NULL DEFAULT 300 CHECK (60..1800), low_balance_threshold_usd DECIMAL(20,4) (nullable; OVERSEAS only), low_balance_alert_email VARCHAR(255) (nullable), status VARCHAR(20) NOT NULL DEFAULT ONBOARDING CHECK IN (ONBOARDING, ACTIVE, SUSPENDED, INACTIVE), is_active BOOLEAN NOT NULL DEFAULT FALSE, created_at TIMESTAMPTZ, updated_at TIMESTAMPTZ, created_by VARCHAR(120), updated_by VARCHAR(120). partner_type is immutable after status transitions to ACTIVE. | • Create a Flyway (or Liquibase) migration file V10_3_001__create_partner.sql • Define the partner table with all columns, types, constraints, and CHECK clauses listed in context • Add UNIQUE index on partner_code • Add a partial index on status WHERE is_active = TRUE for fast active-partner lookup • Write a rollback script (DROP TABLE partner) | Migration file V10_3_001__create_partner.sql that applies cleanly on an empty schema and rolls back without error | • INSERT a LOCAL partner with partner_code GME_REMIT succeeds; INSERT a duplicate partner_code raises unique-constraint violation • INSERT with partner_type = BROKER raises CHECK violation; only LOCAL and OVERSEAS are accepted • INSERT with rate_quote_ttl_seconds = 59 or 1801 raises CHECK violation; 60 and 1800 succeed • SELECT on is_active index returns only rows where is_active = TRUE • Rollback removes the table cleanly; re-apply recreates it without error | 30 |  | FS | PRD-07
10.3-T02 | admin-ui | 10.3 | 10. Admin System | Partner management & credentials | 2 | DB migration: create partner_credential table | Partner API credentials are key+secret pairs. The secret is stored as a bcrypt hash; plaintext is shown once at generation and never retrievable. Table columns: id BIGINT PK, partner_id BIGINT FK partner NOT NULL, api_key VARCHAR(64) UNIQUE NOT NULL, api_secret_hash VARCHAR(128) NOT NULL, is_active BOOLEAN NOT NULL DEFAULT TRUE, expires_at TIMESTAMPTZ (NULL = no expiry), created_at TIMESTAMPTZ, updated_at TIMESTAMPTZ, created_by VARCHAR(120), updated_by VARCHAR(120). Business rule: only one active credential per partner at a time — enforce via partial unique index on partner_id WHERE is_active = TRUE. All credential operations must be audit-logged (see ticket 10.3-T06 for audit trail). | • Create migration file V10_3_002__create_partner_credential.sql • Define partner_credential table with all columns and FK to partner • Add UNIQUE index on api_key • Add partial unique index on (partner_id) WHERE is_active = TRUE to enforce single-active-credential invariant • Write rollback script | Migration file V10_3_002__create_partner_credential.sql | • INSERT two active credentials for the same partner raises unique-constraint violation on the partial index • INSERT one active and one inactive credential for the same partner succeeds • Deleting partner cascades or is prevented (FK constraint raises error if partner deleted while credential exists — confirm behaviour is RESTRICT) • api_key UNIQUE index rejects duplicate key across different partners • Rollback removes table cleanly | 25 | 10.3-T01 | FS | PRD-07
10.3-T03 | admin-ui | 10.3 | 10. Admin System | Partner management & credentials | 2 | DB migration: create prefunding_account and prefunding_ledger_entry tables | OVERSEAS partners (e.g. SendMN, T-Bank) maintain a prepaid USD balance. prefunding_account: id BIGINT PK, partner_id BIGINT FK partner UNIQUE NOT NULL, currency CHAR(3) NOT NULL DEFAULT USD, balance DECIMAL(20,4) NOT NULL DEFAULT 0, low_balance_threshold DECIMAL(20,4) NOT NULL DEFAULT 10000.0000, created_at/updated_at/created_by/updated_by. prefunding_ledger_entry is append-only (no updated_at, no deletes): id BIGINT PK, account_id BIGINT FK prefunding_account NOT NULL, txn_ref VARCHAR(64), entry_type VARCHAR(20) NOT NULL CHECK IN (DEBIT_PAYMENT, DEBIT_REVERSAL, CREDIT_TOPUP, CREDIT_REVERSAL), amount DECIMAL(20,4) NOT NULL CHECK > 0, balance_after DECIMAL(20,4) NOT NULL, note VARCHAR(255), created_at TIMESTAMPTZ NOT NULL, created_by VARCHAR(120). Index: (account_id, created_at) for balance history. One prefunding_account per partner (UNIQUE on partner_id). | • Create migration file V10_3_003__create_prefunding.sql • Define prefunding_account table with UNIQUE constraint on partner_id and balance column • Define prefunding_ledger_entry as append-only (no updated_at column, no UPDATE triggers on amount/balance_after) • Add compound index on (account_id, created_at) on ledger • Add CHECK constraint on entry_type and amount > 0 • Write rollback script | Migration file V10_3_003__create_prefunding.sql | • INSERT a second prefunding_account for the same partner_id raises unique-constraint violation • INSERT a ledger entry with amount = 0 or negative raises CHECK violation • INSERT a ledger entry with entry_type = TRANSFER raises CHECK violation • Compound index (account_id, created_at) is present and used by EXPLAIN for balance history query: SELECT * FROM prefunding_ledger_entry WHERE account_id = 1 ORDER BY created_at DESC • Currency column defaults to USD; attempting to set currency = EUR succeeds (no currency CHECK here — validated at app layer per 10.3-T09) | 30 | 10.3-T01 | FS | PRD-07
10.3-T04 | admin-ui | 10.3 | 10. Admin System | Partner management & credentials | 2 | DB migration: create low_balance_alert_config table | Each OVERSEAS partner has a configurable low-balance alert. The system fires an email when balance drops below threshold after a deduction; the triggering transaction is NOT blocked. Table: id BIGINT PK, partner_id BIGINT FK partner UNIQUE NOT NULL, threshold_usd DECIMAL(20,4) NOT NULL DEFAULT 10000.0000, alert_email VARCHAR(255) NOT NULL (comma-separated for multiple recipients; validated at app layer), is_active BOOLEAN NOT NULL DEFAULT TRUE, created_at/updated_at/created_by/updated_by. UNIQUE on partner_id (one config per partner). Default threshold is USD 10,000 (per SendMN use-case). | • Create migration file V10_3_004__create_low_balance_alert_config.sql • Define low_balance_alert_config table with UNIQUE on partner_id • Set default value for threshold_usd = 10000.0000 • Write rollback script | Migration file V10_3_004__create_low_balance_alert_config.sql | • INSERT two alert_config rows for the same partner_id raises unique-constraint violation • INSERT with threshold_usd = 0 is accepted at DB layer (validated as >= 0 at app layer — no negative balance threshold makes sense but zero is valid edge case) • Default threshold_usd is 10000.0000 when not supplied • Rollback drops table without error • FK to partner raises error if partner does not exist | 20 | 10.3-T01 | FS | PRD-07
10.3-T05 | admin-ui | 10.3 | 10. Admin System | Partner management & credentials | 2 | DB migration: add audit_log table for admin-system events | All write operations in the Admin System generate an immutable audit log entry. Table: id UUID PK DEFAULT gen_random_uuid(), timestamp_utc TIMESTAMPTZ NOT NULL DEFAULT now(), actor_user_id VARCHAR(120) NOT NULL, actor_display_name VARCHAR(200), actor_ip_address INET, event_type VARCHAR(60) NOT NULL (e.g. partner.created, partner.credential_generated, partner.credential_revoked, prefunding.topup_recorded, prefunding.adjustment_created), entity_type VARCHAR(40) NOT NULL (e.g. partner, partner_credential, prefunding_account), entity_id VARCHAR(60) NOT NULL, previous_value JSONB, new_value JSONB, description TEXT, metadata JSONB, created_at TIMESTAMPTZ NOT NULL DEFAULT now(). NO updated_at. The application service account must have INSERT-only permission (no UPDATE or DELETE) — enforced via GRANT in migration. Indexes: (entity_type, entity_id), (actor_user_id), (timestamp_utc). | • Create migration file V10_3_005__create_audit_log.sql • Define audit_log table with UUID PK and all columns listed in context • Add indexes on (entity_type, entity_id), actor_user_id, and timestamp_utc • Add GRANT INSERT ON audit_log TO app_role; REVOKE UPDATE, DELETE ON audit_log FROM app_role • Write rollback script (DROP TABLE only — no REVOKE needed if role dropped) | Migration file V10_3_005__create_audit_log.sql | • INSERT into audit_log succeeds for the app_role • UPDATE on audit_log raises permission error for app_role • DELETE on audit_log raises permission error for app_role • Index on (entity_type, entity_id) present and used by EXPLAIN for query WHERE entity_type = partner AND entity_id = 42 • Rollback drops table without error | 30 |  | FS | PRD-07
10.3-T06 | admin-ui | 10.3 | 10. Admin System | Partner management & credentials | 2 | Implement AuditLogService: write immutable audit entries | AuditLogService is the single write path for all Admin System audit events. It must: accept (actorUserId, actorDisplayName, actorIp, eventType, entityType, entityId, previousValue, newValue, description, metadata); persist one row to audit_log with timestamp_utc = NOW() UTC; be transactional — the audit INSERT must succeed or the calling operation must fail (use same DB transaction). Event type codes are dot-separated: partner.created, partner.updated, partner.activated, partner.suspended, partner.credential_generated, partner.credential_revoked, prefunding.account_created, prefunding.topup_recorded, prefunding.adjustment_created, prefunding.alert_threshold_updated. previousValue and newValue are serialized as JSONB. | • Create AuditLogService class with a writeEntry(AuditEntryRequest) method • Accept the fields listed in context; persist to audit_log in the same DB transaction as the calling operation • Throw AuditWriteException (which rolls back the outer transaction) if the INSERT fails • Provide a queryByEntity(entityType, entityId, pageable) read method returning paginated AuditLogEntry DTOs • Add an integration test: calling writeEntry within a transaction that is then rolled back must NOT persist the audit row | AuditLogService class (Java) with writeEntry and queryByEntity methods, and integration test | • writeEntry with valid inputs inserts exactly one row with correct event_type and entity_id • writeEntry called inside a transaction that is rolled back does not persist the row (ACID test) • queryByEntity returns rows sorted by timestamp_utc DESC, paginated correctly • Calling writeEntry with null actorUserId throws IllegalArgumentException before any DB call • Querying for a non-existent entity returns an empty page, not an error | 45 | 10.3-T05 | FS | PRD-07
10.3-T07 | admin-ui | 10.3 | 10. Admin System | Partner management & credentials | 2 | Implement PartnerRepository: CRUD and lookup methods | PartnerRepository wraps the partner table. Required methods: save(Partner), findById(Long), findByPartnerCode(String), findAllByStatus(String, Pageable), existsByPartnerCode(String), updateStatus(Long partnerId, String newStatus, String updatedBy). All writes must update updated_at = NOW() and updated_by. The findByPartnerCode lookup is used at API authentication time and must be backed by the UNIQUE index on partner_code. Use DECIMAL types (not float/double) for monetary columns. partner_type is read from DB but must not be writable after status = ACTIVE (enforced at service layer, not repository). | • Create JPA entity Partner mapped to the partner table with all columns • Create PartnerRepository (Spring Data JPA) with custom queries for findByPartnerCode and findAllByStatus • Ensure DECIMAL(20,4) maps to BigDecimal in Java for low_balance_threshold_usd • Write integration tests against a test DB (Testcontainers) for each method • Verify that findByPartnerCode uses the UNIQUE index (check via EXPLAIN in test) | Partner JPA entity + PartnerRepository with integration tests | • findByPartnerCode(GME_REMIT) returns the correct partner after INSERT • findAllByStatus(ACTIVE, pageable) returns only ACTIVE partners • save() with a duplicate partner_code throws DataIntegrityViolationException • low_balance_threshold_usd round-trips as BigDecimal 10000.0000 without floating-point error • updateStatus() updates status and updated_by but not partner_type or collection_ccy | 40 | 10.3-T01 | FS | PRD-07
10.3-T08 | admin-ui | 10.3 | 10. Admin System | Partner management & credentials | 2 | Implement PartnerCredentialService: generate and revoke API credentials | Credentials are generated by GME Ops. On generate: (1) deactivate any existing active credential for the partner (set is_active = FALSE), (2) generate a cryptographically random api_key (UUID v4 hex, no dashes, 32 chars) and api_secret (32-byte random, base64url-encoded, 44 chars), (3) hash the secret with BCrypt cost 12, (4) persist the new credential with is_active = TRUE, (5) return the plaintext secret ONCE (never stored). On revoke: set is_active = FALSE on the active credential. Only one active credential per partner at a time — enforced by partial unique index on partner_id WHERE is_active = TRUE (see 10.3-T02) AND in service logic. Both operations are audit-logged with event_type partner.credential_generated or partner.credential_revoked. Partner must be in ACTIVE or ONBOARDING status to generate credentials. | • Create PartnerCredentialService with generateCredentials(partnerId, actorUserId, actorIp) method • Implement deactivate-existing + generate-new in a single DB transaction • Use SecureRandom for key and secret generation; BCrypt strength 12 for hashing • Return a CredentialIssuanceResult DTO containing api_key and plaintext api_secret (shown once) • Implement revokeCredentials(partnerId, actorUserId, actorIp) that sets is_active = FALSE • Call AuditLogService.writeEntry for both operations within the same transaction | PartnerCredentialService with generateCredentials and revokeCredentials, unit and integration tests | • generateCredentials for a partner with an existing active credential deactivates the old one and creates a new one — only one active credential remains • api_secret returned in plaintext; subsequent calls to find the secret return only the hash (plaintext not stored) • BCrypt hash of the returned plaintext secret matches api_secret_hash in DB: BCrypt.checkpw(plaintext, hash) == true • revokeCredentials sets is_active = FALSE; partner has zero active credentials afterwards • generateCredentials for a SUSPENDED partner throws PartnerNotEligibleException • Audit log contains event partner.credential_generated with entity_id = partner_id after successful generation | 50 | 10.3-T02, 10.3-T06, 10.3-T07 | FS | PRD-07
10.3-T09 | admin-ui | 10.3 | 10. Admin System | Partner management & credentials | 2 | Implement PartnerService: create and validate partner | PartnerService.createPartner accepts: partnerCode (uppercase alphanumeric, max 20 chars, unique), name (max 100 chars), partnerType (LOCAL¦OVERSEAS), collectionCcy (ISO 4217, must exist in currency registry), settleACcy (ISO 4217, must exist), webhookUrl (HTTPS required), rateQuoteTtlSeconds (60..1800, default 300), contactEmail (required for low-balance alerts). Validation rules: (1) partnerCode must match regex [A-Z0-9_]{1,20}; (2) webhookUrl must be HTTPS; (3) for LOCAL partners, collectionCcy must equal settleACcy (e.g. both KRW); (4) for OVERSEAS partners, GME expects settleACcy = USD (warn if not); (5) if collectionCcy == settleACcy, the system notes potential same-currency rule later. Status is set to ONBOARDING on create. Calls AuditLogService with event_type partner.created. Returns the created partner entity including its generated id. | • Create PartnerService.createPartner(CreatePartnerRequest, actorUserId, actorIp) method • Validate partnerCode regex, name length, webhookUrl HTTPS, rateQuoteTtlSeconds range • Validate collectionCcy and settleACcy exist in the currency registry table (treasury_rate has an entry or they are USD) • For LOCAL: enforce collectionCcy == settleACcy; for OVERSEAS: warn (not block) if settleACcy != USD • Persist via PartnerRepository.save() with status = ONBOARDING • Call AuditLogService.writeEntry(partner.created, previous = null, new = partner as JSON) | PartnerService.createPartner with input validation and audit, plus unit tests covering each validation rule | • createPartner with partnerCode GME-REMIT (hyphen) throws ValidationException (only A-Z0-9_ allowed) • createPartner with webhookUrl http://example.com (not HTTPS) throws ValidationException • createPartner LOCAL with collectionCcy = MNT and settleACcy = KRW throws ValidationException (must be equal for LOCAL) • createPartner with duplicate partnerCode throws DuplicatePartnerException • Successful create persists status = ONBOARDING and is_active = FALSE • Audit log entry partner.created exists with new_value containing the partner_code after successful create | 45 | 10.3-T05, 10.3-T06, 10.3-T07 | FS | PRD-07
10.3-T10 | admin-ui | 10.3 | 10. Admin System | Partner management & credentials | 2 | Implement PartnerService: activate partner with pre-condition checks | Activating a partner (status ONBOARDING -> ACTIVE) requires: (1) settlementCurrency set; (2) at least one active API credential exists (see 10.3-T08); (3) webhookUrl is set (HTTPS); (4) for OVERSEAS partners: prefunding_account exists AND balance > 0. Activation sets status = ACTIVE, is_active = TRUE, and records updated_at. partner_type becomes immutable after activation (any subsequent attempt to change partner_type raises ImmutableFieldException). Audit event: partner.activated. If any pre-condition fails, return a structured error listing which conditions are unmet, e.g. {unmet: [NO_ACTIVE_CREDENTIAL, PREFUNDING_BALANCE_ZERO]}. | • Create PartnerService.activatePartner(partnerId, actorUserId, actorIp) method • Check all 4 pre-conditions; collect unmet conditions into a list • If list is non-empty throw PartnerActivationException(unmet list) • Set status = ACTIVE, is_active = TRUE, updated_at = NOW() • Mark partner_type as immutable: add a guard in updatePartner that throws ImmutableFieldException if partner is ACTIVE and partnerType field is changed • Call AuditLogService.writeEntry(partner.activated) | PartnerService.activatePartner with pre-condition checks and immutability guard, plus unit tests | • Activating a LOCAL partner with no active credential returns unmet = [NO_ACTIVE_CREDENTIAL] • Activating an OVERSEAS partner with balance = 0 returns unmet = [PREFUNDING_BALANCE_ZERO] • Activating with all conditions met sets status = ACTIVE and is_active = TRUE • After activation, calling updatePartner with a changed partner_type throws ImmutableFieldException • Audit log entry partner.activated with entity_id = partner_id exists after successful activation • Attempting to activate an already-ACTIVE partner throws IllegalStateException (idempotency guard) | 40 | 10.3-T08, 10.3-T09 | FS | PRD-07
10.3-T11 | admin-ui | 10.3 | 10. Admin System | Partner management & credentials | 2 | Implement PartnerService: suspend and reactivate partner | Suspending a partner (status ACTIVE -> SUSPENDED) halts all new payment processing for that partner. Reactivating (SUSPENDED -> ACTIVE) restores processing. Suspension does not affect in-flight transactions (they are already committed). On suspension: set status = SUSPENDED, is_active = FALSE. On reactivation: re-run the same pre-condition checks as activation (10.3-T10): credential, webhookUrl, and for OVERSEAS balance > 0. Audit events: partner.suspended and partner.reactivated. Both operations require actorUserId and actorIp for the audit trail. | • Create PartnerService.suspendPartner(partnerId, reason, actorUserId, actorIp) method • Set status = SUSPENDED, is_active = FALSE, persist • Call AuditLogService.writeEntry(partner.suspended, metadata includes reason string) • Create PartnerService.reactivatePartner(partnerId, actorUserId, actorIp) method • Run same pre-condition checks as activatePartner; throw PartnerActivationException if unmet • On success set status = ACTIVE, is_active = TRUE; call audit writeEntry(partner.reactivated) | PartnerService.suspendPartner and reactivatePartner, with unit tests | • suspendPartner on ACTIVE partner sets status = SUSPENDED and is_active = FALSE • suspendPartner on ONBOARDING partner throws IllegalStateException (can only suspend ACTIVE partners) • reactivatePartner on a partner with zero balance (OVERSEAS) returns unmet = [PREFUNDING_BALANCE_ZERO] • After reactivatePartner succeeds, status = ACTIVE and is_active = TRUE • Audit log contains partner.suspended and partner.reactivated events with actor info • suspendPartner is idempotent: calling it twice does not error | 35 | 10.3-T10 | FS | PRD-07
10.3-T12 | admin-ui | 10.3 | 10. Admin System | Partner management & credentials | 2 | Implement PrefundingService: create prefunding account on partner creation | When an OVERSEAS partner is created, a prefunding_account row must be created. For LOCAL partners, no prefunding_account is created. The initial balance is set when Ops records the first top-up or at activation (see 10.3-T13). prefunding_account.currency is always USD. prefunding_account.balance starts at 0.0000. The low_balance_threshold defaults to 10000.0000 USD (configurable per 10.3-T04). PrefundingService.createAccountForPartner(partnerId, thresholdUsd) creates the account and inserts a corresponding low_balance_alert_config row with the given threshold and alert_email from the partner record. Audit event: prefunding.account_created. | • Create PrefundingService.createAccountForPartner(partnerId, thresholdUsd, alertEmail, actorUserId) method • Validate partnerType == OVERSEAS before creating account; throw UnsupportedOperationException for LOCAL • Insert prefunding_account row with balance = 0, currency = USD, low_balance_threshold = thresholdUsd • Insert low_balance_alert_config row with threshold_usd and alert_email; is_active = TRUE • Call AuditLogService.writeEntry(prefunding.account_created) in the same transaction • Test that calling this method twice for the same partner throws DataIntegrityViolationException (UNIQUE on partner_id) | PrefundingService.createAccountForPartner with account and alert config creation, unit and integration tests | • Calling for a LOCAL partner throws UnsupportedOperationException • Calling for an OVERSEAS partner creates prefunding_account with balance = 0.0000 and currency = USD • low_balance_alert_config is created with threshold = 10000.0000 by default when thresholdUsd = null • Calling twice for the same partner throws DataIntegrityViolationException • Audit log entry prefunding.account_created with entity_id = account_id exists after success | 35 | 10.3-T03, 10.3-T04, 10.3-T06, 10.3-T07 | FS | PRD-07
10.3-T13 | admin-ui | 10.3 | 10. Admin System | Partner management & credentials | 2 | Implement PrefundingService: record top-up atomically | Ops records a top-up when a partner wires funds to GME. Top-up inputs: partnerId, amountUsd (BigDecimal, > 0), bankRef (required, non-empty string), valueDate (required date), notes (optional). Processing: (1) SELECT FOR UPDATE the prefunding_account row; (2) add amountUsd to balance; (3) INSERT a prefunding_ledger_entry with entry_type = CREDIT_TOPUP, amount = amountUsd, balance_after = new balance, txn_ref = null, note = bankRef; (4) COMMIT — all three steps in one transaction. Audit event: prefunding.topup_recorded with previous_value = old balance, new_value = new balance. Returns a TopUpResult with new balance and ledger entry id. | • Create PrefundingService.recordTopUp(RecordTopUpRequest, actorUserId, actorIp) method • SELECT FOR UPDATE the prefunding_account; throw AccountNotFoundException if missing • Validate amountUsd > 0 and bankRef non-empty; throw ValidationException otherwise • Update balance = balance + amountUsd; INSERT ledger entry CREDIT_TOPUP with balance_after • Call AuditLogService.writeEntry(prefunding.topup_recorded, previous = old balance, new = new balance) • Return TopUpResult(newBalance, ledgerEntryId) | PrefundingService.recordTopUp with SELECT FOR UPDATE atomicity, integration test including concurrent top-up scenario | • recordTopUp with amountUsd = 0 throws ValidationException • recordTopUp with empty bankRef throws ValidationException • After recordTopUp(100.00) on account with balance 500.00, balance = 600.0000 • ledger entry has entry_type = CREDIT_TOPUP, amount = 100.0000, balance_after = 600.0000 • Concurrent top-ups of 100.00 and 200.00 on balance 500.00 result in final balance = 800.0000 (not 600 or 700 — SELECT FOR UPDATE prevents race) • Audit log contains prefunding.topup_recorded with previous_value = 500.0000 and new_value = 600.0000 | 50 | 10.3-T03, 10.3-T06, 10.3-T12 | FS | PRD-07
10.3-T14 | admin-ui | 10.3 | 10. Admin System | Partner management & credentials | 2 | Implement PrefundingService: deduct balance atomically (payment path) | For OVERSEAS partners, prefunding is deducted before any scheme call. Deduction must be ATOMIC: SELECT ... FOR UPDATE on prefunding_account, check balance >= deductionAmountUsd, subtract, INSERT ledger entry DEBIT_PAYMENT. If balance < deductionAmountUsd, throw InsufficientPrefundingException (transaction is rejected; scheme is never called). After deduction, check if balance < low_balance_threshold — if so, trigger LowBalanceAlertService.sendAlert (async OK). Deduction and scheme call are separate operations; if the scheme subsequently fails, a DEBIT_REVERSAL entry is created by a separate reversal path (10.3-T15). This method is called from the payment orchestration layer — it must be fast: target < 50 ms under normal load. | • Create PrefundingService.deductBalance(partnerId, deductionAmountUsd, txnRef, actorUserId) method • SELECT FOR UPDATE prefunding_account WHERE partner_id = ? • If balance < deductionAmountUsd throw InsufficientPrefundingException(currentBalance, requested) • balance = balance - deductionAmountUsd; INSERT ledger entry DEBIT_PAYMENT with balance_after • After commit, if new balance < low_balance_threshold call LowBalanceAlertService.checkAndAlert(partnerId) asynchronously • Return DeductionResult(newBalance, ledgerEntryId) | PrefundingService.deductBalance with SELECT FOR UPDATE, InsufficientPrefundingException on zero/low balance, unit and integration tests | • deductBalance of 200.00 on account with balance 150.00 throws InsufficientPrefundingException without modifying the balance • deductBalance of 100.00 on account with balance 500.00 results in balance = 400.0000 and ledger entry DEBIT_PAYMENT with balance_after = 400.0000 • Two concurrent deductions of 300.00 on a balance of 500.00: exactly one succeeds (balance = 200.00), exactly one throws InsufficientPrefundingException — SELECT FOR UPDATE prevents double-spend • txnRef is stored on the ledger entry for traceability back to the transaction • balance = 0 after deduction triggers LowBalanceAlertService.checkAndAlert call; balance = 5000.00 with threshold 10000.00 also triggers alert • deductBalance for a LOCAL partner (no prefunding_account) throws AccountNotFoundException immediately | 55 | 10.3-T03, 10.3-T12 | FS | PRD-07
10.3-T15 | admin-ui | 10.3 | 10. Admin System | Partner management & credentials | 2 | Implement PrefundingService: reverse deduction (cancellation and refund path) | When a payment is cancelled or a refund is confirmed by ZeroPay (DEBIT_REVERSAL), the deducted amount must be credited back to the prefunding balance. reverseDeduction inputs: partnerId, originalTxnRef, reversalAmountUsd, reversalType (CANCEL¦REFUND_CONFIRMED). Processing: SELECT FOR UPDATE on prefunding_account, add reversalAmountUsd to balance, INSERT ledger entry with entry_type = DEBIT_REVERSAL or CREDIT_REVERSAL (use DEBIT_REVERSAL for payment cancellation and CREDIT_REVERSAL for refund confirmation per 10.3-T03 schema). Reversal must be idempotent: if a ledger entry for the same originalTxnRef with entry_type DEBIT_REVERSAL already exists, return the existing result without double-crediting. Audit event: prefunding.deduction_reversed. | • Create PrefundingService.reverseDeduction(partnerId, originalTxnRef, reversalAmountUsd, actorUserId) method • Check for existing DEBIT_REVERSAL ledger entry with the same txn_ref; if found return existing result (idempotency) • SELECT FOR UPDATE prefunding_account • balance = balance + reversalAmountUsd; INSERT DEBIT_REVERSAL ledger entry with balance_after • Call AuditLogService.writeEntry(prefunding.deduction_reversed) • Return ReversalResult(newBalance, ledgerEntryId) | PrefundingService.reverseDeduction with idempotency guard, integration tests including duplicate-call scenario | • reverseDeduction of 100.00 on balance 200.00 results in balance = 300.0000 and DEBIT_REVERSAL ledger entry with balance_after = 300.0000 • Calling reverseDeduction twice with the same originalTxnRef returns the same ledgerEntryId without creating a second ledger entry (idempotency) • reverseDeduction with reversalAmountUsd = 0 throws ValidationException • Concurrent reversal calls for the same txnRef: exactly one ledger row created (idempotency + SELECT FOR UPDATE) • Audit log entry prefunding.deduction_reversed exists after first call; no second audit entry on idempotent replay | 45 | 10.3-T14 | FS | PRD-07
10.3-T16 | admin-ui | 10.3 | 10. Admin System | Partner management & credentials | 2 | Implement LowBalanceAlertService: threshold check and email alert | After every deduction, the system checks if the partner balance has dropped below the configured threshold. If balance < threshold: send an email to all addresses in low_balance_alert_config.alert_email (comma-separated). Email content must include: partner name, current balance (e.g. USD 8,500.00), threshold (e.g. USD 10,000.00), and a suggested top-up amount (threshold - balance, rounded up to nearest 100). The transaction that triggered the alert is NOT blocked. If balance <= 0: send an urgent alert and set partner.is_active = FALSE (payments suspended). Alert delivery uses the platform email service (SMTP relay / SES). Deduplication: do not send a second alert within 1 hour for the same partner (use a last_alert_sent_at column or a simple Redis key with TTL 3600s). | • Create LowBalanceAlertService.checkAndAlert(partnerId) method called asynchronously after deduction • Query low_balance_alert_config for the partner; if not found or is_active = FALSE, return without action • Compare balance against threshold; if balance < threshold prepare low-balance email • Parse comma-separated alert_email; send email to each address via EmailSendPort (interface, injectable) • If balance <= 0: send urgent email AND call PartnerService.suspendPartner(reason = ZERO_BALANCE) • Implement 1-hour deduplication using last_alert_sent_at in low_balance_alert_config or a cache TTL | LowBalanceAlertService.checkAndAlert with email composition and deduplication, unit tests with mock EmailSendPort | • balance = 8500.00 with threshold = 10000.00: email sent to all addresses in alert_email with suggested top-up = 1500.00 (10000 - 8500) • balance = 15000.00 with threshold = 10000.00: no email sent • balance = 0.00: urgent email sent AND partner is_active set to FALSE • Second alert within 1 hour for same partner is suppressed (no duplicate email) • Alert is sent again after 1 hour deduplication window expires • Email content includes partner name, current balance formatted as USD 8,500.00, and threshold USD 10,000.00 | 50 | 10.3-T04, 10.3-T11, 10.3-T14 | FS | PRD-07
10.3-T17 | admin-ui | 10.3 | 10. Admin System | Partner management & credentials | 2 | Implement PrefundingService: record manual adjustment with mandatory reason | Finance or Ops (with appropriate RBAC) can create a manual ADJUSTMENT entry on a prefunding ledger to correct recording errors (e.g. a top-up was entered with the wrong amount). Inputs: partnerId, adjustmentAmountUsd (positive = credit, negative = debit), reason (mandatory, min 10 chars), actorUserId. Processing: SELECT FOR UPDATE on prefunding_account, compute new balance = balance + adjustmentAmountUsd, validate new balance >= 0 (no negative balance allowed), INSERT ledger entry. entry_type: CREDIT_TOPUP if adjustmentAmountUsd > 0, DEBIT_REVERSAL if < 0. Audit event: prefunding.adjustment_created with mandatory reason in metadata. Returns new balance and ledger entry id. | • Create PrefundingService.recordAdjustment(RecordAdjustmentRequest, actorUserId, actorIp) method • Validate reason is non-null and >= 10 chars; validate adjustmentAmountUsd != 0 • SELECT FOR UPDATE prefunding_account; compute newBalance = balance + adjustmentAmountUsd • Validate newBalance >= 0; throw InsufficientPrefundingException if adjustment would result in negative balance • INSERT appropriate ledger entry type; call AuditLogService.writeEntry(prefunding.adjustment_created, metadata = {reason}) • Return AdjustmentResult(newBalance, ledgerEntryId) | PrefundingService.recordAdjustment with reason validation and negative-balance guard, unit tests | • adjustmentAmountUsd = -600.00 on balance 500.00 throws InsufficientPrefundingException (would go negative) • adjustmentAmountUsd = +100.00 on balance 500.00 results in balance = 600.0000 with CREDIT_TOPUP ledger entry • adjustmentAmountUsd = -100.00 on balance 500.00 results in balance = 400.0000 with DEBIT_REVERSAL ledger entry • reason with fewer than 10 chars throws ValidationException • Audit log entry prefunding.adjustment_created contains the reason in metadata | 40 | 10.3-T13 | FS | PRD-07
10.3-T18 | admin-ui | 10.3 | 10. Admin System | Partner management & credentials | 2 | Implement PartnerQueryService: partner list and detail with prefunding balance | The Admin System partner list view requires a paginated query returning: partner_code, name, partner_type, settle_a_ccy, status, prefunding_balance_usd (for OVERSEAS only; null for LOCAL), last_updated. The detail view adds: collection_ccy, webhook_url, rate_quote_ttl_seconds, active API key (not secret), credential created_at and last_used_at (last_used_at is updated at API authentication time per 10.3-T22), low_balance_threshold, alert_email, and prefunding ledger summary (last 5 entries). Queries must be efficient: partner list should execute in < 100 ms for up to 1000 partners. | • Create PartnerQueryService.listPartners(PartnerListFilter, Pageable) returning Page<PartnerSummaryDTO> • Left-join partner with prefunding_account for balance (null for LOCAL) • Join with partner_credential WHERE is_active = TRUE to surface active api_key (never secret) • Create PartnerQueryService.getPartnerDetail(partnerId) returning PartnerDetailDTO • Include low_balance_alert_config fields and last 5 prefunding_ledger_entry rows • Write integration tests asserting balance null for LOCAL and correct for OVERSEAS | PartnerQueryService with listPartners and getPartnerDetail, integration tests | • listPartners returns null prefunding_balance_usd for LOCAL partner GME_REMIT • listPartners returns correct balance for OVERSEAS partner SENDMN • getPartnerDetail returns active api_key string but NOT api_secret_hash • getPartnerDetail returns last 5 ledger entries ordered by created_at DESC • Filtering listPartners by status = ACTIVE excludes ONBOARDING and SUSPENDED partners • Page 2 of listPartners with pageSize = 10 returns partners 11-20 in stable sort order | 40 | 10.3-T07, 10.3-T08, 10.3-T12 | FS | PRD-07
10.3-T19 | admin-ui | 10.3 | 10. Admin System | Partner management & credentials | 2 | REST endpoint: POST /admin/partners — create partner | Admin API endpoint for creating a new partner. Access: OPS_OPERATOR and SUPER_ADMIN only (FINANCE_ANALYST and ADMIN_VIEWER return 403). Request body fields match PartnerService.createPartner: partnerCode, name, partnerType (LOCAL¦OVERSEAS), collectionCcy, settleACcy, webhookUrl (HTTPS), rateQuoteTtlSeconds (60-1800), contactEmail. For OVERSEAS partners, optional prefundingThresholdUsd (default 10000) and alertEmail. On success: 201 Created with partner id, partnerCode, status = ONBOARDING. On validation error: 400 with field-level error details. On duplicate partnerCode: 409 Conflict. Actor identity is extracted from the JWT/session. | • Create AdminPartnerController.createPartner(@RequestBody CreatePartnerRequest, Principal) endpoint • Validate request with @Valid annotations and custom validators for partnerCode regex and webhookUrl HTTPS • Call PartnerService.createPartner(); for OVERSEAS also call PrefundingService.createAccountForPartner() • Map exceptions to HTTP responses: ValidationException -> 400, DuplicatePartnerException -> 409 • Enforce RBAC: @PreAuthorize(hasRole(OPS_OPERATOR) or hasRole(SUPER_ADMIN)) • Integration test the endpoint with MockMvc or TestRestTemplate | POST /admin/partners endpoint with RBAC, validation, and integration tests | • POST with valid LOCAL partner body returns 201 with status = ONBOARDING • POST with http:// webhook URL returns 400 with error on field webhookUrl • POST with duplicate partnerCode returns 409 • POST with FINANCE_ANALYST role returns 403 • POST OVERSEAS partner creates both partner and prefunding_account in same request • Audit log entry partner.created exists after successful 201 response | 45 | 10.3-T09, 10.3-T12 | FS | PRD-07
10.3-T20 | admin-ui | 10.3 | 10. Admin System | Partner management & credentials | 2 | REST endpoint: PUT /admin/partners/{id}/activate — activate partner | Endpoint for activating a partner (ONBOARDING -> ACTIVE). Access: OPS_OPERATOR and SUPER_ADMIN. Calls PartnerService.activatePartner(id). On success: 200 with updated status = ACTIVE. If pre-conditions unmet: 422 Unprocessable Entity with body listing unmet conditions, e.g. {unmetConditions: [NO_ACTIVE_CREDENTIAL, PREFUNDING_BALANCE_ZERO]}. If partner not found: 404. If partner already ACTIVE: 200 (idempotent). Actor identity from JWT. | • Create PUT /admin/partners/{id}/activate endpoint in AdminPartnerController • Call PartnerService.activatePartner(id, actorUserId, actorIp) • Map PartnerActivationException to 422 with unmetConditions list in response body • Map PartnerNotFoundException to 404 • Apply RBAC: OPS_OPERATOR or SUPER_ADMIN • Integration test: activate with missing credential, activate with zero balance (OVERSEAS), successful activation | PUT /admin/partners/{id}/activate endpoint with pre-condition error mapping, integration tests | • Activate a LOCAL partner with no credential returns 422 with unmetConditions = [NO_ACTIVE_CREDENTIAL] • Activate an OVERSEAS partner with balance = 0 returns 422 with unmetConditions = [PREFUNDING_BALANCE_ZERO] • Activate a fully configured LOCAL partner returns 200 with status = ACTIVE • Activating an already-ACTIVE partner returns 200 (idempotent, no error) • Calling with ADMIN_VIEWER role returns 403 • Audit log entry partner.activated exists after 200 response | 35 | 10.3-T10, 10.3-T19 | FS | PRD-07
10.3-T21 | admin-ui | 10.3 | 10. Admin System | Partner management & credentials | 2 | REST endpoint: POST /admin/partners/{id}/credentials — generate API credentials | Endpoint for generating a new API key+secret for a partner. Access: OPS_OPERATOR and SUPER_ADMIN. Calls PartnerCredentialService.generateCredentials(). Response body: {apiKey: string, apiSecret: string (plaintext, shown ONCE), createdAt: ISO-8601}. The response must include a prominent warning header or body note: apiSecret is shown only once and cannot be retrieved. On success: 201. If partner not found: 404. If partner is SUSPENDED: 403. Any existing active credential is automatically deactivated. | • Create POST /admin/partners/{id}/credentials endpoint • Call PartnerCredentialService.generateCredentials(partnerId, actorUserId, actorIp) • Return 201 with CredentialIssuanceResponse: {apiKey, apiSecret, warningMessage: Copy this secret now — it will not be shown again, createdAt} • Map PartnerNotFoundException to 404, PartnerNotEligibleException to 403 • Apply RBAC: OPS_OPERATOR or SUPER_ADMIN • Integration test: verify apiSecret not retrievable after first response | POST /admin/partners/{id}/credentials endpoint with one-time secret disclosure, integration tests | • 201 response includes both apiKey and apiSecret in plaintext • Calling the endpoint twice: second call returns a new apiKey and apiSecret; querying DB shows only one active credential (the new one) • GET /admin/partners/{id}/credentials (view endpoint per 10.3-T18) returns apiKey but NOT apiSecret • Calling for a SUSPENDED partner returns 403 • Audit log entry partner.credential_generated with entity_id = partner_id exists after 201 • ADMIN_VIEWER role returns 403 | 35 | 10.3-T08, 10.3-T19 | FS | PRD-07
10.3-T22 | admin-ui | 10.3 | 10. Admin System | Partner management & credentials | 2 | REST endpoint: DELETE /admin/partners/{id}/credentials — revoke credentials | Endpoint for revoking the active API credential of a partner. After revocation, the partner cannot authenticate API calls until new credentials are generated (10.3-T21). Access: OPS_OPERATOR and SUPER_ADMIN. Requires an explicit confirmation flag in request body: {confirm: true}. On success: 200 with {status: revoked, revokedAt: ISO-8601}. If no active credential exists: 404. If partner not found: 404. Audit event: partner.credential_revoked. | • Create DELETE /admin/partners/{id}/credentials endpoint (or POST /admin/partners/{id}/credentials/revoke if DELETE body not supported by proxy) • Require confirm = true in request body; return 400 if absent or false • Call PartnerCredentialService.revokeCredentials(partnerId, actorUserId, actorIp) • Map no-active-credential case to 404 with message: no active credential found for this partner • Apply RBAC: OPS_OPERATOR or SUPER_ADMIN • Integration test: revoke, then attempt partner API auth should fail | Revoke-credential endpoint with confirmation gate, integration tests | • Request without confirm = true returns 400 • Successful revoke returns 200 with revokedAt timestamp • After revoke, attempting partner API authentication with the old credential returns 401 • Revoking when no active credential exists returns 404 • Audit log entry partner.credential_revoked exists after successful revoke • ADMIN_VIEWER returns 403 | 30 | 10.3-T08, 10.3-T19 | FS | PRD-07
10.3-T23 | admin-ui | 10.3 | 10. Admin System | Partner management & credentials | 2 | REST endpoint: POST /admin/partners/{id}/prefunding/topups — record top-up | Endpoint for recording a prefunding top-up. Access: OPS_OPERATOR and SUPER_ADMIN (Finance Analyst can also view but not record; RBAC enforced). Request: {amountUsd: decimal, bankRef: string required, valueDate: date YYYY-MM-DD, notes: string optional}. Calls PrefundingService.recordTopUp(). On success: 201 with {newBalanceUsd, ledgerEntryId, recordedAt}. If partner is LOCAL (no prefunding account): 422 with message: LOCAL partners do not have prefunding accounts. If amountUsd <= 0: 400. Audit event: prefunding.topup_recorded. | • Create POST /admin/partners/{id}/prefunding/topups endpoint • Validate amountUsd > 0 and bankRef non-empty • Call PrefundingService.recordTopUp(partnerId, request, actorUserId, actorIp) • Map AccountNotFoundException (LOCAL partner) to 422 • Return 201 with TopUpResponse including new balance • Apply RBAC: OPS_OPERATOR or SUPER_ADMIN for writes | POST /admin/partners/{id}/prefunding/topups endpoint with validation, integration tests | • POST with amountUsd = -50 returns 400 • POST for a LOCAL partner returns 422 with appropriate message • Successful POST returns 201 with newBalanceUsd = previous balance + amountUsd • Audit log entry prefunding.topup_recorded exists after 201 • Concurrent POST requests (2x100.00 on balance 500.00) result in final balance = 700.00 (atomicity check in integration test) • FINANCE_ANALYST role returns 403 for this write endpoint | 35 | 10.3-T13, 10.3-T19 | FS | PRD-07
10.3-T24 | admin-ui | 10.3 | 10. Admin System | Partner management & credentials | 2 | REST endpoint: GET /admin/partners/{id}/prefunding/ledger — ledger history | Paginated ledger view for a partner's prefunding account. Access: OPS_OPERATOR, SUPER_ADMIN, and FINANCE_ANALYST (read access per RBAC matrix in PRD-07 §12.3). Returns paginated list of ledger entries ordered by created_at DESC. Each entry includes: id, entry_type, amount, balance_after, txn_ref (nullable), note, created_at, created_by. Default page size 20; max 100. Filter by entry_type (optional) and date range (optional). Returns 200 with Page<LedgerEntryDTO>. If partner is LOCAL: 404 (no account). If partner not found: 404. | • Create GET /admin/partners/{id}/prefunding/ledger endpoint • Support query params: entryType (optional), fromDate, toDate, page, size • Call PartnerQueryService or PrefundingService.getLedgerHistory(partnerId, filter, pageable) • Apply RBAC: allow OPS_OPERATOR, SUPER_ADMIN, FINANCE_ANALYST • Return 404 for LOCAL partners or unknown partner id • Integration test with multiple entry types and date filters | GET /admin/partners/{id}/prefunding/ledger endpoint with filtering and pagination, integration tests | • Returns entries ordered by created_at DESC • Filter by entryType = CREDIT_TOPUP returns only top-up entries • ADMIN_VIEWER role returns 403 • GET for LOCAL partner returns 404 • Pagination: page 0 size 2 returns 2 entries; page 1 returns the next 2 • Date range filter fromDate = 2026-01-01 toDate = 2026-01-31 returns only entries in January 2026 | 35 | 10.3-T18, 10.3-T23 | FS | PRD-07
10.3-T25 | admin-ui | 10.3 | 10. Admin System | Partner management & credentials | 2 | REST endpoint: GET /admin/partners and GET /admin/partners/{id} — list and detail | List endpoint: GET /admin/partners returns Page<PartnerSummaryDTO> (partnerCode, name, partnerType, settleACcy, status, prefundingBalanceUsd, lastUpdated). Filter params: status, partnerType, search (name or code partial). Calls PartnerQueryService.listPartners(). Detail endpoint: GET /admin/partners/{id} returns PartnerDetailDTO including all identity, settlement, credential (apiKey only), and prefunding summary fields. Access for both: OPS_OPERATOR, SUPER_ADMIN, FINANCE_ANALYST (read). ADMIN_VIEWER gets 403 per permission matrix. Return 404 if id not found. | • Create GET /admin/partners endpoint with filter and pagination params • Create GET /admin/partners/{id} endpoint • Call PartnerQueryService.listPartners and getPartnerDetail respectively • Apply RBAC: allow OPS_OPERATOR, SUPER_ADMIN, FINANCE_ANALYST • Return 404 for unknown id • Integration tests with various filter combinations | GET /admin/partners and GET /admin/partners/{id} endpoints with RBAC, integration tests | • GET /admin/partners?status=ACTIVE returns only ACTIVE partners • GET /admin/partners?partnerType=OVERSEAS returns only OVERSEAS partners • GET /admin/partners/{id} returns apiKey but no api_secret_hash field in response • GET /admin/partners/{nonexistent} returns 404 • ADMIN_VIEWER role returns 403 on both endpoints • prefundingBalanceUsd is null in summary for LOCAL partner and a decimal value for OVERSEAS | 35 | 10.3-T18, 10.3-T19 | FS | PRD-07
10.3-T26 | admin-ui | 10.3 | 10. Admin System | Partner management & credentials | 2 | Unit tests: PartnerService validation edge cases | Exhaustive unit tests for all validation rules in PartnerService (10.3-T09, T10, T11). Test class PartnerServiceValidationTest. Use Mockito to stub PartnerRepository and AuditLogService. Test vectors must cover: (A) createPartner validations; (B) activatePartner pre-condition combinations; (C) updatePartner immutability after activation. | • Write test cases A1-A5 for createPartner: partnerCode with hyphen, non-HTTPS webhook, LOCAL with mismatched currencies, duplicate code, valid LOCAL, valid OVERSEAS • Write test cases B1-B4 for activatePartner: no credential, no prefunding account (OVERSEAS), zero balance (OVERSEAS), all conditions met (LOCAL), all conditions met (OVERSEAS) • Write test cases C1-C2 for updatePartner immutability: change partnerType after ACTIVE throws ImmutableFieldException, change name after ACTIVE succeeds • Run all tests; assert 0 failures | PartnerServiceValidationTest class with minimum 11 named test cases covering all rules above | • A1: partnerCode GME-REMIT throws ValidationException with message containing partnerCode • A3: LOCAL partner with collectionCcy = MNT and settleACcy = KRW throws ValidationException • B1: activatePartner with no credential returns unmet list containing NO_ACTIVE_CREDENTIAL • B3: activatePartner OVERSEAS with balance = 0 returns unmet list containing PREFUNDING_BALANCE_ZERO • C1: updating partnerType after ACTIVE throws ImmutableFieldException • All 11+ tests pass with 0 failures in CI | 40 | 10.3-T09, 10.3-T10, 10.3-T11 | FS | PRD-07
10.3-T27 | admin-ui | 10.3 | 10. Admin System | Partner management & credentials | 2 | Unit tests: PrefundingService atomicity and edge cases | Unit and integration tests for PrefundingService (10.3-T13, T14, T15, T17). Focus on: atomicity of top-up and deduction under concurrency, insufficient balance rejection, deduction reversal idempotency, and negative-balance guard on adjustments. Use Testcontainers (real PostgreSQL) for concurrency tests. | • Write PrefundingServiceAtomicityTest using Testcontainers for a real PostgreSQL instance • Test concurrent top-ups: 10 threads each adding 100.00 on initial balance 0 -> expect final balance = 1000.00 • Test concurrent deductions: 10 threads each deducting 60.00 on balance 500.00 -> expect 8 succeed, 2 fail with InsufficientPrefundingException and final balance = 20.00 • Test reversal idempotency: call reverseDeduction 5 times with same txnRef -> exactly 1 ledger row, balance credited once • Test adjustment negative-balance guard: adjustment of -600.00 on balance 500.00 throws exception | PrefundingServiceAtomicityTest class with concurrency and idempotency tests against real PostgreSQL | • Concurrent top-ups test: final balance equals thread_count * amount with no lost updates • Concurrent deductions test: number of successful deductions = floor(500.00 / 60.00) = 8; final balance = 500.00 - 8*60.00 = 20.00 • Reversal idempotency: exactly one DEBIT_REVERSAL ledger entry after 5 calls with same txnRef • Adjustment -600 on balance 500 throws InsufficientPrefundingException; balance unchanged • All tests pass in CI with Testcontainers PostgreSQL 15 | 55 | 10.3-T13, 10.3-T14, 10.3-T15, 10.3-T17 | FS | PRD-07
10.3-T28 | admin-ui | 10.3 | 10. Admin System | Partner management & credentials | 2 | Unit tests: PartnerCredentialService key generation and bcrypt | Unit tests for PartnerCredentialService (10.3-T08). Verify: (1) api_key format (32 hex chars, no dashes); (2) api_secret format (base64url, 44 chars); (3) bcrypt hash of returned plaintext matches DB hash; (4) single-active-credential invariant under concurrent generation; (5) revoke sets is_active = FALSE. | • Write PartnerCredentialServiceTest with Mockito stubs for repository and audit • Test generateCredentials returns api_key matching [a-f0-9]{32} regex • Test BCrypt.checkpw(returnedPlaintext, storedHash) == true • Test that generating credentials when one active credential exists: call verify is_active = FALSE on old, new row is_active = TRUE • Test revokeCredentials: sets is_active = FALSE on the active credential • Test generateCredentials for SUSPENDED partner throws PartnerNotEligibleException | PartnerCredentialServiceTest class with 6 named test cases | • api_key matches [a-f0-9]{32} • api_secret is 44 chars and valid base64url • BCrypt.checkpw(returnedSecret, storedHash) returns true in all test cases • After generateCredentials, only one row with is_active = TRUE for the partner • revokeCredentials leaves zero active credentials for the partner • SUSPENDED partner test throws PartnerNotEligibleException | 40 | 10.3-T08 | FS | PRD-07
10.3-T29 | admin-ui | 10.3 | 10. Admin System | Partner management & credentials | 2 | Unit tests: LowBalanceAlertService threshold and deduplication | Unit tests for LowBalanceAlertService (10.3-T16). Use Mockito to stub EmailSendPort. Test all alert thresholds and the 1-hour deduplication logic. | • Write LowBalanceAlertServiceTest with mocked EmailSendPort and mocked PrefundingAccountRepository • Test: balance 8500 with threshold 10000 -> EmailSendPort.send called once with correct addresses and suggested top-up = 1500.00 • Test: balance 15000 with threshold 10000 -> no email sent • Test: balance 0 -> urgent email sent AND PartnerService.suspendPartner called • Test deduplication: first call sends email; second call within 1 hour suppressed; call after 1 hour sends again (mock the clock) • Test comma-separated alert_email: partner with alert_email = ops@gme.com,finance@gme.com -> EmailSendPort.send called for each address | LowBalanceAlertServiceTest class with 5 named test cases, all passing | • EmailSendPort.send called with suggested top-up = (threshold - balance) = 1500.00 when balance = 8500 • No email when balance > threshold • balance = 0: suspendPartner called with reason = ZERO_BALANCE • Deduplication: only one email sent for two calls within 1 hour • Comma-separated emails: both ops@gme.com and finance@gme.com receive separate calls to EmailSendPort.send | 35 | 10.3-T16 | FS | PRD-07
10.3-T30 | admin-ui | 10.3 | 10. Admin System | Partner management & credentials | 2 | Admin UI: Partner list page (read-only display) | React (or the project front-end framework) page at /admin/partners. Displays a table with columns: Partner Name, Partner Code, Type (LOCAL¦OVERSEAS badge), Settlement Currency, Status (coloured badge: ONBOARDING=grey, ACTIVE=green, SUSPENDED=red), Prefunding Balance (USD for OVERSEAS; dash for LOCAL), Last Updated. Fetches from GET /admin/partners with filter params mapped to query parameters. Supports filters: Status (multi-select), Type (multi-select), Search (text input, debounced 300ms). Pagination with 20 rows per page. Actions per row: View, Manage (Edit/Activate/Suspend). Prefunding balance shown as USD 12,345.67; red text if below threshold. | • Create PartnerListPage component fetching GET /admin/partners • Implement filter bar with Status and Type multi-selects and a debounced search input • Render table with all 7 columns; format balance as USD 12,345.67 or dash • Show balance in red text when balance < low_balance_threshold • Implement pagination controls • Add row actions: View links to /admin/partners/{id}; Manage opens edit modal or links to edit page | PartnerListPage component with filters, pagination, balance color indicator, and row actions; renders correctly in Storybook or with mock API | • Table renders 20 rows per page; Next button fetches page 2 • LOCAL partner row shows dash in Prefunding Balance column • OVERSEAS partner with balance 8500 and threshold 10000 shows USD 8,500.00 in red • Status filter ACTIVE hides ONBOARDING and SUSPENDED rows • Search input debounces: typing fast sends only one request after 300ms pause • All 7 columns present with correct labels | 55 | 10.3-T25 | FS | PRD-07
10.3-T31 | admin-ui | 10.3 | 10. Admin System | Partner management & credentials | 2 | Admin UI: Create partner form — identity and settlement sections | Form at /admin/partners/new. Sections: (1) Identity: Partner Name (text, required, max 100), Partner Code (text, uppercase alphanumeric + underscore, max 20, unique-validated on blur), Partner Type (LOCAL¦OVERSEAS radio, immutable after activation — show tooltip), Contact Email (email, required), Webhook URL (HTTPS, required), Rate Quote TTL (integer 60-1800, default 300). (2) Settlement: Collection Currency (select from currency registry), Settlement A Currency (auto-set to same as Collection if LOCAL; editable for OVERSEAS). For OVERSEAS, show Prefunding section (10.3-T32). On submit call POST /admin/partners; show field errors from 400 response inline; show 409 as banner error on Partner Code field. | • Create CreatePartnerForm component with react-hook-form or equivalent • Implement Section 1 fields with inline validation (regex on Partner Code, HTTPS on Webhook URL) • Implement Section 2 Settlement fields; auto-set Settle A = Collection for LOCAL on partnerType change • Implement submit handler calling POST /admin/partners; map 400 errors to field-level messages • Map 409 to banner on Partner Code field: This code is already in use • Storybook/unit tests for each validation state | CreatePartnerForm component with identity and settlement sections; validation and API error display | • Entering partner code GME-REMIT (hyphen) shows inline error: only letters, numbers, and underscores • Entering http:// webhook URL shows inline error: must be HTTPS • Selecting LOCAL auto-sets Settlement A to match Collection Currency and disables the field • 409 response shows banner error on Partner Code field • Valid form submission calls POST /admin/partners with correct JSON body • Partner Type radio shows tooltip: cannot be changed after activation | 55 | 10.3-T19, 10.3-T30 | FS | PRD-07
10.3-T32 | admin-ui | 10.3 | 10. Admin System | Partner management & credentials | 2 | Admin UI: Create partner form — prefunding setup section (OVERSEAS only) | This section is visible only when Partner Type = OVERSEAS. Fields: Prefunding Account ID (text, required, auto-generated suggestion = PFUND-{PARTNERCODE}), Initial Prefunding Balance (decimal USD, >= 0, required for activation but can be 0 at creation), Low-Balance Alert Threshold (decimal USD, default 10000, >= 0), Alert Recipients (comma-separated emails, required minimum 1, validated format). Section is hidden and its fields excluded from form submission when Partner Type = LOCAL. | • Add conditional prefunding section to CreatePartnerForm (visible only when partnerType = OVERSEAS) • Implement Prefunding Account ID with auto-suggested value PFUND-{PARTNERCODE} that updates as user types code • Implement alert threshold with default 10000; validate >= 0 • Implement Alert Recipients with email-list validation (split by comma, validate each as email) • Exclude section entirely from form payload when partnerType = LOCAL • Unit test: switch partnerType from OVERSEAS to LOCAL -> section disappears and fields excluded from payload | Prefunding section integrated into CreatePartnerForm; conditional visibility and email-list validation | • Section invisible when partnerType = LOCAL • Section visible when partnerType = OVERSEAS • Alert Recipients field rejects non-email entries: ops@gme.com,not-an-email shows validation error • Prefunding Account ID auto-suggests PFUND-SENDMN when partner code is SENDMN • Switching from OVERSEAS to LOCAL removes prefundingThresholdUsd from submitted JSON body • Default threshold = 10000 is pre-filled when section becomes visible | 40 | 10.3-T31 | FS | PRD-07
10.3-T33 | admin-ui | 10.3 | 10. Admin System | Partner management & credentials | 2 | Admin UI: Partner detail page — identity, credential, and action buttons | Page at /admin/partners/{id}. Fetches GET /admin/partners/{id}. Displays: (1) Identity section (all fields, read-only with Edit button for name/webhook/ttl); (2) API Credentials section showing apiKey and createdAt (no secret); button Generate New Credentials (POST /admin/partners/{id}/credentials) shows confirmation modal; button Revoke Credentials (DELETE) shows confirmation modal with warning This will immediately block partner API access; (3) Activation action buttons: Activate (if ONBOARDING), Suspend (if ACTIVE), Reactivate (if SUSPENDED). Credential generation shows a one-time modal with the apiSecret and a Copy button; modal warns Copy and store the secret now — it cannot be retrieved again. | • Create PartnerDetailPage fetching GET /admin/partners/{id} • Render identity section with inline Edit button opening an edit drawer • Render API Credentials section with apiKey and Generate/Revoke buttons • Implement Generate modal: call POST, display apiSecret in one-time modal with Copy button; modal does not re-show on close • Implement Revoke modal: require confirmation text before enabling Revoke button • Render status-dependent action button (Activate/Suspend/Reactivate) and call corresponding endpoints | PartnerDetailPage with credential management and status action buttons; Storybook stories for ONBOARDING, ACTIVE, SUSPENDED states | • Generate New Credentials modal shows apiSecret exactly once; closing and reopening does not show secret again • Revoke Credentials button disabled until user types CONFIRM in confirmation input • Activate button visible only when status = ONBOARDING; Suspend only when ACTIVE; Reactivate only when SUSPENDED • apiKey is displayed; api_secret_hash is not present in page HTML or network response • After Suspend action, page re-fetches and shows SUSPENDED badge • Activate 422 response displays list of unmet conditions to the operator | 55 | 10.3-T20, 10.3-T21, 10.3-T22, 10.3-T25 | FS | PRD-07
10.3-T34 | admin-ui | 10.3 | 10. Admin System | Partner management & credentials | 2 | Admin UI: Prefunding balance panel and top-up form | On the partner detail page (OVERSEAS only), render a Prefunding panel showing: current balance (USD), low-balance threshold, traffic-light indicator (green >= 150% threshold, amber 100-149%, red < 100%), last top-up date and amount, last deduction date and amount. Record Top-Up button opens a modal form: Amount (USD, > 0), Bank Reference (required), Value Date (date picker), Notes (optional). On submit call POST /admin/partners/{id}/prefunding/topups; show new balance in panel on success. Ledger link opens GET /admin/partners/{id}/prefunding/ledger in a paginated side-panel. | • Add Prefunding panel to PartnerDetailPage (visible only when partner_type = OVERSEAS) • Render balance with traffic-light icon based on balance / threshold ratio • Implement Record Top-Up modal with validation (amount > 0, bankRef required) • On submit call POST topups endpoint; update balance display on 201 response • Add Ledger button opening paginated ledger side-panel calling GET /admin/partners/{id}/prefunding/ledger • Test traffic-light thresholds: balance 15000 threshold 10000 = green (150%); balance 10500 threshold 10000 = amber (105%); balance 9000 threshold 10000 = red (90%) | Prefunding panel component with top-up modal, traffic-light indicator, and ledger side-panel; unit tests for traffic-light logic | • balance 15000 / threshold 10000 = 150%: green indicator • balance 10500 / threshold 10000 = 105%: amber indicator • balance 9000 / threshold 10000 = 90%: red indicator • Top-up with amount = 0 shows validation error; amount = 100.00 succeeds and updates balance display • Ledger side-panel renders entries sorted by created_at DESC • Panel is not rendered for LOCAL partners | 50 | 10.3-T23, 10.3-T24, 10.3-T33 | FS | PRD-07
10.3-T35 | admin-ui | 10.3 | 10. Admin System | Partner management & credentials | 2 | Admin UI: Audit log view for partner events | On the partner detail page, add an Audit Log tab showing all audit events where entity_type = partner AND entity_id = {partnerId}. Also include related events: entity_type = partner_credential AND entity_id = any credential for this partner, and entity_type = prefunding_account. Table columns: Timestamp (UTC), Actor, Event Type (human-readable label), Field Changed, Previous Value, New Value. Sorted by timestamp DESC, paginated 20 per page. Export CSV button calls backend CSV export. Access: OPS_OPERATOR and SUPER_ADMIN only (FINANCE_ANALYST and ADMIN_VIEWER cannot see audit log per PRD-07 §12.3). | • Add Audit Log tab to PartnerDetailPage • Fetch audit entries via GET /admin/partners/{id}/audit (new endpoint below) with pagination • Render table with 6 columns; format event_type codes as human-readable labels (e.g. partner.activated -> Partner Activated) • Implement CSV export button triggering download • Hide tab for FINANCE_ANALYST and ADMIN_VIEWER (check role in UI state) • Create GET /admin/partners/{id}/audit backend endpoint returning paginated audit entries for the partner and its credentials/prefunding | Audit Log tab on partner detail page with CSV export; backend GET /admin/partners/{id}/audit endpoint; RBAC hiding for non-authorized roles | • Tab visible for OPS_OPERATOR; not visible for FINANCE_ANALYST • Entries include partner.credential_generated events with partner credential entity • CSV export downloads file with correct headers: timestamp,actor,eventType,entityType,entityId,previousValue,newValue • partner.activated event shows previousValue = {status: ONBOARDING} and newValue = {status: ACTIVE} • Pagination: page 0 size 20 fetches first 20 entries; next page fetches correctly • Events sorted by timestamp DESC (newest first) | 55 | 10.3-T06, 10.3-T33 | FS | PRD-07
10.3-T36 | admin-ui | 10.3 | 10. Admin System | Partner management & credentials | 2 | E2E integration test: full partner onboarding flow (LOCAL) | End-to-end test simulating the complete onboarding of a LOCAL partner (GME_REMIT_TEST) using the Admin API. Flow: (1) POST /admin/partners -> ONBOARDING; (2) POST /admin/partners/{id}/credentials -> get apiKey+apiSecret; (3) PUT /admin/partners/{id}/activate -> expect 422 NO_ACTIVE_CREDENTIAL is NOT in unmet (credential just generated); (4) confirm status = ACTIVE; (5) verify partner appears in GET /admin/partners list with status ACTIVE; (6) verify audit log has partner.created, partner.credential_generated, partner.activated entries in order. Use a dedicated test PostgreSQL database (Testcontainers). Clean up after test. | • Create PartnerOnboardingLocalE2ETest using Spring Boot test context and Testcontainers • Execute the 6-step flow against the running application • Assert each step response code and body • Query the audit_log table directly to verify event sequence • Assert no prefunding_account row exists for the LOCAL partner • Tear down by deleting the test partner or rolling back the transaction | PartnerOnboardingLocalE2ETest class with 6 sequential assertions, passing in CI | • Step 1: POST returns 201 with status = ONBOARDING • Step 2: POST credentials returns 201 with apiKey (32 chars) and apiSecret (44 chars) • Step 3: PUT activate returns 200 with status = ACTIVE (all pre-conditions met) • Step 4: GET /admin/partners/{id} shows status = ACTIVE and is_active = TRUE • Step 5: GET /admin/partners?status=ACTIVE includes the new partner • Step 6: audit_log contains exactly 3 events in order: partner.created, partner.credential_generated, partner.activated | 55 | 10.3-T19, 10.3-T20, 10.3-T21, 10.3-T25 | FS | PRD-07
10.3-T37 | admin-ui | 10.3 | 10. Admin System | Partner management & credentials | 2 | E2E integration test: full partner onboarding flow (OVERSEAS with prefunding) | End-to-end test for OVERSEAS partner (SENDMN_TEST). Flow: (1) POST /admin/partners OVERSEAS with threshold 10000, alertEmail = test@gme.com -> ONBOARDING + prefunding_account created with balance 0; (2) attempt activate -> expect 422 with unmet = [NO_ACTIVE_CREDENTIAL, PREFUNDING_BALANCE_ZERO]; (3) POST credentials; (4) attempt activate -> expect 422 with unmet = [PREFUNDING_BALANCE_ZERO]; (5) POST top-up 50000.00; (6) PUT activate -> 200 ACTIVE; (7) simulate deduction of 45000.00 -> balance = 5000 < threshold 10000 -> low-balance alert email triggered; (8) verify audit log sequence. | • Create PartnerOnboardingOverseasE2ETest with Testcontainers and mocked EmailSendPort • Execute 8-step flow sequentially • Assert each step response and DB state • After step 7: verify EmailSendPort.send was called with suggested top-up = 5000.00 and correct recipient • After step 7: verify balance = 5000.00 in prefunding_account • Verify audit log has 6 events in order: partner.created, prefunding.account_created, partner.credential_generated, prefunding.topup_recorded, partner.activated, prefunding.deduction_reversed (if applicable) | PartnerOnboardingOverseasE2ETest class with 8 sequential assertions, passing in CI | • Step 2: 422 response lists both NO_ACTIVE_CREDENTIAL and PREFUNDING_BALANCE_ZERO • Step 4: 422 response lists only PREFUNDING_BALANCE_ZERO (credential now exists) • Step 6: 200 response with status = ACTIVE after top-up • Step 7: balance = 5000.0000 in prefunding_account after deduction of 45000.00 • Step 7: EmailSendPort.send called with suggested top-up = 5000.00 (threshold 10000 - balance 5000) • Audit log contains prefunding.account_created event immediately after partner.created | 55 | 10.3-T14, 10.3-T16, 10.3-T36 | FS | PRD-07
10.4-T01 | admin-ui | 10.4 | 10. Admin System | Rule/Mapping page — 4 sections | 2 | Add rule table DB migration: currency quadruple, rate sources, margins, service charge | The rule table is the join record (partner_id, scheme_id, direction). It stores the full currency quadruple auto-derived at creation (collection_ccy, settle_a_ccy, settle_b_ccy, payout_ccy), two rate source slots (rate_coll_source, rate_pay_source each CHECK IN ('IDENTITY','LIVE','MANUAL','PARTNER')), optional manual overrides (manual_rate_coll DECIMAL(20,8), manual_rate_pay DECIMAL(20,8)), override expiry dates (rate_coll_override_expires DATE, rate_pay_override_expires DATE), margins m_a and m_b (DECIMAL(8,6) DEFAULT 0 CHECK >= 0), service_charge_amount DECIMAL(20,4) DEFAULT 0, service_charge_ccy CHAR(3) must equal settle_a_ccy, is_same_ccy_shortcircuit BOOLEAN computed on save, status VARCHAR(20) CHECK IN ('DRAFT','ACTIVE','SUSPENDED'), effective_from TIMESTAMPTZ, standard audit cols (created_at, updated_at, created_by, updated_by). DB-level CHECK: is_same_ccy_shortcircuit OR (m_a + m_b) >= 0.02. UNIQUE constraint (partner_id, scheme_id, direction). | • Create Flyway/Liquibase migration file V10_4_001__create_rule_table.sql • Add all columns with types, NOT NULL constraints, and CHECK constraints as specified • Add UNIQUE INDEX on (partner_id, scheme_id, direction) • Add FK constraints to partner and qr_scheme tables • Add DB-level CHECK constraint: is_same_ccy_shortcircuit = TRUE OR (m_a + m_b) >= 0.02 | Migration file V10_4_001__create_rule_table.sql that applies cleanly on a fresh schema | • Migration applies without error on empty schema; table has all 20+ columns with correct types • UNIQUE constraint rejects duplicate (partner_id=1, scheme_id=1, direction='INBOUND') insert • DB CHECK rejects INSERT with is_same_ccy_shortcircuit=false, m_a=0.005, m_b=0.010 (sum=1.5% < 2%) • DB CHECK accepts INSERT with is_same_ccy_shortcircuit=true, m_a=0, m_b=0 • manual_rate_coll column accepts NULL when rate_coll_source = 'LIVE' | 35 |  | FS | PRD-07, RATE-04
10.4-T02 | admin-ui | 10.4 | 10. Admin System | Rule/Mapping page — 4 sections | 2 | Add service_charge_tier table DB migration | The service_charge_tier table provides optional volume-tier overrides for service charge per rule. Columns: id BIGINT PK auto-increment, rule_id BIGINT FK -> rule NOT NULL, min_collection_usd DECIMAL(20,4) NOT NULL (lower bound inclusive), max_collection_usd DECIMAL(20,4) NULL (upper bound exclusive; NULL = no cap), charge_amount DECIMAL(20,4) NOT NULL CHECK >= 0, standard audit cols (created_at, updated_at, created_by, updated_by). If no tier rows exist for a rule, the flat rule.service_charge_amount applies. Tiers are indexed by collection_usd (the USD pool amount before margin deduction). | • Create migration file V10_4_002__create_service_charge_tier_table.sql • Add FK to rule table with ON DELETE CASCADE • Add CHECK constraint: charge_amount >= 0 • Add CHECK constraint: max_collection_usd IS NULL OR max_collection_usd > min_collection_usd • Add index on rule_id for efficient tier lookup at transaction time | Migration file V10_4_002__create_service_charge_tier_table.sql | • FK ON DELETE CASCADE removes tier rows when parent rule is deleted • CHECK rejects row with max_collection_usd=100 and min_collection_usd=200 • CHECK rejects negative charge_amount • NULL max_collection_usd is accepted (open-ended top tier) • Index on rule_id exists in EXPLAIN plan for SELECT WHERE rule_id = ? | 20 | 10.4-T01 | FS | PRD-07, RATE-04
10.4-T03 | admin-ui | 10.4 | 10. Admin System | Rule/Mapping page — 4 sections | 2 | Add rule_audit_log table DB migration | Every field-level change on the mapping page must be audit-logged with: rule_id, event type ('rule_field_changed'), actor_user_id VARCHAR, timestamp_utc TIMESTAMPTZ, field_name VARCHAR(80), previous_value TEXT, new_value TEXT, rule_key JSON (partner_code, scheme_code, direction). Audit rows are immutable (no UPDATE/DELETE). This table feeds the Rule Audit History view. Per PRD-07 §6.4.5 the audit event format is: {event, actor_user_id, timestamp_utc, rule_key:{partner, scheme, direction}, field, previous_value, new_value}. | • Create migration V10_4_003__create_rule_audit_log_table.sql • Include columns: id BIGINT PK, rule_id BIGINT FK (nullable so records survive rule deletion), event VARCHAR(60) DEFAULT 'rule_field_changed', actor_user_id VARCHAR(120), timestamp_utc TIMESTAMPTZ NOT NULL DEFAULT NOW(), field_name VARCHAR(80), previous_value TEXT, new_value TEXT, rule_key JSONB • Add index on rule_id for history view queries • Add index on timestamp_utc for time-range searches • Do NOT add any UPDATE or DELETE privileges in migration comments | Migration file V10_4_003__create_rule_audit_log_table.sql | • Table created with all required columns and correct types • Index on rule_id present • Row inserted for field_name='m_a', previous_value='0.010000', new_value='0.012500' is retrievable • No DB-level UPDATE or DELETE constraint violation on attempts to modify existing rows (verify no ON UPDATE trigger exists) • JSONB rule_key column accepts valid JSON and rejects malformed strings | 20 | 10.4-T01 | FS | PRD-07, RATE-04
10.4-T04 | admin-ui | 10.4 | 10. Admin System | Rule/Mapping page — 4 sections | 2 | Implement RuleRepository: CRUD + currency quadruple auto-derivation on create | When a rule is created via the Admin portal, the system must auto-derive the 4 currency fields from the partner and scheme profiles: collection_ccy <- partner.collection_currency, settle_a_ccy <- partner.settlement_currency, settle_b_ccy <- qr_scheme.settlement_currency, payout_ccy <- qr_scheme.payout_currency. The is_same_ccy_shortcircuit flag must be computed on save: true iff collection_ccy = settle_a_ccy = settle_b_ccy = payout_ccy. The effective_from timestamp is set to NOW() on every save. Repository must also support findByPartnerSchemeDirection (primary key lookup) and findAll for list view. | • Create RuleRepository interface with methods: save(Rule), findById(Long), findByPartnerSchemeDirection(Long partnerId, Long schemeId, String direction), findAll() • Implement JPA/JDBC mapping to the rule table • On create, join to partner and qr_scheme to populate the 4 currency fields before insert • Compute is_same_ccy_shortcircuit = (collection_ccy.equals(settle_a_ccy) && settle_a_ccy.equals(settle_b_ccy) && settle_b_ccy.equals(payout_ccy)) • Set effective_from = Instant.now() on every save; do not allow caller to override this field | RuleRepository class and Rule entity with auto-derivation logic | • Creating a rule for GME Remit (collect=KRW, settleA=KRW) on ZeroPay (settleB=KRW, payout=KRW) sets is_same_ccy_shortcircuit=true • Creating a rule for SendMN (collect=MNT, settleA=USD) on ZeroPay (settleB=KRW, payout=KRW) sets is_same_ccy_shortcircuit=false • collection_ccy is populated from partner, not from caller input • findByPartnerSchemeDirection returns empty Optional for non-existent (partnerId=99, schemeId=1, direction='INBOUND') • effective_from is set to current UTC on every save call | 40 | 10.4-T01 | FS | PRD-07, RATE-04
10.4-T05 | admin-ui | 10.4 | 10. Admin System | Rule/Mapping page — 4 sections | 2 | Implement RuleService: rate source auto-resolution logic | Each rule has two rate source slots. Source type must be auto-resolved by the system at create/load time (not stored manually by operator): IDENTITY if settle_a_ccy='USD' (coll leg) or settle_b_ccy='USD' (pay leg); LIVE if settle ccy != USD and no operator MANUAL override is in effect; MANUAL if operator has set an override and the override has not expired; PARTNER if the qr_scheme.rate_source_pay='PARTNER' (scheme-level config). The operator can only switch a LIVE leg to MANUAL — they cannot override IDENTITY or PARTNER. For same-currency short-circuit rules, both slots must be IDENTITY regardless. | • Create RuleService.resolveRateSource(Rule rule, String leg) that returns RateSourceType enum • For leg='coll': if settle_a_ccy='USD' -> IDENTITY; elif scheme configured PARTNER for coll -> PARTNER; elif manual_rate_coll is set and (rate_coll_override_expires IS NULL OR rate_coll_override_expires >= today) -> MANUAL; else -> LIVE • For leg='pay': if settle_b_ccy='USD' -> IDENTITY; elif scheme.rate_source_pay='PARTNER' -> PARTNER; elif manual_rate_pay is set and not expired -> MANUAL; else -> LIVE • Override same-currency short-circuit: if is_same_ccy_shortcircuit=true, both legs return IDENTITY • Call resolveRateSource on every rule load so the displayed badge is always current | RuleService.resolveRateSource(Rule, String) method returning RateSourceType | • Rule with settle_a_ccy='USD' returns IDENTITY for coll leg regardless of any manual_rate_coll value • Rule with settle_a_ccy='MNT', no override -> LIVE for coll leg • Rule with settle_a_ccy='MNT', manual_rate_coll=0.00072, no expiry -> MANUAL for coll leg • Rule with manual_rate_coll set but rate_coll_override_expires='2025-01-01' (past date) -> LIVE for coll leg • is_same_ccy_shortcircuit=true rule returns IDENTITY for both legs | 35 | 10.4-T04 | FS | PRD-07, RATE-04
10.4-T06 | admin-ui | 10.4 | 10. Admin System | Rule/Mapping page — 4 sections | 2 | Implement Section 1 API endpoint: GET /admin/rules/{id}/currency-setup | The Mapping Page Section 1 shows the operator the 5 read-only currency fields for the rule: collection_ccy, settle_a_ccy, usd_intermediary (always 'USD', displayed as N/A when is_same_ccy_shortcircuit=true), settle_b_ccy, payout_ccy. It also returns a same_ccy_notice flag (boolean) and, when true, the notice text: 'Same-currency rule - USD pool bypassed. collection_amount = target_payout + service_charge directly. Margin must be 0.' All fields are derived from the rule; none are editable. This endpoint serves the frontend read-only section. | • Create GET /admin/rules/{id}/currency-setup handler in AdminRuleController • Return DTO: CurrencySetupDTO {collection_ccy, settle_a_ccy, usd_intermediary, settle_b_ccy, payout_ccy, same_ccy_shortcircuit: boolean, same_ccy_notice: String¦null} • Set usd_intermediary='USD' always; set it to null or 'N/A' in the same_ccy_notice context per spec • Load rule by id; if not found, return 404 • Require ROLE_OPS or ROLE_FINANCE_ANALYST to call this endpoint (read-only access is broad) | GET /admin/rules/{id}/currency-setup handler and CurrencySetupDTO | • Rule id=1 (SendMN INBOUND: coll=MNT, settleA=USD, settleB=KRW, payout=KRW) returns same_ccy_shortcircuit=false and usd_intermediary='USD' • Rule id=2 (GME Remit DOMESTIC: all KRW) returns same_ccy_shortcircuit=true and same_ccy_notice contains 'USD pool bypassed' • Unknown rule id returns HTTP 404 • No field in response is editable or writable (all are display-only in DTO) • Unauthenticated request returns HTTP 401 | 30 | 10.4-T04 | FS | PRD-07, RATE-04
10.4-T07 | admin-ui | 10.4 | 10. Admin System | Rule/Mapping page — 4 sections | 2 | Implement Section 2 API endpoint: GET /admin/rules/{id}/rate-config | Section 2 Rate Configuration shows two legs (coll and pay). For each leg, the response includes: slot_label (e.g. 'Collection Leg - USD -> MNT'), auto_derived_source (IDENTITY/LIVE/MANUAL/PARTNER resolved by RuleService.resolveRateSource), current_treasury_rate (from treasury_rate table, shown if LIVE or MANUAL; null if IDENTITY or PARTNER), override_source (current toggle state: LIVE or MANUAL), manual_rate_value (decimal, null if not MANUAL), override_expiry_date (date or null). For same-currency rules, both legs show IDENTITY and override_toggle_enabled=false. Current treasury rate is fetched as: SELECT rate FROM treasury_rate WHERE ccy_pair = 'usd_{ccy}' ORDER BY effective_at DESC LIMIT 1. | • Create GET /admin/rules/{id}/rate-config handler • Build RateConfigDTO with nested CollLegDTO and PayLegDTO each containing the 6 fields above • Call RuleService.resolveRateSource for each leg to determine badge • Query treasury_rate for latest rate for each ccy; skip if IDENTITY • Set override_toggle_enabled=false if resolved source is IDENTITY, PARTNER, or same-currency • Require ROLE_OPS to call | GET /admin/rules/{id}/rate-config handler and RateConfigDTO | • SendMN INBOUND rule: coll leg returns source=IDENTITY (settleA=USD), pay leg returns source=LIVE (settleB=KRW) with current treasury rate value • GME Remit DOMESTIC rule: both legs return source=IDENTITY, override_toggle_enabled=false • Rule with manual override set on coll leg: returns source=MANUAL, manual_rate_value populated, override_toggle_enabled=true • treasury_rate not found for ccy pair: current_treasury_rate=null in response, no 500 error • PARTNER source leg returns override_toggle_enabled=false | 40 | 10.4-T05 | FS | PRD-07, RATE-04
10.4-T08 | admin-ui | 10.4 | 10. Admin System | Rule/Mapping page — 4 sections | 2 | Implement Section 2 API endpoint: PATCH /admin/rules/{id}/rate-config (set/clear MANUAL override) | The operator can switch a LIVE leg to MANUAL by providing a manual_rate_value (decimal, > 0) and optional override_expiry_date. They can revert to LIVE by clearing the override. Constraints: only LIVE legs can be switched to MANUAL; IDENTITY and PARTNER legs reject override attempts. MANUAL rate must be > 0. If the new manual rate deviates more than +-20% from the current LIVE treasury rate for that ccy, a deviation_warning flag is returned (HTTP 200 with warning=true) and the save is tentative; the caller must re-POST with confirm=true to commit. All saved changes are audit-logged to rule_audit_log with field names 'rate_coll_source'/'rate_pay_source', 'manual_rate_coll'/'manual_rate_pay', 'rate_coll_override_expires'/'rate_pay_override_expires'. | • Create PATCH /admin/rules/{id}/rate-config accepting RateConfigUpdateDTO {leg: 'coll'¦'pay', action: 'SET_MANUAL'¦'CLEAR_MANUAL', manual_rate_value: Decimal, override_expiry_date: Date, confirm: boolean} • Validate: if action=SET_MANUAL and resolved source != LIVE, return 422 with error 'Cannot override IDENTITY or PARTNER leg' • Validate manual_rate_value > 0 when action=SET_MANUAL • Compute deviation: abs(manual_rate_value - current_treasury_rate) / current_treasury_rate; if > 0.20 and confirm!=true, return 200 with deviation_warning=true without saving • On confirmed save, update rule and write audit log entries for each changed field • Require ROLE_OPS | PATCH /admin/rules/{id}/rate-config handler with deviation guard | • Attempting MANUAL override on IDENTITY leg (settleA=USD) returns HTTP 422 with error message • SET_MANUAL with manual_rate_value=0 returns validation error • SET_MANUAL on LIVE leg with rate 30% above treasury and confirm=false returns 200 deviation_warning=true, rule NOT updated in DB • Same request with confirm=true saves rule and writes audit log entry with field='manual_rate_coll', previous_value='null', new_value='0.00092500' • CLEAR_MANUAL on a MANUAL leg sets manual_rate_coll=NULL and rate_coll_source resolves back to LIVE; audit log entry written | 50 | 10.4-T07, 10.4-T03 | FS | PRD-07, RATE-04
10.4-T09 | admin-ui | 10.4 | 10. Admin System | Rule/Mapping page — 4 sections | 2 | Implement Section 3 API endpoint: GET /admin/rules/{id}/margin | Section 3 returns margin fields for the rule: m_a (DECIMAL stored as fraction e.g. 0.010000 = 1%), m_b, combined_margin (m_a + m_b as fraction), and display_percent values for UI. Also returns is_same_ccy_shortcircuit so the UI knows to lock both fields at 0. For cross-border rules, combined must be >= 0.02 (2%). For same-currency rules, both must be 0. The response includes validation hints: min_combined_required (0.02 for cross-border, 0 for same-ccy) and fields_locked (true when same-currency). | • Create GET /admin/rules/{id}/margin handler • Return MarginDTO: {m_a: decimal, m_b: decimal, combined_margin: decimal, m_a_pct: string, m_b_pct: string, combined_pct: string, is_same_ccy: boolean, min_combined_required: decimal, fields_locked: boolean} • Compute m_a_pct = m_a * 100 formatted to 4 decimal places (e.g. '1.0000') • Set min_combined_required=0.02 when is_same_ccy_shortcircuit=false, else 0 • Set fields_locked=true when is_same_ccy_shortcircuit=true • Require ROLE_OPS or ROLE_FINANCE_ANALYST | GET /admin/rules/{id}/margin handler and MarginDTO | • SendMN INBOUND rule with m_a=0.01, m_b=0.01 returns combined_margin=0.02, combined_pct='2.0000', fields_locked=false • GME Remit DOMESTIC (same-ccy) with m_a=0, m_b=0 returns fields_locked=true, min_combined_required=0 • Rule with m_a=0.005, m_b=0.005 (cross-border) returns combined_pct='1.0000' and min_combined_required=0.02 • m_a_pct for m_a=0.0125 returns '1.2500' • HTTP 404 for unknown rule id | 25 | 10.4-T04 | FS | PRD-07, RATE-04
10.4-T10 | admin-ui | 10.4 | 10. Admin System | Rule/Mapping page — 4 sections | 2 | Implement Section 3 API endpoint: PATCH /admin/rules/{id}/margin with validation | Operator updates m_a and m_b. Both are DECIMAL(8,6) fractions (e.g. 0.010000 = 1%). Validation: each >= 0; each <= 1.0 (100%); max 4 decimal places when expressed as percent (max 6 as fraction). For cross-border rules (is_same_ccy_shortcircuit=false): m_a + m_b must be >= 0.02 (2% combined minimum, hard floor — Save button should be disabled on frontend, backend also enforces). For same-currency rules: m_a and m_b must both equal 0. All changes audit-logged to rule_audit_log with field names 'm_a' and 'm_b', previous and new values stored as 6-decimal strings (e.g. '0.010000'). Changes apply immediately to new transactions upon save; existing committed transactions unaffected. | • Create PATCH /admin/rules/{id}/margin accepting MarginUpdateDTO {m_a: decimal, m_b: decimal} • Validate m_a >= 0 and m_b >= 0 • Validate m_a <= 1.0 and m_b <= 1.0 • For cross-border rules: reject with 422 if m_a + m_b < 0.02; error message: 'Cross-border rules require a combined margin of at least 2.00%' • For same-currency rules: reject with 422 if m_a != 0 or m_b != 0 • On success, write audit log entries for m_a and m_b if changed; update rule; set effective_from=NOW() • Require ROLE_OPS | PATCH /admin/rules/{id}/margin handler with all validation rules | • Cross-border rule: PATCH with m_a=0.005, m_b=0.005 (1% total) returns HTTP 422 with 'combined margin' error message • Cross-border rule: PATCH with m_a=0.010000, m_b=0.010000 (2% total) returns HTTP 200 and rule updated • Same-currency rule: PATCH with m_a=0.01, m_b=0 returns HTTP 422 • Successful change from m_a=0.01 to m_a=0.0125: audit log row has field='m_a', previous_value='0.010000', new_value='0.012500' • m_a=-0.001 returns HTTP 422 with validation error | 40 | 10.4-T09, 10.4-T03 | FS | PRD-07, RATE-04
10.4-T11 | admin-ui | 10.4 | 10. Admin System | Rule/Mapping page — 4 sections | 2 | Implement Section 4 API endpoint: GET /admin/rules/{id}/service-charge | Section 4 returns the flat per-transaction service charge and optional volume-tier table. Response fields: service_charge_amount DECIMAL(20,4), service_charge_ccy CHAR(3) (always = settle_a_ccy; display-only), volume_tiers_enabled BOOLEAN (true if at least one tier row exists), tiers: array of {id, min_collection_usd, max_collection_usd (null = open-ended), charge_amount}. Service charge is always in Settle A currency. Example: GME Remit DOMESTIC -> settle_a_ccy=KRW, service_charge_amount=500. OVERSEAS SendMN -> settle_a_ccy=USD. | • Create GET /admin/rules/{id}/service-charge handler • Return ServiceChargeDTO: {service_charge_amount, service_charge_ccy, volume_tiers_enabled, tiers: List<TierDTO>} • Populate service_charge_ccy from rule.settle_a_ccy (never from caller input) • Fetch all tier rows from service_charge_tier WHERE rule_id=? ORDER BY min_collection_usd ASC • Set volume_tiers_enabled = !tiers.isEmpty() • Require ROLE_OPS or ROLE_FINANCE_ANALYST | GET /admin/rules/{id}/service-charge handler and ServiceChargeDTO | • GME Remit rule returns service_charge_ccy='KRW' regardless of any input • Rule with no tier rows returns volume_tiers_enabled=false and tiers=[] • Rule with 2 tiers returns volume_tiers_enabled=true and tiers sorted by min_collection_usd ascending • Tier with max_collection_usd=null is represented as null in JSON response • HTTP 404 for unknown rule id | 25 | 10.4-T04 | FS | PRD-07, RATE-04
10.4-T12 | admin-ui | 10.4 | 10. Admin System | Rule/Mapping page — 4 sections | 2 | Implement Section 4 API endpoint: PATCH /admin/rules/{id}/service-charge (flat charge update) | Operator updates the flat service charge. service_charge_amount must be >= 0 (0 is valid for domestic rules); max 4 decimal places. service_charge_ccy is NOT accepted from the caller — it is always derived from rule.settle_a_ccy and any submitted currency is ignored. On save: audit log entry with field='service_charge_amount', previous and new values. The change applies to new transactions immediately. Note: this endpoint handles only the flat charge; tier table management is separate (T13/T14). | • Create PATCH /admin/rules/{id}/service-charge accepting ServiceChargeUpdateDTO {service_charge_amount: decimal} • Validate service_charge_amount >= 0 • Validate max 4 decimal places (reject e.g. 500.12345) • Set service_charge_ccy = rule.settle_a_ccy (ignore any ccy field in request) • Write audit log entry for service_charge_amount if changed • Update rule.service_charge_amount; set effective_from=NOW() • Require ROLE_OPS | PATCH /admin/rules/{id}/service-charge handler | • service_charge_amount=500.0000 accepted; rule updated with service_charge_ccy set to rule's settle_a_ccy, not any caller-provided value • service_charge_amount=-1 returns HTTP 422 • service_charge_amount=500.12345 (5 decimal places) returns HTTP 422 • service_charge_amount=0 accepted (domestic rules may have 0) • Audit log entry written with field='service_charge_amount', previous_value='500.0000', new_value='750.0000' | 30 | 10.4-T11, 10.4-T03 | FS | PRD-07, RATE-04
10.4-T13 | admin-ui | 10.4 | 10. Admin System | Rule/Mapping page — 4 sections | 2 | Implement service charge tier CRUD API: POST and DELETE /admin/rules/{id}/service-charge/tiers | The operator can add/remove volume tiers for service charge. Tiers are indexed by collection_usd (USD pool value before margin deduction). Each tier: min_collection_usd (inclusive), max_collection_usd (exclusive, NULL = open-ended), charge_amount >= 0 in settle_a_ccy. Business rule: tier ranges must not overlap (validated on add). A gap between tiers is allowed but flagged as a warning. The flat charge is the fallback if no tier matches at runtime. Tiers are only relevant for cross-border rules where collection_usd is computed; for same-currency short-circuit rules, tiers may exist but will never be used (warn, do not block). | • Create POST /admin/rules/{id}/service-charge/tiers accepting TierCreateDTO {min_collection_usd, max_collection_usd, charge_amount} • Validate charge_amount >= 0; min_collection_usd >= 0; max_collection_usd > min_collection_usd when not null • Check overlap: query existing tiers for rule, reject if new range overlaps any existing tier • Detect and return gap_warning=true if new tier leaves a gap with adjacent tiers (non-fatal) • Create DELETE /admin/rules/{id}/service-charge/tiers/{tier_id} that removes a single tier • Audit-log tier add/remove with field='service_charge_tier', previous_value=null for add, new_value=null for delete • Require ROLE_OPS | POST and DELETE /admin/rules/{id}/service-charge/tiers handlers with overlap validation | • Add tier {min=0, max=100, charge=500} and tier {min=100, max=200, charge=300} succeeds (contiguous, no overlap) • Add tier {min=50, max=150, charge=400} when {min=0, max=100} exists returns HTTP 422 overlap error • DELETE tier_id=5 removes the row and audit log entry is written • Add tier with charge_amount=-1 returns HTTP 422 • Add tier with max=50, min=100 (max < min) returns HTTP 422 | 45 | 10.4-T02, 10.4-T03, 10.4-T11 | FS | PRD-07, RATE-04
10.4-T14 | admin-ui | 10.4 | 10. Admin System | Rule/Mapping page — 4 sections | 2 | Implement tier contiguity check service and gap-detection warning | When the operator adds or modifies tiers, the system must validate contiguity: no tier range overlaps another and gaps (missing USD ranges) generate a warning. Implementation: load all tiers for rule sorted by min_collection_usd; for each pair of adjacent tiers, check tier[i].max_collection_usd == tier[i+1].min_collection_usd (contiguous) or tier[i].max_collection_usd < tier[i+1].min_collection_usd (gap). Overlap: tier[i].max_collection_usd > tier[i+1].min_collection_usd. This service is used by both the POST tier endpoint (T13) and the GET endpoint to return live warnings to the UI. | • Create TierValidationService.validate(List<ServiceChargeTier> tiers) returning TierValidationResult {overlaps: List<String>, gaps: List<String>} • Sort tiers by min_collection_usd ascending • For each adjacent pair: if tiers[i].max_collection_usd > tiers[i+1].min_collection_usd -> overlap error • If tiers[i].max_collection_usd < tiers[i+1].min_collection_usd -> gap warning (record range) • Return overlaps list (hard errors) and gaps list (warnings) • Expose validation result in GET /admin/rules/{id}/service-charge response as tier_validation field | TierValidationService class used in tier CRUD and GET responses | • Tiers [{0-100},{100-200},{200-null}] returns empty overlaps and empty gaps • Tiers [{0-100},{90-200}] returns overlap error mentioning range 90-100 • Tiers [{0-100},{150-200}] returns gap warning mentioning range 100-150 • Single tier returns empty overlaps and empty gaps • Empty tier list returns empty overlaps and empty gaps | 35 | 10.4-T13 | FS | PRD-07, RATE-04
10.4-T15 | admin-ui | 10.4 | 10. Admin System | Rule/Mapping page — 4 sections | 2 | Implement Review Changes diff service and POST /admin/rules/{id}/review endpoint | Before saving the mapping page, the operator clicks 'Review Changes'. The backend computes a field-level diff of proposed values vs currently saved values and returns it. The diff must cover all editable fields: rate_coll_source, rate_pay_source, manual_rate_coll, manual_rate_pay, rate_coll_override_expires, rate_pay_override_expires, m_a, m_b, service_charge_amount, and tier changes. Each changed field entry: {field_name, previous_value, new_value, section (1-4)}. Unchanged fields are omitted. This is a read-only preview — it does not persist anything. | • Create POST /admin/rules/{id}/review accepting MappingPageDraftDTO (all 4 sections combined) • Load current rule from DB • Compute diff: for each field in the draft, compare to current; if different, add to diff list • Return ReviewChangesDTO: {changes: List<{field_name, section, previous_value, new_value}>, any_changes: boolean} • No DB writes in this endpoint • Require ROLE_OPS | POST /admin/rules/{id}/review diff endpoint and ReviewChangesDTO | • Draft with m_a changed from 0.010000 to 0.012500 returns changes list with entry {field='m_a', previous='0.010000', new='0.012500', section=3} • Draft identical to current state returns any_changes=false and empty changes list • Draft changing both manual_rate_coll and m_b returns 2 entries in changes list • Endpoint does not modify the rule record in DB (verify by GET after call) • HTTP 422 returned if draft fails any validation rule (e.g. cross-border m_a+m_b < 0.02) | 35 | 10.4-T10, 10.4-T12 | FS | PRD-07, RATE-04
10.4-T16 | admin-ui | 10.4 | 10. Admin System | Rule/Mapping page — 4 sections | 2 | Implement atomic rule save: POST /admin/rules/{id}/save with full audit logging | After reviewing, the operator clicks Save Rule. All four sections are committed atomically in one DB transaction. The save must: (1) validate all fields across all sections; (2) write all changed fields to rule_audit_log atomically with the rule update; (3) set effective_from=NOW() on the rule; (4) if is_new_rule (status=DRAFT for first save), keep status=DRAFT; if existing ACTIVE rule, changes take effect immediately. Audit log format per field: {event:'rule_field_changed', actor_user_id, timestamp_utc, rule_key:{partner, scheme, direction}, field, previous_value, new_value}. The entire operation must roll back if any part fails. | • Create POST /admin/rules/{id}/save accepting MappingPageSaveDTO • Open a single DB transaction • Run all cross-section validations (rate source consistency, margin floors, service charge >= 0, tier contiguity) • Compute changed fields vs current DB state • Write one rule_audit_log row per changed field within the same transaction • Update rule record with new values and effective_from=NOW() • Commit; return SaveResultDTO {rule_id, effective_from, audit_entries_written: int} | POST /admin/rules/{id}/save transactional handler with audit log writes | • Saving m_a=0.0125 and m_b=0.0075 (cross-border, combined=2%) succeeds and audit log has 2 rows with correct before/after values • If audit log write fails (simulate constraint error), rule update is also rolled back (verify DB state unchanged) • Saving a cross-border rule with m_a=0.005, m_b=0.005 returns HTTP 422 and no partial changes in DB • effective_from on rule is updated to current UTC on every successful save • audit_entries_written in response equals the number of actually changed fields | 50 | 10.4-T15, 10.4-T03 | FS | PRD-07, RATE-04
10.4-T17 | admin-ui | 10.4 | 10. Admin System | Rule/Mapping page — 4 sections | 2 | Implement Activate Rule endpoint: POST /admin/rules/{id}/activate | After initial creation, a DRAFT rule must be explicitly activated by the operator. Activation sets status='ACTIVE' and effective_from=NOW(). Constraint: a rule cannot be activated if it would violate any config guard: cross-border rules need m_a+m_b >= 0.02; service_charge_ccy must equal settle_a_ccy; rate source must be validly resolved. Once ACTIVE, the rule is used by the rate engine for new transactions. A DRAFT rule is never used by the engine. Activation is logged to rule_audit_log with field='status', previous_value='DRAFT', new_value='ACTIVE'. Only ROLE_OPS can activate. | • Create POST /admin/rules/{id}/activate handler • Validate rule is in DRAFT status (reject 422 if already ACTIVE or SUSPENDED) • Run all config guard checks (margin floor for cross-border, service_charge_ccy = settle_a_ccy, valid rate source) • Set rule.status='ACTIVE', rule.effective_from=NOW() • Write audit log entry: field='status', previous_value='DRAFT', new_value='ACTIVE' • Return ActivationResultDTO {rule_id, status, effective_from} • Require ROLE_OPS | POST /admin/rules/{id}/activate handler | • DRAFT cross-border rule with m_a+m_b=0.02 activates successfully; status in DB is 'ACTIVE' • DRAFT cross-border rule with m_a+m_b=0.015 returns HTTP 422 with margin error; status remains DRAFT • Calling activate on already-ACTIVE rule returns HTTP 422 • Audit log has entry for field='status' with previous='DRAFT', new='ACTIVE' • effective_from is updated to current UTC on activation | 30 | 10.4-T16 | FS | PRD-07, RATE-04
10.4-T18 | admin-ui | 10.4 | 10. Admin System | Rule/Mapping page — 4 sections | 2 | Implement rule list view API: GET /admin/rules with summary columns | The Rule List View table (PRD-07 §6.2) needs these columns: partner_name, scheme_name, direction, rate_source_summary (e.g. 'IDENTITY/LIVE'), combined_margin_pct (m_a+m_b as percentage string, e.g. '2.00%'), service_charge_display (e.g. '500 KRW' or '0.50 USD'), status, last_modified. Actions available per row: View/Edit, Activate/Deactivate, View Audit History. The endpoint supports optional query params: partner_id, scheme_id, direction, status for filtering. | • Create GET /admin/rules handler with optional query params • Join rule to partner (for name) and qr_scheme (for name) tables • Compute rate_source_summary as '{coll_source}/{pay_source}' • Compute combined_margin_pct as ((m_a + m_b) * 100) formatted to 2 decimal places + '%' • Format service_charge_display as '{amount} {ccy}' • Return paginated RuleListDTO with items and total_count; default page_size=20 • Require ROLE_OPS or ROLE_FINANCE_ANALYST | GET /admin/rules paginated list endpoint with filtering | • Returns all rules when no filters applied • Filter by status='ACTIVE' returns only active rules • Rule for SendMN INBOUND shows rate_source_summary='IDENTITY/LIVE' (settleA=USD->IDENTITY, settleB=KRW->LIVE) • combined_margin_pct for m_a=0.01, m_b=0.01 returns '2.00%' • service_charge_display for amount=500, ccy='KRW' returns '500 KRW' | 35 | 10.4-T04 | FS | PRD-07, RATE-04
10.4-T19 | admin-ui | 10.4 | 10. Admin System | Rule/Mapping page — 4 sections | 2 | Implement audit history API: GET /admin/rules/{id}/audit-history with CSV export | The Rule Audit History view (PRD-07 §6.5) shows a chronological table of all rule_audit_log rows for a rule. Columns: timestamp_utc, actor (display name + user ID), field_changed, previous_value, new_value, effective_from (= timestamp_utc of the save). Supports CSV export. The CSV must include all columns with proper escaping. Query should be paginated with optional date-range filter params: from_utc, to_utc. | • Create GET /admin/rules/{id}/audit-history with optional params: from_utc, to_utc, page, page_size; default page_size=50 • Join rule_audit_log to users table for actor display name • Return AuditHistoryDTO {items: List<AuditEntryDTO>, total_count, rule_key} • Support GET /admin/rules/{id}/audit-history?format=csv that returns Content-Type: text/csv with all rows (no pagination limit) • CSV columns in order: timestamp_utc, actor_user_id, actor_name, field_changed, previous_value, new_value, effective_from • Require ROLE_OPS or ROLE_FINANCE_ANALYST | GET /admin/rules/{id}/audit-history endpoint with JSON and CSV modes | • Returns rows in descending timestamp_utc order by default • from_utc filter excludes entries before that timestamp • format=csv response has Content-Type: text/csv and header row as first line • CSV values with commas (e.g. a previous_value containing a comma) are properly double-quoted • Empty rule (no changes ever) returns empty items list with total_count=0 | 35 | 10.4-T03, 10.4-T16 | FS | PRD-07, RATE-04
10.4-T20 | admin-ui | 10.4 | 10. Admin System | Rule/Mapping page — 4 sections | 2 | Implement rule deactivation: POST /admin/rules/{id}/deactivate | An ACTIVE rule can be suspended/deactivated. Status changes to SUSPENDED. A SUSPENDED rule is not used by the rate engine for new transactions. Existing committed transactions are unaffected. The operator must confirm via the UI (backend receives a confirm=true param). Deactivation is audit-logged: field='status', previous_value='ACTIVE', new_value='SUSPENDED'. Reactivation (SUSPENDED -> ACTIVE) uses the existing activate endpoint. Only ROLE_OPS can deactivate. | • Create POST /admin/rules/{id}/deactivate accepting {confirm: boolean} • Reject with 400 if confirm != true • Reject with 422 if rule is not ACTIVE (e.g. already DRAFT or SUSPENDED) • Set rule.status='SUSPENDED', rule.effective_from=NOW() • Write audit log entry field='status', previous_value='ACTIVE', new_value='SUSPENDED' • Return {rule_id, status: 'SUSPENDED', effective_from} • Require ROLE_OPS | POST /admin/rules/{id}/deactivate handler | • ACTIVE rule deactivated with confirm=true: status becomes 'SUSPENDED' in DB • Calling deactivate with confirm=false returns HTTP 400 • Calling deactivate on DRAFT rule returns HTTP 422 • Audit log entry written with field='status', previous_value='ACTIVE', new_value='SUSPENDED' • After deactivation, rate engine calls for that rule return RULE_NOT_ACTIVE error (verify by calling rate engine with rule id) | 25 | 10.4-T17 | FS | PRD-07, RATE-04
10.4-T21 | admin-ui | 10.4 | 10. Admin System | Rule/Mapping page — 4 sections | 2 | Implement RuleConfigLoader used by rate engine: fetch active rule by partner+scheme+direction | The rate engine (separate component) must fetch the active rule configuration at quote time. It calls RuleConfigLoader.loadActiveRule(partnerId, schemeId, direction) which returns a RuleConfig value object containing all rate engine inputs: rate_coll_source, rate_pay_source, manual_rate_coll, manual_rate_pay, m_a, m_b, service_charge_amount, service_charge_ccy, is_same_ccy_shortcircuit, and the collection/settle/payout currencies. Returns RULE_NOT_ACTIVE error if no ACTIVE rule exists. Also resolves current treasury rate for LIVE legs inline (calls treasury_rate table). Changes that have been saved (effective_from <= NOW()) are reflected immediately; the loader never returns stale config from a pre-save snapshot. | • Create RuleConfigLoader.loadActiveRule(Long partnerId, Long schemeId, String direction) • Query rule WHERE partner_id=? AND scheme_id=? AND direction=? AND status='ACTIVE' • If not found, throw RuleNotFoundException('RULE_NOT_ACTIVE') • Resolve treasury rate for LIVE legs: SELECT rate FROM treasury_rate WHERE ccy_pair=? ORDER BY effective_at DESC LIMIT 1 • Check MANUAL override expiry: if rate_coll_override_expires < TODAY, treat as LIVE and log warning • Return RuleConfig value object with all fields • Add caching with TTL=5s to avoid hammering DB on high-volume payment processing (evict on rule save) | RuleConfigLoader class used by the rate engine | • Returns correct RuleConfig for ACTIVE SendMN INBOUND rule including m_a=0.01, m_b=0.01 • Throws RuleNotFoundException for DRAFT or SUSPENDED rule • Returns LIVE source for coll leg of SendMN (settleA=USD -> IDENTITY, not LIVE) • Expired MANUAL override (rate_coll_override_expires yesterday) returns LIVE source with current treasury rate • Cache eviction: saving a rule change via T16 causes next loadActiveRule call to return updated values within 5s | 45 | 10.4-T05, 10.4-T16 | FS | PRD-07, RATE-04
10.4-T22 | admin-ui | 10.4 | 10. Admin System | Rule/Mapping page — 4 sections | 2 | Implement service charge tier resolution at transaction time | At quote time, the rate engine must resolve the correct service_charge for the transaction using the tier table. Resolution logic: if volume_tiers_enabled (tiers exist for rule) AND the rule is cross-border (not same-ccy short-circuit), find the tier where min_collection_usd <= collection_usd < max_collection_usd (NULL max = open-ended). If a matching tier exists, use tier.charge_amount. If no tier matches (gap in coverage), fall back to rule.service_charge_amount. If is_same_ccy_shortcircuit=true, always use flat rule.service_charge_amount regardless of tiers. This logic is part of the rate engine, called after Step 2 (collection_usd is known). | • Create ServiceChargeTierResolver.resolve(Long ruleId, BigDecimal collection_usd, boolean is_same_ccy) returning BigDecimal charge_amount • If is_same_ccy=true, return flat rule.service_charge_amount immediately • Query service_charge_tier WHERE rule_id=? AND min_collection_usd <= collection_usd AND (max_collection_usd IS NULL OR max_collection_usd > collection_usd) • If row found, return tier.charge_amount • If no row found, return rule.service_charge_amount as fallback • Log a warning if fallback is used due to a gap in tier coverage | ServiceChargeTierResolver class integrated into rate engine quote flow | • collection_usd=150 with tier {min=100, max=200, charge=300} returns 300 • collection_usd=250 with tiers {0-100:500, 100-200:300} and no tier for 200+ returns flat rule charge (fallback) • is_same_ccy=true with tiers present returns flat rule charge, not tier value • collection_usd=100 with tier {min=100, max=200} (inclusive lower bound) returns tier charge (not out of range) • collection_usd=200 with tier {min=100, max=200} (exclusive upper bound) does NOT match this tier | 35 | 10.4-T02, 10.4-T21 | FS | PRD-07, RATE-04
10.4-T23 | admin-ui | 10.4 | 10. Admin System | Rule/Mapping page — 4 sections | 2 | Unit tests: currency quadruple auto-derivation and same-ccy short-circuit detection | Test RuleService and RuleRepository auto-derivation logic. Key scenarios: (1) LOCAL partner GME Remit (collect=KRW, settleA=KRW) on ZeroPay (settleB=KRW, payout=KRW) -> is_same_ccy_shortcircuit=true. (2) OVERSEAS SendMN (collect=MNT, settleA=USD) on ZeroPay (settleB=KRW, payout=KRW) -> is_same_ccy_shortcircuit=false. (3) Hypothetical all-USD rule -> is_same_ccy_shortcircuit=true. The quadruple must come from partner/scheme, never from caller. | • Write unit test class RuleCurrencyDerivationTest using JUnit 5 + Mockito • Test case 1: build Partner(collect=KRW, settleA=KRW), Scheme(settleB=KRW, payout=KRW); call deriveRule(); assert is_same_ccy_shortcircuit=true and all 4 ccy fields correct • Test case 2: build Partner(collect=MNT, settleA=USD), Scheme(settleB=KRW, payout=KRW); assert is_same_ccy_shortcircuit=false • Test case 3: build Partner(collect=USD, settleA=USD), Scheme(settleB=USD, payout=USD); assert is_same_ccy_shortcircuit=true • Test case 4: verify caller-provided ccy fields are ignored (pass wrong values, assert derived values are correct) | RuleCurrencyDerivationTest.java with 4 passing test cases | • Test 1 passes: all KRW rule -> is_same_ccy_shortcircuit=true • Test 2 passes: MNT/USD/KRW/KRW rule -> is_same_ccy_shortcircuit=false • Test 3 passes: all USD -> is_same_ccy_shortcircuit=true • Test 4 passes: caller-provided ccy overridden by derived values • All 4 tests pass with mvn test -Dtest=RuleCurrencyDerivationTest | 30 | 10.4-T04 | FS | PRD-07, RATE-04
10.4-T24 | admin-ui | 10.4 | 10. Admin System | Rule/Mapping page — 4 sections | 2 | Unit tests: rate source resolution across all 4 source types | Test RuleService.resolveRateSource for all source type transitions. Key vectors: (A) settleA=USD -> IDENTITY (coll leg); (B) settleA=MNT, no override -> LIVE; (C) settleA=MNT, manual_rate_coll=0.00072, no expiry -> MANUAL; (D) manual_rate_coll set but override expired yesterday -> LIVE; (E) scheme.rate_source_pay=PARTNER -> PARTNER; (F) is_same_ccy_shortcircuit=true -> both legs IDENTITY regardless. Use mocked treasury_rate and scheme. | • Write RateSourceResolutionTest with 6 test cases • Mock TreasuryRateRepository and QrSchemeRepository • Test A: settle_a_ccy='USD' -> resolveRateSource(rule,'coll') = IDENTITY • Test B: settle_a_ccy='MNT', no override -> LIVE • Test C: settle_a_ccy='MNT', manual set, no expiry -> MANUAL • Test D: settle_a_ccy='MNT', manual set, expiry=yesterday -> LIVE • Test E: scheme configured PARTNER for pay leg -> PARTNER • Test F: is_same_ccy_shortcircuit=true -> both coll and pay return IDENTITY | RateSourceResolutionTest.java with 6 passing test cases | • Test A passes • Test B passes • Test C passes • Test D passes: expired override falls back to LIVE • Tests E and F pass • All 6 tests pass with mvn test -Dtest=RateSourceResolutionTest | 30 | 10.4-T05 | FS | PRD-07, RATE-04
10.4-T25 | admin-ui | 10.4 | 10. Admin System | Rule/Mapping page — 4 sections | 2 | Unit tests: margin validation — cross-border floor and same-ccy lock | Test the margin validation logic in the PATCH /margin handler. Key vectors: (1) cross-border rule, m_a=0.005, m_b=0.005 (1% combined) -> reject with MARGIN_TOO_LOW; (2) cross-border rule, m_a=0.01, m_b=0.01 (2% combined, exact floor) -> accept; (3) cross-border rule, m_a=0.015, m_b=0.01 (2.5%) -> accept; (4) same-ccy rule, m_a=0, m_b=0 -> accept; (5) same-ccy rule, m_a=0.01 -> reject; (6) negative m_a -> reject; (7) m_a=1.0 (100%) and m_b=0 -> accept (no upper cap on individual margin); (8) m_a=0.5, m_b=0.51 (combined 101%) -> reject (> 100% each is nonsensical; combined > 1.0 is rejected). | • Write MarginValidationTest with 8 test cases using MockMvc or direct service call • Each test provides a rule (cross-border or same-ccy), input m_a and m_b, and asserts HTTP status code and error message when applicable • Test 1: 422 with message containing '2.00%' • Test 2: 200 ok • Test 3: 200 ok • Test 4: 200 ok • Tests 5-8: 422 with appropriate messages | MarginValidationTest.java with 8 passing test cases | • Test 1 passes: m_a+m_b=1% cross-border is rejected • Test 2 passes: m_a+m_b=2% exactly is accepted • Test 4 passes: same-ccy m_a=0, m_b=0 accepted • Test 5 passes: same-ccy m_a=0.01 rejected • All 8 tests pass with mvn test -Dtest=MarginValidationTest | 30 | 10.4-T10 | FS | PRD-07, RATE-04
10.4-T26 | admin-ui | 10.4 | 10. Admin System | Rule/Mapping page — 4 sections | 2 | Unit tests: service charge tier resolution with boundary conditions | Test ServiceChargeTierResolver.resolve with boundary conditions at tier edges. Numeric vectors: (A) collection_usd=100.00, tiers [{0-100:500},{100-200:300}] -> lower bound is inclusive so 100 matches SECOND tier: charge=300. (B) collection_usd=99.9999, same tiers -> matches first tier: charge=500. (C) collection_usd=200, tiers [{0-100:500},{100-200:300}] -> no tier covers 200 (max=200 is exclusive), fallback to flat. (D) collection_usd=350, tiers [{0-100:500},{100-null:300}] -> matches open-ended tier: charge=300. (E) is_same_ccy=true with tiers -> always flat. (F) no tiers at all -> flat charge. | • Write ServiceChargeTierResolverTest with 6 test cases • Use in-memory tier lists (no DB needed) • Test A: 100.00 matches second tier (min=100 inclusive) • Test B: 99.9999 matches first tier • Test C: 200.00 falls through to flat fallback • Test D: 350.00 matches open-ended tier • Test E: is_same_ccy=true returns flat regardless • Test F: empty tiers list returns flat | ServiceChargeTierResolverTest.java with 6 passing test cases | • Test A passes: boundary value 100 routes to min=100 tier • Test B passes: 99.9999 routes to min=0 tier • Test C passes: fallback used when no tier covers value • Test D passes: NULL max_collection_usd treated as infinity • Tests E and F pass • All 6 tests pass with mvn test -Dtest=ServiceChargeTierResolverTest | 30 | 10.4-T22 | FS | PRD-07, RATE-04
10.4-T27 | admin-ui | 10.4 | 10. Admin System | Rule/Mapping page — 4 sections | 2 | Unit tests: audit log write correctness and atomicity | Test that audit log entries are written correctly on rule save and that the save+audit is atomic (both succeed or both roll back). Use exact field name strings and value format: 6-decimal fraction for m_a/m_b (e.g. '0.010000'), 8-decimal for manual rates. Test rule_key JSON format: {partner, scheme, direction}. Also test that a transaction rollback (simulated by throwing after rule update, before audit log commit) leaves both rule and audit log unchanged. | • Write RuleSaveAuditTest with 4 test cases using @Transactional test with Spring context or TestContainers • Test 1: save m_a from 0.01 to 0.0125 -> audit log has field='m_a', previous_value='0.010000', new_value='0.012500' • Test 2: save with no changes -> no audit log rows written (audit_entries_written=0) • Test 3: simulate failure mid-transaction -> rule DB value unchanged AND no audit log row present • Test 4: save changing both m_a and manual_rate_coll -> 2 audit log rows, each with correct field name and values | RuleSaveAuditTest.java with 4 passing test cases | • Test 1 passes: previous_value format is '0.010000' (6 decimal fraction, not percent) • Test 2 passes: no spurious audit rows on no-op save • Test 3 passes: rollback leaves DB clean (atomicity confirmed) • Test 4 passes: both fields appear in audit log in same transaction • All 4 tests pass | 40 | 10.4-T16 | FS | PRD-07, RATE-04
10.4-T28 | admin-ui | 10.4 | 10. Admin System | Rule/Mapping page — 4 sections | 2 | Unit tests: MANUAL rate deviation guard (+-20% guard-rail) | Test the deviation guard in PATCH /admin/rules/{id}/rate-config. The guard fires when abs(manual_rate - live_rate) / live_rate > 0.20. Vectors: current treasury.usd_krw = 1380.00. (A) manual=1380.00 -> no deviation, saves immediately. (B) manual=1100.00 -> deviation = (1380-1100)/1380 = 20.3% -> guard fires, returns deviation_warning=true, does NOT save. (C) same request with confirm=true -> saves. (D) manual=1656.01 -> deviation = (1656.01-1380)/1380 = 20.0% -> exactly at limit -> guard fires. (E) manual=1655.99 -> 19.99% -> no warning, saves. | • Write ManualRateDeviationTest with 5 test cases using MockMvc • Mock treasury rate as 1380.00 for usd_krw • Test A: 0% deviation -> HTTP 200, rule saved, no deviation_warning • Test B: 20.3% deviation, confirm=false -> HTTP 200 deviation_warning=true, rule NOT saved • Test C: 20.3% deviation, confirm=true -> HTTP 200, rule saved • Test D: exactly 20.0% deviation -> guard fires (>= 20% triggers warning) • Test E: 19.99% deviation -> no guard, rule saved immediately | ManualRateDeviationTest.java with 5 passing test cases | • Test A passes • Test B passes: DB not updated when deviation_warning=true and no confirm • Test C passes: confirm=true bypasses warning and saves • Test D passes: 20.0% triggers guard (boundary condition) • All 5 tests pass with mvn test -Dtest=ManualRateDeviationTest | 35 | 10.4-T08 | FS | PRD-07, RATE-04
10.4-T29 | admin-ui | 10.4 | 10. Admin System | Rule/Mapping page — 4 sections | 2 | Unit tests: RuleConfigLoader — active rule fetch, expiry, and cache eviction | Test RuleConfigLoader.loadActiveRule behavior. Vectors: (1) ACTIVE rule returns correct RuleConfig. (2) DRAFT rule throws RuleNotFoundException. (3) SUSPENDED rule throws RuleNotFoundException. (4) Expired MANUAL override (rate_coll_override_expires < TODAY) returns LIVE source. (5) Cache eviction: modify rule, verify loader returns fresh config on next call within 5s (test with TestClock). Use mocked repository. | • Write RuleConfigLoaderTest with 5 test cases • Mock RuleRepository, TreasuryRateRepository • Test 1: ACTIVE rule found -> RuleConfig contains m_a=0.01, m_b=0.01, is_same_ccy=false • Test 2: DRAFT rule -> throws RuleNotFoundException with message RULE_NOT_ACTIVE • Test 3: SUSPENDED rule -> throws RuleNotFoundException • Test 4: manual_rate_coll set, override_expires=yesterday -> resolvedSource=LIVE • Test 5: save new m_a=0.0125 -> cache evicted -> next loadActiveRule returns m_a=0.0125 | RuleConfigLoaderTest.java with 5 passing test cases | • Test 1 passes: correct m_a/m_b in returned config • Test 2 passes: DRAFT throws correct exception • Test 3 passes: SUSPENDED throws correct exception • Test 4 passes: expired override falls back to LIVE • Test 5 passes: post-eviction reload returns updated values • All 5 tests pass | 35 | 10.4-T21 | FS | PRD-07, RATE-04
10.4-T30 | admin-ui | 10.4 | 10. Admin System | Rule/Mapping page — 4 sections | 2 | Integration test: full mapping page save round-trip with audit trail verification | End-to-end test covering: create rule (DRAFT), populate all 4 sections via PATCH endpoints, call Review Changes (verify diff), call Save, call Activate, call GET /audit-history (verify entries). Use TestContainers with real PostgreSQL. Partner: SendMN (collect=MNT, settleA=USD). Scheme: ZeroPay (settleB=KRW, payout=KRW). Direction: INBOUND. Target config: rate_coll_source=IDENTITY, rate_pay_source=LIVE, m_a=0.01, m_b=0.01, service_charge_amount=0.36, service_charge_ccy=USD. Verify pool identity invariant holds for a sample transaction using this config. | • Write MappingPageIntegrationTest extending AbstractIntegrationTest (TestContainers PostgreSQL) • Step 1: POST /admin/rules to create DRAFT rule for SendMN+ZeroPay+INBOUND • Step 2: PATCH /margin with m_a=0.01, m_b=0.01; assert 200 • Step 3: PATCH /service-charge with service_charge_amount=0.36; assert 200 • Step 4: POST /review; assert changes list has service_charge_amount and margin entries • Step 5: POST /save; assert audit_entries_written=2 • Step 6: POST /activate; assert status=ACTIVE • Step 7: GET /audit-history; assert entries for m_a, m_b, service_charge_amount, status fields • Step 8: call RuleConfigLoader.loadActiveRule; assert RuleConfig fields match saved values | MappingPageIntegrationTest.java with 8-step end-to-end test passing on real DB | • All 8 steps pass sequentially with no errors • Audit history returns >= 4 entries (m_a, m_b, service_charge_amount, status=ACTIVE) • RuleConfig from loader has m_a=0.01, m_b=0.01, service_charge_amount=0.36, service_charge_ccy='USD' • Rule status in DB is 'ACTIVE' after step 6 • No rule changes visible to rate engine before step 6 (status=DRAFT is not returned by loadActiveRule) | 55 | 10.4-T19, 10.4-T21, 10.4-T17 | FS | PRD-07, RATE-04
10.4-T31 | admin-ui | 10.4 | 10. Admin System | Rule/Mapping page — 4 sections | 2 | Integration test: pool identity invariant with saved rule config | Using the saved rule from T30 (SendMN INBOUND: m_a=0.01, m_b=0.01, settleA=USD IDENTITY, settleB=KRW LIVE), execute the 5-step rate engine with target_payout=50000 KRW and treasury.usd_krw=1380.00 and verify: payout_usd_cost=36.2319, collection_usd=36.9714, collection_margin_usd=0.3697, payout_margin_usd=0.3697, send_amount=36.9714 (IDENTITY leg), collection_amount=36.9714+0.36=37.3314. Pool identity: ¦36.9714-0.3697-0.3697-36.2319¦ < 0.01. This test exercises the rate engine reading config from the rule, not testing the engine itself independently. | • Write PoolIdentityIntegrationTest using TestContainers • Insert treasury rate usd_krw=1380.00 in treasury_rate table • Insert active rule from T30 config • Call RateEngineService.computeQuote(ruleId, target_payout=50000, payout_ccy='KRW') • Assert each 5-step output matches expected values to 4 decimal places • Assert ¦collection_usd - collection_margin_usd - payout_margin_usd - payout_usd_cost¦ < 0.01 • Assert offer_rate_coll = 36.9714 / (36.9714 - 0.3697) = approx 1.01010 | PoolIdentityIntegrationTest.java verifying rate engine reads and uses mapping page config correctly | • payout_usd_cost = 36.2319 +/- 0.0001 • collection_usd = 36.9714 +/- 0.0001 • collection_margin_usd = payout_margin_usd = 0.3697 +/- 0.0001 • Pool identity: abs difference < 0.01 USD • offer_rate_coll = 1.0101 +/- 0.0001 | 45 | 10.4-T30 | FS | PRD-07, RATE-04
10.5-T01 | admin-ui | 10.5 | 10. Admin System | FX/Treasury rate management | 1 | Create treasury_rate DB migration: table, constraints, indexes | GMEPay+ stores all FX treasury rates in the table treasury_rate. Schema (from DAT-03): id BIGINT PK auto-increment, ccy_pair VARCHAR(10) NOT NULL (e.g. usd_krw), rate DECIMAL(20,8) NOT NULL CHECK > 0, source VARCHAR(10) NOT NULL CHECK IN ('LIVE','MANUAL'), effective_at TIMESTAMPTZ NOT NULL, created_at TIMESTAMPTZ NOT NULL DEFAULT NOW(), updated_at TIMESTAMPTZ NOT NULL, created_by VARCHAR(120) NULL, updated_by VARCHAR(120) NULL. Rate convention: treasury.usd_{ccy} = units of {ccy} per 1 USD (e.g. usd_krw = 1350.00 means 1 USD = 1350 KRW). The current effective rate for a ccy_pair is the row with the greatest effective_at <= NOW(). | • Write a Flyway/Liquibase migration file (e.g. V10_5_001__create_treasury_rate.sql) • Add the table DDL with all columns, types, NOT NULL constraints, and CHECK constraints exactly as specified • Add a unique-style index on (ccy_pair, effective_at DESC) to support efficient current-rate lookups • Add a non-unique index on ccy_pair alone for history queries • Seed an initial row: ccy_pair='usd_usd', rate=1.00000000, source='MANUAL', effective_at=NOW(), created_by='SYSTEM' (USD identity; never updated manually) | Migration file V10_5_001__create_treasury_rate.sql creating the treasury_rate table with all constraints and indexes | • Migration applies cleanly on a fresh schema (no errors) • CHECK (rate > 0) rejects INSERT of rate = 0.0 and rate = -1.0 • CHECK (source IN ('LIVE','MANUAL')) rejects source = 'FEED' • Index on (ccy_pair, effective_at DESC) exists and is used by EXPLAIN on SELECT ... WHERE ccy_pair='usd_krw' ORDER BY effective_at DESC LIMIT 1 • Seed row for usd_usd with rate=1.0 and source='MANUAL' is present after migration | 30 |  | FS | PRD-07, RATE-04
10.5-T02 | admin-ui | 10.5 | 10. Admin System | FX/Treasury rate management | 1 | Create treasury_rate_audit DB migration: append-only audit trail table | Every write to treasury_rate must produce an append-only audit log entry (PRD-07 §13). The audit table treasury_rate_audit stores: id BIGINT PK auto-increment, treasury_rate_id BIGINT NOT NULL FK -> treasury_rate.id, event_type VARCHAR(30) NOT NULL CHECK IN ('RATE_CREATED','RATE_SUPERSEDED'), ccy_pair VARCHAR(10) NOT NULL, previous_rate DECIMAL(20,8) NULL (NULL for first entry per ccy_pair), new_rate DECIMAL(20,8) NOT NULL, source VARCHAR(10) NOT NULL, effective_at TIMESTAMPTZ NOT NULL, actor_user_id VARCHAR(120) NOT NULL, actor_display_name VARCHAR(255) NOT NULL, actor_ip INET NULL, notes TEXT NULL, created_at TIMESTAMPTZ NOT NULL DEFAULT NOW(). The table must be insert-only at the application service account level. | • Write migration file V10_5_002__create_treasury_rate_audit.sql • Add the table DDL with all columns, constraints, and FK to treasury_rate • Add index on (ccy_pair, created_at DESC) for history queries • Add index on actor_user_id for actor-based audit searches • Grant INSERT-only privilege on this table to the application DB role (revoke UPDATE/DELETE) | Migration file V10_5_002__create_treasury_rate_audit.sql creating the treasury_rate_audit table with constraints and restricted grants | • Migration applies after T01 with no errors • FK treasury_rate_audit.treasury_rate_id -> treasury_rate.id enforces referential integrity (reject orphan insert) • Application DB role can INSERT but SELECT on UPDATE attempt raises permission denied • event_type CHECK rejects value 'MODIFIED' • Index on (ccy_pair, created_at DESC) is present | 25 | 10.5-T01 | FS | PRD-07, RATE-04
10.5-T03 | admin-ui | 10.5 | 10. Admin System | FX/Treasury rate management | 1 | Define TreasuryRate JPA entity and TreasuryRateAudit JPA entity | GMEPay+ backend is Java + PostgreSQL. Map the two tables from T01/T02 to JPA entities. TreasuryRate fields: id, ccyPair (String), rate (BigDecimal), source (enum RateSource: LIVE/MANUAL), effectiveAt (OffsetDateTime), createdAt, updatedAt, createdBy, updatedBy. TreasuryRateAudit fields: id, treasuryRate (ManyToOne), eventType (enum: RATE_CREATED/RATE_SUPERSEDED), ccyPair, previousRate (nullable BigDecimal), newRate, source (RateSource), effectiveAt, actorUserId, actorDisplayName, actorIp (String nullable), notes (String nullable), createdAt. Use DECIMAL(20,8) via @Column(precision=20,scale=8). RateSource must be stored as STRING in DB. | • Create TreasuryRate.java entity with all fields, @Entity, @Table(name='treasury_rate'), @Column annotations • Create RateSource.java enum with LIVE and MANUAL values • Create TreasuryRateAudit.java entity with all fields, @Entity, @Table(name='treasury_rate_audit'), @ManyToOne(fetch=LAZY) to TreasuryRate • Annotate id fields with @GeneratedValue(strategy=IDENTITY) • Confirm @Enumerated(EnumType.STRING) on both source fields | TreasuryRate.java, TreasuryRateAudit.java, RateSource.java in the domain model package | • Both entities compile without error • RateSource.LIVE and RateSource.MANUAL map to string values 'LIVE' and 'MANUAL' in DB column • TreasuryRate.rate is BigDecimal with precision 20 scale 8 per @Column annotation • TreasuryRateAudit.previousRate is nullable (no NOT NULL constraint in entity) • @ManyToOne on TreasuryRateAudit.treasuryRate uses LAZY fetch | 30 | 10.5-T01, 10.5-T02 | FS | PRD-07, RATE-04
10.5-T04 | admin-ui | 10.5 | 10. Admin System | FX/Treasury rate management | 1 | Implement TreasuryRateRepository: current rate lookup and history queries | The rate engine resolves cost_rate_coll = treasury.usd_{settle_a_ccy} and cost_rate_pay = treasury.usd_{settle_b_ccy} using the most recent effective rate (greatest effective_at <= NOW()). TreasuryRateRepository needs: findCurrentRate(ccyPair, asOf): returns Optional<TreasuryRate> with greatest effective_at <= asOf; findHistory(ccyPair, pageable): all rows for a ccy_pair ordered by effective_at DESC; findAllCurrentRates(asOf): one current row per ccy_pair for the rate list view. Use Spring Data JPA or JPQL. The usd_usd identity row (rate=1.0) must be returned by findCurrentRate('usd_usd', ...) but is never manually editable. | • Create TreasuryRateRepository extending JpaRepository<TreasuryRate, Long> • Add findCurrentRate: @Query SELECT t FROM TreasuryRate t WHERE t.ccyPair = :ccyPair AND t.effectiveAt <= :asOf ORDER BY t.effectiveAt DESC LIMIT 1 • Add findHistory: return Page<TreasuryRate> ordered by effectiveAt DESC for given ccyPair • Add findAllCurrentRates: native or JPQL DISTINCT ON / subquery to return one row per ccy_pair with max effectiveAt <= :asOf • Write a repository integration test with 3 rows for usd_krw at t1 < t2 < t3 and assert findCurrentRate at t2+1s returns row t2 | TreasuryRateRepository.java with current-rate, history, and all-current queries, plus integration test | • findCurrentRate('usd_krw', t2+1s) returns row with effective_at=t2 when rows exist at t1, t2, t3 (t3 is future) • findCurrentRate returns Optional.empty() when no row has effective_at <= asOf • findHistory returns all rows for ccy_pair newest-first • findAllCurrentRates returns exactly one row per ccy_pair (the most recent) • findCurrentRate('usd_usd', NOW()) returns the seed identity row with rate=1.0 | 40 | 10.5-T03 | FS | PRD-07, RATE-04
10.5-T05 | admin-ui | 10.5 | 10. Admin System | FX/Treasury rate management | 1 | Implement TreasuryRateAuditRepository: insert and history queries | treasury_rate_audit is append-only. TreasuryRateAuditRepository must support: save(TreasuryRateAudit) for inserts only (no update/delete methods exposed); findByCcyPairOrderByCreatedAtDesc(ccyPair, pageable) for history view; findByActorUserId(actorUserId, pageable) for audit log filtering. The audit table uses insert-only DB grants (from T02). Actor data (userId, displayName, IP) comes from the authenticated portal session context. | • Create TreasuryRateAuditRepository extending JpaRepository<TreasuryRateAudit, Long> • Expose save() for inserts; do NOT expose saveAndFlush or any bulk update/delete derived queries • Add findByCcyPairOrderByCreatedAtDesc(String ccyPair, Pageable pageable) • Add findByActorUserIdOrderByCreatedAtDesc(String actorUserId, Pageable pageable) • Write unit test: verify that calling save() results in a row in DB and that the row is immutable (no update path exists on the repository interface) | TreasuryRateAuditRepository.java with save and query methods | • save() inserts a row with all required fields populated • findByCcyPairOrderByCreatedAtDesc returns rows newest-first for that ccy_pair • findByActorUserId filters correctly for a given actor • No updateBy... or deleteBy... method signatures exist on the repository interface • Attempting to call entityManager.merge() on an audit entity in a test throws or produces a new insert, never an UPDATE SQL statement | 25 | 10.5-T03 | FS | PRD-07, RATE-04
10.5-T06 | admin-ui | 10.5 | 10. Admin System | FX/Treasury rate management | 1 | Implement TreasuryRateService.getCurrentRate(ccyPair): rate lookup with RATE_UNAVAILABLE guard | The rate engine calls TreasuryRateService.getCurrentRate(ccyPair, asOf) to obtain the BigDecimal cost rate. If no row is found (treasury never updated for that ccy_pair, or all rows are future-dated), the service must throw RateUnavailableException (mapped to error code RATE_UNAVAILABLE). The usd_usd identity pair always resolves to 1.0 (seed row). Per RATE-04 assumption A3: Phase 1 does not block on staleness - the system uses whatever value is stored. The method signature: BigDecimal getCurrentRate(String ccyPair, OffsetDateTime asOf) throws RateUnavailableException. | • Create TreasuryRateService.java (Spring @Service) • Inject TreasuryRateRepository • Implement getCurrentRate(ccyPair, asOf): call findCurrentRate; if empty throw RateUnavailableException(ccyPair) • Create RateUnavailableException.java with field ccyPair and message 'No treasury rate available for {ccyPair} as of {asOf}' • Write unit tests: (a) rate found returns BigDecimal; (b) no row -> throws RateUnavailableException; (c) future-only rows -> throws RateUnavailableException | TreasuryRateService.java with getCurrentRate method and RateUnavailableException.java | • getCurrentRate('usd_krw', NOW()) returns 1350.00 when that is the stored rate • getCurrentRate for a ccy_pair with no rows throws RateUnavailableException • getCurrentRate where all rows have effective_at in the future throws RateUnavailableException • RateUnavailableException.getCcyPair() returns the requested ccy_pair string • getCurrentRate('usd_usd', NOW()) returns 1.0 from the identity seed row | 35 | 10.5-T04 | FS | PRD-07, RATE-04
10.5-T07 | admin-ui | 10.5 | 10. Admin System | FX/Treasury rate management | 1 | Implement TreasuryRateService.saveRate(): validate, persist, audit | When an Ops Operator saves a new treasury rate via the admin portal, TreasuryRateService.saveRate() must: (1) validate rate > 0; (2) enforce guard-rail: if a previous rate exists and the new rate deviates by more than the configured guard-rail threshold (default 10%) from it, the caller must supply confirmed=true or the service throws GuardRailWarningException; (3) insert a new treasury_rate row (do NOT update the old row - all entries are historical); (4) write a treasury_rate_audit row with event_type=RATE_CREATED, previousRate=old rate or null, actor fields from the passed ActorContext; (5) return the saved TreasuryRateDTO. Method: TreasuryRateDTO saveRate(SaveRateCommand cmd, ActorContext actor, boolean confirmed). | • Add saveRate(SaveRateCommand cmd, ActorContext actor, boolean confirmed) to TreasuryRateService • Validate cmd.rate > 0; throw InvalidRateException if not • Load current rate for cmd.ccyPair; compute deviation = abs(newRate - oldRate) / oldRate * 100 • If deviation > guardRailPercent (inject from config, default 10.0) AND confirmed == false, throw GuardRailWarningException(deviation, oldRate) • Insert new TreasuryRate row with source=MANUAL and effective_at = cmd.effectiveAt (default NOW() if not supplied) • Insert TreasuryRateAudit row: eventType=RATE_CREATED, previousRate=oldRate or null, newRate, actor fields from ActorContext, notes from cmd | saveRate() method on TreasuryRateService with GuardRailWarningException and InvalidRateException | • saveRate with rate=0 throws InvalidRateException • saveRate with rate=1500 when existing rate=1350 (deviation=11.1%) and confirmed=false throws GuardRailWarningException • saveRate with same input and confirmed=true inserts the row and returns a TreasuryRateDTO • Inserted row has source=MANUAL and effective_at equal to cmd.effectiveAt or current timestamp • Audit row is created with previousRate=1350.00 and newRate=1500.00 and actor fields populated | 45 | 10.5-T05, 10.5-T06 | FS | PRD-07, RATE-04
10.5-T08 | admin-ui | 10.5 | 10. Admin System | FX/Treasury rate management | 1 | Implement TreasuryRateService: effective-date future-dating and same-ccyPair active history | Ops may pre-announce a rate by supplying effective_at in the future (e.g. next business day 00:00 UTC). saveRate() must allow future effective_at values. The current rate at any point in time is the row with the greatest effective_at <= that point. Multiple rows for the same ccy_pair are allowed and represent a full history (no row is ever updated or deleted). The UI history view shows Effective Until = effective_at of the next newer row, or 'Current' if none. TreasuryRateService needs getHistory(ccyPair, pageable) returning List<TreasuryRateHistoryDTO> where each row includes effectiveUntil computed as next row's effectiveAt or null. | • Add getHistory(String ccyPair, Pageable pageable) to TreasuryRateService • Retrieve page from TreasuryRateRepository.findHistory(ccyPair, pageable) • For each row, compute effectiveUntil = effectiveAt of the chronologically next row; set null (current) for the most recent row • Map to TreasuryRateHistoryDTO: rateValue, effectiveFrom, effectiveUntil (nullable), updatedBy, updatedAt, notes • Write unit test: insert 3 rows for usd_krw at t1=2026-01-01, t2=2026-02-01, t3=2026-03-01; assert getHistory returns t3 with effectiveUntil=null, t2 with effectiveUntil=t3, t1 with effectiveUntil=t2 | getHistory() method and TreasuryRateHistoryDTO with effectiveUntil computation | • Most recent row (greatest effectiveAt) has effectiveUntil=null in DTO • Middle row has effectiveUntil = effectiveAt of the next newer row • Rows are returned newest-first • A future-dated row (effectiveAt > NOW()) appears in history with effectiveUntil=null until superseded • getHistory for an unknown ccy_pair returns an empty list (no exception) | 35 | 10.5-T04 | FS | PRD-07, RATE-04
10.5-T09 | admin-ui | 10.5 | 10. Admin System | FX/Treasury rate management | 1 | Implement TreasuryRateService: getAllCurrentRates() for rate list view | The FX Rates list view (PRD-07 §7.2) shows one row per registered currency with its current rate (greatest effective_at <= NOW()), last-updated-by, last-updated-at, effective-from, and source. TreasuryRateService.getAllCurrentRates() must return one TreasuryRateListDTO per registered ccy_pair. The usd_usd row must appear with rate=1.0 and source=MANUAL but must NOT be editable via the save endpoint. The list should also include registered currencies that have no rate yet (rate=null, indicating action required). | • Add getAllCurrentRates(OffsetDateTime asOf) to TreasuryRateService • Call TreasuryRateRepository.findAllCurrentRates(asOf) to get one row per ccy_pair • Also load all registered ccy_pairs (from a CurrencyRegistry or config list); merge to include pairs with no rate (rate=null) • Map each to TreasuryRateListDTO: ccyPair, ratePairDisplay (e.g. USD / KRW), currentRate, lastUpdatedBy, lastUpdatedAt, effectiveFrom, source • Write unit test: seed usd_krw and usd_mnt rows but not usd_eur; assert eur appears in list with null currentRate | getAllCurrentRates() method and TreasuryRateListDTO | • Returns one entry per registered ccy_pair (not per row) • usd_krw entry shows rate=1350.00 when that is the most recent row • usd_usd entry shows rate=1.0000 and source=MANUAL • A registered ccy_pair with no rate rows has currentRate=null in the DTO • List is ordered alphabetically by ccyPair | 35 | 10.5-T04 | FS | PRD-07, RATE-04
10.5-T10 | admin-ui | 10.5 | 10. Admin System | FX/Treasury rate management | 1 | Create CurrencyRegistry: registered currencies config and validation | Only registered currencies can have treasury rates entered against them (PRD-07 §7.5). USD is always present and cannot be removed. The CurrencyRegistry maintains the list of known ccy codes. In Phase 1 this can be a DB-backed table or a config list. TreasuryRateService.saveRate() must reject attempts to save a rate for an unregistered currency. Additionally, USD (ccy_pair=usd_usd) must be treated as an identity currency: it always has rate=1.0 and source=MANUAL, and saveRate() must reject attempts to update it. | • Create currency_registry DB table (or config): id BIGINT PK, ccy_code VARCHAR(10) NOT NULL UNIQUE, display_name VARCHAR(60), is_identity BOOLEAN NOT NULL DEFAULT FALSE, is_active BOOLEAN NOT NULL DEFAULT TRUE, created_at TIMESTAMPTZ • Add migration V10_5_003__create_currency_registry.sql seeding USD (is_identity=true), KRW, MNT, EUR, THB as active • Create CurrencyRegistry.java service with isRegistered(ccyCode) and isIdentity(ccyCode) methods • Add validation in TreasuryRateService.saveRate(): if !isRegistered(ccyPair) throw UnknownCurrencyException; if isIdentity throw IdentityRateMutationException • Write unit test: saveRate for usd_usd throws IdentityRateMutationException; saveRate for 'usd_xyz' (unregistered) throws UnknownCurrencyException | currency_registry migration, CurrencyRegistry.java, and validation hooks in saveRate() | • saveRate for usd_usd (identity) throws IdentityRateMutationException • saveRate for an unregistered ccy_pair throws UnknownCurrencyException • getAllCurrentRates() returns usd_usd with is_identity=true flag in DTO • isRegistered('usd_krw') returns true; isRegistered('usd_xyz') returns false • USD row cannot be deleted from currency_registry by normal application paths | 40 | 10.5-T07 | FS | PRD-07, RATE-04
10.5-T11 | admin-ui | 10.5 | 10. Admin System | FX/Treasury rate management | 1 | Implement GET /admin/v1/fx-rates REST endpoint: current rate list | Admin API endpoint for the FX Rates list view. Requires authenticated portal session with role OPS_OPERATOR, FINANCE_ANALYST, ADMIN_VIEWER, or SUPER_ADMIN (all roles can view rates per PRD-07 §12.3 permission matrix). Returns the list of current treasury rates from TreasuryRateService.getAllCurrentRates(). Response: array of {ccyPair, ratePairDisplay, currentRate, lastUpdatedBy, lastUpdatedAt, effectiveFrom, source}. HTTP 200 on success. If a rate is missing for a registered currency, currentRate field is null. | • Create FxRateController.java in the admin API package with @RestController and base path /admin/v1/fx-rates • Implement GET / handler calling TreasuryRateService.getAllCurrentRates(OffsetDateTime.now()) • Apply @PreAuthorize or role-check middleware for OPS_OPERATOR ¦ FINANCE_ANALYST ¦ ADMIN_VIEWER ¦ SUPER_ADMIN • Map TreasuryRateListDTO list to JSON response array • Write controller unit test: mock service returns 2 entries; assert HTTP 200 and JSON array length = 2 • Write security test: unauthenticated request returns HTTP 401; request with PARTNER role returns HTTP 403 | GET /admin/v1/fx-rates endpoint in FxRateController.java | • GET /admin/v1/fx-rates returns HTTP 200 with JSON array when called by OPS_OPERATOR • Unauthenticated request returns HTTP 401 • Request with PARTNER role returns HTTP 403 • Response includes usd_usd entry with currentRate=1.0 • A registered currency with no rate has currentRate=null in response (not omitted) | 35 | 10.5-T09, 10.5-T10 | FS | PRD-07, RATE-04
10.5-T12 | admin-ui | 10.5 | 10. Admin System | FX/Treasury rate management | 1 | Implement GET /admin/v1/fx-rates/{ccyPair}/history REST endpoint | Rate history endpoint for a single currency pair (PRD-07 §7.4). All roles with view-rate access (OPS_OPERATOR, FINANCE_ANALYST, ADMIN_VIEWER, SUPER_ADMIN) can view history. Returns paginated list of TreasuryRateHistoryDTO rows for the given ccy_pair: rateValue, effectiveFrom, effectiveUntil (null = current), updatedBy, updatedAt, notes. Path param ccyPair is case-insensitive (normalise to lowercase). Pagination: page and size query params; default size=50, max=200. Returns HTTP 404 if ccy_pair is not registered. | • Add GET /{ccyPair}/history endpoint to FxRateController • Normalise ccyPair path param to lowercase • Validate ccyPair is registered via CurrencyRegistry; return 404 with body {error: 'UNKNOWN_CURRENCY', ccyPair: ...} if not • Call TreasuryRateService.getHistory(ccyPair, pageable) • Return {data: [...], page, size, totalElements} envelope • Write controller test: usd_krw with 5 rows returns correct pagination; unknown ccy returns 404 | GET /admin/v1/fx-rates/{ccyPair}/history endpoint | • Returns HTTP 200 with paginated history array for registered ccy_pair • Returns HTTP 404 with UNKNOWN_CURRENCY error body for unregistered ccy_pair • Path param USD_KRW is normalised to usd_krw and resolves correctly • Most recent row has effectiveUntil=null in response • Page=0, size=2 with 5 rows returns 2 rows and totalElements=5 | 30 | 10.5-T08, 10.5-T11 | FS | PRD-07, RATE-04
10.5-T13 | admin-ui | 10.5 | 10. Admin System | FX/Treasury rate management | 1 | Implement POST /admin/v1/fx-rates/{ccyPair} REST endpoint: manual rate entry | The rate entry endpoint allows OPS_OPERATOR or SUPER_ADMIN (not FINANCE_ANALYST or ADMIN_VIEWER per permission matrix) to submit a new manual rate. Request body: {rate: decimal, effectiveAt: ISO-8601 datetime (optional, default NOW()), notes: string (optional)}. The service layer handles guard-rail logic (T07). If the guard-rail fires (deviation > 10% from previous rate) AND the request lacks confirmed=true, the endpoint returns HTTP 409 with {error: 'GUARD_RAIL_WARNING', deviation: X, previousRate: Y, message: 'Rate deviates X% from current value Y. Resend with confirmed=true to proceed.'}. On success returns HTTP 201 with the created TreasuryRateDTO. | • Add POST /{ccyPair} endpoint to FxRateController • Extract actor context (userId, displayName, IP) from authenticated session • Parse request body to SaveRateCommand; extract optional confirmed=true query/body param • Call TreasuryRateService.saveRate(cmd, actor, confirmed) • Catch GuardRailWarningException and return HTTP 409 with structured error body • Catch InvalidRateException and return HTTP 400; catch UnknownCurrencyException and return HTTP 404; catch IdentityRateMutationException and return HTTP 422 • Return HTTP 201 Created with TreasuryRateDTO body on success | POST /admin/v1/fx-rates/{ccyPair} endpoint with guard-rail 409 response | • POST with rate=1500 for usd_krw (prev=1350, deviation=11.1%) and no confirmed param returns HTTP 409 with deviation=11.1 and previousRate=1350.00 • POST with same body and confirmed=true returns HTTP 201 and new rate row • POST with rate=0 returns HTTP 400 • POST for usd_usd returns HTTP 422 • FINANCE_ANALYST role returns HTTP 403 | 40 | 10.5-T07, 10.5-T10, 10.5-T12 | FS | PRD-07, RATE-04
10.5-T14 | admin-ui | 10.5 | 10. Admin System | FX/Treasury rate management | 1 | Implement guard-rail threshold config: configurable ±% via application properties | The guard-rail deviation threshold for rate entry is configurable (PRD-07 Assumption A-09: default 10%, configurable via system parameter; UX spec §9 references ±20% for rule mapping page - the rate list uses ±10% per §7.3). The threshold must be externally configurable (application.yml property fx.rate.guard-rail.threshold-pct, default 10.0). TreasuryRateService must read this value at startup. Allow range 1.0 to 50.0; reject out-of-range config at startup with a clear error message. | • Add @ConfigurationProperties class FxRateProperties with field guardRailThresholdPct (double, default 10.0) • Inject FxRateProperties into TreasuryRateService and use guardRailThresholdPct in the deviation check • Add validation: @Min(1) @Max(50) on the property field, or manual check in @PostConstruct • Add application.yml entry fx.rate.guard-rail.threshold-pct: 10.0 • Write unit test: set threshold to 5.0; submit new rate of 1400 when previous=1350 (deviation=3.7%); assert no GuardRailWarningException • Write unit test: same threshold=5.0; submit 1430 (deviation=5.9%); assert GuardRailWarningException fires | FxRateProperties.java config class with guardRailThresholdPct wired into TreasuryRateService | • Default threshold=10.0 is used when property is not set • Setting fx.rate.guard-rail.threshold-pct=5.0 causes warning at 5.1% deviation but not at 4.9% • Invalid property value (e.g. 0.5) causes startup failure with descriptive error • FxRateProperties is exposed as a Spring bean and injectable • GuardRailWarningException carries the configured threshold value in its fields | 30 | 10.5-T07 | FS | PRD-07, RATE-04
10.5-T15 | admin-ui | 10.5 | 10. Admin System | FX/Treasury rate management | 1 | Unit tests: TreasuryRateService saveRate() - validation and guard-rail edge cases | Explicit unit-test ticket for edge-case coverage of TreasuryRateService.saveRate(). Rate convention: treasury.usd_{ccy} = units of {ccy} per 1 USD. Fixture rates from QA spec: usd_krw=1350.00, usd_mnt=3500.00, usd_eur=0.9200, usd_thb=35.500. Guard-rail default=10%. All tests use mocked TreasuryRateRepository and TreasuryRateAuditRepository. | • Create TreasuryRateServiceTest.java with JUnit 5 + Mockito • Test case A: rate=0 -> InvalidRateException • Test case B: rate=-0.01 -> InvalidRateException • Test case C: usd_krw existing=1350, new=1200 (deviation=11.1%), confirmed=false -> GuardRailWarningException with deviation approx 11.1 and previousRate=1350.00 • Test case D: same as C with confirmed=true -> inserts row and audit; returns DTO with rate=1200 • Test case E: first-ever rate for a new ccy_pair (previousRate null), any positive rate -> no guard-rail warning even if deviation would be large • Test case F: effectiveAt is future date 2026-12-31 00:00 UTC -> row saved with that effectiveAt; findCurrentRate(ccyPair, 2026-12-30) returns old rate; findCurrentRate(ccyPair, 2026-12-31T00:01) returns new | TreasuryRateServiceTest.java covering 6 edge-case scenarios | • All 6 test cases pass (green) • Test D verifies audit row has previousRate=1350 and newRate=1200 • Test E explicitly asserts no GuardRailWarningException when no previous rate exists • Test F verifies temporal isolation: old rate still effective before future effective_at • Test C verifies GuardRailWarningException.getDeviation() > 10.0 and < 12.0 | 45 | 10.5-T07, 10.5-T14 | FS | PRD-07, RATE-04
10.5-T16 | admin-ui | 10.5 | 10. Admin System | FX/Treasury rate management | 1 | Unit tests: TreasuryRateService getCurrentRate() - rate resolution and RATE_UNAVAILABLE | Explicit unit-test ticket for TreasuryRateService.getCurrentRate() edge cases. Rate resolution rule: return the row with greatest effective_at <= asOf. If none, throw RateUnavailableException. RATE-04 Assumption A3: Phase 1 does not enforce staleness - any stored value is used as-is. The usd_usd identity pair always resolves (from seed row). All tests use mocked TreasuryRateRepository. | • Create TreasuryRateGetRateTest.java with JUnit 5 + Mockito • Test case A: two rows usd_krw at t1=1350, t2=1400; query at t2+1s -> returns 1400 • Test case B: same rows; query at t1+1s -> returns 1350 (t2 is future relative to query time) • Test case C: no rows for usd_mnt -> RateUnavailableException with ccyPair='usd_mnt' • Test case D: only future row for usd_eur (effectiveAt=tomorrow) -> RateUnavailableException • Test case E: usd_usd -> always returns BigDecimal(1.0) via seed row • Test case F: very old stale row (1 year ago) for usd_krw -> still returned with no exception (Phase 1 no staleness block) | TreasuryRateGetRateTest.java covering 6 rate-resolution scenarios | • All 6 test cases pass (green) • Test B verifies temporal priority: query time determines which row is effective • Test C verifies RateUnavailableException.getCcyPair() = 'usd_mnt' • Test D verifies future-only row does not satisfy <= asOf and triggers exception • Test F passes without exception (confirming no staleness guard in Phase 1) | 35 | 10.5-T06 | FS | PRD-07, RATE-04
10.5-T17 | admin-ui | 10.5 | 10. Admin System | FX/Treasury rate management | 1 | Integrate TreasuryRateService into RateEngine: resolve cost_rate_coll and cost_rate_pay | The rate engine resolves cost rates at quote-issuance time. Per RATE-04: cost_rate_coll = treasury.usd_{settle_a_ccy} and cost_rate_pay = treasury.usd_{settle_b_ccy}. Identity leg: if settle_A = USD, cost_rate_coll = 1.0 (no lookup needed; guaranteed by usd_usd seed). The RateEngine must call TreasuryRateService.getCurrentRate(ccyPair, quoteIssuedAt) for each non-identity leg. RateUnavailableException must propagate as RATE_UNAVAILABLE error to the partner API. This ticket wires TreasuryRateService into the existing RateEngine (or its rate-resolution method) replacing any stub/hardcoded value. | • Locate the RateEngine class and its rate-resolution logic (resolveCostRate method or equivalent) • Inject TreasuryRateService into RateEngine • For settle_a_ccy: if ccy == 'USD' use 1.0 (identity); else call getCurrentRate('usd_'+settle_a_ccy.toLowerCase(), quoteIssuedAt) • For settle_b_ccy: same pattern • Wrap RateUnavailableException as a domain exception that maps to HTTP 503 / error code RATE_UNAVAILABLE in the partner API layer • Write integration test: seed usd_krw=1380 in DB; call RateEngine for KRW payout; assert cost_rate_pay=1380.00 | RateEngine wired to TreasuryRateService for live rate resolution, replacing any stub | • RateEngine resolves cost_rate_pay=1380.00 from DB when treasury.usd_krw=1380.00 • RateEngine uses cost_rate_coll=1.0 for USD settle_a (identity leg) without a DB lookup • RateEngine throws RATE_UNAVAILABLE when no treasury row exists for the requested ccy_pair • Integration test with seeded rate passes and the returned quote uses the seeded rate value • No hardcoded or stub rate values remain in RateEngine after this change | 45 | 10.5-T06, 10.5-T10 | FS | PRD-07, RATE-04
10.5-T18 | admin-ui | 10.5 | 10. Admin System | FX/Treasury rate management | 1 | Implement rate snapshot at quote commit: lock treasury rate into transaction record | RATE-04 rate-lock rule: at commit time (when scheme call succeeds), all USD pool values and derived rates are permanently recorded on the transaction. Subsequent treasury/margin changes have no effect on committed transactions. The transaction record must store the rate values used at quote time: cost_rate_coll_locked, cost_rate_pay_locked (both DECIMAL(20,8)). These are populated from the quote snapshot at commit. This ticket ensures the fields exist on the transaction entity and that they are written at commit and never overwritten. A BOK report reading from the committed record must see the locked values regardless of current treasury state. | • Add columns cost_rate_coll_locked DECIMAL(20,8) and cost_rate_pay_locked DECIMAL(20,8) to the transaction/payment table via migration V10_5_004__add_locked_rate_columns.sql (nullable until committed, then populated) • Add corresponding fields to the Transaction/Payment JPA entity • In TransactionOrchestrator (or commit handler), write these fields at commit time from the quote snapshot; use a single UPDATE that sets both fields atomically with status change to COMMITTED • Ensure no code path exists that updates these fields post-commit (add a guard: if already set, throw IllegalStateException) • Write integration test: commit a transaction with treasury rate 1350; update treasury to 1400; assert transaction record still shows cost_rate_pay_locked=1350.00 | Migration V10_5_004 and locked-rate write logic in TransactionOrchestrator | • Committed transaction has cost_rate_coll_locked and cost_rate_pay_locked populated • After updating treasury.usd_krw from 1350 to 1400, a previously committed transaction still shows cost_rate_pay_locked=1350.00 • Attempting to overwrite a locked rate (call commit path twice) throws or is a no-op (no second UPDATE) • Both fields are null for PENDING transactions (pre-commit) • Migration V10_5_004 applies cleanly on top of prior migrations | 50 | 10.5-T06, 10.5-T17 | FS | PRD-07, RATE-04
10.5-T19 | admin-ui | 10.5 | 10. Admin System | FX/Treasury rate management | 1 | Audit log wiring: emit treasury_rate.changed audit event on every saveRate() | PRD-07 §13 requires every FX rate change to produce an audit log entry with: event type 'treasury_rate.changed', entity type 'treasury_rate', entity id (new row id), previous value (serialized old rate + effective_at), new value (serialized new rate + effective_at), actor user id, display name, IP, timestamp. The audit entry must be inserted in the same DB transaction as the treasury_rate row insert. Failure to insert the audit row must roll back the rate insert (atomicity). The audit entry description must be human-readable, e.g. 'USD/KRW rate updated from 1350.00 to 1500.00 by ops@gme.com'. | • Verify @Transactional annotation on TreasuryRateService.saveRate() covers both the treasury_rate insert and the TreasuryRateAudit insert • Ensure TreasuryRateAuditRepository.save() is called within the same transaction as TreasuryRate insert • Build the audit entry description string: 'USD/{CCY} rate updated from {prev} to {new} by {actor}' • For first-ever rate entry (no previous), use description 'USD/{CCY} initial rate set to {new} by {actor}' • Write integration test: force TreasuryRateAuditRepository.save() to throw; assert the treasury_rate row is also rolled back | @Transactional saveRate() with audit row atomically co-inserted, integration test for rollback | • Both treasury_rate and treasury_rate_audit rows are inserted in a single transaction • If audit insert fails, treasury_rate insert is rolled back (no orphan rate row) • Audit description for update reads 'USD/KRW rate updated from 1350.00 to 1500.00 by {actor}' • Audit description for first entry reads 'USD/MNT initial rate set to 3500.00 by {actor}' • Audit entry actor_user_id matches the portal session userId | 40 | 10.5-T07, 10.5-T05 | FS | PRD-07, RATE-04
10.5-T20 | admin-ui | 10.5 | 10. Admin System | FX/Treasury rate management | 1 | Implement GET /admin/v1/fx-rates/{ccyPair} endpoint: single currency current rate detail | Endpoint for the rate detail / update form to pre-populate. Returns the current rate details for a single ccy_pair including: ccyPair, ratePairDisplay (e.g. USD / KRW), currentRate, lastUpdatedBy, lastUpdatedAt, effectiveFrom, source, notes (from last entry). Required roles: OPS_OPERATOR, FINANCE_ANALYST, ADMIN_VIEWER, SUPER_ADMIN. Returns HTTP 404 if ccy_pair is not registered. Also returns isIdentity=true for usd_usd to allow the UI to disable the edit button. | • Add GET /{ccyPair} endpoint to FxRateController • Normalise ccyPair to lowercase • Check CurrencyRegistry; return 404 if unregistered • Call TreasuryRateService.getCurrentRate(ccyPair, NOW()) - if no row, return 200 with currentRate=null (rate not yet set) • Also call getHistory(ccyPair, first page) to get the notes from the latest entry • Return TreasuryRateDetailDTO: ccyPair, ratePairDisplay, currentRate, lastUpdatedBy, lastUpdatedAt, effectiveFrom, source, notes, isIdentity • Write controller test: usd_krw returns 200 with currentRate=1350; usd_xyz returns 404 | GET /admin/v1/fx-rates/{ccyPair} endpoint returning TreasuryRateDetailDTO | • Returns HTTP 200 with currentRate=1350.00 for registered usd_krw • Returns HTTP 404 for unregistered ccy_pair • usd_usd response has isIdentity=true and currentRate=1.0 • Registered currency with no rate rows returns HTTP 200 with currentRate=null (not 404) • ADMIN_VIEWER role can access (read-only) | 30 | 10.5-T11, 10.5-T13 | FS | PRD-07, RATE-04
10.5-T21 | admin-ui | 10.5 | 10. Admin System | FX/Treasury rate management | 1 | Implement rate history CSV export: GET /admin/v1/fx-rates/{ccyPair}/history/export | PRD-07 §13.5 requires audit/history export to CSV. The rate history export endpoint returns all historical rows for a ccy_pair as a CSV file. Columns: Rate Value, Effective From (UTC ISO-8601), Effective Until (UTC ISO-8601 or 'Current'), Updated By, Updated At (UTC), Notes. The response Content-Type must be text/csv and Content-Disposition attachment filename should be fx_rate_history_{ccyPair}_{yyyyMMdd}.csv. Maximum rows: 10,000 (hard limit; return HTTP 400 with message if exceeded - this is a future-proofing guard). Required roles: OPS_OPERATOR, FINANCE_ANALYST, SUPER_ADMIN (ADMIN_VIEWER excluded per permission matrix for exports). | • Add GET /{ccyPair}/history/export endpoint to FxRateController • Check role: OPS_OPERATOR ¦ FINANCE_ANALYST ¦ SUPER_ADMIN; reject ADMIN_VIEWER with 403 • Validate ccy_pair registered; return 404 if not • Load full history (unpaginated) up to 10,001 rows; if count > 10,000 return HTTP 400 with message 'History exceeds export limit of 10,000 rows' • Build CSV string with header row and data rows; set effectiveUntil as ISO-8601 or string 'Current' • Set response headers: Content-Type: text/csv; Content-Disposition: attachment; filename=fx_rate_history_usd_krw_20260605.csv | GET /admin/v1/fx-rates/{ccyPair}/history/export CSV endpoint | • Returns CSV file with correct Content-Disposition filename for usd_krw export • CSV has header row: Rate Value,Effective From,Effective Until,Updated By,Updated At,Notes • Most-recent row has Effective Until = 'Current' in CSV • ADMIN_VIEWER role returns HTTP 403 • More than 10,000 history rows triggers HTTP 400 with descriptive message | 35 | 10.5-T12 | FS | PRD-07, RATE-04
10.5-T22 | admin-ui | 10.5 | 10. Admin System | FX/Treasury rate management | 1 | Unit tests: rate history effectiveUntil computation and pagination | Explicit unit test for TreasuryRateService.getHistory() correctness. History rows must be returned newest-first with effectiveUntil computed as the next newer row's effectiveAt, or null for the most recent row. Pagination must be correct: page 0 of size 2 for 5 rows returns 2 rows, totalElements=5. Edge cases: single row (effectiveUntil=null), exactly 2 rows, future-dated rows. | • Create TreasuryRateHistoryTest.java with JUnit 5 + Mockito • Test A: 3 rows at t1, t2, t3; getHistory page 0 size 10 -> 3 rows, t3 effectiveUntil=null, t2 effectiveUntil=t3, t1 effectiveUntil=t2 • Test B: 1 row -> effectiveUntil=null • Test C: 5 rows; getHistory page 0 size 2 -> 2 rows returned, totalElements=5 • Test D: 2 rows where t2 is future-dated -> newest row is t2 (effectiveUntil=null), t1 effectiveUntil=t2 • Test E: no rows -> empty list, no exception | TreasuryRateHistoryTest.java with 5 test cases | • All 5 test cases pass (green) • Test A: t2 row has effectiveUntil equal to t3's effectiveAt (not t3's createdAt) • Test C: page 1 size 2 returns rows 3 and 4 (correct offset) • Test D: future-dated row still appears as effectiveUntil=null since it is the most recent • Test E returns empty Page without NullPointerException | 30 | 10.5-T08 | FS | PRD-07, RATE-04
10.5-T23 | admin-ui | 10.5 | 10. Admin System | FX/Treasury rate management | 1 | Integration test: full rate update flow - save, audit, history, and rate engine resolution | End-to-end integration test covering the complete manual rate update flow. Exercises: POST rate -> verify treasury_rate row inserted -> verify audit row inserted -> GET history shows new row -> GET current rate shows new value -> simulate rate engine quote and verify cost_rate_pay uses new value. Uses a real test DB (PostgreSQL via Testcontainers). Rate fixture: usd_krw starts at 1350.00; update to 1380.00; verify engine uses 1380.00 for a KRW payout of 10000. | • Create FxRateIntegrationTest.java using @SpringBootTest and Testcontainers PostgreSQL • Seed: insert usd_krw=1350.00 row • Call POST /admin/v1/fx-rates/usd_krw with {rate:1380.00, notes:'Daily update'} as OPS_OPERATOR -> assert HTTP 201 • Call GET /admin/v1/fx-rates/usd_krw -> assert currentRate=1380.00 • Call GET /admin/v1/fx-rates/usd_krw/history -> assert first row has rateValue=1380.00 and second has 1350.00 • Call TreasuryRateService.getCurrentRate('usd_krw', NOW()) -> assert returns 1380.00 • Assert treasury_rate_audit table has 1 new row with previousRate=1350.00 and newRate=1380.00 | FxRateIntegrationTest.java with full end-to-end scenario | • POST returns HTTP 201 and new treasury_rate row exists in DB • Audit row has previousRate=1350.00 and newRate=1380.00 with actor fields populated • GET current rate returns 1380.00 after update • History shows 1380.00 as current and 1350.00 as previous with effectiveUntil set correctly • getCurrentRate returns 1380.00 (rate engine would use this value for cost_rate_pay in KRW payout calculation) | 50 | 10.5-T13, 10.5-T19, 10.5-T17 | FS | PRD-07, RATE-04
10.5-T24 | admin-ui | 10.5 | 10. Admin System | FX/Treasury rate management | 1 | Integration test: guard-rail 409 round-trip and confirmed=true acceptance | Integration test for the guard-rail warning flow. Starting rate usd_krw=1350.00; submit 1560.00 (deviation=15.6%, above default 10% threshold). First POST must return HTTP 409 with deviation and previousRate. Second POST with confirmed=true must return HTTP 201. Verify DB state, audit, and that a PENDING transaction quote issued before the update still uses the old rate (T18 rate-lock), while a new quote issued after uses 1560.00. | • Seed usd_krw=1350.00 in test DB • POST /admin/v1/fx-rates/usd_krw {rate:1560.00} -> assert HTTP 409, body.error='GUARD_RAIL_WARNING', body.deviation approx 15.6, body.previousRate=1350.00 • POST same body with confirmed=true -> assert HTTP 201 • Assert treasury_rate table has new row with rate=1560.00 • Assert audit row has previousRate=1350.00 and newRate=1560.00 • Assert getCurrentRate('usd_krw', time just before update) returns 1350.00 • Assert getCurrentRate('usd_krw', time after update) returns 1560.00 | GuardRailIntegrationTest.java covering 409 and confirmed=true round-trip | • First POST returns HTTP 409 with GUARD_RAIL_WARNING and deviation between 15 and 16 • Confirmed POST returns HTTP 201 and DB shows new rate row • Temporal query before update effective_at returns 1350.00 • Temporal query after effective_at returns 1560.00 • Audit row exists with previousRate=1350.00 and newRate=1560.00 | 45 | 10.5-T13, 10.5-T14, 10.5-T23 | FS | PRD-07, RATE-04
10.5-T25 | admin-ui | 10.5 | 10. Admin System | FX/Treasury rate management | 1 | Write OpenAPI documentation for FX rate management endpoints | PRD-07 requires the Admin API to be documented. The four FX rate endpoints (GET list, GET detail, GET history, POST save) and the history CSV export must be documented in OpenAPI 3.0 YAML/annotation format. Each endpoint needs: summary, description (including role requirements), request/response schema, error codes (400/401/403/404/409/422), and example request/response. The guard-rail 409 response schema must be documented with fields: error, deviation, previousRate, message. | • Add @Operation, @ApiResponse, @Parameter annotations to all endpoints in FxRateController.java • Document GET / list: role requirement, response schema TreasuryRateListDTO array • Document GET /{ccyPair}: 200, 404 responses; note isIdentity field for usd_usd • Document POST /{ccyPair}: 201, 400, 403, 404, 409 (GUARD_RAIL_WARNING), 422 responses; document confirmed query param • Document GET /{ccyPair}/history: pagination params, 404 • Document GET /{ccyPair}/history/export: 200 CSV, 400 (row limit), 403, 404 • Verify springdoc-openapi generates correct spec by loading /v3/api-docs and checking fx-rates paths exist | OpenAPI annotations on FxRateController.java with all 5 endpoints documented | • GET /v3/api-docs includes /admin/v1/fx-rates path with GET operation • POST /{ccyPair} documents 409 response with schema containing error, deviation, previousRate fields • confirmed query parameter is documented on the POST endpoint • Export endpoint documents text/csv as response media type • All error codes 400, 401, 403, 404, 409, 422 are listed in @ApiResponse annotations where applicable | 35 | 10.5-T13, 10.5-T21 | FS | PRD-07, RATE-04
10.6-T01 | admin-ui | 10.6 | 10. Admin System | Transaction monitoring | 2 | Add DB indexes for transaction search filter dimensions | WBS 10.6 — Transaction Monitoring UI (Admin System). The transaction table has columns: partner_id, scheme_id, status, direction, payment_mode, committed_at, hub_txn_ref, txn_ref (partner_txn_ref), merchant_id, failure_origin, failure_code. Composite indexes already exist per DAT-03: (partner_id, committed_at), (scheme_id, completed_at), (status, committed_at), (scheme_ref), (hub_txn_ref). The search UI (PRD-07 §8.2) also filters by: partner_txn_ref (exact), merchant_id (partial LIKE), failure_origin, failure_code, and payout amount range. Slow filter paths need covering indexes. | • Review existing indexes on the transaction table in the migration history. • Add index on (partner_txn_ref) for exact-match lookup. • Add index on (merchant_id) supporting LIKE prefix search (btree sufficient for prefix). • Add composite index on (failure_origin, status) for failure-origin filter combined with status. • Add index on (target_payout, payout_ccy) for amount-range filter. • Write migration file V10_6_001__txn_search_indexes.sql. | Migration file V10_6_001__txn_search_indexes.sql with 4 new indexes on the transaction table | • \EXPLAIN SELECT on hub_txn_ref = 'HUB-001' uses index scan (not seq scan) on the new index. • \EXPLAIN SELECT on merchant_id LIKE 'MRC-1%' uses index scan. • \EXPLAIN SELECT on target_payout BETWEEN 5000 AND 20000 AND payout_ccy = 'KRW' uses index scan. • Migration is idempotent — running it twice does not error (use CREATE INDEX IF NOT EXISTS). • No existing index is dropped or altered. | 30 |  | FS | PRD-07
10.6-T02 | admin-ui | 10.6 | 10. Admin System | Transaction monitoring | 2 | Define TransactionSearchCriteria DTO and repository search method signature | WBS 10.6. The Admin System backend (Java + Spring) needs a typed search criteria object covering all 10 filter dimensions from PRD-07 §8.2: partnerId (Set<Long>), schemeId (Set<Long>), direction (Set<String>), status (Set<String>), dateFrom/dateTo (OffsetDateTime, max span 90 days), hubTxnRef (String exact), partnerTxnRef (String exact), merchantId (String partial), failureOrigin (String), failureCode (String), payoutAmountFrom/payoutAmountTo (BigDecimal). Also pagination: page (0-based), pageSize (default 50), sortField (TIMESTAMP¦PAYOUT_AMOUNT¦PARTNER¦STATUS), sortDirection (ASC¦DESC). | • Create class TransactionSearchCriteria in package com.gmepayplus.admin.txn.dto. • Add all 13 filter fields with types as described in context; add page/pageSize/sortField/sortDirection. • Add bean-validation annotations: dateFrom required if dateTo present; date span <= 90 days (custom constraint DateRangeMax90Days); pageSize max 50. • Create interface TransactionRepository method signature: Page<TransactionSummary> search(TransactionSearchCriteria criteria). • Create TransactionSummary projection interface/record with columns from PRD-07 §8.3: hubTxnRef, committedAt, partnerName, schemeName, direction, mode, targetPayout, payoutCcy, collectionAmount, collectionCcy, serviceCharge, status, durationMs. | TransactionSearchCriteria DTO class and TransactionRepository.search signature with TransactionSummary projection | • @Valid on TransactionSearchCriteria rejects dateFrom=2025-01-01 dateTo=2025-04-15 (span=104 days > 90) with constraint violation. • @Valid accepts dateFrom=2025-01-01 dateTo=2025-03-31 (span=89 days). • pageSize=100 fails validation; pageSize=50 passes. • TransactionSummary contains all 13 columns from PRD-07 §8.3 — compile check. • sortField enum rejects unknown value at deserialization. | 35 | 10.6-T01 | FS | PRD-07
10.6-T03 | admin-ui | 10.6 | 10. Admin System | Transaction monitoring | 2 | Implement JPQL/Criteria query for dynamic transaction search | WBS 10.6. Implement the repository method TransactionRepository.search(TransactionSearchCriteria) using JPA Criteria API (or QueryDSL) so predicates are added only when the filter field is non-null/non-empty. Join transaction to partner (for partnerName), qr_scheme (schemeName). Apply merchant_id LIKE predicate as lower(t.merchantId) LIKE lower(:mid)+'%'. Apply date filter on committed_at column. Default date range when both dateFrom and dateTo are null: last 24 hours (now() minus 24h). Sort maps: TIMESTAMP -> committed_at, PAYOUT_AMOUNT -> target_payout, PARTNER -> partner.name, STATUS -> status. | • Create TransactionRepositoryCustom interface and TransactionRepositoryImpl. • In search(), build a list of Predicates; add each only when the corresponding criteria field is non-null/non-empty. • Join to partner entity for name; join to qr_scheme for name. • Implement LIKE predicate for merchantId (case-insensitive prefix). • Map sortField enum to CriteriaBuilder.asc/desc on the correct path. • Return Page<TransactionSummary> using entityManager.createQuery + count query. | TransactionRepositoryImpl.search() — functional Criteria-API query covering all 10 filter dimensions | • Calling search with only status=[APPROVED] and partner=[SendMN id] returns only rows matching both filters (verified against test DB rows). • Calling search with no filters returns transactions from the last 24 hours only (default range). • Calling search with merchantId='MRC' returns rows where merchant_id starts with 'MRC' case-insensitively. • Calling search with dateFrom and dateTo spanning 5 days returns 0 rows for an empty date range (no false positives). • Total count query uses the same predicates as the data query (no count/data mismatch). | 55 | 10.6-T02 | FS | PRD-07
10.6-T04 | admin-ui | 10.6 | 10. Admin System | Transaction monitoring | 2 | Add GET /admin/v1/transactions search endpoint | WBS 10.6. Expose the transaction search as a REST endpoint secured by RBAC. Roles OPS_ADMIN, OPS_VIEWER, FINANCE, SUPER_ADMIN may call it. ADMIN_VIEWER may search but cannot see locked pool values (that is enforced in the detail endpoint, not search). Endpoint: GET /admin/v1/transactions with query params matching TransactionSearchCriteria. Returns: { data: [TransactionSummary], page, pageSize, totalCount, totalPages }. Response time SLA: <= 2 seconds for typical query (enforced by index + pagination). Include response header X-Query-Duration-Ms for monitoring. | • Create TransactionController with @GetMapping('/admin/v1/transactions'). • Bind query params to TransactionSearchCriteria via @Valid @ModelAttribute; return 400 on validation failure with error details. • Call transactionService.search(criteria); service delegates to repository. • Map Page<TransactionSummary> to TransactionListResponse DTO. • Add @PreAuthorize checking role is one of OPS_ADMIN, OPS_VIEWER, FINANCE, SUPER_ADMIN. • Add response header X-Query-Duration-Ms recording elapsed milliseconds. | GET /admin/v1/transactions endpoint in TransactionController with RBAC and pagination response | • GET /admin/v1/transactions?status=APPROVED&partnerId=2&dateFrom=2025-05-01&dateTo=2025-05-07 returns HTTP 200 with correct result set. • Request with dateFrom=2025-01-01&dateTo=2025-04-15 returns HTTP 400 with field error on date range. • Unauthenticated request returns 401; request with role PARTNER returns 403. • Response includes X-Query-Duration-Ms header with a numeric value. • Response body contains totalCount, page=0, pageSize=50 for a default request. | 40 | 10.6-T03 | FS | PRD-07
10.6-T05 | admin-ui | 10.6 | 10. Admin System | Transaction monitoring | 2 | Implement transaction list CSV export endpoint (up to 100,000 rows) | WBS 10.6. PRD-07 §8.2 specifies CSV export of all matching results up to 100,000 rows. The CSV columns are a superset of the list view: all §8.3 columns plus offer_rate_coll, scheme_ref, merchant_id, merchant_name, full hub_txn_ref. The export streams directly to HTTP response to avoid OOM; uses the same TransactionSearchCriteria filter. Endpoint: GET /admin/v1/transactions/export. Roles: same as search. File name header: Content-Disposition: attachment; filename=gmepay_txns_{from}_{to}.csv. | • Add @GetMapping('/admin/v1/transactions/export') to TransactionController. • Validate criteria (same @Valid rules); if date range missing default to last 24h. • Use ScrollableResults or Spring Data Scroll API to stream rows in pages of 1000 without loading all into memory. • Write CSV header row then data rows via Jackson CsvMapper or manual StringBuilder; flush each page to HttpServletResponse OutputStream. • Cap at 100,000 rows; if count would exceed, write up to 100,000 rows and add response header X-Export-Truncated: true. • Set Content-Type: text/csv; charset=UTF-8 and Content-Disposition header with formatted filename. | GET /admin/v1/transactions/export streaming CSV endpoint with 100k row cap | • Export for a 7-day date range with 300 matching rows produces a CSV file with 301 lines (header + 300 data rows) and correct column order. • Export where count > 100,000 returns exactly 100,000 data rows and includes header X-Export-Truncated: true. • CSV includes column offer_rate_coll and full hub_txn_ref (not truncated). • Memory usage does not grow proportionally with result size (streamed in pages of 1000 — verify no full-list collection in service layer). • Unauthenticated request returns 401 before any data is written. | 55 | 10.6-T04 | FS | PRD-07
10.6-T06 | admin-ui | 10.6 | 10. Admin System | Transaction monitoring | 2 | Define TransactionDetailResponse DTO with full locked rate/pool fields | WBS 10.6. PRD-07 §8.5.2 specifies 15 locked rate/pool fields shown in the detail view: target_payout, payout_usd_cost, collection_usd, collection_margin_usd, payout_margin_usd, send_amount, service_charge, collection_amount, cost_rate_coll, cost_rate_pay, offer_rate_coll, cross_rate, rate_quote_ttl_seconds, rate_quote_valid_until, and is_same_ccy_shortcircuit. For same-currency transactions (is_same_ccy_shortcircuit=true) the USD pool fields (payout_usd_cost, collection_usd, collection_margin_usd, payout_margin_usd, offer_rate_coll, cross_rate) must be null and a flag sameCcyShortCircuit=true set. ADMIN_VIEWER role must not see pool/margin values. | • Create TransactionDetailResponse record with: identity section (§8.5.1 fields), ratePool section (§8.5.2 fields), eventTrail list (§8.5.3), prefundingEntry (§8.5.4, nullable), settlementLinkage (§8.5.5, nullable). • For ratePool, use BigDecimal for all monetary/rate fields; include sameCcyShortCircuit boolean. • Create RoleAwareTransactionDetailResponse that zeroes/nulls pool fields if caller role = ADMIN_VIEWER. • Add EventTrailStep record: step (int 1-8), eventType (String), occurredAt (OffsetDateTime), durationMs (Integer nullable), detail (Map<String,Object>), absent (boolean), absentReason (String). • Add PrefundingEntry record: balanceBefore, deductionAmountUsd, balanceAfter (all BigDecimal). | TransactionDetailResponse DTO hierarchy with role-aware pool value masking and EventTrailStep record | • TransactionDetailResponse for a cross-border txn contains all 15 rate/pool fields as non-null. • TransactionDetailResponse for a same-ccy txn has sameCcyShortCircuit=true and payout_usd_cost=null, collection_usd=null, collection_margin_usd=null, payout_margin_usd=null. • RoleAwareTransactionDetailResponse when role=ADMIN_VIEWER sets collection_margin_usd and payout_margin_usd to null. • EventTrailStep with absent=true has absentReason populated (e.g. 'Step skipped: LOCAL partner has no prefunding deduction'). • Compile-time check: all 15 fields in §8.5.2 exist on the DTO. | 40 | 10.6-T02 | FS | PRD-07
10.6-T07 | admin-ui | 10.6 | 10. Admin System | Transaction monitoring | 2 | Implement transaction detail service — load txn + event trail + prefunding entry + settlement linkage | WBS 10.6. The detail service loads a single transaction by hub_txn_ref, joining: partner, qr_scheme, merchant, rate_quote. It also loads the transaction_event rows (step 1-8) ordered by step, the prefunding_ledger_entry linked to this txn (for OVERSEAS), and settlement batch linkage (ZP0011/ZP0061/ZP0065 references stored in a settlement_txn_link table). For LOCAL partners, step 2 (prefunding_deducted) is absent — show as grayed with reason 'LOCAL partner: no prefunding deduction'. For absent steps beyond step 2, show reason 'Not yet reached' or 'Failed before this step'. | • Create TransactionDetailService.getDetail(String hubTxnRef, String callerRole). • Load transaction + joins in a single JPQL query by hub_txn_ref; throw NotFoundException if not found. • Load List<TransactionEvent> by txn_id ordered by step asc. • Build full 8-step trail: for each step 1-8, find matching event or mark absent with reason. • For OVERSEAS txn, load prefunding_ledger_entry where txn_id matches and entry_type=DEDUCTION; map to PrefundingEntry. • Load settlement linkage rows; map to SettlementLinkage list. • Apply role masking via RoleAwareTransactionDetailResponse before returning. | TransactionDetailService.getDetail() returning fully-populated TransactionDetailResponse | • For a LOCAL partner txn, eventTrail[step=2].absent=true and absentReason contains 'LOCAL partner'. • For an OVERSEAS partner txn, eventTrail[step=2].absent=false and prefundingEntry is non-null with correct deductionAmountUsd. • For a FAILED txn that stopped at step 4, steps 5-8 have absent=true with reason 'Not yet reached'. • When hub_txn_ref does not exist, service throws NotFoundException (maps to HTTP 404). • For a same-ccy txn, ratePool.sameCcyShortCircuit=true and USD pool fields are all null. | 55 | 10.6-T06 | FS | PRD-07
10.6-T08 | admin-ui | 10.6 | 10. Admin System | Transaction monitoring | 2 | Add GET /admin/v1/transactions/{hubTxnRef} detail endpoint | WBS 10.6. Expose the detail service as a REST endpoint. Path: GET /admin/v1/transactions/{hubTxnRef}. Roles: OPS_ADMIN, OPS_VIEWER, FINANCE, SUPER_ADMIN, ADMIN_VIEWER all allowed, but ADMIN_VIEWER receives masked pool values (handled in service via RoleAwareTransactionDetailResponse). Return HTTP 404 when not found; 200 with full TransactionDetailResponse otherwise. Log the access in the audit log (actor, timestamp, hubTxnRef accessed) — read-only audit entry type TXN_DETAIL_VIEWED. | • Add @GetMapping('/admin/v1/transactions/{hubTxnRef}') to TransactionController. • Extract calling user's role from SecurityContext; pass to transactionDetailService.getDetail(hubTxnRef, role). • Catch NotFoundException and return ResponseEntity with 404 and problem-detail body. • After successful retrieval, call auditService.log(TXN_DETAIL_VIEWED, hubTxnRef, actor). • Add @PreAuthorize for all five roles. • Return 200 with TransactionDetailResponse body. | GET /admin/v1/transactions/{hubTxnRef} endpoint with RBAC, audit logging, and 404 handling | • GET /admin/v1/transactions/HUB-999-NOTEXIST returns HTTP 404 with body containing field hubTxnRef. • GET /admin/v1/transactions/HUB-001 with role=ADMIN_VIEWER returns HTTP 200 but collection_margin_usd and payout_margin_usd are null in response. • GET /admin/v1/transactions/HUB-001 with role=OPS_ADMIN returns all 15 pool fields populated. • Audit log contains an entry with actor, action=TXN_DETAIL_VIEWED, entityRef=HUB-001 within 1 second of request. • Unauthenticated request returns 401. | 35 | 10.6-T07 | FS | PRD-07
10.6-T09 | admin-ui | 10.6 | 10. Admin System | Transaction monitoring | 2 | Implement event trail duration_ms computation and step-ordering invariant | WBS 10.6. PRD-07 §8.5.3 shows each step has duration_ms = milliseconds since previous step. transaction_event table has columns: step (INT 1-8), occurred_at (TIMESTAMPTZ), duration_ms (INT). The detail view must display computed delta regardless of whether duration_ms was stored. Also, if occurred_at values are stored out-of-order (e.g. clock skew), the service must sort by step, not occurred_at. PRD-07 assumption A-10: all 8 steps are stored on every transaction record from day one; absent steps have occurred_at=NULL. | • In TransactionDetailService, after loading events, sort by step ascending. • For each step, compute display duration_ms: if step.duration_ms is non-null use it; else compute as DATEDIFF_MS(current_step.occurred_at, previous_step.occurred_at) where previous has a non-null occurred_at. • Step 1 always shows duration_ms as null (dash). • If occurred_at is null for a step, duration_ms is also shown as null. • Unit test: provide 3 events with clock-skew ordering (step 3 occurred_at < step 2 occurred_at) and assert output is sorted by step, not by time. | Duration-computation logic in TransactionDetailService with sort-by-step guarantee | • Given step1.occurred_at=T+0, step2.occurred_at=T+200ms, step3.occurred_at=T+150ms (clock skew), output trail is [step1, step2, step3] in step order, not time order. • step1 display durationMs = null. • step2 display durationMs = 200. • step3 display durationMs: if stored duration_ms present use it; else computed as step3.occurred_at - step2.occurred_at = -50 (show as null or 0 to avoid negative display — document behavior in code comment). • A step with occurred_at=null shows durationMs=null regardless of neighbors. | 35 | 10.6-T07 | FS | PRD-07
10.6-T10 | admin-ui | 10.6 | 10. Admin System | Transaction monitoring | 2 | Implement pool identity validation check on detail load (diagnostic flag) | WBS 10.6. PRD-07 §8.5.2 states locked values are authoritative for settlement and BOK reporting. The detail view should surface a diagnostic warning if the committed values violate the pool identity invariant: collection_usd - collection_margin_usd - payout_margin_usd == payout_usd_cost (tolerance 0.01 USD). This is not a blocking error — it flags a data quality issue for Ops investigation. Add a field poolIdentityOk (boolean) and poolIdentityDelta (BigDecimal) to TransactionDetailResponse.ratePool. Same-ccy txns always have poolIdentityOk=true (N/A). | • Add fields poolIdentityOk (Boolean) and poolIdentityDelta (BigDecimal) to the ratePool section of TransactionDetailResponse. • In TransactionDetailService, after loading the txn, for non-same-ccy txns compute: delta = collection_usd - collection_margin_usd - payout_margin_usd - payout_usd_cost using BigDecimal. • Set poolIdentityOk = abs(delta) <= 0.01; set poolIdentityDelta = delta. • For same-ccy txns, set poolIdentityOk = true, poolIdentityDelta = null. • Log a WARN if poolIdentityOk = false, including hubTxnRef and delta value. | Pool identity check in TransactionDetailService with poolIdentityOk and poolIdentityDelta fields on response | • Given collection_usd=1000.00, collection_margin_usd=10.00, payout_margin_usd=8.00, payout_usd_cost=982.00: delta=0.00, poolIdentityOk=true. • Given collection_usd=1000.00, collection_margin_usd=10.00, payout_margin_usd=8.00, payout_usd_cost=981.98: delta=0.02 > 0.01, poolIdentityOk=false. • Given collection_usd=1000.00, collection_margin_usd=10.00, payout_margin_usd=8.00, payout_usd_cost=981.995: abs(delta)=0.005 <= 0.01, poolIdentityOk=true. • For a same-ccy txn (is_same_ccy_shortcircuit=true), poolIdentityOk=true and poolIdentityDelta=null. • A WARN log line is emitted when poolIdentityOk=false. | 30 | 10.6-T07 | FS | PRD-07
10.6-T11 | admin-ui | 10.6 | 10. Admin System | Transaction monitoring | 2 | Add DB index on transaction_event(txn_id, step) for trail lookups | WBS 10.6. The detail view loads up to 8 transaction_event rows by txn_id ordered by step. The existing schema in DAT-03 does not list a composite index on (txn_id, step). Without it, loading the 8-step trail for every detail page open causes a full scan of a large event table. This ticket adds the covering index. | • Create migration V10_6_002__txn_event_trail_index.sql. • Add CREATE UNIQUE INDEX IF NOT EXISTS uix_txn_event_txn_step ON transaction_event(txn_id, step) — unique because each txn has at most one event per step. • Add plain index on transaction_event(txn_id) for queries that load all events for a txn without step filter. • Verify EXPLAIN SELECT * FROM transaction_event WHERE txn_id=? ORDER BY step uses index scan. | Migration V10_6_002__txn_event_trail_index.sql with unique composite index on transaction_event(txn_id, step) | • Migration applies cleanly on schema with existing transaction_event rows. • EXPLAIN SELECT * FROM transaction_event WHERE txn_id=42 ORDER BY step shows Index Scan using uix_txn_event_txn_step. • Attempting to insert a second row for txn_id=42, step=3 raises unique constraint violation. • Migration is idempotent (CREATE INDEX IF NOT EXISTS). | 20 | 10.6-T01 | FS | PRD-07
10.6-T12 | admin-ui | 10.6 | 10. Admin System | Transaction monitoring | 2 | Define TransactionStatusEnum and map status values to display labels and terminal/non-terminal flag | WBS 10.6. PRD-07 §8.4 defines 10 status values: PENDING, COMMITTED, SUBMITTED_TO_SCHEME, SCHEME_APPROVED, APPROVED, UNCERTAIN, FAILED, CANCELLED, REFUNDED, REFUND_PENDING. The UI needs: (a) a display label for each, (b) a terminal flag (FAILED, CANCELLED, REFUNDED are terminal; APPROVED and SCHEME_APPROVED are final-success), (c) a color hint (RED for FAILED, AMBER for UNCERTAIN/REFUND_PENDING, GREEN for APPROVED/REFUNDED, GREY for CANCELLED, BLUE for in-progress). The frontend and backend filter chips both depend on this enum. | • Create Java enum TransactionStatus with 10 values. • Add fields: displayLabel (String), terminal (boolean), colorHint (enum: RED/AMBER/GREEN/GREY/BLUE). • Annotate each value per spec: FAILED/CANCELLED terminal=true colorHint=RED/GREY; APPROVED terminal=true colorHint=GREEN; UNCERTAIN terminal=false colorHint=AMBER; PENDING/COMMITTED/SUBMITTED_TO_SCHEME/SCHEME_APPROVED terminal=false colorHint=BLUE; REFUNDED terminal=true colorHint=GREEN; REFUND_PENDING terminal=false colorHint=AMBER. • Expose a GET /admin/v1/transactions/status-values endpoint that returns the enum list as JSON for frontend filter chip population. • Write a small unit test asserting terminal and colorHint for all 10 values. | TransactionStatus enum with display metadata and GET /admin/v1/transactions/status-values endpoint | • FAILED.terminal=true, FAILED.colorHint=RED. • APPROVED.terminal=true, APPROVED.colorHint=GREEN. • UNCERTAIN.terminal=false, UNCERTAIN.colorHint=AMBER. • GET /admin/v1/transactions/status-values returns a JSON array of 10 objects each containing value, displayLabel, terminal, colorHint. • Unit test passes for all 10 status values. | 30 |  | FS | PRD-07
10.6-T13 | admin-ui | 10.6 | 10. Admin System | Transaction monitoring | 2 | Add failure_origin and failure_code columns to transaction table migration | WBS 10.6. PRD-07 §8.2 filter includes Failure Origin (REQUEST/SETTLEMENT/PAYOUT/INTERNAL) and Failure Code (free text, e.g. INSUFFICIENT_PREFUNDING, PARTNER_B_QUOTE_DEVIATION). These two columns must exist on the transaction table. DAT-03 may not have explicitly called them out — add them now if missing. Failure Origin is a VARCHAR(20) enum-like column; Failure Code is VARCHAR(100). Both are nullable (null = no failure). | • Check existing transaction table DDL for failure_origin and failure_code columns. • If missing, create migration V10_6_003__txn_failure_columns.sql adding: failure_origin VARCHAR(20) NULL CHECK (failure_origin IN ('REQUEST','SETTLEMENT','PAYOUT','INTERNAL')); failure_code VARCHAR(100) NULL. • Add a partial index on (failure_origin, status) WHERE failure_origin IS NOT NULL. • Update TransactionSummary projection and TransactionDetailResponse to include failureOrigin and failureCode fields. | Migration V10_6_003__txn_failure_columns.sql and updated projections with failureOrigin/failureCode | • INSERT with failure_origin='UNKNOWN' violates check constraint. • INSERT with failure_origin='REQUEST', failure_code='INSUFFICIENT_PREFUNDING' succeeds. • INSERT with failure_origin=NULL, failure_code=NULL succeeds (non-failure txn). • TransactionSummary includes failureCode field — compile check. • EXPLAIN SELECT on failure_origin='REQUEST' AND status='FAILED' uses the partial index. | 25 | 10.6-T01 | FS | PRD-07
10.6-T14 | admin-ui | 10.6 | 10. Admin System | Transaction monitoring | 2 | Implement UNCERTAIN status resolution tracking in event trail | WBS 10.6. PRD-07 §8.4 states UNCERTAIN transactions are resolved to APPROVED or FAILED within 24 hours via ZeroPay batch reconciliation. When resolved, the transaction_event table receives a new event of type TRANSACTION_STATUS_UPDATED (step 6) with detail containing resolvedFrom='UNCERTAIN' and resolvedTo='APPROVED'¦'FAILED'. The event trail must show this resolution event with elapsed time since UNCERTAIN was set. The detail view must show a note when the current status was previously UNCERTAIN. | • In TransactionDetailService, check if any transaction_event has eventType=TRANSACTION_STATUS_UPDATED and detail.resolvedFrom='UNCERTAIN'. • If found, set a boolean field resolvedFromUncertain=true and resolvedAt=occurred_at on the ratePool/identity section of TransactionDetailResponse. • In the event trail display, step 6 with resolvedFrom='UNCERTAIN' shows a note: 'Resolved from UNCERTAIN via batch reconciliation at {resolvedAt}'. • Add a field resolvedFromUncertain (Boolean) and resolvedAt (OffsetDateTime) to TransactionDetailResponse identity section. • Unit test: build an event trail with step 6 eventType=TRANSACTION_STATUS_UPDATED detail={resolvedFrom:'UNCERTAIN',resolvedTo:'APPROVED'} and assert resolvedFromUncertain=true. | UNCERTAIN resolution tracking fields on TransactionDetailResponse and corresponding service logic | • A txn with step-6 event detail={resolvedFrom='UNCERTAIN',resolvedTo='APPROVED'} produces resolvedFromUncertain=true and resolvedAt populated in the response. • A txn with no UNCERTAIN resolution produces resolvedFromUncertain=false (or null) and resolvedAt=null. • The EventTrailStep for step 6 in this case includes detail map containing resolvedFrom and resolvedTo keys. • Unit test passes for UNCERTAIN->APPROVED and UNCERTAIN->FAILED resolution cases. • A currently-UNCERTAIN txn (step 6 absent) has resolvedFromUncertain=false. | 35 | 10.6-T07 | FS | PRD-07
10.6-T15 | admin-ui | 10.6 | 10. Admin System | Transaction monitoring | 2 | Unit tests — TransactionSearchCriteria validation rules | WBS 10.6. The TransactionSearchCriteria DTO has validation constraints that must be unit-tested exhaustively: date range max 90 days, dateFrom required when dateTo present (and vice versa), pageSize max 50, amount range from <= to. Use JUnit 5 + Hibernate Validator to test the bean constraints without a Spring context. | • Create TransactionSearchCriteriaValidationTest in the test package. • Test: dateFrom=null dateTo=2025-05-01 -> constraint violation on dateFrom. • Test: dateFrom=2025-01-01 dateTo=2025-04-15 (104 days) -> violation on date range. • Test: dateFrom=2025-01-01 dateTo=2025-03-31 (89 days) -> no violation. • Test: pageSize=51 -> violation; pageSize=50 -> no violation. • Test: payoutAmountFrom=500 payoutAmountTo=100 -> violation (from > to). | TransactionSearchCriteriaValidationTest with 8+ test cases covering all constraint rules | • All 8+ test cases pass. • Date-range-over-90-days test produces exactly one ConstraintViolation on the dateRangeMax90Days constraint. • pageSize=51 test produces violation on pageSize field. • payoutAmountFrom > payoutAmountTo test produces violation identifying the cross-field constraint. • Zero test cases use Spring context (pure unit test, fast < 3s total). | 30 | 10.6-T02 | FS | PRD-07
10.6-T16 | admin-ui | 10.6 | 10. Admin System | Transaction monitoring | 2 | Unit tests — TransactionDetailService pool identity check | WBS 10.6. The pool identity invariant is collection_usd - collection_margin_usd - payout_margin_usd == payout_usd_cost (tolerance 0.01 USD). Unit test TransactionDetailService.computePoolIdentity with multiple numeric vectors including edge cases around the tolerance boundary. | • Create TransactionDetailServicePoolIdentityTest using Mockito to stub the repository. • Test vector A: collection_usd=1000.00, collection_margin_usd=10.00, payout_margin_usd=8.00, payout_usd_cost=982.00 -> delta=0.00, ok=true. • Test vector B: collection_usd=1000.00, collection_margin_usd=10.00, payout_margin_usd=8.00, payout_usd_cost=981.98 -> delta=0.02, ok=false. • Test vector C: delta=0.01 exactly -> ok=true (boundary, inclusive). • Test vector D: delta=-0.01 exactly -> ok=true (negative delta within tolerance). • Test vector E: delta=0.011 -> ok=false. • Test same-ccy txn: is_same_ccy_shortcircuit=true -> poolIdentityOk=true, poolIdentityDelta=null. | TransactionDetailServicePoolIdentityTest with 7 test vectors covering boundary conditions | • All 7 test vectors pass. • Vector B correctly produces poolIdentityOk=false. • Vector C and D (boundary +/-0.01) both produce poolIdentityOk=true. • Vector E (0.011) produces poolIdentityOk=false. • Same-ccy test produces poolIdentityDelta=null. | 30 | 10.6-T10 | FS | PRD-07
10.6-T17 | admin-ui | 10.6 | 10. Admin System | Transaction monitoring | 2 | Unit tests — event trail step ordering and duration_ms computation | WBS 10.6. Test the event trail service logic for step sorting, duration computation, and absent-step handling. Uses Mockito to stub repository; tests run without a database. | • Create EventTrailServiceTest. • Test sort-by-step: supply events with out-of-order occurred_at (step3 < step2 time); assert output ordered by step. • Test duration: step1 at T+0ms, step2 at T+200ms -> step2.durationMs=200. • Test absent step: supply only steps 1,3,4,5,6,7,8 (step 2 missing, partner type=LOCAL) -> trail has 8 entries; entry at step 2 has absent=true, absentReason contains 'LOCAL'. • Test absent from failure: supply steps 1-4, txn status=FAILED -> steps 5-8 have absent=true, absentReason contains 'Not yet reached'. • Test null occurred_at step: step4.occurred_at=null -> step4.durationMs=null. | EventTrailServiceTest with 5+ test scenarios covering ordering, duration, and absent-step logic | • All 5+ tests pass. • Out-of-order time test: output index 0=step1, index 1=step2, index 2=step3 (by step not time). • Duration test: step1.durationMs=null, step2.durationMs=200. • LOCAL partner step-2 absent test: eventTrail.get(1).absent=true. • Null occurred_at test: eventTrail.get(3).durationMs=null. | 35 | 10.6-T09 | FS | PRD-07
10.6-T18 | admin-ui | 10.6 | 10. Admin System | Transaction monitoring | 2 | Unit tests — TransactionSearchCriteria default date range and sort mapping | WBS 10.6. When neither dateFrom nor dateTo is provided, the search must default to the last 24 hours. Also verify that each sortField enum value maps to the correct transaction table column name in the generated query. These behaviors live in TransactionRepositoryImpl and must be tested. | • Create TransactionRepositoryImplTest using an in-memory H2 database or Testcontainers PostgreSQL. • Insert 3 transactions: T1 at now()-30h (outside 24h window), T2 at now()-12h, T3 at now()-1h. • Call search with empty TransactionSearchCriteria (no dateFrom, no dateTo) and assert only T2 and T3 are returned. • Test sort: call with sortField=PAYOUT_AMOUNT sortDirection=DESC; assert rows sorted descending by target_payout. • Test sort: call with sortField=PARTNER sortDirection=ASC; assert rows sorted by partner.name ascending. | TransactionRepositoryImplTest with default-date-range and sort-mapping integration tests | • Default date range test: T1 (now-30h) is excluded; T2 and T3 are returned. • Result page totalCount=2 for default range test. • PAYOUT_AMOUNT DESC test: row with highest target_payout is first. • PARTNER ASC test: rows in alphabetical order by partner name. • Tests run against real SQL (H2 or Testcontainers) — no mocked query builder. | 50 | 10.6-T03 | FS | PRD-07
10.6-T19 | admin-ui | 10.6 | 10. Admin System | Transaction monitoring | 2 | Unit tests — RBAC pool value masking in detail response | WBS 10.6. ADMIN_VIEWER role sees the transaction detail but collection_margin_usd and payout_margin_usd must be null (masked). All other roles receive full values. Test the RoleAwareTransactionDetailResponse logic. | • Create RoleAwareResponseTest. • Build a TransactionDetailResponse with collection_margin_usd=10.00 and payout_margin_usd=8.00. • Apply role masking for ADMIN_VIEWER; assert both fields are null in the result. • Apply role masking for OPS_ADMIN; assert both fields retain original values. • Apply role masking for FINANCE; assert both fields retain original values. • Apply role masking for OPS_VIEWER; assert both fields retain original values. | RoleAwareResponseTest with 4 test cases covering all roles | • ADMIN_VIEWER test: collection_margin_usd=null, payout_margin_usd=null. • OPS_ADMIN test: collection_margin_usd=10.00, payout_margin_usd=8.00 (unmasked). • FINANCE test: values unmasked. • OPS_VIEWER test: values unmasked. • No other fields are inadvertently nulled by masking logic for any role. | 25 | 10.6-T06 | FS | PRD-07
10.6-T20 | admin-ui | 10.6 | 10. Admin System | Transaction monitoring | 2 | Integration test — transaction search endpoint with filter combinations | WBS 10.6. End-to-end Spring MockMvc integration test for GET /admin/v1/transactions. Uses a test database seeded with known rows covering multiple partners, statuses, and date ranges. Verifies HTTP contract including pagination headers and filter correctness. | • Create TransactionSearchControllerIT using @SpringBootTest + MockMvc. • Seed: 5 APPROVED rows for partner SendMN, 3 FAILED rows for partner T-Bank, 2 UNCERTAIN rows for SendMN, all within last 7 days; 1 row 10 days ago. • Test 1: filter partner=SendMN status=APPROVED -> expect 5 rows, HTTP 200. • Test 2: filter partner=SendMN status=APPROVED dateFrom=now-7d dateTo=now -> expect 5 rows (old row excluded). • Test 3: filter failureOrigin=REQUEST -> expect only rows with failure_origin=REQUEST. • Test 4: invalid date range (104 days) -> HTTP 400 with error body. • Test 5: no auth header -> HTTP 401. | TransactionSearchControllerIT with 5 integration test scenarios | • Test 1 returns HTTP 200, data array size=5, totalCount=5. • Test 2 excludes the 10-day-old row. • Test 3 returns only rows with failureOrigin=REQUEST. • Test 4 returns HTTP 400 with field error referencing the date range constraint. • Test 5 returns HTTP 401. | 55 | 10.6-T04, 10.6-T13 | FS | PRD-07
10.6-T21 | admin-ui | 10.6 | 10. Admin System | Transaction monitoring | 2 | Integration test — transaction detail endpoint for cross-border and same-currency transactions | WBS 10.6. End-to-end MockMvc test for GET /admin/v1/transactions/{hubTxnRef} covering: (a) cross-border txn with full 8-step trail, (b) same-ccy txn with pool N/A, (c) OVERSEAS txn with prefunding entry, (d) LOCAL txn with absent step 2, (e) not-found hub ref. | • Create TransactionDetailControllerIT with @SpringBootTest + MockMvc. • Seed a cross-border APPROVED txn (SendMN, KRW payout) with all 8 event rows and a prefunding ledger entry. • Seed a same-ccy APPROVED txn (GME Remit, KRW) with is_same_ccy_shortcircuit=true. • Test A: GET cross-border txn -> HTTP 200, eventTrail has 8 entries, step 2 present, payout_usd_cost non-null, poolIdentityOk=true. • Test B: GET same-ccy txn -> HTTP 200, sameCcyShortCircuit=true, collection_usd=null, prefundingEntry=null (LOCAL). • Test C: GET non-existent hub_txn_ref -> HTTP 404. • Test D: GET cross-border txn with role=ADMIN_VIEWER -> HTTP 200 but collection_margin_usd=null. | TransactionDetailControllerIT with 4 integration test scenarios | • Test A: response body eventTrail[1].absent=false (step 2 present for OVERSEAS); prefundingEntry non-null. • Test B: response body sameCcyShortCircuit=true, collection_usd field is null or absent. • Test C: HTTP 404 response. • Test D: collection_margin_usd=null in response body. • All 4 tests pass in CI. | 55 | 10.6-T08, 10.6-T14 | FS | PRD-07
10.6-T22 | admin-ui | 10.6 | 10. Admin System | Transaction monitoring | 2 | Frontend: Transaction search page — filter panel component | WBS 10.6. Admin System frontend (React/TypeScript). Build the filter panel for the Transaction Monitoring search page. Filters from PRD-07 §8.2: Partner (multi-select), QR Scheme (multi-select), Direction (multi-select: INBOUND/OUTBOUND/DOMESTIC/HUB), Status (multi-select, chips loaded from GET /admin/v1/transactions/status-values), Date Range picker (default last 24h, max 90 days), Transaction ID (text, exact), Partner Transaction Ref (text), Merchant ID (text, partial), Failure Origin (select), Failure Code (text), Payout Amount range (from/to). Include an Apply Filters and Reset button. | • Create TxnFilterPanel component with controlled form state (React Hook Form or useState). • Render multi-select dropdowns for Partner, Scheme, Direction, Status; load Status options from /admin/v1/transactions/status-values on mount. • Render DateRangePicker with default=[now-24h, now] and max-span validation of 90 days; show inline error if exceeded. • Render text inputs for Transaction ID, Partner Txn Ref, Merchant ID, Failure Code; single select for Failure Origin. • Render numeric inputs for payout amount from/to; validate from <= to. • On Apply, emit onFilterChange(criteria) callback with the current filter values. • On Reset, restore all fields to defaults. | TxnFilterPanel React component with all 10 filter dimensions, validation, and onFilterChange callback | • Setting date range > 90 days shows inline error message and disables Apply button. • Resetting clears all fields and date range returns to default last-24h. • Status multi-select chips are populated from the /status-values API response on mount. • Setting payoutAmountFrom > payoutAmountTo shows inline error. • onFilterChange is called with a correctly-typed criteria object matching the backend DTO shape when Apply is clicked. | 55 | 10.6-T12 | FS | PRD-07
10.6-T23 | admin-ui | 10.6 | 10. Admin System | Transaction monitoring | 2 | Frontend: Transaction list table component with pagination and sort | WBS 10.6. Admin System frontend. Build the TxnListTable component that renders the search results from GET /admin/v1/transactions. Columns (PRD-07 §8.3): Hub Txn Ref (clickable link), Timestamp (UTC), Partner, Scheme, Direction, Mode, Payout Amount, Collection Amount, Service Charge, Status (colored chip), Duration. Pagination: 50 rows/page with page controls. Sort: clicking column headers for Timestamp, Payout Amount, Partner, Status toggles ASC/DESC and re-fetches. | • Create TxnListTable component accepting props: data (TransactionSummary[]), totalCount, page, pageSize, onPageChange, onSortChange. • Render table with 11 columns; Hub Txn Ref column renders as a link navigating to /admin/transactions/{hubTxnRef}. • Status column renders as a colored chip using colorHint from TransactionStatus enum (green/amber/red/grey/blue). • Clicking sortable column header calls onSortChange(field, direction). • Render pagination controls showing page X of Y; Prev/Next buttons. • Show empty state message when data is empty. | TxnListTable React component with 11 columns, sort headers, pagination controls, and status chips | • Hub Txn Ref column renders as an anchor tag with href=/admin/transactions/{hubTxnRef}. • Clicking Timestamp column header first time emits onSortChange('TIMESTAMP','ASC'); second click emits onSortChange('TIMESTAMP','DESC'). • Status chip for APPROVED renders with green background; UNCERTAIN with amber; FAILED with red. • When data=[] renders empty state message (not an empty table with no rows). • Pagination shows correct page label and Prev disabled on page 0. | 45 | 10.6-T22 | FS | PRD-07
10.6-T24 | admin-ui | 10.6 | 10. Admin System | Transaction monitoring | 2 | Frontend: Transaction search page — wire filter panel + list table + export button | WBS 10.6. Admin System frontend. Compose TxnFilterPanel and TxnListTable on the /admin/transactions route. On Apply Filters, call GET /admin/v1/transactions with the filter criteria + page=0 + default sort. On page change or sort change, re-fetch with updated params. Export button calls GET /admin/v1/transactions/export with same filters and triggers file download. Show loading spinner during fetch; show error banner on API error. | • Create TransactionSearchPage component at route /admin/transactions. • Hold state: criteria, page, sortField, sortDirection; initialize page=0, sort=TIMESTAMP DESC, criteria=defaults. • On TxnFilterPanel.onFilterChange: reset page to 0 and update criteria state. • useEffect triggers GET /admin/v1/transactions whenever criteria, page, or sort changes; set loading=true before fetch. • Pass result data to TxnListTable; pass totalCount for pagination. • Export button: GET /admin/v1/transactions/export with current criteria; set response as blob and trigger download with filename from Content-Disposition header. • Show error banner when API returns 4xx/5xx. | TransactionSearchPage React page component wiring filter, table, pagination, sort, and CSV export | • Applying a filter resets page to 0 and triggers a new fetch with the filter params. • Changing page from 0 to 1 triggers fetch with page=1 using the same filter criteria. • Clicking Export triggers a file download with filename matching gmepay_txns_{from}_{to}.csv pattern. • A 400 response from the API displays a visible error banner (not a blank page or unhandled exception). • Loading spinner is visible between filter apply and data render. | 55 | 10.6-T23 | FS | PRD-07
10.6-T25 | admin-ui | 10.6 | 10. Admin System | Transaction monitoring | 2 | Frontend: Transaction detail page — identity/metadata and locked rate panel | WBS 10.6. Admin System frontend. Build the TransactionDetailPage at route /admin/transactions/:hubTxnRef. Section 1: Identity and Metadata (PRD-07 §8.5.1): Hub Txn Ref, Partner Txn Ref, Partner name, Scheme name, Direction, Mode, Merchant ID/Name, Timestamp UTC+KST, Current Status chip. Section 2: Locked Rate and Pool Values (PRD-07 §8.5.2): display all 15 fields as a read-only table; for same-currency txns show N/A with note 'Same-currency short-circuit applied'; show poolIdentityOk warning banner if poolIdentityOk=false. | • Create TransactionDetailPage fetching GET /admin/v1/transactions/:hubTxnRef on mount; handle 404 (show not-found page) and loading. • Render IdentitySection with all §8.5.1 fields; format timestamps as 'YYYY-MM-DD HH:mm:ss UTC / KST' side by side. • Render RatePoolPanel as a two-column table: field label ¦ value; for same-ccy rows show 'N/A' with tooltip. • If poolIdentityOk=false render a yellow warning banner: 'Pool identity check failed: delta = {poolIdentityDelta} USD. Ops investigation required.' • Mask collection_margin_usd and payout_margin_usd rows when response values are null (ADMIN_VIEWER) by showing '—' instead. | TransactionDetailPage React page with identity section and rate/pool panel including pool-identity warning | • For a cross-border txn all 15 rate/pool rows are populated with numeric values. • For a same-ccy txn, payout_usd_cost row shows 'N/A' and a note 'Same-currency short-circuit applied' is visible. • When poolIdentityOk=false a yellow warning banner is visible with the delta value. • When poolIdentityOk=true no warning banner is shown. • When collection_margin_usd is null in the response (ADMIN_VIEWER), that row shows a dash rather than null/undefined. | 55 | 10.6-T24 | FS | PRD-07
10.6-T26 | admin-ui | 10.6 | 10. Admin System | Transaction monitoring | 2 | Frontend: Transaction detail page — 8-step event trail timeline | WBS 10.6. Admin System frontend. Render the event trail section of TransactionDetailPage as a vertical numbered timeline (PRD-07 §8.5.3). Each step shows: step number, event type label, occurred_at (UTC), duration since previous step (ms), and detail payload (expandable JSON). Absent steps are grayed out with the absentReason text. Steps with failures (eventType contains FAILED or detail.failureCode present) are highlighted in red. | • Create EventTrailTimeline component accepting eventTrail: EventTrailStep[]. • Render 8 step slots in order 1-8; for present steps render the full row; for absent steps render grayed row with step number, name, and absentReason. • For step 1, show durationMs as '—'; for others show '{durationMs} ms' or '—' if null. • If step has detail payload, render an expandable Disclosure/Accordion with JSON viewer. • Highlight step row red if detail.failureCode is present or eventType ends in _FAILED or _DECLINED. • If resolvedFromUncertain=true in the page-level response, show a banner above the trail: 'This transaction was previously UNCERTAIN and was resolved via batch reconciliation.' | EventTrailTimeline React component with 8-step vertical timeline, absent-step graying, failure highlighting, and UNCERTAIN-resolution banner | • Step 2 with absent=true renders grayed with absentReason text visible. • Step 1 shows duration as dash. • Step 3 with durationMs=150 shows '150 ms'. • A step with detail.failureCode='INSUFFICIENT_PREFUNDING' renders with red highlight. • resolvedFromUncertain=true displays the UNCERTAIN resolution banner above the timeline. | 50 | 10.6-T25 | FS | PRD-07
10.6-T27 | admin-ui | 10.6 | 10. Admin System | Transaction monitoring | 2 | Frontend: Transaction detail page — prefunding entry and settlement linkage sections | WBS 10.6. Admin System frontend. PRD-07 §8.5.4: For OVERSEAS partners, show prefunding deduction entry: balance before, deduction amount (USD), balance after. PRD-07 §8.5.5: Show settlement linkage — which ZeroPay batch files (ZP0011/ZP0061/ZP0065) included this transaction, with batch date and registration result. If prefundingEntry is null (LOCAL partner) show the section header with a note 'Not applicable: LOCAL partner has no prefunding account'. If settlementLinkage is empty show 'Not yet included in a settlement batch'. | • Create PrefundingEntryPanel component: if prefundingEntry non-null render 3-row table (balanceBefore, deductionAmountUsd, balanceAfter in USD); else render not-applicable note. • Create SettlementLinkagePanel component: if settlementLinkage non-empty render table with columns: File Type, Batch Date, File Ref, Registration Result; else render pending note. • Format all USD values with 2 decimal places and 'USD' prefix. • Integrate both panels into TransactionDetailPage below the event trail section. | PrefundingEntryPanel and SettlementLinkagePanel React components integrated into TransactionDetailPage | • For OVERSEAS txn with prefundingEntry: panel shows balanceBefore=10000.00 USD, deductionAmountUsd=150.00 USD, balanceAfter=9850.00 USD. • For LOCAL txn (prefundingEntry=null): panel shows 'Not applicable: LOCAL partner has no prefunding account'. • For txn with settlementLinkage=[{fileType:'ZP0011', batchDate:'2025-05-01', fileRef:'ZP0011_20250501', result:'REGISTERED'}]: panel shows one row with those values. • For txn with empty settlementLinkage: panel shows 'Not yet included in a settlement batch'. • USD amounts formatted to 2 decimal places with USD prefix. | 40 | 10.6-T26 | FS | PRD-07
10.6-T28 | admin-ui | 10.6 | 10. Admin System | Transaction monitoring | 2 | Backend: Add settlement_txn_link table migration for settlement linkage in detail view | WBS 10.6. PRD-07 §8.5.5 requires showing which ZeroPay settlement batch files included a given transaction. This requires a junction table settlement_txn_link: id (BIGINT PK), txn_id (BIGINT FK transaction), file_type (VARCHAR(10), e.g. ZP0011/ZP0061/ZP0065), batch_date (DATE), file_ref (VARCHAR(100)), registration_result (VARCHAR(20): REGISTERED/REJECTED/PENDING), created_at (TIMESTAMPTZ). Add the migration and corresponding JPA entity. | • Create migration V10_6_004__settlement_txn_link.sql with the table DDL and FK constraint to transaction. • Add index on (txn_id) for fast detail-page lookup. • Create SettlementTxnLink JPA entity in com.gmepayplus.settlement.domain. • Add OneToMany from Transaction to SettlementTxnLink (lazy fetch). • Expose settlementLinkage list in TransactionDetailService by fetching SettlementTxnLink rows where txn_id matches. | Migration V10_6_004__settlement_txn_link.sql and SettlementTxnLink JPA entity with index on txn_id | • Migration applies cleanly; table exists with correct columns and FK constraint. • Inserting a row with txn_id pointing to a non-existent transaction raises FK violation. • EXPLAIN SELECT * FROM settlement_txn_link WHERE txn_id=42 uses index scan. • TransactionDetailService.getDetail() populates settlementLinkage list from the new table. • TransactionDetailResponse.settlementLinkage is a non-null list (empty list if no rows). | 35 | 10.6-T07 | FS | PRD-07
10.6-T29 | admin-ui | 10.6 | 10. Admin System | Transaction monitoring | 2 | Backend: Audit log entry for transaction detail view access | WBS 10.6. Every time an Ops/Finance/Admin user opens a transaction detail page, the action must be audit-logged (PRD-07 §12 and SEC-09 non-repudiation requirement). Audit entry fields: actor (hub_user email), action=TXN_DETAIL_VIEWED, entity_type=TRANSACTION, entity_ref=hub_txn_ref, occurred_at, ip_address (from request). Write to the existing audit_log table (schema from DAT-03/SEC-09: id, actor, action, entity_type, entity_ref, occurred_at, ip_address, detail JSONB). | • Verify audit_log table has columns: id, actor, action, entity_type, entity_ref, occurred_at, ip_address, detail. • In TransactionDetailService or as a Spring AOP @AfterReturning aspect on the controller method, create and persist an AuditLogEntry with action=TXN_DETAIL_VIEWED after successful retrieval. • Extract IP address from HttpServletRequest (use X-Forwarded-For header first, fallback to remoteAddr). • Ensure audit write is in a separate transaction (REQUIRES_NEW) so that a detail-load failure does not roll back the audit entry. • Unit test: mock auditLogRepository; call getDetail; verify auditLogRepository.save called once with correct action and entityRef. | Audit logging for TXN_DETAIL_VIEWED events in a separate transaction with IP capture | • Calling getDetail('HUB-001', role) inserts one audit_log row with action=TXN_DETAIL_VIEWED and entity_ref=HUB-001. • Audit entry is committed even if the detail response serialization throws an exception (separate transaction). • ip_address field is populated from X-Forwarded-For header when present. • ip_address falls back to remoteAddr when X-Forwarded-For is absent. • audit_log rows cannot be deleted via any service method (no delete method exposed on AuditLogRepository). | 40 | 10.6-T08 | FS | PRD-07
10.6-T30 | admin-ui | 10.6 | 10. Admin System | Transaction monitoring | 2 | Backend: Endpoint and query performance test — search returns <= 2s for typical filter | WBS 10.6. PRD-07 §15.5 acceptance criterion: transaction search by Partner=SendMN, Status=APPROVED, last 7 days returns correct result set within 2 seconds. Write a JMH micro-benchmark or a Testcontainers-based timing test against a dataset of 100,000 transaction rows with representative distribution. | • Set up a Testcontainers PostgreSQL instance with a Flyway migration + seed script generating 100,000 transaction rows (Python or SQL loop): mix of partners, statuses, dates. • Run TransactionRepository.search with criteria: partnerId=<SendMN id>, status=[APPROVED], dateFrom=now-7d, dateTo=now. • Assert p50 query time <= 500ms and p99 <= 2000ms (measure 10 runs). • Run with EXPLAIN ANALYZE and assert index scan (not seq scan) is used on the (status, committed_at) index. • Document results in a test comment. | Performance integration test asserting p99 <= 2000ms for the standard search scenario against 100k rows | • Test seed inserts 100,000 rows without error. • p50 query time <= 500ms across 10 runs. • p99 query time <= 2000ms across 10 runs. • EXPLAIN ANALYZE output shows Index Scan on the (status, committed_at) composite index. • Test is tagged @Tag('performance') and excluded from default CI (runs on demand / nightly). | 55 | 10.6-T03, 10.6-T11 | FS | PRD-07
10.6-T31 | admin-ui | 10.6 | 10. Admin System | Transaction monitoring | 2 | Frontend: Transaction detail page — Cancel and Refund action buttons (conditional display) | WBS 10.6. The transaction detail page must show action buttons based on transaction state and user role, per PRD-07 §10. Cancel button: visible when status is COMMITTED or SUBMITTED_TO_SCHEME and the role is OPS_ADMIN or SUPER_ADMIN. Refund button: visible when status is APPROVED or SCHEME_APPROVED and role is OPS_ADMIN or SUPER_ADMIN. Clicking either opens a confirmation dialog (implementation of the dialog is a separate ticket for WBS 10.7/10.8 — this ticket only adds the buttons with correct visibility logic). Buttons are absent (not disabled) when conditions are not met. | • In TransactionDetailPage, receive callerRole from auth context. • Compute canCancel: status in ['COMMITTED','SUBMITTED_TO_SCHEME'] AND role in ['OPS_ADMIN','SUPER_ADMIN']. • Compute canRefund: status in ['APPROVED','SCHEME_APPROVED'] AND role in ['OPS_ADMIN','SUPER_ADMIN']. • Render Cancel button only when canCancel=true; Refund button only when canRefund=true. • Clicking Cancel or Refund calls a passed onCancelClick or onRefundClick callback (no dialog implemented here). • Unit test: assert button visibility for 5 combinations of status and role. | Conditional Cancel/Refund button logic in TransactionDetailPage with unit tests for 5 role-status combinations | • status=COMMITTED, role=OPS_ADMIN: Cancel visible, Refund not rendered. • status=APPROVED, role=OPS_ADMIN: Refund visible, Cancel not rendered. • status=FAILED, role=OPS_ADMIN: neither button rendered. • status=COMMITTED, role=FINANCE: neither button rendered (Finance cannot cancel). • status=APPROVED, role=SUPER_ADMIN: Refund visible. | 35 | 10.6-T25 | FS | PRD-07
10.6-T32 | admin-ui | 10.6 | 10. Admin System | Transaction monitoring | 2 | Docs: OpenAPI spec for /admin/v1/transactions search and detail endpoints | WBS 10.6. Add OpenAPI 3.0 annotations (or YAML) for the two transaction monitoring endpoints: GET /admin/v1/transactions (search) and GET /admin/v1/transactions/{hubTxnRef} (detail). Document all query parameters with types and constraints, all response schemas referencing TransactionListResponse and TransactionDetailResponse, error responses (400, 401, 403, 404), and the RBAC role requirement in the security section. | • Add @Operation, @Parameter, and @ApiResponse annotations to TransactionController search and detail methods (if using springdoc-openapi). • Document each query parameter with description, required flag, example value, and constraint (e.g. dateFrom: date-time, example: 2025-05-01T00:00:00Z). • Document TransactionListResponse and TransactionDetailResponse schemas inline or via $ref. • Document 400 error response with ConstraintViolationProblem schema; 404 with ProblemDetail schema. • Verify generated Swagger UI shows correct schema at /v3/api-docs. | OpenAPI annotations/YAML for /admin/v1/transactions and /admin/v1/transactions/{hubTxnRef} visible in Swagger UI | • GET /admin/v1/transactions in Swagger UI shows all 13 query parameters with descriptions. • TransactionDetailResponse schema in Swagger UI includes eventTrail array with EventTrailStep fields. • 400 response documented with ConstraintViolationProblem example. • /v3/api-docs endpoint returns valid JSON with no schema validation errors (run openapi-validator). • Security requirement 'bearerAuth' is listed for both endpoints. | 40 | 10.6-T08 | FS | PRD-07
10.7-T01 | admin-ui | 10.7 | 10. Admin System | Prefunding management UI | 2 | Create DB migration: prefunding_account table | GMEPay+ prefunds OVERSEAS partners only. Table prefunding_account stores one row per OVERSEAS partner: id BIGINT PK, partner_id BIGINT FK->partner UNIQUE, currency CHAR(3) always USD, balance DECIMAL(20,4) current balance updated atomically, low_balance_threshold DECIMAL(20,4) default 10000.00, created_at/updated_at/created_by/updated_by. Balance updates MUST use SELECT FOR UPDATE - no app-level locking. LOCAL partners (e.g. GME Remit) never have a row here. | • Write Flyway/Liquibase migration file V10_7_001__create_prefunding_account.sql • Add columns as specified; set NOT NULL constraints on all required fields • Add UNIQUE constraint on partner_id • Add DEFAULT 10000.00 on low_balance_threshold • Add CHECK constraint: balance >= 0 and low_balance_threshold > 0 • Run migration on dev DB; confirm schema with \d prefunding_account | Migration file V10_7_001__create_prefunding_account.sql applied successfully to dev DB | • Table exists with all 9 columns at correct types after migration runs • UNIQUE constraint on partner_id rejects a second insert for the same partner • Inserting balance = -1.00 is rejected by CHECK constraint • Inserting low_balance_threshold = 0 is rejected by CHECK constraint • Default value of low_balance_threshold is 10000.0000 when not supplied | 25 |  | FS | PRD-07
10.7-T02 | admin-ui | 10.7 | 10. Admin System | Prefunding management UI | 2 | Create DB migration: prefunding_ledger_entry table | prefunding_ledger_entry is append-only; every debit or credit creates one immutable row. Columns: id BIGINT PK, account_id BIGINT FK->prefunding_account, txn_ref VARCHAR(64) nullable (transaction.txn_ref for debits; internal ref for top-ups), entry_type VARCHAR(20) values DEBIT_PAYMENT/DEBIT_REVERSAL/CREDIT_TOPUP/CREDIT_REVERSAL/CREDIT_ADJUSTMENT, amount DECIMAL(20,4) always positive (direction conveyed by entry_type), balance_after DECIMAL(20,4) running balance snapshot, note VARCHAR(255), created_at TIMESTAMPTZ immutable (no updated_at), created_by VARCHAR(120). Index on (account_id, created_at) for history queries. No UPDATE or DELETE permitted via app service account. | • Write migration V10_7_002__create_prefunding_ledger_entry.sql • Define all columns with correct nullability; entry_type as VARCHAR(20) with CHECK IN list • Add index on (account_id, created_at) • Add CHECK constraint: amount > 0 • Confirm no updated_at column exists • Grant INSERT-only privilege to app service account; revoke UPDATE/DELETE | Migration file V10_7_002__create_prefunding_ledger_entry.sql applied; app account has INSERT-only on this table | • All 10 columns present at correct types after migration • INSERT with amount = 0 is rejected by CHECK constraint • INSERT with entry_type = INVALID_TYPE is rejected by CHECK constraint • UPDATE on any row returns permission denied for app service account • Index idx_prefunding_ledger_entry_account_date exists on (account_id, created_at) | 25 | 10.7-T01 | FS | PRD-07
10.7-T03 | admin-ui | 10.7 | 10. Admin System | Prefunding management UI | 2 | Create DB migration: low_balance_alert_config table | low_balance_alert_config stores per-partner alert settings for OVERSEAS partners. Columns: id BIGINT PK, partner_id BIGINT FK->partner UNIQUE, threshold_usd DECIMAL(20,4) default 10000.00, alert_email VARCHAR(255) partner contact email (comma-separated for multiple recipients per PRD-07 §5.3.3), is_active BOOLEAN default true, created_at/updated_at/created_by/updated_by. Separate from prefunding_account.low_balance_threshold to allow independent alert config management. A partner may have only one alert config row (UNIQUE on partner_id). | • Write migration V10_7_003__create_low_balance_alert_config.sql • Add all columns with NOT NULL on required fields • Add UNIQUE on partner_id • Add CHECK: threshold_usd > 0 • Insert default row automatically via trigger or handle in service layer (document choice) | Migration file V10_7_003__create_low_balance_alert_config.sql applied to dev DB | • Table exists with all 8 columns after migration • UNIQUE constraint on partner_id prevents duplicate rows for same partner • Inserting threshold_usd = 0 is rejected • alert_email column accepts multiple addresses separated by commas (at least 255 chars wide) • is_active defaults to TRUE when not supplied | 20 | 10.7-T01 | FS | PRD-07
10.7-T04 | admin-ui | 10.7 | 10. Admin System | Prefunding management UI | 2 | Implement PrefundingAccountRepository with atomic balance update | OVERSEAS partner prefunding balance must be updated atomically using SELECT FOR UPDATE. Repository targets prefunding_account table. Key operations: findByPartnerId(partnerId) returning Optional<PrefundingAccount>; deductBalance(accountId, amount) using SELECT FOR UPDATE inside a transaction - must fail with InsufficientBalanceException if balance - amount < 0; creditBalance(accountId, amount) for top-ups. Use DECIMAL types throughout - never double/float. All methods annotated @Transactional where needed. | • Create entity class PrefundingAccount mapping prefunding_account table • Create PrefundingAccountRepository (JPA or JDBC; your choice - document) • Implement deductBalance using native query SELECT ... FOR UPDATE then UPDATE; throw InsufficientBalanceException if resulting balance < 0 • Implement creditBalance for CREDIT_TOPUP and CREDIT_REVERSAL ops • Write integration test against real Postgres (testcontainers) confirming atomic deduction under 2 concurrent threads - only one should succeed when balance = exactly 1 deduction amount | PrefundingAccountRepository class with deductBalance, creditBalance, findByPartnerId methods; integration test passing | • deductBalance(accountId=1, amount=100.00) on account with balance=100.00 sets balance to 0.0000 and returns updated entity • deductBalance(accountId=1, amount=100.01) on account with balance=100.00 throws InsufficientBalanceException without mutating the row • Two concurrent threads both calling deductBalance for 100.00 on a 100.00-balance account: only one succeeds, one throws InsufficientBalanceException; final balance = 0 • creditBalance(accountId=1, amount=50000.00) increases balance by 50000.00 and returns new total • All money fields use DECIMAL(20,4) / BigDecimal; no double/float anywhere in the call chain | 45 | 10.7-T01 | FS | PRD-07
10.7-T05 | admin-ui | 10.7 | 10. Admin System | Prefunding management UI | 2 | Implement PrefundingLedgerEntryRepository and ledger append service | prefunding_ledger_entry is append-only. Every balance change must create a corresponding ledger entry atomically in the same transaction as the balance update. Entry types: DEBIT_PAYMENT (payment deduction), DEBIT_REVERSAL (cancellation reversal), CREDIT_TOPUP (manual top-up), CREDIT_REVERSAL (refund confirmed), CREDIT_ADJUSTMENT (manual correction). Each entry records amount (always positive), balance_after (running balance snapshot), txn_ref (nullable), note, created_by. | • Create PrefundingLedgerEntry entity and repository with insertEntry method • Create LedgerAppendService with methods: appendDebit(accountId, amount, balanceAfter, txnRef, createdBy), appendCredit(accountId, entryType, amount, balanceAfter, ref, note, createdBy) • Ensure both deductBalance in T04 and creditBalance call appendEntry in the same @Transactional scope • Create findByAccountIdOrderByCreatedAtDesc(accountId, Pageable) for the ledger view | PrefundingLedgerEntryRepository and LedgerAppendService; all balance changes produce a matching ledger row | • After a deductBalance call for USD 120.50, exactly one DEBIT_PAYMENT ledger entry exists with amount=120.5000 and balance_after equal to the new balance • After a creditBalance (CREDIT_TOPUP) call for USD 50000.00, ledger row has entry_type=CREDIT_TOPUP, amount=50000.0000 • If the DB transaction rolls back, no ledger entry is persisted (atomicity check) • findByAccountIdOrderByCreatedAtDesc returns entries newest-first with correct pagination • balance_after in each ledger entry matches the sequence of running balance: e.g. start 200.00, deduct 50.00 -> entry balance_after=150.0000, deduct 30.00 -> entry balance_after=120.0000 | 40 | 10.7-T04 | FS | PRD-07
10.7-T06 | admin-ui | 10.7 | 10. Admin System | Prefunding management UI | 2 | Implement TopUpRecordingService - record manual top-up with audit log | Ops records a top-up when a partner wire arrives. Fields from PRD-07 §9.3: partner_id, top_up_amount_usd (Decimal USD > 0), bank_ref (required text), value_date (date funds received), notes (optional). The service must: (1) call creditBalance atomically, (2) append a CREDIT_TOPUP ledger entry, (3) write an audit log entry with actor, timestamp, entity_type=prefunding_account, event_type=prefunding.topup_recorded, previous_balance, new_balance. RBAC: only OPS_OPERATOR and SUPER_ADMIN may call this endpoint. LOCAL partners must be rejected. | • Create TopUpRequest DTO with fields: partnerId, amountUsd BigDecimal, bankRef String, valueDate LocalDate, notes String • Create TopUpRecordingService.recordTopUp(TopUpRequest, actorUserId) with @Transactional • Validate: partner exists, partner type = OVERSEAS, amountUsd > 0, bankRef not blank • Call PrefundingAccountRepository.creditBalance then LedgerAppendService.appendCredit in same transaction • Write audit log entry via AuditLogService • Return TopUpResult with ledger entry id, new balance, timestamp | TopUpRecordingService with recordTopUp method; audit entry written on each call | • recordTopUp for SendMN (OVERSEAS) with amountUsd=50000.00 increases displayed balance by 50000.00 immediately • Calling recordTopUp on GME Remit (LOCAL partner) throws PartnerTypeException with message indicating prefunding not applicable • recordTopUp with amountUsd=0 throws ValidationException • Audit log entry exists with event_type=prefunding.topup_recorded, previous_balance and new_balance populated correctly • If creditBalance fails, no audit entry and no ledger entry are persisted (rollback) | 40 | 10.7-T05 | FS | PRD-07
10.7-T07 | admin-ui | 10.7 | 10. Admin System | Prefunding management UI | 2 | Implement ManualAdjustmentService - Finance-initiated balance corrections | Finance Analyst (FINANCE_ANALYST role) or SUPER_ADMIN can create manual ADJUSTMENT entries to correct recording errors (PRD-07 §9.4). Fields: partner_id, adjustment_amount_usd (positive or negative decimal), reason (mandatory text >= 10 chars), entry_type always CREDIT_ADJUSTMENT for positive or a separate DEBIT_ADJUSTMENT type for negative. The resulting balance must never go below 0 - negative adjustments that would cause negative balance must be rejected. All adjustments are audit-logged. OPS_OPERATOR cannot create adjustments per permission matrix (§12.3). | • Create AdjustmentRequest DTO: partnerId, adjustmentAmountUsd BigDecimal, reason String • Create ManualAdjustmentService.applyAdjustment(AdjustmentRequest, actorUserId) • Enforce RBAC: reject if caller role is OPS_OPERATOR • Validate: reason length >= 10 chars, adjustmentAmountUsd != 0 • Load account with SELECT FOR UPDATE; check resulting balance >= 0 before applying • Append ledger entry CREDIT_ADJUSTMENT (positive) or DEBIT_ADJUSTMENT (negative); write audit log | ManualAdjustmentService.applyAdjustment with RBAC, validation, atomic balance update, and audit entry | • FINANCE_ANALYST applies adjustment of +1000.00 on account with balance 5000.00; new balance is 6000.0000 with CREDIT_ADJUSTMENT ledger entry • OPS_OPERATOR calling applyAdjustment receives 403 / AccessDeniedException • Negative adjustment of -6000.00 on account with balance 5000.00 is rejected with error indicating insufficient balance • reason of 5 chars is rejected with ValidationException • Audit log entry includes previous_balance, new_balance, reason text, and actor ID | 35 | 10.7-T05 | FS | PRD-07
10.7-T08 | admin-ui | 10.7 | 10. Admin System | Prefunding management UI | 2 | Implement LowBalanceAlertService - post-deduction alert logic | After each successful deduction, the system checks if the new balance < low_balance_threshold (from prefunding_account). If so, it sends an email alert to all addresses in low_balance_alert_config.alert_email for that partner. Alert content per PRD-07 §9.5: partner name, current balance, threshold, suggested top-up amount (= threshold * 2 - current_balance). A second URGENT alert fires when balance reaches USD 0.00 or below (which should only occur via adjustment, not payment since deductBalance prevents negative balances). Alerts do NOT block transactions. | • Create LowBalanceAlertService.checkAndAlert(partnerId, newBalanceUsd) - called after every deductBalance • Load low_balance_alert_config for partner; if is_active = false, skip • If newBalanceUsd < threshold_usd and previous balance was >= threshold_usd, send LOW_BALANCE email to all recipients in alert_email (split on comma) • If newBalanceUsd <= 0, send URGENT_ZERO_BALANCE email and post in-portal dashboard alert via DashboardAlertService • Email subject and body must include: partner name, current balance USD, threshold USD, suggested top-up = max(threshold*2 - newBalance, threshold) • Write audit log entry with event_type=prefunding.low_balance_alert_triggered | LowBalanceAlertService.checkAndAlert integrated into deduction flow; email sent when crossing threshold | • Deduction taking SendMN balance from 12000.00 to 8500.00 (threshold=10000.00) sends exactly one LOW_BALANCE email to all configured recipients • Deduction taking balance from 8000.00 to 7000.00 (already below threshold) does NOT send a duplicate alert (only fires on crossing, not every deduction while below) • Deduction to exactly 0.00 triggers URGENT_ZERO_BALANCE email in addition to or instead of normal LOW_BALANCE email • Alert email body contains: partner name, current balance 8500.00 USD, threshold 10000.00 USD, suggested top-up amount • If alert_config.is_active = false, no email is sent after deduction below threshold | 40 | 10.7-T05, 10.7-T03 | FS | PRD-07
10.7-T09 | admin-ui | 10.7 | 10. Admin System | Prefunding management UI | 2 | Implement PrefundingDashboardService - real-time balance summary per partner | The Prefunding Dashboard (PRD-07 §9.2) shows a summary card per OVERSEAS partner: partner name, current balance USD, low_balance_threshold, balance as % of threshold, traffic-light status (GREEN >= 150%, AMBER 100-150%, RED < 100%), last deduction timestamp+amount, last top-up timestamp+amount. Balances must be real-time (no caching - query live DB). Sourced from prefunding_account and last 2 ledger entries by type. | • Create PrefundingDashboardEntry DTO with fields: partnerId, partnerName, balanceUsd, thresholdUsd, balancePct (2dp), trafficLight enum GREEN/AMBER/RED, lastDeductionAt, lastDeductionAmountUsd, lastTopUpAt, lastTopUpAmountUsd • Create PrefundingDashboardService.getDashboardEntries() querying all OVERSEAS partners with their prefunding_account • Compute balancePct = (balance / threshold) * 100; assign trafficLight: >= 150 = GREEN, 100 <= x < 150 = AMBER, < 100 = RED • Fetch last DEBIT_PAYMENT entry and last CREDIT_TOPUP entry per account for last-deduction/top-up fields • Return list sorted by trafficLight severity (RED first, then AMBER, then GREEN) | PrefundingDashboardService.getDashboardEntries() returning real-time DTO list sorted by severity | • Partner with balance=8500.00, threshold=10000.00 returns balancePct=85.00 and trafficLight=RED • Partner with balance=14000.00, threshold=10000.00 returns balancePct=140.00 and trafficLight=AMBER • Partner with balance=18000.00, threshold=10000.00 returns balancePct=180.00 and trafficLight=GREEN • RED entries appear before AMBER before GREEN in returned list • lastDeductionAt and lastDeductionAmountUsd match the most recent DEBIT_PAYMENT entry for that account | 35 | 10.7-T05 | FS | PRD-07
10.7-T10 | admin-ui | 10.7 | 10. Admin System | Prefunding management UI | 2 | Implement PrefundingLedgerQueryService - paginated ledger view with filtering | PRD-07 §9.4 requires a full transaction-level ledger per partner with columns: ledger entry id, timestamp UTC, entry_type (TOPUP/DEDUCTION/ADJUSTMENT/REFUND_REVERSAL), amount, balance_after, hub_txn_ref (for DEBIT_PAYMENT entries), reference (bank ref for TOPUP), recorded_by. Supports pagination (default 50 per page) and filter by entry_type and date range. Note: entry_type display labels differ from DB enum: DEBIT_PAYMENT shows as DEDUCTION, CREDIT_TOPUP shows as TOPUP, CREDIT_ADJUSTMENT/DEBIT_ADJUSTMENT shows as ADJUSTMENT, DEBIT_REVERSAL/CREDIT_REVERSAL shows as REFUND_REVERSAL. | • Create LedgerEntryDTO with all display columns including mapped display_type • Create PrefundingLedgerQueryService.getLedger(partnerId, entryTypeFilter, fromDate, toDate, Pageable) • Map DB entry_type enum to display labels as specified • Join with transaction table on txn_ref to get hub_txn_ref for DEBIT_PAYMENT entries • Return Page<LedgerEntryDTO> ordered by created_at DESC • Validate partnerId is OVERSEAS partner; throw PartnerNotFoundException otherwise | PrefundingLedgerQueryService.getLedger returning paginated, filtered, display-mapped ledger entries | • Query for partnerId=SendMN with no filters returns all entries newest-first, max 50 per page • DEBIT_PAYMENT entry in DB appears in result with display_type=DEDUCTION and hub_txn_ref populated from linked transaction • CREDIT_TOPUP entry appears with display_type=TOPUP and bank reference in reference column • Filter by entry_type=TOPUP returns only CREDIT_TOPUP rows • Date range filter from 2026-06-01 to 2026-06-05 excludes entries outside that window | 35 | 10.7-T05 | FS | PRD-07
10.7-T11 | admin-ui | 10.7 | 10. Admin System | Prefunding management UI | 2 | REST API: GET /admin/v1/prefunding/dashboard - prefunding summary endpoint | Admin API endpoint returning the real-time prefunding dashboard data (PRD-07 §9.2). RBAC: roles OPS_OPERATOR, FINANCE_ANALYST, SUPER_ADMIN may read; ADMIN_VIEWER is not permitted per permission matrix §12.3. Response is an array of summary cards. Must not cache - always reads live DB. Response fields per PrefundingDashboardEntry DTO from T09. | • Create PrefundingController with GET /admin/v1/prefunding/dashboard • Apply @PreAuthorize or role-check for OPS_OPERATOR, FINANCE_ANALYST, SUPER_ADMIN; reject ADMIN_VIEWER with 403 • Call PrefundingDashboardService.getDashboardEntries() • Wrap in standard API envelope {data: [...], meta: {count, as_of: ISO-8601 timestamp}} • Write integration test: 200 with correct payload for authorized role, 403 for ADMIN_VIEWER | GET /admin/v1/prefunding/dashboard endpoint returning real-time summary; integration test passing | • GET with FINANCE_ANALYST JWT returns 200 with array of partner summary objects including trafficLight • GET with ADMIN_VIEWER JWT returns 403 • Response body includes as_of timestamp within 1 second of query time • Partner with balance=8500, threshold=10000 appears in response with trafficLight=RED and balancePct=85.00 • Response time < 500ms with up to 10 OVERSEAS partners in DB | 35 | 10.7-T09 | FS | PRD-07
10.7-T12 | admin-ui | 10.7 | 10. Admin System | Prefunding management UI | 2 | REST API: GET /admin/v1/prefunding/{partnerId}/ledger - ledger pagination endpoint | Admin API endpoint for the paginated prefunding ledger view (PRD-07 §9.4). Supports query params: page (0-indexed), size (default 50, max 200), entryType (optional filter), from (ISO date), to (ISO date). RBAC: OPS_OPERATOR, FINANCE_ANALYST, SUPER_ADMIN allowed; ADMIN_VIEWER not permitted. Response includes entries plus pagination metadata (totalElements, totalPages, currentPage). | • Add GET /admin/v1/prefunding/{partnerId}/ledger to PrefundingController • Validate partnerId path variable; return 404 if partner not found • Apply role check; return 403 for ADMIN_VIEWER • Parse and validate query params; reject size > 200 with 400 • Call PrefundingLedgerQueryService.getLedger with params • Return {data: [LedgerEntryDTO], pagination: {page, size, totalElements, totalPages}} | GET /admin/v1/prefunding/{partnerId}/ledger endpoint with pagination and filtering | • GET /admin/v1/prefunding/prt_sendmn_001/ledger returns 200 with up to 50 entries and pagination metadata • GET with page=0&size=5 returns exactly 5 entries when more than 5 exist • GET with entryType=TOPUP returns only TOPUP entries • GET with unknown partnerId returns 404 • GET with ADMIN_VIEWER JWT returns 403 | 30 | 10.7-T10 | FS | PRD-07
10.7-T13 | admin-ui | 10.7 | 10. Admin System | Prefunding management UI | 2 | REST API: POST /admin/v1/prefunding/{partnerId}/topup - record top-up | Ops records a manual top-up via this endpoint (PRD-07 §9.3). Request body: amountUsd (decimal string, required, > 0), bankRef (string, required), valueDate (ISO date, required), notes (string, optional). RBAC: OPS_OPERATOR and SUPER_ADMIN only. Response: new balance, ledger entry id, timestamp. Idempotency: if the same bankRef is submitted twice for the same partner within 24 hours, return 409 Conflict with the original entry id. | • Add POST /admin/v1/prefunding/{partnerId}/topup to PrefundingController • Apply role check; FINANCE_ANALYST and ADMIN_VIEWER get 403 • Deserialize and validate request body: amountUsd > 0, bankRef not blank, valueDate present and not in future • Check idempotency: if CREDIT_TOPUP ledger entry with same bankRef+partnerId exists within 24h, return 409 with existing entry id • Call TopUpRecordingService.recordTopUp; return 201 with {ledgerEntryId, newBalanceUsd, timestamp} • Integration test covering success, duplicate, and FINANCE_ANALYST 403 cases | POST /admin/v1/prefunding/{partnerId}/topup endpoint with idempotency and RBAC; integration tests passing | • POST with amountUsd=50000.00 and valid bankRef returns 201; balance increases by 50000.00 • Second POST with same bankRef for same partner within 24h returns 409 with original ledger entry id • POST with amountUsd=0 returns 400 with validation error • FINANCE_ANALYST token returns 403 • POST on a LOCAL partner returns 400/422 with error indicating prefunding not applicable to LOCAL partners | 40 | 10.7-T06 | FS | PRD-07
10.7-T14 | admin-ui | 10.7 | 10. Admin System | Prefunding management UI | 2 | REST API: POST /admin/v1/prefunding/{partnerId}/adjustment - manual adjustment | Finance Analyst or Super Admin creates a manual adjustment to correct a recording error (PRD-07 §9.4). Request: adjustmentAmountUsd (decimal, non-zero, positive or negative), reason (string, min 10 chars). Negative adjustment that would cause balance < 0 must be rejected with 422. Requires two-step confirmation per PRD-07 §14.2 UX notes - implement as: first POST returns a preview object (no DB write); client must confirm via POST with confirm=true flag. RBAC: FINANCE_ANALYST and SUPER_ADMIN only; OPS_OPERATOR gets 403. | • Add POST /admin/v1/prefunding/{partnerId}/adjustment to PrefundingController • Apply role check: reject OPS_OPERATOR with 403 • Parse body: adjustmentAmountUsd, reason, confirm (boolean, default false) • If confirm=false: return preview {currentBalance, adjustmentAmount, projectedBalance} with 200, no DB write • If confirm=true: call ManualAdjustmentService.applyAdjustment; return 201 with new balance and ledger entry id • Return 422 if projected balance would be negative (both preview and confirmed paths) | POST /admin/v1/prefunding/{partnerId}/adjustment endpoint with two-step confirmation flow | • POST with confirm=false returns preview object showing projectedBalance = currentBalance + adjustmentAmountUsd, no DB rows created • POST with confirm=true and valid data returns 201; new ledger entry exists with correct entry_type • OPS_OPERATOR token returns 403 • adjustmentAmountUsd=-6000.00 on account with balance=5000.00 returns 422 on both preview and confirmed paths • reason of 9 chars returns 400 | 40 | 10.7-T07 | FS | PRD-07
10.7-T15 | admin-ui | 10.7 | 10. Admin System | Prefunding management UI | 2 | REST API: GET /admin/v1/prefunding/{partnerId}/balance - real-time balance point | Simple endpoint returning the current real-time balance for one partner - used by dashboard refresh and other modules that need balance without full ledger. Must NOT use any cache layer; reads directly from prefunding_account table. Response: {partnerId, balanceUsd, thresholdUsd, isBelow Threshold, lastUpdatedAt}. RBAC: OPS_OPERATOR, FINANCE_ANALYST, SUPER_ADMIN. PRD-07 §14.1: prefunding balance reads must be real-time reflecting atomic DB state. | • Add GET /admin/v1/prefunding/{partnerId}/balance to PrefundingController • Apply role check • Load prefunding_account by partnerId; return 404 if not found or if partner is LOCAL type • Compute isBelow Threshold = balance < low_balance_threshold • Return {partnerId, balanceUsd, thresholdUsd, isBelowThreshold, currency: USD, asOf: now()} • Verify no Redis/cache layer is bypassed - always queries Postgres directly | GET /admin/v1/prefunding/{partnerId}/balance endpoint returning live balance | • Response isBelowThreshold=true when balanceUsd=8500.00 and thresholdUsd=10000.00 • Response isBelowThreshold=false when balanceUsd=15000.00 and thresholdUsd=10000.00 • GET on LOCAL partner partnerId returns 404 or 400 with clear error • asOf timestamp in response is within 100ms of request time • Two sequential calls returning different balances (if a deduction occurred between them) confirms no caching | 25 | 10.7-T04 | FS | PRD-07
10.7-T16 | admin-ui | 10.7 | 10. Admin System | Prefunding management UI | 2 | Prefunding Dashboard UI page - balance summary cards with traffic-light indicators | Admin System frontend: Prefunding module main page showing one summary card per OVERSEAS partner (PRD-07 §9.2, §14.2). Each card: partner name, balance USD (2dp), threshold USD, balance %, traffic-light badge (RED/AMBER/GREEN per §9.2 thresholds: green >= 150%, amber 100-150%, red < 100%), last deduction, last top-up. Cards sorted RED first. Clicking a card navigates to that partner ledger page. UX: traffic-light uses CSS colour classes (red=#D32F2F, amber=#F57C00, green=#388E3C). Refresh button re-fetches from GET /admin/v1/prefunding/dashboard (no auto-poll). | • Create PrefundingDashboardPage component (React or framework in use) • Fetch data from GET /admin/v1/prefunding/dashboard on mount and on Refresh click • Render one card per entry with all required fields; apply CSS class based on trafficLight enum value • Show Loading spinner while fetch in progress; show error banner on API error • Sort cards: RED first, AMBER second, GREEN third • Write a component test: mock API returning 2 partners (one RED, one GREEN); assert RED renders first with correct colour class | PrefundingDashboardPage component with traffic-light cards, sorted by severity, with Refresh button | • Partner with trafficLight=RED renders with CSS class or background colour #D32F2F or equivalent red token • Partner with trafficLight=GREEN renders with green styling and appears after RED partner in DOM order • Clicking a card navigates to /admin/prefunding/{partnerId}/ledger • Refresh button triggers a new GET request and re-renders updated balances • If API returns 403, page displays an access-denied message rather than blank or crash | 50 | 10.7-T11 | FS | PRD-07
10.7-T17 | admin-ui | 10.7 | 10. Admin System | Prefunding management UI | 2 | Prefunding Ledger UI page - paginated ledger table with filters | Admin System frontend: per-partner prefunding ledger view (PRD-07 §9.4). Table columns: Ledger Entry ID, Timestamp (UTC), Type (display name: TOPUP/DEDUCTION/ADJUSTMENT/REFUND_REVERSAL), Amount USD (coloured: green for credit, red for debit), Balance After USD, Hub Txn Ref (link to transaction detail if present), Reference, Recorded By. Filters: entry type multi-select, date range picker. Pagination: 50 rows per page with next/prev. Balance reads must be real-time; no stale cache. Data from GET /admin/v1/prefunding/{partnerId}/ledger. | • Create PrefundingLedgerPage component accepting partnerId from route param • Render filter bar: entry type multi-select (TOPUP, DEDUCTION, ADJUSTMENT, REFUND_REVERSAL), date range (from/to date pickers) • Render table with all 8 columns; amount positive = green text, negative = red text • Implement pagination using page/size query params; show total record count • Hub Txn Ref cell: if present, render as link to /admin/transactions/{txnRef} • Fetch from API on filter change with debounce 300ms; show loading state | PrefundingLedgerPage component with filtered, paginated ledger table | • DEDUCTION entry renders amount in red text; TOPUP entry renders amount in green text • Applying filter type=TOPUP causes API request with entryType=TOPUP param and table re-renders with only TOPUP rows • Hub Txn Ref cell renders as clickable link when txn_ref is present; renders dash when null • Pagination controls: Next button disabled on last page; Prev button disabled on page 0 • Component test: mock 55 entries, assert page 1 shows 50 rows and Next button is enabled | 50 | 10.7-T12 | FS | PRD-07
10.7-T18 | admin-ui | 10.7 | 10. Admin System | Prefunding management UI | 2 | Top-Up Recording UI form with confirmation dialog | Admin System frontend: Top-Up Recording form (PRD-07 §9.3). Accessible from Prefunding Dashboard via Record Top-Up button (visible only to OPS_OPERATOR and SUPER_ADMIN). Fields: Partner (pre-selected if from partner context), Top-Up Amount USD (positive decimal), Bank Reference (text, required), Value Date (date picker, required, not future), Notes (optional textarea). On submit: show confirmation dialog with all entered values + current and projected balance; confirm triggers POST /admin/v1/prefunding/{partnerId}/topup. On success: show success toast with new balance; refresh dashboard. | • Create TopUpFormModal component with all required fields and validation • Add confirmation dialog showing: partner name, amount, bankRef, valueDate, current balance, projected balance • On dialog confirm: POST to /admin/v1/prefunding/{partnerId}/topup with {amountUsd, bankRef, valueDate, notes} • Handle 409 Conflict: show warning that this bankRef was already recorded, display original entry ID • Handle 400/422: show inline field errors • On success: emit event to parent to refresh balance; show toast with new balance USD | TopUpFormModal component with validation, confirmation dialog, and 409 duplicate handling | • Submitting form without bankRef shows required field error inline before confirmation dialog opens • Confirmation dialog displays projected balance = current balance + entered amount (e.g. current=5000, amount=50000, projected=55000.00) • Entering a future date in valueDate shows validation error • On 409 response, modal shows a warning containing the original ledger entry ID • After successful submit, dashboard card for that partner shows updated balance without full page reload | 45 | 10.7-T13, 10.7-T16 | FS | PRD-07
10.7-T19 | admin-ui | 10.7 | 10. Admin System | Prefunding management UI | 2 | Manual Adjustment UI form with two-step preview-then-confirm flow | Admin System frontend: Manual Adjustment form (PRD-07 §9.4, §14.2). Accessible to FINANCE_ANALYST and SUPER_ADMIN only (OPS_OPERATOR must not see the button). Fields: Adjustment Amount USD (can be positive or negative), Reason (required, min 10 chars). Flow: (1) submit triggers POST with confirm=false to get preview response; (2) show preview dialog with current balance, adjustment, projected balance; (3) if projected < 0 show error in dialog; (4) user clicks Confirm triggers POST with confirm=true. Uses two-step UX per PRD-07 §14.2. | • Create AdjustmentFormModal with adjustmentAmountUsd (number input, positive or negative) and reason (textarea, min 10 chars client-side) • On first submit: POST /admin/v1/prefunding/{partnerId}/adjustment with confirm=false; render preview dialog with API-returned projectedBalance • In preview dialog: if projectedBalance < 0 show red error and disable Confirm button • On Confirm click: POST same endpoint with confirm=true; handle success and errors • Hide Record Adjustment button entirely for OPS_OPERATOR role (check from auth context) • Write component test: assert Confirm button is disabled when API preview returns projectedBalance=-500 | AdjustmentFormModal component with two-step flow, negative balance guard, and role-based visibility | • First POST (confirm=false) does not create a DB row; preview dialog shows correct projectedBalance • If adjustment would result in projectedBalance < 0, Confirm button is disabled and error message shown in dialog • Reason field of 9 chars prevents form submission with client-side validation error • OPS_OPERATOR auth context: Record Adjustment button not rendered in DOM • Successful confirm=true POST closes modal and dashboard balance reflects adjustment | 45 | 10.7-T14, 10.7-T16 | FS | PRD-07
10.7-T20 | admin-ui | 10.7 | 10. Admin System | Prefunding management UI | 2 | Low-balance banner on Admin Dashboard - in-portal urgent alert | When any OVERSEAS partner balance reaches USD 0.00 (urgent alert case per PRD-07 §9.5), the Admin Dashboard must display a persistent red banner: Partner {name} prefunding balance is USD 0.00 - all payments suspended. Banner is dismissible for the session but reappears on next login if balance is still 0. Dashboard also shows amber badge on partners between 0 and threshold. Banner data sourced from GET /admin/v1/prefunding/dashboard checking for balanceUsd=0 entries. Payments-suspended state is enforced in backend (T04 InsufficientBalanceException) but this ticket only covers the in-portal banner display. | • In Admin Dashboard component, fetch GET /admin/v1/prefunding/dashboard and filter for entries with balanceUsd <= 0 • Render a dismissible red banner for each zero-balance partner: Partner {name} has USD 0.00 prefunding balance - payments are suspended • Store dismissed banner IDs in sessionStorage; do not show dismissed ones until next session • For AMBER entries (balanceUsd < thresholdUsd and > 0), show a smaller amber warning badge in the left-nav Prefunding menu item showing count • Auto-refresh dashboard data every 60 seconds on the Dashboard page only | Dashboard component showing red zero-balance banners and amber nav badge; session-dismiss working | • Partner with balanceUsd=0 renders a red banner with partner name and suspended warning • Dismissing banner removes it from view; it reappears on page reload (sessionStorage cleared on close) • Partner with balanceUsd=5000 and threshold=10000 causes amber badge with count=1 on Prefunding nav item • Partner with balanceUsd=15000 and threshold=10000 causes no banner or badge • Dashboard data auto-refreshes every 60 seconds (verify with network request timing) | 40 | 10.7-T11, 10.7-T08 | FS | PRD-07
10.7-T21 | admin-ui | 10.7 | 10. Admin System | Prefunding management UI | 2 | Email alert delivery integration - low-balance and urgent email via notification service | LowBalanceAlertService (T08) needs to actually send emails. The notification infrastructure sends emails via the Hub internal NotificationService. Email template for LOW_BALANCE: subject = GMEPay+ Alert: Low Prefunding Balance - {partnerName}; body fields per PRD-07 §9.5: partner name, current balance USD, threshold USD, suggested top-up = max(threshold * 2 - balance, threshold). URGENT template: subject = URGENT: {partnerName} Prefunding Balance Exhausted - Payments Suspended; body includes same fields plus payments-suspended notice. Recipients from low_balance_alert_config.alert_email (split on comma, trimmed). | • Create AlertEmailTemplate enum with LOW_BALANCE and URGENT_ZERO_BALANCE entries plus template rendering • Implement NotificationService.sendLowBalanceAlert(partnerName, balanceUsd, thresholdUsd, recipients) • Wire into LowBalanceAlertService.checkAndAlert from T08 • Write unit test mocking SMTP/email client: deduction from 12000 to 8500 (threshold=10000) sends exactly one LOW_BALANCE email to configured address • Write unit test for URGENT path: balance becomes 0, URGENT_ZERO_BALANCE email is sent • Confirm alert_email with two comma-separated addresses sends to both | NotificationService.sendLowBalanceAlert and sendUrgentZeroBalanceAlert integrated and unit-tested | • Unit test: deduction to 8500 (threshold 10000) calls sendLowBalanceAlert with correct partnerName, balanceUsd, thresholdUsd • Suggested top-up computed as max(10000*2 - 8500, 10000) = 11500.00 appears in email body • alert_email = ops@gme.com,finance@gme.com results in exactly 2 email deliveries • Balance deduction remaining above threshold (15000 -> 12000 with threshold 10000) sends no alert • URGENT template email subject contains the word URGENT and phrase Payments Suspended | 40 | 10.7-T08 | FS | PRD-07
10.7-T22 | admin-ui | 10.7 | 10. Admin System | Prefunding management UI | 2 | Alert threshold configuration - update low_balance_threshold via admin API and UI | The low-balance threshold is configurable per OVERSEAS partner (PRD-07 §5.3.3: default USD 10,000). Ops can update it from the Partner edit page or from the Prefunding module. Backend: PATCH /admin/v1/prefunding/{partnerId}/alert-config updates low_balance_alert_config.threshold_usd and also syncs prefunding_account.low_balance_threshold (both must stay consistent). Validation: threshold > 0. Change is audit-logged. Frontend: a small inline edit widget on the Prefunding Dashboard card showing the threshold with an Edit icon; input > 0 only. | • Create PATCH /admin/v1/prefunding/{partnerId}/alert-config endpoint accepting {thresholdUsd, alertEmail (optional update), isActive} • Validate thresholdUsd > 0; reject with 400 otherwise • Update low_balance_alert_config row; also update prefunding_account.low_balance_threshold to match • Write audit log entry: event_type=prefunding.alert_threshold_updated, previous and new threshold values • Frontend: add inline-edit pencil icon on threshold display in dashboard card; on save call PATCH; re-render with new threshold and updated trafficLight badge • RBAC: OPS_OPERATOR and SUPER_ADMIN only | PATCH /admin/v1/prefunding/{partnerId}/alert-config endpoint and inline-edit UI on dashboard card | • PATCH with thresholdUsd=20000.00 updates both low_balance_alert_config.threshold_usd and prefunding_account.low_balance_threshold to 20000.0000 • PATCH with thresholdUsd=0 returns 400 • Audit log entry exists with previous_threshold and new_threshold after update • After threshold update from 10000 to 20000, partner with balance=15000 now shows trafficLight=AMBER instead of GREEN on dashboard • FINANCE_ANALYST calling PATCH returns 403 | 40 | 10.7-T03, 10.7-T11 | FS | PRD-07
10.7-T23 | admin-ui | 10.7 | 10. Admin System | Prefunding management UI | 2 | Prefunding section on Partner detail page - balance panel and quick-links | The Partner detail page in the Partners module (PRD-07 §5.3.3) must show a Prefunding Setup section for OVERSEAS partners only: prefunding account ID, current balance USD (real-time), low-balance threshold, alert recipients, traffic-light badge. Quick-link buttons: View Ledger (-> /admin/prefunding/{partnerId}/ledger), Record Top-Up (opens TopUpFormModal). For LOCAL partners (e.g. GME Remit), the entire Prefunding section is hidden. Data from GET /admin/v1/prefunding/{partnerId}/balance and alert config. | • In PartnerDetailPage component, conditionally render PrefundingPanel only when partner.type === OVERSEAS • PrefundingPanel fetches GET /admin/v1/prefunding/{partnerId}/balance for live balance • Display: account ID, balance USD (2dp), threshold USD, isBelowThreshold badge, alert_email list • Render View Ledger link and Record Top-Up button (button hidden for FINANCE_ANALYST role) • Write component test: LOCAL partner renders no PrefundingPanel; OVERSEAS partner renders panel with balance data | PrefundingPanel sub-component on PartnerDetailPage; hidden for LOCAL partners; live balance displayed | • PartnerDetailPage for GME Remit (LOCAL) renders no PrefundingPanel section • PartnerDetailPage for SendMN (OVERSEAS) renders PrefundingPanel with live balance and threshold • isBelowThreshold=true in API response renders amber/red indicator on the panel • Record Top-Up button is visible for OPS_OPERATOR and hidden for FINANCE_ANALYST • View Ledger link navigates to /admin/prefunding/prt_sendmn_001/ledger | 35 | 10.7-T15, 10.7-T18 | FS | PRD-07
10.7-T24 | admin-ui | 10.7 | 10. Admin System | Prefunding management UI | 2 | Unit tests: TopUpRecordingService and ManualAdjustmentService logic | Unit-test suite for T06 and T07 service logic. Tests must cover: normal top-up flow, duplicate bankRef idempotency, LOCAL partner rejection, zero-amount validation, adjustment preview vs commit, adjustment negative-balance guard, RBAC enforcement, and audit log invocation. Use Mockito (or equivalent) to mock repositories and AuditLogService. Tests must be self-contained with no DB dependency. | • Create TopUpRecordingServiceTest with test vectors listed in checks • Create ManualAdjustmentServiceTest with test vectors listed in checks • Mock PrefundingAccountRepository, LedgerAppendService, AuditLogService • Verify AuditLogService.log() is called exactly once per successful operation • Assert InsufficientBalanceException is thrown (not a different exception) when balance would go negative • Run tests with ./mvnw test -pl <module> and confirm all pass | TopUpRecordingServiceTest and ManualAdjustmentServiceTest; all tests green | • recordTopUp(partnerId=LOCAL_PARTNER, ...) throws PartnerTypeException • recordTopUp(amountUsd=0) throws ValidationException before any repo call • recordTopUp(amountUsd=50000, bankRef=WIRE-001) succeeds; verify creditBalance called with 50000.0000 and appendCredit called with CREDIT_TOPUP • applyAdjustment called by OPS_OPERATOR role throws AccessDeniedException • applyAdjustment(-6000) on account with balance 5000 throws InsufficientBalanceException; verify no ledger entry appended • applyAdjustment(+1000, reason=fix error in entry) with reason < 10 chars throws ValidationException | 40 | 10.7-T06, 10.7-T07 | FS | PRD-07
10.7-T25 | admin-ui | 10.7 | 10. Admin System | Prefunding management UI | 2 | Unit tests: LowBalanceAlertService threshold-crossing logic | Unit-test suite for T08 LowBalanceAlertService. Key invariant: alert fires only when balance crosses from above threshold to below (not on every deduction while already below). Urgent alert fires when balance <= 0. Tests use mocked NotificationService and mocked prefunding_account reads. | • Create LowBalanceAlertServiceTest • Test 1: previousBalance=12000, newBalance=8500, threshold=10000 -> sendLowBalanceAlert called once • Test 2: previousBalance=8000, newBalance=7000, threshold=10000 -> NO alert (already below; no crossing) • Test 3: previousBalance=12000, newBalance=0, threshold=10000 -> sendUrgentZeroBalanceAlert called (not low-balance) • Test 4: previousBalance=12000, newBalance=10001, threshold=10000 -> no alert (still above threshold) • Test 5: is_active=false on alert config -> no email sent regardless of balance | LowBalanceAlertServiceTest with all 5 test vectors passing | • Test 1 passes: crossing from above to below threshold triggers exactly one LOW_BALANCE email • Test 2 passes: no duplicate alert when already below threshold; NotificationService never called • Test 3 passes: newBalance=0 triggers URGENT path, not LOW_BALANCE • Test 4 passes: balance remains above threshold, no alert sent • Test 5 passes: is_active=false suppresses all notifications | 30 | 10.7-T08 | FS | PRD-07
10.7-T26 | admin-ui | 10.7 | 10. Admin System | Prefunding management UI | 2 | Unit tests: PrefundingAccountRepository atomic deduction (concurrent scenario) | Integration-level unit test (Testcontainers Postgres) verifying SELECT FOR UPDATE prevents double-spend. Scenario: two threads simultaneously call deductBalance on an account with balance=100.00, each deducting 100.00. Expected: exactly one succeeds, one throws InsufficientBalanceException, final balance=0.00. Also tests creditBalance precision using BigDecimal arithmetic. | • Configure Testcontainers Postgres in test scope; apply migrations from T01/T02 • Write ConcurrentDeductionTest: create account with balance=100.00; launch 2 threads calling deductBalance(100.00) simultaneously via ExecutorService • Collect results; assert exactly 1 success and 1 InsufficientBalanceException • Assert final balance = 0.0000 in DB after both threads complete • Write PrecisionTest: creditBalance(0.0001) then creditBalance(0.0001) -> balance = 0.0002 (not 0.00019... floating error) | ConcurrentDeductionTest and PrecisionTest passing against real Postgres via Testcontainers | • Concurrent test: exactly 1 of 2 threads succeeds when both request 100.00 from a 100.00 account • Final DB balance after concurrent test = 0.0000 (not negative, not 100.00) • Precision test: two deductions of 0.0001 each result in balance change of exactly 0.0002 in DECIMAL(20,4) column • creditBalance(50000.00) followed by deductBalance(50000.00) results in balance=0.0000 with no floating-point rounding error • Test runs without external dependencies other than Testcontainers Postgres | 40 | 10.7-T04 | FS | PRD-07
10.7-T27 | admin-ui | 10.7 | 10. Admin System | Prefunding management UI | 2 | Unit tests: PrefundingDashboardService - traffic-light computation and sort order | Unit tests for PrefundingDashboardService (T09) verifying traffic-light classification and sort logic. All tests use mocked repositories; no DB required. | • Create PrefundingDashboardServiceTest • Test balancePct and trafficLight for boundary values: 149.99% = AMBER, 150.00% = GREEN, 100.00% = AMBER, 99.99% = RED • Test sort order: list of [AMBER, GREEN, RED] partners returns [RED, AMBER, GREEN] • Test lastDeduction/lastTopUp fields populated from mocked ledger entries • Test partner with no ledger entries returns null for lastDeductionAt and lastTopUpAt (no NPE) | PrefundingDashboardServiceTest with boundary and sort tests all passing | • balance=14999, threshold=10000 -> balancePct=149.99, trafficLight=AMBER • balance=15000, threshold=10000 -> balancePct=150.00, trafficLight=GREEN • balance=10000, threshold=10000 -> balancePct=100.00, trafficLight=AMBER • balance=9999, threshold=10000 -> balancePct=99.99, trafficLight=RED • List input [AMBER, GREEN, RED] is returned sorted as [RED, AMBER, GREEN] | 25 | 10.7-T09 | FS | PRD-07
10.7-T28 | admin-ui | 10.7 | 10. Admin System | Prefunding management UI | 2 | Acceptance test: end-to-end top-up and deduction flow via API | End-to-end integration test (Spring Boot test with Testcontainers Postgres) covering the full prefunding lifecycle: onboard OVERSEAS partner -> record top-up -> simulate payment deduction -> verify ledger entries -> trigger low-balance check. Verifies all layers (service + repository + DB) work together correctly. Focuses on the data correctness path, not the email delivery. | • Set up test: insert OVERSEAS partner (SendMN) and prefunding_account with balance=0 • POST /admin/v1/prefunding/{id}/topup amountUsd=50000.00 bankRef=TEST-WIRE-001; assert 201 and balance=50000.00 • Directly call PrefundingAccountRepository.deductBalance(accountId, 49500.00) to simulate payment; assert balance=500.00 • GET /admin/v1/prefunding/{id}/balance; assert balanceUsd=500.00 and isBelowThreshold=true (threshold=10000) • GET /admin/v1/prefunding/{id}/ledger; assert 2 entries: CREDIT_TOPUP(50000) and DEBIT_PAYMENT(49500); balance_after values correct • Attempt deductBalance(600.00) on balance=500.00; assert InsufficientBalanceException thrown; balance remains 500.00 | End-to-end integration test passing all 6 assertion steps | • After topup, balance=50000.0000 in DB • After deduction, balance=500.0000 in DB • GET /balance returns isBelowThreshold=true (500 < 10000) • Ledger has exactly 2 entries in correct order with correct balance_after snapshots (50000, then 500) • Overdraft attempt throws InsufficientBalanceException and leaves balance at 500.0000 • All 6 steps pass in a single test run with no manual DB setup required | 50 | 10.7-T13, 10.7-T04, 10.7-T05, 10.7-T26 | FS | PRD-07
10.7-T29 | admin-ui | 10.7 | 10. Admin System | Prefunding management UI | 2 | Docs: Prefunding module operator runbook (inline API docs + Swagger annotations) | Every admin API endpoint must have OpenAPI 3.0 / Swagger annotations so the auto-generated spec is accurate (PRD-07 requirement for operations team). Additionally a short operator runbook comment block in each Service class method explains when and why Ops would use each operation. No separate .md files; documentation lives in code annotations and Swagger. | • Add @Operation, @ApiResponse, @Parameter Swagger annotations to all 5 prefunding endpoints (dashboard, ledger, balance, topup, adjustment) • Document error responses: 400, 403, 404, 409, 422 with description per endpoint • Add Javadoc block to TopUpRecordingService.recordTopUp, ManualAdjustmentService.applyAdjustment, LowBalanceAlertService.checkAndAlert explaining business purpose and when to use • Verify /v3/api-docs renders all 5 endpoints with correct request/response schemas • Add @Schema annotations to all DTO fields with example values (e.g. @Schema(example=50000.00)) | All 5 prefunding endpoints documented in Swagger with examples; key service methods have Javadoc | • GET /v3/api-docs includes all 5 prefunding endpoints with non-empty summary and description • TopUp endpoint schema shows amountUsd with example 50000.00 and bankRef with example WIRE-2026-001 • All 4xx/5xx response codes documented with meaningful description per endpoint • Javadoc on recordTopUp explains the two-phase commit: creditBalance then ledger entry then audit log • Swagger UI renders the prefunding section without errors when loaded in browser | 35 | 10.7-T13, 10.7-T14, 10.7-T15 | FS | PRD-07
10.8-T01 | admin-ui | 10.8 | 10. Admin System | Refund/cancellation handling UI | 2 | Add DB migration: refund table with all Phase 1 columns | PRD-07 §10.3 requires a refund entity. DAT-03 §5.4 defines: refund(id BIGINT PK, txn_id BIGINT FK->transaction, refund_ref VARCHAR(64) UNIQUE, refund_amount DECIMAL(20,4), refund_ccy CHAR(3), reason VARCHAR(255), status VARCHAR(20) [REFUND_PENDING¦REFUND_SUBMITTED¦REFUND_CONFIRMED¦REFUND_FAILED¦REFUNDED], scheme_refund_ref VARCHAR(128), initiated_by VARCHAR(120), created_at TIMESTAMPTZ, updated_at TIMESTAMPTZ, created_by VARCHAR(120), updated_by VARCHAR(120)). The refund_ref is the gme_refund_id used in ZP0021 batch. One refund row per refund request; partial refunds (refund_amount < original target_payout) are supported. | • Create a Flyway/Liquibase migration file V<next>__create_refund_table.sql • Add all columns from DAT-03 §5.4 with correct types and constraints • Add index on txn_id (for fast lookup from transaction detail page) • Add index on status (for batch aggregation of REFUND_PENDING rows) • Add CHECK constraint: status IN ('REFUND_PENDING','REFUND_SUBMITTED','REFUND_CONFIRMED','REFUND_FAILED','REFUNDED') | Migration file V<next>__create_refund_table.sql applied cleanly to local schema | • Migration runs without error on a clean schema; rollback script reverts cleanly • refund_ref column has UNIQUE constraint; inserting duplicate refund_ref raises DB error • refund_amount column is DECIMAL(20,4); inserting a value with 5 decimal places is rejected or rounded per DB precision rules • status column rejects values outside the 5 allowed enum values via CHECK constraint • txn_id FK references transaction.id; inserting a refund with a non-existent txn_id raises FK violation | 30 |  | FS | PRD-07
10.8-T02 | admin-ui | 10.8 | 10. Admin System | Refund/cancellation handling UI | 2 | Add refund_window_days config to qr_scheme table | PRD-07 §10.3.1 and A-07: the refund eligibility window defaults to 90 days and is configurable per scheme. The qr_scheme table (DAT-03 §4.1) needs a new integer column refund_window_days (NOT NULL DEFAULT 90, CHECK refund_window_days > 0). This value is read at refund-initiation time to determine eligibility. | • Create migration file adding refund_window_days INT NOT NULL DEFAULT 90 to qr_scheme • Add CHECK constraint: refund_window_days > 0 • Update the ZeroPay seed/fixture row to set refund_window_days = 90 • Document the column in the schema comments | Migration file adding refund_window_days to qr_scheme, applied cleanly | • Column exists with DEFAULT 90 after migration; existing ZeroPay row reads 90 • Setting refund_window_days = 0 is rejected by CHECK constraint • Setting refund_window_days = 180 persists correctly • Existing qr_scheme rows without an explicit value default to 90 | 20 |  | FS | PRD-07
10.8-T03 | admin-ui | 10.8 | 10. Admin System | Refund/cancellation handling UI | 2 | Add RefundRepository: CRUD + status-update + batch-query methods | The refund table (10.8-T01) needs a Spring Data / JPA repository (or equivalent). Key query patterns needed: findByTxnId, findByStatus(REFUND_PENDING), updateStatus(id, newStatus, updatedBy), countByTxnIdAndStatusNotIn (to guard against duplicate refunds). Use DECIMAL for all monetary fields (never double/float). No UPDATE permitted on refund_amount or txn_id after insert. | • Create RefundEntity JPA class mapping refund table columns • Create RefundRepository interface with findByTxnId, findAllByStatus, updateStatus • Add a method findPendingRefundsForBatch() returning rows with status=REFUND_PENDING ordered by created_at ASC • Ensure updateStatus uses optimistic locking (version field or explicit WHERE status=<expected>) to detect race conditions • Write a constructor that disallows null txn_id, null refund_amount, or refund_amount <= 0 | RefundRepository class and RefundEntity with all columns mapped | • findAllByStatus(REFUND_PENDING) returns only rows in that status • updateStatus fails (throws OptimisticLockException or returns 0 rows updated) if concurrent update has already changed status • Constructor throws IllegalArgumentException when refund_amount is 0 or negative • findByTxnId returns all refunds for that transaction (allowing detection of already-refunded state) • No floating-point types (float, double) used for monetary fields; DECIMAL/BigDecimal only | 40 | 10.8-T01 | FS | PRD-07
10.8-T04 | admin-ui | 10.8 | 10. Admin System | Refund/cancellation handling UI | 2 | Implement RefundEligibilityService: validate a transaction is refundable | PRD-07 §10.3.1: a refund is eligible when (1) transaction status is APPROVED or SCHEME_APPROVED, (2) transaction created_at is within the scheme's refund_window_days of today (KST), (3) transaction has not already been refunded (no existing refund row in status other than REFUND_FAILED), (4) transaction is linked to an active ZeroPay merchant record (merchant.is_active = true). Return a typed result (eligible=true/false + reason code). KST = UTC+9; use ZoneId.of('Asia/Seoul') for date arithmetic. | • Create RefundEligibilityService.checkEligibility(txnId) -> EligibilityResult • Check transaction.status in [APPROVED, SCHEME_APPROVED]; else return NOT_ELIGIBLE_STATUS • Check (today_KST - transaction.created_at_KST) <= scheme.refund_window_days; else return NOT_ELIGIBLE_WINDOW • Query refund table: if any row for txn_id with status not in [REFUND_FAILED] exists, return ALREADY_REFUNDED • Check merchant.is_active = true for the merchant linked to this transaction; else return MERCHANT_INACTIVE • Return ELIGIBLE if all checks pass | RefundEligibilityService class with checkEligibility method and EligibilityResult enum/record | • Transaction in FAILED status returns NOT_ELIGIBLE_STATUS • Transaction created 91 days ago with scheme refund_window_days=90 returns NOT_ELIGIBLE_WINDOW; 89 days ago returns ELIGIBLE (all other checks pass) • Transaction with an existing refund in REFUND_PENDING status returns ALREADY_REFUNDED • Transaction with a REFUND_FAILED refund and no other refund returns ELIGIBLE (failed refund does not block retry) • Transaction linked to a merchant with is_active=false returns MERCHANT_INACTIVE | 45 | 10.8-T01, 10.8-T02, 10.8-T03 | FS | PRD-07
10.8-T05 | admin-ui | 10.8 | 10. Admin System | Refund/cancellation handling UI | 2 | Implement RefundInitiationService: create refund record and audit log entry | PRD-07 §10.3.2: on Submit Refund, the backend must (a) call RefundEligibilityService, (b) validate refund_amount <= original transaction target_payout (payout ccy), (c) insert a refund row in status REFUND_PENDING with a unique refund_ref (e.g. 'RFD-' + hub_txn_ref + '-' + timestamp millis), (d) write an audit log entry with event_type='refund.initiated', actor_user_id, entity_type='refund', entity_id, previous_value=null, new_value=JSON of refund record. The parent transaction status must NOT change at this point (it transitions only when ZP0022 confirms). Reason codes are: CUSTOMER_REQUEST, MERCHANT_ERROR, SETTLEMENT_ERROR. | • Create RefundInitiationService.initiateRefund(txnId, refundAmount, reasonCode, internalNotes, actorUserId) • Call RefundEligibilityService; throw RefundNotEligibleException with reason code if not eligible • Validate refundAmount <= transaction.target_payout; throw RefundAmountExceededException if not • Generate unique refund_ref using format 'RFD-{hub_txn_ref}-{epochMillis}' • Insert refund row with status=REFUND_PENDING inside a @Transactional block • Write audit log entry (event_type=refund.initiated, actor_user_id, entity_id=refund.id) • Return the created RefundRecord | RefundInitiationService with initiateRefund method, wrapped in @Transactional | • Calling initiateRefund on an APPROVED transaction with refund_amount = original target_payout creates one REFUND_PENDING row and one audit log entry • Calling initiateRefund with refund_amount = original_payout + 1 KRW throws RefundAmountExceededException (e.g. original KRW 10000, attempted KRW 10001) • Calling initiateRefund twice on the same transaction throws RefundNotEligibleException with reason ALREADY_REFUNDED on the second call • Audit log entry contains actor_user_id, event_type=refund.initiated, and new_value JSON including refund_amount and reason_code • Transaction status remains APPROVED after initiation (not yet REFUND_PENDING on the transaction itself) | 50 | 10.8-T03, 10.8-T04 | FS | PRD-07
10.8-T06 | admin-ui | 10.8 | 10. Admin System | Refund/cancellation handling UI | 2 | Implement admin-portal cancel for same-day COMMITTED/SUBMITTED_TO_SCHEME transactions | PRD-07 §10.2: Ops can cancel a transaction via portal if status is COMMITTED or SUBMITTED_TO_SCHEME and it is still the same calendar day (KST) as transaction creation. On cancel: (a) call the ZeroPay real-time cancel API via the scheme adapter, (b) for OVERSEAS partners reverse the prefunding deduction (insert a REFUND_REVERSAL ledger entry with positive amount = original deduction), (c) set transaction.status = CANCELLED, (d) write audit log entry event_type=transaction.cancelled. Same-day = created_at_KST.date == today_KST.date. This is distinct from the post-settlement refund flow. | • Create CancellationService.cancelTransaction(txnId, actorUserId) • Validate transaction.status in [COMMITTED, SUBMITTED_TO_SCHEME]; else throw CancellationNotAllowedException • Validate same-day window: transaction.created_at in KST must equal today KST date; else throw CancellationWindowExpiredException • Call scheme adapter cancelPayment(hub_txn_ref); handle adapter errors • If partner is OVERSEAS: insert prefunding_ledger_entry type=REFUND_REVERSAL, amount=+original_deduction_usd, atomically update prefunding_account.balance • Update transaction.status = CANCELLED inside @Transactional • Write audit log entry event_type=transaction.cancelled with actor_user_id | CancellationService class with cancelTransaction method | • Cancelling a COMMITTED OVERSEAS transaction on the same day sets status=CANCELLED and creates a REFUND_REVERSAL prefunding ledger entry equal to the original collection_amount in USD • Cancelling a LOCAL (GME Remit) COMMITTED transaction sets status=CANCELLED with no prefunding ledger entry • Attempting to cancel an APPROVED (post-scheme) transaction throws CancellationNotAllowedException • Cancelling a transaction created on a previous KST calendar day throws CancellationWindowExpiredException even if fewer than 24 hours have passed (e.g. created at 23:50 KST yesterday, cancelled at 00:10 KST today is rejected) • Audit log entry is written with event_type=transaction.cancelled and actor_user_id | 55 | 10.8-T03 | FS | PRD-07
10.8-T07 | admin-ui | 10.8 | 10. Admin System | Refund/cancellation handling UI | 2 | Implement ZP0021 batch file generator: aggregate REFUND_PENDING rows into fixed-width file | SCH-06 §6.2: ZP0021 is transmitted by GME to ZeroPay at ~02:00 KST daily. Scope: all refunds in status REFUND_PENDING where the refund was created before the batch cutoff (i.e. created_at_KST < today 02:00 KST). Record layout (fixed-width): record_type CHAR(1)='D', gme_refund_id CHAR(20), original_zeropay_txn_ref CHAR(20), gme_original_txn_id CHAR(20), merchant_id CHAR(10), refund_date DATE(8) YYYYMMDD KST, refund_time TIME(6) HHMMSS KST, refund_amount_krw NUM(12) right-justified zero-padded, merchant_fee_adj_amt NUM(12), partner_type CHAR(1) [D=Domestic/I=International], refund_reason_code CHAR(2), status_code CHAR(1)='R'. File header and trailer follow ZP0011 pattern with file_type=ZP0021. | • Create Zp0021BatchGenerator.generateFile(settlementDate) that queries all REFUND_PENDING refunds for the given business date • Map each refund record to the fixed-width layout using the ZP0021 field definitions • Write file header (file_type=ZP0021) and trailer (record count) • Persist a settlement_batch row and settlement_file row for this batch run • Update each included refund row from REFUND_PENDING to REFUND_SUBMITTED atomically • Return the generated file bytes / path for SFTP upload | Zp0021BatchGenerator class with generateFile method producing a compliant fixed-width file | • A refund with refund_amount=10000 KRW produces a record with refund_amount_krw field right-justified zero-padded to 12 digits: '000000010000' • refund_reason_code CUSTOMER_REQUEST maps to scheme-defined 2-char code (e.g. '01'); verify mapping table is complete for all 3 reason codes • After batch generation all included refund rows have status=REFUND_SUBMITTED; rows created after the batch cutoff remain REFUND_PENDING • File trailer record count equals the number of detail records in the file • Domestic partner (GME Remit) produces partner_type='D'; overseas (SendMN) produces 'I' | 55 | 10.8-T03 | FS | PRD-07
10.8-T08 | admin-ui | 10.8 | 10. Admin System | Refund/cancellation handling UI | 2 | Implement ZP0022 result file processor: parse and apply refund registration results | SCH-06 §6.3: ZeroPay returns ZP0022 by ~05:00 KST. Record layout: original_zeropay_txn_ref CHAR(20), gme_refund_id CHAR(20), result_code CHAR(2) [00=Success], result_message VARCHAR(100), registered_refund_amount NUM(12), adjustment_settlement_date DATE(8). Match key is original_zeropay_txn_ref + gme_refund_id. Success (result_code=00): update refund.status=REFUND_CONFIRMED, store scheme_refund_ref, then trigger post-confirmation handler. Failure (result_code != 00): update refund.status=REFUND_FAILED with error stored in reason field; send Ops alert. For UNCERTAIN reconciliation: on ZP0022 receipt also resolve UNCERTAIN transactions per SAD-02 §5.4. | • Create Zp0022Processor.processFile(fileBytes) that parses the fixed-width file • For each record look up refund by gme_refund_id; log and skip if not found (log as MISSING_REFUND_REF exception) • If result_code=00: update status to REFUND_CONFIRMED, store scheme_refund_ref = gme_refund_id echo, write audit log event_type=refund.confirmed • If result_code != 00: update status to REFUND_FAILED, store error in reason, write audit log event_type=refund.failed, emit Ops alert • If registered_refund_amount != refund.refund_amount: flag as AMOUNT_MISMATCH exception record for Ops review; do not mark CONFIRMED • After all records, call RefundCompletionService to apply post-confirmation steps | Zp0022Processor class with processFile method and associated audit logging | • Record with result_code=00 transitions refund to REFUND_CONFIRMED and writes audit log • Record with result_code=01 (example failure) transitions refund to REFUND_FAILED and triggers Ops alert • registered_refund_amount=9000 vs refund.refund_amount=10000 KRW creates an AMOUNT_MISMATCH exception record and does NOT mark the refund CONFIRMED • A gme_refund_id in ZP0022 that does not exist in the refund table is logged as MISSING_REFUND_REF exception and processing continues (no crash) • Processing is idempotent: re-processing the same ZP0022 file does not create duplicate audit log entries or double-apply prefunding reversals | 55 | 10.8-T03, 10.8-T07 | FS | PRD-07
10.8-T09 | admin-ui | 10.8 | 10. Admin System | Refund/cancellation handling UI | 2 | Implement RefundCompletionService: apply prefunding reversal on REFUND_CONFIRMED (OVERSEAS only) | PRD-07 §10.3.2: for OVERSEAS partners, the prefunding balance is reversed when ZeroPay confirms the refund via ZP0022 (not at initiation). Specifically: (1) insert prefunding_ledger_entry type=REFUND_REVERSAL with amount=+refund_amount_in_usd (convert from KRW using the rate locked on the original transaction: locked cost_rate_pay = treasury.usd_krw at commit time), (2) update prefunding_account.balance atomically via SELECT FOR UPDATE, (3) update refund.status from REFUND_CONFIRMED to REFUNDED, (4) write audit log event_type=refund.completed. For LOCAL partners (GME Remit) skip steps 1-2, still update to REFUNDED. Conversion: reversal_usd = refund_amount_krw / locked_cost_rate_pay (cost_rate_pay from the original transaction's locked rate). | • Create RefundCompletionService.applyCompletion(refundId) called by Zp0022Processor on each confirmed refund • Load refund and original transaction; check partner type • If OVERSEAS: compute reversal_usd = refund_amount / transaction.cost_rate_pay (BigDecimal, scale 8) • Insert prefunding_ledger_entry type=REFUND_REVERSAL inside SELECT FOR UPDATE on prefunding_account • Update refund.status = REFUNDED atomically in same transaction • Write audit log entry event_type=refund.completed with actor=SYSTEM | RefundCompletionService with applyCompletion method, @Transactional | • OVERSEAS refund of KRW 10000 with locked cost_rate_pay=1350.000000 produces reversal_usd = 10000/1350 = 7.407407 USD (stored to 8 decimal places) in prefunding ledger • LOCAL (GME Remit) refund completion updates status to REFUNDED with no prefunding_ledger_entry created • Concurrent calls to applyCompletion for the same refund_id: second call finds status already REFUNDED and exits without creating a duplicate ledger entry (idempotency via status check inside SELECT FOR UPDATE) • prefunding_account.balance increases by reversal_usd after completion for OVERSEAS partner • Audit log entry event_type=refund.completed is written with entity_id = refund.id | 50 | 10.8-T03, 10.8-T08 | FS | PRD-07
10.8-T10 | admin-ui | 10.8 | 10. Admin System | Refund/cancellation handling UI | 2 | Expose admin API endpoint POST /admin/v1/transactions/{id}/refund | The refund initiation flow (10.8-T05) must be callable from the admin portal UI. Endpoint: POST /admin/v1/transactions/{id}/refund. Auth: requires OPS_OPERATOR or SUPER_ADMIN role (RBAC check per PRD-07 §12.3). Request body: {refund_amount: decimal, reason_code: enum[CUSTOMER_REQUEST¦MERCHANT_ERROR¦SETTLEMENT_ERROR], internal_notes: string min 20 chars}. Response 201: {refund_id, refund_ref, status: REFUND_PENDING, refund_amount, refund_ccy}. Error 409 if ALREADY_REFUNDED; 422 if amount exceeds original or ineligible status; 403 if caller lacks permission. | • Create RefundController with POST /admin/v1/transactions/{id}/refund handler • Add request body validation: refund_amount > 0, reason_code in allowed set, internal_notes >= 20 chars • Enforce RBAC: reject with 403 if authenticated user role is not OPS_OPERATOR or SUPER_ADMIN • Call RefundInitiationService.initiateRefund; map exceptions to HTTP status codes • Return 201 with RefundResponse DTO on success • Add endpoint to OpenAPI spec | RefundController with POST /admin/v1/transactions/{id}/refund endpoint, RBAC-enforced | • POST with valid body and OPS_OPERATOR session returns 201 with status=REFUND_PENDING • POST with FINANCE_ANALYST session returns 403 • POST with refund_amount > original target_payout returns 422 with error code REFUND_AMOUNT_EXCEEDED • POST with internal_notes of 19 characters returns 422 with field validation error • POST for a transaction that already has a REFUND_PENDING refund returns 409 with error code ALREADY_REFUNDED | 45 | 10.8-T05 | FS | PRD-07
10.8-T11 | admin-ui | 10.8 | 10. Admin System | Refund/cancellation handling UI | 2 | Expose admin API endpoint POST /admin/v1/transactions/{id}/cancel (portal cancel) | CancellationService (10.8-T06) must be callable from the admin portal UI. Endpoint: POST /admin/v1/transactions/{id}/cancel. Auth: OPS_OPERATOR or SUPER_ADMIN only. No request body required (actor is the authenticated user). Response 200: {hub_txn_ref, status: CANCELLED, cancelled_at, cancelled_by}. Error 409 if status not cancelable; 422 if same-day window expired. This is the admin-portal cancel path; the partner API cancel (API-05 §4.6) is a separate endpoint/flow. | • Create or extend TransactionAdminController with POST /admin/v1/transactions/{id}/cancel • Enforce RBAC: 403 if not OPS_OPERATOR or SUPER_ADMIN • Call CancellationService.cancelTransaction(txnId, actorUserId) • Map CancellationNotAllowedException to 409; CancellationWindowExpiredException to 422 • Return 200 with CancelResponse DTO on success • Add endpoint to OpenAPI spec | POST /admin/v1/transactions/{id}/cancel endpoint handler | • POST on a COMMITTED OVERSEAS transaction on the same KST day returns 200 and transaction status becomes CANCELLED • POST on an APPROVED (post-scheme) transaction returns 409 • POST on a transaction from a prior KST date returns 422 • POST with ADMIN_VIEWER session returns 403 • Response body includes cancelled_by matching the authenticated user ID | 35 | 10.8-T06 | FS | PRD-07
10.8-T12 | admin-ui | 10.8 | 10. Admin System | Refund/cancellation handling UI | 2 | Expose admin API: GET /admin/v1/refunds — paginated refund list with filters | PRD-07 §10.3.5 requires a Refund module list view. Endpoint: GET /admin/v1/refunds. Query params: status (optional, multi-value), partner_id (optional), date_from/date_to (optional, KST), page/size (default size=50). Response: paginated list of refunds with fields: refund_id, refund_ref, hub_txn_ref, partner_name, scheme_name, refund_amount, refund_ccy, reason_code, status, initiated_by, created_at. Auth: OPS_OPERATOR, FINANCE_ANALYST, SUPER_ADMIN, ADMIN_VIEWER (all roles can view per PRD-07 §12.3 View Refund Status). | • Create GET /admin/v1/refunds handler in RefundController • Accept query params: status[], partner_id, date_from, date_to, page, size • Build JPA/SQL query with dynamic filters and pagination • Join to transaction, partner, scheme tables for display fields • Return paginated RefundListResponse with total_count • Enforce read access for all four roles; no write permission check needed for GET | GET /admin/v1/refunds endpoint with pagination and filtering | • GET with status=REFUND_PENDING returns only rows in that status • GET with date_from=2026-06-01 and date_to=2026-06-05 returns only refunds created in that window (KST) • ADMIN_VIEWER session can call GET and receives 200 (not 403) • Response includes total_count matching the number of records in the filtered result set • GET with page=2 and size=10 returns the correct second page of results | 40 | 10.8-T03 | FS | PRD-07
10.8-T13 | admin-ui | 10.8 | 10. Admin System | Refund/cancellation handling UI | 2 | Expose admin API: GET /admin/v1/refunds/{id} — refund detail view | Ops needs to view individual refund details. Endpoint: GET /admin/v1/refunds/{id}. Returns full refund record plus linked transaction summary (hub_txn_ref, original target_payout, merchant_id, merchant_name, partner_name, scheme_name), and status history (all audit log entries for this refund_id). Auth: all four roles can read refund status (PRD-07 §12.3). | • Add GET /admin/v1/refunds/{id} handler • Load refund row; 404 if not found • Load linked transaction summary fields • Query audit_log for entity_type=refund AND entity_id=id to build status history list • Return RefundDetailResponse including refund fields, transaction summary, and status_history array • Enforce minimum role = ADMIN_VIEWER | GET /admin/v1/refunds/{id} endpoint returning full detail and audit history | • Returns 404 for non-existent refund_id • Response includes original transaction hub_txn_ref and target_payout amount • status_history array contains at least one entry (the refund.initiated audit event) • ADMIN_VIEWER role returns 200; unauthenticated call returns 401 • After a full refund lifecycle (REFUND_PENDING -> REFUND_SUBMITTED -> REFUND_CONFIRMED -> REFUNDED), status_history has 4 entries in chronological order | 35 | 10.8-T10, 10.8-T12 | FS | PRD-07
10.8-T14 | admin-ui | 10.8 | 10. Admin System | Refund/cancellation handling UI | 2 | Expose admin API: GET /admin/v1/refunds/batches — daily batch summary view | PRD-07 §10.3.5 requires a batch sub-view showing refunds grouped by daily batch: batch_date, total_count, total_krw_amount, zp0021_transmission_status (PENDING¦SENT¦FAILED), zp0021_sent_at, zp0022_receipt_status (PENDING¦RECEIVED¦FAILED), zp0022_received_at, per_status_breakdown (count per status). Source: settlement_batch and settlement_file tables for ZP0021/ZP0022 entries, joined to refund rows. Auth: all four roles. | • Add GET /admin/v1/refunds/batches handler with optional date_from/date_to filter • Query settlement_batch filtered to file_type IN ('ZP0021','ZP0022') • For each batch date, aggregate: total refund count, total KRW amount, status breakdown from refund table • Include ZP0021 file transmission status and ZP0022 receipt status from settlement_file rows • Return list of RefundBatchSummary sorted by batch_date DESC • Default to last 30 days if no date filter provided | GET /admin/v1/refunds/batches endpoint returning daily batch summaries | • Response for a date with 3 refunds shows total_count=3 and correct total_krw_amount • zp0021_transmission_status=SENT only when a settlement_file row with file_type=ZP0021 and status=SENT exists for that batch_date • zp0022_receipt_status=RECEIVED only when a settlement_file row with file_type=ZP0022 and status=RECEIVED exists • per_status_breakdown shows correct counts, e.g. {REFUNDED: 2, REFUND_FAILED: 1} for a batch with those outcomes • Date with no refunds does not appear in the result list | 40 | 10.8-T07, 10.8-T08 | FS | PRD-07
10.8-T15 | admin-ui | 10.8 | 10. Admin System | Refund/cancellation handling UI | 2 | Admin UI: Refund Initiation form on transaction detail page | PRD-07 §10.3.2 and UX-11: the transaction detail page must show an Initiate Refund button when the transaction is eligible (status APPROVED or SCHEME_APPROVED, within refund window, not already refunded, active merchant). Clicking the button opens a modal/form with fields: Refund Amount (decimal, payout ccy, pre-filled with original target_payout, editable down to 1 KRW), Reason Code (select: CUSTOMER_REQUEST ¦ MERCHANT_ERROR ¦ SETTLEMENT_ERROR), Internal Notes (textarea, min 20 chars). Two-step confirm per UX-11 (danger primary button labelled 'Refund transaction {hub_txn_ref}?'). On success show toast; on error show inline error message. | • Add Initiate Refund button to transaction detail page; visible only if GET /admin/v1/transactions/{id} returns is_refundable=true • Build refund modal component with Refund Amount, Reason Code, Internal Notes fields • Validate client-side: amount > 0 and <= original payout, notes >= 20 chars, reason code selected • Show two-step confirmation dialog with danger-styled primary button naming the hub_txn_ref • On confirm call POST /admin/v1/transactions/{id}/refund; show success toast or inline error • After success, refresh transaction status to reflect refund link | Refund initiation modal component wired to the transaction detail page | • Initiate Refund button is absent when transaction.status=FAILED • Attempting to submit with refund_amount=0 shows inline validation error before API call • Attempting to submit with internal_notes='short note' (< 20 chars) shows inline validation error • Confirmation dialog heading reads 'Refund transaction {hub_txn_ref}?' with danger (red) primary button • After successful submission, transaction detail page shows a link to the new refund record in REFUND_PENDING status | 55 | 10.8-T10 | FS | PRD-07
10.8-T16 | admin-ui | 10.8 | 10. Admin System | Refund/cancellation handling UI | 2 | Admin UI: same-day Cancel button on transaction detail page | PRD-07 §10.2: a Cancel button appears on the transaction detail page when status is COMMITTED or SUBMITTED_TO_SCHEME and the transaction was created today (KST). The button must be absent for post-settlement states. Two-step confirm dialog required (UX-11 danger pattern). On success transition displayed status to CANCELLED. For OVERSEAS partners the cancel result must confirm prefunding was reversed (show balance-after in success message). | • Add Cancel button to transaction detail page; show only when status in [COMMITTED, SUBMITTED_TO_SCHEME] and is_same_day=true from API • Build two-step cancel confirmation modal with danger-styled button labelled 'Cancel transaction {hub_txn_ref}?' • On confirm call POST /admin/v1/transactions/{id}/cancel • On success: update displayed status to CANCELLED; if partner is OVERSEAS display 'Prefunding balance restored' message • On error 409 or 422: show descriptive error (e.g. 'Transaction cannot be cancelled after settlement') • Hide Cancel button after successful cancellation; show Cancelled badge instead | Cancel button component on transaction detail page, wired to cancel endpoint | • Cancel button visible for COMMITTED transaction created today; absent for APPROVED transaction • Cancel button absent for transaction created on a prior KST date even if < 24h ago • Confirmation modal heading includes hub_txn_ref • After successful cancel, status badge shows CANCELLED and Cancel button is removed • FINANCE_ANALYST user sees no Cancel button (enforced client-side via role check; server also returns 403) | 45 | 10.8-T11 | FS | PRD-07
10.8-T17 | admin-ui | 10.8 | 10. Admin System | Refund/cancellation handling UI | 2 | Admin UI: Refunds module list page with status filters and batch sub-view | PRD-07 §3.1 defines a top-level Refunds navigation module. The main tab shows a paginated list (50/page) using GET /admin/v1/refunds. Columns (max 6 per UX-11): Refund Ref, Transaction Ref, Partner, Refund Amount (KRW), Status (badge), Initiated At. Filter bar: Status (multi-select), Partner (select), Date range. A secondary tab labelled 'Batches' shows the daily batch summary from GET /admin/v1/refunds/batches. All four roles can access this module (PRD-07 §12.3 View Refund Status). | • Create Refunds module page with two tabs: Refunds list and Batches • Implement Refunds list tab with filter bar and paginated table (columns: Refund Ref, Transaction Ref, Partner, Amount, Status, Initiated At) • Status column shows colour-coded badge (REFUND_PENDING=amber, REFUNDED=green, REFUND_FAILED=red) • Implement Batches tab with table (columns: Batch Date, Count, Total KRW, ZP0021 Status, ZP0022 Status, Breakdown) • Clicking a refund row navigates to GET /admin/v1/refunds/{id} detail page • Add Refunds link to persistent left sidebar navigation | Refunds module page with list and batch tabs in the admin portal UI | • Refunds list shows amber badge for REFUND_PENDING, green for REFUNDED, red for REFUND_FAILED • Filtering by status=REFUNDED shows only completed refunds • Batches tab shows one row per business day with ZP0021 and ZP0022 statuses • Table has no more than 6 columns (per UX-11 convention) • ADMIN_VIEWER user can navigate to the Refunds module and view the list (no 403) | 55 | 10.8-T12, 10.8-T14 | FS | PRD-07
10.8-T18 | admin-ui | 10.8 | 10. Admin System | Refund/cancellation handling UI | 2 | Admin UI: Refund detail page | Clicking a refund row in the Refunds module opens a detail page backed by GET /admin/v1/refunds/{id}. Fields to display: Refund Ref, status badge, Refund Amount + currency, Reason Code, Internal Notes, Initiated By, Initiated At, Linked Transaction (hub_txn_ref as link), Merchant Name, Partner Name, Scheme Refund Ref (when available from ZP0022), Status History timeline. For FAILED refunds show error message and a Retry Refund button (which calls POST /admin/v1/transactions/{txn_id}/refund again with same parameters, only for OPS_OPERATOR/SUPER_ADMIN). | • Create RefundDetailPage component fetching from GET /admin/v1/refunds/{id} • Display all fields listed in context with read-only layout • Render Status History as a chronological timeline (one entry per audit log event for this refund) • Show Retry Refund button only when status=REFUND_FAILED and user role is OPS_OPERATOR or SUPER_ADMIN • Wire Retry Refund button to POST /admin/v1/transactions/{txn_id}/refund with original parameters • Show scheme_refund_ref field when status=REFUND_CONFIRMED or REFUNDED | Refund detail page component rendered from GET /admin/v1/refunds/{id} | • Status History timeline shows events in ascending time order • scheme_refund_ref is displayed when status=REFUNDED but absent/empty when status=REFUND_PENDING • Retry Refund button is visible for REFUND_FAILED status with OPS_OPERATOR role; absent for ADMIN_VIEWER • Linked Transaction hub_txn_ref is a clickable link to the transaction detail page • Internal Notes field (min 20 chars) is fully displayed without truncation | 45 | 10.8-T13 | FS | PRD-07
10.8-T19 | admin-ui | 10.8 | 10. Admin System | Refund/cancellation handling UI | 2 | Add is_refundable and is_cancelable flags to transaction detail API response | The UI needs to know whether to show the Refund and Cancel buttons without duplicating eligibility logic client-side. Extend the GET /admin/v1/transactions/{id} response DTO to include: is_refundable (boolean): true iff RefundEligibilityService.checkEligibility returns ELIGIBLE; is_cancelable (boolean): true iff status in [COMMITTED, SUBMITTED_TO_SCHEME] and created_at_KST.date == today_KST.date. These flags are computed server-side on every detail page load (no caching). | • Extend TransactionDetailResponse DTO with is_refundable and is_cancelable boolean fields • In TransactionAdminController.getTransactionDetail, call RefundEligibilityService and evaluate cancellation window • Set is_refundable=true only when eligibility result is ELIGIBLE • Set is_cancelable=true only when status in [COMMITTED, SUBMITTED_TO_SCHEME] and same KST date • Add unit test cases covering each flag value combination • Update OpenAPI spec for the response schema | TransactionDetailResponse DTO with is_refundable and is_cancelable fields, populated server-side | • APPROVED transaction within 90-day window with no existing refund and active merchant returns is_refundable=true • FAILED transaction returns is_refundable=false • COMMITTED transaction created today returns is_cancelable=true; same transaction tomorrow returns is_cancelable=false • Transaction with status=APPROVED (post-scheme settlement) returns is_cancelable=false • Response is consistent with what RefundEligibilityService.checkEligibility returns (no logic duplication) | 35 | 10.8-T04, 10.8-T06 | FS | PRD-07
10.8-T20 | admin-ui | 10.8 | 10. Admin System | Refund/cancellation handling UI | 2 | Cron job: schedule ZP0021 batch generation at 02:00 KST daily | SCH-06 §6.2: ZP0021 must be transmitted to ZeroPay by 02:00 KST. A scheduled cron job must trigger Zp0021BatchGenerator.generateFile(previousBusinessDay) at 01:50 KST (10 minutes before deadline) and then SFTP-upload the file via the ZeroPay scheme adapter. The job must be idempotent: if re-run for the same settlement_date, it must detect the existing settlement_batch row and skip re-generation. If no REFUND_PENDING refunds exist, the job must still generate a file (empty body with header/trailer) and transmit it per ZeroPay requirements. | • Create Zp0021BatchJob @Scheduled(cron='50 1 * * *', zone='Asia/Seoul') • Check for existing settlement_batch row with file_type=ZP0021 and settlement_date=previousBusinessDay; skip if already SENT • Call Zp0021BatchGenerator.generateFile(previousBusinessDay) • Upload file via SchemeAdapter.sftpUpload(filePath, scheme=ZEROPAY) • Update settlement_batch/settlement_file status to SENT or FAILED • Log and alert Ops on any exception (P2 alert) | Zp0021BatchJob scheduled component with idempotency guard | • Running the job twice for the same settlement_date: second run detects existing settlement_batch with status=SENT and exits without generating a second file • Running the job when zero REFUND_PENDING refunds exist generates a valid file with header and trailer only (0 detail records) and transmits it • Job fires at 01:50 KST (verify via integration test with mocked clock) • SFTP upload failure sets settlement_batch.status=FAILED and emits an ops alert; job does not mark refunds as REFUND_SUBMITTED if upload fails • After a successful run, all refunds included in the file have status=REFUND_SUBMITTED | 45 | 10.8-T07 | FS | PRD-07
10.8-T21 | admin-ui | 10.8 | 10. Admin System | Refund/cancellation handling UI | 2 | Cron job: schedule ZP0022 result polling and processing at 05:00 KST daily | SCH-06 §6.3: ZeroPay delivers ZP0022 by ~05:00 KST. A scheduled job polls the SFTP inbound directory for a ZP0022 file for previousBusinessDay at 05:10 KST. If found, call Zp0022Processor.processFile. If not found by 05:30 KST, raise a P2 alert. Job must be idempotent: if ZP0022 was already processed for that date (settlement_file row exists with status=PROCESSED), skip. Mark settlement_file status=PROCESSED on success or FAILED on error. | • Create Zp0022PollingJob @Scheduled(cron='10 5 * * *', zone='Asia/Seoul') • Check settlement_file for file_type=ZP0022 and settlement_date; skip if already PROCESSED • Poll SFTP inbound path for a ZP0022 file matching the date pattern • If file found: call Zp0022Processor.processFile, update settlement_file status=PROCESSED • If file not found after 20-minute wait (retry twice at 5-minute intervals): log P2 alert and set status=MISSING • Add retry job at 05:30 KST if initial run finds no file | Zp0022PollingJob scheduled component with retry and idempotency logic | • If ZP0022 file found at 05:10: all refunds processed, settlement_file.status=PROCESSED, no second processing on retry • If file not found by 05:30: settlement_file.status=MISSING and an ops alert is emitted • Re-running after status=PROCESSED exits without reprocessing (idempotency) • Processing 3 refunds (2 success, 1 fail): 2 records reach REFUNDED/REFUND_CONFIRMED, 1 reaches REFUND_FAILED • Any exception during processFile sets settlement_file.status=FAILED (not PROCESSED) and emits ops alert | 45 | 10.8-T08 | FS | PRD-07
10.8-T22 | admin-ui | 10.8 | 10. Admin System | Refund/cancellation handling UI | 2 | Unit tests: RefundEligibilityService — all eligibility branches | 10.8-T04 implements RefundEligibilityService. This ticket adds exhaustive unit tests covering all 5 eligibility branches using JUnit 5 + Mockito. Exact test vectors must cover boundary conditions for the refund window calculation. Reference data: refund_window_days=90 (ZeroPay default). KST timezone: ZoneId.of('Asia/Seoul'). | • Create RefundEligibilityServiceTest class • Test NOT_ELIGIBLE_STATUS: transaction.status=FAILED returns NOT_ELIGIBLE_STATUS • Test NOT_ELIGIBLE_WINDOW boundary: transaction created exactly 90 days ago (same time) → ELIGIBLE; 90 days + 1 second ago → NOT_ELIGIBLE_WINDOW • Test ALREADY_REFUNDED: existing refund with status=REFUND_PENDING → ALREADY_REFUNDED; existing refund with status=REFUND_FAILED only → ELIGIBLE • Test MERCHANT_INACTIVE: merchant.is_active=false → MERCHANT_INACTIVE • Test ELIGIBLE: all conditions pass → ELIGIBLE | RefundEligibilityServiceTest with ≥ 8 test methods covering all branches and boundary cases | • All 8+ test methods pass in CI • Boundary: created_at = now minus exactly 90 days → ELIGIBLE (not yet expired at the boundary) • Boundary: created_at = now minus 90 days and 1 second → NOT_ELIGIBLE_WINDOW • Test for ALREADY_REFUNDED with REFUND_FAILED existing refund returns ELIGIBLE (retry allowed) • 100% branch coverage on checkEligibility method (verified by JaCoCo or equivalent) | 45 | 10.8-T04 | FS | PRD-07
10.8-T23 | admin-ui | 10.8 | 10. Admin System | Refund/cancellation handling UI | 2 | Unit tests: RefundInitiationService — amount validation and duplicate guard | 10.8-T05 implements RefundInitiationService. Unit tests must cover: (a) amount validation (exact boundary: refund_amount == target_payout passes; refund_amount = target_payout + 0.0001 fails for KRW since KRW has 0 decimal precision), (b) duplicate guard (ALREADY_REFUNDED), (c) partial refund (refund_amount = 5000 on a 10000 KRW transaction), (d) audit log entry written on success, (e) transaction status NOT updated to REFUND_PENDING. | • Create RefundInitiationServiceTest with mocked RefundEligibilityService and RefundRepository • Test full-amount refund: amount = 10000 KRW on 10000 KRW txn → success, refund.status=REFUND_PENDING • Test partial refund: amount = 5000 KRW on 10000 KRW txn → success • Test amount exceeded: amount = 10001 KRW on 10000 KRW txn → RefundAmountExceededException • Test duplicate call: second initiateRefund on same txnId with existing REFUND_PENDING → exception • Test audit log: verify AuditLogService.log called with event_type=refund.initiated and correct entity fields • Test ineligible transaction: eligibility returns NOT_ELIGIBLE_STATUS → RefundNotEligibleException | RefundInitiationServiceTest with ≥ 7 test methods | • All 7+ test methods pass • Amount = 10001 KRW on 10000 KRW transaction throws RefundAmountExceededException (not passes) • Transaction status is NOT changed by initiateRefund (verified by asserting no updateStatus call on transaction) • AuditLogService.log is called exactly once per successful initiation • refund_ref generated by service matches expected format 'RFD-{hub_txn_ref}-{millis}' | 40 | 10.8-T05 | FS | PRD-07
10.8-T24 | admin-ui | 10.8 | 10. Admin System | Refund/cancellation handling UI | 2 | Unit tests: Zp0021BatchGenerator — file layout and edge cases | 10.8-T07 implements Zp0021BatchGenerator. Tests must verify fixed-width field formatting, empty-batch handling, and status transition. Key format rule: refund_amount_krw is NUM(12) right-justified zero-padded. Reason code mapping: CUSTOMER_REQUEST→'CR', MERCHANT_ERROR→'ME', SETTLEMENT_ERROR→'SE' (use scheme-defined codes; confirm mapping in implementation; use those codes in tests). Partner type: D for Domestic (LOCAL), I for International (OVERSEAS). | • Create Zp0021BatchGeneratorTest • Test single-record file: KRW 10000 refund produces refund_amount_krw='000000010000' (12 chars) • Test record partner_type: LOCAL partner → 'D'; OVERSEAS → 'I' • Test empty batch: 0 REFUND_PENDING records → file with only header and trailer, record count = 0 • Test status transition: after generateFile, all included refunds have status=REFUND_SUBMITTED • Test idempotency guard: calling generateFile twice for same date returns existing file without creating second settlement_batch row | Zp0021BatchGeneratorTest with ≥ 6 test methods validating file format and state transitions | • refund_amount_krw for KRW 1 is '000000000001' (12 chars, right-justified zero-padded) • refund_amount_krw for KRW 999999999999 is '999999999999' (maximum 12-digit value fits) • Empty-batch file has exactly 2 lines (header + trailer) with trailer record_count=0 • After generateFile, refund rows included in file have status=REFUND_SUBMITTED; a refund created after batch cutoff remains REFUND_PENDING • File header contains file_type='ZP0021' | 45 | 10.8-T07 | FS | PRD-07
10.8-T25 | admin-ui | 10.8 | 10. Admin System | Refund/cancellation handling UI | 2 | Unit tests: Zp0022Processor — result code handling and idempotency | 10.8-T08 implements Zp0022Processor. Tests must verify: success path (result_code=00), failure path (result_code != 00), amount mismatch exception, missing refund ref handling, and idempotency (reprocessing same file does not double-apply). Use representative test data matching ZP0022 field layout. | • Create Zp0022ProcessorTest • Test success: record with result_code=00 → refund.status=REFUND_CONFIRMED, scheme_refund_ref populated, audit log written • Test failure: result_code=01 → refund.status=REFUND_FAILED, Ops alert emitted • Test amount mismatch: registered_refund_amount=9000 vs refund.refund_amount=10000 → AMOUNT_MISMATCH exception record created, refund stays REFUND_SUBMITTED • Test missing ref: gme_refund_id not found in DB → MISSING_REFUND_REF logged, processing continues without exception • Test idempotency: reprocessing file with already-REFUNDED refund → no second audit log entry or prefunding reversal | Zp0022ProcessorTest with ≥ 6 test methods | • result_code=00 transitions refund to REFUND_CONFIRMED in test • result_code=01 transitions refund to REFUND_FAILED in test • Amount mismatch does NOT set status to REFUND_CONFIRMED • Idempotency test: processFile called twice with same file does not create 2 audit log entries for the same refund • Missing gme_refund_id does not throw uncaught exception; test completes with MISSING_REFUND_REF log entry | 45 | 10.8-T08 | FS | PRD-07
10.8-T26 | admin-ui | 10.8 | 10. Admin System | Refund/cancellation handling UI | 2 | Unit tests: RefundCompletionService — prefunding reversal math for OVERSEAS | 10.8-T09 implements RefundCompletionService. Test the USD reversal computation: reversal_usd = refund_amount_krw / locked cost_rate_pay (from transaction). Representative vector: KRW 10000 refund, locked cost_rate_pay = 1350.000000 (treasury.usd_krw at commit time), expected reversal_usd = 10000 / 1350.000000 = 7.40740740... USD stored to 8 decimal places (7.40740741 after rounding). Also test LOCAL partner skip, idempotency, and concurrent call protection. | • Create RefundCompletionServiceTest • Test OVERSEAS: KRW 10000 / cost_rate_pay 1350.0 = reversal_usd 7.40740741 (BigDecimal HALF_UP 8 dp) • Test OVERSEAS: KRW 5000 / cost_rate_pay 1380.0 = 3.62318841 USD (verify to 8 dp) • Test LOCAL: applyCompletion for LOCAL partner creates no prefunding_ledger_entry, sets status=REFUNDED • Test idempotency: calling applyCompletion on already-REFUNDED record exits without creating duplicate ledger entry • Test concurrent lock: mock SELECT FOR UPDATE contention → second call waits or retries, final balance correct | RefundCompletionServiceTest with ≥ 5 test methods covering math and edge cases | • KRW 10000 / 1350.0 yields BigDecimal 7.40740741 (8 decimal places, HALF_UP rounding) • KRW 5000 / 1380.0 yields BigDecimal 3.62318841 • LOCAL partner test has zero calls to prefunding ledger repository • Idempotency: second call to applyCompletion returns without error and ledger has exactly 1 REFUND_REVERSAL entry • Status transitions from REFUND_CONFIRMED to REFUNDED in both OVERSEAS and LOCAL cases | 40 | 10.8-T09 | FS | PRD-07
10.8-T27 | admin-ui | 10.8 | 10. Admin System | Refund/cancellation handling UI | 2 | Integration test: full refund lifecycle E2E (initiate -> ZP0021 -> ZP0022 -> complete) | End-to-end test covering the complete Phase 1 refund path: (1) create an APPROVED OVERSEAS transaction with locked cost_rate_pay=1350, target_payout=KRW 10000; (2) call POST /admin/v1/transactions/{id}/refund with amount=KRW 10000, reason=CUSTOMER_REQUEST, notes='Test refund for customer request integration'; (3) run Zp0021BatchGenerator for that date and verify file contains the refund; (4) feed a synthetic ZP0022 success response with result_code=00; (5) call Zp0022Processor; (6) verify final state: refund.status=REFUNDED, prefunding_ledger_entry REFUND_REVERSAL = 7.40740741 USD, transaction.status unchanged (still APPROVED). | • Create RefundLifecycleIntegrationTest using @SpringBootTest with test DB • Insert a test APPROVED OVERSEAS (SendMN) transaction with target_payout=10000 KRW, locked cost_rate_pay=1350.000000 • Call POST /admin/v1/transactions/{id}/refund via MockMvc; assert 201 and refund.status=REFUND_PENDING • Run Zp0021BatchGenerator; assert file generated, refund.status=REFUND_SUBMITTED • Synthesize ZP0022 success record; call Zp0022Processor.processFile • Assert refund.status=REFUNDED, prefunding_ledger_entry.amount=7.40740741, transaction.status=APPROVED (unchanged) | RefundLifecycleIntegrationTest with full lifecycle covered in a single test scenario | • All 6 lifecycle steps pass in sequence with no intermediate failures • Final refund.status=REFUNDED • Final prefunding_ledger_entry.amount=7.40740741 USD (8 decimal places) • transaction.status remains APPROVED throughout (not modified by refund flow) • Audit log contains 3 entries for this refund_id: refund.initiated, refund.confirmed, refund.completed | 55 | 10.8-T05, 10.8-T07, 10.8-T08, 10.8-T09 | FS | PRD-07
10.8-T28 | admin-ui | 10.8 | 10. Admin System | Refund/cancellation handling UI | 2 | Integration test: same-day cancel lifecycle E2E (OVERSEAS, prefunding reversal) | Test portal cancel for an OVERSEAS partner (SendMN): (1) insert COMMITTED transaction with prefunding deduction of collection_amount=2.00 USD, (2) call POST /admin/v1/transactions/{id}/cancel (same KST day), (3) assert transaction.status=CANCELLED, (4) assert prefunding_ledger_entry REFUND_REVERSAL with amount=+2.00 USD, (5) assert prefunding_account.balance increased by 2.00 USD. Also test that cancel is rejected if called the following KST day (transaction.created_at set to yesterday KST). | • Create CancellationIntegrationTest using @SpringBootTest with test DB • Insert COMMITTED OVERSEAS transaction with prefunding_deduction=2.00 USD and today KST date • Call POST /admin/v1/transactions/{id}/cancel; assert 200 and status=CANCELLED • Assert prefunding_ledger_entry type=REFUND_REVERSAL amount=2.00 USD created • Assert prefunding_account.balance increased by 2.00 USD • Repeat with created_at set to yesterday KST; assert 422 response | CancellationIntegrationTest covering same-day success and prior-day rejection | • Same-day cancel returns 200, transaction.status=CANCELLED, prefunding_ledger_entry.amount=+2.00 USD • Prior-day cancel returns 422 • LOCAL partner same-day cancel returns 200 with no prefunding_ledger_entry • Audit log contains event_type=transaction.cancelled with actor_user_id matching test user • Calling cancel a second time on an already-CANCELLED transaction returns 409 | 50 | 10.8-T06, 10.8-T11 | FS | PRD-07
10.8-T29 | admin-ui | 10.8 | 10. Admin System | Refund/cancellation handling UI | 2 | RBAC enforcement tests: verify permission matrix for refund and cancel actions | PRD-07 §12.3: Initiate Refund and admin Cancel require OPS_OPERATOR or SUPER_ADMIN. FINANCE_ANALYST and ADMIN_VIEWER must receive 403. View Refund Status (GET /admin/v1/refunds, GET /admin/v1/refunds/{id}, GET /admin/v1/refunds/batches) must be accessible to all four roles. Tests should use Spring Security test utilities with role mocking. | • Create RefundRbacTest using @SpringBootTest + @WithMockUser • Test POST /admin/v1/transactions/{id}/refund with FINANCE_ANALYST → 403 • Test POST /admin/v1/transactions/{id}/refund with ADMIN_VIEWER → 403 • Test POST /admin/v1/transactions/{id}/cancel with FINANCE_ANALYST → 403 • Test GET /admin/v1/refunds with ADMIN_VIEWER → 200 • Test GET /admin/v1/refunds/{id} with ADMIN_VIEWER → 200 • Test GET /admin/v1/refunds/batches with FINANCE_ANALYST → 200 | RefundRbacTest class with ≥ 7 role/endpoint combinations verified | • FINANCE_ANALYST POST /refund returns 403 • ADMIN_VIEWER POST /cancel returns 403 • ADMIN_VIEWER GET /refunds returns 200 (not 403) • SUPER_ADMIN POST /refund returns 201 (not 403) • Unauthenticated POST /refund returns 401 (not 403) | 35 | 10.8-T10, 10.8-T11, 10.8-T12, 10.8-T13, 10.8-T14 | FS | PRD-07
10.8-T30 | admin-ui | 10.8 | 10. Admin System | Refund/cancellation handling UI | 2 | Ops alert: notify Ops when ZP0022 refund registration fails or file missing | PRD-07 §10.3.4 and SCH-06 §6.4: when ZP0022 returns a failed result_code for a refund, an Ops alert must be sent. Also, if ZP0022 file is not received by 05:30 KST, a P2 alert fires. Use the existing notification service (email to Ops alert recipients or portal in-app notification). Alert content must include: refund_ref, hub_txn_ref, failure reason, current timestamp. An AMOUNT_MISMATCH exception must also trigger an alert and create an exception queue record visible in the Admin portal. | • Extend Zp0022Processor to call NotificationService.sendOpsAlert on REFUND_FAILED outcome • Alert body must include: refund_ref, hub_txn_ref, result_code, result_message, current KST timestamp • For AMOUNT_MISMATCH: insert an exception_record row and call NotificationService.sendOpsAlert with discrepancy details • Extend Zp0022PollingJob to call NotificationService.sendOpsAlert when status=MISSING (file not received by 05:30 KST) • Write unit test: mock Zp0022Processor with REFUND_FAILED outcome; assert NotificationService.sendOpsAlert called with correct arguments | Ops alert wiring in Zp0022Processor and Zp0022PollingJob, with unit test | • REFUND_FAILED outcome triggers NotificationService.sendOpsAlert exactly once with refund_ref and hub_txn_ref in message • AMOUNT_MISMATCH outcome creates an exception_record row with discrepancy_amount = ¦registered - submitted¦ and triggers an alert • ZP0022 file not received by 05:30 KST sets settlement_file.status=MISSING and triggers a P2 ops alert • Successful refund (result_code=00) does NOT trigger any alert • Alert for missing file includes the expected_arrival_time=05:00 KST in the message body | 40 | 10.8-T08, 10.8-T21 | FS | PRD-07
10.8-T31 | admin-ui | 10.8 | 10. Admin System | Refund/cancellation handling UI | 2 | Admin portal docs: developer README for refund/cancellation module | A developer joining the team needs to understand how to run the refund batch locally, simulate ZP0022 responses in dev/sandbox, and understand the state machine transitions. Document: (1) how to manually trigger Zp0021BatchJob in local dev, (2) how to place a synthetic ZP0022 file in the SFTP mock directory to trigger Zp0022PollingJob, (3) the full refund state machine diagram (REFUND_PENDING->REFUND_SUBMITTED->REFUND_CONFIRMED->REFUNDED and REFUND_FAILED branch), (4) RBAC summary table for refund/cancel actions, (5) how partial refunds work (amount < original). Place in docs/admin-portal/refund-cancellation.md. | • Create docs/admin-portal/refund-cancellation.md • Section 1: Refund state machine (ASCII diagram showing all 5 states and transitions) • Section 2: Cancellation flow (same-day window rule, KST timezone note, prefunding reversal for OVERSEAS) • Section 3: Running batches locally (curl/CLI commands to trigger Zp0021BatchJob and place ZP0022 mock file) • Section 4: RBAC table for refund/cancel/view actions per role • Section 5: Partial refund rules and examples | docs/admin-portal/refund-cancellation.md covering state machine, batch ops, RBAC, and partial refunds | • State machine diagram shows all 5 refund statuses and valid transitions • Cancellation window rule is documented: same KST calendar date as creation, not rolling 24h • Local dev instructions include the exact command to trigger Zp0021BatchJob outside of cron • RBAC table lists all 4 roles with Y/N for Initiate Refund, Cancel, View Refund Status • Partial refund example: original KRW 10000, partial refund KRW 3000, partial refund succeeds | 35 | 10.8-T09, 10.8-T16, 10.8-T17 | FS | PRD-07
10.9-T01 | admin-ui | 10.9 | 10. Admin System | Settlement & revenue dashboards | 2 | Define SettlementBatchDTO and RevenueReportDTO interface contracts | WBS 10.9 builds the Settlement & Revenue UI module (PRD-07 §11). The backend must expose two primary read models: (1) SettlementBatchDTO: settlement_date (DATE/KST), scheme_id, file_type (ZP0011/ZP0021/ZP0061/ZP0062/ZP0063/ZP0064/ZP0065/ZP0066), direction (GME_TO_ZP¦ZP_TO_GME), status (PENDING/GENERATED/TRANSMITTED/RECEIVED/RECONCILED/ERROR), transaction_count, total_amount, total_amount_ccy, transmitted_at, received_at, reconciled_at, error_detail. (2) RevenueReportRowDTO: period, partner_id, partner_name, scheme_id, transaction_count, gross_payout_krw, merchant_fee_total_krw, gme_scheme_share_krw (70% of net merchant fee), collection_margin_usd, payout_margin_usd, total_fx_margin_usd, service_charges_settle_a_ccy, service_charge_ccy, total_revenue_krw_equiv. Both DTOs must be documented as Java interfaces/records in the admin-service module. | • Create SettlementBatchDTO as a Java record with all fields listed in context; use BigDecimal for monetary amounts, LocalDate for settlement_date, OffsetDateTime for timestamps • Create RevenueReportRowDTO as a Java record with all fields listed in context; total_revenue_krw_equiv is derived (scheme_share + fx_margin_converted + service_charge_converted) • Create RevenueReportSummaryDTO containing List<RevenueReportRowDTO> rows and summary totals: total_gme_scheme_share_krw, total_fx_margin_usd, total_service_charges, grand_total_revenue_krw_equiv • Create SettlementBatchListDTO as a paged wrapper (content, totalElements, page, size) • Add Javadoc to each DTO field referencing the source column in settlement_batch or revenue_record tables | Java records SettlementBatchDTO, RevenueReportRowDTO, RevenueReportSummaryDTO, SettlementBatchListDTO in admin-service/src/main/java/.../dto/settlement/ package | • SettlementBatchDTO compiles with all 14 required fields; no field omitted • RevenueReportRowDTO contains exactly collection_margin_usd and payout_margin_usd as separate BigDecimal fields (not combined) and a separate total_fx_margin_usd field • total_revenue_krw_equiv field is present in RevenueReportRowDTO and its Javadoc notes it is derived from scheme_share + converted FX margin + converted service charge • RevenueReportSummaryDTO contains a List<RevenueReportRowDTO> and three BigDecimal summary totals • All DTO classes are immutable records (no setters) | 30 |  | FS | PRD-07
10.9-T02 | admin-ui | 10.9 | 10. Admin System | Settlement & revenue dashboards | 2 | Define RevenueReportFilterDTO and BatchStatusFilterDTO query parameter objects | The Settlement & Revenue UI supports filters. Revenue report (PRD-07 §11.3.2): period type (DAILY/WEEKLY/MONTHLY/CUSTOM), date_from, date_to, partner_id (nullable), scheme_id (nullable), direction (nullable), revenue_stream (SCHEME_FEE¦FX_MARGIN¦ALL). Settlement batch filter (PRD-07 §11.2.2): settlement_date, scheme_id (nullable). These are validated query param POJOs used by AdminSettlementController. | • Create RevenueReportFilterDTO with fields: periodType (enum DAILY/WEEKLY/MONTHLY/CUSTOM), dateFrom (LocalDate), dateTo (LocalDate), partnerId (Long nullable), schemeId (Long nullable), direction (enum INBOUND/OUTBOUND/DOMESTIC/HUB nullable), revenueStream (enum SCHEME_FEE/FX_MARGIN/ALL, default ALL) • Add Bean Validation: @NotNull on periodType, dateFrom, dateTo; custom cross-field validator that dateTo >= dateFrom and date range <= 366 days • Create SettlementBatchFilterDTO with: settlementDate (LocalDate, @NotNull), schemeId (Long nullable) • Add unit test: RevenueReportFilterDTOValidationTest verifies (a) missing dateFrom fails validation, (b) dateTo before dateFrom fails, (c) range of 400 days fails, (d) valid 30-day MONTHLY filter passes | RevenueReportFilterDTO, SettlementBatchFilterDTO POJOs with validation annotations; RevenueReportFilterDTOValidationTest | • Validator rejects dateTo=2026-05-01 with dateFrom=2026-06-01 (reversed range) • Validator rejects date range of 400 days • Validator accepts dateFrom=2026-05-01 dateTo=2026-05-31 with periodType=MONTHLY • partnerId and schemeId are nullable and absence does not fail validation • revenueStream defaults to ALL when not supplied | 25 | 10.9-T01 | FS | PRD-07
10.9-T03 | admin-ui | 10.9 | 10. Admin System | Settlement & revenue dashboards | 2 | Create AdminSettlementController REST endpoints skeleton | The Admin System backend (admin-service) exposes a REST API consumed by the frontend. PRD-07 §11 requires two groups of endpoints: (A) Settlement batch status: GET /admin/settlement/batches?settlementDate=&schemeId= returning SettlementBatchListDTO. (B) Revenue reporting: GET /admin/revenue/report?[filter params] returning RevenueReportSummaryDTO; GET /admin/revenue/export/csv?[same params] returning a streaming CSV download. Access control: FINANCE_ANALYST, OPS_OPERATOR, SUPER_ADMIN roles may call GET; no write endpoints in this module. | • Create AdminSettlementController in admin-service with @RestController @RequestMapping('/admin/settlement') • Add GET /batches endpoint accepting SettlementBatchFilterDTO as @ModelAttribute; return ResponseEntity<SettlementBatchListDTO>; stub with empty list • Create AdminRevenueController with @RequestMapping('/admin/revenue') • Add GET /report accepting RevenueReportFilterDTO; return ResponseEntity<RevenueReportSummaryDTO>; stub with empty summary • Add GET /export/csv accepting same filter; set Content-Type: text/csv, Content-Disposition: attachment; filename=revenue_report_{dateFrom}_{dateTo}.csv; stub returns empty CSV with header row • Annotate all endpoints with @PreAuthorize('hasAnyRole(SUPER_ADMIN,OPS_OPERATOR,FINANCE_ANALYST)') | AdminSettlementController and AdminRevenueController classes with three stubbed endpoints and role-based security annotations | • GET /admin/settlement/batches without authentication returns 401 • GET /admin/settlement/batches with ADMIN_VIEWER role returns 403 • GET /admin/settlement/batches with FINANCE_ANALYST role returns 200 (empty list) • GET /admin/revenue/export/csv with valid filter returns Content-Type: text/csv header • Endpoint GET /admin/revenue/report returns RevenueReportSummaryDTO shape (empty) with HTTP 200 | 35 | 10.9-T01, 10.9-T02 | FS | PRD-07
10.9-T04 | admin-ui | 10.9 | 10. Admin System | Settlement & revenue dashboards | 2 | Implement SettlementBatchQueryService - fetch batch status by date and scheme | The settlement_batch table (DAT-03 §7.1 / §10.5) stores one row per daily batch run per scheme per file type. Columns used: id, scheme_id, file_type (ZP0011/ZP0021/ZP0061/ZP0062/ZP0063/ZP0064/ZP0065/ZP0066), direction, settlement_date (KST DATE), window, status (PENDING/GENERATED/TRANSMITTED/RECEIVED/RECONCILED/ERROR), transaction_count, total_amount, total_amount_ccy, transmitted_at, received_at, reconciled_at, error_detail. The UI shows a row-per-date view with one column per file type status. The daily timeline is: ZP0011 ~02:00, ZP0012 ~05:00, ZP0061 ~05:00, ZP0062 ~10:00, ZP0063 ~14:00, ZP0064 ~19:00, ZP0065 ~22:00, ZP0066 ~22:00 (all KST). | • Create SettlementBatchQueryService with method List<SettlementBatchDTO> getBatchesByDate(LocalDate settlementDate, Long schemeId) • Implement JPQL query: SELECT b FROM SettlementBatch b WHERE b.settlementDate = :date AND (:schemeId IS NULL OR b.schemeId = :schemeId) ORDER BY b.fileType • Map JPA entity fields to SettlementBatchDTO; ensure BigDecimal is used for total_amount; preserve null transmitted_at/received_at/reconciled_at as null in DTO • Add a second method SettlementBatchSummaryDTO getBatchSummaryForDate(LocalDate date) that returns aggregate: total transaction_count, total gross payout KRW across all ZP006x batches for that date • Handle edge case: if no rows exist for a given date/scheme combination return empty list (not 404) | SettlementBatchQueryService class with two public methods; backed by SettlementBatchRepository JPA repository | • Given settlement_date=2026-06-01 with ZP0061 status=TRANSMITTED and ZP0062 status=RECEIVED, the returned list contains exactly two DTOs with correct statuses • When schemeId=null the method returns batches across all schemes for the date • When no rows exist for date=2026-06-01, method returns empty list without throwing • total_amount in DTO for a batch row with total_amount=12345678.0 returns BigDecimal with value 12345678.00 (2dp after mapping) • getBatchSummaryForDate correctly sums transaction_count across ZP0065 and ZP0066 file types only | 40 | 10.9-T01 | FS | PRD-07
10.9-T05 | admin-ui | 10.9 | 10. Admin System | Settlement & revenue dashboards | 2 | Implement ReconciliationQueryService - fetch and aggregate reconciliation items | The reconciliation_item table (DAT-03 §7.3) has: id, batch_id (FK settlement_batch), txn_ref, scheme_ref, match_status (MATCHED/DISCREPANCY/MISSING_GME/MISSING_SCHEME), gme_amount, scheme_amount, discrepancy_amount, ccy, resolution_status (UNRESOLVED/RESOLVED/ESCALATED), resolved_by, resolved_at, resolution_note. The UI (PRD-07 §11.2.3) shows reconciliation_status per batch as Matched/Discrepancy/Pending, and allows drilldown to flagged items. An auto-flag occurs for: MISSING_IN_SCHEME (txn present in GME but absent from ZP0062/ZP0064), AMOUNT_MISMATCH (¦gme_amount - scheme_amount¦ > 0), SCHEME_REJECTION (scheme explicitly rejected the txn). | • Create ReconciliationQueryService with method ReconciliationSummaryDTO getReconciliationSummaryForBatch(Long batchId) • ReconciliationSummaryDTO contains: batchId, totalItems, matchedCount, discrepancyCount, missingInSchemeCount, missingInGmeCount, unresolvedCount, overallStatus (MATCHED if discrepancyCount+missingCount=0, DISCREPANCY otherwise, PENDING if no items yet) • Add method Page<ReconciliationItemDTO> getDiscrepancyItems(Long batchId, Pageable pageable) returning only non-MATCHED items • Add method void markResolved(Long itemId, String operatorId, String note) that sets resolution_status=RESOLVED, resolved_by, resolved_at=now(); audit-logs the action with entity_type='reconciliation_item' • Handle edge: batchId not found -> throw ReconciliationNotFoundException (maps to 404) | ReconciliationQueryService with four methods; ReconciliationSummaryDTO; ReconciliationItemDTO | • Given batch with 100 items: 95 MATCHED, 3 AMOUNT_MISMATCH, 2 MISSING_IN_SCHEME, overallStatus=DISCREPANCY • Given batch with 100 items all MATCHED, overallStatus=MATCHED • Given batch with 0 reconciliation_items, overallStatus=PENDING • markResolved on already-RESOLVED item throws AlreadyResolvedException (not silently succeeds) • getDiscrepancyItems with batchId that has only MATCHED items returns empty page | 45 | 10.9-T01 | FS | PRD-07
10.9-T06 | admin-ui | 10.9 | 10. Admin System | Settlement & revenue dashboards | 2 | Implement RevenueReportQueryService - aggregate revenue_record by filter | The revenue_record table (DAT-03 §8.2) has: id, txn_id (FK transaction), partner_id, scheme_id, revenue_date (DATE), fx_margin_usd (=collection_margin_usd+payout_margin_usd as DECIMAL(20,4)), service_charge_amount (DECIMAL(20,4)), service_charge_ccy (CHAR(3)), fee_share_pct (DECIMAL(6,4), e.g. 0.7000 for 70%), estimated_fee_share_usd (DECIMAL(20,4)). The report groups rows by (period, partner, scheme) and aggregates. total_fx_margin_usd = SUM(fx_margin_usd). gme_scheme_share = SUM(estimated_fee_share_usd). service_charges in settle_a_ccy = SUM(service_charge_amount) grouped by service_charge_ccy. total_revenue_krw_equiv = (gme_scheme_share + total_fx_margin_usd) converted using current treasury.usd_krw rate, plus service_charge_amount if service_charge_ccy=KRW. Filtering: dateFrom/dateTo on revenue_date; partnerId optional; schemeId optional; direction via JOIN to transaction.direction; revenueStream: SCHEME_FEE hides fx_margin columns, FX_MARGIN hides scheme_share column. | • Create RevenueReportQueryService with method RevenueReportSummaryDTO getReport(RevenueReportFilterDTO filter) • Build JPQL aggregation: SELECT rr.partner_id, rr.scheme_id, COUNT(rr.id), SUM(rr.fx_margin_usd), SUM(rr.estimated_fee_share_usd), SUM(rr.service_charge_amount), rr.service_charge_ccy GROUP BY rr.partner_id, rr.scheme_id, rr.service_charge_ccy WHERE rr.revenue_date BETWEEN :from AND :to AND (:partnerId IS NULL OR rr.partner_id=:partnerId) • Join to transaction to filter by direction when filter.direction is non-null • Fetch current treasury rate usd_krw from treasury_rate table for KRW conversion in total_revenue_krw_equiv calculation; use BigDecimal multiply, scale to 0 (KRW has 0 decimal places) • Build summary totals across all rows; return RevenueReportSummaryDTO with list of rows and aggregated totals • When revenueStream=SCHEME_FEE, zero out fx_margin fields in each row DTO; when FX_MARGIN, zero out gme_scheme_share_krw | RevenueReportQueryService class with getReport(RevenueReportFilterDTO) method | • Given 3 revenue_record rows for partner SendMN on 2026-06-01: fx_margin_usd=[1.00, 2.00, 1.50], estimated_fee_share_usd=[0.50, 0.50, 0.50], getReport returns total_fx_margin_usd=4.50 and gme_scheme_share sum=1.50 for that partner • When filter.revenueStream=SCHEME_FEE the returned rows have total_fx_margin_usd=0.00 • When filter.revenueStream=FX_MARGIN the returned rows have gme_scheme_share_krw=0 • Conversion: total_fx_margin_usd=100.00 with usd_krw=1350.42 yields total_revenue_krw_equiv contribution of 135042 KRW (rounded to 0 dp) • Filter by direction=INBOUND returns only revenue_records whose linked transaction.direction='INBOUND' | 55 | 10.9-T01, 10.9-T02 | FS | PRD-07
10.9-T07 | admin-ui | 10.9 | 10. Admin System | Settlement & revenue dashboards | 2 | Wire settlement batch query service into AdminSettlementController | AdminSettlementController.getBatches() (created in T03) currently returns an empty stub. It must call SettlementBatchQueryService.getBatchesByDate(). The controller accepts SettlementBatchFilterDTO (@ModelAttribute), validates it, calls the service, and returns SettlementBatchListDTO. Pagination: the list is small (max 10 file-type rows per date per scheme) so no DB-level pagination is needed; the wrapper DTO provides totalElements for frontend parity. | • Inject SettlementBatchQueryService into AdminSettlementController • Replace stub implementation: validate SettlementBatchFilterDTO (@Valid); call getBatchesByDate(filter.settlementDate, filter.schemeId) • Wrap result in SettlementBatchListDTO with totalElements=list.size(), page=0, size=list.size() • Add @ExceptionHandler for MethodArgumentNotValidException returning HTTP 400 with field-level error map • Write integration test: AdminSettlementControllerIT seeds two settlement_batch rows for 2026-06-01 (ZP0061 TRANSMITTED, ZP0062 RECEIVED) and verifies GET /admin/settlement/batches?settlementDate=2026-06-01 returns 200 with content array size=2 and correct statuses | Updated AdminSettlementController.getBatches() fully wired; AdminSettlementControllerIT integration test | • GET /admin/settlement/batches?settlementDate=2026-06-01 with seeded rows returns HTTP 200 and content[].length=2 • Returned DTO contains file_type=ZP0061 with status=TRANSMITTED and file_type=ZP0062 with status=RECEIVED • GET /admin/settlement/batches without settlementDate param returns HTTP 400 with error on field settlementDate • ADMIN_VIEWER JWT returns HTTP 403 • GET /admin/settlement/batches?settlementDate=2026-06-01&schemeId=999 (no matching rows) returns 200 with empty content list | 40 | 10.9-T03, 10.9-T04 | FS | PRD-07
10.9-T08 | admin-ui | 10.9 | 10. Admin System | Settlement & revenue dashboards | 2 | Wire revenue report query service into AdminRevenueController | AdminRevenueController.getReport() (T03 stub) must call RevenueReportQueryService.getReport(filter). Validation is via @Valid on RevenueReportFilterDTO. The endpoint returns RevenueReportSummaryDTO as JSON. The summary DTO includes totals row and a list of per-partner-scheme rows. KRW values must be serialized as integers (0 decimal places per currency scale rules); USD values as strings with 4 decimal places to avoid floating-point loss. | • Inject RevenueReportQueryService into AdminRevenueController • Replace stub: call service.getReport(filter), return ResponseEntity.ok(summary) • Configure Jackson serializer: BigDecimal fields with _krw suffix serialized as rounded integer strings; _usd suffix fields serialized with 4 decimal places • Add @ExceptionHandler for validation errors: return HTTP 400 with errors map • Write AdminRevenueControllerIT: seed 5 revenue_record rows for May 2026 and verify GET /admin/revenue/report?periodType=MONTHLY&dateFrom=2026-05-01&dateTo=2026-05-31 returns correct totals • Verify that the response body total_revenue_krw_equiv rounds to nearest whole KRW (no decimal point in JSON) | Updated AdminRevenueController.getReport() fully wired; AdminRevenueControllerIT | • GET /admin/revenue/report with 5 seeded rows returns HTTP 200 with rows[].length matching distinct partner-scheme combos • JSON field total_fx_margin_usd serialized as '4.5000' (4dp string) not as float 4.5 • JSON field total_revenue_krw_equiv serialized as integer 135042 not 135042.00 • GET /admin/revenue/report without dateFrom returns HTTP 400 • Request with dateTo before dateFrom returns HTTP 400 with message referencing the cross-field rule | 40 | 10.9-T03, 10.9-T06 | FS | PRD-07
10.9-T09 | admin-ui | 10.9 | 10. Admin System | Settlement & revenue dashboards | 2 | Implement CSV export endpoint for revenue report | GET /admin/revenue/export/csv (stubbed in T03) must stream a CSV file. Columns (PRD-07 §11.3.2): Period, Partner, Scheme, Transaction Count, Gross Payout (KRW), Merchant Fee Total (KRW), GME Scheme Share (KRW), Collection Margin (USD), Payout Margin (USD), Total FX Margin (USD), Service Charges (Settle A ccy), Service Charge Ccy, Total Revenue (KRW equiv). The CSV is generated synchronously for up to 366 days of data. The system must complete within 10 seconds for a 30-day period (PRD-07 §15.8). Audit event DATA_EXPORT must be logged (entity_type=revenue_report, actor from JWT, timestamp, filter params as metadata JSON). | • Create RevenueCsvExportService with method void writeCsv(RevenueReportFilterDTO filter, OutputStream out, String actorId) using Apache Commons CSV or OpenCSV • Write header row with exact column names from context; write one data row per RevenueReportRowDTO • Format KRW amounts as plain integers (no decimals, comma-separated thousands); USD amounts as 0.0000 (4dp); service charges in their native ccy with 2dp • After writing CSV, call AuditLogService.log(DATA_EXPORT, 'revenue_report', null, actorId, Map.of('filter', filterJson)) • Wire into AdminRevenueController.exportCsv(): set Content-Disposition attachment filename=revenue_report_{dateFrom}_{dateTo}.csv, stream via StreamingResponseBody • Integration test: request export for 30-day period, download body, parse CSV, verify header row and that row count matches getReport row count for same filter | RevenueCsvExportService; updated AdminRevenueController.exportCsv(); integration test | • CSV header row exactly matches the 13 column names listed in the context (case-sensitive) • KRW value of 45000 appears in CSV as '45,000' (comma thousands, no decimal) • USD value of 4.5 appears as '4.5000' • Audit log entry DATA_EXPORT created with actor_id from JWT and metadata containing dateFrom and dateTo • GET /admin/revenue/export/csv returns Content-Disposition header attachment; filename=revenue_report_2026-05-01_2026-05-31.csv for matching dates | 50 | 10.9-T06, 10.9-T03 | FS | PRD-07
10.9-T10 | admin-ui | 10.9 | 10. Admin System | Settlement & revenue dashboards | 2 | Implement ReconciliationDetailController endpoints | PRD-07 §11.2.3: Ops can view flagged reconciliation items for a batch and mark them resolved. Endpoints needed: GET /admin/settlement/batches/{batchId}/reconciliation returning ReconciliationSummaryDTO; GET /admin/settlement/batches/{batchId}/reconciliation/items?page=&size= returning Page<ReconciliationItemDTO> (non-MATCHED only); POST /admin/settlement/batches/{batchId}/reconciliation/items/{itemId}/resolve with body {note: string} marking the item RESOLVED. POST endpoint requires OPS_OPERATOR or SUPER_ADMIN; GET endpoints also accessible to FINANCE_ANALYST. All resolution actions are audit-logged with entity_type=reconciliation_item and event DATA_EXPORT not applicable here - use RESOLVE action. | • Add three endpoints to AdminSettlementController (or a new ReconciliationController) • GET /{batchId}/reconciliation: call ReconciliationQueryService.getReconciliationSummaryForBatch(batchId), return 200 or 404 if batch not found • GET /{batchId}/reconciliation/items: call getDiscrepancyItems(batchId, pageable), return 200 with Page<ReconciliationItemDTO> • POST /{batchId}/reconciliation/items/{itemId}/resolve: @PreAuthorize OPS_OPERATOR¦SUPER_ADMIN only; call markResolved(itemId, actorId, note); return 204 • Add exception handler for ReconciliationNotFoundException -> HTTP 404 • Integration test: seed batch + 2 DISCREPANCY items, verify GET items returns both, POST resolve on item 1 returns 204, subsequent GET shows item 1 has resolution_status=RESOLVED | Reconciliation endpoints in ReconciliationController; integration test ReconciliationControllerIT | • GET /admin/settlement/batches/999/reconciliation returns HTTP 404 when batch 999 does not exist • GET items endpoint with FINANCE_ANALYST returns 200 • POST resolve with FINANCE_ANALYST returns 403 • POST resolve on already-RESOLVED item returns HTTP 409 with error message • Integration test passes: resolve item returns 204, subsequent GET reconciliation shows unresolvedCount decremented by 1 | 45 | 10.9-T05, 10.9-T03 | FS | PRD-07
10.9-T11 | admin-ui | 10.9 | 10. Admin System | Settlement & revenue dashboards | 2 | Implement settlement batch status aggregation for UI dashboard view | PRD-07 §11.2.2 and UX-11 §4.9: the UI shows one row per settlement date with columns for each batch file status. The backend needs to transform the list of settlement_batch rows (one per file_type) into a pivot structure: BatchDayStatusDTO {settlementDate, scheme, transactionCount (from ZP0065), grossPayoutKrw (total_amount from ZP0065), gmeFeeShareKrw (from settlement computation), netSettlementKrw, batchStatuses: Map<fileType, String>}. gmeFeeShareKrw = grossPayoutKrw x fee_share_pct (e.g. 70% = 0.70) for Domestic batches; for International (gross settlement) gmeFeeShareKrw is invoiced separately so it is 0 in this view. netSettlementKrw = grossPayoutKrw - gmeFeeShareKrw. | • Create BatchDayStatusDTO with fields: settlementDate, schemeName, transactionCount, grossPayoutKrw (BigDecimal, KRW), gmeFeeShareKrw (BigDecimal, KRW), netSettlementKrw (BigDecimal, KRW), batchStatuses (Map<String, String> of fileType->status) • Add method BatchDayStatusDTO aggregateDayStatus(List<SettlementBatchDTO> dayBatches, String settlementModel) to SettlementBatchQueryService • transactionCount from fileType=ZP0065 row if present, else 0; grossPayoutKrw from total_amount of ZP0065 row • If settlementModel=DOMESTIC: gmeFeeShareKrw = grossPayoutKrw.multiply(schemeFeePct).setScale(0, HALF_UP); else gmeFeeShareKrw=0 • netSettlementKrw = grossPayoutKrw.subtract(gmeFeeShareKrw); batchStatuses = map each DTO to fileType->status • Expose aggregated view via updated GET /admin/settlement/batches endpoint: return List<BatchDayStatusDTO> when query param view=DAY_SUMMARY is present | BatchDayStatusDTO; aggregateDayStatus() method; updated GET /admin/settlement/batches?view=DAY_SUMMARY | • Given ZP0065 row: total_amount=1000000.00 KRW, fee_share_pct=0.70, settlementModel=DOMESTIC: gmeFeeShareKrw=700000, netSettlementKrw=300000 • Given settlementModel=INTERNATIONAL: gmeFeeShareKrw=0, netSettlementKrw=grossPayoutKrw • batchStatuses map contains entries for all file types present in input list • When ZP0065 row is absent, transactionCount=0 and grossPayoutKrw=0 • GET /admin/settlement/batches?settlementDate=2026-06-01&view=DAY_SUMMARY returns List<BatchDayStatusDTO> | 45 | 10.9-T04, 10.9-T07 | FS | PRD-07
10.9-T12 | admin-ui | 10.9 | 10. Admin System | Settlement & revenue dashboards | 2 | Build frontend SettlementBatchStatusTable React component | UX-11 §4.9 wireframe shows a settlement batch table with columns: Batch (file type), Due (KST time), Status (Sent/Acknowledged/Failed/Recv/LATE/Matched/Discrepancy), File ID, Actions ([View] / [Reconcile] / [Retry]). Status uses color indicators: green tick for success states (TRANSMITTED/RECEIVED/RECONCILED), red X for ERROR, amber clock for PENDING/LATE. The component fetches from GET /admin/settlement/batches?settlementDate={date}&schemeId={schemeId}. The table must not exceed 5 visible columns per the no-horizontal-scroll convention; Actions column is the 5th. | • Create SettlementBatchStatusTable.tsx accepting props: settlementDate (string ISO), schemeId (number¦null) • Fetch data from GET /admin/settlement/batches on mount and on prop change; show loading spinner during fetch • Map status to badge variant: TRANSMITTED/RECEIVED/RECONCILED -> success (green); ERROR -> danger (red); PENDING -> warning (amber); GENERATED -> info (blue) • Compute LATE status client-side: if status=PENDING and current UTC time > due time KST for that file type (ZP0061 due 05:00 KST = 20:00 UTC prior day, ZP0062 due 10:00 KST = 01:00 UTC, ZP0063 due 14:00 KST = 05:00 UTC, ZP0064 due 19:00 KST = 10:00 UTC) render LATE badge • Actions: show [View] for all rows; show [Reconcile] only when status=RECEIVED and fileType in (ZP0062, ZP0064); show [Retry] only when status=ERROR | SettlementBatchStatusTable.tsx component with fetch, status badge rendering, and conditional actions | • Component renders 5 columns maximum (Batch, Due, Status, File ID, Actions) • Row with status=TRANSMITTED shows green success badge • Row with status=PENDING past ZP0062 due time 10:00 KST shows LATE amber badge • [Reconcile] button only visible on rows with fileType=ZP0062 or ZP0064 and status=RECEIVED • [Retry] button visible only on ERROR rows; [View] visible on all rows | 55 | 10.9-T07 | FS | PRD-07
10.9-T13 | admin-ui | 10.9 | 10. Admin System | Settlement & revenue dashboards | 2 | Build frontend RevenueSummaryCard React component | UX-11 §4.9 wireframe shows a REVENUE SUMMARY card above the batch table with four KPI tiles: Scheme fee share (USD, 70% of net ZeroPay), FX margin total (USD, sum of m_a+m_b extracted), Service fees total (USD flat charges), Total revenue (USD). The component receives the RevenueReportSummaryDTO from the parent page (already fetched) and renders the summary totals. Data comes from the /admin/revenue/report endpoint with period/scheme filters from the page-level filter bar. USD values are displayed with 2dp and comma thousands. The card is read-only. | • Create RevenueSummaryCard.tsx accepting prop: summary: RevenueReportSummaryDTO ¦ null • If null, render skeleton loader (4 grey placeholder tiles) • Render four KPI tiles: Scheme Fee Share = summary.totalGmeSchemeShareKrw converted display (show both USD equiv and KRW); FX Margin Total = summary.totalFxMarginUsd; Service Fees Total = derived from service charge sum in summary; Total Revenue = summary.grandTotalRevenueKrwEquiv • Format USD with 2dp, comma thousands separator; KRW as integer with comma thousands and KRW suffix • Add aria-label to each tile value for screen reader accessibility (e.g. 'Scheme fee share: USD 1,234.56') | RevenueSummaryCard.tsx component with four KPI tiles and loading state | • When summary=null, four skeleton placeholder elements are rendered (not an error state) • USD value 1234.56 renders as '1,234.56' • KRW value 135042 renders as '135,042 KRW' • Each tile has an aria-label attribute containing the label and formatted value • Component renders without errors when all summary numeric fields are 0.0000 | 30 | 10.9-T08 | FS | PRD-07
10.9-T14 | admin-ui | 10.9 | 10. Admin System | Settlement & revenue dashboards | 2 | Build frontend RevenueReportTable React component with filter bar | PRD-07 §11.3.2 and UX-11 §4.9: the revenue report view has a filter bar (Period type dropdown: DAILY/WEEKLY/MONTHLY/CUSTOM; date-from/date-to pickers; Partner dropdown; Scheme dropdown; Revenue stream dropdown: ALL/SCHEME_FEE/FX_MARGIN) and a paginated table. Table columns (max 6): Period, Partner, Scheme, Transaction Count, Total FX Margin (USD), GME Scheme Share (KRW). Additional columns accessible in an expandable row detail panel: Gross Payout KRW, Merchant Fee Total KRW, Collection Margin USD, Payout Margin USD, Service Charges, Total Revenue KRW equiv. An Export CSV button triggers GET /admin/revenue/export/csv with the same filter params. | • Create RevenueReportTable.tsx with state: filters (RevenueReportFilter), data (RevenueReportSummaryDTO¦null), loading • Filter bar: period type select, date-from/date-to date pickers (disabled when periodType != CUSTOM), partner select (populated from GET /admin/partners/list), scheme select, revenue stream select • On Search button click: validate dateFrom <= dateTo, then fetch GET /admin/revenue/report with filter params; update data state • Table: 6 visible columns (Period, Partner, Scheme, Txn Count, Total FX Margin USD, GME Scheme Share KRW); each row has an expand toggle showing the 7-field detail panel • Export CSV button: onClick fetches /admin/revenue/export/csv, triggers browser download via Blob URL; show loading spinner on button during fetch • Show RevenueSummaryCard above the table using the summary totals from the same response | RevenueReportTable.tsx component with filter bar, paginated table, row expand, and CSV export button | • Filter bar disables date pickers when periodType=MONTHLY and auto-populates dateFrom/dateTo to start/end of selected month • Search with dateTo before dateFrom shows inline error 'Date range is invalid' before making API call • Expanded row panel shows Collection Margin USD and Payout Margin USD as separate fields • Export CSV button triggers browser file download with filename matching pattern revenue_report_{from}_{to}.csv • When revenueStream=SCHEME_FEE, the Total FX Margin USD column shows '--' (not 0) to distinguish suppressed from zero | 55 | 10.9-T08, 10.9-T09, 10.9-T13 | FS | PRD-07
10.9-T15 | admin-ui | 10.9 | 10. Admin System | Settlement & revenue dashboards | 2 | Build frontend ReconciliationDetailModal component | PRD-07 §11.2.3: from the batch status table, clicking [Reconcile] on a ZP0062 or ZP0064 row opens a modal showing reconciliation summary (total items, matched count, discrepancy count) and a list of flagged items (non-MATCHED). Each flagged item shows: txn_ref, scheme_ref, match_status (MISSING_IN_SCHEME/AMOUNT_MISMATCH/SCHEME_REJECTION), gme_amount, scheme_amount, discrepancy_amount, resolution_status (UNRESOLVED/RESOLVED/ESCALATED). OPS_OPERATOR users see a [Mark Resolved] button per UNRESOLVED item; FINANCE_ANALYST users see items read-only. Resolving requires a confirmation step with a mandatory note field. | • Create ReconciliationDetailModal.tsx accepting props: batchId (number), fileType (string), isOpen (boolean), onClose ()=>void, userRole (string) • On open: fetch GET /admin/settlement/batches/{batchId}/reconciliation and GET /admin/settlement/batches/{batchId}/reconciliation/items?page=0&size=50 • Render summary tile row (total, matched, discrepancies, unresolved) above item list • Item list: columns: Txn Ref, Status badge, GME Amount, Scheme Amount, Discrepancy, Resolution • For OPS_OPERATOR: [Mark Resolved] button per UNRESOLVED row; clicking opens inline note input (required, min 10 chars) + [Confirm] button; on confirm POST /{batchId}/reconciliation/items/{itemId}/resolve {note}; on success update item row to RESOLVED • FINANCE_ANALYST sees items but no [Mark Resolved] button (controlled by userRole prop) | ReconciliationDetailModal.tsx component with summary, item list, and resolve workflow | • Modal fetches data on open and shows loading spinner before data arrives • UNRESOLVED item shows [Mark Resolved] when userRole=OPS_OPERATOR • [Confirm] is disabled until note field has >= 10 characters • After successful POST resolve, the row's resolution_status updates to RESOLVED inline without full modal reload • When userRole=FINANCE_ANALYST, no [Mark Resolved] button is rendered on any row | 55 | 10.9-T10, 10.9-T12 | FS | PRD-07
10.9-T16 | admin-ui | 10.9 | 10. Admin System | Settlement & revenue dashboards | 2 | Build frontend SettlementRevenuePage container and route | PRD-07 §3 nav map: the Settlement section has sub-items Batch Status, Revenue, Reconciliation. In Phase 1 these are tabs on a single page (/admin/settlement-revenue). The page-level filter bar (Period, Partner, Scheme) is shared between the batch view and revenue view to avoid re-entering. The Revenue tab shows RevenueSummaryCard + RevenueReportTable. The Batch Status tab shows SettlementBatchStatusTable. State for the shared filter is lifted to the page container. The page is accessible to SUPER_ADMIN, OPS_OPERATOR, FINANCE_ANALYST (checked via route guard); ADMIN_VIEWER is redirected to /403. | • Create SettlementRevenuePage.tsx at route /admin/settlement-revenue • Add role guard: if user role is ADMIN_VIEWER redirect to /403 • Page-level state: activeTab (BATCH_STATUS¦REVENUE), settlementDate (default today KST), partnerId, schemeId, dateFrom, dateTo, periodType • Render shared filter bar at top (date/partner/scheme selectors) • Render tab switcher; tab BATCH_STATUS renders SettlementBatchStatusTable with settlementDate+schemeId; tab REVENUE renders RevenueReportTable with full filter • On tab switch: preserve filter state; do not re-fetch unnecessarily (use React Query or similar with filter as cache key) • Add breadcrumb: Settlement / Settlement & Revenue | SettlementRevenuePage.tsx container with routing, role guard, tab switcher, and shared filter state | • Visiting /admin/settlement-revenue as ADMIN_VIEWER redirects to /403 • Switching from BATCH_STATUS to REVENUE tab preserves the selected partner and scheme • Page breadcrumb displays 'Settlement / Settlement & Revenue' • Shared filter bar renders period selector, partner selector, scheme selector in a single row • On initial load, settlementDate defaults to today's KST date (not UTC) | 50 | 10.9-T12, 10.9-T14 | FS | PRD-07
10.9-T17 | admin-ui | 10.9 | 10. Admin System | Settlement & revenue dashboards | 2 | Unit test RevenueReportQueryService aggregation logic | RevenueReportQueryService (T06) performs: (1) aggregation of fx_margin_usd and estimated_fee_share_usd, (2) grouping by partner+scheme, (3) KRW conversion using treasury rate, (4) revenueStream filter (zero-out fields). These are logic-bearing and require unit tests with exact numeric vectors independent of the database. treasury.usd_krw = 1350.42 in test vectors. Three-revenue-stream scenario: fx_margin_usd=4.50, estimated_fee_share_usd=1.50, service_charge_amount=500 KRW (service_charge_ccy=KRW). Expected total_revenue_krw_equiv = (1.50+4.50)*1350.42 + 500 = 8102.52 + 500 = 8602.52, rounded to 8603 KRW. | • Create RevenueReportQueryServiceTest in admin-service test package • Test 1 - full aggregation: mock repository returning 3 revenue_record rows for partner SendMN (fx_margin_usd=[1.00,2.00,1.50], estimated_fee_share_usd=[0.50,0.50,0.50], service_charge_amount=0); verify total_fx_margin_usd=4.50, gme_scheme_share=1.50 • Test 2 - KRW conversion: use treasury usd_krw=1350.42; fx_margin_usd=4.50, fee_share=1.50, service_charge KRW=500; verify total_revenue_krw_equiv=8603 (rounded HALF_UP to 0dp) • Test 3 - revenueStream=SCHEME_FEE filter: verify returned row has total_fx_margin_usd=0.00 and gme_scheme_share > 0 • Test 4 - revenueStream=FX_MARGIN filter: verify returned row has gme_scheme_share=0 and total_fx_margin_usd > 0 • Test 5 - empty result: mock returns empty list; verify summary has all totals=0 and rows=[] | RevenueReportQueryServiceTest with 5 unit tests, all passing | • Test 1 asserts total_fx_margin_usd equals new BigDecimal('4.50') using compareTo (not equals to avoid scale mismatch) • Test 2 asserts total_revenue_krw_equiv == 8603 (integer, no decimal) • Test 3 asserts total_fx_margin_usd.compareTo(BigDecimal.ZERO)==0 when revenueStream=SCHEME_FEE • Test 4 asserts gme_scheme_share_krw == 0 when revenueStream=FX_MARGIN • Test 5 runs without NullPointerException and returns summary.grandTotalRevenueKrwEquiv=0 | 40 | 10.9-T06 | FS | PRD-07
10.9-T18 | admin-ui | 10.9 | 10. Admin System | Settlement & revenue dashboards | 2 | Unit test ReconciliationQueryService summary and resolution logic | ReconciliationQueryService (T05) computes overallStatus from discrepancy/missing counts and enforces resolution state transitions (UNRESOLVED -> RESOLVED; already-RESOLVED throws). Test vectors: Batch A: 100 items (95 MATCHED, 3 AMOUNT_MISMATCH, 2 MISSING_IN_SCHEME) -> overallStatus=DISCREPANCY. Batch B: 50 items (50 MATCHED) -> overallStatus=MATCHED. Batch C: 0 items -> overallStatus=PENDING. Resolution: item in RESOLVED state -> AlreadyResolvedException. | • Create ReconciliationQueryServiceTest • Test 1 - discrepancy detection: mock 100 items (95 MATCHED, 3 AMOUNT_MISMATCH, 2 MISSING_IN_SCHEME); assert overallStatus=DISCREPANCY, discrepancyCount=3, missingInSchemeCount=2, unresolvedCount=5 • Test 2 - all matched: mock 50 MATCHED items; assert overallStatus=MATCHED, discrepancyCount=0 • Test 3 - empty batch: mock 0 items; assert overallStatus=PENDING • Test 4 - resolve transition: mock item with resolution_status=UNRESOLVED; call markResolved; verify resolved_at is non-null and resolution_status=RESOLVED • Test 5 - double resolve guard: call markResolved on item with resolution_status=RESOLVED; verify AlreadyResolvedException is thrown | ReconciliationQueryServiceTest with 5 unit tests, all passing | • Test 1: overallStatus.name() equals 'DISCREPANCY' and unresolvedCount equals 5 • Test 2: overallStatus.name() equals 'MATCHED' • Test 3: overallStatus.name() equals 'PENDING' • Test 4: after markResolved, the item's resolved_at timestamp is within 2 seconds of now • Test 5: AlreadyResolvedException thrown (not silently ignored) | 35 | 10.9-T05 | FS | PRD-07
10.9-T19 | admin-ui | 10.9 | 10. Admin System | Settlement & revenue dashboards | 2 | Unit test BatchDayStatusDTO aggregation for net vs gross settlement | SettlementBatchQueryService.aggregateDayStatus() (T11) computes gmeFeeShareKrw and netSettlementKrw based on settlementModel (DOMESTIC vs INTERNATIONAL). Domestic: fee_share_pct=0.70; given grossPayoutKrw=1000000.00, gmeFeeShareKrw=700000, netSettlementKrw=300000. International: gmeFeeShareKrw=0, netSettlementKrw=grossPayoutKrw. Edge: KRW amounts must scale to 0 decimal places. Verify batchStatuses map built correctly from a mixed list of fileType rows. | • Create BatchDayStatusAggregationTest • Test 1 - domestic net settlement: mock ZP0065 batch row with total_amount=1000000.00, fee_share_pct=0.70, settlementModel=DOMESTIC; assert gmeFeeShareKrw=700000, netSettlementKrw=300000 (both BigDecimal with scale 0) • Test 2 - international gross settlement: same ZP0065 row with settlementModel=INTERNATIONAL; assert gmeFeeShareKrw=0, netSettlementKrw=1000000 • Test 3 - KRW scale: input total_amount=1000000.9999 (from DECIMAL(20,4)); assert gmeFeeShareKrw and netSettlementKrw both have scale=0 (rounded HALF_UP) • Test 4 - batchStatuses map: input list [ZP0061 TRANSMITTED, ZP0062 RECEIVED, ZP0063 ERROR]; assert map keys contain 'ZP0061','ZP0062','ZP0063' with correct status values • Test 5 - missing ZP0065: input list has no ZP0065 row; assert transactionCount=0 and grossPayoutKrw=BigDecimal.ZERO | BatchDayStatusAggregationTest with 5 unit tests, all passing | • Test 1: gmeFeeShareKrw.compareTo(new BigDecimal('700000'))==0 and scale()==0 • Test 2: gmeFeeShareKrw.compareTo(BigDecimal.ZERO)==0 • Test 3: no ArithmeticException thrown; result has scale=0 • Test 4: map.get('ZP0063') equals 'ERROR' • Test 5: grossPayoutKrw.compareTo(BigDecimal.ZERO)==0 | 35 | 10.9-T11 | FS | PRD-07
10.9-T20 | admin-ui | 10.9 | 10. Admin System | Settlement & revenue dashboards | 2 | Unit test RevenueCsvExportService column names, formatting, and audit logging | RevenueCsvExportService (T09) must produce a CSV with exact column headers and correctly formatted numeric values. KRW integers use comma thousands separator; USD uses 4dp. The service must emit a DATA_EXPORT audit log entry after writing. Test vectors: one RevenueReportRowDTO with total_fx_margin_usd=BigDecimal('4.5000'), gme_scheme_share_krw=135042, service_charge_amount=500.00 KRW. | • Create RevenueCsvExportServiceTest • Test 1 - header row: call writeCsv with empty filter and empty rows list; parse resulting CSV string; assert first row contains all 13 expected column names in order • Test 2 - KRW formatting: single row with gme_scheme_share_krw=135042; assert the corresponding CSV cell contains '135,042' (comma thousands, no decimal point) • Test 3 - USD formatting: single row with total_fx_margin_usd=BigDecimal('4.5'); assert CSV cell contains '4.5000' (4dp) • Test 4 - audit log: mock AuditLogService; call writeCsv; verify auditLogService.log was called with action=DATA_EXPORT, entityType='revenue_report' • Test 5 - empty rows: writeCsv with zero rows produces exactly one line (header) and no data rows | RevenueCsvExportServiceTest with 5 unit tests, all passing | • Test 1: header row string contains exactly the substring 'GME Scheme Share (KRW)' (exact case) • Test 2: cell value is '135,042' not '135042' or '135,042.00' • Test 3: cell value is '4.5000' not '4.5' or '4.50' • Test 4: verify(auditLogService).log(eq(DATA_EXPORT), eq('revenue_report'), ...) called once • Test 5: CSV output split by line-separator has length == 1 (header only, no trailing empty line) | 40 | 10.9-T09 | FS | PRD-07
10.9-T21 | admin-ui | 10.9 | 10. Admin System | Settlement & revenue dashboards | 2 | Add DB indexes for settlement and revenue query performance | The settlement_batch and revenue_record tables are queried heavily by the dashboard. settlement_batch is queried by (settlement_date, scheme_id) and by (batch_id) for reconciliation drilldown. revenue_record is queried by (revenue_date, partner_id, scheme_id) for the revenue report aggregation. reconciliation_item is queried by (batch_id, match_status) to retrieve non-MATCHED items. Without indexes these queries will full-scan as data grows. PRD-07 §14.1: CSV export for 30-day period must complete within 10 seconds. | • Create Flyway migration V10_9__settlement_revenue_indexes.sql • Add index: CREATE INDEX IF NOT EXISTS idx_settlement_batch_date_scheme ON settlement_batch(settlement_date, scheme_id) • Add index: CREATE INDEX IF NOT EXISTS idx_settlement_batch_status ON settlement_batch(status) WHERE status IN ('PENDING','ERROR') • Add index: CREATE INDEX IF NOT EXISTS idx_revenue_record_date_partner_scheme ON revenue_record(revenue_date, partner_id, scheme_id) • Add index: CREATE INDEX IF NOT EXISTS idx_reconciliation_item_batch_match ON reconciliation_item(batch_id, match_status) • Verify migration runs cleanly on a dev DB with flyway migrate; confirm explain plan for SELECT * FROM revenue_record WHERE revenue_date BETWEEN '2026-05-01' AND '2026-05-31' uses the new index | Flyway migration V10_9__settlement_revenue_indexes.sql with 4 index definitions | • Migration runs without error via mvn flyway:migrate on a clean schema • EXPLAIN on SELECT ... FROM settlement_batch WHERE settlement_date='2026-06-01' AND scheme_id=1 shows Index Scan using idx_settlement_batch_date_scheme • EXPLAIN on SELECT ... FROM revenue_record WHERE revenue_date BETWEEN '2026-05-01' AND '2026-05-31' shows Index Scan using idx_revenue_record_date_partner_scheme • EXPLAIN on SELECT ... FROM reconciliation_item WHERE batch_id=1 AND match_status != 'MATCHED' shows Index Scan using idx_reconciliation_item_batch_match • Migration is idempotent: running twice does not error (IF NOT EXISTS) | 30 |  | FS | PRD-07
10.9-T22 | admin-ui | 10.9 | 10. Admin System | Settlement & revenue dashboards | 2 | Add merchant fee schedule read-only reference view to Settlement module | PRD-07 §11.3.3: the Settlement & Revenue module must display the merchant fee schedule for the scheme as a reference (read-only; edits go through the Schemes module). The fee schedule is stored in qr_scheme (fee_schedule JSON or structured fee_tier columns per DAT-03). The view shows: merchant type, fee rate %, domestic/crossborder distinction, GME fee share %. This gives Finance context for reconciling revenue figures. The endpoint is GET /admin/settlement/fee-schedule?schemeId=. FINANCE_ANALYST, OPS_OPERATOR, SUPER_ADMIN may access. | • Create MerchantFeeScheduleDTO with fields: schemeId, schemeName, feeRows: List<FeeRowDTO> where FeeRowDTO has merchantType, feeRatePct, settlementType (DOMESTIC¦INTERNATIONAL), gmeFeeSharePct • Add method List<MerchantFeeScheduleDTO> getFeeSchedule(Long schemeId) to SettlementBatchQueryService (or a new FeeScheduleQueryService): query qr_scheme joined to fee configuration • Add GET /admin/settlement/fee-schedule?schemeId= endpoint in AdminSettlementController; @PreAuthorize same roles as other settlement endpoints • Create FeeSchedulePanel.tsx React component: renders a read-only table of merchant types and fee rates; data fetched when Settlement page loads; no edit capability • Verify a FINANCE_ANALYST user can see the panel; verify clicking fee rows does not offer any edit interaction | MerchantFeeScheduleDTO; GET /admin/settlement/fee-schedule endpoint; FeeSchedulePanel.tsx | • GET /admin/settlement/fee-schedule?schemeId=1 returns HTTP 200 with at least one fee row for ZeroPay • FeeRowDTO contains gmeFeeSharePct field with value 0.70 (70%) for ZeroPay scheme • FeeSchedulePanel.tsx renders a table with no input fields or edit buttons • ADMIN_VIEWER role receives 403 from the endpoint • schemeId=999 (non-existent) returns empty list (not 404) | 40 | 10.9-T03 | FS | PRD-07
10.9-T23 | admin-ui | 10.9 | 10. Admin System | Settlement & revenue dashboards | 2 | Audit-log all export and resolution actions in Settlement module | PRD-07 §13.2 requires that data exports and settlement resolution actions are audit-logged. The audit_log table (DAT-03 §9.1) has: actor_id (VARCHAR), actor_type (OPERATOR), action (CREATE/UPDATE/DELETE/ACTIVATE/DEACTIVATE), entity_type (VARCHAR), entity_id, previous_value (JSON), new_value (JSON), ip_address, description. For this module: (1) CSV export: action=UPDATE (repurpose as DATA_EXPORT event code in description), entity_type='revenue_report'. (2) Reconciliation item resolve: action=UPDATE, entity_type='reconciliation_item', entity_id=itemId, previous_value={resolution_status:'UNRESOLVED'}, new_value={resolution_status:'RESOLVED', resolved_by, resolution_note}. (3) Flag exception: action=UPDATE, entity_type='reconciliation_item', new_value={resolution_status:'ESCALATED'}. Actor IP must be captured from HttpServletRequest. | • Confirm AuditLogService.log(String action, String entityType, Long entityId, String actorId, String actorIp, Map previousValue, Map newValue, String description) method exists (add if missing) • In RevenueCsvExportService.writeCsv: after streaming CSV, call auditLogService.log with action='DATA_EXPORT', entityType='revenue_report', entityId=null, description containing dateFrom/dateTo filter values • In ReconciliationQueryService.markResolved: call auditLogService.log with action='UPDATE', entityType='reconciliation_item', entityId=itemId, previous={resolution_status:'UNRESOLVED'}, new={resolution_status:'RESOLVED', note} • In any future escalation path: action='UPDATE', new_value={resolution_status:'ESCALATED'} • Integration test: call exportCsv endpoint, then query audit_log table, verify one entry with action='DATA_EXPORT' and actor_id matching the JWT subject | AuditLogService integration in RevenueCsvExportService and ReconciliationQueryService; integration test verifying audit entries | • After POST resolve item 42, audit_log contains one row with entity_type='reconciliation_item' and entity_id=42 • Audit row new_value JSON contains key resolution_status with value RESOLVED • After GET /admin/revenue/export/csv, audit_log contains row with action=DATA_EXPORT and description containing the filter dateFrom value • audit_log entry actor_ip is populated (not null) from the HTTP request context • No audit entry is created when a read-only GET endpoint is called (only writes are audited) | 40 | 10.9-T09, 10.9-T10 | FS | PRD-07
10.9-T24 | admin-ui | 10.9 | 10. Admin System | Settlement & revenue dashboards | 2 | Integration test: full settlement batch status flow end-to-end | Validates the complete backend flow for T04+T07+T11: seed settlement_batch rows, call GET /admin/settlement/batches, verify SettlementBatchListDTO response, call DAY_SUMMARY view, verify BatchDayStatusDTO aggregation. Uses a test PostgreSQL DB (Testcontainers). Seed data: settlement_date=2026-06-01, scheme=ZeroPay (id=1), rows: ZP0061 TRANSMITTED total_amount=0, ZP0062 RECEIVED total_amount=0, ZP0065 RECONCILED total_amount=1000000.00 KRW, transaction_count=150. fee_share_pct=0.70 for ZeroPay. | • Create SettlementBatchIntegrationTest using @SpringBootTest with Testcontainers PostgreSQL • Seed 3 settlement_batch rows as described in context using a SQL script or @Sql annotation • Test 1: GET /admin/settlement/batches?settlementDate=2026-06-01 returns HTTP 200 with content.length=3 and statuses matching seeded values • Test 2: GET /admin/settlement/batches?settlementDate=2026-06-01&view=DAY_SUMMARY returns HTTP 200 with single BatchDayStatusDTO having transactionCount=150, grossPayoutKrw=1000000, gmeFeeShareKrw=700000, netSettlementKrw=300000 • Test 3: GET /admin/settlement/batches?settlementDate=2026-07-01 (no rows) returns HTTP 200 with empty content • Test 4: Unauthenticated request returns HTTP 401 | SettlementBatchIntegrationTest with 4 test cases, all passing against Testcontainers DB | • Test 1 passes: content array has 3 elements with file_type values ZP0061, ZP0062, ZP0065 • Test 2 passes: gmeFeeShareKrw equals 700000 and netSettlementKrw equals 300000 • Test 3 passes: empty content list returned (not 404) • Test 4 passes: 401 returned for unauthenticated request • All 4 tests pass in CI without manual DB setup | 55 | 10.9-T07, 10.9-T11 | FS | PRD-07
10.9-T25 | admin-ui | 10.9 | 10. Admin System | Settlement & revenue dashboards | 2 | Integration test: revenue report query and CSV export end-to-end | Validates RevenueReportQueryService + AdminRevenueController + RevenueCsvExportService together. Seed: 5 revenue_record rows for May 2026: partner=SendMN (id=2), scheme=ZeroPay (id=1), fx_margin_usd=[1.00,2.00,1.50,0.50,0.50], estimated_fee_share_usd=[0.30,0.30,0.30,0.30,0.30], service_charge_amount=0. treasury_rate usd_krw=1350.42 seeded. Expected totals: total_fx_margin_usd=5.50, gme_scheme_share=1.50, total_revenue_krw_equiv = (5.50+1.50)*1350.42 = 9452.94 rounded to 9453 KRW. | • Create RevenueReportIntegrationTest using @SpringBootTest + Testcontainers • Seed revenue_record rows and treasury_rate row via @Sql script • Test 1: GET /admin/revenue/report?periodType=MONTHLY&dateFrom=2026-05-01&dateTo=2026-05-31 returns HTTP 200 with summary.totalFxMarginUsd='5.5000' and summary.grandTotalRevenueKrwEquiv=9453 • Test 2: same filter with revenueStream=SCHEME_FEE returns rows with totalFxMarginUsd='0.0000' • Test 3: GET /admin/revenue/export/csv with same filter returns HTTP 200 with Content-Type: text/csv; parse CSV body; first row is header; data rows total correct tx count • Test 4: verify audit_log has one DATA_EXPORT entry after the CSV export call | RevenueReportIntegrationTest with 4 test cases, all passing against Testcontainers DB | • Test 1: grandTotalRevenueKrwEquiv equals 9453 (integer) • Test 2: all row DTOs have totalFxMarginUsd with value 0.0000 when revenueStream=SCHEME_FEE • Test 3: CSV body row count (excluding header) equals 1 (one partner-scheme group) • Test 4: audit_log table contains exactly one row with action=DATA_EXPORT after the export call • Test 1 assertion uses exact BigDecimal comparison for totalFxMarginUsd: '5.5000' | 55 | 10.9-T08, 10.9-T09, 10.9-T23 | FS | PRD-07
10.10-T01 | admin-ui | 10.10 | 10. Admin System | User & role management (RBAC) | 1 | Create DB migration: hub_role table with 4 canonical roles | DAT-03 §9.2 defines hub_role: id (BIGINT PK), role_code VARCHAR(20) UNIQUE NOT NULL, permissions JSONB NOT NULL, created_at TIMESTAMPTZ, updated_at TIMESTAMPTZ. Four canonical role_codes: SUPER_ADMIN, OPS_OPERATOR, FINANCE_ANALYST, ADMIN_VIEWER. These are seeded once; application logic references them by role_code string. | • Create Flyway migration V10_10_001__create_hub_role.sql • Define table hub_role with columns: id BIGINT GENERATED ALWAYS AS IDENTITY PRIMARY KEY, role_code VARCHAR(20) NOT NULL UNIQUE, permissions JSONB NOT NULL DEFAULT '{}', created_at TIMESTAMPTZ NOT NULL DEFAULT now(), updated_at TIMESTAMPTZ NOT NULL DEFAULT now() • Add seed INSERT for all four roles with empty permissions JSONB • Add unique index on role_code • Verify migration runs cleanly on a fresh schema | Flyway migration file V10_10_001__create_hub_role.sql with table DDL and 4 seed rows | • Migration applies without error on empty schema and on top of prior migrations • SELECT COUNT(*) FROM hub_role returns 4 after seed • role_code column has UNIQUE constraint: inserting a 5th row with role_code='SUPER_ADMIN' raises unique-violation error • permissions column accepts and returns valid JSONB: UPDATE hub_role SET permissions='{"view_dashboard":true}' WHERE role_code='ADMIN_VIEWER' succeeds • Rollback/undo migration removes table cleanly (no orphan objects) | 25 |  | FS | PRD-07, SEC-09
10.10-T02 | admin-ui | 10.10 | 10. Admin System | User & role management (RBAC) | 1 | Create DB migration: hub_user table with FK to hub_role | DAT-03 §9.2 defines hub_user: id (BIGINT PK), email VARCHAR(254) UNIQUE NOT NULL, name VARCHAR(200) NOT NULL, role_id BIGINT FK -> hub_role NOT NULL, is_active BOOLEAN NOT NULL DEFAULT true, password_hash VARCHAR(255) NOT NULL, must_change_password BOOLEAN NOT NULL DEFAULT false, failed_login_count INT NOT NULL DEFAULT 0, locked_until TIMESTAMPTZ NULL, last_login_at TIMESTAMPTZ NULL, created_at TIMESTAMPTZ NOT NULL DEFAULT now(), updated_at TIMESTAMPTZ NOT NULL DEFAULT now(), created_by BIGINT FK -> hub_user NULL (self-ref; NULL for bootstrap user). SEC-09 §3.1: 5 consecutive failures lock the account; lockout cleared by IT admin. | • Create Flyway migration V10_10_002__create_hub_user.sql • Define hub_user table with all columns listed in context • Add FK constraint hub_user.role_id -> hub_role.id (ON DELETE RESTRICT) • Add self-referential FK hub_user.created_by -> hub_user.id (ON DELETE SET NULL) • Add unique index on email; add index on role_id; add index on is_active • Insert bootstrap SUPER_ADMIN user with email='admin@gmeremit.com', must_change_password=true | Flyway migration V10_10_002__create_hub_user.sql with full hub_user DDL, FK constraints, indexes, and bootstrap user seed | • Migration applies after T01 with no errors • SELECT COUNT(*) FROM hub_user returns 1 (bootstrap user) • Inserting a hub_user with a non-existent role_id raises FK violation • Inserting a duplicate email raises unique-constraint violation • Bootstrap user has must_change_password=true and role_code SUPER_ADMIN confirmed via JOIN • failed_login_count defaults to 0 and locked_until defaults to NULL | 30 | 10.10-T01 | FS | PRD-07, SEC-09
10.10-T03 | admin-ui | 10.10 | 10. Admin System | User & role management (RBAC) | 1 | Define RbacPermission enum and permissions JSONB schema | The hub_role.permissions JSONB column encodes which actions a role may perform. The 20 actions from PRD-07 §12.3 permission matrix are: VIEW_DASHBOARD, CREATE_EDIT_SCHEME, ACTIVATE_SUSPEND_SCHEME, VIEW_SCHEME_CONFIG, CREATE_EDIT_PARTNER, VIEW_API_CREDENTIALS, GENERATE_REVOKE_API_CREDENTIALS, CREATE_EDIT_RULE, UPDATE_FX_RATES, VIEW_FX_RATE_HISTORY, SEARCH_VIEW_TRANSACTIONS, VIEW_LOCKED_RATE_POOL_VALUES, VIEW_PREFUNDING_BALANCE, RECORD_TOP_UP, CREATE_MANUAL_ADJUSTMENT, INITIATE_REFUND, VIEW_REFUND_STATUS, VIEW_SETTLEMENT_BATCHES, EXPORT_REVENUE_REPORT, MANAGE_USERS_AND_ROLES, VIEW_AUDIT_LOG, EXPORT_AUDIT_LOG. permissions JSONB stores a set of these keys each with boolean true. | • Create Java enum RbacPermission with one constant per action name listed in context (22 constants) • Create PermissionSet value class wrapping Set<RbacPermission> with methods: has(RbacPermission), toJsonb(), fromJsonb(String) • Write unit test PermissionSetTest: serialize and deserialize a set of 3 permissions and verify round-trip equality • Add Hibernate custom type or JPA AttributeConverter to map permissions JSONB column to Set<RbacPermission> | RbacPermission.java enum, PermissionSet.java value class, PermissionSetTest.java, and JPA AttributeConverter PermissionSetConverter.java | • RbacPermission.values().length == 22 • PermissionSet.fromJsonb('{"VIEW_DASHBOARD":true,"RECORD_TOP_UP":true}') returns a set with exactly VIEW_DASHBOARD and RECORD_TOP_UP • PermissionSet.fromJsonb('{}') returns empty set with no exception • Serializing a set of all 22 permissions and deserializing returns identical set • Unknown key in JSONB (e.g. 'LEGACY_KEY') is silently ignored during deserialization (forward-compatibility) | 35 | 10.10-T01 | FS | PRD-07, SEC-09
10.10-T04 | admin-ui | 10.10 | 10. Admin System | User & role management (RBAC) | 1 | Seed canonical permission sets for all four hub_role rows | PRD-07 §12.3 defines the permission matrix for 4 roles. SUPER_ADMIN has all 22 permissions. OPS_OPERATOR has: VIEW_DASHBOARD, CREATE_EDIT_SCHEME, ACTIVATE_SUSPEND_SCHEME, VIEW_SCHEME_CONFIG, CREATE_EDIT_PARTNER, VIEW_API_CREDENTIALS, GENERATE_REVOKE_API_CREDENTIALS, CREATE_EDIT_RULE, UPDATE_FX_RATES, VIEW_FX_RATE_HISTORY, SEARCH_VIEW_TRANSACTIONS, VIEW_LOCKED_RATE_POOL_VALUES, VIEW_PREFUNDING_BALANCE, RECORD_TOP_UP, INITIATE_REFUND, VIEW_REFUND_STATUS, VIEW_SETTLEMENT_BATCHES, EXPORT_REVENUE_REPORT, VIEW_AUDIT_LOG. FINANCE_ANALYST has: VIEW_DASHBOARD, VIEW_FX_RATE_HISTORY, SEARCH_VIEW_TRANSACTIONS, VIEW_LOCKED_RATE_POOL_VALUES, VIEW_PREFUNDING_BALANCE, CREATE_MANUAL_ADJUSTMENT, VIEW_REFUND_STATUS, VIEW_SETTLEMENT_BATCHES, EXPORT_REVENUE_REPORT. ADMIN_VIEWER has: VIEW_DASHBOARD, VIEW_FX_RATE_HISTORY, SEARCH_VIEW_TRANSACTIONS, VIEW_REFUND_STATUS. | • Create Flyway migration V10_10_003__seed_role_permissions.sql • For each of the 4 hub_role rows UPDATE permissions = '<jsonb>' WHERE role_code='<code>' • Build the JSONB literal for each role from the exact permission lists in context • Add a CHECK or comment for the SUPER_ADMIN assertion (all 22 keys present) | Flyway migration V10_10_003__seed_role_permissions.sql populating hub_role.permissions for all 4 roles | • After migration, SUPER_ADMIN permissions JSONB contains exactly 22 keys all set to true • OPS_OPERATOR does NOT have MANAGE_USERS_AND_ROLES or EXPORT_AUDIT_LOG or CREATE_MANUAL_ADJUSTMENT keys • FINANCE_ANALYST does NOT have CREATE_EDIT_SCHEME, CREATE_EDIT_PARTNER, or MANAGE_USERS_AND_ROLES • ADMIN_VIEWER has exactly 4 permissions: VIEW_DASHBOARD, VIEW_FX_RATE_HISTORY, SEARCH_VIEW_TRANSACTIONS, VIEW_REFUND_STATUS • Migration is idempotent: running it twice on the same DB produces no error and same result | 25 | 10.10-T03 | FS | PRD-07, SEC-09
10.10-T05 | admin-ui | 10.10 | 10. Admin System | User & role management (RBAC) | 1 | Implement HubUserRepository and HubRoleRepository (JPA) | Hub services need CRUD access to hub_user and hub_role tables. hub_user fields include email, name, role_id (FK), is_active, password_hash, must_change_password, failed_login_count, locked_until, last_login_at, created_by. hub_role fields: role_code, permissions (JSONB mapped via PermissionSetConverter from T03). Use Spring Data JPA repositories. Password hash stored using BCrypt (strength 12). Entity classes must use the PermissionSetConverter from T03. | • Create HubRole JPA entity mapping hub_role columns; use @Convert(converter=PermissionSetConverter.class) for permissions • Create HubUser JPA entity mapping hub_user columns; use @ManyToOne to HubRole • Create HubRoleRepository extends JpaRepository<HubRole,Long> with findByRoleCode(String roleCode) • Create HubUserRepository extends JpaRepository<HubUser,Long> with findByEmail(String email), findAllByIsActiveTrue(), findAllByRoleId(Long roleId) • Write RepositoryIT integration test: save a user, reload it, verify role permissions round-trip via PermissionSetConverter | HubRole.java, HubUser.java entity classes; HubRoleRepository.java; HubUserRepository.java; RepositoryIT.java | • HubRoleRepository.findByRoleCode('SUPER_ADMIN') returns a non-empty Optional • HubUserRepository.findByEmail on the bootstrap user returns correct entity with role SUPER_ADMIN • Saving a new HubUser with must_change_password=true and reloading returns must_change_password=true • HubUser.role.permissions.has(RbacPermission.VIEW_DASHBOARD) is true for SUPER_ADMIN and false for a role with empty permissions • Integration test passes against real embedded H2 or Testcontainers Postgres | 40 | 10.10-T03, 10.10-T04 | FS | PRD-07, SEC-09
10.10-T06 | admin-ui | 10.10 | 10. Admin System | User & role management (RBAC) | 1 | Implement AuthenticationService: login, lockout, session JWT issuance | SEC-09 §3.1 specifies Admin Portal auth: max 5 consecutive failures lock the account (locked_until set by IT admin unlock, not timed); session duration 8 hours max; idle timeout 30 minutes (enforced by frontend inactivity + backend token TTL). Phase 1 uses local portal accounts (SSO is Phase 2). JWT tokens: internal service JWTs have 1-hour TTL (SEC-09 §2.7) but portal sessions use 8h max / 30min idle pattern: issue short-lived access token (30min) + refresh token (8h). On login: verify BCrypt password, check is_active, check locked_until IS NULL, reset failed_login_count=0 on success, increment on failure (lock account when count reaches 5). Audit event: AUTH_LOGIN_SUCCESS or AUTH_LOGIN_FAILED. | • Create AuthenticationService.login(email, password) returning TokenPair(accessToken, refreshToken) • Implement lockout logic: if failed_login_count >= 5 set locked_until = 'infinity' and throw AccountLockedException • On success: set last_login_at=now(), failed_login_count=0 • Issue JWT access token (sub=userId, role=role_code, permissions=Set<RbacPermission>, exp=now+30min, jti=UUID) • Issue opaque refresh token (UUID stored hashed in hub_user.refresh_token_hash, exp=now+8h) • Publish AuditEvent(AUTH_LOGIN_SUCCESS or AUTH_LOGIN_FAILED, actor_id, ip_address) via application event | AuthenticationService.java with login(), unlockUser() methods and AccountLockedException; JWT claims documented inline | • Correct password returns TokenPair with non-null accessToken and refreshToken • Wrong password 5 times sets hub_user.locked_until to a non-null value and 6th attempt throws AccountLockedException without further incrementing count • Correct password after account is locked throws AccountLockedException regardless of credentials • Decoded JWT contains role_code and at least one permission from the user's role • must_change_password=true is included as a claim in the JWT so the frontend can force the change flow | 55 | 10.10-T05 | FS | PRD-07, SEC-09
10.10-T07 | admin-ui | 10.10 | 10. Admin System | User & role management (RBAC) | 1 | Implement RbacFilter: JWT extraction and SecurityContext population | Every Admin Portal API request must carry a valid JWT access token (Authorization: Bearer <token>). The filter decodes and validates the JWT (signature, expiry), extracts userId, role_code, and Set<RbacPermission> from claims, and populates Spring SecurityContext with a HubPrincipal. No DB lookup on every request; all needed data is in the JWT. Return HTTP 401 on missing/invalid/expired token. Token is issued by AuthenticationService (T06) and signed with an HMAC-SHA256 secret loaded from application config (never hardcoded). | • Create HubPrincipal implementing Authentication with userId, roleCode, Set<RbacPermission> • Create JwtRbacFilter extends OncePerRequestFilter: extract Bearer token, validate with JJWT, build HubPrincipal, set in SecurityContext • Register filter in Spring Security filter chain before UsernamePasswordAuthenticationFilter • Return 401 JSON {error:'UNAUTHORIZED'} on missing/invalid token; return 401 {error:'TOKEN_EXPIRED'} on expiry • Exempt /api/admin/auth/login and /api/admin/auth/refresh from filter | HubPrincipal.java, JwtRbacFilter.java, and SecurityConfig.java wiring the filter | • Request with valid token populates SecurityContext with correct userId and permissions • Request with no Authorization header returns HTTP 401 with error code UNAUTHORIZED • Request with expired token (exp in the past) returns HTTP 401 with error code TOKEN_EXPIRED • Request with a tampered token signature returns HTTP 401 • Request to /api/admin/auth/login passes through without requiring a token | 45 | 10.10-T06 | FS | PRD-07, SEC-09
10.10-T08 | admin-ui | 10.10 | 10. Admin System | User & role management (RBAC) | 1 | Implement @RequiresPermission annotation and PermissionEnforcer AOP aspect | Controller methods need declarative RBAC enforcement. Design: @RequiresPermission(RbacPermission.MANAGE_USERS_AND_ROLES) on a method causes the AOP aspect to check HubPrincipal.permissions.has(required) before invocation. If check fails: throw AccessDeniedException which maps to HTTP 403 {error:'FORBIDDEN', requiredPermission:'MANAGE_USERS_AND_ROLES'}. Use Spring AOP @Around. HubPrincipal is retrieved from SecurityContextHolder (populated by JwtRbacFilter in T07). | • Create @RequiresPermission annotation with RbacPermission value() • Create PermissionEnforcerAspect @Aspect @Component with @Around advice targeting methods annotated with @RequiresPermission • Extract HubPrincipal from SecurityContextHolder; throw AccessDeniedException if principal is null or permissions check fails • Create GlobalExceptionHandler mapping AccessDeniedException to 403 response body {error:'FORBIDDEN',requiredPermission:'<name>'} • Write unit test PermissionEnforcerTest: mock principal with OPS_OPERATOR permissions; call method requiring MANAGE_USERS_AND_ROLES; assert 403 | RequiresPermission.java annotation, PermissionEnforcerAspect.java, AccessDeniedException.java, and PermissionEnforcerTest.java | • Method annotated @RequiresPermission(MANAGE_USERS_AND_ROLES) called with SUPER_ADMIN principal proceeds without exception • Same method called with OPS_OPERATOR principal throws AccessDeniedException • AccessDeniedException maps to HTTP 403 response with requiredPermission field set to 'MANAGE_USERS_AND_ROLES' • Unauthenticated call (no principal in context) throws AccessDeniedException with error UNAUTHORIZED • Method with no annotation is never intercepted by the aspect (verified via invocation count) | 40 | 10.10-T07 | FS | PRD-07, SEC-09
10.10-T09 | admin-ui | 10.10 | 10. Admin System | User & role management (RBAC) | 1 | Implement UserManagementService: create user, assign role, deactivate, reactivate | PRD-07 §12.4: only SUPER_ADMIN can manage users. Operations: (a) create user with email, name, role_code -> generates temporary password (UUID-based), sets must_change_password=true, hashes with BCrypt strength 12; (b) assign a different role to an existing user; (c) deactivate user (is_active=false, invalidate sessions); (d) reactivate user (is_active=true, reset locked_until=NULL, failed_login_count=0). All operations must emit an audit event: USER_CREATED, USER_ROLE_ASSIGNED, USER_DEACTIVATED, USER_REACTIVATED. A user cannot deactivate themselves. SUPER_ADMIN is the only role that can perform these operations (enforced via @RequiresPermission(MANAGE_USERS_AND_ROLES) from T08). | • Create UserManagementService with methods: createUser(email, name, roleCode, createdBy), assignRole(userId, roleCode, actorId), deactivateUser(userId, actorId), reactivateUser(userId, actorId) • In createUser: validate email format and uniqueness (throw DuplicateEmailException if exists), generate temp password, BCrypt hash, set must_change_password=true • In deactivateUser: throw SelfDeactivationException if userId==actorId • Emit AuditEvent for each operation with actor_id, entity_type='hub_user', entity_id, event_type code, previous_value/new_value JSON • Annotate each service method with @RequiresPermission(MANAGE_USERS_AND_ROLES) | UserManagementService.java with 4 operations plus DuplicateEmailException.java and SelfDeactivationException.java | • createUser with duplicate email throws DuplicateEmailException; no DB row is written • Created user has must_change_password=true and password_hash is BCrypt-encoded (starts with '$2a$12$') • deactivateUser where actorId==userId throws SelfDeactivationException • reactivateUser clears locked_until=NULL and failed_login_count=0 • Each of the 4 operations fires exactly one AuditEvent with correct event_type code | 50 | 10.10-T08 | FS | PRD-07, SEC-09
10.10-T10 | admin-ui | 10.10 | 10. Admin System | User & role management (RBAC) | 1 | Implement ForcePasswordChange flow: validate and update password | PRD-07 §12.4: new users are created with a temporary password and must_change_password=true. SEC-09 §3.2 password policy (applied to all portal users): minimum 12 characters; must contain at least one uppercase, one lowercase, one digit, one special character; cannot reuse the previous password. On successful change: set must_change_password=false, update password_hash (BCrypt strength 12), revoke all existing refresh tokens for the user. JWT claim must_change_password=true forces the frontend to the change-password screen before any other action. Emit audit event PASSWORD_CHANGED. | • Create PasswordChangeService.changePassword(userId, currentPassword, newPassword) method • Validate: currentPassword matches stored hash (BCrypt verify); newPassword != currentPassword (no reuse check against stored hash); newPassword passes complexity rule (regex: (?=.*[A-Z])(?=.*[a-z])(?=.*\d)(?=.*[^A-Za-z0-9]).{12,}) • Update password_hash with BCrypt strength 12; set must_change_password=false; nullify refresh_token_hash • Emit AuditEvent PASSWORD_CHANGED with actor=userId • Create PasswordChangeController POST /api/admin/auth/password-change; allow unauthenticated but require valid access-token with must_change_password=true claim OR authenticated session | PasswordChangeService.java, PasswordChangeController.java, and PasswordPolicyValidator.java | • Password 'abc' (11 chars, no complexity) is rejected with INVALID_PASSWORD_POLICY • Password equal to current password is rejected with PASSWORD_REUSE_DENIED • Valid new password updates password_hash and sets must_change_password=false • After successful change, old access token with must_change_password=true claim is still technically valid for the 30-min TTL but refresh token is revoked (refresh attempt returns 401) • Audit event PASSWORD_CHANGED is emitted exactly once per successful change | 45 | 10.10-T06, 10.10-T09 | FS | PRD-07, SEC-09
10.10-T11 | admin-ui | 10.10 | 10. Admin System | User & role management (RBAC) | 1 | Implement force-password-reset by Super Admin | PRD-07 §12.4: Super Admin can force a password reset for any user. This sets must_change_password=true and generates a new temporary password (UUID-based), invalidates all existing sessions by nullifying refresh_token_hash. The temporary password should be returned once in the API response for the Super Admin to communicate to the user out-of-band (it is hashed immediately; never stored in plain text in DB). Emit audit event PASSWORD_RESET_FORCED with actor=superAdminId and entity=targetUserId. | • Add UserManagementService.forcePasswordReset(targetUserId, actorId) method • Generate UUID-based temp password; BCrypt-hash it; store hash; set must_change_password=true; nullify refresh_token_hash • Return plain temp password as a one-time value in the service return object • Annotate with @RequiresPermission(MANAGE_USERS_AND_ROLES) • Add endpoint POST /api/admin/users/{userId}/force-password-reset returning {temporaryPassword: '...'} in response body • Emit AuditEvent PASSWORD_RESET_FORCED | Extended UserManagementService.forcePasswordReset() and endpoint in UserManagementController.java | • After forcePasswordReset, old refresh token returns 401 on token refresh attempt • must_change_password is true after the call • Returned temporaryPassword matches the BCrypt-stored hash (verify with BCrypt.checkpw) • Calling endpoint as OPS_OPERATOR returns HTTP 403 • Audit event PASSWORD_RESET_FORCED logged with correct actor_id and entity_id | 35 | 10.10-T09, 10.10-T10 | FS | PRD-07, SEC-09
10.10-T12 | admin-ui | 10.10 | 10. Admin System | User & role management (RBAC) | 1 | Implement unlock-user endpoint (IT Admin / Super Admin clears lockout) | SEC-09 §3.1: 5 consecutive login failures lock the account (locked_until set to infinity). Only Super Admin can unlock. Unlocking: set locked_until=NULL, failed_login_count=0. Emit audit event USER_UNLOCKED with actor and target user IDs. A Super Admin may not lock themselves out inadvertently via this path (already prevented by deactivate guard; unlock itself is always safe). Endpoint: POST /api/admin/users/{userId}/unlock. | • Add UserManagementService.unlockUser(targetUserId, actorId) method • Set locked_until=NULL and failed_login_count=0 on the target hub_user row • Annotate with @RequiresPermission(MANAGE_USERS_AND_ROLES) • Emit AuditEvent USER_UNLOCKED • Add POST /api/admin/users/{userId}/unlock endpoint returning 200 {status:'unlocked'} • Verify idempotency: calling unlock on a non-locked user succeeds without error | unlockUser() method in UserManagementService.java and unlock endpoint in UserManagementController.java | • After 5 failed logins the user is locked; calling unlock allows 6th login attempt to succeed if password is correct • Unlock called by OPS_OPERATOR returns HTTP 403 • Unlock on an already-unlocked user returns HTTP 200 (idempotent) • locked_until and failed_login_count are both NULL/0 after unlock • AuditEvent USER_UNLOCKED is emitted with actor_id and entity_id | 30 | 10.10-T09 | FS | PRD-07, SEC-09
10.10-T13 | admin-ui | 10.10 | 10. Admin System | User & role management (RBAC) | 1 | Implement GET /api/admin/users list and GET /api/admin/users/{id} detail | PRD-07 §12.4: Super Admin can view all users including last_login_at and session history per user. Response should include: id, email, name, role_code, is_active, last_login_at, created_at, created_by_name. Sensitive fields NOT returned: password_hash, refresh_token_hash, failed_login_count, locked_until (omit from response DTO). List endpoint supports optional filters: ?is_active=true¦false&role_code=OPS_OPERATOR. Both endpoints require @RequiresPermission(MANAGE_USERS_AND_ROLES). | • Create UserResponseDto with fields: id, email, name, roleCode, isActive, lastLoginAt, createdAt, createdByName • Create UserManagementController GET /api/admin/users with optional query params is_active and role_code; map to HubUserRepository query • Create GET /api/admin/users/{id} returning single UserResponseDto or 404 if not found • Annotate both with @RequiresPermission(MANAGE_USERS_AND_ROLES) • Write controller slice test: mock service; verify password_hash field is absent from JSON response | UserManagementController.java list+detail endpoints and UserResponseDto.java | • GET /api/admin/users with OPS_OPERATOR token returns HTTP 403 • GET /api/admin/users returns all 4 seed users when called as SUPER_ADMIN (bootstrap + 3 test users) • Response JSON does NOT contain password_hash, refresh_token_hash, failed_login_count, or locked_until fields • GET /api/admin/users?role_code=FINANCE_ANALYST returns only Finance Analyst users • GET /api/admin/users/{nonExistentId} returns HTTP 404 | 35 | 10.10-T09 | FS | PRD-07, SEC-09
10.10-T14 | admin-ui | 10.10 | 10. Admin System | User & role management (RBAC) | 1 | Implement POST /api/admin/users (create user) and PUT /api/admin/users/{id}/role (assign role) | PRD-07 §12.4: Super Admin creates new portal users with email, name, and role_code. A temporary password is returned once in the response. Super Admin can also reassign a user to a different role. Request body for create: {email, name, roleCode}. Request body for role assign: {roleCode}. Both require @RequiresPermission(MANAGE_USERS_AND_ROLES). Audit events USER_CREATED and USER_ROLE_ASSIGNED must fire (implemented in UserManagementService T09). Return 409 on duplicate email. Role assignment to a non-existent roleCode returns 400. | • Add POST /api/admin/users endpoint calling UserManagementService.createUser(); return 201 {userId, email, name, roleCode, temporaryPassword} • Add PUT /api/admin/users/{id}/role endpoint calling UserManagementService.assignRole(); return 200 {userId, roleCode} • Validate request body with @Valid: email must be RFC-5321 format; name 1-200 chars; roleCode must be one of 4 canonical values • Return 409 {error:'DUPLICATE_EMAIL'} when email already exists • Return 400 {error:'INVALID_ROLE_CODE'} when roleCode is not a known role | Create-user and assign-role endpoints in UserManagementController.java with @Valid request DTOs | • POST with valid body returns 201 and temporaryPassword is a non-empty string • POST with email='not-an-email' returns 400 with field validation error • POST with existing email returns 409 with error code DUPLICATE_EMAIL • PUT /api/admin/users/{id}/role with roleCode='UNKNOWN' returns 400 • PUT with OPS_OPERATOR token returns 403 | 40 | 10.10-T09, 10.10-T13 | FS | PRD-07, SEC-09
10.10-T15 | admin-ui | 10.10 | 10. Admin System | User & role management (RBAC) | 1 | Implement POST /api/admin/users/{id}/deactivate and /reactivate endpoints | PRD-07 §12.4: Super Admin can deactivate (is_active=false) and reactivate (is_active=true) user accounts. Deactivating a user also invalidates their active sessions by nullifying refresh_token_hash. A Super Admin cannot deactivate themselves. Reactivation clears locked_until and failed_login_count. Both operations require @RequiresPermission(MANAGE_USERS_AND_ROLES). Audit events USER_DEACTIVATED and USER_REACTIVATED must be emitted (implemented in UserManagementService T09). Deactivating an already-inactive user is idempotent (200 OK, no error). | • Add POST /api/admin/users/{id}/deactivate calling UserManagementService.deactivateUser(userId, actorId) • Add POST /api/admin/users/{id}/reactivate calling UserManagementService.reactivateUser(userId, actorId) • Map SelfDeactivationException to HTTP 422 {error:'CANNOT_DEACTIVATE_SELF'} • Both endpoints return 200 {userId, isActive} after success • Add 404 guard if userId does not exist | Deactivate and reactivate endpoints in UserManagementController.java | • Deactivating an active user returns 200 and is_active becomes false in DB • After deactivation, login attempt returns 401 (is_active check in AuthenticationService) • Deactivate where actorId==userId returns HTTP 422 with error CANNOT_DEACTIVATE_SELF • Reactivate restores is_active=true and clears locked_until • Deactivating an already-inactive user returns 200 (idempotent) | 30 | 10.10-T09, 10.10-T13 | FS | PRD-07, SEC-09
10.10-T16 | admin-ui | 10.10 | 10. Admin System | User & role management (RBAC) | 1 | Implement token refresh endpoint POST /api/admin/auth/refresh | Session design (T06): access tokens expire in 30 minutes; refresh tokens expire in 8 hours (SEC-09 §3.1 8h max session). POST /api/admin/auth/refresh accepts {refreshToken: '<opaque-uuid>'}, validates it against the hashed value in hub_user.refresh_token_hash (BCrypt), checks is_active=true and locked_until IS NULL, checks refresh token not older than 8h (stored as refresh_token_issued_at TIMESTAMPTZ on hub_user). On success: issues a new access token (30min) and rotates refresh token (new UUID, rehash, update DB). On failure: return 401. | • Add refresh_token_hash VARCHAR(255) and refresh_token_issued_at TIMESTAMPTZ columns to hub_user via migration V10_10_004__add_refresh_token_cols.sql • Implement TokenRefreshService.refresh(rawRefreshToken) method: lookup user by finding matching hash, validate age (now - refresh_token_issued_at < 8h), issue new access JWT, rotate refresh token • Return 401 {error:'INVALID_REFRESH_TOKEN'} if hash not found or age exceeded • Return 401 {error:'ACCOUNT_INACTIVE'} if is_active=false • Create POST /api/admin/auth/refresh endpoint (no auth filter required) | Migration V10_10_004, TokenRefreshService.java, and refresh endpoint in AuthController.java | • Valid refresh token within 8h returns new accessToken and new refreshToken • Using the old refreshToken after rotation returns 401 INVALID_REFRESH_TOKEN (single-use rotation) • Refresh token older than 8h (refresh_token_issued_at + 8h < now) returns 401 • Refresh token belonging to a deactivated user returns 401 ACCOUNT_INACTIVE • New access token contains correct role and permissions for the user | 50 | 10.10-T06, 10.10-T07 | FS | PRD-07, SEC-09
10.10-T17 | admin-ui | 10.10 | 10. Admin System | User & role management (RBAC) | 1 | Implement POST /api/admin/auth/logout endpoint | Logging out invalidates the session by nullifying hub_user.refresh_token_hash. The access token (JWT) cannot be server-side revoked (stateless); it expires naturally within 30 minutes. Logout must accept the current valid access token (Bearer) and nullify refresh_token_hash for the authenticated user (extracted from JWT sub claim). Emit audit event AUTH_LOGOUT. After logout, token refresh returns 401. Phase 1 local accounts only; SSO logout is Phase 2. | • Create POST /api/admin/auth/logout endpoint; protected by JwtRbacFilter (requires valid access token) • Extract userId from HubPrincipal in SecurityContext • Set hub_user.refresh_token_hash=NULL for that userId • Emit AuditEvent AUTH_LOGOUT with actor_id and ip_address • Return 204 No Content on success | Logout endpoint in AuthController.java | • POST /api/admin/auth/logout with valid token returns 204 and clears refresh_token_hash in DB • Subsequent POST /api/admin/auth/refresh with the old refresh token returns 401 • Logout with no token returns 401 (filter rejects) • AuditEvent AUTH_LOGOUT is emitted with the correct actor userId • Second logout call (after first already cleared token hash) returns 204 (idempotent) | 25 | 10.10-T16 | FS | PRD-07, SEC-09
10.10-T18 | admin-ui | 10.10 | 10. Admin System | User & role management (RBAC) | 1 | Implement Admin Portal permission guard: Users & Roles module visibility | PRD-07 §15.9 acceptance: OPS_OPERATOR cannot access the Users & Roles module; FINANCE_ANALYST and ADMIN_VIEWER also cannot. Only SUPER_ADMIN (with MANAGE_USERS_AND_ROLES permission) can see and access this module. Backend: all /api/admin/users/** and /api/admin/roles/** routes already require @RequiresPermission(MANAGE_USERS_AND_ROLES) (T08-T15). Frontend: the nav item 'Users & Roles' must be conditionally rendered based on permissions in the JWT. This ticket implements a backend endpoint the frontend uses to determine which nav items to show. | • Create GET /api/admin/me endpoint returning {userId, email, name, roleCode, permissions:[...]} from current HubPrincipal • This endpoint is protected by JwtRbacFilter (any authenticated user can call it) • Response permissions field is the array of RbacPermission names the user holds • Frontend will use permissions.includes('MANAGE_USERS_AND_ROLES') to decide nav visibility • Write a controller test asserting ADMIN_VIEWER token returns permissions without MANAGE_USERS_AND_ROLES | GET /api/admin/me endpoint in AuthController.java returning current user profile and permissions list | • SUPER_ADMIN token returns permissions array containing MANAGE_USERS_AND_ROLES • OPS_OPERATOR token returns permissions array NOT containing MANAGE_USERS_AND_ROLES • ADMIN_VIEWER token returns permissions array with exactly VIEW_DASHBOARD, VIEW_FX_RATE_HISTORY, SEARCH_VIEW_TRANSACTIONS, VIEW_REFUND_STATUS • Unauthenticated request returns 401 • Response contains roleCode field matching the user's actual role_code from DB | 25 | 10.10-T07, 10.10-T13 | FS | PRD-07, SEC-09
10.10-T19 | admin-ui | 10.10 | 10. Admin System | User & role management (RBAC) | 1 | Implement view-only credential masking: ADMIN_VIEWER cannot see pool values or API credentials | PRD-07 §15.9: ADMIN_VIEWER can search transactions but cannot see locked pool values or API credentials. This is enforced at the service/controller layer, not just UI. Pool value fields (collection_usd, payout_usd_cost, collection_margin_usd, payout_margin_usd, offer_rate_coll, cross_rate) must be omitted or replaced with null in transaction detail responses when the caller lacks VIEW_LOCKED_RATE_POOL_VALUES. API credential fields (api_key, api_secret_hash) must be omitted from partner detail responses when caller lacks VIEW_API_CREDENTIALS. | • Create ResponseMaskingService with maskTransactionDetail(TransactionDetailDto dto, Set<RbacPermission> perms) and maskPartnerDetail(PartnerDetailDto dto, Set<RbacPermission> perms) • In maskTransactionDetail: if perms does not contain VIEW_LOCKED_RATE_POOL_VALUES, set collection_usd, payout_usd_cost, collection_margin_usd, payout_margin_usd, offer_rate_coll, cross_rate to null • In maskPartnerDetail: if perms does not contain VIEW_API_CREDENTIALS, set api_key and api_secret_hash to null • Inject ResponseMaskingService into TransactionController and PartnerController; call masking after fetching data • Write unit test with 4 scenarios: SUPER_ADMIN sees all fields; ADMIN_VIEWER sees null pool values and null credentials | ResponseMaskingService.java and unit test ResponseMaskingServiceTest.java | • ADMIN_VIEWER calling GET /api/admin/transactions/{id} receives response where collection_usd is null • FINANCE_ANALYST calling GET /api/admin/transactions/{id} receives response where collection_usd is non-null (FINANCE_ANALYST has VIEW_LOCKED_RATE_POOL_VALUES) • ADMIN_VIEWER calling GET /api/admin/partners/{id} receives response where api_key is null • OPS_OPERATOR calling GET /api/admin/partners/{id} receives api_key non-null • Masking does not alter the underlying DB entity; re-fetching returns full data for SUPER_ADMIN | 40 | 10.10-T08 | FS | PRD-07, SEC-09
10.10-T20 | admin-ui | 10.10 | 10. Admin System | User & role management (RBAC) | 1 | Implement AuditEventService and admin_audit_log table | PRD-07 §13 and DAT-03: audit_log table stores immutable append-only entries. Fields per §13.3: id UUID PK, occurred_at TIMESTAMPTZ ms precision, actor_user_id BIGINT FK hub_user, actor_display_name VARCHAR(200), actor_ip_address INET, event_type VARCHAR(60) (e.g. USER_CREATED, AUTH_LOGIN_FAILED), entity_type VARCHAR(40) (hub_user, hub_role, partner, scheme, rule, etc.), entity_id VARCHAR(64), previous_value JSONB, new_value JSONB, description TEXT, metadata JSONB. No UPDATE or DELETE permitted (application service account has INSERT-only permission on this table per DAT-03 §9.1). | • Create Flyway migration V10_10_005__create_admin_audit_log.sql with table DDL; no FK enforcement on actor_user_id to allow system/bootstrap events without a user row • Create AuditLogEntry JPA entity (insertable=true, updatable=false for all columns to enforce immutability at ORM layer) • Create AuditEventService.log(AuditEventDto) method that persists via a dedicated EntityManager with INSERT-only semantics • Define AuditEventDto record with all fields from context • Consume Spring ApplicationEvents (published by T09/T10/etc.) and delegate to AuditEventService in an @EventListener | Migration V10_10_005, AuditLogEntry.java entity, AuditEventService.java, AuditEventDto.java | • INSERT into admin_audit_log succeeds; subsequent UPDATE raises an exception (ORM @Column(updatable=false) guard) • AuditEventService.log() with AUTH_LOGIN_FAILED event results in a row with correct event_type in DB • ApplicationEvent published by UserManagementService.createUser() results in a persisted audit row within the same transaction • occurred_at stored with millisecond precision (not second) • Attempting to delete a row via AuditEventService throws UnsupportedOperationException | 45 | 10.10-T02 | FS | PRD-07, SEC-09
10.10-T21 | admin-ui | 10.10 | 10. Admin System | User & role management (RBAC) | 1 | Implement audit log search endpoint GET /api/admin/audit-log | PRD-07 §13.5: audit log is searchable by actor (user ID), event_type, entity_type, entity_id, date range (required; max 12-month window per query), ip_address. Results paginated at 100 per page. Requires @RequiresPermission(VIEW_AUDIT_LOG) - only SUPER_ADMIN and OPS_OPERATOR have this permission. Date range is required: reject if start_date or end_date missing; reject if range exceeds 366 days. Max 100 rows per page; page param (0-based). | • Create AuditLogSearchRequest DTO with fields: actorUserId (Long, optional), eventType (String, optional), entityType (String, optional), entityId (String, optional), startDate (LocalDate, required), endDate (LocalDate, required), ipAddress (String, optional), page (int default 0) • Create AuditLogRepository with dynamic query using JPA Specification or QueryDSL • Create GET /api/admin/audit-log endpoint; validate date range present and <= 366 days; annotate @RequiresPermission(VIEW_AUDIT_LOG) • Return paginated response {content:[...], totalElements, page, pageSize:100} • Reject requests without startDate/endDate with 400 {error:'DATE_RANGE_REQUIRED'} | AuditLogRepository.java with search, AuditLogController.java with GET endpoint, AuditLogSearchRequest.java | • Request without startDate returns HTTP 400 DATE_RANGE_REQUIRED • Request with date range of 400 days returns HTTP 400 DATE_RANGE_EXCEEDS_MAX • ADMIN_VIEWER token returns HTTP 403 (lacks VIEW_AUDIT_LOG) • OPS_OPERATOR token with valid date range returns 200 with paginated results • Filter by entity_type='hub_user' returns only user-management events | 45 | 10.10-T20, 10.10-T08 | FS | PRD-07, SEC-09
10.10-T22 | admin-ui | 10.10 | 10. Admin System | User & role management (RBAC) | 1 | Implement audit log CSV export POST /api/admin/audit-log/export | PRD-07 §13.5: CSV export of all matching audit log entries; up to 500,000 rows. Exports up to 30-day window complete synchronously within 30 seconds; windows > 30 days are queued as async jobs with email notification when ready. Requires @RequiresPermission(EXPORT_AUDIT_LOG) - only SUPER_ADMIN has this. CSV columns: id, occurred_at, actor_display_name, actor_ip_address, event_type, entity_type, entity_id, previous_value (JSON string), new_value (JSON string), description. Synchronous response: Content-Disposition: attachment; filename=audit_log_<start>_<end>.csv. | • Create AuditLogExportService.export(AuditLogSearchRequest request) that streams CSV rows using JPA ScrollableResults or JdbcTemplate streaming • For window <= 30 days: stream directly to HTTP response as application/octet-stream with Content-Disposition header • For window > 30 days: queue an AsyncExportJob (store in DB table audit_export_job), return 202 {jobId, message:'Export queued; you will receive an email when ready'} • Annotate endpoint POST /api/admin/audit-log/export with @RequiresPermission(EXPORT_AUDIT_LOG) • Write a test that exports 10 seed audit rows and validates CSV column headers and row count | AuditLogExportService.java, export endpoint in AuditLogController.java, CSV column spec | • Export with date range of 7 days returns HTTP 200 with Content-Disposition header containing 'attachment' • CSV first row contains expected headers: id,occurred_at,actor_display_name,actor_ip_address,event_type,entity_type,entity_id,previous_value,new_value,description • Export with date range > 30 days returns HTTP 202 with jobId in response body • OPS_OPERATOR token returns HTTP 403 (lacks EXPORT_AUDIT_LOG) • Export of 10 seed rows produces CSV with exactly 11 lines (1 header + 10 data rows) | 50 | 10.10-T21 | FS | PRD-07, SEC-09
10.10-T23 | admin-ui | 10.10 | 10. Admin System | User & role management (RBAC) | 1 | Unit tests: AuthenticationService login and lockout logic | Test the lockout and session logic of AuthenticationService (T06) with exact input/output scenarios. Use JUnit 5 + Mockito; no real DB. Scenarios: (a) correct credentials, (b) wrong password increments failed_login_count, (c) 5th failure locks account (locked_until != null), (d) locked account rejects even with correct password, (e) unlocked account (T12) allows login again, (f) inactive account (is_active=false) rejects login with ACCOUNT_INACTIVE error. | • Create AuthenticationServiceTest.java with 6 test methods as described in context • Mock HubUserRepository to return pre-configured HubUser stubs • Assert failed_login_count increments on each wrong password call • Assert locked_until is non-null after the 5th consecutive failure • Assert that a 6th call with correct password still throws AccountLockedException (account remains locked) • Assert is_active=false user throws AccountInactiveException regardless of password | AuthenticationServiceTest.java with 6 named test methods covering all lockout scenarios | • Test (a) correctCredentials: returns TokenPair with non-null accessToken • Test (b) wrongPasswordOnce: hub_user.failed_login_count==1 after call • Test (c) fiveConsecutiveFailures: hub_user.locked_until is non-null • Test (d) lockedAccountCorrectPassword: throws AccountLockedException • Test (e) after unlockUser() sets locked_until=null and failed_login_count=0: correct login succeeds • Test (f) inactiveUser: throws AccountInactiveException | 40 | 10.10-T06, 10.10-T12 | FS | PRD-07, SEC-09
10.10-T24 | admin-ui | 10.10 | 10. Admin System | User & role management (RBAC) | 1 | Unit tests: PermissionEnforcer - all 4 roles against permission matrix | Systematically verify that every role-permission combination from PRD-07 §12.3 is correctly enforced. 22 permissions x 4 roles = 88 combinations. Test method pattern: given a HubPrincipal with role X, call PermissionEnforcerAspect check for permission Y, assert granted or denied. Key boundary cases: FINANCE_ANALYST has CREATE_MANUAL_ADJUSTMENT but not RECORD_TOP_UP; OPS_OPERATOR has RECORD_TOP_UP but not CREATE_MANUAL_ADJUSTMENT; ADMIN_VIEWER has VIEW_REFUND_STATUS but not VIEW_LOCKED_RATE_POOL_VALUES or VIEW_PREFUNDING_BALANCE. | • Create PermissionMatrixTest.java • Build a parameterized test @ParameterizedTest @MethodSource with tuples of (roleCode, permission, expectedGranted) • Source method returns all 88 role-permission pairs from the canonical matrix in T04 • For each tuple: create HubPrincipal with the role's canonical permissions, invoke aspect check, assert granted or denied • Flag any tuple where expected != actual as a test failure with descriptive message | PermissionMatrixTest.java with 88 parameterized test cases derived from the canonical matrix | • FINANCE_ANALYST + CREATE_MANUAL_ADJUSTMENT -> granted • FINANCE_ANALYST + RECORD_TOP_UP -> denied • OPS_OPERATOR + MANAGE_USERS_AND_ROLES -> denied • ADMIN_VIEWER + VIEW_LOCKED_RATE_POOL_VALUES -> denied • SUPER_ADMIN + any of the 22 permissions -> all 22 granted | 45 | 10.10-T08, 10.10-T04 | FS | PRD-07, SEC-09
10.10-T25 | admin-ui | 10.10 | 10. Admin System | User & role management (RBAC) | 1 | Unit tests: UserManagementService create, assign role, deactivate, reactivate | Test UserManagementService (T09) with Mockito-mocked repositories. Verify: (a) createUser persists a user with BCrypt hash and must_change_password=true; (b) createUser with duplicate email throws DuplicateEmailException and does NOT call repository.save(); (c) assignRole updates role_id; (d) deactivateUser with actorId==userId throws SelfDeactivationException; (e) deactivate sets is_active=false and nullifies refresh_token_hash; (f) reactivate clears locked_until and failed_login_count; (g) all 4 operations fire exactly one AuditEvent each. | • Create UserManagementServiceTest.java with 7 test methods as listed in context • Mock HubUserRepository and HubRoleRepository; mock ApplicationEventPublisher • In test (a): capture the saved HubUser entity and verify password_hash starts with '$2a$12$' • In test (b): stub repository.findByEmail() to return non-empty Optional; verify save() never called • In test (d): call deactivateUser(userId=5, actorId=5); assert SelfDeactivationException thrown • In tests (e)(f): verify specific field values on the captured save() argument | UserManagementServiceTest.java with 7 test methods all passing | • Test (a): saved user.passwordHash starts with '$2a$12$' (BCrypt strength 12 prefix) • Test (a): saved user.mustChangePassword==true • Test (b): repository.save() is never invoked when email is duplicate • Test (d): SelfDeactivationException thrown when userId==actorId • Test (g): ApplicationEventPublisher.publishEvent() called exactly once per operation with correct AuditEventDto.eventType | 45 | 10.10-T09 | FS | PRD-07, SEC-09
10.10-T26 | admin-ui | 10.10 | 10. Admin System | User & role management (RBAC) | 1 | Unit tests: ResponseMaskingService field nullification by role | Test ResponseMaskingService (T19) with 4 scenarios corresponding to the 4 roles. TransactionDetailDto has fields: txnRef, status, collectionUsd, payoutUsdCost, collectionMarginUsd, payoutMarginUsd, offerRateColl, crossRate, and non-sensitive fields (partnerName, amount, currency). PartnerDetailDto has fields: partnerId, partnerName, apiKey, apiSecretHash, and non-sensitive fields. Verify masking does not touch non-sensitive fields. | • Create ResponseMaskingServiceTest.java • Build canonical PermissionSet for each of the 4 roles (reuse PermissionSet.fromJsonb from T03 or derive from T04 seeds) • Test maskTransactionDetail for each role; assert pool fields null only for ADMIN_VIEWER; non-sensitive fields (partnerName, amount) always non-null • Test maskPartnerDetail for each role; assert apiKey null for FINANCE_ANALYST and ADMIN_VIEWER; assert apiKey non-null for SUPER_ADMIN and OPS_OPERATOR • Verify masking returns a new DTO (does not mutate the input) | ResponseMaskingServiceTest.java with 8 test methods (2 DTO types x 4 roles) | • ADMIN_VIEWER: collectionUsd is null, partnerName is non-null in masked TransactionDetailDto • FINANCE_ANALYST: collectionUsd is non-null in masked TransactionDetailDto • ADMIN_VIEWER: apiKey is null in masked PartnerDetailDto • OPS_OPERATOR: apiKey is non-null in masked PartnerDetailDto • Input DTO fields are unchanged after masking call (immutability) | 35 | 10.10-T19 | FS | PRD-07, SEC-09
10.10-T27 | admin-ui | 10.10 | 10. Admin System | User & role management (RBAC) | 1 | Integration test: full RBAC flow - login, access guarded endpoint, token refresh, logout | End-to-end integration test using Testcontainers (PostgreSQL) and Spring Boot test slice. Verifies: (a) OPS_OPERATOR logs in and gets JWT; (b) OPS_OPERATOR calls GET /api/admin/users returns 403; (c) SUPER_ADMIN logs in; (d) SUPER_ADMIN calls GET /api/admin/users returns 200; (e) SUPER_ADMIN creates a new OPS_OPERATOR user; (f) new user logs in with temp password; (g) new user is forced to change password; (h) after password change, new user gets a normal JWT without must_change_password claim; (i) token refresh works; (j) logout invalidates refresh token. | • Create RbacIntegrationTest.java with @SpringBootTest and @Testcontainers (or embedded Postgres) • Use MockMvc or TestRestTemplate; run Flyway migrations including seed data from T01-T05 • Implement steps (a)-(j) as an ordered @Test sequence or @TestMethodOrder • Assert HTTP status codes match expectations at each step • Assert specific JWT claim values at steps (f) and (h) | RbacIntegrationTest.java covering the 10-step scenario described in context | • Step (b) returns HTTP 403 with OPS_OPERATOR token • Step (d) returns HTTP 200 with SUPER_ADMIN token • Step (f) JWT contains claim must_change_password=true • Step (h) JWT does NOT contain must_change_password=true (or it is false) • Step (j) token refresh after logout returns HTTP 401 INVALID_REFRESH_TOKEN | 55 | 10.10-T17, 10.10-T14, 10.10-T10 | FS | PRD-07, SEC-09
10.10-T28 | admin-ui | 10.10 | 10. Admin System | User & role management (RBAC) | 1 | Integration test: audit log immutability and event coverage for user management | Verifies that audit log entries are correctly written and cannot be deleted for all user management operations. Uses Testcontainers Postgres. Sequence: (a) SUPER_ADMIN creates a user -> verify USER_CREATED event in audit log; (b) assign role -> USER_ROLE_ASSIGNED; (c) force password reset -> PASSWORD_RESET_FORCED; (d) deactivate -> USER_DEACTIVATED; (e) reactivate -> USER_REACTIVATED; (f) unlock -> USER_UNLOCKED; (g) attempt DELETE on admin_audit_log via JdbcTemplate -> verify exception or 0 rows affected. Also verify AUTH_LOGIN_FAILED event written on bad-password attempt. | • Create AuditLogIntegrationTest.java with @SpringBootTest and Testcontainers Postgres • Perform each user management operation via service layer (not REST); then query admin_audit_log by event_type • Assert each operation produces exactly 1 audit row with correct entity_id • Attempt JDBC DELETE FROM admin_audit_log WHERE id=<id>; assert either exception or rowsAffected==0 (depends on DB-level permission setup; mock the permission by testing ORM updatable=false guard) • Verify AUTH_LOGIN_FAILED written after 1 bad login attempt | AuditLogIntegrationTest.java verifying 7 event types and immutability guard | • USER_CREATED audit row exists after createUser() call with correct actor_user_id • USER_DEACTIVATED audit row contains previous_value JSON with is_active:true • Attempting UPDATE on audit log entity via JPA throws exception (updatable=false columns) • AUTH_LOGIN_FAILED row written with actor_ip_address matching the test IP • All 7 event types (USER_CREATED, USER_ROLE_ASSIGNED, PASSWORD_RESET_FORCED, USER_DEACTIVATED, USER_REACTIVATED, USER_UNLOCKED, AUTH_LOGIN_FAILED) have at least 1 row after running all operations | 50 | 10.10-T20, 10.10-T27 | FS | PRD-07, SEC-09
10.10-T29 | admin-ui | 10.10 | 10. Admin System | User & role management (RBAC) | 1 | Implement Users & Roles UI: user list table (React component) | PRD-07 §12 / UX-11: The Users & Roles module shows a table of admin users. Columns: Name, Email, Role, Status (Active/Inactive badge), Last Login, Actions (Edit Role / Deactivate / Reactivate / Force Reset). Visible only when permissions.includes('MANAGE_USERS_AND_ROLES') (from GET /api/admin/me). Uses GET /api/admin/users API (T13). Data displayed: UserResponseDto fields. No horizontal scroll; max 6 columns (per CONVENTIONS.md). Role badge uses colour coding: SUPER_ADMIN=red, OPS_OPERATOR=blue, FINANCE_ANALYST=green, ADMIN_VIEWER=grey. | • Create UserListPage.tsx React component fetching GET /api/admin/users • Render a table with 6 columns: Name, Email, Role (badge), Status (badge), Last Login (formatted datetime), Actions • Conditionally render 'Users & Roles' nav link only when hasPermission('MANAGE_USERS_AND_ROLES') from useAuth() hook • Role badge colours: SUPER_ADMIN=#DC2626, OPS_OPERATOR=#2563EB, FINANCE_ANALYST=#16A34A, ADMIN_VIEWER=#6B7280 • Actions column: show Deactivate button for active users, Reactivate for inactive; always show Edit Role and Force Reset | UserListPage.tsx React component with permission-gated nav link | • Nav link 'Users & Roles' is not rendered in DOM when user has OPS_OPERATOR role (verified via React Testing Library query) • Table renders 4 columns visible without horizontal scroll at 1280px viewport • SUPER_ADMIN badge has background color #DC2626 • Deactivate button is shown for is_active=true users; Reactivate for is_active=false users • Empty state message is rendered when no users are returned from API | 50 | 10.10-T13, 10.10-T18 | FS | PRD-07, SEC-09
10.10-T30 | admin-ui | 10.10 | 10. Admin System | User & role management (RBAC) | 1 | Implement Users & Roles UI: create user modal and assign role form | PRD-07 §12.4 / UX-11: The Create User modal collects: Email, Full Name, Role (dropdown with 4 canonical roles). On submit calls POST /api/admin/users (T14). On success shows a one-time dialog displaying the temporary password with a copy-to-clipboard button and a warning 'This password will not be shown again'. Role selector shows all 4 role codes with human-readable labels: SUPER_ADMIN=Super Admin, OPS_OPERATOR=Ops Operator, FINANCE_ANALYST=Finance Analyst, ADMIN_VIEWER=Admin Viewer. Assign Role uses PUT /api/admin/users/{id}/role (T14). Both forms use inline validation. | • Create CreateUserModal.tsx with controlled form fields: email, name, roleCode selector • On POST success: render TemporaryPasswordDialog.tsx showing temporaryPassword from API response with copy button • Create AssignRoleModal.tsx with role selector dropdown; calls PUT /api/admin/users/{id}/role • Inline validation: email format check before submit; name min 1 char; roleCode required • Handle 409 DUPLICATE_EMAIL response by showing inline error 'A user with this email already exists' | CreateUserModal.tsx, TemporaryPasswordDialog.tsx, and AssignRoleModal.tsx React components | • Submitting form with invalid email format shows inline error without API call • On successful create, TemporaryPasswordDialog renders with the temporary password value • TemporaryPasswordDialog copy button copies text to clipboard (jsdom navigator.clipboard mock) • 409 response from API renders inline field error on the email field • Role dropdown renders exactly 4 options with human-readable labels | 50 | 10.10-T29, 10.10-T14 | FS | PRD-07, SEC-09
10.10-T31 | admin-ui | 10.10 | 10. Admin System | User & role management (RBAC) | 1 | Implement Users & Roles UI: deactivate, reactivate, force-reset confirmation dialogs | PRD-07 §14.2: destructive or irreversible actions require a two-step confirmation with a summary dialog before execution. Deactivating a user, reactivating, and forcing a password reset all require confirmation dialogs. Dialog content: Deactivate - 'Deactivate [Name]? They will be immediately logged out and cannot log in until reactivated.'; Force Reset - 'Reset password for [Name]? A new temporary password will be generated. Their current sessions will be invalidated.'; Reactivate - 'Reactivate [Name]? They will be able to log in again.' Actions call POST /api/admin/users/{id}/deactivate, POST /api/admin/users/{id}/reactivate, POST /api/admin/users/{id}/force-password-reset (T11, T15). | • Create ConfirmActionDialog.tsx generic dialog with title, description, confirm/cancel buttons and loading state • Wire Deactivate button in UserListPage to open ConfirmActionDialog; on confirm call deactivate API; on success refresh list • Wire Reactivate button similarly • Wire Force Reset to open dialog; on confirm call force-reset API; on success show TemporaryPasswordDialog with new temp password • Handle 422 CANNOT_DEACTIVATE_SELF by showing error toast 'You cannot deactivate your own account' | ConfirmActionDialog.tsx reusable component and wiring in UserListPage.tsx | • Clicking Deactivate opens dialog with correct user name in description text • Clicking Cancel on dialog does not call the API (verified with mock assertions) • Successful deactivation closes dialog and user's status badge changes to Inactive in list • Force Reset success shows TemporaryPasswordDialog with new temporary password • 422 CANNOT_DEACTIVATE_SELF response shows error toast with correct message | 45 | 10.10-T30, 10.10-T11, 10.10-T15 | FS | PRD-07, SEC-09
10.10-T32 | admin-ui | 10.10 | 10. Admin System | User & role management (RBAC) | 1 | Implement forced-password-change screen (first login flow) | PRD-07 §12.4: new users must change their password on first login. JWT claim must_change_password=true triggers this. On login success if must_change_password=true, frontend redirects to /admin/change-password before any other route. Form collects: Current Password, New Password, Confirm New Password. Submits to POST /api/admin/auth/password-change (T10). Password policy displayed on screen: min 12 chars, uppercase, lowercase, digit, special character. On success: re-issues JWT (must_change_password no longer true) and redirects to dashboard. | • Create ChangePasswordPage.tsx route /admin/change-password • In router/auth guard: check JWT claim must_change_password; if true redirect to /admin/change-password regardless of target route • Form fields: currentPassword, newPassword, confirmNewPassword with show/hide toggles • Display password policy checklist with live validation (green/red indicators per rule as user types) • On 400 INVALID_PASSWORD_POLICY response display specific failed rule; on 400 PASSWORD_REUSE_DENIED show 'New password cannot be the same as current password' | ChangePasswordPage.tsx and route guard update in AuthGuard.tsx | • User with must_change_password=true JWT navigating to /admin/dashboard is redirected to /admin/change-password • Entering newPassword='Short1!' (less than 12 chars) shows live indicator for min-length rule as red • Entering mismatched confirmNewPassword shows inline error before submit • On successful change, user is redirected to /admin/dashboard with a new JWT where must_change_password is absent or false • Typing a password meeting all rules turns all 5 policy indicators green | 50 | 10.10-T10, 10.10-T29 | FS | PRD-07, SEC-09
10.10-T33 | admin-ui | 10.10 | 10. Admin System | User & role management (RBAC) | 1 | Frontend unit tests: UserListPage permission gating and RBAC rendering | React Testing Library tests for UserListPage.tsx (T29) and related modals. Verify permission-gated rendering for different roles by mocking the useAuth() hook to return different permission sets. Key scenarios: (a) OPS_OPERATOR: Users & Roles nav link absent; (b) SUPER_ADMIN: nav link present; (c) table renders correct badge colours; (d) ADMIN_VIEWER does not have access to this page at all (redirect); (e) create user button only visible to SUPER_ADMIN. | • Create UserListPage.test.tsx using React Testing Library and vitest/jest • Mock GET /api/admin/users with msw (Mock Service Worker) returning 3 test users • For each of 4 roles: render UserListPage with mocked useAuth() permissions; assert nav visibility • Assert role badge colour for SUPER_ADMIN row is #DC2626 (computed style or className) • Assert create user button is present for SUPER_ADMIN and absent for non-SUPER_ADMIN roles | UserListPage.test.tsx with 6+ test cases covering permission rendering | • With OPS_OPERATOR permissions, queryByText('Users & Roles') in nav returns null • With SUPER_ADMIN permissions, getByText('Users & Roles') in nav is found • With SUPER_ADMIN, 'Create User' button is present in DOM • With FINANCE_ANALYST permissions, 'Create User' button is absent • Table row for a SUPER_ADMIN user has the correct red badge class/style | 40 | 10.10-T29 | FS | PRD-07, SEC-09
10.11-T01 | admin-ui | 10.11 | 10. Admin System | Audit log viewer | 2 | Add prev_hash and entry_hash columns to audit_log migration | SEC-09 §6.3 requires a SHA-256 hash chain on the audit_log table: each row stores entry_hash (SHA-256 of this row's canonical fields) and prev_hash (entry_hash of the immediately preceding row; NULL for the very first row). This enables the daily integrity check job to detect any tampering or deletion. The audit_log table (DAT-03 §10.7) currently has: id BIGINT PK, actor_id VARCHAR(120), actor_type VARCHAR(20), action VARCHAR(20), entity_type VARCHAR(50), entity_id BIGINT, before_value JSONB, after_value JSONB, occurred_at TIMESTAMPTZ, ip_address INET, request_id VARCHAR(64). No UPDATE or DELETE is ever permitted; retention >= 7 years. | • Write Flyway migration V10_11_001: ALTER TABLE audit_log ADD COLUMN prev_hash CHAR(64) NULL, ADD COLUMN entry_hash CHAR(64) NOT NULL DEFAULT '' • Add a partial index: CREATE INDEX idx_audit_log_occurred_at ON audit_log(occurred_at DESC) • Add a unique index on entry_hash to prevent duplicate chain entries: CREATE UNIQUE INDEX idx_audit_log_entry_hash ON audit_log(entry_hash) WHERE entry_hash <> '' • Document canonical hash input: SHA-256 of concat(id¦¦actor_id¦¦actor_type¦¦action¦¦entity_type¦¦entity_id::text¦¦COALESCE(before_value::text,'')¦¦COALESCE(after_value::text,'')¦¦occurred_at::text¦¦COALESCE(prev_hash,'')) in migration comments • Verify migration applies on an existing audit_log table without data loss | Flyway migration V10_11_001 adding prev_hash CHAR(64) NULL and entry_hash CHAR(64) NOT NULL to audit_log, with index on occurred_at and unique index on entry_hash | • Migration applies cleanly on a table with existing rows (entry_hash defaults to empty string pending backfill) • prev_hash column is NULL for the first row inserted after migration • Inserting two rows with identical entry_hash raises a unique constraint violation • occurred_at DESC index is present and used by EXPLAIN for ORDER BY occurred_at DESC queries • No existing audit_log data is modified or deleted by the migration | 30 | 10.1-T01 | FS | PRD-07, SEC-09
10.11-T02 | admin-ui | 10.11 | 10. Admin System | Audit log viewer | 2 | Implement AuditLogWriter service with SHA-256 hash-chain computation | All write operations in the Admin System must call AuditLogWriter.write() which inserts one row into audit_log and computes the hash chain. The canonical hash input is: SHA-256(id::text + actor_id + actor_type + action + entity_type + entity_id::text + COALESCE(before_value::jsonb::text,'') + COALESCE(after_value::jsonb::text,'') + occurred_at::ISO8601 + COALESCE(prev_hash,'')). prev_hash = entry_hash of the row with the largest id less than the new row. The insert must be atomic: use a DB-level serialisable transaction or SELECT MAX(id) FOR UPDATE to prevent concurrent inserts racing on prev_hash. The application service account must have INSERT-only (no UPDATE, no DELETE) on audit_log; this is enforced at DB-user grant level. Retention >= 7 years; never purge via application code. | • Create AuditLogWriter.write(actor_id, actor_type, action, entity_type, entity_id, before_value, after_value, ip_address, request_id) method • Inside a serialisable transaction: SELECT entry_hash FROM audit_log ORDER BY id DESC LIMIT 1 FOR UPDATE to obtain prev_hash • Compute occurred_at = current UTC timestamp (server-generated, not client-supplied) • Compute entry_hash = hex(SHA-256(canonical_string)) where canonical_string is defined above • INSERT row; if unique-constraint violation on entry_hash, retry with fresh occurred_at (max 3 retries, then throw) • Verify the service account has INSERT only (no UPDATE/DELETE) on audit_log by running an UPDATE and asserting it is rejected with a permission error in the test suite | AuditLogWriter service class with hash-chain insert logic and unit tests | • Two successive writes produce rows where row2.prev_hash == row1.entry_hash • entry_hash is a valid 64-char hex string (SHA-256 output) • prev_hash of the very first row in a clean test DB is NULL • Concurrent write from two threads produces a valid linear chain (no duplicate prev_hash) • An attempt to UPDATE an audit_log row via the application service account is rejected with a DB permission error | 50 | 10.11-T01 | FS | PRD-07, SEC-09
10.11-T03 | admin-ui | 10.11 | 10. Admin System | Audit log viewer | 2 | Integrate AuditLogWriter into all Admin System write operations | PRD-07 §13.2 lists every write operation that must generate an audit log entry: config changes (create/edit scheme, partner, rule, treasury rate), credential operations (generate/revoke API key), refund operations, prefunding operations (top-up, manual adjustment), settlement actions (flag/resolve exception), user management (create user, assign role, deactivate), auth events (login success/failure, logout). Each entry requires: actor_id (from JWT sub), actor_role (from JWT role_code), action (CREATE/UPDATE/DELETE/ACTIVATE/DEACTIVATE), entity_type (table name), entity_id (row PK), before_value (JSONB snapshot before change; NULL for CREATE), after_value (JSONB snapshot after change; NULL for DELETE), ip_address (from request context), request_id (trace ID). before_value and after_value must never contain plaintext secrets (API secret, password hash). The call to AuditLogWriter.write() must happen in the same DB transaction as the business write so they are atomic. | • Identify all service methods that perform Admin System writes (at minimum: SchemeService, PartnerService, RuleService, TreasuryRateService, CredentialService, RefundService, PrefundingService, UserService, AuthService) • For each service method wrap the business write + AuditLogWriter.write() in a single transaction • Strip sensitive fields from before_value/after_value: remove password_hash, api_secret_hash, signing_secret_hash before serialising to JSONB • Add integration test for rule update: assert audit_log gains exactly one row with entity_type='rule', action='UPDATE', before_value.m_a = old value, after_value.m_a = new value • Add integration test for credential generation: assert audit_log row has entity_type='partner', action='UPDATE', after_value does NOT contain api_secret | Updated service layer where every Admin write atomically appends an audit_log entry, plus integration tests for rule-update and credential-generation audit entries | • Updating rule m_a from 1.00 to 1.25 produces audit_log row: action=UPDATE, entity_type=rule, before_value.m_a=1.00, after_value.m_a=1.25, actor_id=operator UUID • Generating API credentials produces audit_log row with entity_type=partner; after_value must not contain plaintext or hashed api_secret field • Creating a new partner produces audit_log row with action=CREATE, before_value=null • If the business write succeeds but AuditLogWriter.write() throws, the entire transaction rolls back (no silent audit gaps) • Auth events (login success, login failure) are written to audit_log with actor_type=OPERATOR and ip_address populated | 55 | 10.11-T02, 10.1-T03 | FS | PRD-07, SEC-09
10.11-T04 | admin-ui | 10.11 | 10. Admin System | Audit log viewer | 2 | Create GET /admin/audit-log API endpoint with filter and pagination | PRD-07 §13.5 defines the audit log search filters: actor (actor_id), event_type (maps to action column or a derived event_code), entity_type, entity_id, date_range (required; max 12-month window), ip_address. Results are paginated at 100 rows per page, ordered by occurred_at DESC. RBAC: VIEW_AUDIT_LOG permission required (SUPER_ADMIN and OPS_OPERATOR only; see PRD-07 §12.3). Query parameters: actor_id (optional), action (optional, multi-value), entity_type (optional), entity_id (optional BIGINT), from_date (required ISO-8601 UTC), to_date (required ISO-8601 UTC), ip_address (optional), page (default 1), page_size (default 100 max 100). Response: {total_count, page, page_size, items: [{id, actor_id, actor_type, action, entity_type, entity_id, occurred_at, ip_address, request_id, has_diff: bool}]}. before_value and after_value are NOT returned in the list response (only in the detail endpoint). | • Create GET /admin/audit-log handler; apply PermissionGuard(VIEW_AUDIT_LOG) • Parse and validate query params: from_date required, to_date required, window = to_date - from_date must be <= 366 days; reject with 400 DATE_RANGE_EXCEEDS_LIMIT otherwise • Build dynamic WHERE clause from provided filters; always include: occurred_at BETWEEN from_date AND to_date • Execute COUNT query for total_count, then SELECT with LIMIT 100 OFFSET (page-1)*100 ORDER BY occurred_at DESC • Return 200 JSON response; include has_diff=true when before_value IS NOT NULL or after_value IS NOT NULL • Return 403 FORBIDDEN if user lacks VIEW_AUDIT_LOG permission; 401 if unauthenticated | GET /admin/audit-log endpoint with filter, pagination, and RBAC guard | • Request with from_date=2026-01-01 and to_date=2027-02-01 (>12 months) returns 400 DATE_RANGE_EXCEEDS_LIMIT • Request by FINANCE_ANALYST (lacking VIEW_AUDIT_LOG) returns 403 FORBIDDEN • Filtering by entity_type=rule and entity_id=42 returns only rows where entity_type=rule AND entity_id=42 • Response items do not include before_value or after_value fields (only has_diff boolean) • page=2 with page_size=100 returns rows 101-200 ordered by occurred_at DESC | 50 | 10.11-T02, 10.1-T03 | FS | PRD-07, SEC-09
10.11-T05 | admin-ui | 10.11 | 10. Admin System | Audit log viewer | 2 | Create GET /admin/audit-log/{id} detail endpoint | Clicking [View] in the audit log list (UX-11 §4.11) opens an audit detail panel showing: entity before_value (JSONB), entity after_value (JSONB), and action metadata (ip_address, actor_id, actor_role, actor_type, occurred_at millisecond precision, request_id, entry_hash, prev_hash). RBAC: VIEW_AUDIT_LOG required. The entry_hash and prev_hash are exposed so Super Admins can manually verify chain integrity. Sensitive fields (api_secret_hash, password_hash, signing_secret_hash) must never appear in any response regardless of role. | • Create GET /admin/audit-log/{id} handler; apply PermissionGuard(VIEW_AUDIT_LOG) • Fetch single audit_log row by id BIGINT; return 404 if not found • Sanitise before_value and after_value JSONB: strip any keys matching the blocklist [api_secret_hash, password_hash, signing_secret_hash, secret_hash] before returning • Return 200 with full row: id, actor_id, actor_type, action, entity_type, entity_id, before_value (sanitised), after_value (sanitised), occurred_at, ip_address, request_id, entry_hash, prev_hash • Write unit test: fetch detail of an audit entry created for a credential-generation event; assert api_secret_hash is absent from after_value | GET /admin/audit-log/{id} detail endpoint with sanitised JSONB fields | • Fetching a rule-update entry returns before_value.m_a and after_value.m_a with the actual numeric values • Fetching a credential-generation entry returns after_value without any field matching *secret* or *hash* pattern • Fetching a non-existent id returns 404 • entry_hash and prev_hash are present in the response body • ADMIN_VIEWER requesting the endpoint receives 403 FORBIDDEN | 35 | 10.11-T04 | FS | PRD-07, SEC-09
10.11-T06 | admin-ui | 10.11 | 10. Admin System | Audit log viewer | 2 | Implement audit log CSV export endpoint (sync and async paths) | PRD-07 §13.5 and §14.1: export to CSV of all matching entries, up to 500,000 rows. Exports <= 30-day window must complete synchronously within 30 seconds (return CSV as attachment). Exports > 30 days (and up to 12 months) are queued as async jobs; the endpoint returns 202 Accepted with a job_id; when complete the operator receives an email notification with a download link. RBAC: EXPORT_AUDIT_LOG permission required (SUPER_ADMIN only; OPS_OPERATOR does NOT have EXPORT_AUDIT_LOG per PRD-07 §12.3). CSV columns: id, occurred_at (UTC ISO-8601), actor_id, actor_type, action, entity_type, entity_id, ip_address, request_id, has_diff. before_value and after_value are NOT included in the CSV export (security: bulk export of config snapshots is out of scope). | • Create POST /admin/audit-log/export accepting same filter params as the search endpoint (from_date, to_date required; same 12-month max window guard) • Apply PermissionGuard(EXPORT_AUDIT_LOG); return 403 if OPS_OPERATOR or lower • If window <= 30 days: stream query results directly to CSV response (Content-Disposition: attachment; filename=audit_log_{from}_{to}.csv) with RFC 4180 formatting • If window > 30 days: enqueue async export job (store in audit_export_job table: id UUID, user_id, filter_params JSONB, status PENDING/RUNNING/DONE/FAILED, file_url, created_at, completed_at); return 202 {job_id} • On async completion: write CSV to object storage (S3-compatible); update audit_export_job.file_url; send email to requesting user's address with pre-signed download URL (24h TTL) | POST /admin/audit-log/export endpoint with sync path (<=30 days) and async path (>30 days), audit_export_job table migration, and unit tests | • OPS_OPERATOR calling export returns 403 FORBIDDEN • 7-day window export returns Content-Type: text/csv with correct CSV headers as first row and no before_value/after_value columns • 35-day window export returns 202 with a job_id UUID and creates a row in audit_export_job with status=PENDING • Async job on completion writes file_url and sets status=DONE; file_url is a pre-signed URL expiring in 24 hours • CSV row count for a 7-day window matches the total_count returned by the GET /admin/audit-log endpoint for the same date range | 55 | 10.11-T04 | FS | PRD-07, SEC-09
10.11-T07 | admin-ui | 10.11 | 10. Admin System | Audit log viewer | 2 | Create audit_export_job DB table migration | The async CSV export path (WBS 10.11-T06) requires a persistent job tracking table. The table stores: id (UUID v4 PK), user_id (FK -> hub_user.id), filter_params (JSONB: from_date, to_date, actor_id, action, entity_type, entity_id, ip_address), status (VARCHAR(10): PENDING, RUNNING, DONE, FAILED), estimated_row_count (INT nullable), file_url (TEXT nullable; pre-signed S3 URL), error_message (TEXT nullable), created_at (TIMESTAMPTZ NOT NULL DEFAULT NOW()), started_at (TIMESTAMPTZ NULL), completed_at (TIMESTAMPTZ NULL). Index on (user_id, created_at DESC) for status polling queries. Jobs older than 30 days can be purged by a scheduled cleanup job (the file itself expires via S3 lifecycle rule). | • Write Flyway migration V10_11_002 creating audit_export_job table with all columns and constraints • Add CHECK constraint on status: IN ('PENDING','RUNNING','DONE','FAILED') • Add index on (user_id, created_at DESC) • Add a scheduled cleanup migration comment noting that rows older than 30 days are purged by the background job defined in 10.11-T14 • Verify migration applies cleanly; test insert of a PENDING row and transition to DONE | Flyway migration V10_11_002 creating audit_export_job table | • Inserting a row with status='INVALID' raises a CHECK constraint violation • user_id FK rejects an unknown hub_user UUID • status can transition from PENDING to RUNNING to DONE in successive UPDATE statements (table is NOT append-only unlike audit_log) • Index on (user_id, created_at DESC) is visible in pg_indexes • completed_at is NULL for a PENDING row and NOT NULL after a DONE update | 25 | 10.1-T01 | FS | PRD-07, SEC-09
10.11-T08 | admin-ui | 10.11 | 10. Admin System | Audit log viewer | 2 | Implement daily audit log hash-chain integrity check job | SEC-09 §6.3 and NFR-10 N-18 require a daily job that verifies the SHA-256 hash chain is unbroken. The job must: (1) read all audit_log rows in id-ascending order; (2) for each row, recompute entry_hash from the canonical fields and compare to the stored entry_hash; (3) verify row[n].prev_hash == row[n-1].entry_hash; (4) if any mismatch is found, raise a P1 alert (AUDIT_LOG_CHAIN_BREAK) and write the finding to a separate admin-only table audit_integrity_check_result. The job result is written to audit_integrity_check_result (id UUID, run_at TIMESTAMPTZ, rows_checked INT, status VARCHAR(10) OK/FAILED, first_break_id BIGINT NULL, error_detail TEXT NULL). Per SEC-09, the result is available at an admin-only monitoring endpoint. | • Write Flyway migration V10_11_003 creating audit_integrity_check_result table with columns: id UUID PK, run_at TIMESTAMPTZ NOT NULL, rows_checked INT NOT NULL, status VARCHAR(10) CHECK IN ('OK','FAILED'), first_break_id BIGINT NULL FK -> audit_log(id), error_detail TEXT NULL • Implement IntegrityCheckJob.run(): stream audit_log rows ORDER BY id ASC in batches of 10,000 using a keyset cursor; for each row recompute entry_hash and verify prev_hash linkage • On first mismatch: record first_break_id, set status=FAILED, stop scan, write result row, emit P1 alert metric AUDIT_LOG_CHAIN_BREAK=1 • On success: set status=OK, write result row, emit metric AUDIT_LOG_CHAIN_BREAK=0 • Schedule job to run daily at 03:00 UTC (outside ZeroPay batch window 01:30-05:30 KST = 16:30-22:30 UTC previous day; 03:00 UTC = 12:00 KST, well outside window) | Flyway migration V10_11_003, IntegrityCheckJob class, and unit tests covering both OK and FAILED chain scenarios | • A clean audit_log with 1,000 rows and correct hash chain produces status=OK with rows_checked=1000 • Manually corrupting entry_hash on row id=500 causes the job to report status=FAILED with first_break_id=500 • Manually deleting a row (simulated by setting prev_hash mismatch) causes FAILED with the first affected row id • Job result row is written to audit_integrity_check_result regardless of outcome • P1 alert metric AUDIT_LOG_CHAIN_BREAK is emitted as 1 on failure, 0 on success | 55 | 10.11-T02 | FS | PRD-07, SEC-09
10.11-T09 | admin-ui | 10.11 | 10. Admin System | Audit log viewer | 2 | Create GET /admin/audit-integrity-check endpoint (Super Admin only) | SEC-09 §6.3 states the integrity check job result is written to an admin-only monitoring endpoint. PRD-07 A-11 confirms this is visible to Super Admins in the Admin System. The endpoint returns the most recent N integrity check results from audit_integrity_check_result. RBAC: SUPER_ADMIN role only (not even OPS_OPERATOR). Response: {items: [{id, run_at, rows_checked, status, first_break_id, error_detail}], latest_status: 'OK'¦'FAILED'¦'NEVER_RUN'}. latest_status is 'NEVER_RUN' when the table is empty. If latest_status is FAILED, response HTTP status is 200 (not 5xx) but the payload makes the failure explicit; it is the monitoring system's job to alert. | • Create GET /admin/audit-integrity-check handler • Apply PermissionGuard requiring role_code = SUPER_ADMIN (not just VIEW_AUDIT_LOG; use a dedicated check) • Query audit_integrity_check_result ORDER BY run_at DESC LIMIT 10 • Compute latest_status from the most recent row status; return NEVER_RUN if no rows exist • Return 200 with items array and latest_status field • Write integration test: seed two result rows (OK then FAILED); assert latest_status=FAILED and items length=2 | GET /admin/audit-integrity-check endpoint restricted to SUPER_ADMIN, with integration test | • OPS_OPERATOR calling the endpoint receives 403 FORBIDDEN • FINANCE_ANALYST calling the endpoint receives 403 FORBIDDEN • Empty audit_integrity_check_result table returns 200 with latest_status=NEVER_RUN • Two rows (first OK, second FAILED) return latest_status=FAILED • Response items are ordered most-recent-first (run_at DESC) | 30 | 10.11-T08, 10.1-T03 | FS | PRD-07, SEC-09
10.11-T10 | admin-ui | 10.11 | 10. Admin System | Audit log viewer | 2 | Build Audit Log list view UI component (filter bar + results table) | UX-11 §4.11 shows the Audit Log screen: a filter bar with [Date from] [Date to] [Actor] [Entity type dropdown] [Search] button, and a results table with columns: Time (KST display), Actor, Action, Entity, Detail. Dates are stored as UTC; the UI displays occurred_at converted to KST (+09:00). The table is paginated (100 rows per page) with Prev/Next controls. The RBAC gate means the Audit Log nav item is only visible to SUPER_ADMIN and OPS_OPERATOR (VIEW_AUDIT_LOG permission). Filters: date range defaults to today; Actor is a free-text input matching actor_id substring; Entity type is a fixed dropdown (scheme, partner, rule, treasury_rate, partner_credential, user, prefunding, settlement, auth). The Date from and Date to fields reject a range wider than 12 months with an inline error. | • Create AuditLogListPage component with filter bar inputs and [Search] button • Implement GET /admin/audit-log call with constructed query params on Search click; show loading indicator during fetch • Render results table with columns: Time (occurred_at converted from UTC to KST, format: YYYY-MM-DD HH:mm:ss KST), Actor (actor_id), Action (action), Entity (entity_type/entity_id), Detail ([View] button) • Show inline error 'Date range cannot exceed 12 months' if to_date - from_date > 366 days (client-side guard before API call) • Implement pagination: show current page, total rows, Prev/Next buttons; disable Prev on page 1; disable Next when page*100 >= total_count • Hide Audit Log nav item for roles without VIEW_AUDIT_LOG (FINANCE_ANALYST, ADMIN_VIEWER) | AuditLogListPage React component with filter bar, paginated results table, and RBAC-gated nav item | • Selecting Date from=2025-01-01 and Date to=2026-06-01 (>12 months) shows inline error and does not call the API • Table column Time shows occurred_at in KST: UTC 2026-06-05T05:00:00Z displays as 2026-06-05 14:00:00 KST • ADMIN_VIEWER session does not show Audit Log in the left nav • Clicking Next on the last page does not trigger an API call (Next button is disabled) • Searching by actor_id='ops@gme' returns only rows where actor_id contains that substring | 55 | 10.11-T04 | FS | PRD-07, SEC-09
10.11-T11 | admin-ui | 10.11 | 10. Admin System | Audit log viewer | 2 | Build Audit Log entry detail panel UI component | UX-11 §4.11: clicking [View] on an audit log row opens a detail panel (slide-over or modal) showing: entity before_value (formatted JSON), entity after_value (formatted JSON), and metadata: ip_address, actor_id, actor_role, actor_type, occurred_at (millisecond precision UTC + KST), request_id, entry_hash, prev_hash. The panel calls GET /admin/audit-log/{id}. For CREATE events before_value is null (display 'N/A - new record'). For DELETE events after_value is null (display 'N/A - record deleted'). The JSON diff viewer highlights changed keys in yellow when both before and after are present (inline diff). entry_hash and prev_hash are shown in a collapsible 'Chain Integrity' section visible only to SUPER_ADMIN. | • Create AuditEntryDetailPanel component accepting entry_id prop; call GET /admin/audit-log/{id} on open • Display metadata section: occurred_at (both UTC and KST), actor_id, actor_role, ip_address, request_id • Render before_value and after_value as syntax-highlighted JSON; show 'N/A - new record' / 'N/A - record deleted' for null values • Implement inline JSON diff: when both before and after are non-null, highlight keys that differ with a yellow background • Add collapsible 'Chain Integrity' section showing entry_hash and prev_hash; visible only when user role = SUPER_ADMIN • Write component test: given a rule-update entry with before_value.m_a=1.00 and after_value.m_a=1.25, assert m_a key is highlighted as changed | AuditEntryDetailPanel React component with JSON diff display and SUPER_ADMIN-only hash chain section | • CREATE event panel shows before_value area as 'N/A - new record' and after_value as the new entity JSON • Rule update entry highlights m_a in yellow when before_value.m_a != after_value.m_a • SUPER_ADMIN sees Chain Integrity section with 64-char entry_hash and prev_hash (or 'null' for first record) • OPS_OPERATOR does not see the Chain Integrity section • Panel closes on Escape key or clicking outside; re-opening re-fetches the entry | 45 | 10.11-T05, 10.11-T10 | FS | PRD-07, SEC-09
10.11-T12 | admin-ui | 10.11 | 10. Admin System | Audit log viewer | 2 | Build Audit Log CSV export UI: Export button and async job status polling | PRD-07 §13.5: the audit log list view has an [Export CSV] button. Export is available only to SUPER_ADMIN (EXPORT_AUDIT_LOG permission). The button calls POST /admin/audit-log/export with the current filter params. If the window is <= 30 days the browser receives a CSV file download immediately. If the window is > 30 days the API returns 202 with a job_id; the UI shows an 'Export queued' toast with a status link. The status link opens a polling view that shows the job status (PENDING, RUNNING, DONE, FAILED); on DONE it renders a download link. Polling interval: every 10 seconds, stop after DONE or FAILED or after 10 minutes (timeout). | • Add [Export CSV] button to AuditLogListPage; render only when user has EXPORT_AUDIT_LOG permission (SUPER_ADMIN only) • On click: call POST /admin/audit-log/export with current filter params; if response is 200 with Content-Type: text/csv trigger browser file download with filename audit_log_{from}_{to}.csv • If response is 202: extract job_id from body; show toast 'Export queued - job {job_id}'; render [Check Status] link • Implement ExportJobStatusPanel: poll GET /admin/audit-log/export-jobs/{job_id} every 10 seconds; display status badge (PENDING=grey, RUNNING=blue, DONE=green, FAILED=red); on DONE show [Download] link to file_url • Stop polling after DONE, FAILED, or 10 minutes; show timeout message if 10-min limit reached • Write component test: mock 202 response, verify toast shown, verify poll URL called after 10s | Export button on AuditLogListPage and ExportJobStatusPanel component with polling logic | • OPS_OPERATOR does not see the [Export CSV] button • 7-day window export triggers a browser file download without a job_id toast • 35-day window export shows 'Export queued' toast and does not trigger a direct download • ExportJobStatusPanel stops polling and shows [Download] link when job status transitions to DONE • Polling stops after 10 minutes of no DONE/FAILED response and displays a timeout message | 50 | 10.11-T06, 10.11-T10 | FS | PRD-07, SEC-09
10.11-T13 | admin-ui | 10.11 | 10. Admin System | Audit log viewer | 2 | Add GET /admin/audit-log/export-jobs/{job_id} status endpoint | The async export polling UI (10.11-T12) calls GET /admin/audit-log/export-jobs/{job_id} to check progress. Response: {job_id, status, estimated_row_count, file_url (null until DONE), created_at, started_at, completed_at, error_message (null unless FAILED)}. RBAC: user must be SUPER_ADMIN AND the requesting user_id must match audit_export_job.user_id (a user cannot poll another user's job). Return 404 if job_id does not exist. Return 403 if job exists but belongs to a different user. When status=DONE, file_url is a pre-signed S3 URL (24h TTL); if the URL has expired (>24h since completed_at), re-generate a fresh pre-signed URL on each request. | • Create GET /admin/audit-log/export-jobs/{job_id} handler; apply PermissionGuard(EXPORT_AUDIT_LOG) • Fetch audit_export_job by id; return 404 if not found • Assert job.user_id == authenticated user_id; return 403 FORBIDDEN if mismatch (even for SUPER_ADMIN calling another user's job) • If status=DONE and completed_at < NOW() - 24h, regenerate pre-signed URL with 24h TTL and return fresh URL (do not update file_url in DB; serve fresh on every call) • Return 200 JSON with all fields; file_url is null when status is not DONE • Write unit test: user A cannot access job belonging to user B; returns 403 | GET /admin/audit-log/export-jobs/{job_id} endpoint with ownership check and URL regeneration logic | • Fetching a PENDING job returns status=PENDING with file_url=null • Fetching a DONE job within 24h returns the original file_url (pre-signed, non-null) • Fetching a DONE job after 24h since completion returns a freshly generated pre-signed URL (different from original) • User B requesting User A's job_id returns 403 FORBIDDEN even if both are SUPER_ADMIN • Non-existent job_id returns 404 | 40 | 10.11-T06, 10.11-T07 | FS | PRD-07, SEC-09
10.11-T14 | admin-ui | 10.11 | 10. Admin System | Audit log viewer | 2 | Implement async CSV export worker and cleanup job | When an audit_export_job row is created with status=PENDING (by 10.11-T06), a background worker must pick it up, generate the CSV, upload to object storage, and update the job to DONE. Worker steps: (1) SELECT ... FOR UPDATE SKIP LOCKED to claim a PENDING job and set status=RUNNING; (2) stream audit_log query with filter_params JSONB fields as WHERE clauses, ORDER BY occurred_at DESC, in batches of 10,000 rows; (3) write CSV rows (columns: id, occurred_at, actor_id, actor_type, action, entity_type, entity_id, ip_address, request_id, has_diff); (4) upload to S3-compatible storage at key audit-exports/{user_id}/{job_id}.csv; (5) generate pre-signed URL (24h TTL); (6) update job to DONE with file_url and completed_at. On failure: set status=FAILED with error_message. A separate cleanup job runs daily and deletes audit_export_job rows older than 30 days; it does NOT delete the underlying audit_log rows. Object storage lifecycle rule (separate config) expires the CSV files after 24h. | • Implement AuditExportWorker.process(jobId): claim job with SELECT FOR UPDATE SKIP LOCKED, transition to RUNNING • Stream audit_log rows matching filter_params in batches of 10,000 (keyset pagination by id); write to a temp file in CSV format • Upload completed CSV to S3 at key audit-exports/{user_id}/{job_id}.csv; generate 24h pre-signed URL • Update job to DONE (file_url, completed_at); send email notification via EmailService to job.user.email • On any exception: catch, update job to FAILED (error_message = exception message truncated to 500 chars), re-throw for monitoring • Implement AuditExportCleanupJob: DELETE FROM audit_export_job WHERE created_at < NOW() - INTERVAL '30 days'; schedule at 04:00 UTC daily | AuditExportWorker and AuditExportCleanupJob classes with integration tests | • Worker processes a PENDING job and transitions status: PENDING -> RUNNING -> DONE within the test • CSV file for a 35-day filter with 50,000 rows has exactly 50,000 data rows plus 1 header row • Simulated S3 upload failure causes job status to transition to FAILED with non-empty error_message • Two concurrent workers both claiming PENDING jobs do not both claim the same job (SELECT FOR UPDATE SKIP LOCKED enforced) • Cleanup job deletes job rows older than 30 days and does not touch rows newer than 30 days | 55 | 10.11-T07, 10.11-T06 | FS | PRD-07, SEC-09
10.11-T15 | admin-ui | 10.11 | 10. Admin System | Audit log viewer | 2 | Add audit log search DB indexes for filter performance | The GET /admin/audit-log endpoint (10.11-T04) runs queries filtered by occurred_at (required range), actor_id (optional), action (optional), entity_type (optional), entity_id (optional), ip_address (optional). With 7-year retention and high write volume, unindexed queries will time out. Required indexes: (occurred_at DESC) already added in T01; additionally need (entity_type, entity_id, occurred_at DESC) for entity-scoped history queries; (actor_id, occurred_at DESC) for actor filter; (action, occurred_at DESC) for event-type filter. All are partial or composite B-tree indexes. Use BRIN index on occurred_at as an alternative for very large tables if the PG version supports it and data is written in time order. | • Write Flyway migration V10_11_004 adding indexes: CREATE INDEX CONCURRENTLY idx_audit_log_entity ON audit_log(entity_type, entity_id, occurred_at DESC) • Add: CREATE INDEX CONCURRENTLY idx_audit_log_actor ON audit_log(actor_id, occurred_at DESC) • Add: CREATE INDEX CONCURRENTLY idx_audit_log_action ON audit_log(action, occurred_at DESC) • Add: CREATE INDEX CONCURRENTLY idx_audit_log_ip ON audit_log(ip_address, occurred_at DESC) WHERE ip_address IS NOT NULL • Run EXPLAIN ANALYZE on each of the four common query patterns and confirm Index Scan (not Seq Scan) is used for a table with 1M rows | Flyway migration V10_11_004 with four CONCURRENT indexes and EXPLAIN output showing index usage | • EXPLAIN ANALYZE for WHERE entity_type='rule' AND entity_id=42 ORDER BY occurred_at DESC uses idx_audit_log_entity • EXPLAIN ANALYZE for WHERE actor_id='ops-user-001' ORDER BY occurred_at DESC uses idx_audit_log_actor • EXPLAIN ANALYZE for WHERE action='UPDATE' ORDER BY occurred_at DESC uses idx_audit_log_action • Migration uses CONCURRENTLY so it does not lock the table; verify no AccessExclusiveLock during index creation • All four indexes appear in pg_indexes with the correct table name audit_log | 35 | 10.11-T01 | FS | PRD-07, SEC-09
10.11-T16 | admin-ui | 10.11 | 10. Admin System | Audit log viewer | 2 | Expose per-entity audit history from entity detail pages | PRD-07 §14.2 states: 'The audit history for a rule, partner, or scheme must be accessible within one click from the entity detail view.' Each entity detail page (Partner Detail, Scheme Detail, Rule/Mapping Page) must show a tab or section 'Audit History' that calls GET /admin/audit-log?entity_type={type}&entity_id={id}&from_date={90daysAgo}&to_date={today} and renders a compact read-only table (no export, no filter bar) with columns: Time (KST), Actor, Action, Detail [View]. RBAC: only users with VIEW_AUDIT_LOG see this tab; others see a locked icon and 'Access restricted'. The tab is not a full page navigation - it is an in-page tab on the existing entity detail component. | • Create shared EntityAuditHistoryTab component accepting entity_type and entity_id props • On tab activation (lazy-load): call GET /admin/audit-log with entity_type, entity_id, from_date=NOW()-90d, to_date=NOW(), page_size=100 • Render compact table: occurred_at (KST), actor_id, action, [View] button (opens AuditEntryDetailPanel) • If user lacks VIEW_AUDIT_LOG: render a greyed-out tab with lock icon and tooltip 'Requires OPS_OPERATOR or SUPER_ADMIN' • Add EntityAuditHistoryTab to: PartnerDetailPage, SchemeDetailPage, RuleMappingPage • Write component test: FINANCE_ANALYST sees the locked tab on PartnerDetailPage; OPS_OPERATOR sees audit rows | EntityAuditHistoryTab component integrated into PartnerDetailPage, SchemeDetailPage, and RuleMappingPage | • Clicking the Audit History tab on Partner id=5 loads GET /admin/audit-log?entity_type=partner&entity_id=5 (lazy, not on page load) • FINANCE_ANALYST visiting Partner Detail sees 'Audit History' tab with lock icon and no data rows • Clicking [View] on an audit row opens the AuditEntryDetailPanel with correct entry_id • Table shows at most 100 rows (from_date=90 days ago); if more exist a 'View full audit log' link navigates to the main Audit Log page pre-filtered • Audit history tab is present on RuleMappingPage for the current rule's (partner_id, scheme_id, direction) entity | 45 | 10.11-T10, 10.11-T11, 10.11-T04 | FS | PRD-07, SEC-09
10.11-T17 | admin-ui | 10.11 | 10. Admin System | Audit log viewer | 2 | Unit tests: AuditLogWriter hash-chain correctness with edge-case vectors | AuditLogWriter (10.11-T02) must produce correct SHA-256 hash chains. Canonical input: SHA-256(id::text + actor_id + actor_type + action + entity_type + entity_id::text + COALESCE(before_value::jsonb::text,'') + COALESCE(after_value::jsonb::text,'') + occurred_at::ISO8601ms + COALESCE(prev_hash,'')). Edge cases: first row (prev_hash=NULL -> use empty string), before_value=NULL (CREATE), after_value=NULL (DELETE), JSONB with Unicode characters, entity_id=0, concurrent inserts. | • Write test vector 1: first row insert - actor_id='sys', actor_type='SYSTEM', action='CREATE', entity_type='partner', entity_id=1, before_value=null, after_value={name:'T-Bank'}, occurred_at='2026-06-05T00:00:00.000Z'; assert entry_hash = expected SHA-256 hex (compute expected value in test setup) • Write test vector 2: second row uses prev_hash = row1.entry_hash; assert row2.entry_hash != row1.entry_hash and row2.prev_hash == row1.entry_hash • Write test vector 3: CREATE row (before_value=null) - canonical uses empty string for before_value; assert hash differs from a row where before_value='{}' • Write test vector 4: Unicode in after_value (e.g. partner name '한결원') - assert hash is a valid 64-char hex string and is deterministic across two runs • Write test vector 5: simulate concurrent insert race by calling write() from two threads simultaneously in a test transaction; assert only one prev_hash chain is produced (linear, no forks) | Unit test class AuditLogWriterHashChainTest with 5 named test vectors, each with explicit expected hash value or invariant | • Test vector 1: entry_hash is exactly the SHA-256 hex of the canonical string with empty prev_hash • Test vector 2: row2.prev_hash == row1.entry_hash exactly • Test vector 3: hash for before_value=null differs from hash for before_value='{}' • Test vector 4: Unicode input produces a valid 64-char lowercase hex entry_hash deterministically • Test vector 5: concurrent inserts produce a linear chain with no two rows sharing the same prev_hash | 45 | 10.11-T02 | FS | PRD-07, SEC-09
10.11-T18 | admin-ui | 10.11 | 10. Admin System | Audit log viewer | 2 | Unit tests: GET /admin/audit-log endpoint filter and pagination logic | The search endpoint (10.11-T04) must correctly apply all five filters, enforce the 12-month window, paginate at 100 rows, and respect RBAC. Test vectors: (A) exact date boundary, (B) multi-value action filter, (C) entity_type + entity_id combo, (D) 12-month+1-day rejection, (E) page 2 offset correctness, (F) FINANCE_ANALYST rejected. | • Seed test DB with 250 audit_log rows: 100 action=UPDATE entity_type=rule, 100 action=CREATE entity_type=partner, 50 action=DELETE entity_type=scheme; occurred_at spanning 2026-01-01 to 2026-06-30 • Test A: from_date=2026-01-01T00:00:00Z to_date=2026-01-01T23:59:59Z returns only rows where occurred_at is within that day • Test B: action=UPDATE filter returns exactly 100 rows • Test C: entity_type=rule AND entity_id=specific_id returns only those rows • Test D: from_date=2025-01-01 to_date=2026-01-02 (>366 days) returns 400 DATE_RANGE_EXCEEDS_LIMIT • Test E: page=1 returns rows 1-100; page=2 returns rows 101-200; page=3 returns rows 201-250 (total_count=250); page=4 returns empty items array • Test F: request authenticated as FINANCE_ANALYST returns 403 | Integration test class AuditLogSearchEndpointTest with 6 named test cases | • Test A: response items all have occurred_at between 2026-01-01T00:00:00Z and 2026-01-01T23:59:59Z • Test B: total_count=100 when action=UPDATE filter applied • Test D: HTTP 400 with error code DATE_RANGE_EXCEEDS_LIMIT for >366-day window • Test E: page=3 returns 50 rows; page=4 returns 0 rows with total_count=250 • Test F: FINANCE_ANALYST token returns HTTP 403 | 40 | 10.11-T04 | FS | PRD-07, SEC-09
10.11-T19 | admin-ui | 10.11 | 10. Admin System | Audit log viewer | 2 | Unit tests: immutability enforcement - no UPDATE or DELETE on audit_log | SEC-09 §6.3 and DAT-03 §10.7 require that the audit_log table is strictly append-only. The application service account must have INSERT-only permissions. This must be verified via automated tests, not just by convention. Test: (1) the application DB user can INSERT a row; (2) any attempt to UPDATE an audit_log row via the application DB user is rejected with a PostgreSQL permission error; (3) any attempt to DELETE an audit_log row via the application DB user is rejected; (4) the AuditLogWriter service does not expose any update or delete method. Additionally, attempting to delete via the Admin API (if any DELETE /admin/audit-log route were mistakenly wired) must return 403, per PRD-07 §15.10. | • Write DB-level test: connect as the application service account; INSERT one row into audit_log; assert success • Attempt UPDATE audit_log SET actor_id='tampered' WHERE id=<inserted_id>; assert PostgreSQL raises 42501 (insufficient_privilege) • Attempt DELETE FROM audit_log WHERE id=<inserted_id>; assert PostgreSQL raises 42501 • Confirm AuditLogWriter class has no update() or delete() methods (static analysis or reflection test) • Confirm no route in the Admin API router maps to DELETE /admin/audit-log or PUT /admin/audit-log; write a route-table scan test asserting no such routes exist | Test class AuditLogImmutabilityTest with 5 assertions covering DB permissions and application-layer guards | • INSERT by application DB user succeeds • UPDATE by application DB user raises SQL error code 42501 (insufficient_privilege) • DELETE by application DB user raises SQL error code 42501 • AuditLogWriter class contains no public update() or delete() method • Admin router has no DELETE or PUT route matching /admin/audit-log* | 35 | 10.11-T02, 10.11-T03 | FS | PRD-07, SEC-09
10.11-T20 | admin-ui | 10.11 | 10. Admin System | Audit log viewer | 2 | Unit tests: IntegrityCheckJob detection of chain breaks and deletions | The daily hash-chain integrity job (10.11-T08) must detect two failure modes: (1) an entry whose stored entry_hash does not match the recomputed hash (tampering of a field value), and (2) a break in the prev_hash chain (e.g. a row was deleted, causing the next row's prev_hash to not match the predecessor's entry_hash). Test vectors must cover: OK chain, single-field tamper on row 500 of 1000, deleted middle row (rows 1-499 then 501-1000 in sequence), last-row tamper, empty table. | • Test vector 1 (OK): seed 1,000 rows with correct hash chain; run job; assert result row has status=OK, rows_checked=1000 • Test vector 2 (field tamper): insert 1,000 rows correctly, then UPDATE audit_log SET actor_id='hacked' WHERE id=500 using DBA account (bypassing app-layer); run job; assert status=FAILED, first_break_id=500 • Test vector 3 (deletion): insert 1,000 rows, DELETE row 500 using DBA account; run job; assert status=FAILED, first_break_id=501 (the row whose prev_hash no longer matches row 499's entry_hash) • Test vector 4 (last-row tamper): tamper row 1000; assert status=FAILED, first_break_id=1000 • Test vector 5 (empty table): run job on empty audit_log; assert status=OK, rows_checked=0 | Test class IntegrityCheckJobTest with 5 test vectors covering OK and all FAILED scenarios | • Test vector 1: status=OK, rows_checked=1000, first_break_id=NULL • Test vector 2: status=FAILED, first_break_id=500 • Test vector 3: status=FAILED, first_break_id=501 • Test vector 4: status=FAILED, first_break_id=1000 • Test vector 5: status=OK, rows_checked=0, no result row error | 45 | 10.11-T08 | FS | PRD-07, SEC-09
10.11-T21 | admin-ui | 10.11 | 10. Admin System | Audit log viewer | 2 | E2E test: rule margin change produces correct audit entry visible in UI | End-to-end acceptance test covering the full flow: OPS_OPERATOR changes rule m_a from 1.00 to 1.25 for SendMN x ZeroPay x INBOUND via the Mapping Page -> system writes audit_log entry -> entry appears in Audit Log list view within 5 seconds (PRD-07 §15.10 acceptance criteria) -> clicking [View] on the entry shows before_value.m_a=1.00 and after_value.m_a=1.25. This test also verifies the entity audit history tab on the Rule Mapping Page shows the same entry. | • Seed DB: create hub_user with role OPS_OPERATOR; create rule SendMN x ZeroPay x INBOUND with m_a=1.00, m_b=1.50 • Log in as OPS_OPERATOR; navigate to Mapping Page for SendMN x ZeroPay x INBOUND • Change m_a from 1.00 to 1.25; click Save Rule • Assert audit_log contains a row within 5 seconds: entity_type=rule, action=UPDATE, before_value.m_a=1.00 (or '1.00'), after_value.m_a=1.25 (or '1.25'), actor_id=ops_user_id • Navigate to Audit Log screen; search with entity_type=rule and entity_id=<rule_id>; assert the entry is visible in the results table • Click [View] on the entry; assert detail panel shows before_value.m_a=1.00 and after_value.m_a=1.25 | E2E test AuditLogRuleChangeE2ETest covering the full margin-change -> audit-log-visible flow | • audit_log row is present within 5 seconds of Save Rule (poll with 500ms interval up to 5s) • audit_log row has actor_id matching the OPS_OPERATOR user UUID (not a generic SYSTEM actor) • Detail panel before_value.m_a is '1.00' or 1.00 (numeric or string, consistent with serialisation) • Detail panel after_value.m_a is '1.25' or 1.25 • The Audit History tab on the Rule Mapping Page also shows this entry without navigating away | 50 | 10.11-T10, 10.11-T11, 10.11-T16, 10.11-T03 | FS | PRD-07, SEC-09
10.11-T22 | admin-ui | 10.11 | 10. Admin System | Audit log viewer | 2 | E2E test: SUPER_ADMIN CSV export for 7-day window completes within 30 seconds | PRD-07 §14.1 and §15.10 require: CSV export of a 7-day audit log completes within 30 seconds. This E2E test seeds a realistic volume of audit_log rows (~5,000 rows over 7 days), triggers the export, and measures elapsed time. It also verifies CSV integrity: correct headers, no before_value/after_value columns, row count matches the search total_count, and entry for a known rule-change is present. | • Seed audit_log with 5,000 rows spread over a 7-day window (2026-06-01 to 2026-06-07) using a test data factory • Log in as SUPER_ADMIN; navigate to Audit Log screen; set date filter to 2026-06-01 - 2026-06-07; click Search; verify total_count=5000 • Click [Export CSV]; measure wall-clock time from click to browser download complete (or file save to disk in headless mode) • Assert elapsed time <= 30 seconds • Parse downloaded CSV: assert first row is header row with columns id,occurred_at,actor_id,actor_type,action,entity_type,entity_id,ip_address,request_id,has_diff • Assert CSV has exactly 5,001 lines (1 header + 5,000 data rows); assert no before_value or after_value column exists | E2E test AuditLogExportE2ETest with timing assertion and CSV integrity checks | • Export of 5,000 rows completes in <= 30 seconds • CSV header row is exactly: id,occurred_at,actor_id,actor_type,action,entity_type,entity_id,ip_address,request_id,has_diff • CSV has 5,001 lines (1 header + 5,000 data rows) • No before_value or after_value column appears in the CSV • OPS_OPERATOR attempting export sees button absent (not rendered); direct API call returns 403 | 45 | 10.11-T06, 10.11-T10, 10.11-T12 | FS | PRD-07, SEC-09
10.11-T23 | admin-ui | 10.11 | 10. Admin System | Audit log viewer | 2 | Documentation: Audit Log Viewer operator guide | The Admin System requires inline contextual documentation for operators. The audit log viewer is a compliance-critical feature; operators must understand what is logged, what immutability means, how to interpret hash chain fields, and how to use the export for regulatory submissions. Document format: Confluence-style markdown page stored alongside the Admin System frontend source. Audience: GME Ops and Finance staff. Sections: Overview, What is logged (categories table), How to search (filter reference), Export options (sync vs async), Hash chain integrity (Super Admin only), Data retention (7 years for config changes per SEC-09 §6.2), FAQ. | • Write docs/admin/audit-log-viewer.md covering: Overview (1 paragraph on purpose per PRD-07 §13.1), What is logged (reproduce the 8-category table from PRD-07 §13.2), Search filters reference (reproduce filter table from PRD-07 §13.5 with examples), Export (sync <= 30 days; async > 30 days; email notification; SUPER_ADMIN only), Hash Chain Integrity (entry_hash/prev_hash definition; how to interpret the Chain Integrity section; what SUPER_ADMIN should do if integrity check fails), Data retention (7 years for config change audit; 3 years for auth events; 1 year for API access logs), FAQ (3 entries: 'Can I delete an audit entry?', 'Why is before_value null?', 'The export job shows FAILED - what next?') • Ensure all field names match the DB schema (actor_id, entity_type, entity_id, before_value, after_value, occurred_at, entry_hash, prev_hash) • Add a worked example showing the JSON diff for a rule m_a change from 1.00 to 1.25 | docs/admin/audit-log-viewer.md operator guide covering all 7 sections with worked examples | • Document contains the 8-category table from PRD-07 §13.2 (config changes, FX rate changes, credential ops, refund ops, prefunding ops, settlement actions, user management, auth events) • Export section clearly distinguishes sync path (<= 30 days) from async path (> 30 days) with the 30-second SLA stated • Hash Chain section explains entry_hash and prev_hash without requiring the reader to know SHA-256 implementation details • FAQ answers 'Can I delete an audit entry?' with 'No - audit entries are permanently immutable; deletion requires DBA escalation and is itself logged' • Worked example shows before_value.m_a: 1.00 and after_value.m_a: 1.25 for a rule update event | 35 | 10.11-T11, 10.11-T12 | FS | PRD-07, SEC-09
11.1-T01 | partner-portal-ui | 11.1 | 11. Partner Portal | Portal shell, scoped auth & isolation | 3 | DB migration: portal_user table with partner scope and auth fields | The Partner Portal requires a separate user-account store from the Partner API credential store. Each portal user belongs to exactly one partner (partner_id FK, non-nullable). Auth fields required: email (unique), password_hash (bcrypt, cost >= 12), totp_secret_hash (TOTP seed stored hashed), totp_recovery_codes (hashed array), role (ENUM: PARTNER_ADMIN ¦ PARTNER_VIEWER), is_active (BOOLEAN), failed_login_count (INT default 0), locked_until (TIMESTAMPTZ nullable), last_login_at (TIMESTAMPTZ), created_by_operator_id (UUID FK to admin_users), created_at, updated_at. UUIDs (v4) for all IDs per SEC-09 T-09 (no enumerable IDs). | • Create migration file V11_1_001__portal_user.sql • Define table portal_users with columns: id UUID PK DEFAULT gen_random_uuid(), partner_id UUID NOT NULL REFERENCES partners(id), email VARCHAR(254) NOT NULL, password_hash VARCHAR(128) NOT NULL, totp_secret_hash VARCHAR(128) NOT NULL, totp_recovery_codes TEXT[] NOT NULL DEFAULT '{}', role VARCHAR(32) NOT NULL CHECK (role IN ('PARTNER_ADMIN','PARTNER_VIEWER')), is_active BOOLEAN NOT NULL DEFAULT TRUE, failed_login_count INT NOT NULL DEFAULT 0, locked_until TIMESTAMPTZ NULL, last_login_at TIMESTAMPTZ NULL, created_by_operator_id UUID NOT NULL REFERENCES admin_users(id), created_at TIMESTAMPTZ NOT NULL DEFAULT now(), updated_at TIMESTAMPTZ NOT NULL DEFAULT now() • Add unique constraint on (email) -- email is globally unique across all partners • Add index idx_portal_users_partner_id on portal_users(partner_id) • Run migration and verify schema via \d portal_users | Migration file V11_1_001__portal_user.sql applied cleanly to the dev database | • Table portal_users exists with all specified columns and correct types • UNIQUE constraint on email: inserting duplicate email raises DB error • FK partner_id references partners(id); inserting non-existent partner_id raises FK error • role column rejects values outside PARTNER_ADMIN and PARTNER_VIEWER • id is UUID v4 (no sequential integer); two rows get distinct UUIDs | 25 |  | FS | PRD-08, SEC-09
11.1-T02 | partner-portal-ui | 11.1 | 11. Partner Portal | Portal shell, scoped auth & isolation | 3 | DB migration: portal_session table for JWT refresh-token tracking | Portal sessions issue short-lived JWTs (access token) plus a refresh token stored server-side for revocation. Table portal_sessions: id UUID PK, portal_user_id UUID FK portal_users(id) NOT NULL, refresh_token_hash VARCHAR(128) NOT NULL (SHA-256 of plaintext token), issued_at TIMESTAMPTZ NOT NULL, expires_at TIMESTAMPTZ NOT NULL (issued_at + 24h absolute limit per PRD-08 §2.1), last_active_at TIMESTAMPTZ NOT NULL (updated on each valid request for idle-timeout tracking), revoked_at TIMESTAMPTZ NULL, revocation_reason VARCHAR(64) NULL. Session idle timeout = 15 min (SEC-09 §3.2); absolute limit = 24 h (PRD-08 §2.1). | • Create migration file V11_1_002__portal_session.sql • Define table portal_sessions with columns as described in context • Add index idx_portal_sessions_user on portal_sessions(portal_user_id) • Add index idx_portal_sessions_expires on portal_sessions(expires_at) for cleanup jobs • Run migration and verify schema | Migration file V11_1_002__portal_session.sql applied cleanly | • portal_user_id FK enforced: inserting orphan user_id raises error • expires_at = issued_at + interval '24 hours' enforced by application (DB column allows any value; test enforced at service layer in T08) • revoked_at is nullable: active sessions have NULL revoked_at • idx_portal_sessions_expires index exists for efficient expired-session cleanup • Dual-index (portal_user_id, revoked_at) allows fast lookup of active sessions per user | 20 | 11.1-T01 | FS | PRD-08, SEC-09
11.1-T03 | partner-portal-ui | 11.1 | 11. Partner Portal | Portal shell, scoped auth & isolation | 3 | DB migration: portal_notification table (per-user, per-partner alerts) | PRD-08 §9.1 specifies in-portal notifications stored per-partner-user: types LOW_BALANCE (High severity), STATEMENT_READY (Info), SETTLEMENT_CONFIRMED (Info), WEBHOOK_FAILURE (Warning). Table portal_notifications: id UUID PK, portal_user_id UUID FK portal_users(id) NOT NULL, partner_id UUID FK partners(id) NOT NULL (denormalised for fast partner-scoped queries), notification_type VARCHAR(64) NOT NULL, severity VARCHAR(16) NOT NULL CHECK (severity IN ('HIGH','WARNING','INFO')), title VARCHAR(255) NOT NULL, body TEXT NOT NULL, is_read BOOLEAN NOT NULL DEFAULT FALSE, read_at TIMESTAMPTZ NULL, created_at TIMESTAMPTZ NOT NULL DEFAULT now(). Notifications are per-user: dismissing clears only that user's record (other users on same partner retain their own copy). | • Create migration file V11_1_003__portal_notification.sql • Define table portal_notifications with all columns • Add index idx_portal_notifications_user_unread on (portal_user_id, is_read) WHERE is_read = FALSE for fast unread-count queries • Add index idx_portal_notifications_partner on (partner_id, created_at DESC) • Run migration and verify | Migration file V11_1_003__portal_notification.sql applied cleanly | • notification_type accepts any non-null varchar; application-layer enum validated in T14 • severity column rejects values outside HIGH / WARNING / INFO • is_read defaults to FALSE; read_at is NULL for unread rows • Partial index idx_portal_notifications_user_unread covers only unread rows • SELECT COUNT(*) WHERE portal_user_id = X AND is_read = FALSE uses the partial index (confirmed via EXPLAIN) | 20 | 11.1-T01 | FS | PRD-08, SEC-09
11.1-T04 | partner-portal-ui | 11.1 | 11. Partner Portal | Portal shell, scoped auth & isolation | 3 | PortalUserRepository: CRUD with mandatory partner_id filter | Data isolation is the most critical security property (PRD-08 §2.2, SEC-09 §3.5). Every query on portal_users must include WHERE partner_id = :authenticated_partner_id at the repository layer, not only in business logic. Class PortalUserRepository (Spring Data JPA or equivalent). Methods: findByIdAndPartnerId(UUID id, UUID partnerId): Optional<PortalUser>; findByEmailAndPartnerId(String email, UUID partnerId): Optional<PortalUser>; findAllByPartnerId(UUID partnerId, Pageable): Page<PortalUser>; save(PortalUser): PortalUser; the repository must NOT expose findById(UUID) without a partner_id parameter (to prevent accidental cross-partner lookup). | • Create entity class PortalUser mapping to portal_users table • Create PortalUserRepository extending JpaRepository • Define only the partner-scoped query methods listed in context • Annotate findById (inherited) as @Deprecated with javadoc 'Use findByIdAndPartnerId instead' to warn callers • Write a unit test PortalUserRepositoryTest that inserts two users from different partners and asserts findByIdAndPartnerId(user_b_id, partner_a_id) returns empty | PortalUserRepository.java with all partner-scoped query methods; PortalUserRepositoryTest passing | • findByIdAndPartnerId(userB.id, partnerA.id) returns Optional.empty() even when userB exists in DB • findAllByPartnerId(partnerA.id) returns only users belonging to partnerA • Inherited findById is deprecated with clear javadoc warning • Test class asserts cross-partner query returns empty (not an error/exception) • save() persists a new PortalUser with all required non-null fields set | 35 | 11.1-T01 | FS | PRD-08, SEC-09
11.1-T05 | partner-portal-ui | 11.1 | 11. Partner Portal | Portal shell, scoped auth & isolation | 3 | PortalUserService: provision first Partner Admin via Admin System call | GME Ops provisions the first Partner Admin account during partner onboarding (PRD-08 §2.3 assumption A-02). This is an internal Admin System action, not self-registration. PortalUserService.createPortalUser(CreatePortalUserCommand cmd) where cmd contains: partner_id, email, plain_password, role, created_by_operator_id. Rules: password must be >= 12 chars with complexity (uppercase + lowercase + digit + special char); hash with BCrypt cost 12; generate TOTP secret (Base32), derive totp_secret_hash; generate 8 recovery codes (alphanumeric, 10 chars each), store each hashed (SHA-256); only one PARTNER_ADMIN per partner may be created via this method for the initial account (subsequent admin invitations use T06). Return PortalUserCreatedResult with plain TOTP secret and plain recovery codes (shown once; caller displays and then discards). | • Implement CreatePortalUserCommand record with fields partner_id, email, plain_password, role, created_by_operator_id • Implement validation: password length >= 12 and matches regex (?=.*[A-Z])(?=.*[a-z])(?=.*\d)(?=.*\W); throw PasswordPolicyException if fails • BCrypt hash password with cost 12; generate TOTP secret via library (e.g. GoogleAuthenticator or dev.samstevens.totp); hash secret for storage • Generate 8 recovery codes, hash each individually, store array • Persist via PortalUserRepository.save() • Return PortalUserCreatedResult containing plain_totp_secret and plain_recovery_codes (NOT stored) | PortalUserService.createPortalUser() method; PortalUserServiceTest with password-policy and TOTP-setup cases | • Password 'password' (no complexity) throws PasswordPolicyException • Password 'Tr0ub4dor&3xP!' (12 chars, complexity OK) persists successfully • Returned plain_totp_secret is Base32 and produces valid 6-digit OTPs when seeded into an authenticator • Stored totp_secret_hash differs from plain_totp_secret (it is a hash) • 8 recovery codes returned; each stored as a distinct SHA-256 hash in totp_recovery_codes array | 45 | 11.1-T04 | FS | PRD-08, SEC-09
11.1-T06 | partner-portal-ui | 11.1 | 11. Partner Portal | Portal shell, scoped auth & isolation | 3 | PortalUserService: Partner Admin invites Viewer (partner-scoped user management) | A Partner Admin can invite additional portal users within the same partner (PRD-08 §2.3). A Partner Viewer cannot manage users (AC-14). Method PortalUserService.invitePortalUser(UUID actorUserId, UUID actorPartnerId, InvitePortalUserCommand cmd). cmd contains: email, role. Rules: actorUserId must belong to actorPartnerId and have role PARTNER_ADMIN (throw InsufficientRoleException if Viewer); invited user's partner_id = actorPartnerId (never from cmd); invited email must not already exist in portal_users (globally unique per T01 schema constraint); new user is created with is_active=TRUE and a temporary password sent via email (plain password returned to caller for email dispatch; stored hashed). Partner Admin cannot create another PARTNER_ADMIN via invite (only GME Ops can via T05); role must be PARTNER_VIEWER. | • Add invitePortalUser method to PortalUserService • Validate actor role: load actor via PortalUserRepository.findByIdAndPartnerId(actorUserId, actorPartnerId); throw InsufficientRoleException if role != PARTNER_ADMIN • Reject cmd.role != PARTNER_VIEWER with InvalidRoleException (only Viewers created via invite) • Check email uniqueness; throw EmailAlreadyExistsException if duplicate • Generate temporary password (16 chars random alphanumeric), hash it, create user record • Return InviteResult with plain temporary password for email dispatch | PortalUserService.invitePortalUser() method; unit tests for role guard, email-uniqueness guard, and successful invite | • Viewer actor throws InsufficientRoleException • Actor from different partner (wrong actorPartnerId) gets empty actor lookup -> throws EntityNotFoundException • Inviting with role=PARTNER_ADMIN throws InvalidRoleException • Duplicate email throws EmailAlreadyExistsException (or propagates DB unique violation) • Successful invite sets invited user's partner_id = actorPartnerId (not a value from cmd) | 40 | 11.1-T05 | FS | PRD-08, SEC-09
11.1-T07 | partner-portal-ui | 11.1 | 11. Partner Portal | Portal shell, scoped auth & isolation | 3 | PortalAuthService: login with username+password+TOTP validation | SEC-09 §3.2: login requires email + password + TOTP code. Account lockout: 5 consecutive failures -> 15-minute lockout (locked_until = now() + 15 min). Password checked via BCrypt; TOTP checked against TOTP secret (30-second window, allow 1 step tolerance = codes T-1, T, T+1). If TOTP fails but password succeeded, still increment failed_login_count (TOTP failure is an auth failure). Recovery code path: if totp_code matches one of the hashed recovery codes, accept login and nullify that recovery code entry from the array. On success: reset failed_login_count to 0 and locked_until to NULL; update last_login_at. Method: PortalAuthService.login(LoginRequest req) -> LoginResult(accessToken, refreshToken, expiresAt). | • Implement PortalAuthService.login(LoginRequest) accepting email, password, totp_code • Load user by email; if not found return generic AuthFailedException (do not reveal whether email exists) • Check locked_until: if non-null and in the future, throw AccountLockedException with unlock time • Verify BCrypt password; on mismatch increment failed_login_count; if count reaches 5 set locked_until = now() + 15 min; throw AuthFailedException • Verify TOTP code against stored (un-hashed) secret using TOTP library with window=1; on mismatch apply same increment/lockout logic; throw AuthFailedException • On success: reset failed_login_count=0, locked_until=NULL, last_login_at=now(); issue JWT access token (15 min TTL) and refresh token (store hash in portal_sessions); return LoginResult | PortalAuthService.login() method; unit tests covering wrong-password lockout, TOTP failure, recovery-code login, successful login | • After 5 wrong passwords, locked_until is set approximately 15 min in the future and subsequent attempts throw AccountLockedException • Wrong TOTP (correct password) also increments failed_login_count • Valid TOTP code from T-1 window (previous 30-sec slot) is accepted (window tolerance) • Using a recovery code succeeds and that code is removed from the stored array (cannot be reused) • Successful login resets failed_login_count to 0 and updates last_login_at | 55 | 11.1-T05 | FS | PRD-08, SEC-09
11.1-T08 | partner-portal-ui | 11.1 | 11. Partner Portal | Portal shell, scoped auth & isolation | 3 | PortalAuthService: JWT issuance, idle-timeout enforcement, and session revocation | PRD-08 §2.1: session idle timeout = 15 min (SEC-09 §3.2 for Partner Portal); absolute session limit = 24 h. JWT access token: short-lived 15 min; claims must include sub (portal_user_id), partner_id, role, exp, iat, jti (unique per token). Refresh token: opaque UUID stored as SHA-256 hash in portal_sessions.refresh_token_hash; used to issue a new access token and update last_active_at. Idle check: if now() - last_active_at > 15 min OR now() > expires_at, session is expired (return 401 SESSION_EXPIRED). Logout: set revoked_at = now(), revocation_reason = 'LOGOUT'. Partner_id in JWT claims is authoritative -- never read partner_id from request body or URL path parameter. | • Implement issueTokenPair(PortalUser user) -> TokenPair(accessToken JWT, refreshToken UUID) • JWT claims: sub=user.id.toString(), partner_id=user.partnerId.toString(), role=user.role, exp=now+15min, iat=now, jti=random UUID • Store SHA-256(refreshToken) in portal_sessions with expires_at=now+24h, last_active_at=now • Implement refreshSession(String refreshToken): lookup by SHA-256 hash, check revoked_at IS NULL, check now < expires_at, check now - last_active_at <= 15 min; if all OK update last_active_at and issue new access token • Implement logout(String refreshToken): set revoked_at=now, revocation_reason=LOGOUT • Write unit tests for idle-timeout rejection, absolute-expiry rejection, revoked-session rejection, and successful refresh | PortalAuthService token-management methods; PortalAuthServiceTest covering timeout and revocation scenarios | • JWT access token contains partner_id claim matching the user's partner_id • refreshSession() called with last_active_at = now() - 16 min returns 401 SESSION_EXPIRED (idle timeout breach) • refreshSession() called at now() = issued_at + 25h returns 401 SESSION_EXPIRED (absolute limit breach) • logout() sets revoked_at; subsequent refreshSession() call returns 401 SESSION_REVOKED • Decoded JWT jti is unique across two consecutive issueTokenPair() calls | 50 | 11.1-T07, 11.1-T02 | FS | PRD-08, SEC-09
11.1-T09 | partner-portal-ui | 11.1 | 11. Partner Portal | Portal shell, scoped auth & isolation | 3 | PortalSecurityFilter: extract partner_id from JWT claims and bind to request context | SEC-09 §3.5 and PRD-08 §2.2: partner_id must come from the authenticated JWT claims -- never from URL path params or request body. Implement a servlet filter (or Spring Security filter) PortalJwtAuthFilter that: (1) extracts Bearer token from Authorization header, (2) validates signature and exp, (3) extracts partner_id and portal_user_id and role claims, (4) populates a PortalSecurityContext (thread-local or Spring SecurityContextHolder) with PortalPrincipal{partnerId, userId, role}. If token is absent or invalid, return HTTP 401. If token is valid but role check fails for the endpoint, return HTTP 403. The filter must run before any controller handler. partner_id from path variables (e.g. /{partner_slug}/...) must be validated against JWT partner_id in a separate guard (see T10). | • Implement PortalPrincipal record: UUID partnerId, UUID userId, PortalRole role • Implement PortalJwtAuthFilter extending OncePerRequestFilter • Extract Bearer token; validate via JWT library using server secret; on failure return 401 with body {error: INVALID_TOKEN} • Populate SecurityContextHolder with UsernamePasswordAuthenticationToken carrying PortalPrincipal • Skip filter for public endpoints: POST /portal/auth/login, POST /portal/auth/refresh • Write unit tests using MockMvc: request with valid token populates principal; expired token returns 401; missing token returns 401 | PortalJwtAuthFilter.java; PortalJwtAuthFilterTest covering valid, expired, and missing token cases | • Request with valid JWT sets SecurityContextHolder principal with correct partner_id UUID • Request with expired JWT (exp in past) returns HTTP 401 with error=INVALID_TOKEN • Request with tampered JWT signature returns HTTP 401 • POST /portal/auth/login proceeds without Authorization header (public endpoint) • PortalPrincipal.partnerId equals the partner_id claim in the JWT -- not a value from the request URL | 45 | 11.1-T08 | FS | PRD-08, SEC-09
11.1-T10 | partner-portal-ui | 11.1 | 11. Partner Portal | Portal shell, scoped auth & isolation | 3 | PortalOwnershipGuard: validate URL path partner_slug against JWT partner_id | Portal URLs are partner-scoped: /{partner_slug}/transactions/{hub_txn_ref} etc. (PRD-08 §5). The partner_slug in the URL is cosmetic but must still be validated against the authenticated JWT partner_id to prevent IDOR where a user replaces the slug with another partner's slug. PortalOwnershipGuard is a Spring HandlerInterceptor (or AOP aspect) that: (1) resolves partner_slug from the path variable to a partner UUID by querying the partner table, (2) asserts partner UUID == PortalPrincipal.partnerId from JWT, (3) if mismatch returns HTTP 403 FORBIDDEN (not 404 -- the slug mismatch is an auth violation, not a not-found). This guard applies to all portal endpoints that include {partner_slug} in the path. Note: transaction-detail cross-partner access returns 404, not 403 (PRD-08 §5 -- do not reveal existence); the guard returns 403 only for slug mismatch at routing level. | • Implement PortalOwnershipGuard implementing HandlerInterceptor • In preHandle: extract partner_slug path variable; resolve to partner UUID via PartnerRepository.findBySlug(slug); if not found return 404 • Compare resolved UUID with PortalPrincipal.partnerId; if mismatch return 403 with body {error: PARTNER_MISMATCH} • Register guard for all paths matching /portal/{partner_slug}/** • Write unit test: user from partnerA accessing /portal/partnerB-slug/ returns 403; user accessing own slug proceeds | PortalOwnershipGuard.java; PortalOwnershipGuardTest covering own-slug pass and cross-partner-slug rejection | • GET /portal/partner-b-slug/transactions with JWT for partner-A returns HTTP 403 PARTNER_MISMATCH • GET /portal/partner-a-slug/transactions with JWT for partner-A proceeds to controller • GET /portal/unknown-slug/transactions returns HTTP 404 (slug not found) • Guard does not query partner_id from query params or request body • Mismatch result is HTTP 403, not HTTP 401 (token is valid but ownership violated) | 35 | 11.1-T09 | FS | PRD-08, SEC-09
11.1-T11 | partner-portal-ui | 11.1 | 11. Partner Portal | Portal shell, scoped auth & isolation | 3 | PortalRoleGuard: annotation-driven RBAC enforcement for PARTNER_ADMIN-only endpoints | PRD-08 §2.3 and SEC-09 §3.4.2: two roles exist in the portal -- PARTNER_ADMIN (full read + user management) and PARTNER_VIEWER (read only, no user management). User-management endpoints (invite user, deactivate user, list users) are ADMIN-only. Implement a custom annotation @RequiresPortalRole(PortalRole.PARTNER_ADMIN) and a Spring AOP aspect or HandlerMethodArgumentResolver that reads PortalPrincipal.role from the security context and throws InsufficientRoleException (-> HTTP 403) if the role requirement is not met. The annotation should be applicable to controller methods. Read-only endpoints (GET transactions, GET balance etc.) require any authenticated portal user (no role annotation needed -- filter T09 is sufficient). | • Define @RequiresPortalRole annotation with PortalRole[] value() • Implement PortalRoleAspect: @Around advice on methods annotated with @RequiresPortalRole; read PortalPrincipal from SecurityContext; if role not in value() throw InsufficientRoleException • Map InsufficientRoleException to HTTP 403 in global exception handler with body {error: INSUFFICIENT_ROLE, required: PARTNER_ADMIN} • Annotate PortalUserManagementController methods (inviteUser, deactivateUser, listUsers) with @RequiresPortalRole(PARTNER_ADMIN) • Write unit test: Viewer calling inviteUser() returns 403; Admin calling inviteUser() proceeds | @RequiresPortalRole annotation + PortalRoleAspect; PortalRoleAspectTest with Viewer and Admin scenarios | • PARTNER_VIEWER calling POST /portal/{slug}/users/invite returns HTTP 403 INSUFFICIENT_ROLE • PARTNER_ADMIN calling POST /portal/{slug}/users/invite is not blocked by the aspect • Aspect reads role from SecurityContextHolder (PortalPrincipal), not from request body • GET /portal/{slug}/transactions (no @RequiresPortalRole annotation) allows both ADMIN and VIEWER • InsufficientRoleException mapped to HTTP 403 -- not 401 or 500 | 35 | 11.1-T09 | FS | PRD-08, SEC-09
11.1-T12 | partner-portal-ui | 11.1 | 11. Partner Portal | Portal shell, scoped auth & isolation | 3 | POST /portal/auth/login endpoint: wire LoginRequest to PortalAuthService | Public REST endpoint for portal login. POST /portal/auth/login accepts JSON {email, password, totp_code}. Calls PortalAuthService.login() (T07). Returns 200 with {access_token, refresh_token, expires_in_seconds: 900, partner_id, role} on success. Error mappings: AuthFailedException -> 401 {error: AUTH_FAILED} (do not distinguish wrong password vs wrong TOTP to prevent oracle attacks); AccountLockedException -> 423 {error: ACCOUNT_LOCKED, unlock_at: ISO-8601}; missing/invalid body fields -> 400. Rate-limiting: login endpoint subject to 20 failed attempts per IP per 10 min (SEC-09 §5.4) -- configure at API Gateway or via a filter; this ticket implements the endpoint and service wiring only. | • Create PortalAuthController with POST /portal/auth/login mapped method • Define LoginRequest DTO: email (not blank), password (not blank), totp_code (not blank, 6 digits or recovery format) • Call PortalAuthService.login(); map exceptions to HTTP responses as specified • Return LoginResponse DTO: access_token, refresh_token, expires_in_seconds=900, partner_id (UUID string), role • Write integration test (MockMvc): valid credentials return 200 with access_token; wrong password returns 401 with error=AUTH_FAILED; locked account returns 423 with unlock_at | PortalAuthController.login() endpoint; PortalAuthControllerTest with success, wrong-credential, and lockout scenarios | • POST /portal/auth/login with valid email+password+TOTP returns 200 and non-null access_token and refresh_token • Wrong password returns 401 {error: AUTH_FAILED} -- body does not reveal whether email was found • Wrong TOTP (correct password) also returns 401 {error: AUTH_FAILED} -- same response shape • Locked account returns 423 with unlock_at field set to the locked_until value • Missing totp_code field returns 400 validation error | 40 | 11.1-T07, 11.1-T08 | FS | PRD-08, SEC-09
11.1-T13 | partner-portal-ui | 11.1 | 11. Partner Portal | Portal shell, scoped auth & isolation | 3 | POST /portal/auth/refresh and POST /portal/auth/logout endpoints | POST /portal/auth/refresh: accepts {refresh_token} (opaque UUID string), calls PortalAuthService.refreshSession(). Returns 200 {access_token, expires_in_seconds:900} on success; 401 SESSION_EXPIRED if idle or absolute timeout exceeded; 401 SESSION_REVOKED if logout was called. POST /portal/auth/logout: requires valid Bearer access token (goes through PortalJwtAuthFilter); accepts {refresh_token} in body; calls PortalAuthService.logout(). Returns 204 No Content. Both endpoints are unauthenticated (for refresh) or authenticated (for logout) as noted. | • Add refreshSession endpoint: POST /portal/auth/refresh, no auth filter required; accept RefreshRequest {refresh_token}; call PortalAuthService.refreshSession(); return RefreshResponse {access_token, expires_in_seconds} • Map SessionExpiredException -> 401 {error: SESSION_EXPIRED}; SessionRevokedException -> 401 {error: SESSION_REVOKED} • Add logout endpoint: POST /portal/auth/logout, requires Bearer token (PortalJwtAuthFilter); accept LogoutRequest {refresh_token}; call PortalAuthService.logout(); return 204 • Write integration tests: successful refresh returns new access_token; calling refresh after logout returns 401 SESSION_REVOKED; refresh after 16-min idle returns 401 SESSION_EXPIRED | PortalAuthController.refresh() and logout() endpoints; integration tests covering revocation and expiry paths | • POST /portal/auth/refresh with valid non-expired token returns 200 with new access_token • POST /portal/auth/logout returns 204; subsequent POST /portal/auth/refresh with same refresh_token returns 401 SESSION_REVOKED • POST /portal/auth/refresh with refresh_token whose last_active_at is 16 min ago returns 401 SESSION_EXPIRED • POST /portal/auth/logout without valid Bearer token returns 401 (filter rejects) • Refresh response does not return a new refresh_token -- only a new short-lived access_token | 35 | 11.1-T08, 11.1-T12 | FS | PRD-08, SEC-09
11.1-T14 | partner-portal-ui | 11.1 | 11. Partner Portal | Portal shell, scoped auth & isolation | 3 | GET /portal/{partner_slug}/dashboard/summary: partner-scoped dashboard aggregate | PRD-08 §3 Dashboard. Returns: (a) balance panel (OVERSEAS partners only: current_balance USD, low_balance_threshold, last_topup_date, reserved_pending USD), (b) today-activity (txn count, payout_volume in KRW, collection_volume in partner settle-A ccy, success_rate), (c) recent-10-transactions list (txn_timestamp KST, hub_txn_ref truncated to 12 chars, merchant_name, target_payout, payout_ccy, collection_amount, collection_ccy, txn_status). partner_id sourced exclusively from JWT claims (PortalPrincipal). LOCAL partners (type=LOCAL) get null balance panel. Today = current calendar day in KST (UTC+09:00 constant offset, Korea has no DST). Success rate = approved / (approved + declined) * 100 for today; division by zero -> null. | • Implement DashboardService.getDashboardSummary(UUID partnerId): load partner type; conditionally build balance panel; query today-activity aggregates; fetch 10 most recent transactions • For today-activity: WHERE partner_id = :partnerId AND txn_timestamp >= today_kst_start AND txn_timestamp < today_kst_start + 1 day (KST = UTC+9, use AT TIME ZONE or offset arithmetic) • For balance panel: only if partner.type = OVERSEAS; fetch prefunding_balance record for partner; low_balance_threshold from partner config • Truncate hub_txn_ref to first 12 chars in the response • Map to DashboardSummaryResponse DTO; wire to GET /portal/{partner_slug}/dashboard/summary controller method | DashboardService.getDashboardSummary() + controller endpoint; unit test with OVERSEAS and LOCAL partner scenarios | • LOCAL partner response has balancePanel = null • OVERSEAS partner with balance USD 8000 and threshold USD 10000 has balancePanel.lowBalanceIndicator = true • Today-activity count uses KST date boundary: transaction at 2026-06-05T00:30+09:00 (= 2026-06-04T15:30Z) is counted in June 5 KST day • hub_txn_ref in recent-transactions list is exactly 12 characters (truncated) • success_rate = null (not NaN or error) when approved + declined = 0 today | 55 | 11.1-T09, 11.1-T10 | FS | PRD-08, SEC-09
11.1-T15 | partner-portal-ui | 11.1 | 11. Partner Portal | Portal shell, scoped auth & isolation | 3 | GET /portal/{partner_slug}/transactions: partner-scoped paginated transaction list | PRD-08 §4. Filters: date range (default last 7 days; max 90-day range per query), scheme (dropdown of partner's mapped schemes), direction (Domestic/Inbound/Outbound/Hub), status (multi-select: Approved/Declined/Pending/Cancelled/Refunded), amount_min/amount_max (in partner settle-A ccy), payment_mode (MPM/CPM). Pagination: default 50 rows; sizes 25/50/100; returns page, pageSize, totalCount, totalPages. All queries enforce WHERE partner_id = :authenticated_partner_id (from JWT, never from request params). Columns: txn_timestamp (KST), hub_txn_ref, scheme_name, direction, target_payout, payout_ccy, collection_amount, collection_ccy, txn_status, payment_mode. | • Implement TransactionQueryService.listTransactions(UUID partnerId, TransactionFilter filter, Pageable pageable) • Apply partner_id filter first; then apply optional filters in any combination; ensure compound index on (partner_id, txn_timestamp DESC) is used • Validate date range: max span = 90 days; throw DateRangeExceededException -> 400 if exceeded • Wire to GET /portal/{partner_slug}/transactions with query params: from_date, to_date, scheme, direction, status (repeatable), amount_min, amount_max, mode, page (0-indexed), page_size (25/50/100 default 50) • Return PagedTransactionResponse: items list + pagination metadata | TransactionQueryService.listTransactions() + controller GET endpoint; unit tests for filter combinations and range validation | • Query with no optional filters returns up to 50 transactions all belonging to authenticated partner (none from other partners) • Date range span of 91 days returns HTTP 400 with error=DATE_RANGE_EXCEEDED • status=Approved&status=Declined (multi-value) returns transactions in either status • amount_min=100 amount_max=50 (inverted range) returns HTTP 400 with validation error • Total count in response matches actual DB count matching the filter for that partner | 55 | 11.1-T09, 11.1-T10 | FS | PRD-08, SEC-09
11.1-T16 | partner-portal-ui | 11.1 | 11. Partner Portal | Portal shell, scoped auth & isolation | 3 | GET /portal/{partner_slug}/transactions/{hub_txn_ref}: partner-scoped transaction detail | PRD-08 §5. Returns full transaction detail including: target_payout, payout_ccy, collection_amount, collection_ccy, service_charge, send_amount, offer_rate, cross_rate. For cross-border (direction != Domestic): also collection_usd, payout_usd_cost, rate_locked_at. For Domestic (same-currency): USD pool fields NOT included in response. Field visibility rule from PRD-08 §5.1: m_a, m_b, cost_rate_coll, cost_rate_pay, collection_margin_usd, payout_margin_usd are NEVER returned (internal only). Status+event trail: simplified 4-step view {Initiated, Scheme Processing, Approved/Declined, Notified} with timestamps derived from the 8-step internal trail. Scheme reference: scheme_txn_ref, scheme_name, merchant_id, merchant_name, payment_mode. CRITICAL: if transaction belongs to a different partner, return HTTP 404 (not 403) -- do not reveal existence (PRD-08 §5). | • Implement TransactionDetailService.getDetail(UUID partnerId, String hubTxnRef): query WHERE hub_txn_ref = :ref AND partner_id = :partnerId; return Optional • Map Optional.empty() to HTTP 404 (applies whether txn does not exist OR belongs to another partner) • Build response DTO excluding m_a, m_b, cost_rate_coll, cost_rate_pay, collection_margin_usd, payout_margin_usd • Conditionally include USD pool fields: if direction in (Inbound, Outbound, Hub) include collection_usd, payout_usd_cost, rate_locked_at; if Domestic omit • Map 8-step internal trail to 4-step partner view: step1=Initiated(step2 timestamp), step2=Scheme Processing(step4), step3=Approved/Declined(step5), step4=Notified(step7 or step8 whichever available) • Wire to GET /portal/{partner_slug}/transactions/{hub_txn_ref} | TransactionDetailService + controller endpoint; unit tests for cross-partner 404, domestic-no-USD-fields, cross-border-has-USD-fields | • Requesting a hub_txn_ref that belongs to another partner returns HTTP 404 (not 403) • Requesting a non-existent hub_txn_ref returns HTTP 404 (same response as cross-partner) • Response for cross-border transaction contains collection_usd and payout_usd_cost fields • Response for Domestic transaction does NOT contain collection_usd or payout_usd_cost fields • Response for any transaction never contains m_a, m_b, cost_rate_coll, cost_rate_pay, collection_margin_usd, or payout_margin_usd fields | 50 | 11.1-T15 | FS | PRD-08, SEC-09
11.1-T17 | partner-portal-ui | 11.1 | 11. Partner Portal | Portal shell, scoped auth & isolation | 3 | GET /portal/{partner_slug}/transactions/export: CSV export with 10k-row cap and field restrictions | PRD-08 §4.4. Export all rows matching current filter (same params as list endpoint T15) up to 10,000 rows. Columns: txn_timestamp, hub_txn_ref (FULL, not truncated), scheme_txn_ref, scheme_name, direction, target_payout, payout_ccy, collection_amount, collection_ccy, service_charge, offer_rate, merchant_id, merchant_name, payment_mode, txn_status. NEVER include m_a, m_b, cost_rate_coll, cost_rate_pay, collection_margin_usd, payout_margin_usd (PRD-08 §4.4 data restriction). Filename format: gmepay_txns_{partner_id}_{from_date}_{to_date}.csv (e.g. gmepay_txns_abc123_2026-05-01_2026-05-31.csv). Max 10,000 rows per request; return HTTP 400 with error=EXPORT_LIMIT_EXCEEDED and instruction to use sub-ranges if query would return > 10,000 rows. | • Implement TransactionExportService.exportCsv(UUID partnerId, TransactionFilter filter): count matching rows first; if > 10000 throw ExportLimitExceededException • Fetch up to 10000 rows applying same partner_id filter as T15 • Build CSV using streaming writer (do not buffer all rows in heap); columns as specified; timestamp in ISO-8601 UTC • Set Content-Type: text/csv; Content-Disposition: attachment; filename=gmepay_txns_{partner_id}_{from}_{to}.csv • Assert excluded fields are absent by inspecting CSV header row in test; wire to GET /portal/{partner_slug}/transactions/export with same query params as list endpoint | TransactionExportService + controller endpoint; CsvExportTest asserting column list and exclusion of internal fields | • CSV header row contains hub_txn_ref (full) and does not contain columns m_a, m_b, cost_rate_coll, cost_rate_pay, collection_margin_usd, payout_margin_usd • Filter returning 10001 matching rows returns HTTP 400 error=EXPORT_LIMIT_EXCEEDED before any CSV bytes are written • Filter returning 5000 rows returns 5000 data rows plus 1 header row (total 5001 lines) • Filename header matches pattern gmepay_txns_{partner_id}_{from_date}_{to_date}.csv • hub_txn_ref column contains full UUID (not truncated 12-char version used in list view) | 50 | 11.1-T15 | FS | PRD-08, SEC-09
11.1-T18 | partner-portal-ui | 11.1 | 11. Partner Portal | Portal shell, scoped auth & isolation | 3 | GET /portal/{partner_slug}/balance: real-time prefunding balance (OVERSEAS only) | PRD-08 §6.1. OVERSEAS partners only: current_balance (USD, 2 decimal places), low_balance_threshold (USD), status_indicator (GREEN if balance > threshold, RED if balance <= threshold), last_updated timestamp. LOCAL partners: return HTTP 404 (balance section does not exist for them -- per PRD-08 §6 'this section is displayed only for OVERSEAS partners'). Balance is the real-time available balance; atomic deductions are immediately reflected. Query: SELECT current_balance FROM partner_prefunding WHERE partner_id = :partnerId. Threshold from partner config table field low_balance_threshold_usd (default 10000.00). | • Implement BalanceService.getBalance(UUID partnerId): load partner; if partner.type != OVERSEAS return BalanceResult.notApplicable() • Query partner_prefunding for current balance; load low_balance_threshold_usd from partner_config • Compute status: GREEN if current_balance > threshold, RED if current_balance <= threshold • Map notApplicable to HTTP 404 in controller • Return BalanceResponse {available_balance_usd, low_balance_threshold_usd, status_indicator, last_updated} for OVERSEAS partners • Wire to GET /portal/{partner_slug}/balance; protect with PortalJwtAuthFilter | BalanceService.getBalance() + controller endpoint; unit tests for OVERSEAS success, LOCAL 404, and threshold boundary | • LOCAL partner GET /portal/{slug}/balance returns HTTP 404 • OVERSEAS partner with balance=10000.00 and threshold=10000.00 returns status_indicator=RED (at-threshold is RED, not GREEN) • OVERSEAS partner with balance=10000.01 and threshold=10000.00 returns status_indicator=GREEN • Balance value returned as USD with 2 decimal places (e.g. 10000.00 not 10000 or 10000.0) • Endpoint rejects request without valid JWT (401 from PortalJwtAuthFilter) | 35 | 11.1-T09, 11.1-T10 | FS | PRD-08, SEC-09
11.1-T19 | partner-portal-ui | 11.1 | 11. Partner Portal | Portal shell, scoped auth & isolation | 3 | GET /portal/{partner_slug}/balance/ledger: prefunding movement history with running balance | PRD-08 §6.2. Paginated ledger of all prefunding balance movements for OVERSEAS partners. Columns: movement_timestamp (KST), type (DEBIT/CREDIT/ADJUSTMENT), reference (hub_txn_ref for debits, top-up ref for credits), amount_usd (negative for debits, positive for credits), running_balance_usd. Default view: last 30 days; filterable by date range max 1 year. Running balance is stored in the prefunding_ledger table (not computed on-the-fly) to ensure consistency. LOCAL partners return HTTP 404. Pagination: default 50 rows, sizes 25/50/100. The sum of all amount_usd entries must equal the current_balance in partner_prefunding (invariant; validated in T21 unit test). | • Implement LedgerService.getLedger(UUID partnerId, DateRange range, Pageable pageable): validate partner.type=OVERSEAS; validate date range <= 1 year • Query prefunding_ledger WHERE partner_id = :partnerId AND movement_timestamp BETWEEN :from AND :to ORDER BY movement_timestamp DESC • Map to LedgerEntryResponse list with fields: movement_timestamp (KST), type, reference, amount_usd, running_balance_usd • Wire to GET /portal/{partner_slug}/balance/ledger with query params from_date, to_date, page, page_size • LOCAL partner or non-OVERSEAS partner -> HTTP 404 | LedgerService.getLedger() + controller endpoint; unit tests for OVERSEAS paginated result and LOCAL 404 | • LOCAL partner returns HTTP 404 • Date range > 1 year returns HTTP 400 with error=DATE_RANGE_EXCEEDED • Debit entries have negative amount_usd (e.g. -150.00); credit entries have positive amount_usd • Results ordered by movement_timestamp descending (most recent first) • All results in response have partner_id = authenticated partner_id (cross-partner isolation) | 40 | 11.1-T09, 11.1-T10, 11.1-T18 | FS | PRD-08, SEC-09
11.1-T20 | partner-portal-ui | 11.1 | 11. Partner Portal | Portal shell, scoped auth & isolation | 3 | GET /portal/{partner_slug}/statements: settlement statement list and download links | PRD-08 §7.1-7.3. List of settlement periods for authenticated partner. Columns: period (e.g. 'May 2026'), settlement_date, total_transactions, total_payout_volume (payout ccy), total_collection (Settle-A ccy), total_service_fees (Settle-A ccy), status (Draft/Confirmed/Disputed), download_pdf_url, download_csv_url. Data restriction: m_a, m_b, GME margin not included. Statements retained 7 years (SEC-09 §6.2). GET /portal/{partner_slug}/statements returns list. GET /portal/{partner_slug}/statements/{statement_id}/download?format=pdf¦csv returns the file (or presigned URL to file in object storage). Statement is partner-scoped: statement_id must belong to authenticated partner (return 404 otherwise). | • Implement StatementService.listStatements(UUID partnerId): query partner_statements WHERE partner_id = :partnerId ORDER BY period DESC • Build StatementListResponse: items with period, settlement_date, totals, status, statement_id • Implement StatementService.getDownloadUrl(UUID partnerId, UUID statementId, String format): verify statement belongs to partner (404 if not); return presigned URL or stream PDF/CSV • Wire GET /portal/{partner_slug}/statements and GET /portal/{partner_slug}/statements/{statement_id}/download • Return 404 if statement_id belongs to another partner (do not reveal existence) | StatementService + controller endpoints for list and download; unit tests for partner ownership 404 and format selection | • Listing statements returns only statements belonging to authenticated partner • Requesting download for another partner's statement_id returns HTTP 404 • download?format=pdf returns a PDF (Content-Type: application/pdf or presigned URL) • download?format=csv returns a CSV (Content-Type: text/csv or presigned URL) • CSV download columns do not include m_a, m_b, collection_margin_usd, payout_margin_usd, or GME revenue fields | 45 | 11.1-T09, 11.1-T10 | FS | PRD-08, SEC-09
11.1-T21 | partner-portal-ui | 11.1 | 11. Partner Portal | Portal shell, scoped auth & isolation | 3 | GET /portal/{partner_slug}/credentials: read-only API credentials view | PRD-08 §8.1. Read-only view of partner API configuration. Shown fields: api_key_id (public key identifier), api_key_status (Active/Revoked), webhook_url, webhook_last_delivery_status, webhook_last_delivery_at, sandbox_api_key_id, sandbox_base_url, rate_quote_ttl_seconds. NEVER show: api_secret_hash or any value that could reconstruct the API secret (PRD-08 §8.1 -- API Secret = No). Source tables: partner_credential, partner_webhook_config, partner_config. All data is scoped to authenticated partner_id from JWT. | • Implement CredentialsViewService.getCredentialsView(UUID partnerId): load partner_credential (active record), partner_webhook_config, partner_config for the authenticated partner • Map to CredentialsViewResponse: include only fields listed in context; exclude api_secret_hash and any secret-bearing column • Wire to GET /portal/{partner_slug}/credentials • Write unit test asserting api_secret_hash is NOT present in the serialised JSON response (use ObjectMapper to inspect all keys) | CredentialsViewService + GET /portal/{partner_slug}/credentials endpoint; unit test asserting secret exclusion | • Response JSON does not contain key api_secret, api_secret_hash, or any variant of 'secret' (case-insensitive scan of JSON keys) • api_key_id is the public identifier UUID, not the hashed value • webhook_url field is present in response • Response scoped to authenticated partner: partner B cannot read partner A credentials (returns partner B data when JWT = partner B) • rate_quote_ttl_seconds is present and matches partner_config.rate_quote_ttl_seconds value | 30 | 11.1-T09, 11.1-T10 | FS | PRD-08, SEC-09
11.1-T22 | partner-portal-ui | 11.1 | 11. Partner Portal | Portal shell, scoped auth & isolation | 3 | PortalUserManagementController: list and deactivate portal users (PARTNER_ADMIN only) | PRD-08 §2.3: Partner Admin can invite/deactivate other portal users within the same partner. Deactivating a user sets is_active=FALSE and immediately revokes all their active portal sessions (set revoked_at=now() on all their portal_sessions where revoked_at IS NULL). Listing users is admin-only (Partner Viewer sees no user management screen -- AC-14). Endpoints: GET /portal/{partner_slug}/users (list all users for partner); DELETE /portal/{partner_slug}/users/{user_id} (deactivate; 204 on success). Both require @RequiresPortalRole(PARTNER_ADMIN). A user cannot deactivate themselves (self-deactivation not allowed; return 400 SELF_DEACTIVATION_FORBIDDEN). | • Add listUsers(UUID partnerId): query portal_users WHERE partner_id = :partnerId; return list of {id, email, role, is_active, last_login_at} • Add deactivateUser(UUID actorUserId, UUID partnerId, UUID targetUserId): verify actor and target belong to same partnerId; reject if actorUserId == targetUserId with SelfDeactivationException; set target is_active=FALSE; revoke all target sessions • Wire GET /portal/{partner_slug}/users with @RequiresPortalRole(PARTNER_ADMIN) • Wire DELETE /portal/{partner_slug}/users/{user_id} with @RequiresPortalRole(PARTNER_ADMIN) • Write tests: Viewer calling list/deactivate gets 403; Admin deactivating self gets 400; cross-partner deactivation gets 404 | PortalUserManagementController with list and deactivate; tests for role guard, self-deactivation, and cross-partner isolation | • PARTNER_VIEWER calling GET /portal/{slug}/users returns HTTP 403 • PARTNER_ADMIN deactivating own user_id returns HTTP 400 SELF_DEACTIVATION_FORBIDDEN • PARTNER_ADMIN deactivating a user_id from a different partner returns HTTP 404 (not 403) • Successful deactivation sets is_active=FALSE and revokes all active sessions for target user • After deactivation, target user's refresh token returns 401 SESSION_REVOKED on next refresh attempt | 45 | 11.1-T11, 11.1-T06, 11.1-T13 | FS | PRD-08, SEC-09
11.1-T23 | partner-portal-ui | 11.1 | 11. Partner Portal | Portal shell, scoped auth & isolation | 3 | GET /portal/{partner_slug}/notifications: list unread + mark-as-read endpoint | PRD-08 §9.1. Notification bell: unread count shown on portal header. Types: LOW_BALANCE (High), STATEMENT_READY (Info), SETTLEMENT_CONFIRMED (Info), WEBHOOK_FAILURE (Warning). Notifications are per-user: marking read affects only the calling user's record. Endpoints: GET /portal/{partner_slug}/notifications returns {unread_count, notifications: [{id, type, severity, title, body, is_read, created_at}]}. POST /portal/{partner_slug}/notifications/{notification_id}/read marks one notification as read (sets is_read=TRUE, read_at=now()). Notification belongs to the calling portal_user_id AND partner_id (both from JWT claims). Attempting to mark another user's notification returns 404. | • Implement NotificationService.listNotifications(UUID userId, UUID partnerId): query portal_notifications WHERE portal_user_id = :userId AND partner_id = :partnerId ORDER BY created_at DESC LIMIT 50; count unread separately • Implement NotificationService.markAsRead(UUID userId, UUID partnerId, UUID notificationId): query WHERE id = :notificationId AND portal_user_id = :userId AND partner_id = :partnerId; if empty return 404; set is_read=TRUE, read_at=now() • Wire GET endpoint returning NotificationListResponse {unread_count, notifications} • Wire POST /{notification_id}/read returning 204 • Write unit test: marking another user's notification returns 404; marking own notification sets is_read=TRUE | NotificationService + GET notifications + POST .../read endpoints; unit tests for user-scoped isolation | • GET notifications for user A returns only notifications with portal_user_id = user A (not user B of same partner) • POST /notifications/{id}/read where notification belongs to different user returns HTTP 404 • POST /notifications/{id}/read on own notification: subsequent GET shows is_read=TRUE for that notification • unread_count in GET response matches count of is_read=FALSE notifications for that user • Endpoint requires valid JWT (PortalJwtAuthFilter enforces 401 for unauthenticated) | 40 | 11.1-T09, 11.1-T10, 11.1-T03 | FS | PRD-08, SEC-09
11.1-T24 | partner-portal-ui | 11.1 | 11. Partner Portal | Portal shell, scoped auth & isolation | 3 | NotificationDispatcher: create in-portal notifications on trigger events | PRD-08 §9.1. Notifications are created when: (1) LOW_BALANCE -- triggered by prefunding deduction that causes balance < threshold; (2) STATEMENT_READY -- triggered by settlement statement generation job; (3) SETTLEMENT_CONFIRMED -- triggered by GME Ops confirming a settlement period; (4) WEBHOOK_FAILURE -- triggered after 3 consecutive webhook delivery failures. NotificationDispatcher.createForAllPartnerUsers(UUID partnerId, NotificationType type, String title, String body) creates one portal_notification row per active portal_user belonging to that partner. Integration points: prefunding deduction service calls createForAllPartnerUsers on LOW_BALANCE; webhook delivery tracker calls it on 3rd consecutive failure. Notification data must not include internal margin or rate fields. | • Implement NotificationDispatcher.createForAllPartnerUsers(UUID partnerId, NotificationType type, String title, String body) • Load all portal_users WHERE partner_id = :partnerId AND is_active = TRUE • For each user insert portal_notifications row with portal_user_id, partner_id, type, severity (derived from type enum), title, body, is_read=FALSE • Annotate method @Transactional • Write unit test: calling for partner with 3 active users + 1 deactivated user creates exactly 3 notifications • Write unit test: LOW_BALANCE notification has severity=HIGH; STATEMENT_READY has severity=INFO | NotificationDispatcher.createForAllPartnerUsers() + unit tests for active-user filtering and severity mapping | • For partner with 3 active + 1 deactivated user, exactly 3 notification rows are inserted • Notifications are inserted with is_read=FALSE and read_at=NULL • LOW_BALANCE -> severity=HIGH; WEBHOOK_FAILURE -> severity=WARNING; STATEMENT_READY -> severity=INFO; SETTLEMENT_CONFIRMED -> severity=INFO • Each notification row has portal_user_id set to one of the active users (not null, not deactivated user) • Method is transactional: if any insert fails, all inserts roll back (no partial creation) | 35 | 11.1-T03, 11.1-T05 | FS | PRD-08, SEC-09
11.1-T25 | partner-portal-ui | 11.1 | 11. Partner Portal | Portal shell, scoped auth & isolation | 3 | EmailNotificationService: send email alerts for low-balance and statement events | PRD-08 §9.2. Email sent to partner's registered alert_email_addresses (one or more, stored in partner_config.alert_emails JSON array, set by GME Ops). Trigger events: (1) balance drops below threshold -> email {current_balance USD, threshold USD, top-up instructions, GME account team contact}; (2) balance reaches zero -> urgent email (all overseas payments suspended); (3) statement_ready -> email {link to portal statement page, period summary}; (4) settlement_confirmed -> email with confirmation totals. Email delivery via configured SMTP/SES. If alert_emails is empty or null for a partner, skip silently and log a warning. Emails must not include m_a, m_b, or GME internal revenue figures. | • Implement EmailNotificationService.sendLowBalanceAlert(UUID partnerId, BigDecimal currentBalance, BigDecimal threshold) • Load alert_emails from partner_config; if empty log WARN and return • Build email body: current balance (USD 2dp), threshold (USD 2dp), static top-up instructions text, GME account team contact placeholder • If currentBalance.compareTo(BigDecimal.ZERO) == 0, set subject prefix URGENT and note payments suspended • Send via JavaMailSender or AWS SES client; log send attempt and result • Write unit tests using mock mail sender: verifies to-addresses, that balance=0.00 triggers urgent subject, that alert_emails=[] skips silently | EmailNotificationService.sendLowBalanceAlert() + unit tests with mock mail sender | • Email is sent to all addresses in alert_emails array (e.g. 2 addresses -> 2 to-field recipients OR one email with multiple recipients) • partner with alert_emails=[] results in zero emails sent and a WARN log entry • Balance=0.00 email has subject containing 'URGENT' (case-insensitive) • Balance=5000.00 threshold=10000.00 email body contains '5000.00' and '10000.00' • Email body does not contain substrings m_a, m_b, cost_rate, margin_usd, or collection_margin | 40 | 11.1-T24 | FS | PRD-08, SEC-09
11.1-T26 | partner-portal-ui | 11.1 | 11. Partner Portal | Portal shell, scoped auth & isolation | 3 | Integration test: full partner-scoped auth flow and cross-partner isolation | SEC-09 §3.5 and PRD-08 §2.2. IDOR testing is a mandatory test case (SEC-09 §3.5). This test ticket covers end-to-end auth and isolation using two real database-backed partners (partner_a and partner_b) with one portal user each. Tests run against an embedded/test database. Isolation invariant: partner_a user can never retrieve partner_b transactions, balance, or statements -- and gets HTTP 404 (not 403 or 500) for transaction detail and HTTP 404 for balance (if partner_b is LOCAL). | • Set up two partners: partner_a (OVERSEAS, balance USD 5000.00) and partner_b (LOCAL) with one portal user each • Create 3 transactions for partner_a and 2 for partner_b • Log in as partner_a user (POST /portal/auth/login); extract access_token • Assert GET /portal/partner_a_slug/transactions returns 3 rows all with partner_id = partner_a • Assert GET /portal/partner_a_slug/transactions/{partner_b_txn_ref} returns HTTP 404 • Assert GET /portal/partner_b_slug/transactions with partner_a JWT returns HTTP 403 PARTNER_MISMATCH (slug guard T10) • Assert GET /portal/partner_a_slug/balance returns 200 for OVERSEAS partner_a; GET /portal/partner_b_slug/balance (as partner_b user) returns 404 for LOCAL partner_b | PortalIsolationIntegrationTest class with all IDOR and auth-flow scenarios passing | • partner_a user GET transactions returns exactly 3 rows, all partner_id = partner_a • partner_a user accessing partner_b transaction ref returns HTTP 404 • partner_a JWT used against partner_b slug returns HTTP 403 PARTNER_MISMATCH • partner_b (LOCAL) balance endpoint returns HTTP 404 • partner_a user login with wrong password 5 times results in 423 ACCOUNT_LOCKED on 6th attempt | 55 | 11.1-T12, 11.1-T14, 11.1-T15, 11.1-T16, 11.1-T18, 11.1-T10 | FS | PRD-08, SEC-09
11.1-T27 | partner-portal-ui | 11.1 | 11. Partner Portal | Portal shell, scoped auth & isolation | 3 | Unit tests: PortalAuthService TOTP, lockout, recovery-code, and session-expiry edge cases | Logic-bearing edge cases for PortalAuthService (T07, T08) require dedicated unit-test coverage. Test vectors: (a) TOTP window: code for T-1 slot accepted; code for T-2 slot rejected; (b) lockout: 4 failures -> not locked; 5th failure -> locked; locked account returns AccountLockedException before password check; (c) recovery code: used once and removed; reuse of same code fails; (d) idle timeout: last_active_at 14 min ago -> refresh succeeds; 16 min ago -> SESSION_EXPIRED; (e) absolute timeout: issued 23h59m ago -> refresh succeeds; issued 24h1m ago -> SESSION_EXPIRED. All tests use mocked repositories -- no DB required. | • Write PortalAuthServiceUnitTest with @ExtendWith(MockitoExtension.class) • Test T-1 TOTP slot acceptance and T-2 slot rejection using a fixed TOTP secret and known window • Test lockout progression: 4 failures leave locked_until null; 5th failure sets locked_until approximately now+15min • Test recovery code single-use: first use succeeds and removes code; immediate reuse of same code fails AuthFailedException • Test idle timeout boundary: mock last_active_at 14 min ago returns new token; 16 min ago throws SessionExpiredException • Test absolute timeout boundary: issued_at 23h59m ago succeeds; issued_at 24h1m ago throws SessionExpiredException | PortalAuthServiceUnitTest class with all 6+ test cases passing | • TOTP T-2 window (60+ seconds old code) throws AuthFailedException • 5th consecutive failed login sets locked_until = now + 15min (within +-5s tolerance) • Recovery code that was used in the test is absent from the stored array after login • refreshSession with last_active_at = now - 14min returns a new access_token JWT • refreshSession with last_active_at = now - 16min throws SessionExpiredException • refreshSession with issued_at = now - 24h - 1min throws SessionExpiredException | 50 | 11.1-T07, 11.1-T08 | FS | PRD-08, SEC-09
11.1-T28 | partner-portal-ui | 11.1 | 11. Partner Portal | Portal shell, scoped auth & isolation | 3 | Unit tests: data-isolation invariants for TransactionQueryService and BalanceService | Unit tests verifying that repository methods used by TransactionQueryService (T15) and BalanceService (T18) always include partner_id in WHERE clauses. Uses @DataJpaTest with an H2 or embedded Postgres. Test vectors: (a) 10 txns for partner_a and 5 for partner_b -- query with partner_a id returns exactly 10; (b) balance for partner_a = USD 8000; query with partner_b id returns partner_b balance, not 8000; (c) ledger running-balance invariant: sum of all amount_usd entries for a partner equals current_balance in partner_prefunding (use partner_a with 3 credits and 2 debits). | • Write TransactionIsolationRepositoryTest with @DataJpaTest • Insert 10 transactions for partner_a and 5 for partner_b • Call transactionRepository.findByPartnerId(partner_a_id) and assert size = 10 • Call transactionRepository.findByPartnerId(partner_b_id) and assert size = 5 • Write BalanceIsolationTest: insert balances for both partners; assert getBalance(partner_a_id) returns partner_a balance • Write LedgerInvariantTest: seed 3 credits (+500 each) and 2 debits (-100 each) for partner_a; assert sum = 1300; assert current_balance in prefunding table = 1300.00 | TransactionIsolationRepositoryTest + BalanceIsolationTest + LedgerInvariantTest all passing | • transactionRepository.findByPartnerId(partner_a_id) returns 10 rows; not 15 (no partner_b leakage) • getBalance(partner_a_id) returns 8000.00 USD regardless of partner_b balance value • Sum of amount_usd for partner_a ledger entries = current_balance in partner_prefunding for partner_a (tolerance 0.00) • KST date-boundary test: transaction at 2026-06-05T00:00:00+09:00 (= 2026-06-04T15:00Z) counts in KST June 5 today-filter • All assertions use BigDecimal.compareTo(expected) == 0 (not == or .equals on double) | 50 | 11.1-T15, 11.1-T18, 11.1-T19 | FS | PRD-08, SEC-09
11.1-T29 | partner-portal-ui | 11.1 | 11. Partner Portal | Portal shell, scoped auth & isolation | 3 | Portal shell: React app scaffold with auth context, router, and protected-route wrapper | The Partner Portal is a separate frontend SPA from the Admin System (PRD-08 assumption A-06). Tech stack per project convention. The shell provides: (a) PortalAuthContext holding {accessToken, partnerId, role, logout()}; (b) React Router with routes: /login (public), /{partnerSlug}/dashboard, /{partnerSlug}/transactions, /{partnerSlug}/transactions/:ref, /{partnerSlug}/balance, /{partnerSlug}/balance/ledger, /{partnerSlug}/statements, /{partnerSlug}/credentials, /{partnerSlug}/users (admin only); (c) ProtectedRoute component that redirects to /login if no valid access token in context; (d) RoleProtectedRoute (wraps user-management route) that shows 403 page if role != PARTNER_ADMIN. | • Scaffold React app (Vite or CRA) with TypeScript; install React Router, axios, react-query or SWR • Implement PortalAuthContext: store access_token + partner_id + role in memory (not localStorage for XSS safety); persist refresh_token in httpOnly cookie or memory • Implement ProtectedRoute: check PortalAuthContext.accessToken; if null redirect to /login • Implement RoleProtectedRoute: additionally check role == PARTNER_ADMIN; if not, render Forbidden403 component • Define all routes as specified; lazy-load each page component • Write ProtectedRoute unit test: renders children when token present; redirects when token absent | Portal SPA scaffold with all routes, PortalAuthContext, ProtectedRoute, and RoleProtectedRoute components | • Navigating to /{slug}/dashboard without a token redirects to /login • Navigating to /{slug}/users as PARTNER_VIEWER renders the Forbidden403 component (not redirect) • PortalAuthContext.logout() clears accessToken; next render triggers redirect to /login • All routes compile with TypeScript strict mode (no any types on auth context) • Access token is NOT stored in localStorage (inspectable via document.cookie or memory check in unit test) | 55 |  | FS | PRD-08, SEC-09
11.1-T30 | partner-portal-ui | 11.1 | 11. Partner Portal | Portal shell, scoped auth & isolation | 3 | Login page: email + password + TOTP form with lockout feedback | PRD-08 §2.1. Login form fields: email, password, totp_code (6-digit numeric or recovery code). On submit: POST /portal/auth/login; store returned access_token in PortalAuthContext; store refresh_token per T29 convention; redirect to /{partnerSlug}/dashboard (partnerSlug derived from partner_id by looking up slug mapping on login response or a separate API call). Error states: 401 -> show generic 'Invalid credentials' (do not distinguish password vs TOTP -- oracle prevention); 423 ACCOUNT_LOCKED -> show 'Account locked until {unlock_at formatted in user local time}'; 400 validation -> inline field errors. TOTP input should be auto-focused when password is filled (UX). Loading state on submit button. | • Create LoginPage component with controlled form state for email, password, totp_code • On submit call POST /portal/auth/login via axios; disable submit button while loading • On 200 success: store tokens in PortalAuthContext; redirect to /{partnerSlug}/dashboard • On 401: display 'Invalid credentials or one-time code. Please try again.' (no distinction) • On 423: display 'Account locked. Try again after {unlock_at local time}' • Write unit tests (React Testing Library): form submission sends correct payload; 401 shows generic error; 423 shows unlock time | LoginPage component; LoginPage.test.tsx with API success, 401, and 423 scenarios | • Form submits JSON {email, password, totp_code} to POST /portal/auth/login • 401 response shows generic message not revealing which field was wrong • 423 response shows unlock time formatted in browser local time (not raw ISO-8601) • Submit button is disabled while request is in-flight (prevents double-submit) • After successful login, window location is /{partnerSlug}/dashboard (redirect confirmed in test) | 50 | 11.1-T29, 11.1-T12 | FS | PRD-08, SEC-09
11.1-T31 | partner-portal-ui | 11.1 | 11. Partner Portal | Portal shell, scoped auth & isolation | 3 | Portal header: notification bell with unread count and session-expiry auto-logout | PRD-08 §9.1: notification bell in portal header shows unread count. Auto-logout: when an API call returns 401 SESSION_EXPIRED or SESSION_REVOKED, clear PortalAuthContext and redirect to /login (with flash message 'Your session has expired. Please log in again.'). Notification bell: polls GET /portal/{slug}/notifications every 60 seconds; shows red badge with unread_count when > 0. Clicking bell opens notification dropdown (list of 10 most recent; clicking each marks it read). Header also shows partner name, logged-in user email, and a Logout button. | • Create PortalHeader component: partner name, user email, logout button, notification bell • Implement useNotifications hook: fetch GET /{slug}/notifications on mount and every 60s via setInterval; expose {unread_count, notifications, markAsRead} • markAsRead(id): POST /{slug}/notifications/{id}/read; optimistically set is_read=TRUE in local state • Implement global axios response interceptor: on 401 with error=SESSION_EXPIRED or SESSION_REVOKED call PortalAuthContext.logout() and navigate to /login with flash • Logout button: calls POST /portal/auth/logout then clears context and redirects to /login • Write unit test: 401 SESSION_EXPIRED on any API call triggers logout and redirect | PortalHeader component + useNotifications hook + axios interceptor; test for auto-logout on 401 SESSION_EXPIRED | • Notification bell shows red badge with count=3 when API returns unread_count=3 • Clicking a notification calls POST .../read and the item shows as read without full page reload • Any API call returning 401 {error: SESSION_EXPIRED} clears auth context and redirects to /login • Logout button calls POST /portal/auth/logout and then navigates to /login • Poll interval is 60 seconds (confirm via jest fake timers: after 60s, a second fetch is made) | 50 | 11.1-T29, 11.1-T23, 11.1-T13 | FS | PRD-08, SEC-09
11.2-T01 | partner-portal-ui | 11.2 | 11. Partner Portal | Dashboard (balance/volume/alerts) | 3 | Create portal_notification DB migration for in-portal alerts | PRD-08 §9.1 specifies in-portal notifications for Partner Portal users. Each notification belongs to a partner_portal_user. Fields: id (UUID v4 PK), partner_id (UUID FK -> partner, NOT NULL), user_id (UUID FK -> partner_portal_user, NOT NULL), notification_type (VARCHAR(40): LOW_BALANCE¦STATEMENT_READY¦SETTLEMENT_CONFIRMED¦WEBHOOK_FAILURE), severity (VARCHAR(10): HIGH¦INFO¦WARNING), title VARCHAR(200), body TEXT, is_read (BOOLEAN DEFAULT false), created_at (TIMESTAMPTZ), read_at (TIMESTAMPTZ nullable), dismissed_for_session (BOOLEAN DEFAULT false). Indexes: (user_id, is_read) for bell-count query; (partner_id, created_at DESC) for listing. | • Create Flyway/Liquibase migration V11_2_001: create portal_notification table with all columns listed above • Add index idx_portal_notification_user_unread on (user_id, is_read) for fast unread-count query • Add index idx_portal_notification_partner_created on (partner_id, created_at DESC) for partner-scoped listing • Add CHECK constraint notification_type IN (LOW_BALANCE, STATEMENT_READY, SETTLEMENT_CONFIRMED, WEBHOOK_FAILURE) • Verify migration applies and rolls back cleanly on fresh schema | Flyway migration V11_2_001 creating portal_notification table with indexes and constraint | • Table accepts a row with all required fields; UUID PK auto-generated • notification_type outside the allowed enum raises a CHECK constraint violation • Index idx_portal_notification_user_unread exists and is used by EXPLAIN on SELECT ... WHERE user_id=? AND is_read=false • Inserting a row with a NULL partner_id raises NOT NULL violation • dismissed_for_session defaults to false when not provided | 30 |  | FS | PRD-08
11.2-T02 | partner-portal-ui | 11.2 | 11. Partner Portal | Dashboard (balance/volume/alerts) | 3 | Create partner_portal_user DB migration for portal user accounts | PRD-08 §2.1 and §2.3: each portal user belongs to exactly one partner. partner_portal_user: id (UUID v4 PK), partner_id (UUID FK -> partner NOT NULL), email (VARCHAR(255) UNIQUE NOT NULL), name (VARCHAR(120) NOT NULL), role (VARCHAR(20): PARTNER_ADMIN¦PARTNER_VIEWER NOT NULL), is_active (BOOLEAN DEFAULT true NOT NULL), totp_secret (TEXT nullable, stored encrypted), totp_verified (BOOLEAN DEFAULT false), recovery_codes (JSONB nullable, hashed), consecutive_failures (SMALLINT DEFAULT 0), locked_until (TIMESTAMPTZ nullable), last_login_at (TIMESTAMPTZ nullable), created_at, updated_at, created_by (UUID FK -> hub_user nullable). Index on (partner_id, email). | • Create migration V11_2_002: create partner_portal_user with all columns above • Add UNIQUE index on email (global, not per-partner — email is login key) • Add index idx_ppu_partner_id on (partner_id) to support per-partner user list • Add CHECK role IN (PARTNER_ADMIN, PARTNER_VIEWER) • Add partner_portal_credential table: user_id (UUID PK FK), password_hash TEXT NOT NULL, must_change BOOLEAN DEFAULT true, updated_at TIMESTAMPTZ | Migrations V11_2_002 creating partner_portal_user and partner_portal_credential tables | • Two users with the same email across different partners raise UNIQUE violation (email is globally unique) • role outside (PARTNER_ADMIN, PARTNER_VIEWER) raises CHECK constraint violation • partner_portal_credential.user_id is PK; second insert for same user_id raises violation • is_active defaults to true; null insert raises NOT NULL violation • CHECK constraint exists on role column and rejects SUPER_ADMIN | 35 | 11.2-T01 | FS | PRD-08
11.2-T03 | partner-portal-ui | 11.2 | 11. Partner Portal | Dashboard (balance/volume/alerts) | 3 | Create portal_session_dismiss DB migration for session-dismissed alerts | PRD-08 §3.4: the low-balance alert on the Dashboard is dismissible for the current session only. To track session-level dismissals without storing state in the JWT (stateless-session-compatible), record dismissals in a short-lived table. portal_session_dismiss: id (UUID v4 PK), session_id (UUID NOT NULL), notification_type (VARCHAR(40) NOT NULL), partner_id (UUID NOT NULL), dismissed_at (TIMESTAMPTZ DEFAULT now()), expires_at (TIMESTAMPTZ NOT NULL). Index on (session_id, notification_type). A scheduled job purges rows where expires_at < now(); retention max 24 hours matching absolute session limit. | • Create migration V11_2_003: create portal_session_dismiss table with all columns above • Add index idx_psd_session_type on (session_id, notification_type) for lookup at dashboard render • Add partial index or note that expires_at is used by purge job (no FK to session; session_id is opaque UUID from JWT) • Document in migration comment that rows are purged by a scheduled cleanup job when expires_at < now() • Verify constraint: notification_type CHECK IN (LOW_BALANCE, SETTLEMENT_DUE) | Migration V11_2_003 creating portal_session_dismiss table | • Row inserted with session_id + LOW_BALANCE is retrievable by (session_id, LOW_BALANCE) lookup • notification_type outside (LOW_BALANCE, SETTLEMENT_DUE) raises CHECK violation • expires_at is NOT NULL; null insert raises violation • Index idx_psd_session_type appears in EXPLAIN for the session-dismiss lookup • Two rows with the same (session_id, notification_type) are allowed (no unique constraint needed; presence of any row = dismissed) | 25 | 11.2-T01 | FS | PRD-08