## WBS
WBS Code | WS # | Workstream | Task / Work Package | Description | Phase | Component | Source Doc(s) | Effort (PD) | Dependencies | Key Deliverable | Primary Role | Tickets | Done | Partial | Not Started | % Done | Status (audit 2026-06-10) | Completion Phase (v3)
1.1 | 1 | 1. Project Management & Mobilization | Project kickoff & mobilization | Team onboarding, access, comms plan, tooling setup. | 1 | Cross-cutting | DOC-00, PM-14 | 5 | - | Kickoff pack, RACI confirmed | PM | 15 | 0 | 1 | 14 | 0% | IN PROGRESS | R0
1.2 | 1 | 1. Project Management & Mobilization | Requirements walkthrough & open-item resolution | Confirm scope; drive OI-01 (customer approval UX), OI-02 (tax-invoice API), OI-03 (BOK format) to decisions. | 1 | Cross-cutting | All | 6 | 1.1 | Clarification log, updated assumptions | BA | 20 | 0 | 0 | 20 | 0% | NOT STARTED | R0
1.3 | 1 | 1. Project Management & Mobilization | Delivery plan, environments & estimates | Detailed schedule, environment plan, refined estimates per this WBS. | 1 | Cross-cutting | PM-14 | 5 | 1.1 | Baselined plan | PM | 33 | 3 | 3 | 27 | 9% | IN PROGRESS | R0
1.4 | 1 | 1. Project Management & Mobilization | Architecture & design sign-off | Review SAD/data model with GME; approve approach. | 1 | Cross-cutting | SAD-02 | 4 | 2.1,3.1 | Signed-off design | ARCH | 30 | 0 | 0 | 30 | 0% | NOT STARTED | R0
1.5 | 1 | 1. Project Management & Mobilization | Ongoing project management & reporting | Sprint ceremonies, status reporting, risk/RAID upkeep across all phases. | 1 | Cross-cutting | PM-14 | 40 | 1.3 | Status reports, RAID log | PM | 30 | 0 | 0 | 30 | 0% | NOT STARTED | R8
1.6 | 1 | 1. Project Management & Mobilization | As-built documentation & handover | Update specs to as-built, API docs, ops handover materials. | 4 | Cross-cutting | DOC-00 | 10 | 16.5 | As-built docs | BA | 22 | 0 | 0 | 22 | 0% | NOT STARTED | R8
2.1 | 2 | 2. Architecture & Technical Foundation | Finalize system architecture & tech stack | Component architecture, service boundaries, tech choices. | 1 | Cross-cutting | SAD-02 | 6 | 1.1 | Architecture baseline | ARCH | 33 | 1 | 16 | 16 | 3% | IN PROGRESS | R0
2.2 | 2 | 2. Architecture & Technical Foundation | Service/module structure & scaffolding | Hub Core, scheme adapters, API gateway module skeletons. | 1 | Hub Core | SAD-02 | 5 | 2.1 | Service skeletons | ARCH | 28 | 2 | 20 | 6 | 7% | IN PROGRESS | R0
2.3 | 2 | 2. Architecture & Technical Foundation | Coding standards, repo, branching, CI scaffold | Repos, branching model, lint/format, build scaffold. | 1 | Cross-cutting | OPS-13 | 4 | 2.1 | Standards & repo | ARCH | 27 | 0 | 0 | 27 | 0% | NOT STARTED | R0
2.4 | 2 | 2. Architecture & Technical Foundation | Cross-cutting libs: money, currency, errors | Decimal/money type, currency scale, canonical error model. | 1 | Hub Core | RATE-04, API-05 | 6 | 2.3 | Shared libraries | BE | 25 | 0 | 14 | 11 | 0% | IN PROGRESS | R1
2.5 | 2 | 2. Architecture & Technical Foundation | Configuration framework (config-not-code) | Schemes/partners/rules/rates as runtime config; no deploy to add. | 1 | Cross-cutting | NFR-10, SAD-02 | 8 | 2.4 | Config framework | BE | 33 | 0 | 4 | 29 | 0% | IN PROGRESS | R1
2.6 | 2 | 2. Architecture & Technical Foundation | Internationalization framework | Multi-currency (KRW/USD/…), Korean/English support. | 1 | Cross-cutting | NFR-10 | 4 | 2.4 | i18n framework | BE | 26 | 0 | 0 | 26 | 0% | NOT STARTED | R4
3.1 | 3 | 3. Data Layer & Persistence | Database design & ERD implementation | Physical schema from DAT-03; constraints & indexes. | 1 | Hub Core | DAT-03 | 8 | 2.1 | DB schema v1 | DBA | 29 | 0 | 7 | 22 | 0% | IN PROGRESS | R1
3.2 | 3 | 3. Data Layer & Persistence | Core entities: Scheme/Partner/Rule/Direction | Generic entity tables; rule = partner×scheme×direction. | 1 | Hub Core | DAT-03 | 6 | 3.1 | Entity model; + Partner.settlement_rounding_mode field | BE | 35 | 2 | 8 | 25 | 6% | IN PROGRESS | R1
3.3 | 3 | 3. Data Layer & Persistence | Transaction & event tables (8-step trail) | Transaction store + immutable event trail. | 1 | Hub Core | DAT-03, PRD-07 | 6 | 3.1 | Txn schema; + locked booked_settlement_amount & rounding_mode & residual | BE | 21 | 0 | 4 | 17 | 0% | IN PROGRESS | R1
3.4 | 3 | 3. Data Layer & Persistence | Treasury/FX rate tables (effective-dated) | treasury.usd_{ccy} store with history/effective dating. | 1 | Hub Core | RATE-04 | 4 | 3.1 | Rate tables | BE | 24 | 0 | 1 | 23 | 0% | IN PROGRESS | R1
3.5 | 3 | 3. Data Layer & Persistence | Prefunding ledger tables (double-entry) | Balance + ledger entries for prefunding. | 1 | Hub Core | DAT-03 | 5 | 3.1 | Ledger schema | BE | 24 | 0 | 9 | 15 | 0% | IN PROGRESS | R1
3.6 | 3 | 3. Data Layer & Persistence | Audit log tables (immutable) | actor/timestamp/previous-value config audit store. | 1 | Cross-cutting | SEC-09 | 4 | 3.1 | Audit schema | BE | 24 | 0 | 0 | 24 | 0% | NOT STARTED | R1
3.7 | 3 | 3. Data Layer & Persistence | Migration framework & seed data | Versioned reversible migrations; reference/seed data. | 1 | Hub Core | OPS-13 | 5 | 3.1 | Migration tooling | DBA | 28 | 1 | 7 | 20 | 4% | IN PROGRESS | R1
4.1 | 4 | 4. Rate Engine & FX | Treasury rate sourcing model | IDENTITY/LIVE/MANUAL/PARTNER resolution per leg. | 1 | Hub Core | RATE-04 | 6 | 3.4 | Rate sourcing svc | BE | 18 | 0 | 2 | 16 | 0% | IN PROGRESS | R1
4.2 | 4 | 4. Rate Engine & FX | 5-step RECEIVE-mode calculation engine | payout_usd_cost→collection_usd→margins→send_amount→collection_amount. | 1 | Hub Core | RATE-04 | 12 | 2.4,4.1 | Rate engine core | BE | 16 | 0 | 13 | 3 | 0% | IN PROGRESS | R2
4.3 | 4 | 4. Rate Engine & FX | USD pool identity assertion | Invariant check within 0.01 USD tolerance. | 1 | Hub Core | RATE-04 | 5 | 4.2 | Identity guard | BE | 9 | 0 | 1 | 8 | 0% | IN PROGRESS | R2
4.4 | 4 | 4. Rate Engine & FX | Derived BOK outputs | offer_rate_coll (FX1015 #14), cross_rate. | 1 | Hub Core | RATE-04, SEC-09 | 4 | 4.2 | Derived outputs | BE | 10 | 0 | 3 | 7 | 0% | IN PROGRESS | R2
4.5 | 4 | 4. Rate Engine & FX | Identity legs & same-currency short-circuit | USD legs (rate=1.0); skip pool when all ccy equal. | 1 | Hub Core | RATE-04 | 6 | 4.2 | Special-case logic | BE | 11 | 0 | 3 | 8 | 0% | IN PROGRESS | R2
4.6 | 4 | 4. Rate Engine & FX | Partner B authoritative quote & deviation | Quote fetch, tolerance check, DEVIATION/UNAVAILABLE errors. | 1 | Hub Core | RATE-04, API-05 | 6 | 4.2 | Partner-B handler | BE | 15 | 0 | 0 | 15 | 0% | NOT STARTED | R1
4.7 | 4 | 4. Rate Engine & FX | Rate quote lifecycle, TTL & rate-lock | Quote issuance, validUntil, lock on commit. | 1 | Hub Core | RATE-04 | 6 | 4.2 | Quote/lock svc | BE | 15 | 0 | 0 | 15 | 0% | NOT STARTED | R1
4.8 | 4 | 4. Rate Engine & FX | Rounding & precision rules | Per-currency scale & rounding at defined points. | 1 | Hub Core | RATE-04 | 4 | 4.2 | Rounding module | BE | 11 | 0 | 4 | 7 | 0% | IN PROGRESS | R2
4.9 | 4 | 4. Rate Engine & FX | Rate engine unit tests vs vectors | Implement RV-01..RV-10 from QA-12 §4. | 1 | Hub Core | QA-12 | 8 | 4.2,4.3,4.5 | Vector test suite | QA | 12 | 0 | 3 | 9 | 0% | IN PROGRESS | R2
5.1 | 5 | 5. Transaction Processing (MPM/CPM) | Transaction state machine | Lifecycle/status model for MPM & CPM. | 1 | Hub Core | RATE-04, API-05 | 8 | 3.3 | State machine | BE | 32 | 1 | 6 | 25 | 3% | IN PROGRESS | R2
5.2 | 5 | 5. Transaction Processing (MPM/CPM) | Fixed MPM execution flow | POST /payments; prefund deduction point (MPM). | 1 | Hub Core | API-05, RATE-04 | 8 | 5.1,4.7,6.2 | MPM flow | BE | 28 | 0 | 6 | 22 | 0% | IN PROGRESS | R2
5.3 | 5 | 5. Transaction Processing (MPM/CPM) | CPM token generation & flow | cpm/generate; prefund deduction point (CPM). | 1 | Hub Core | API-05 | 8 | 5.1,6.2 | CPM flow | BE | 25 | 0 | 4 | 21 | 0% | IN PROGRESS | R2
5.4 | 5 | 5. Transaction Processing (MPM/CPM) | QR parsing (EMVCo) & merchant resolution | Parse MPM/CPM payloads; resolve merchant/QR. | 1 | Hub Core | SCH-06 | 6 | 5.1 | QR parser | BE | 22 | 8 | 3 | 11 | 36% | IN PROGRESS | R2
5.5 | 5 | 5. Transaction Processing (MPM/CPM) | CommitTransaction & payment.approved | Finalize txn; assemble approved payload. | 1 | Hub Core | API-05, RATE-04 | 5 | 5.2,5.3 | Commit logic; + book settlement under partner rule, lock on txn, post residual | BE | 36 | 0 | 4 | 32 | 0% | IN PROGRESS | R2
5.6 | 5 | 5. Transaction Processing (MPM/CPM) | Same-day cancellation | Cancel flow (refunds are admin-only in P1). | 1 | Hub Core | API-05 | 4 | 5.5 | Cancel flow | BE | 26 | 0 | 3 | 23 | 0% | IN PROGRESS | R2
5.7 | 5 | 5. Transaction Processing (MPM/CPM) | Idempotency & request dedup | Idempotency keys, safe retries. | 1 | Hub Core | API-05 | 5 | 5.1 | Idempotency svc | BE | 20 | 0 | 0 | 20 | 0% | NOT STARTED | R2
5.8 | 5 | 5. Transaction Processing (MPM/CPM) | Direction routing & extensibility | Inbound/Domestic live; Outbound/Hub scaffolding. | 1 | Hub Core | BRD-01, SAD-02 | 6 | 5.1 | Routing logic | BE | 25 | 0 | 1 | 24 | 0% | IN PROGRESS | R2
6.1 | 6 | 6. Prefunding & Wallet Ledger | Prefunding balance & top-up recording | Balance model; record top-ups (Ops-entered). | 1 | Hub Core | DAT-03, PRD-07 | 5 | 3.5 | Balance svc | BE | 31 | 0 | 8 | 23 | 0% | IN PROGRESS | R1
6.2 | 6 | 6. Prefunding & Wallet Ledger | Atomic deduction (SELECT FOR UPDATE) | Concurrency-safe deduction before scheme call. | 1 | Hub Core | RATE-04, NFR-10 | 6 | 6.1 | Deduction svc | BE | 28 | 0 | 8 | 20 | 0% | IN PROGRESS | R1
6.3 | 6 | 6. Prefunding & Wallet Ledger | Insufficient-balance rejection | Reject pre-scheme when balance < amount. | 1 | Hub Core | API-05 | 3 | 6.2 | Guard logic | BE | 22 | 0 | 9 | 13 | 0% | IN PROGRESS | R1
6.4 | 6 | 6. Prefunding & Wallet Ledger | Low-balance alerting | Per-partner threshold alerts. | 1 | Hub Core | PRD-07 | 3 | 6.1 | Alert rule | BE | 25 | 0 | 0 | 25 | 0% | NOT STARTED | R1
6.5 | 6 | 6. Prefunding & Wallet Ledger | Ledger reconciliation & statements | Reconcile ledger; generate statements. | 2 | Hub Core | RATE-04 | 5 | 6.1 | Recon report | BE | 30 | 0 | 0 | 30 | 0% | NOT STARTED | R2
7.1 | 7 | 7. Settlement, Reconciliation & Revenue | Settlement model: net vs gross | Domestic net; international gross. | 2 | Hub Core | RATE-04, SCH-06 | 6 | 5.5 | Settlement svc | BE | 35 | 3 | 5 | 27 | 9% | IN PROGRESS | R2
7.2 | 7 | 7. Settlement, Reconciliation & Revenue | Scheme fee share (70/30) computation | Compute GME 70% of net merchant fee. | 2 | Hub Core | RATE-04, BRD-01 | 5 | 7.1 | Fee-share calc | BE | 19 | 2 | 1 | 16 | 11% | IN PROGRESS | R2
7.3 | 7 | 7. Settlement, Reconciliation & Revenue | FX margin + service fee capture | Record margin & flat service fee revenue. | 2 | Hub Core | RATE-04 | 4 | 5.5 | Revenue capture; + rounding-residual posting to REVENUE_ROUNDING | BE | 26 | 0 | 6 | 20 | 0% | IN PROGRESS | R2
7.4 | 7 | 7. Settlement, Reconciliation & Revenue | Daily reconciliation engine | Pool identity, settlement files, prefunding ledger. | 2 | Hub Core | RATE-04, SCH-06 | 8 | 7.1,9.6 | Recon engine | BE | 28 | 0 | 4 | 24 | 0% | IN PROGRESS | R2
7.5 | 7 | 7. Settlement, Reconciliation & Revenue | Revenue reporting & exports | Revenue reports; exportable to Finance. | 2 | Hub Core | PRD-07 | 6 | 7.2,7.3 | Revenue reports | BE | 26 | 0 | 0 | 26 | 0% | NOT STARTED | R7
7.6 | 7 | 7. Settlement, Reconciliation & Revenue | Gross settlement & monthly invoicing | Whole-amount settle; monthly merchant invoice; 0.21% ZP share. | 2 | Hub Core | SCH-06 | 6 | 7.1 | Invoicing logic | BE | 24 | 0 | 1 | 23 | 0% | IN PROGRESS | R2
8.1 | 8 | 8. Partner (Northbound) API | API gateway & versioning framework | Base REST framework, /v1, conventions. | 1 | API-N | API-05 | 5 | 2.2 | API base | BE | 26 | 3 | 6 | 17 | 12% | IN PROGRESS | R3
8.2 | 8 | 8. Partner (Northbound) API | Auth: API key + HMAC signing | Per-partner creds (hashed), signing, replay protection. | 1 | API-N | API-05, SEC-09 | 6 | 8.1,13.2 | Auth module | BE | 22 | 1 | 7 | 14 | 5% | IN PROGRESS | R3
8.3 | 8 | 8. Partner (Northbound) API | POST /rates (quote) | Quote endpoint returning offer_rate, validUntil. | 1 | API-N | API-05, RATE-04 | 4 | 8.1,4.7 | Quote endpoint | BE | 1 | 0 | 0 | 1 | 0% | NOT STARTED | R2
8.4 | 8 | 8. Partner (Northbound) API | POST /payments & /cpm/generate | Execute MPM and issue CPM token. | 1 | API-N | API-05 | 6 | 8.1,5.2,5.3 | Payment endpoints | BE | 32 | 0 | 11 | 21 | 0% | IN PROGRESS | R2
8.5 | 8 | 8. Partner (Northbound) API | Query/cancel/merchant/balance endpoints | GET /payments/{id}, /cancel, /merchants, /balance. | 1 | API-N | API-05 | 5 | 8.1,6.1 | Supporting endpoints | BE | 30 | 0 | 11 | 19 | 0% | IN PROGRESS | R2
8.6 | 8 | 8. Partner (Northbound) API | Webhooks: events, signing, retry | Event delivery, signatures, backoff, ordering. | 1 | API-N | API-05 | 8 | 8.1,5.5 | Webhook svc | BE | 26 | 0 | 9 | 17 | 0% | IN PROGRESS | R2
8.7 | 8 | 8. Partner (Northbound) API | Error model & codes | Standard envelope + full error-code set. | 1 | API-N | API-05 | 3 | 8.1 | Error catalog | BE | 18 | 4 | 5 | 9 | 22% | IN PROGRESS | R2
8.8 | 8 | 8. Partner (Northbound) API | Rate limiting & IP allowlist | Throttling and allowlist enforcement. | 1 | API-N | API-05, SEC-09 | 3 | 8.1 | Throttle/allowlist | BE | 21 | 0 | 0 | 21 | 0% | NOT STARTED | R3
8.9 | 8 | 8. Partner (Northbound) API | OpenAPI finalization & sandbox | Validate vs partner-api.yaml; sandbox env. | 1 | API-N | API-05 | 5 | 8.3,8.4,8.5 | Sandbox + spec | BE | 28 | 0 | 10 | 18 | 0% | IN PROGRESS | R7
8.10 | 8 | 8. Partner (Northbound) API | Partner integration & certification kit | Onboarding guide, cert checklist. | 3 | API-N | API-05 | 5 | 8.9 | Integration kit | BA | 30 | 1 | 14 | 15 | 3% | IN PROGRESS | R7
9.1 | 9 | 9. QR Scheme Integration (ZeroPay) | Scheme Adapter abstraction | Pluggable adapter interface for any scheme. | 2 | API-S | SCH-06 | 6 | 2.2 | Adapter interface | ARCH | 31 | 1 | 6 | 24 | 3% | IN PROGRESS | R2
9.2 | 9 | 9. QR Scheme Integration (ZeroPay) | SFTP connectivity, keys, PGP | Secure SFTP, key mgmt, file naming/retention. | 2 | API-S | SCH-06, SEC-09 | 6 | 9.1,14.3 | SFTP channel | DevOps | 34 | 0 | 2 | 32 | 0% | IN PROGRESS | R7
9.3 | 9 | 9. QR Scheme Integration (ZeroPay) | Merchant & QR synchronization | ZP0041/45/47/51/55 + ZP0043/53; delta+full recon. | 2 | API-S | SCH-06 | 12 | 9.2,3.2 | Sync jobs | BE | 30 | 0 | 2 | 28 | 0% | IN PROGRESS | R7
9.4 | 9 | 9. QR Scheme Integration (ZeroPay) | Payment result exchange (ZP0011/0012) | Outbound result; inbound result matching. | 2 | API-S | SCH-06 | 8 | 9.2,5.5 | Payment batch | BE | 25 | 0 | 3 | 22 | 0% | IN PROGRESS | R2
9.5 | 9 | 9. QR Scheme Integration (ZeroPay) | Refund result exchange (ZP0021/0022) | Refund batch round-trip. | 2 | API-S | SCH-06 | 6 | 9.4 | Refund batch | BE | 27 | 0 | 0 | 27 | 0% | NOT STARTED | R7
9.6 | 9 | 9. QR Scheme Integration (ZeroPay) | Settlement files (ZP0061–0066) | Settlement requests/results & details. | 2 | API-S | SCH-06 | 12 | 9.4,7.1 | Settlement batch | BE | 34 | 0 | 2 | 32 | 0% | IN PROGRESS | R7
9.7 | 9 | 9. QR Scheme Integration (ZeroPay) | Batch scheduler & window monitoring | Schedule ZP jobs; alert on missed windows. | 2 | API-S | SCH-06, OPS-13 | 6 | 9.2,14.6 | Batch scheduler | DevOps | 25 | 0 | 0 | 25 | 0% | NOT STARTED | R7
9.8 | 9 | 9. QR Scheme Integration (ZeroPay) | Reconciliation & exception handling | Unmatched/late/partial handling, retransmit. | 2 | API-S | SCH-06 | 8 | 9.4,9.6 | Exception handling | BE | 32 | 0 | 3 | 29 | 0% | IN PROGRESS | R7
9.9 | 9 | 9. QR Scheme Integration (ZeroPay) | Scheme status/reason code mapping | Map ZP codes to API-05 error model. | 2 | API-S | SCH-06 | 3 | 9.4 | Code mapping | BE | 22 | 0 | 5 | 17 | 0% | IN PROGRESS | R2
9.10 | 9 | 9. QR Scheme Integration (ZeroPay) | 한결원/KFTC test env integration & cert | End-to-end against ZeroPay test environment. | 2 | API-S | SCH-06, PM-14 | 10 | 9.3,9.4,9.6 | Scheme cert | QA | 36 | 0 | 1 | 35 | 0% | IN PROGRESS | R7
10.1 | 10 | 10. Admin System | Admin app shell, nav & auth (SSO/2FA) | Shell, navigation, admin authentication. | 1 | Admin | PRD-07, UX-11 | 6 | 12.1,13.2 | Admin shell | FS | 24 | 0 | 7 | 17 | 0% | IN PROGRESS | R4
10.2 | 10 | 10. Admin System | Scheme management screens | Create/edit scheme, connectivity, status. | 2 | Admin | PRD-07 | 5 | 10.1,3.2 | Scheme UI | FS | 28 | 0 | 1 | 27 | 0% | IN PROGRESS | R4
10.3 | 10 | 10. Admin System | Partner management & credentials | Onboard partner, type, settlement ccy, API creds. | 2 | Admin | PRD-07 | 6 | 10.1,8.2 | Partner UI; + settlement-rounding-mode setting on partner | FS | 37 | 0 | 3 | 34 | 0% | IN PROGRESS ¦ SUPERSEDED — see WS 21 / docs/PARTNER_SETUP_PLAN.md | R4
10.4 | 10 | 10. Admin System | Rule/Mapping page — 4 sections | Currency / Rate config / Margin / Service charge. | 2 | Admin | PRD-07, RATE-04 | 12 | 10.3,4.1 | Mapping page | FS | 31 | 0 | 0 | 31 | 0% | NOT STARTED | R4
10.5 | 10 | 10. Admin System | FX/Treasury rate management | Manual rate entry & history (P1). | 1 | Admin | PRD-07, RATE-04 | 5 | 10.1,3.4 | Rate admin UI | FS | 25 | 0 | 1 | 24 | 0% | IN PROGRESS | R4
10.6 | 10 | 10. Admin System | Transaction monitoring | Search/filter, detail, 8-step trail, locked values. | 2 | Admin | PRD-07 | 8 | 10.1,3.3 | Monitoring UI | FS | 32 | 0 | 2 | 30 | 0% | IN PROGRESS | R4
10.7 | 10 | 10. Admin System | Prefunding management UI | Balances, top-ups, ledger, alerts. | 2 | Admin | PRD-07 | 5 | 10.1,6.1 | Prefund UI | FS | 29 | 0 | 0 | 29 | 0% | NOT STARTED | R4
10.8 | 10 | 10. Admin System | Refund/cancellation handling UI | Admin-initiated refunds & batch to scheme. | 2 | Admin | PRD-07 | 5 | 10.1,9.5 | Refund UI | FS | 31 | 0 | 0 | 31 | 0% | NOT STARTED | R4
10.9 | 10 | 10. Admin System | Settlement & revenue dashboards | Batches, net/gross, two revenue streams, exports. | 2 | Admin | PRD-07 | 6 | 10.1,7.5 | Revenue UI | FS | 25 | 0 | 3 | 22 | 0% | IN PROGRESS | R4
10.10 | 10 | 10. Admin System | User & role management (RBAC) | Roles, permission matrix administration. | 1 | Admin | PRD-07, SEC-09 | 5 | 10.1,13.2 | RBAC UI | FS | 33 | 0 | 0 | 33 | 0% | NOT STARTED | R4
10.11 | 10 | 10. Admin System | Audit log viewer | Search/export immutable audit trail. | 2 | Admin | PRD-07, SEC-09 | 4 | 10.1,3.6 | Audit UI | FS | 23 | 0 | 1 | 22 | 0% | IN PROGRESS | R4
11.1 | 11 | 11. Partner Portal | Portal shell, scoped auth & isolation | Partner-scoped login; strict data isolation. | 3 | Portal | PRD-08, SEC-09 | 6 | 12.1,13.2 | Portal shell | FS | 31 | 0 | 3 | 28 | 0% | IN PROGRESS | R4
11.2 | 11 | 11. Partner Portal | Dashboard (balance/volume/alerts) | Summary widgets incl. low-balance. | 3 | Portal | PRD-08 | 4 | 11.1 | Dashboard | FS | 30 | 0 | 2 | 28 | 0% | IN PROGRESS | R4
11.3 | 11 | 11. Partner Portal | Transaction history (filter/export) | Filterable list with CSV export. | 3 | Portal | PRD-08 | 5 | 11.1,3.3 | History view | FS | 32 | 0 | 4 | 28 | 0% | IN PROGRESS | R4
11.4 | 11 | 11. Partner Portal | Transaction detail view | Full detail incl. rates & locked values. | 3 | Portal | PRD-08 | 4 | 11.3 | Detail view | FS | 28 | 0 | 3 | 25 | 0% | IN PROGRESS | R4
11.5 | 11 | 11. Partner Portal | Prefunding/balance & statements | Balance, ledger, downloadable statements. | 3 | Portal | PRD-08 | 4 | 11.1,6.1 | Statements | FS | 30 | 0 | 0 | 30 | 0% | NOT STARTED | R4
11.6 | 11 | 11. Partner Portal | API & credentials view | View key id, webhook status, sandbox info. | 3 | Portal | PRD-08, API-05 | 3 | 11.1,8.2 | Creds view | FS | 24 | 0 | 5 | 19 | 0% | IN PROGRESS | R4
11.7 | 11 | 11. Partner Portal | Notifications (in-portal + email) | Low balance, settlement complete. | 3 | Portal | PRD-08 | 3 | 11.1 | Notifications | FS | 27 | 0 | 0 | 27 | 0% | NOT STARTED | R4
12.1 | 12 | 12. UX/UI & Frontend Foundation | Design system & component library | Tokens, components, status badges, money formatting. | 1 | Cross-cutting | UX-11 | 8 | 1.4 | Design system | UX | 35 | 0 | 15 | 20 | 0% | IN PROGRESS | R4
12.2 | 12 | 12. UX/UI & Frontend Foundation | Admin screens: wireframe→hi-fi | Designs for all Admin modules incl. mapping page. | 1 | Admin | UX-11, PRD-07 | 8 | 12.1 | Admin designs | UX | 42 | 0 | 13 | 29 | 0% | IN PROGRESS | R4
12.3 | 12 | 12. UX/UI & Frontend Foundation | Portal screens: wireframe→hi-fi | Designs for Partner Portal screens. | 3 | Portal | UX-11, PRD-08 | 5 | 12.1 | Portal designs | UX | 38 | 0 | 14 | 24 | 0% | IN PROGRESS | R4
12.4 | 12 | 12. UX/UI & Frontend Foundation | Money/margin input components | Validated inputs (e.g. m_a+m_b≥2%). | 1 | Cross-cutting | UX-11, RATE-04 | 4 | 12.1 | Input components | FE | 23 | 0 | 0 | 23 | 0% | NOT STARTED | R4
12.5 | 12 | 12. UX/UI & Frontend Foundation | Accessibility (WCAG AA) & i18n | KO/EN, responsive, accessible. | 2 | Cross-cutting | UX-11, NFR-10 | 5 | 12.1 | A11y/i18n pass | FE | 31 | 0 | 3 | 28 | 0% | IN PROGRESS | R4
13.1 | 13 | 13. Security & Compliance | Security architecture & secrets/encryption | Zones, secrets mgmt, TLS/mTLS, at-rest encryption. | 1 | Cross-cutting | SEC-09 | 6 | 2.1 | Security baseline | Sec | 32 | 1 | 1 | 30 | 3% | IN PROGRESS | R3
13.2 | 13 | 13. Security & Compliance | RBAC model & permission matrix | Roles × capabilities for Admin & Portal. | 1 | Cross-cutting | SEC-09, PRD-07 | 5 | 13.1 | RBAC model | Sec | 29 | 0 | 1 | 28 | 0% | IN PROGRESS | R3
13.3 | 13 | 13. Security & Compliance | Threat model (STRIDE) & mitigations | Key threats + mitigations register. | 1 | Cross-cutting | SEC-09 | 4 | 13.1 | Threat model | Sec | 28 | 2 | 5 | 21 | 7% | IN PROGRESS | R3
13.4 | 13 | 13. Security & Compliance | App security: OWASP API Top 10 | Input validation, anti-fraud hooks, scanning. | 2 | Cross-cutting | SEC-09 | 6 | 8.1 | Security controls | Sec | 33 | 1 | 3 | 29 | 3% | IN PROGRESS | R3
13.5 | 13 | 13. Security & Compliance | Audit/logging & SIEM export | Audit pipeline, retention, SIEM feed. | 2 | Cross-cutting | SEC-09 | 5 | 3.6 | Audit pipeline | Sec | 23 | 0 | 1 | 22 | 0% | IN PROGRESS | R3
13.6 | 13 | 13. Security & Compliance | Data privacy (PIPA) & retention | PII inventory, minimization, residency, retention. | 2 | Cross-cutting | SEC-09 | 4 | 13.1 | Privacy controls | Sec | 23 | 0 | 0 | 23 | 0% | NOT STARTED | R3
13.7 | 13 | 13. Security & Compliance | BOK FX reporting capture | Capture FX1014/FX1015 fields [OI-03 pending]. | 3 | Cross-cutting | SEC-09, RATE-04 | 6 | 4.4,1.2 | BOK data capture | BE | 28 | 0 | 5 | 23 | 0% | IN PROGRESS | R7
13.8 | 13 | 13. Security & Compliance | AML/KYC hooks & monitoring | Transaction monitoring/screening hooks (partner does KYC). | 2 | Cross-cutting | SEC-09 | 5 | 5.1 | Monitoring hooks | Sec | 23 | 0 | 0 | 23 | 0% | NOT STARTED | R7
13.9 | 13 | 13. Security & Compliance | Credential lifecycle & key rotation | Issue/rotate/revoke partner & SFTP keys. | 2 | Cross-cutting | SEC-09 | 4 | 8.2,9.2 | Key lifecycle | Sec | 29 | 0 | 0 | 29 | 0% | NOT STARTED | R3
13.10 | 13 | 13. Security & Compliance | Security testing & penetration test | App/pen testing against SEC-09. | 3 | Cross-cutting | SEC-09, QA-12 | 8 | 13.4 | Pen-test report | Sec | 36 | 0 | 1 | 35 | 0% | IN PROGRESS | R6
14.1 | 14 | 14. DevOps, Infrastructure & Observability | Environment provisioning | dev/test/staging/prod incl. ZP test env access. | 1 | Infra | OPS-13 | 8 | 1.1 | Environments | DevOps | 40 | 0 | 0 | 40 | 0% | NOT STARTED | R5
14.2 | 14 | 14. DevOps, Infrastructure & Observability | CI/CD pipeline | Build/test/scan/deploy, gated promotion, rollback. | 1 | Infra | OPS-13 | 8 | 2.3 | CI/CD | DevOps | 32 | 0 | 0 | 32 | 0% | NOT STARTED | R5
14.3 | 14 | 14. DevOps, Infrastructure & Observability | IaC & networking/zones | Infra-as-code, network zones (SEC-09). | 1 | Infra | OPS-13, SEC-09 | 8 | 14.1 | IaC + network | DevOps | 29 | 0 | 0 | 29 | 0% | NOT STARTED | R5
14.4 | 14 | 14. DevOps, Infrastructure & Observability | Database HA, cache, queue | Primary+replica, cache, message queue. | 1 | Infra | OPS-13, NFR-10 | 6 | 14.3,3.1 | Data infra | DevOps | 33 | 0 | 0 | 33 | 0% | NOT STARTED | R5
14.5 | 14 | 14. DevOps, Infrastructure & Observability | Secrets manager & config injection | Centralized secrets; env config matrix. | 1 | Infra | OPS-13, SEC-09 | 4 | 14.3 | Secrets mgmt | DevOps | 24 | 0 | 0 | 24 | 0% | NOT STARTED | R5
14.6 | 14 | 14. DevOps, Infrastructure & Observability | Observability: metrics/logs/tracing | Dashboards, structured logs, tracing. | 1 | Infra | OPS-13, NFR-10 | 8 | 14.2 | Observability | DevOps | 25 | 0 | 0 | 25 | 0% | NOT STARTED | R5
14.7 | 14 | 14. DevOps, Infrastructure & Observability | Alerting catalog | SLOs, batch windows, pool-identity, prefund, webhooks. | 2 | Infra | OPS-13 | 5 | 14.6 | Alert catalog | DevOps | 31 | 0 | 0 | 31 | 0% | NOT STARTED | R5
14.8 | 14 | 14. DevOps, Infrastructure & Observability | Backup & DR (RTO/RPO) + drill | Backups, failover, DR drill. | 2 | Infra | OPS-13, NFR-10 | 6 | 14.4 | DR plan + drill | DevOps | 25 | 0 | 0 | 25 | 0% | NOT STARTED | R5
15.1 | 15 | 15. Quality Assurance & Testing | Test strategy, plan & environments | Levels, entry/exit criteria, environments. | 1 | Cross-cutting | QA-12 | 5 | 1.3 | Test plan | QA | 44 | 0 | 6 | 38 | 0% | IN PROGRESS | R6
15.2 | 15 | 15. Quality Assurance & Testing | Test data management | Synthetic partners/schemes/merchants/rates. | 1 | Cross-cutting | QA-12 | 4 | 15.1 | Test data sets | QA | 34 | 0 | 4 | 30 | 0% | IN PROGRESS | R6
15.3 | 15 | 15. Quality Assurance & Testing | Rate-engine test vectors execution | Run RV-01..RV-10; verify identity & rounding. | 1 | Hub Core | QA-12, RATE-04 | 6 | 4.9 | Vector results; + rounding-residual reconciliation tests | QA | 24 | 1 | 4 | 19 | 4% | IN PROGRESS | R2
15.4 | 15 | 15. Quality Assurance & Testing | Functional test suites per component | Hub/Admin/Portal/API/ZeroPay/prefund/refund. | 2 | Cross-cutting | QA-12 | 12 | 15.1 | Functional suites | QA | 50 | 0 | 6 | 44 | 0% | IN PROGRESS | R2
15.5 | 15 | 15. Quality Assurance & Testing | API contract & webhook testing | Validate vs OpenAPI; webhook delivery/retry. | 2 | API-N | QA-12, API-05 | 6 | 8.9 | Contract tests | QA | 37 | 1 | 3 | 33 | 3% | IN PROGRESS | R6
15.6 | 15 | 15. Quality Assurance & Testing | ZeroPay batch round-trip testing | All ZP00xx file generation/parse/timing. | 2 | API-S | QA-12, SCH-06 | 8 | 9.10 | Batch test report | QA | 39 | 2 | 2 | 35 | 5% | IN PROGRESS | R7
15.7 | 15 | 15. Quality Assurance & Testing | Integration & end-to-end testing | Quote→execute→scheme→approved→settle flows. | 2 | Cross-cutting | QA-12 | 10 | 15.4 | E2E results | QA | 46 | 0 | 0 | 46 | 0% | NOT STARTED | R6
15.8 | 15 | 15. Quality Assurance & Testing | Performance & load testing | Against NFR-10 latency/TPS/batch-window targets. | 3 | Cross-cutting | QA-12, NFR-10 | 6 | 15.7 | Perf report | QA | 28 | 0 | 0 | 28 | 0% | NOT STARTED | R6
15.9 | 15 | 15. Quality Assurance & Testing | UAT support & business sign-off | Business scenarios, GME Ops/Finance sign-off. | 3 | Cross-cutting | QA-12 | 6 | 15.7 | UAT sign-off | QA | 30 | 0 | 1 | 29 | 0% | IN PROGRESS | R8
15.10 | 15 | 15. Quality Assurance & Testing | Regression & defect management | Regression packs, triage, exit gates. | 3 | Cross-cutting | QA-12 | 8 | 15.4 | Defect/exit report | QA | 31 | 0 | 0 | 31 | 0% | NOT STARTED | R6
16.1 | 16 | 16. Deployment, Go-Live & Hypercare | Go-live readiness & cutover plan | Readiness checklist, cutover & rollback plan. | 3 | Cross-cutting | OPS-13, PM-14 | 5 | 15.9 | Cutover plan | DevOps | 29 | 0 | 0 | 29 | 0% | NOT STARTED | R5
16.2 | 16 | 16. Deployment, Go-Live & Hypercare | Phase 3 go-live: GME Remit domestic | Production launch (target Oct 10, 2026). | 3 | Cross-cutting | PM-14 | 5 | 16.1 | P3 live | DevOps | 35 | 0 | 0 | 35 | 0% | NOT STARTED | R8
16.3 | 16 | 16. Deployment, Go-Live & Hypercare | Phase 4 onboarding: overseas partners | Onboard T-Bank/SendMN; prefunding live. | 4 | Cross-cutting | PM-14, API-05 | 8 | 16.2,8.10 | P4 partners live | BE | 42 | 0 | 0 | 42 | 0% | NOT STARTED | R8
16.4 | 16 | 16. Deployment, Go-Live & Hypercare | Production smoke tests & monitoring | Validate prod flows & alerting post-deploy. | 3 | Cross-cutting | OPS-13 | 4 | 16.2 | Smoke results | QA | 30 | 0 | 0 | 30 | 0% | NOT STARTED | R8
16.5 | 16 | 16. Deployment, Go-Live & Hypercare | Hypercare (14-day) & stabilization | Heightened support window post-launch. | 4 | Cross-cutting | OPS-13 | 10 | 16.2 | Hypercare report | All | 32 | 0 | 0 | 32 | 0% | NOT STARTED | R8
16.6 | 16 | 16. Deployment, Go-Live & Hypercare | Operational runbook handover & training | Runbook walkthrough, Ops training. | 4 | Cross-cutting | OPS-13 | 5 | 16.5 | Runbook + training | DevOps | 27 | 0 | 0 | 27 | 0% | NOT STARTED | R8
17.1 | 17 | 17. Real-Stack Gap Closure | Docker-capable build & CI environment | Stand up a build host/runner with Docker so docker-compose + Testcontainers can run; wire into GitHub Actions. Single biggest unlock: every H2/stub PARTIAL depends on it. | 1 | platform-infra | Audit 2026-06-10 / WBS v3 re-baseline | 5 | - | CI job runs docker-compose stack + Testcontainers ITs green | DevOps | 3 |  |  |  |  | NOT STARTED | R0
17.2 | 17 | 17. Real-Stack Gap Closure | H2 → real PostgreSQL per service | Replace H2-in-PG-mode test DBs with real PostgreSQL via docker-compose + Testcontainers ITs for all 12 persistence-bearing services; verify Flyway migrations against PG 16. | 1 | all data services | Audit 2026-06-10 / WBS v3 re-baseline | 18 | 17.1 | Repository ITs green on real PostgreSQL for 12 services | Backend | 12 |  |  |  |  | NOT STARTED | R1
17.3 | 17 | 17. Real-Stack Gap Closure | Redis wiring (cache/TTL/idempotency) | Replace in-memory stores with Redis: rate-quote TTL store (rate-fx), idempotency keys (transaction-mgmt/api-gateway), config cache (config-registry). | 1 | rate-fx, txn-mgmt, config-registry | Audit 2026-06-10 / WBS v3 re-baseline | 6 | 17.1 | Redis-backed stores with ITs | Backend | 3 |  |  |  |  | NOT STARTED | R1
17.4 | 17 | 17. Real-Stack Gap Closure | Kafka producer + Schema Registry | Implement KafkaEventPublisher behind lib-events EventPublisher; outbox publishers drain to Kafka; notification-webhook consumes payment.approved; Schema Registry with subject naming + compatibility rules. | 1 | lib-events, all outbox services | Audit 2026-06-10 / WBS v3 re-baseline | 10 | 17.1 | Events flow producer→Kafka→consumer in compose stack | Backend | 5 |  |  |  |  | NOT STARTED | R1
17.5 | 17 | 17. Real-Stack Gap Closure | Stub→REST client flip, E2E verified | Promote Rest*Client @Primary impls to verified: payment-executor's 7 clients and ops-partner-bff's 10 clients exercised against live services on the compose stack; delete/demote stubs to test scope. | 2 | payment-executor, ops-partner-bff | Audit 2026-06-10 / WBS v3 re-baseline | 10 | 17.1,17.2 | Inter-service REST calls verified E2E; stubs test-only | Backend | 3 |  |  |  |  | NOT STARTED | R2
17.6 | 17 | 17. Real-Stack Gap Closure | Registry persistence (scheme/rule/treasury) | Persist Scheme, Routing-Rule and Treasury registries in config-registry (currently in-memory/seed): entities, Flyway, CRUD endpoints, effective-dating. | 1 | config-registry | Audit 2026-06-10 / WBS v3 re-baseline | 8 | 17.2 | Registries survive restart; CRUD + ITs green | Backend | 3 |  |  |  |  | NOT STARTED | R1
17.7 | 17 | 17. Real-Stack Gap Closure | MongoDB merchant/QR mirror | Stand up MongoDB for merchant-qr-data (per architecture diagram); move lookup store from memory to Mongo; nightly sync job skeleton. | 2 | merchant-qr-data | Audit 2026-06-10 / WBS v3 re-baseline | 5 | 17.1 | Mongo-backed merchant lookup with ITs | Backend | 2 |  |  |  |  | NOT STARTED | R1
17.8 | 17 | 17. Real-Stack Gap Closure | Object storage (MinIO) for files | S3-compatible MinIO in compose; statements, recon files and ZP batch files stored/retrieved via a small lib-storage client. | 2 | settlement, scheme-adapter, BFF | Audit 2026-06-10 / WBS v3 re-baseline | 5 | 17.1 | Files round-trip through MinIO | Backend | 2 |  |  |  |  | NOT STARTED | R1
18.1 | 18 | 18. Missing Components | ops-partner-bff legitimization & real wiring | The BFF was built ahead of tickets (19 endpoints + 18 test classes). Legitimize in WBS; wire its 10 clients to real services; add auth pass-through. | 2 | ops-partner-bff | Audit 2026-06-10 / WBS v3 re-baseline | 6 | 17.5 | BFF serves both UIs from live services | Backend | 2 |  |  |  |  | NOT STARTED | R2
18.2 | 18 | 18. Missing Components | Nginx WAF edge | Nginx reverse proxy + WAF rules in front of api-gateway and the UIs per the architecture diagram (decision 18.7 governs final edge shape). | 2 | edge | Audit 2026-06-10 / WBS v3 re-baseline | 6 | 18.7 | Nginx fronts the compose stack with WAF ruleset | DevOps | 2 |  |  |  |  | NOT STARTED | R3
18.3 | 18 | 18. Missing Components | SFTP Gateway service | Dedicated SFTP gateway (per architecture diagram) brokering KFTC batch file exchange: inbound/outbound directories, PGP encrypt/decrypt, key mgmt, pickup/drop schedule. | 2 | sftp-gateway | Audit 2026-06-10 / WBS v3 re-baseline | 8 | 17.8 | ZP files flow disk↔SFTP↔adapter in compose stack | Backend | 3 |  |  |  |  | NOT STARTED | R2
18.4 | 18 | 18. Missing Components | Real authentication (replace demo login) | Replace password=demo stub: auth-identity issues JWTs (OAuth2 password/client-credentials), BFF validates, RBAC roles enforced, refresh rotation, login rate-limit. | 2 | auth-identity, ops-partner-bff, UIs | Audit 2026-06-10 / WBS v3 re-baseline | 10 | 17.2 | Login works end-to-end with real JWT + RBAC | Backend | 4 |  |  |  |  | NOT STARTED | R3
18.5 | 18 | 18. Missing Components | UI contract-drift prevention | Per-slice Vitest contract tests pinned to the BFF wire contract (already started); add CI check that fails on BFF DTO/UI field drift; Playwright-free smoke via vitest+jsdom. | 2 | admin-ui, partner-portal-ui | Audit 2026-06-10 / WBS v3 re-baseline | 4 | 18.1 | CI fails on contract drift; 19 pages smoke-tested | Frontend | 2 |  |  |  |  | NOT STARTED | R4
18.6 | 18 | 18. Missing Components | docker-compose E2E money-path harness | One command brings up the full stack + seeded demo data; scripted E2E: quote→route→prefund deduct→execute→ZP simulate→commit→settlement booking+rounding residual→webhook; asserts ledger invariants. | 2 | qa-platform | Audit 2026-06-10 / WBS v3 re-baseline | 8 | 17.1,17.5 | Money-path E2E green in CI | QA | 3 |  |  |  |  | NOT STARTED | R2
18.7 | 18 | 18. Missing Components | Stack decision record (ADR) | Resolve user-pending contradictions: Kafka vs RabbitMQ, Spring Cloud Gateway vs Nginx, MongoDB keep/drop, Rocky Linux images, Elasticsearch role. Write ADRs; align code. | 1 | architecture | Audit 2026-06-10 / WBS v3 re-baseline | 2 | - | ADR-001..005 merged; stack matches one source of truth | Architect | 1 |  |  |  |  | NOT STARTED | R0
20.1 | 20 | 20. Phase-2+ Scheme Adapters | KHQR adapter (Cambodia) | Bakong KHQR scheme adapter: EMVCo profile, member bank API, settlement files. Expand WBS when partner contract lands. | 4 | scheme-adapter-khqr | Audit 2026-06-10 / WBS v3 re-baseline | 40 | 9.1,16.2 | KHQR adapter certified | Backend | 1 |  |  |  |  | NOT STARTED | R8
20.2 | 20 | 20. Phase-2+ Scheme Adapters | QPay adapter (Mongolia) | QPay scheme adapter. Expand WBS when partner contract lands. | 4 | scheme-adapter-qpay | Audit 2026-06-10 / WBS v3 re-baseline | 35 | 9.1,16.2 | QPay adapter certified | Backend | 1 |  |  |  |  | NOT STARTED | R8
20.3 | 20 | 20. Phase-2+ Scheme Adapters | QRIS adapter (Indonesia) | QRIS scheme adapter. Expand WBS when partner contract lands. | 4 | scheme-adapter-qris | Audit 2026-06-10 / WBS v3 re-baseline | 40 | 9.1,16.2 | QRIS adapter certified | Backend | 1 |  |  |  |  | NOT STARTED | R8
20.4 | 20 | 20. Phase-2+ Scheme Adapters | SBP adapter (Russia) | SBP scheme adapter (sanctions/compliance review first). Expand WBS when cleared. | 4 | scheme-adapter-sbp | Audit 2026-06-10 / WBS v3 re-baseline | 35 | 9.1,16.2,13.8 | SBP adapter certified | Backend | 1 |  |  |  |  | NOT STARTED | R8
20.5 | 20 | 20. Phase-2+ Scheme Adapters | PromptPay adapter (Thailand) | PromptPay scheme adapter. Expand WBS when partner contract lands. | 4 | scheme-adapter-promptpay | Audit 2026-06-10 / WBS v3 re-baseline | 35 | 9.1,16.2 | PromptPay adapter certified | Backend | 1 |  |  |  |  | NOT STARTED | R8
21.0 | 21 | 21. Partner Setup re-baseline | WS 21 — Partner Setup re-baseline (8 vertical slices) | Re-baselines Partner Setup against DAT-03 §4.3 + PRD-07 §5.3: the 4-field demo (/partners/new with partnerId/type/settlementCurrency/settlementRoundingMode) is replaced by an 8-step wizard delivered as 8 vertical slices (21.1–21.8). Architecture locked by ADR-006..014. Sole source of truth: docs/PARTNER_SETUP_PLAN.md. | 2 | Cross-cutting (config-registry + ops-partner-bff + admin-ui + auth-identity + prefunding + notification-webhook + kyb-adapter) | PARTNER_SETUP_PLAN.md; DAT-03 §4.3; PRD-07 §5.3; ADR-006..014 | 60 | 10.3 (superseded), 8.x, 13.x | 8-step partner onboarding wizard, end-to-end FSM, full audit + 4-eyes + KYB + bitemporal aggregate | FS | 179 | 0 | 0 | 179 | 0% | NOT STARTED (re-baselined 2026-06-11) | R0..R3
21.1 | 21 | 21. Partner Setup re-baseline | Slice 1 — Identity + Foundation | Wizard scaffold + step 1 (Identity). Foundation primitives every later slice depends on: resolve String↔Long Partner ID schism (adopt partner_id BIGINT surrogate + partner_code VARCHAR(20) unique business key per ADR-013 Expand/Backfill/Contract); collapse 5 Partner DTO shapes into canonical PartnerView (read) + PartnerCommand (write) in lib-api-contracts. Bitemporal partner table (ADR-010 SCD-Type-6, valid_from/to + recorded_at/superseded_at + current-flag). change_request table + Spring State Machine (ADR-008 DRAFT→PROPOSED→APPROVED→APPLIED, REJECTED terminal). audit_log infra (ADR-007 dedicated audit Postgres DB, INSERT-only role, hash chain, Kafka topic gmepay.audit.partner, lib-audit). Keycloak service (ADR-011 docker-compose Rocky 9, Postgres-backed); api-gateway becomes OAuth2 resource server; ops-partner-bff password=demo retired. Identity fields on partner: partner_code UNIQUE, legal_name_local, legal_name_romanized, tax_id + type discriminator (KR-BRN/KH-VAT/VN-MST/SG-UEN/generic), country_of_incorporation ISO-3166-α2, legal_form enum (CORP/LLC/MTO/EMI/BANK/OTHER), structured registered_address + operating_address, lei ISO-17442. Draft endpoints POST/PATCH/GET /v1/admin/partners/draft. RestConfigRegistryClient + admin-ui client.js updated. UI: wizard scaffold (8 tabs/stepper, server-side draft persistence per ADR-012), step-1 form with Yup regional validators, draft list with Resume button, Keycloak OIDC login replaces demo auth. | 1 | Cross-cutting / Foundation | PARTNER_SETUP_PLAN.md §Slice 1; ADR-007/008/010/011/012/013 | 10 | 10.1, 8.2, 13.1, 13.2 | Bitemporal partner aggregate + change_request FSM + audit_log + Keycloak; wizard step 1 live | FS | 22 | 0 | 0 | 22 | 0% | NOT STARTED | R0
21.2 | 21 | 21. Partner Setup re-baseline | Slice 2 — Contacts | Wizard step 2 + 4-eyes machinery surfaced in UI. Backend: partner_contact child table (bitemporal) — id BIGSERIAL, partner_id FK, role enum (OPS_24X7/FINANCE/COMPLIANCE_MLRO/TECH/LEGAL/INCIDENT), name, email, phone_e164, is_authorized_signatory BOOL, notes. Reuse change_request from Slice 1. BFF: PATCH /v1/admin/partners/draft/{id}/step-2 (bulk replace), POST /v1/admin/partners/{id}/contacts (propose change), POST /v1/admin/partners/change-requests/{id}/approve. UI: multi-row contact editor with role dropdown + E.164 phone validation; generic Approval queue page (checker sees PROPOSED CRs, Approve/Reject with reason); read-only paginated audit log viewer on partner detail page. | 2 | Admin + BFF + config-registry | PARTNER_SETUP_PLAN.md §Slice 2; ADR-008 | 8 | 21.1 | partner_contact entity + approval queue UI + audit log viewer | FS | 15 | 0 | 0 | 15 | 0% | NOT STARTED | R1
21.3 | 21 | 21. Partner Setup re-baseline | Slice 3 — KYB | Wizard step 3 + document vault + KYB screening adapter. Backend: MinIO bucket gmepay-partner-vault with object-lock compliance mode (ADR-006); lib-vault wraps MinIO SDK with virus-scan hook + Vault-key encryption. partner_document (bitemporal): id, partner_id FK, doc_type enum (LICENSE/CERT_INCORPORATION/AOA/BOARD_RESOLUTION/UBO_DECLARATION/FINANCIALS/CBDDQ/OTHER), vault_uri, version, expiry_date, verified_by, verified_at. partner_kyb (bitemporal): risk_rating (LOW/MEDIUM/HIGH), risk_rationale, next_review_date, license_type/number/authority/expiry, ubo_set_jsonb (array of {name, ownership_pct, is_pep, country}), wolfsberg_cbddq_doc_id FK. KybProvider port in lib-kyb (ADR-009). StubKybAdapter for internal dev; OctaKybAdapter lands when sandbox creds arrive. Kafka topic gmepay.kyb.screening, outbox-published same txn. New service services/kyb-adapter (Spring Boot module). UI: license details, UBO entry table (name + ownership% + PEP toggle + country), drag-drop document upload, Wolfsberg CBDDQ upload, Run screening button, document viewer modal with version history, screening result panel (latest result, decision history, rescreen). | 2 | KYB + Vault + Admin | PARTNER_SETUP_PLAN.md §Slice 3; ADR-006 (Vault), ADR-009 (KYB port) | 10 | 21.1 | MinIO vault + lib-vault + kyb-adapter service + partner_document/partner_kyb tables + step-3 UI | FS | 18 | 0 | 0 | 18 | 0% | NOT STARTED | R1
21.4 | 21 | 21. Partner Setup re-baseline | Slice 4 — Banking & Settlement | Wizard step 4 — settlement bank accounts, settlement cycle, methods, calendars. Backend: partner_bank_account (bitemporal) — id, partner_id FK, currency ISO-4217, bank_name, bic_swift, iban_or_account_number, account_holder_name, bank_country ISO-3166, intermediary_bic (opt), verification_status (UNVERIFIED/KFTC_VERIFIED/BANK_LETTER/MICRO_DEPOSIT), verification_evidence_doc_id FK, verification_date, is_primary BOOL, swift_charge_bearer (OUR/BEN/SHA), purpose (PAYOUT/FLOAT_TOPUP/REFUND). partner_settlement_config (bitemporal): partner_id PK, cycle_t_plus_n INT, cutoff_time, cutoff_timezone, settlement_method (SWIFT_MT103/KR_FIRM_BANKING/BAKONG/NAPAS_247/PROMPT_PAY/FAST_SG/OTHER). business_day_calendar seeded with Korean + ASEAN holidays go-live + 2 years (Chuseok, Tet, Songkran, Lunar New Year, etc.). KFTC 계좌실명조회 verification stub — port abstraction AccountVerificationProvider with KftcVerificationAdapter + StubVerificationAdapter. UI: bank account multi-row editor with per-row verification button, settlement config panel (cycle/cutoff/method/timezone picker), settlement preview ("with these settings, your Mon 11:30 KST txn pays out Wed 11:30 KST"). | 2 | Banking + Settlement | PARTNER_SETUP_PLAN.md §Slice 4; ADR-008; CAL-01 holiday calendars | 9 | 21.2 | partner_bank_account + partner_settlement_config + business_day_calendar + KFTC verification port + step-4 UI | FS | 20 | 0 | 0 | 20 | 0% | NOT STARTED | R2
21.5 | 21 | 21. Partner Setup re-baseline | Slice 5 — Prefunding (OVERSEAS only) | Wizard step 5 + wire-up of existing PartnerBalanceEntity into partner-create txn. Backend: when partner is activated with funding_model=PREFUNDED or HYBRID, prefunding service creates balance row in same change_request. partner_prefunding_config (bitemporal): funding_model (PREFUNDED/POSTPAID/HYBRID), opening_balance_usd, low_balance_threshold_usd (default 10000), alert_tier_70/85/95_pct, credit_limit_usd (NULL=no limit), auto_suspend_on_breach BOOL, float_top_up_bank_account_id FK (purpose=FLOAT_TOPUP), top_up_reference_pattern VARCHAR (e.g. GMP-{partner_code}-{yyyyMMdd}), collateral_amount_usd (opt). Tier-alert generation: Kafka topic gmepay.prefunding.alert produced when balance crosses threshold; notification-webhook consumes. Auto-suspend: balance<0 (or breach + auto_suspend_on_breach=true) publishes change_request(aggregate=partner, payload=status:SUSPENDED) with proposed_by=system — requires operator approval to lift. UI step 5 (OVERSEAS only): funding model radio, opening balance + ccy, threshold inputs with live preview, credit limit, top-up bank picker (filtered to FLOAT_TOPUP purpose), reference pattern preview. Prefunding dashboard tile on partner detail page: current balance, threshold gauge with tier coloring, recent top-ups, recent alerts. | 2 | Prefunding + Admin | PARTNER_SETUP_PLAN.md §Slice 5 | 8 | 21.4 | partner_prefunding_config + PartnerBalanceEntity wired into create txn + tier alerts + auto-suspend + step-5 UI | FS | 17 | 0 | 0 | 17 | 0% | NOT STARTED | R2
21.6 | 21 | 21. Partner Setup re-baseline | Slice 6 — Commercial Terms | Wizard step 6 — financial-correctness slice (ccy split + rules + fees + FX + limits + contract). Backend: split settlement_currency into collection_ccy + settle_a_ccy (DAT-03 §4.3 + PRD-07 §5.3.2) via Expand/Backfill/Contract (ADR-013) across 3 releases. Rule persistence: today only POST /v1/rules/validate exists; add POST /v1/rules (create) + GET /v1/rules (list per partner) + PUT /v1/rules/{id} (update via change_request). Schema includes existing lib-domain Rule.validate "m_a + m_b ≥ 2%" invariant. partner_fee_schedule (bitemporal) per (partner × scheme × direction): fixed_fee, bps_fee, tier table (volume bands → bps). partner_fx_config (bitemporal): margin_bps, reference_rate_source (SEOUL_FX_BROKER/PARTNER_PROVIDED/MID_MARKET), quote_hold_seconds (default 300, range 60–1800). partner_limits (bitemporal): per_txn_min/max_usd, daily/monthly/annual_cap_usd. 소액해외송금업 hard-enforced server-side: per_txn ≤ 5000 USD, annual ≤ 50000 USD for that license type. partner_contract (bitemporal): effective_from/to, auto_renewal BOOL, notice_period_days, refund_chargeback_policy (PARTNER_BEARS/MERCHANT_BEARS/SHARED), termination_reason. transaction-mgmt + rate-fx updated to read new collection_ccy / settle_a_ccy split. UI step 6: split ccy picker, rule editor (multi-row per scheme/direction with margin sliders), fee schedule, FX margin slider + reference source + quote hold, limits with 소액해외송금업 visual cap markers, contract dates + auto-renewal toggle. | 2 | Pricing + FX + Limits + Contract | PARTNER_SETUP_PLAN.md §Slice 6; ADR-013 Expand/Backfill/Contract; DAT-03 §4.3; PRD-07 §5.3.2 | 12 | 21.4 | collection_ccy/settle_a_ccy split + rule persistence + fee schedule + FX config + limits + contract + step-6 UI | FS | 25 | 0 | 0 | 25 | 0% | NOT STARTED | R2
21.7 | 21 | 21. Partner Setup re-baseline | Slice 7 — Schemes & Corridors | Wizard step 7 — scheme enablement + corridor matrix + per-partner scheme credentials. Backend: partner_scheme (bitemporal): partner_id, scheme_id, direction (INBOUND/OUTBOUND/BOTH), role (ACQUIRER/ISSUER/BOTH), zeropay_merchant_id, zeropay_sub_merchant_id, kftc_institution_code, partner_type_char (D/I — Zp0011 derivation). partner_corridor (bitemporal): partner_id, src_country, src_ccy, dst_country, dst_ccy, go_live_date, is_active. SchemeRouter rewrite from hardcoded KR→ZEROPAY to data-driven (reads partner_scheme join). Per-partner scheme credentials stored in Vault (ADR-006 pattern), referenced by partner_scheme.vault_secret_id. Approval method per (partner × scheme × payment_mode CPM/MPM): approval_method enum (CONFIRMATION/SILENT) — closes OI-01 / 1.2-T03. Operating hours per scheme (settlement cutoffs): seeded for ZeroPay (24×7 with KFTC 16:30 KST cutoff), Bakong (24×7 with NBC 09:00–15:00 ICT), etc. UI step 7: scheme enablement matrix (rows=schemes, columns=direction × role, checkboxes), per-row drill-down for ZeroPay specifics (merchantId, sub-merchantId, institution code, D/I, approval method per CPM/MPM), corridor matrix builder, operating hours preview. | 2 | Schemes + Corridors + Routing | PARTNER_SETUP_PLAN.md §Slice 7; ADR-006; OI-01 | 10 | 21.6 | partner_scheme + partner_corridor + data-driven SchemeRouter + Vault-stored creds + step-7 UI | FS | 22 | 0 | 0 | 22 | 0% | NOT STARTED | R2
21.8 | 21 | 21. Partner Setup re-baseline | Slice 8 — Credentials + Lifecycle + Reporting | Wizard step 8 — credential issuance + full FSM + regulatory reporting attributes. Backend: wire existing auth-identity/ApiKeyEntity + PrincipalEntity + notification-webhook/WebhookEndpointEntity into partner-create txn (the wire-up debt). Generate API key + HMAC secret on activation, return plaintext ONCE in response, store hash. IP allowlist: partner_ip_allowlist (up to 10 CIDRs); api-gateway pre-signature 403 enforcement. mTLS cert exchange: partner_mtls_cert (bitemporal) — cert_pem, fingerprint_sha256, expiry_date, status; mTLS verification at Nginx layer (ADR-002). Sandbox vs production credential pairs: partner_credential_environment enum (SANDBOX/PRODUCTION); sandbox prefix pk_test_/sk_test_. Credential rotation: scheduled job proposes rotation change_request at 11 months (12-month rotation per SEC-09); revoke endpoint with audit_log entry. Full FSM: Draft → KYB-Pending → KYB-Approved → Contract-Signed → Sandbox → UAT → Live → Suspended → Terminated. Transitions are change_request-gated; go-live + suspend require 4-eyes. Activation pre-condition gate: returns 422 + unmet[] until legal_name set, KYB approved, ≥1 verified bank account per settle_ccy, contracts signed, prefunding row created if OVERSEAS, ≥4 role contacts, ≥1 scheme enabled, sanctions clear or operator-overridden. Post-activation immutability: partner_code, country_of_incorporation, partner_type, collection_ccy, settle_a_ccy locked after first Live transition; mutations → 400 IMMUTABLE_AFTER_ACTIVATION. Suspension reason codes: LIMIT_BREACH/SANCTIONS_HIT/CREDENTIAL_COMPROMISE/KYB_LAPSED/CONTRACT_EXPIRED/OPERATOR_INITIATED. BOK 외환거래보고 attributes: bok_txn_code, bok_fx_reporting_category (INDIVIDUAL_AGGREGATE/INSTITUTIONAL), bok_remitter_type. Hometax e-tax-invoice: hometax_issuer_cert_id FK to vault doc, vat_treatment (ZERO_RATED_EXPORT/STANDARD/EXEMPT). KoFIU STR/CTR: kofiu_entity_id, ctr_threshold_krw (default 10,000,000), per-corridor STR enable flag. PIPA cross-border PII transfer notice: pipa_jurisdiction_allowlist[], legal_basis_code enum. Travel Rule (TRP/Sygna/IVMS101): travel_rule_protocol enum + endpoint config; ≥KRW 1M transfers must include IVMS101 originator + beneficiary block. UI step 8: Review tab (full summary with anchor jumps), Activate button (calls pre-condition gate, shows unmet[]), one-time credential modal (API key + HMAC + webhook signing secret, copy-to-clipboard, dismiss confirmation), confirmation operator stored secrets. Partner detail page (post-activation): status header with FSM menu, credential rotation panel, audit log full view, BOK/Hometax/KoFIU reporting settings tab, status-action menu (Suspend/Reactivate/Terminate with reason). | 3 | Credentials + FSM + Regulatory Reporting | PARTNER_SETUP_PLAN.md §Slice 8; ADR-002 (mTLS); ADR-008 (4-eyes); SEC-09 rotation | 13 | 21.5, 21.7 | Credential issuance + full lifecycle FSM + activation gate + BOK/Hometax/KoFIU/PIPA/Travel-Rule reporting attrs + step-8 UI | FS | 40 | 0 | 0 | 40 | 0% | NOT STARTED | R3

## Completion Plan v3
GMEPay+ — Completion Plan v3 (re-baselined after the 2026-06-10 code audit)
Every WBS code is mapped to one executable completion phase R0–R8. Sequence is dependency-true: R0 unlocks Testcontainers/compose; R1 makes persistence real; R2 proves the money path E2E; R3–R6 are productionization; R7 is external-party bound; R8 is launch.
Phase | Name | Owner | WBS codes | Tickets | Done | Partial | Not started | % D+P | Exit gate | External blockers
R0 | Decisions & build environment | AI agents + GME + user | 1.1 1.2 1.3 1.4 2.1 2.2 2.3 17.1 18.7 | 190 | 6 | 40 | 144 | 24% | Docker-capable CI green; stack ADRs signed (Kafka/RabbitMQ, Gateway/Nginx, Mongo) | —
R1 | Persistence & real wiring (gap closure) | AI agents | 2.4 2.5 3.1 3.2 3.3 3.4 3.5 3.6 3.7 4.1 4.6 4.7 6.1 6.2 6.3 6.4 17.2 17.3 17.4 17.6 17.7 17.8 | 424 | 3 | 81 | 340 | 20% | All 12 services on real PostgreSQL; Redis/Kafka/Mongo/MinIO wired; registries persistent | —
R2 | Money-path E2E on compose stack | AI agents | 4.2 4.3 4.4 4.5 4.8 4.9 5.1 5.2 5.3 5.4 5.5 5.6 5.7 5.8 6.5 7.1 7.2 7.3 7.4 7.6 8.3 8.4 8.5 8.6 8.7 9.1 9.4 9.9 15.3 15.4 17.5 18.1 18.3 18.6 | 715 | 20 | 131 | 564 | 21% | Scripted E2E quote→commit→settlement+rounding residual→webhook green in CI | —
R3 | Edge & security | AI agents + GME Security | 8.1 8.2 8.8 13.1 13.2 13.3 13.4 13.5 13.6 13.9 18.2 18.4 | 272 | 8 | 24 | 240 | 12% | Nginx WAF up; real JWT auth + RBAC; Vault for secrets; HMAC/idempotency at edge | —
R4 | UI completion against live BFF | AI agents | 2.6 10.1 10.2 10.3 10.4 10.5 10.6 10.7 10.8 10.9 10.10 10.11 11.1 11.2 11.3 11.4 11.5 11.6 11.7 12.1 12.2 12.3 12.4 12.5 18.5 | 717 | 0 | 80 | 637 | 11% | All admin + portal WBS screens functional vs live BFF; contract-drift CI gate | —
R5 | Infrastructure & observability | GME DevOps (agents author IaC) | 14.1 14.2 14.3 14.4 14.5 14.6 14.7 14.8 16.1 | 268 | 0 | 0 | 268 | 0% | Staging on K8s via CI/CD; OTel+Prometheus/Grafana+ELK+Jaeger; backup/DR drill | —
R6 | Hardening, performance, pen test | Agents author; GME validates | 13.10 15.1 15.2 15.5 15.7 15.8 15.10 | 256 | 1 | 14 | 241 | 6% | NFR-10 load targets met; pen test passed; regression suite green | —
R7 | Compliance & certification | GME + external parties | 7.5 8.9 8.10 9.2 9.3 9.5 9.6 9.7 9.8 9.10 13.7 13.8 15.6 | 392 | 3 | 41 | 348 | 11% | KFTC/ZeroPay certified; BOK FX1014/1015 verified; Hometax integrated; AML live | KFTC test env, BOK OI-03, Hometax OI-02
R8 | UAT, go-live & hypercare | GME business + partners | 1.5 1.6 15.9 16.2 16.3 16.4 16.5 16.6 20.1 20.2 20.3 20.4 20.5 | 253 | 0 | 1 | 252 | 0% | UAT signed; production cutover rehearsed; 14-day hypercare; Phase-2 adapters start | —
| TOTAL |  |  | 3487 | 41 | 412 | 3034 | 13%

## Summary
GMEPay+ — WBS Summary & Effort Rollup
Indicative planning estimates (person-days). See Legend for assumptions.
Effort by Workstream
WS # | Workstream | Tasks | Effort (PD) | % of Total
1 | 1. Project Management & Mobilization
2 | 2. Architecture & Technical Foundation
3 | 3. Data Layer & Persistence
4 | 4. Rate Engine & FX
5 | 5. Transaction Processing (MPM/CPM)
6 | 6. Prefunding & Wallet Ledger
7 | 7. Settlement, Reconciliation & Revenue
8 | 8. Partner (Northbound) API
9 | 9. QR Scheme Integration (ZeroPay)
10 | 10. Admin System
11 | 11. Partner Portal
12 | 12. UX/UI & Frontend Foundation
13 | 13. Security & Compliance
14 | 14. DevOps, Infrastructure & Observability
15 | 15. Quality Assurance & Testing
16 | 16. Deployment, Go-Live & Hypercare
TOTAL
Effort by Phase
Phase | Description | Tasks | Effort (PD) | % of Total
1 | P1 — Build Core (Apr 10–Jun 20)
2 | P2 — Integrate ZeroPay (May 15–Jul 31)
3 | P3 — Launch Domestic (Aug 1–Oct 10)
4 | P4 — Launch Overseas (Oct 1–Dec 10)
TOTAL
Indicative Conversions
Total effort (person-days)
Person-weeks (5 PD/week)
Person-months (21 PD/month)
Calendar months @ 6 FTE
Calendar months @ 8 FTE

## Phases & Milestones
GMEPay+ — Phases & Key Milestones
Go-live: October 10, 2026 (GME Remit domestic). Critical path: 한결원/KFTC test environment available by mid-May 2026.
Phase | Name | Period (2026) | Duration | Gate / Entry Criteria | Primary Deliverables
P1 | Build Core | Apr 10 – Jun 20 | ~10 weeks | Design sign-off | Hub Core, Rate Engine, Data layer, Partner API, Admin foundation
P2 | Integrate ZeroPay | May 15 – Jul 31 | ~11 weeks (overlap) | KFTC test env ready | Scheme adapter, ZP00xx batch flows, Settlement & reconciliation
P3 | Launch Domestic | Aug 1 – Oct 10 | ~10 weeks | UAT sign-off | GME Remit live, Partner Portal, Perf & security testing, Go-live
P4 | Launch Overseas | Oct 1 – Dec 10 | ~10 weeks | P3 stable | T-Bank/SendMN onboarding, prefunding live, hypercare, handover
Key Milestones
Milestone | Target | Depends on
Architecture & design sign-off | Apr 2026 | Requirements walkthrough
Rate engine passes all test vectors | May 2026 | WS4, WS15.3
KFTC/한결원 test environment available | Mid-May 2026 | External (KFTC)
Partner API sandbox live | May 2026 | WS8
ZeroPay batch round-trip certified | Jul 2026 | WS9.10
Settlement & reconciliation verified | Jul 2026 | WS7, WS9.6
UAT sign-off | Sep 2026 | WS15.9
GME Remit domestic GO-LIVE | Oct 10, 2026 | WS16.2
First overseas partner live | Within 3 months of go-live | WS16.3

## Legend
GMEPay+ — WBS Legend, Conventions & Assumptions
Column definitions
WBS Code | Hierarchical identifier (workstream.task).
Phase | Primary delivery phase (1–4). Some tasks span phases; primary phase shown for rollup.
Component | Hub Core / Admin / Portal / API-N (northbound) / API-S (scheme) / Infra / Cross-cutting.
Source Doc(s) | Specification document(s) the task derives from (codes per DOC-00).
Effort (PD) | Indicative effort in person-days for estimation; refine with vendor.
Dependencies | Predecessor WBS codes that should complete (or substantially progress) first.
Primary Role | Lead discipline; most tasks need supporting roles too.
Role abbreviations
PM / BA | Project Manager / Business Analyst
ARCH | Solution/Software Architect
BE / FE / FS | Backend / Frontend / Full-stack Engineer
DBA | Database Engineer
UX | UX/UI Designer
DevOps | DevOps / SRE
QA | Quality Assurance / Test Engineer
Sec | Security Engineer
Source document codes
BRD-01 / SAD-02 / DAT-03 | Business Requirements / System Architecture / Data Model
RATE-04 / API-05 / SCH-06 | Rate Engine / Partner API / ZeroPay Integration
PRD-07 / PRD-08 / SEC-09 | Admin System / Partner Portal / Security & Compliance
NFR-10 / UX-11 / QA-12 | NFR & SLA / UX-UI / Test Plan
OPS-13 / PM-14 / REF-15 | DevOps & Runbook / Project Plan / Glossary
DOC-00 | Documentation Index & Handover
Estimating assumptions
Basis | Effort is indicative for planning only, derived from the specification scope; not a fixed-price commitment.
Working calendar | 5 person-days/week; 21 person-days/month assumed.
Exclusions | Partner app development, merchant onboarding, and KFTC-side build are out of scope (GME/partner/scheme responsibilities).
Open items | OI-01 customer-approval UX, OI-02 tax-invoice API, OI-03 BOK reporting format may change scope when resolved (see WS1.2).
Risk buffer | Add project contingency (e.g. 15–20%) on top of the WBS total; not included here.